Introduction & Project Context

Slide / Section Title: “Alima Nuclear Reactor Shutdown Analysis”

Key Points to Cover:

We have 2,641 total shutdown projects for safety-case development.

Of those, 262 projects finished more effectively (actual ≤ original duration) and 3,879 finished less effectively (actual > original duration).

Our goal: not only report on historical cost and timeline performance, but also build predictive models for future shutdown projects both in terms of man-hours effectiveness and final cost.

Data Sources & Preparation

Power BI Get Data: Imported three tables from our Excel/PBI dataset:

sc_plans – contains planned vs. actual durations, percent complete, effectiveness ratio.

cost – contains original and actual costs, remaining cost, and final cost.

template – contains activity-level floats and scheduling metadata.

Power Query Steps:

Convert dates (start_date, finish_date) to Date types.

Create unified actual_mh column:

if [is_complete]=1 then [actual_duration]

else [original_duration] - [remaining_duration]

Create unified actual_spend column similarly for costs.

Calculate eff_ratio = original_duration / actual_mh and cost_eff = original_cost / actual_spend.

Filter out any activities/projects with missing critical data.

Historical Analysis Visuals in Power BI

Timeline Effectiveness Bar Chart:

X = Project or Year, Y = Avg(eff_ratio), Color = Completed vs. Ongoing.

Cost Trend Line:

X = Year, Y = Sum(final_cost), Legend = Project.

Scatter: Man-Hours vs. Cost:

X = original_duration, Y = final_cost, Size = physical_%_complete, Color = eff_ratio.

Gantt-Style Schedule Performance:

Bars for Planned vs. Actual duration per activity.

Float Heatmap:

Rows = Activity, Columns = total_float, Color intensity shows slack.

Python-Powered Predictive Pipeline

Here’s where Python inside Power BI takes us from descriptive to prescriptive.

Features & Target Definition

Inputs: original_duration, actual_duration, workpack_id, year

Target: log-transformed final_cost (to tame skew)

Edge-Case Handling

0 rows: Display “No data” message

1 row: Plot baseline (pred = actual) with perfect MAE/R²

≥ 2 rows: Proceed to full modeling

Data Prep in Script

mdl = df[['original_duration','actual_duration','year','workpack_id','final_cost']].copy()

mdl['log_cost'] = np.log(mdl['final_cost'])

X = pd.get_dummies(mdl[['original_duration','actual_duration','year','workpack_id']], drop_first=True)

y = mdl['log_cost']

Train/Test Split

Dynamic 30% test size (but at least one sample per set).

Fixed random_state=42 for reproducibility.

Modeling & Back-Transformation

model = RandomForestRegressor(n_estimators=100, random_state=42)

model.fit(X_train, y_train)

ylog_pred = model.predict(X_test)

y_pred = np.exp(ylog_pred)      # back to original cost scale

Evaluation Metrics

MAE on original costs (e.g. ₦636 k average error)

R² (e.g. 0.61 → 61 % cost variance explained)

Visualization of Predictions

Scatter: Actual vs. Predicted Final Cost

45° reference line for perfect predictions

Dynamic chart title reporting n, MAE, and R²

Pathways to Further Improvement

A short menu of next steps to boost model power and interpretability.

Feature Enrichment

Add project_type, team_size, complexity scores, rolling historic performance.

Derive temporal features: start_month, season, day_of_week.

Robust Validation & Tuning

Swap single split for 5-fold CV.

Use RandomizedSearchCV or Optuna for hyperparameter optimization.

Integrate via scikit-learn Pipelines to bundle preprocessing + modeling.

Advanced Models & Ensembles

Try XGBoost, LightGBM, or stacking ensembles.

Compare with linear models (ElasticNet) for regularization benefits.

Outlier & Skew Handling

Clip extreme eff_ratio or cost_eff values before training.

Use TransformedTargetRegressor to cleanly encapsulate log-target logic.

Explainability & Diagnostics

Plot feature importances to identify top drivers of cost.

Use SHAP values for per-project explanations in the report.