ER6668LT | W213 | W213.29220 | TOR Essential Defueling Safety Case | Verify Operator Claims Matrix | 27-Mar-23 A | 27-Mar-23 | 21-Apr-23 A | 21-pr-23 | 9 | 0 | 18 | 100% |  | Completed
ER6371LT | W202 | W202.A2206600 | HRA Reactors Shutdown Essential Safety Cases | Hold Risk Workshop | 30-Mar-23 A | 30-Mar-23 | 30-Mar-23 A | 30-Mar-23 | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2206600 | HYA Reactors Shutdown Essential Safety Cases | Hold Risk Workshop | 30-Mar-23 A | 30-Mar-23 | 30-Mar-23 A | 30-Mar-23 | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A28240 | HYB Essential Defueling Safety Case | CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN Available | 31-Mar-23 A | 31-Mar-23 | 31-Mar-23 A | 31-Mar-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A28800 | HYB Essential Defueling Safety Case | Fuel Free Verification methods, an assessment against the ALARP principle EAN Available | 31-Mar-23 A | 31-Mar-23 | 31-Mar-23 A | 31-Mar-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A28240 | TOR Essential Defueling Safety Case | CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN Available | 31-Mar-23 A | 31-Mar-23 | 31-Mar-23 A | 31-Mar-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A28800 | TOR Essential Defueling Safety Case | Fuel Free Verification methods, an assessment against the ALARP principle EAN Available | 31-Mar-23 A | 31-Mar-23 | 31-Mar-23 A | 31-Mar-23 | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | 2430 | HRA Reactors Shutdown Essential Safety Cases | Stn RE Endorsed | 31-Mar-23 A | 31-Mar-23 | 26-May-23 A | 26-May-23 | 5 | 0 | 36 | 100% |  | Completed
ER6371LT | W202 | 2420 | HRA Reactors Shutdown Essential Safety Cases | CO Endorsed | 31-Mar-23 A | 31-Mar-23 | 26-May-23 A | 26-May-23 | 5 | 0 | 36 | 100% |  | Completed
ER6661LT | W206 | 2430 | HYA Reactors Shutdown Essential Safety Cases | Stn RE Endorsed | 31-Mar-23 A | 31-Mar-23 | 26-May-23 A | 26-May-23 | 5 | 0 | 36 | 100% |  | Completed
ER6661LT | W206 | 2420 | HYA Reactors Shutdown Essential Safety Cases | CO Endorsed | 31-Mar-23 A | 31-Mar-23 | 26-May-23 A | 26-May-23 | 5 | 0 | 36 | 100% |  | Completed
ER6371LT | W202 | W202.A2206610 | HRA Reactors Shutdown Essential Safety Cases | Complete Risk Log with Estimates | 31-Mar-23 A | 31-Mar-23 | 31-Mar-23 A | 31-Mar-23 | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2206610 | HYA Reactors Shutdown Essential Safety Cases | Complete Risk Log with Estimates | 31-Mar-23 A | 31-Mar-23 | 31-Mar-23 A | 31-Mar-23 | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A25760 | HYB Essential Defueling Safety Case | Judgement Based Work Diversion EAN Available | 31-Mar-23 A | 31-Mar-23 | 31-Mar-23 A | 31-Mar-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.8990 | HYB Essential Defueling Safety Case | Discovery Milestone - FM Underload Veto - Drafted | 31-Mar-23 A | 31-Mar-23 | 31-Mar-23 A | 31-Mar-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A28720 | HYB Essential Defueling Safety Case | CSP/Diagrid Structural Integrity Summary Report Available | 31-Mar-23 A | 31-Mar-23 | 31-Mar-23 A | 31-Mar-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A25760 | TOR Essential Defueling Safety Case | Judgement Based Work Diversion EAN Available | 31-Mar-23 A | 31-Mar-23 | 31-Mar-23 A | 31-Mar-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.8990 | TOR Essential Defueling Safety Case | Discovery Milestone - FM Underload Veto - Drafted | 31-Mar-23 A | 31-Mar-23 | 31-Mar-23 A | 31-Mar-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A28720 | TOR Essential Defueling Safety Case | CSP/Diagrid Structural Integrity Summary Report Available | 31-Mar-23 A | 31-Mar-23 | 31-Mar-23 A | 31-Mar-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3150 | HNB Enhanced Defuelling Safety Cases | Produce MF | 03-Apr-23 A | 03-pr-23 | 11-Apr-23 A | 11-pr-23 | 5 | 0 | 4 | 100% |  | Completed
ER6378LT | W222 | W222.3060 | HRA Fuel Handling Essential Safety Case | ETC (DD-PF) April 23 only | 03-Apr-23 A | 03-pr-23 | 28-Apr-23 A | 28-pr-23 | 18 | 0 | 17 | 100% |  | Completed
ER6650LT | W226 | W226.3060 | HYA Fuel Handling Essential Safety Case | ETC (April 23 Only) | 03-Apr-23 A | 03-pr-23 | 28-Apr-23 A | 28-pr-23 | 14 | 0 | 17 | 100% |  | Completed
ER6666LT | W209 | W209.29480 | HYB Essential Defueling Safety Case | Structural Integrity (SI) Justification - Liner & Penetrations - (Civils Follow-On Work) | 03-Apr-23 A | 03-pr-23 | 19-May-23 A | 19-May-23 | 1 | 0 | 30 | 100% |  | Completed
ER6666LT | W209 | W209.A31270 | HYB Essential Defueling Safety Case | Draft PSA Documentation | 03-Apr-23 A | 03-pr-23 | 15-Dec-23 A | 15-Dec-23 | 0 | 0 | 179 | 100% |  | Completed
ER6666LT | W209 | W209.A31330 | HYB Essential Defueling Safety Case | Fuelling Machine Purging Requirements During Defueling (Cost Summary) (Claim 5) | 03-Apr-23 A | 03-pr-23 | 28-Jul-23 A | 28-Jul-23 | 187 | 0 | 79 | 100% |  | Completed
ER6666LT | W209 | W209.A31350 | HYB Essential Defueling Safety Case | Draft Fuelling Machine Purging Requirements During Defueling | 03-Apr-23 A | 03-pr-23 | 14-Apr-23 A | 14-pr-23 | 0 | 0 | 8 | 100% |  | Completed
ER6668LT | W213 | W213.29480 | TOR Essential Defueling Safety Case | Structural Integrity (SI) Justification - Liner & Penetrations - (Civils Follow-On Work) | 03-Apr-23 A | 03-pr-23 | 19-May-23 A | 19-May-23 | 1 | 0 | 30 | 100% |  | Completed
ER6668LT | W213 | W213.A31270 | TOR Essential Defueling Safety Case | Draft PSA Documentation | 03-Apr-23 A | 03-pr-23 | 15-Dec-23 A | 15-Dec-23 | 0 | 0 | 178 | 100% |  | Completed
ER6668LT | W213 | W213.A31330 | TOR Essential Defueling Safety Case | Fuelling Machine Purging Requirements During Defueling (Cost Summary) (Claim 5) | 03-Apr-23 A | 03-pr-23 | 28-Jul-23 A | 28-Jul-23 | 187 | 0 | 79 | 100% |  | Completed
ER6668LT | W213 | W213.A31350 | TOR Essential Defueling Safety Case | Draft Fuelling Machine Purging Requirements During Defueling | 03-Apr-23 A | 03-pr-23 | 14-Apr-23 A | 14-pr-23 | 0 | 0 | 8 | 100% |  | Completed
ER6666LT | W209 | W209.A29030 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Summary of Compliance with RADWASTE Assessment Principles EAN to CDMS | 03-Apr-23 A | 03-pr-23 | 14-Apr-23 A | 14-pr-23 | 8 | 0 | 8 | 100% |  | Completed
ER6371LT | W202 | W202.A2206580 | HRA Reactors Shutdown Essential Safety Cases | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 03-Apr-23 A | 03-pr-23 | 03-Apr-23 A | 03-pr-23 | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A2206590 | HRA Reactors Shutdown Essential Safety Cases | Ensure Alignment of Schedule & Estimate | 03-Apr-23 A | 03-pr-23 | 03-Apr-23 A | 03-pr-23 | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A2206710 | HRA Reactors Shutdown Essential Safety Cases | Workshop to agree scope, effort and links | 03-Apr-23 A | 03-pr-23 | 04-Apr-23 A | 04-pr-23 | 2 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A2206580 | HYA Reactors Shutdown Essential Safety Cases | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 03-Apr-23 A | 03-pr-23 | 03-Apr-23 A | 03-pr-23 | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2206590 | HYA Reactors Shutdown Essential Safety Cases | Ensure Alignment of Schedule & Estimate | 03-Apr-23 A | 03-pr-23 | 03-Apr-23 A | 03-pr-23 | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2206710 | HYA Reactors Shutdown Essential Safety Cases | Workshop to agree scope, effort and links | 03-Apr-23 A | 03-pr-23 | 04-Apr-23 A | 04-pr-23 | 2 | 0 | 2 | 100% |  | Completed
ER6372LT | W203 | W203.A3660 | HNB Enhanced Defuelling Safety Cases | Produce MF | 03-Apr-23 A | 03-pr-23 | 11-Apr-23 A | 11-pr-23 | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A29030 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Summary of Compliance with RADWASTE Assessment Principles EAN to CDMS | 03-Apr-23 A | 03-pr-23 | 14-Apr-23 A | 14-pr-23 | 8 | 0 | 8 | 100% |  | Completed
W232LT | W232 | W232.A1260 | DNB Enhanced Safety Cases | Verify supporting reference <PSA Sensitivity Study> | 04-Apr-23 A | 04-pr-23 | 07-Apr-23 A | 07-pr-23 | 10 | 0 | 3 | 100% |  | Completed
W232LT | W232 | W232.A1230 | DNB Enhanced Safety Cases | FEGO / TOG Stakeholder Mgmt | 04-Apr-23 A | 04-pr-23 | 11-Apr-23 A | 11-pr-23 | 9 | 0 | 4 | 100% |  | Completed
ER6371LT | W202 | W202.A2206620 | HRA Reactors Shutdown Essential Safety Cases | Update Schedule/Estimate from Risk Log & Add Provisions | 04-Apr-23 A | 04-pr-23 | 04-Apr-23 A | 04-pr-23 | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2206620 | HYA Reactors Shutdown Essential Safety Cases | Update Schedule/Estimate from Risk Log & Add Provisions | 04-Apr-23 A | 04-pr-23 | 04-Apr-23 A | 04-pr-23 | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A2206630 | HRA Reactors Shutdown Essential Safety Cases | Add Data to IAB Paper | 05-Apr-23 A | 05-pr-23 | 05-Apr-23 A | 05-pr-23 | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2206630 | HYA Reactors Shutdown Essential Safety Cases | Add Data to IAB Paper | 05-Apr-23 A | 05-pr-23 | 05-Apr-23 A | 05-pr-23 | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A2206640 | HRA Reactors Shutdown Essential Safety Cases | PCL Validate & Approve Baseline Package for PRC Submission | 06-Apr-23 A | 06-pr-23 | 06-Apr-23 A | 06-pr-23 | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2206640 | HYA Reactors Shutdown Essential Safety Cases | PCL Validate & Approve Baseline Package for PRC Submission | 06-Apr-23 A | 06-pr-23 | 06-Apr-23 A | 06-pr-23 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A1430 | DNB Enhanced Safety Cases | EDF Technical review of supporting reference <PSA Sensitivity Study> | 10-Apr-23 A | 10-pr-23 | 12-Apr-23 A | 12-pr-23 | 10 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A3330 | HNB Enhanced Defuelling Safety Cases | Issue MF | 11-Apr-23 A | 11-pr-23 | 11-Apr-23 A | 11-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3380 | HNB Enhanced Defuelling Safety Cases | CO & CA appointed | 11-Apr-23 A | 11-pr-23 | 11-Apr-23 A | 11-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A29250 | HYB Essential Defueling Safety Case | Technical Review of Defuelling Hazards Review EAN | 11-Apr-23 A | 11-pr-23 | 14-Apr-23 A | 14-pr-23 | 20 | 0 | 4 | 100% |  | Completed
ER6668LT | W213 | W213.A29250 | TOR Essential Defueling Safety Case | Technical Review of Defuelling Hazards Review EAN | 11-Apr-23 A | 11-pr-23 | 14-Apr-23 A | 14-pr-23 | 20 | 0 | 4 | 100% |  | Completed
ER6372LT | W203 | W203.A3840 | HNB Enhanced Defuelling Safety Cases | Issue MF | 11-Apr-23 A | 11-pr-23 | 11-Apr-23 A | 11-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3890 | HNB Enhanced Defuelling Safety Cases | CO & CA appointed | 11-Apr-23 A | 11-pr-23 | 11-Apr-23 A | 11-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3210 | HNB Enhanced Defuelling Safety Cases | Hold project kick start meeting with Station & key suppliers | 12-Apr-23 A | 12-pr-23 | 18-Apr-23 A | 18-pr-23 | 5 | 0 | 4 | 100% |  | Completed
ER6372LT | W203 | W203.A3480 | HNB Enhanced Defuelling Safety Cases | Identify verifier for the case & establish all other resources | 12-Apr-23 A | 12-pr-23 | 18-Apr-23 A | 18-pr-23 | 5 | 0 | 4 | 100% |  | Completed
ER6666LT | W209 | W209.A24800 | HYB Essential Defueling Safety Case | Verify Human Factors Assessment of Misloading / Mis-Defueling Faults EAN & Issue | 12-Apr-23 A | 12-pr-23 | 16-Jun-23 A | 16-Jun-23 | 14 | 0 | 45 | 100% |  | Completed
ER6371LT | W202 | W202.A2206550 | HRA Reactors Shutdown Essential Safety Cases | Gate C+ PRC Paper Submission | 12-Apr-23 A | 12-pr-23 | 12-Apr-23 A | 12-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206670 | HRA Reactors Shutdown Essential Safety Cases | PRC Members Review PRC Documentation | 12-Apr-23 A | 12-pr-23 | 17-Apr-23 A | 17-pr-23 | 4 | 0 | 4 | 100% |  | Completed
ER6661LT | W206 | W206.A2206550 | HYA Reactors Shutdown Essential Safety Cases | Gate C+ PRC Paper Submission | 12-Apr-23 A | 12-pr-23 | 12-Apr-23 A | 12-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206670 | HYA Reactors Shutdown Essential Safety Cases | PRC Members Review PRC Documentation | 12-Apr-23 A | 12-pr-23 | 17-Apr-23 A | 17-pr-23 | 4 | 0 | 4 | 100% |  | Completed
ER6372LT | W203 | W203.A3720 | HNB Enhanced Defuelling Safety Cases | Hold project kick start meeting with Station & key suppliers | 12-Apr-23 A | 12-pr-23 | 18-Apr-23 A | 18-pr-23 | 5 | 0 | 5 | 100% |  | Completed
ER6372LT | W203 | W203.A3990 | HNB Enhanced Defuelling Safety Cases | Identify verifier for the case & establish all other resources | 12-Apr-23 A | 12-pr-23 | 18-Apr-23 A | 18-pr-23 | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A24800 | TOR Essential Defueling Safety Case | Verify Human Factors Assessment of Misloading / Mis-Defueling Faults EAN & Issue | 12-Apr-23 A | 12-pr-23 | 16-Jun-23 A | 16-Jun-23 | 14 | 0 | 45 | 100% |  | Completed
W232LT | W232 | W232.A1480 | DNB Enhanced Safety Cases | Supporting reference <PSA Sensitivity Study> approved | 14-Apr-23 A | 14-pr-23 | 14-Apr-23 A | 14-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.28900 | HYB Essential Defueling Safety Case | Discover Milestone - Review need for Further HF Assessment | 14-Apr-23 A | 14-pr-23 | 14-Apr-23 A | 14-pr-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.2020 | DNB Enhanced Safety Cases | >>>OUTGOING ENABLER PSA Sensitivity Study Complete | 14-Apr-23 A | 14-pr-23 | 14-Apr-23 A | 14-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.28900 | TOR Essential Defueling Safety Case | Discover Milestone - Review need for Further HF Assessment | 14-Apr-23 A | 14-pr-23 | 14-Apr-23 A | 14-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A29040 | HYB Essential Defueling Safety Case | Summary of Compliance with RADWASTE Assessment Principles EAN Available | 14-Apr-23 A | 14-pr-23 | 14-Apr-23 A | 14-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A29040 | TOR Essential Defueling Safety Case | Summary of Compliance with RADWASTE Assessment Principles EAN Available | 14-Apr-23 A | 14-pr-23 | 14-Apr-23 A | 14-pr-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2740 | DNB Enhanced Safety Cases | Verify supporting reference <Maintenance Review of FR Plant> | 17-Apr-23 A | 17-pr-23 | 23-May-23 A | 23-May-23 | 10 | 0 | 25 | 100% |  | Completed
ER6666LT | W209 | W209.A29260 | HYB Essential Defueling Safety Case | Supplier Update and Issue Defuelling Hazards Review EAN | 17-Apr-23 A | 17-pr-23 | 20-Jul-23 A | 20-Jul-23 | 5 | 0 | 66 | 100% |  | Completed
ER6666LT | W209 | W209.A29980 | HYB Essential Defueling Safety Case | Technical Review of FM Underload Protection Mods Prelim Design (GLM) | 17-Apr-23 A | 17-pr-23 | 10-May-23 A | 10-May-23 | 16 | 0 | 16 | 100% |  | Completed
ER6666LT | W209 | W209.A31360 | HYB Essential Defueling Safety Case | Verify Fuelling Machine Purging Requirements During Defueling | 17-Apr-23 A | 17-pr-23 | 21-Jul-23 A | 21-Jul-23 | 32 | 0 | 67 | 100% |  | Completed
ER6668LT | W213 | W213.A29260 | TOR Essential Defueling Safety Case | Supplier Update and Issue Defuelling Hazards Review EAN | 17-Apr-23 A | 17-pr-23 | 20-Jul-23 A | 20-Jul-23 | 5 | 0 | 66 | 100% |  | Completed
ER6668LT | W213 | W213.A29980 | TOR Essential Defueling Safety Case | Technical Review of FM Underload Protection Mods Prelim Design (GLM) | 17-Apr-23 A | 17-pr-23 | 10-May-23 A | 10-May-23 | 16 | 0 | 16 | 100% |  | Completed
ER6668LT | W213 | W213.A31360 | TOR Essential Defueling Safety Case | Verify Fuelling Machine Purging Requirements During Defueling | 17-Apr-23 A | 17-pr-23 | 21-Jul-23 A | 21-Jul-23 | 32 | 0 | 67 | 100% |  | Completed
ER6666LT | W209 | W209.7360 | HYB Essential Defueling Safety Case | Case Officer Tech Lead Review Claim 6 and Address Comments | 18-Apr-23 A | 18-pr-23 | 13-Jun-23 A | 13-Jun-23 | 20 | 0 | 38 | 100% |  | Completed
ER6668LT | W213 | W213.7360 | TOR Essential Defueling Safety Case | Case Officer Tech Lead Review Claim 6 and Address Comments | 18-Apr-23 A | 18-pr-23 | 13-Jun-23 A | 13-Jun-23 | 20 | 0 | 38 | 100% |  | Completed
ER6372LT | W203 | W203.A3450 | HNB Enhanced Defuelling Safety Cases | Categorisation by station | 19-Apr-23 A | 19-pr-23 | 19-Apr-23 A | 19-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3960 | HNB Enhanced Defuelling Safety Cases | Categorisation by station | 19-Apr-23 A | 19-pr-23 | 19-Apr-23 A | 19-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3220 | HNB Enhanced Defuelling Safety Cases | Agree resource & timescales with suppliers for delivering key refs, incl contingency, risk & allowance for rework | 20-Apr-23 A | 20-pr-23 | 20-Apr-23 A | 20-pr-23 | 5 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3730 | HNB Enhanced Defuelling Safety Cases | Agree resource & timescales with suppliers for delivering key refs, incl contingency, risk & allowance for rework | 20-Apr-23 A | 20-pr-23 | 20-Apr-23 A | 20-pr-23 | 5 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 1955 | HYA Fuel Handling Essential Safety Case | Final Update of Head Document (Needs PSA Numbers and Verified Draft FDD **ACTION** Review Predecsessors ie 5 key Docs) | 20-Apr-23 A | 20-pr-23 | 22-Nov-23 A | 22-Nov-23 | 20 | 0 | 151 | 100% |  | Completed
ER6666LT | W209 | W209.A30970 | HYB Essential Defueling Safety Case | Technical Review of Channel X | 21-Apr-23 A | 21-pr-23 | 22-May-23 A | 22-May-23 | 30 | 0 | 19 | 100% |  | Completed
W232LT | W232 | W232.A2930 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Discovery Milestone: Moisture Detection Capability | 21-Apr-23 A | 21-pr-23 | 21-Apr-23 A | 21-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A30970 | TOR Essential Defueling Safety Case | Technical Review of Channel X | 21-Apr-23 A | 21-pr-23 | 22-May-23 A | 22-May-23 | 30 | 0 | 19 | 100% |  | Completed
W232LT | W232 | W232.B6620 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Summary | 21-Apr-23 A | 21-pr-23 | 21-Apr-23 A | 21-pr-23 | 69 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6630 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Summary | 21-Apr-23 A | 21-pr-23 | 21-Apr-23 A | 21-pr-23 | 10 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6640 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Approve Task Sheet | 21-Apr-23 A | 21-pr-23 | 21-Apr-23 A | 21-pr-23 | 2 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6650 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Pre Job Brief | 21-Apr-23 A | 21-pr-23 | 21-Apr-23 A | 21-pr-23 | 2 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6660 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Draft and issue Task Sheet | 21-Apr-23 A | 21-pr-23 | 21-Apr-23 A | 21-pr-23 | 10 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6670 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Prepare Draft EAN | 21-Apr-23 A | 21-pr-23 | 21-Apr-23 A | 21-pr-23 | 20 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6690 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Draft EAN Reviewed by EDF SQEP | 21-Apr-23 A | 21-pr-23 | 21-Apr-23 A | 21-pr-23 | 10 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6700 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Address Comments from EDF Review on Draft EAN | 21-Apr-23 A | 21-pr-23 | 21-Apr-23 A | 21-pr-23 | 10 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6720 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Moisture Detection Capability - EAN Completed and Uploaded to CDMS | 21-Apr-23 A | 21-pr-23 | 21-Apr-23 A | 21-pr-23 | 10 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6740 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Moisture Detection Capability - TSA Internal Review of Draft EAN | 21-Apr-23 A | 21-pr-23 | 21-Apr-23 A | 21-pr-23 | 5 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A25920 | HYB Essential Defueling Safety Case | Safety Case Requirements EAN - TASK E EAN Available | 21-Apr-23 A | 21-pr-23 | 21-Apr-23 A | 21-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A26800 | HYB Essential Defueling Safety Case | Boron Bead Injection Feasibility & Control Rod Isolation EAN Available | 21-Apr-23 A | 21-pr-23 | 21-Apr-23 A | 21-pr-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B6680 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Issue Draft EAN to EDF for Review. | 21-Apr-23 A | 21-pr-23 | 21-Apr-23 A | 21-pr-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B6710 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Issue Final EAN | 21-Apr-23 A | 21-pr-23 | 21-Apr-23 A | 21-pr-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B6730 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Moisture Detection Capability - EAN Completed | 21-Apr-23 A | 21-pr-23 | 21-Apr-23 A | 21-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A25920 | TOR Essential Defueling Safety Case | Safety Case Requirements EAN - TASK E EAN Available | 21-Apr-23 A | 21-pr-23 | 21-Apr-23 A | 21-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A26800 | TOR Essential Defueling Safety Case | Boron Bead Injection Feasibility & Control Rod Isolation EAN Available | 21-Apr-23 A | 21-pr-23 | 21-Apr-23 A | 21-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A24590 | HYB Essential Defueling Safety Case | Verify Human Reliability Baseline Report EAN & Issue for Technical Review | 24-Apr-23 A | 24-pr-23 | 03-Jul-23 A | 03-Jul-23 | 15 | 0 | 48 | 100% |  | Completed
ER6372LT | W203 | W203.A3620 | HNB Enhanced Defuelling Safety Cases | Produce supporting reference <Purge and Pressurisation> | 24-Apr-23 A | 24-pr-23 | 19-May-23 A | 19-May-23 | 20 | 0 | 18 | 100% |  | Completed
ER6372LT | W203 | W203.A4130 | HNB Enhanced Defuelling Safety Cases | Produce supporting reference <IFD Deluge> | 24-Apr-23 A | 24-pr-23 | 09-Jun-23 A | 09-Jun-23 | 10 | 0 | 31 | 100% |  | Completed
ER6372LT | W203 | W203.B1030 | HNB Enhanced Defuelling Safety Cases | Produce supporting reference <Dropped Fuel Consequences EAN> | 24-Apr-23 A | 24-pr-23 | 26-May-23 A | 26-May-23 | 20 | 0 | 22 | 100% |  | Completed
ER6668LT | W213 | W213.A24590 | TOR Essential Defueling Safety Case | Verify Human Reliability Baseline Report EAN & Issue for Technical Review | 24-Apr-23 A | 24-pr-23 | 03-Jul-23 A | 03-Jul-23 | 15 | 0 | 48 | 100% |  | Completed
ER6666LT | W209 | W209.28980 | HYB Essential Defueling Safety Case | Decision Milestone on Boron Bead Injection | 25-Apr-23 A | 25-pr-23 | 25-Apr-23 A | 25-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A27290 | HRA Fuel Handling Essential Safety Case | Revise Project Definition Document (PDD) | 25-Apr-23 A | 25-pr-23 | 25-Apr-23 A | 25-pr-23 | 5 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A27380 | HRA Fuel Handling Essential Safety Case | Hold Risk Workshop | 25-Apr-23 A | 25-pr-23 | 25-Apr-23 A | 25-pr-23 | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A27400 | HRA Fuel Handling Essential Safety Case | Estimate Scope +/- 10% Lifecycle | 25-Apr-23 A | 25-pr-23 | 02-May-23 A | 02-May-23 | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A27410 | HRA Fuel Handling Essential Safety Case | Plan Scope in Primavera Level 2 Lifecycle) | 25-Apr-23 A | 25-pr-23 | 02-May-23 A | 02-May-23 | 1 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A27290 | HYA Fuel Handling Essential Safety Case | Revise Project Definition Document (PDD) | 25-Apr-23 A | 25-pr-23 | 25-Apr-23 A | 25-pr-23 | 5 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27380 | HYA Fuel Handling Essential Safety Case | Hold Risk Workshop | 25-Apr-23 A | 25-pr-23 | 25-Apr-23 A | 25-pr-23 | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27400 | HYA Fuel Handling Essential Safety Case | Estimate Scope +/- 10% Lifecycle | 25-Apr-23 A | 25-pr-23 | 02-May-23 A | 02-May-23 | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A27410 | HYA Fuel Handling Essential Safety Case | Plan Scope in Primavera Level 2 Lifecycle) | 25-Apr-23 A | 25-pr-23 | 02-May-23 A | 02-May-23 | 1 | 0 | 5 | 100% |  | Completed
ER6372LT | W203 | W203.A3340 | HNB Enhanced Defuelling Safety Cases | INSA agree MF and Identify INSA Resource (KDM) | 25-Apr-23 A | 25-pr-23 | 25-Apr-23 A | 25-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3540 | HNB Enhanced Defuelling Safety Cases | INSA Approval Date Identified | 25-Apr-23 A | 25-pr-23 | 25-Apr-23 A | 25-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3550 | HNB Enhanced Defuelling Safety Cases | Provide Provisional NSC Date | 25-Apr-23 A | 25-pr-23 | 25-Apr-23 A | 25-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.28980 | TOR Essential Defueling Safety Case | Decision Milestone on Boron Bead Injection | 25-Apr-23 A | 25-pr-23 | 25-Apr-23 A | 25-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206660 | HRA Reactors Shutdown Essential Safety Cases | Hold PRC Meeting | 25-Apr-23 A | 25-pr-23 | 25-Apr-23 A | 25-pr-23 | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2206660 | HYA Reactors Shutdown Essential Safety Cases | Hold PRC Meeting | 25-Apr-23 A | 25-pr-23 | 25-Apr-23 A | 25-pr-23 | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A2206680 | HRA Reactors Shutdown Essential Safety Cases | Gate C+ PRC Paper Approval | 25-Apr-23 A | 25-pr-23 | 25-Apr-23 A | 25-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206680 | HYA Reactors Shutdown Essential Safety Cases | Gate C+ PRC Paper Approval | 25-Apr-23 A | 25-pr-23 | 25-Apr-23 A | 25-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206730 | HRA Reactors Shutdown Essential Safety Cases | Gate C+ PRC Paper Approval | 25-Apr-23 A | 25-pr-23 | 25-Apr-23 A | 25-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206730 | HYA Reactors Shutdown Essential Safety Cases | Gate C+ PRC Paper Approval | 25-Apr-23 A | 25-pr-23 | 25-Apr-23 A | 25-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3850 | HNB Enhanced Defuelling Safety Cases | INSA agree MF and Identify INSA Resource (KDM) - <IFD Deluge> | 25-Apr-23 A | 25-pr-23 | 25-Apr-23 A | 25-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A4050 | HNB Enhanced Defuelling Safety Cases | INSA Approval Date Identified | 25-Apr-23 A | 25-pr-23 | 25-Apr-23 A | 25-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A4060 | HNB Enhanced Defuelling Safety Cases | Provide Provisional NSC Date | 25-Apr-23 A | 25-pr-23 | 25-Apr-23 A | 25-pr-23 | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5205 | HRA Reactors Shutdown Essential Safety Cases | SC - Safety Case development - INSA - HRA - C-D - INSA | 26-Apr-23 A | 26-pr-23 | 02-Oct-24 A | 02-Oct-24 | 124 | 0 | 364 | 100% |  | Completed
ER6661LT | W206 | W206.A5205 | HYA Reactors Shutdown Essential Safety Cases | SC - Safety Case development - INSA - HYA - C-D - INSA | 26-Apr-23 A | 26-pr-23 | 10-Oct-24 A | 10-Oct-24 | 124 | 0 | 369 | 100% |  | Completed
ER6371LT | W202 | W202.A5255 | HRA Reactors Shutdown Essential Safety Cases | INSA review & iteration of comments (using BARRIER MODEL) (HRA) (Resumed after Event Recovery) | 26-Apr-23 A | 26-pr-23 | 31-Jul-23 A | 31-Jul-23 | 25 | 0 | 65 | 100% |  | Completed
ER6661LT | W206 | W206.A5255 | HYA Reactors Shutdown Essential Safety Cases | INSA review & iteration of comments (using BARRIER MODEL) (HYA) (Resumed after Event Recovery) | 26-Apr-23 A | 26-pr-23 | 31-Jul-23 A | 31-Jul-23 | 25 | 0 | 65 | 100% |  | Completed
ER6372LT | W203 | W203.A3160 | HNB Enhanced Defuelling Safety Cases | Produce draft NSRS (using BARRIER MODEL) | 26-Apr-23 A | 26-pr-23 | 31-May-23 A | 31-May-23 | 10 | 0 | 22 | 100% |  | Completed
ER6666LT | W209 | W209.A27110 | HYB Essential Defueling Safety Case | Complete TR Form and Upload FPU Integrity Analysis EAN to CDMS | 26-Apr-23 A | 26-pr-23 | 12-May-23 A | 12-May-23 | 5 | 0 | 10 | 100% |  | Completed
ER6372LT | W203 | W203.A3670 | HNB Enhanced Defuelling Safety Cases | Produce draft NSRS (using BARRIER MODEL) | 26-Apr-23 A | 26-pr-23 | 31-Jul-23 A | 31-Jul-23 | 15 | 0 | 65 | 100% |  | Completed
ER6668LT | W213 | W213.A27110 | TOR Essential Defueling Safety Case | Complete TR Form and Upload FPU Integrity Analysis EAN to CDMS | 26-Apr-23 A | 26-pr-23 | 12-May-23 A | 12-May-23 | 5 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.25900 | HYB Essential Defueling Safety Case | Verify Human Reliability Assessment of Unsubstantiated Claims EAN & Issue for Technical Review | 28-Apr-23 A | 28-pr-23 | 28-Jul-23 A | 28-Jul-23 | 15 | 0 | 63 | 100% |  | Completed
ER6668LT | W213 | W213.25900 | TOR Essential Defueling Safety Case | Verify Human Reliability Assessment of Unsubstantiated Claims EAN & Issue for Technical Review | 28-Apr-23 A | 28-pr-23 | 28-Jul-23 A | 28-Jul-23 | 15 | 0 | 63 | 100% |  | Completed
ER6666LT | W209 | W209.7020 | HYB Essential Defueling Safety Case | Update Claim 2 | 01-May-23 A | 01-May-23 | 27-Oct-23 A | 27-Oct-23 | 9 | 0 | 126 | 100% |  | Completed
ER6668LT | W213 | W213.7020 | TOR Essential Defueling Safety Case | Update Claim 2 | 01-May-23 A | 01-May-23 | 27-Oct-23 A | 27-Oct-23 | 9 | 0 | 125 | 100% |  | Completed
ER6666LT | W209 | W209.29510 | HYB Essential Defueling Safety Case | PVCS Draindown Volume Calc Note - EAN Available | 02-May-23 A | 02-May-23 | 10-Jan-24 A | 10-Jan-24 | 1 | 0 | 175 | 100% |  | Completed
ER6668LT | W213 | W213.29510 | TOR Essential Defueling Safety Case | PVCS Draindown Volume Calc Note - EAN Available | 02-May-23 A | 02-May-23 | 10-Jan-24 A | 10-Jan-24 | 1 | 0 | 175 | 100% |  | Completed
ER6666LT | W209 | W209.A24640 | HYB Essential Defueling Safety Case | Pre Job Brief for Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN | 02-May-23 A | 02-May-23 | 02-May-23 A | 02-May-23 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6500 | DNB Enhanced Safety Cases | Core Support Plate Structural Integrity Criticality - Summary | 02-May-23 A | 02-May-23 | 23-Jun-23 A | 23-Jun-23 | 30 | 0 | 36 | 100% |  | Completed
W232LT | W232 | W232.B6530 | DNB Enhanced Safety Cases | Core Support Plate Structural Integrity Criticality - Draft and issue Task Sheet | 02-May-23 A | 02-May-23 | 31-May-23 A | 31-May-23 | 10 | 0 | 19 | 100% |  | Completed
ER6668LT | W213 | W213.A24640 | TOR Essential Defueling Safety Case | Pre Job Brief for Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN | 02-May-23 A | 02-May-23 | 02-May-23 A | 02-May-23 | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A24650 | HYB Essential Defueling Safety Case | Draft Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN | 03-May-23 A | 03-May-23 | 03-May-23 A | 03-May-23 | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A30600 | HYB Essential Defueling Safety Case | Draft FM Direct Process Protection Design | 03-May-23 A | 03-May-23 | 24-May-23 A | 24-May-23 | 68 | 0 | 14 | 100% |  | Completed
ER6378LT | W222 | W222.A27390 | HRA Fuel Handling Essential Safety Case | Ensure Alignment of Schedule & Estimate | 03-May-23 A | 03-May-23 | 03-May-23 A | 03-May-23 | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A27390 | HYA Fuel Handling Essential Safety Case | Ensure Alignment of Schedule & Estimate | 03-May-23 A | 03-May-23 | 03-May-23 A | 03-May-23 | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A24650 | TOR Essential Defueling Safety Case | Draft Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN | 03-May-23 A | 03-May-23 | 03-May-23 A | 03-May-23 | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A30600 | TOR Essential Defueling Safety Case | Draft FM Direct Process Protection Design | 03-May-23 A | 03-May-23 | 24-May-23 A | 24-May-23 | 68 | 0 | 14 | 100% |  | Completed
ER6666LT | W209 | W209.A31390 | HYB Essential Defueling Safety Case | Pre Job Brief for Stress Modelling | 04-May-23 A | 04-May-23 | 04-May-23 A | 04-May-23 | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A31390 | TOR Essential Defueling Safety Case | Pre Job Brief for Stress Modelling | 04-May-23 A | 04-May-23 | 04-May-23 A | 04-May-23 | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A24660 | HYB Essential Defueling Safety Case | Verify Human Reliability Assessment of New and/or Modified Human Based Safety Claims & Issue for Technical Review | 04-May-23 A | 04-May-23 | 04-May-23 A | 04-May-23 | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A27370 | HRA Fuel Handling Essential Safety Case | Complete Risk Log with Estimates | 04-May-23 A | 04-May-23 | 04-May-23 A | 04-May-23 | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A27370 | HYA Fuel Handling Essential Safety Case | Complete Risk Log with Estimates | 04-May-23 A | 04-May-23 | 04-May-23 A | 04-May-23 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2490 | DNB Enhanced Safety Cases | Structural Integrity TOG Engagement | 04-May-23 A | 04-May-23 | 04-May-23 A | 04-May-23 | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A24660 | TOR Essential Defueling Safety Case | Verify Human Reliability Assessment of New and/or Modified Human Based Safety Claims & Issue for Technical Review | 04-May-23 A | 04-May-23 | 04-May-23 A | 04-May-23 | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A31400 | HYB Essential Defueling Safety Case | Draft Review of Stress Modelling EAN | 05-May-23 A | 05-May-23 | 24-May-23 A | 24-May-23 | 0 | 0 | 12 | 100% |  | Completed
ER6668LT | W213 | W213.A31400 | TOR Essential Defueling Safety Case | Draft Review of Stress Modelling EAN | 05-May-23 A | 05-May-23 | 24-May-23 A | 24-May-23 | 0 | 0 | 12 | 100% |  | Completed
ER6666LT | W209 | W209.A24670 | HYB Essential Defueling Safety Case | Technical Review of Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN | 05-May-23 A | 05-May-23 | 05-May-23 A | 05-May-23 | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A27360 | HRA Fuel Handling Essential Safety Case | Update Schedule/Estimate from Risk Log & Add Provisions | 05-May-23 A | 05-May-23 | 05-May-23 A | 05-May-23 | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A27360 | HYA Fuel Handling Essential Safety Case | Update Schedule/Estimate from Risk Log & Add Provisions | 05-May-23 A | 05-May-23 | 05-May-23 A | 05-May-23 | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A24670 | TOR Essential Defueling Safety Case | Technical Review of Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN | 05-May-23 A | 05-May-23 | 05-May-23 A | 05-May-23 | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A24680 | HYB Essential Defueling Safety Case | Supplier Update and Issue Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN | 09-May-23 A | 09-May-23 | 09-May-23 A | 09-May-23 | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A27350 | HRA Fuel Handling Essential Safety Case | Add Data to PRC Paper | 09-May-23 A | 09-May-23 | 09-May-23 A | 09-May-23 | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A27350 | HYA Fuel Handling Essential Safety Case | Add Data to PRC Paper | 09-May-23 A | 09-May-23 | 09-May-23 A | 09-May-23 | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A24680 | TOR Essential Defueling Safety Case | Supplier Update and Issue Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN | 09-May-23 A | 09-May-23 | 09-May-23 A | 09-May-23 | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A24690 | HYB Essential Defueling Safety Case | Complete Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN to CDMS | 10-May-23 A | 10-May-23 | 10-May-23 A | 10-May-23 | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A27340 | HRA Fuel Handling Essential Safety Case | PCL Validate & Approve Baseline Package for PRC Submission | 10-May-23 A | 10-May-23 | 10-May-23 A | 10-May-23 | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A27340 | HYA Fuel Handling Essential Safety Case | PCL Validate & Approve Baseline Package for PRC Submission | 10-May-23 A | 10-May-23 | 10-May-23 A | 10-May-23 | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A24690 | TOR Essential Defueling Safety Case | Complete Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN to CDMS | 10-May-23 A | 10-May-23 | 10-May-23 A | 10-May-23 | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A24700 | HYB Essential Defueling Safety Case | Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN Available | 10-May-23 A | 10-May-23 | 10-May-23 A | 10-May-23 | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A27420 | HRA Fuel Handling Essential Safety Case | Issue PRC Paper to R4 PRC Members | 10-May-23 A | 10-May-23 | 10-May-23 A | 10-May-23 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27420 | HYA Fuel Handling Essential Safety Case | Issue PRC Paper to R4 PRC Members | 10-May-23 A | 10-May-23 | 10-May-23 A | 10-May-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A24700 | TOR Essential Defueling Safety Case | Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN Available | 10-May-23 A | 10-May-23 | 10-May-23 A | 10-May-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A29990 | HYB Essential Defueling Safety Case | Supplier Update and Issue FM Underload Protection Mods Prelim Design (GLM) | 11-May-23 A | 11-May-23 | 17-May-23 A | 17-May-23 | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A27330 | HRA Fuel Handling Essential Safety Case | PRC Members Review PRC Documentation | 11-May-23 A | 11-May-23 | 17-May-23 A | 17-May-23 | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A27335 | HYA Fuel Handling Essential Safety Case | PRC Members Review PRC Documentation | 11-May-23 A | 11-May-23 | 17-May-23 A | 17-May-23 | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A29990 | TOR Essential Defueling Safety Case | Supplier Update and Issue FM Underload Protection Mods Prelim Design (GLM) | 11-May-23 A | 11-May-23 | 17-May-23 A | 17-May-23 | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.A27120 | HYB Essential Defueling Safety Case | FPU Integrity Analysis EAN Available | 12-May-23 A | 12-May-23 | 12-May-23 A | 12-May-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A27120 | TOR Essential Defueling Safety Case | FPU Integrity Analysis EAN Available | 12-May-23 A | 12-May-23 | 12-May-23 A | 12-May-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A29630 | HYB Essential Defueling Safety Case | TASK F Review of the Discharge Limits (Permits) EAN Available | 12-May-23 A | 12-May-23 | 12-May-23 A | 12-May-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A29630 | TOR Essential Defueling Safety Case | TASK F Review of the Discharge Limits (Permits) EAN Available | 12-May-23 A | 12-May-23 | 12-May-23 A | 12-May-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A4960 | DNB Enhanced Safety Cases | Discovery Milestone: What Further Supporting Work Do We Require? | 15-May-23 A | 15-May-23 | 15-May-23 A | 15-May-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.29500 | HYB Essential Defueling Safety Case | Fuel Plug Unit Thermal Shield Performance During Defuelling - EAN Available | 17-May-23 A | 17-May-23 | 15-Jun-23 A | 15-Jun-23 | 1 | 0 | 21 | 100% |  | Completed
ER6668LT | W213 | W213.29500 | TOR Essential Defueling Safety Case | Fuel Plug Unit Thermal Shield Performance During Defuelling - EAN Available | 17-May-23 A | 17-May-23 | 15-Jun-23 A | 15-Jun-23 | 1 | 0 | 21 | 100% |  | Completed
ER6666LT | W209 | W209.A30000 | HYB Essential Defueling Safety Case | Complete TR Form and Upload FM Underload Protection Mods Prelim Design (GLM) to CDMS | 18-May-23 A | 18-May-23 | 19-May-23 A | 19-May-23 | 5 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A30000 | TOR Essential Defueling Safety Case | Complete TR Form and Upload FM Underload Protection Mods Prelim Design (GLM) to CDMS | 18-May-23 A | 18-May-23 | 19-May-23 A | 19-May-23 | 5 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A29770 | HYB Essential Defueling Safety Case | ALARP Review of Not Draining the PVCS (Report) Available | 19-May-23 A | 19-May-23 | 19-May-23 A | 19-May-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A30010 | HYB Essential Defueling Safety Case | FM Underload Protection Mods Prelim Design (GLM) Available | 19-May-23 A | 19-May-23 | 19-May-23 A | 19-May-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A29770 | TOR Essential Defueling Safety Case | ALARP Review of Not Draining the PVCS (Report) Available | 19-May-23 A | 19-May-23 | 19-May-23 A | 19-May-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A30010 | TOR Essential Defueling Safety Case | FM Underload Protection Mods Prelim Design (GLM) Available | 19-May-23 A | 19-May-23 | 19-May-23 A | 19-May-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A30980 | HYB Essential Defueling Safety Case | Supplier Update and Issue Channel X | 22-May-23 A | 22-May-23 | 22-May-23 A | 22-May-23 | 5 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A30990 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Channel X to CDMS | 22-May-23 A | 22-May-23 | 31-May-23 A | 31-May-23 | 5 | 0 | 6 | 100% |  | Completed
ER6668LT | W213 | W213.A30980 | TOR Essential Defueling Safety Case | Supplier Update and Issue Channel X | 22-May-23 A | 22-May-23 | 22-May-23 A | 22-May-23 | 5 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A30990 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Channel X to CDMS | 22-May-23 A | 22-May-23 | 31-May-23 A | 31-May-23 | 5 | 0 | 6 | 100% |  | Completed
ER6372LT | W203 | W203.A3610 | HNB Enhanced Defuelling Safety Cases | Verify supporting reference <Purge and Pressurisation> | 22-May-23 A | 22-May-23 | 24-May-23 A | 24-May-23 | 3 | 0 | 3 | 100% |  | Completed
ER6378LT | W222 | W222.A27430 | HRA Fuel Handling Essential Safety Case | Gate C+ for Region 1 - HRA Defuelling Fuel Handling Essential Safety Case | 23-May-23 A | 23-May-23 | 23-May-23 A | 23-May-23 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W222.A27430 | HYA Fuel Handling Essential Safety Case | Gate C+ for Region 1 - HYA Defuelling Fuel Handling Essential Safety Case | 23-May-23 A | 23-May-23 | 23-May-23 A | 23-May-23 | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A27320 | HRA Fuel Handling Essential Safety Case | Hold R4 PRC Meeting | 23-May-23 A | 23-May-23 | 23-May-23 A | 23-May-23 | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A27325 | HYA Fuel Handling Essential Safety Case | Hold R4 PRC Meeting | 23-May-23 A | 23-May-23 | 23-May-23 A | 23-May-23 | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A30610 | HYB Essential Defueling Safety Case | Verify FM Direct Process Protection Design & Issue for Technic | 24-May-23 A | 24-May-23 | 24-May-23 A | 24-May-23 | 40 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A30620 | HYB Essential Defueling Safety Case | Technical Review of FM Direct Process Protection Design | 24-May-23 A | 24-May-23 | 24-May-23 A | 24-May-23 | 30 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A30630 | HYB Essential Defueling Safety Case | Supplier Update and Issue FM Direct Process Protection Design | 24-May-23 A | 24-May-23 | 24-May-23 A | 24-May-23 | 15 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A30640 | HYB Essential Defueling Safety Case | Complete TR Form and Upload FM Direct Process Protection Design | 24-May-23 A | 24-May-23 | 24-May-23 A | 24-May-23 | 5 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A30650 | HYB Essential Defueling Safety Case | FM Direct Process Protection Design Available | 24-May-23 A | 24-May-23 | 24-May-23 A | 24-May-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.9010 | HYB Essential Defueling Safety Case | Discovery Milestone - FM Direct Process Protection Design - Drafted | 24-May-23 A | 24-May-23 | 24-May-23 A | 24-May-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A30610 | TOR Essential Defueling Safety Case | Verify FM Direct Process Protection Design & Issue for Technic | 24-May-23 A | 24-May-23 | 24-May-23 A | 24-May-23 | 40 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A30620 | TOR Essential Defueling Safety Case | Technical Review of FM Direct Process Protection Design | 24-May-23 A | 24-May-23 | 24-May-23 A | 24-May-23 | 30 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A30630 | TOR Essential Defueling Safety Case | Supplier Update and Issue FM Direct Process Protection Design | 24-May-23 A | 24-May-23 | 24-May-23 A | 24-May-23 | 15 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A30640 | TOR Essential Defueling Safety Case | Complete TR Form and Upload FM Direct Process Protection Design | 24-May-23 A | 24-May-23 | 24-May-23 A | 24-May-23 | 5 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A30650 | TOR Essential Defueling Safety Case | FM Direct Process Protection Design Available | 24-May-23 A | 24-May-23 | 24-May-23 A | 24-May-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.9010 | TOR Essential Defueling Safety Case | Discovery Milestone - FM Direct Process Protection Design - Drafted | 24-May-23 A | 24-May-23 | 24-May-23 A | 24-May-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2750 | DNB Enhanced Safety Cases | EDF Technical review of supporting reference <Maintenance Review of FR Plant> | 24-May-23 A | 24-May-23 | 30-Jun-23 A | 30-Jun-23 | 10 | 0 | 26 | 100% |  | Completed
ER6378LT | W222 | W222.A27310 | HRA Fuel Handling Essential Safety Case | Modify Estimate, Schedule & Risk Log as Required | 24-May-23 A | 24-May-23 | 25-May-23 A | 25-May-23 | 2 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | W226.A27315 | HYA Fuel Handling Essential Safety Case | Modify Estimate, Schedule & Risk Log as Required | 24-May-23 A | 24-May-23 | 25-May-23 A | 25-May-23 | 2 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.A31410 | HYB Essential Defueling Safety Case | Verify Review of Stress Modelling EAN & Issue for Technical Review | 25-May-23 A | 25-May-23 | 30-Jun-23 A | 30-Jun-23 | 0 | 0 | 25 | 100% |  | Completed
ER6668LT | W213 | W213.A31410 | TOR Essential Defueling Safety Case | Verify Review of Stress Modelling EAN & Issue for Technical Review | 25-May-23 A | 25-May-23 | 30-Jun-23 A | 30-Jun-23 | 0 | 0 | 25 | 100% |  | Completed
ER6372LT | W203 | W203.A3600 | HNB Enhanced Defuelling Safety Cases | BE Technical review of supporting reference <Purge and Pressurisation> | 25-May-23 A | 25-May-23 | 30-May-23 A | 30-May-23 | 3 | 0 | 3 | 100% |  | Completed
ER6378LT | W222 | W222.A27300 | HRA Fuel Handling Essential Safety Case | Update Cost Management Tool | 26-May-23 A | 26-May-23 | 26-May-23 A | 26-May-23 | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A27305 | HYA Fuel Handling Essential Safety Case | Update Cost Management Tool | 26-May-23 A | 26-May-23 | 26-May-23 A | 26-May-23 | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.B1020 | HNB Enhanced Defuelling Safety Cases | Verify supporting reference <Dropped Fuel Consequences EAN> | 29-May-23 A | 29-May-23 | 31-May-23 A | 31-May-23 | 3 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A5545 | HRA Reactors Shutdown Essential Safety Cases | Verification Complete - (Event Recovery) - EC 363682 | 30-May-23 A | 30-May-23 | 30-May-23 A | 30-May-23 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5545 | HYA Reactors Shutdown Essential Safety Cases | Verification Complete - (Event Recovery) - EC 363676 | 30-May-23 A | 30-May-23 | 30-May-23 A | 30-May-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A2670 | HNB Enhanced Defuelling Safety Cases | All key supporting technical references complete <RESUMED 01.03.2023> - Purge and Pressurisation | 30-May-23 A | 30-May-23 | 30-May-23 A | 30-May-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3590 | HNB Enhanced Defuelling Safety Cases | Supporting reference <Purge and Pressurisation> approved | 30-May-23 A | 30-May-23 | 30-May-23 A | 30-May-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3640 | HNB Enhanced Defuelling Safety Cases | All supporting references completed | 30-May-23 A | 30-May-23 | 30-May-23 A | 30-May-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A2590 | HNB Enhanced Defuelling Safety Cases | XXXX DISCOVERY MILESTONE: Decision to Proceed with EC Production XXXX | 31-May-23 A | 31-May-23 | 31-May-23 A | 31-May-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A31000 | HYB Essential Defueling Safety Case | Channel X Available | 31-May-23 A | 31-May-23 | 31-May-23 A | 31-May-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3650 | HNB Enhanced Defuelling Safety Cases | Draft NSRS complete - Purge and Pressurisation | 31-May-23 A | 31-May-23 | 31-May-23 A | 31-May-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A31000 | TOR Essential Defueling Safety Case | Channel X Available | 31-May-23 A | 31-May-23 | 31-May-23 A | 31-May-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.B1010 | HNB Enhanced Defuelling Safety Cases | BE Technical review of supporting reference <Dropped Fuel Consequences EAN> | 01-Jun-23 A | 01-Jun-23 | 05-Jun-23 A | 05-Jun-23 | 3 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.29520 | HYB Essential Defueling Safety Case | Draft - HYB R:77 (Deformed Standpipe Liner) EAN | 01-Jun-23 A | 01-Jun-23 | 16-Jun-23 A | 16-Jun-23 | 1 | 0 | 12 | 100% |  | Completed
ER6668LT | W213 | W213.29520 | TOR Essential Defueling Safety Case | Draft - TOR R:77 (Deformed Standpipe Liner) EAN | 01-Jun-23 A | 01-Jun-23 | 16-Jun-23 A | 16-Jun-23 | 1 | 0 | 12 | 100% |  | Completed
ER6372LT | W203 | W203.A1870 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Define Project Control Structures (WBS/CBS/OBS/PBS) | 01-Jun-23 A | 01-Jun-23 | 01-Jun-23 A | 01-Jun-23 | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1890 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 01-Jun-23 A | 01-Jun-23 | 01-Jun-23 A | 01-Jun-23 | 5 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1900 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 01-Jun-23 A | 01-Jun-23 | 01-Jun-23 A | 01-Jun-23 | 5 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1920 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Ensure Alignment of Schedule & Estimate | 01-Jun-23 A | 01-Jun-23 | 01-Jun-23 A | 01-Jun-23 | 3 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1930 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Hold Risk Workshop | 01-Jun-23 A | 01-Jun-23 | 01-Jun-23 A | 01-Jun-23 | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1940 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Complete Risk Log with Estimates | 01-Jun-23 A | 01-Jun-23 | 01-Jun-23 A | 01-Jun-23 | 2 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1950 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Update Schedule/Estimate from Risk Log & Add Provisions | 01-Jun-23 A | 01-Jun-23 | 01-Jun-23 A | 01-Jun-23 | 2 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1960 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Add Data to PRC Paper | 01-Jun-23 A | 01-Jun-23 | 01-Jun-23 A | 01-Jun-23 | 2 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1970 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> PCL Validate & Approve Baseline Package for PRC Submission | 01-Jun-23 A | 01-Jun-23 | 01-Jun-23 A | 01-Jun-23 | 3 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1880 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Prepare Draft Project Definition Document (PDD) | 01-Jun-23 A | 01-Jun-23 | 01-Jun-23 A | 01-Jun-23 | 5 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A2000 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Hold PRC Meeting | 01-Jun-23 A | 01-Jun-23 | 01-Jun-23 A | 01-Jun-23 | 1 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A1990 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> PRC Members Review PRC Documentation | 01-Jun-23 A | 01-Jun-23 | 01-Jun-23 A | 01-Jun-23 | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1850 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Confirm Objectives to be Delivered at Gate B | 01-Jun-23 A | 01-Jun-23 | 01-Jun-23 A | 01-Jun-23 | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1860 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Initial high level scope of programme | 01-Jun-23 A | 01-Jun-23 | 01-Jun-23 A | 01-Jun-23 | 2 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1910 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Workshop to agree scope, effort and links | 01-Jun-23 A | 01-Jun-23 | 01-Jun-23 A | 01-Jun-23 | 5 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A2110 | HNB Enhanced Defuelling Safety Cases | Project Management Gate B - C | 01-Jun-23 A | 01-Jun-23 | 19-Nov-24 A | 19-Nov-24 | 107 | 0 | 375 | 100% |  | Completed
W232LT | W232 | W232.B6510 | DNB Enhanced Safety Cases | Core Support Plate Structural Integrity Criticality - Approve Task Sheet | 01-Jun-23 A | 01-Jun-23 | 20-Jun-23 A | 20-Jun-23 | 5 | 0 | 13 | 100% |  | Completed
ER6372LT | W203 | W203.A3170 | HNB Enhanced Defuelling Safety Cases | Station comments on NSRS | 01-Jun-23 A | 01-Jun-23 | 23-Jun-23 A | 23-Jun-23 | 10 | 0 | 17 | 100% |  | Completed
ER6372LT | W203 | W203.A3180 | HNB Enhanced Defuelling Safety Cases | Key Stakeholders (Peer) comments on NSRS | 01-Jun-23 A | 01-Jun-23 | 23-Jun-23 A | 23-Jun-23 | 10 | 0 | 17 | 100% |  | Completed
ER6372LT | W203 | W203.A4040 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Develop plan with further iterations | 01-Jun-23 A | 01-Jun-23 | 01-Jun-23 A | 01-Jun-23 | 10 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1980 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Gate B PRC Paper Submission | 01-Jun-23 A | 01-Jun-23 | 01-Jun-23 A | 01-Jun-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A2020 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Gate B PRC Paper Approval | 01-Jun-23 A | 01-Jun-23 | 01-Jun-23 A | 01-Jun-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A4000 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Issue agreed work programme to stakeholders & suppliers | 01-Jun-23 A | 01-Jun-23 | 01-Jun-23 A | 01-Jun-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.B1000 | HNB Enhanced Defuelling Safety Cases | Supporting reference <Dropped Fuel Consequences EAN> approved | 05-Jun-23 A | 05-Jun-23 | 05-Jun-23 A | 05-Jun-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7100 | HYB Essential Defueling Safety Case | Verification of Claim 3 | 07-Jun-23 A | 07-Jun-23 | 13-Nov-23 A | 13-Nov-23 | 28 | 0 | 112 | 100% |  | Completed
ER6668LT | W213 | W213.7100 | TOR Essential Defueling Safety Case | Verification of Claim 3 | 07-Jun-23 A | 07-Jun-23 | 13-Nov-23 A | 13-Nov-23 | 28 | 0 | 113 | 100% |  | Completed
W232LT | W232 | W232.A1700 | DNB Enhanced Safety Cases | Verification of the case (using BARRIER MODEL) | 08-Jun-23 A | 08-Jun-23 | 12-Jul-23 A | 12-Jul-23 | 20 | 0 | 24 | 100% |  | Completed
ER6666LT | W209 | W209.7440 | HYB Essential Defueling Safety Case | Author Claim 7 | 12-Jun-23 A | 12-Jun-23 | 12-Jan-24 A | 12-Jan-24 | 40 | 0 | 151 | 100% |  | Completed
ER6666LT | W209 | W209.8410 | HYB Essential Defueling Safety Case | Claim 7 Production ## (Cost Summary) | 12-Jun-23 A | 12-Jun-23 | 26-Jan-24 A | 26-Jan-24 | 156 | 0 | 161 | 100% |  | Completed
ER6372LT | W203 | W203.A4120 | HNB Enhanced Defuelling Safety Cases | Verify supporting reference <IFD Deluge> | 12-Jun-23 A | 12-Jun-23 | 15-Jun-23 A | 15-Jun-23 | 3 | 0 | 3 | 100% |  | Completed
ER6372LT | W203 | W203.B1070 | HNB Enhanced Defuelling Safety Cases | Produce supporting reference <PSA Updates> | 12-Jun-23 A | 12-Jun-23 | 03-Nov-23 A | 03-Nov-23 | 20 | 0 | 104 | 100% |  | Completed
ER6668LT | W213 | W213.7440 | TOR Essential Defueling Safety Case | Author Claim 7 | 12-Jun-23 A | 12-Jun-23 | 12-Jan-24 A | 12-Jan-24 | 40 | 0 | 151 | 100% |  | Completed
ER6668LT | W213 | W213.8410 | TOR Essential Defueling Safety Case | Claim 7 Production ## (Cost Summary) | 12-Jun-23 A | 12-Jun-23 | 26-Jan-24 A | 26-Jan-24 | 152 | 0 | 161 | 100% |  | Completed
ER6371LT | W202 | 3010 | HRA Reactors Shutdown Essential Safety Cases | Lesson Learn - Verification Phase | 12-Jun-23 A | 12-Jun-23 | 12-Jun-23 A | 12-Jun-23 | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | 3010 | HYA Reactors Shutdown Essential Safety Cases | Lesson Learn - Verification Phase | 12-Jun-23 A | 12-Jun-23 | 12-Jun-23 A | 12-Jun-23 | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.29120 | HYB Essential Defueling Safety Case | Upload to CDMS | 13-Jun-23 A | 13-Jun-23 | 19-Jun-23 A | 19-Jun-23 | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.29120 | TOR Essential Defueling Safety Case | Upload to CDMS | 13-Jun-23 A | 13-Jun-23 | 19-Jun-23 A | 19-Jun-23 | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.7370 | HYB Essential Defueling Safety Case | Verification of Claim 6 | 14-Jun-23 A | 14-Jun-23 | 10-Nov-23 A | 10-Nov-23 | 20 | 0 | 106 | 100% |  | Completed
ER6668LT | W213 | W213.7370 | TOR Essential Defueling Safety Case | Verification of Claim 6 | 14-Jun-23 A | 14-Jun-23 | 10-Nov-23 A | 10-Nov-23 | 20 | 0 | 107 | 100% |  | Completed
ER6372LT | W203 | W203.A4110 | HNB Enhanced Defuelling Safety Cases | BE Technical review of supporting reference <IFD Deluge> | 15-Jun-23 A | 15-Jun-23 | 30-Jun-23 A | 30-Jun-23 | 3 | 0 | 11 | 100% |  | Completed
ER6666LT | W209 | W209.A30730 | HYB Essential Defueling Safety Case | Complete TR Form and Issue Channel 1 - HYB to CDMS | 16-Jun-23 A | 16-Jun-23 | 14-Jul-23 A | 14-Jul-23 | 15 | 0 | 21 | 100% |  | Completed
ER6668LT | W213 | W213.A30730 | TOR Essential Defueling Safety Case | Complete TR Form and Issue Channel 1 - TOR to CDMS | 16-Jun-23 A | 16-Jun-23 | 14-Jul-23 A | 14-Jul-23 | 15 | 0 | 21 | 100% |  | Completed
ER6371LT | W202 | 1636 | HRA Reactors Shutdown Essential Safety Cases | Re-Write of FDD v3 | 19-Jun-23 A | 19-Jun-23 | 18-Jul-23 A | 18-Jul-23 | 1 | 0 | 21 | 100% |  | Completed
ER6661LT | W206 | 1636 | HYA Reactors Shutdown Essential Safety Cases | Re-Write of FDD v3 | 19-Jun-23 A | 19-Jun-23 | 18-Jul-23 A | 18-Jul-23 | 1 | 0 | 21 | 100% |  | Completed
ER6666LT | W209 | W209.29440 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Human Factors Assessment of Misloading / Mis-Defueling Faults EAN to CDMS | 19-Jun-23 A | 19-Jun-23 | 30-Jun-23 A | 30-Jun-23 | 5 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.29530 | HYB Essential Defueling Safety Case | Verify - HYB R:77 (Deformed Standpipe Liner) EAN | 19-Jun-23 A | 19-Jun-23 | 20-Jul-23 A | 20-Jul-23 | 1 | 0 | 24 | 100% |  | Completed
ER6668LT | W213 | W213.29440 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Human Factors Assessment of Misloading / Mis-Defueling Faults EAN to CDMS | 19-Jun-23 A | 19-Jun-23 | 30-Jun-23 A | 30-Jun-23 | 5 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.29530 | TOR Essential Defueling Safety Case | Verify - TOR R:77 (Deformed Standpipe Liner) EAN | 19-Jun-23 A | 19-Jun-23 | 20-Jul-23 A | 20-Jul-23 | 1 | 0 | 24 | 100% |  | Completed
ER6666LT | W209 | W209.7430 | HYB Essential Defueling Safety Case | PJB for Claim 7 Authoring | 20-Jun-23 A | 20-Jun-23 | 20-Jun-23 A | 20-Jun-23 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B6520 | DNB Enhanced Safety Cases | Core Support Plate Structural Integrity Criticality - Pre Job Brief | 20-Jun-23 A | 20-Jun-23 | 23-Jun-23 A | 23-Jun-23 | 5 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.7430 | TOR Essential Defueling Safety Case | PJB for Claim 7 Authoring | 20-Jun-23 A | 20-Jun-23 | 20-Jun-23 A | 20-Jun-23 | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7180 | HYB Essential Defueling Safety Case | Case Officer Tech Lead Review Claim 5 | 21-Jun-23 A | 21-Jun-23 | 15-Dec-23 A | 15-Dec-23 | 10 | 0 | 126 | 100% |  | Completed
ER6668LT | W213 | W213.7180 | TOR Essential Defueling Safety Case | Case Officer Tech Lead Review Claim 5 | 21-Jun-23 A | 21-Jun-23 | 15-Dec-23 A | 15-Dec-23 | 10 | 0 | 126 | 100% |  | Completed
ER6372LT | W203 | W203.A3510 | HNB Enhanced Defuelling Safety Cases | INA comments on NSRS | 23-Jun-23 A | 23-Jun-23 | 24-Jul-23 A | 24-Jul-23 | 10 | 0 | 21 | 100% |  | Completed
W232LT | W232 | W232.B6490 | DNB Enhanced Safety Cases | Core Support Plate Structural Integrity Criticality - Summary | 26-Jun-23 A | 26-Jun-23 | 25-Sep-23 A | 25-Sep-23 | 87 | 0 | 64 | 100% |  | Completed
W232LT | W232 | W232.B6540 | DNB Enhanced Safety Cases | Core Support Plate Structural Integrity Criticality - Prepare Draft EAN | 26-Jun-23 A | 26-Jun-23 | 21-Aug-23 A | 21-ug-23 | 20 | 0 | 40 | 100% |  | Completed
ER6666LT | W209 | W209.9020 | HYB Essential Defueling Safety Case | Discovery Milestone - HF assessment of Misloading/Misdefueling - EAN Available | 30-Jun-23 A | 30-Jun-23 | 30-Jun-23 A | 30-Jun-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1490 | DNB Enhanced Safety Cases | All supporting references completed | 30-Jun-23 A | 30-Jun-23 | 30-Jun-23 A | 30-Jun-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2760 | DNB Enhanced Safety Cases | Supporting reference <Maintenance Review of FR Plant> approved | 30-Jun-23 A | 30-Jun-23 | 30-Jun-23 A | 30-Jun-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A4100 | HNB Enhanced Defuelling Safety Cases | Supporting reference <IFD Deluge> approved | 30-Jun-23 A | 30-Jun-23 | 30-Jun-23 A | 30-Jun-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.9020 | TOR Essential Defueling Safety Case | Discovery Milestone - HF assessment of Misloading/Misdefueling - EAN Available | 30-Jun-23 A | 30-Jun-23 | 30-Jun-23 A | 30-Jun-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.29450 | HYB Essential Defueling Safety Case | Human Factors Assessment of Misloading / Mis-Defueling Faults EAN Available (REV 001) | 30-Jun-23 A | 30-Jun-23 | 30-Jun-23 A | 30-Jun-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.29450 | TOR Essential Defueling Safety Case | Human Factors Assessment of Misloading / Mis-Defueling Faults EAN Available (REV 001) | 30-Jun-23 A | 30-Jun-23 | 30-Jun-23 A | 30-Jun-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3240 | HNB Enhanced Defuelling Safety Cases | CA to agree with CO format of the safety case & produce agreed contents page | 03-Jul-23 A | 03-Jul-23 | 06-Jul-23 A | 06-Jul-23 | 2 | 0 | 3 | 100% |  | Completed
ER6372LT | W203 | W203.A3530 | HNB Enhanced Defuelling Safety Cases | Develop plan with further iterations | 03-Jul-23 A | 03-Jul-23 | 14-Jul-23 A | 14-Jul-23 | 10 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.A24600 | HYB Essential Defueling Safety Case | Technical Review of Human Reliability Baseline Report EAN | 04-Jul-23 A | 04-Jul-23 | 31-Jul-23 A | 31-Jul-23 | 16 | 0 | 20 | 100% |  | Completed
ER6668LT | W213 | W213.A24600 | TOR Essential Defueling Safety Case | Technical Review of Human Reliability Baseline Report EAN | 04-Jul-23 A | 04-Jul-23 | 31-Jul-23 A | 31-Jul-23 | 16 | 0 | 20 | 100% |  | Completed
ER6372LT | W203 | W203.A3250 | HNB Enhanced Defuelling Safety Cases | Prepare the Safety Case Proposal - <Purge and Pressurisation> | 10-Jul-23 A | 10-Jul-23 | 19-Aug-23 A | 19-ug-23 | 12 | 0 | 30 | 100% |  | Completed
W232LT | W232 | W232.A1750 | DNB Enhanced Safety Cases | Issue to CO & Station for comments | 12-Jul-23 A | 12-Jul-23 | 12-Jul-23 A | 12-Jul-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A30740 | HYB Essential Defueling Safety Case | Channel 1 Detailed Design Spec - HYB Available | 14-Jul-23 A | 14-Jul-23 | 14-Jul-23 A | 14-Jul-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A30740 | TOR Essential Defueling Safety Case | Channel 1 Detailed Design Spec - TOR Available | 14-Jul-23 A | 14-Jul-23 | 14-Jul-23 A | 14-Jul-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3760 | HNB Enhanced Defuelling Safety Cases | Prepare the Safety Case Proposal | 17-Jul-23 A | 17-Jul-23 | 20-Nov-23 A | 20-Nov-23 | 28 | 0 | 90 | 100% |  | Completed
W232LT | W232 | W232.A1760 | DNB Enhanced Safety Cases | Incorporate CO & Station comments | 17-Jul-23 A | 17-Jul-23 | 21-Jul-23 A | 21-Jul-23 | 5 | 0 | 4 | 100% |  | Completed
ER6666LT | W209 | W209.A31120 | HYB Essential Defueling Safety Case | Upload Defueling Process Flow to CDMS | 18-Jul-23 A | 18-Jul-23 | 31-Jul-23 A | 31-Jul-23 | 5 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.A31120 | TOR Essential Defueling Safety Case | Upload Defueling Process Flow to CDMS | 18-Jul-23 A | 18-Jul-23 | 31-Jul-23 A | 31-Jul-23 | 5 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | 1646 | HRA Reactors Shutdown Essential Safety Cases | Verifed updated FDD v3 | 19-Jul-23 A | 19-Jul-23 | 09-Oct-23 A | 09-Oct-23 | 10 | 0 | 57 | 100% |  | Completed
ER6661LT | W206 | 1646 | HYA Reactors Shutdown Essential Safety Cases | Verifed updated FDD v3 | 19-Jul-23 A | 19-Jul-23 | 09-Oct-23 A | 09-Oct-23 | 10 | 0 | 57 | 100% |  | Completed
ER6666LT | W209 | W209.A29270 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Defuelling Hazards Review EAN to CDMS | 21-Jul-23 A | 21-Jul-23 | 31-Jul-23 A | 31-Jul-23 | 5 | 0 | 6 | 100% |  | Completed
ER6666LT | W209 | W209.29540 | HYB Essential Defueling Safety Case | Complete HYB R:77 (Deformed Standpipe Liner) EAN and Upload to CDMS | 21-Jul-23 A | 21-Jul-23 | 31-Jul-23 A | 31-Jul-23 | 5 | 0 | 6 | 100% |  | Completed
ER6668LT | W213 | W213.A29270 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Defuelling Hazards Review EAN to CDMS | 21-Jul-23 A | 21-Jul-23 | 31-Jul-23 A | 31-Jul-23 | 5 | 0 | 6 | 100% |  | Completed
ER6668LT | W213 | W213.29540 | TOR Essential Defueling Safety Case | Complete TOR R:77 (Deformed Standpipe Liner) EAN and Upload to CDMS | 21-Jul-23 A | 21-Jul-23 | 31-Jul-23 A | 31-Jul-23 | 5 | 0 | 6 | 100% |  | Completed
W232LT | W232 | W232.A1810 | DNB Enhanced Safety Cases | Key Stakeholders Approval, if requested | 24-Jul-23 A | 24-Jul-23 | 25-Jul-23 A | 25-Jul-23 | 5 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.29150 | HYB Essential Defueling Safety Case | Verification | 24-Jul-23 A | 24-Jul-23 | 20-Oct-23 A | 20-Oct-23 | 12 | 0 | 64 | 100% |  | Completed
ER6372LT | W203 | W203.A3350 | HNB Enhanced Defuelling Safety Cases | Incorporate INA, Station, ED (peer) comments | 24-Jul-23 A | 24-Jul-23 | 25-Jul-23 A | 25-Jul-23 | 3 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.A31420 | HYB Essential Defueling Safety Case | Technical Review of Stress Modelling EAN | 24-Jul-23 A | 24-Jul-23 | 11-Aug-23 A | 11-ug-23 | 10 | 0 | 14 | 100% |  | Completed
ER6668LT | W213 | W213.29150 | TOR Essential Defueling Safety Case | Verification | 24-Jul-23 A | 24-Jul-23 | 20-Oct-23 A | 20-Oct-23 | 12 | 0 | 63 | 100% |  | Completed
ER6668LT | W213 | W213.A31420 | TOR Essential Defueling Safety Case | Technical Review of Stress Modelling EAN | 24-Jul-23 A | 24-Jul-23 | 11-Aug-23 A | 11-ug-23 | 10 | 0 | 14 | 100% |  | Completed
ER6666LT | W209 | W209.A31370 | HYB Essential Defueling Safety Case | Upload Fuelling Machine Purging Requirements During Defueling to CDMS | 24-Jul-23 A | 24-Jul-23 | 28-Jul-23 A | 28-Jul-23 | 5 | 0 | 4 | 100% |  | Completed
ER6668LT | W213 | W213.A31370 | TOR Essential Defueling Safety Case | Upload Fuelling Machine Purging Requirements During Defueling to CDMS | 24-Jul-23 A | 24-Jul-23 | 28-Jul-23 A | 28-Jul-23 | 5 | 0 | 4 | 100% |  | Completed
ER6372LT | W203 | W203.A3490 | HNB Enhanced Defuelling Safety Cases | Issue agreed work programme to stakeholders & suppliers | 24-Jul-23 A | 24-Jul-23 | 24-Jul-23 A | 24-Jul-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A2450 | HNB Enhanced Defuelling Safety Cases | NSRS approved - Purge and Pressurisation | 25-Jul-23 A | 25-Jul-23 | 25-Jul-23 A | 25-Jul-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3190 | HNB Enhanced Defuelling Safety Cases | Issue final NSRS - <Purge and Pressurisation> | 25-Jul-23 A | 25-Jul-23 | 25-Jul-23 A | 25-Jul-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3200 | HNB Enhanced Defuelling Safety Cases | Station agree NSRS (KDM) - <Purge and Pressurisation> | 25-Jul-23 A | 25-Jul-23 | 25-Jul-23 A | 25-Jul-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3230 | HNB Enhanced Defuelling Safety Cases | Consolidate & issue to stakeholders & suppliers agreed NSRS | 25-Jul-23 A | 25-Jul-23 | 26-Jul-23 A | 26-Jul-23 | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A3370 | HNB Enhanced Defuelling Safety Cases | Key Stakeholders (DA) agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 25-Jul-23 A | 25-Jul-23 | 25-Jul-23 A | 25-Jul-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3520 | HNB Enhanced Defuelling Safety Cases | INA agree NSRS - <Purge and Pressurisation> | 25-Jul-23 A | 25-Jul-23 | 25-Jul-23 A | 25-Jul-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1770 | DNB Enhanced Safety Cases | Produce verification file | 26-Jul-23 A | 26-Jul-23 | 28-Jul-23 A | 28-Jul-23 | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A5290 | HRA Reactors Shutdown Essential Safety Cases | Incorporate INSA comments (HRA) | 28-Jul-23 A | 28-Jul-23 | 19-Sep-23 A | 19-Sep-23 | 9 | 0 | 36 | 100% |  | Completed
ER6661LT | W206 | W206.A5290 | HYA Reactors Shutdown Essential Safety Cases | Incorporate INSA comments (HYA) | 28-Jul-23 A | 28-Jul-23 | 19-Sep-23 A | 19-Sep-23 | 9 | 0 | 36 | 100% |  | Completed
W232LT | W232 | W232.A4930 | DNB Enhanced Safety Cases | Lessons Learned Workshop 2 - FPU Safety Case Authored | 28-Jul-23 A | 28-Jul-23 | 28-Jul-23 A | 28-Jul-23 | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A31380 | HYB Essential Defueling Safety Case | Fuelling Machine Purging Requirements During Defueling Available | 28-Jul-23 A | 28-Jul-23 | 28-Jul-23 A | 28-Jul-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A31380 | TOR Essential Defueling Safety Case | Fuelling Machine Purging Requirements During Defueling Available | 28-Jul-23 A | 28-Jul-23 | 28-Jul-23 A | 28-Jul-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A29280 | HYB Essential Defueling Safety Case | Defuelling Hazards Review EAN Available | 31-Jul-23 A | 31-Jul-23 | 31-Jul-23 A | 31-Jul-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A24610 | HYB Essential Defueling Safety Case | Supplier Update and Issue Human Reliability Baseline Report EAN | 31-Jul-23 A | 31-Jul-23 | 23-Aug-23 A | 23-ug-23 | 5 | 0 | 18 | 100% |  | Completed
ER6668LT | W213 | W213.A29280 | TOR Essential Defueling Safety Case | Defuelling Hazards Review EAN Available | 31-Jul-23 A | 31-Jul-23 | 31-Jul-23 A | 31-Jul-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A24610 | TOR Essential Defueling Safety Case | Supplier Update and Issue Human Reliability Baseline Report EAN | 31-Jul-23 A | 31-Jul-23 | 23-Aug-23 A | 23-ug-23 | 5 | 0 | 18 | 100% |  | Completed
ER6666LT | W209 | W209.25910 | HYB Essential Defueling Safety Case | Technical Review of Human Reliability Assessment of Unsubstantiated Claims EAN | 31-Jul-23 A | 31-Jul-23 | 29-Sep-23 A | 29-Sep-23 | 6 | 0 | 44 | 100% |  | Completed
ER6668LT | W213 | W213.25910 | TOR Essential Defueling Safety Case | Technical Review of Human Reliability Assessment of Unsubstantiated Claims EAN | 31-Jul-23 A | 31-Jul-23 | 29-Sep-23 A | 29-Sep-23 | 6 | 0 | 44 | 100% |  | Completed
ER6666LT | W209 | W209.A31130 | HYB Essential Defueling Safety Case | Defueling Process Flow Available | 31-Jul-23 A | 31-Jul-23 | 31-Jul-23 A | 31-Jul-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A4160 | HNB Enhanced Defuelling Safety Cases | Draft NSRS complete - IFD Deluge | 31-Jul-23 A | 31-Jul-23 | 31-Jul-23 A | 31-Jul-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A31130 | TOR Essential Defueling Safety Case | Defueling Process Flow Available | 31-Jul-23 A | 31-Jul-23 | 31-Jul-23 A | 31-Jul-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1800 | DNB Enhanced Safety Cases | Issue high quality verified draft issue A with verification file to INSA & station (T - 3 weeks before NSC date) *(KDM)* | 02-Aug-23 A | 02-ug-23 | 02-Aug-23 A | 02-ug-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1780 | DNB Enhanced Safety Cases | Verification complete | 02-Aug-23 A | 02-ug-23 | 02-Aug-23 A | 02-ug-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1790 | DNB Enhanced Safety Cases | Submit for approval - Categoriser ratifies; RE/CO endorsement | 02-Aug-23 A | 02-ug-23 | 02-Aug-23 A | 02-ug-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7380 | HYB Essential Defueling Safety Case | Update Claim 6 | 03-Aug-23 A | 03-ug-23 | 10-Nov-23 A | 10-Nov-23 | 19 | 0 | 70 | 100% |  | Completed
ER6668LT | W213 | W213.7380 | TOR Essential Defueling Safety Case | Update Claim 6 | 03-Aug-23 A | 03-ug-23 | 10-Nov-23 A | 10-Nov-23 | 19 | 0 | 71 | 100% |  | Completed
ER6666LT | W209 | W209.28860 | HYB Essential Defueling Safety Case | Verification of PSA following Updates | 04-Aug-23 A | 04-ug-23 | 08-Dec-23 A | 08-Dec-23 | 5 | 0 | 90 | 100% |  | Completed
ER6668LT | W213 | W213.28860 | TOR Essential Defueling Safety Case | Verification of PSA following Updates | 04-Aug-23 A | 04-ug-23 | 08-Dec-23 A | 08-Dec-23 | 5 | 0 | 89 | 100% |  | Completed
W232LT | W232 | W232.A1820 | DNB Enhanced Safety Cases | INSA review & iteration of comments (using BARRIER MODEL) | 04-Aug-23 A | 04-ug-23 | 08-Aug-23 A | 08-ug-23 | 10 | 0 | 2 | 100% |  | Completed
W232LT | W232 | W232.A2870 | DNB Enhanced Safety Cases | Carry out ALARP Review of OEM NSP Removal | 07-Aug-23 A | 07-ug-23 | 25-Sep-23 A | 25-Sep-23 | 34 | 0 | 34 | 100% |  | Completed
ER6372LT | W203 | W203.B1060 | HNB Enhanced Defuelling Safety Cases | Verify supporting reference <PSA Updates> | 08-Aug-23 A | 08-ug-23 | 08-Nov-23 A | 08-Nov-23 | 3 | 0 | 66 | 100% |  | Completed
W232LT | W232 | W232.A1840 | DNB Enhanced Safety Cases | Incorporate INSA comments | 09-Aug-23 A | 09-ug-23 | 15-Aug-23 A | 15-ug-23 | 5 | 0 | 4 | 100% |  | Completed
ER6372LT | W203 | W203.A3280 | HNB Enhanced Defuelling Safety Cases | Verification of the case (using BARRIER MODEL) - <Purge and Pressurisation> | 11-Aug-23 A | 11-ug-23 | 25-Aug-23 A | 25-ug-23 | 13 | 0 | 10 | 100% |  | Completed
ER6372LT | W203 | W203.A3570 | HNB Enhanced Defuelling Safety Cases | Specialist Assessment | 11-Aug-23 A | 11-ug-23 | 25-Aug-23 A | 25-ug-23 | 13 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.1435 | HYB Essential Defueling Safety Case | Prepare the Safety Case Proposal - Part 1 | 14-Aug-23 A | 14-ug-23 | 22-Dec-23 A | 22-Dec-23 | 1 | 0 | 93 | 100% |  | Completed
ER6666LT | W209 | W209.A31430 | HYB Essential Defueling Safety Case | Supplier Update and Issue Stress Modelling EAN | 14-Aug-23 A | 14-ug-23 | 18-Aug-23 A | 18-ug-23 | 5 | 0 | 4 | 100% |  | Completed
ER6668LT | W213 | W213.1435 | TOR Essential Defueling Safety Case | Prepare the Safety Case Proposal - Part 1 | 14-Aug-23 A | 14-ug-23 | 22-Dec-23 A | 22-Dec-23 | 1 | 0 | 93 | 100% |  | Completed
ER6668LT | W213 | W213.A31430 | TOR Essential Defueling Safety Case | Supplier Update and Issue Stress Modelling EAN | 14-Aug-23 A | 14-ug-23 | 18-Aug-23 A | 18-ug-23 | 5 | 0 | 4 | 100% |  | Completed
W232LT | W232 | W232.A1870 | DNB Enhanced Safety Cases | INSA Final Approval *(KDM)* | 16-Aug-23 A | 16-ug-23 | 17-Aug-23 A | 17-ug-23 | 5 | 0 | 2 | 100% |  | Completed
ER6372LT | W203 | W203.A3680 | HNB Enhanced Defuelling Safety Cases | Station comments on NSRS | 18-Aug-23 A | 18-ug-23 | 24-Aug-23 A | 24-ug-23 | 5 | 0 | 4 | 100% |  | Completed
ER6372LT | W203 | W203.A3690 | HNB Enhanced Defuelling Safety Cases | Key Stakeholders (Peer) comments on NSRS | 18-Aug-23 A | 18-ug-23 | 24-Aug-23 A | 24-ug-23 | 5 | 0 | 4 | 100% |  | Completed
W232LT | W232 | W232.A4940 | DNB Enhanced Safety Cases | Lessons Learned Workshop 3 - FPU Safety Case Verified | 18-Aug-23 A | 18-ug-23 | 18-Aug-23 A | 18-ug-23 | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A3270 | HNB Enhanced Defuelling Safety Cases | Produce verification plan | 19-Aug-23 A | 19-ug-23 | 20-Aug-23 A | 20-ug-23 | 2 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A31440 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Stress Modelling EAN to CDMS | 21-Aug-23 A | 21-ug-23 | 25-Aug-23 A | 25-ug-23 | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A31440 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Stress Modelling EAN to CDMS | 21-Aug-23 A | 21-ug-23 | 25-Aug-23 A | 25-ug-23 | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.A2600 | DNB Enhanced Safety Cases | Assess Results of Lift Lower Trials | 21-Aug-23 A | 21-ug-23 | 25-Aug-23 A | 25-ug-23 | 9 | 0 | 4 | 100% |  | Completed
W232LT | W232 | W232.B6610 | DNB Enhanced Safety Cases | Core Support Plate Structural Integrity Criticality - TSA Internal Review of Draft EAN | 22-Aug-23 A | 22-ug-23 | 04-Sep-23 A | 04-Sep-23 | 5 | 0 | 8 | 100% |  | Completed
ER6372LT | W203 | W203.A4020 | HNB Enhanced Defuelling Safety Cases | INA comments on NSRS | 24-Aug-23 A | 24-ug-23 | 03-Nov-23 A | 03-Nov-23 | 5 | 0 | 51 | 100% |  | Completed
ER6666LT | W209 | W209.A24620 | HYB Essential Defueling Safety Case | Complete Review of Human Reliability Baseline Report EAN to CDMS | 24-Aug-23 A | 24-ug-23 | 31-Aug-23 A | 31-ug-23 | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A24620 | TOR Essential Defueling Safety Case | Complete Review of Human Reliability Baseline Report EAN to CDMS | 24-Aug-23 A | 24-ug-23 | 31-Aug-23 A | 31-ug-23 | 5 | 0 | 5 | 100% |  | Completed
ER6372LT | W203 | W203.A3460 | HNB Enhanced Defuelling Safety Cases | Issue to CO & Station for comments - <Purge and Pressurisation> | 25-Aug-23 A | 25-ug-23 | 25-Aug-23 A | 25-ug-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A31450 | HYB Essential Defueling Safety Case | Stress Modelling EAN Available | 25-Aug-23 A | 25-ug-23 | 25-Aug-23 A | 25-ug-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A31450 | TOR Essential Defueling Safety Case | Stress Modelling EAN Available | 25-Aug-23 A | 25-ug-23 | 25-Aug-23 A | 25-ug-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3260 | HNB Enhanced Defuelling Safety Cases | Incorporate CO & Station comments | 28-Aug-23 A | 28-ug-23 | 29-Aug-23 A | 29-ug-23 | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A3290 | HNB Enhanced Defuelling Safety Cases | Produce verification file | 29-Aug-23 A | 29-ug-23 | 29-Aug-23 A | 29-ug-23 | 2 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A3300 | HNB Enhanced Defuelling Safety Cases | Issue high quality verified draft issue A with verification file to INSA & station (KDM) - <Purge and Pressurisation> | 29-Aug-23 A | 29-ug-23 | 29-Aug-23 A | 29-ug-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3310 | HNB Enhanced Defuelling Safety Cases | INSA review & iteration of comments (using BARRIER MODEL) | 29-Aug-23 A | 29-ug-23 | 12-Sep-23 A | 12-Sep-23 | 10 | 0 | 11 | 100% |  | Completed
ER6372LT | W203 | W203.A3410 | HNB Enhanced Defuelling Safety Cases | Verification complete | 29-Aug-23 A | 29-ug-23 | 29-Aug-23 A | 29-ug-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3420 | HNB Enhanced Defuelling Safety Cases | Submit for approval - Categoriser ratifies; RE/CO endorsement | 29-Aug-23 A | 29-ug-23 | 29-Aug-23 A | 29-ug-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3430 | HNB Enhanced Defuelling Safety Cases | Key Stakeholders Approval, if requested | 29-Aug-23 A | 29-ug-23 | 05-Sep-23 A | 05-Sep-23 | 5 | 0 | 6 | 100% |  | Completed
ER6666LT | W209 | W209.A31280 | HYB Essential Defueling Safety Case | Verify PSA Documentation & Issue for Technical Review | 29-Aug-23 A | 29-ug-23 | 03-Jun-24 A | 03-Jun-24 | 31 | 0 | 193 | 100% |  | Completed
ER6668LT | W213 | W213.A31280 | TOR Essential Defueling Safety Case | Verify PSA Documentation & Issue for Technical Review | 29-Aug-23 A | 29-ug-23 | 03-Jun-24 A | 03-Jun-24 | 31 | 0 | 193 | 100% |  | Completed
ER6666LT | W209 | W209.9030 | HYB Essential Defueling Safety Case | Discovery Milestone - Human Reliability Baseline Report - EAN Available | 31-Aug-23 A | 31-ug-23 | 31-Aug-23 A | 31-ug-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.9030 | TOR Essential Defueling Safety Case | Discovery Milestone - Human Reliability Baseline Report - EAN Available | 31-Aug-23 A | 31-ug-23 | 31-Aug-23 A | 31-ug-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A24630 | HYB Essential Defueling Safety Case | Human Reliability Baseline Report EAN Available | 31-Aug-23 A | 31-ug-23 | 31-Aug-23 A | 31-ug-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A24630 | TOR Essential Defueling Safety Case | Human Reliability Baseline Report EAN Available | 31-Aug-23 A | 31-ug-23 | 31-Aug-23 A | 31-ug-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1880 | DNB Enhanced Safety Cases | Station Approval for mod implementation (including station review meeting) | 01-Sep-23 A | 01-Sep-23 | 07-Sep-23 A | 07-Sep-23 | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.7970 | HYB Essential Defueling Safety Case | Draft Human Factors Integration Plan EAN (REV 001) | 04-Sep-23 A | 04-Sep-23 | 13-Oct-23 A | 13-Oct-23 | 10 | 0 | 30 | 100% |  | Completed
ER6668LT | W213 | W213.7970 | TOR Essential Defueling Safety Case | Draft Human Factors Integration Plan EAN (REV 001) | 04-Sep-23 A | 04-Sep-23 | 13-Oct-23 A | 13-Oct-23 | 10 | 0 | 29 | 100% |  | Completed
W232LT | W232 | W232.B6550 | DNB Enhanced Safety Cases | Core Support Plate Structural Integrity Criticality - Issue Draft EAN to EDF for Review. | 04-Sep-23 A | 04-Sep-23 | 04-Sep-23 A | 04-Sep-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B6560 | DNB Enhanced Safety Cases | Core Support Plate Structural Integrity Criticality - Draft EAN Reviewed by EDF SQEP | 05-Sep-23 A | 05-Sep-23 | 18-Sep-23 A | 18-Sep-23 | 10 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | 001955a | HYA Fuel Handling Essential Safety Case | Claim 5 Updates - Needs FDD | 05-Sep-23 A | 05-Sep-23 | 21-Sep-23 A | 21-Sep-23 | 15 | 0 | 12 | 100% |  | Completed
W232LT | W232 | W232.A1900 | DNB Enhanced Safety Cases | Station Approval Obtained and CAT 2 Safety Case Complete *(KDM)* | 07-Sep-23 A | 07-Sep-23 | 07-Sep-23 A | 07-Sep-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2610 | DNB Enhanced Safety Cases | Define Benefits and Objectives of Cold Defuelling | 11-Sep-23 A | 11-Sep-23 | 25-Sep-23 A | 25-Sep-23 | 15 | 0 | 10 | 100% |  | Completed
ER6372LT | W203 | W203.A3470 | HNB Enhanced Defuelling Safety Cases | Incorporate INSA comments | 13-Sep-23 A | 13-Sep-23 | 29-Sep-23 A | 29-Sep-23 | 1 | 0 | 12 | 100% |  | Completed
ER6666LT | W209 | W209.A27410 | HYB Essential Defueling Safety Case | Technical Review of Fuel Route PSA Update EAN | 18-Sep-23 A | 18-Sep-23 | 22-Dec-23 A | 22-Dec-23 | 15 | 0 | 70 | 100% |  | Completed
ER6668LT | W213 | W213.A27410 | TOR Essential Defueling Safety Case | Technical Review of Fuel Route PSA Update EAN | 18-Sep-23 A | 18-Sep-23 | 22-Dec-23 A | 22-Dec-23 | 15 | 0 | 69 | 100% |  | Completed
ER6666LT | W209 | W209.28940 | HYB Essential Defueling Safety Case | Update Claim 3 | 18-Sep-23 A | 18-Sep-23 | 13-Nov-23 A | 13-Nov-23 | 5 | 0 | 40 | 100% |  | Completed
ER6668LT | W213 | W213.28940 | TOR Essential Defueling Safety Case | Update Claim 3 | 18-Sep-23 A | 18-Sep-23 | 13-Nov-23 A | 13-Nov-23 | 5 | 0 | 41 | 100% |  | Completed
ER6666LT | W209 | W209.7710 | HYB Essential Defueling Safety Case | Early INA Review Claim 1 | 19-Sep-23 A | 19-Sep-23 | 29-Nov-23 A | 29-Nov-23 | 20 | 0 | 51 | 100% |  | Completed
ER6668LT | W213 | W213.7710 | TOR Essential Defueling Safety Case | INSA Pre Review Claim 1 | 19-Sep-23 A | 19-Sep-23 | 29-Nov-23 A | 29-Nov-23 | 20 | 0 | 51 | 100% |  | Completed
W232LT | W232 | W232.B6570 | DNB Enhanced Safety Cases | Core Support Plate Structural Integrity Criticality - Address Comments from EDF Review on Draft EAN | 19-Sep-23 A | 19-Sep-23 | 22-Sep-23 A | 22-Sep-23 | 10 | 0 | 3 | 100% |  | Completed
W232LT | W232 | W232.B6580 | DNB Enhanced Safety Cases | Core Support Plate Structural Integrity Criticality - Issue Final EAN | 22-Sep-23 A | 22-Sep-23 | 22-Sep-23 A | 22-Sep-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B6590 | DNB Enhanced Safety Cases | Core Support Plate Structural Integrity Criticality - EAN Completed and Uploaded to CDMS | 22-Sep-23 A | 22-Sep-23 | 25-Sep-23 A | 25-Sep-23 | 10 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 001955b | HYA Fuel Handling Essential Safety Case | Claim 6 Updates - ALARP | 22-Sep-23 A | 22-Sep-23 | 07-Nov-23 A | 07-Nov-23 | 4 | 0 | 33 | 100% |  | Completed
W232LT | W232 | W232.B6600 | DNB Enhanced Safety Cases | Core Support Plate Structural Integrity Criticality - EAN Completed | 25-Sep-23 A | 25-Sep-23 | 25-Sep-23 A | 25-Sep-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.29180 | HYB Essential Defueling Safety Case | Produce new Defuelling SSR text | 25-Sep-23 A | 25-Sep-23 | 08-Dec-23 A | 08-Dec-23 | 20 | 0 | 55 | 100% |  | Completed
ER6668LT | W213 | W213.29180 | TOR Essential Defueling Safety Case | Produce new Defuelling SSR text | 25-Sep-23 A | 25-Sep-23 | 08-Dec-23 A | 08-Dec-23 | 20 | 0 | 55 | 100% |  | Completed
W232LT | W232 | W232.A2880 | DNB Enhanced Safety Cases | Discovery Milestone - Warm Extraction Acceptable Y/N | 25-Sep-23 A | 25-Sep-23 | 01-Nov-23 A | 01-Nov-23 | 15 | 0 | 28 | 100% |  | Completed
ER6666LT | W209 | W209.5360 | HYB Essential Defueling Safety Case | CLAIM 1 - Sub Critical Margin (SCM) | 28-Sep-23 A | 28-Sep-23 | 28-Sep-23 A | 28-Sep-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.6960 | HYB Essential Defueling Safety Case | Claim 1 Ready | 28-Sep-23 A | 28-Sep-23 | 28-Sep-23 A | 28-Sep-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.5360 | TOR Essential Defueling Safety Case | CLAIM 1 - Sub Critical Margin (SCM) | 28-Sep-23 A | 28-Sep-23 | 28-Sep-23 A | 28-Sep-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.6960 | TOR Essential Defueling Safety Case | Claim 1 Ready | 28-Sep-23 A | 28-Sep-23 | 28-Sep-23 A | 28-Sep-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A2650 | HNB Enhanced Defuelling Safety Cases | >>>OUTGOING ENABLER (W104, W153) Reactor S/D Enhanced INSA Finally Approved | 29-Sep-23 A | 29-Sep-23 | 29-Sep-23 A | 29-Sep-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.25920 | HYB Essential Defueling Safety Case | Supplier Update and Issue Human Reliability Assessment of Unsubstantiated Claims EAN | 29-Sep-23 A | 29-Sep-23 | 06-Oct-23 A | 06-Oct-23 | 5 | 0 | 6 | 100% |  | Completed
ER6372LT | W203 | W203.A3500 | HNB Enhanced Defuelling Safety Cases | INSA Final Approval (KDM) - <Purge and Pressurisation> | 29-Sep-23 A | 29-Sep-23 | 29-Sep-23 A | 29-Sep-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.25920 | TOR Essential Defueling Safety Case | Supplier Update and Issue Human Reliability Assessment of Unsubstantiated Claims EAN | 29-Sep-23 A | 29-Sep-23 | 06-Oct-23 A | 06-Oct-23 | 5 | 0 | 6 | 100% |  | Completed
W232LT | W232 | W232.A2620 | DNB Enhanced Safety Cases | Review Output from the Discovery Milestones | 02-Oct-23 A | 02-Oct-23 | 13-Oct-23 A | 13-Oct-23 | 10 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.A2920 | DNB Enhanced Safety Cases | Discovery Milestone: Core Support Plate Structural Integrity Criticality | 02-Oct-23 A | 02-Oct-23 | 02-Oct-23 A | 02-Oct-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2560 | DNB Enhanced Safety Cases | TOG sentences CSP strategy | 02-Oct-23 A | 02-Oct-23 | 02-Oct-23 A | 02-Oct-23 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A1910 | DNB Enhanced Safety Cases | Post Job Debrief | 04-Oct-23 A | 04-Oct-23 | 04-Oct-23 A | 04-Oct-23 | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.28910 | HYB Essential Defueling Safety Case | Discovery Milestone - Review need for any Post Fault Actions | 05-Oct-23 A | 05-Oct-23 | 05-Oct-23 A | 05-Oct-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.28910 | TOR Essential Defueling Safety Case | Discovery Milestone - Review need for any Post Fault Actions | 05-Oct-23 A | 05-Oct-23 | 05-Oct-23 A | 05-Oct-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2150 | DNB Enhanced Safety Cases | Mod requested, Initiate EC, identify RE, register EC & identify milestones in AMS | 05-Oct-23 A | 05-Oct-23 | 05-Oct-23 A | 05-Oct-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2220 | DNB Enhanced Safety Cases | Raise Engineering Request (as required) | 05-Oct-23 A | 05-Oct-23 | 11-Oct-23 A | 11-Oct-23 | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.A28310 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Fault Definition Document (FDD) EAN to CDMS | 06-Oct-23 A | 06-Oct-23 | 10-Oct-23 A | 10-Oct-23 | 5 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.25930 | HYB Essential Defueling Safety Case | Complete Review of Human Reliability Assessment of Unsubstantiated Claims EAN to CDMS | 06-Oct-23 A | 06-Oct-23 | 06-Oct-23 A | 06-Oct-23 | 5 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.25940 | HYB Essential Defueling Safety Case | Human Reliability Assessment of Unsubstantiated Claims EAN Available | 06-Oct-23 A | 06-Oct-23 | 06-Oct-23 A | 06-Oct-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.25930 | TOR Essential Defueling Safety Case | Complete Review of Human Reliability Assessment of Unsubstantiated Claims EAN to CDMS | 06-Oct-23 A | 06-Oct-23 | 06-Oct-23 A | 06-Oct-23 | 5 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.25940 | TOR Essential Defueling Safety Case | Human Reliability Assessment of Unsubstantiated Claims EAN Available | 06-Oct-23 A | 06-Oct-23 | 06-Oct-23 A | 06-Oct-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A28310 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Fault Definition Document (FDD) EAN to CDMS | 06-Oct-23 A | 06-Oct-23 | 10-Oct-23 A | 10-Oct-23 | 5 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | 1630 | HRA Reactors Shutdown Essential Safety Cases | Upload Fault Definition Document to AMS | 09-Oct-23 A | 09-Oct-23 | 11-Oct-23 A | 11-Oct-23 | 1 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | 1630 | HYA Reactors Shutdown Essential Safety Cases | Upload Fault Definition Document to AMS | 09-Oct-23 A | 09-Oct-23 | 11-Oct-23 A | 11-Oct-23 | 1 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | W222.A25270 | HRA Fuel Handling Essential Safety Case | Reauthor FDD in Report REP (REV 000) & approve on AMS (EVENT RECOVERY 1630) | 09-Oct-23 A | 09-Oct-23 | 11-Oct-23 A | 11-Oct-23 | 1 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | W226.A25270 | HYA Fuel Handling Essential Safety Case | Reauthor FDD in Report REP (REV 000) & approve on AMS (EVENT RECOVERY 1630) | 09-Oct-23 A | 09-Oct-23 | 11-Oct-23 A | 11-Oct-23 | 1 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.A28320 | HYB Essential Defueling Safety Case | Fault Definition Document (FDD) EAN Available | 10-Oct-23 A | 10-Oct-23 | 10-Oct-23 A | 10-Oct-23 | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | 1940 | HRA Reactors Shutdown Essential Safety Cases | Updated All technical references for SC's | 10-Oct-23 A | 10-Oct-23 | 22-Dec-23 A | 22-Dec-23 | 1 | 0 | 53 | 100% |  | Completed
ER6661LT | W206 | 1940 | HYA Reactors Shutdown Essential Safety Cases | Updated All technical references for SC's | 10-Oct-23 A | 10-Oct-23 | 22-Dec-23 A | 22-Dec-23 | 1 | 0 | 53 | 100% |  | Completed
W232LT | W232 | W232.A2430 | DNB Enhanced Safety Cases | CO & CA appointed | 11-Oct-23 A | 11-Oct-23 | 11-Oct-23 A | 11-Oct-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2440 | DNB Enhanced Safety Cases | Key Stakeholders Identified | 11-Oct-23 A | 11-Oct-23 | 11-Oct-23 A | 11-Oct-23 | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.3070 | HRA Fuel Handling Essential Safety Case | FDD Post Job Debrief & Lessons Learnt | 12-Oct-23 A | 12-Oct-23 | 12-Oct-23 A | 12-Oct-23 | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A27465 | HRA Fuel Handling Essential Safety Case | FDD Lessons Learnt Complete | 12-Oct-23 A | 12-Oct-23 | 12-Oct-23 A | 12-Oct-23 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27465 | HYA Fuel Handling Essential Safety Case | FDD Lessons Learnt Complete | 12-Oct-23 A | 12-Oct-23 | 12-Oct-23 A | 12-Oct-23 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.3070 | HYA Fuel Handling Essential Safety Case | FDD Post Job Debrief & Lessons Learnt | 12-Oct-23 A | 12-Oct-23 | 12-Oct-23 A | 12-Oct-23 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2210 | DNB Enhanced Safety Cases | Develop initial programme plan using mandatory template | 12-Oct-23 A | 12-Oct-23 | 18-Oct-23 A | 18-Oct-23 | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A28320 | TOR Essential Defueling Safety Case | Fault Definition Document (FDD) EAN Available | 12-Oct-23 A | 12-Oct-23 | 12-Oct-23 A | 12-Oct-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3440 | HNB Enhanced Defuelling Safety Cases | Station approval for mod implementation (including station review meeting) | 13-Oct-23 A | 13-Oct-23 | 13-Oct-23 A | 13-Oct-23 | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A3580 | HNB Enhanced Defuelling Safety Cases | Station Approval Obtained and CAT 2 Safety Case Complete *(KDM)* (FEEDS TO SUMMARY SCHEDULE) | 13-Oct-23 A | 13-Oct-23 | 13-Oct-23 A | 13-Oct-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1980 | DNB Enhanced Safety Cases | Produce Draft NSRS (using BARRIER MODEL) | 16-Oct-23 A | 16-Oct-23 | 07-Dec-23 A | 07-Dec-23 | 39 | 0 | 38 | 100% |  | Completed
ER6668LT | W213 | W213.7270 | TOR Essential Defueling Safety Case | Case Officer Tech Lead Review Claim 4 | 16-Oct-23 A | 16-Oct-23 | 19-Oct-23 A | 19-Oct-23 | 5 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.7270 | HYB Essential Defueling Safety Case | Case Officer Tech Lead Review Claim 4 | 16-Oct-23 A | 16-Oct-23 | 19-Oct-23 A | 19-Oct-23 | 5 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.7980 | HYB Essential Defueling Safety Case | Verify Human Factors Integration Plan EAN and Issue for Technical Review (REV 001) | 16-Oct-23 A | 16-Oct-23 | 06-Nov-23 A | 06-Nov-23 | 12 | 0 | 16 | 100% |  | Completed
W232LT | W232 | W232.A2630 | DNB Enhanced Safety Cases | Prepare Decision Paper | 16-Oct-23 A | 16-Oct-23 | 27-Oct-23 A | 27-Oct-23 | 10 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.7980 | TOR Essential Defueling Safety Case | Verify Human Factors Integration Plan EAN and Issue for Technical Review (REV 001) | 16-Oct-23 A | 16-Oct-23 | 06-Nov-23 A | 06-Nov-23 | 12 | 0 | 16 | 100% |  | Completed
W232LT | W232 | W232.A2450 | DNB Enhanced Safety Cases | CA PJB Held | 18-Oct-23 A | 18-Oct-23 | 18-Oct-23 A | 18-Oct-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A4980 | DNB Enhanced Safety Cases | Discovery Milestone: Cat 2 Case Feasible- go/no go | 18-Oct-23 A | 18-Oct-23 | 18-Oct-23 A | 18-Oct-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B6760 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Re-entrant Seal Stiction - Summary | 19-Oct-23 A | 19-Oct-23 | 19-Oct-23 A | 19-Oct-23 | 14 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6770 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Re-entrant Seal Stiction - Approve Task Sheet | 19-Oct-23 A | 19-Oct-23 | 19-Oct-23 A | 19-Oct-23 | 2 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B6790 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Re-entrant Seal Stiction - Draft and issue Task Sheet | 19-Oct-23 A | 19-Oct-23 | 19-Oct-23 A | 19-Oct-23 | 10 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1970 | DNB Enhanced Safety Cases | Produce MF (as required) | 19-Oct-23 A | 19-Oct-23 | 25-Oct-23 A | 25-Oct-23 | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.B6750 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Re-entrant Seal Stiction - Summary | 19-Oct-23 A | 19-Oct-23 | 19-Oct-23 A | 19-Oct-23 | 22 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6780 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Re-entrant Seal Stiction - Pre Job Brief | 19-Oct-23 A | 19-Oct-23 | 19-Oct-23 A | 19-Oct-23 | 2 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6800 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Re-entrant Seal Stiction - Prepare Draft EAN | 19-Oct-23 A | 19-Oct-23 | 19-Oct-23 A | 19-Oct-23 | 20 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6820 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727>Re-entrant Seal Stiction - Draft EAN Reviewed by EDF SQEP | 19-Oct-23 A | 19-Oct-23 | 19-Oct-23 A | 19-Oct-23 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6830 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727>Re-entrant Seal Stiction - Address Comments from EDF Review on Draft EAN | 19-Oct-23 A | 19-Oct-23 | 19-Oct-23 A | 19-Oct-23 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6850 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727>Re-entrant Seal Stiction - EAN Completed and Uploaded to CDMS | 19-Oct-23 A | 19-Oct-23 | 19-Oct-23 A | 19-Oct-23 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6870 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727>Re-entrant Seal Stiction - TSA Internal Review of Draft EAN | 19-Oct-23 A | 19-Oct-23 | 19-Oct-23 A | 19-Oct-23 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6810 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727>Re-entrant Seal Stiction - Issue Draft EAN to EDF for Review. | 19-Oct-23 A | 19-Oct-23 | 19-Oct-23 A | 19-Oct-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B6840 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727>Re-entrant Seal Stiction - Issue Final EAN | 19-Oct-23 A | 19-Oct-23 | 19-Oct-23 A | 19-Oct-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B6860 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727>Re-entrant Seal Stiction - EAN Completed (FEED TOS UMMARY SCHEDULE) | 19-Oct-23 A | 19-Oct-23 | 19-Oct-23 A | 19-Oct-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2940 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727>Discovery Milestone: Re-entrant Seal Stiction | 19-Oct-23 A | 19-Oct-23 | 19-Oct-23 A | 19-Oct-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7280 | HYB Essential Defueling Safety Case | Verification of Claim 4 | 20-Oct-23 A | 20-Oct-23 | 01-Dec-23 A | 01-Dec-23 | 5 | 0 | 31 | 100% |  | Completed
ER6666LT | W209 | W209.7290 | HYB Essential Defueling Safety Case | Update Claim 4 | 20-Oct-23 A | 20-Oct-23 | 20-Dec-23 A | 20-Dec-23 | 8 | 0 | 43 | 100% |  | Completed
ER6668LT | W213 | W213.7280 | TOR Essential Defueling Safety Case | Verification of Claim 4 | 20-Oct-23 A | 20-Oct-23 | 01-Dec-23 A | 01-Dec-23 | 10 | 0 | 31 | 100% |  | Completed
ER6668LT | W213 | W213.7290 | TOR Essential Defueling Safety Case | Update Claim 4 | 20-Oct-23 A | 20-Oct-23 | 20-Dec-23 A | 20-Dec-23 | 4 | 0 | 43 | 100% |  | Completed
ER6650LT | W226 | 001955d | HYA Fuel Handling Essential Safety Case | Claim 2 Updates - H&I PSA Worker Risk | 20-Oct-23 A | 20-Oct-23 | 16-Nov-23 A | 16-Nov-23 | 4 | 0 | 20 | 100% |  | Completed
ER6668LT | W213 | W213.29160 | TOR Essential Defueling Safety Case | Technical Review | 23-Oct-23 A | 23-Oct-23 | 27-Nov-23 A | 27-Nov-23 | 10 | 0 | 25 | 100% |  | Completed
ER6666LT | W209 | W209.29160 | HYB Essential Defueling Safety Case | Technical Review | 23-Oct-23 A | 23-Oct-23 | 27-Nov-23 A | 27-Nov-23 | 7 | 0 | 26 | 100% |  | Completed
W232LT | W232 | W232.A4950 | DNB Enhanced Safety Cases | Lessons Learned Workshop 1 - TOG Learning | 25-Oct-23 A | 25-Oct-23 | 25-Oct-23 A | 25-Oct-23 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2160 | DNB Enhanced Safety Cases | Issue MF (as required) | 25-Oct-23 A | 25-Oct-23 | 25-Oct-23 A | 25-Oct-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2270 | DNB Enhanced Safety Cases | Categorisation by RE / Station | 26-Oct-23 A | 26-Oct-23 | 01-Nov-23 A | 01-Nov-23 | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.A2300 | DNB Enhanced Safety Cases | Identify verifier for the case & establish all other resources | 26-Oct-23 A | 26-Oct-23 | 01-Nov-23 A | 01-Nov-23 | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | 001955e | HYA Fuel Handling Essential Safety Case | Claim 4 Updates - Refuelling Cooling | 26-Oct-23 A | 26-Oct-23 | 16-Nov-23 A | 16-Nov-23 | 4 | 0 | 15 | 100% |  | Completed
ER6666LT | W209 | W209.5370 | HYB Essential Defueling Safety Case | CLAIM 2 - Shutdown and Fuel Handling Cooling | 27-Oct-23 A | 27-Oct-23 | 27-Oct-23 A | 27-Oct-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.5370 | TOR Essential Defueling Safety Case | CLAIM 2 - Shutdown and Fuel Handling Cooling | 27-Oct-23 A | 27-Oct-23 | 27-Oct-23 A | 27-Oct-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.7050 | TOR Essential Defueling Safety Case | Claim 2 Ready | 27-Oct-23 A | 27-Oct-23 | 27-Oct-23 A | 27-Oct-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3560 | HNB Enhanced Defuelling Safety Cases | Post Job Debrief | 27-Oct-23 A | 27-Oct-23 | 27-Oct-23 A | 27-Oct-23 | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 001955f | HYA Fuel Handling Essential Safety Case | Claim 3 - No updates Required | 27-Oct-23 A | 27-Oct-23 | 27-Oct-23 A | 27-Oct-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7050 | HYB Essential Defueling Safety Case | Claim 2 Ready | 27-Oct-23 A | 27-Oct-23 | 27-Oct-23 A | 27-Oct-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.7720 | TOR Essential Defueling Safety Case | INSA Pre Review Claim 2 | 30-Oct-23 A | 30-Oct-23 | 21-Dec-23 A | 21-Dec-23 | 20 | 0 | 38 | 100% |  | Completed
ER6666LT | W209 | W209.7720 | HYB Essential Defueling Safety Case | Early INA Review Claim 2 | 30-Oct-23 A | 30-Oct-23 | 21-Dec-23 A | 21-Dec-23 | 20 | 0 | 38 | 100% |  | Completed
W232LT | W232 | W232.A2640 | DNB Enhanced Safety Cases | Obtain Agreement from Programme Board | 30-Oct-23 A | 30-Oct-23 | 14-Dec-23 A | 14-Dec-23 | 10 | 0 | 34 | 100% |  | Completed
ER6371LT | W202 | W202.B5540 | HRA Reactors Shutdown Essential Safety Cases | Reactor Case INSA held for FH Case INSA | 31-Oct-23 A | 31-Oct-23 | 31-Oct-23 A | 31-Oct-23 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.B5540 | HYA Reactors Shutdown Essential Safety Cases | Reactor Case INSA held for FH Case INSA | 31-Oct-23 A | 31-Oct-23 | 31-Oct-23 A | 31-Oct-23 | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A25660 | HRA Fuel Handling Essential Safety Case | Worker Risk Assessment Updates (REV 001) (EVENT RECOVERY 2000f) | 01-Nov-23 A | 01-Nov-23 | 02-Nov-23 A | 02-Nov-23 | 22 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A25660 | HYA Fuel Handling Essential Safety Case | Worker Risk Assessment Updates (REV 001) (EVENT RECOVERY 2000f) | 01-Nov-23 A | 01-Nov-23 | 02-Nov-23 A | 02-Nov-23 | 2 | 0 | 2 | 100% |  | Completed
W232LT | W232 | W232.A2170 | DNB Enhanced Safety Cases | INSA agree MF (as required) *(KDM)* | 02-Nov-23 A | 02-Nov-23 | 03-Nov-23 A | 03-Nov-23 | 2 | 0 | 2 | 100% |  | Completed
W232LT | W232 | W232.A2400 | DNB Enhanced Safety Cases | INSA Approval Date Identified | 03-Nov-23 A | 03-Nov-23 | 03-Nov-23 A | 03-Nov-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2410 | DNB Enhanced Safety Cases | Provide Provisional NSC Date (as required) | 03-Nov-23 A | 03-Nov-23 | 03-Nov-23 A | 03-Nov-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3860 | HNB Enhanced Defuelling Safety Cases | Incorporate INA, Station, ED (peer) comments | 06-Nov-23 A | 06-Nov-23 | 10-Nov-23 A | 10-Nov-23 | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.28840 | HYB Essential Defueling Safety Case | Technical Review of Human Factors Integration Plan EAN (REV 001) | 07-Nov-23 A | 07-Nov-23 | 17-Jan-24 A | 17-Jan-24 | 10 | 0 | 49 | 100% |  | Completed
ER6668LT | W213 | W213.28840 | TOR Essential Defueling Safety Case | Technical Review of Human Factors Integration Plan EAN (REV 001) | 07-Nov-23 A | 07-Nov-23 | 17-Jan-24 A | 17-Jan-24 | 10 | 0 | 49 | 100% |  | Completed
ER6650LT | W226 | 001955c | HYA Fuel Handling Essential Safety Case | Claim 1 Updates - Defuelling Process Specification | 08-Nov-23 A | 08-Nov-23 | 16-Nov-23 A | 16-Nov-23 | 3 | 0 | 6 | 100% |  | Completed
ER6372LT | W203 | W203.B1050 | HNB Enhanced Defuelling Safety Cases | BE Technical review of supporting reference <PSA Updates> | 09-Nov-23 A | 09-Nov-23 | 14-Nov-23 A | 14-Nov-23 | 4 | 0 | 4 | 100% |  | Completed
ER6666LT | W209 | W209.5410 | HYB Essential Defueling Safety Case | CLAIM 6 - Configuration Control | 10-Nov-23 A | 10-Nov-23 | 10-Nov-23 A | 10-Nov-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7410 | HYB Essential Defueling Safety Case | Claim 6 Ready | 10-Nov-23 A | 10-Nov-23 | 10-Nov-23 A | 10-Nov-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7760 | HYB Essential Defueling Safety Case | Early INA Review Claim 6 | 10-Nov-23 A | 10-Nov-23 | 10-Nov-23 A | 10-Nov-23 | 20 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.5410 | TOR Essential Defueling Safety Case | CLAIM 6 - Configuration Control | 10-Nov-23 A | 10-Nov-23 | 10-Nov-23 A | 10-Nov-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.7760 | TOR Essential Defueling Safety Case | INSA Pre Review Claim 6 | 10-Nov-23 A | 10-Nov-23 | 10-Nov-23 A | 10-Nov-23 | 20 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3700 | HNB Enhanced Defuelling Safety Cases | Issue final NSRS | 10-Nov-23 A | 10-Nov-23 | 10-Nov-23 A | 10-Nov-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.7410 | TOR Essential Defueling Safety Case | Claim 6 Ready | 10-Nov-23 A | 10-Nov-23 | 10-Nov-23 A | 10-Nov-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.5380 | HYB Essential Defueling Safety Case | CLAIM 3 - Containment and Structural Integrity | 13-Nov-23 A | 13-Nov-23 | 13-Nov-23 A | 13-Nov-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7140 | HYB Essential Defueling Safety Case | Claim 3 Ready | 13-Nov-23 A | 13-Nov-23 | 13-Nov-23 A | 13-Nov-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A4170 | HNB Enhanced Defuelling Safety Cases | NSRS approved - IFD Deluge | 13-Nov-23 A | 13-Nov-23 | 13-Nov-23 A | 13-Nov-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.5380 | TOR Essential Defueling Safety Case | CLAIM 3 - Containment and Structural Integrity | 13-Nov-23 A | 13-Nov-23 | 13-Nov-23 A | 13-Nov-23 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 001955g | HYA Fuel Handling Essential Safety Case | Head Document Formatting Checks | 13-Nov-23 A | 13-Nov-23 | 21-Nov-23 A | 21-Nov-23 | 2 | 0 | 7 | 100% |  | Completed
ER6372LT | W203 | W203.A3710 | HNB Enhanced Defuelling Safety Cases | Station agree NSRS (KDM) - <IFD Deluge> | 13-Nov-23 A | 13-Nov-23 | 13-Nov-23 A | 13-Nov-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3880 | HNB Enhanced Defuelling Safety Cases | Key Stakeholders (DA) agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 13-Nov-23 A | 13-Nov-23 | 13-Nov-23 A | 13-Nov-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A4030 | HNB Enhanced Defuelling Safety Cases | INA agree NSRS | 13-Nov-23 A | 13-Nov-23 | 13-Nov-23 A | 13-Nov-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.7140 | TOR Essential Defueling Safety Case | Claim 3 Ready | 13-Nov-23 A | 13-Nov-23 | 13-Nov-23 A | 13-Nov-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7730 | HYB Essential Defueling Safety Case | Early INA Review Claim 3 | 14-Nov-23 A | 14-Nov-23 | 24-Jan-24 A | 24-Jan-24 | 20 | 0 | 48 | 100% |  | Completed
ER6372LT | W203 | W203.A4180 | HNB Enhanced Defuelling Safety Cases | All key supporting technical references complete <RESUMED 01.03.2023> - IFD Deluge | 14-Nov-23 A | 14-Nov-23 | 14-Nov-23 A | 14-Nov-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3740 | HNB Enhanced Defuelling Safety Cases | Consolidate & issue to stakeholders & suppliers agreed NSRS | 14-Nov-23 A | 14-Nov-23 | 14-Nov-23 A | 14-Nov-23 | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.7730 | TOR Essential Defueling Safety Case | Early INA Review Claim 3 | 14-Nov-23 A | 14-Nov-23 | 24-Jan-24 A | 24-Jan-24 | 20 | 0 | 49 | 100% |  | Completed
ER6372LT | W203 | W203.A4150 | HNB Enhanced Defuelling Safety Cases | All supporting references completed | 14-Nov-23 A | 14-Nov-23 | 14-Nov-23 A | 14-Nov-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.B1040 | HNB Enhanced Defuelling Safety Cases | Supporting reference <PSA Updates> approved | 14-Nov-23 A | 14-Nov-23 | 14-Nov-23 A | 14-Nov-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3750 | HNB Enhanced Defuelling Safety Cases | CA to agree with CO format of the safety case & produce agreed contents page | 15-Nov-23 A | 15-Nov-23 | 16-Nov-23 A | 16-Nov-23 | 2 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.A29080 | HYB Essential Defueling Safety Case | Verify Defuelling Handling Deterministic Assessment EAN & Issue for Technical Review | 17-Nov-23 A | 17-Nov-23 | 19-Jan-24 A | 19-Jan-24 | 5 | 0 | 43 | 100% |  | Completed
ER6668LT | W213 | W213.A29080 | TOR Essential Defueling Safety Case | Verify Defuelling Handling Deterministic Assessment EAN & Issue for Technical Review | 17-Nov-23 A | 17-Nov-23 | 19-Jan-24 A | 19-Jan-24 | 5 | 0 | 43 | 100% |  | Completed
ER6372LT | W203 | W203.A3780 | HNB Enhanced Defuelling Safety Cases | Produce verification plan | 17-Nov-23 A | 17-Nov-23 | 20-Nov-23 A | 20-Nov-23 | 2 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | 1956 | HYA Fuel Handling Essential Safety Case | Verification Pre Job Brief (Head Document) | 20-Nov-23 A | 20-Nov-23 | 20-Nov-23 A | 20-Nov-23 | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A3790 | HNB Enhanced Defuelling Safety Cases | Verification of the case (using BARRIER MODEL) | 21-Nov-23 A | 21-Nov-23 | 04-Dec-23 A | 04-Dec-23 | 10 | 0 | 10 | 100% |  | Completed
ER6372LT | W203 | W203.A4080 | HNB Enhanced Defuelling Safety Cases | Specialist Assessment | 21-Nov-23 A | 21-Nov-23 | 04-Dec-23 A | 04-Dec-23 | 10 | 0 | 10 | 100% |  | Completed
ER6378LT | W222 | 001962a | HRA Fuel Handling Essential Safety Case | Station RE Verification | 22-Nov-23 A | 22-Nov-23 | 28-Dec-23 A | 28-Dec-23 | 13 | 0 | 24 | 100% |  | Completed
ER6378LT | W222 | 1963 | HRA Fuel Handling Essential Safety Case | Sub Verifiers First Round Comments | 22-Nov-23 A | 22-Nov-23 | 20-Dec-23 A | 20-Dec-23 | 13 | 0 | 21 | 100% |  | Completed
ER6378LT | W222 | 1962 | HRA Fuel Handling Essential Safety Case | Station RE Verification | 22-Nov-23 A | 22-Nov-23 | 27-Nov-23 A | 27-Nov-23 | 13 | 0 | 4 | 100% |  | Completed
ER6378LT | W222 | 1961 | HRA Fuel Handling Essential Safety Case | Lead Verifier and Detail checkers first Round comments | 22-Nov-23 A | 22-Nov-23 | 17-Dec-23 A | 17-Dec-23 | 13 | 0 | 25 | 100% |  | Completed
ER6378LT | W222 | 1960 | HRA Fuel Handling Essential Safety Case | Verification of Head Document | 22-Nov-23 A | 22-Nov-23 | 21-Mar-24 A | 21-Mar-24 | 25 | 0 | 80 | 100% |  | Completed
ER6650LT | W226 | 001962a | HYA Fuel Handling Essential Safety Case | Station RE Verification Grant | 22-Nov-23 A | 22-Nov-23 | 28-Dec-23 A | 28-Dec-23 | 13 | 0 | 24 | 100% |  | Completed
ER6650LT | W226 | 1963 | HYA Fuel Handling Essential Safety Case | Sub Verifiers First Round Comments Grant | 22-Nov-23 A | 22-Nov-23 | 20-Dec-23 A | 20-Dec-23 | 13 | 0 | 21 | 100% |  | Completed
ER6650LT | W226 | 1962 | HYA Fuel Handling Essential Safety Case | Station RE Verification Grant | 22-Nov-23 A | 22-Nov-23 | 27-Nov-23 A | 27-Nov-23 | 13 | 0 | 4 | 100% |  | Completed
ER6650LT | W226 | 1961 | HYA Fuel Handling Essential Safety Case | Lead Verifier and Detail checkers first Round comments Grant | 22-Nov-23 A | 22-Nov-23 | 17-Dec-23 A | 17-Dec-23 | 13 | 0 | 25 | 100% |  | Completed
ER6650LT | W226 | 001955h | HYA Fuel Handling Essential Safety Case | Cross Referencing Checks | 22-Nov-23 A | 22-Nov-23 | 22-Nov-23 A | 22-Nov-23 | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 1960 | HYA Fuel Handling Essential Safety Case | Verification of Head Document Grant | 22-Nov-23 A | 22-Nov-23 | 22-Feb-24 A | 22-Feb-24 | 25 | 0 | 60 | 100% |  | Completed
ER6668LT | W213 | W213.29170 | TOR Essential Defueling Safety Case | Upload to CDMS | 28-Nov-23 A | 28-Nov-23 | 22-Dec-23 A | 22-Dec-23 | 12 | 0 | 18 | 100% |  | Completed
ER6666LT | W209 | W209.29170 | HYB Essential Defueling Safety Case | Upload to CDMS | 28-Nov-23 A | 28-Nov-23 | 22-Dec-23 A | 22-Dec-23 | 5 | 0 | 19 | 100% |  | Completed
W520LT | W520 | W520.A1260 | FLEETWIDE CTO Defueling Safety Case Delivery | ETC (DD-PF) 2023 | 01-Dec-23 A | 01-Dec-23 | 22-Dec-23 A | 22-Dec-23 | 16 | 0 | 15 | 100% |  | Completed
ER6666LT | W209 | W209.7450 | HYB Essential Defueling Safety Case | Case Officer Tech Lead Review Claim 7 | 01-Dec-23 A | 01-Dec-23 | 17-Jan-24 A | 17-Jan-24 | 5 | 0 | 31 | 100% |  | Completed
ER6668LT | W213 | W213.7450 | TOR Essential Defueling Safety Case | Case Officer Tech Lead Review Claim 7 | 01-Dec-23 A | 01-Dec-23 | 17-Jan-24 A | 17-Jan-24 | 5 | 0 | 31 | 100% |  | Completed
ER6372LT | W203 | W203.A3800 | HNB Enhanced Defuelling Safety Cases | Produce verification file | 05-Dec-23 A | 05-Dec-23 | 06-Dec-23 A | 06-Dec-23 | 2 | 0 | 2 | 100% |  | Completed
ER6372LT | W203 | W203.A3970 | HNB Enhanced Defuelling Safety Cases | Issue to CO & Station for comments | 06-Dec-23 A | 06-Dec-23 | 06-Dec-23 A | 06-Dec-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3770 | HNB Enhanced Defuelling Safety Cases | Incorporate CO & Station comments | 07-Dec-23 A | 07-Dec-23 | 11-Dec-23 A | 11-Dec-23 | 4 | 0 | 2 | 100% |  | Completed
ER6372LT | W203 | W203.A3940 | HNB Enhanced Defuelling Safety Cases | Key Stakeholders Approval, if requested | 07-Dec-23 A | 07-Dec-23 | 11-Dec-23 A | 11-Dec-23 | 5 | 0 | 2 | 100% |  | Completed
W232LT | W232 | W232.A2980 | DNB Enhanced Safety Cases | Produce Draft NSRS Complete | 07-Dec-23 A | 07-Dec-23 | 07-Dec-23 A | 07-Dec-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3810 | HNB Enhanced Defuelling Safety Cases | Issue high quality verified draft issue A with verification file to INSA & station (KDM) - <IFD Deluge> | 11-Dec-23 A | 11-Dec-23 | 11-Dec-23 A | 11-Dec-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3920 | HNB Enhanced Defuelling Safety Cases | Verification complete | 11-Dec-23 A | 11-Dec-23 | 11-Dec-23 A | 11-Dec-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3930 | HNB Enhanced Defuelling Safety Cases | Submit for approval - Categoriser ratifies; RE/CO endorsement | 11-Dec-23 A | 11-Dec-23 | 11-Dec-23 A | 11-Dec-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.29190 | HYB Essential Defueling Safety Case | Include verified defuelling fault schedule from Task 2 to complete defuelling SSR | 11-Dec-23 A | 11-Dec-23 | 11-Dec-23 A | 11-Dec-23 | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.29190 | TOR Essential Defueling Safety Case | Include verified defuelling fault schedule from Task 2 to complete defuelling SSR | 11-Dec-23 A | 11-Dec-23 | 11-Dec-23 A | 11-Dec-23 | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.1425 | HYB Essential Defueling Safety Case | Produce verification plan | 12-Dec-23 A | 12-Dec-23 | 12-Dec-23 A | 12-Dec-23 | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.29210 | HYB Essential Defueling Safety Case | Verification/TR/specialist assessment (station review) of SSR text only as fault schedule already QA2 | 12-Dec-23 A | 12-Dec-23 | 31-Jan-24 A | 31-Jan-24 | 6 | 0 | 33 | 100% |  | Completed
ER6372LT | W203 | W203.A3820 | HNB Enhanced Defuelling Safety Cases | INSA review & iteration of comments (using BARRIER MODEL) | 12-Dec-23 A | 12-Dec-23 | 15-Dec-23 A | 15-Dec-23 | 10 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.1425 | TOR Essential Defueling Safety Case | Produce verification plan | 12-Dec-23 A | 12-Dec-23 | 12-Dec-23 A | 12-Dec-23 | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.29210 | TOR Essential Defueling Safety Case | Verification/TR/specialist assessment (station review) of SSR text only as fault schedule already QA2 | 12-Dec-23 A | 12-Dec-23 | 31-Jan-24 A | 31-Jan-24 | 6 | 0 | 33 | 100% |  | Completed
ER6666LT | W209 | W209.29200 | HYB Essential Defueling Safety Case | Draft SSR Ready for review and uploaded to ADL alongside Cat 1 Ready to Review | 12-Dec-23 A | 12-Dec-23 | 31-Jan-24 A | 31-Jan-24 | 1 | 0 | 33 | 100% |  | Completed
ER6668LT | W213 | W213.29200 | TOR Essential Defueling Safety Case | Draft SSR Ready for review and uploaded to ADL alongside Cat 1 Ready to Review | 12-Dec-23 A | 12-Dec-23 | 31-Jan-24 A | 31-Jan-24 | 1 | 0 | 33 | 100% |  | Completed
ER6372LT | W203 | W203.1010 | HNB Enhanced Defuelling Safety Cases | Purge and Pressurisation - Lessons Learnt Review Complete | 14-Dec-23 A | 14-Dec-23 | 14-Dec-23 A | 14-Dec-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7230 | HYB Essential Defueling Safety Case | Claim 5 Ready | 15-Dec-23 A | 15-Dec-23 | 15-Dec-23 A | 15-Dec-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.7230 | TOR Essential Defueling Safety Case | Claim 5 Ready | 15-Dec-23 A | 15-Dec-23 | 15-Dec-23 A | 15-Dec-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2650 | DNB Enhanced Safety Cases | Obtain Agreement from Executive (FEED TO SUMMARY SCHEDULE) | 15-Dec-23 A | 15-Dec-23 | 21-Dec-23 A | 21-Dec-23 | 5 | 0 | 5 | 100% |  | Completed
ER6372LT | W203 | W203.A3980 | HNB Enhanced Defuelling Safety Cases | Incorporate INSA comments | 16-Dec-23 A | 16-Dec-23 | 19-Dec-23 A | 19-Dec-23 | 10 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A29090 | HYB Essential Defueling Safety Case | Technical Review of Defuelling Handling Deterministic Assessment EAN | 18-Dec-23 A | 18-Dec-23 | 24-Jan-24 A | 24-Jan-24 | 5 | 0 | 24 | 100% |  | Completed
ER6668LT | W213 | W213.A29090 | TOR Essential Defueling Safety Case | Technical Review of Defuelling Handling Deterministic Assessment EAN | 18-Dec-23 A | 18-Dec-23 | 24-Jan-24 A | 24-Jan-24 | 5 | 0 | 25 | 100% |  | Completed
ER6378LT | W222 | 001964a | HRA Fuel Handling Essential Safety Case | Repsond to First Round Comments | 18-Dec-23 A | 18-Dec-23 | 08-Feb-24 A | 08-Feb-24 | 14 | 0 | 35 | 100% |  | Completed
ER6378LT | W222 | 1964 | HRA Fuel Handling Essential Safety Case | Respond to First Round comments (Claim 5 Re-write & Peer Review) | 18-Dec-23 A | 18-Dec-23 | 08-Feb-24 A | 08-Feb-24 | 14 | 0 | 32 | 100% |  | Completed
ER6650LT | W226 | 001964a | HYA Fuel Handling Essential Safety Case | Repsond to First Round Comments | 18-Dec-23 A | 18-Dec-23 | 08-Feb-24 A | 08-Feb-24 | 14 | 0 | 35 | 100% |  | Completed
ER6650LT | W226 | 1964 | HYA Fuel Handling Essential Safety Case | Respond to First Round comments (Claim 5 Re-write & Peer Review) Grant | 18-Dec-23 A | 18-Dec-23 | 31-Jan-24 A | 31-Jan-24 | 14 | 0 | 26 | 100% |  | Completed
ER6666LT | W209 | W209.5400 | HYB Essential Defueling Safety Case | CLAIM 4 - Dropped Fuel Plug Assemblies | 20-Dec-23 A | 20-Dec-23 | 20-Dec-23 A | 20-Dec-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7320 | HYB Essential Defueling Safety Case | Claim 4 Ready | 20-Dec-23 A | 20-Dec-23 | 20-Dec-23 A | 20-Dec-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.5400 | TOR Essential Defueling Safety Case | CLAIM 4 - Dropped Fuel Plug Assemblies | 20-Dec-23 A | 20-Dec-23 | 20-Dec-23 A | 20-Dec-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.7320 | TOR Essential Defueling Safety Case | Claim 4 Ready | 20-Dec-23 A | 20-Dec-23 | 20-Dec-23 A | 20-Dec-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1990 | DNB Enhanced Safety Cases | Station comments on NSRS | 20-Dec-23 A | 20-Dec-23 | 19-Jan-24 A | 19-Jan-24 | 8 | 0 | 19 | 100% |  | Completed
W232LT | W232 | W232.A2000 | DNB Enhanced Safety Cases | Key Stakeholders (Peer) comments on NSRS (as required) | 20-Dec-23 A | 20-Dec-23 | 19-Jan-24 A | 19-Jan-24 | 8 | 0 | 19 | 100% |  | Completed
ER6372LT | W203 | W203.A3950 | HNB Enhanced Defuelling Safety Cases | Station approval for mod implementation (including station review meeting) | 21-Dec-23 A | 21-Dec-23 | 21-Dec-23 A | 21-Dec-23 | 1 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A4010 | HNB Enhanced Defuelling Safety Cases | INSA Final Approval (KDM) - <IFD Deluge> | 21-Dec-23 A | 21-Dec-23 | 21-Dec-23 A | 21-Dec-23 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A4090 | HNB Enhanced Defuelling Safety Cases | Station Approval Obtained and CAT 2 Safety Case Complete *(KDM)* (FEEDS TO SUMMARY SCHEDULE) - <IFD Deluge> | 21-Dec-23 A | 21-Dec-23 | 21-Dec-23 A | 21-Dec-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1465 | HYB Essential Defueling Safety Case | Cost Summary for Veriification - (Cost Summary) ## | 22-Dec-23 A | 22-Dec-23 | 31-May-24 A | 31-May-24 | 95 | 0 | 108 | 100% |  | Completed
ER6666LT | W209 | W209.5390 | HYB Essential Defueling Safety Case | CLAIM 5 - Faults | 22-Dec-23 A | 22-Dec-23 | 22-Dec-23 A | 22-Dec-23 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.8700 | HYB Essential Defueling Safety Case | Claims Integration | 22-Dec-23 A | 22-Dec-23 | 31-Jan-24 A | 31-Jan-24 | 5 | 0 | 26 | 100% |  | Completed
ER6668LT | W213 | W213.1465 | TOR Essential Defueling Safety Case | Cost Summary for Veriification - (Cost Summary) ## | 22-Dec-23 A | 22-Dec-23 | 31-May-24 A | 31-May-24 | 93 | 0 | 108 | 100% |  | Completed
ER6668LT | W213 | W213.5390 | TOR Essential Defueling Safety Case | CLAIM 5 - Faults | 22-Dec-23 A | 22-Dec-23 | 22-Dec-23 A | 22-Dec-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.8700 | TOR Essential Defueling Safety Case | Claims Integration | 22-Dec-23 A | 22-Dec-23 | 31-Jan-24 A | 31-Jan-24 | 5 | 0 | 25 | 100% |  | Completed
ER6378LT | W222 | W222.A27445 | HRA Fuel Handling Essential Safety Case | All Technical References (EVENT RECOVERY) Complete | 22-Dec-23 A | 22-Dec-23 | 22-Dec-23 A | 22-Dec-23 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27445 | HYA Fuel Handling Essential Safety Case | All Technical References (EVENT RECOVERY) Complete | 22-Dec-23 A | 22-Dec-23 | 22-Dec-23 A | 22-Dec-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2950 | DNB Enhanced Safety Cases | Decision Milestone - Cold Defuelling Feasibility and Benefits | 22-Dec-23 A | 22-Dec-23 | 22-Dec-23 A | 22-Dec-23 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A4970 | DNB Enhanced Safety Cases | >>>OUTGOING ENABLER Decision Milestone - Cold Defuelling Feasibility and Benefits | 22-Dec-23 A | 22-Dec-23 | 22-Dec-23 A | 22-Dec-23 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A27420 | TOR Essential Defueling Safety Case | Supplier Update and Issue Fuel Route PSA Update EAN | 27-Dec-23 A | 27-Dec-23 | 12-Jan-24 A | 12-Jan-24 | 5 | 0 | 12 | 100% |  | Completed
ER6666LT | W209 | W209.A27420 | HYB Essential Defueling Safety Case | Supplier Update and Issue Fuel Route PSA Update EAN | 27-Dec-23 A | 27-Dec-23 | 12-Jan-24 A | 12-Jan-24 | 10 | 0 | 12 | 100% |  | Completed
ER6666LT | W209 | W209.A30020 | HYB Essential Defueling Safety Case | Compliance Arrangement Review EAN - Scope No Longer Required ## (Cost Summary) (Claim 6) | 02-Jan-24 A | 02-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 71 | 0 | 21 | 100% |  | Completed
ER6666LT | W209 | W209.A30030 | HYB Essential Defueling Safety Case | HOLDING LINE - Compliance Arrangement Review EAN - Scope No Longer Required | 02-Jan-24 A | 02-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 71 | 0 | 21 | 100% |  | Completed
ER6666LT | W209 | W209.A30110 | HYB Essential Defueling Safety Case | HOLDING LINE - Substantiate Station Comply with New Controls - Scope No Longer Required | 02-Jan-24 A | 02-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 71 | 0 | 21 | 100% |  | Completed
ER6666LT | W209 | W209.A30100 | HYB Essential Defueling Safety Case | Substantiate Station Comply with New Controls - Scope No Longer Required ## (Cost Summary) (Claim 6) | 02-Jan-24 A | 02-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 71 | 0 | 21 | 100% |  | Completed
ER6666LT | W209 | W209.A30880 | HYB Essential Defueling Safety Case | Plant Area Review in Support of Argument 6.1 EAN - Scope No Longer Required ## (Cost Summary) (Claim 6) | 02-Jan-24 A | 02-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 24 | 0 | 21 | 100% |  | Completed
ER6666LT | W209 | W209.A30890 | HYB Essential Defueling Safety Case | HOLDING LINE - Plant Area Review in Support of Argument 6.1 EAN - Scope No Longer Required | 02-Jan-24 A | 02-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 24 | 0 | 21 | 100% |  | Completed
W232LT | W232 | W232.A2890 | DNB Enhanced Safety Cases | <TRANSFER SCOPE TO W699 CN 1727> Cat 2 EC for Cold Extraction (if required) | 02-Jan-24 A | 02-Jan-24 | 01-Feb-24 A | 01-Feb-24 | 62 | 0 | 22 | 100% |  | Completed
ER6668LT | W213 | W213.A30020 | TOR Essential Defueling Safety Case | Compliance Arrangement Review EAN - Scope No Longer Required ## (Cost Summary) (Claim 6) | 02-Jan-24 A | 02-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 71 | 0 | 21 | 100% |  | Completed
ER6668LT | W213 | W213.A30030 | TOR Essential Defueling Safety Case | HOLDING LINE - Compliance Arrangement Review EAN - Scope No Longer Required | 02-Jan-24 A | 02-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 71 | 0 | 21 | 100% |  | Completed
ER6668LT | W213 | W213.A30110 | TOR Essential Defueling Safety Case | HOLDING LINE - Substantiate Station Comply with New Controls - Scope No Longer Required | 02-Jan-24 A | 02-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 71 | 0 | 21 | 100% |  | Completed
ER6668LT | W213 | W213.A30100 | TOR Essential Defueling Safety Case | Substantiate Station Comply with New Controls - Scope No Longer Required ## (Cost Summary) (Claim 6) | 02-Jan-24 A | 02-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 71 | 0 | 21 | 100% |  | Completed
ER6668LT | W213 | W213.A30880 | TOR Essential Defueling Safety Case | Plant Area Review in Support of Argument 6.1 EAN - Scope No Longer Required ## (Cost Summary) (Claim 6) | 02-Jan-24 A | 02-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 24 | 0 | 21 | 100% |  | Completed
ER6668LT | W213 | W213.A30890 | TOR Essential Defueling Safety Case | HOLDING LINE - Plant Area Review in Support of Argument 6.1 EAN - Scope No Longer Required | 02-Jan-24 A | 02-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 24 | 0 | 21 | 100% |  | Completed
ER6666LT | W209 | W209.1445 | HYB Essential Defueling Safety Case | Obtain CO Review & Detail Checker | 08-Jan-24 A | 08-Jan-24 | 01-Feb-24 A | 01-Feb-24 | 5 | 0 | 18 | 100% |  | Completed
ER6666LT | W209 | W209.29490 | HYB Essential Defueling Safety Case | Final Authoring Consolidation Check | 08-Jan-24 A | 08-Jan-24 | 01-Feb-24 A | 01-Feb-24 | 5 | 0 | 18 | 100% |  | Completed
ER6668LT | W213 | W213.1445 | TOR Essential Defueling Safety Case | Obtain CO Review & Detail Checker | 08-Jan-24 A | 08-Jan-24 | 01-Feb-24 A | 01-Feb-24 | 5 | 0 | 18 | 100% |  | Completed
ER6668LT | W213 | W213.29490 | TOR Essential Defueling Safety Case | Final Authoring Consolidation Check | 08-Jan-24 A | 08-Jan-24 | 01-Feb-24 A | 01-Feb-24 | 5 | 0 | 18 | 100% |  | Completed
ER6668LT | W213 | W213.A27430 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Fuel Route PSA Update EAN to CDMS | 15-Jan-24 A | 15-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 13 | 0 | 13 | 100% |  | Completed
ER6666LT | W209 | W209.A27430 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Fuel Route PSA Update EAN to CDMS | 15-Jan-24 A | 15-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 5 | 0 | 13 | 100% |  | Completed
ER6666LT | W209 | W209.7460 | HYB Essential Defueling Safety Case | Verification of Claim 7 | 17-Jan-24 A | 17-Jan-24 | 17-Jan-24 A | 17-Jan-24 | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.7470 | HYB Essential Defueling Safety Case | Update Claim 7 | 17-Jan-24 A | 17-Jan-24 | 26-Jan-24 A | 26-Jan-24 | 1 | 0 | 8 | 100% |  | Completed
ER6668LT | W213 | W213.7460 | TOR Essential Defueling Safety Case | Verification of Claim 7 | 17-Jan-24 A | 17-Jan-24 | 17-Jan-24 A | 17-Jan-24 | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.7470 | TOR Essential Defueling Safety Case | Update Claim 7 | 17-Jan-24 A | 17-Jan-24 | 26-Jan-24 A | 26-Jan-24 | 1 | 0 | 8 | 100% |  | Completed
ER6666LT | W209 | W209.28850 | HYB Essential Defueling Safety Case | Supplier Update and Issue Human Factors Integration Plan EAN (REV 001) | 18-Jan-24 A | 18-Jan-24 | 15-Mar-24 A | 15-Mar-24 | 3 | 0 | 42 | 100% |  | Completed
ER6668LT | W213 | W213.28850 | TOR Essential Defueling Safety Case | Supplier Update and Issue Human Factors Integration Plan EAN (REV 001) | 18-Jan-24 A | 18-Jan-24 | 15-Mar-24 A | 15-Mar-24 | 9 | 0 | 41 | 100% |  | Completed
W232LT | W232 | W232.A2040 | DNB Enhanced Safety Cases | Agree resource & timescales with suppliers for delivering key refs, incl contingency, risk & allowance for rework | 19-Jan-24 A | 19-Jan-24 | 11-Mar-24 A | 11-Mar-24 | 5 | 0 | 36 | 100% |  | Completed
W232LT | W232 | W232.A2970 | DNB Enhanced Safety Cases | Incorporate Station, ED (peer) comments | 22-Jan-24 A | 22-Jan-24 | 26-Jan-24 A | 26-Jan-24 | 1 | 0 | 4 | 100% |  | Completed
ER6372LT | W203 | W203.C1020 | HNB Enhanced Defuelling Safety Cases | Agree resource & timescales with suppliers for delivering key refs, incl contingency, risk & allowance for rework | 23-Jan-24 A | 23-Jan-24 | 29-Jan-24 A | 29-Jan-24 | 5 | 0 | 5 | 100% |  | Completed
ER6372LT | W203 | W203.C1010 | HNB Enhanced Defuelling Safety Cases | Mod requested, Initiate EC, identify RE, register EC & identify milestones in AMS | 23-Jan-24 A | 23-Jan-24 | 23-Jan-24 A | 23-Jan-24 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1000 | HNB Enhanced Defuelling Safety Cases | Raise Engineering Request (as required) | 23-Jan-24 A | 23-Jan-24 | 29-Jan-24 A | 29-Jan-24 | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.A29100 | HYB Essential Defueling Safety Case | Supplier Update and Issue Defuelling Handling Deterministic Assessment EAN | 25-Jan-24 A | 25-Jan-24 | 29-Jan-24 A | 29-Jan-24 | 3 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.A29100 | TOR Essential Defueling Safety Case | Supplier Update and Issue Defuelling Handling Deterministic Assessment EAN | 25-Jan-24 A | 25-Jan-24 | 29-Jan-24 A | 29-Jan-24 | 3 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.5420 | HYB Essential Defueling Safety Case | CLAIM 7 - NSP / ALARP | 26-Jan-24 A | 26-Jan-24 | 26-Jan-24 A | 26-Jan-24 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.5420 | TOR Essential Defueling Safety Case | CLAIM 7 - NSP / ALARP | 26-Jan-24 A | 26-Jan-24 | 26-Jan-24 A | 26-Jan-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2030 | DNB Enhanced Safety Cases | Hold project kick start meeting with Station & key suppliers | 26-Jan-24 A | 26-Jan-24 | 26-Mar-24 A | 26-Mar-24 | 5 | 0 | 42 | 100% |  | Completed
ER6666LT | W209 | W209.7500 | HYB Essential Defueling Safety Case | Claim 7 Ready | 26-Jan-24 A | 26-Jan-24 | 26-Jan-24 A | 26-Jan-24 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.7500 | TOR Essential Defueling Safety Case | Claim 7 Ready | 26-Jan-24 A | 26-Jan-24 | 26-Jan-24 A | 26-Jan-24 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7750 | HYB Essential Defueling Safety Case | Early INA Review Claim 4 | 29-Jan-24 A | 29-Jan-24 | 29-Feb-24 A | 29-Feb-24 | 3 | 0 | 23 | 100% |  | Completed
ER6668LT | W213 | W213.7750 | TOR Essential Defueling Safety Case | Early INA Review Claim 4 | 29-Jan-24 A | 29-Jan-24 | 29-Feb-24 A | 29-Feb-24 | 3 | 0 | 23 | 100% |  | Completed
ER6372LT | W203 | W203.C1030 | HNB Enhanced Defuelling Safety Cases | CO & CA appointed | 29-Jan-24 A | 29-Jan-24 | 29-Jan-24 A | 29-Jan-24 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1040 | HNB Enhanced Defuelling Safety Cases | Key Stakeholders Identified | 29-Jan-24 A | 29-Jan-24 | 29-Jan-24 A | 29-Jan-24 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A29110 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Defuelling Handling Deterministic Assessment EAN to CDMS | 30-Jan-24 A | 30-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 5 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A29110 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Defuelling Handling Deterministic Assessment EAN to CDMS | 30-Jan-24 A | 30-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 5 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.C1060 | HNB Enhanced Defuelling Safety Cases | Hold project kick start meeting with Station & key suppliers | 30-Jan-24 A | 30-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 5 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.C1050 | HNB Enhanced Defuelling Safety Cases | Develop initial programme plan using mandatory template | 30-Jan-24 A | 30-Jan-24 | 05-Feb-24 A | 05-Feb-24 | 5 | 0 | 5 | 100% |  | Completed
W730LT_UN | W730 | W730.1180 | HYB Enhanced Defueling Safety Cases | >>>INCOMING ENABLER (W209) Supporting References Complete | 31-Jan-24 A | 31-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 0 | 0 | 0 | 100% |  | Completed
W730LT_UN | W730 | W730.1190 | HYB Enhanced Defueling Safety Cases | >>>MIRROR OF INCOMING ENABLER (W209) Supporting References Complete | 31-Jan-24 A | 31-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1034 | HYB Essential Defueling Safety Case | All Key Supporting Technical References Completed for HYB Essential Defueling Safety Case | 31-Jan-24 A | 31-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1350 | HYB Essential Defueling Safety Case | >>>OUTGOING ENABLER (W730, W305) Supporting References Complete | 31-Jan-24 A | 31-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1405 | HYB Essential Defueling Safety Case | All Supporting References Approved and Issued | 31-Jan-24 A | 31-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A29120 | HYB Essential Defueling Safety Case | Defuelling Handling Deterministic Assessment EAN Available | 31-Jan-24 A | 31-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1350 | TOR Essential Defueling Safety Case | >>>OUTGOING ENABLER (W731, W214) Supporting References Complete | 31-Jan-24 A | 31-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1034 | TOR Essential Defueling Safety Case | All Key Supporting Technical References Completed for TOR Essential Defueling Safety Case | 31-Jan-24 A | 31-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1405 | TOR Essential Defueling Safety Case | All Supporting References Approved and Issued | 31-Jan-24 A | 31-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A29120 | TOR Essential Defueling Safety Case | Defuelling Handling Deterministic Assessment EAN Available | 31-Jan-24 A | 31-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 0 | 0 | 0 | 100% |  | Completed
W731LT_UN | W731 | W731.1000 | TOR Enhanced Defueling Safety Cases | >>>MIRROR OF INCOMING ENABLER (W209) Supporting References Complete | 31-Jan-24 A | 31-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 0 | 0 | 0 | 100% |  | Completed
W731LT_UN | W731 | W731.1010 | TOR Enhanced Defueling Safety Cases | >>>INCOMING ENABLER (W209) Supporting References Complete | 31-Jan-24 A | 31-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A27440 | HYB Essential Defueling Safety Case | Fuel Route PSA Update EAN Available | 31-Jan-24 A | 31-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A27440 | TOR Essential Defueling Safety Case | Fuel Route PSA Update EAN Available | 31-Jan-24 A | 31-Jan-24 | 31-Jan-24 A | 31-Jan-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2900 | DNB Enhanced Safety Cases | Clearance to Remove High Risk OEM NSPs | 01-Feb-24 A | 01-Feb-24 | 01-Feb-24 A | 01-Feb-24 | 10 | 0 | 0 | 100% |  | Completed
W230LT | W230 | W230.1010 | HYB Enhanced Defueling Safety Case Strategy | Project Start | 01-Feb-24 A | 01-Feb-24 | 01-Feb-24 A | 01-Feb-24 | 0 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.1010 | TOR Enhanced Defueling Safety Case Strategy | Project Start | 01-Feb-24 A | 01-Feb-24 | 01-Feb-24 A | 01-Feb-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2050 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Agree design proposals with Station in the case of hardware mods | 01-Feb-24 A | 01-Feb-24 | 01-Feb-24 A | 01-Feb-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2200 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Produce supporting reference <Structural Integrity Report 1 EAN> | 01-Feb-24 A | 01-Feb-24 | 01-Feb-24 A | 01-Feb-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B3020 | DNB Enhanced Safety Cases | Confirm Objectives to be Delivered at Gate B | 01-Feb-24 A | 01-Feb-24 | 16-Feb-24 A | 16-Feb-24 | 1 | 0 | 11 | 100% |  | Completed
W232LT | W232 | W232.A2820 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Agree design proposals with Station in the case of hardware mods | 01-Feb-24 A | 01-Feb-24 | 01-Feb-24 A | 01-Feb-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2830 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Produce supporting reference <OEM Lifting Integrity> | 01-Feb-24 A | 01-Feb-24 | 01-Feb-24 A | 01-Feb-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2045 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Structural Integrity Report 1 - Summary | 01-Feb-24 A | 01-Feb-24 | 05-Feb-24 A | 05-Feb-24 | 3 | 0 | 3 | 100% |  | Completed
W232LT | W232 | W232.A2815 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> OEM Lifting Integrity - Summary | 01-Feb-24 A | 01-Feb-24 | 05-Feb-24 A | 05-Feb-24 | 3 | 0 | 3 | 100% |  | Completed
ER6372LT | W203 | W203.C1090 | HNB Enhanced Defuelling Safety Cases | Agree design proposals with Station in the case of hardware mods | 01-Feb-24 A | 01-Feb-24 | 07-Feb-24 A | 07-Feb-24 | 5 | 0 | 5 | 100% |  | Completed
ER6372LT | W203 | W203.C1100 | HNB Enhanced Defuelling Safety Cases | Produce supporting reference <Enhanced Defueling rate EC> | 01-Feb-24 A | 01-Feb-24 | 08-Apr-24 A | 08-pr-24 | 20 | 0 | 45 | 100% |  | Completed
ER6378LT | W222 | 001965i | HRA Fuel Handling Essential Safety Case | Second Round Verification | 01-Feb-24 A | 01-Feb-24 | 14-Feb-24 A | 14-Feb-24 | 10 | 0 | 10 | 100% |  | Completed
ER6378LT | W222 | 001965g | HRA Fuel Handling Essential Safety Case | Second Round Verification | 01-Feb-24 A | 01-Feb-24 | 21-Feb-24 A | 21-Feb-24 | 10 | 0 | 14 | 100% |  | Completed
ER6378LT | W222 | 001965f | HRA Fuel Handling Essential Safety Case | Second Round Verification | 01-Feb-24 A | 01-Feb-24 | 20-Feb-24 A | 20-Feb-24 | 10 | 0 | 13 | 100% |  | Completed
ER6378LT | W222 | 001965h | HRA Fuel Handling Essential Safety Case | Second Round Verification | 01-Feb-24 A | 01-Feb-24 | 22-Feb-24 A | 22-Feb-24 | 10 | 0 | 15 | 100% |  | Completed
ER6378LT | W222 | 001965e | HRA Fuel Handling Essential Safety Case | Second Round Verification | 01-Feb-24 A | 01-Feb-24 | 22-Feb-24 A | 22-Feb-24 | 10 | 0 | 15 | 100% |  | Completed
ER6378LT | W222 | 001965d | HRA Fuel Handling Essential Safety Case | Second Round Verification | 01-Feb-24 A | 01-Feb-24 | 23-Feb-24 A | 23-Feb-24 | 10 | 0 | 16 | 100% |  | Completed
ER6378LT | W222 | 001965c | HRA Fuel Handling Essential Safety Case | Second Round Verification | 01-Feb-24 A | 01-Feb-24 | 19-Mar-24 A | 19-Mar-24 | 10 | 0 | 33 | 100% |  | Completed
ER6378LT | W222 | 001965b | HRA Fuel Handling Essential Safety Case | Second Round Verification (Claim 5) | 01-Feb-24 A | 01-Feb-24 | 21-Feb-24 A | 21-Feb-24 | 15 | 0 | 15 | 100% |  | Completed
ER6378LT | W222 | 001965a | HRA Fuel Handling Essential Safety Case | Second Round Verification | 01-Feb-24 A | 01-Feb-24 | 08-Feb-24 A | 08-Feb-24 | 15 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | 1965 | HRA Fuel Handling Essential Safety Case | Second Round Verification | 01-Feb-24 A | 01-Feb-24 | 29-Feb-24 A | 29-Feb-24 | 10 | 0 | 20 | 100% |  | Completed
W232LT | W232 | W232.C1390 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Lifting Integrity Faults> - Summary Bar | 01-Feb-24 A | 01-Feb-24 | 03-Apr-24 A | 03-pr-24 | 43 | 0 | 43 | 100% |  | Completed
W232LT | W232 | W232.C1400 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Lifting Integrity Faults> - Draft and issue RFS | 01-Feb-24 A | 01-Feb-24 | 14-Feb-24 A | 14-Feb-24 | 10 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.C1630 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Further Review of Shock Loaded Unit Events> - Summary Bar | 01-Feb-24 A | 01-Feb-24 | 03-Apr-24 A | 03-pr-24 | 43 | 0 | 43 | 100% |  | Completed
W232LT | W232 | W232.C1640 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Further Review of Shock Loaded Unit Events> - Draft and issue RFS | 01-Feb-24 A | 01-Feb-24 | 14-Feb-24 A | 14-Feb-24 | 10 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.1475 | HYB Essential Defueling Safety Case | Issue to Peer CO & Station for comments | 02-Feb-24 A | 02-Feb-24 | 02-Feb-24 A | 02-Feb-24 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.8730 | HYB Essential Defueling Safety Case | Chemistry - Specialist Assessments | 02-Feb-24 A | 02-Feb-24 | 30-Apr-24 A | 30-pr-24 | 20 | 0 | 60 | 100% |  | Completed
ER6666LT | W209 | W209.8740 | HYB Essential Defueling Safety Case | Civils - Specialist Assessments | 02-Feb-24 A | 02-Feb-24 | 30-Apr-24 A | 30-pr-24 | 20 | 0 | 60 | 100% |  | Completed
ER6666LT | W209 | W209.8750 | HYB Essential Defueling Safety Case | Emergency Arrangements - Specialist Assessments | 02-Feb-24 A | 02-Feb-24 | 30-Apr-24 A | 30-pr-24 | 20 | 0 | 60 | 100% |  | Completed
ER6666LT | W209 | W209.8770 | HYB Essential Defueling Safety Case | Env Protection & Radwaste - Specialist Assessments | 02-Feb-24 A | 02-Feb-24 | 30-Apr-24 A | 30-pr-24 | 20 | 0 | 60 | 100% |  | Completed
ER6666LT | W209 | W209.8780 | HYB Essential Defueling Safety Case | Health Physics - Specialist Assessments | 02-Feb-24 A | 02-Feb-24 | 30-Apr-24 A | 30-pr-24 | 20 | 0 | 60 | 100% |  | Completed
ER6666LT | W209 | W209.8790 | HYB Essential Defueling Safety Case | Liabilities - Specialist Assessments | 02-Feb-24 A | 02-Feb-24 | 30-Apr-24 A | 30-pr-24 | 20 | 0 | 60 | 100% |  | Completed
ER6666LT | W209 | W209.8800 | HYB Essential Defueling Safety Case | Nuclear Safety - Specialist Assessments | 02-Feb-24 A | 02-Feb-24 | 30-Apr-24 A | 30-pr-24 | 20 | 0 | 60 | 100% |  | Completed
ER6666LT | W209 | W209.8810 | HYB Essential Defueling Safety Case | Ops - Specialist Assessments | 02-Feb-24 A | 02-Feb-24 | 30-Apr-24 A | 30-pr-24 | 20 | 0 | 60 | 100% |  | Completed
ER6666LT | W209 | W209.8820 | HYB Essential Defueling Safety Case | PSSR - Liner & Pens - Specialist Assessments | 02-Feb-24 A | 02-Feb-24 | 30-Apr-24 A | 30-pr-24 | 20 | 0 | 60 | 100% |  | Completed
ER6666LT | W209 | W209.8880 | HYB Essential Defueling Safety Case | (C - D SANCTION) - Safety Case Development - (Cost Summary) ## (C to D) | 02-Feb-24 A | 02-Feb-24 | 2025-09-23 | 45923 | 395 | 142 | 415 | 75% | 0 | In Progress
ER6666LT | W209 | W209.8890 | HYB Essential Defueling Safety Case | (C - D SANCTION) - Project Management - (Cost Summary) ## (C to D) | 02-Feb-24 A | 02-Feb-24 | 2025-09-23 | 45923 | 395 | 142 | 415 | 75% | 0 | In Progress
ER6666LT | W209 | W209.28930 | HYB Essential Defueling Safety Case | Verification of the case - First Round Comments (using BARRIER MODEL) | 02-Feb-24 A | 02-Feb-24 | 30-Apr-24 A | 30-pr-24 | 20 | 0 | 61 | 100% |  | Completed
ER6668LT | W213 | W213.1475 | TOR Essential Defueling Safety Case | Issue to Peer CO & Station for comments | 02-Feb-24 A | 02-Feb-24 | 02-Feb-24 A | 02-Feb-24 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.8730 | TOR Essential Defueling Safety Case | Chemistry - Specialist Assessments (if Necessary) | 02-Feb-24 A | 02-Feb-24 | 30-Apr-24 A | 30-pr-24 | 20 | 0 | 60 | 100% |  | Completed
ER6668LT | W213 | W213.8740 | TOR Essential Defueling Safety Case | Civils - Specialist Assessments (if Necessary) | 02-Feb-24 A | 02-Feb-24 | 30-Apr-24 A | 30-pr-24 | 20 | 0 | 60 | 100% |  | Completed
ER6668LT | W213 | W213.8750 | TOR Essential Defueling Safety Case | Emergency Arrangements - Specialist Assessments (if Necessary) | 02-Feb-24 A | 02-Feb-24 | 30-Apr-24 A | 30-pr-24 | 20 | 0 | 60 | 100% |  | Completed
ER6668LT | W213 | W213.8770 | TOR Essential Defueling Safety Case | Env Protection & Radwaste - Specialist Assessments (if Necessary) | 02-Feb-24 A | 02-Feb-24 | 30-Apr-24 A | 30-pr-24 | 20 | 0 | 60 | 100% |  | Completed
ER6668LT | W213 | W213.8780 | TOR Essential Defueling Safety Case | H&V - Specialist Assessments (if Necessary) | 02-Feb-24 A | 02-Feb-24 | 30-Apr-24 A | 30-pr-24 | 20 | 0 | 60 | 100% |  | Completed
ER6668LT | W213 | W213.8790 | TOR Essential Defueling Safety Case | Liabilities - Specialist Assessments (if Necessary) | 02-Feb-24 A | 02-Feb-24 | 30-Apr-24 A | 30-pr-24 | 20 | 0 | 60 | 100% |  | Completed
ER6668LT | W213 | W213.8800 | TOR Essential Defueling Safety Case | Nuclear Safety - Specialist Assessments (if Necessary) | 02-Feb-24 A | 02-Feb-24 | 30-Apr-24 A | 30-pr-24 | 20 | 0 | 60 | 100% |  | Completed
ER6668LT | W213 | W213.8810 | TOR Essential Defueling Safety Case | Ops - Specialist Assessments (if Necessary) | 02-Feb-24 A | 02-Feb-24 | 30-Apr-24 A | 30-pr-24 | 20 | 0 | 60 | 100% |  | Completed
ER6668LT | W213 | W213.8820 | TOR Essential Defueling Safety Case | PSSR - Specialist Assessments (if Necessary) | 02-Feb-24 A | 02-Feb-24 | 30-Apr-24 A | 30-pr-24 | 20 | 0 | 60 | 100% |  | Completed
ER6668LT | W213 | W213.8880 | TOR Essential Defueling Safety Case | (C - D SANCTION) - Safety Case Development - (Cost Summary) ## (C to D) | 02-Feb-24 A | 02-Feb-24 | 2025-09-23 | 45923 | 395 | 142 | 415 | 75% | 0 | In Progress
ER6668LT | W213 | W213.8890 | TOR Essential Defueling Safety Case | (C - D SANCTION) - Project Management - (Cost Summary) ## (C to D) | 02-Feb-24 A | 02-Feb-24 | 2025-09-23 | 45923 | 395 | 142 | 415 | 75% | 0 | In Progress
ER6668LT | W213 | W213.28930 | TOR Essential Defueling Safety Case | Verification of the case (using BARRIER MODEL) | 02-Feb-24 A | 02-Feb-24 | 30-Apr-24 A | 30-pr-24 | 20 | 0 | 60 | 100% |  | Completed
ER6666LT | W209 | W209.29620 | HYB Essential Defueling Safety Case | PSSR - PCPV - Specialist Assessments | 02-Feb-24 A | 02-Feb-24 | 30-Apr-24 A | 30-pr-24 | 20 | 0 | 60 | 100% |  | Completed
ER6666LT | W209 | W209.29630 | HYB Essential Defueling Safety Case | APEX - PCPV Specialist Assessments | 02-Feb-24 A | 02-Feb-24 | 30-Apr-24 A | 30-pr-24 | 20 | 0 | 60 | 100% |  | Completed
W232LT | W232 | W232.A2350 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Verify supporting reference <Structural Integrity Report 1 EAN> | 02-Feb-24 A | 02-Feb-24 | 02-Feb-24 A | 02-Feb-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B3030 | DNB Enhanced Safety Cases | Initial high level scope of programme | 02-Feb-24 A | 02-Feb-24 | 16-Feb-24 A | 16-Feb-24 | 1 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.A2770 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Agree design proposals with Station in the case of hardware mods | 02-Feb-24 A | 02-Feb-24 | 02-Feb-24 A | 02-Feb-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2780 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Produce supporting reference <Structural Integrity Report 2 EAN> | 02-Feb-24 A | 02-Feb-24 | 02-Feb-24 A | 02-Feb-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2840 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Verify supporting reference <OEM Lifting Integrity> | 02-Feb-24 A | 02-Feb-24 | 02-Feb-24 A | 02-Feb-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2765 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Structural Integrity Report 2 - Summary | 02-Feb-24 A | 02-Feb-24 | 06-Feb-24 A | 06-Feb-24 | 3 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.1455 | HYB Essential Defueling Safety Case | Verification Commenced (T-11) | 02-Feb-24 A | 02-Feb-24 | 02-Feb-24 A | 02-Feb-24 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1036 | HYB Essential Defueling Safety Case | Safety Case Paper Authoring Complete EC 371387 -HYB Essential Defueling Safety Case | 02-Feb-24 A | 02-Feb-24 | 02-Feb-24 A | 02-Feb-24 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1455 | TOR Essential Defueling Safety Case | Verification Commenced (T-11) | 02-Feb-24 A | 02-Feb-24 | 02-Feb-24 A | 02-Feb-24 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1036 | TOR Essential Defueling Safety Case | Safety Case Paper Authoring Complete EC 371386 -TOR Essential Defueling Safety Case | 02-Feb-24 A | 02-Feb-24 | 02-Feb-24 A | 02-Feb-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2360 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> BE Technical review of supporting reference <Structural Integrity Report 1 EAN> | 05-Feb-24 A | 05-Feb-24 | 05-Feb-24 A | 05-Feb-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2790 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Verify supporting reference <Structural Integrity Report 2 EAN> | 05-Feb-24 A | 05-Feb-24 | 05-Feb-24 A | 05-Feb-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2850 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> BE Technical review of supporting reference <OEM Lifting Integrity> | 05-Feb-24 A | 05-Feb-24 | 05-Feb-24 A | 05-Feb-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2370 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Supporting reference <Structural Integrity Report 1 EAN> approved | 05-Feb-24 A | 05-Feb-24 | 05-Feb-24 A | 05-Feb-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2860 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Supporting reference <OEM Lifting Integrity> approved | 05-Feb-24 A | 05-Feb-24 | 05-Feb-24 A | 05-Feb-24 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 001965f | HYA Fuel Handling Essential Safety Case | Second Round Verification Grant | 06-Feb-24 A | 06-Feb-24 | 20-Feb-24 A | 20-Feb-24 | 10 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.A2800 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> BE Technical review of supporting reference <Structural Integrity Report 2 EAN> | 06-Feb-24 A | 06-Feb-24 | 06-Feb-24 A | 06-Feb-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1240 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Weld Inspection Data> - Summary Bar | 06-Feb-24 A | 06-Feb-24 | 03-Apr-24 A | 03-pr-24 | 40 | 0 | 40 | 100% |  | Completed
W232LT | W232 | W232.C1250 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Weld Inspection Data> - Draft and issue RFS | 06-Feb-24 A | 06-Feb-24 | 19-Feb-24 A | 19-Feb-24 | 10 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.A2810 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Supporting reference <Structural Integrity Report 2 EAN> approved | 06-Feb-24 A | 06-Feb-24 | 06-Feb-24 A | 06-Feb-24 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 001965g | HYA Fuel Handling Essential Safety Case | Second Round Verification Grant | 07-Feb-24 A | 07-Feb-24 | 21-Feb-24 A | 21-Feb-24 | 10 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.C1460 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Shock Loaded Unit Events> - Prepare Draft EAN | 07-Feb-24 A | 07-Feb-24 | 04-Apr-24 A | 04-pr-24 | 40 | 0 | 40 | 100% |  | Completed
ER6372LT | W203 | W203.A4070 | HNB Enhanced Defuelling Safety Cases | Post Job Debrief | 08-Feb-24 A | 08-Feb-24 | 08-Feb-24 A | 08-Feb-24 | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 001965h | HYA Fuel Handling Essential Safety Case | Second Round Verification Grant | 08-Feb-24 A | 08-Feb-24 | 22-Feb-24 A | 22-Feb-24 | 10 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | 001965e | HYA Fuel Handling Essential Safety Case | Second Round Verification Grant | 08-Feb-24 A | 08-Feb-24 | 22-Feb-24 A | 22-Feb-24 | 10 | 0 | 10 | 100% |  | Completed
ER6372LT | W203 | W203.1020 | HNB Enhanced Defuelling Safety Cases | IFD Deluge - Lessons Learnt Review Complete | 08-Feb-24 A | 08-Feb-24 | 08-Feb-24 A | 08-Feb-24 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 001965a | HYA Fuel Handling Essential Safety Case | Second Round Verification Grant | 09-Feb-24 A | 09-Feb-24 | 01-Mar-24 A | 01-Mar-24 | 15 | 0 | 15 | 100% |  | Completed
ER6372LT | W203 | W203.C1140 | HNB Enhanced Defuelling Safety Cases | CA to agree with CO format of the safety case & produce agreed contents page | 13-Feb-24 A | 13-Feb-24 | 14-Feb-24 A | 14-Feb-24 | 2 | 0 | 2 | 100% |  | Completed
ER6372LT | W203 | W203.C1130 | HNB Enhanced Defuelling Safety Cases | Identify verifier for the case & establish all other resources | 13-Feb-24 A | 13-Feb-24 | 19-Feb-24 A | 19-Feb-24 | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | 1965 | HYA Fuel Handling Essential Safety Case | Second Round Verification Grant | 15-Feb-24 A | 15-Feb-24 | 29-Feb-24 A | 29-Feb-24 | 10 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.C1410 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Lifting Integrity Faults> - Supplier prepare and issue Offer | 15-Feb-24 A | 15-Feb-24 | 15-Mar-24 A | 15-Mar-24 | 8 | 0 | 21 | 100% |  | Completed
W232LT | W232 | W232.C1650 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Further Review of Shock Loaded Unit Events> - Supplier prepare and issue Offer | 15-Feb-24 A | 15-Feb-24 | 15-Mar-24 A | 15-Mar-24 | 8 | 0 | 21 | 100% |  | Completed
W232LT | W232 | W232.A2470 | DNB Enhanced Safety Cases | INSA Resource Identified | 19-Feb-24 A | 19-Feb-24 | 19-Feb-24 A | 19-Feb-24 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.2020 | HYB Essential Defueling Safety Case | Hold Gate C Equivalent Mid Job Brief | 20-Feb-24 A | 20-Feb-24 | 23-Feb-24 A | 23-Feb-24 | 25 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.29260 | HYB Essential Defueling Safety Case | Lessons Learnt Activity – Following Technical References | 20-Feb-24 A | 20-Feb-24 | 23-Feb-24 A | 23-Feb-24 | 25 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.29280 | HYB Essential Defueling Safety Case | Lessons Learnt Activitiy - Following Authoring of SC | 20-Feb-24 A | 20-Feb-24 | 23-Feb-24 A | 23-Feb-24 | 20 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.2020 | TOR Essential Defueling Safety Case | Hold Gate C Equivalent Mid Job Brief | 20-Feb-24 A | 20-Feb-24 | 23-Feb-24 A | 23-Feb-24 | 25 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.29260 | TOR Essential Defueling Safety Case | Lessons Learnt Activity – Following Technical References | 20-Feb-24 A | 20-Feb-24 | 23-Feb-24 A | 23-Feb-24 | 25 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.29280 | TOR Essential Defueling Safety Case | Lessons Learnt Activitiy - Following Authoring of SC | 20-Feb-24 A | 20-Feb-24 | 23-Feb-24 A | 23-Feb-24 | 20 | 0 | 3 | 100% |  | Completed
ER6372LT | W203 | W203.C1170 | HNB Enhanced Defuelling Safety Cases | Produce verification plan | 20-Feb-24 A | 20-Feb-24 | 21-Feb-24 A | 21-Feb-24 | 2 | 0 | 2 | 100% |  | Completed
W232LT | W232 | W232.C1260 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Weld Inspection Data> - Supplier prepare and issue Offer | 20-Feb-24 A | 20-Feb-24 | 15-Mar-24 A | 15-Mar-24 | 8 | 0 | 18 | 100% |  | Completed
W232LT | W232 | W232.A2330 | DNB Enhanced Safety Cases | INA comments on NSRS | 21-Feb-24 A | 21-Feb-24 | 28-Feb-24 A | 28-Feb-24 | 5 | 0 | 5 | 100% |  | Completed
W230LT | W230 | W230.1850 | HYB Enhanced Defueling Safety Case Strategy | ## Technical Development / Project Management - Pre Gate A - (Cost Summary) ## | 22-Feb-24 A | 22-Feb-24 | 28-Jun-24 A | 28-Jun-24 | 626 | 0 | 88 | 100% |  | Completed
W230LT | W230 | W230.1910 | HYB Enhanced Defueling Safety Case Strategy | HYB Enhanced SC's & Cat C MoTA Workshop | 22-Feb-24 A | 22-Feb-24 | 22-Feb-24 A | 22-Feb-24 | 1 | 0 | 0 | 100% |  | Completed
W230LT | W230 | W230.3730 | HYB Enhanced Defueling Safety Case Strategy | ## Technical Development / Project Management - Pre Gate A - (Cost Summary) ## SUNK COSTS | 22-Feb-24 A | 22-Feb-24 | 28-Jun-24 A | 28-Jun-24 | 626 | 0 | 88 | 100% |  | Completed
W234LT | W234 | W234.1850 | TOR Enhanced Defueling Safety Case Strategy | ## Technical Development / Project Management - Pre Gate A - (Cost Summary) ## | 22-Feb-24 A | 22-Feb-24 | 28-Jun-24 A | 28-Jun-24 | 626 | 0 | 88 | 100% |  | Completed
W234LT | W234 | W234.1910 | TOR Enhanced Defueling Safety Case Strategy | TOR Enhanced SC's & Cat C MoTA Workshop | 22-Feb-24 A | 22-Feb-24 | 22-Feb-24 A | 22-Feb-24 | 1 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.3730 | TOR Enhanced Defueling Safety Case Strategy | ## Technical Development / Project Management - Pre Gate A - (Cost Summary) ## SUNK COSTS | 22-Feb-24 A | 22-Feb-24 | 28-Jun-24 A | 28-Jun-24 | 626 | 0 | 88 | 100% |  | Completed
ER6666LT | W209 | W209.1062 | HYB Essential Defueling Safety Case | Gate C Equivalent Mid Job Brief Held | 23-Feb-24 A | 23-Feb-24 | 23-Feb-24 A | 23-Feb-24 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.29270 | HYB Essential Defueling Safety Case | Lessons Learnt Milestone - Technical References | 23-Feb-24 A | 23-Feb-24 | 23-Feb-24 A | 23-Feb-24 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.29290 | HYB Essential Defueling Safety Case | Lessons Learnt Milestone - Authoring of the Safety Case | 23-Feb-24 A | 23-Feb-24 | 23-Feb-24 A | 23-Feb-24 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1062 | TOR Essential Defueling Safety Case | Gate C Equivalent Mid Job Brief Held | 23-Feb-24 A | 23-Feb-24 | 23-Feb-24 A | 23-Feb-24 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.29270 | TOR Essential Defueling Safety Case | Lessons Learnt Milestone - Technical References | 23-Feb-24 A | 23-Feb-24 | 23-Feb-24 A | 23-Feb-24 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.29290 | TOR Essential Defueling Safety Case | Lessons Learnt Milestone - Authoring of the Safety Case | 23-Feb-24 A | 23-Feb-24 | 23-Feb-24 A | 23-Feb-24 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1485 | HYB Essential Defueling Safety Case | Incorporate all stakeholder comments | 29-Feb-24 A | 29-Feb-24 | 31-May-24 A | 31-May-24 | 10 | 0 | 63 | 100% |  | Completed
ER6668LT | W213 | W213.1485 | TOR Essential Defueling Safety Case | Incorporate all stakeholder comments | 29-Feb-24 A | 29-Feb-24 | 31-May-24 A | 31-May-24 | 10 | 0 | 63 | 100% |  | Completed
W230LT | W230 | W230.1920 | HYB Enhanced Defueling Safety Case Strategy | TOR Enhanced SC's & Cat C MoTA Workshop | 29-Feb-24 A | 29-Feb-24 | 29-Feb-24 A | 29-Feb-24 | 1 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.1920 | TOR Enhanced Defueling Safety Case Strategy | TOR Enhanced SC's & Cat C MoTA Workshop | 29-Feb-24 A | 29-Feb-24 | 29-Feb-24 A | 29-Feb-24 | 1 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.1020 | HRA Enhanced Defueling Safety Case | Review of station OPEX | 01-Mar-24 A | 01-Mar-24 | 29-Mar-24 A | 29-Mar-24 | 1 | 0 | 20 | 100% |  | Completed
ER6698LT | W224 | W224.1030 | HRA Enhanced Defueling Safety Case | Mass | 01-Mar-24 A | 01-Mar-24 | 29-Mar-24 A | 29-Mar-24 | 1 | 0 | 20 | 100% |  | Completed
ER6698LT | W224 | W224.1040 | HRA Enhanced Defueling Safety Case | MSM Handling and attachment to Tie Bar | 01-Mar-24 A | 01-Mar-24 | 29-Mar-24 A | 29-Mar-24 | 1 | 0 | 20 | 100% |  | Completed
ER6698LT | W224 | W224.1050 | HRA Enhanced Defueling Safety Case | Storing and loading into the IFDF | 01-Mar-24 A | 01-Mar-24 | 29-Mar-24 A | 29-Mar-24 | 1 | 0 | 20 | 100% |  | Completed
ER6698LT | W224 | W224.1060 | HRA Enhanced Defueling Safety Case | Operations Tooling | 01-Mar-24 A | 01-Mar-24 | 29-Mar-24 A | 29-Mar-24 | 1 | 0 | 20 | 100% |  | Completed
ER6698LT | W224 | W224.1070 | HRA Enhanced Defueling Safety Case | Removal/Release mechanism | 01-Mar-24 A | 01-Mar-24 | 29-Mar-24 A | 29-Mar-24 | 1 | 0 | 20 | 100% |  | Completed
ER6698LT | W224 | W224.1080 | HRA Enhanced Defueling Safety Case | Chamfers and curves | 01-Mar-24 A | 01-Mar-24 | 30-Apr-24 A | 30-pr-24 | 1 | 0 | 40 | 100% |  | Completed
ER6698LT | W224 | W224.A1110 | HRA Enhanced Defueling Safety Case | Project Start | 01-Mar-24 A | 01-Mar-24 | 01-Mar-24 A | 01-Mar-24 | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.3530 | HRA Enhanced Defueling Safety Case | Pre Gate A Actual Cost | 01-Mar-24 A | 01-Mar-24 | 24-May-24 A | 24-May-24 | 62 | 0 | 58 | 100% |  | Completed
ER6701LT | W228 | W228.3530 | HYA Enhanced Defueling Safety Case | Pre Gate A Actual Cost | 01-Mar-24 A | 01-Mar-24 | 24-May-24 A | 24-May-24 | 62 | 0 | 58 | 100% |  | Completed
ER6701LT | W228 | W228.A1110 | HYA Enhanced Defueling Safety Case | Project Start | 01-Mar-24 A | 01-Mar-24 | 01-Mar-24 A | 01-Mar-24 | 0 | 0 | 0 | 100% |  | Completed
ER6701LT | W228 | W228.1080 | HYA Enhanced Defueling Safety Case | Chamfers and curves | 01-Mar-24 A | 01-Mar-24 | 30-Apr-24 A | 30-pr-24 | 1 | 0 | 40 | 100% |  | Completed
ER6701LT | W228 | W228.1070 | HYA Enhanced Defueling Safety Case | Removal/Release mechanism | 01-Mar-24 A | 01-Mar-24 | 29-Mar-24 A | 29-Mar-24 | 1 | 0 | 20 | 100% |  | Completed
ER6701LT | W228 | W228.1060 | HYA Enhanced Defueling Safety Case | Operations Tooling | 01-Mar-24 A | 01-Mar-24 | 29-Mar-24 A | 29-Mar-24 | 1 | 0 | 20 | 100% |  | Completed
ER6701LT | W228 | W228.1050 | HYA Enhanced Defueling Safety Case | Storing and loading into the IFDF | 01-Mar-24 A | 01-Mar-24 | 29-Mar-24 A | 29-Mar-24 | 1 | 0 | 20 | 100% |  | Completed
ER6701LT | W228 | W228.1040 | HYA Enhanced Defueling Safety Case | MSM Handling and attachment to Tie Bar | 01-Mar-24 A | 01-Mar-24 | 29-Mar-24 A | 29-Mar-24 | 1 | 0 | 20 | 100% |  | Completed
ER6701LT | W228 | W228.1030 | HYA Enhanced Defueling Safety Case | Mass | 01-Mar-24 A | 01-Mar-24 | 29-Mar-24 A | 29-Mar-24 | 1 | 0 | 20 | 100% |  | Completed
ER6701LT | W228 | W228.1020 | HYA Enhanced Defueling Safety Case | Review of station OPEX | 01-Mar-24 A | 01-Mar-24 | 29-Mar-24 A | 29-Mar-24 | 1 | 0 | 20 | 100% |  | Completed
ER6701LT | W228 | W228.1010 | HYA Enhanced Defueling Safety Case | Sunk Cost (Mar - Dec 24) | 01-Mar-24 A | 01-Mar-24 | 31-Dec-24 A | 31-Dec-24 | 1 | 0 | 210 | 100% |  | Completed
ER6666LT | W209 | W209.8760 | HYB Essential Defueling Safety Case | Computing - Specialist Assessments (Not Required) | 01-Mar-24 A | 01-Mar-24 | 04-Mar-24 A | 04-Mar-24 | 20 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2180 | DNB Enhanced Safety Cases | Incorporate INA, Station, ED (peer) comments | 01-Mar-24 A | 01-Mar-24 | 04-Mar-24 A | 04-Mar-24 | 4 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2500 | DNB Enhanced Safety Cases | Cat 2 EC Scoping Workshop | 01-Mar-24 A | 01-Mar-24 | 04-Mar-24 A | 04-Mar-24 | 2 | 0 | 2 | 100% |  | Completed
W232LT | W232 | W232.B3120 | DNB Enhanced Safety Cases | Define Project Control Structures (WBS/CBS/OBS/PBS) | 01-Mar-24 A | 01-Mar-24 | 01-Mar-24 A | 01-Mar-24 | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.8760 | TOR Essential Defueling Safety Case | Computing - Specialist Assessments (if Necessary) | 01-Mar-24 A | 01-Mar-24 | 04-Mar-24 A | 04-Mar-24 | 20 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 2130 | HYA Fuel Handling Essential Safety Case | LSD Updates | 01-Mar-24 A | 01-Mar-24 | 07-Mar-24 A | 07-Mar-24 | 5 | 0 | 5 | 100% |  | Completed
ER6698LT | W224 | W224.1090 | HRA Enhanced Defueling Safety Case | Latching / nonsliding | 01-Mar-24 A | 01-Mar-24 | 30-Apr-24 A | 30-pr-24 | 1 | 0 | 40 | 100% |  | Completed
ER6701LT | W228 | W228.1090 | HYA Enhanced Defueling Safety Case | Latching / nonsliding | 01-Mar-24 A | 01-Mar-24 | 30-Apr-24 A | 30-pr-24 | 1 | 0 | 40 | 100% |  | Completed
W232LT | W232 | W232.A2010 | DNB Enhanced Safety Cases | Issue final NSRS | 04-Mar-24 A | 04-Mar-24 | 04-Mar-24 A | 04-Mar-24 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2020 | DNB Enhanced Safety Cases | Station agree NSRS *(KDM)* | 04-Mar-24 A | 04-Mar-24 | 04-Mar-24 A | 04-Mar-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2190 | DNB Enhanced Safety Cases | Key Stakeholders agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 04-Mar-24 A | 04-Mar-24 | 04-Mar-24 A | 04-Mar-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2340 | DNB Enhanced Safety Cases | INA agree NSRS | 04-Mar-24 A | 04-Mar-24 | 04-Mar-24 A | 04-Mar-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A3000 | DNB Enhanced Safety Cases | NSRS Station Approval | 04-Mar-24 A | 04-Mar-24 | 04-Mar-24 A | 04-Mar-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B3140 | DNB Enhanced Safety Cases | Prepare Draft Project Definition Document (PDD) | 04-Mar-24 A | 04-Mar-24 | 28-Mar-24 A | 28-Mar-24 | 1 | 0 | 18 | 100% |  | Completed
W232LT | W232 | W232.B3150 | DNB Enhanced Safety Cases | Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 04-Mar-24 A | 04-Mar-24 | 04-Mar-24 A | 04-Mar-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2990 | DNB Enhanced Safety Cases | NSRS INA Review/Approval | 04-Mar-24 A | 04-Mar-24 | 04-Mar-24 A | 04-Mar-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2390 | DNB Enhanced Safety Cases | Develop plan with further iterations | 05-Mar-24 A | 05-Mar-24 | 26-Mar-24 A | 26-Mar-24 | 10 | 0 | 15 | 100% |  | Completed
W232LT | W232 | W232.B3350 | DNB Enhanced Safety Cases | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 05-Mar-24 A | 05-Mar-24 | 28-Mar-24 A | 28-Mar-24 | 1 | 0 | 17 | 100% |  | Completed
ER6650LT | W226 | 001965i | HYA Fuel Handling Essential Safety Case | Second Round Verification Grant | 05-Mar-24 A | 05-Mar-24 | 15-Mar-24 A | 15-Mar-24 | 10 | 0 | 8 | 100% |  | Completed
ER6650LT | W226 | 001965d | HYA Fuel Handling Essential Safety Case | Second Round Verification | 05-Mar-24 A | 05-Mar-24 | 19-Apr-24 A | 19-pr-24 | 10 | 0 | 31 | 100% |  | Completed
ER6650LT | W226 | 001965c | HYA Fuel Handling Essential Safety Case | Second Round Verification Grant | 05-Mar-24 A | 05-Mar-24 | 19-Mar-24 A | 19-Mar-24 | 10 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | 001965b | HYA Fuel Handling Essential Safety Case | Second Round Verification (Claim 5) | 05-Mar-24 A | 05-Mar-24 | 22-Mar-24 A | 22-Mar-24 | 15 | 0 | 13 | 100% |  | Completed
W232LT | W232 | W232.B3370 | DNB Enhanced Safety Cases | Ensure Alignment of Schedule & Estimate | 06-Mar-24 A | 06-Mar-24 | 28-Mar-24 A | 28-Mar-24 | 1 | 0 | 16 | 100% |  | Completed
W232LT | W232 | W232.B3440 | DNB Enhanced Safety Cases | Hold Risk Workshop | 07-Mar-24 A | 07-Mar-24 | 07-Mar-24 A | 07-Mar-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B3490 | DNB Enhanced Safety Cases | Complete Risk Log with Estimates | 08-Mar-24 A | 08-Mar-24 | 28-Mar-24 A | 28-Mar-24 | 1 | 0 | 14 | 100% |  | Completed
W232LT | W232 | W232.B3500 | DNB Enhanced Safety Cases | Update Schedule/Estimate from Risk Log & Add Provisions | 11-Mar-24 A | 11-Mar-24 | 28-Mar-24 A | 28-Mar-24 | 1 | 0 | 13 | 100% |  | Completed
W232LT | W232 | W232.B3580 | DNB Enhanced Safety Cases | Add Data to PRC Paper | 12-Mar-24 A | 12-Mar-24 | 28-Mar-24 A | 28-Mar-24 | 1 | 0 | 12 | 100% |  | Completed
W230LT | W230 | W230.1930 | HYB Enhanced Defueling Safety Case Strategy | Kick-Off/Setting to Work Meeting | 13-Mar-24 A | 13-Mar-24 | 13-Mar-24 A | 13-Mar-24 | 1 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.1930 | TOR Enhanced Defueling Safety Case Strategy | Kick-Off/Setting to Work Meeting | 13-Mar-24 A | 13-Mar-24 | 13-Mar-24 A | 13-Mar-24 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B3670 | DNB Enhanced Safety Cases | PCL Validate & Approve Baseline Package for PRC Submission | 13-Mar-24 A | 13-Mar-24 | 28-Mar-24 A | 28-Mar-24 | 1 | 0 | 11 | 100% |  | Completed
ER6668LT | W213 | W213.7990 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Human Factors Integration Plan EAN to CDMS (REV 001) | 18-Mar-24 A | 18-Mar-24 | 28-Mar-24 A | 28-Mar-24 | 5 | 0 | 8 | 100% |  | Completed
ER6650LT | W226 | 1990 | HYA Fuel Handling Essential Safety Case | Update Proposal (First Draft) Including Appendices & Implementation | 18-Mar-24 A | 18-Mar-24 | 09-May-24 A | 09-May-24 | 25 | 0 | 36 | 100% |  | Completed
ER6666LT | W209 | W209.7990 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Human Factors Integration Plan EAN to CDMS (REV 001) | 18-Mar-24 A | 18-Mar-24 | 28-Mar-24 A | 28-Mar-24 | 5 | 0 | 9 | 100% |  | Completed
W232LT | W232 | W232.C1270 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Weld Inspection Data> - Review Offer, prepare and issue CI | 18-Mar-24 A | 18-Mar-24 | 22-Mar-24 A | 22-Mar-24 | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.C1420 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Lifting Integrity Faults> - Review Offer, prepare and issue CI | 18-Mar-24 A | 18-Mar-24 | 22-Mar-24 A | 22-Mar-24 | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.C1660 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Further Review of Shock Loaded Unit Events> - Review Offer, prepare and issue CI | 18-Mar-24 A | 18-Mar-24 | 22-Mar-24 A | 22-Mar-24 | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | 1990 | HRA Fuel Handling Essential Safety Case | Update Proposal (First Draft) Including Appendices & Implementation | 19-Mar-24 A | 19-Mar-24 | 13-May-24 A | 13-May-24 | 25 | 0 | 37 | 100% |  | Completed
W232LT | W232 | W232.A2025 | DNB Enhanced Safety Cases | <NEW SCOPE CN1743> NSRS Presented to NSC (for complex CAT 2 cases) | 20-Mar-24 A | 20-Mar-24 | 20-Mar-24 A | 20-Mar-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2060 | DNB Enhanced Safety Cases | Consolidate & issue to stakeholders & suppliers agreed NSRS (as required) | 21-Mar-24 A | 21-Mar-24 | 27-Mar-24 A | 27-Mar-24 | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | 1968 | HRA Fuel Handling Essential Safety Case | Repsond to Second Round and Tidy Up | 22-Mar-24 A | 22-Mar-24 | 05-Apr-24 A | 05-pr-24 | 10 | 0 | 8 | 100% |  | Completed
ER6378LT | W222 | W222.A24330 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Living Safety Document EAN | 25-Mar-24 A | 25-Mar-24 | 26-Mar-24 A | 26-Mar-24 | 5 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A24330 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Living Safety Document EAN | 25-Mar-24 A | 25-Mar-24 | 26-Mar-24 A | 26-Mar-24 | 5 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1280 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Weld Inspection Data> - Supplier mobilisation time | 25-Mar-24 A | 25-Mar-24 | 02-Apr-24 A | 02-pr-24 | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.C1430 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Lifting Integrity Faults> - Supplier mobilisation time | 25-Mar-24 A | 25-Mar-24 | 02-Apr-24 A | 02-pr-24 | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.C1670 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Further Review of Shock Loaded Unit Events> - Supplier mobilisation time | 25-Mar-24 A | 25-Mar-24 | 02-Apr-24 A | 02-pr-24 | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.A2310 | DNB Enhanced Safety Cases | Issue agreed work programme to stakeholders & suppliers | 26-Mar-24 A | 26-Mar-24 | 26-Mar-24 A | 26-Mar-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2460 | DNB Enhanced Safety Cases | Verifier PJB Held | 26-Mar-24 A | 26-Mar-24 | 26-Mar-24 A | 26-Mar-24 | 0 | 0 | 0 | 100% |  | Completed
W230LT | W230 | W230.1870 | HYB Enhanced Defueling Safety Case Strategy | Initial Categorisation by Station | 26-Mar-24 A | 26-Mar-24 | 26-Mar-24 A | 26-Mar-24 | 0 | 0 | 0 | 100% |  | Completed
W230LT | W230 | W230.1940 | HYB Enhanced Defueling Safety Case Strategy | H2T Enhanced SC's EC Strategy Opex/L&L | 26-Mar-24 A | 26-Mar-24 | 26-Mar-24 A | 26-Mar-24 | 1 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.1870 | TOR Enhanced Defueling Safety Case Strategy | Initial Categorisation by Station | 26-Mar-24 A | 26-Mar-24 | 26-Mar-24 A | 26-Mar-24 | 0 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.1940 | TOR Enhanced Defueling Safety Case Strategy | H2T Enhanced SC's EC Strategy Opex/L&L | 26-Mar-24 A | 26-Mar-24 | 26-Mar-24 A | 26-Mar-24 | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 1968 | HYA Fuel Handling Essential Safety Case | Repsond to Second Round and Tidy Up | 26-Mar-24 A | 26-Mar-24 | 05-Apr-24 A | 05-pr-24 | 10 | 0 | 6 | 100% |  | Completed
ER6378LT | W222 | W222.A24340 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Living Safety Document EAN to CDMS | 27-Mar-24 A | 27-Mar-24 | 22-Jul-24 A | 22-Jul-24 | 5 | 0 | 80 | 100% |  | Completed
ER6650LT | W226 | W226.A24340 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Living Safety Document EAN to CDMS | 27-Mar-24 A | 27-Mar-24 | 02-Sep-24 A | 02-Sep-24 | 5 | 0 | 108 | 100% |  | Completed
W230LT | W230 | W230.1950 | HYB Enhanced Defueling Safety Case Strategy | Pre Job Brief | 27-Mar-24 A | 27-Mar-24 | 27-Mar-24 A | 27-Mar-24 | 1 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.1950 | TOR Enhanced Defueling Safety Case Strategy | Pre Job Brief | 27-Mar-24 A | 27-Mar-24 | 27-Mar-24 A | 27-Mar-24 | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.8000 | TOR Essential Defueling Safety Case | Human Factors Integration Plan EAN Available (REV 001) | 28-Mar-24 A | 28-Mar-24 | 28-Mar-24 A | 28-Mar-24 | 0 | 0 | 0 | 100% |  | Completed
W230LT | W230 | W230.1310 | HYB Enhanced Defueling Safety Case Strategy | Confirm Objectives to be Delivered at Gate A (FEEDS TO SUMMARY SCHEDULE) | 28-Mar-24 A | 28-Mar-24 | 03-Apr-24 A | 03-pr-24 | 10 | 0 | 3 | 100% |  | Completed
W230LT | W230 | W230.1960 | HYB Enhanced Defueling Safety Case Strategy | Draft Report | 28-Mar-24 A | 28-Mar-24 | 03-Jun-24 A | 03-Jun-24 | 1 | 0 | 44 | 100% |  | Completed
W234LT | W234 | W234.1310 | TOR Enhanced Defueling Safety Case Strategy | Confirm Objectives to be Delivered at Gate A (FEEDS TO SUMMARY SCHEDULE) | 28-Mar-24 A | 28-Mar-24 | 03-Apr-24 A | 03-pr-24 | 10 | 0 | 3 | 100% |  | Completed
W234LT | W234 | W234.1960 | TOR Enhanced Defueling Safety Case Strategy | Draft Report | 28-Mar-24 A | 28-Mar-24 | 03-Jun-24 A | 03-Jun-24 | 1 | 0 | 44 | 100% |  | Completed
ER6666LT | W209 | W209.8000 | HYB Essential Defueling Safety Case | Human Factors Integration Plan - EAN Available (REV 001) | 28-Mar-24 A | 28-Mar-24 | 28-Mar-24 A | 28-Mar-24 | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.1110 | HRA Enhanced Defueling Safety Case | Feasibility Workshop Tech Reports CNL) - early technical reference | 02-Apr-24 A | 02-pr-24 | 10-May-24 A | 10-May-24 | 21 | 0 | 28 | 100% |  | Completed
ER6698LT | W224 | W224.1120 | HRA Enhanced Defueling Safety Case | Requirements Elicitation Workshop | 02-Apr-24 A | 02-pr-24 | 30-Apr-24 A | 30-pr-24 | 21 | 0 | 20 | 100% |  | Completed
ER6698LT | W224 | W224.1130 | HRA Enhanced Defueling Safety Case | Meeting Output/Notes | 02-Apr-24 A | 02-pr-24 | 24-May-24 A | 24-May-24 | 21 | 0 | 38 | 100% |  | Completed
ER6698LT | W224 | W224.1170 | HRA Enhanced Defueling Safety Case | Scheme Design | 02-Apr-24 A | 02-pr-24 | 07-Aug-24 A | 07-ug-24 | 42 | 0 | 89 | 100% |  | Completed
ER6698LT | W224 | W224.1180 | HRA Enhanced Defueling Safety Case | Main/Key Features , for estimating purposes | 02-Apr-24 A | 02-pr-24 | 31-Oct-24 A | 31-Oct-24 | 42 | 0 | 149 | 100% |  | Completed
ER6701LT | W228 | W228.1180 | HYA Enhanced Defueling Safety Case | Main/Key Features , for estimating purposes | 02-Apr-24 A | 02-pr-24 | 31-Oct-24 A | 31-Oct-24 | 42 | 0 | 149 | 100% |  | Completed
ER6701LT | W228 | W228.1170 | HYA Enhanced Defueling Safety Case | Scheme Design | 02-Apr-24 A | 02-pr-24 | 07-Aug-24 A | 07-ug-24 | 42 | 0 | 89 | 100% |  | Completed
ER6701LT | W228 | W228.1130 | HYA Enhanced Defueling Safety Case | Meeting Output/Notes | 02-Apr-24 A | 02-pr-24 | 24-May-24 A | 24-May-24 | 21 | 0 | 38 | 100% |  | Completed
ER6701LT | W228 | W228.1120 | HYA Enhanced Defueling Safety Case | Requirements Elicitation Workshop | 02-Apr-24 A | 02-pr-24 | 30-Apr-24 A | 30-pr-24 | 21 | 0 | 20 | 100% |  | Completed
ER6701LT | W228 | W228.1110 | HYA Enhanced Defueling Safety Case | Feasibility Workshop Tech Reports CNL) - early technical reference | 02-Apr-24 A | 02-pr-24 | 10-May-24 A | 10-May-24 | 21 | 0 | 28 | 100% |  | Completed
ER6666LT | W209 | W209.1415 | HYB Essential Defueling Safety Case | Populate Affected Documents List | 02-Apr-24 A | 02-pr-24 | 28-Jun-24 A | 28-Jun-24 | 10 | 0 | 62 | 100% |  | Completed
ER6668LT | W213 | W213.1415 | TOR Essential Defueling Safety Case | Populate Affected Documents List | 02-Apr-24 A | 02-pr-24 | 28-Jun-24 A | 28-Jun-24 | 10 | 0 | 62 | 100% |  | Completed
W232LT | W232 | W232.C1290 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Weld Inspection Data> - Pre Job Brief | 03-Apr-24 A | 03-pr-24 | 03-Apr-24 A | 03-pr-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1440 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Lifting Integrity Faults> - Pre Job Brief | 03-Apr-24 A | 03-pr-24 | 03-Apr-24 A | 03-pr-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1680 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Further Review of Shock Loaded Unit Events> - Pre Job Brief | 03-Apr-24 A | 03-pr-24 | 03-Apr-24 A | 03-pr-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C3040 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Weld Inspection Data> - Prepare Draft EAN - Part 1 | 04-Apr-24 A | 04-pr-24 | 23-Apr-24 A | 23-pr-24 | 14 | 0 | 14 | 100% |  | Completed
W232LT | W232 | W232.C3050 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Lifting Integrity Faults> - Prepare Draft EAN - Part 1 | 04-Apr-24 A | 04-pr-24 | 23-Apr-24 A | 23-pr-24 | 14 | 0 | 14 | 100% |  | Completed
W232LT | W232 | W232.A5680 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Further Review of Shock Loaded Unit Events> - Prepare Draft EAN - Part 1 | 04-Apr-24 A | 04-pr-24 | 23-Apr-24 A | 23-pr-24 | 14 | 0 | 14 | 100% |  | Completed
W230LT | W230 | W230.1300 | HYB Enhanced Defueling Safety Case Strategy | Initial high level scope of programme | 04-Apr-24 A | 04-pr-24 | 07-May-24 A | 07-May-24 | 5 | 0 | 23 | 100% |  | Completed
W234LT | W234 | W234.1300 | TOR Enhanced Defueling Safety Case Strategy | Initial high level scope of programme | 04-Apr-24 A | 04-pr-24 | 07-May-24 A | 07-May-24 | 5 | 0 | 23 | 100% |  | Completed
W232LT | W232 | W232.C1470 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Shock Loaded Unit Events> - Issue Draft EAN to EDF for Review. | 04-Apr-24 A | 04-pr-24 | 04-Apr-24 A | 04-pr-24 | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | 1970 | HRA Fuel Handling Essential Safety Case | Upload into AMS | 05-Apr-24 A | 05-pr-24 | 19-Jul-24 A | 19-Jul-24 | 1 | 0 | 74 | 100% |  | Completed
ER6650LT | W226 | 1970 | HYA Fuel Handling Essential Safety Case | Upload into AMS | 05-Apr-24 A | 05-pr-24 | 19-Jul-24 A | 19-Jul-24 | 1 | 0 | 74 | 100% |  | Completed
ER6378LT | W222 | 1969 | HRA Fuel Handling Essential Safety Case | Head Document Verification Complete | 05-Apr-24 A | 05-pr-24 | 05-Apr-24 A | 05-pr-24 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 1969 | HYA Fuel Handling Essential Safety Case | Head Document Verification Complete | 05-Apr-24 A | 05-pr-24 | 05-Apr-24 A | 05-pr-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3060 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Shock Loaded Unit Events> - Draft EAN Reviewed by EDF SQEP - Part 1 | 05-Apr-24 A | 05-pr-24 | 23-Apr-24 A | 23-pr-24 | 13 | 0 | 13 | 100% |  | Completed
ER6666LT | W209 | W209.29570 | HYB Essential Defueling Safety Case | Verification Schedule Risk - (Risk Ref 28381) | 08-Apr-24 A | 08-pr-24 | 08-Apr-24 A | 08-pr-24 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.29580 | HYB Essential Defueling Safety Case | Risk Milestone - Verification (Risk Ref 28381) - Verification Substantially Complete | 08-Apr-24 A | 08-pr-24 | 08-Apr-24 A | 08-pr-24 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.29570 | TOR Essential Defueling Safety Case | Verification Schedule Risk - (Risk Ref 28381) | 08-Apr-24 A | 08-pr-24 | 08-Apr-24 A | 08-pr-24 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.29580 | TOR Essential Defueling Safety Case | Risk Milestone - Verification (Risk Ref 28381) - Verification Substantially Complete | 08-Apr-24 A | 08-pr-24 | 08-Apr-24 A | 08-pr-24 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1220 | HNB Enhanced Defuelling Safety Cases | Verify supporting reference <Enhanced Defueling rate EC> | 08-Apr-24 A | 08-pr-24 | 19-Apr-24 A | 19-pr-24 | 10 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.B4020 | DNB Enhanced Safety Cases | Gate B PRC Paper Submission | 10-Apr-24 A | 10-pr-24 | 10-Apr-24 A | 10-pr-24 | 1 | 0 | 1 | 100% |  | Completed
W230LT | W230 | W230.1860 | HYB Enhanced Defueling Safety Case Strategy | PM / CO and PCE Create Initial Plan of Work | 11-Apr-24 A | 11-pr-24 | 15-May-24 A | 15-May-24 | 0 | 0 | 24 | 100% |  | Completed
W234LT | W234 | W234.1860 | TOR Enhanced Defueling Safety Case Strategy | PM / CO and PCE Create Initial Plan of Work | 11-Apr-24 A | 11-pr-24 | 15-May-24 A | 15-May-24 | 0 | 0 | 24 | 100% |  | Completed
W232LT | W232 | W232.B4030 | DNB Enhanced Safety Cases | PRC Members Review PRC Documentation | 11-Apr-24 A | 11-pr-24 | 17-Apr-24 A | 17-pr-24 | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.29640 | HYB Essential Defueling Safety Case | Complete TR Statement - IFD EAN | 12-Apr-24 A | 12-pr-24 | 23-Apr-24 A | 23-pr-24 | 1 | 0 | 7 | 100% |  | Completed
ER6666LT | W209 | W209.29660 | HYB Essential Defueling Safety Case | Close Out TR Comments - (Dose Band Review & Post Fault Action EAN) | 12-Apr-24 A | 12-pr-24 | 20-May-24 A | 20-May-24 | 1 | 0 | 26 | 100% |  | Completed
ER6666LT | W209 | W209.29690 | HYB Essential Defueling Safety Case | Complete Verification - (Failed Fuel Handling in ODR condition) | 12-Apr-24 A | 12-pr-24 | 12-Jun-24 A | 12-Jun-24 | 1 | 0 | 41 | 100% |  | Completed
ER6668LT | W213 | W209.29640 | TOR Essential Defueling Safety Case | Complete TR Statement - IFD EAN | 12-Apr-24 A | 12-pr-24 | 23-Apr-24 A | 23-pr-24 | 1 | 0 | 7 | 100% |  | Completed
ER6668LT | W213 | W209.29660 | TOR Essential Defueling Safety Case | Close Out TR Comments - (Dose Band Review & Post Fault Action EAN) | 12-Apr-24 A | 12-pr-24 | 20-May-24 A | 20-May-24 | 1 | 0 | 26 | 100% |  | Completed
ER6668LT | W213 | W209.29690 | TOR Essential Defueling Safety Case | Complete Verification - (Failed Fuel Handling in ODR condition) | 12-Apr-24 A | 12-pr-24 | 12-Jun-24 A | 12-Jun-24 | 1 | 0 | 41 | 100% |  | Completed
ER6372LT | W203 | W203.C1270 | HNB Enhanced Defuelling Safety Cases | BE Technical review of supporting reference <Enhanced Defueling rate EC> | 22-Apr-24 A | 22-pr-24 | 28-Jun-24 A | 28-Jun-24 | 10 | 0 | 48 | 100% |  | Completed
W232LT | W232 | W232.A2690 | DNB Enhanced Safety Cases | Gate B PRC Paper Approval (DNB) | 23-Apr-24 A | 23-pr-24 | 23-Apr-24 A | 23-pr-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B4300 | DNB Enhanced Safety Cases | Hold PRC Meeting | 23-Apr-24 A | 23-pr-24 | 23-Apr-24 A | 23-pr-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B4310 | DNB Enhanced Safety Cases | Gate B PRC Paper Approval | 23-Apr-24 A | 23-pr-24 | 23-Apr-24 A | 23-pr-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B1000 | DNB Enhanced Safety Cases | < BASELINE COST INCREASE PENDING CN 3472>Project Management - B-D | 23-Apr-24 A | 23-pr-24 | 2026-02-20 | 46073 | 412 | 247 | 464 | 45% | 5 | In Progress
W232LT | W232 | W232.B1010 | DNB Enhanced Safety Cases | Technical Oversight - B-D | 23-Apr-24 A | 23-pr-24 | 2026-02-20 | 46073 | 412 | 247 | 464 | 45% | 5 | In Progress
ER6666LT | W209 | W209.29650 | HYB Essential Defueling Safety Case | Issue on CDMS - IFD EAN | 24-Apr-24 A | 24-pr-24 | 30-Apr-24 A | 30-pr-24 | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W209.29650 | TOR Essential Defueling Safety Case | Issue on CDMS - IFD EAN | 24-Apr-24 A | 24-pr-24 | 30-Apr-24 A | 30-pr-24 | 5 | 0 | 4 | 100% |  | Completed
W232LT | W232 | W232.C1150 | DNB Enhanced Safety Cases | <Review of Weld Inspection Data> - Summary | 24-Apr-24 A | 24-pr-24 | 30-Sep-24 A | 30-Sep-24 | 106 | 0 | 110 | 100% |  | Completed
W232LT | W232 | W232.C1160 | DNB Enhanced Safety Cases | <Review of Weld Inspection Data> - Prepare Draft EAN - Part 2 | 24-Apr-24 A | 24-pr-24 | 23-May-24 A | 23-May-24 | 21 | 0 | 21 | 100% |  | Completed
W232LT | W232 | W232.C1300 | DNB Enhanced Safety Cases | <Review of Lifting Integrity Faults> - Summary | 24-Apr-24 A | 24-pr-24 | 30-Sep-24 A | 30-Sep-24 | 105 | 0 | 110 | 100% |  | Completed
W232LT | W232 | W232.C1310 | DNB Enhanced Safety Cases | <Review of Lifting Integrity Faults> - Prepare Draft EAN - Part 2 | 24-Apr-24 A | 24-pr-24 | 13-May-24 A | 13-May-24 | 21 | 0 | 12 | 100% |  | Completed
W232LT | W232 | W232.C1450 | DNB Enhanced Safety Cases | <Review of Shock Loaded Unit Events> - Summary | 24-Apr-24 A | 24-pr-24 | 24-May-24 A | 24-May-24 | 28 | 0 | 21 | 100% |  | Completed
W232LT | W232 | W232.C1480 | DNB Enhanced Safety Cases | <Review of Shock Loaded Unit Events> - Draft EAN Reviewed by EDF SQEP - Part 2 | 24-Apr-24 A | 24-pr-24 | 03-May-24 A | 03-May-24 | 8 | 0 | 8 | 100% |  | Completed
W232LT | W232 | W232.C1540 | DNB Enhanced Safety Cases | <SCOPE NAME CHANGE CN 2615><Further Review of Shock Loaded Unit Events (Group 1)> - Summary | 24-Apr-24 A | 24-pr-24 | 08-Oct-24 A | 08-Oct-24 | 115 | 0 | 116 | 100% |  | Completed
W232LT | W232 | W232.C1550 | DNB Enhanced Safety Cases | <SCOPE NAME CHANGE CN 2615><Further Review of Shock Loaded Unit Events (Group 1)> - Prepare Draft EAN - Part 2 | 24-Apr-24 A | 24-pr-24 | 08-Aug-24 A | 08-ug-24 | 21 | 0 | 75 | 100% |  | Completed
ER6372LT | W203 | W203.C1070 | HNB Enhanced Defuelling Safety Cases | CA PJB Held | 25-Apr-24 A | 25-pr-24 | 25-Apr-24 A | 25-pr-24 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1080 | HNB Enhanced Defuelling Safety Cases | Produce MF (as required) | 29-Apr-24 A | 29-pr-24 | 10-Jun-24 A | 10-Jun-24 | 5 | 0 | 29 | 100% |  | Completed
ER6372LT | W203 | W203.C1380 | HNB Enhanced Defuelling Safety Cases | Prepare the Safety Case Proposal (including OPEX Review) | 29-Apr-24 A | 29-pr-24 | 28-Jun-24 A | 28-Jun-24 | 10 | 0 | 42 | 100% |  | Completed
W232LT | W232 | W232.A2080 | DNB Enhanced Safety Cases | Rev 000 - Prepare the Safety Case Proposal (including OPEX Review) | 01-May-24 A | 01-May-24 | 08-Oct-24 A | 08-Oct-24 | 35 | 0 | 111 | 100% |  | Completed
ER6698LT | W224 | W224. A1010 | HRA Enhanced Defueling Safety Case | Prepare Schedule [FEEDS TO SUMMARY SCHEDULE] | 01-May-24 A | 01-May-24 | 28-May-24 A | 28-May-24 | 5 | 0 | 17 | 100% |  | Completed
ER6698LT | W224 | W224. A1020 | HRA Enhanced Defueling Safety Case | Prepare Cost Estimates | 01-May-24 A | 01-May-24 | 28-May-24 A | 28-May-24 | 5 | 0 | 17 | 100% |  | Completed
ER6698LT | W224 | W224. A1030 | HRA Enhanced Defueling Safety Case | Write IRM Paper | 01-May-24 A | 01-May-24 | 22-May-24 A | 22-May-24 | 15 | 0 | 15 | 100% |  | Completed
ER6701LT | W228 | W228. A1030 | HYA Enhanced Defueling Safety Case | Write IRM Paper | 01-May-24 A | 01-May-24 | 22-May-24 A | 22-May-24 | 15 | 0 | 15 | 100% |  | Completed
ER6701LT | W228 | W228. A1020 | HYA Enhanced Defueling Safety Case | Prepare Cost Estimates | 01-May-24 A | 01-May-24 | 28-May-24 A | 28-May-24 | 5 | 0 | 17 | 100% |  | Completed
ER6701LT | W228 | W228. A1010 | HYA Enhanced Defueling Safety Case | Prepare Schedule [FEEDS TO SUMMARY SCHEDULE] | 01-May-24 A | 01-May-24 | 28-May-24 A | 28-May-24 | 5 | 0 | 17 | 100% |  | Completed
W232LT | W232 | W232.C1490 | DNB Enhanced Safety Cases | <Review of Shock Loaded Unit Events> - Address Comments from EDF Review on Draft EAN | 07-May-24 A | 07-May-24 | 20-May-24 A | 20-May-24 | 10 | 0 | 10 | 100% |  | Completed
W230LT | W230 | W230.1290 | HYB Enhanced Defueling Safety Case Strategy | Update Schedule/Estimate from Risk Log & Add Provisions | 08-May-24 A | 08-May-24 | 14-May-24 A | 14-May-24 | 5 | 0 | 5 | 100% |  | Completed
W234LT | W234 | W234.1290 | TOR Enhanced Defueling Safety Case Strategy | Update Schedule/Estimate from Risk Log & Add Provisions | 08-May-24 A | 08-May-24 | 14-May-24 A | 14-May-24 | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | 2030 | HRA Fuel Handling Essential Safety Case | Update Verification Plan | 09-May-24 A | 09-May-24 | 10-May-24 A | 10-May-24 | 2 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | 2030 | HYA Fuel Handling Essential Safety Case | Update Verification Plan | 09-May-24 A | 09-May-24 | 10-May-24 A | 10-May-24 | 2 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | 1991 | HYA Fuel Handling Essential Safety Case | Update Proposal Peer Review | 10-May-24 A | 10-May-24 | 14-May-24 A | 14-May-24 | 3 | 0 | 3 | 100% |  | Completed
ER6378LT | W222 | 1991 | HRA Fuel Handling Essential Safety Case | Update Proposal Peer Review | 13-May-24 A | 13-May-24 | 14-May-24 A | 14-May-24 | 2 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | 2040 | HRA Fuel Handling Essential Safety Case | Secure Verification Resource | 13-May-24 A | 13-May-24 | 13-May-24 A | 13-May-24 | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 2040 | HYA Fuel Handling Essential Safety Case | Secure Verification Resource | 13-May-24 A | 13-May-24 | 13-May-24 A | 13-May-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1380 | DNB Enhanced Safety Cases | <Review of Lifting Integrity Faults> - TSA Internal Review of Draft EAN | 14-May-24 A | 14-May-24 | 23-Jul-24 A | 23-Jul-24 | 10 | 0 | 49 | 100% |  | Completed
ER6378LT | W222 | 2050 | HRA Fuel Handling Essential Safety Case | Verification PJB | 14-May-24 A | 14-May-24 | 14-May-24 A | 14-May-24 | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 2050 | HYA Fuel Handling Essential Safety Case | Verification PJB | 14-May-24 A | 14-May-24 | 14-May-24 A | 14-May-24 | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | 2071 | HRA Fuel Handling Essential Safety Case | Sub-verifier(s) including GAP review (HHB OPEX) First Round | 15-May-24 A | 15-May-24 | 05-Jun-24 A | 05-Jun-24 | 15 | 0 | 15 | 100% |  | Completed
ER6378LT | W222 | 1992 | HRA Fuel Handling Essential Safety Case | Update Proposal (Second Draft) | 15-May-24 A | 15-May-24 | 21-May-24 A | 21-May-24 | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | 2068 | HRA Fuel Handling Essential Safety Case | First Round Verification - Stn Verifier Comments | 15-May-24 A | 15-May-24 | 05-Jun-24 A | 05-Jun-24 | 15 | 0 | 15 | 100% |  | Completed
ER6378LT | W222 | 2060 | HRA Fuel Handling Essential Safety Case | Verification including GAP review (Lead Verifier)(HHB OPEX) First Round | 15-May-24 A | 15-May-24 | 05-Jun-24 A | 05-Jun-24 | 15 | 0 | 15 | 100% |  | Completed
ER6378LT | W222 | 2070 | HRA Fuel Handling Essential Safety Case | Sub-verifier(s) including GAP review (HHB OPEX) First Round | 15-May-24 A | 15-May-24 | 05-Jun-24 A | 05-Jun-24 | 15 | 0 | 15 | 100% |  | Completed
ER6650LT | W226 | 2071 | HYA Fuel Handling Essential Safety Case | Sub-verifier(s) including GAP review (HHB OPEX) First Round | 15-May-24 A | 15-May-24 | 08-Jul-24 A | 08-Jul-24 | 15 | 0 | 38 | 100% |  | Completed
ER6650LT | W226 | 1992 | HYA Fuel Handling Essential Safety Case | Update Proposal (Second Draft) | 15-May-24 A | 15-May-24 | 21-May-24 A | 21-May-24 | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | 2068 | HYA Fuel Handling Essential Safety Case | First Round Verification - Stn Verifier Comments | 15-May-24 A | 15-May-24 | 08-Jul-24 A | 08-Jul-24 | 15 | 0 | 38 | 100% |  | Completed
ER6650LT | W226 | 2060 | HYA Fuel Handling Essential Safety Case | Verification including GAP review (Lead Verifier)(HHB OPEX) First Round | 15-May-24 A | 15-May-24 | 01-Jul-24 A | 01-Jul-24 | 15 | 0 | 32 | 100% |  | Completed
ER6650LT | W226 | 2070 | HYA Fuel Handling Essential Safety Case | Sub-verifier(s) including GAP review (HHB OPEX) First Round | 15-May-24 A | 15-May-24 | 08-Jul-24 A | 08-Jul-24 | 15 | 0 | 38 | 100% |  | Completed
W230LT | W230 | W230.1280 | HYB Enhanced Defueling Safety Case Strategy | Draft / Add Data to PRC/IMS2 Paper | 15-May-24 A | 15-May-24 | 03-Jun-24 A | 03-Jun-24 | 5 | 0 | 13 | 100% |  | Completed
W230LT | W230 | W230.1270 | HYB Enhanced Defueling Safety Case Strategy | Summary for HYB Fuel Handling Enhanced Safety Cases W230 | 15-May-24 A | 15-May-24 | 2026-05-19 | 46161 | 321 | 306 | 509 | 0% | 0 | In Progress
W234LT | W234 | W234.1280 | TOR Enhanced Defueling Safety Case Strategy | Draft / Add Data to PRC/IMS2 Paper | 15-May-24 A | 15-May-24 | 03-Jun-24 A | 03-Jun-24 | 5 | 0 | 13 | 100% |  | Completed
W234LT | W234 | W234.1270 | TOR Enhanced Defueling Safety Case Strategy | Summary for TOR Fuel Handling Enhanced Safety Cases W230 | 15-May-24 A | 15-May-24 | 2026-05-19 | 46161 | 321 | 306 | 509 | 0% | 0 | In Progress
W230LT | W230 | W230.1880 | HYB Enhanced Defueling Safety Case Strategy | Appoint CO / AE / RE | 16-May-24 A | 16-May-24 | 16-May-24 A | 16-May-24 | 1 | 0 | 1 | 100% |  | Completed
W234LT | W234 | W234.1880 | TOR Enhanced Defueling Safety Case Strategy | Appoint CO / AE / RE | 16-May-24 A | 16-May-24 | 16-May-24 A | 16-May-24 | 1 | 0 | 1 | 100% |  | Completed
W230LT | W230 | W230.1890 | HYB Enhanced Defueling Safety Case Strategy | Key Stakeholders Identified | 17-May-24 A | 17-May-24 | 17-May-24 A | 17-May-24 | 1 | 0 | 1 | 100% |  | Completed
W234LT | W234 | W234.1890 | TOR Enhanced Defueling Safety Case Strategy | Key Stakeholders Identified | 17-May-24 A | 17-May-24 | 17-May-24 A | 17-May-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1500 | DNB Enhanced Safety Cases | <Review of Shock Loaded Unit Events> - Issue Final EAN | 20-May-24 A | 20-May-24 | 20-May-24 A | 20-May-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A4990 | DNB Enhanced Safety Cases | Lessons Learned Workshop - FPU Safety Case Ph 3 NSRS Approved | 21-May-24 A | 21-May-24 | 21-May-24 A | 21-May-24 | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.1200 | HRA Fuel Handling Essential Safety Case | Verification and SAs of the case (using BARRIER MODEL) (PART 2 - IMPACT from EVENT RECOVERY) | 21-May-24 A | 21-May-24 | 16-Jul-24 A | 16-Jul-24 | 40 | 0 | 40 | 100% |  | Completed
ER6650LT | W226 | W226.1200 | HYA Fuel Handling Essential Safety Case | Verification of the case (using BARRIER MODEL) (PART 2 - IMPACT from EVENT RECOVERY) | 21-May-24 A | 21-May-24 | 16-Jul-24 A | 16-Jul-24 | 40 | 0 | 40 | 100% |  | Completed
ER6650LT | W226 | W226.3020 | HYA Fuel Handling Essential Safety Case | Lesson Learn - Event Recovery Phase | 21-May-24 A | 21-May-24 | 21-May-24 A | 21-May-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1510 | DNB Enhanced Safety Cases | <Review of Shock Loaded Unit Events> - EAN Completed and Uploaded to CDMS | 21-May-24 A | 21-May-24 | 24-May-24 A | 24-May-24 | 10 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.29670 | HYB Essential Defueling Safety Case | Complete TR Statement - (Dose Band Review & Post Fault Action EAN) | 21-May-24 A | 21-May-24 | 23-May-24 A | 23-May-24 | 3 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W209.29670 | TOR Essential Defueling Safety Case | Complete TR Statement - (Dose Band Review & Post Fault Action EAN) | 21-May-24 A | 21-May-24 | 23-May-24 A | 23-May-24 | 3 | 0 | 3 | 100% |  | Completed
ER6378LT | W222 | W222.1210 | HRA Fuel Handling Essential Safety Case | EVENT RECOVERY MILESTONE - AMS Milestone - EC Ready for Review - Activity No 2020 | 21-May-24 A | 21-May-24 | 21-May-24 A | 21-May-24 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.1210 | HYA Fuel Handling Essential Safety Case | EVENT RECOVERY MILESTONE - AMS Milestone - EC Ready for Review - Activity No 2020 | 21-May-24 A | 21-May-24 | 21-May-24 A | 21-May-24 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 2020 | HYA Fuel Handling Essential Safety Case | AMS Milestone - Ready for Review | 21-May-24 A | 21-May-24 | 21-May-24 A | 21-May-24 | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A27485 | HRA Fuel Handling Essential Safety Case | AMS Ready for Review | 21-May-24 A | 21-May-24 | 21-May-24 A | 21-May-24 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27485 | HYA Fuel Handling Essential Safety Case | AMS Ready for Review | 21-May-24 A | 21-May-24 | 21-May-24 A | 21-May-24 | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224. A1040 | HRA Enhanced Defueling Safety Case | IRM Paper stakeholder sign off | 23-May-24 A | 23-May-24 | 07-Jun-24 A | 07-Jun-24 | 5 | 0 | 11 | 100% |  | Completed
ER6701LT | W228 | W228. A1040 | HYA Enhanced Defueling Safety Case | IRM Paper stakeholder sign off | 23-May-24 A | 23-May-24 | 07-Jun-24 A | 07-Jun-24 | 5 | 0 | 11 | 100% |  | Completed
W232LT | W232 | W232.C1520 | DNB Enhanced Safety Cases | <Review of Shock Loaded Unit Events> - EAN Completed | 24-May-24 A | 24-May-24 | 24-May-24 A | 24-May-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1230 | DNB Enhanced Safety Cases | <Review of Weld Inspection Data> - TSA Internal Review of Draft EAN | 24-May-24 A | 24-May-24 | 21-Jun-24 A | 21-Jun-24 | 10 | 0 | 19 | 100% |  | Completed
ER6666LT | W209 | W209.29680 | HYB Essential Defueling Safety Case | Issue on CDMS - (Dose Band Review & Post Fault Action EAN) | 24-May-24 A | 24-May-24 | 03-Jun-24 A | 03-Jun-24 | 5 | 0 | 6 | 100% |  | Completed
ER6668LT | W213 | W209.29680 | TOR Essential Defueling Safety Case | Issue on CDMS - (Dose Band Review & Post Fault Action EAN) | 24-May-24 A | 24-May-24 | 03-Jun-24 A | 03-Jun-24 | 5 | 0 | 6 | 100% |  | Completed
ER6698LT | W224 | W224.1340 | HRA Enhanced Defueling Safety Case | RFS | 28-May-24 A | 28-May-24 | 07-Jun-24 A | 07-Jun-24 | 10 | 0 | 9 | 100% |  | Completed
ER6701LT | W228 | W228.1340 | HYA Enhanced Defueling Safety Case | RFS | 28-May-24 A | 28-May-24 | 07-Jun-24 A | 07-Jun-24 | 10 | 0 | 9 | 100% |  | Completed
ER6378LT | W222 | W222.3020 | HRA Fuel Handling Essential Safety Case | Lesson Learn - Event Recovery Phase | 28-May-24 A | 28-May-24 | 28-May-24 A | 28-May-24 | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.1495 | HYB Essential Defueling Safety Case | Final Verification - (Including = CLAIM 7 Update and Detailed Check) | 31-May-24 A | 31-May-24 | 18-Sep-24 A | 18-Sep-24 | 20 | 0 | 78 | 100% |  | Completed
ER6668LT | W213 | W213.1495 | TOR Essential Defueling Safety Case | Final Verification - (Including = CLAIM 7 Update and Detailed Check) | 31-May-24 A | 31-May-24 | 18-Sep-24 A | 18-Sep-24 | 20 | 0 | 78 | 100% |  | Completed
ER6698LT | W224 | W224.1250 | HRA Enhanced Defueling Safety Case | RFS | 03-Jun-24 A | 03-Jun-24 | 14-Jun-24 A | 14-Jun-24 | 1 | 0 | 10 | 100% |  | Completed
ER6698LT | W224 | W224.3810 | HRA Enhanced Defueling Safety Case | WBS Cost Summary Analysis in support of Tie Bar Buckling | 03-Jun-24 A | 03-Jun-24 | 2025-03-03 | 45719 | 162 | 0 | 191 | 100% | 251 | In Progress
ER6701LT | W228 | W228.3810 | HYA Enhanced Defueling Safety Case | WBS Cost Summary Analysis in support of Tie Bar Buckling | 03-Jun-24 A | 03-Jun-24 | 03-Feb-25 A | 03-Feb-25 | 162 | 0 | 171 | 100% |  | Completed
ER6701LT | W228 | W228.1250 | HYA Enhanced Defueling Safety Case | RFS | 03-Jun-24 A | 03-Jun-24 | 14-Jun-24 A | 14-Jun-24 | 1 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.A31290 | HYB Essential Defueling Safety Case | Technical Review of PSA Documentation | 04-Jun-24 A | 04-Jun-24 | 17-Jun-24 A | 17-Jun-24 | 10 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.A31290 | TOR Essential Defueling Safety Case | Technical Review of PSA Documentation | 04-Jun-24 A | 04-Jun-24 | 17-Jun-24 A | 17-Jun-24 | 10 | 0 | 10 | 100% |  | Completed
W230LT | W230 | W230.1320 | HYB Enhanced Defueling Safety Case Strategy | Prepare Draft Project Definition Document (PDD) | 04-Jun-24 A | 04-Jun-24 | 07-Jun-24 A | 07-Jun-24 | 4 | 0 | 4 | 100% |  | Completed
W230LT | W230 | W230.1970 | HYB Enhanced Defueling Safety Case Strategy | Verified by TSA | 04-Jun-24 A | 04-Jun-24 | 17-Jun-24 A | 17-Jun-24 | 10 | 0 | 10 | 100% |  | Completed
W234LT | W234 | W234.1320 | TOR Enhanced Defueling Safety Case Strategy | Prepare Draft Project Definition Document (PDD) | 04-Jun-24 A | 04-Jun-24 | 07-Jun-24 A | 07-Jun-24 | 4 | 0 | 4 | 100% |  | Completed
W234LT | W234 | W234.1970 | TOR Enhanced Defueling Safety Case Strategy | Verified by TSA | 04-Jun-24 A | 04-Jun-24 | 17-Jun-24 A | 17-Jun-24 | 10 | 0 | 10 | 100% |  | Completed
ER6378LT | W222 | 2072 | HRA Fuel Handling Essential Safety Case | Respond to First Round Comments | 06-Jun-24 A | 06-Jun-24 | 08-Jul-24 A | 08-Jul-24 | 23 | 0 | 23 | 100% |  | Completed
W230LT | W230 | W230.1330 | HYB Enhanced Defueling Safety Case Strategy | PCL Validate & Approve Baseline Package for PRC Submission | 10-Jun-24 A | 10-Jun-24 | 11-Jun-24 A | 11-Jun-24 | 2 | 0 | 2 | 100% |  | Completed
W234LT | W234 | W234.1330 | TOR Enhanced Defueling Safety Case Strategy | PCL Validate & Approve Baseline Package for PRC Submission | 10-Jun-24 A | 10-Jun-24 | 11-Jun-24 A | 11-Jun-24 | 2 | 0 | 2 | 100% |  | Completed
ER6372LT | W203 | W203.C1110 | HNB Enhanced Defuelling Safety Cases | Issue MF (as required) | 10-Jun-24 A | 10-Jun-24 | 10-Jun-24 A | 10-Jun-24 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1160 | HNB Enhanced Defuelling Safety Cases | Produce draft NSRS (using BARRIER MODEL) | 11-Jun-24 A | 11-Jun-24 | 14-Jun-24 A | 14-Jun-24 | 4 | 0 | 4 | 100% |  | Completed
ER6372LT | W203 | W203.C1120 | HNB Enhanced Defuelling Safety Cases | Categorisation by RE / Station | 11-Jun-24 A | 11-Jun-24 | 12-Jun-24 A | 12-Jun-24 | 2 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.29700 | HYB Essential Defueling Safety Case | Issue on CDMS - (Failed Fuel Handling in ODR condition) | 12-Jun-24 A | 12-Jun-24 | 12-Jun-24 A | 12-Jun-24 | 5 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W209.29700 | TOR Essential Defueling Safety Case | Issue on CDMS - (Failed Fuel Handling in ODR condition) | 12-Jun-24 A | 12-Jun-24 | 12-Jun-24 A | 12-Jun-24 | 5 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224. A1050 | HRA Enhanced Defueling Safety Case | Gate A PRC Paper Submission | 12-Jun-24 A | 12-Jun-24 | 12-Jun-24 A | 12-Jun-24 | 0 | 0 | 0 | 100% |  | Completed
ER6701LT | W228 | W228. A1050 | HYA Enhanced Defueling Safety Case | Gate A PRC Paper Submission | 12-Jun-24 A | 12-Jun-24 | 12-Jun-24 A | 12-Jun-24 | 0 | 0 | 0 | 100% |  | Completed
W230LT | W230 | W230.1340 | HYB Enhanced Defueling Safety Case Strategy | Gate A PRC Paper Submission | 12-Jun-24 A | 12-Jun-24 | 12-Jun-24 A | 12-Jun-24 | 1 | 0 | 1 | 100% |  | Completed
W234LT | W234 | W234.1340 | TOR Enhanced Defueling Safety Case Strategy | Gate A PRC Paper Submission | 12-Jun-24 A | 12-Jun-24 | 12-Jun-24 A | 12-Jun-24 | 1 | 0 | 1 | 100% |  | Completed
W230LT | W230 | W230.1360 | HYB Enhanced Defueling Safety Case Strategy | PRC Members Review PRC/IMS2 Documentation | 13-Jun-24 A | 13-Jun-24 | 24-Jun-24 A | 24-Jun-24 | 8 | 0 | 8 | 100% |  | Completed
W234LT | W234 | W234.1360 | TOR Enhanced Defueling Safety Case Strategy | PRC Members Review PRC/IMS2 Documentation | 13-Jun-24 A | 13-Jun-24 | 24-Jun-24 A | 24-Jun-24 | 8 | 0 | 8 | 100% |  | Completed
ER6372LT | W203 | W203.C1200 | HNB Enhanced Defuelling Safety Cases | Station comments on NSRS | 17-Jun-24 A | 17-Jun-24 | 18-Jun-24 A | 18-Jun-24 | 2 | 0 | 2 | 100% |  | Completed
ER6372LT | W203 | W203.C1210 | HNB Enhanced Defuelling Safety Cases | Key Stakeholders (Peer) comments on NSRS (as required) | 17-Jun-24 A | 17-Jun-24 | 18-Jun-24 A | 18-Jun-24 | 2 | 0 | 2 | 100% |  | Completed
ER6372LT | W203 | W203.C1250 | HNB Enhanced Defuelling Safety Cases | Develop plan with further iterations | 17-Jun-24 A | 17-Jun-24 | 26-Jun-24 A | 26-Jun-24 | 10 | 0 | 7 | 100% |  | Completed
W230LT | W230 | W230.1980 | HYB Enhanced Defueling Safety Case Strategy | Issued to EDF for Technical Reviews | 17-Jun-24 A | 17-Jun-24 | 17-Jun-24 A | 17-Jun-24 | 0 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.1980 | TOR Enhanced Defueling Safety Case Strategy | Issued to EDF for Technical Reviews | 17-Jun-24 A | 17-Jun-24 | 17-Jun-24 A | 17-Jun-24 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A31300 | HYB Essential Defueling Safety Case | Supplier Update and Issue PSA Documentation | 18-Jun-24 A | 18-Jun-24 | 24-Jun-24 A | 24-Jun-24 | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A31300 | TOR Essential Defueling Safety Case | Supplier Update and Issue PSA Documentation | 18-Jun-24 A | 18-Jun-24 | 24-Jun-24 A | 24-Jun-24 | 5 | 0 | 5 | 100% |  | Completed
W230LT | W230 | W230.1990 | HYB Enhanced Defueling Safety Case Strategy | Tech Review by EDF SQEP | 18-Jun-24 A | 18-Jun-24 | 28-Jun-24 A | 28-Jun-24 | 9 | 0 | 9 | 100% |  | Completed
W234LT | W234 | W234.1990 | TOR Enhanced Defueling Safety Case Strategy | Tech Review by EDF SQEP | 18-Jun-24 A | 18-Jun-24 | 28-Jun-24 A | 28-Jun-24 | 9 | 0 | 9 | 100% |  | Completed
ER6372LT | W203 | W203.C1230 | HNB Enhanced Defuelling Safety Cases | INSA Resource Identified | 18-Jun-24 A | 18-Jun-24 | 18-Jun-24 A | 18-Jun-24 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1150 | HNB Enhanced Defuelling Safety Cases | INSA agree MF (as required) *(EC375412)* | 20-Jun-24 A | 20-Jun-24 | 20-Jun-24 A | 20-Jun-24 | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.C1180 | HNB Enhanced Defuelling Safety Cases | INSA Approval Date Identified | 20-Jun-24 A | 20-Jun-24 | 20-Jun-24 A | 20-Jun-24 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1190 | HNB Enhanced Defuelling Safety Cases | Provide Provisional NSC Date (as required) | 20-Jun-24 A | 20-Jun-24 | 20-Jun-24 A | 20-Jun-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1170 | DNB Enhanced Safety Cases | <Review of Weld Inspection Data> - Issue Draft EAN to EDF for Review. | 21-Jun-24 A | 21-Jun-24 | 21-Jun-24 A | 21-Jun-24 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1240 | HNB Enhanced Defuelling Safety Cases | INA comments on NSRS | 24-Jun-24 A | 24-Jun-24 | 28-Jun-24 A | 28-Jun-24 | 5 | 0 | 5 | 100% |  | Completed
ER6698LT | W224 | W224.1010 | HRA Enhanced Defueling Safety Case | Sunk Cost (Mar - Dec 24) | 24-Jun-24 A | 24-Jun-24 | 31-Dec-24 A | 31-Dec-24 | 1 | 0 | 133 | 100% |  | Completed
ER6698LT | W224 | W224.A1010 | HRA Enhanced Defueling Safety Case | Gate A for Defuelling Programme Enhancement ECs (HH1) | 25-Jun-24 A | 25-Jun-24 | 25-Jun-24 A | 25-Jun-24 | 0 | 0 | 0 | 100% |  | Completed
ER6701LT | W228 | W228.A1010 | HYA Enhanced Defueling Safety Case | Gate A for Defuelling Programme Enhancement ECs (HH1) | 25-Jun-24 A | 25-Jun-24 | 25-Jun-24 A | 25-Jun-24 | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.A1061 | HRA Enhanced Defueling Safety Case | Hold PRC | 25-Jun-24 A | 25-Jun-24 | 25-Jun-24 A | 25-Jun-24 | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A31310 | HYB Essential Defueling Safety Case | Complete TR Form and PSA Documentation to CDMS | 25-Jun-24 A | 25-Jun-24 | 31-Jul-24 A | 31-Jul-24 | 10 | 0 | 27 | 100% |  | Completed
ER6668LT | W213 | W213.A31310 | TOR Essential Defueling Safety Case | Complete TR Form and PSA Documentation to CDMS | 25-Jun-24 A | 25-Jun-24 | 31-Jul-24 A | 31-Jul-24 | 10 | 0 | 27 | 100% |  | Completed
ER6701LT | W228 | W228.A1061 | HYA Enhanced Defueling Safety Case | Hold PRC | 25-Jun-24 A | 25-Jun-24 | 25-Jun-24 A | 25-Jun-24 | 1 | 0 | 1 | 100% |  | Completed
W230LT | W230 | W230.1390 | HYB Enhanced Defueling Safety Case Strategy | Hold PRC Meeting | 25-Jun-24 A | 25-Jun-24 | 25-Jun-24 A | 25-Jun-24 | 1 | 0 | 1 | 100% |  | Completed
W234LT | W234 | W234.1390 | TOR Enhanced Defueling Safety Case Strategy | Hold PRC Meeting | 25-Jun-24 A | 25-Jun-24 | 25-Jun-24 A | 25-Jun-24 | 1 | 0 | 1 | 100% |  | Completed
ER6698LT | W224 | W224. A1070 | HRA Enhanced Defueling Safety Case | Gate A PRC Paper Approval | 25-Jun-24 A | 25-Jun-24 | 25-Jun-24 A | 25-Jun-24 | 0 | 0 | 0 | 100% |  | Completed
ER6701LT | W228 | W228. A1070 | HYA Enhanced Defueling Safety Case | Gate A PRC Paper Approval | 25-Jun-24 A | 25-Jun-24 | 25-Jun-24 A | 25-Jun-24 | 0 | 0 | 0 | 100% |  | Completed
W230LT | W230 | W230.1120 | HYB Enhanced Defueling Safety Case Strategy | Gate A Approved | 25-Jun-24 A | 25-Jun-24 | 25-Jun-24 A | 25-Jun-24 | 0 | 0 | 0 | 100% |  | Completed
W230LT | W230 | W230.1350 | HYB Enhanced Defueling Safety Case Strategy | Gate A PRC Paper Approval | 25-Jun-24 A | 25-Jun-24 | 25-Jun-24 A | 25-Jun-24 | 0 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.1120 | TOR Enhanced Defueling Safety Case Strategy | Gate A Approved | 25-Jun-24 A | 25-Jun-24 | 25-Jun-24 A | 25-Jun-24 | 0 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.1350 | TOR Enhanced Defueling Safety Case Strategy | Gate A PRC Paper Approval | 25-Jun-24 A | 25-Jun-24 | 25-Jun-24 A | 25-Jun-24 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1330 | HNB Enhanced Defuelling Safety Cases | Verifier PJB Held | 26-Jun-24 A | 26-Jun-24 | 26-Jun-24 A | 26-Jun-24 | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.A1160 | HRA Enhanced Defueling Safety Case | Gate A-B Programme Management External - Cost Summary | 26-Jun-24 A | 26-Jun-24 | 12-Feb-25 A | 12-Feb-25 | 127 | 0 | 162 | 100% |  | Completed
ER6698LT | W224 | W224.A1170 | HRA Enhanced Defueling Safety Case | Gate A-B Programme Management Internal - Cost Summary | 26-Jun-24 A | 26-Jun-24 | 12-Feb-25 A | 12-Feb-25 | 0 | 0 | 162 | 100% |  | Completed
ER6698LT | W224 | W224. A1080 | HRA Enhanced Defueling Safety Case | Funds Released | 26-Jun-24 A | 26-Jun-24 | 10-Jul-24 A | 10-Jul-24 | 12 | 0 | 11 | 100% |  | Completed
ER6701LT | W228 | W228. A1080 | HYA Enhanced Defueling Safety Case | Funds Released | 26-Jun-24 A | 26-Jun-24 | 09-Jul-24 A | 09-Jul-24 | 12 | 0 | 10 | 100% |  | Completed
ER6701LT | W228 | W228.A1170 | HYA Enhanced Defueling Safety Case | Gate A-B Programme Management Internal - Cost Summary | 26-Jun-24 A | 26-Jun-24 | 12-Feb-25 A | 12-Feb-25 | 0 | 0 | 162 | 100% |  | Completed
ER6701LT | W228 | W228.A1160 | HYA Enhanced Defueling Safety Case | Gate A-B Programme Management External - Cost Summary | 26-Jun-24 A | 26-Jun-24 | 12-Feb-25 A | 12-Feb-25 | 127 | 0 | 162 | 100% |  | Completed
W230LT | W230 | W230.1380 | HYB Enhanced Defueling Safety Case Strategy | Modify Estimate, Schedule & Risk Log as Required | 26-Jun-24 A | 26-Jun-24 | 28-Jun-24 A | 28-Jun-24 | 3 | 0 | 3 | 100% |  | Completed
W234LT | W234 | W234.1380 | TOR Enhanced Defueling Safety Case Strategy | Modify Estimate, Schedule & Risk Log as Required | 26-Jun-24 A | 26-Jun-24 | 28-Jun-24 A | 28-Jun-24 | 3 | 0 | 3 | 100% |  | Completed
W230LT | W230 | W230.1370 | HYB Enhanced Defueling Safety Case Strategy | Modify PRC Paper as Required | 27-Jun-24 A | 27-Jun-24 | 28-Jun-24 A | 28-Jun-24 | 2 | 0 | 2 | 100% |  | Completed
W234LT | W234 | W234.1370 | TOR Enhanced Defueling Safety Case Strategy | Modify PRC Paper as Required | 27-Jun-24 A | 27-Jun-24 | 28-Jun-24 A | 28-Jun-24 | 2 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.A29160 | HYB Essential Defueling Safety Case | Verify Defuelling Worker Risk Assessment EAN & Issue for Technical Review | 28-Jun-24 A | 28-Jun-24 | 26-Jul-24 A | 26-Jul-24 | 5 | 0 | 21 | 100% |  | Completed
ER6668LT | W213 | W213.A29160 | TOR Essential Defueling Safety Case | Verify Defuelling Worker Risk Assessment EAN & Issue for Technical Review | 28-Jun-24 A | 28-Jun-24 | 26-Jul-24 A | 26-Jul-24 | 5 | 0 | 21 | 100% |  | Completed
ER6372LT | W203 | W203.C1280 | HNB Enhanced Defuelling Safety Cases | Issue final NSRS | 28-Jun-24 A | 28-Jun-24 | 28-Jun-24 A | 28-Jun-24 | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.C1290 | HNB Enhanced Defuelling Safety Cases | Station agree NSRS *(EC375412)* | 28-Jun-24 A | 28-Jun-24 | 28-Jun-24 A | 28-Jun-24 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1340 | HNB Enhanced Defuelling Safety Cases | Consolidate & issue to stakeholders & suppliers agreed NSRS (as required) | 28-Jun-24 A | 28-Jun-24 | 28-Jun-24 A | 28-Jun-24 | 1 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1260 | HNB Enhanced Defuelling Safety Cases | Incorporate INA, Station, ED (peer) comments | 28-Jun-24 A | 28-Jun-24 | 28-Jun-24 A | 28-Jun-24 | 2 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.C1300 | HNB Enhanced Defuelling Safety Cases | Key Stakeholders agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 28-Jun-24 A | 28-Jun-24 | 28-Jun-24 A | 28-Jun-24 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1350 | HNB Enhanced Defuelling Safety Cases | Issue agreed work programme to stakeholders & suppliers | 28-Jun-24 A | 28-Jun-24 | 28-Jun-24 A | 28-Jun-24 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1320 | HNB Enhanced Defuelling Safety Cases | INA agree NSRS | 28-Jun-24 A | 28-Jun-24 | 28-Jun-24 A | 28-Jun-24 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A4190 | HNB Enhanced Defuelling Safety Cases | All key supporting technical references complete - Enhanced Defueling rate EC | 28-Jun-24 A | 28-Jun-24 | 28-Jun-24 A | 28-Jun-24 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1360 | HNB Enhanced Defuelling Safety Cases | Supporting reference <Enhanced Defueling rate EC> approved | 28-Jun-24 A | 28-Jun-24 | 28-Jun-24 A | 28-Jun-24 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1370 | HNB Enhanced Defuelling Safety Cases | All supporting references completed | 28-Jun-24 A | 28-Jun-24 | 28-Jun-24 A | 28-Jun-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1330 | DNB Enhanced Safety Cases | <Review of Lifting Integrity Faults> - Draft EAN Reviewed by EDF SQEP | 01-Jul-24 A | 01-Jul-24 | 09-Aug-24 A | 09-ug-24 | 10 | 0 | 30 | 100% |  | Completed
ER6650LT | W226 | 2072 | HYA Fuel Handling Essential Safety Case | Respond to First Round Comments | 01-Jul-24 A | 01-Jul-24 | 08-Jul-24 A | 08-Jul-24 | 6 | 0 | 6 | 100% |  | Completed
W232LT | W232 | W232.A3050 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 2164> Rev 000 - ONR Approval of Safety Case (Letter sent to initiate) EC 374183 KDM | 01-Jul-24 A | 01-Jul-24 | 01-Jul-24 A | 01-Jul-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A3060 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 2164> Rev 000 - KDM - ONR Agree/Acknowledge Safety Case EC 374183 KDM | 01-Jul-24 A | 01-Jul-24 | 01-Jul-24 A | 01-Jul-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5550 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 2164> Rev 001 - ONR Approval of Safety Case (Letter sent to initiate) EC 374183 KDM | 01-Jul-24 A | 01-Jul-24 | 01-Jul-24 A | 01-Jul-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5560 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 2164> Rev 001 - KDM - ONR Agree/Acknowledge Safety Case EC 374183 KDM | 01-Jul-24 A | 01-Jul-24 | 01-Jul-24 A | 01-Jul-24 | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.1410 | HRA Enhanced Defueling Safety Case | Contract Award | 01-Jul-24 A | 01-Jul-24 | 12-Jul-24 A | 12-Jul-24 | 10 | 0 | 10 | 100% |  | Completed
ER6701LT | W228 | W228.1410 | HYA Enhanced Defueling Safety Case | Contract Award | 01-Jul-24 A | 01-Jul-24 | 12-Jul-24 A | 12-Jul-24 | 10 | 0 | 10 | 100% |  | Completed
W772LT | W772 | W772LT.A1260 | DNB Pull Harder Safety Case | Mod Requested, Identify RE and EC Request Raised and Screened | 01-Jul-24 A | 01-Jul-24 | 25-Jul-24 A | 25-Jul-24 | 19 | 0 | 19 | 100% |  | Completed
W772LT | W772 | W772LT.A2200 | DNB Pull Harder Safety Case | Project Start | 01-Jul-24 A | 01-Jul-24 | 01-Jul-24 A | 01-Jul-24 | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.D2080 | DNB Pull Harder Safety Case | Project Management - Pre Gate A | 01-Jul-24 A | 01-Jul-24 | 04-Oct-24 A | 04-Oct-24 | 104 | 0 | 68 | 100% |  | Completed
W772LT | W772 | W772LT.D2110 | DNB Pull Harder Safety Case | Technical Support - Pre Gate A | 01-Jul-24 A | 01-Jul-24 | 04-Oct-24 A | 04-Oct-24 | 104 | 0 | 68 | 100% |  | Completed
ER6698LT | W224 | W224.1280 | HRA Enhanced Defueling Safety Case | EDF Review and contract awards | 03-Jul-24 A | 03-Jul-24 | 26-Jul-24 A | 26-Jul-24 | 15 | 0 | 18 | 100% |  | Completed
ER6701LT | W228 | W228.1280 | HYA Enhanced Defueling Safety Case | EDF Review and contract awards | 03-Jul-24 A | 03-Jul-24 | 26-Jul-24 A | 26-Jul-24 | 1 | 0 | 18 | 100% |  | Completed
ER6701LT | W228 | W228.3740 | HYA Enhanced Defueling Safety Case | EC Register | 05-Jul-24 A | 05-Jul-24 | 19-Jul-24 A | 19-Jul-24 | 10 | 0 | 11 | 100% |  | Completed
ER6698LT | W224 | W224.3740 | HRA Enhanced Defueling Safety Case | EC Register | 05-Jul-24 A | 05-Jul-24 | 15-Jul-24 A | 15-Jul-24 | 10 | 0 | 5 | 100% |  | Completed
ER6372LT | W203 | W203.C1400 | HNB Enhanced Defuelling Safety Cases | Issue to CO & Station for comments | 05-Jul-24 A | 05-Jul-24 | 05-Jul-24 A | 05-Jul-24 | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.1190 | HRA Enhanced Defueling Safety Case | RFS - Trip Function | 08-Jul-24 A | 08-Jul-24 | 09-Aug-24 A | 09-ug-24 | 10 | 0 | 25 | 100% |  | Completed
ER6701LT | W228 | W228.1190 | HYA Enhanced Defueling Safety Case | RFS - Trip Function | 08-Jul-24 A | 08-Jul-24 | 09-Aug-24 A | 09-ug-24 | 10 | 0 | 25 | 100% |  | Completed
ER6372LT | W203 | W203.D1390 | HNB Enhanced Defuelling Safety Cases | Mod requested, Initiate EC, identify RE, register EC & identify milestones in AMS | 08-Jul-24 A | 08-Jul-24 | 08-Jul-24 A | 08-Jul-24 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1470 | HNB Enhanced Defuelling Safety Cases | Raise Engineering Request (as required) | 08-Jul-24 A | 08-Jul-24 | 15-Jul-24 A | 15-Jul-24 | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | 2075 | HYA Fuel Handling Essential Safety Case | Station Verifiers (HHB OPEX) Second Round | 08-Jul-24 A | 08-Jul-24 | 16-Jul-24 A | 16-Jul-24 | 7 | 0 | 7 | 100% |  | Completed
ER6650LT | W226 | 2076 | HYA Fuel Handling Essential Safety Case | Lead Verifier Second Round | 08-Jul-24 A | 08-Jul-24 | 16-Jul-24 A | 16-Jul-24 | 7 | 0 | 7 | 100% |  | Completed
ER6650LT | W226 | 2074 | HYA Fuel Handling Essential Safety Case | Sub-verifier(s) including GAP review (HHB OPEX) Second Round | 08-Jul-24 A | 08-Jul-24 | 16-Jul-24 A | 16-Jul-24 | 7 | 0 | 7 | 100% |  | Completed
ER6650LT | W226 | 2073 | HYA Fuel Handling Essential Safety Case | Sub-verifier(s) including GAP review (HHB OPEX) Second Round | 08-Jul-24 A | 08-Jul-24 | 16-Jul-24 A | 16-Jul-24 | 10 | 0 | 7 | 100% |  | Completed
ER6650LT | W226 | 2082 | HYA Fuel Handling Essential Safety Case | CTO Civils, Nuclear Liabilities, Environmental (GEM), Specialist Assessment(s) | 08-Jul-24 A | 08-Jul-24 | 16-Jul-24 A | 16-Jul-24 | 7 | 0 | 7 | 100% |  | Completed
ER6650LT | W226 | 2081 | HYA Fuel Handling Essential Safety Case | HYA Nuclear Safety, Env, Rad Protection, Radwaste, Ops, Emergency Arrangements, Specialist Assessment(s) | 08-Jul-24 A | 08-Jul-24 | 16-Jul-24 A | 16-Jul-24 | 7 | 0 | 7 | 100% |  | Completed
ER6650LT | W226 | 2080 | HYA Fuel Handling Essential Safety Case | HRA Nuclear Safety, Env, Rad Protection, Radwaste, Ops, Emergency Arrangements,Chemistry,Specialist Assessment(s) | 08-Jul-24 A | 08-Jul-24 | 16-Jul-24 A | 16-Jul-24 | 7 | 0 | 7 | 100% |  | Completed
ER6378LT | W222 | 2075 | HRA Fuel Handling Essential Safety Case | Station Verifiers (HHB OPEX) Second Round | 09-Jul-24 A | 09-Jul-24 | 16-Jul-24 A | 16-Jul-24 | 10 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | 2076 | HRA Fuel Handling Essential Safety Case | Lead Verifier Second Round | 09-Jul-24 A | 09-Jul-24 | 16-Jul-24 A | 16-Jul-24 | 10 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | 2074 | HRA Fuel Handling Essential Safety Case | Sub-verifier(s) including GAP review (HHB OPEX) Second Round | 09-Jul-24 A | 09-Jul-24 | 16-Jul-24 A | 16-Jul-24 | 10 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | 2073 | HRA Fuel Handling Essential Safety Case | Sub-verifier(s) including GAP review (HHB OPEX) Second Round | 09-Jul-24 A | 09-Jul-24 | 16-Jul-24 A | 16-Jul-24 | 10 | 0 | 6 | 100% |  | Completed
ER6378LT | W222 | 2082 | HRA Fuel Handling Essential Safety Case | CTO Civils, Nuclear Liabilities, Environmental (GEM), Specialist Assessment(s) | 09-Jul-24 A | 09-Jul-24 | 16-Jul-24 A | 16-Jul-24 | 10 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | 2081 | HRA Fuel Handling Essential Safety Case | HYA Nuclear Safety, Env, Rad Protection, Radwaste, Ops, Emergency Arrangements, Specialist Assessment(s) | 09-Jul-24 A | 09-Jul-24 | 16-Jul-24 A | 16-Jul-24 | 10 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | 2080 | HRA Fuel Handling Essential Safety Case | HRA Nuclear Safety, Env, Rad Protection, Radwaste, Ops, Emergency Arrangements,Chemistry,Specialist Assessment(s) | 09-Jul-24 A | 09-Jul-24 | 16-Jul-24 A | 16-Jul-24 | 10 | 0 | 5 | 100% |  | Completed
W230LT | W230 | W230.3710 | HYB Enhanced Defueling Safety Case Strategy | Tech Review by EDF SQEP (Continued) | 12-Jul-24 A | 12-Jul-24 | 18-Jul-24 A | 18-Jul-24 | 5 | 0 | 5 | 100% |  | Completed
W230LT | W230 | W230.3720 | HYB Enhanced Defueling Safety Case Strategy | ## Technical Development / Project Management - Gate A - D - (Cost Summary) ## | 12-Jul-24 A | 12-Jul-24 | 20-Dec-24 A | 20-Dec-24 | 115 | 0 | 115 | 100% |  | Completed
W234LT | W234 | W234.3710 | TOR Enhanced Defueling Safety Case Strategy | Tech Review by EDF SQEP (Continued) | 12-Jul-24 A | 12-Jul-24 | 18-Jul-24 A | 18-Jul-24 | 5 | 0 | 5 | 100% |  | Completed
W234LT | W234 | W234.3720 | TOR Enhanced Defueling Safety Case Strategy | ## Technical Development / Project Management - Gate A - D - (Cost Summary) ## | 12-Jul-24 A | 12-Jul-24 | 20-Dec-24 A | 20-Dec-24 | 115 | 0 | 115 | 100% |  | Completed
ER6372LT | W203 | W203.D1680 | HNB Enhanced Defuelling Safety Cases | CO & CA appointed | 15-Jul-24 A | 15-Jul-24 | 15-Jul-24 A | 15-Jul-24 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1690 | HNB Enhanced Defuelling Safety Cases | Key Stakeholders Identified | 15-Jul-24 A | 15-Jul-24 | 15-Jul-24 A | 15-Jul-24 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 2150 | HYA Fuel Handling Essential Safety Case | PJB with INA | 15-Jul-24 A | 15-Jul-24 | 15-Jul-24 A | 15-Jul-24 | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 2140 | HYA Fuel Handling Essential Safety Case | Re-attach to ADL | 15-Jul-24 A | 15-Jul-24 | 16-Jul-24 A | 16-Jul-24 | 2 | 0 | 2 | 100% |  | Completed
ER6698LT | W224 | W224.1260 | HRA Enhanced Defueling Safety Case | PJB | 15-Jul-24 A | 15-Jul-24 | 19-Jul-24 A | 19-Jul-24 | 5 | 0 | 5 | 100% |  | Completed
ER6701LT | W228 | W228.1260 | HYA Enhanced Defueling Safety Case | PJB | 15-Jul-24 A | 15-Jul-24 | 19-Jul-24 A | 19-Jul-24 | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A4720 | HRA Fuel Handling Essential Safety Case | Issue to CO & Station for comments | 16-Jul-24 A | 16-Jul-24 | 16-Jul-24 A | 16-Jul-24 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A29170 | HYB Essential Defueling Safety Case | Technical Review of Defuelling Worker Risk Assessment EAN | 16-Jul-24 A | 16-Jul-24 | 31-Jul-24 A | 31-Jul-24 | 0 | 0 | 12 | 100% |  | Completed
ER6668LT | W213 | W213.A29170 | TOR Essential Defueling Safety Case | Technical Review of Defuelling Worker Risk Assessment EAN | 16-Jul-24 A | 16-Jul-24 | 31-Jul-24 A | 31-Jul-24 | 10 | 0 | 12 | 100% |  | Completed
ER6372LT | W203 | W203.D1460 | HNB Enhanced Defuelling Safety Cases | Develop initial programme plan using mandatory template | 16-Jul-24 A | 16-Jul-24 | 22-Jul-24 A | 22-Jul-24 | 5 | 0 | 4 | 100% |  | Completed
ER6698LT | W224 | W224.3720 | HRA Enhanced Defueling Safety Case | NSRS | 16-Jul-24 A | 16-Jul-24 | 29-Jul-24 A | 29-Jul-24 | 49 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | 2170 | HYA Fuel Handling Essential Safety Case | *****INSA****** | 17-Jul-24 A | 17-Jul-24 | 29-Aug-24 A | 29-ug-24 | 30 | 0 | 31 | 100% |  | Completed
ER6378LT | W222 | W222.A4680 | HRA Fuel Handling Essential Safety Case | Incorporate all stakeholder comments and Final Sign Off | 17-Jul-24 A | 17-Jul-24 | 17-Jul-24 A | 17-Jul-24 | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A4740 | HRA Fuel Handling Essential Safety Case | Final Verification - Statement Issued | 17-Jul-24 A | 17-Jul-24 | 17-Jul-24 A | 17-Jul-24 | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A4970 | HRA Fuel Handling Essential Safety Case | INSA review & iteration of comments (using BARRIER MODEL) | 17-Jul-24 A | 17-Jul-24 | 27-Aug-24 A | 27-ug-24 | 25 | 0 | 28 | 100% |  | Completed
ER6378LT | W222 | W222.A4990 | HRA Fuel Handling Essential Safety Case | DA (Authorised Designer) Approval of CAT1 Safety Case | 17-Jul-24 A | 17-Jul-24 | 23-Jul-24 A | 23-Jul-24 | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A4740 | HYA Fuel Handling Essential Safety Case | Final Verification | 17-Jul-24 A | 17-Jul-24 | 17-Jul-24 A | 17-Jul-24 | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A4680 | HYA Fuel Handling Essential Safety Case | Incorporate all stakeholder comments and Final Sign Off | 17-Jul-24 A | 17-Jul-24 | 17-Jul-24 A | 17-Jul-24 | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.1130 | HRA Fuel Handling Essential Safety Case | Safety Case Development Costs - INSA Phase (C to D ) ##Cost Summary## | 17-Jul-24 A | 17-Jul-24 | 18-Sep-24 A | 18-Sep-24 | 65 | 0 | 45 | 100% |  | Completed
ER6378LT | W222 | W222.1140 | HRA Fuel Handling Essential Safety Case | Project Management Costs - INSA Phase (C to D ) ##Cost Summary## | 17-Jul-24 A | 17-Jul-24 | 18-Sep-24 A | 18-Sep-24 | 65 | 0 | 45 | 100% |  | Completed
ER6650LT | W226 | 2100 | HYA Fuel Handling Essential Safety Case | CO Endorsed | 17-Jul-24 A | 17-Jul-24 | 17-Jul-24 A | 17-Jul-24 | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 2110 | HYA Fuel Handling Essential Safety Case | Stn RE Endorsed | 17-Jul-24 A | 17-Jul-24 | 17-Jul-24 A | 17-Jul-24 | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A4710 | HRA Fuel Handling Essential Safety Case | Submit for approval - Categoriser ratifies; RE/CO endorsement | 17-Jul-24 A | 17-Jul-24 | 17-Jul-24 A | 17-Jul-24 | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A4960 | HRA Fuel Handling Essential Safety Case | Verified Draft Available for INSA (T-7) ECs(HRA-363840) - HRA Defuelling Fuel Handling Essential SC | 17-Jul-24 A | 17-Jul-24 | 17-Jul-24 A | 17-Jul-24 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A4960 | HYA Fuel Handling Essential Safety Case | Verified Draft Available for INSA (T-7) ECs(HYA-363839) - HYA Defuelling Fuel Handling Essential SC | 17-Jul-24 A | 17-Jul-24 | 17-Jul-24 A | 17-Jul-24 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A4720 | HYA Fuel Handling Essential Safety Case | Issue to CO & Station for comments | 17-Jul-24 A | 17-Jul-24 | 17-Jul-24 A | 17-Jul-24 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A4710 | HYA Fuel Handling Essential Safety Case | Submit for approval - Categoriser ratifies; RE/CO endorsement | 17-Jul-24 A | 17-Jul-24 | 17-Jul-24 A | 17-Jul-24 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A4990 | HYA Fuel Handling Essential Safety Case | DA (Authorised Designer) Approval of CAT1 Safety Case | 18-Jul-24 A | 18-Jul-24 | 24-Jul-24 A | 24-Jul-24 | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A4970 | HYA Fuel Handling Essential Safety Case | INSA review & iteration of comments (using BARRIER MODEL) | 18-Jul-24 A | 18-Jul-24 | 29-Aug-24 A | 29-ug-24 | 25 | 0 | 30 | 100% |  | Completed
ER6650LT | W226 | W226.1130 | HYA Fuel Handling Essential Safety Case | Safety Case Development Costs - INSA Phase (C to D ) ##Cost Summary## | 18-Jul-24 A | 18-Jul-24 | 18-Sep-24 A | 18-Sep-24 | 64 | 0 | 44 | 100% |  | Completed
ER6650LT | W226 | W226.1140 | HYA Fuel Handling Essential Safety Case | Project Management Costs - INSA Phase (C to D ) ##Cost Summary## | 18-Jul-24 A | 18-Jul-24 | 18-Sep-24 A | 18-Sep-24 | 64 | 0 | 44 | 100% |  | Completed
ER6378LT | W222 | 1971 | HRA Fuel Handling Essential Safety Case | Issue Head Document onto CDMS | 18-Jul-24 A | 18-Jul-24 | 19-Jul-24 A | 19-Jul-24 | 2 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | 1971 | HYA Fuel Handling Essential Safety Case | Issue Head Document onto CDMS | 18-Jul-24 A | 18-Jul-24 | 19-Jul-24 A | 19-Jul-24 | 2 | 0 | 2 | 100% |  | Completed
W230LT | W230 | W230.2000 | HYB Enhanced Defueling Safety Case Strategy | TSA Addressess Comments | 19-Jul-24 A | 19-Jul-24 | 26-Nov-24 A | 26-Nov-24 | 10 | 0 | 92 | 100% |  | Completed
W772LT | W772 | W772LT.A1200 | DNB Pull Harder Safety Case | Initiate and Register EC and identify Milestones in AMS EC 375698<DNB Pull Harder SC> | 19-Jul-24 A | 19-Jul-24 | 26-Jul-24 A | 26-Jul-24 | 5 | 0 | 5 | 100% |  | Completed
W234LT | W234 | W234.2000 | TOR Enhanced Defueling Safety Case Strategy | TSA Addressess Comments | 19-Jul-24 A | 19-Jul-24 | 26-Nov-24 A | 26-Nov-24 | 10 | 0 | 92 | 100% |  | Completed
ER6701LT | W228 | W228.3720 | HYA Enhanced Defueling Safety Case | NSRS | 19-Jul-24 A | 19-Jul-24 | 02-Aug-24 A | 02-ug-24 | 21 | 0 | 10 | 100% |  | Completed
ER6372LT | W203 | W203.D1710 | HNB Enhanced Defuelling Safety Cases | CA PJB Held | 22-Jul-24 A | 22-Jul-24 | 22-Jul-24 A | 22-Jul-24 | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.1270 | HRA Enhanced Defueling Safety Case | Information Gathering | 22-Jul-24 A | 22-Jul-24 | 06-Sep-24 A | 06-Sep-24 | 29 | 0 | 34 | 100% |  | Completed
ER6701LT | W228 | W228.1270 | HYA Enhanced Defueling Safety Case | Information Gathering | 22-Jul-24 A | 22-Jul-24 | 06-Sep-24 A | 06-Sep-24 | 29 | 0 | 34 | 100% |  | Completed
ER6372LT | W203 | W203.D1280 | HNB Enhanced Defuelling Safety Cases | Agree resource & timescales with suppliers for delivering key refs, incl contingency, risk & allowance for rework | 22-Jul-24 A | 22-Jul-24 | 26-Jul-24 A | 26-Jul-24 | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A24350 | HRA Fuel Handling Essential Safety Case | Living Safety Document EAN Available | 22-Jul-24 A | 22-Jul-24 | 22-Jul-24 A | 22-Jul-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1180 | DNB Enhanced Safety Cases | <Review of Weld Inspection Data> - Draft EAN Reviewed by EDF SQEP | 23-Jul-24 A | 23-Jul-24 | 05-Aug-24 A | 05-ug-24 | 10 | 0 | 10 | 100% |  | Completed
ER6701LT | W228 | W228.1520 | HYA Enhanced Defueling Safety Case | Hold PJB | 23-Jul-24 A | 23-Jul-24 | 30-Jul-24 A | 30-Jul-24 | 1 | 0 | 6 | 100% |  | Completed
ER6698LT | W224 | W224.1520 | HRA Enhanced Defueling Safety Case | Hold PJB | 24-Jul-24 A | 24-Jul-24 | 29-Jul-24 A | 29-Jul-24 | 5 | 0 | 4 | 100% |  | Completed
W232LT | W232 | W232.A2110 | DNB Enhanced Safety Cases | Rev 000 - Verification of the case (using BARRIER MODEL) | 25-Jul-24 A | 25-Jul-24 | 08-Oct-24 A | 08-Oct-24 | 30 | 0 | 52 | 100% |  | Completed
W772LT | W772 | W772LT.A1680 | DNB Pull Harder Safety Case | CO and PCE Create Initial Plan of Work ==> KDM | 26-Jul-24 A | 26-Jul-24 | 05-Aug-24 A | 05-ug-24 | 7 | 0 | 7 | 100% |  | Completed
ER6372LT | W203 | W203.D1270 | HNB Enhanced Defuelling Safety Cases | Hold project kick start meeting with Station & key suppliers | 29-Jul-24 A | 29-Jul-24 | 19-Nov-24 A | 19-Nov-24 | 5 | 0 | 80 | 100% |  | Completed
ER6701LT | W228 | W228.1590 | HYA Enhanced Defueling Safety Case | Analysis | 30-Jul-24 A | 30-Jul-24 | 30-Aug-24 A | 30-ug-24 | 1 | 0 | 23 | 100% |  | Completed
ER6698LT | W224 | W224.1590 | HRA Enhanced Defueling Safety Case | Analysis | 30-Jul-24 A | 30-Jul-24 | 30-Aug-24 A | 30-ug-24 | 15 | 0 | 23 | 100% |  | Completed
ER6666LT | W209 | W209.A29180 | HYB Essential Defueling Safety Case | Supplier Update and Issue Defuelling Worker Risk Assessment EAN | 31-Jul-24 A | 31-Jul-24 | 07-Aug-24 A | 07-ug-24 | 5 | 0 | 6 | 100% |  | Completed
ER6666LT | W209 | W209.A29190 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Defuelling Worker Risk Assessment EAN to CDMS | 31-Jul-24 A | 31-Jul-24 | 09-Aug-24 A | 09-ug-24 | 4 | 0 | 8 | 100% |  | Completed
ER6668LT | W213 | W213.A29180 | TOR Essential Defueling Safety Case | Supplier Update and Issue Defuelling Worker Risk Assessment EAN | 31-Jul-24 A | 31-Jul-24 | 07-Aug-24 A | 07-ug-24 | 5 | 0 | 6 | 100% |  | Completed
ER6668LT | W213 | W213.A29190 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Defuelling Worker Risk Assessment EAN to CDMS | 31-Jul-24 A | 31-Jul-24 | 09-Aug-24 A | 09-ug-24 | 5 | 0 | 8 | 100% |  | Completed
ER6666LT | W209 | W209.A31320 | HYB Essential Defueling Safety Case | PSA Documentation Available | 31-Jul-24 A | 31-Jul-24 | 31-Jul-24 A | 31-Jul-24 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A31320 | TOR Essential Defueling Safety Case | PSA Documentation Available | 31-Jul-24 A | 31-Jul-24 | 31-Jul-24 A | 31-Jul-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1320 | DNB Enhanced Safety Cases | <Review of Lifting Integrity Faults> - Issue Draft EAN to EDF for Review. | 01-Aug-24 A | 01-ug-24 | 01-Aug-24 A | 01-ug-24 | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.2510 | HRA Enhanced Defueling Safety Case | RFS Load Trace TSA Support | 01-Aug-24 A | 01-ug-24 | 14-Aug-24 A | 14-ug-24 | 10 | 0 | 10 | 100% |  | Completed
ER6701LT | W228 | W228.2510 | HYA Enhanced Defueling Safety Case | RFS Load Trace TSA Support | 01-Aug-24 A | 01-ug-24 | 14-Aug-24 A | 14-ug-24 | 10 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.C1190 | DNB Enhanced Safety Cases | <Review of Weld Inspection Data> - Address Comments from EDF Review on Draft EAN | 06-Aug-24 A | 06-ug-24 | 19-Aug-24 A | 19-ug-24 | 10 | 0 | 10 | 100% |  | Completed
W772LT | W772 | W772LT.A1000 | DNB Pull Harder Safety Case | Produce MF EC 375698 <DNB Pull Harder SC> & obtain approval | 06-Aug-24 A | 06-ug-24 | 16-Aug-24 A | 16-ug-24 | 9 | 0 | 9 | 100% |  | Completed
ER6378LT | W222 | W222.1010 | HRA Fuel Handling Essential Safety Case | Discovery Milestone - Confirm INSA Review Period | 06-Aug-24 A | 06-ug-24 | 06-Aug-24 A | 06-ug-24 | 0 | 0 | 0 | 100% |  | Completed
ER6701LT | W228 | W228.3650 | HYA Enhanced Defueling Safety Case | Production/Author CETS | 07-Aug-24 A | 07-ug-24 | 20-Aug-24 A | 20-ug-24 | 35 | 0 | 9 | 100% |  | Completed
ER6701LT | W228 | W228.1300 | HYA Enhanced Defueling Safety Case | EDF Review | 07-Aug-24 A | 07-ug-24 | 09-Sep-24 A | 09-Sep-24 | 23 | 0 | 23 | 100% |  | Completed
ER6698LT | W224 | W224.1300 | HRA Enhanced Defueling Safety Case | EDF Review | 07-Aug-24 A | 07-ug-24 | 09-Sep-24 A | 09-Sep-24 | 23 | 0 | 23 | 100% |  | Completed
ER6698LT | W224 | W224.3650 | HRA Enhanced Defueling Safety Case | Production/Author CETS | 07-Aug-24 A | 07-ug-24 | 20-Aug-24 A | 20-ug-24 | 25 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | W226.1010 | HYA Fuel Handling Essential Safety Case | Discovery Milestone - Confirm INSA Review Period | 07-Aug-24 A | 07-ug-24 | 07-Aug-24 A | 07-ug-24 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1020 | HNB Enhanced Defuelling Safety Cases | Plan Scope in Primavera Level 2 Lifecycle) | 08-Aug-24 A | 08-ug-24 | 14-Aug-24 A | 14-ug-24 | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.C1620 | DNB Enhanced Safety Cases | <SCOPE NAME CHANGE CN 2615><Further Review of Shock Loaded Unit Events (Group 1)> - TSA Internal Review of Draft | 09-Aug-24 A | 09-ug-24 | 22-Aug-24 A | 22-ug-24 | 10 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.A29200 | HYB Essential Defueling Safety Case | Defuelling Worker Risk Assessment EAN Available | 09-Aug-24 A | 09-ug-24 | 09-Aug-24 A | 09-ug-24 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A29200 | TOR Essential Defueling Safety Case | Defuelling Worker Risk Assessment EAN Available | 09-Aug-24 A | 09-ug-24 | 09-Aug-24 A | 09-ug-24 | 0 | 0 | 0 | 100% |  | Completed
ER6701LT | W228 | W228.2150 | HYA Enhanced Defueling Safety Case | Outline Safety Case Strategy - Trip function change | 12-Aug-24 A | 12-ug-24 | 29-Aug-24 A | 29-ug-24 | 10 | 0 | 12 | 100% |  | Completed
ER6701LT | W228 | W228.2140 | HYA Enhanced Defueling Safety Case | Outline Safety Case Strategy - Software based load trace change | 12-Aug-24 A | 12-ug-24 | 29-Aug-24 A | 29-ug-24 | 10 | 0 | 12 | 100% |  | Completed
ER6701LT | W228 | W228.2130 | HYA Enhanced Defueling Safety Case | Outline Safety Case Strategy - Gripping Sleeve/BoB Weight | 12-Aug-24 A | 12-ug-24 | 29-Aug-24 A | 29-ug-24 | 10 | 0 | 12 | 100% |  | Completed
W232LT | W232 | W232.C1340 | DNB Enhanced Safety Cases | <Review of Lifting Integrity Faults> - Address Comments from EDF Review on Draft EAN | 12-Aug-24 A | 12-ug-24 | 23-Aug-24 A | 23-ug-24 | 10 | 0 | 10 | 100% |  | Completed
ER6698LT | W224 | W224.1200 | HRA Enhanced Defueling Safety Case | EDF Review and contract awards | 12-Aug-24 A | 12-ug-24 | 02-Sep-24 A | 02-Sep-24 | 15 | 0 | 15 | 100% |  | Completed
ER6698LT | W224 | W224.2130 | HRA Enhanced Defueling Safety Case | Outline Safety Case Strategy - Gripping Sleeve/BoB Weight | 12-Aug-24 A | 12-ug-24 | 29-Aug-24 A | 29-ug-24 | 10 | 0 | 12 | 100% |  | Completed
ER6698LT | W224 | W224.2140 | HRA Enhanced Defueling Safety Case | Outline Safety Case Strategy - Software based load trace change | 12-Aug-24 A | 12-ug-24 | 29-Aug-24 A | 29-ug-24 | 10 | 0 | 12 | 100% |  | Completed
ER6698LT | W224 | W224.2150 | HRA Enhanced Defueling Safety Case | Outline Safety Case Strategy - Trip function change | 12-Aug-24 A | 12-ug-24 | 29-Aug-24 A | 29-ug-24 | 10 | 0 | 12 | 100% |  | Completed
ER6701LT | W228 | W228.1200 | HYA Enhanced Defueling Safety Case | EDF Review and contract awards | 12-Aug-24 A | 12-ug-24 | 02-Sep-24 A | 02-Sep-24 | 15 | 0 | 15 | 100% |  | Completed
ER6701LT | W228 | W228.3660 | HYA Enhanced Defueling Safety Case | Author | 13-Aug-24 A | 13-ug-24 | 31-Oct-24 A | 31-Oct-24 | 1 | 0 | 56 | 100% |  | Completed
ER6698LT | W224 | W224.3660 | HRA Enhanced Defueling Safety Case | Author | 13-Aug-24 A | 13-ug-24 | 01-Nov-24 A | 01-Nov-24 | 16 | 0 | 57 | 100% |  | Completed
ER6698LT | W224 | W224.2460 | HRA Enhanced Defueling Safety Case | Supplier Return Period | 15-Aug-24 A | 15-ug-24 | 30-Aug-24 A | 30-ug-24 | 10 | 0 | 11 | 100% |  | Completed
ER6701LT | W228 | W228.2460 | HYA Enhanced Defueling Safety Case | Supplier Return Period | 15-Aug-24 A | 15-ug-24 | 30-Aug-24 A | 30-ug-24 | 10 | 0 | 11 | 100% |  | Completed
ER6372LT | W203 | W203.D1030 | HNB Enhanced Defuelling Safety Cases | Estimate Scope +/- 10% Lifecycle | 15-Aug-24 A | 15-ug-24 | 21-Aug-24 A | 21-ug-24 | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | 2205 | HYA Fuel Handling Essential Safety Case | *******INA Support paper going to NSC (T-3) Target******* | 19-Aug-24 A | 19-ug-24 | 19-Aug-24 A | 19-ug-24 | 1 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772LT.A1310 | DNB Pull Harder Safety Case | Initial Categorisation by Station ==> KDM | 19-Aug-24 A | 19-ug-24 | 19-Aug-24 A | 19-ug-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1200 | DNB Enhanced Safety Cases | <Review of Weld Inspection Data> - Issue Final EAN | 19-Aug-24 A | 19-ug-24 | 19-Aug-24 A | 19-ug-24 | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.KDM.SP01 | DNB Pull Harder Safety Case | KDM - Gate EC1 completed EC 375698 <DNB Pull Harder SC> | 19-Aug-24 A | 19-ug-24 | 19-Aug-24 A | 19-ug-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1210 | DNB Enhanced Safety Cases | <Review of Weld Inspection Data> - EAN Completed and Uploaded to CDMS | 20-Aug-24 A | 20-ug-24 | 30-Sep-24 A | 30-Sep-24 | 5 | 0 | 28 | 100% |  | Completed
W772LT | W772 | W772LT.A1010 | DNB Pull Harder Safety Case | Produce draft NSRS (using BARRIER MODEL) | 20-Aug-24 A | 20-ug-24 | 10-Oct-24 A | 10-Oct-24 | 28 | 0 | 36 | 100% |  | Completed
W772LT | W772 | W772LT.A1250 | DNB Pull Harder Safety Case | Appoint CO & CA | 20-Aug-24 A | 20-ug-24 | 20-Aug-24 A | 20-ug-24 | 1 | 0 | 1 | 100% |  | Completed
ER6701LT | W228 | W228.3700 | HYA Enhanced Defueling Safety Case | Verify | 21-Aug-24 A | 21-ug-24 | 04-Sep-24 A | 04-Sep-24 | 1 | 0 | 10 | 100% |  | Completed
ER6698LT | W224 | W224.3700 | HRA Enhanced Defueling Safety Case | Verify | 21-Aug-24 A | 21-ug-24 | 04-Sep-24 A | 04-Sep-24 | 11 | 0 | 10 | 100% |  | Completed
W772LT | W772 | W772LT.A1110 | DNB Pull Harder Safety Case | CA to agree with CO format of the safety case | 21-Aug-24 A | 21-ug-24 | 22-Aug-24 A | 22-ug-24 | 2 | 0 | 2 | 100% |  | Completed
W772LT | W772 | W772LT.A1340 | DNB Pull Harder Safety Case | Identify verifier for the case & establish all other resources | 21-Aug-24 A | 21-ug-24 | 30-Aug-24 A | 30-ug-24 | 7 | 0 | 7 | 100% |  | Completed
ER6698LT | W224 | W224.1290 | HRA Enhanced Defueling Safety Case | Author SWIFT Briefing Pack | 22-Aug-24 A | 22-ug-24 | 13-Sep-24 A | 13-Sep-24 | 16 | 0 | 16 | 100% |  | Completed
ER6701LT | W228 | W228.1290 | HYA Enhanced Defueling Safety Case | Author Draft SWIFT Report - Confirm Nodes | 22-Aug-24 A | 22-ug-24 | 13-Sep-24 A | 13-Sep-24 | 16 | 0 | 16 | 100% |  | Completed
ER6372LT | W203 | W203.D1040 | HNB Enhanced Defuelling Safety Cases | Ensure Alignment of Schedule & Estimate | 22-Aug-24 A | 22-ug-24 | 27-Aug-24 A | 27-ug-24 | 3 | 0 | 3 | 100% |  | Completed
W232LT | W232 | W232.C1560 | DNB Enhanced Safety Cases | <SCOPE NAME CHANGE CN 2615><Further Review of Shock Loaded Unit Events (Group 1)> - Issue Draft EAN to EDF for R | 22-Aug-24 A | 22-ug-24 | 22-Aug-24 A | 22-ug-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1570 | DNB Enhanced Safety Cases | <SCOPE NAME CHANGE CN 2615><Further Review of Shock Loaded Unit Events (Group 1)> - Draft EAN Reviewed by EDF SQ | 23-Aug-24 A | 23-ug-24 | 06-Sep-24 A | 06-Sep-24 | 10 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.C1350 | DNB Enhanced Safety Cases | <Review of Lifting Integrity Faults> - Issue Final EAN | 23-Aug-24 A | 23-ug-24 | 23-Aug-24 A | 23-ug-24 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1200 | HNB Enhanced Defuelling Safety Cases | Revise Project Definition Document (PDD) | 26-Aug-24 A | 26-ug-24 | 02-Oct-24 A | 02-Oct-24 | 5 | 0 | 26 | 100% |  | Completed
W232LT | W232 | W232.C1360 | DNB Enhanced Safety Cases | <Review of Lifting Integrity Faults> - EAN Completed and Uploaded to CDMS | 27-Aug-24 A | 27-ug-24 | 30-Sep-24 A | 30-Sep-24 | 5 | 0 | 24 | 100% |  | Completed
ER6698LT | W224 | W224.2430 | HRA Enhanced Defueling Safety Case | EDF Review and contract awards | 28-Aug-24 A | 28-ug-24 | 30-Aug-24 A | 30-ug-24 | 10 | 0 | 3 | 100% |  | Completed
ER6701LT | W228 | W228.2430 | HYA Enhanced Defueling Safety Case | EDF Review and contract awards | 28-Aug-24 A | 28-ug-24 | 30-Aug-24 A | 30-ug-24 | 10 | 0 | 3 | 100% |  | Completed
ER6372LT | W203 | W203.D1050 | HNB Enhanced Defuelling Safety Cases | Hold Risk Workshop | 28-Aug-24 A | 28-ug-24 | 28-Aug-24 A | 28-ug-24 | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 2200 | HYA Fuel Handling Essential Safety Case | INA Support paper going to NSC (T-3) | 29-Aug-24 A | 29-ug-24 | 29-Aug-24 A | 29-ug-24 | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.D1060 | HNB Enhanced Defuelling Safety Cases | Complete Risk Log with Estimates | 29-Aug-24 A | 29-ug-24 | 30-Aug-24 A | 30-ug-24 | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A5300 | HRA Reactors Shutdown Essential Safety Cases | INSA Assessment substantially comp (T-3 weeks before NSC date) EC 363682 <Reactor Shutdown Essential SC> (Cat 1 MS) HRA | 29-Aug-24 A | 29-ug-24 | 29-Aug-24 A | 29-ug-24 | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5310 | HRA Reactors Shutdown Essential Safety Cases | INSA Assessment substantially comp (T-3 weeks before NSC date) EC 363682 Reactor Shutdown Essential SC (Cat 1 MS) (HRA) | 29-Aug-24 A | 29-ug-24 | 29-Aug-24 A | 29-ug-24 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5300 | HYA Reactors Shutdown Essential Safety Cases | INSA Assessment substantially comp (T-3 weeks before NSC date) EC 363676 <Reactor Shutdown Essential SC> (Cat 1 MS) HYA | 29-Aug-24 A | 29-ug-24 | 29-Aug-24 A | 29-ug-24 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5310 | HYA Reactors Shutdown Essential Safety Cases | INSA Assessment substantially comp (T-3 weeks before NSC date) EC 363676 Reactor Shutdown Essential SC (Cat 1 MS) (HYA) | 29-Aug-24 A | 29-ug-24 | 29-Aug-24 A | 29-ug-24 | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A5010 | HRA Fuel Handling Essential Safety Case | INSA Assess substantially comp (T-3 wks<NSC date) ECs (HRA-363840) Essential Fuel Handling Safety Case | 29-Aug-24 A | 29-ug-24 | 29-Aug-24 A | 29-ug-24 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A5010 | HYA Fuel Handling Essential Safety Case | INSA Assess substntlly comp (T-3 wks<NSC date) ECs (HYA-363839) Essential Fuel Handling Safety Case | 29-Aug-24 A | 29-ug-24 | 29-Aug-24 A | 29-ug-24 | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206180 | HRA Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W222, HRA Security Plan) INSA Assessment substantially comp (T - 3 weeks before NSC date) | 29-Aug-24 A | 29-ug-24 | 29-Aug-24 A | 29-ug-24 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206240 | HYA Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W226, HYA Security Plan) INSA Assessment substantially comp (T - 3 weeks before NSC date) | 29-Aug-24 A | 29-ug-24 | 29-Aug-24 A | 29-ug-24 | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.1020 | HRA Fuel Handling Essential Safety Case | >>>OUTGOING ENABLER (HRA Security Plan (W155)) INSA Assessment substantially comp (T - 3 weeks before NSC date) | 29-Aug-24 A | 29-ug-24 | 29-Aug-24 A | 29-ug-24 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.1020 | HYA Fuel Handling Essential Safety Case | >>>OUTGOING ENABLER (HYA Security Plan (W156)) INSA Assessment substantially comp (T - 3 weeks before NSC date) | 29-Aug-24 A | 29-ug-24 | 29-Aug-24 A | 29-ug-24 | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.1360 | HRA Reactors Shutdown Essential Safety Cases | >>>INCOMING ENABLER (W222) INA Support paper going to NSC (T-3) | 29-Aug-24 A | 29-ug-24 | 29-Aug-24 A | 29-ug-24 | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.1370 | HRA Reactors Shutdown Essential Safety Cases | >>>MIRROR of INCOMING ENABLER (W222) INA Support paper going to NSC (T-3) | 29-Aug-24 A | 29-ug-24 | 29-Aug-24 A | 29-ug-24 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.B1360 | HYA Reactors Shutdown Essential Safety Cases | >>>INCOMING ENABLER (W226) INA Support paper going to NSC (T-3) | 29-Aug-24 A | 29-ug-24 | 29-Aug-24 A | 29-ug-24 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.B1370 | HYA Reactors Shutdown Essential Safety Cases | >>>MIRROR of INCOMING ENABLER (W226) INA Support paper going to NSC (T-3) | 29-Aug-24 A | 29-ug-24 | 29-Aug-24 A | 29-ug-24 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5540 | HYA Reactors Shutdown Essential Safety Cases | >>>INTERFACE MILESTONE (W226) INA Support paper going to NSC (T-3) | 29-Aug-24 A | 29-ug-24 | 29-Aug-24 A | 29-ug-24 | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206540 | HRA Reactors Shutdown Essential Safety Cases | >>>INTERFACE MILESTONE (W222) INA Support paper going to NSC (T-3) | 29-Aug-24 A | 29-ug-24 | 29-Aug-24 A | 29-ug-24 | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5270 | HRA Reactors Shutdown Essential Safety Cases | Prepare Station Director's Brief (HRA) | 30-Aug-24 A | 30-ug-24 | 11-Sep-24 A | 11-Sep-24 | 5 | 0 | 8 | 100% |  | Completed
ER6661LT | W206 | W206.A5270 | HYA Reactors Shutdown Essential Safety Cases | Prepare Station Director's Brief (HYA) | 30-Aug-24 A | 30-ug-24 | 11-Sep-24 A | 11-Sep-24 | 5 | 0 | 8 | 100% |  | Completed
ER6378LT | W222 | W222.A1520 | HRA Fuel Handling Essential Safety Case | Prepare Station Director's Brief | 30-Aug-24 A | 30-ug-24 | 11-Sep-24 A | 11-Sep-24 | 5 | 0 | 9 | 100% |  | Completed
ER6378LT | W222 | W222.A5000 | HRA Fuel Handling Essential Safety Case | Incorporate INSA comments | 30-Aug-24 A | 30-ug-24 | 05-Sep-24 A | 05-Sep-24 | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A5000 | HYA Fuel Handling Essential Safety Case | Incorporate INSA comments | 30-Aug-24 A | 30-ug-24 | 05-Sep-24 A | 05-Sep-24 | 5 | 0 | 4 | 100% |  | Completed
ER6650LT | W226 | W226.A1520 | HYA Fuel Handling Essential Safety Case | Prepare Station Director's Brief | 30-Aug-24 A | 30-ug-24 | 11-Sep-24 A | 11-Sep-24 | 5 | 0 | 8 | 100% |  | Completed
ER6650LT | W226 | 2180 | HYA Fuel Handling Essential Safety Case | Respond to Minor INSA Comments | 30-Aug-24 A | 30-ug-24 | 05-Sep-24 A | 05-Sep-24 | 5 | 0 | 4 | 100% |  | Completed
ER6650LT | W226 | 2210 | HYA Fuel Handling Essential Safety Case | pre-NSC notification period to be determined/agreed (T-3)(Jun=29 May)(Jul=26 Jun) | 30-Aug-24 A | 30-ug-24 | 30-Aug-24 A | 30-ug-24 | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 2190 | HYA Fuel Handling Essential Safety Case | Close Out Minor INSA Comments | 30-Aug-24 A | 30-ug-24 | 05-Sep-24 A | 05-Sep-24 | 5 | 0 | 4 | 100% |  | Completed
ER6701LT | W228 | W228.1400 | HYA Enhanced Defueling Safety Case | HYA Reduce IFDF Cooling Requirements Reduce cooling to one blower | 02-Sep-24 A | 02-Sep-24 | 02-Jan-25 A | 02-Jan-25 | 64 | 0 | 86 | 100% |  | Completed
ER6650LT | W226 | W226.A24350 | HYA Fuel Handling Essential Safety Case | Living Safety Document EAN Available | 02-Sep-24 A | 02-Sep-24 | 02-Sep-24 A | 02-Sep-24 | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.1400 | HRA Enhanced Defueling Safety Case | HRA Reduce IFDF Cooling Requirements Reduce Cooling to one Blower | 02-Sep-24 A | 02-Sep-24 | 02-Jan-25 A | 02-Jan-25 | 64 | 0 | 85 | 100% |  | Completed
ER6698LT | W224 | W224.2530 | HRA Enhanced Defueling Safety Case | Hold PJB for TSA Support | 02-Sep-24 A | 02-Sep-24 | 02-Sep-24 A | 02-Sep-24 | 1 | 0 | 1 | 100% |  | Completed
ER6698LT | W224 | W224.2570 | HRA Enhanced Defueling Safety Case | Technical Discussion | 02-Sep-24 A | 02-Sep-24 | 17-Sep-24 A | 17-Sep-24 | 12 | 0 | 12 | 100% |  | Completed
ER6701LT | W228 | W228.2570 | HYA Enhanced Defueling Safety Case | Technical Discussion for PC1/PC2 software | 02-Sep-24 A | 02-Sep-24 | 17-Sep-24 A | 17-Sep-24 | 1 | 0 | 12 | 100% |  | Completed
ER6701LT | W228 | W228.2530 | HYA Enhanced Defueling Safety Case | Hold PJB for TSA Support | 02-Sep-24 A | 02-Sep-24 | 02-Sep-24 A | 02-Sep-24 | 1 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772LT.D3000 | DNB Pull Harder Safety Case | Define Project Control Structures (WBS/CBS/OBS/PBS) | 02-Sep-24 A | 02-Sep-24 | 02-Sep-24 A | 02-Sep-24 | 1 | 0 | 1 | 100% |  | Completed
ER6698LT | W224 | W224.1210 | HRA Enhanced Defueling Safety Case | Hold PJB | 03-Sep-24 A | 03-Sep-24 | 16-Sep-24 A | 16-Sep-24 | 5 | 0 | 9 | 100% |  | Completed
ER6701LT | W228 | W228.1210 | HYA Enhanced Defueling Safety Case | Hold PJB | 03-Sep-24 A | 03-Sep-24 | 16-Sep-24 A | 16-Sep-24 | 5 | 0 | 9 | 100% |  | Completed
W772LT | W772 | W772LT.D3010 | DNB Pull Harder Safety Case | Plan Scope in Primavera (level 2 for Phase A to B & Level 1 for Lifecycle | 03-Sep-24 A | 03-Sep-24 | 18-Oct-24 A | 18-Oct-24 | 34 | 0 | 34 | 100% |  | Completed
W772LT | W772 | W772LT.D3020 | DNB Pull Harder Safety Case | Estimate scope (+/- 10% A-B & +/- 50% Lifecycle | 03-Sep-24 A | 03-Sep-24 | 18-Oct-24 A | 18-Oct-24 | 34 | 0 | 34 | 100% |  | Completed
ER6698LT | W224 | W224.3710 | HRA Enhanced Defueling Safety Case | TR of CETS (may Not be Needed) | 05-Sep-24 A | 05-Sep-24 | 05-Sep-24 A | 05-Sep-24 | 11 | 0 | 1 | 100% |  | Completed
ER6701LT | W228 | W228.3710 | HYA Enhanced Defueling Safety Case | TR of CETS | 05-Sep-24 A | 05-Sep-24 | 05-Sep-24 A | 05-Sep-24 | 1 | 0 | 1 | 100% |  | Completed
ER6698LT | W224 | W224.1325 | HRA Enhanced Defueling Safety Case | KDM - CETS ISSUE PoC and Detailed Design for BoB Weight and Gripping Sleeve | 09-Sep-24 A | 09-Sep-24 | 09-Sep-24 A | 09-Sep-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1580 | DNB Enhanced Safety Cases | <SCOPE NAME CHANGE CN 2615><Further Review of Shock Loaded Unit Events (Group 1)> - Address Comments from EDF Re | 09-Sep-24 A | 09-Sep-24 | 08-Oct-24 A | 08-Oct-24 | 10 | 0 | 21 | 100% |  | Completed
ER6698LT | W224 | W224.1330 | HRA Enhanced Defueling Safety Case | KDM - CETS ISSUE Approval | 09-Sep-24 A | 09-Sep-24 | 09-Sep-24 A | 09-Sep-24 | 0 | 0 | 0 | 100% |  | Completed
ER6701LT | W228 | W228.1330 | HYA Enhanced Defueling Safety Case | KDM - CETS ISSUE Approval | 09-Sep-24 A | 09-Sep-24 | 09-Sep-24 A | 09-Sep-24 | 0 | 0 | 0 | 100% |  | Completed
ER6701LT | W228 | W228.1325 | HYA Enhanced Defueling Safety Case | KDM - CETS ISSUE PoC and Detailed Design for BoB Weight and Gripping Sleeve | 09-Sep-24 A | 09-Sep-24 | 09-Sep-24 A | 09-Sep-24 | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.2200 | HRA Enhanced Defueling Safety Case | Issue CETS for Tender | 10-Sep-24 A | 10-Sep-24 | 26-Sep-24 A | 26-Sep-24 | 5 | 0 | 12 | 100% |  | Completed
ER6701LT | W228 | W228.2200 | HYA Enhanced Defueling Safety Case | Issue CETS for Tender | 10-Sep-24 A | 10-Sep-24 | 26-Sep-24 A | 26-Sep-24 | 5 | 0 | 12 | 100% |  | Completed
ER6701LT | W228 | W228.1220 | HYA Enhanced Defueling Safety Case | Optioneering Workshop | 16-Sep-24 A | 16-Sep-24 | 02-Jan-25 A | 02-Jan-25 | 5 | 0 | 75 | 100% |  | Completed
ER6698LT | W224 | W224.1220 | HRA Enhanced Defueling Safety Case | Optioneering Studying Report | 16-Sep-24 A | 16-Sep-24 | 02-Jan-25 A | 02-Jan-25 | 5 | 0 | 75 | 100% |  | Completed
ER6371LT | W202 | W202.A5330 | HRA Reactors Shutdown Essential Safety Cases | NSC Presentation Date EC 363682 <Reactor Shutdown Essential SC> (Cat 1 B KDM) (T) (HRA) | 18-Sep-24 A | 18-Sep-24 | 18-Sep-24 A | 18-Sep-24 | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5350 | HRA Reactors Shutdown Essential Safety Cases | NSC Consideration & advice to Station Director (HRA) | 18-Sep-24 A | 18-Sep-24 | 02-Oct-24 A | 02-Oct-24 | 11 | 0 | 11 | 100% |  | Completed
ER6371LT | W202 | W202.A5340 | HRA Reactors Shutdown Essential Safety Cases | NSC Presentation Date (T) EC (HRA-363682) Reactor Shutdown Essential Safety Case | 18-Sep-24 A | 18-Sep-24 | 18-Sep-24 A | 18-Sep-24 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5330 | HYA Reactors Shutdown Essential Safety Cases | NSC Presentation Date EC 363676 <Reactor Shutdown Essential SC> (Cat 1 B KDM) (T) (HYA) | 18-Sep-24 A | 18-Sep-24 | 18-Sep-24 A | 18-Sep-24 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5350 | HYA Reactors Shutdown Essential Safety Cases | NSC Consideration & advice to Station Director (HYA) | 18-Sep-24 A | 18-Sep-24 | 02-Oct-24 A | 02-Oct-24 | 11 | 0 | 11 | 100% |  | Completed
ER6661LT | W206 | W206.A5340 | HYA Reactors Shutdown Essential Safety Cases | NSC Presentation Date (T) EC (HYA-363676) Reactor Shutdown Essential Safety Case | 18-Sep-24 A | 18-Sep-24 | 18-Sep-24 A | 18-Sep-24 | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A4980 | HRA Fuel Handling Essential Safety Case | NSC Presentation Date (T) ECs (HRA-363840) Essential Fuel Handling Safety Case | 18-Sep-24 A | 18-Sep-24 | 18-Sep-24 A | 18-Sep-24 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1038 | TOR Essential Defueling Safety Case | Verification Complete/ Verified Draft A Issued for INSA (T-7) EC 371386 - TOR Essential Defueling Safety Case | 18-Sep-24 A | 18-Sep-24 | 18-Sep-24 A | 18-Sep-24 | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A27280 | HRA Fuel Handling Essential Safety Case | NSC Presentation Date (T) ECs (HRA-363840) Essential Fuel Handling Safety Case | 18-Sep-24 A | 18-Sep-24 | 18-Sep-24 A | 18-Sep-24 | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A27330 | HYA Fuel Handling Essential Safety Case | NSC Presentation Date (T) ECs (HYA-363839) Essential Fuel Handling Safety Case | 18-Sep-24 A | 18-Sep-24 | 18-Sep-24 A | 18-Sep-24 | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 2220 | HYA Fuel Handling Essential Safety Case | NSC Meeting | 18-Sep-24 A | 18-Sep-24 | 18-Sep-24 A | 18-Sep-24 | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A4980 | HYA Fuel Handling Essential Safety Case | NSC Presentation Date (T) ECs (HYA-363839) Essential Fuel Handling Safety Case | 18-Sep-24 A | 18-Sep-24 | 18-Sep-24 A | 18-Sep-24 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1505 | HYB Essential Defueling Safety Case | Submit for approval - Categoriser ratifies; RE/CO endorsement | 18-Sep-24 A | 18-Sep-24 | 18-Sep-24 A | 18-Sep-24 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1038 | HYB Essential Defueling Safety Case | Verification Complete/ Verified Draft A Issued for INSA (T-7) EC 371387 - HYB Essential Defueling Safety Case | 18-Sep-24 A | 18-Sep-24 | 18-Sep-24 A | 18-Sep-24 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1505 | TOR Essential Defueling Safety Case | Submit for approval - Categoriser ratifies; RE/CO endorsement | 18-Sep-24 A | 18-Sep-24 | 18-Sep-24 A | 18-Sep-24 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1525 | TOR Essential Defueling Safety Case | DA (Authorised Designer) Approval of CAT1 Safety Case | 19-Sep-24 A | 19-Sep-24 | 20-Sep-24 A | 20-Sep-24 | 5 | 0 | 2 | 100% |  | Completed
ER6668LT | W213 | W213.1535 | TOR Essential Defueling Safety Case | INSA review & iteration of comments (using BARRIER MODEL) | 19-Sep-24 A | 19-Sep-24 | 31-Jan-25 A | 31-Jan-25 | 20 | 0 | 93 | 100% |  | Completed
ER6378LT | W222 | W222.A1660 | HRA Fuel Handling Essential Safety Case | NSC Consideration & advice to Station Director | 19-Sep-24 A | 19-Sep-24 | 02-Oct-24 A | 02-Oct-24 | 10 | 0 | 9 | 100% |  | Completed
ER6650LT | W226 | W226.A1660 | HYA Fuel Handling Essential Safety Case | NSC Consideration & advice to Station Director | 19-Sep-24 A | 19-Sep-24 | 02-Oct-24 A | 02-Oct-24 | 10 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.1525 | HYB Essential Defueling Safety Case | DA (Authorised Designer) Approval of CAT1 Safety Case | 19-Sep-24 A | 19-Sep-24 | 20-Sep-24 A | 20-Sep-24 | 5 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.1535 | HYB Essential Defueling Safety Case | INSA review & iteration of comments (using BARRIER MODEL) | 19-Sep-24 A | 19-Sep-24 | 31-Jan-25 A | 31-Jan-25 | 20 | 0 | 94 | 100% |  | Completed
ER6666LT | W209 | W209.29300 | HYB Essential Defueling Safety Case | Lessons Learnt Activity - Following Verification of the SC | 19-Sep-24 A | 19-Sep-24 | 23-Oct-24 A | 23-Oct-24 | 10 | 0 | 24 | 100% |  | Completed
ER6668LT | W213 | W213.29300 | TOR Essential Defueling Safety Case | Lessons Learnt Activity - Following Verification of the SC | 19-Sep-24 A | 19-Sep-24 | 23-Oct-24 A | 23-Oct-24 | 10 | 0 | 25 | 100% |  | Completed
ER6650LT | W226 | 2240 | HYA Fuel Handling Essential Safety Case | Respond to NSC as appropriate | 19-Sep-24 A | 19-Sep-24 | 02-Oct-24 A | 02-Oct-24 | 10 | 0 | 9 | 100% |  | Completed
ER6650LT | W226 | 2230 | HYA Fuel Handling Essential Safety Case | NSC Minutes Issued | 19-Sep-24 A | 19-Sep-24 | 10-Oct-24 A | 10-Oct-24 | 10 | 0 | 15 | 100% |  | Completed
ER6698LT | W224 | W224.2520 | HRA Enhanced Defueling Safety Case | Author CETS Issue for Load Trace | 23-Sep-24 A | 23-Sep-24 | 2025-03-07 | 45723 | 30 | 5 | 117 | 80% | 190 | In Progress
ER6701LT | W228 | W228.2520 | HYA Enhanced Defueling Safety Case | Author Issue for Load Trace | 23-Sep-24 A | 23-Sep-24 | 2025-03-07 | 45723 | 30 | 5 | 117 | 80% | 190 | In Progress
W232LT | W232 | W232.A2100 | DNB Enhanced Safety Cases | Rev 000 - Produce verification plan | 23-Sep-24 A | 23-Sep-24 | 30-Sep-24 A | 30-Sep-24 | 2 | 0 | 5 | 100% |  | Completed
ER6372LT | W203 | W203.C1390 | HNB Enhanced Defuelling Safety Cases | Verification of the case (using BARRIER MODEL) | 26-Sep-24 A | 26-Sep-24 | 15-Nov-24 A | 15-Nov-24 | 0 | 0 | 37 | 100% |  | Completed
ER6378LT | W222 | W222.3090 | HRA Fuel Handling Essential Safety Case | Verification of Proposal Lessons Learnt Review Complete | 26-Sep-24 A | 26-Sep-24 | 26-Sep-24 A | 26-Sep-24 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.3080 | HYA Fuel Handling Essential Safety Case | Verification of Proposal - Lesson Learnt Review Complete | 26-Sep-24 A | 26-Sep-24 | 26-Sep-24 A | 26-Sep-24 | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.2210 | HRA Enhanced Defueling Safety Case | Supplier Return Period | 27-Sep-24 A | 27-Sep-24 | 02-Jan-25 A | 02-Jan-25 | 14 | 0 | 66 | 100% |  | Completed
ER6701LT | W228 | W228.2210 | HYA Enhanced Defueling Safety Case | Supplier Return Period | 27-Sep-24 A | 27-Sep-24 | 02-Jan-25 A | 02-Jan-25 | 14 | 0 | 66 | 100% |  | Completed
ER6378LT | W222 | W222.3050 | HRA Fuel Handling Essential Safety Case | Lesson Learn - Verification Phase | 27-Sep-24 A | 27-Sep-24 | 27-Sep-24 A | 27-Sep-24 | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.3050 | HYA Fuel Handling Essential Safety Case | Lesson Learn - Verification Phase | 27-Sep-24 A | 27-Sep-24 | 27-Sep-24 A | 27-Sep-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1220 | DNB Enhanced Safety Cases | <Review of Weld Inspection Data> - EAN Completed | 30-Sep-24 A | 30-Sep-24 | 30-Sep-24 A | 30-Sep-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1370 | DNB Enhanced Safety Cases | <Review of Lifting Integrity Faults> - EAN Completed | 30-Sep-24 A | 30-Sep-24 | 30-Sep-24 A | 30-Sep-24 | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A1070 | DNB Pull Harder Safety Case | Create EC Definition Document if not part of Project Definition Document (Insert Template Ref) | 30-Sep-24 A | 30-Sep-24 | 30-Sep-24 A | 30-Sep-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2090 | DNB Enhanced Safety Cases | Rev 000 - Incorporate CO & Station comments | 01-Oct-24 A | 01-Oct-24 | 08-Oct-24 A | 08-Oct-24 | 5 | 0 | 5 | 100% |  | Completed
W772LT | W772 | W772LT.A1460 | DNB Pull Harder Safety Case | Continue to Develop & resource mandatory template ==> KDM | 01-Oct-24 A | 01-Oct-24 | 01-Oct-24 A | 01-Oct-24 | 1 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A1060 | DNB Pull Harder Safety Case | Hold project kick start meeting with Station & key suppliers | 01-Oct-24 A | 01-Oct-24 | 02-Oct-24 A | 02-Oct-24 | 2 | 0 | 2 | 100% |  | Completed
W772LT | W772 | W772LT.A1350 | DNB Pull Harder Safety Case | Circulate work programme to stakeholders for agreement | 02-Oct-24 A | 02-Oct-24 | 09-Oct-24 A | 09-Oct-24 | 5 | 0 | 5 | 100% |  | Completed
W772LT | W772 | W772LT.KDM.SP03 | DNB Pull Harder Safety Case | KDM - Gate EC2 completed and Cat 1 Baselined EC 375698 <DNB Pull Harder SC> | 02-Oct-24 A | 02-Oct-24 | 02-Oct-24 A | 02-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1600 | DNB Enhanced Safety Cases | <SCOPE NAME CHANGE CN 2615><Further Review of Shock Loaded Unit Events (Group 1)> - EAN Completed and Uploaded t | 02-Oct-24 A | 02-Oct-24 | 08-Oct-24 A | 08-Oct-24 | 3 | 0 | 4 | 100% |  | Completed
ER6372LT | W203 | W203.D1070 | HNB Enhanced Defuelling Safety Cases | Update Schedule/Estimate from Risk Log & Add Provisions | 03-Oct-24 A | 03-Oct-24 | 11-Oct-24 A | 11-Oct-24 | 2 | 0 | 6 | 100% |  | Completed
W772LT | W772 | W772LT.A1090 | DNB Pull Harder Safety Case | Agree INSA resource with INA | 03-Oct-24 A | 03-Oct-24 | 04-Oct-24 A | 04-Oct-24 | 2 | 0 | 2 | 100% |  | Completed
W772LT | W772 | W772LT.A1520 | DNB Pull Harder Safety Case | Commence Supporting References or Supporting EC's | 04-Oct-24 A | 04-Oct-24 | 04-Oct-24 A | 04-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.D2090 | DNB Pull Harder Safety Case | Project Management - Gate A - D | 04-Oct-24 A | 04-Oct-24 | 2025-09-18 | 45918 | 225 | 139 | 242 | 42% | 4 | In Progress
W772LT | W772 | W772LT.D2100 | DNB Pull Harder Safety Case | Technical Support - Gate A - D | 04-Oct-24 A | 04-Oct-24 | 2025-09-18 | 45918 | 225 | 139 | 242 | 42% | 4 | In Progress
W772LT | W772 | W772LT.T1250 | DNB Pull Harder Safety Case | <Operating Strategy for Pull Harder Facility> - Prepare Draft EAN / Report | 04-Oct-24 A | 04-Oct-24 | 25-Oct-24 A | 25-Oct-24 | 15 | 0 | 15 | 100% |  | Completed
W232LT | W232 | W232.A2120 | DNB Enhanced Safety Cases | Rev 000 - Produce verification file | 07-Oct-24 A | 07-Oct-24 | 08-Oct-24 A | 08-Oct-24 | 2 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2250 | DNB Enhanced Safety Cases | Rev 000 - Key Stakeholders Approval, if requested | 07-Oct-24 A | 07-Oct-24 | 08-Oct-24 A | 08-Oct-24 | 5 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2070 | DNB Enhanced Safety Cases | Rev 000 - CA to agree with CO format of the safety case & produce agreed contents page | 07-Oct-24 A | 07-Oct-24 | 08-Oct-24 A | 08-Oct-24 | 2 | 0 | 2 | 100% |  | Completed
W232LT | W232 | W232.A2130 | DNB Enhanced Safety Cases | Rev 000 - Verified Draft Issue A with verification file to INSA & station *(KDM)* | 08-Oct-24 A | 08-Oct-24 | 08-Oct-24 A | 08-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2140 | DNB Enhanced Safety Cases | Rev 000 - INSA review & iteration of comments (using BARRIER MODEL) | 08-Oct-24 A | 08-Oct-24 | 18-Oct-24 A | 18-Oct-24 | 20 | 0 | 8 | 100% |  | Completed
W232LT | W232 | W232.A2230 | DNB Enhanced Safety Cases | Rev 000 - Verification complete | 08-Oct-24 A | 08-Oct-24 | 08-Oct-24 A | 08-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2240 | DNB Enhanced Safety Cases | Rev 000 - Submit for approval - Categoriser ratifies; RE/CO endorsement | 08-Oct-24 A | 08-Oct-24 | 08-Oct-24 A | 08-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2280 | DNB Enhanced Safety Cases | Rev 000 - Issue to CO & Station for comments | 08-Oct-24 A | 08-Oct-24 | 08-Oct-24 A | 08-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A3010 | DNB Enhanced Safety Cases | All Technical References Complete - Rev 000 | 08-Oct-24 A | 08-Oct-24 | 08-Oct-24 A | 08-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A3020 | DNB Enhanced Safety Cases | Safety Case Authoring Complete - Rev 000 | 08-Oct-24 A | 08-Oct-24 | 08-Oct-24 A | 08-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A3030 | DNB Enhanced Safety Cases | Safety Case Verification Complete - Rev 000 | 08-Oct-24 A | 08-Oct-24 | 08-Oct-24 A | 08-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1590 | DNB Enhanced Safety Cases | <SCOPE NAME CHANGE CN 2615><Further Review of Shock Loaded Unit Events (Group 1)> - Issue Final EAN | 08-Oct-24 A | 08-Oct-24 | 08-Oct-24 A | 08-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1610 | DNB Enhanced Safety Cases | <SCOPE NAME CHANGE CN 2615><Further Review of Shock Loaded Unit Events (Group 1)> - EAN Completed | 08-Oct-24 A | 08-Oct-24 | 08-Oct-24 A | 08-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2380 | DNB Enhanced Safety Cases | Rev 000 - All supporting references completed | 08-Oct-24 A | 08-Oct-24 | 08-Oct-24 A | 08-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A1630 | DNB Pull Harder Safety Case | Baseline Plan to Verification Commenced (T-11) ==> KDM | 09-Oct-24 A | 09-Oct-24 | 09-Oct-24 A | 09-Oct-24 | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5360 | HRA Reactors Shutdown Essential Safety Cases | INSA Final Approval EC 363682 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HRA) | 10-Oct-24 A | 10-Oct-24 | 10-Oct-24 A | 10-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5380 | HRA Reactors Shutdown Essential Safety Cases | INSA Final Approval EC 363682 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HRA) | 10-Oct-24 A | 10-Oct-24 | 10-Oct-24 A | 10-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5360 | HYA Reactors Shutdown Essential Safety Cases | INSA Final Approval EC 363676 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HYA) | 10-Oct-24 A | 10-Oct-24 | 10-Oct-24 A | 10-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5380 | HYA Reactors Shutdown Essential Safety Cases | INSA Final Approval EC 363676 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HYA) | 10-Oct-24 A | 10-Oct-24 | 10-Oct-24 A | 10-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206510 | HRA Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W285)(W148) INSA Finally Approved | 10-Oct-24 A | 10-Oct-24 | 10-Oct-24 A | 10-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206310 | HYA Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W286) (W148) INSA Finally Approved | 10-Oct-24 A | 10-Oct-24 | 10-Oct-24 A | 10-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A1015 | DNB Pull Harder Safety Case | Draft NSRS Verify - Atkins | 10-Oct-24 A | 10-Oct-24 | 31-Oct-24 A | 31-Oct-24 | 10 | 0 | 15 | 100% |  | Completed
ER6378LT | W222 | W222.A17490 | HRA Fuel Handling Essential Safety Case | INSA Final Approval EC 363840 HRA Defuelling Fuel Handling Essential Safety Case (Cat 1 Milestone) | 10-Oct-24 A | 10-Oct-24 | 10-Oct-24 A | 10-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A17490 | HYA Fuel Handling Essential Safety Case | INSA Final Approval EC 363839 HYA Defuelling Fuel Handling Essential Safety Case (Cat 1 Milestone) | 10-Oct-24 A | 10-Oct-24 | 10-Oct-24 A | 10-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.1040 | HRA Fuel Handling Essential Safety Case | >>>OUTGOING ENABLER (W285) INSA Final Approval | 10-Oct-24 A | 10-Oct-24 | 10-Oct-24 A | 10-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27320 | HYA Fuel Handling Essential Safety Case | >>>OUTGOING ENABLER (W286) CAT 1 Fuel Handling SC INSA Finally Approved | 10-Oct-24 A | 10-Oct-24 | 10-Oct-24 A | 10-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5370 | HRA Reactors Shutdown Essential Safety Cases | CAT 1 Satety Case Submitted to ONR - Reactor Shutdown Essential SC HRA | 10-Oct-24 A | 10-Oct-24 | 11-Oct-24 A | 11-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5370 | HYA Reactors Shutdown Essential Safety Cases | CAT 1 Satety Case Submitted to ONR - Reactor Shutdown Essential SC HYA | 10-Oct-24 A | 10-Oct-24 | 11-Oct-24 A | 11-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.1220 | HRA Fuel Handling Essential Safety Case | Letter Sent to ONR to Initiate Acknowlegement / Agreement | 11-Oct-24 A | 11-Oct-24 | 11-Oct-24 A | 11-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.1190 | HYA Fuel Handling Essential Safety Case | Letter Sent to ONR to Initiate Acknowledgement / Agreement | 11-Oct-24 A | 11-Oct-24 | 11-Oct-24 A | 11-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 2250 | HYA Fuel Handling Essential Safety Case | Draft HRA Formal ONR Letter/Review | 11-Oct-24 A | 11-Oct-24 | 11-Oct-24 A | 11-Oct-24 | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 2260 | HYA Fuel Handling Essential Safety Case | Draft HYA Formal ONR Letter/Review | 11-Oct-24 A | 11-Oct-24 | 11-Oct-24 A | 11-Oct-24 | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 2270 | HYA Fuel Handling Essential Safety Case | Station Directors sign letters | 11-Oct-24 A | 11-Oct-24 | 11-Oct-24 A | 11-Oct-24 | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 2280 | HYA Fuel Handling Essential Safety Case | Safety Case Submitted to the ONR | 11-Oct-24 A | 11-Oct-24 | 11-Oct-24 A | 11-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5390 | HRA Reactors Shutdown Essential Safety Cases | ONR Approval of Safety Case EC 363682 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HRA) | 14-Oct-24 A | 14-Oct-24 | 24-Jan-25 A | 24-Jan-25 | 63 | 0 | 71 | 100% |  | Completed
ER6661LT | W206 | W206.A5390 | HYA Reactors Shutdown Essential Safety Cases | ONR Approval of Safety Case EC 363676 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HYA) | 14-Oct-24 A | 14-Oct-24 | 24-Jan-25 A | 24-Jan-25 | 63 | 0 | 71 | 100% |  | Completed
ER6378LT | W222 | W222.A17500 | HRA Fuel Handling Essential Safety Case | ONR Approval of SC (Letter sent to initiate) HYA HRA Defuelling Fuel Handling Essential Safety Case | 14-Oct-24 A | 14-Oct-24 | 24-Jan-25 A | 24-Jan-25 | 63 | 0 | 71 | 100% |  | Completed
ER6378LT | W222 | W222.1150 | HRA Fuel Handling Essential Safety Case | Safety Case Development Costs - ONR Phase (C to D ) ##Cost Summary## | 14-Oct-24 A | 14-Oct-24 | 24-Jan-25 A | 24-Jan-25 | 63 | 0 | 72 | 100% |  | Completed
ER6378LT | W222 | W222.1160 | HRA Fuel Handling Essential Safety Case | Project Management Costs - ONR Phase (C to D ) ##Cost Summary## | 14-Oct-24 A | 14-Oct-24 | 24-Jan-25 A | 24-Jan-25 | 63 | 0 | 72 | 100% |  | Completed
ER6371LT | W202 | W202.A2206530 | HRA Reactors Shutdown Essential Safety Cases | SC - Safety Case development - tech oversight Cat 1 - HRA - C-D - STN | 14-Oct-24 A | 14-Oct-24 | 21-Feb-25 A | 21-Feb-25 | 94 | 0 | 91 | 100% |  | Completed
ER6661LT | W206 | W206.A2206330 | HYA Reactors Shutdown Essential Safety Cases | SC - Safety Case development - tech oversight Cat 1 - HYA - C-D - STN | 14-Oct-24 A | 14-Oct-24 | 21-Feb-25 A | 21-Feb-25 | 94 | 0 | 91 | 100% |  | Completed
ER6372LT | W203 | W203.D1080 | HNB Enhanced Defuelling Safety Cases | Add Data to PRC Paper | 14-Oct-24 A | 14-Oct-24 | 18-Oct-24 A | 18-Oct-24 | 2 | 0 | 4 | 100% |  | Completed
ER6650LT | W226 | W226.A17500 | HYA Fuel Handling Essential Safety Case | ONR Approval of SC (Letter sent to initiate) HYA HRA Defuelling Fuel Handling Essential Safety Case | 14-Oct-24 A | 14-Oct-24 | 24-Jan-25 A | 24-Jan-25 | 64 | 0 | 71 | 100% |  | Completed
ER6650LT | W226 | W226.1150 | HYA Fuel Handling Essential Safety Case | Safety Case Development Costs - ONR Phase (C to D ) ##Cost Summary## | 14-Oct-24 A | 14-Oct-24 | 13-Jan-25 A | 13-Jan-25 | 63 | 0 | 63 | 100% |  | Completed
ER6650LT | W226 | W226.1160 | HYA Fuel Handling Essential Safety Case | Project Management Costs - ONR Phase (C to D ) ##Cost Summary## | 14-Oct-24 A | 14-Oct-24 | 24-Jan-25 A | 24-Jan-25 | 63 | 0 | 72 | 100% |  | Completed
W772LT | W772 | W772LT.A1020 | DNB Pull Harder Safety Case | Station comments on NSRS | 14-Oct-24 A | 14-Oct-24 | 31-Oct-24 A | 31-Oct-24 | 8 | 0 | 13 | 100% |  | Completed
W772LT | W772 | W772LT.A1030 | DNB Pull Harder Safety Case | DA (Peer) comments on NSRS | 14-Oct-24 A | 14-Oct-24 | 31-Oct-24 A | 31-Oct-24 | 8 | 0 | 13 | 100% |  | Completed
W772LT | W772 | W772LT.A2000 | DNB Pull Harder Safety Case | Load Path Assessment - Preliminary Work - DNB Defuelling | 14-Oct-24 A | 14-Oct-24 | 22-Nov-24 A | 22-Nov-24 | 30 | 0 | 30 | 100% |  | Completed
W772LT | W772 | W772LT.A2250 | DNB Pull Harder Safety Case | Load Path Assessment - Preliminary Work - Atkins | 14-Oct-24 A | 14-Oct-24 | 22-Nov-24 A | 22-Nov-24 | 30 | 0 | 30 | 100% |  | Completed
W772LT | W772 | W772LT.T1170 | DNB Pull Harder Safety Case | <Specification for Pull Harder Facility> - Prepare Draft EAN / Report | 14-Oct-24 A | 14-Oct-24 | 18-Oct-24 A | 18-Oct-24 | 5 | 0 | 5 | 100% |  | Completed
ER6698LT | W224 | W224.2190 | HRA Enhanced Defueling Safety Case | SWIFT Workshop | 15-Oct-24 A | 15-Oct-24 | 15-Oct-24 A | 15-Oct-24 | 5 | 0 | 1 | 100% |  | Completed
ER6701LT | W228 | W228.2190 | HYA Enhanced Defueling Safety Case | SWIFT Workshop | 15-Oct-24 A | 15-Oct-24 | 21-Oct-24 A | 21-Oct-24 | 5 | 0 | 5 | 100% |  | Completed
ER6701LT | W228 | W228.2180 | HYA Enhanced Defueling Safety Case | SWIFT Report (Update & Verify) | 16-Oct-24 A | 16-Oct-24 | 02-Jan-25 A | 02-Jan-25 | 20 | 0 | 53 | 100% |  | Completed
ER6698LT | W224 | W224.2180 | HRA Enhanced Defueling Safety Case | SWIFT Report (Update & Verify) | 16-Oct-24 A | 16-Oct-24 | 02-Jan-25 A | 02-Jan-25 | 20 | 0 | 53 | 100% |  | Completed
W232LT | W232 | W232.A2290 | DNB Enhanced Safety Cases | Rev 000 - Incorporate INSA comments | 18-Oct-24 A | 18-Oct-24 | 25-Oct-24 A | 25-Oct-24 | 10 | 0 | 5 | 100% |  | Completed
W772LT | W772 | W772LT.T1180 | DNB Pull Harder Safety Case | <Specification for Pull Harder Facility> - Issue Draft EAN / Report for Tech Review. | 18-Oct-24 A | 18-Oct-24 | 18-Oct-24 A | 18-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1090 | HNB Enhanced Defuelling Safety Cases | PCL Validate & Approve Baseline Package for PRC Submission | 21-Oct-24 A | 21-Oct-24 | 25-Oct-24 A | 25-Oct-24 | 3 | 0 | 4 | 100% |  | Completed
W772LT | W772 | W772LT.D3030 | DNB Pull Harder Safety Case | Ensure Alignment of Schedule & Estimate | 21-Oct-24 A | 21-Oct-24 | 22-Oct-24 A | 22-Oct-24 | 2 | 0 | 2 | 100% |  | Completed
W772LT | W772 | W772LT.T1190 | DNB Pull Harder Safety Case | <Specification for Pull Harder Facility> - Draft EAN / Report Tech Reviewed by EDF SQEP | 21-Oct-24 A | 21-Oct-24 | 28-Oct-24 A | 28-Oct-24 | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.29310 | HYB Essential Defueling Safety Case | Lessons Learnt Milestone - Verification of the Safety Case | 23-Oct-24 A | 23-Oct-24 | 23-Oct-24 A | 23-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.D3040 | DNB Pull Harder Safety Case | Hold Risk Workshop | 23-Oct-24 A | 23-Oct-24 | 23-Oct-24 A | 23-Oct-24 | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.29310 | TOR Essential Defueling Safety Case | Lessons Learnt Milestone - Verification of the Safety Case | 23-Oct-24 A | 23-Oct-24 | 23-Oct-24 A | 23-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.D3050 | DNB Pull Harder Safety Case | Finalise Risk Log | 24-Oct-24 A | 24-Oct-24 | 25-Oct-24 A | 25-Oct-24 | 2 | 0 | 2 | 100% |  | Completed
W772LT | W772 | W772LT.T1260 | DNB Pull Harder Safety Case | <Operating Strategy for Pull Harder Facility> - Issue Draft EAN / Report for Tech Review. | 25-Oct-24 A | 25-Oct-24 | 25-Oct-24 A | 25-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.D3060 | DNB Pull Harder Safety Case | Update Schedule from Risk Log/Estimate, Adding Provisions | 28-Oct-24 A | 28-Oct-24 | 30-Oct-24 A | 30-Oct-24 | 3 | 0 | 3 | 100% |  | Completed
W772LT | W772 | W772LT.T1200 | DNB Pull Harder Safety Case | <Specification for Pull Harder Facility> - Address Comments from EDF Review on Draft EAN / Report | 28-Oct-24 A | 28-Oct-24 | 28-Oct-24 A | 28-Oct-24 | 1 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772LT.T1210 | DNB Pull Harder Safety Case | <Specification for Pull Harder Facility> - Issue Final EAN / Report to FMAPS | 28-Oct-24 A | 28-Oct-24 | 28-Oct-24 A | 28-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2320 | DNB Enhanced Safety Cases | Rev 000 - INSA Final Approval *(KDM)* | 28-Oct-24 A | 28-Oct-24 | 29-Oct-24 A | 29-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5000 | DNB Enhanced Safety Cases | Lessons Learned Workshop - FPU Safety Case Ph 3 Rev 000 Technical References complete | 29-Oct-24 A | 29-Oct-24 | 29-Oct-24 A | 29-Oct-24 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5010 | DNB Enhanced Safety Cases | Lessons Learned Workshop - FPU Safety Case Ph 3 Rev 000 Authored | 29-Oct-24 A | 29-Oct-24 | 29-Oct-24 A | 29-Oct-24 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5020 | DNB Enhanced Safety Cases | Lessons Learned Workshop - FPU Safety Case Ph 3 Rev 000 Verified | 29-Oct-24 A | 29-Oct-24 | 29-Oct-24 A | 29-Oct-24 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A3040 | DNB Enhanced Safety Cases | Safety Case INA Final Approval - Rev 000 | 29-Oct-24 A | 29-Oct-24 | 29-Oct-24 A | 29-Oct-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5330 | DNB Enhanced Safety Cases | Hold project kick start meeting with Station & key suppliers | 29-Oct-24 A | 29-Oct-24 | 07-Nov-24 A | 07-Nov-24 | 5 | 0 | 7 | 100% |  | Completed
W232LT | W232 | W232.A5340 | DNB Enhanced Safety Cases | Agree resource & timescales with suppliers for delivering key refs, incl contingency, risk & allowance for rework | 29-Oct-24 A | 29-Oct-24 | 07-Nov-24 A | 07-Nov-24 | 5 | 0 | 7 | 100% |  | Completed
W772LT | W772 | W772LT.T1220 | DNB Pull Harder Safety Case | <Specification for Pull Harder Facility> - FMAPS Review EAN / Report | 29-Oct-24 A | 29-Oct-24 | 04-Nov-24 A | 04-Nov-24 | 5 | 0 | 5 | 100% |  | Completed
W772LT | W772 | W772LT.A1035 | DNB Pull Harder Safety Case | INSA comments on NSRS | 31-Oct-24 A | 31-Oct-24 | 08-Nov-24 A | 08-Nov-24 | 10 | 0 | 6 | 100% |  | Completed
W772LT | W772 | W772LT.D3070 | DNB Pull Harder Safety Case | Add Data to PRC Paper | 31-Oct-24 A | 31-Oct-24 | 31-Oct-24 A | 31-Oct-24 | 1 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772LT.D3080 | DNB Pull Harder Safety Case | PCL Validate & Approve Baseline Package for PRC Submission | 01-Nov-24 A | 01-Nov-24 | 05-Nov-24 A | 05-Nov-24 | 3 | 0 | 3 | 100% |  | Completed
W232LT | W232 | W232.A2260 | DNB Enhanced Safety Cases | Rev 000 - Station Approval for mod implementation (including station review meeting) | 04-Nov-24 A | 04-Nov-24 | 07-Nov-24 A | 07-Nov-24 | 5 | 0 | 3 | 100% |  | Completed
W772LT | W772 | W772LT.T1230 | DNB Pull Harder Safety Case | <Specification for Pull Harder Facility> - EAN / Report Completed | 04-Nov-24 A | 04-Nov-24 | 04-Nov-24 A | 04-Nov-24 | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.3670 | HRA Enhanced Defueling Safety Case | Verify | 05-Nov-24 A | 05-Nov-24 | 02-Jan-25 A | 02-Jan-25 | 10 | 0 | 39 | 100% |  | Completed
ER6701LT | W228 | W228.3670 | HYA Enhanced Defueling Safety Case | Verify | 05-Nov-24 A | 05-Nov-24 | 02-Jan-25 A | 02-Jan-25 | 10 | 0 | 39 | 100% |  | Completed
ER6372LT | W203 | W203.D1000 | HNB Enhanced Defuelling Safety Cases | Issue PRC Paper to PRC Members | 06-Nov-24 A | 06-Nov-24 | 06-Nov-24 A | 06-Nov-24 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1100 | HNB Enhanced Defuelling Safety Cases | PRC Members Review IRM Documentation | 06-Nov-24 A | 06-Nov-24 | 12-Nov-24 A | 12-Nov-24 | 5 | 0 | 5 | 100% |  | Completed
W772LT | W772 | W772LT.D3090 | DNB Pull Harder Safety Case | Gate A PRC Paper Submission | 06-Nov-24 A | 06-Nov-24 | 06-Nov-24 A | 06-Nov-24 | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.D3100 | DNB Pull Harder Safety Case | PRC Members Review PRC Documentation | 06-Nov-24 A | 06-Nov-24 | 12-Nov-24 A | 12-Nov-24 | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.2010 | DNB Enhanced Safety Cases | >>>OUTGOING ENABLER DNB Enhanced Safety Case Station Approved - Rev 000 | 07-Nov-24 A | 07-Nov-24 | 07-Nov-24 A | 07-Nov-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1070 | DNB Enhanced Safety Cases | All Safety Cases Approved - Rev 000 (FEED TO SUMMARY SCHEDULE) | 07-Nov-24 A | 07-Nov-24 | 07-Nov-24 A | 07-Nov-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2480 | DNB Enhanced Safety Cases | Rev 000 - Station Approval Obtained and CAT 2 Safety Case Complete *(KDM)* | 07-Nov-24 A | 07-Nov-24 | 07-Nov-24 A | 07-Nov-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5390 | DNB Enhanced Safety Cases | Issue agreed work programme to stakeholders & suppliers | 07-Nov-24 A | 07-Nov-24 | 07-Nov-24 A | 07-Nov-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5400 | DNB Enhanced Safety Cases | Develop plan with further iterations and confirm approval from key stakeholders | 07-Nov-24 A | 07-Nov-24 | 18-Dec-24 A | 18-Dec-24 | 10 | 0 | 29 | 100% |  | Completed
W232LT | W232 | W232.A5420 | DNB Enhanced Safety Cases | Key Stakeholders Identified | 07-Nov-24 A | 07-Nov-24 | 07-Nov-24 A | 07-Nov-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5430 | DNB Enhanced Safety Cases | CA PJB Held | 07-Nov-24 A | 07-Nov-24 | 07-Nov-24 A | 07-Nov-24 | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A1037 | DNB Pull Harder Safety Case | Incorporate INSA, Station, DA (peer) comments | 08-Nov-24 A | 08-Nov-24 | 21-Nov-24 A | 21-Nov-24 | 10 | 0 | 9 | 100% |  | Completed
W772LT | W772 | W772.A1000 | DNB Pull Harder Safety Case | Discovery Milestone: Human Factors Confirm Requirements | 08-Nov-24 A | 08-Nov-24 | 08-Nov-24 A | 08-Nov-24 | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.1380 | HRA Reactors Shutdown Essential Safety Cases | Review of Reactor Ess Safety Case 1 - (INSA) Lessons Learnt Review Complete | 11-Nov-24 A | 11-Nov-24 | 11-Nov-24 A | 11-Nov-24 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.1380 | HYA Reactors Shutdown Essential Safety Cases | Review of Reactor Ess Safety Case 1 - (INSA) Lessons Learnt Review Complete | 11-Nov-24 A | 11-Nov-24 | 11-Nov-24 A | 11-Nov-24 | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2130 | DNB Pull Harder Safety Case | <Human Factors> - Advice and Review | 11-Nov-24 A | 11-Nov-24 | 17-Dec-24 A | 17-Dec-24 | 20 | 0 | 26 | 100% |  | Completed
ER6650LT | W226 | W226.1380 | HYA Fuel Handling Essential Safety Case | Review of Reactor Ess Safety Case 1 - Lessons Learnt Review Complete | 11-Nov-24 A | 11-Nov-24 | 11-Nov-24 A | 11-Nov-24 | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.1385 | HRA Fuel Handling Essential Safety Case | INSA Final Approval - Lessons Learnt Review Complete | 11-Nov-24 A | 11-Nov-24 | 11-Nov-24 A | 11-Nov-24 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.1385 | HYA Fuel Handling Essential Safety Case | INSA Final Approval - Lessons Learnt Review Complete | 11-Nov-24 A | 11-Nov-24 | 11-Nov-24 A | 11-Nov-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1930 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><FPU Handling with Uninspected Welds item 6> - Summary Bar | 12-Nov-24 A | 12-Nov-24 | 12-Nov-24 A | 12-Nov-24 | 29 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1940 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><FPU Handling with Uninspected Welds item 6> - Draft and issue RFS | 12-Nov-24 A | 12-Nov-24 | 12-Nov-24 A | 12-Nov-24 | 10 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1950 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><FPU Handling with Uninspected Welds item 6> - Supplier prepare and issue Offer | 12-Nov-24 A | 12-Nov-24 | 12-Nov-24 A | 12-Nov-24 | 8 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1960 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><FPU Handling with Uninspected Welds item 6> - Review Offer, prepare and issue CI | 12-Nov-24 A | 12-Nov-24 | 12-Nov-24 A | 12-Nov-24 | 5 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1970 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><FPU Handling with Uninspected Welds item 6> - Supplier mobilisation time | 12-Nov-24 A | 12-Nov-24 | 12-Nov-24 A | 12-Nov-24 | 5 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1980 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><FPU Handling with Uninspected Welds item 6> - Pre Job Brief | 12-Nov-24 A | 12-Nov-24 | 12-Nov-24 A | 12-Nov-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2170 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><ESA Handling with OEM NSPs item 8> - Summary Bar | 12-Nov-24 A | 12-Nov-24 | 12-Nov-24 A | 12-Nov-24 | 29 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2180 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><ESA Handling with OEM NSPs item 8> - Draft and issue RFS | 12-Nov-24 A | 12-Nov-24 | 12-Nov-24 A | 12-Nov-24 | 10 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2190 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><ESA Handling with OEM NSPs item 8> - Supplier prepare and issue Offer | 12-Nov-24 A | 12-Nov-24 | 12-Nov-24 A | 12-Nov-24 | 8 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2200 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><ESA Handling with OEM NSPs item 8> - Review Offer, prepare and issue CI | 12-Nov-24 A | 12-Nov-24 | 12-Nov-24 A | 12-Nov-24 | 5 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2210 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><ESA Handling with OEM NSPs item 8> - Supplier mobilisation time | 12-Nov-24 A | 12-Nov-24 | 12-Nov-24 A | 12-Nov-24 | 5 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2220 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><ESA Handling with OEM NSPs item 8> - Pre Job Brief | 12-Nov-24 A | 12-Nov-24 | 12-Nov-24 A | 12-Nov-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2410 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 10> - Summary Bar | 12-Nov-24 A | 12-Nov-24 | 12-Nov-24 A | 12-Nov-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2420 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 10> - Draft and issue RFS | 12-Nov-24 A | 12-Nov-24 | 12-Nov-24 A | 12-Nov-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2430 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 10> - Supplier prepare and issue Offer | 12-Nov-24 A | 12-Nov-24 | 12-Nov-24 A | 12-Nov-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2440 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 10> - Review Offer, prepare and issue CI | 12-Nov-24 A | 12-Nov-24 | 12-Nov-24 A | 12-Nov-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2450 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 10> - Supplier mobilisation time | 12-Nov-24 A | 12-Nov-24 | 12-Nov-24 A | 12-Nov-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2460 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 10> - Pre Job Brief | 12-Nov-24 A | 12-Nov-24 | 12-Nov-24 A | 12-Nov-24 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2740 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 13> - Summary Bar | 12-Nov-24 A | 12-Nov-24 | 12-Nov-24 A | 12-Nov-24 | 29 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2750 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 13> - Draft and issue RFS | 12-Nov-24 A | 12-Nov-24 | 12-Nov-24 A | 12-Nov-24 | 10 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2760 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 13> - Supplier prepare and issue Offer | 12-Nov-24 A | 12-Nov-24 | 12-Nov-24 A | 12-Nov-24 | 8 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2770 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 13> - Review Offer, prepare and issue CI | 12-Nov-24 A | 12-Nov-24 | 12-Nov-24 A | 12-Nov-24 | 5 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2780 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 13> - Supplier mobilisation time | 12-Nov-24 A | 12-Nov-24 | 12-Nov-24 A | 12-Nov-24 | 5 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2790 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 13> - Pre Job Brief | 12-Nov-24 A | 12-Nov-24 | 12-Nov-24 A | 12-Nov-24 | 1 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772.A1010 | DNB Pull Harder Safety Case | <S'standt'n of Funct'l Cap of PWTS and DWTS at the Enh'ed Overload Trip Settings> - Prepare Draft EAN / Report | 13-Nov-24 A | 13-Nov-24 | 14-Feb-25 A | 14-Feb-25 | 20 | 0 | 65 | 100% |  | Completed
W232LT | W232 | W232.C2890 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Summary | 14-Nov-24 A | 14-Nov-24 | 14-Nov-24 A | 14-Nov-24 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C2900 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Prepare Draft EAN | 14-Nov-24 A | 14-Nov-24 | 14-Nov-24 A | 14-Nov-24 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C2910 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Issue Draft EAN to EDF for Review. | 14-Nov-24 A | 14-Nov-24 | 14-Nov-24 A | 14-Nov-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C2920 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Draft EAN Reviewed by EDF SQEP | 14-Nov-24 A | 14-Nov-24 | 14-Nov-24 A | 14-Nov-24 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C2930 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Address Comments from EDF Review on Draft EAN | 14-Nov-24 A | 14-Nov-24 | 14-Nov-24 A | 14-Nov-24 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C2940 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Issue Final EAN | 14-Nov-24 A | 14-Nov-24 | 14-Nov-24 A | 14-Nov-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C2950 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - EAN Completed and Uploaded to CDMS | 14-Nov-24 A | 14-Nov-24 | 14-Nov-24 A | 14-Nov-24 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C2960 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - EAN Completed | 14-Nov-24 A | 14-Nov-24 | 14-Nov-24 A | 14-Nov-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C2970 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Summary Bar | 14-Nov-24 A | 14-Nov-24 | 14-Nov-24 A | 14-Nov-24 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C2980 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Draft and issue RFS | 14-Nov-24 A | 14-Nov-24 | 14-Nov-24 A | 14-Nov-24 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C2990 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Supplier prepare and issue Offer | 14-Nov-24 A | 14-Nov-24 | 14-Nov-24 A | 14-Nov-24 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3000 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Review Offer, prepare and issue CI | 14-Nov-24 A | 14-Nov-24 | 14-Nov-24 A | 14-Nov-24 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3010 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Supplier mobilisation time | 14-Nov-24 A | 14-Nov-24 | 14-Nov-24 A | 14-Nov-24 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3020 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Pre Job Brief | 14-Nov-24 A | 14-Nov-24 | 14-Nov-24 A | 14-Nov-24 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3030 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - TSA Internal Review of Draft EAN | 14-Nov-24 A | 14-Nov-24 | 14-Nov-24 A | 14-Nov-24 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5690 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events (Group 2)> - Draft Task Sheet | 14-Nov-24 A | 14-Nov-24 | 14-Nov-24 A | 14-Nov-24 | 15 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5700 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events (Group 2)> - Issue Task sheet | 14-Nov-24 A | 14-Nov-24 | 14-Nov-24 A | 14-Nov-24 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5710 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events (Group 2)> - Review Task sheet | 14-Nov-24 A | 14-Nov-24 | 14-Nov-24 A | 14-Nov-24 | 5 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5720 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events (Group 2)> - Approve Task sheet | 14-Nov-24 A | 14-Nov-24 | 14-Nov-24 A | 14-Nov-24 | 5 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5730 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events (Group 2)> - Search for station Lifetime Record | 14-Nov-24 A | 14-Nov-24 | 14-Nov-24 A | 14-Nov-24 | 20 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5740 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events (Group 2)> - Review station Lifetime Record | 14-Nov-24 A | 14-Nov-24 | 14-Nov-24 A | 14-Nov-24 | 20 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5750 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit (Group 2)>-Issue finding from Review of Lifetime Record | 14-Nov-24 A | 14-Nov-24 | 14-Nov-24 A | 14-Nov-24 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5760 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit (Grp 2)> Hold scoping session with DA, SAG and Station | 14-Nov-24 A | 14-Nov-24 | 14-Nov-24 A | 14-Nov-24 | 5 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5770 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events (Group 2)> - Issue scope for review | 14-Nov-24 A | 14-Nov-24 | 14-Nov-24 A | 14-Nov-24 | 10 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5780 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events (Group 2)> - Approve Scope | 14-Nov-24 A | 14-Nov-24 | 14-Nov-24 A | 14-Nov-24 | 10 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 2290 | HYA Fuel Handling Essential Safety Case | ONR issue letter of No Objection | 14-Nov-24 A | 14-Nov-24 | 24-Jan-25 A | 24-Jan-25 | 37 | 0 | 45 | 100% |  | Completed
ER6698LT | W224 | W224. A1550 | HRA Enhanced Defueling Safety Case | Write & Prepare IRM Paper [Schedule, Cost, Estimates, Risks] | 18-Nov-24 A | 18-Nov-24 | 02-Jan-25 A | 02-Jan-25 | 15 | 0 | 30 | 100% |  | Completed
ER6701LT | W228 | W228. A1550 | HYA Enhanced Defueling Safety Case | Write & Prepare IRM Paper [Schedule, Cost, Estimates, Risks] | 18-Nov-24 A | 18-Nov-24 | 02-Jan-25 A | 02-Jan-25 | 15 | 0 | 30 | 100% |  | Completed
ER6372LT | W203 | W203.C1410 | HNB Enhanced Defuelling Safety Cases | Incorporate CO & Station comments | 18-Nov-24 A | 18-Nov-24 | 18-Nov-24 A | 18-Nov-24 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1420 | HNB Enhanced Defuelling Safety Cases | Produce verification file | 18-Nov-24 A | 18-Nov-24 | 18-Nov-24 A | 18-Nov-24 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1120 | HNB Enhanced Defuelling Safety Cases | Modify Estimate, Schedule & Risk Log as Required | 19-Nov-24 A | 19-Nov-24 | 19-Nov-24 A | 19-Nov-24 | 3 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A4220 | HNB Enhanced Defuelling Safety Cases | SC - Cost of Contract - Atkins realis Contract | 19-Nov-24 A | 19-Nov-24 | 17-Jan-25 A | 17-Jan-25 | 99 | 0 | 40 | 100% |  | Completed
ER6372LT | W203 | W203.D1110 | HNB Enhanced Defuelling Safety Cases | Hold PRC Meeting | 19-Nov-24 A | 19-Nov-24 | 19-Nov-24 A | 19-Nov-24 | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.E4200 | HNB Enhanced Defuelling Safety Cases | Project Management C - D | 19-Nov-24 A | 19-Nov-24 | 17-Jan-25 A | 17-Jan-25 | 101 | 0 | 40 | 100% |  | Completed
ER6372LT | W203 | W203.E1550 | HNB Enhanced Defuelling Safety Cases | Station Oversight C - D | 19-Nov-24 A | 19-Nov-24 | 17-Jan-25 A | 17-Jan-25 | 101 | 0 | 40 | 100% |  | Completed
W772LT | W772 | W772LT.D3110 | DNB Pull Harder Safety Case | Hold PRC Meeting | 19-Nov-24 A | 19-Nov-24 | 19-Nov-24 A | 19-Nov-24 | 1 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772LT.D3120 | DNB Pull Harder Safety Case | Modify Estimate, Schedule & Risk Log as Required | 19-Nov-24 A | 19-Nov-24 | 19-Nov-24 A | 19-Nov-24 | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A4210 | HNB Enhanced Defuelling Safety Cases | Gate C PRC Paper Approval | 19-Nov-24 A | 19-Nov-24 | 19-Nov-24 A | 19-Nov-24 | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.D3130 | DNB Pull Harder Safety Case | Gate A PRC Paper Approval | 19-Nov-24 A | 19-Nov-24 | 19-Nov-24 A | 19-Nov-24 | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.D2065 | DNB Pull Harder Safety Case | Gate A PRC Paper Approval | 19-Nov-24 A | 19-Nov-24 | 19-Nov-24 A | 19-Nov-24 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1290 | HNB Enhanced Defuelling Safety Cases | Agree design proposals with Station in the case of hardware mods | 20-Nov-24 A | 20-Nov-24 | 26-Nov-24 A | 26-Nov-24 | 5 | 0 | 4 | 100% |  | Completed
ER6372LT | W203 | W203.D1450 | HNB Enhanced Defuelling Safety Cases | Produce supporting reference <Generic Hoist Trip Setting Increase SC> | 20-Nov-24 A | 20-Nov-24 | 17-Dec-24 A | 17-Dec-24 | 20 | 0 | 19 | 100% |  | Completed
ER6372LT | W203 | W203.D1550 | HNB Enhanced Defuelling Safety Cases | Identify verifier for the case & establish all other resources | 20-Nov-24 A | 20-Nov-24 | 26-Nov-24 A | 26-Nov-24 | 5 | 0 | 4 | 100% |  | Completed
ER6372LT | W203 | W203.D1310 | HNB Enhanced Defuelling Safety Cases | CA to agree with CO format of the safety case & produce agreed contents page | 25-Nov-24 A | 25-Nov-24 | 26-Nov-24 A | 26-Nov-24 | 2 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772LT.A2260 | DNB Pull Harder Safety Case | <Load Path Assessment> - Summary | 25-Nov-24 A | 25-Nov-24 | 2025-04-23 | 45770 | 103 | 36 | 103 | 0% | 8 | In Progress
W772LT | W772 | W772LT.A2270 | DNB Pull Harder Safety Case | <Load Path Assessment> - Prepare Draft EAN | 25-Nov-24 A | 25-Nov-24 | 2025-03-07 | 45723 | 37 | 5 | 72 | 85% | 8 | In Progress
W232LT | W232 | W232.C3070 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events> - Summary | 26-Nov-24 A | 26-Nov-24 | 26-Nov-24 A | 26-Nov-24 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3080 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events> - Prepare Draft EAN - Group 2 | 26-Nov-24 A | 26-Nov-24 | 26-Nov-24 A | 26-Nov-24 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3090 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events> - Issue Draft EAN to EDF for Review. | 26-Nov-24 A | 26-Nov-24 | 26-Nov-24 A | 26-Nov-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3100 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events> - Draft EAN Reviewed by EDF SQEP | 26-Nov-24 A | 26-Nov-24 | 26-Nov-24 A | 26-Nov-24 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3110 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events> - Address Comments from EDF Review on | 26-Nov-24 A | 26-Nov-24 | 26-Nov-24 A | 26-Nov-24 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3120 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events> - Issue Final EAN | 26-Nov-24 A | 26-Nov-24 | 26-Nov-24 A | 26-Nov-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3130 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events> - EAN Completed and Uploaded to CDMS | 26-Nov-24 A | 26-Nov-24 | 26-Nov-24 A | 26-Nov-24 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3140 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events> - EAN Completed | 26-Nov-24 A | 26-Nov-24 | 26-Nov-24 A | 26-Nov-24 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3085 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events> - TSA Internal Review of Draft EAN | 26-Nov-24 A | 26-Nov-24 | 26-Nov-24 A | 26-Nov-24 | 1 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1220 | HNB Enhanced Defuelling Safety Cases | Produce draft NSRS (using BARRIER MODEL) | 27-Nov-24 A | 27-Nov-24 | 03-Dec-24 A | 03-Dec-24 | 5 | 0 | 4 | 100% |  | Completed
ER6372LT | W203 | W203.D1340 | HNB Enhanced Defuelling Safety Cases | Produce verification plan | 27-Nov-24 A | 27-Nov-24 | 28-Nov-24 A | 28-Nov-24 | 2 | 0 | 1 | 100% |  | Completed
W230LT | W230 | W230.2010 | HYB Enhanced Defueling Safety Case Strategy | TSA Issue Final Report | 27-Nov-24 A | 27-Nov-24 | 18-Dec-24 A | 18-Dec-24 | 1 | 0 | 16 | 100% |  | Completed
W234LT | W234 | W234.2010 | TOR Enhanced Defueling Safety Case Strategy | TSA Issue Final Report | 27-Nov-24 A | 27-Nov-24 | 18-Dec-24 A | 18-Dec-24 | 1 | 0 | 16 | 100% |  | Completed
W232LT | W232 | W232.A2420 | DNB Enhanced Safety Cases | Rev 000 - Post Job Debrief | 28-Nov-24 A | 28-Nov-24 | 28-Nov-24 A | 28-Nov-24 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5030 | DNB Enhanced Safety Cases | Lessons Learned Workshop - FPU Safety Case Ph 3 Rev 000 Station approved | 28-Nov-24 A | 28-Nov-24 | 28-Nov-24 A | 28-Nov-24 | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5220 | DNB Enhanced Safety Cases | Lessons Learned Workshop - FPU Safety Case Ph 3 Rev 000 INSA | 28-Nov-24 A | 28-Nov-24 | 28-Nov-24 A | 28-Nov-24 | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A27130 | HRA Fuel Handling Essential Safety Case | ETC (DD-PF) 2024 | 02-Dec-24 A | 02-Dec-24 | 31-Dec-24 A | 31-Dec-24 | 20 | 0 | 20 | 100% |  | Completed
ER6650LT | W226 | W226.A27130 | HYA Fuel Handling Essential Safety Case | ETC (DD-PF) 2024 | 02-Dec-24 A | 02-Dec-24 | 31-Dec-24 A | 31-Dec-24 | 20 | 0 | 20 | 100% |  | Completed
W520LT | W520 | W520.A1030 | FLEETWIDE CTO Defueling Safety Case Delivery | 2024 Costs | 02-Dec-24 A | 02-Dec-24 | 27-Dec-24 A | 27-Dec-24 | 18 | 0 | 18 | 100% |  | Completed
W520LT | W520 | W520.A1290 | FLEETWIDE CTO Defueling Safety Case Delivery | ETC (DD-PF) 2024 | 02-Dec-24 A | 02-Dec-24 | 02-Dec-24 A | 02-Dec-24 | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.T1270 | DNB Pull Harder Safety Case | <Operating Strategy for Pull Harder Facility> - Draft EAN / Report Tech Reviewed by EDF SQEP | 02-Dec-24 A | 02-Dec-24 | 13-Dec-24 A | 13-Dec-24 | 10 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.C3410 | DNB Enhanced Safety Cases | <NEW SCOPE CN3472> Scoping of Requirement | 02-Dec-24 A | 02-Dec-24 | 31-Dec-24 A | 31-Dec-24 | 18 | 0 | 19 | 100% |  | Completed
ER6372LT | W203 | W203.D1230 | HNB Enhanced Defuelling Safety Cases | Station comments on NSRS | 04-Dec-24 A | 04-Dec-24 | 13-Dec-24 A | 13-Dec-24 | 8 | 0 | 7 | 100% |  | Completed
ER6372LT | W203 | W203.D1240 | HNB Enhanced Defuelling Safety Cases | Key Stakeholders (Peer) comments on NSRS (as required) | 04-Dec-24 A | 04-Dec-24 | 13-Dec-24 A | 13-Dec-24 | 8 | 0 | 7 | 100% |  | Completed
W772LT | W772 | W772LT.KDM.A1047-1 | DNB Pull Harder Safety Case | KDM - <NEW SCOPE CN 3373> - NSRS presented at NSC | 04-Dec-24 A | 04-Dec-24 | 04-Dec-24 A | 04-Dec-24 | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A1047 | DNB Pull Harder Safety Case | <NEW SCOPE CN 3373> - NSRS presented at NSC | 04-Dec-24 A | 04-Dec-24 | 04-Dec-24 A | 04-Dec-24 | 1 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772.A1110 | DNB Pull Harder Safety Case | <New SCOPE PENDING CN3634> - <Cavendish PWTS Funct Capability Report> - Produce Report | 05-Dec-24 A | 05-Dec-24 | 06-Jan-25 A | 06-Jan-25 | 1 | 0 | 20 | 100% |  | Completed
W772LT | W772 | W772LT.A1057 | DNB Pull Harder Safety Case | <NEW SCOPE CN 3373> - Address NSC Comments | 05-Dec-24 A | 05-Dec-24 | 18-Dec-24 A | 18-Dec-24 | 10 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.C1840 | DNB Enhanced Safety Cases | <SCOPE CHANGE CN3472><FPU Uninspected Welds lifting integrity (including sub-veto faults)> - Summary | 06-Dec-24 A | 06-Dec-24 | 2025-09-05 | 45905 | 188 | 130 | 188 | 0% | 5 | In Progress
W232LT | W232 | W232.C3150 | DNB Enhanced Safety Cases | <NEW SCOPE CN3472> - Review faults | 06-Dec-24 A | 06-Dec-24 | 10-Jan-25 A | 10-Jan-25 | 14 | 0 | 22 | 100% |  | Completed
W232LT | W232 | W232.C3330 | DNB Enhanced Safety Cases | <NEW SCOPE CN3472> Review Technical note to be issued to SAG | 06-Dec-24 A | 06-Dec-24 | 10-Jan-25 A | 10-Jan-25 | 11 | 0 | 23 | 100% |  | Completed
W232LT | W232 | W232.A5470 | DNB Enhanced Safety Cases | Draft task sheet | 06-Dec-24 A | 06-Dec-24 | 24-Jan-25 A | 24-Jan-25 | 33 | 0 | 33 | 100% |  | Completed
W232LT | W232 | W232.C3325 | DNB Enhanced Safety Cases | <SCOPE CHANGE CN3472><NSP Pin Failure> - Summary | 06-Dec-24 A | 06-Dec-24 | 2025-08-07 | 45876 | 168 | 110 | 168 | 0% | 25 | In Progress
ER6666LT | W209 | W209.1545 | HYB Essential Defueling Safety Case | Incorporate INSA comments | 09-Dec-24 A | 09-Dec-24 | 19-Feb-25 A | 19-Feb-25 | 22 | 0 | 50 | 100% |  | Completed
ER6668LT | W213 | W213.1545 | TOR Essential Defueling Safety Case | Incorporate INSA comments | 09-Dec-24 A | 09-Dec-24 | 19-Feb-25 A | 19-Feb-25 | 27 | 0 | 49 | 100% |  | Completed
ER6372LT | W203 | W203.D1730 | HNB Enhanced Defuelling Safety Cases | INSA Resource Identified | 13-Dec-24 A | 13-Dec-24 | 13-Dec-24 A | 13-Dec-24 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1580 | HNB Enhanced Defuelling Safety Cases | INA comments on NSRS | 16-Dec-24 A | 16-Dec-24 | 20-Dec-24 A | 20-Dec-24 | 5 | 0 | 4 | 100% |  | Completed
W772LT | W772 | W772LT.T1280 | DNB Pull Harder Safety Case | <Operating Strategy for Pull Harder Facility> - Address Comments from EDF Review on Draft EAN / Report | 16-Dec-24 A | 16-Dec-24 | 28-Feb-25 A | 28-Feb-25 | 5 | 0 | 51 | 100% |  | Completed
ER6372LT | W203 | W203.D1640 | HNB Enhanced Defuelling Safety Cases | Develop plan with further iterations | 17-Dec-24 A | 17-Dec-24 | 02-Jan-25 A | 02-Jan-25 | 10 | 0 | 9 | 100% |  | Completed
W772LT | W772 | W772LT.A2140 | DNB Pull Harder Safety Case | <Human Factors> - Populate HF Template | 17-Dec-24 A | 17-Dec-24 | 17-Dec-24 A | 17-Dec-24 | 5 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1600 | HNB Enhanced Defuelling Safety Cases | Verify supporting reference <Generic Hoist Trip Setting Increase SC> | 18-Dec-24 A | 18-Dec-24 | 03-Jan-25 A | 03-Jan-25 | 10 | 0 | 9 | 100% |  | Completed
W772LT | W772 | W772LT.A1125 | DNB Pull Harder Safety Case | Proposal - Preliminary Work | 18-Dec-24 A | 18-Dec-24 | 06-Jan-25 A | 06-Jan-25 | 26 | 0 | 11 | 100% |  | Completed
W232LT | W232 | W232.C1850 | DNB Enhanced Safety Cases | <SCOPE CHANGE CN3472><FPU Uninspected Welds lifting integrity (including sub-veto faults)> - Prepare Draft EAN Part 1 | 19-Dec-24 A | 19-Dec-24 | 23-Jan-25 A | 23-Jan-25 | 20 | 0 | 22 | 100% |  | Completed
W772LT | W772 | W772LT.KDM.A1067-1 | DNB Pull Harder Safety Case | KDM - <NEW SCOPE CN 3373> - Final INSA Approval and Re-sign Milestones | 19-Dec-24 A | 19-Dec-24 | 19-Dec-24 A | 19-Dec-24 | 0 | 0 | 0 | 100% |  | Completed
W230LT | W230 | W230.2020 | HYB Enhanced Defueling Safety Case Strategy | TR Completed and Uploaded to CDMS | 19-Dec-24 A | 19-Dec-24 | 20-Dec-24 A | 20-Dec-24 | 2 | 0 | 2 | 100% |  | Completed
W772LT | W772 | W772LT.A1040 | DNB Pull Harder Safety Case | Issue final NSRS | 19-Dec-24 A | 19-Dec-24 | 19-Dec-24 A | 19-Dec-24 | 1 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772LT.A1050 | DNB Pull Harder Safety Case | Station agree NSRS ==> KDM | 19-Dec-24 A | 19-Dec-24 | 19-Dec-24 A | 19-Dec-24 | 10 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772LT.A1235 | DNB Pull Harder Safety Case | Circulate NSRS for Relevant Stakeholders | 19-Dec-24 A | 19-Dec-24 | 19-Dec-24 A | 19-Dec-24 | 5 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772LT.A1230 | DNB Pull Harder Safety Case | DA & INSA agree NSRS (for authorised designers-NSRS must be reviewed by DA) ==> KDM | 19-Dec-24 A | 19-Dec-24 | 19-Dec-24 A | 19-Dec-24 | 10 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772LT.A1500 | DNB Pull Harder Safety Case | Send NSRS to ONR to determine level of review required (Acknowledgement or Agreement) | 19-Dec-24 A | 19-Dec-24 | 19-Dec-24 A | 19-Dec-24 | 1 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772LT.A1510 | DNB Pull Harder Safety Case | ONR L4 Meeting | 19-Dec-24 A | 19-Dec-24 | 19-Dec-24 A | 19-Dec-24 | 1 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772LT.A1067 | DNB Pull Harder Safety Case | <NEW SCOPE CN 3373> - Final INSA Approval and Re-sign Milestones | 19-Dec-24 A | 19-Dec-24 | 19-Dec-24 A | 19-Dec-24 | 12 | 0 | 1 | 100% |  | Completed
W234LT | W234 | W234.2020 | TOR Enhanced Defueling Safety Case Strategy | TR Completed and Uploaded to CDMS | 19-Dec-24 A | 19-Dec-24 | 20-Dec-24 A | 20-Dec-24 | 2 | 0 | 2 | 100% |  | Completed
W772LT | W772 | W772LT.KDM.SP02 | DNB Pull Harder Safety Case | KDM - NSRS agreed by stakeholders EC 375698 <DNB Pull Harder SC> | 19-Dec-24 A | 19-Dec-24 | 19-Dec-24 A | 19-Dec-24 | 0 | 0 | 0 | 100% |  | Completed
W230LT | W230 | W230.1900 | HYB Enhanced Defueling Safety Case Strategy | EC Kick Off Meeting & Early Strategy Development | 20-Dec-24 A | 20-Dec-24 | 20-Dec-24 A | 20-Dec-24 | 2 | 0 | 1 | 100% |  | Completed
W230LT | W230 | W230.3760 | HYB Enhanced Defueling Safety Case Strategy | HYB Enhanced Defueling Rate: Strategy EAN Complete | 20-Dec-24 A | 20-Dec-24 | 20-Dec-24 A | 20-Dec-24 | 0 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.1900 | TOR Enhanced Defueling Safety Case Strategy | EC Kick Off Meeting & Early Strategy Development | 20-Dec-24 A | 20-Dec-24 | 20-Dec-24 A | 20-Dec-24 | 2 | 0 | 1 | 100% |  | Completed
W234LT | W234 | W234.3760 | TOR Enhanced Defueling Safety Case Strategy | TOR Enhanced Defueling Rate: Strategy EAN Complete | 20-Dec-24 A | 20-Dec-24 | 20-Dec-24 A | 20-Dec-24 | 0 | 0 | 0 | 100% |  | Completed
W230LT | W230 | W230.2030 | HYB Enhanced Defueling Safety Case Strategy | Strategy EAN Complete | 20-Dec-24 A | 20-Dec-24 | 20-Dec-24 A | 20-Dec-24 | 0 | 0 | 0 | 100% |  | Completed
W230LT | W230 | W230.3740 | HYB Enhanced Defueling Safety Case Strategy | HYB - EC Kick Off Meeting & Early Strategy Development | 20-Dec-24 A | 20-Dec-24 | 20-Dec-24 A | 20-Dec-24 | 0 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.2030 | TOR Enhanced Defueling Safety Case Strategy | Strategy EAN Complete | 20-Dec-24 A | 20-Dec-24 | 20-Dec-24 A | 20-Dec-24 | 0 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.3740 | TOR Enhanced Defueling Safety Case Strategy | TOR - EC Kick Off Meeting & Early Strategy Development | 20-Dec-24 A | 20-Dec-24 | 20-Dec-24 A | 20-Dec-24 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1420 | HNB Enhanced Defuelling Safety Cases | Incorporate INA, Station, ED (peer) comments | 23-Dec-24 A | 23-Dec-24 | 31-Dec-24 A | 31-Dec-24 | 5 | 0 | 4 | 100% |  | Completed
W232LT | W232 | W232.A5050 | DNB Enhanced Safety Cases | <SCOPE CHANGE CN3472> Rev 001 - Prepare the Safety Case Proposal (including OPEX Review) | 02-Jan-25 A | 02-Jan-25 | 2025-09-19 | 45919 | 45 | 33 | 182 | 0% | 5 | In Progress
W232LT | W232 | W232.C2230 | DNB Enhanced Safety Cases | <SCOPE NAME CHANGE CN3472><FPU and ESA Handling with OEM NSPs> - Summary | 02-Jan-25 A | 02-Jan-25 | 2025-08-06 | 45875 | 109 | 104 | 151 | 0% | 26 | In Progress
W232LT | W232 | W232.C2240 | DNB Enhanced Safety Cases | <SCOPE NAME CHANGE CN3472><FPU and ESA Handling with OEM NSPs> - Prepare Draft EAN Part1 | 02-Jan-25 A | 02-Jan-25 | 2025-03-24 | 45740 | 20 | 0 | 57 | 50% | 6 | In Progress
ER6701LT | W228 | W228.2220 | HYA Enhanced Defueling Safety Case | Contract Negotiations | 02-Jan-25 A | 02-Jan-25 | 03-Feb-25 A | 03-Feb-25 | 1 | 0 | 23 | 100% |  | Completed
ER6372LT | W203 | W203.D1250 | HNB Enhanced Defuelling Safety Cases | Issue final NSRS | 02-Jan-25 A | 02-Jan-25 | 02-Jan-25 A | 02-Jan-25 | 1 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1260 | HNB Enhanced Defuelling Safety Cases | Station agree NSRS *(KDM)* <Generic Hoist Trip Setting Increase EC375945> | 02-Jan-25 A | 02-Jan-25 | 02-Jan-25 A | 02-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1720 | HNB Enhanced Defuelling Safety Cases | Verifier PJB Held | 02-Jan-25 A | 02-Jan-25 | 02-Jan-25 A | 02-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5570 | DNB Enhanced Safety Cases | <NEW SCOPE PENDING CN3754> - Prepare and Populate Affected Documents List Rev 000 | 02-Jan-25 A | 02-Jan-25 | 2025-03-07 | 45723 | 10 | 5 | 47 | 1% | 244 | In Progress
ER6372LT | W203 | W203.C1460 | HNB Enhanced Defuelling Safety Cases | Issue high quality verified draft iss A with verification file to INSA & station (T - 3 wks before NSC date) *(E375412)* | 02-Jan-25 A | 02-Jan-25 | 02-Jan-25 A | 02-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1480 | HNB Enhanced Defuelling Safety Cases | INSA review & iteration of comments (using BARRIER MODEL) | 02-Jan-25 A | 02-Jan-25 | 04-Feb-25 A | 04-Feb-25 | 6 | 0 | 23 | 100% |  | Completed
ER6372LT | W203 | W203.C1430 | HNB Enhanced Defuelling Safety Cases | Verification complete | 02-Jan-25 A | 02-Jan-25 | 02-Jan-25 A | 02-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1440 | HNB Enhanced Defuelling Safety Cases | Submit for approval - Categoriser ratifies; RE/CO endorsement | 02-Jan-25 A | 02-Jan-25 | 02-Jan-25 A | 02-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1470 | HNB Enhanced Defuelling Safety Cases | Key Stakeholders Approval, if requested | 02-Jan-25 A | 02-Jan-25 | 10-Jan-25 A | 10-Jan-25 | 7 | 0 | 7 | 100% |  | Completed
ER6378LT | W222 | W222.A27475 | HRA Fuel Handling Essential Safety Case | ETC (DD-PF) 2025 | 02-Jan-25 A | 02-Jan-25 | 2025-03-31 | 45747 | 63 | 21 | 63 | 50% | 0 | In Progress
ER6650LT | W226 | W226.A27475 | HYA Fuel Handling Essential Safety Case | ETC (DD-PF) 2025 | 02-Jan-25 A | 02-Jan-25 | 2025-03-31 | 45747 | 63 | 21 | 63 | 50% | 0 | In Progress
ER6698LT | W224 | W224.1230 | HRA Enhanced Defueling Safety Case | Design Feedback into Scheme | 02-Jan-25 A | 02-Jan-25 | 08-Jan-25 A | 08-Jan-25 | 5 | 0 | 5 | 100% |  | Completed
ER6698LT | W224 | W224.1310 | HRA Enhanced Defueling Safety Case | HAZOP - Feed into CETS (trip Function) | 02-Jan-25 A | 02-Jan-25 | 02-Jan-25 A | 02-Jan-25 | 1 | 0 | 1 | 100% |  | Completed
ER6698LT | W224 | W224.1530 | HRA Enhanced Defueling Safety Case | Review & Approval | 02-Jan-25 A | 02-Jan-25 | 15-Jan-25 A | 15-Jan-25 | 10 | 0 | 10 | 100% |  | Completed
ER6698LT | W224 | W224.2220 | HRA Enhanced Defueling Safety Case | Contract Negotiations | 02-Jan-25 A | 02-Jan-25 | 03-Feb-25 A | 03-Feb-25 | 9 | 0 | 22 | 100% |  | Completed
ER6698LT | W224 | W224.2580 | HRA Enhanced Defueling Safety Case | Author CETS CETS for Trip Functions | 02-Jan-25 A | 02-Jan-25 | 2025-03-07 | 45723 | 10 | 5 | 47 | 89% | 26 | In Progress
ER6698LT | W224 | W224. A1560 | HRA Enhanced Defueling Safety Case | IRM Paper Stakeholder Sign Off | 02-Jan-25 A | 02-Jan-25 | 06-Jan-25 A | 06-Jan-25 | 8 | 0 | 2 | 100% |  | Completed
ER6698LT | W224 | W224.1240 | HRA Enhanced Defueling Safety Case | TR of Optioneering | 02-Jan-25 A | 02-Jan-25 | 2025-03-03 | 45719 | 10 | 1 | 43 | 100% | 30 | In Progress
ER6698LT | W224 | W224.3680 | HRA Enhanced Defueling Safety Case | EdF Technical Review | 02-Jan-25 A | 02-Jan-25 | 31-Jan-25 A | 31-Jan-25 | 11 | 0 | 21 | 100% |  | Completed
ER6701LT | W228 | W228.3680 | HYA Enhanced Defueling Safety Case | EdF Technical Review | 02-Jan-25 A | 02-Jan-25 | 28-Jan-25 A | 28-Jan-25 | 11 | 0 | 18 | 100% |  | Completed
ER6701LT | W228 | W228.1240 | HYA Enhanced Defueling Safety Case | TR of Optioneering | 02-Jan-25 A | 02-Jan-25 | 2025-03-03 | 45719 | 10 | 1 | 43 | 97% | 30 | In Progress
ER6701LT | W228 | W228. A1560 | HYA Enhanced Defueling Safety Case | IRM Paper stakeholder sign off | 02-Jan-25 A | 02-Jan-25 | 06-Jan-25 A | 06-Jan-25 | 8 | 0 | 2 | 100% |  | Completed
ER6701LT | W228 | W228.2580 | HYA Enhanced Defueling Safety Case | Author CETS for Trip Functions | 02-Jan-25 A | 02-Jan-25 | 2025-03-07 | 45723 | 10 | 5 | 47 | 89% | 26 | In Progress
ER6701LT | W228 | W228.1530 | HYA Enhanced Defueling Safety Case | Review & Approval | 02-Jan-25 A | 02-Jan-25 | 15-Jan-25 A | 15-Jan-25 | 10 | 0 | 10 | 100% |  | Completed
ER6701LT | W228 | W228.1310 | HYA Enhanced Defueling Safety Case | HAZOP - Feed into CETS (trip Function) | 02-Jan-25 A | 02-Jan-25 | 02-Jan-25 A | 02-Jan-25 | 1 | 0 | 1 | 100% |  | Completed
ER6701LT | W228 | W228.1230 | HYA Enhanced Defueling Safety Case | Design Feedback into Scheme | 02-Jan-25 A | 02-Jan-25 | 08-Jan-25 A | 08-Jan-25 | 5 | 0 | 5 | 100% |  | Completed
ER6372LT | W203 | W203.D1210 | HNB Enhanced Defuelling Safety Cases | Produce MF (as required) | 02-Jan-25 A | 02-Jan-25 | 02-Jan-25 A | 02-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1400 | HNB Enhanced Defuelling Safety Cases | Issue MF (as required) | 02-Jan-25 A | 02-Jan-25 | 02-Jan-25 A | 02-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1520 | HNB Enhanced Defuelling Safety Cases | Categorisation by RE / Station | 02-Jan-25 A | 02-Jan-25 | 08-Jan-25 A | 08-Jan-25 | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.C3420 | DNB Enhanced Safety Cases | <NEW SCOPE CN3472> Draft SCDP | 02-Jan-25 A | 02-Jan-25 | 07-Jan-25 A | 07-Jan-25 | 14 | 0 | 3 | 100% |  | Completed
ER6372LT | W203 | W203.D1430 | HNB Enhanced Defuelling Safety Cases | NSORC agree NSRS (SZB Only) | 02-Jan-25 A | 02-Jan-25 | 02-Jan-25 A | 02-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1440 | HNB Enhanced Defuelling Safety Cases | Key Stakeholders agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 02-Jan-25 A | 02-Jan-25 | 02-Jan-25 A | 02-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1590 | HNB Enhanced Defuelling Safety Cases | INA agree NSRS | 02-Jan-25 A | 02-Jan-25 | 02-Jan-25 A | 02-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1300 | HNB Enhanced Defuelling Safety Cases | Consolidate & issue to stakeholders & suppliers agreed NSRS (as required) | 03-Jan-25 A | 03-Jan-25 | 09-Jan-25 A | 09-Jan-25 | 5 | 0 | 4 | 100% |  | Completed
ER6372LT | W203 | W203.D1610 | HNB Enhanced Defuelling Safety Cases | BE Technical review of supporting reference <Generic Hoist Trip Setting Increase SC> | 06-Jan-25 A | 06-Jan-25 | 17-Jan-25 A | 17-Jan-25 | 10 | 0 | 9 | 100% |  | Completed
W772LT | W772 | W772.A1120 | DNB Pull Harder Safety Case | <New SCOPE PENDING CN3634> - <Cavendish PWTS Report> - EDF TR Round 1 | 06-Jan-25 A | 06-Jan-25 | 10-Jan-25 A | 10-Jan-25 | 1 | 0 | 5 | 100% |  | Completed
W772LT | W772 | W772LT.A1145 | DNB Pull Harder Safety Case | Pre Job Brief | 06-Jan-25 A | 06-Jan-25 | 06-Jan-25 A | 06-Jan-25 | 10 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772LT.A1130 | DNB Pull Harder Safety Case | Prepare the Safety Case Proposal | 07-Jan-25 A | 07-Jan-25 | 2025-04-29 | 45776 | 40 | 35 | 79 | 50% | 4 | In Progress
ER6698LT | W224 | W224. A1570 | HRA Enhanced Defueling Safety Case | Gate B-D PRC Paper Submission | 08-Jan-25 A | 08-Jan-25 | 08-Jan-25 A | 08-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3430 | DNB Enhanced Safety Cases | <NEW SCOPE CN3472> Review SCDP | 08-Jan-25 A | 08-Jan-25 | 16-Jan-25 A | 16-Jan-25 | 10 | 0 | 6 | 100% |  | Completed
ER6372LT | W203 | W203.D1560 | HNB Enhanced Defuelling Safety Cases | Issue agreed work programme to stakeholders & suppliers | 09-Jan-25 A | 09-Jan-25 | 09-Jan-25 A | 09-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1410 | HNB Enhanced Defuelling Safety Cases | INSA agree MF (as required) *(KDM)* <Generic Hoist Trip Setting Increase EC375945> | 09-Jan-25 A | 09-Jan-25 | 10-Jan-25 A | 10-Jan-25 | 2 | 0 | 2 | 100% |  | Completed
W772LT | W772 | W772.A1130 | DNB Pull Harder Safety Case | <New SCOPE PENDING CN3634> - <Cavendish PWTS Report> - Address Comments | 10-Jan-25 A | 10-Jan-25 | 28-Jan-25 A | 28-Jan-25 | 1 | 0 | 13 | 100% |  | Completed
W232LT | W232 | W232.C3160 | DNB Enhanced Safety Cases | <NEW SCOPE CN3472> - Draft specification of R6 assessment to be issue to SAG will include OEM NSPs | 10-Jan-25 A | 10-Jan-25 | 13-Jan-25 A | 13-Jan-25 | 14 | 0 | 2 | 100% |  | Completed
ER6372LT | W203 | W203.D1650 | HNB Enhanced Defuelling Safety Cases | INSA Approval Date Identified | 10-Jan-25 A | 10-Jan-25 | 10-Jan-25 A | 10-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1660 | HNB Enhanced Defuelling Safety Cases | Provide Provisional NSC Date (as required) | 10-Jan-25 A | 10-Jan-25 | 10-Jan-25 A | 10-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224. A1580 | HRA Enhanced Defueling Safety Case | Hold PRC | 13-Jan-25 A | 13-Jan-25 | 22-Jan-25 A | 22-Jan-25 | 1 | 0 | 1 | 100% |  | Completed
ER6701LT | W228 | W228. A1580 | HYA Enhanced Defueling Safety Case | Hold PRC | 13-Jan-25 A | 13-Jan-25 | 22-Jan-25 A | 22-Jan-25 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C3340 | DNB Enhanced Safety Cases | <NEW SCOPE CN3472> Atkins to issue Technical note to SAG | 13-Jan-25 A | 13-Jan-25 | 13-Jan-25 A | 13-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3360 | DNB Enhanced Safety Cases | Decision Point Milestone - (NSP Pin Failure) | 13-Jan-25 A | 13-Jan-25 | 13-Jan-25 A | 13-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3170 | DNB Enhanced Safety Cases | <NEW SCOPE CN3472> - Issue specification to SAG | 13-Jan-25 A | 13-Jan-25 | 13-Jan-25 A | 13-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.1190 | HRA Fuel Handling Essential Safety Case | Station Approval of HRA Defuelling Fuel Handling Essential Safety Case | 14-Jan-25 A | 14-Jan-25 | 27-Jan-25 A | 27-Jan-25 | 10 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | W226.1195 | HYA Fuel Handling Essential Safety Case | Station Approval of HYA Defuelling Fuel Handling Essential Safety Case | 14-Jan-25 A | 14-Jan-25 | 29-Jan-25 A | 29-Jan-25 | 10 | 0 | 11 | 100% |  | Completed
ER6698LT | W224 | W224.2160 | HRA Enhanced Defueling Safety Case | Best Option/ALARP Strategy >>> Discovery Milestone | 16-Jan-25 A | 16-Jan-25 | 29-Jan-25 A | 29-Jan-25 | 10 | 0 | 10 | 100% |  | Completed
ER6701LT | W228 | W228.2160 | HYA Enhanced Defueling Safety Case | Best Option/ALARP Strategy | 16-Jan-25 A | 16-Jan-25 | 29-Jan-25 A | 29-Jan-25 | 10 | 0 | 10 | 100% |  | Completed
W772LT | W772 | W772LT.A2630 | DNB Pull Harder Safety Case | <<NEW SCOPE PENDING CN3634><Load Path Assessment Appendix - Fixed DWTS> > - Pre Job Brief | 16-Jan-25 A | 16-Jan-25 | 16-Jan-25 A | 16-Jan-25 | 133 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.D1320 | HNB Enhanced Defuelling Safety Cases | Prepare the Safety Case Proposal (including OPEX Review) | 17-Jan-25 A | 17-Jan-25 | 17-Jan-25 A | 17-Jan-25 | 30 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1330 | HNB Enhanced Defuelling Safety Cases | Incorporate CO & Station comments | 17-Jan-25 A | 17-Jan-25 | 17-Jan-25 A | 17-Jan-25 | 5 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1350 | HNB Enhanced Defuelling Safety Cases | Verification of the case (using BARRIER MODEL) | 17-Jan-25 A | 17-Jan-25 | 17-Jan-25 A | 17-Jan-25 | 20 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1360 | HNB Enhanced Defuelling Safety Cases | Produce verification file | 17-Jan-25 A | 17-Jan-25 | 17-Jan-25 A | 17-Jan-25 | 2 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1380 | HNB Enhanced Defuelling Safety Cases | INSA review & iteration of comments (using BARRIER MODEL) | 17-Jan-25 A | 17-Jan-25 | 17-Jan-25 A | 17-Jan-25 | 10 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1480 | HNB Enhanced Defuelling Safety Cases | Verification complete | 17-Jan-25 A | 17-Jan-25 | 17-Jan-25 A | 17-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1510 | HNB Enhanced Defuelling Safety Cases | Station Approval for mod implementation (including station review meeting) | 17-Jan-25 A | 17-Jan-25 | 17-Jan-25 A | 17-Jan-25 | 5 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1530 | HNB Enhanced Defuelling Safety Cases | Issue to CO & Station for comments | 17-Jan-25 A | 17-Jan-25 | 17-Jan-25 A | 17-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1570 | HNB Enhanced Defuelling Safety Cases | INSA Final Approval *(KDM)* <Generic Hoist Trip Setting Increase EC375945> | 17-Jan-25 A | 17-Jan-25 | 17-Jan-25 A | 17-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1620 | HNB Enhanced Defuelling Safety Cases | Supporting reference <Generic Hoist Trip Setting Increase SC> approved | 17-Jan-25 A | 17-Jan-25 | 17-Jan-25 A | 17-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1630 | HNB Enhanced Defuelling Safety Cases | All supporting references completed | 17-Jan-25 A | 17-Jan-25 | 17-Jan-25 A | 17-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1670 | HNB Enhanced Defuelling Safety Cases | Post Job Debrief | 17-Jan-25 A | 17-Jan-25 | 17-Jan-25 A | 17-Jan-25 | 1 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1740 | HNB Enhanced Defuelling Safety Cases | Station Approval Obtained and CAT 2 Safety Case Complete *(KDM)* <Generic Hoist Trip Setting Increase EC375945> | 17-Jan-25 A | 17-Jan-25 | 17-Jan-25 A | 17-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1900 | HNB Enhanced Defuelling Safety Cases | All key supporting technical references complete - Generic Hoist Trip Setting Increase SC | 17-Jan-25 A | 17-Jan-25 | 17-Jan-25 A | 17-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.3690 | HRA Enhanced Defueling Safety Case | Approve | 17-Jan-25 A | 17-Jan-25 | 2025-03-03 | 45719 | 2 | 0 | 31 | 98% | 251 | In Progress
ER6701LT | W228 | W228.3690 | HYA Enhanced Defueling Safety Case | Approve | 17-Jan-25 A | 17-Jan-25 | 2025-03-03 | 45719 | 2 | 0 | 31 | 100% | 251 | In Progress
W772LT | W772 | W772LT.A2640 | DNB Pull Harder Safety Case | <<NEW SCOPE PENDING CN3634><Load Path Assessment Appendix - Fixed DWTS> > - Prepare Draft Report | 17-Jan-25 A | 17-Jan-25 | 28-Feb-25 A | 28-Feb-25 | 21 | 0 | 30 | 100% |  | Completed
ER6698LT | W224 | W224.3920 | HRA Enhanced Defueling Safety Case | Issue RFS | 21-Jan-25 A | 21-Jan-25 | 05-Feb-25 A | 05-Feb-25 | 10 | 0 | 12 | 100% |  | Completed
ER6701LT | W228 | W228.3920 | HYA Enhanced Defueling Safety Case | Issue RFS | 21-Jan-25 A | 21-Jan-25 | 07-Feb-25 A | 07-Feb-25 | 10 | 0 | 13 | 100% |  | Completed
ER6698LT | W224 | W224.A1600 | HRA Enhanced Defueling Safety Case | Cost Summary - CFD & AMP2D | 21-Jan-25 A | 21-Jan-25 | 2025-07-15 | 45853 | 122 | 93 | 122 | 0% | 158 | In Progress
ER6701LT | W228 | W228.A1600 | HYA Enhanced Defueling Safety Case | Cost Summary - CFD & AMP2D | 21-Jan-25 A | 21-Jan-25 | 2025-07-16 | 45854 | 123 | 94 | 123 | 20.56% | 157 | In Progress
W232LT | W232 | W232.C3440 | DNB Enhanced Safety Cases | Decision Point Milestone - Hold Safety Case Decision Panel | 23-Jan-25 A | 23-Jan-25 | 23-Jan-25 A | 23-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3580 | DNB Enhanced Safety Cases | <SCOPE CHANGE CN3472><FPU Uninspected Welds lifting integrity incl'g sub-veto faults> - Mid Job Brief | 23-Jan-25 A | 23-Jan-25 | 23-Jan-25 A | 23-Jan-25 | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5400 | HRA Reactors Shutdown Essential Safety Cases | ONR Agree/Acknowledge Safety Case EC 363682 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HRA) | 24-Jan-25 A | 24-Jan-25 | 24-Jan-25 A | 24-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5410 | HRA Reactors Shutdown Essential Safety Cases | ONR Agree/Acknowledge Safety Case EC 363682 <Reactor Shutdown Essential SC> (Cat 1 MS) (HRA) (FEEDS SUMMARY SCHEDULE) | 24-Jan-25 A | 24-Jan-25 | 24-Jan-25 A | 24-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5400 | HYA Reactors Shutdown Essential Safety Cases | ONR Agree/Acknowledge Safety Case EC 363676 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HYA) | 24-Jan-25 A | 24-Jan-25 | 24-Jan-25 A | 24-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5410 | HYA Reactors Shutdown Essential Safety Cases | ONR Agree/Acknowledge Safety Case EC 363676 <Reactor Shutdown Essential SC> (Cat 1 MS) (HYA) (FEEDS SUMMARY SCHEDULE) | 24-Jan-25 A | 24-Jan-25 | 24-Jan-25 A | 24-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206250 | HYA Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W104, HNB Security Plan) ONR Approved | 24-Jan-25 A | 24-Jan-25 | 24-Jan-25 A | 24-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.1030 | HYA Fuel Handling Essential Safety Case | >>>OUTGOING ENABLER (W283, HYA Security Plan, W206) HYA Fuel Handling Essential Safety Case ONR Approved | 24-Jan-25 A | 24-Jan-25 | 24-Jan-25 A | 24-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.1330 | HRA Reactors Shutdown Essential Safety Cases | >>>INCOMING ENABLER (W222) HRA Fuel Handling Essential Safety Case ONR Approved | 24-Jan-25 A | 24-Jan-25 | 24-Jan-25 A | 24-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.1340 | HRA Reactors Shutdown Essential Safety Cases | >>>MIRROR of INCOMING ENABLER(W222) HRA Fuel Handling Essential Safety Case ONR Approved | 24-Jan-25 A | 24-Jan-25 | 24-Jan-25 A | 24-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.13125 | HYA Reactors Shutdown Essential Safety Cases | >>>INCOMING ENABLER (W226) HYA Fuel Handling Essential Safety Case ONR Approved | 24-Jan-25 A | 24-Jan-25 | 24-Jan-25 A | 24-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.13135 | HYA Reactors Shutdown Essential Safety Cases | >>>MIRROR of INCOMING ENABLER (W226) HYA Fuel Handling Essential Safety Case ONR Approved | 24-Jan-25 A | 24-Jan-25 | 24-Jan-25 A | 24-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.13145 | HYA Reactors Shutdown Essential Safety Cases | >>>INTERFACE MILESTONE (W226) HYA Fuel Handling Essential Safety Case ONR Approved | 24-Jan-25 A | 24-Jan-25 | 24-Jan-25 A | 24-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A1150 | DNB Pull Harder Safety Case | Produce verification plan | 24-Jan-25 A | 24-Jan-25 | 31-Jan-25 A | 31-Jan-25 | 2 | 0 | 6 | 100% |  | Completed
ER6378LT | W222 | W222.A13370 | HRA Fuel Handling Essential Safety Case | Cat 1 Safety Case Complete (ONR LI Issued) HRA Defuelling Fuel Handling Essential Safety Case | 24-Jan-25 A | 24-Jan-25 | 24-Jan-25 A | 24-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A17480 | HRA Fuel Handling Essential Safety Case | ONR Agree/Acknowledge SC ECs(HRA-363840) HRA Defuelling Fuel Handling Essential SC (Cat 1 KDM) (FEEDS SUMMARY SCHEDULE) | 24-Jan-25 A | 24-Jan-25 | 24-Jan-25 A | 24-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A17480 | HYA Fuel Handling Essential Safety Case | ONR Agree/Acknowledge SC ECs(HYA-363839) HYA Defuelling Fuel Handling Essential SC (Cat 1 KDM) (FEEDS SUMMARY SCHEDULE) | 24-Jan-25 A | 24-Jan-25 | 24-Jan-25 A | 24-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A13370 | HYA Fuel Handling Essential Safety Case | Cat 1 Safety Case Complete (ONR LI Issued) HYA Defuelling Fuel Handling Essential Safety Case | 24-Jan-25 A | 24-Jan-25 | 24-Jan-25 A | 24-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.1030 | HRA Fuel Handling Essential Safety Case | >>>OUTGOING ENABLER (HRA Security Plan (W155), W202) - HRA Fuel Handling Essential Safety Case ONR Approved | 24-Jan-25 A | 24-Jan-25 | 24-Jan-25 A | 24-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.1180 | HRA Fuel Handling Essential Safety Case | Safety Case Development Costs - Safety Case Closeout & Gate D Prep ##Cost Summary## | 24-Jan-25 A | 24-Jan-25 | 2025-03-31 | 45747 | 55 | 21 | 46 | 50% | 0 | In Progress
ER6378LT | W222 | W222.1170 | HRA Fuel Handling Essential Safety Case | Project Management Costs - Safety Case Closeout & Gate D Prep ##Cost Summary## | 24-Jan-25 A | 24-Jan-25 | 2025-03-31 | 45747 | 55 | 21 | 46 | 50% | 0 | In Progress
ER6650LT | W226 | W226.1170 | HYA Fuel Handling Essential Safety Case | Project Management Costs - Safety Case Closeout & Gate D Prep ##Cost Summary## | 24-Jan-25 A | 24-Jan-25 | 2025-03-31 | 45747 | 55 | 21 | 46 | 50% | 0 | In Progress
ER6650LT | W226 | W226.1180 | HYA Fuel Handling Essential Safety Case | Safety Case Development Costs - Safety Case Closeout & Gate D Prep ##Cost Summary## | 24-Jan-25 A | 24-Jan-25 | 2025-03-31 | 45747 | 55 | 21 | 46 | 50% | 0 | In Progress
ER6371LT | W202 | W202.1350 | HRA Reactors Shutdown Essential Safety Cases | >>>INTERFACE MILESTONE (W222) HRA Fuel Handling Essential Safety Case ONR Approved | 24-Jan-25 A | 24-Jan-25 | 24-Jan-25 A | 24-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5530 | HRA Reactors Shutdown Essential Safety Cases | Station Approval Period | 27-Jan-25 A | 27-Jan-25 | 27-Jan-25 A | 27-Jan-25 | 10 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1690 | DNB Enhanced Safety Cases | <SCOPE CHANGE CN3472><FPU Sub-veto fault frequency> - Summary | 27-Jan-25 A | 27-Jan-25 | 2025-06-03 | 45811 | 98 | 63 | 88 | 0% | 72 | In Progress
W232LT | W232 | W232.C1700 | DNB Enhanced Safety Cases | <SCOPE CHANGE CN3472><FPU Sub-veto fault frequency> - Prepare Draft EAN Part 1 | 27-Jan-25 A | 27-Jan-25 | 21-Feb-25 A | 21-Feb-25 | 20 | 0 | 20 | 100% |  | Completed
ER6701LT | W228 | W228. A1591 | HYA Enhanced Defueling Safety Case | Gate B PRC Paper Approval | 27-Jan-25 A | 27-Jan-25 | 27-Jan-25 A | 27-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2420 | DNB Pull Harder Safety Case | <Load Path Assessment> - R6 Monte Carlo Assessment | 27-Jan-25 A | 27-Jan-25 | 28-Feb-25 A | 28-Feb-25 | 10 | 0 | 24 | 100% |  | Completed
ER6378LT | W222 | W222.A18960 | HRA Fuel Handling Essential Safety Case | Prepare PRC Paper & Gate Package for Gate D | 27-Jan-25 A | 27-Jan-25 | 2025-03-05 | 45721 | 10 | 3 | 28 | 10% | 0 | In Progress
ER6650LT | W226 | W226.A18960 | HYA Fuel Handling Essential Safety Case | Prepare PRC Paper & Gate Package for Gate D | 27-Jan-25 A | 27-Jan-25 | 2025-03-05 | 45721 | 10 | 3 | 28 | 0% | 0 | In Progress
W232LT | W232 | W232.A5480 | DNB Enhanced Safety Cases | Review task sheet | 27-Jan-25 A | 27-Jan-25 | 31-Jan-25 A | 31-Jan-25 | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A5420 | HRA Reactors Shutdown Essential Safety Cases | Station Approve EC 363682 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HRA) (FEEDS TO SUMMARY SCHEDULE) | 27-Jan-25 A | 27-Jan-25 | 27-Jan-25 A | 27-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A18480 | HRA Fuel Handling Essential Safety Case | Station Approve ECs (HRA-363840) HRA Defuelling Fuel Handling Essential Safety Case (Cat 1 KDM) Delivered (FEEDS TO SUMM | 27-Jan-25 A | 27-Jan-25 | 27-Jan-25 A | 27-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206200 | HRA Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W104 HPB Security Plan)(W285)(W148) CAT 1 Reactors Shutdown SC Station Approved | 27-Jan-25 A | 27-Jan-25 | 27-Jan-25 A | 27-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A27270 | HRA Fuel Handling Essential Safety Case | >>>OUTGOING ENABLER (W285)(W148) CAT 1 Fuel Handling SC Station Approved | 27-Jan-25 A | 27-Jan-25 | 27-Jan-25 A | 27-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772.A1140 | DNB Pull Harder Safety Case | <New SCOPE PENDING CN3634> - <Cavendish PWTS Report> - EDF TR Round 2 | 28-Jan-25 A | 28-Jan-25 | 31-Jan-25 A | 31-Jan-25 | 1 | 0 | 4 | 100% |  | Completed
ER6371LT | W202 | W202.A5430 | HRA Reactors Shutdown Essential Safety Cases | Revise all Affected Drawings and Documents for EC Approval (HRA) | 28-Jan-25 A | 28-Jan-25 | 14-Feb-25 A | 14-Feb-25 | 10 | 0 | 13 | 100% |  | Completed
ER6378LT | W222 | W222.A17470 | HRA Fuel Handling Essential Safety Case | Revise all Affected Drawings and Documents Following EC Approval | 28-Jan-25 A | 28-Jan-25 | 10-Feb-25 A | 10-Feb-25 | 10 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | W226.A17470 | HYA Fuel Handling Essential Safety Case | Revise all Affected Drawings and Documents following EC Approval | 28-Jan-25 A | 28-Jan-25 | 10-Feb-25 A | 10-Feb-25 | 10 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | W226.A18480 | HYA Fuel Handling Essential Safety Case | Station Approve ECs (HYA-363839) HYA Defuelling Fuel Handling Essential Safety Case (Cat 1 KDM) Delivered (FEEDS TO SUMM | 29-Jan-25 A | 29-Jan-25 | 29-Jan-25 A | 29-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2150 | DNB Pull Harder Safety Case | <Human Factors> - Review and Finalise HF Template | 29-Jan-25 A | 29-Jan-25 | 29-Jan-25 A | 29-Jan-25 | 5 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2180 | DNB Pull Harder Safety Case | <Human Factors> - HF Template Complete | 29-Jan-25 A | 29-Jan-25 | 29-Jan-25 A | 29-Jan-25 | 5 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5430 | HYA Reactors Shutdown Essential Safety Cases | Revise all Affected Drawings and Documents for EC Approval (HYA) | 31-Jan-25 A | 31-Jan-25 | 14-Feb-25 A | 14-Feb-25 | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.A5420 | HYA Reactors Shutdown Essential Safety Cases | Station Approve EC 363676 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HYA) (FEEDS TO SUMMARY SCHEDULE) | 31-Jan-25 A | 31-Jan-25 | 31-Jan-25 A | 31-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206220 | HYA Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W286)(W149) CAT 1 Reactors Shutdown SC Station Approved | 31-Jan-25 A | 31-Jan-25 | 31-Jan-25 A | 31-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27310 | HYA Fuel Handling Essential Safety Case | >>>OUTGOING ENABLER (W286)(W149) CAT 1 Fuel Handling SC Station Approved | 31-Jan-25 A | 31-Jan-25 | 31-Jan-25 A | 31-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5530 | HYA Reactors Shutdown Essential Safety Cases | Station Approval Period | 31-Jan-25 A | 31-Jan-25 | 31-Jan-25 A | 31-Jan-25 | 10 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 2295 | HYA Fuel Handling Essential Safety Case | Station Approval of Safety Case | 31-Jan-25 A | 31-Jan-25 | 31-Jan-25 A | 31-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224. A1591 | HRA Enhanced Defueling Safety Case | Gate B PRC Paper Approval | 31-Jan-25 A | 31-Jan-25 | 31-Jan-25 A | 31-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
ER6701LT | W228 | W228. A1570 | HYA Enhanced Defueling Safety Case | Gate B-D PRC Paper Submission | 31-Jan-25 A | 31-Jan-25 | 31-Jan-25 A | 31-Jan-25 | 0 | 0 | 0 | 100% |  | Completed
W730LT_UN | W730 | W730.1270 | HYB Enhanced Defueling Safety Cases | Summary for HYB Fuel Handling Enhanced Safety Cases W230 | 03-Feb-25 A | 03-Feb-25 | 2028-03-27 | 46839 | 801 | 781 | 801 | 0% | 0 | In Progress
W730LT_UN | W730 | W730.1010 | HYB Enhanced Defueling Safety Cases | Project Start | 03-Feb-25 A | 03-Feb-25 | 03-Feb-25 A | 03-Feb-25 | 0 | 0 | 0 | 100% |  | Completed
W730LT_UN | W730 | W730.1410 | HYB Enhanced Defueling Safety Cases | Confirm Objectives to be Delivered at Gate B | 03-Feb-25 A | 03-Feb-25 | 13-Feb-25 A | 13-Feb-25 | 9 | 0 | 9 | 100% |  | Completed
ER6698LT | W224 | W224. A1600 | HRA Enhanced Defueling Safety Case | Funds Released | 03-Feb-25 A | 03-Feb-25 | 12-Feb-25 A | 12-Feb-25 | 8 | 0 | 8 | 100% |  | Completed
ER6701LT | W228 | W228. A1600 | HYA Enhanced Defueling Safety Case | Funds Released | 03-Feb-25 A | 03-Feb-25 | 12-Feb-25 A | 12-Feb-25 | 8 | 0 | 8 | 100% |  | Completed
W230LT | W230 | W230.2050 | HYB Enhanced Defueling Safety Case Strategy | ## HYB Enhanced Defueling Rate: A - D Phase Funding - (Cost Summary) ## | 03-Feb-25 A | 03-Feb-25 | 2025-06-20 | 45828 | 96 | 76 | 96 | 0% | 230 | In Progress
W230LT | W230 | W230.2060 | HYB Enhanced Defueling Safety Case Strategy | HYB Enhanced Defueling Rate: Strategy Development & Produce MF EC NNNNN & Obtain Approval | 03-Feb-25 A | 03-Feb-25 | 10-Feb-25 A | 10-Feb-25 | 6 | 0 | 6 | 100% |  | Completed
ER6698LT | W224 | W224.A1590 | HRA Enhanced Defueling Safety Case | Gate B for Defuelling Programme Enhancement ECs (HH1) | 03-Feb-25 A | 03-Feb-25 | 03-Feb-25 A | 03-Feb-25 | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2105 | DNB Pull Harder Safety Case | EC Appendix 4 - Test Schedule - Preliminary Work & Authour - EDF | 03-Feb-25 A | 03-Feb-25 | 14-Feb-25 A | 14-Feb-25 | 10 | 0 | 10 | 100% |  | Completed
ER6701LT | W228 | W228.A1590 | HYA Enhanced Defueling Safety Case | Gate B for Defuelling Programme Enhancement ECs (HH1) | 03-Feb-25 A | 03-Feb-25 | 03-Feb-25 A | 03-Feb-25 | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5490 | DNB Enhanced Safety Cases | Approve task sheet | 03-Feb-25 A | 03-Feb-25 | 2025-03-21 | 45737 | 5 | 15 | 35 | 50% | 6 | In Progress
W772LT | W772 | W772.A1150 | DNB Pull Harder Safety Case | <New SCOPE PENDING CN3634> - <Cavendish PWTS Report> - Complete ( Incorporated into Appendix 1 ) | 03-Feb-25 A | 03-Feb-25 | 21-Feb-25 A | 21-Feb-25 | 5 | 0 | 14 | 100% |  | Completed
W234LT | W234 | W234.2050 | TOR Enhanced Defueling Safety Case Strategy | ## TOR Enhanced Defueling Rate: A - D Phase Funding - (Cost Summary) ## | 03-Feb-25 A | 03-Feb-25 | 2025-06-20 | 45828 | 96 | 76 | 96 | 0% | 230 | In Progress
W234LT | W234 | W234.2130 | TOR Enhanced Defueling Safety Case Strategy | TOR Enhanced Defueling Rate: Produce draft NSRS (using BARRIER MODEL) | 03-Feb-25 A | 03-Feb-25 | 28-Feb-25 A | 28-Feb-25 | 20 | 0 | 20 | 100% |  | Completed
W234LT | W234 | W234.2060 | TOR Enhanced Defueling Safety Case Strategy | TOR Enhanced Defueling Rate: Strategy Development & Produce MF EC NNNNN & Obtain Approval | 03-Feb-25 A | 03-Feb-25 | 10-Feb-25 A | 10-Feb-25 | 6 | 0 | 6 | 100% |  | Completed
W772LT | W772 | W772LT.A2460 | DNB Pull Harder Safety Case | <Load Path Assessment> - Analysis of Fault Case 18cs of Pull Harder Loads | 03-Feb-25 A | 03-Feb-25 | 2025-03-07 | 45723 | 10 | 5 | 25 | 90% | 8 | In Progress
W772LT | W772 | W772LT.A2720 | DNB Pull Harder Safety Case | <Load Path Assessment> -Cyclic Loading of Seized OEM NSP Welds Assessment | 03-Feb-25 A | 03-Feb-25 | 28-Feb-25 A | 28-Feb-25 | 10 | 0 | 19 | 100% |  | Completed
W731LT_UN | W731 | W731.1020 | TOR Enhanced Defueling Safety Cases | Confirm Objectives to be Delivered at Gate B | 03-Feb-25 A | 03-Feb-25 | 13-Feb-25 A | 13-Feb-25 | 9 | 0 | 9 | 100% |  | Completed
W731LT_UN | W731 | W731.1030 | TOR Enhanced Defueling Safety Cases | Project Start | 03-Feb-25 A | 03-Feb-25 | 03-Feb-25 A | 03-Feb-25 | 0 | 0 | 0 | 100% |  | Completed
W731LT_UN | W731 | W731.1040 | TOR Enhanced Defueling Safety Cases | Summary for TOR Fuel Handling Enhanced Safety Cases W230 | 03-Feb-25 A | 03-Feb-25 | 2028-03-27 | 46839 | 801 | 781 | 801 | 0% | 0 | In Progress
ER6372LT | W203 | W203.C1510 | HNB Enhanced Defuelling Safety Cases | Station Approval for mod implementation (including station review meeting) | 04-Feb-25 A | 04-Feb-25 | 04-Feb-25 A | 04-Feb-25 | 5 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1490 | HNB Enhanced Defuelling Safety Cases | Incorporate INSA comments | 04-Feb-25 A | 04-Feb-25 | 04-Feb-25 A | 04-Feb-25 | 5 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1500 | HNB Enhanced Defuelling Safety Cases | INSA Final Approval *(EC375412)* | 04-Feb-25 A | 04-Feb-25 | 04-Feb-25 A | 04-Feb-25 | 5 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1530 | HNB Enhanced Defuelling Safety Cases | Post Job Debrief | 04-Feb-25 A | 04-Feb-25 | 04-Feb-25 A | 04-Feb-25 | 1 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1520 | HNB Enhanced Defuelling Safety Cases | Station Approval Obtained and CAT 2 Safety Case Complete *(EC375412)* | 04-Feb-25 A | 04-Feb-25 | 04-Feb-25 A | 04-Feb-25 | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D4230 | HNB Enhanced Defuelling Safety Cases | EC Station Approved - EC375412 | 04-Feb-25 A | 04-Feb-25 | 04-Feb-25 A | 04-Feb-25 | 0 | 0 | 0 | 100% |  | Completed
ER6701LT | W228 | W228.3930 | HYA Enhanced Defueling Safety Case | Supplier Return RFS | 06-Feb-25 A | 06-Feb-25 | 2025-03-05 | 45721 | 20 | 3 | 20 | 80% | 36 | In Progress
ER6698LT | W224 | W224.3930 | HRA Enhanced Defueling Safety Case | Supplier Return RFS | 06-Feb-25 A | 06-Feb-25 | 2025-03-05 | 45721 | 20 | 3 | 20 | 85% | 36 | In Progress
ER6378LT | W222 | W222.A17460 | HRA Fuel Handling Essential Safety Case | Develop Implementation & closeout Plan | 11-Feb-25 A | 11-Feb-25 | 2025-03-10 | 45726 | 10 | 6 | 20 | 10% | 14 | In Progress
ER6650LT | W226 | W226.A17460 | HYA Fuel Handling Essential Safety Case | Develop Implementation & closeout Plan | 11-Feb-25 A | 11-Feb-25 | 2025-03-10 | 45726 | 10 | 6 | 20 | 10% | 14 | In Progress
W230LT | W230 | W230.2130 | HYB Enhanced Defueling Safety Case Strategy | HYB Enhanced Defueling Rate: Produce draft NSRS (using BARRIER MODEL) | 11-Feb-25 A | 11-Feb-25 | 28-Feb-25 A | 28-Feb-25 | 14 | 0 | 14 | 100% |  | Completed
W232LT | W232 | W232.C3590 | DNB Enhanced Safety Cases | <SCOPE CHANGE CN3472><FPU Uninspected Welds lifting integrity incl'g sub-veto faults> - Prepare Draft EAN Part 2 | 13-Feb-25 A | 13-Feb-25 | 2025-05-19 | 45796 | 40 | 28 | 65 | 0% | 5 | In Progress
ER6698LT | W224 | W224.1580 | HRA Enhanced Defueling Safety Case | PJB | 13-Feb-25 A | 13-Feb-25 | 21-Feb-25 A | 21-Feb-25 | 7 | 0 | 7 | 100% |  | Completed
ER6698LT | W224 | W224.1680 | HRA Enhanced Defueling Safety Case | Design Activities – Bob Weight & Gripping Sleeve | 13-Feb-25 A | 13-Feb-25 | 2025-03-05 | 45721 | 15 | 3 | 15 | 80% | 37 | In Progress
ER6698LT | W224 | W224.1690 | HRA Enhanced Defueling Safety Case | Draft Drawings - Bob Weight & Gripping Sleeve | 13-Feb-25 A | 13-Feb-25 | 2025-03-03 | 45719 | 10 | 1 | 13 | 80% | 29 | In Progress
ER6698LT | W224 | W224.3200 | HRA Enhanced Defueling Safety Case | Start Gate B Activities | 13-Feb-25 A | 13-Feb-25 | 13-Feb-25 A | 13-Feb-25 | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.3300 | HRA Enhanced Defueling Safety Case | Gate B-D Programme Management External - Cost Summary | 13-Feb-25 A | 13-Feb-25 | 2026-01-19 | 46041 | 235 | 223 | 235 | 5% | 26 | In Progress
ER6698LT | W224 | W224.3400 | HRA Enhanced Defueling Safety Case | Gate B-D Programme Management Internal - Cost Summary | 13-Feb-25 A | 13-Feb-25 | 2026-01-19 | 46041 | 235 | 223 | 235 | 5% | 26 | In Progress
ER6701LT | W228 | W228.3400 | HYA Enhanced Defueling Safety Case | Gate B-D Programme Management Internal - Cost Summary | 13-Feb-25 A | 13-Feb-25 | 2026-01-19 | 46041 | 235 | 223 | 235 | 5% | 26 | In Progress
ER6701LT | W228 | W228.3300 | HYA Enhanced Defueling Safety Case | Gate B-D Programme Management External - Cost Summary | 13-Feb-25 A | 13-Feb-25 | 2026-01-19 | 46041 | 235 | 223 | 235 | 5% | 26 | In Progress
ER6701LT | W228 | W228.3200 | HYA Enhanced Defueling Safety Case | Start Gate B Activities | 13-Feb-25 A | 13-Feb-25 | 13-Feb-25 A | 13-Feb-25 | 0 | 0 | 0 | 100% |  | Completed
ER6701LT | W228 | W228.1690 | HYA Enhanced Defueling Safety Case | Draft Drawings – Bob Weight & Gripping Sleeve | 13-Feb-25 A | 13-Feb-25 | 2025-03-03 | 45719 | 10 | 1 | 13 | 80% | 30 | In Progress
ER6701LT | W228 | W228.1680 | HYA Enhanced Defueling Safety Case | Design Activities – Bob Weight & Gripping Sleeve | 13-Feb-25 A | 13-Feb-25 | 2025-03-05 | 45721 | 15 | 3 | 15 | 80% | 37 | In Progress
ER6701LT | W228 | W228.1580 | HYA Enhanced Defueling Safety Case | PJB | 13-Feb-25 A | 13-Feb-25 | 21-Feb-25 A | 21-Feb-25 | 7 | 0 | 7 | 100% |  | Completed
ER6371LT | W202 | W202.A5440 | HRA Reactors Shutdown Essential Safety Cases | Develop Implementation & closeout Plan (HRA) | 14-Feb-25 A | 14-Feb-25 | 21-Feb-25 A | 21-Feb-25 | 10 | 0 | 6 | 100% |  | Completed
ER6371LT | W202 | W202.A5500 | HRA Reactors Shutdown Essential Safety Cases | Prepare Gate D PRC Paper | 14-Feb-25 A | 14-Feb-25 | 2025-03-11 | 45727 | 6 | 3 | 18 | 25% | 0 | In Progress
ER6661LT | W206 | W206.A5500 | HYA Reactors Shutdown Essential Safety Cases | Prepare Gate D PRC Paper | 14-Feb-25 A | 14-Feb-25 | 2025-03-11 | 45727 | 6 | 3 | 18 | 25% | 0 | In Progress
ER6371LT | W202 | W202.A2206520 | HRA Reactors Shutdown Essential Safety Cases | Phase 2 Project Management - Gate D - E | 14-Feb-25 A | 14-Feb-25 | 2025-03-31 | 45747 | 37 | 21 | 32 | 43% | 0 | In Progress
ER6661LT | W206 | W206.A2206320 | HYA Reactors Shutdown Essential Safety Cases | Phase 2 Project Management - Gate D - E | 14-Feb-25 A | 14-Feb-25 | 2025-03-31 | 45747 | 33 | 21 | 32 | 43% | 0 | In Progress
W730LT_UN | W730 | W730.1400 | HYB Enhanced Defueling Safety Cases | Initial high level scope of programme | 14-Feb-25 A | 14-Feb-25 | 20-Feb-25 A | 20-Feb-25 | 5 | 0 | 5 | 100% |  | Completed
W772LT | W772 | W772.A1100 | DNB Pull Harder Safety Case | Annual Leave - James Derbyshire | 14-Feb-25 A | 14-Feb-25 | 2025-03-14 | 45730 | 21 | 10 | 21 | 50% | 152 | In Progress
W232LT | W232 | W232.A5810 | DNB Enhanced Safety Cases | Annual Leave - James Derbyshire | 14-Feb-25 A | 14-Feb-25 | 2025-03-14 | 45730 | 21 | 10 | 21 | 50% | 259 | In Progress
W731LT_UN | W731 | W731.1070 | TOR Enhanced Defueling Safety Cases | Initial high level scope of programme | 14-Feb-25 A | 14-Feb-25 | 20-Feb-25 A | 20-Feb-25 | 5 | 0 | 5 | 100% |  | Completed
W772LT | W772 | W772.A1020 | DNB Pull Harder Safety Case | <S'standt'n of Funct'l Cap of PWTS & DWTS at the Enh'ed O'load Trip Sett's> - Issue Draft EAN / Report for Tech Review. | 14-Feb-25 A | 14-Feb-25 | 14-Feb-25 A | 14-Feb-25 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5440 | HYA Reactors Shutdown Essential Safety Cases | Develop Implementation & closeout Plan (HYA) | 17-Feb-25 A | 17-Feb-25 | 21-Feb-25 A | 21-Feb-25 | 10 | 0 | 5 | 100% |  | Completed
ER6701LT | W228 | W228.2690 | HYA Enhanced Defueling Safety Case | Preliminary Design (including drawings and relevant analysis) | 17-Feb-25 A | 17-Feb-25 | 2025-03-28 | 45744 | 30 | 20 | 30 | 33% | 20 | In Progress
W232LT | W232 | W232.A5820 | DNB Enhanced Safety Cases | <NEW SCOPE PENDING CN3754> - Review of OEMNSP growth values load Trace OpEX (To confirm growth values unchanged) | 17-Feb-25 A | 17-Feb-25 | 2025-04-17 | 45764 | 34 | 34 | 44 | 30% | 101 | In Progress
ER6698LT | W224 | W224.2690 | HRA Enhanced Defueling Safety Case | Preliminary Design (including drawings and relevant analysis) | 17-Feb-25 A | 17-Feb-25 | 2025-03-28 | 45744 | 30 | 20 | 30 | 33% | 20 | In Progress
W772LT | W772 | W772LT.A2160 | DNB Pull Harder Safety Case | <Test Schedulet> - Prepare Draft Report | 17-Feb-25 A | 17-Feb-25 | 21-Feb-25 A | 21-Feb-25 | 10 | 0 | 4 | 100% |  | Completed
W772LT | W772 | W772LT.A2340 | DNB Pull Harder Safety Case | <Load Path Assessment> - TSA Review/Verify Draft EAN | 17-Feb-25 A | 17-Feb-25 | 2025-03-10 | 45726 | 16 | 1 | 16 | 50% | 8 | In Progress
ER6371LT | W202 | W202.1390 | HRA Reactors Shutdown Essential Safety Cases | Review of Reactor Ess Safety Case 2 - (ONR & Station Approved) Lessons Learnt Review Complete | 18-Feb-25 A | 18-Feb-25 | 18-Feb-25 A | 18-Feb-25 | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.1391 | HYA Reactors Shutdown Essential Safety Cases | Review of Reactor Ess Safety Case 2 - (ONR & Station Approved) Lessons Learnt Review Complete | 18-Feb-25 A | 18-Feb-25 | 18-Feb-25 A | 18-Feb-25 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.1390 | HYA Fuel Handling Essential Safety Case | Review of Reactor Ess Safety Case 2 - Lessons Learnt Review Complete | 18-Feb-25 A | 18-Feb-25 | 18-Feb-25 A | 18-Feb-25 | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.1395 | HRA Fuel Handling Essential Safety Case | Station Approval of Safety Case - Lessons Learnt Review Complete | 18-Feb-25 A | 18-Feb-25 | 18-Feb-25 A | 18-Feb-25 | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.1395 | HYA Fuel Handling Essential Safety Case | Station Approval of Safety Case - Lessons Learnt Review Complete | 18-Feb-25 A | 18-Feb-25 | 18-Feb-25 A | 18-Feb-25 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1555 | TOR Essential Defueling Safety Case | Prepare Station Director's Brief | 20-Feb-25 A | 20-Feb-25 | 20-Feb-25 A | 20-Feb-25 | 5 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.29590 | TOR Essential Defueling Safety Case | INSA Schedule Risk - (Risk Ref 28382) - Generic (Potential) | 20-Feb-25 A | 20-Feb-25 | 24-Feb-25 A | 24-Feb-25 | 0 | 0 | 2 | 100% |  | Completed
W772LT | W772 | W772LT.A1580 | DNB Pull Harder Safety Case | Specialist Assessments if Necessary (Expand as Required) | 20-Feb-25 A | 20-Feb-25 | 2025-05-29 | 45806 | 20 | 20 | 67 | 0% | 8 | In Progress
W772LT | W772 | W772LT.A2470 | DNB Pull Harder Safety Case | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Nuclear Fuel Group - Review and Comment | 20-Feb-25 A | 20-Feb-25 | 20-Feb-25 A | 20-Feb-25 | 10 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2480 | DNB Pull Harder Safety Case | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Human Factors (Human Reliability Assessment) - Review and Comment | 20-Feb-25 A | 20-Feb-25 | 20-Feb-25 A | 20-Feb-25 | 10 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2490 | DNB Pull Harder Safety Case | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Human Factors - (Work Procedures) - Review and Comment | 20-Feb-25 A | 20-Feb-25 | 20-Feb-25 A | 20-Feb-25 | 10 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2500 | DNB Pull Harder Safety Case | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Engineering (Instrumentation & Control) - Review and Comment | 20-Feb-25 A | 20-Feb-25 | 20-Feb-25 A | 20-Feb-25 | 10 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2510 | DNB Pull Harder Safety Case | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Engineering (Mechanical Systems) - Review and Comment | 20-Feb-25 A | 20-Feb-25 | 20-Feb-25 A | 20-Feb-25 | 10 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2520 | DNB Pull Harder Safety Case | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Structural Integrity (Structural Analysis) - Review and Comment | 20-Feb-25 A | 20-Feb-25 | 20-Feb-25 A | 20-Feb-25 | 10 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2550 | DNB Pull Harder Safety Case | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Nuclear Fuel Group - Close Comments | 20-Feb-25 A | 20-Feb-25 | 20-Feb-25 A | 20-Feb-25 | 10 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2560 | DNB Pull Harder Safety Case | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Human Factors (Human Reliability Assessment) - Close Comments | 20-Feb-25 A | 20-Feb-25 | 20-Feb-25 A | 20-Feb-25 | 10 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2570 | DNB Pull Harder Safety Case | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Human Factors - (Work Procedures) - Close Comments | 20-Feb-25 A | 20-Feb-25 | 20-Feb-25 A | 20-Feb-25 | 10 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2580 | DNB Pull Harder Safety Case | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Engineering (Instrumentation & Control) - Close Comments | 20-Feb-25 A | 20-Feb-25 | 20-Feb-25 A | 20-Feb-25 | 10 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2590 | DNB Pull Harder Safety Case | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Engineering (Mechanical Systems) - Close Comments | 20-Feb-25 A | 20-Feb-25 | 20-Feb-25 A | 20-Feb-25 | 10 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2600 | DNB Pull Harder Safety Case | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Structural Integrity (Structural Analysis) - Close Comments | 20-Feb-25 A | 20-Feb-25 | 20-Feb-25 A | 20-Feb-25 | 10 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1555 | HYB Essential Defueling Safety Case | Prepare Station Director's Brief | 20-Feb-25 A | 20-Feb-25 | 20-Feb-25 A | 20-Feb-25 | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.29590 | HYB Essential Defueling Safety Case | INSA Schedule Risk - (Risk Ref 28382) - Generic (Unknown) | 20-Feb-25 A | 20-Feb-25 | 24-Feb-25 A | 24-Feb-25 | 3 | 0 | 3 | 100% |  | Completed
ER6698LT | W224 | W224.2230 | HRA Enhanced Defueling Safety Case | Contract Award | 20-Feb-25 A | 20-Feb-25 | 2025-03-04 | 45720 | 4 | 2 | 9 | 70% | 240 | In Progress
ER6701LT | W228 | W228.2230 | HYA Enhanced Defueling Safety Case | Contract Award | 20-Feb-25 A | 20-Feb-25 | 2025-03-04 | 45720 | 4 | 2 | 9 | 70% | 240 | In Progress
ER6371LT | W202 | W202.A5450 | HRA Reactors Shutdown Essential Safety Cases | Safety Case Post Job Debrief (HRA) | 21-Feb-25 A | 21-Feb-25 | 21-Feb-25 A | 21-Feb-25 | 1 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5450 | HYA Reactors Shutdown Essential Safety Cases | Safety Case Post Job Debrief (HYA) | 21-Feb-25 A | 21-Feb-25 | 21-Feb-25 A | 21-Feb-25 | 1 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2350 | DNB Pull Harder Safety Case | <Test Schedule> - Issue Draft EAN / Report for Tech Review. | 21-Feb-25 A | 21-Feb-25 | 21-Feb-25 A | 21-Feb-25 | 0 | 0 | 0 | 100% |  | Completed
W730LT_UN | W730 | W730.1420 | HYB Enhanced Defueling Safety Cases | Prepare Draft Project Definition Document (PDD) | 21-Feb-25 A | 21-Feb-25 | 2025-03-06 | 45722 | 10 | 4 | 10 | 80% | 3 | In Progress
W730LT_UN | W730 | W730.1430 | HYB Enhanced Defueling Safety Cases | PCL Validate & Approve Baseline Package for PRC Submission | 21-Feb-25 A | 21-Feb-25 | 2025-03-06 | 45722 | 10 | 4 | 10 | 80% | 3 | In Progress
W730LT_UN | W730 | W730.1440 | HYB Enhanced Defueling Safety Cases | Add Data to PRC / IMS2 Paper | 21-Feb-25 A | 21-Feb-25 | 2025-03-06 | 45722 | 10 | 4 | 10 | 80% | 3 | In Progress
W730LT_UN | W730 | W730.1450 | HYB Enhanced Defueling Safety Cases | Update Schedule/Estimate from Risk Log & Add Provisions | 21-Feb-25 A | 21-Feb-25 | 2025-03-06 | 45722 | 10 | 4 | 10 | 80% | 3 | In Progress
W730LT_UN | W730 | W730.1510 | HYB Enhanced Defueling Safety Cases | Define Project Control Structures (WBS/CBS/OBS/PBS) | 21-Feb-25 A | 21-Feb-25 | 2025-03-06 | 45722 | 10 | 4 | 10 | 80% | 3 | In Progress
W731LT_UN | W731 | W731.1080 | TOR Enhanced Defueling Safety Cases | Define Project Control Structures (WBS/CBS/OBS/PBS) | 21-Feb-25 A | 21-Feb-25 | 2025-03-06 | 45722 | 10 | 4 | 10 | 80% | 3 | In Progress
W731LT_UN | W731 | W731.1090 | TOR Enhanced Defueling Safety Cases | Update Schedule/Estimate from Risk Log & Add Provisions | 21-Feb-25 A | 21-Feb-25 | 2025-03-06 | 45722 | 10 | 4 | 10 | 80% | 3 | In Progress
W731LT_UN | W731 | W731.1100 | TOR Enhanced Defueling Safety Cases | Add Data to PRC / IMS2 Paper | 21-Feb-25 A | 21-Feb-25 | 2025-03-06 | 45722 | 10 | 4 | 10 | 80% | 3 | In Progress
W731LT_UN | W731 | W731.1110 | TOR Enhanced Defueling Safety Cases | PCL Validate & Approve Baseline Package for PRC Submission | 21-Feb-25 A | 21-Feb-25 | 2025-03-06 | 45722 | 10 | 4 | 10 | 80% | 3 | In Progress
W731LT_UN | W731 | W731.1120 | TOR Enhanced Defueling Safety Cases | Prepare Draft Project Definition Document (PDD) | 21-Feb-25 A | 21-Feb-25 | 2025-03-06 | 45722 | 10 | 4 | 10 | 80% | 3 | In Progress
ER6666LT | W209 | W209.29600 | HYB Essential Defueling Safety Case | Risk Milestone - INSA Schedule Risk - (Risk Ref 28382) - INSA Substantially Complete | 24-Feb-25 A | 24-Feb-25 | 24-Feb-25 A | 24-Feb-25 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.29600 | TOR Essential Defueling Safety Case | Risk Milestone - INSA Schedule Risk - (Risk Ref 28382) - INSA Substantially Complete | 24-Feb-25 A | 24-Feb-25 | 24-Feb-25 A | 24-Feb-25 | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2170 | DNB Pull Harder Safety Case | <Test Schedule> - Draft EAN / Report Tech Reviewed by EDF SQEP | 24-Feb-25 A | 24-Feb-25 | 28-Feb-25 A | 28-Feb-25 | 5 | 0 | 4 | 100% |  | Completed
W772LT | W772 | W772.A1030 | DNB Pull Harder Safety Case | <S'standt'n of Funct'l Cap of PWTS & DWTS at the Enh'ed O'load Trip Sett's> - Draft EAN / Report TR by EDF SQEP | 24-Feb-25 A | 24-Feb-25 | 28-Feb-25 A | 28-Feb-25 | 5 | 0 | 4 | 100% |  | Completed
W232LT | W232 | W232.C3560 | DNB Enhanced Safety Cases | <SCOPE CHANGE CN3472><FPU Sub-veto fault frequency> - Mid Job Brief | 24-Feb-25 A | 24-Feb-25 | 24-Feb-25 A | 24-Feb-25 | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C3570 | DNB Enhanced Safety Cases | <SCOPE CHANGE CN3472><FPU Sub-veto fault frequency> - Prepare Draft EAN Part 2 | 25-Feb-25 A | 25-Feb-25 | 2025-03-31 | 2025-03-31 | 25 | 21 | 25 | 10% | 56 | In Progress
ER6666LT | W209 | W209.1042 | HYB Essential Defueling Safety Case | INSA Assessment Substantially Comp (T-3) weeks before NSC date)) | 26-Feb-25 A | 26-Feb-25 | 26-Feb-25 A | 26-Feb-25 | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.4970 | HYB Essential Defueling Safety Case | >>>OUTGOING ENABLER (W273) INSA Approved | 26-Feb-25 A | 26-Feb-25 | 26-Feb-25 A | 26-Feb-25 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.4970 | TOR Essential Defueling Safety Case | >>>OUTGOING ENABLER (W274) INSA Approved | 26-Feb-25 A | 26-Feb-25 | 26-Feb-25 A | 26-Feb-25 | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1042 | TOR Essential Defueling Safety Case | INSA Assessment Substantially Comp (T-3) weeks before NSC date)) | 26-Feb-25 A | 26-Feb-25 | 26-Feb-25 A | 26-Feb-25 | 0 | 0 | 0 | 100% |  | Completed
W230LT | W230 | W230.3770 | HYB Enhanced Defueling Safety Case Strategy | HYB Enhanced Defueling Rate: Produce draft NSRS (using BARRIER MODEL) | 28-Feb-25 A | 28-Feb-25 | 28-Feb-25 A | 28-Feb-25 | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.T1290 | DNB Pull Harder Safety Case | <Operating Strategy for Pull Harder Facility> - Issue Final EAN / Report | 28-Feb-25 A | 28-Feb-25 | 28-Feb-25 A | 28-Feb-25 | 0 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.3770 | TOR Enhanced Defueling Safety Case Strategy | TOR Enhanced Defueling Rate: Produce draft NSRS (using BARRIER MODEL) | 28-Feb-25 A | 28-Feb-25 | 28-Feb-25 A | 28-Feb-25 | 0 | 0 | 0 | 100% |  | Completed
DESCRIPTIVE ANALYSIS
[8 empty] | median | 5 | 0 | 4
[8 empty] | mode | 0 | 0 | 0
[8 empty] | mean | 21.4977 | 0.73532 | 29.1478
[8 empty] | standard deviation | 65.5676 | 15.3941 | 82.7435
[8 empty] | simple variance | 4299.1081 | 236.9783 | 6846.4892
[8 empty] | minimum value | 0 | 0 | 0
[8 empty] | maximum value | 1920 | 781 | 1625
[8 empty] | count | 8497 | 8497 | 8497
[8 empty] | kurtosis | 141.2697 | 1638.9033 | 92.4085
[8 empty] | skewness | 8.9127 | 36.2203 | 7.7922
[8 empty] | t value | 8.9346 | 1.9602 | 7.8075
[8 empty] | margin of error | 8.9359 | 0.32736 | 7.808
[8 empty] | conf interval lower | 22.6463 | 0.40795 | 30.5322
[8 empty] | conf interval upper | 22.6463 | 1.0627 | 30.5319
Formulas:
Finish cleaned = [Finish]

## DESCRIPTIVE ANALYSIS SC PLANS
DESCRIPTIVE ANALYSIS
median | 5 | 0 | 4
mode | 0 | 0 | 0
mean | 21.4977 | 0.73532 | 29.1478
standard deviation | 65.5676 | 15.3941 | 82.7435
simple variance | 4299.1081 | 236.9783 | 6846.4892
minimum value | 0 | 0 | 0
maximum value | 1920 | 781 | 1625
count | 8497 | 8497 | 8497
kurtosis | 141.2697 | 1638.9033 | 92.4085
skewness | 8.9127 | 36.2203 | 7.7922
t value | 8.9346 | 1.9602 | 7.8075
margin of error | 8.9359 | 0.32736 | 7.808
conf interval lower | 22.6463 | 0.40795 | 30.5322
conf interval upper | 22.6463 | 1.0627 | 30.5319

## Template
Activity ID | Activity Name | Start | Finish | Original Duration | Total Float
A1700 | ONR Approval of Safety Case (Letter sent to initiate) EC NNNNN <Enter Paper Title Here> ==> KDM | 2023-06-22 | 2023-12-07 | 120 | 0
A1430 | Prepare the Safety Case Proposal | 2022-10-24 | 2023-02-15 | 80 | 0
A1340 | Produce supporting reference <Insert Title> | 2022-07-28 | 2022-09-22 | 40 | 0
A1400 | Scope Work or Produce RFS | 2022-06-30 | 2022-07-27 | 20 | 0
A1570 | Specialist Assessments if Necessary (Expand as Required) | 2023-02-23 | 2023-03-22 | 20 | 6
A1350 | Verify supporting reference or EDF Technical review of supporting reference <Insert Title> | 2022-09-23 | 2022-10-13 | 15 | 0
A1620 | INSA review & iteration of comments (using BARRIER MODEL) | 2023-03-31 | 2023-04-24 | 15 | 0
A1060 | CO and PCE Create Initial Plan of Work ==> KDM | 2022-02-09 | 2022-02-22 | 10 | 17
A1730 | Develop Implementation & closeout Plan | 2023-12-27 | 2024-01-10 | 10 | 20
A1590 | Prepare and Populate Affected Documents List | 2022-10-21 | 2022-11-03 | 10 | 298
A1720 | Revise all Affected Drawings and Documents for EC Approval | 2023-12-11 | 2023-12-22 | 10 | 20
A1530 | Final Verification ==> KDM | 2023-03-17 | 2023-03-30 | 10 | 0
A1110 | SRD comments on NSRS | 2022-04-06 | 2022-04-21 | 10 | 17
A1150 | DA & SRD agree NSRS (for authorised designers-NSRS must be reviewed by DA) ==> KDM | 2022-05-11 | 2022-05-24 | 10 | 17
A1120 | Incorporate SRD, Station, DA (peer) comments | 2022-04-22 | 2022-05-06 | 10 | 17
A10100 | Initiate and Register EC and identify Milestones in AMS EC NNNNN<Enter Paper Title Here> | 2022-01-11 | 2022-01-24 | 10 | 17
A1460 | Verification of the case (using BARRIER MODEL) | 2023-02-23 | 2023-03-08 | 10 | 0
A1240 | Create EC Definition Document if not part of Project Definition Document (Insert Template Ref) | 2022-03-09 | 2022-03-22 | 10 | 17
A1140 | Station agree NSRS ==> KDM | 2022-05-11 | 2022-05-24 | 10 | 17
A1100 | DA (Peer) comments on NSRS | 2022-03-09 | 2022-03-22 | 10 | 37
A1090 | Station comments on NSRS | 2022-03-09 | 2022-03-22 | 10 | 37
A1080 | Produce draft NSRS (using BARRIER MODEL) | 2022-02-23 | 2022-03-08 | 10 | 17
A1010 | Produce MF EC NNNNN <Enter Paper Title Here> & obtain approval | 2022-01-25 | 2022-02-07 | 10 | 17
A1230 | Hold Case Conference as Appropriate | 2022-02-23 | 2022-03-01 | 5 | 490
A1380 | Address TR or Verifiers Comments <Insert Title> | 2022-10-14 | 2022-10-20 | 5 | 0
A1520 | Prepare Station Director's Brief | 2023-03-31 | 2023-04-06 | 5 | 45
A1280 | Circulate work programme to stakeholders for agreement | 2022-07-04 | 2022-07-08 | 5 | 401
A1260 | Identify verifier for the case & establish all other resources | 2022-02-10 | 2022-02-16 | 5 | 41
A1630 | Incorporate INSA comments | 2023-04-25 | 2023-05-02 | 5 | 0
A1660 | NSC Consideration & advice to Station Director ==> KDM | 2023-06-01 | 2023-06-07 | 5 | 10
A1610 | DA (Authorised Designer) Approval of CAT1 Safety Case | 2023-03-31 | 2023-04-06 | 5 | 15
A1000 | Mod Requested, Identify RE and EC Request Raised and Screened | 2022-01-04 | 2022-01-10 | 5 | 17
A1440 | Obtain peer review (if required) ==> KDM | 2023-02-16 | 2023-02-22 | 5 | 0
A1180 | Circulate NSRS for Relevant Stakeholders | 2022-06-23 | 2022-06-29 | 5 | 0
A1270 | Agree INSA resource with INA | 2022-03-30 | 2022-04-05 | 5 | 17
A1330 | Agree design proposals with Station in the case of hardware mods | 2022-03-30 | 2022-04-05 | 5 | 465
A1250 | Hold project kick start meeting with Station & key suppliers | 2022-03-23 | 2022-03-29 | 5 | 17
A1490 | Incorporate all stakeholder comments | 2023-03-09 | 2023-03-13 | 3 | 3
A1420 | Produce verification plan | 2022-10-24 | 2022-10-25 | 2 | 326
A1070 | CA to agree with CO format of the safety case | 2022-02-10 | 2022-02-11 | 2 | 173
A1320 | Baseline Plan to Verification Commenced (T-11) ==> KDM | 2022-07-11 | 2022-07-11 | 1 | 401
A1220 | NSRS Presented to NSC (for complex CAT 1 cases) | 2022-06-22 | 2022-06-22 | 1 | 0
A1190 | Send NSRS to ONR to determine level of review required (Acknowledgement or Agreement) | 2022-06-30 | 2022-06-30 | 1 | 79
A1290 | Continue to Develop & resource mandatory template ==> KDM | 2022-07-01 | 2022-07-01 | 1 | 401
A1470 | NSORC review and agree NSC CAT 1 Paper - < insert title > (SZB Only) | 2023-03-16 | 2023-03-16 | 1 | 0
A1690 | Post Job Debrief | 2024-02-08 | 2024-02-08 | 1 | 0
A1020 | Initial Categorisation by Station ==> KDM | 2022-02-08 | 2022-02-08 | 1 | 17
KDM.BU.02 | KDM - Station Approve EC NNNNN <Enter Paper Title Here> | 2023-12-08 | 2023-12-08 | 1 | 0
A1030 | Appoint CO & CA | 2022-02-09 | 2022-02-09 | 1 | 41
A1160 | NSORC agree NSRS (SZB) ==> KDM | 2022-05-25 | 2022-05-25 | 1 | 17
A1130 | Issue final NSRS | 2022-05-09 | 2022-05-09 | 1 | 17
A1550 | Verification Commenced (T-11) | 2023-02-23 | 2023-02-23 | 0 | 243
KDM.PR02 | KDM - Safety Case Paper Authoring Complete EC NNNNN <Enter Paper Title Here> (Cat 1 KDM) ==> KDM | 2023-02-22 | 2023-02-22 | 0 | 0
A1560 | Issue to NSORC (SZB) | 2023-03-08 | 2023-03-08 | 0 | 0
A1200 | Issue to NSORC (SZB Only) | 2022-05-06 | 2022-05-06 | 0 | 24
KDM.SP06 | KDM - ONR Agree/Acknowledge Safety Case EC NNNNN <Enter Paper Title Here> ==> KDM | 2023-12-07 | 2023-12-07 | 0 | 0
KDM.SP05 | KDM - INSA Final Approval EC NNNNN <Enter Paper Title Here> | 2023-06-21 | 2023-06-21 | 0 | 0
KDM.PR01 | KDM - Gate EC3 Completed and NSC/ONR dates Committed | 2023-02-22 | 2023-02-22 | 0 | 243
A1390 | Commence Supporting References or Supporting EC's | 2022-06-29 | 2022-06-29 | 0 | 0
KDM.SP03 | KDM - Gate EC2 completed and Cat 1 Baselined EC NNNNN <Enter Paper Title Here> | 2022-07-04 | 2022-07-04 | 0 | 406
KDM.SP01 | KDM - Gate EC1 completed EC NNNNN <Enter Paper Title Here> | 2022-02-22 | 2022-02-22 | 0 | 17
A1410 | All supporting references Approved and Issued | 2022-10-20 | 2022-10-20 | 0 | 0
A1370 | Supporting reference Complete <Insert Title> Approved and issued | 2022-10-20 | 2022-10-20 | 0 | 0
KDM.SP02 | KDM - NSRS agreed by stakeholders EC NNNNN <Enter Paper Title Here> | 2022-05-25 | 2022-05-25 | 0 | 17
A1640 | INSA Assessment Substantially Comp (T - 3 weeks before NSC date) ==> KDM | 2023-05-02 | 2023-05-02 | 0 | 0
A1480 | Issue to CO & Station for comments | 2023-03-08 | 2023-03-08 | 0 | 3
A1510 | Submit for approval - Categoriser ratifies; RE/CO endorsement ==> KDM | 2023-03-30 | 2023-03-30 | 0 | 0
KDM.BU01 | KDM - Safetc Case Presented at NSC EC NNNNN <Enter Paper Title Here> (Cat 1 KDM) (T) ==> KDM | 2023-05-23 | 2023-05-23 | 0 | 0
KDM.PR03 | KDM - Verification Complete/ Verified Draft A Issued for INSA (T-7) EC NNNNN <Enter Paper Title Here> ==> KDM | 2023-03-30 | 2023-03-30 | 0 | 0

## ALR2 2024 Year Table
Workpack | Project Name | Year of Month | Change in Submission Aug to Latest | Change in Submission June To Aug | Change in Submission Overall | Actuals & Gate 2 Submission Cost | Actuals & June Submission Cost | Actuals & Submission Cost
W200 | Prog 6.1-Reg.1 Reactors Shutdown SC | 2020 | £0K | £0K | £0K | -£4K | -£4K | -£4K
W200 | Prog 6.1-Reg.1 Reactors Shutdown SC | 2019 | £0K | £0K | £0K | £161K | £161K | £161K
W200 | Prog 6.1-Reg.1 Reactors Shutdown SC | 2018 | £0K | £0K | £0K | £1,371K | £1,371K | £1,371K
W200 | Prog 6.1-Reg.1 Reactors Shutdown SC | 2017 | £0K | £0K | £0K | £488K | £488K | £488K
W201 | HNB Reactors Shutdown Essential SC | 2022 | £0K | £0K | £0K | £27K | £27K | £27K
W201 | HNB Reactors Shutdown Essential SC | 2021 | £0K | £0K | £0K | £269K | £269K | £269K
W201 | HNB Reactors Shutdown Essential SC | 2020 | £0K | £0K | £0K | £1,309K | £1,309K | £1,309K
W201 | HNB Reactors Shutdown Essential SC | 2019 | £0K | £0K | £0K | £2,732K | £2,732K | £2,732K
W201 | HNB Reactors Shutdown Essential SC | 2018 | £0K | £0K | £0K | £42K | £42K | £42K
W202 | HRA Reactors Shutdown Essential Safety Cases | 2025 | £0K | £0K | £0K | £38K | £38K | £38K
W202 | HRA Reactors Shutdown Essential Safety Cases | 2024 | £0K | £0K | £0K | £103K | £103K | £103K
W202 | HRA Reactors Shutdown Essential Safety Cases | 2023 | £0K | £0K | £0K | £186K | £186K | £186K
W202 | HRA Reactors Shutdown Essential Safety Cases | 2022 | £0K | £0K | £0K | £354K | £354K | £354K
W202 | HRA Reactors Shutdown Essential Safety Cases | 2021 | £0K | £0K | £0K | £587K | £587K | £587K
W202 | HRA Reactors Shutdown Essential Safety Cases | 2020 | £0K | £0K | £0K | £808K | £808K | £808K
W202 | HRA Reactors Shutdown Essential Safety Cases | 2019 | £0K | £0K | £0K | £29K | £29K | £29K
W203 | HNB Enhanced Defuelling Safety Cases | 2025 | £0K | £0K | £0K | £30K | £30K | £30K
W203 | HNB Enhanced Defuelling Safety Cases | 2024 | £0K | £0K | £0K | £115K | £115K | £115K
W203 | HNB Enhanced Defuelling Safety Cases | 2023 | £0K | £0K | £0K | £142K | £142K | £142K
W203 | HNB Enhanced Defuelling Safety Cases | 2022 | £0K | £0K | £0K | £0K | £0K | £0K
W203 | HNB Enhanced Defuelling Safety Cases | 2021 | £0K | £0K | £0K | £22K | £22K | £22K
W203 | HNB Enhanced Defuelling Safety Cases | 2020 | £0K | £0K | £0K | £30K | £30K | £30K
W204 | HRA Reactors Shutdown Enhanced SC | 2020 | £0K | £0K | £0K | £0K | £0K | £0K
W205 | HPB Reactor Shutdown Essential SC | 2022 | £0K | £0K | £0K | £33K | £33K | £33K
W205 | HPB Reactor Shutdown Essential SC | 2021 | £0K | £0K | £0K | £275K | £275K | £275K
W205 | HPB Reactor Shutdown Essential SC | 2020 | £0K | £0K | £0K | £427K | £427K | £427K
W206 | HYA Reactors Shutdown Essential Safety Cases | 2025 | £0K | £0K | £0K | £38K | £38K | £38K
W206 | HYA Reactors Shutdown Essential Safety Cases | 2024 | £0K | £0K | £0K | £107K | £107K | £107K
W206 | HYA Reactors Shutdown Essential Safety Cases | 2023 | £0K | £0K | £0K | £173K | £173K | £173K
W206 | HYA Reactors Shutdown Essential Safety Cases | 2022 | £0K | £0K | £0K | £361K | £361K | £361K
W206 | HYA Reactors Shutdown Essential Safety Cases | 2021 | £0K | £0K | £0K | £586K | £586K | £586K
W206 | HYA Reactors Shutdown Essential Safety Cases | 2020 | £0K | £0K | £0K | £422K | £422K | £422K
W207 | HPB Enhanced Defuelling Safety Cases | 2025 | £0K | £0K | £0K | £30K | £30K | £30K
W207 | HPB Enhanced Defuelling Safety Cases | 2024 | £0K | £0K | £0K | £121K | £121K | £121K
W207 | HPB Enhanced Defuelling Safety Cases | 2023 | £0K | £0K | £0K | £176K | £176K | £176K
W207 | HPB Enhanced Defuelling Safety Cases | 2022 | £0K | £0K | £0K | £0K | £0K | £0K
W207 | HPB Enhanced Defuelling Safety Cases | 2021 | £0K | £0K | £0K | £35K | £35K | £35K
W207 | HPB Enhanced Defuelling Safety Cases | 2020 | £0K | £0K | £0K | £15K | £15K | £15K
W209 | HYB Essential Defueling Safety Case | 2025 | £0K | £0K | £0K | £94K | £94K | £94K
W209 | HYB Essential Defueling Safety Case | 2024 | £0K | £0K | £0K | £505K | £505K | £505K
W209 | HYB Essential Defueling Safety Case | 2023 | £0K | £0K | £0K | £1,087K | £1,087K | £1,087K
W209 | HYB Essential Defueling Safety Case | 2022 | £0K | £0K | £0K | £1,349K | £1,349K | £1,349K
W209 | HYB Essential Defueling Safety Case | 2021 | £0K | £0K | £0K | £100K | £100K | £100K
W211 | DNB Follow-on Defuelling Safety Case | 2025 | £0K | £0K | £0K | £15K | £15K | £15K
W211 | DNB Follow-on Defuelling Safety Case | 2024 | £0K | £0K | £0K | £416K | £416K | £416K
W211 | DNB Follow-on Defuelling Safety Case | 2023 | £0K | £0K | £0K | £805K | £805K | £805K
W211 | DNB Follow-on Defuelling Safety Case | 2022 | £0K | £0K | £0K | £1,016K | £1,016K | £1,016K
W211 | DNB Follow-on Defuelling Safety Case | 2021 | £0K | £0K | £0K | £78K | £78K | £78K
W211 | DNB Follow-on Defuelling Safety Case | 2020 | £0K | £0K | £0K | £136K | £136K | £136K
W213 | TOR Essential Defueling Safety Case | 2025 | £0K | £0K | £0K | £86K | £86K | £86K
W213 | TOR Essential Defueling Safety Case | 2024 | £0K | £0K | £0K | £457K | £457K | £457K
W213 | TOR Essential Defueling Safety Case | 2023 | £0K | £0K | £0K | £1,068K | £1,068K | £1,068K
W213 | TOR Essential Defueling Safety Case | 2022 | £0K | £0K | £0K | £1,332K | £1,332K | £1,332K
W213 | TOR Essential Defueling Safety Case | 2021 | £0K | £0K | £0K | £117K | £117K | £117K
W220 | Prog 6.2-Reg.1 Stn Fuel Route Handl.SC | 2020 | £0K | £0K | £0K | -£6K | -£6K | -£6K
W220 | Prog 6.2-Reg.1 Stn Fuel Route Handl.SC | 2019 | £0K | £0K | £0K | £109K | £109K | £109K
W220 | Prog 6.2-Reg.1 Stn Fuel Route Handl.SC | 2018 | £0K | £0K | £0K | £1,343K | £1,343K | £1,343K
W220 | Prog 6.2-Reg.1 Stn Fuel Route Handl.SC | 2017 | £0K | £0K | £0K | £531K | £531K | £531K
W221 | HNB Fuel Handling Essential Safety Case | 2022 | £0K | £0K | £0K | £66K | £66K | £66K
W221 | HNB Fuel Handling Essential Safety Case | 2021 | £0K | £0K | £0K | £304K | £304K | £304K
W221 | HNB Fuel Handling Essential Safety Case | 2020 | £0K | £0K | £0K | £1,204K | £1,204K | £1,204K
W221 | HNB Fuel Handling Essential Safety Case | 2019 | £0K | £0K | £0K | £2,479K | £2,479K | £2,479K
W221 | HNB Fuel Handling Essential Safety Case | 2018 | £0K | £0K | £0K | £226K | £226K | £226K
W222 | HRA Fuel Handling Essential Safety Case | 2025 | £0K | £0K | £0K | £45K | £45K | £45K
W222 | HRA Fuel Handling Essential Safety Case | 2024 | £0K | £0K | £0K | £299K | £299K | £299K
W222 | HRA Fuel Handling Essential Safety Case | 2023 | £0K | £0K | £0K | £338K | £338K | £338K
W222 | HRA Fuel Handling Essential Safety Case | 2022 | £0K | £0K | £0K | £435K | £435K | £435K
W222 | HRA Fuel Handling Essential Safety Case | 2021 | £0K | £0K | £0K | £963K | £963K | £963K
W222 | HRA Fuel Handling Essential Safety Case | 2020 | £0K | £0K | £0K | £1,291K | £1,291K | £1,291K
W222 | HRA Fuel Handling Essential Safety Case | 2019 | £0K | £0K | £0K | £43K | £43K | £43K
W224 | HRA Enhanced Defueling Safety Case | 2026 | £3K | £5K | £8K | £13K | £7K | £15K
W224 | HRA Enhanced Defueling Safety Case | 2025 | £43K | £117K | £160K | £788K | £671K | £831K
W224 | HRA Enhanced Defueling Safety Case | 2024 | £0K | £66K | £66K | £249K | £182K | £249K
W224 | HRA Enhanced Defueling Safety Case | 2023 | £0K | £0K | £0K | £17K | £17K | £17K
W225 | HPB Fuel Handling Essential SC | 2022 | £0K | £0K | £0K | £74K | £74K | £74K
W225 | HPB Fuel Handling Essential SC | 2021 | £0K | £0K | £0K | £284K | £284K | £284K
W225 | HPB Fuel Handling Essential SC | 2020 | £0K | £0K | £0K | £410K | £410K | £410K
W226 | HYA Fuel Handling Essential Safety Case | 2025 | £0K | £0K | £0K | £45K | £45K | £45K
W226 | HYA Fuel Handling Essential Safety Case | 2024 | £0K | £0K | £0K | £303K | £303K | £303K
W226 | HYA Fuel Handling Essential Safety Case | 2023 | £0K | £0K | £0K | £337K | £337K | £337K
W226 | HYA Fuel Handling Essential Safety Case | 2022 | £0K | £0K | £0K | £492K | £492K | £492K
W226 | HYA Fuel Handling Essential Safety Case | 2021 | £0K | £0K | £0K | £960K | £960K | £960K
W226 | HYA Fuel Handling Essential Safety Case | 2020 | £0K | £0K | £0K | £730K | £730K | £730K
W228 | HYA Enhanced Defueling Safety Case | 2026 | £3K | £5K | £8K | £13K | £7K | £15K
W228 | HYA Enhanced Defueling Safety Case | 2025 | £43K | £117K | £160K | £788K | £671K | £831K
W228 | HYA Enhanced Defueling Safety Case | 2024 | £0K | £68K | £68K | £250K | £182K | £250K
W228 | HYA Enhanced Defueling Safety Case | 2023 | £0K | £0K | £0K | £17K | £17K | £17K
W229 | HYB SC Superseded by W209 | 2022 | £0K | £0K | £0K | £0K | £0K | £0K
W229 | HYB SC Superseded by W209 | 2021 | £0K | £0K | £0K | £0K | £0K | £0K
W230 | HYB Enhanced Defueling Safety Case Strategy | 2025 | £0K | £0K | £0K | £154K | £154K | £154K
W230 | HYB Enhanced Defueling Safety Case Strategy | 2024 | £0K | £0K | £0K | £108K | £108K | £108K
W231 | DNB Fuel Handling Essential SC | 2023 | £0K | £0K | £0K | -£6K | -£6K | -£6K
W231 | DNB Fuel Handling Essential SC | 2022 | £0K | £0K | £0K | £9K | £9K | £9K
W231 | DNB Fuel Handling Essential SC | 2021 | £0K | £0K | £0K | £165K | £165K | £165K
W231 | DNB Fuel Handling Essential SC | 2020 | £0K | £0K | £0K | £29K | £29K | £29K
W232 | DNB Enhanced Safety Cases | 2025 | £0K | £0K | £0K | £403K | £403K | £403K
W232 | DNB Enhanced Safety Cases | 2024 | £0K | £0K | £0K | £473K | £473K | £473K
W232 | DNB Enhanced Safety Cases | 2023 | £0K | £0K | £0K | £613K | £613K | £613K
W232 | DNB Enhanced Safety Cases | 2022 | £0K | £0K | £0K | £57K | £57K | £57K
W233 | TOR Fuel Handling Essential SC | 2022 | £0K | £0K | £0K | -£13K | -£13K | -£13K
W233 | TOR Fuel Handling Essential SC | 2021 | £0K | £0K | £0K | £0K | £0K | £0K
W234 | TOR Enhanced Defueling Safety Case Strategy | 2025 | £0K | £0K | £0K | £154K | £154K | £154K
W234 | TOR Enhanced Defueling Safety Case Strategy | 2024 | £0K | £0K | £0K | £108K | £108K | £108K
W520 | FLEETWIDE CTO Defueling Safety Case Delivery | 2026 | £740K | £0K | £740K | £498K | £498K | £1,239K
W520 | FLEETWIDE CTO Defueling Safety Case Delivery | 2025 | £168K | £0K | £168K | £1,070K | £1,070K | £1,239K
W520 | FLEETWIDE CTO Defueling Safety Case Delivery | 2024 | £0K | £0K | £0K | £885K | £885K | £885K
W520 | FLEETWIDE CTO Defueling Safety Case Delivery | 2023 | £0K | £0K | £0K | £976K | £976K | £976K
W520 | FLEETWIDE CTO Defueling Safety Case Delivery | 2022 | £0K | £0K | £0K | £1,128K | £1,128K | £1,128K
W520 | FLEETWIDE CTO Defueling Safety Case Delivery | 2021 | £0K | £0K | £0K | £685K | £685K | £685K
W521 | DNB Initial Defuelling Safety Case | 2023 | £0K | £0K | £0K | £33K | £33K | £33K
W521 | DNB Initial Defuelling Safety Case | 2022 | £0K | £0K | £0K | £1,223K | £1,223K | £1,223K
W521 | DNB Initial Defuelling Safety Case | 2021 | £0K | £0K | £0K | £1,965K | £1,965K | £1,965K
W699 | DNB Cold Defuelling Safety Case | 2025 | £0K | £0K | £0K | £206K | £206K | £206K
W699 | DNB Cold Defuelling Safety Case | 2024 | £0K | £0K | £0K | £423K | £423K | £423K
W730 | HYB Enhanced Defueling Safety Cases | 2027 | £0K | £0K | £0K | £323K | £323K | £323K
W730 | HYB Enhanced Defueling Safety Cases | 2026 | £0K | £0K | £0K | £423K | £423K | £423K
W730 | HYB Enhanced Defueling Safety Cases | 2025 | £0K | £0K | £0K | £398K | £398K | £398K
W731 | TOR Enhanced Defueling Safety Cases | 2027 | £0K | £0K | £0K | £323K | £323K | £323K
W731 | TOR Enhanced Defueling Safety Cases | 2026 | £0K | £0K | £0K | £423K | £423K | £423K
W731 | TOR Enhanced Defueling Safety Cases | 2025 | £0K | £0K | £0K | £398K | £398K | £398K
W772 | DNB Pull Harder Safety Case | 2026 | £206K | £0K | £206K | 0 | 0 | £206K
W772 | DNB Pull Harder Safety Case | 2025 | £423K | £0K | £423K | 0 | 0 | £423K
W783 | DNB Tie Bar Cutting Removal Safety Case | 2025 | £315K | £0K | £315K | 0 | 0 | £315K
W784 | DNB Cold Depressurised Safety Case | 2026 | £206K | £0K | £206K | 0 | 0 | £206K
W784 | DNB Cold Depressurised Safety Case | 2025 | £423K | £0K | £423K | 0 | 0 | £423K