## sc_plans
Project ID | CTO.PG.Workpack Number | Activity ID | Project Name | Activity Name | start_date | finish_date | original_duration | remaining_duration | completion_duration | actual_duration | physical_%_complete | effectiveness | is_complete | activity_status
ER6243LT | W200 | A10430 | REGION 1 Reactors Shutdown Safety Cases Programme | P.10.01.01 - Defuelling Shutdown Safety Cases - Project Management | 2017-05-02 | 2017-12-29 | 149 | 0 | 169 | 241 | 100% | 0.61826 | 1 | Completed
ER6243LT | W200 | A10440 | REGION 1 Reactors Shutdown Safety Cases Programme | P.10.01.02 - Defuelling Shutdown Safety Cases - Safety Case | 2017-05-02 | 2017-12-29 | 149 | 0 | 169 | 241 | 100% | 0.61826 | 1 | Completed
ER6243LT | W200 | A10450 | REGION 1 Reactors Shutdown Safety Cases Programme | P.10.01.03 - Defuelling Shutdown Safety Cases - Operation Compliance | 2017-05-02 | 2017-12-29 | 149 | 0 | 169 | 241 | 100% | 0.61826 | 1 | Completed
ER6243LT | W200 | A10490 | REGION 1 Reactors Shutdown Safety Cases Programme | P.10.01.11 - Defuelling Shutdown Safety Cases - Vessel Integrity | 2017-05-02 | 2017-12-29 | 140 | 0 | 169 | 241 | 100% | 0.58091 | 1 | Completed
ER6243LT | W200 | A10840 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - RFS Summary - PCPV Hanging Plug Unit | 2017-05-02 | 2017-09-22 | 96 | 0 | 101 | 143 | 100% | 0.67133 | 1 | Completed
ER6243LT | W200 | A10850 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Prepare Request for Service (RFS) | 2017-05-02 | 2017-06-09 | 24 | 0 | 27 | 38 | 100% | 0.63158 | 1 | Completed
ER6243LT | W200 | A13070 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Verification Engineering Specification | 2017-05-02 | 2017-06-16 | 33 | 0 | 32 | 45 | 100% | 0.73333 | 1 | Completed
ER6243LT | W200 | A13180 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity Summary - Outline Investment | 2017-05-02 | 2019-03-19 | 488 | 0 | 477 | 686 | 100% | 0.71137 | 1 | Completed
ER6244LT | W220 | A1000 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Cost Profile and Reporting Activity | 2017-05-02 | 2019-12-02 | 1920 | 0 | 656 | 944 | 100% | 2.0339 | 1 | Completed
ER6244LT | W220 | A1130 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Project Management Costs Gate A to Gate B | 2017-05-02 | 2019-01-16 | 359 | 0 | 434 | 624 | 100% | 0.57532 | 1 | Completed
ER6243LT | W200 | RSSC.PM.A100 | REGION 1 Reactors Shutdown Safety Cases Programme | Project Management for the phase of work to Gate B | 2017-05-02 | 2019-10-11 | 359 | 0 | 620 | 892 | 100% | 0.40247 | 1 | Completed
ER6243LT | W200 | A3000 | REGION 1 Reactors Shutdown Safety Cases Programme | Project Start Date [FEEDS TO SUMMARY SCHEDULE] | 2017-05-02 | 2017-05-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A1740 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Project Start Date [FEEDS TO SUMMARY SCHEDULE] | 2017-05-02 | 2017-05-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A3040.C0 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Alignment of Internal Resource to the Plan and Contractor Resource to Execute Gate A to B | 2017-05-02 | 2017-05-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A4060 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.01 - Project Management | 2017-05-02 | 2017-12-29 | 170 | 0 | 169 | 241 | 100% | 0.70539 | 1 | Completed
ER6244LT | W220 | A4070 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.02 - Safety Case (Del 3005569) | 2017-05-02 | 2017-12-29 | 170 | 0 | 169 | 241 | 100% | 0.70539 | 1 | Completed
ER6244LT | W220 | A4100 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.05 - Defuelling Process (Del 3005570) | 2017-05-02 | 2018-04-30 | 170 | 0 | 252 | 363 | 100% | 0.46832 | 1 | Completed
ER6244LT | W220 | A4170 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.12 - Structural Integrity (Del 3005574) | 2017-05-02 | 2018-01-31 | 170 | 0 | 191 | 274 | 100% | 0.62044 | 1 | Completed
ER6244LT | W220 | A5620 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for Dropped FPU impact on Reactor Internals and Standpipe Breach EAN (HPB and HNB) | 2017-05-02 | 2017-05-08 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6243LT | W200 | A11930 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - RFS Summary | 2017-05-02 | 2017-07-07 | 55 | 0 | 48 | 66 | 100% | 0.83333 | 1 | Completed
ER6243LT | W200 | A11940 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Prepare Request for Service (RFS) Specification | 2017-05-02 | 2017-05-05 | 5 | 0 | 4 | 3 | 100% | 1.6667 | 1 | Completed
ER6243LT | W200 | A11950 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Review, Approve and Issue RFS to Supplier | 2017-05-02 | 2017-05-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11929 | REGION 1 Reactors Shutdown Safety Cases Programme | Operation Compliance Summary - Outline Investment | 2017-05-02 | 2018-12-20 | 446 | 0 | 417 | 597 | 100% | 0.74707 | 1 | Completed
ER6243LT | W200 | A1000 | REGION 1 Reactors Shutdown Safety Cases Programme | Summary for HNB Reactors Shutdown Safety Cases Programme W200 | 2017-05-02 | 2020-04-15 | 1 | 0 | 748 | 1079 | 100% | 0.00092678 | 1 | Completed
ER6244LT | W220 | W220.A1030 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Summary for Defuelling Programme Fuel Handling Safety Case W220 | 2017-05-02 | 2020-04-15 | 1 | 0 | 749 | 1079 | 100% | 0.00092678 | 1 | Completed
ER6244LT | W220 | A4080 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.09 - Radiological Consequences | 2017-05-03 | 2018-01-31 | 170 | 0 | 190 | 273 | 100% | 0.62271 | 1 | Completed
ER6243LT | W200 | A11960 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Prepare and Issue Offer | 2017-05-03 | 2017-05-31 | 33 | 0 | 20 | 28 | 100% | 1.1786 | 1 | Completed
ER6244LT | W220 | A5100 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for CO2 purity and decay heat report | 2017-05-09 | 2017-06-26 | 5 | 0 | 33 | 48 | 100% | 0.10417 | 1 | Completed
ER6244LT | W220 | A5630 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for Dropped FPU impact on Reactor Internals and Standpipe Breach EAN (HPB and HNB) | 2017-05-09 | 2017-05-10 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6243LT | W200 | A3030.C0 | REGION 1 Reactors Shutdown Safety Cases Programme | Approval of programme optioneering phase 2 for Region 1 stations gate A to B | 2017-05-11 | 2017-05-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A3040 | REGION 1 Reactors Shutdown Safety Cases Programme | Alignment of Internal Resource to the Plan and Contractor Resource to Excute Gate A to B | 2017-05-11 | 2017-05-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5640 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued by FNC for Dropped FPU impact on Reactor Internals and Standpipe Breach EAN (HPB and HNB) | 2017-05-11 | 2017-06-12 | 22 | 0 | 22 | 32 | 100% | 0.6875 | 1 | Completed
ER6244LT | W220 | A5650 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for Dropped FPU impact on Reactor Internals and Standpipe Breach EAN (HPB and HNB) | 2017-05-15 | 2017-05-16 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6244LT | W220 | A5750 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for Dropped FPU impact on Reactor Internals EAN (HYA and HRA) | 2017-05-16 | 2017-05-16 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5660 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete req. approval and issue CI for Dropped FPU impact on Reactor Internals and Standpipe Breach EAN (HPB and HNB) | 2017-05-17 | 2017-05-18 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6244LT | W220 | A5760 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for Dropped FPU impact on Reactor Internals EAN (HYA and HRA) | 2017-05-17 | 2017-05-17 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5770 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued by FNC for Dropped FPU impact on Reactor Internals EAN (HYA and HRA) | 2017-05-18 | 2017-05-24 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A6400 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Dropped FPU Impact on Reactor Internals Assessments (HPB/HNB): Req Approved | 2017-05-18 | 2017-05-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A10510 | REGION 1 Reactors Shutdown Safety Cases Programme | P.10.01.19 - Defuelling Shutdown Safety Cases - Supporting Systems | 2017-05-19 | 2017-05-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5670 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2017-05-19 | 2017-05-19 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5680 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for Dropped FPU impact on Reactor Internals and Standpipe Breach EAN (HPB and HNB) | 2017-05-22 | 2017-05-22 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5690 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Dropped FPU impact on Reactor Internals and Standpipe Breach EAN (HPB and HNB) | 2017-05-22 | 2017-05-26 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6244LT | W220 | A5780 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for Dropped FPU impact on Reactor Internals EAN (HYA and HRA) | 2017-05-25 | 2017-05-31 | 10 | 0 | 3 | 6 | 100% | 1.6667 | 1 | Completed
ER6244LT | W220 | A5700 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Dropped FPU impact on Reactor Internals and Standpipe Breach EAN (HPB and HNB) verified & issued for tech. review | 2017-05-26 | 2017-05-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11970 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Review and Negotiate Offer | 2017-05-31 | 2017-06-16 | 5 | 0 | 13 | 16 | 100% | 0.3125 | 1 | Completed
ER6244LT | W220 | A2180.C0 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Approval of Programme Detailed Optioneering (Phase 2) for Region 1 Stations Gate A to B | 2017-05-31 | 2017-05-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A4110 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.06 - Lifting Integrity (Del 3005571) | 2017-06-01 | 2017-10-31 | 106 | 0 | 107 | 152 | 100% | 0.69737 | 1 | Completed
ER6243LT | W200 | A10520 | REGION 1 Reactors Shutdown Safety Cases Programme | P.10.01.22 - Defuelling Shutdown Safety Cases - Decommissioning Phase | 2017-06-01 | 2017-06-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A1270 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Establish fuelling machine trip settings/overrun speeds for new PIFA/IFA/Loading FPUs for defuelling. HPB and HNB | 2017-06-01 | 2018-01-02 | 150 | 0 | 150 | 215 | 100% | 0.69767 | 1 | Completed
ER6243LT | W200 | A10420 | REGION 1 Reactors Shutdown Safety Cases Programme | P.10 - Reactors Shutdown Safety Cases | 2017-06-01 | 2017-06-01 | 0 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A10540 | REGION 1 Reactors Shutdown Safety Cases Programme | P.10.01.25 - Defuelling Shutdown Safety Cases - Station Support | 2017-06-01 | 2017-06-01 | 0 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5710 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical review of Dropped FPU impact on Reactor Internals and Standpipe Breach EAN (HPB and HNB) | 2017-06-01 | 2017-06-14 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6244LT | W220 | A5790 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for Dropped FPU impact on Reactor Internals EAN (HYA and HRA) | 2017-06-01 | 2017-06-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A8510 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for Initial Fault Studies and Risk Estimation Report (HYA/HRA) | 2017-06-01 | 2017-06-09 | 7 | 0 | 7 | 8 | 100% | 0.875 | 1 | Completed
ER6244LT | W220 | A1240 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Large batch refuelling - feasibility/impact on reactor operations (including radial shuffling and fuel route logistics) | 2017-06-02 | 2017-10-30 | 106 | 0 | 106 | 150 | 100% | 0.70667 | 1 | Completed
ER6244LT | W220 | A8220 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Dropped FPU Impact on Reactor Internals Assessments (HPB/HNB): Req Approved | 2017-06-07 | 2017-06-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5800 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2017-06-08 | 2017-06-12 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6244LT | W220 | A5810.EJ | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for Dropped FPU impact on Reactor Internals EAN (HYA and HRA) | 2017-06-12 | 2017-06-12 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5820 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Dropped FPU impact on Reactor Internals Report (HYA and HRA) | 2017-06-12 | 2017-08-01 | 60 | 0 | 37 | 50 | 100% | 1.2 | 1 | Completed
ER6244LT | W220 | A8520 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for Initial Fault Studies and Risk Estimation Report (HYA/HRA) | 2017-06-12 | 2017-06-16 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6244LT | W220 | A5230 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for Refuelling Cooling Assessment EAN | 2017-06-15 | 2017-07-21 | 13 | 0 | 26 | 36 | 100% | 0.36111 | 1 | Completed
ER6244LT | W220 | A5720 | REGION 1 Defuelling Programme Fuel Handling Safety Case | FNC update and issue Dropped FPU impact on Reactor Internals and Standpipe Breach EAN (HPB and HNB) | 2017-06-15 | 2017-06-16 | 10 | 0 | 1 | 1 | 100% | 10 | 1 | Completed
ER6244LT | W220 | A7180 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for Impact of Empty Channels on Reactor Cooling EAN | 2017-06-15 | 2017-07-21 | 13 | 0 | 26 | 36 | 100% | 0.36111 | 1 | Completed
ER6244LT | W220 | A7310 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for Minimum Forced Gas Circulation Requirements EAN | 2017-06-15 | 2017-08-01 | 13 | 0 | 34 | 47 | 100% | 0.2766 | 1 | Completed
ER6243LT | W200 | A13080 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Address Verification Comments | 2017-06-19 | 2017-07-19 | 10 | 0 | 22 | 30 | 100% | 0.33333 | 1 | Completed
ER6244LT | W220 | A5730 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload Dropped FPU impact on Reactor Internals and Standpipe Breach EAN (HPB and HNB) to CDMS | 2017-06-19 | 2017-08-16 | 10 | 0 | 43 | 58 | 100% | 0.17241 | 1 | Completed
ER6243LT | W200 | A11980 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Complete Requisition Approval and Issue CI | 2017-06-19 | 2017-06-19 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8530 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued by supplier for Initial Fault Studies and Risk Estimation Report (HYA/HRA) | 2017-06-19 | 2017-06-20 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6244LT | W220 | A8540 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for Initial Fault Studies and Risk Estimation Report (HYA/HRA) | 2017-06-21 | 2017-06-21 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8550 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for Initial Fault Studies and Risk Estimation Report (HYA/HRA) | 2017-06-22 | 2017-06-22 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8560 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2017-06-23 | 2017-06-30 | 6 | 0 | 6 | 7 | 100% | 0.85714 | 1 | Completed
ER6243LT | W200 | A11990 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Supplier Mobilisation Time | 2017-06-26 | 2017-07-07 | 12 | 0 | 10 | 11 | 100% | 1.0909 | 1 | Completed
ER6244LT | W220 | A5110 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS to Amec for CO2 purity and decay heat report | 2017-06-27 | 2017-06-30 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6244LT | W220 | A4150 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.10 - Fault Studies (Del 3005573) | 2017-07-03 | 2018-01-31 | 106 | 0 | 148 | 212 | 100% | 0.5 | 1 | Completed
ER6244LT | W220 | A4270 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.23 - Maintenance (Del 3005582) | 2017-07-03 | 2018-01-31 | 106 | 0 | 148 | 212 | 100% | 0.5 | 1 | Completed
ER6243LT | W200 | A11730 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - RFS Summary Thermal Hydraulics (MACE) | 2017-07-03 | 2017-11-16 | 109 | 0 | 97 | 136 | 100% | 0.80147 | 1 | Completed
ER6243LT | W200 | A11740 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Prepare Request for Service (RFS) Specification | 2017-07-03 | 2017-09-06 | 9 | 0 | 46 | 65 | 100% | 0.13846 | 1 | Completed
ER6243LT | W200 | A13220 | REGION 1 Reactors Shutdown Safety Cases Programme | Reactor Physics Summary - Outline Investment | 2017-07-03 | 2019-02-28 | 434 | 0 | 421 | 605 | 100% | 0.71736 | 1 | Completed
ER6244LT | W220 | A4120 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.07 - Fuel Storage Conditions (Del 3005572) | 2017-07-03 | 2018-06-29 | 127 | 0 | 251 | 361 | 100% | 0.3518 | 1 | Completed
ER6244LT | W220 | A4130 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.20 - Fuel Route Facilities (Del 3005580) | 2017-07-03 | 2018-01-31 | 127 | 0 | 148 | 212 | 100% | 0.59906 | 1 | Completed
ER6244LT | W220 | A4220 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.17 - Stringer Integrity (Del 3005579) | 2017-07-03 | 2018-01-31 | 127 | 0 | 148 | 212 | 100% | 0.59906 | 1 | Completed
ER6244LT | W220 | A4250 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.21 - Human Factors (Del 3005581) | 2017-07-03 | 2018-01-31 | 127 | 0 | 148 | 212 | 100% | 0.59906 | 1 | Completed
ER6243LT | W200 | A10460 | REGION 1 Reactors Shutdown Safety Cases Programme | P.10.01.04 - Defuelling Shutdown Safety Cases - Reactor Physics | 2017-07-03 | 2018-01-31 | 116 | 0 | 148 | 212 | 100% | 0.54717 | 1 | Completed
ER6244LT | W220 | A5120 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued by Amec for CO2 purity and decay heat report | 2017-07-03 | 2017-07-04 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6244LT | W220 | A6140 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for Buffer Store Defueling EAN (HPB and HNB) | 2017-07-03 | 2017-09-07 | 21 | 0 | 48 | 66 | 100% | 0.31818 | 1 | Completed
ER6244LT | W220 | A6270 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for IFDF Defueling EAN (HPB and HNB) | 2017-07-03 | 2017-09-07 | 21 | 0 | 48 | 66 | 100% | 0.31818 | 1 | Completed
ER6244LT | W220 | A6530 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for IFDF Defueling EAN (HYA and HRA) | 2017-07-03 | 2017-08-01 | 16 | 0 | 22 | 29 | 100% | 0.55172 | 1 | Completed
ER6244LT | W220 | A8240 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 2017-07-03 | 2017-07-06 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6244LT | W220 | A8370 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 2017-07-03 | 2017-07-06 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6244LT | W220 | A8570 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for Initial Fault Studies and Risk Estimation Report (HYA/HRA) | 2017-07-03 | 2017-07-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5130 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for CO2 purity and decay heat report | 2017-07-05 | 2017-07-11 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A8250 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 2017-07-07 | 2017-07-12 | 4 | 0 | 4 | 5 | 100% | 0.8 | 1 | Completed
ER6244LT | W220 | A8380 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 2017-07-07 | 2017-07-12 | 4 | 0 | 4 | 5 | 100% | 0.8 | 1 | Completed
ER6244LT | W220 | A8640 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for Initial Fault Studies and Risk Estimation Report (HPB/HNB) | 2017-07-11 | 2017-07-17 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A5140 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for CO2 purity and decay heat report | 2017-07-12 | 2017-07-14 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6244LT | W220 | A6660 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for Ponds and Flasks EAN (HPB and HNB) | 2017-07-13 | 2017-09-07 | 13 | 0 | 40 | 56 | 100% | 0.23214 | 1 | Completed
ER6244LT | W220 | A7440 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for Assessment of Temperatures vs Decay Heat for Natural Circulation EAN | 2017-07-13 | 2017-08-01 | 14 | 0 | 14 | 19 | 100% | 0.73684 | 1 | Completed
ER6244LT | W220 | A8260 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued for Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 2017-07-13 | 2017-07-18 | 4 | 0 | 4 | 5 | 100% | 0.8 | 1 | Completed
ER6244LT | W220 | A8390 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued for Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 2017-07-13 | 2017-07-18 | 4 | 0 | 4 | 5 | 100% | 0.8 | 1 | Completed
ER6243LT | W200 | A10470 | REGION 1 Reactors Shutdown Safety Cases Programme | P.10.01.08 - Defuelling Shutdown Safety Cases - Cooling - Normal Operations | 2017-07-17 | 2018-01-31 | 66 | 0 | 138 | 198 | 100% | 0.33333 | 1 | Completed
ER6244LT | W220 | A5150 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Amec mobilisation | 2017-07-17 | 2017-07-19 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6244LT | W220 | A8650 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for Initial Fault Studies and Risk Estimation Report (HPB/HNB) | 2017-07-18 | 2017-07-24 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A8270 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 2017-07-19 | 2017-07-24 | 4 | 0 | 4 | 5 | 100% | 0.8 | 1 | Completed
ER6244LT | W220 | A8400 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 2017-07-19 | 2017-07-24 | 4 | 0 | 4 | 5 | 100% | 0.8 | 1 | Completed
ER6243LT | W200 | A10860 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Review, Approve and Issue RFS to Supplier | 2017-07-20 | 2017-07-20 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5160 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for CO2 purity and decay heat report | 2017-07-20 | 2017-07-20 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5170 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft CO2 purity and decay heat report | 2017-07-20 | 2018-01-02 | 30 | 0 | 114 | 166 | 100% | 0.18072 | 1 | Completed
ER6243LT | W200 | A13200 | REGION 1 Reactors Shutdown Safety Cases Programme | Risk Workshop Held | 2017-07-20 | 2017-07-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A10870 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Prepare and Issue Offer | 2017-07-21 | 2017-08-24 | 15 | 0 | 24 | 34 | 100% | 0.44118 | 1 | Completed
ER6244LT | W220 | A5240 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for Refuelling Cooling Assessment EAN | 2017-07-24 | 2017-07-28 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6244LT | W220 | A7190 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for Impact of Empty Channels on Reactor Cooling EAN | 2017-07-24 | 2017-07-28 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6244LT | W220 | A7830 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for Review Radial Shuffling Safety Case EAN (HYA and HRA) | 2017-07-24 | 2017-08-01 | 5 | 0 | 7 | 8 | 100% | 0.625 | 1 | Completed
ER6244LT | W220 | A8770 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for Fuel Free Verification EAN | 2017-07-24 | 2017-08-03 | 8 | 0 | 9 | 10 | 100% | 0.8 | 1 | Completed
ER6244LT | W220 | A9540 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for Fuel Free Verification EAN | 2017-07-24 | 2017-08-03 | 8 | 0 | 9 | 10 | 100% | 0.8 | 1 | Completed
ER6244LT | W220 | A9670 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for Fuel Free Verification EAN | 2017-07-24 | 2017-08-03 | 8 | 0 | 9 | 10 | 100% | 0.8 | 1 | Completed
ER6244LT | W220 | A9800 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for Fuel Free Verification EAN | 2017-07-24 | 2017-08-03 | 8 | 0 | 9 | 10 | 100% | 0.8 | 1 | Completed
ER6244LT | W220 | A8280 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for Justify Zero Maintenance for FPU Prior to Load in Shutdown Reactor EAN | 2017-07-25 | 2017-09-06 | 4 | 0 | 31 | 43 | 100% | 0.093023 | 1 | Completed
ER6244LT | W220 | A8410 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for Justify Zero Maintenance for FPU Prior to Load in Shutdown Reactor EAN | 2017-07-25 | 2017-09-06 | 4 | 0 | 31 | 43 | 100% | 0.093023 | 1 | Completed
ER6244LT | W220 | A8660 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued by supplier for Initial Fault Studies and Risk Estimation Report (HPB/HNB) | 2017-07-25 | 2017-07-26 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6243LT | W200 | RSSC.OC.A100 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - QA3 rpt from defuelling SDM compliance optioneering & control rod/flux detector/monitoring arrangements | 2017-07-27 | 2018-06-29 | 235 | 0 | 233 | 337 | 100% | 0.69733 | 1 | Completed
ER6243LT | W200 | RSSC.OC.A102 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Pre Job Brief | 2017-07-27 | 2017-07-27 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8670 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for Initial Fault Studies and Risk Estimation Report (HPB/HNB) | 2017-07-27 | 2017-07-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.OC.A105 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Prepare QA3 SDM Defuelling Strategy Optioneering Report (1st Phase) | 2017-07-28 | 2017-10-31 | 34 | 0 | 66 | 95 | 100% | 0.35789 | 1 | Completed
ER6244LT | W220 | A8680 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for Initial Fault Studies and Risk Estimation Report (HPB/HNB) | 2017-07-28 | 2017-07-31 | 2 | 0 | 2 | 3 | 100% | 0.66667 | 1 | Completed
ER6244LT | W220 | A8690 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2017-07-31 | 2017-07-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8700 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for Initial Fault Studies and Risk Estimation Report (HPB/HNB) | 2017-07-31 | 2017-07-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8710 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Initial Fault Studies and Risk Estimation Report (HPB/HNB) | 2017-07-31 | 2017-10-30 | 60 | 0 | 65 | 91 | 100% | 0.65934 | 1 | Completed
ER6244LT | W220 | A3460 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Update defueling options EAN to Rev 001 for defueling mode | 2017-08-01 | 2017-08-11 | 9 | 0 | 9 | 10 | 100% | 0.9 | 1 | Completed
ER6244LT | W220 | A4280 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.18 - Interlock Changes | 2017-08-01 | 2018-01-31 | 19 | 0 | 127 | 183 | 100% | 0.10383 | 1 | Completed
ER6244LT | W220 | A5880 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for Dropped FPU Impact on Buffer Store EAN (HPB and HNB) | 2017-08-01 | 2017-08-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A6010 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for Dropped FPU Impact on Buffer Store EAN (HYA and HRA) | 2017-08-01 | 2017-08-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A6790 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for Waste Vault Storage Capacity EAN (HPB and HNB) | 2017-08-01 | 2017-09-07 | 19 | 0 | 27 | 37 | 100% | 0.51351 | 1 | Completed
ER6244LT | W220 | A6920 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for Ponds and Flasks EAN (HYA and HRA) | 2017-08-01 | 2017-08-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A7050 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for Waste Vault Storage Capacity EAN (HYA and HRA) | 2017-08-01 | 2017-08-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A7200 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued for Impact of Empty Channels on Reactor Cooling EAN | 2017-08-01 | 2017-08-04 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6244LT | W220 | A7960 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for CRA Isolation Requirements EAN | 2017-08-01 | 2017-09-02 | 19 | 0 | 23 | 32 | 100% | 0.59375 | 1 | Completed
ER6244LT | W220 | A8910 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for Fuelling Machine Light Load Protection & Interlocks EAN (HPB/HNB) | 2017-08-01 | 2017-08-04 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6244LT | W220 | A9930 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for Fuelling Machine Light Load Protection & Interlocks EAN(HYA and HRA) | 2017-08-01 | 2017-08-04 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6244LT | W220 | A5830.EJ | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Dropped FPU impact on Reactor Internals Report (HYA and HRA) verified and issued for technical review | 2017-08-01 | 2017-08-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5840 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical review of Dropped FPU impact on Reactor Internals Report (HYA and HRA) | 2017-08-02 | 2017-09-08 | 42 | 0 | 27 | 37 | 100% | 1.1351 | 1 | Completed
ER6244LT | W220 | A6540 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for IFDF Defueling EAN (HYA and HRA) | 2017-08-02 | 2017-08-03 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6244LT | W220 | A6930 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for Ponds and Flasks EAN (HYA and HRA) | 2017-08-02 | 2017-08-03 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6244LT | W220 | A7060 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for Waste Vault Storage Capacity EAN (HYA and HRA) | 2017-08-02 | 2017-08-03 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6244LT | W220 | A7320 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for Minimum Forced Gas Circulation Requirements EAN | 2017-08-02 | 2017-08-03 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6244LT | W220 | A7450 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for Assessment of Temperatures vs Decay Heat for Natural Circulation EAN | 2017-08-02 | 2017-08-03 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6244LT | W220 | A7840 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for Review Radial Shuffling Safety Case EAN (HYA and HRA) | 2017-08-02 | 2017-08-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A7850 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued for Review Radial Shuffling Safety Case EAN (HYA and HRA) | 2017-08-03 | 2017-08-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6550 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued by supplier for IFDF Defueling EAN (HYA and HRA) | 2017-08-04 | 2017-08-04 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6940 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued by supplier for Ponds and Flasks EAN (HYA and HRA) | 2017-08-04 | 2017-08-04 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A7070 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued by supplier for Waste Vault Storage Capacity EAN (HYA and HRA) | 2017-08-04 | 2017-08-04 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A7330 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued for Minimum Forced Gas Circulation Requirements EAN | 2017-08-04 | 2017-08-04 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A7460 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued for Assessment of Temperatures vs Decay Heat for Natural Circulation EAN | 2017-08-04 | 2017-08-04 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A7860 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for Review Radial Shuffling Safety Case EAN (HYA and HRA) | 2017-08-04 | 2017-08-04 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8780 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for Fuel Free Verification EAN | 2017-08-04 | 2017-08-07 | 2 | 0 | 2 | 3 | 100% | 0.66667 | 1 | Completed
ER6244LT | W220 | A9550 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for Fuel Free Verification EAN | 2017-08-04 | 2017-08-07 | 2 | 0 | 2 | 3 | 100% | 0.66667 | 1 | Completed
ER6244LT | W220 | A9680 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for Fuel Free Verification EAN | 2017-08-04 | 2017-08-07 | 2 | 0 | 2 | 3 | 100% | 0.66667 | 1 | Completed
ER6244LT | W220 | A9810 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for Fuel Free Verification EAN | 2017-08-04 | 2017-08-07 | 2 | 0 | 2 | 3 | 100% | 0.66667 | 1 | Completed
ER6243LT | W200 | RSSC.OC.A170 | REGION 1 Reactors Shutdown Safety Cases Programme | Principles of Fuel Free Verification - RFS Review Before it is Issued to Supplier (HPB, HNB) | 2017-08-07 | 2017-08-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.OC.A500 | REGION 1 Reactors Shutdown Safety Cases Programme | Principles of Fuel Free Verification - RFS Review Before it is Issued to Supplier (HYA, HAR) | 2017-08-07 | 2017-08-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6560 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for IFDF Defueling EAN (HYA and HRA) | 2017-08-07 | 2017-08-11 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6244LT | W220 | A6950 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for Ponds and Flasks EAN (HYA and HRA) | 2017-08-07 | 2017-08-11 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6244LT | W220 | A7080 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for Waste Vault Storage Capacity EAN (HYA and HRA) | 2017-08-07 | 2017-08-11 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6244LT | W220 | A7210 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for Impact of Empty Channels on Reactor Cooling EAN | 2017-08-07 | 2017-08-11 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6244LT | W220 | A7340 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for Minimum Forced Gas Circulation Requirements EAN | 2017-08-07 | 2017-08-11 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6244LT | W220 | A7470 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for Assessment of Temperatures vs Decay Heat for Natural Circulation EAN | 2017-08-07 | 2017-08-11 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6244LT | W220 | A7870 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for Review Radial Shuffling Safety Case EAN (HYA and HRA) | 2017-08-07 | 2017-08-07 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8920 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for Fuelling Machine Light Load Protection & Interlocks EAN (HPB/HNB) | 2017-08-07 | 2017-08-11 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6244LT | W220 | A9940 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for Fuelling Machine Light Load Protection & Interlocks EAN (HYA and HRA) | 2017-08-07 | 2017-08-11 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6244LT | W220 | A5890 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for Dropped FPU Impact on Buffer Store EAN (HPB and HNB) | 2017-08-08 | 2017-08-14 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A6020 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for Dropped FPU Impact on Buffer Store EAN (HYA and HRA) | 2017-08-08 | 2017-08-14 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A7880 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation (HYA and HRA) | 2017-08-08 | 2017-08-08 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8790 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued for Fuel Free Verification EAN | 2017-08-08 | 2017-08-25 | 14 | 0 | 14 | 17 | 100% | 0.82353 | 1 | Completed
ER6244LT | W220 | A9560 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued for Fuel Free Verification EAN | 2017-08-08 | 2017-08-25 | 14 | 0 | 14 | 17 | 100% | 0.82353 | 1 | Completed
ER6244LT | W220 | A9690 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued for Fuel Free Verification EAN | 2017-08-08 | 2017-08-25 | 14 | 0 | 14 | 17 | 100% | 0.82353 | 1 | Completed
ER6244LT | W220 | A9820 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued for Fuel Free Verification EAN | 2017-08-08 | 2017-08-25 | 14 | 0 | 14 | 17 | 100% | 0.82353 | 1 | Completed
ER6244LT | W220 | A7890 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for Review Radial Shuffling Safety Case EAN (HYA and HRA) | 2017-08-09 | 2017-08-09 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A3580 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Defueling Options EAN Available for Verification | 2017-08-11 | 2017-08-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6570 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for IFDF Defueling EAN (HYA and HRA) | 2017-08-14 | 2017-08-15 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6244LT | W220 | A6960 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for Ponds and Flasks EAN (HYA and HRA) | 2017-08-14 | 2017-08-15 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6244LT | W220 | A7090 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for Waste Vault Storage Capacity EAN (HYA and HRA) | 2017-08-14 | 2017-08-15 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6244LT | W220 | A7220 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for Impact of Empty Channels on Reactor Cooling EAN | 2017-08-14 | 2017-08-15 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6244LT | W220 | A3590 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Verification Review of Defueling Options EAN | 2017-08-14 | 2018-02-01 | 10 | 0 | 119 | 171 | 100% | 0.05848 | 1 | Completed
ER6244LT | W220 | A8930 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued by supplier for Fuelling Machine Light Load Protection & Interlocks EAN (HPB/HNB) | 2017-08-14 | 2017-08-18 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6244LT | W220 | A9950 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued by supplier for Fuelling Machine Light Load Protection & Interlocks EAN (HYA and HRA) | 2017-08-14 | 2017-08-18 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6244LT | W220 | A5900 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued by supplier for Dropped FPU Impact on Buffer Store EAN (HPB and HNB) | 2017-08-15 | 2017-08-21 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A6030 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued by supplier for Dropped FPU Impact on Buffer Store EAN (HYA and HRA) | 2017-08-15 | 2017-08-21 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A6580 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2017-08-16 | 2017-08-16 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6970 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2017-08-16 | 2017-08-16 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A7100 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2017-08-16 | 2017-08-16 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A7230 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2017-08-16 | 2017-08-16 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5740.EJ | REGION 1 Defuelling Programme Fuel Handling Safety Case | Dropped FPU impact on Reactor Internals and Standpipe Breach EAN (HPB and HNB) available | 2017-08-16 | 2017-08-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6590 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for IFDF Defueling EAN (HYA and HRA) | 2017-08-17 | 2017-08-17 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6600 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft IFDF Defueling EAN (HYA and HRA) | 2017-08-17 | 2018-05-14 | 16 | 0 | 186 | 270 | 100% | 0.059259 | 1 | Completed
ER6244LT | W220 | A6980 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for Ponds and Flasks EAN (HYA and HRA) | 2017-08-17 | 2017-08-17 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6990 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Ponds and Flasks EAN (HYA and HRA) | 2017-08-17 | 2018-05-14 | 16 | 0 | 186 | 270 | 100% | 0.059259 | 1 | Completed
ER6244LT | W220 | A7110 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for Waste Vault Storage Capacity EAN (HYA and HRA) | 2017-08-17 | 2017-08-17 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A7120 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Waste Vault Storage Capacity EAN (HYA and HRA) | 2017-08-17 | 2018-05-14 | 16 | 0 | 186 | 270 | 100% | 0.059259 | 1 | Completed
ER6244LT | W220 | A7240 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for Impact of Empty Channels on Reactor Cooling EAN | 2017-08-17 | 2017-08-17 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A10480 | REGION 1 Reactors Shutdown Safety Cases Programme | P.10.01.10 - Defuelling Shutdown Safety Cases - Fault Studies | 2017-08-21 | 2018-01-31 | 61 | 0 | 113 | 163 | 100% | 0.37423 | 1 | Completed
ER6243LT | W200 | A10530 | REGION 1 Reactors Shutdown Safety Cases Programme | P.10.01.23 - Defuelling Shutdown Safety Cases - Maintenance | 2017-08-21 | 2017-12-29 | 0 | 0 | 91 | 130 | 100% | 0 | 1 | Completed
ER6243LT | W200 | A13580 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - RFS Summary Credible Hazards and Faults | 2017-08-21 | 2017-09-29 | 28 | 0 | 28 | 39 | 100% | 0.71795 | 1 | Completed
ER6243LT | W200 | A13590 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Prepare Request for Service (RFS) Specification | 2017-08-21 | 2017-08-25 | 2 | 0 | 4 | 4 | 100% | 0.5 | 1 | Completed
ER6243LT | W200 | A14870 | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - RFS Summary - Summary of TS Charges Required | 2017-08-21 | 2017-10-12 | 50 | 0 | 37 | 52 | 100% | 0.96154 | 1 | Completed
ER6243LT | W200 | A14880 | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - Prepare Request for Service (RFS) Specification | 2017-08-21 | 2017-08-22 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6243LT | W200 | A16710 | REGION 1 Reactors Shutdown Safety Cases Programme | Fault Studies Summary | 2017-08-21 | 2018-07-13 | 236 | 0 | 226 | 326 | 100% | 0.72393 | 1 | Completed
ER6244LT | W220 | A8940 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for Fuelling Machine Light Load Protection & Interlocks EAN (HPB/HNB) | 2017-08-21 | 2017-08-22 | 24 | 0 | 1 | 1 | 100% | 24 | 1 | Completed
ER6244LT | W220 | A9960 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for Fuelling Machine Light Load Protection & Interlocks EAN (HYA and HRA) | 2017-08-21 | 2017-08-22 | 24 | 0 | 1 | 1 | 100% | 24 | 1 | Completed
ER6244LT | W220 | A5910 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for Dropped FPU Impact on Buffer Store EAN (HPB and HNB) | 2017-08-22 | 2017-08-29 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6244LT | W220 | A6040 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for Dropped FPU Impact on Buffer Store EAN (HYA and HRA) | 2017-08-22 | 2017-08-29 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6243LT | W200 | A14890 | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - Review, Approve and Issue RFS to Supplier | 2017-08-23 | 2017-08-23 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15000 | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - Request for Service (RFS) Specification Issued | 2017-08-23 | 2017-08-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8950 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for Fuelling Machine Light Load Protection & Interlocks EAN (HPB/HNB) | 2017-08-23 | 2017-09-04 | 12 | 0 | 8 | 12 | 100% | 1 | 1 | Completed
ER6244LT | W220 | A9970 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for Fuelling Machine Light Load Protection & Interlocks EAN (HYA and HRA) | 2017-08-23 | 2017-09-04 | 12 | 0 | 8 | 12 | 100% | 1 | 1 | Completed
ER6243LT | W200 | A13170.EI | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Initial Offer Issued for Review | 2017-08-24 | 2017-08-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14900 | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - Prepare and Issue Offer | 2017-08-24 | 2017-08-25 | 5 | 0 | 1 | 1 | 100% | 5 | 1 | Completed
ER6243LT | W200 | A15010 | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - Initial Offer Issued for Review | 2017-08-25 | 2017-08-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A10880 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Review and Negotiate Offer | 2017-08-25 | 2017-08-31 | 4 | 0 | 4 | 6 | 100% | 0.66667 | 1 | Completed
ER6243LT | W200 | A13600 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Review, Approve and Issue RFS to Supplier | 2017-08-28 | 2017-08-29 | 1 | 0 | 1 | 1 | 100% | 1 | 1 | Completed
ER6243LT | W200 | A14910 | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - Review and Negotiate Offer | 2017-08-28 | 2017-09-08 | 5 | 0 | 8 | 11 | 100% | 0.45455 | 1 | Completed
ER6243LT | W200 | A13610 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Prepare and Issue Offer | 2017-08-29 | 2017-09-08 | 5 | 0 | 8 | 10 | 100% | 0.5 | 1 | Completed
ER6243LT | W200 | A13650 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Request for Service (RFS) Specification Issued | 2017-08-29 | 2017-08-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8800 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for Fuel Free Verification EAN | 2017-08-29 | 2017-09-04 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A9570 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for Fuel Free Verification EAN | 2017-08-29 | 2017-09-04 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A9700 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for Fuel Free Verification EAN | 2017-08-29 | 2017-09-04 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A9830 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for Fuel Free Verification EAN | 2017-08-29 | 2017-09-04 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A1080 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Produce draft NSRS for HPB and HNB (using BARRIER MODEL) | 2017-08-31 | 2018-10-19 | 135 | 0 | 289 | 414 | 100% | 0.32609 | 1 | Completed
ER6243LT | W200 | A11170 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - RFS Summary - Rad Con's Requirements for Post NSRS | 2017-09-01 | 2017-09-19 | 7 | 0 | 12 | 18 | 100% | 0.38889 | 1 | Completed
ER6243LT | W200 | A11180 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Prepare Request for Service (RFS) Specification | 2017-09-01 | 2017-09-04 | 2 | 0 | 1 | 3 | 100% | 0.66667 | 1 | Completed
ER6243LT | W200 | A11400 | REGION 1 Reactors Shutdown Safety Cases Programme | Assessm't of Other Faults - RFS Summary | 2017-09-01 | 2017-09-21 | 12 | 0 | 14 | 20 | 100% | 0.6 | 1 | Completed
ER6243LT | W200 | A11410 | REGION 1 Reactors Shutdown Safety Cases Programme | Assessm't of Other Faults - Prepare Request for Service (RFS) Specification | 2017-09-01 | 2017-09-05 | 2 | 0 | 2 | 4 | 100% | 0.5 | 1 | Completed
ER6243LT | W200 | A11405 | REGION 1 Reactors Shutdown Safety Cases Programme | Assessm't of Other Faults - Start Specifying the Work | 2017-09-01 | 2017-09-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15720 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Review NSP's for Shutdown Cooling Safety Cases (HPB, HNB) | 2017-09-01 | 2017-09-18 | 20 | 0 | 11 | 17 | 100% | 1.1765 | 1 | Completed
ER6243LT | W200 | A15780 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Review NSP's for Shutdown Cooling Safety Cases (HYA, HAR) | 2017-09-01 | 2017-09-18 | 20 | 0 | 11 | 17 | 100% | 1.1765 | 1 | Completed
ER6244LT | W220 | A9280 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for Fuel Storage Conditions EAN | 2017-09-01 | 2017-09-29 | 1 | 0 | 20 | 28 | 100% | 0.035714 | 1 | Completed
ER6243LT | W200 | A10890 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Complete Requisition Approval and Issue CI | 2017-09-01 | 2017-09-22 | 2 | 0 | 15 | 21 | 100% | 0.095238 | 1 | Completed
ER6244LT | W220 | A5250 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued for Refuelling Cooling Assessment EAN | 2017-09-01 | 2017-09-04 | 2 | 0 | 2 | 3 | 100% | 0.66667 | 1 | Completed
ER6244LT | W220 | A5920 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for Dropped FPU Impact on Buffer Store EAN (HPB and HNB) | 2017-09-01 | 2017-09-05 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6244LT | W220 | A6050 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for Dropped FPU Impact on Buffer Store EAN (HYA and HRA) | 2017-09-01 | 2017-09-05 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6243LT | W200 | A10885 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Offer Accepted/Approved | 2017-09-01 | 2017-09-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A9030 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Prepare RFS/Spec for Fuel Storage Conditions EAN | 2017-09-01 | 2017-09-29 | 21 | 0 | 21 | 28 | 100% | 0.75 | 1 | Completed
ER6243LT | W200 | A15180 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Linking BAT/BPM into optioneering Specification (HPB, HNB) | 2017-09-01 | 2017-09-15 | 11 | 0 | 10 | 14 | 100% | 0.78571 | 1 | Completed
ER6243LT | W200 | A15420 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Linking BAT/BPM into optioneering Specification (HYA, HAR) | 2017-09-01 | 2017-09-15 | 11 | 0 | 10 | 14 | 100% | 0.78571 | 1 | Completed
ER6243LT | W200 | A14540 | REGION 1 Reactors Shutdown Safety Cases Programme | Principles of Fuel Free Verification - Review of Offer before Req is approved & CI Issued (HPB, HNB) | 2017-09-04 | 2017-09-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14560 | REGION 1 Reactors Shutdown Safety Cases Programme | Principles of Fuel Free Verification - Review of Offer before Req is approved & CI Issued (HYA, HAR) | 2017-09-04 | 2017-09-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A7970 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for CRA Isolation Requirements EAN | 2017-09-04 | 2017-09-08 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6243LT | W200 | A11190 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Review, Approve and Issue RFS to Supplier | 2017-09-05 | 2017-09-05 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11195 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Request for Service (RFS) Specification Issued | 2017-09-05 | 2017-09-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5260 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for Refuelling Cooling Assessment EAN | 2017-09-05 | 2017-09-06 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6244LT | W220 | A8810 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for Fuel Free Verification EAN | 2017-09-05 | 2017-09-11 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A8960 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2017-09-05 | 2017-09-11 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A9580 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for Fuel Free Verification EAN | 2017-09-05 | 2017-09-11 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A9710 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for Fuel Free Verification EAN | 2017-09-05 | 2017-09-11 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A9840 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for Fuel Free Verification EAN | 2017-09-05 | 2017-09-11 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A9980 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2017-09-05 | 2017-09-11 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6243LT | W200 | A11200 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Prepare and Issue Offer | 2017-09-06 | 2017-09-12 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6243LT | W200 | A11420 | REGION 1 Reactors Shutdown Safety Cases Programme | Assessm't of Other Faults - Review, Approve and Issue RFS to Supplier | 2017-09-06 | 2017-09-07 | 1 | 0 | 1 | 1 | 100% | 1 | 1 | Completed
ER6244LT | W220 | A5930 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2017-09-06 | 2017-09-06 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6060 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2017-09-06 | 2017-09-06 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.VI.A100 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Structural Integrity Calcs for the Impact of Hanging the Plug Unit from the Pilecap (HPB, HNB) | 2017-09-07 | 2019-03-19 | 398 | 0 | 387 | 558 | 100% | 0.71326 | 1 | Completed
ER6243LT | W200 | RSSC.VI.A105 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Pre Job Brief (HPB, HNB) | 2017-09-07 | 2017-09-07 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11425 | REGION 1 Reactors Shutdown Safety Cases Programme | Assessm't of Other Faults - Request for Service (RFS) Specification Issued | 2017-09-07 | 2017-09-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5270 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for Refuelling Cooling Assessment EAN | 2017-09-07 | 2017-09-07 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5940 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for Dropped FPU Impact on Buffer Store EAN (HPB and HNB) | 2017-09-07 | 2017-09-07 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5950 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Dropped FPU Impact on Buffer Store EAN (HPB and HNB) | 2017-09-07 | 2018-01-05 | 45 | 0 | 84 | 120 | 100% | 0.375 | 1 | Completed
ER6244LT | W220 | A6070 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for Dropped FPU Impact on Buffer Store EAN (HYA and HRA) | 2017-09-07 | 2017-09-07 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6080 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Dropped FPU Impact on Buffer Store EAN (HYA and HRA) | 2017-09-07 | 2018-01-05 | 45 | 0 | 84 | 120 | 100% | 0.375 | 1 | Completed
ER6244LT | W220 | A8290 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2017-09-07 | 2017-09-11 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6244LT | W220 | A8420 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2017-09-07 | 2017-09-11 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6243LT | W200 | RSSC.VI.A160 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Structural Integrity Calcs for the Impact of Hanging the Plug Unit from the Pilecap (HYA, HAR) | 2017-09-08 | 2019-03-19 | 397 | 0 | 386 | 557 | 100% | 0.71275 | 1 | Completed
ER6243LT | W200 | A10900 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Supplier Mobilisation Time | 2017-09-08 | 2017-09-11 | 10 | 0 | 1 | 3 | 100% | 3.3333 | 1 | Completed
ER6243LT | W200 | RSSC.VI.A106 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Prepare Basis of Design Report (Phase 1) for Structural Integrity of PCPV (HPB, HNB) | 2017-09-08 | 2017-10-31 | 111 | 0 | 37 | 53 | 100% | 2.0943 | 1 | Completed
ER6243LT | W200 | RSSC.VI.A165 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Prepare Basis of Design Report (Phase 1) for Structural Integrity of PCPV (HYA, HAR) | 2017-09-08 | 2017-10-31 | 111 | 0 | 37 | 53 | 100% | 2.0943 | 1 | Completed
ER6243LT | W200 | A11100 | REGION 1 Reactors Shutdown Safety Cases Programme | Closure and Seal Integrity - RFS review before it is issued to Supplier (HPB, HNB) | 2017-09-08 | 2017-09-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11140 | REGION 1 Reactors Shutdown Safety Cases Programme | Closure and Seal Integrity - RFS review before it is issued to Supplier (HYA, HAR) | 2017-09-08 | 2017-09-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11430 | REGION 1 Reactors Shutdown Safety Cases Programme | Assessm't of Other Faults - Prepare and Issue Offer | 2017-09-12 | 2017-09-12 | 5 | 0 | 2 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A13660 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Initial Offer Issued for Review | 2017-09-08 | 2017-09-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15020 | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - Offer Accepted/Approved | 2017-09-08 | 2017-09-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5280 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2017-09-08 | 2017-09-08 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6150 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for Buffer Store Defueling EAN (HPB and HNB) | 2017-09-08 | 2017-09-14 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A6280 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for IFDF Defueling EAN (HPB and HNB) | 2017-09-08 | 2017-09-14 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A6670 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for Ponds and Flasks EAN (HPB and HNB) | 2017-09-08 | 2017-09-14 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A6800 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for Waste Vault Storage Capacity EAN (HPB and HNB) | 2017-09-08 | 2017-09-13 | 4 | 0 | 4 | 5 | 100% | 0.8 | 1 | Completed
ER6243LT | W200 | A13620 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Review and Negotiate Offer | 2017-09-11 | 2017-09-11 | 5 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A13670 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Offer Accepted/Approved | 2017-09-11 | 2017-09-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14920 | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - Complete Requisition Approval and Issue CI | 2017-09-11 | 2017-09-29 | 1 | 0 | 14 | 18 | 100% | 0.055556 | 1 | Completed
ER6244LT | W220 | A5290 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for Refuelling Cooling Assessment EAN | 2017-09-11 | 2017-09-11 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5300 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Refuelling Cooling Assessment EAN | 2017-09-11 | 2018-02-23 | 15 | 0 | 116 | 165 | 100% | 0.090909 | 1 | Completed
ER6244LT | W220 | A5850 | REGION 1 Defuelling Programme Fuel Handling Safety Case | FNC update and issue Dropped FPU impact on Reactor Internals Report (HYA and HRA) | 2017-09-11 | 2017-09-15 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6244LT | W220 | A7980 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued for CRA Isolation Requirements EAN | 2017-09-11 | 2017-09-15 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6243LT | W200 | A11205 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Initial Offer Issued for Review | 2017-09-12 | 2017-09-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11435 | REGION 1 Reactors Shutdown Safety Cases Programme | Assessm't of Other Faults - Initial Offer Issued for Review | 2017-09-12 | 2017-09-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A13630 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Complete Requisition Approval and Issue CI | 2017-09-12 | 2017-09-25 | 1 | 0 | 9 | 13 | 100% | 0.076923 | 1 | Completed
ER6244LT | W220 | A8300 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 2017-09-12 | 2017-09-12 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8820 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2017-09-12 | 2017-09-21 | 8 | 0 | 8 | 9 | 100% | 0.88889 | 1 | Completed
ER6244LT | W220 | A8970 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for Fuelling Machine Light Load Protection & Interlocks EAN (HPB/HNB) | 2017-09-12 | 2017-09-12 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8980 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Fuelling Machine Light Load Protection & Interlocks EAN (HYA and HRA) | 2017-09-12 | 2018-02-22 | 49 | 0 | 115 | 163 | 100% | 0.30061 | 1 | Completed
ER6244LT | W220 | A9590 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2017-09-12 | 2017-09-21 | 8 | 0 | 8 | 9 | 100% | 0.88889 | 1 | Completed
ER6244LT | W220 | A9720 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2017-09-12 | 2017-09-21 | 8 | 0 | 8 | 9 | 100% | 0.88889 | 1 | Completed
ER6244LT | W220 | A9850 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2017-09-12 | 2017-09-21 | 8 | 0 | 8 | 9 | 100% | 0.88889 | 1 | Completed
ER6244LT | W220 | A9990 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for Fuelling Machine Light Load Protection & Interlocks EAN (HYA and HRA) | 2017-09-12 | 2017-09-12 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A10000 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Fuelling Machine Light Load Protection & Interlocks EAN (HYA/HRA) | 2017-09-12 | 2018-08-01 | 49 | 0 | 225 | 323 | 100% | 0.1517 | 1 | Completed
ER6243LT | W200 | A11210 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Review and Negotiate Offer | 2017-09-13 | 2017-09-15 | 5 | 0 | 2 | 2 | 100% | 2.5 | 1 | Completed
ER6243LT | W200 | A11440 | REGION 1 Reactors Shutdown Safety Cases Programme | Assessm't of Other Faults - Review and Negotiate Offer | 2017-09-13 | 2017-09-15 | 5 | 0 | 2 | 2 | 100% | 2.5 | 1 | Completed
ER6244LT | W220 | A8310 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 2017-09-13 | 2018-01-12 | 85 | 0 | 84 | 121 | 100% | 0.70248 | 1 | Completed
ER6244LT | W220 | A8430 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 2017-09-13 | 2017-09-13 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8440 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 2017-09-13 | 2018-01-12 | 85 | 0 | 84 | 121 | 100% | 0.70248 | 1 | Completed
ER6244LT | W220 | A6810 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued by supplier for Waste Vault Storage Capacity EAN (HPB and HNB) | 2017-09-14 | 2017-09-25 | 8 | 0 | 8 | 11 | 100% | 0.72727 | 1 | Completed
ER6243LT | W200 | A11215 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Offer Accepted/Approved | 2017-09-15 | 2017-09-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11445 | REGION 1 Reactors Shutdown Safety Cases Programme | Assessm't of Other Faults - Offer Accepted/Approved | 2017-09-15 | 2017-09-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15190 | REGION 1 Reactors Shutdown Safety Cases Programme | Linking BAT/BPM into optioneering Specification Agreed (HPB, HNB) | 2017-09-15 | 2017-09-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15430 | REGION 1 Reactors Shutdown Safety Cases Programme | Linking BAT/BPM into optioneering Specification Agreed (HYA, HAR) | 2017-09-15 | 2017-09-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6160 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued by supplier for Buffer Store Defueling EAN (HPB and HNB) | 2017-09-15 | 2017-09-25 | 7 | 0 | 7 | 10 | 100% | 0.7 | 1 | Completed
ER6244LT | W220 | A6290 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued by supplier for IFDF Defueling EAN (HPB and HNB) | 2017-09-15 | 2017-09-25 | 7 | 0 | 7 | 10 | 100% | 0.7 | 1 | Completed
ER6244LT | W220 | A6680 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued by supplier for Ponds and Flasks EAN (HPB and HNB) | 2017-09-15 | 2017-09-25 | 7 | 0 | 7 | 10 | 100% | 0.7 | 1 | Completed
ER6243LT | W200 | A11220 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Complete Requisition Approval and Issue CI | 2017-09-18 | 2017-09-19 | 1 | 0 | 1 | 1 | 100% | 1 | 1 | Completed
ER6243LT | W200 | A11450 | REGION 1 Reactors Shutdown Safety Cases Programme | Assessm't of Other Faults - Complete Requisition Approval and Issue CI | 2017-09-18 | 2017-09-19 | 1 | 0 | 1 | 1 | 100% | 1 | 1 | Completed
ER6243LT | W200 | A15200 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Linking BAT/BPM into optioneering Report (HPB, HNB) | 2017-09-18 | 2017-09-22 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6243LT | W200 | A15440 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Linking BAT/BPM into optioneering Report (HYA, HAR) | 2017-09-18 | 2017-09-22 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6243LT | W200 | A15730 | REGION 1 Reactors Shutdown Safety Cases Programme | Review NSP's for Shutdown Cooling Safety Cases Agreed (HPB, HNB) | 2017-09-18 | 2017-09-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15790 | REGION 1 Reactors Shutdown Safety Cases Programme | Review NSP's for Shutdown Cooling Safety Cases Agreed (HYA, HAR) | 2017-09-18 | 2017-09-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5860 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload Dropped FPU impact on Reactor Internals Report (HYA and HRA) to CDMS | 2017-09-18 | 2017-09-22 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6244LT | W220 | A7990 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for CRA Isolation Requirements EAN | 2017-09-18 | 2017-09-22 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6243LT | W200 | A11230 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Supplier Mobilisation Time | 2017-09-19 | 2017-09-19 | 7 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15740 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Review NSP's for Shutdown Cooling Safety Cases Report (HPB, HNB) | 2017-09-19 | 2017-10-31 | 40 | 0 | 30 | 42 | 100% | 0.95238 | 1 | Completed
ER6243LT | W200 | A15800 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Review NSP's for Shutdown Cooling Safety Cases Report (HYA, HAR) | 2017-09-19 | 2017-10-31 | 40 | 0 | 30 | 42 | 100% | 0.95238 | 1 | Completed
ER6243LT | W200 | A11460 | REGION 1 Reactors Shutdown Safety Cases Programme | Assessm't of Other Faults - Supplier Mobilisation Time | 2017-09-20 | 2017-09-21 | 12 | 0 | 1 | 1 | 100% | 12 | 1 | Completed
ER6243LT | W200 | RSSC.FS.A120 | REGION 1 Reactors Shutdown Safety Cases Programme | Review of assumptions and revision of fault schedules for reactor defuelling (HPB, HNB) | 2017-09-22 | 2018-07-13 | 221 | 0 | 203 | 294 | 100% | 0.7517 | 1 | Completed
ER6243LT | W200 | A15120 | REGION 1 Reactors Shutdown Safety Cases Programme | Assessm't of Other Faults - Pre Job Brief (HPB, HNB) | 2017-09-22 | 2017-09-22 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15210 | REGION 1 Reactors Shutdown Safety Cases Programme | Draft Linking BAT/BPM into optioneering Report Available for Review (HPB, HNB) | 2017-09-22 | 2017-09-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15450 | REGION 1 Reactors Shutdown Safety Cases Programme | Draft Linking BAT/BPM into optioneering Report Available for Review (HYA, HAR) | 2017-09-22 | 2017-09-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8830 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for Fuel Free Verification EAN | 2017-09-22 | 2017-09-22 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A9600 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for Fuel Free Verification EAN | 2017-09-22 | 2017-09-22 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A9730 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for Fuel Free Verification EAN | 2017-09-22 | 2017-09-22 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A9860 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for Fuel Free Verification EAN | 2017-09-22 | 2017-09-22 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5870.EJ | REGION 1 Defuelling Programme Fuel Handling Safety Case | Dropped FPU impact on Reactor Internals Rerport (HYA and HRA) available | 2017-09-22 | 2017-09-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.FS.A190 | REGION 1 Reactors Shutdown Safety Cases Programme | Review of assumptions and revision of fault schedules for reactor defuelling (HYA, HAR) | 2017-09-25 | 2018-07-13 | 220 | 0 | 202 | 291 | 100% | 0.75601 | 1 | Completed
ER6243LT | W200 | RSSC.FS.A340 | REGION 1 Reactors Shutdown Safety Cases Programme | Assessm't of Other Faults - Prepare Fault Studies Report (HPB, HNB) | 2017-09-25 | 2017-12-22 | 30 | 0 | 65 | 88 | 100% | 0.34091 | 1 | Completed
ER6243LT | W200 | RSSC.FS.A380 | REGION 1 Reactors Shutdown Safety Cases Programme | Assessm't of Other Faults - Prepare Fault Studies Report (HYA, HAR) | 2017-09-25 | 2017-12-08 | 30 | 0 | 55 | 74 | 100% | 0.40541 | 1 | Completed
ER6243LT | W200 | A13640 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Supplier Mobilisation Time | 2017-09-25 | 2017-09-29 | 7 | 0 | 4 | 4 | 100% | 1.75 | 1 | Completed
ER6243LT | W200 | A15220 | REGION 1 Reactors Shutdown Safety Cases Programme | Review & Acceptance of Linking BAT/BPM into optioneering Report (HPB, HNB) | 2017-09-25 | 2017-12-13 | 36 | 0 | 57 | 79 | 100% | 0.4557 | 1 | Completed
ER6243LT | W200 | A15460 | REGION 1 Reactors Shutdown Safety Cases Programme | Review & Acceptance of Linking BAT/BPM into optioneering Report (HYA, HAR) | 2017-09-25 | 2017-12-13 | 58 | 0 | 57 | 79 | 100% | 0.73418 | 1 | Completed
ER6244LT | W220 | A8000 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for CRA Isolation Requirements EAN | 2017-09-25 | 2017-09-29 | 4 | 0 | 4 | 4 | 100% | 1 | 1 | Completed
ER6244LT | W220 | A8840 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Fuel Free Verification EAN | 2017-09-25 | 2018-02-23 | 68 | 0 | 106 | 151 | 100% | 0.45033 | 1 | Completed
ER6244LT | W220 | A5870.EJ10 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Dropped FPU Impact on Reactor Internals Report upreved (HYA and HRA) | 2017-09-25 | 2017-12-22 | 21 | 0 | 64 | 88 | 100% | 0.23864 | 1 | Completed
ER6244LT | W220 | A9610 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Fuel Free Verification EAN | 2017-09-25 | 2018-07-09 | 68 | 0 | 199 | 287 | 100% | 0.23693 | 1 | Completed
ER6244LT | W220 | A9740 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Fuel Free Verification EAN | 2017-09-25 | 2018-09-27 | 68 | 0 | 256 | 367 | 100% | 0.18529 | 1 | Completed
ER6244LT | W220 | A9870 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Fuel Free Verification EAN | 2017-09-25 | 2018-05-04 | 68 | 0 | 155 | 221 | 100% | 0.30769 | 1 | Completed
ER6243LT | W200 | A11750 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Review, Approve and Issue RFS to Supplier | 2017-09-26 | 2017-09-26 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11760 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Prepare and Issue Offer | 2017-09-26 | 2017-10-11 | 5 | 0 | 11 | 15 | 100% | 0.33333 | 1 | Completed
ER6243LT | W200 | A11755 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Request for Service (RFS) Specification Issued | 2017-09-26 | 2017-09-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6170 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for Buffer Store Defueling EAN (HPB and HNB) | 2017-09-26 | 2017-10-03 | 6 | 0 | 6 | 7 | 100% | 0.85714 | 1 | Completed
ER6244LT | W220 | A6300 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for IFDF Defueling EAN (HPB and HNB) | 2017-09-26 | 2017-10-03 | 6 | 0 | 6 | 7 | 100% | 0.85714 | 1 | Completed
ER6244LT | W220 | A6690 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for Ponds and Flasks EAN (HPB and HNB) | 2017-09-26 | 2017-10-03 | 6 | 0 | 6 | 7 | 100% | 0.85714 | 1 | Completed
ER6244LT | W220 | A6820 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for Waste Vault Storage Capacity EAN (HPB and HNB) | 2017-09-26 | 2017-10-03 | 6 | 0 | 6 | 7 | 100% | 0.85714 | 1 | Completed
ER6243LT | W200 | A11110 | REGION 1 Reactors Shutdown Safety Cases Programme | Closure and Seal Integrity - Review of Offer before the Req is approved and CI issued (HPB, HNB) | 2017-09-29 | 2017-09-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11150 | REGION 1 Reactors Shutdown Safety Cases Programme | Closure and Seal Integrity - Review of Offer before the Req is approved and CI issued (HYA, HAR) | 2017-09-29 | 2017-09-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.FS.A170 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Credible Hazards and Faults Summary (HPB, HNB) | 2017-10-02 | 2018-06-29 | 193 | 0 | 187 | 270 | 100% | 0.71481 | 1 | Completed
ER6243LT | W200 | A14930 | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - Supplier Mobilisation Time | 2017-10-02 | 2017-10-12 | 7 | 0 | 8 | 10 | 100% | 0.7 | 1 | Completed
ER6243LT | W200 | A15110 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Pre Job Brief (HPB, HNB) | 2017-10-02 | 2017-10-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A9290 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for Fuel Storage Conditions EAN | 2017-10-02 | 2017-10-05 | 2 | 0 | 3 | 3 | 100% | 0.66667 | 1 | Completed
ER6244LT | W220 | A6310 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for IFDF Defueling EAN (HPB and HNB) | 2017-10-02 | 2017-10-27 | 20 | 0 | 20 | 25 | 100% | 0.8 | 1 | Completed
ER6244LT | W220 | A8010 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2017-10-02 | 2017-10-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A9040 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review, approve and issue RFS for Fuel Storage Conditions EAN | 2017-10-02 | 2017-10-05 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6243LT | W200 | RSSC.FS.A300 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Credible Hazards and Faults (HPB, HNB) | 2017-10-03 | 2017-11-21 | 20 | 0 | 35 | 49 | 100% | 0.40816 | 1 | Completed
ER6243LT | W200 | A13510 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Credible Hazards and Faults Summary (HYA, HAR) | 2017-10-03 | 2018-06-29 | 192 | 0 | 186 | 269 | 100% | 0.71375 | 1 | Completed
ER6243LT | W200 | A13570 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Credible Hazards and Faults (HYA, HAR) | 2017-10-03 | 2018-01-03 | 20 | 0 | 63 | 92 | 100% | 0.21739 | 1 | Completed
ER6244LT | W220 | A8020 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for CRA Isolation Requirements EAN | 2017-10-03 | 2017-10-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8030 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft CRA Isolation Requirements EAN | 2017-10-03 | 2018-02-28 | 47 | 0 | 103 | 148 | 100% | 0.31757 | 1 | Completed
ER6244LT | W220 | A6180 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for Buffer Store Defueling EAN (HPB and HNB) | 2017-10-04 | 2017-10-27 | 20 | 0 | 18 | 23 | 100% | 0.86957 | 1 | Completed
ER6244LT | W220 | A6700 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for Ponds and Flasks EAN (HPB and HNB) | 2017-10-04 | 2017-10-27 | 20 | 0 | 18 | 23 | 100% | 0.86957 | 1 | Completed
ER6244LT | W220 | A6830 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for Waste Vault Storage Capacity EAN (HPB and HNB) | 2017-10-04 | 2017-10-27 | 20 | 0 | 18 | 23 | 100% | 0.86957 | 1 | Completed
ER6244LT | W220 | A9300 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued by supplier for Fuel Storage Conditions EAN | 2017-10-06 | 2017-10-12 | 1 | 0 | 4 | 6 | 100% | 0.16667 | 1 | Completed
ER6244LT | W220 | A9050 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Offer prepared and issued by supplier for Fuel Storage Conditions EAN | 2017-10-06 | 2017-10-12 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6243LT | W200 | A11765 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Initial Offer issued for Review | 2017-10-11 | 2017-10-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11770 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Review and Negotiate Offer | 2017-10-12 | 2017-10-23 | 5 | 0 | 7 | 11 | 100% | 0.45455 | 1 | Completed
ER6243LT | W200 | A14850 | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - Summary of TS Charges Required (HPB, HNB) | 2017-10-13 | 2018-07-06 | 224 | 0 | 183 | 266 | 100% | 0.84211 | 1 | Completed
ER6243LT | W200 | A14940 | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - Pre Job Brief (HPB, HNB) | 2017-10-13 | 2017-10-13 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15030 | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - Summary of TS Charges Required (HYA, HAR) | 2017-10-13 | 2018-07-06 | 224 | 0 | 183 | 266 | 100% | 0.84211 | 1 | Completed
ER6243LT | W200 | A15050 | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - Pre Job Brief (HYA, HAR) | 2017-10-13 | 2017-10-13 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A9310 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for Fuel Storage Conditions EAN | 2017-10-13 | 2017-10-18 | 5 | 0 | 3 | 5 | 100% | 1 | 1 | Completed
ER6244LT | W220 | A9060 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review and negotiate offer for Fuel Storage Conditions EAN | 2017-10-13 | 2017-10-18 | 4 | 0 | 4 | 5 | 100% | 0.8 | 1 | Completed
ER6243LT | W200 | A14990 | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - Summary of TS Charges Required (HPB, HNB) | 2017-10-16 | 2018-02-16 | 35 | 0 | 86 | 123 | 100% | 0.28455 | 1 | Completed
ER6243LT | W200 | A15100 | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - Summary of TS Charges Required (HYA, HAR) | 2017-10-16 | 2018-02-16 | 35 | 0 | 86 | 123 | 100% | 0.28455 | 1 | Completed
ER6243LT | W200 | RSSC.FS.A100 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Rad Con's Requirements for Post NSRS (HPB, HNB) | 2017-10-19 | 2018-06-29 | 180 | 0 | 174 | 253 | 100% | 0.71146 | 1 | Completed
ER6243LT | W200 | RSSC.FS.A280 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Pre Job Brief (HPB, HNB) | 2017-10-19 | 2017-10-19 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A13430 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Rad Con's Requirements for Post NSRS (HYA, HAR) Summary | 2017-10-19 | 2018-06-29 | 185 | 0 | 174 | 253 | 100% | 0.73123 | 1 | Completed
ER6243LT | W200 | A13450 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Pre Job Brief (HYA, HAR) | 2017-10-19 | 2017-10-19 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A9320 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for Fuel Storage Conditions EAN | 2017-10-19 | 2017-11-27 | 2 | 0 | 27 | 39 | 100% | 0.051282 | 1 | Completed
ER6243LT | W200 | RSSC.FS.A290 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Rad Con's Requirements for Post NSRS (HPB, HNB) | 2017-10-20 | 2018-01-25 | 20 | 0 | 66 | 97 | 100% | 0.20619 | 1 | Completed
ER6243LT | W200 | A13500 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Rad Con's Requirements for Post NSRS (HYA, HAR) | 2017-10-20 | 2018-01-25 | 20 | 0 | 66 | 97 | 100% | 0.20619 | 1 | Completed
ER6243LT | W200 | A11775 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Offer Accepted/Approved | 2017-10-23 | 2017-10-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A1440 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Assess interlock changes required for staggered operation of reactors, defueling mode & FPUs back in reactor (HPB & HNB) | 2017-10-23 | 2018-02-14 | 80 | 0 | 80 | 114 | 100% | 0.70175 | 1 | Completed
ER6243LT | W200 | A11780 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Complete Requisition Approval and Issue CI | 2017-10-24 | 2017-11-10 | 1 | 0 | 13 | 17 | 100% | 0.058824 | 1 | Completed
ER6244LT | W220 | A6190 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2017-10-30 | 2017-10-30 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6320 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2017-10-30 | 2017-10-30 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6710 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2017-10-30 | 2017-10-30 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6840 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2017-10-30 | 2017-10-30 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8720 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Initial Fault Studies and Risk Estimation Report verified and issued for Verification (HPB/HNB) | 2017-10-30 | 2017-10-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15750 | REGION 1 Reactors Shutdown Safety Cases Programme | Draft Review NSP's for Shutdown Cooling Safety CasesReport Available for Review (HPB, HNB) | 2017-10-31 | 2017-10-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15810 | REGION 1 Reactors Shutdown Safety Cases Programme | Draft Review NSP's for Shutdown Cooling Safety CasesReport Available for Review (HYA, HAR) | 2017-10-31 | 2017-10-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6200 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for Buffer Store Defueling EAN (HPB and HNB) | 2017-10-31 | 2017-10-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6210 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Buffer Store Defueling EAN (HPB and HNB) | 2017-10-31 | 2018-03-26 | 86 | 0 | 102 | 146 | 100% | 0.58904 | 1 | Completed
ER6244LT | W220 | A6330 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for IFDF Defueling EAN (HPB and HNB) | 2017-10-31 | 2017-10-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6340 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft IFDF Defueling EAN (HPB and HNB) | 2017-10-31 | 2018-03-26 | 86 | 0 | 102 | 146 | 100% | 0.58904 | 1 | Completed
ER6244LT | W220 | A6720 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for Ponds and Flasks EAN (HPB and HNB) | 2017-10-31 | 2017-10-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6730 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Ponds and Flasks EAN (HPB and HNB) | 2017-10-31 | 2018-03-26 | 86 | 0 | 102 | 146 | 100% | 0.58904 | 1 | Completed
ER6244LT | W220 | A6850 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for Waste Vault Storage Capacity EAN (HPB and HNB) | 2017-10-31 | 2017-10-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6860 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Waste Vault Storage Capacity EAN (HPB and HNB) | 2017-10-31 | 2018-03-26 | 86 | 0 | 102 | 146 | 100% | 0.58904 | 1 | Completed
ER6244LT | W220 | A8730 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Verification of Initial Fault Studies and Risk Estimation Report (HPB/HNB) | 2017-10-31 | 2018-01-02 | 16 | 0 | 42 | 63 | 100% | 0.25397 | 1 | Completed
ER6244LT | W220 | A4200 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.15 - Pile Cap Equipment | 2017-11-01 | 2018-06-29 | 41 | 0 | 165 | 240 | 100% | 0.17083 | 1 | Completed
ER6244LT | W220 | A3640 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Guidance for batch size for defuelling during staggered operation | 2017-11-03 | 2017-11-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A10500 | REGION 1 Reactors Shutdown Safety Cases Programme | P.10.01.13 - Defuelling Shutdown Safety Cases - Reactor Control System | 2017-11-03 | 2017-12-29 | 0 | 0 | 38 | 56 | 100% | 0 | 1 | Completed
ER6243LT | W200 | A11790 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Supplier Mobilisation Time | 2017-11-13 | 2017-11-16 | 1 | 0 | 3 | 3 | 100% | 0.33333 | 1 | Completed
ER6243LT | W200 | A13130.EA | REGION 1 Reactors Shutdown Safety Cases Programme | Contract Variation approved for next phase | 2017-11-17 | 2017-11-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A13140 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Prepare QA3 SDM Defuelling Strategy Optioneering Report (2nd Phase) | 2017-11-17 | 2018-01-26 | 61 | 0 | 47 | 70 | 100% | 0.87143 | 1 | Completed
ER6243LT | W200 | A11280 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Credible Hazards and Faults verified and issued for Technical Review (HPB, HNB) | 2017-11-21 | 2017-11-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11290 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Credible Hazards and Faults Technical Review by SQEP (HPB, HNB) | 2017-11-21 | 2018-03-14 | 10 | 0 | 78 | 113 | 100% | 0.088496 | 1 | Completed
ER6243LT | W200 | A12140 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - RFS Summary - High Level Impact Assessment | 2017-11-21 | 2018-02-12 | 67 | 0 | 56 | 83 | 100% | 0.80723 | 1 | Completed
ER6243LT | W200 | A12150 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Prepare Request for Service (RFS) Specification | 2017-11-21 | 2017-12-12 | 5 | 0 | 15 | 21 | 100% | 0.2381 | 1 | Completed
ER6243LT | W200 | A12145 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Start Specifying the Work | 2017-11-21 | 2017-11-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15880 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - RFS Summary - Overall Delivery Plan | 2017-11-21 | 2018-02-12 | 50 | 0 | 56 | 83 | 100% | 0.60241 | 1 | Completed
ER6243LT | W200 | A15890 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Prepare Request for Service (RFS) Specification | 2017-11-21 | 2017-12-15 | 5 | 0 | 18 | 24 | 100% | 0.20833 | 1 | Completed
ER6243LT | W200 | A16090 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Start Specifying the Work | 2017-11-21 | 2017-11-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A9330 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2017-11-27 | 2017-11-27 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A9340 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for Fuel Storage Conditions EAN | 2017-11-27 | 2017-11-27 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A9350 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Fuel Storage Conditions EAN | 2017-11-27 | 2018-03-29 | 16 | 0 | 86 | 122 | 100% | 0.13115 | 1 | Completed
ER6243LT | W200 | A14620 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics - RFS Summary - PCPV Integrity for Changing Temperatures | 2017-12-01 | 2018-02-20 | 55 | 0 | 55 | 81 | 100% | 0.67901 | 1 | Completed
ER6243LT | W200 | A14630 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics - Prepare Request for Service (RFS) Specification | 2017-12-01 | 2017-12-13 | 9 | 0 | 9 | 12 | 100% | 0.75 | 1 | Completed
ER6243LT | W200 | A16370 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Contract Variation for next phase | 2017-12-01 | 2018-01-24 | 1 | 0 | 35 | 54 | 100% | 0.018519 | 1 | Completed
ER6243LT | W200 | WP365807.A1000 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Contract Variation for next phase | 2017-12-01 | 2018-01-24 | 1 | 0 | 35 | 54 | 100% | 0.018519 | 1 | Completed
ER6244LT | W220 | A7350 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for Minimum Forced Gas Circulation Requirements EAN | 2017-12-01 | 2017-12-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A7480 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for Assessment of Temperatures vs Decay Heat for Natural Circulation EAN | 2017-12-01 | 2017-12-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6243LT | W200 | A15760 | REGION 1 Reactors Shutdown Safety Cases Programme | Review & Acceptance of Review NSP's for Shutdown Cooling Safety Cases Report (HPB, HNB) (Not Req'd move to Post Gate B) | 2017-12-04 | 2018-08-23 | 20 | 0 | 181 | 262 | 100% | 0.076336 | 1 | Completed
ER6243LT | W200 | A15820 | REGION 1 Reactors Shutdown Safety Cases Programme | Review & Acceptance of Review NSP's for Shutdown Cooling Safety Cases Report (HYA, HAR)(Not Req'd move to Post Gate B) | 2017-12-04 | 2018-08-23 | 20 | 0 | 181 | 262 | 100% | 0.076336 | 1 | Completed
ER6243LT | W200 | RSSC.RP.A110 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Thermal Hydraulics (MACE) Report (PH1) | 2017-12-06 | 2018-11-07 | 239 | 0 | 233 | 336 | 100% | 0.71131 | 1 | Completed
ER6243LT | W200 | RSSC.RP.A112 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Pre Job Brief (PH1) | 2017-12-06 | 2017-12-06 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11510 | REGION 1 Reactors Shutdown Safety Cases Programme | Assessm't of Other Faults - Fault Studies Report verified and issued for Technical Review (HYA, HAR) | 2017-12-08 | 2017-12-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A7360 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2017-12-08 | 2017-12-14 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A7490 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2017-12-08 | 2017-12-14 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6243LT | W200 | RSSC.RP.A240 | REGION 1 Reactors Shutdown Safety Cases Programme | Develop approach to cooling flows with empty channels (HPB, HNB) | 2017-12-11 | 2017-12-29 | 20 | 0 | 12 | 18 | 100% | 1.1111 | 1 | Completed
ER6243LT | W200 | RSSC.RP.A250 | REGION 1 Reactors Shutdown Safety Cases Programme | Develop approach to cooling flows with empty channels (HYA, HAR) | 2017-12-11 | 2017-12-29 | 20 | 0 | 12 | 18 | 100% | 1.1111 | 1 | Completed
ER6243LT | W200 | A12160 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Review, Approve and Issue RFS to Supplier | 2017-12-13 | 2017-12-15 | 3 | 0 | 2 | 2 | 100% | 1.5 | 1 | Completed
ER6243LT | W200 | A13310 | REGION 1 Reactors Shutdown Safety Cases Programme | Linking BAT/BPM into optioneering Report Issued to CDMS (HPB, HNB) | 2017-12-13 | 2017-12-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A13320 | REGION 1 Reactors Shutdown Safety Cases Programme | Linking BAT/BPM into optioneering Report Issued to CDMS (HYA, HAR) | 2017-12-13 | 2017-12-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15900 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Review, Approve and Issue RFS to Supplier | 2017-12-13 | 2017-12-15 | 3 | 0 | 2 | 2 | 100% | 1.5 | 1 | Completed
ER6243LT | W200 | A14640 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics - Review, Approve and Issue RFS to Supplier | 2017-12-14 | 2017-12-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14820 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics - Request for Service (RFS) Specification Issued | 2017-12-14 | 2017-12-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A12165 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Request for Service (RFS) Specification Issued | 2017-12-15 | 2017-12-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14650 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics - Prepare and Issue Offer | 2017-12-15 | 2017-12-21 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6243LT | W200 | A16060 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Request for Service (RFS) Specification Issued | 2017-12-15 | 2017-12-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A7370 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for Minimum Forced Gas Circulation Requirements EAN | 2017-12-15 | 2017-12-15 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A7500 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for Assessment of Temperatures vs Decay Heat for Natural Circulation EAN | 2017-12-15 | 2017-12-15 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14830 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics - Initial Offer issued for Review | 2017-12-21 | 2017-12-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11360 | REGION 1 Reactors Shutdown Safety Cases Programme | Assessm't of Other Faults - Fault Studies Report verified and issued for Technical Review (HPB, HNB) | 2017-12-22 | 2017-12-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5870.EJ20 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Dropped FPU Impact on Reactor Internals Report Rev001 available (HYA and HRA) | 2017-12-22 | 2017-12-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.RP.A380.EB | REGION 1 Reactors Shutdown Safety Cases Programme | Heat transfer/thermal hydraulics initial assessments (HPB, HNB) | 2017-12-29 | 2017-12-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.RP.A390.EB | REGION 1 Reactors Shutdown Safety Cases Programme | Heat transfer/thermal hydraulics initial assessments (HYA, HAR) | 2017-12-29 | 2017-12-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A13230 | REGION 1 Reactors Shutdown Safety Cases Programme | Determine reactor/core temperature over time - Element decay heat over time - Review CHT for Depress'd ops C02. | 2017-12-29 | 2017-12-29 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A13240 | REGION 1 Reactors Shutdown Safety Cases Programme | Determine reactor/core temperature over time - Element decay heat over time - Review CHT for Depress'd ops C02. | 2017-12-29 | 2017-12-29 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A3610 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Failed fuel strategy agreed (HPB and HNB) | 2017-12-29 | 2017-12-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A3620 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Failed fuel strategy agreed (HYA and HRA) | 2017-12-29 | 2017-12-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A4290 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.01 - Project Management | 2018-01-01 | 2020-04-03 | 148 | 0 | 572 | 823 | 100% | 0.17983 | 1 | Completed
ER6243LT | W200 | A10560 | REGION 1 Reactors Shutdown Safety Cases Programme | P.10.01.01 - Defuelling Shutdown Safety Cases - Project Management | 2018-01-02 | 2020-04-15 | 346 | 0 | 578 | 834 | 100% | 0.41487 | 1 | Completed
ER6243LT | W200 | A10570 | REGION 1 Reactors Shutdown Safety Cases Programme | P.10.01.02 - Defuelling Shutdown Safety Cases - Safety Case | 2018-01-02 | 2019-10-11 | 197 | 0 | 450 | 647 | 100% | 0.30448 | 1 | Completed
ER6243LT | W200 | A10580 | REGION 1 Reactors Shutdown Safety Cases Programme | P.10.01.03 - Defuelling Shutdown Safety Cases - Operation Compliance | 2018-01-02 | 2018-12-20 | 122 | 0 | 247 | 352 | 100% | 0.34659 | 1 | Completed
ER6243LT | W200 | A10620 | REGION 1 Reactors Shutdown Safety Cases Programme | P.10.01.11 - Defuelling Shutdown Safety Cases - Vessel Integrity | 2018-01-02 | 2019-03-19 | 83 | 0 | 307 | 441 | 100% | 0.18821 | 1 | Completed
ER6243LT | W200 | A10630 | REGION 1 Reactors Shutdown Safety Cases Programme | P.10.01.13 - Defuelling Shutdown Safety Cases - Reactor Control System | 2018-01-02 | 2018-09-21 | 118 | 0 | 183 | 262 | 100% | 0.45038 | 1 | Completed
ER6243LT | W200 | A10640 | REGION 1 Reactors Shutdown Safety Cases Programme | P.10.01.19 - Defuelling Shutdown Safety Cases - Supporting Systems | 2018-01-02 | 2019-07-23 | 80 | 0 | 393 | 567 | 100% | 0.14109 | 1 | Completed
ER6243LT | W200 | RSSC.RP.A115 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Develop Thermal Hydraulics (MACE) Scoping Report (PH1) | 2018-01-02 | 2018-04-27 | 20 | 0 | 81 | 115 | 100% | 0.17391 | 1 | Completed
ER6243LT | W200 | A13190 | REGION 1 Reactors Shutdown Safety Cases Programme | Support Systems Summary - Outline Investment | 2018-01-02 | 2019-07-23 | 337 | 0 | 393 | 567 | 100% | 0.59436 | 1 | Completed
ER6243LT | W200 | A15910 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Prepare and Issue Offer | 2018-01-02 | 2018-01-03 | 10 | 0 | 1 | 1 | 100% | 10 | 1 | Completed
ER6243LT | W200 | A16100 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Support System Specification (HPB, HNB) | 2018-01-02 | 2018-01-10 | 20 | 0 | 6 | 8 | 100% | 2.5 | 1 | Completed
ER6243LT | W200 | A16160 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Support System Specification (HYA, HAR) | 2018-01-02 | 2018-01-10 | 20 | 0 | 6 | 8 | 100% | 2.5 | 1 | Completed
ER6244LT | W220 | A1370 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Assess dropped fuel assembly impact on reactor internals (at different temps.) & determine reactor damage HPB and HNB | 2018-01-02 | 2018-06-22 | 120 | 0 | 120 | 171 | 100% | 0.70175 | 1 | Completed
ER6244LT | W220 | A4040 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Identify issues related to HYA/HRA tie bars left on the FPUs and returned to the reactor for safe store | 2018-01-02 | 2018-03-26 | 60 | 0 | 60 | 83 | 100% | 0.72289 | 1 | Completed
ER6244LT | W220 | A4300 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.02 - Safety Case | 2018-01-02 | 2018-10-31 | 103 | 0 | 211 | 302 | 100% | 0.34106 | 1 | Completed
ER6244LT | W220 | A4330 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.05 - Defuelling Process | 2018-01-02 | 2019-03-15 | 63 | 0 | 306 | 437 | 100% | 0.14416 | 1 | Completed
ER6244LT | W220 | A4340 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.06 - Lifting Integrity | 2018-01-02 | 2018-06-29 | 167 | 0 | 124 | 178 | 100% | 0.9382 | 1 | Completed
ER6244LT | W220 | A4360 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.20 - Fuel Route Facilities | 2018-01-02 | 2018-08-31 | 128 | 0 | 169 | 241 | 100% | 0.53112 | 1 | Completed
ER6244LT | W220 | A4370 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.09 - Radiological Consequences | 2018-01-02 | 2018-12-31 | 167 | 0 | 253 | 363 | 100% | 0.46006 | 1 | Completed
ER6244LT | W220 | A4380 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.10 - Fault Studies | 2018-01-02 | 2018-12-31 | 148 | 0 | 253 | 363 | 100% | 0.40771 | 1 | Completed
ER6244LT | W220 | A4400 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.12 - Structural Integrity | 2018-01-02 | 2018-12-31 | 148 | 0 | 253 | 363 | 100% | 0.40771 | 1 | Completed
ER6244LT | W220 | A4430 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.15 - Pile Cap Equipment | 2018-01-02 | 2018-12-31 | 22 | 0 | 253 | 363 | 100% | 0.060606 | 1 | Completed
ER6244LT | W220 | A4450 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.17 - Stringer Integrity | 2018-01-02 | 2018-12-31 | 148 | 0 | 253 | 363 | 100% | 0.40771 | 1 | Completed
ER6244LT | W220 | A4460 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.18 - Interlock Changes | 2018-01-02 | 2018-12-31 | 147 | 0 | 253 | 363 | 100% | 0.40496 | 1 | Completed
ER6244LT | W220 | A4480 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.21 - Human Factors | 2018-01-02 | 2018-12-31 | 84 | 0 | 253 | 363 | 100% | 0.2314 | 1 | Completed
ER6244LT | W220 | A4500 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.23 - Maintenance | 2018-01-02 | 2018-06-29 | 148 | 0 | 124 | 178 | 100% | 0.83146 | 1 | Completed
ER6243LT | W200 | A10660 | REGION 1 Reactors Shutdown Safety Cases Programme | P.10.01.23 - Defuelling Shutdown Safety Cases - Maintenance | 2018-01-02 | 2018-07-06 | 52 | 0 | 129 | 185 | 100% | 0.28108 | 1 | Completed
ER6244LT | W220 | A5180 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft CO2 purity and decay heat report verified and issued for technical review | 2018-01-02 | 2018-01-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5190 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical review of CO2 purity and decay heat report | 2018-01-02 | 2018-09-03 | 19 | 0 | 170 | 244 | 100% | 0.077869 | 1 | Completed
ER6243LT | W200 | A12170 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Prepare and Issue Offer | 2018-01-02 | 2018-01-03 | 5 | 0 | 1 | 1 | 100% | 5 | 1 | Completed
ER6243LT | W200 | A13210 | REGION 1 Reactors Shutdown Safety Cases Programme | Project Quality Plan Audit | 2018-01-02 | 2018-01-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8200 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Risk Workshop Held | 2018-01-02 | 2018-01-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8210 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Project Quality Plan Audit | 2018-01-02 | 2018-01-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8740 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier update and issue Initial Fault Studies and Risk Estimation Report (HPB/HNB) | 2018-01-02 | 2018-01-22 | 15 | 0 | 15 | 20 | 100% | 0.75 | 1 | Completed
ER6244LT | W220 | A9530 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.07 - Fuel Storage Conditions | 2018-01-02 | 2018-08-31 | 0 | 0 | 168 | 241 | 100% | 0 | 1 | Completed
ER6244LT | W220 | A10420 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Optioneering Report for HPB/HNB | 2018-01-02 | 2018-03-20 | 18 | 0 | 56 | 77 | 100% | 0.23377 | 1 | Completed
ER6244LT | W220 | A10490 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Optioneering Report for HRA/HYA | 2018-01-02 | 2018-06-15 | 18 | 0 | 115 | 164 | 100% | 0.10976 | 1 | Completed
ER6243LT | W200 | A12175 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Initial Offer Issued for Review | 2018-01-03 | 2018-01-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A13530 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Credible Hazards and Faults verified and issued for Technical Review (HYA, HAR) | 2018-01-03 | 2018-01-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16070 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Initial Offer Issued for Review | 2018-01-03 | 2018-01-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A3710 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Decision on any changes to FM trip settings (HPB) and HNB) | 2018-01-03 | 2018-01-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A1860 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Establish fuelling machine trip settings/overrun speeds for new PIFA/IFA/Loading FPUs for defuelling. HYA and HRA | 2018-01-03 | 2018-07-31 | 145 | 0 | 145 | 209 | 100% | 0.69378 | 1 | Completed
ER6243LT | W200 | A12180 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Review and Negotiate Offer | 2018-01-04 | 2018-01-08 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6243LT | W200 | A13540 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Credible Hazards and Faults Technical Review by SQEP (HYA, HAR) | 2018-01-04 | 2018-03-14 | 10 | 0 | 49 | 69 | 100% | 0.14493 | 1 | Completed
ER6243LT | W200 | A15920 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Review and Negotiate Offer | 2018-01-04 | 2018-01-08 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6244LT | W220 | A5960 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Dropped FPU Impact on Buffer Store EAN (HPB and HNB) verified and issued for technical review | 2018-01-05 | 2018-01-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6090 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Dropped FPU Impact on Buffer Store EAN (HYA and HRA) verified and issued for technical review | 2018-01-05 | 2018-01-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A12185 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Offer Accepted/Approved | 2018-01-05 | 2018-01-08 | 0 | 0 | 0 | 3 | 100% | 0 | 1 | Completed
ER6243LT | W200 | A16080 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Offer Accepted/Approved | 2018-01-05 | 2018-01-08 | 0 | 0 | 0 | 3 | 100% | 0 | 1 | Completed
ER6244LT | W220 | A5970 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical review of Dropped FPU Impact on Buffer Store EAN (HPB and HNB) | 2018-01-08 | 2018-01-12 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6244LT | W220 | A6100 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical review of Dropped FPU Impact on Buffer Store EAN (HYA and HRA) | 2018-01-08 | 2018-01-15 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6243LT | W200 | A12190 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Complete Requisition Approval and Issue CI | 2018-01-09 | 2018-02-02 | 5 | 0 | 18 | 24 | 100% | 0.20833 | 1 | Completed
ER6243LT | W200 | A15930 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Complete Requisition Approval and Issue CI | 2018-01-09 | 2018-02-02 | 5 | 0 | 18 | 24 | 100% | 0.20833 | 1 | Completed
ER6243LT | W200 | A16110 | REGION 1 Reactors Shutdown Safety Cases Programme | Support System Specification Agreed (HPB, HNB) | 2018-01-10 | 2018-01-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16170 | REGION 1 Reactors Shutdown Safety Cases Programme | Support System Specification Agreed (HYA, HAR) | 2018-01-10 | 2018-01-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8320 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Justify Zero Maintenance for FPU Prio to Load in Shutdown Reactor EAN verified and issued for technical review | 2018-01-12 | 2018-01-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8450 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Justify Zero Maintenance for FPU Prio to Load in Shutdown Reactor EAN verified and issued for technical review | 2018-01-12 | 2018-01-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5980 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier update and issue Dropped FPU Impact on Buffer Store EAN (HPB and HNB) | 2018-01-15 | 2018-01-19 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6244LT | W220 | A6110 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier update and issue Dropped FPU Impact on Buffer Store EAN (HYA and HRA) | 2018-01-15 | 2018-01-19 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6244LT | W220 | A8330 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical review of Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 2018-01-15 | 2018-01-19 | 13 | 0 | 4 | 4 | 100% | 3.25 | 1 | Completed
ER6244LT | W220 | A8460 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical review of Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 2018-01-15 | 2018-01-19 | 13 | 0 | 4 | 4 | 100% | 3.25 | 1 | Completed
ER6244LT | W220 | A8340 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier update and issue Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 2018-01-22 | 2018-01-24 | 10 | 0 | 2 | 2 | 100% | 5 | 1 | Completed
ER6244LT | W220 | A8470 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier update and issue Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 2018-01-22 | 2018-01-24 | 20 | 0 | 2 | 2 | 100% | 10 | 1 | Completed
ER6244LT | W220 | A5990 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload Dropped FPU Impact on Buffer Store EAN (HPB and HNB) to CDMS | 2018-01-22 | 2018-01-31 | 8 | 0 | 8 | 9 | 100% | 0.88889 | 1 | Completed
ER6244LT | W220 | A6120 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload Dropped FPU Impact on Buffer Store EAN (HYA and HRA) to CDMS | 2018-01-22 | 2018-01-31 | 8 | 0 | 8 | 9 | 100% | 0.88889 | 1 | Completed
ER6244LT | W220 | A8750 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload Initial Fault Studies and Risk Estimation Report to CDMS (HPB/HNB) | 2018-01-23 | 2018-02-09 | 10 | 0 | 14 | 17 | 100% | 0.58824 | 1 | Completed
ER6243LT | W200 | RSSC.RP.A200 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Thermal Hydraulics (MACE) Calculations Report (PH2) | 2018-01-24 | 2018-11-07 | 223 | 0 | 200 | 287 | 100% | 0.777 | 1 | Completed
ER6243LT | W200 | RSSC.RP.A205 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Develop Thermal Hydraulics (MACE) Calculations Report (PH2) | 2018-01-24 | 2018-04-27 | 20 | 0 | 65 | 93 | 100% | 0.21505 | 1 | Completed
ER6243LT | W200 | A16240 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Contract Variation approved for next phase (HPB, HNB) | 2018-01-24 | 2018-01-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16260 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Contract Variation approved for next phase (HYA, HAR) | 2018-01-24 | 2018-01-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11240 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Draft Rad Con's Requirements for Post NSRS verified and issued for Technical Review (HPB, HNB) | 2018-01-24 | 2018-01-25 | 0 | 0 | 0 | 1 | 100% | 0 | 1 | Completed
ER6244LT | W220 | A8350 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN to CDMS | 2018-01-25 | 2018-01-29 | 10 | 0 | 2 | 4 | 100% | 2.5 | 1 | Completed
ER6244LT | W220 | A8480 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN to CDMS | 2018-01-25 | 2018-01-29 | 15 | 0 | 2 | 4 | 100% | 3.75 | 1 | Completed
ER6243LT | W200 | A13460 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Draft Rad Con's Requirements for Post NSRS verified and issued for Technical Review (HYA, HAR) | 2018-01-25 | 2018-01-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14040 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - RFS Summary - Optionnering for CR and N2 systems (Deleted No Longer Req'd) | 2018-01-25 | 2018-01-25 | 93 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14050 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Prepare Request for Service (RFS) Specification (Deleted No Longer Req'd) | 2018-01-25 | 2018-01-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14060 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Review, Approve and Issue RFS to Supplier (Deleted No Longer Req'd) | 2018-01-25 | 2018-01-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14100 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Review and Negotiate Offer (Deleted No Longer Req'd) | 2018-01-25 | 2018-01-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14120 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Complete Requisition Approval and Issue CI (Deleted No Longer Req'd) | 2018-01-25 | 2018-01-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14130 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Supplier Mobilisation Time (Deleted No Longer Req'd) | 2018-01-25 | 2018-01-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14070 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Request for Service (RFS) Specification Issued (Deleted No Longer Req'd) | 2018-01-25 | 2018-01-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14090 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Initial Offer Issued for Review (Deleted No Longer Req'd) | 2018-01-25 | 2018-01-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14110 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Offer Accepted/Approved (Deleted No Longer Req'd) | 2018-01-25 | 2018-01-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16250 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Prepare Engineering Substantiation Report (Phase 2) for Structural Integrity of PCPV (HPB, HNB) | 2018-01-25 | 2018-05-25 | 54 | 0 | 83 | 120 | 100% | 0.45 | 1 | Completed
ER6243LT | W200 | A16270 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Prepare Engineering Substantiation Report (Phase 2) for Structural Integrity of PCPV (HYA, HAR) | 2018-01-25 | 2018-05-25 | 54 | 0 | 83 | 120 | 100% | 0.45 | 1 | Completed
ER6243LT | W200 | A14080 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Prepare and Issue Offer (Deleted No Longer Req'd) | 2018-01-25 | 2018-01-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A12020.EA | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Draft QA3 SDM Defuelling Strategy Optioneering Report verified and issued for Tech Review | 2018-01-26 | 2018-01-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A12030 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - QA3 SDM Defuelling Strategy Optioneering Report Technical Review by SQEP | 2018-01-29 | 2018-03-14 | 12 | 0 | 32 | 44 | 100% | 0.27273 | 1 | Completed
ER6244LT | W220 | A8360 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN available | 2018-01-29 | 2018-01-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8490 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN available | 2018-01-29 | 2018-01-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15600 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Human Factor Principles for Reactors in Different Conditions (HPB, HNB) | 2018-01-29 | 2018-02-23 | 20 | 0 | 20 | 25 | 100% | 0.8 | 1 | Completed
ER6243LT | W200 | A15660 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Human Factor Principles for Reactors in Different Conditions (HYA, HAR) | 2018-01-29 | 2018-02-23 | 20 | 0 | 19 | 25 | 100% | 0.8 | 1 | Completed
ER6244LT | W220 | A6000.EJ | REGION 1 Defuelling Programme Fuel Handling Safety Case | Dropped FPU Impact on Buffer Store EAN (HPB and HNB) available | 2018-01-31 | 2018-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6130.EJ | REGION 1 Defuelling Programme Fuel Handling Safety Case | Dropped FPU Impact on Buffer Store EAN (HYA and HRA) available | 2018-01-31 | 2018-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A10590 | REGION 1 Reactors Shutdown Safety Cases Programme | P.10.01.04 - Defuelling Shutdown Safety Cases - Reactor Physics | 2018-02-01 | 2019-02-28 | 45 | 0 | 272 | 392 | 100% | 0.1148 | 1 | Completed
ER6243LT | W200 | A10600 | REGION 1 Reactors Shutdown Safety Cases Programme | P.10.01.08 - Defuelling Shutdown Safety Cases - Cooling - Normal Operations | 2018-02-01 | 2018-08-23 | 0 | 0 | 141 | 203 | 100% | 0 | 1 | Completed
ER6243LT | W200 | A10610 | REGION 1 Reactors Shutdown Safety Cases Programme | P.10.01.10 - Defuelling Shutdown Safety Cases - Fault Studies | 2018-02-01 | 2018-07-13 | 7 | 0 | 112 | 162 | 100% | 0.04321 | 1 | Completed
ER6244LT | W220 | A3600 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Update and Issue Defueling Options EAN | 2018-02-01 | 2018-02-14 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6244LT | W220 | A10220 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Permit Depressurised Fuelling Machine to Access IFD | 2018-02-01 | 2018-02-23 | 17 | 0 | 17 | 22 | 100% | 0.77273 | 1 | Completed
ER6244LT | W220 | A4730 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.19 - EP - Supporting Systems | 2018-02-01 | 2018-12-31 | 0 | 0 | 231 | 333 | 100% | 0 | 1 | Completed
ER6243LT | W200 | A12200 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Supplier Mobilisation Time | 2018-02-05 | 2018-02-12 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6243LT | W200 | A15940 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Supplier Mobilisation Time | 2018-02-05 | 2018-02-12 | 26 | 0 | 5 | 7 | 100% | 3.7143 | 1 | Completed
ER6244LT | W220 | A8900 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Final Update of Initial Fault Studies and Risk Estimation Report to CDMS (HPB/HNB) | 2018-02-12 | 2018-04-10 | 10 | 0 | 40 | 57 | 100% | 0.17544 | 1 | Completed
ER6243LT | W200 | RSSC.RCS.A100 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Undertake a High Level Impact Assessment & C&I BoD (HPB, HNB) | 2018-02-14 | 2018-09-21 | 162 | 0 | 152 | 219 | 100% | 0.73973 | 1 | Completed
ER6243LT | W200 | RSSC.RCS.A102 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Pre Job Brief (HPB, HNB) | 2018-02-14 | 2018-02-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.RCS.A110 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Undertake a High Level Impact Assessment & C&I BoD (HYA, HAR) | 2018-02-15 | 2018-09-21 | 151 | 0 | 151 | 218 | 100% | 0.69266 | 1 | Completed
ER6243LT | W200 | RSSC.RCS.A105 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Prepare Impact Assessment Report & C&I BoD (HPB, HNB) (Deliverable 1 Hold Point) | 2018-02-15 | 2018-05-09 | 56 | 0 | 56 | 83 | 100% | 0.6747 | 1 | Completed
ER6243LT | W200 | RSSC.RCS.A320 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Prepare Impact Assessment Report & C&I BoD (HYA, HAR) (Deliverable 1 Hold Point) | 2018-02-15 | 2018-05-09 | 58 | 0 | 56 | 83 | 100% | 0.6988 | 1 | Completed
ER6244LT | W220 | A3720 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload Defueling Options EAN to CDMS | 2018-02-15 | 2018-02-28 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6243LT | W200 | A14950 | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - Draft Summary of TS Charges Required verified and issued for Technical Review (HPB, HNB) | 2018-02-16 | 2018-02-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15060 | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - Draft Summary of TS Charges Required verified and issued for Technical Review (HYA, HAR) | 2018-02-16 | 2018-02-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A7900 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Review Radial Shuffling Safety Case EAN - Rev 001 | 2018-02-19 | 2018-03-30 | 8 | 0 | 29 | 39 | 100% | 0.20513 | 1 | Completed
ER6243LT | W200 | RSSC.RP.A120 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics - PCPV Integrity for Changing Temperatures Report Completed (HPB, HNB) (Not Req'd 20.02.18 as per DA) | 2018-02-20 | 2018-02-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.RP.A210 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics - PCPV Integrity for Changing Temperatures Report Completed (HYA, HAR) (Not Req'd 20.02.18 as per DA) | 2018-02-20 | 2018-02-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14580 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics - PCPV Integrity for Changing Temperatures Summary (HPB, HNB) (Not Req'd 20.02.18 as per DA) | 2018-02-20 | 2018-02-20 | 20 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14600 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics - PCPV Integrity for Changing Temperatures Summary (HYA, HAR) (Not Req'd 20.02.18 as per DA) | 2018-02-20 | 2018-02-20 | 20 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14660 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics - Review and Negotiate Offer (Not Req'd 20.02.18 as per DA) | 2018-02-20 | 2018-02-20 | 5 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14670 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics - Complete Requisition Approval and Issue CI (Not Req'd 20.02.18 as per DA) | 2018-02-20 | 2018-02-20 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14680 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics - Supplier Mobilisation Time (Not Req'd 20.02.18 as per DA) | 2018-02-20 | 2018-02-20 | 7 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14700 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics - Pre Job Brief (HPB, HNB) (Not Req'd 20.02.18 as per DA) | 2018-02-20 | 2018-02-20 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14710 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics-Draft PCPV Integrity for Changing Temp Report verified & issued for TR (Not Req'd 20.02.18 as per DA) | 2018-02-20 | 2018-02-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14720 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics - PCPV Integrity for Changing Temp Report Technical Review by SQEP (Not Req'd 20.02.18 as per DA) | 2018-02-20 | 2018-02-20 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14730 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics - Update and issue PCPV Integrity for Changing Temp Report (HPB, HNB) (Not Req'd 20.02.18 as per DA) | 2018-02-20 | 2018-02-20 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14740 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics - Complete TR form and upload to CDMS (HPB, HNB) (Not Req'd 20.02.18 as per DA) | 2018-02-20 | 2018-02-20 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14750 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics - PCPV Integrity for Changing Temperatures Report (HPB, HNB) (Not Req'd 20.02.18 as per DA) | 2018-02-20 | 2018-02-20 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14770 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics-Draft PCPV Integrity for Changing Temp Report verified & issued for TR (Not Req'd 20.02.18 as per DA) | 2018-02-20 | 2018-02-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14780 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics - PCPV Integrity for Changing Temperatures Report TR by SQEP (Not Req'd 20.02.18 as per DA) | 2018-02-20 | 2018-02-20 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14790 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics - Update and issue PCPV Integrity for Changing Temp Report (HYA, HAR) (Not Req'd 20.02.18 as per DA) | 2018-02-20 | 2018-02-20 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14800 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics - Complete TR form and upload to CDMS (HYA, HAR) (Not Req'd 20.02.18 as per DA) | 2018-02-20 | 2018-02-20 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14810 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics - PCPV Integrity for Changing Temperatures Report (HYA, HAR) (Not Req'd 20.02.18 as per DA) | 2018-02-20 | 2018-02-20 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14840 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics - Offer Accepted/Approved (Not Req'd 20.02.18 as per DA) | 2018-02-20 | 2018-02-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8990 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Fuelling Machine Light Load Protection & Interlocks EAN (HYA and HRA) verified and issued for technical review | 2018-02-20 | 2018-02-22 | 0 | 0 | 0 | 2 | 100% | 0 | 1 | Completed
ER6244LT | W220 | A5310 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Refuelling Cooling Assessment EAN verified and issued for technical review | 2018-02-23 | 2018-02-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8850 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Fuel Free Verification EAN issued for Verification | 2018-02-23 | 2018-02-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14550 | REGION 1 Reactors Shutdown Safety Cases Programme | Principles of Fuel Free Verification - Receipt of the Draft Report for TR (HPB, HNB) | 2018-02-23 | 2018-02-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14570 | REGION 1 Reactors Shutdown Safety Cases Programme | Principles of Fuel Free Verification - Receipt of the Draft Report for TR (HYA, HAR) | 2018-02-23 | 2018-02-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15610 | REGION 1 Reactors Shutdown Safety Cases Programme | Human Factor Principles for Reactors in Different Conditions Specification Agreed (HPB, HNB) | 2018-02-23 | 2018-02-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15670 | REGION 1 Reactors Shutdown Safety Cases Programme | Human Factor Principles for Reactors in Different Conditions Specification Agreed (HYA, HAR) | 2018-02-23 | 2018-02-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A10230 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Permit Depressurised Fuelling Machine to Access IFD verified and issued for technical review | 2018-02-23 | 2018-02-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15620 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Human Factor Principles for Reactors in Different Conditions Report (HPB, HNB) | 2018-02-26 | 2018-05-31 | 40 | 0 | 64 | 94 | 100% | 0.42553 | 1 | Completed
ER6243LT | W200 | A15680 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Human Factor Principles for Reactors in Different Conditions Report (HYA, HAR) | 2018-02-26 | 2018-05-31 | 40 | 0 | 64 | 94 | 100% | 0.42553 | 1 | Completed
ER6244LT | W220 | A5320 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical review of Refuelling Cooling Assessment EAN | 2018-02-26 | 2018-06-01 | 26 | 0 | 66 | 95 | 100% | 0.27368 | 1 | Completed
ER6244LT | W220 | A8860 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical Review of Fuel Free Verification EAN | 2018-02-26 | 2018-03-12 | 8 | 0 | 11 | 14 | 100% | 0.57143 | 1 | Completed
ER6243LT | W200 | A14140 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Optionnering for CR and N2 systems Summary (HPB, HNB) | 2018-02-27 | 2018-08-31 | 132 | 0 | 128 | 185 | 100% | 0.71351 | 1 | Completed
ER6243LT | W200 | A14150 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Workshop (HPB, HNB) | 2018-02-27 | 2018-02-27 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A10080 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Dropped FPU RadCons Analysis of Core Support Plate Failure | 2018-02-27 | 2018-07-09 | 25 | 0 | 90 | 132 | 100% | 0.18939 | 1 | Completed
ER6243LT | W200 | A11120 | REGION 1 Reactors Shutdown Safety Cases Programme | Closure and Seal Integrity - Receipt of the draft report for TR (HPB, HNB) | 2018-02-28 | 2018-02-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11160 | REGION 1 Reactors Shutdown Safety Cases Programme | Closure and Seal Integrity - Receipt of the draft report for TR (HYA, HAR) | 2018-02-28 | 2018-02-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14160 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Draft Optioneering for CR and N2 systems Report (HPB, HNB) | 2018-02-28 | 2018-06-29 | 24 | 0 | 83 | 121 | 100% | 0.19835 | 1 | Completed
ER6244LT | W220 | A3730.EC | REGION 1 Defuelling Programme Fuel Handling Safety Case | Defueling Options EAN Rev 001 Available | 2018-02-28 | 2018-02-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14960 | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - Summary of TS Charges Required Technical Review by SQEP (HPB, HNB) | 2018-03-01 | 2018-03-14 | 11 | 0 | 9 | 13 | 100% | 0.84615 | 1 | Completed
ER6243LT | W200 | A15070 | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - Summary of TS Charges Required Technical Review by SQEP (HYA, HAR) | 2018-03-01 | 2018-03-14 | 11 | 0 | 9 | 13 | 100% | 0.84615 | 1 | Completed
ER6243LT | W200 | A16120 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Support System Report (HPB, HNB) | 2018-03-01 | 2018-04-12 | 40 | 0 | 28 | 42 | 100% | 0.95238 | 1 | Completed
ER6243LT | W200 | A16180 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Support System Report (HYA, HAR) | 2018-03-01 | 2018-04-12 | 40 | 0 | 28 | 42 | 100% | 0.95238 | 1 | Completed
ER6244LT | W220 | A8580 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Initial Fault Studies and Risk Estimation Report (HYA/HRA) | 2018-03-01 | 2018-03-29 | 21 | 0 | 21 | 28 | 100% | 0.75 | 1 | Completed
ER6244LT | W220 | A10150 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Review of Rad Cons for Lower Decay Heat for Input into PSA | 2018-03-01 | 2018-07-02 | 60 | 0 | 84 | 123 | 100% | 0.4878 | 1 | Completed
ER6243LT | W200 | A1050 | REGION 1 Reactors Shutdown Safety Cases Programme | Confirm Objectives to be Delivered at Gate C | 2018-03-06 | 2018-03-19 | 10 | 0 | 9 | 13 | 100% | 0.76923 | 1 | Completed
ER6244LT | W220 | A8040 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft CRA Isolation Requirements EAN verified and issued for technical review | 2018-03-07 | 2018-03-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8050 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical review of CRA Isolation Requirements EAN | 2018-03-08 | 2018-05-11 | 20 | 0 | 44 | 64 | 100% | 0.3125 | 1 | Completed
ER6243LT | W200 | A11250 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Rad Con's Requirements for Post NSRS Technical Review by SQEP (HPB, HNB) | 2018-03-12 | 2018-04-06 | 11 | 0 | 17 | 25 | 100% | 0.44 | 1 | Completed
ER6243LT | W200 | A11370 | REGION 1 Reactors Shutdown Safety Cases Programme | Assessm't of Other Faults - Fault Studies Report Technical Review by SQEP (HPB, HNB) | 2018-03-12 | 2018-05-15 | 10 | 0 | 44 | 64 | 100% | 0.15625 | 1 | Completed
ER6243LT | W200 | A11520 | REGION 1 Reactors Shutdown Safety Cases Programme | Assessm't of Other Faults - Fault Studies Report Technical Review by SQEP (HYA, HAR) | 2018-03-12 | 2018-05-15 | 10 | 0 | 44 | 64 | 100% | 0.15625 | 1 | Completed
ER6243LT | W200 | A13470 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Rad Con's Requirements for Post NSRS Technical Review by SQEP (HYA, HAR) | 2018-03-12 | 2018-04-06 | 11 | 0 | 17 | 25 | 100% | 0.44 | 1 | Completed
ER6243LT | W200 | A15520 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Summary of supporting references Specification (HYA, HAR) | 2018-03-12 | 2018-03-13 | 20 | 0 | 1 | 1 | 100% | 20 | 1 | Completed
ER6243LT | W200 | A15515 | REGION 1 Reactors Shutdown Safety Cases Programme | Summary of Supporting References required for Safety Case (HYA, HAR) | 2018-03-12 | 2018-08-21 | 112 | 0 | 112 | 162 | 100% | 0.69136 | 1 | Completed
ER6243LT | W200 | A15280 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Summary of supporting references Specification (HPB, HNB) | 2018-03-12 | 2018-03-13 | 20 | 0 | 1 | 1 | 100% | 20 | 1 | Completed
ER6243LT | W200 | A15275 | REGION 1 Reactors Shutdown Safety Cases Programme | Summary of Supporting References required for Safety Case (HPB, HNB) | 2018-03-12 | 2018-08-21 | 146 | 0 | 112 | 162 | 100% | 0.90123 | 1 | Completed
ER6243LT | W200 | A15290 | REGION 1 Reactors Shutdown Safety Cases Programme | Summary of supporting references Specification Agreed (HPB, HNB) | 2018-03-13 | 2018-03-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15530 | REGION 1 Reactors Shutdown Safety Cases Programme | Summary of supporting references Specification Agreed (HYA, HAR) | 2018-03-13 | 2018-03-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8870 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Update and issue Fuel Free Verification EAN | 2018-03-13 | 2018-05-08 | 5 | 0 | 38 | 56 | 100% | 0.089286 | 1 | Completed
ER6243LT | W200 | A15300 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Summary of supporting references Report (HPB, HNB) | 2018-03-14 | 2018-05-04 | 40 | 0 | 36 | 51 | 100% | 0.78431 | 1 | Completed
ER6243LT | W200 | A15540 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Summary of supporting references Report (HYA, HAR) | 2018-03-14 | 2018-05-04 | 40 | 0 | 36 | 51 | 100% | 0.78431 | 1 | Completed
ER6244LT | W220 | A2080 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Assess interlock changes required for staggered operation of reactors, defueling mode & FPUs back in reactor (HYA & HRA) | 2018-03-14 | 2018-07-10 | 80 | 0 | 80 | 118 | 100% | 0.67797 | 1 | Completed
ER6243LT | W200 | A11300 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Update and issue Credible Hazards and Faults (HPB, HNB) | 2018-03-15 | 2018-05-04 | 5 | 0 | 34 | 50 | 100% | 0.1 | 1 | Completed
ER6243LT | W200 | A13550 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Update and issue Credible Hazards and Faults (HYA, HAR) | 2018-03-15 | 2018-05-04 | 5 | 0 | 34 | 50 | 100% | 0.1 | 1 | Completed
ER6243LT | W200 | A12040 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Update and issue QA3 SDM Defuelling Strategy Optioneering Report | 2018-03-15 | 2018-04-12 | 10 | 0 | 18 | 28 | 100% | 0.35714 | 1 | Completed
ER6243LT | W200 | RSSC.CNO.A100 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Systems - Cooling Plant Availability (Optioneering) (HPB, HNB) | 2018-03-20 | 2018-08-23 | 119 | 0 | 108 | 156 | 100% | 0.76282 | 1 | Completed
ER6243LT | W200 | A11550 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Systems - RFS Summary - Cooling Plant Availability (Optioneering) | 2018-03-20 | 2018-03-20 | 29 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11560 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Systems - Prepare (RFS) Cooling Plant Availability (Optioneering) Specification (N/A Using Existing Contract) | 2018-03-20 | 2018-03-20 | 10 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11570 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Systems - Review, Approve and Issue RFS to Supplier (N/A Using Existing Contract) | 2018-03-20 | 2018-03-20 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11580 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Systems - Prepare and Issue Offer (N/A Using Existing Contract) | 2018-03-20 | 2018-03-20 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11590 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Systems - Review and Negotiate Offer (N/A Using Existing Contract) | 2018-03-20 | 2018-03-20 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11600 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Systems - Complete Requisition Approval and Issue CI (N/A Using Existing Contract) | 2018-03-20 | 2018-03-20 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11610 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Systems - Supplier Mobilisation Time (N/A Using Existing Contract) | 2018-03-20 | 2018-03-20 | 7 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.CNO.A101 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Systems - Pre Job Brief (HPB, HNB) (N/A Using Existing Contract) | 2018-03-20 | 2018-03-20 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11575 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Systems - Request for Service (RFS) Specification Issued (N/A Using Existing Contract) | 2018-03-20 | 2018-03-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11585 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Systems - Initial Offer Issued for Review (N/A Using Existing Contract) | 2018-03-20 | 2018-03-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11595 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Systems - Offer Accepted/Approved (N/A Using Existing Contract) | 2018-03-20 | 2018-03-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.CNO.A105 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Systems - Cooling Plant Availability (Optioneering) (HPB, HNB) | 2018-03-21 | 2018-06-29 | 48 | 0 | 68 | 100 | 100% | 0.48 | 1 | Completed
ER6244LT | W220 | A10440 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical Review of Optioneering Report for HPB/HNB | 2018-03-21 | 2018-07-13 | 16 | 0 | 79 | 114 | 100% | 0.14035 | 1 | Completed
ER6244LT | W220 | A4050 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Confirm that HYA/HRA tie bars can be left on the FPUs and returned to the reactor for safe store | 2018-03-26 | 2018-03-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6220 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Buffer Store Defueling EAN verified and issued for technical review (HPB and HNB) | 2018-03-26 | 2018-03-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6350 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft IFDF Defueling EAN verified and issued for technical review (HPB and HNB) | 2018-03-26 | 2018-03-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6740 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Ponds and Flasks EAN verified and issued for technical review (HPB and HNB) | 2018-03-26 | 2018-03-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6870 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Waste Vault Storage Capacity EAN verified and issued for technical review (HPB and HNB) | 2018-03-26 | 2018-03-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6230 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical review of Buffer Store Defueling EAN (HPB and HNB) | 2018-03-27 | 2018-05-04 | 23 | 0 | 27 | 38 | 100% | 0.60526 | 1 | Completed
ER6244LT | W220 | A6360 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical review of IFDF Defueling EAN (HPB and HNB) | 2018-03-27 | 2018-05-04 | 23 | 0 | 27 | 38 | 100% | 0.60526 | 1 | Completed
ER6244LT | W220 | A6750 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical review of Ponds and Flasks EAN (HPB and HNB) | 2018-03-27 | 2018-05-04 | 23 | 0 | 27 | 38 | 100% | 0.60526 | 1 | Completed
ER6244LT | W220 | A6880 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical review of Waste Vault Storage Capacity EAN (HPB and HNB) | 2018-03-27 | 2018-05-04 | 23 | 0 | 27 | 38 | 100% | 0.60526 | 1 | Completed
ER6244LT | W220 | A8590 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Initial Fault Studies and Risk Estimation Report verified and issued for technical review (HYA/HRA) | 2018-03-29 | 2018-03-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A9360 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Fuel Storage Conditions EAN verified and issued for technical review (HYA and HRA) | 2018-03-29 | 2018-03-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A7910 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Review Radial Shuffling Safety Case EAN issued for verification - Rev 001 | 2018-03-29 | 2018-03-30 | 0 | 0 | 0 | 1 | 100% | 0 | 1 | Completed
ER6243LT | W200 | A14970 | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - Update and issue Summary of TS Charges Required (HPB, HNB) | 2018-04-03 | 2018-05-04 | 10 | 0 | 24 | 31 | 100% | 0.32258 | 1 | Completed
ER6243LT | W200 | A15080 | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - Update and issue Summary of TS Charges Required (HYA, HAR) | 2018-04-03 | 2018-05-04 | 10 | 0 | 24 | 31 | 100% | 0.32258 | 1 | Completed
ER6244LT | W220 | A7920 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Verification of Review Radial Shuffling Safety Case EAN - Rev 001 | 2018-04-03 | 2018-05-31 | 41 | 0 | 41 | 58 | 100% | 0.7069 | 1 | Completed
ER6244LT | W220 | A9370 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical review of Fuel Storage Conditions EAN | 2018-04-03 | 2018-07-09 | 23 | 0 | 68 | 97 | 100% | 0.23711 | 1 | Completed
ER6243LT | W200 | A11260 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Update and issue Rad Con's Requirements for Post NSRS (HPB, HNB) | 2018-04-09 | 2018-06-07 | 5 | 0 | 42 | 59 | 100% | 0.084746 | 1 | Completed
ER6243LT | W200 | A13480 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Update and issue Rad Con's Requirements for Post NSRS (HYA, HAR) | 2018-04-09 | 2018-06-07 | 5 | 0 | 42 | 59 | 100% | 0.084746 | 1 | Completed
ER6244LT | W220 | A10070 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Define H&I Work to Support Detailed PSA | 2018-04-10 | 2018-04-10 | 20 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8760 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Initial Fault Studies and Risk Estimation Report available (HPB/HNB) | 2018-04-10 | 2018-04-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16130 | REGION 1 Reactors Shutdown Safety Cases Programme | Draft Support System Report Available for Review (HPB, HNB) | 2018-04-10 | 2018-04-12 | 0 | 0 | 0 | 2 | 100% | 0 | 1 | Completed
ER6243LT | W200 | A16190 | REGION 1 Reactors Shutdown Safety Cases Programme | Draft Support System Report Available for Review (HYA, HAR) | 2018-04-10 | 2018-04-12 | 0 | 0 | 0 | 2 | 100% | 0 | 1 | Completed
ER6243LT | W200 | A1040 | REGION 1 Reactors Shutdown Safety Cases Programme | Initial high level scope of programme | 2018-04-12 | 2018-07-20 | 10 | 0 | 69 | 99 | 100% | 0.10101 | 1 | Completed
ER6243LT | W200 | A16140 | REGION 1 Reactors Shutdown Safety Cases Programme | Review & Acceptance of Support System Report (HPB, HNB) | 2018-04-13 | 2018-06-14 | 16 | 0 | 42 | 62 | 100% | 0.25806 | 1 | Completed
ER6243LT | W200 | A16200 | REGION 1 Reactors Shutdown Safety Cases Programme | Review & Acceptance of Support System Report (HYA, HAR) | 2018-04-13 | 2018-06-14 | 20 | 0 | 42 | 62 | 100% | 0.32258 | 1 | Completed
ER6243LT | W200 | A14210 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Optionnering for CR and N2 systems Summary (HYA, HAR) | 2018-04-25 | 2018-08-31 | 91 | 0 | 89 | 128 | 100% | 0.71094 | 1 | Completed
ER6243LT | W200 | A14220 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Workshop (HYA, HAR) | 2018-04-25 | 2018-04-25 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14230 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Draft Optionnering for CR and N2 systems Report (HYA, HAR) | 2018-04-26 | 2018-06-29 | 24 | 0 | 44 | 64 | 100% | 0.375 | 1 | Completed
ER6243LT | W200 | A11820 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Draft Thermal Hydraulics (MACE) Scoping Report verified and issued for Technical Review(PH1) | 2018-04-27 | 2018-04-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11880 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Draft (MACE) Calculations Report verified and issued for Technical Review(PH2) | 2018-04-27 | 2018-04-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.CNO.A140 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Systems - Cooling Plant Availability (Optioneering) (HYA, HAR) | 2018-04-30 | 2018-08-23 | 112 | 0 | 81 | 115 | 100% | 0.97391 | 1 | Completed
ER6243LT | W200 | RSSC.CNO.A145 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Systems - Cooling Plant Availability (Optioneering) (HYA, HAR) | 2018-04-30 | 2018-06-29 | 32 | 0 | 42 | 60 | 100% | 0.53333 | 1 | Completed
ER6243LT | W200 | A12050 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Complete TR form and upload to CDMS | 2018-05-01 | 2018-06-29 | 21 | 0 | 41 | 59 | 100% | 0.35593 | 1 | Completed
ER6243LT | W200 | A16550 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Initial Review & Recommendation by WOOD | 2018-05-01 | 2018-05-15 | 10 | 0 | 9 | 14 | 100% | 0.71429 | 1 | Completed
ER6243LT | W200 | A16590 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Initial Review & Recommendation | 2018-05-01 | 2018-05-15 | 10 | 0 | 9 | 14 | 100% | 0.71429 | 1 | Completed
ER6244LT | W220 | A1300 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Determine fuel storage conditions - general guidance that will inform reactor storageand for ex-reactor facilities | 2018-05-01 | 2018-07-31 | 64 | 0 | 64 | 91 | 100% | 0.7033 | 1 | Completed
ER6244LT | W220 | A1310 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review Inter-Granular Attack (IGA) assessments - determine whether these would need to be updated to support defuelling. | 2018-05-01 | 2018-07-31 | 64 | 0 | 64 | 91 | 100% | 0.7033 | 1 | Completed
ER6244LT | W220 | A8600 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical review of Initial Fault Studies and Risk Estimation Report (HYA/HRA) | 2018-05-01 | 2018-07-16 | 21 | 0 | 53 | 76 | 100% | 0.27632 | 1 | Completed
ER6244LT | W220 | A9000 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical review of Fuelling Machine Light Load Protection & Interlocks EAN (HPB and HNB) | 2018-05-01 | 2018-06-01 | 22 | 0 | 22 | 31 | 100% | 0.70968 | 1 | Completed
ER6244LT | W220 | A9880 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Fuel Free Verification EAN verified and issued for technical review | 2018-05-04 | 2018-05-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11310 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Complete TR form and upload to CDMS (HPB, HNB) | 2018-05-07 | 2018-06-29 | 5 | 0 | 37 | 53 | 100% | 0.09434 | 1 | Completed
ER6243LT | W200 | A13560 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Complete TR form and upload to CDMS (HYA, HAR) | 2018-05-07 | 2018-06-29 | 5 | 0 | 37 | 53 | 100% | 0.09434 | 1 | Completed
ER6244LT | W220 | A6240 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier update and issue Buffer Store Defueling EAN (HPB and HNB) | 2018-05-08 | 2018-05-18 | 9 | 0 | 9 | 10 | 100% | 0.9 | 1 | Completed
ER6244LT | W220 | A6370 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier update and issue IFDF Defueling EAN (HPB and HNB) | 2018-05-08 | 2018-05-18 | 9 | 0 | 9 | 10 | 100% | 0.9 | 1 | Completed
ER6244LT | W220 | A6760 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier update and issue Ponds and Flasks EAN (HPB and HNB) | 2018-05-08 | 2018-05-18 | 9 | 0 | 9 | 10 | 100% | 0.9 | 1 | Completed
ER6244LT | W220 | A6890 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier update and issue Waste Vault Storage Capacity EAN (HPB and HNB) | 2018-05-08 | 2018-05-18 | 9 | 0 | 9 | 10 | 100% | 0.9 | 1 | Completed
ER6244LT | W220 | A8060 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier update and issue CRA Isolation Requirements EAN | 2018-05-08 | 2018-05-25 | 20 | 0 | 13 | 17 | 100% | 1.1765 | 1 | Completed
ER6244LT | W220 | A9890 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical review of Fuel Free Verification EAN | 2018-05-08 | 2018-07-11 | 9 | 0 | 46 | 64 | 100% | 0.14062 | 1 | Completed
ER6244LT | W220 | A8890 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Fuel Free Verification EAN available | 2018-05-08 | 2018-05-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A12230 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Draft Impact Assessment Report & C&I BoD verified and issued for Technical Review (HPB, HNB) | 2018-05-09 | 2018-05-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A12270 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Draft Impact Assessment Report & C&I BoD verified and issued for Technical Review (HYA, HAR) | 2018-05-09 | 2018-05-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A12240 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Impact Assessment Report & C&I BoD Technical Review by SQEP (HPB, HNB) | 2018-05-10 | 2018-06-29 | 10 | 0 | 35 | 50 | 100% | 0.2 | 1 | Completed
ER6243LT | W200 | A12280 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Impact Assessment Report & C&I BoD Technical Review by SQEP (HYA, HAR) | 2018-05-10 | 2018-06-29 | 10 | 0 | 35 | 50 | 100% | 0.2 | 1 | Completed
ER6244LT | W220 | A6610 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft IFDF Defueling EAN verified and issued for technical review (HYA and HRA) | 2018-05-14 | 2018-05-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A7000 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Ponds and Flasks EAN verified and issued for technical review (HYA and HRA) | 2018-05-14 | 2018-05-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A7130 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Waste Vault Storage Capacity EAN verified and issued for technical review (HYA and HRA) | 2018-05-14 | 2018-05-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6620 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical review of IFDF Defueling EAN (HYA and HRA) | 2018-05-15 | 2018-05-21 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A7010 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical review of Ponds and Flasks EAN (HYA and HRA) | 2018-05-15 | 2018-05-21 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A7140 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical review of Waste Vault Storage Capacity EAN (HYA and HRA) | 2018-05-15 | 2018-05-21 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6243LT | W200 | A11380 | REGION 1 Reactors Shutdown Safety Cases Programme | Assessm't of Other Faults - Update and issue Fault Studies Report (HPB, HNB) | 2018-05-16 | 2018-05-31 | 5 | 0 | 10 | 15 | 100% | 0.33333 | 1 | Completed
ER6243LT | W200 | A11530 | REGION 1 Reactors Shutdown Safety Cases Programme | Assessm't of Other Faults - Update and issue Fault Studies Report (HYA, HAR) | 2018-05-16 | 2018-05-31 | 5 | 0 | 10 | 15 | 100% | 0.33333 | 1 | Completed
ER6243LT | W200 | A16560 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Prepare Updated Draft Summary Document | 2018-05-16 | 2018-06-29 | 15 | 0 | 31 | 44 | 100% | 0.34091 | 1 | Completed
ER6243LT | W200 | A16600 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Prepare Updated HPB Defuelling Dataset | 2018-05-16 | 2018-06-29 | 15 | 0 | 31 | 44 | 100% | 0.34091 | 1 | Completed
ER6244LT | W220 | A6250 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload Buffer Store Defueling EAN to CDMS (HPB and HNB) | 2018-05-21 | 2018-08-17 | 4 | 0 | 64 | 88 | 100% | 0.045455 | 1 | Completed
ER6244LT | W220 | A6380 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload IFDF Defueling EAN to CDMS (HPB and HNB) | 2018-05-21 | 2018-08-17 | 4 | 0 | 64 | 88 | 100% | 0.045455 | 1 | Completed
ER6244LT | W220 | A6770 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload Ponds and Flasks EAN to CDMS (HPB and HNB) | 2018-05-21 | 2018-08-17 | 4 | 0 | 64 | 88 | 100% | 0.045455 | 1 | Completed
ER6244LT | W220 | A6900 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload Waste Vault Storage Capacity EAN to CDMS (HPB and HNB) | 2018-05-21 | 2018-08-17 | 4 | 0 | 64 | 88 | 100% | 0.045455 | 1 | Completed
ER6244LT | W220 | A6630 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier update and issue IFDF Defueling EAN (HYA and HRA) | 2018-05-22 | 2018-05-25 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6244LT | W220 | A7020 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier update and issue Ponds and Flasks EAN (HYA and HRA) | 2018-05-22 | 2018-05-25 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6244LT | W220 | A7150 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier update and issue Waste Vault Storage Capacity EAN (HYA and HRA) | 2018-05-22 | 2018-05-25 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6243LT | W200 | A10920 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Engineering Substantiation Report verified and issued for Technical Review (HPB, HNB) | 2018-05-25 | 2018-05-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A10980 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Engineering Substantiation Report verified and issued for Technical Review (HYA, HAR) | 2018-05-25 | 2018-05-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6640 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload IFDF Defueling EAN to CDMS (HYA and HRA) | 2018-05-29 | 2018-07-27 | 3 | 0 | 44 | 59 | 100% | 0.050847 | 1 | Completed
ER6244LT | W220 | A7030 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload Ponds and Flasks EAN to CDMS (HYA and HRA) | 2018-05-29 | 2018-07-27 | 3 | 0 | 44 | 59 | 100% | 0.050847 | 1 | Completed
ER6244LT | W220 | A7160 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload Waste Vault Storage Capacity EAN to CDMS (HYA and HRA) | 2018-05-29 | 2018-07-27 | 3 | 0 | 44 | 59 | 100% | 0.050847 | 1 | Completed
ER6244LT | W220 | A8070 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload CRA Isolation Requirements EAN to CDMS | 2018-05-29 | 2018-06-04 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A10360 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Review of Safety Case Limits & LOLER Inspection Requirements | 2018-06-01 | 2018-12-17 | 85 | 0 | 141 | 199 | 100% | 0.42714 | 1 | Completed
ER6244LT | W220 | A10540 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical Review of OPR Cycle Times EAN | 2018-06-01 | 2018-08-01 | 43 | 0 | 44 | 61 | 100% | 0.70492 | 1 | Completed
ER6244LT | W220 | A10580 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Review of Off-Load Pressurised Refuelling Safety Case for Defuelling Verified and Issued for TR | 2018-06-01 | 2018-06-08 | 21 | 0 | 5 | 7 | 100% | 3 | 1 | Completed
ER6244LT | W220 | A10830 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft HHB Scoping Review Assessing Radcons 90days after EoG | 2018-06-01 | 2018-07-02 | 5 | 0 | 21 | 31 | 100% | 0.16129 | 1 | Completed
ER6243LT | W200 | A1010 | REGION 1 Reactors Shutdown Safety Cases Programme | Produce MF EC 363701 & 364023 <NSRS SC Approach & Outline> & obtain approval (HPB, HNB) | 2018-06-04 | 2018-08-28 | 5 | 0 | 60 | 85 | 100% | 0.058824 | 1 | Completed
ER6243LT | W200 | A10190 | REGION 1 Reactors Shutdown Safety Cases Programme | Produce MF EC 363682 & 363676 <NSRS SC Approach & Outline> & obtain approval (HYA, HAR) | 2018-06-04 | 2018-08-21 | 5 | 0 | 56 | 78 | 100% | 0.064103 | 1 | Completed
ER6243LT | W200 | RSSC.VI.A230.EI | REGION 1 Reactors Shutdown Safety Cases Programme | Closure and Seal Integrity - Issue of the report on to CDMS. (HPB, HNB) | 2018-06-04 | 2018-06-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.VI.A240.EI | REGION 1 Reactors Shutdown Safety Cases Programme | Closure and Seal Integrity - Issue of the report on to CDMS (HYA, HAR) | 2018-06-04 | 2018-06-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5330 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier update and issue Refuelling Cooling Assessment EAN | 2018-06-04 | 2018-08-01 | 10 | 0 | 43 | 58 | 100% | 0.17241 | 1 | Completed
ER6244LT | W220 | A7930 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Update and issue Review Radial Shuffling Safety Case EAN - Rev 001 | 2018-06-04 | 2018-06-08 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6244LT | W220 | A9010 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier update and issue Fuelling Machine Light Load Protection & Interlocks EAN (HPB and HNB) | 2018-06-04 | 2018-06-07 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6244LT | W220 | A8080.EC | REGION 1 Defuelling Programme Fuel Handling Safety Case | CRA Isolation Requirements EAN available | 2018-06-04 | 2018-06-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16530 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Draft Human Factors Integration Plan EAN (HPB, HNB) | 2018-06-06 | 2018-07-31 | 20 | 0 | 39 | 55 | 100% | 0.36364 | 1 | Completed
ER6243LT | W200 | A16540 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Draft Human Factors Integration Plan EAN (HYA, HAR) | 2018-06-06 | 2018-07-31 | 20 | 0 | 40 | 55 | 100% | 0.36364 | 1 | Completed
ER6244LT | W220 | A7950.EC | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review Radial Shuffling Safety Case EAN available - Rev 001 | 2018-06-06 | 2018-06-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11270 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Complete TR form and upload to CDMS (HPB, HNB) | 2018-06-08 | 2018-06-29 | 5 | 0 | 15 | 21 | 100% | 0.2381 | 1 | Completed
ER6244LT | W220 | A9020 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload Fuelling Machine Light Load Protection & Interlocks EAN (HPB and HNB) to CDMS | 2018-06-08 | 2018-06-15 | 6 | 0 | 6 | 7 | 100% | 0.85714 | 1 | Completed
ER6243LT | W200 | A13490 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Complete TR form and upload to CDMS (HYA, HAR) | 2018-06-08 | 2018-06-29 | 5 | 0 | 15 | 21 | 100% | 0.2381 | 1 | Completed
ER6243LT | W200 | A3120 | REGION 1 Reactors Shutdown Safety Cases Programme | Mod Requested, Identify RE and EC Request Raised and Screened (HPB, HNB) | 2018-06-11 | 2018-07-13 | 5 | 0 | 24 | 32 | 100% | 0.15625 | 1 | Completed
ER6243LT | W200 | A10310 | REGION 1 Reactors Shutdown Safety Cases Programme | Mod Requested, Identify RE and EC Request Raised and Screened (HYA, HAR) | 2018-06-11 | 2018-08-07 | 5 | 0 | 42 | 57 | 100% | 0.087719 | 1 | Completed
ER6244LT | W220 | A10590 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical Review of Review of Off-Load Pressurised Refuelling Safety Case for Defuelling | 2018-06-11 | 2018-08-21 | 22 | 0 | 52 | 71 | 100% | 0.30986 | 1 | Completed
ER6244LT | W220 | A9900 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier update and issue Fuel Free Verification EAN | 2018-06-13 | 2018-07-18 | 5 | 0 | 26 | 35 | 100% | 0.14286 | 1 | Completed
ER6243LT | W200 | A15840 | REGION 1 Reactors Shutdown Safety Cases Programme | Overall Delivery Plan - Produce Overall Delivery Plan (HPB, HNB) (No Longer Req,d) | 2018-06-14 | 2018-06-14 | 13 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15850 | REGION 1 Reactors Shutdown Safety Cases Programme | Overall Delivery Plan - Produce Overall Delivery Plan (HYA, HAR) (No Longer Req,d) | 2018-06-14 | 2018-06-14 | 65 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15950 | REGION 1 Reactors Shutdown Safety Cases Programme | Overall Delivery Plan - Pre Job Brief (HPB, HNB)(No Longer Req,d) | 2018-06-14 | 2018-06-14 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16030 | REGION 1 Reactors Shutdown Safety Cases Programme | Overall Delivery Plan - Update and issue Overall Delivery Plan (HYA, HAR) (No Longer Req,d) | 2018-06-14 | 2018-06-14 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15970 | REGION 1 Reactors Shutdown Safety Cases Programme | Overall Delivery Plan - Overall Delivery Plan Technical Review by SQEP (HPB, HNB) (No Longer Req,d) | 2018-06-14 | 2018-06-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15980 | REGION 1 Reactors Shutdown Safety Cases Programme | Overall Delivery Plan - Update and issue Overall Delivery Plan (HPB, HNB) (No Longer Req,d) | 2018-06-14 | 2018-06-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15990 | REGION 1 Reactors Shutdown Safety Cases Programme | Overall Delivery Plan - Complete TR form and upload to CDMS (HPB, HNB) (No Longer Req,d) | 2018-06-14 | 2018-06-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16000 | REGION 1 Reactors Shutdown Safety Cases Programme | Overall Delivery Plan - Prepare Overall Delivery Plan (HPB, HNB) (Deliverable 1 Post Hold Point) (No Longer Req,d) | 2018-06-14 | 2018-06-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16020 | REGION 1 Reactors Shutdown Safety Cases Programme | Overall Delivery Plan - Overall Delivery Plan Technical Review by SQEP (HYA, HAR) (No Longer Req,d) | 2018-06-14 | 2018-06-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16040 | REGION 1 Reactors Shutdown Safety Cases Programme | Overall Delivery Plan - Complete TR form and upload to CDMS (HYA, HAR) (No Longer Req,d) | 2018-06-14 | 2018-06-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16050 | REGION 1 Reactors Shutdown Safety Cases Programme | Overall Delivery Plan - Prepare Overall Delivery Plan (HYA, HAR) (Deliverable 1 Post Hold Point) (No Longer Req,d) | 2018-06-14 | 2018-06-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15860 | REGION 1 Reactors Shutdown Safety Cases Programme | Overall Delivery Plan - Overall Delivery Plan for required plant modifications Completed. (HPB, HNB) (No Longer Req,d) | 2018-06-14 | 2018-06-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15870 | REGION 1 Reactors Shutdown Safety Cases Programme | Overall Delivery Plan - Overall Delivery Plan for required plant modifications Completed. (HYA, HAR) (No Longer Req,d) | 2018-06-14 | 2018-06-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15960 | REGION 1 Reactors Shutdown Safety Cases Programme | Overall Delivery Plan - Draft Overall Delivery Plan verified and issued for Tech Review (HPB, HNB) (No Longer Req,d) | 2018-06-14 | 2018-06-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16010 | REGION 1 Reactors Shutdown Safety Cases Programme | Overall Delivery Plan - Draft Overall Delivery Plan verified and issued for Tech Review (HYA, HAR) (No Longer Req,d) | 2018-06-14 | 2018-06-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16720 | REGION 1 Reactors Shutdown Safety Cases Programme | Complete and Issue Contract Variation (HPB, HNB) | 2018-06-15 | 2018-06-29 | 5 | 0 | 10 | 14 | 100% | 0.35714 | 1 | Completed
ER6243LT | W200 | A16750 | REGION 1 Reactors Shutdown Safety Cases Programme | Complete and Issue Contract Variation (HYA, HAR) | 2018-06-15 | 2018-06-29 | 5 | 0 | 10 | 14 | 100% | 0.35714 | 1 | Completed
ER6244LT | W220 | A6130 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Fuelling Machine Light Load Protection & Interlocks EAN (HPB and HNB) available | 2018-06-15 | 2018-06-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A10500 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical Review of Optioneering Report for HRA/HYA | 2018-06-18 | 2018-07-27 | 10 | 0 | 30 | 39 | 100% | 0.25641 | 1 | Completed
ER6244LT | W220 | A1650 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Confirm reactor internals damage (at diff. temps) & buffer store plant damage caused by dropped FPU impact (HPB & HNB) | 2018-06-22 | 2018-06-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.FS.A200 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Rad Con's Requirements for Post NSRS Identified and Scoped Completed (HPB, HNB) | 2018-06-29 | 2018-06-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.FS.A210 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Credible Hazards and Faults Identified and Scoped Completed (HPB, HNB) | 2018-06-29 | 2018-06-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11640 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Systems - Draft Cooling Plant Availability (Optioneering) verified and issued for Technical Review (HPB, HNB) | 2018-06-29 | 2018-06-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11690 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Systems - Draft Cooling Plant Availability (Optioneering) verified and issued for Technical Review (HYA, HAR) | 2018-06-29 | 2018-06-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A12060.EA | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - QA3 SDM Defuelling Strategy Optioneering Report Completed | 2018-06-29 | 2018-06-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A13440 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Rad Con's Requirements for Post NSRS Identified and Scoped Completed (HYA, HAR) | 2018-06-29 | 2018-06-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A13520 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Faults - Credible Hazards and Faults Identified and Scoped Completed (HYA, HAR) | 2018-06-29 | 2018-06-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14170 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Draft Optioneering for CR and N2 systems verified and issued for Technical Review (HPB, HNB) | 2018-06-29 | 2018-06-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14240 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Draft Optionnering for CR and N2 systems verified and issued for Technical Review (HYA, HAR) | 2018-06-29 | 2018-06-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A10930 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Engineering Substantiation Report Technical Review by SQEP (HPB, HNB) | 2018-07-02 | 2018-07-13 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6243LT | W200 | A11390 | REGION 1 Reactors Shutdown Safety Cases Programme | Assessm't of Other Faults - Complete TR form and upload to CDMS (HPB, HNB) | 2018-07-02 | 2018-07-13 | 5 | 0 | 9 | 11 | 100% | 0.45455 | 1 | Completed
ER6243LT | W200 | A11540 | REGION 1 Reactors Shutdown Safety Cases Programme | Assessm't of Other Faults - Complete TR form and upload to CDMS (HYA, HAR) | 2018-07-02 | 2018-07-13 | 5 | 0 | 9 | 11 | 100% | 0.45455 | 1 | Completed
ER6243LT | W200 | A11650 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Systems - Cooling Plant Availability (Optioneering) Technical Review by SQEP (HPB, HNB) | 2018-07-02 | 2018-07-16 | 10 | 0 | 10 | 14 | 100% | 0.71429 | 1 | Completed
ER6243LT | W200 | A11700 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Systems - Cooling Plant Availability (Optioneering) Technical Review by SQEP (HYA, HAR) | 2018-07-02 | 2018-07-16 | 10 | 0 | 10 | 14 | 100% | 0.71429 | 1 | Completed
ER6243LT | W200 | A12250 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Update and issue Impact Assessment Report & C&I BoD (HPB, HNB) | 2018-07-02 | 2018-07-30 | 10 | 0 | 20 | 28 | 100% | 0.35714 | 1 | Completed
ER6243LT | W200 | A12290 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Update and issue Impact Assessment Report & C&I BoD (HYA, HAR) | 2018-07-02 | 2018-07-30 | 10 | 0 | 20 | 28 | 100% | 0.35714 | 1 | Completed
ER6243LT | W200 | A14180 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Optioneering for CR and N2 systems Technical Review by SQEP (HPB, HNB) | 2018-07-02 | 2018-07-16 | 19 | 0 | 10 | 14 | 100% | 1.3571 | 1 | Completed
ER6243LT | W200 | A14250 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Optionnering for CR and N2 systems Technical Review by SQEP (HYA, HAR) | 2018-07-02 | 2018-07-16 | 19 | 0 | 10 | 14 | 100% | 1.3571 | 1 | Completed
ER6243LT | W200 | A14980 | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - Complete TR form and upload to CDMS (HPB, HNB) | 2018-07-02 | 2018-07-06 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6243LT | W200 | A15090 | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - Complete TR form and upload to CDMS (HYA, HAR) | 2018-07-02 | 2018-07-06 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6243LT | W200 | A16630 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Ageing & Degradation - Engineering Substantiation Report Technical Review by SQEP (HPB, HNB) | 2018-07-02 | 2018-07-13 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6243LT | W200 | A16670 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Ageing & Degradation - Engineering Substantiation Report Technical Review by SQEP (HYA, HAR) | 2018-07-02 | 2018-07-13 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6244LT | W220 | A3330 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Produce draft NSRS for HYA and HRA (using BARRIER MODEL) | 2018-07-02 | 2018-10-19 | 75 | 0 | 79 | 109 | 100% | 0.68807 | 1 | Completed
ER6244LT | W220 | A10290 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Review of Plant Requirements for Defuelling | 2018-07-02 | 2018-12-17 | 60 | 0 | 120 | 168 | 100% | 0.35714 | 1 | Completed
ER6244LT | W220 | A10730 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft HHB Scoping Review Assessing Radcons 90days after EoG Verified and Issued for Technical Review | 2018-07-02 | 2018-07-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A10900 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier mobilisation | 2018-07-02 | 2018-07-04 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6244LT | W220 | A10160 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Review of Rad Cons for Lower Decay Heat for Input into PSA verified and issued for technical review | 2018-07-02 | 2018-07-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16570 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Updated Draft Summary Document Internally Verified | 2018-07-03 | 2018-07-31 | 22 | 0 | 20 | 28 | 100% | 0.78571 | 1 | Completed
ER6243LT | W200 | A16780 | REGION 1 Reactors Shutdown Safety Cases Programme | Develop Draft Station resourced Plans for HPB and HNB | 2018-07-03 | 2018-10-10 | 20 | 0 | 70 | 99 | 100% | 0.20202 | 1 | Completed
ER6243LT | W200 | A16800 | REGION 1 Reactors Shutdown Safety Cases Programme | Develop Draft Station resourced Plans for HNB (Reactor 3 early closure) | 2018-07-03 | 2018-10-10 | 20 | 0 | 70 | 99 | 100% | 0.20202 | 1 | Completed
ER6244LT | W220 | A10170 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical review of Review of Rad Cons for Lower Decay Heat for Input into PSA | 2018-07-03 | 2018-10-19 | 25 | 0 | 78 | 108 | 100% | 0.23148 | 1 | Completed
ER6244LT | W220 | A10905.EJ | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for Dropped FPU impact on Core Support Structure (HYA and HRA) | 2018-07-05 | 2018-07-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A10910 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Dropped FPU impact on Core Support Structure Report (HYA and HRA) | 2018-07-05 | 2018-10-01 | 60 | 0 | 62 | 88 | 100% | 0.68182 | 1 | Completed
ER6243LT | W200 | RSSC.M.A180.ET | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - Report identifying key safety related plant for post operational phase (HPB, HNB) | 2018-07-06 | 2018-07-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.M.A190.ET | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - Report identifying key safety related plant for post operational phase (HYA, HAR) | 2018-07-06 | 2018-07-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14860 | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - Summary of TS Charges Required Identified and Scoped Completed (HPB, HNB) | 2018-07-06 | 2018-07-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15040 | REGION 1 Reactors Shutdown Safety Cases Programme | Maintenance - Summary of TS Charges Required Identified and Scoped Completed (HYA, HAR) | 2018-07-06 | 2018-07-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A10090 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Dropped FPU RadCons Analysis of Core Support Plate Failure verified and issued for technical review | 2018-07-09 | 2018-07-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A9620 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Fuel Free Verification EAN verified and issued for technical review | 2018-07-09 | 2018-07-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A10100 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical review of Dropped FPU RadCons Analysis of Core Support Plate Failure | 2018-07-10 | 2018-12-17 | 29 | 0 | 114 | 160 | 100% | 0.18125 | 1 | Completed
ER6244LT | W220 | A9380 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier update and issue Fuel Storage Conditions EAN | 2018-07-10 | 2018-07-16 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A9630 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical review of Fuel Free Verification EAN | 2018-07-10 | 2018-09-24 | 15 | 0 | 53 | 76 | 100% | 0.19737 | 1 | Completed
ER6244LT | W220 | A3850 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Produce report on interlock changes req. for staggered operation of reactors, defuelling mode and FPUs back in reactor | 2018-07-10 | 2018-07-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.FS.A220.EH | REGION 1 Reactors Shutdown Safety Cases Programme | Assessm't of Other Faults - Preliminary fault schedule for a shutdown reactor, depressurised in CO2 (HPB, HNB) | 2018-07-13 | 2018-07-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.FS.A230.EH | REGION 1 Reactors Shutdown Safety Cases Programme | Assessm't of Other Faults - Preliminary fault schedule for a shutdown reactor, depressurised in CO2 (HYA, HAR) | 2018-07-13 | 2018-07-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.FS.A240.EH | REGION 1 Reactors Shutdown Safety Cases Programme | Assessm't of Other Faults - Consider faults with air atmosphere (HPB, HNB) | 2018-07-13 | 2018-07-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.FS.A250.EH | REGION 1 Reactors Shutdown Safety Cases Programme | Assessm't of Other Faults - Consider faults with air atmosphere (HYA, HAR) | 2018-07-13 | 2018-07-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A10940 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Update and issue Engineering Substantiation Report (HPB, HNB) | 2018-07-16 | 2018-12-17 | 10 | 0 | 109 | 154 | 100% | 0.064935 | 1 | Completed
ER6243LT | W200 | A15310 | REGION 1 Reactors Shutdown Safety Cases Programme | Draft Summary of supporting references Report Available for Review (HPB, HNB) | 2018-07-16 | 2018-07-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15550 | REGION 1 Reactors Shutdown Safety Cases Programme | Draft Summary of supporting references Report Available for Review (HYA, HAR) | 2018-07-16 | 2018-07-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16610 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Updated Defuelling Dataset Internally Verified by TSA | 2018-07-16 | 2018-09-03 | 5 | 0 | 35 | 49 | 100% | 0.10204 | 1 | Completed
ER6243LT | W200 | A16640 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Ageing & Degradation - Update and issue Engineering Substantiation Report (HPB, HNB) | 2018-07-16 | 2018-08-30 | 10 | 0 | 32 | 45 | 100% | 0.22222 | 1 | Completed
ER6244LT | W220 | A10450 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Update and Issue Optioneering Report for HPB/HNB | 2018-07-16 | 2018-08-10 | 5 | 0 | 20 | 25 | 100% | 0.2 | 1 | Completed
ER6244LT | W220 | A3050.C0 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Identify any Major Hardware Changes required for Gate B Submission | 2018-07-16 | 2018-07-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A10990 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Engineering Substantiation Report Technical Review by SQEP (HYA, HAR) | 2018-07-17 | 2018-07-30 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6243LT | W200 | A11660 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Systems - Update and issue Cooling Plant Availability (Optioneering) (HPB, HNB) | 2018-07-17 | 2018-07-24 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6243LT | W200 | A11710 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Systems - Update and issue Cooling Plant Availability (Optioneering) (HYA, HAR) | 2018-07-17 | 2018-07-24 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6243LT | W200 | A14190 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Update and issue Optioneering for CR and N2 systems (HPB, HNB) | 2018-07-17 | 2018-07-24 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6243LT | W200 | A14260 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Update and issue Optionnering for CR and N2 systems (HYA, HAR) | 2018-07-17 | 2018-07-24 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6243LT | W200 | A15320 | REGION 1 Reactors Shutdown Safety Cases Programme | Review & Acceptance of Summary of supporting references Report (HPB, HNB) | 2018-07-17 | 2018-08-21 | 10 | 0 | 25 | 35 | 100% | 0.28571 | 1 | Completed
ER6243LT | W200 | A15560 | REGION 1 Reactors Shutdown Safety Cases Programme | Review & Acceptance of Summary of supporting references Report (HYA, HAR) | 2018-07-17 | 2018-08-21 | 10 | 0 | 25 | 35 | 100% | 0.28571 | 1 | Completed
ER6244LT | W220 | A8610 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier update and issue Initial Fault Studies and Risk Estimation Report (HYA/HRA) | 2018-07-17 | 2018-08-01 | 12 | 0 | 12 | 15 | 100% | 0.8 | 1 | Completed
ER6244LT | W220 | A9390 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload Fuel Storage Conditions EAN to CDMS (HYA and HRA) | 2018-07-17 | 2018-07-25 | 7 | 0 | 7 | 8 | 100% | 0.875 | 1 | Completed
ER6244LT | W220 | A9910 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload Fuel Free Verification EAN to CDMS | 2018-07-19 | 2018-07-25 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6243LT | W200 | ER6243.A1000 | REGION 1 Reactors Shutdown Safety Cases Programme | Define Project Control Structures (WBS/CBS/OBS/PBS) | 2018-07-23 | 2018-07-23 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A1145 | REGION 1 Reactors Shutdown Safety Cases Programme | Workshop to agree scope, effort and links | 2018-07-23 | 2018-12-03 | 17 | 0 | 94 | 133 | 100% | 0.12782 | 1 | Completed
ER6243LT | W200 | ER6243.A1010 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Draft Project Definition Document (PDD) | 2018-07-24 | 2018-12-04 | 22 | 0 | 94 | 133 | 100% | 0.16541 | 1 | Completed
ER6243LT | W200 | RSSC.OC.A540.EA | REGION 1 Reactors Shutdown Safety Cases Programme | Principles of Fuel Free Verification - Issue of the Report onto CDMS (HPB, HNB) | 2018-07-25 | 2018-07-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.CNO.A160.EF | REGION 1 Reactors Shutdown Safety Cases Programme | Report identifying issues/ provide assurance that Carbon deposition with not be a problem during defuelling (HPB, HNB) | 2018-07-25 | 2018-07-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.CNO.A170.EF | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Systems - Report on clad sensitisation aspects (HPB, HNB) | 2018-07-25 | 2018-07-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.CNO.A190.EF | REGION 1 Reactors Shutdown Safety Cases Programme | Report identifying issues/ provide assurance that Carbon deposition with not be a problem during defuelling (HYA, HAR) | 2018-07-25 | 2018-07-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.CNO.A200.EF | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Systems - Report on clad sensitisation aspects (HYA, HAR) | 2018-07-25 | 2018-07-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A7170.EQ10 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Fuel Storage Conditions EAN available | 2018-07-25 | 2018-07-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A9920 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Fuel Free Verification EAN available | 2018-07-25 | 2018-07-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6650.EQ | REGION 1 Defuelling Programme Fuel Handling Safety Case | IFDF Defueling EAN available (HYA and HRA) | 2018-07-27 | 2018-07-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A7040.EQ | REGION 1 Defuelling Programme Fuel Handling Safety Case | Ponds and Flasks EAN available (HYA and HRA) | 2018-07-27 | 2018-07-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A7170.EQ | REGION 1 Defuelling Programme Fuel Handling Safety Case | Waste Vault Storage Capacity EAN available (HYA and HRA) | 2018-07-27 | 2018-07-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A10510 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Update and Issue Optioneering Report for HRA/HYA | 2018-07-30 | 2018-08-10 | 5 | 0 | 10 | 11 | 100% | 0.45455 | 1 | Completed
ER6244LT | W220 | A3700 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Decision on any changes to FM trip settings (HYA and HRA) | 2018-07-31 | 2018-07-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A12260 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Complete TR form and upload to CDMS (HPB, HNB) | 2018-07-31 | 2018-09-21 | 5 | 0 | 37 | 52 | 100% | 0.096154 | 1 | Completed
ER6243LT | W200 | A12300 | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Complete TR form and upload to CDMS (HYA, HAR) | 2018-07-31 | 2018-09-21 | 5 | 0 | 37 | 52 | 100% | 0.096154 | 1 | Completed
ER6243LT | W200 | A15630 | REGION 1 Reactors Shutdown Safety Cases Programme | Draft Human Factor Integration Plan EAN Available for Review (HPB, HNB) | 2018-07-31 | 2018-07-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15690 | REGION 1 Reactors Shutdown Safety Cases Programme | Draft Human Factors Integration Plan EAN Available for Review (HYA, HAR) | 2018-07-31 | 2018-07-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16580 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Updated Draft Summary Document Issued for Technical Review | 2018-07-31 | 2018-07-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16680 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Ageing & Degradation - Update and issue Engineering Substantiation Report (HYA, HAR) | 2018-07-31 | 2018-09-17 | 0 | 0 | 33 | 48 | 100% | 0 | 1 | Completed
ER6243LT | W200 | A11670 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Systems - Complete TR form and upload to CDMS (HPB, HNB) | 2018-08-01 | 2018-08-23 | 5 | 0 | 16 | 22 | 100% | 0.22727 | 1 | Completed
ER6243LT | W200 | A11720 | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Systems - Complete TR form and upload to CDMS (HYA, HAR) | 2018-08-01 | 2018-08-23 | 5 | 0 | 16 | 22 | 100% | 0.22727 | 1 | Completed
ER6244LT | W220 | A10010 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Fuelling Machine Light Load Protection & Interlocks EAN (HYA/HRA) issued for verification | 2018-08-01 | 2018-08-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5340 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload Refuelling Cooling Assessment EAN to CDMS | 2018-08-02 | 2018-08-31 | 21 | 0 | 20 | 29 | 100% | 0.72414 | 1 | Completed
ER6244LT | W220 | A8620 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload Initial Fault Studies and Risk Estimation Report to CDMS (HYA/HRA) | 2018-08-02 | 2018-09-03 | 0 | 0 | 22 | 32 | 100% | 0 | 1 | Completed
ER6244LT | W220 | A10020 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Verification of Fuelling Machine Light Load Protection & Interlocks EAN (HYA/HRA) | 2018-08-02 | 2018-08-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A10030 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Update and issue Fuelling Machine Light Load Protection & Interlocks EAN (HYA/HRA) | 2018-08-02 | 2018-08-15 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6244LT | W220 | A10550 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier Update and Issue OPR Cycle Times EAN | 2018-08-02 | 2018-08-03 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6243LT | W200 | A11830 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Thermal Hydraulics (MACE) Draft Summary Document Technical Review by SQEP (PH1) | 2018-08-06 | 2018-09-21 | 10 | 0 | 33 | 46 | 100% | 0.21739 | 1 | Completed
ER6244LT | W220 | A10560 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR Form and Upload OPR Cycle Times EAN to CDMS | 2018-08-06 | 2018-08-10 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6243LT | W200 | A10100 | REGION 1 Reactors Shutdown Safety Cases Programme | Initiate and Register EC and identify Milestones in AMS EC 363701 & 364023 (HPB, HNB) | 2018-08-10 | 2018-08-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A10270 | REGION 1 Reactors Shutdown Safety Cases Programme | Initiate and Register EC and identify Milestones in AMS EC 363682 & 363676 (HYA, HAR) | 2018-08-10 | 2018-08-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A10570 | REGION 1 Defuelling Programme Fuel Handling Safety Case | OPR Cycle Times EAN Available | 2018-08-10 | 2018-08-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11000 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Update and issue Engineering Substantiation Report (HYA, HAR) | 2018-08-13 | 2018-12-17 | 8 | 0 | 89 | 126 | 100% | 0.063492 | 1 | Completed
ER6244LT | W220 | A10460 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR Form and Upload Optioneering Report for HPB/HNB to CDMS | 2018-08-13 | 2018-08-17 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6244LT | W220 | A10520 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR Form and Upload Optioneering Report for HRA/HYA to CDMS | 2018-08-13 | 2018-08-17 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6243LT | W200 | A1230 | REGION 1 Reactors Shutdown Safety Cases Programme | Hold Case Conference as Appropriate (HPB, HNB) | 2018-08-14 | 2018-08-14 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A10380 | REGION 1 Reactors Shutdown Safety Cases Programme | Hold Case Conference as Appropriate (HYA, HAR) | 2018-08-14 | 2018-08-14 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A1260 | REGION 1 Reactors Shutdown Safety Cases Programme | Identify verifier for the case & establish all other resources (HPB, HNB) | 2018-08-14 | 2018-08-14 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15130 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Mapping Optioneering Specification (HPB, HNB)(Not Required as per DS 27.09.18) | 2018-08-14 | 2018-08-14 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15140 | REGION 1 Reactors Shutdown Safety Cases Programme | Mapping Optioneering Specification Agreed (HPB, HNB) (Not Required as per DS 27.09.18) | 2018-08-14 | 2018-08-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15150 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Mapping Optioneering Report (HPB, HNB) | 2018-08-14 | 2019-02-21 | 20 | 0 | 134 | 191 | 100% | 0.10471 | 1 | Completed
ER6243LT | W200 | A15370 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Mapping Optioneering Specification (HYA, HAR)(Not Required as per DS 27.09.18) | 2018-08-14 | 2018-08-14 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15380 | REGION 1 Reactors Shutdown Safety Cases Programme | Mapping Optioneering Specification Agreed (HYA, HAR)(Not Required as per DS 27.09.18) | 2018-08-14 | 2018-08-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15390 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Mapping Optioneering Report (HYA, HAR) | 2018-08-14 | 2019-02-21 | 20 | 0 | 133 | 191 | 100% | 0.10471 | 1 | Completed
ER6243LT | W200 | A15365 | REGION 1 Reactors Shutdown Safety Cases Programme | Mapping Optioneering - Summary (HYA, HAR) | 2018-08-14 | 2019-02-21 | 121 | 0 | 133 | 191 | 100% | 0.63351 | 1 | Completed
ER6243LT | W200 | A15125 | REGION 1 Reactors Shutdown Safety Cases Programme | Mapping Optioneering - Summary (HPB, HNB) | 2018-08-14 | 2019-02-21 | 101 | 0 | 134 | 191 | 100% | 0.5288 | 1 | Completed
ER6244LT | W220 | A10050 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Fuelling Machine Light Load Protection & Interlocks EAN (HYA/HRA) available | 2018-08-15 | 2018-08-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A14200 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Complete TR form and upload to CDMS (HPB, HNB) | 2018-08-17 | 2018-08-31 | 5 | 0 | 9 | 14 | 100% | 0.35714 | 1 | Completed
ER6243LT | W200 | A14270 | REGION 1 Reactors Shutdown Safety Cases Programme | Ops Compliance - Complete TR form and upload to CDMS (HYA, HAR) | 2018-08-17 | 2018-08-31 | 5 | 0 | 9 | 14 | 100% | 0.35714 | 1 | Completed
ER6244LT | W220 | A6260.EQ | REGION 1 Defuelling Programme Fuel Handling Safety Case | Buffer Store Defueling EAN available (HPB and HNB) | 2018-08-17 | 2018-08-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6390.EQ | REGION 1 Defuelling Programme Fuel Handling Safety Case | IFDF Defueling EAN available (HPB and HNB) | 2018-08-17 | 2018-08-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6780.EQ | REGION 1 Defuelling Programme Fuel Handling Safety Case | Ponds and Flasks EAN available (HPB and HNB) | 2018-08-17 | 2018-08-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A6910.EQ | REGION 1 Defuelling Programme Fuel Handling Safety Case | Waste Vault Storage Capacity EAN available (HPB and HNB) | 2018-08-17 | 2018-08-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A10470 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Optioneering Report for HPB/HNB Available | 2018-08-17 | 2018-08-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A10530 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Optioneering Report for HRA/HYA Available | 2018-08-17 | 2018-08-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A1020 | REGION 1 Reactors Shutdown Safety Cases Programme | Initial Categorisation by Station (HPB, HNB) | 2018-08-21 | 2018-08-28 | 1 | 0 | 4 | 7 | 100% | 0.14286 | 1 | Completed
ER6243LT | W200 | A13250 | REGION 1 Reactors Shutdown Safety Cases Programme | Summary of supporting references required for safety case Issued to CDMS (HPB, HNB) | 2018-08-21 | 2018-08-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A13260 | REGION 1 Reactors Shutdown Safety Cases Programme | Summary of supporting references required for safety case issued to CDMS (HYA, HAR) | 2018-08-21 | 2018-08-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A10320 | REGION 1 Reactors Shutdown Safety Cases Programme | Initial Categorisation by Station (HYA, HAR) | 2018-08-22 | 2018-10-29 | 1 | 0 | 47 | 68 | 100% | 0.014706 | 1 | Completed
ER6244LT | W220 | A10600 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier Update and Issue Review of Off-Load Pressurised Refuelling Safety Case for Defuelling | 2018-08-22 | 2018-08-28 | 5 | 0 | 3 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A10990 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete requisition approval and issue CI for Updated EoG Initial Fault Studies and Risk Estimation Report | 2018-08-22 | 2018-08-22 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.CNO.A150.EF | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Systems - Options for Cooling Post Shutdown - Report (HPB, HNB) | 2018-08-23 | 2018-08-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.CNO.A180.EF | REGION 1 Reactors Shutdown Safety Cases Programme | Cooling Systems - Options for Cooling Post Shutdown - Report (HYA, HAR) | 2018-08-23 | 2018-08-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15770 | REGION 1 Reactors Shutdown Safety Cases Programme | Review NSP's for Shutdown Cooling Safety CasesReport Issued to CDMS (HPB, HNB) (Not Req'd move to Post Gate B) | 2018-08-23 | 2018-08-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15830 | REGION 1 Reactors Shutdown Safety Cases Programme | Review NSP's for Shutdown Cooling Safety CasesReport Issued to CDMS (HYA, HAR)(Not Req'd move to Post Gate B) | 2018-08-23 | 2018-08-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A11000 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier Mobilisation | 2018-08-23 | 2018-08-24 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6244LT | W220 | A11010 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Pre Job Brief for Updated EoG Initial Fault Studies and Risk Estimation Report | 2018-08-28 | 2018-08-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A11020 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Updated EoG Initial Fault Studies and Risk Estimation Report | 2018-08-28 | 2018-10-05 | 35 | 0 | 29 | 38 | 100% | 0.92105 | 1 | Completed
ER6244LT | W220 | A10610 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR Form and Upload Review of Off-Load Pressurised Refuelling Safety Case for Defuelling to CDMS | 2018-08-29 | 2018-08-29 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A10620 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Review of Off-Load Pressurised Refuelling Safety Case for Defuelling Available | 2018-08-29 | 2018-08-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A13390 | REGION 1 Reactors Shutdown Safety Cases Programme | Optionnering for CR and N2 systems to meet shutdown and holddown requirements (HPB, HNB) | 2018-08-31 | 2018-08-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A13400 | REGION 1 Reactors Shutdown Safety Cases Programme | Optionnering for CR and N2 systems to meet shutdown and holddown requirements (HYA, HAR) | 2018-08-31 | 2018-08-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5350.EC | REGION 1 Defuelling Programme Fuel Handling Safety Case | Refuelling Cooling Assessment EAN available | 2018-08-31 | 2018-08-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A1080 | REGION 1 Reactors Shutdown Safety Cases Programme | Produce draft NSRS (using BARRIER MODEL) (HPB, HNB) | 2018-09-03 | 2018-10-24 | 6 | 0 | 37 | 51 | 100% | 0.11765 | 1 | Completed
ER6243LT | W200 | A10200 | REGION 1 Reactors Shutdown Safety Cases Programme | Produce draft NSRS (using BARRIER MODEL) (HYA, HAR) | 2018-09-03 | 2018-10-24 | 6 | 0 | 37 | 51 | 100% | 0.11765 | 1 | Completed
ER6243LT | W200 | A15640 | REGION 1 Reactors Shutdown Safety Cases Programme | Review & Acceptance of Human Factor Integration Plan EAN (HPB, HNB) | 2018-09-03 | 2018-12-20 | 20 | 0 | 78 | 108 | 100% | 0.18519 | 1 | Completed
ER6243LT | W200 | A15700 | REGION 1 Reactors Shutdown Safety Cases Programme | Review & Acceptance of Draft Human Factors Integration Plan EAN (HYA, HAR) | 2018-09-03 | 2018-12-20 | 20 | 0 | 78 | 108 | 100% | 0.18519 | 1 | Completed
ER6243LT | W200 | A16620 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Updated Defuelling Dataset Issued for Technical Review | 2018-09-03 | 2018-09-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16650 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Ageing & Degradation - Complete TR form and upload to CDMS (HPB, HNB) | 2018-09-03 | 2018-09-05 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6244LT | W220 | A8630 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Initial Fault Studies and Risk Estimation Report available (HYA/HRA) | 2018-09-03 | 2018-09-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5200 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Amec update and issue CO2 purity and decay heat report | 2018-09-04 | 2018-09-12 | 7 | 0 | 7 | 8 | 100% | 0.875 | 1 | Completed
ER6243LT | W200 | A11890 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Thermal Hydraulics (MACE) Calculations Report Technical Review by SQEP (PH2) | 2018-09-04 | 2018-09-17 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6243LT | W200 | A16660 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Ageing & Degradation - Engineering Substantiation Report Completed (HPB, HNB) | 2018-09-05 | 2018-09-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16730 | REGION 1 Reactors Shutdown Safety Cases Programme | Draft Support System Report (HPB, HNB) | 2018-09-07 | 2019-01-31 | 50 | 0 | 101 | 146 | 100% | 0.34247 | 1 | Completed
ER6243LT | W200 | A16760 | REGION 1 Reactors Shutdown Safety Cases Programme | Draft Support System Report (HYA, HAR) | 2018-09-07 | 2019-07-22 | 50 | 0 | 219 | 318 | 100% | 0.15723 | 1 | Completed
ER6244LT | W220 | A5210 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload CO2 purity and decay heat report to CDMS | 2018-09-13 | 2018-09-26 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6243LT | W200 | A16690 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Ageing & Degradation - Complete TR form and upload to CDMS (HYA, HAR) | 2018-09-18 | 2018-09-20 | 3 | 0 | 2 | 2 | 100% | 1.5 | 1 | Completed
ER6243LT | W200 | A11900 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Update and issue Defuelling Dataset (PH2) | 2018-09-18 | 2018-09-27 | 10 | 0 | 7 | 9 | 100% | 1.1111 | 1 | Completed
ER6243LT | W200 | A16700 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Ageing & Degradation - Engineering Substantiation Report Completed (HYA, HAR) | 2018-09-20 | 2018-09-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A3080.E0 | REGION 1 Reactors Shutdown Safety Cases Programme | Complete Optioneering Design of Safety Cases (HPB, HNB) | 2018-09-21 | 2018-09-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.RCS.A290.EK | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Impact Assessment Report & C&I BoD for plant modifications Completed. (HPB, HNB) | 2018-09-21 | 2018-09-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.RCS.A310.EK | REGION 1 Reactors Shutdown Safety Cases Programme | RCS Basis of Design - Impact Assessment Report & C&I BoD for plant modifications Completed. (HYA, HAR) | 2018-09-21 | 2018-09-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A10410.E0 | REGION 1 Reactors Shutdown Safety Cases Programme | Complete Optioneering Design of Safety Cases (HYA, HAR) | 2018-09-21 | 2018-09-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A13150.C0 | REGION 1 Reactors Shutdown Safety Cases Programme | Preferred Technical Strategy Endorsed by the Programme Board (HPB, HNB) | 2018-09-21 | 2018-09-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A13160.C0 | REGION 1 Reactors Shutdown Safety Cases Programme | Preferred Technical Strategy Endorsed by the Programme Board (HYA, HAR) | 2018-09-21 | 2018-09-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16460 | REGION 1 Reactors Shutdown Safety Cases Programme | Optioneering of the Defuelling Preparations Programme Completed | 2018-09-21 | 2018-09-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11840 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Update and issue Thermal Hydraulics (MACE) Draft Summary Document (PH1) | 2018-09-24 | 2018-09-27 | 10 | 0 | 3 | 3 | 100% | 3.3333 | 1 | Completed
ER6243LT | W200 | A16290 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Calcs Spec & Model Development Report Completed (PH3)(Not Req'd 24.09.18 as per DS) | 2018-09-24 | 2018-09-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16300 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Draft Calcs Spec & Model Development Report verified and issued for TR(PH3) | 2018-09-24 | 2018-09-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16310 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Calcs Spec & Model Development Report TR by SQEP (PH3)(Not Req'd 24.09.18 as per DS) | 2018-09-24 | 2018-09-24 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16320 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Update and issue Calcs Spec & Model Development Report (PH3)(Not Req'd 24.09.18 as per DS) | 2018-09-24 | 2018-09-24 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16330 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Complete TR form and upload to CDMS (PH3)(Not Req'd 24.09.18 as per DS) | 2018-09-24 | 2018-09-24 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16340 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Develop (MACE) Calcs Spec & Model Development Report (PH3)(Not Req'd 24.09.18 as per DS) | 2018-09-24 | 2018-09-24 | 20 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A9640 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier update and issue Fuel Free Verification EAN | 2018-09-25 | 2018-09-27 | 3 | 0 | 2 | 2 | 100% | 1.5 | 1 | Completed
ER6244LT | W220 | A3080.E0 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete Optioneering Design of Safety Cases | 2018-09-26 | 2018-09-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A5220.EC | REGION 1 Defuelling Programme Fuel Handling Safety Case | CO2 purity and decay heat report available | 2018-09-26 | 2018-09-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15160 | REGION 1 Reactors Shutdown Safety Cases Programme | Draft Mapping Optioneering Report Available for Review (HPB, HNB)(Not Required as per DS 27.09.18) | 2018-09-27 | 2018-09-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15170 | REGION 1 Reactors Shutdown Safety Cases Programme | Review & Acceptance of Mapping Optioneering Report (HPB, HNB)(Not Required as per DS 27.09.18) | 2018-09-27 | 2018-09-27 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15400 | REGION 1 Reactors Shutdown Safety Cases Programme | Draft Mapping Optioneering Report Available for Review (HYA, HAR) (Not Required as per DS 27.09.18) | 2018-09-27 | 2018-09-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15410 | REGION 1 Reactors Shutdown Safety Cases Programme | Review & Acceptance of Mapping Optioneering Report (HYA, HAR) (Not Required as per DS 27.09.18) | 2018-09-27 | 2018-09-27 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A9750 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Fuel Free Verification EAN verified and issued for technical review | 2018-09-27 | 2018-09-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.OC.A550.EA | REGION 1 Reactors Shutdown Safety Cases Programme | Principles of Fuel Free Verification - Issue of the Report onto CDMS (HYA, HAR) | 2018-09-28 | 2018-09-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A9650 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload Fuel Free Verification EAN to CDMS | 2018-09-28 | 2018-09-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A9760 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical review of Fuel Free Verification EAN | 2018-09-28 | 2019-03-08 | 20 | 0 | 113 | 161 | 100% | 0.12422 | 1 | Completed
ER6244LT | W220 | A9660 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Fuel Free Verification EAN available | 2018-09-28 | 2018-09-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A1030 | REGION 1 Reactors Shutdown Safety Cases Programme | Appoint CO & CA (HPB, HNB) | 2018-10-01 | 2018-10-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A1050.E0 | REGION 1 Reactors Shutdown Safety Cases Programme | Gate EC1 completed EC 363701/364023 <NSRS SC Approach & Outline> (Cat 1 Milestone) (HPB, HNB) | 2018-10-01 | 2018-10-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A1250 | REGION 1 Reactors Shutdown Safety Cases Programme | Hold project kick start meeting with Station & key suppliers (HPB, HNB) (Not Req'd until after Gate B) | 2018-10-01 | 2018-10-01 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A1240 | REGION 1 Reactors Shutdown Safety Cases Programme | Create EC Definition Document if not part of Project Definition Document (363701) (HPB, HNB) (See PDD) | 2018-10-01 | 2018-10-01 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A12580 | REGION 1 Reactors Shutdown Safety Cases Programme | Hold project kick start meeting with Station & key suppliers (HYA, HAR) | 2018-10-01 | 2018-10-01 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A12590 | REGION 1 Reactors Shutdown Safety Cases Programme | Create EC Definition Document if not part of Project Definition Document (363676) (HYA, HAR) | 2018-10-01 | 2018-10-01 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16380 | REGION 1 Reactors Shutdown Safety Cases Programme | Draft Environmental Aspect/Impact & Waste Management Assessment Form (HPB, HNB) | 2018-10-01 | 2018-10-02 | 10 | 0 | 2 | 1 | 100% | 10 | 1 | Completed
ER6243LT | W200 | A16420 | REGION 1 Reactors Shutdown Safety Cases Programme | Draft Environmental Aspect/Impact & Waste Management Assessment Form (HYA, HAR) | 2018-10-01 | 2018-10-02 | 10 | 0 | 2 | 1 | 100% | 10 | 1 | Completed
ER6244LT | W220 | A3220 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Hold Case Conference as Appropriate | 2018-10-01 | 2018-10-05 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6244LT | W220 | A10915.EJ | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Dropped FPU impact on Core Support Structure Report (HYA and HRA) verified and issued for technical review | 2018-10-01 | 2018-10-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A1070 | REGION 1 Reactors Shutdown Safety Cases Programme | CA to agree with CO format of the safety case (HPB, HNB) | 2018-10-02 | 2018-10-03 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6244LT | W220 | A10920 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical review of Dropped FPU impact on Core Support Structure Report (HYA and HRA) | 2018-10-02 | 2018-10-18 | 13 | 0 | 13 | 16 | 100% | 0.8125 | 1 | Completed
ER6244LT | W220 | A11030 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Updated EoG Initial Fault Studies and Risk Estimation Report Verified and Issued for Technical Review | 2018-10-05 | 2018-10-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A11040 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical Review of Updated EoG Initial Fault Studies and Risk Estimation Report | 2018-10-08 | 2018-10-18 | 9 | 0 | 9 | 10 | 100% | 0.9 | 1 | Completed
ER6243LT | W200 | A16790 | REGION 1 Reactors Shutdown Safety Cases Programme | Issue Draft Station resourced Plans for Review | 2018-10-10 | 2018-10-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16860 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Pre Job Brief | 2018-10-10 | 2018-10-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16390 | REGION 1 Reactors Shutdown Safety Cases Programme | GEM & Case Officer review of Draft Environmental Aspect/Impact & Waste Management Assessment Form (HPB, HNB) | 2018-10-11 | 2018-11-23 | 10 | 0 | 31 | 43 | 100% | 0.23256 | 1 | Completed
ER6243LT | W200 | A16430 | REGION 1 Reactors Shutdown Safety Cases Programme | GEM & Case Officer review of Draft Environmental Aspect/Impact & Waste Management Assessment Form (HYA, HAR) | 2018-10-11 | 2018-11-23 | 10 | 0 | 31 | 43 | 100% | 0.23256 | 1 | Completed
ER6243LT | W200 | A16870 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Generate Requested Data using the MACE Model | 2018-10-11 | 2018-10-23 | 10 | 0 | 9 | 12 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A11050 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier update and issue Updated EoG Initial Fault Studies and Risk Estimation Report | 2018-10-19 | 2018-10-26 | 6 | 0 | 6 | 7 | 100% | 0.85714 | 1 | Completed
ER6378LT | W222 | W222.A1090 | HRA Fuel Handling Essential Safety Case | Station comments on NSRS | 2018-10-19 | 2018-11-05 | 12 | 0 | 12 | 17 | 100% | 0.70588 | 1 | Completed
ER6378LT | W222 | W222.A1100 | HRA Fuel Handling Essential Safety Case | DA (Peer) comments on NSRS | 2018-10-19 | 2018-11-05 | 12 | 0 | 12 | 17 | 100% | 0.70588 | 1 | Completed
ER6378LT | W222 | W222.A3230 | HRA Fuel Handling Essential Safety Case | INA comments on NSRS | 2018-10-19 | 2019-03-29 | 113 | 0 | 112 | 161 | 100% | 0.70186 | 1 | Completed
ER6378LT | W222 | W222.A8140 | HRA Fuel Handling Essential Safety Case | Draft NSRS Produced for HRA and HYA (using BARRIER model) | 2018-10-19 | 2018-10-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A8140 | HYA Fuel Handling Essential Safety Case | Draft NSRS Produced for HYA and HYA (using BARRIER model) | 2018-10-19 | 2018-10-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A3230 | HYA Fuel Handling Essential Safety Case | INA comments on NSRS | 2018-10-19 | 2019-03-29 | 113 | 0 | 112 | 161 | 100% | 0.70186 | 1 | Completed
ER6650LT | W226 | W226.A1100 | HYA Fuel Handling Essential Safety Case | DA (Peer) comments on NSRS | 2018-10-19 | 2018-11-05 | 12 | 0 | 12 | 17 | 100% | 0.70588 | 1 | Completed
ER6650LT | W226 | W226.A1090 | HYA Fuel Handling Essential Safety Case | Station comments on NSRS | 2018-10-19 | 2018-11-05 | 12 | 0 | 12 | 17 | 100% | 0.70588 | 1 | Completed
ER6244LT | W220 | A8140 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft NSRS Produced for HPB and HNB (using BARRIER model) | 2018-10-19 | 2018-10-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8150 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft NSRS Produced for HYA and HRA (using BARRIER model) | 2018-10-19 | 2018-10-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8160.E0 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft NSRS Produced for HPB and HNB (using BARRIER model) | 2018-10-19 | 2018-10-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8170.E0 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft NSRS Produced for HYA and HRA (using BARRIER model) | 2018-10-19 | 2018-10-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A1090 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Station comments on NSRS | 2018-10-22 | 2018-12-17 | 15 | 0 | 41 | 56 | 100% | 0.26786 | 1 | Completed
ER6244LT | W220 | A1100 | REGION 1 Defuelling Programme Fuel Handling Safety Case | DA (Peer) comments on NSRS | 2018-10-22 | 2018-12-17 | 15 | 0 | 41 | 56 | 100% | 0.26786 | 1 | Completed
ER6244LT | W220 | A3240 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Incorporate INA, Station, DA (peer) comments | 2018-10-22 | 2019-05-29 | 15 | 0 | 150 | 219 | 100% | 0.068493 | 1 | Completed
ER6244LT | W220 | A3230 | REGION 1 Defuelling Programme Fuel Handling Safety Case | INA comments on NSRS | 2018-10-22 | 2019-03-29 | 15 | 0 | 112 | 158 | 100% | 0.094937 | 1 | Completed
ER6244LT | W220 | A3340 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Station comments on NSRS | 2018-10-22 | 2018-12-17 | 50 | 0 | 41 | 56 | 100% | 0.89286 | 1 | Completed
ER6244LT | W220 | A3350 | REGION 1 Defuelling Programme Fuel Handling Safety Case | DA (Peer) comments on NSRS | 2018-10-22 | 2018-12-17 | 50 | 0 | 41 | 56 | 100% | 0.89286 | 1 | Completed
ER6244LT | W220 | A3410 | REGION 1 Defuelling Programme Fuel Handling Safety Case | INA comments on NSRS | 2018-10-22 | 2019-03-29 | 50 | 0 | 112 | 158 | 100% | 0.31646 | 1 | Completed
ER6244LT | W220 | A10180 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier update and issue Review of Rad Cons for Lower Decay Heat for Input into PSA | 2018-10-22 | 2018-10-26 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6243LT | W200 | A16880 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Interim Progress Meeting | 2018-10-23 | 2018-10-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A13030.E0 | REGION 1 Reactors Shutdown Safety Cases Programme | Draft NSRS Produced Ready for Review and Approval (using BARRIER MODEL) (HPB, HNB) | 2018-10-24 | 2018-10-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A13040.E0 | REGION 1 Reactors Shutdown Safety Cases Programme | Draft NSRS Produced Ready for Review and Approval(using BARRIER MODEL) (HYA, HAR) | 2018-10-24 | 2018-10-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16890 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Update the Analysis and Produce QA Grade 2 Technical Note | 2018-10-24 | 2018-11-09 | 10 | 0 | 12 | 16 | 100% | 0.625 | 1 | Completed
ER6243LT | W200 | A1090 | REGION 1 Reactors Shutdown Safety Cases Programme | Station comments on NSRS (HPB, HNB) | 2018-10-25 | 2018-12-03 | 10 | 0 | 27 | 39 | 100% | 0.25641 | 1 | Completed
ER6243LT | W200 | A1100 | REGION 1 Reactors Shutdown Safety Cases Programme | DA (Peer) comments on NSRS (HPB, HNB) | 2018-10-25 | 2018-11-14 | 10 | 0 | 14 | 20 | 100% | 0.5 | 1 | Completed
ER6244LT | W220 | A11060 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload Updated EoG Initial Fault Studies and Risk Estimation Report to CDMS | 2018-10-26 | 2018-10-26 | 3 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A3060.C0 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Develop HPB HNB Detailed Costing and Schedules for Future Phases (Post Gate B) | 2018-10-26 | 2018-10-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A11070 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Updated EoG Initial Fault Studies and Risk Estimation Report Available | 2018-10-26 | 2018-10-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A10300 | REGION 1 Reactors Shutdown Safety Cases Programme | Appoint CO & CA (HYA, HAR) | 2018-10-29 | 2018-10-29 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A10350.E0 | REGION 1 Reactors Shutdown Safety Cases Programme | Gate EC1 completed EC 363676/363682 <NSRS SC Approach & Outline> (Cat 1 Milestone) (HYA, HAR) | 2018-10-29 | 2018-10-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A10190 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload Review of Rad Cons for Lower Decay Heat for Input into PSA to CDMS | 2018-10-29 | 2019-01-18 | 4 | 0 | 57 | 81 | 100% | 0.049383 | 1 | Completed
ER6243LT | W200 | A10220 | REGION 1 Reactors Shutdown Safety Cases Programme | DA (Peer) comments on NSRS (HYA, HAR) | 2018-11-01 | 2018-11-14 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6243LT | W200 | A11850 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Complete TR form and upload to CDMS (PH1) | 2018-11-01 | 2018-11-07 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6243LT | W200 | A11910 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Complete TR form and upload to CDMS (PH2) | 2018-11-01 | 2018-11-07 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6243LT | W200 | A10210 | REGION 1 Reactors Shutdown Safety Cases Programme | Station comments on NSRS (HYA, HAR) | 2018-11-05 | 2018-12-03 | 10 | 0 | 20 | 28 | 100% | 0.35714 | 1 | Completed
ER6243LT | W200 | ER6243.A1020 | REGION 1 Reactors Shutdown Safety Cases Programme | Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 2018-11-05 | 2018-12-07 | 5 | 0 | 24 | 32 | 100% | 0.15625 | 1 | Completed
ER6243LT | W200 | ER6243.A1030 | REGION 1 Reactors Shutdown Safety Cases Programme | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 2018-11-05 | 2018-12-07 | 5 | 0 | 24 | 32 | 100% | 0.15625 | 1 | Completed
ER6243LT | W200 | A11920 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Defuelling Dataset to Support Optioneering / Decision Making Completed (PH2) | 2018-11-07 | 2018-11-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11860 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Thermal Hydraulics (MACE) Draft Summary Document Completed for (PH1) | 2018-11-07 | 2018-11-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A17220 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Update the Analysis and Produce QA Grade 2 TSA Verification | 2018-11-12 | 2018-12-10 | 1 | 0 | 20 | 28 | 100% | 0.035714 | 1 | Completed
ER6243LT | W200 | A16810 | REGION 1 Reactors Shutdown Safety Cases Programme | EDF Review / Verify Station Plans (HPB) (Transfer to W282 Workpack) | 2018-11-19 | 2019-03-05 | 10 | 0 | 73 | 106 | 100% | 0.09434 | 1 | Completed
ER6243LT | W200 | A17190 | REGION 1 Reactors Shutdown Safety Cases Programme | EDF Review / Verify Station Plans (HNB) (Transfer to W282 Workpack) | 2018-11-19 | 2019-03-05 | 10 | 0 | 73 | 106 | 100% | 0.09434 | 1 | Completed
ER6243LT | W200 | A10110 | REGION 1 Reactors Shutdown Safety Cases Programme | SRD comments on NSRS (HPB, HNB) | 2018-12-03 | 2019-04-01 | 10 | 0 | 83 | 119 | 100% | 0.084034 | 1 | Completed
ER6243LT | W200 | A10330 | REGION 1 Reactors Shutdown Safety Cases Programme | SRD comments on NSRS (HYA, HAR) | 2018-12-03 | 2019-04-01 | 10 | 0 | 82 | 119 | 100% | 0.084034 | 1 | Completed
ER6244LT | W220 | A4490 | REGION 1 Defuelling Programme Fuel Handling Safety Case | P20.01.01.22 - Decommissioning Phase | 2018-12-03 | 2018-12-31 | 19 | 0 | 19 | 28 | 100% | 0.67857 | 1 | Completed
ER6370LT | W201 | ER6370.A1250 | HNB Reactors Shutdown Essential Safety Cases | Confirm Objectives to be Delivered at Gate B | 2018-12-03 | 2018-12-04 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | ER6370.A13000 | HNB Reactors Shutdown Essential Safety Cases | Phase 2 Accelerated Start [FEEDS TO SUMMARY SCHEDULE] | 2018-12-03 | 2018-12-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A17320 | HNB Reactors Shutdown Essential Safety Cases | Actuals (PS-29-Feb-2020) | 2018-12-03 | 2020-03-02 | 314 | 0 | 314 | 455 | 100% | 0.69011 | 1 | Completed
ER6370LT | W201 | A1010 | HNB Reactors Shutdown Essential Safety Cases | Summary for HNB Reactors Shutdown Essential Safety Cases W201 | 2018-12-03 | 2022-08-23 | 1 | 0 | 939 | 1359 | 100% | 0.00073584 | 1 | Completed
ER6370LT | W201 | ER6370.A1260 | HNB Reactors Shutdown Essential Safety Cases | Initial high level scope of programme | 2018-12-05 | 2018-12-05 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1020 | HNB Reactors Shutdown Essential Safety Cases | Define Project Control Structures (WBS/CBS/OBS/PBS) | 2018-12-06 | 2018-12-07 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | ER6370.A1110 | HNB Reactors Shutdown Essential Safety Cases | Prepare Draft Project Definition Document (PDD) | 2018-12-06 | 2018-12-10 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6243LT | W200 | A10140 | REGION 1 Reactors Shutdown Safety Cases Programme | Station agree NSRS (HPB, HNB) | 2018-12-10 | 2018-12-11 | 10 | 0 | 1 | 1 | 100% | 10 | 1 | Completed
ER6243LT | W200 | A10240 | REGION 1 Reactors Shutdown Safety Cases Programme | Station agree NSRS (HYA, HAR) | 2018-12-10 | 2018-12-11 | 10 | 0 | 1 | 1 | 100% | 10 | 1 | Completed
ER6243LT | W200 | ER6243.A1040 | REGION 1 Reactors Shutdown Safety Cases Programme | Ensure Alignment of Schedule & Estimate | 2018-12-10 | 2018-12-10 | 2 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1050 | REGION 1 Reactors Shutdown Safety Cases Programme | Hold Risk Workshop | 2018-12-10 | 2018-12-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16900 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Submit QA Grade 2 Technical Note for Technical Review | 2018-12-10 | 2018-12-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A3060.C0 | REGION 1 Reactors Shutdown Safety Cases Programme | Develop Detailed Costing and Schedules for Future Phases (Post Gate B) | 2018-12-11 | 2018-12-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1060 | REGION 1 Reactors Shutdown Safety Cases Programme | Complete Risk Log with Estimates | 2018-12-11 | 2018-12-11 | 2 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1070 | REGION 1 Reactors Shutdown Safety Cases Programme | Update Schedule/Estimate from Risk Log & Add Provisions | 2018-12-11 | 2018-12-11 | 2 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1080 | REGION 1 Reactors Shutdown Safety Cases Programme | Add Data to IRM Paper | 2018-12-11 | 2018-12-11 | 2 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1090 | REGION 1 Reactors Shutdown Safety Cases Programme | PCL Validate & Approve Baseline Package for PRC Submission | 2018-12-11 | 2018-12-11 | 3 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1030 | HNB Reactors Shutdown Essential Safety Cases | Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 2018-12-13 | 2018-12-14 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | ER6370.A1040 | HNB Reactors Shutdown Essential Safety Cases | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 2018-12-13 | 2018-12-14 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | ER6370.A1270 | HNB Reactors Shutdown Essential Safety Cases | Workshop to agree scope, effort and links | 2018-12-13 | 2018-12-14 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6243LT | W200 | A3020.C0 | REGION 1 Reactors Shutdown Safety Cases Programme | Confirm scope post gate 2 | 2018-12-14 | 2018-12-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1100 | REGION 1 Reactors Shutdown Safety Cases Programme | Gate B PRC Paper Submission | 2018-12-14 | 2018-12-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A10110 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier update and issue Dropped FPU RadCons Analysis of Core Support Plate Failure | 2018-12-17 | 2019-02-15 | 14 | 0 | 42 | 60 | 100% | 0.23333 | 1 | Completed
ER6370LT | W201 | ER6370.A1050 | HNB Reactors Shutdown Essential Safety Cases | Ensure Alignment of Schedule & Estimate | 2018-12-17 | 2018-12-18 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | ER6370.A1060 | HNB Reactors Shutdown Essential Safety Cases | Hold Risk Workshop | 2018-12-17 | 2018-12-17 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A10300 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Review of Plant Requirements for Defuelling verified and issued for technical review | 2018-12-17 | 2018-12-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A10370 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Draft Review of Safety Case Limits & LOLER Inspection Requirements verified and issued for technical review | 2018-12-17 | 2018-12-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A11010 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Complete TR form and upload to CDMS (HYA, HAR) | 2018-12-18 | 2019-03-19 | 10 | 0 | 62 | 91 | 100% | 0.10989 | 1 | Completed
ER6243LT | W200 | A10950 | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Complete TR form and upload to CDMS (HPB, HNB) | 2018-12-18 | 2019-03-19 | 10 | 0 | 62 | 91 | 100% | 0.10989 | 1 | Completed
ER6244LT | W220 | A10380 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Technical review of Review of Safety Case Limits & LOLER Inspection Requirements | 2018-12-18 | 2019-01-24 | 30 | 0 | 25 | 37 | 100% | 0.81081 | 1 | Completed
ER6370LT | W201 | ER6370.A1070 | HNB Reactors Shutdown Essential Safety Cases | Complete Risk Log with Estimates | 2018-12-18 | 2018-12-19 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6243LT | W200 | A15650 | REGION 1 Reactors Shutdown Safety Cases Programme | Human Factor Integration Plan EAN Issued to CDMS (HPB, HNB) | 2018-12-20 | 2018-12-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A15710 | REGION 1 Reactors Shutdown Safety Cases Programme | Draft Human Factors Integration Plan EAN Issued to CDMS (HYA, HAR) | 2018-12-20 | 2018-12-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1080 | HNB Reactors Shutdown Essential Safety Cases | Update Schedule/Estimate from Risk Log & Add Provisions | 2018-12-20 | 2018-12-21 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | ER6370.A1090 | HNB Reactors Shutdown Essential Safety Cases | Add Data to IRM Paper | 2018-12-24 | 2018-12-27 | 2 | 0 | 2 | 3 | 100% | 0.66667 | 1 | Completed
ER6370LT | W201 | ER6370.A1100 | HNB Reactors Shutdown Essential Safety Cases | PCL Validate & Approve Baseline Package for PRC Submission | 2018-12-28 | 2019-01-02 | 3 | 0 | 3 | 5 | 100% | 0.6 | 1 | Completed
ER6243LT | W200 | A16440 | REGION 1 Reactors Shutdown Safety Cases Programme | Issue Environmental Aspect/Impact & Waste Management Assessment Form (HYA, HAR) | 2019-01-02 | 2019-01-16 | 3 | 0 | 10 | 14 | 100% | 0.21429 | 1 | Completed
ER6370LT | W201 | ER6370.A7690 | HNB Reactors Shutdown Essential Safety Cases | Safety Case Strategy Development Meetings | 2019-01-02 | 2019-02-13 | 31 | 0 | 31 | 42 | 100% | 0.7381 | 1 | Completed
ER6370LT | W201 | ER6370.A10515 | HNB Reactors Shutdown Essential Safety Cases | Start of Environmental Permitting and Permissioing Scoping and Stakeholder Engagement | 2019-01-02 | 2019-01-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A10710 | HNB Reactors Shutdown Essential Safety Cases | Scoping of Implementation ECs B-C | 2019-01-02 | 2019-11-29 | 233 | 0 | 232 | 331 | 100% | 0.70393 | 1 | Completed
ER6370LT | W201 | ER6370.A10720 | HNB Reactors Shutdown Essential Safety Cases | Prepare Current Code Applicability Range | 2019-01-02 | 2019-01-31 | 22 | 0 | 22 | 29 | 100% | 0.75862 | 1 | Completed
ER6370LT | W201 | ER6370.A10800 | HNB Reactors Shutdown Essential Safety Cases | Prepare Scope Codes and Methods Options and Validation | 2019-01-02 | 2019-01-31 | 22 | 0 | 22 | 29 | 100% | 0.75862 | 1 | Completed
ER6370LT | W201 | ER6370.A10990 | HNB Reactors Shutdown Essential Safety Cases | Prepare SDM Assumptions Document Draft Report | 2019-01-02 | 2019-01-15 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6370LT | W201 | ER6370.A10715 | HNB Reactors Shutdown Essential Safety Cases | Current Code Applicability Range Summary | 2019-01-02 | 2019-04-30 | 82 | 0 | 82 | 118 | 100% | 0.69492 | 1 | Completed
ER6370LT | W201 | ER6370.A10795 | HNB Reactors Shutdown Essential Safety Cases | Scope Codes and Methods Options and Validation Summary | 2019-01-02 | 2019-03-15 | 53 | 0 | 53 | 72 | 100% | 0.73611 | 1 | Completed
ER6370LT | W201 | ER6370.A10985 | HNB Reactors Shutdown Essential Safety Cases | SDM Assumptions Document Summary | 2019-01-02 | 2019-06-03 | 104 | 0 | 104 | 152 | 100% | 0.68421 | 1 | Completed
ER6370LT | W201 | ER6370.A11250 | HNB Reactors Shutdown Essential Safety Cases | Prepare Stress Test Draft EAN | 2019-01-02 | 2019-02-07 | 27 | 0 | 26 | 36 | 100% | 0.75 | 1 | Completed
ER6370LT | W201 | ER6370.A11245 | HNB Reactors Shutdown Essential Safety Cases | Stress Test EAN Summary | 2019-01-02 | 2019-04-12 | 72 | 0 | 72 | 100 | 100% | 0.72 | 1 | Completed
ER6370LT | W201 | ER6370.A16010 | HNB Reactors Shutdown Essential Safety Cases | Prepare Stress Test Draft EAN | 2019-01-02 | 2019-03-15 | 53 | 0 | 52 | 72 | 100% | 0.73611 | 1 | Completed
ER6370LT | W201 | ER6370.A16000 | HNB Reactors Shutdown Essential Safety Cases | ALARP Framework Support for ALARP/BAT/BPM Report Summary | 2019-01-02 | 2019-04-12 | 72 | 0 | 72 | 100 | 100% | 0.72 | 1 | Completed
ER6244LT | W220 | A3070.C0 | REGION 1 Defuelling Programme Fuel Handling Safety Case | [PR KDM] Identify and De-risk Major Threats to the Strategy | 2019-01-02 | 2019-01-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16400 | REGION 1 Reactors Shutdown Safety Cases Programme | Issue Environmental Aspect/Impact & Waste Management Assessment Form (HPB, HNB) | 2019-01-02 | 2019-01-16 | 3 | 0 | 10 | 14 | 100% | 0.21429 | 1 | Completed
ER6244LT | W220 | A10400 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload Review of Safety Case Limits & LOLER Inspection Requirements to CDMS | 2019-01-02 | 2019-01-30 | 21 | 0 | 21 | 28 | 100% | 0.75 | 1 | Completed
ER6244LT | W220 | A3630 | REGION 1 Defuelling Programme Fuel Handling Safety Case | [PR KDM] Draft Failed Fuel Gas Sampling EAN available for Technical Review | 2019-01-02 | 2019-01-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13010 | HNB Reactors Shutdown Essential Safety Cases | Phase 2 Project Start (FEEDS TO SUMMARY SCHEDULE) | 2019-01-02 | 2019-01-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A2270 | HNB Reactors Shutdown Essential Safety Cases | Phase 2 Project Management - Gate B - C | 2019-01-02 | 2020-10-14 | 399 | 0 | 452 | 651 | 100% | 0.6129 | 1 | Completed
ER6370LT | W201 | ER6370.A1530 | HNB Reactors Shutdown Essential Safety Cases | Commence Supporting References or Supporting EC's (HNB) | 2019-01-02 | 2019-01-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7240 | HNB Reactors Shutdown Essential Safety Cases | Prepare Code Validation from Operational Reactor Draft Report | 2019-01-02 | 2019-01-31 | 22 | 0 | 22 | 29 | 100% | 0.75862 | 1 | Completed
ER6370LT | W201 | ER6370.A10520 | HNB Reactors Shutdown Essential Safety Cases | Environmental Permitting and Permissioing Scoping and Stakeholder Engagement | 2019-01-02 | 2019-11-15 | 223 | 0 | 222 | 317 | 100% | 0.70347 | 1 | Completed
ER6370LT | W201 | ER6370.A7235 | HNB Reactors Shutdown Essential Safety Cases | SDM- Code Validation from Operational Reactor Summary | 2019-01-02 | 2019-06-28 | 123 | 0 | 123 | 177 | 100% | 0.69492 | 1 | Completed
ER6370LT | W201 | ER6370.A1000 | HNB Reactors Shutdown Essential Safety Cases | Gate B PRC Paper Submission | 2019-01-02 | 2019-01-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1110 | REGION 1 Reactors Shutdown Safety Cases Programme | PRC Members Review IRM Documentation | 2019-01-03 | 2019-01-09 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A1150 | HNB Reactors Shutdown Essential Safety Cases | PRC Members Review IRM Documentation | 2019-01-03 | 2019-01-09 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A13150 | HNB Reactors Shutdown Essential Safety Cases | Develop Defuelling Dataset Part 1 - Accelerated Work | 2019-01-04 | 2019-01-31 | 20 | 0 | 19 | 27 | 100% | 0.74074 | 1 | Completed
ER6370LT | W201 | ER6370.A13210 | HNB Reactors Shutdown Essential Safety Cases | Prepare ALARP Strategy Document Draft EAN | 2019-01-04 | 2019-02-14 | 30 | 0 | 29 | 41 | 100% | 0.73171 | 1 | Completed
ER6370LT | W201 | ER6370.A13200 | HNB Reactors Shutdown Essential Safety Cases | ALARP Strategy Document Summary | 2019-01-04 | 2019-04-23 | 75 | 0 | 75 | 109 | 100% | 0.68807 | 1 | Completed
ER6243LT | W200 | ER6243.A1120 | REGION 1 Reactors Shutdown Safety Cases Programme | Hold PRC Meeting | 2019-01-10 | 2019-01-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1140 | REGION 1 Reactors Shutdown Safety Cases Programme | Modify Estimate, Schedule & Risk Log as Required | 2019-01-10 | 2019-01-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1120 | HNB Reactors Shutdown Essential Safety Cases | Hold PRC Meeting | 2019-01-10 | 2019-01-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1130 | REGION 1 Reactors Shutdown Safety Cases Programme | Gate B PRC Paper Approval | 2019-01-10 | 2019-01-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1200 | HNB Reactors Shutdown Essential Safety Cases | Gate B PRC Paper Approval | 2019-01-10 | 2019-01-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1150 | REGION 1 Reactors Shutdown Safety Cases Programme | Modify IRM Paper as Required | 2019-01-11 | 2019-01-11 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1130 | HNB Reactors Shutdown Essential Safety Cases | Modify Estimate, Schedule & Risk Log as Required | 2019-01-11 | 2019-01-11 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1140 | HNB Reactors Shutdown Essential Safety Cases | Modify IRM Paper as Required | 2019-01-14 | 2019-01-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A11000 | HNB Reactors Shutdown Essential Safety Cases | Issued SDM Assumptions Document Draft Report to EDF for Review. | 2019-01-15 | 2019-01-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1010 | HNB Reactors Shutdown Essential Safety Cases | Gate B MS PRC Paper Submission | 2019-01-15 | 2019-01-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1170 | HNB Reactors Shutdown Essential Safety Cases | Modify Estimate, Schedule, Cost Tool & Risk Log as Required | 2019-01-15 | 2019-01-15 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1180 | HNB Reactors Shutdown Essential Safety Cases | Update Cost Management Tool | 2019-01-15 | 2019-01-21 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A1190 | HNB Reactors Shutdown Essential Safety Cases | IRM Members Review IRM Documentation | 2019-01-15 | 2019-01-23 | 7 | 0 | 7 | 8 | 100% | 0.875 | 1 | Completed
ER6243LT | W200 | A16410 | REGION 1 Reactors Shutdown Safety Cases Programme | Environmental Aspect/Impact & Waste Management Assessment Form Complete (HPB, HNB) | 2019-01-16 | 2019-01-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16450 | REGION 1 Reactors Shutdown Safety Cases Programme | Environmental Aspect/Impact & Waste Management Assessment Form Complete (HYA, HAR) | 2019-01-16 | 2019-01-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7450 | HNB Reactors Shutdown Essential Safety Cases | Prepare Flux Detection Scoping Draft Report | 2019-01-16 | 2019-04-30 | 73 | 0 | 72 | 104 | 100% | 0.70192 | 1 | Completed
ER6370LT | W201 | ER6370.A11010 | HNB Reactors Shutdown Essential Safety Cases | SDM Assumptions Document Draft Report Reviewed by EDF SQEP | 2019-01-16 | 2019-03-04 | 34 | 0 | 33 | 47 | 100% | 0.7234 | 1 | Completed
ER6370LT | W201 | ER6370.A7445 | HNB Reactors Shutdown Essential Safety Cases | Flux Detection Scoping Summary | 2019-01-16 | 2019-07-19 | 128 | 0 | 128 | 184 | 100% | 0.69565 | 1 | Completed
ER6244LT | W220 | A1670.C0 | REGION 1 Defuelling Programme Fuel Handling Safety Case | [PR KDM] Gate B for HPB HNB Station Fuel Handling Safety Case Programme | 2019-01-16 | 2019-01-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13380 | HNB Reactors Shutdown Essential Safety Cases | Safety Rod Insertion Scoping - Draft and issue RFS | 2019-01-18 | 2019-01-24 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A13375 | HNB Reactors Shutdown Essential Safety Cases | RFS - Safety Rod Insertion Scoping Summary | 2019-01-18 | 2019-05-17 | 83 | 0 | 83 | 119 | 100% | 0.69748 | 1 | Completed
ER6370LT | W201 | ER6370.A13580 | HNB Reactors Shutdown Essential Safety Cases | Scope Additional SDM Calcs - Draft and issue RFS | 2019-01-18 | 2019-02-28 | 30 | 0 | 29 | 41 | 100% | 0.73171 | 1 | Completed
ER6370LT | W201 | ER6370.A13575 | HNB Reactors Shutdown Essential Safety Cases | RFS - Scope Additional SDM Calcs Summary | 2019-01-18 | 2019-02-28 | 30 | 0 | 30 | 41 | 100% | 0.73171 | 1 | Completed
ER6244LT | W220 | A10200 | REGION 1 Defuelling Programme Fuel Handling Safety Case | [KDM] Review of Rad Cons for Lower Decay Heat for Input into PSA available | 2019-01-18 | 2019-01-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A3300 | REGION 1 Defuelling Programme Fuel Handling Safety Case | NSRS Presented to NSC (for complex CAT 1 cases) | 2019-01-23 | 2019-01-23 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A3300 | HRA Fuel Handling Essential Safety Case | NSRS Presented to NSC (for complex CAT 1 cases) | 2019-01-23 | 2019-01-23 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A3300 | HYA Fuel Handling Essential Safety Case | NSRS Presented to NSC (for complex CAT 1 cases) | 2019-01-23 | 2019-01-23 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13390 | HNB Reactors Shutdown Essential Safety Cases | Safety Rod Insertion Scoping - Supplier prepare and issue Offer | 2019-01-25 | 2019-02-07 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6244LT | W220 | A10390 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier update and issue Review of Safety Case Limits & LOLER Inspection Requirements | 2019-01-25 | 2019-01-31 | 4 | 0 | 5 | 6 | 100% | 0.66667 | 1 | Completed
ER6370LT | W201 | ER6370.A4920 | HNB Reactors Shutdown Essential Safety Cases | Prepare C&I Review Specification | 2019-01-28 | 2019-03-04 | 26 | 0 | 25 | 35 | 100% | 0.74286 | 1 | Completed
ER6370LT | W201 | ER6370.A4915 | HNB Reactors Shutdown Essential Safety Cases | C&I Review Summary | 2019-01-28 | 2019-04-12 | 54 | 0 | 54 | 74 | 100% | 0.72973 | 1 | Completed
ER6243LT | W200 | A16150 | REGION 1 Reactors Shutdown Safety Cases Programme | Support System Report Issued to CDMS (HPB, HNB) | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16740 | REGION 1 Reactors Shutdown Safety Cases Programme | Support System Report Review and Acceptance (HPB, HNB) | 2019-01-31 | 2019-01-31 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3640 | HNB Reactors Shutdown Essential Safety Cases | Develop Defuelling Dataset Part 1 | 2019-01-31 | 2019-04-15 | 53 | 0 | 52 | 74 | 100% | 0.71622 | 1 | Completed
ER6370LT | W201 | ER6370.A7950 | HNB Reactors Shutdown Essential Safety Cases | MACE Defuelling Dataset Specification Completed (FNC Summary Report) | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3635 | HNB Reactors Shutdown Essential Safety Cases | Develop Defuelling Dataset Part 1 Summary | 2019-01-31 | 2019-04-15 | 52 | 0 | 52 | 74 | 100% | 0.7027 | 1 | Completed
ER6244LT | W220 | A10410 | REGION 1 Defuelling Programme Fuel Handling Safety Case | [KDM] Review of Safety Case Limits & LOLER Inspection Requirements available | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7250 | HNB Reactors Shutdown Essential Safety Cases | Issued Code Validation from Operational Reactor Draft Report to EDF for Review. | 2019-01-31 | 2019-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8360 | HNB Reactors Shutdown Essential Safety Cases | Prepare Pressure Boundary Seals Specification | 2019-02-01 | 2019-02-22 | 16 | 0 | 15 | 21 | 100% | 0.7619 | 1 | Completed
ER6370LT | W201 | ER6370.A10730 | HNB Reactors Shutdown Essential Safety Cases | Current Code Applicability Range Verified by TSA | 2019-02-01 | 2019-02-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A10810 | HNB Reactors Shutdown Essential Safety Cases | Scope Codes and Methods Options and Validation Verified by TSA | 2019-02-01 | 2019-02-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A8355 | HNB Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals Specification Summary | 2019-02-01 | 2019-05-31 | 81 | 0 | 81 | 119 | 100% | 0.68067 | 1 | Completed
ER6370LT | W201 | ER6370.A13160 | HNB Reactors Shutdown Essential Safety Cases | Validate Model and Datasets Part 1 - Accelerated Work | 2019-02-01 | 2019-03-15 | 31 | 0 | 30 | 42 | 100% | 0.7381 | 1 | Completed
ER6243LT | W200 | A16910 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - QA Grade 2 Technical Note TR by EDF SQEP (Not Req'd as per DS notes 26.02.18) | 2019-02-01 | 2019-02-28 | 15 | 0 | 19 | 27 | 100% | 0.55556 | 1 | Completed
ER6370LT | W201 | ER6370.A3480 | HNB Reactors Shutdown Essential Safety Cases | Verify MACE Code v3.2.2 Defuelling Prototype Model | 2019-02-04 | 2019-03-15 | 30 | 0 | 29 | 39 | 100% | 0.76923 | 1 | Completed
ER6370LT | W201 | ER6370.A13300 | HNB Reactors Shutdown Essential Safety Cases | Prepare Implementation Strategy Document Draft EAN | 2019-02-04 | 2019-03-01 | 20 | 0 | 19 | 25 | 100% | 0.8 | 1 | Completed
ER6370LT | W201 | ER6370.A13290 | HNB Reactors Shutdown Essential Safety Cases | Implementation Strategy Document Summary | 2019-02-04 | 2019-05-31 | 80 | 0 | 80 | 116 | 100% | 0.68966 | 1 | Completed
ER6370LT | W201 | ER6370.A13830 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Margin Head Document - Draft and issue RFS(Call Off Task Sheet) | 2019-02-05 | 2019-03-06 | 22 | 0 | 21 | 29 | 100% | 0.75862 | 1 | Completed
ER6370LT | W201 | ER6370.A13825 | HNB Reactors Shutdown Essential Safety Cases | RFS - Shutdown Margin Head Document Summary | 2019-02-05 | 2019-07-17 | 113 | 0 | 113 | 162 | 100% | 0.69753 | 1 | Completed
ER6370LT | W201 | ER6370.A10740 | HNB Reactors Shutdown Essential Safety Cases | Verified Current Code Applicability Range Issued to EDF for Technical Review. | 2019-02-07 | 2019-02-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A10820 | HNB Reactors Shutdown Essential Safety Cases | Verified Scope Codes and Methods Options and Validation Issued to EDF for Technical Review. | 2019-02-07 | 2019-02-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A10750 | HNB Reactors Shutdown Essential Safety Cases | Current Code Applicability Range Technically Reviewed by EDF SQEP | 2019-02-08 | 2019-03-25 | 32 | 0 | 31 | 45 | 100% | 0.71111 | 1 | Completed
ER6370LT | W201 | ER6370.A10830 | HNB Reactors Shutdown Essential Safety Cases | Scope Codes and Methods Options and Validation Technically Reviewed by EDF SQEP | 2019-02-08 | 2019-03-01 | 16 | 0 | 15 | 21 | 100% | 0.7619 | 1 | Completed
ER6370LT | W201 | ER6370.A13400 | HNB Reactors Shutdown Essential Safety Cases | Safety Rod Insertion Scoping - Review Offer, prepare and issue CI | 2019-02-08 | 2019-02-14 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6243LT | W200 | ER6243.A1160 | REGION 1 Reactors Shutdown Safety Cases Programme | Gate B MS PRC Paper Submission | 2019-02-12 | 2019-02-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1170 | REGION 1 Reactors Shutdown Safety Cases Programme | Update Cost Management Tool | 2019-02-12 | 2019-02-18 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6243LT | W200 | ER6243.A1180 | REGION 1 Reactors Shutdown Safety Cases Programme | IRM Members Review IRM Documentation | 2019-02-12 | 2019-02-18 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A13220 | HNB Reactors Shutdown Essential Safety Cases | ALARP Strategy Document Draft EAN Verified by TSA | 2019-02-15 | 2019-04-05 | 36 | 0 | 35 | 49 | 100% | 0.73469 | 1 | Completed
ER6370LT | W201 | ER6370.A13410 | HNB Reactors Shutdown Essential Safety Cases | Safety Rod Insertion Scoping - Supplier mobilisation time | 2019-02-15 | 2019-02-28 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6370LT | W201 | ER6370.A13480 | HNB Reactors Shutdown Essential Safety Cases | SDM Assessments with Uncertainties - Draft and issue RFS | 2019-02-15 | 2019-02-21 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A13475 | HNB Reactors Shutdown Essential Safety Cases | RFS - SDM Assessments with Uncertainties Summary | 2019-02-15 | 2019-04-29 | 50 | 0 | 50 | 73 | 100% | 0.68493 | 1 | Completed
ER6370LT | W201 | ER6370.A7305 | HNB Reactors Shutdown Essential Safety Cases | DNB Commissiong Core Validation Summary | 2019-02-18 | 2020-02-07 | 246 | 0 | 246 | 354 | 100% | 0.69492 | 1 | Completed
ER6370LT | W201 | ER6370.A7340 | HNB Reactors Shutdown Essential Safety Cases | Prepare DNB Commissiong Core Validation Specification | 2019-02-18 | 2019-03-01 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A15940 | HNB Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity - Draft and issue RFS | 2019-02-18 | 2019-02-22 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A15935 | HNB Reactors Shutdown Essential Safety Cases | RFS - Structures and Equipment Integrity Summary | 2019-02-18 | 2019-04-19 | 45 | 0 | 44 | 60 | 100% | 0.75 | 1 | Completed
ER6370LT | W201 | ER6370.A15990 | HNB Reactors Shutdown Essential Safety Cases | Prepare Timeline for Technical Specification updates for defuelling | 2019-02-18 | 2019-04-12 | 40 | 0 | 39 | 53 | 100% | 0.75472 | 1 | Completed
ER6370LT | W201 | ER6370.A15985 | HNB Reactors Shutdown Essential Safety Cases | Timeline for Technical Specification updates for defuelling Summary | 2019-02-18 | 2019-04-12 | 39 | 0 | 39 | 53 | 100% | 0.73585 | 1 | Completed
ER6244LT | W220 | A10120 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload Dropped FPU RadCons Analysis of Core Support Plate Failure to CDMS | 2019-02-18 | 2019-02-28 | 9 | 0 | 9 | 10 | 100% | 0.9 | 1 | Completed
ER6243LT | W200 | ER6243.A1190 | REGION 1 Reactors Shutdown Safety Cases Programme | Hold MS PRC | 2019-02-20 | 2019-02-20 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1160 | HNB Reactors Shutdown Essential Safety Cases | Hold MS PRC | 2019-02-20 | 2019-02-20 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16520 | REGION 1 Reactors Shutdown Safety Cases Programme | Gate B MS PRC Approval | 2019-02-20 | 2019-02-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1210 | HNB Reactors Shutdown Essential Safety Cases | Gate B MS PRC Approval | 2019-02-20 | 2019-02-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A13380 | REGION 1 Reactors Shutdown Safety Cases Programme | Mapping Optioneering Report Issued (HYA, HAR) | 2019-02-21 | 2019-02-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1200 | REGION 1 Reactors Shutdown Safety Cases Programme | Modify Estimate, Schedule, Cost Tool & Risk Log as Required | 2019-02-21 | 2019-02-26 | 1 | 0 | 3 | 5 | 100% | 0.2 | 1 | Completed
ER6243LT | W200 | A13270 | REGION 1 Reactors Shutdown Safety Cases Programme | Mapping Optioneering Report Issued (HPB, HNB) | 2019-02-21 | 2019-02-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8370 | HNB Reactors Shutdown Essential Safety Cases | Issue Pressure Boundary Seals Specification to EDF Review. | 2019-02-22 | 2019-02-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13490 | HNB Reactors Shutdown Essential Safety Cases | SDM Assessments with Uncertainties - Supplier prepare and issue Offer | 2019-02-22 | 2019-03-07 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6370LT | W201 | ER6370.A8380 | HNB Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals Specification Reviewed by EDF SQEP | 2019-02-25 | 2019-03-08 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A15950 | HNB Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity - Supplier prepare and issue Offer | 2019-02-25 | 2019-04-12 | 35 | 0 | 34 | 46 | 100% | 0.76087 | 1 | Completed
ER6243LT | W200 | A16920 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - TSA Address TR Comments (Not Req'd as per DS notes 26.02.18) | 2019-02-28 | 2019-02-28 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16930 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Issue Final QA Grade 2 Technical Note (Not Req'd as per DS notes 26.02.18) | 2019-02-28 | 2019-02-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16950 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Development of Suitable Boundary Conditions Completed (Not Req'd as per DS notes 26.02.18) | 2019-02-28 | 2019-02-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16940 | REGION 1 Reactors Shutdown Safety Cases Programme | Thermal Hydraulics (MACE) - Complete TR form and upload to CDMS (Not Req'd as per DS notes 26.02.18) | 2019-02-28 | 2019-02-28 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13180 | HNB Reactors Shutdown Essential Safety Cases | Discovery Milestone: Scope confirmation following NSC advice on NSRS and internal workshops (HNB) | 2019-02-28 | 2019-02-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13590 | HNB Reactors Shutdown Essential Safety Cases | Scope Additional SDM Calcs - Supplier prepare and issue Offer | 2019-02-28 | 2019-02-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13600 | HNB Reactors Shutdown Essential Safety Cases | Scope Additional SDM Calcs - Review Offer, prepare and issue CI | 2019-02-28 | 2019-02-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13610 | HNB Reactors Shutdown Essential Safety Cases | Scope Additional SDM Calcs - Supplier mobilisation time | 2019-02-28 | 2019-02-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13620 | HNB Reactors Shutdown Essential Safety Cases | Scope Additional SDM Calcs - Pre Job Brief | 2019-02-28 | 2019-02-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13880 | HNB Reactors Shutdown Essential Safety Cases | Civil Integrity Overview - Draft and issue RFS | 2019-02-28 | 2019-02-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13890 | HNB Reactors Shutdown Essential Safety Cases | Civil Integrity Overview - Supplier prepare and issue Offer | 2019-02-28 | 2019-02-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13900 | HNB Reactors Shutdown Essential Safety Cases | Civil Integrity Overview - Review Offer, prepare and issue CI | 2019-02-28 | 2019-02-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13910 | HNB Reactors Shutdown Essential Safety Cases | Civil Integrity Overview - Supplier mobilisation time | 2019-02-28 | 2019-02-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13875 | HNB Reactors Shutdown Essential Safety Cases | RFS - Civil Integrity Overview Summary | 2019-02-28 | 2019-03-04 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6370LT | W201 | ER6370.A14240 | HNB Reactors Shutdown Essential Safety Cases | Ass'ment of Graphite behaviour for Shutdown Defuelling - Draft and issue RFS | 2019-02-28 | 2019-02-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14250 | HNB Reactors Shutdown Essential Safety Cases | Ass'ment of Graphite behaviour for Shutdown Defuelling - Supplier prepare and issue Offer | 2019-02-28 | 2019-02-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14260 | HNB Reactors Shutdown Essential Safety Cases | Ass'ment of Graphite behaviour for Shutdown Defuelling - Review Offer, prepare and issue CI | 2019-02-28 | 2019-02-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14270 | HNB Reactors Shutdown Essential Safety Cases | Ass'ment of Graphite behaviour for Shutdown Defuelling - Supplier mobilisation time | 2019-02-28 | 2019-02-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14235 | HNB Reactors Shutdown Essential Safety Cases | RFS - Ass'ment of Graphite behaviour for Shutdown Defuelling Summary | 2019-02-28 | 2019-04-30 | 42 | 0 | 42 | 61 | 100% | 0.68852 | 1 | Completed
ER6244LT | W220 | A10130 | REGION 1 Defuelling Programme Fuel Handling Safety Case | [KDM] Dropped FPU RadCons Analysis of Core Support Plate Failure available | 2019-02-28 | 2019-02-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1210 | REGION 1 Reactors Shutdown Safety Cases Programme | Gate B IRM Paper Submission | 2019-03-01 | 2019-03-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A10300 | HNB Reactors Shutdown Essential Safety Cases | Prepare Specification for LSD Strategy Draft Report | 2019-03-01 | 2019-06-03 | 63 | 0 | 63 | 94 | 100% | 0.67021 | 1 | Completed
ER6370LT | W201 | ER6370.A10420 | HNB Reactors Shutdown Essential Safety Cases | Prepare Specification for Boilers and Gas Circulator Performance EAN | 2019-03-01 | 2019-04-10 | 29 | 0 | 28 | 40 | 100% | 0.725 | 1 | Completed
ER6370LT | W201 | ER6370.A10295 | HNB Reactors Shutdown Essential Safety Cases | Specification for LSD Strategy Draft Report Summary | 2019-03-01 | 2019-10-04 | 150 | 0 | 150 | 217 | 100% | 0.69124 | 1 | Completed
ER6370LT | W201 | ER6370.A10415 | HNB Reactors Shutdown Essential Safety Cases | Boilers and Gas Circulator Performance for Changing Plant Conditions Summary | 2019-03-01 | 2020-07-28 | 354 | 0 | 355 | 515 | 100% | 0.68738 | 1 | Completed
ER6370LT | W201 | ER6370.A12305 | HNB Reactors Shutdown Essential Safety Cases | Prepare EPRI Tool - HNB | 2019-03-01 | 2019-04-02 | 23 | 0 | 22 | 32 | 100% | 0.71875 | 1 | Completed
ER6370LT | W201 | ER6370.A12300 | HNB Reactors Shutdown Essential Safety Cases | EPRI Tool Summary - HNB | 2019-03-01 | 2019-05-15 | 51 | 0 | 51 | 75 | 100% | 0.68 | 1 | Completed
ER6370LT | W201 | ER6370.A13310 | HNB Reactors Shutdown Essential Safety Cases | Implementation Strategy Document Draft EAN Verified by TSA | 2019-03-01 | 2019-05-15 | 51 | 0 | 50 | 75 | 100% | 0.68 | 1 | Completed
ER6370LT | W201 | ER6370.A11260 | HNB Reactors Shutdown Essential Safety Cases | Response to Stress Test EAN Verification | 2019-03-01 | 2019-04-05 | 26 | 0 | 25 | 35 | 100% | 0.74286 | 1 | Completed
ER6370LT | W201 | ER6370.A1240 | HNB Reactors Shutdown Essential Safety Cases | Gate B IRM Paper Submission | 2019-03-01 | 2019-03-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4940 | HNB Reactors Shutdown Essential Safety Cases | C&I Review Specification Completed | 2019-03-04 | 2019-03-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7310 | HNB Reactors Shutdown Essential Safety Cases | Prepare DNB Commissiong Core Validation Scoping Draft Report | 2019-03-04 | 2019-05-08 | 45 | 0 | 44 | 65 | 100% | 0.69231 | 1 | Completed
ER6370LT | W201 | ER6370.A10840 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Scope Codes and Methods Options and Validation | 2019-03-04 | 2019-03-08 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A13920 | HNB Reactors Shutdown Essential Safety Cases | Civil Integrity Overview - Pre Job Brief | 2019-03-04 | 2019-03-04 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16820 | REGION 1 Reactors Shutdown Safety Cases Programme | Address EDF Comments on Draft resourced Station Plans (HPB) (Transfer to W282 Workpack) | 2019-03-05 | 2019-03-05 | 4 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16830 | REGION 1 Reactors Shutdown Safety Cases Programme | Re-issue Final resourced Station Plans (HPB) (Transfer to W282 Workpack) | 2019-03-05 | 2019-03-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A17200 | REGION 1 Reactors Shutdown Safety Cases Programme | Address EDF Comments on Draft resourced Station Plans (HNB) (Transfer to W282 Workpack) | 2019-03-05 | 2019-03-05 | 4 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A17210 | REGION 1 Reactors Shutdown Safety Cases Programme | Re-issue Final resourced Station Plans (HNB) (Transfer to W282 Workpack) | 2019-03-05 | 2019-03-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A2840 | HNB Reactors Shutdown Essential Safety Cases | Prepare Civil Integrity Overview Draft EAN | 2019-03-05 | 2019-07-17 | 93 | 0 | 92 | 134 | 100% | 0.69403 | 1 | Completed
ER6370LT | W201 | ER6370.A4950 | HNB Reactors Shutdown Essential Safety Cases | C&I Review Authoring | 2019-03-05 | 2019-04-12 | 29 | 0 | 28 | 38 | 100% | 0.76316 | 1 | Completed
ER6370LT | W201 | ER6370.A7260 | HNB Reactors Shutdown Essential Safety Cases | Code Validation from Operational Reactor Draft Report Reviewed by TSA SQEP | 2019-03-05 | 2019-03-18 | 10 | 0 | 9 | 13 | 100% | 0.76923 | 1 | Completed
ER6370LT | W201 | ER6370.A11020 | HNB Reactors Shutdown Essential Safety Cases | Address Comments from EDF Review on SDM Assumptions Document Draft Report | 2019-03-05 | 2019-04-12 | 29 | 0 | 28 | 38 | 100% | 0.76316 | 1 | Completed
ER6370LT | W201 | ER6370.A2835 | HNB Reactors Shutdown Essential Safety Cases | Civil Integrity Overview Summary | 2019-03-05 | 2019-08-19 | 115 | 0 | 115 | 167 | 100% | 0.68862 | 1 | Completed
ER6370LT | W201 | ER6370.A10850 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Scope Codes and Methods Options and Validation | 2019-03-08 | 2019-03-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13500 | HNB Reactors Shutdown Essential Safety Cases | SDM Assessments with Uncertainties - Review Offer, prepare and issue CI | 2019-03-08 | 2019-03-14 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A3800 | HNB Reactors Shutdown Essential Safety Cases | Validate Model and Datasets Part 1 | 2019-03-11 | 2019-04-15 | 26 | 0 | 25 | 35 | 100% | 0.74286 | 1 | Completed
ER6370LT | W201 | ER6370.A8390 | HNB Reactors Shutdown Essential Safety Cases | Address Comments on Reviewed Pressure Boundary Seals Specification | 2019-03-11 | 2019-04-30 | 35 | 0 | 34 | 50 | 100% | 0.7 | 1 | Completed
ER6370LT | W201 | ER6370.A10860 | HNB Reactors Shutdown Essential Safety Cases | Scope Codes and Methods Options and Validation TR Completed and uploaded to CDMS | 2019-03-11 | 2019-03-15 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A10950 | HNB Reactors Shutdown Essential Safety Cases | Prepare Scope Additional SDM Calcs Draft Report (Phase 1) | 2019-03-11 | 2019-04-26 | 33 | 0 | 32 | 46 | 100% | 0.71739 | 1 | Completed
ER6370LT | W201 | ER6370.A10945 | HNB Reactors Shutdown Essential Safety Cases | Scope Additional SDM Calcs Summary | 2019-03-11 | 2019-09-20 | 134 | 0 | 134 | 193 | 100% | 0.6943 | 1 | Completed
ER6370LT | W201 | ER6370.A3795 | HNB Reactors Shutdown Essential Safety Cases | Validate Model and Datasets Part 1 Summary | 2019-03-11 | 2019-04-15 | 25 | 0 | 25 | 35 | 100% | 0.71429 | 1 | Completed
ER6244LT | W220 | A9770 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Supplier update and issue Fuel Free Verification EAN | 2019-03-11 | 2019-03-22 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6243LT | W200 | A1670.C0 | REGION 1 Reactors Shutdown Safety Cases Programme | Gate B - 6.1 Reactors Shutdown Safety Cases Programme HPB/HNB | 2019-03-13 | 2019-03-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1230 | REGION 1 Reactors Shutdown Safety Cases Programme | Gate B IRM Paper Approval | 2019-03-13 | 2019-03-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1220 | REGION 1 Reactors Shutdown Safety Cases Programme | Hold IRM | 2019-03-13 | 2019-03-13 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1230 | HNB Reactors Shutdown Essential Safety Cases | Hold IRM | 2019-03-13 | 2019-03-13 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1220 | HNB Reactors Shutdown Essential Safety Cases | Gate B IRM Paper Approval | 2019-03-13 | 2019-03-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A10410 | HNB Reactors Shutdown Essential Safety Cases | Prepare Specification for Boiler Supporting Systems EAN | 2019-03-14 | 2019-05-13 | 40 | 0 | 39 | 60 | 100% | 0.66667 | 1 | Completed
ER6370LT | W201 | ER6370.A10405 | HNB Reactors Shutdown Essential Safety Cases | Boiler Supporting Systems Summary | 2019-03-14 | 2020-04-24 | 282 | 0 | 281 | 407 | 100% | 0.69287 | 1 | Completed
ER6370LT | W201 | ER6370.A10870 | HNB Reactors Shutdown Essential Safety Cases | Scope Codes and Methods Options and Validation Completed | 2019-03-15 | 2019-03-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13510 | HNB Reactors Shutdown Essential Safety Cases | SDM Assessments with Uncertainties - Supplier mobilisation time | 2019-03-15 | 2019-03-28 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6370LT | W201 | ER6370.A14940 | HNB Reactors Shutdown Essential Safety Cases | Boiler Control and Protection Draft Report - Draft and issue RFS | 2019-03-15 | 2019-05-01 | 32 | 0 | 31 | 47 | 100% | 0.68085 | 1 | Completed
ER6370LT | W201 | ER6370.A14935 | HNB Reactors Shutdown Essential Safety Cases | RFS - Boiler Control and Protection Draft Report Summary | 2019-03-15 | 2019-05-23 | 47 | 0 | 47 | 69 | 100% | 0.68116 | 1 | Completed
ER6370LT | W201 | ER6370.A14990 | HNB Reactors Shutdown Essential Safety Cases | Reactor Cooling Systems Draft Report - Draft and issue RFS | 2019-03-15 | 2019-05-01 | 32 | 0 | 31 | 47 | 100% | 0.68085 | 1 | Completed
ER6370LT | W201 | ER6370.A14985 | HNB Reactors Shutdown Essential Safety Cases | RFS - Reactor Cooling Systems Draft Report Summary | 2019-03-15 | 2019-05-23 | 47 | 0 | 47 | 69 | 100% | 0.68116 | 1 | Completed
ER6370LT | W201 | ER6370.A2000 | HNB Reactors Shutdown Essential Safety Cases | Prepare Establish Codes and Methods for Safety Case Draft Report | 2019-03-18 | 2019-06-28 | 71 | 0 | 70 | 102 | 100% | 0.69608 | 1 | Completed
ER6370LT | W201 | ER6370.A1999 | HNB Reactors Shutdown Essential Safety Cases | Establish Codes and Methods for Safety Case Summary | 2019-03-18 | 2019-11-08 | 164 | 0 | 164 | 235 | 100% | 0.69787 | 1 | Completed
ER6370LT | W201 | ER6370.A16020 | HNB Reactors Shutdown Essential Safety Cases | Response to ALARP Framework Support for ALARP/BAT/BPM Report Verification | 2019-03-18 | 2019-04-05 | 15 | 0 | 14 | 18 | 100% | 0.83333 | 1 | Completed
ER6243LT | W200 | A3070.C0 | REGION 1 Reactors Shutdown Safety Cases Programme | Identify and De-risk Major Threats to the Strategy | 2019-03-19 | 2019-03-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.VI.A190.EI | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Engineering Substantiation Report Completed (HPB, HNB) | 2019-03-19 | 2019-03-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | RSSC.VI.A200.EI | REGION 1 Reactors Shutdown Safety Cases Programme | PCPV Integrity - Engineering Substantiation Report Completed (HYA, HAR) | 2019-03-19 | 2019-03-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A1270 | REGION 1 Reactors Shutdown Safety Cases Programme | Agree INSA resource with SRD (HPB, HNB) | 2019-03-19 | 2019-03-19 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A1280 | REGION 1 Reactors Shutdown Safety Cases Programme | Circulate work programme to stakeholders for agreement (HPB, HNB) | 2019-03-19 | 2019-03-19 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A12600 | REGION 1 Reactors Shutdown Safety Cases Programme | Agree design proposals with Station in the case of hardware mods (HYA, HAR) | 2019-03-19 | 2019-03-19 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A13050.C0 | REGION 1 Reactors Shutdown Safety Cases Programme | Key Risks Identified and Assumptions underpinned | 2019-03-19 | 2019-03-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7270 | HNB Reactors Shutdown Essential Safety Cases | Address Comments from EDF Review on Code Validation from Operational Reactor Draft Report | 2019-03-19 | 2019-04-30 | 29 | 0 | 28 | 42 | 100% | 0.69048 | 1 | Completed
ER6243LT | W200 | A3050.C0 | REGION 1 Reactors Shutdown Safety Cases Programme | Identify any Major Hardware Changes required for Gate B Submission | 2019-03-19 | 2019-03-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14640 | HNB Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Based Faults) - Draft and issue RFS | 2019-03-25 | 2019-04-05 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A14635 | HNB Reactors Shutdown Essential Safety Cases | RFS - Fault Schedule Review (Plant Based Faults) Summary | 2019-03-25 | 2019-05-17 | 37 | 0 | 37 | 53 | 100% | 0.69811 | 1 | Completed
ER6370LT | W201 | ER6370.A14690 | HNB Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Hazards) - Draft and issue RFS | 2019-03-25 | 2019-04-05 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A14685 | HNB Reactors Shutdown Essential Safety Cases | RFS - Fault Schedule Review (Hazards) Summary | 2019-03-25 | 2019-05-17 | 37 | 0 | 37 | 53 | 100% | 0.69811 | 1 | Completed
ER6244LT | W220 | A9780 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Complete TR form and upload Fuel Free Verification EAN to CDMS | 2019-03-25 | 2019-03-28 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6370LT | W201 | ER6370.A10760 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Current Code Applicability Range | 2019-03-26 | 2019-03-29 | 4 | 0 | 3 | 3 | 100% | 1.3333 | 1 | Completed
ER6378LT | W222 | W222.A14040 | HRA Fuel Handling Essential Safety Case | Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 2019-03-26 | 2019-03-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A14030 | HRA Fuel Handling Essential Safety Case | Define Project Control Structures (WBS/CBS/OBS/PBS) | 2019-03-26 | 2019-03-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A22150 | HRA Fuel Handling Essential Safety Case | EAC (PS - 28-Feb-2020) ##(Cost Summary)## | 2019-03-26 | 2020-02-28 | 257 | 0 | 235 | 339 | 100% | 0.75811 | 1 | Completed
ER6650LT | W226 | W226.A14030 | HYA Fuel Handling Essential Safety Case | Define Project Control Structures (WBS/CBS/OBS/PBS) [FEEDS TO SUMMARY SCHEDULE] | 2019-03-26 | 2019-03-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A14040 | HYA Fuel Handling Essential Safety Case | Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 2019-03-26 | 2019-03-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A12770 | REGION 1 Reactors Shutdown Safety Cases Programme | Identify verifier for the case & establish all other resources (HYA, HAR) (Deferred to W202 Workpack) | 2019-03-27 | 2019-03-27 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A12900 | REGION 1 Reactors Shutdown Safety Cases Programme | Gate EC2 completed EC 363682 & 363676 <NSRS SC Approach & Outline> (Cat 1 Milestone) (HYA, HAR) (Deferred to W202 WP) | 2019-03-27 | 2019-03-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A12610 | REGION 1 Reactors Shutdown Safety Cases Programme | Agree INSA resource with SRD (HYA, HAR) (Deferred to W202 Workpack) | 2019-03-27 | 2019-03-27 | 5 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A12780 | REGION 1 Reactors Shutdown Safety Cases Programme | Circulate work programme to stakeholders for agreement (HYA, HAR) (Deferred to W202 Workpack) | 2019-03-27 | 2019-03-27 | 5 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A12870 | REGION 1 Reactors Shutdown Safety Cases Programme | Develop & resource mandatory template (HYA, HAR) (Deferred to W202 Workpack) | 2019-03-27 | 2019-03-27 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A12980 | REGION 1 Reactors Shutdown Safety Cases Programme | Baseline Plan to Verification Commenced (T-11) (HYA, HAR) (Deferred to W202 Workpack) | 2019-03-27 | 2019-03-27 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13230 | HNB Reactors Shutdown Essential Safety Cases | Verified ALARP Strategy Document Draft EAN Issued to EDF for Technical Review. (Deleted) | 2019-03-28 | 2019-03-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13240 | HNB Reactors Shutdown Essential Safety Cases | ALARP Strategy Document Draft EAN Technically Reviewed by EDF SQEP (Deleted) | 2019-03-28 | 2019-03-28 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13250 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd ALARP Strategy Document Draft EAN (Deleted) | 2019-03-28 | 2019-03-28 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14450 | HNB Reactors Shutdown Essential Safety Cases | Gas Chemistry Assessment - Supplier prepare and issue Offer | 2019-03-28 | 2019-03-28 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14460 | HNB Reactors Shutdown Essential Safety Cases | Gas Chemistry Assessment - Review Offer, prepare and issue CI | 2019-03-28 | 2019-03-28 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14470 | HNB Reactors Shutdown Essential Safety Cases | Gas Chemistry Assessment - Supplier mobilisation time | 2019-03-28 | 2019-03-28 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14480 | HNB Reactors Shutdown Essential Safety Cases | Gas Chemistry Assessment - Pre Job Brief | 2019-03-28 | 2019-03-28 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14435 | HNB Reactors Shutdown Essential Safety Cases | RFS - Gas Chemistry Assessment Specification Summary | 2019-03-28 | 2019-05-10 | 28 | 0 | 28 | 43 | 100% | 0.65116 | 1 | Completed
ER6244LT | W220 | A9790 | REGION 1 Defuelling Programme Fuel Handling Safety Case | [KDM] Fuel Free Verification EAN available | 2019-03-28 | 2019-03-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A10770 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Current Code Applicability Range | 2019-03-29 | 2019-03-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A10430 | HNB Reactors Shutdown Essential Safety Cases | General HF Oversight of Work Carried out on Safety Case (WP1) | 2019-04-01 | 2020-04-30 | 274 | 0 | 274 | 395 | 100% | 0.69367 | 1 | Completed
ER6370LT | W201 | ER6370.A10525 | HNB Reactors Shutdown Essential Safety Cases | ALARP / BAT/ BPM Summary | 2019-04-01 | 2019-11-15 | 159 | 0 | 159 | 228 | 100% | 0.69737 | 1 | Completed
ER6370LT | W201 | ER6370.A13980 | HNB Reactors Shutdown Essential Safety Cases | Component Life Assessment - Draft and issue RFS | 2019-04-01 | 2019-04-12 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A13975 | HNB Reactors Shutdown Essential Safety Cases | RFS - Component Life Assessment Summary | 2019-04-01 | 2019-05-22 | 35 | 0 | 35 | 51 | 100% | 0.68627 | 1 | Completed
ER6370LT | W201 | ER6370.A14090 | HNB Reactors Shutdown Essential Safety Cases | Specification for Standpipe and Guide Tube Integrity Assessment - Draft and issue RFS | 2019-04-01 | 2019-04-12 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A14085 | HNB Reactors Shutdown Essential Safety Cases | RFS - Specification for Standpipe and Guide Tube Integrity Assessment Summary | 2019-04-01 | 2019-05-22 | 35 | 0 | 35 | 51 | 100% | 0.68627 | 1 | Completed
ER6370LT | W201 | ER6370.A14190 | HNB Reactors Shutdown Essential Safety Cases | Specification for Degradation of Boilers - Draft and issue RFS | 2019-04-01 | 2019-04-12 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A14185 | HNB Reactors Shutdown Essential Safety Cases | RFS - Specification for Degradation of Boilers Summary | 2019-04-01 | 2019-05-22 | 35 | 0 | 35 | 51 | 100% | 0.68627 | 1 | Completed
ER6370LT | W201 | ER6370.A14440 | HNB Reactors Shutdown Essential Safety Cases | Prepare Gas Chemistry Specification | 2019-04-01 | 2019-05-10 | 27 | 0 | 26 | 39 | 100% | 0.69231 | 1 | Completed
ER6370LT | W201 | ER6370.A14490 | HNB Reactors Shutdown Essential Safety Cases | Reactor Coolant Chemistry Conditions - Draft and issue RFS | 2019-04-01 | 2019-05-31 | 41 | 0 | 40 | 60 | 100% | 0.68333 | 1 | Completed
ER6370LT | W201 | ER6370.A14485 | HNB Reactors Shutdown Essential Safety Cases | RFS - Reactor Coolant Chemistry Conditions Summary | 2019-04-01 | 2019-07-12 | 71 | 0 | 71 | 102 | 100% | 0.69608 | 1 | Completed
ER6370LT | W201 | ER6370.A15090 | HNB Reactors Shutdown Essential Safety Cases | HF Compliance Assessment for Shutdown Margin - Draft and issue RFS | 2019-04-01 | 2019-04-05 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A15085 | HNB Reactors Shutdown Essential Safety Cases | RFS - HF Compliance Assessment for Shutdown Margin Summary | 2019-04-01 | 2019-04-30 | 20 | 0 | 20 | 29 | 100% | 0.68966 | 1 | Completed
ER6370LT | W201 | ER6370.A15140 | HNB Reactors Shutdown Essential Safety Cases | HF Compliance / Tech Spec As'ment for Core Cooling - Draft and issue RFS | 2019-04-01 | 2019-04-05 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A15135 | HNB Reactors Shutdown Essential Safety Cases | RFS - HF Compliance / Tech Spec As'ment for Core Cooling Summary | 2019-04-01 | 2019-04-30 | 20 | 0 | 20 | 29 | 100% | 0.68966 | 1 | Completed
ER6370LT | W201 | ER6370.A15340 | HNB Reactors Shutdown Essential Safety Cases | HF Risk Assessment Draft Report - Draft and issue RFS | 2019-04-01 | 2019-04-03 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6370LT | W201 | ER6370.A15335 | HNB Reactors Shutdown Essential Safety Cases | RFS - HF Risk Assessment Draft Report Summary | 2019-04-01 | 2019-04-12 | 9 | 0 | 9 | 11 | 100% | 0.81818 | 1 | Completed
ER6370LT | W201 | ER6370.A15840 | HNB Reactors Shutdown Essential Safety Cases | Summary of Compliance with NSPs - Draft and issue RFS | 2019-04-01 | 2019-04-05 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A15835 | HNB Reactors Shutdown Essential Safety Cases | RFS - Summary of Compliance with NSPs Summary | 2019-04-01 | 2019-04-24 | 16 | 0 | 16 | 23 | 100% | 0.69565 | 1 | Completed
ER6370LT | W201 | ER6370.A16130 | HNB Reactors Shutdown Essential Safety Cases | Phase 1: Scoping and Parameters for Station Documentation Update Strategy | 2019-04-01 | 2019-07-08 | 67 | 0 | 66 | 98 | 100% | 0.68367 | 1 | Completed
ER6243LT | W200 | A10260 | REGION 1 Reactors Shutdown Safety Cases Programme | CA to agree with CO format of the safety case (HYA, HAR) | 2019-04-01 | 2019-04-02 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6378LT | W222 | W222.A3240 | HRA Fuel Handling Essential Safety Case | Incorporate INA, Station, DA (peer) comments | 2019-04-01 | 2019-05-24 | 16 | 0 | 36 | 53 | 100% | 0.30189 | 1 | Completed
ER6650LT | W226 | W226.A3240 | HYA Fuel Handling Essential Safety Case | Incorporate INA, Station, DA (peer) comments | 2019-04-01 | 2019-05-24 | 16 | 0 | 36 | 53 | 100% | 0.30189 | 1 | Completed
ER6243LT | W200 | A10760 | REGION 1 Reactors Shutdown Safety Cases Programme | Estimating Uncertainty - 2019 | 2019-04-01 | 2019-04-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14290 | HNB Reactors Shutdown Essential Safety Cases | Specification for Reactor Internals - Draft and issue RFS | 2019-04-02 | 2019-04-12 | 9 | 0 | 8 | 10 | 100% | 0.9 | 1 | Completed
ER6370LT | W201 | ER6370.A14285 | HNB Reactors Shutdown Essential Safety Cases | RFS - Specification for Reactor Internals Summary | 2019-04-02 | 2019-05-22 | 34 | 0 | 34 | 50 | 100% | 0.68 | 1 | Completed
ER6243LT | W200 | A10120 | REGION 1 Reactors Shutdown Safety Cases Programme | Incorporate SRD, Station, DA (peer) comments (HPB, HNB) | 2019-04-02 | 2019-04-30 | 10 | 0 | 18 | 28 | 100% | 0.35714 | 1 | Completed
ER6370LT | W201 | ER6370.A12255 | HNB Reactors Shutdown Essential Safety Cases | EPRI Tool Verified by TSA - HNB | 2019-04-03 | 2019-04-16 | 10 | 0 | 9 | 13 | 100% | 0.76923 | 1 | Completed
ER6243LT | W200 | A10280 | REGION 1 Reactors Shutdown Safety Cases Programme | Incorporate SRD, Station, DA (peer) comments (HYA, HAR) | 2019-04-03 | 2019-04-30 | 10 | 0 | 17 | 27 | 100% | 0.37037 | 1 | Completed
ER6370LT | W201 | ER6370.A15350 | HNB Reactors Shutdown Essential Safety Cases | HF Risk Assessment Draft Report - Supplier prepare and issue Offer | 2019-04-04 | 2019-04-08 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6370LT | W201 | ER6370.A13260 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final ALARP Strategy Document EAN | 2019-04-05 | 2019-04-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14540 | HNB Reactors Shutdown Essential Safety Cases | Claim 2 Containment Head Document - Draft and issue RFS | 2019-04-05 | 2019-04-12 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6370LT | W201 | ER6370.A14535 | HNB Reactors Shutdown Essential Safety Cases | RFS - Specification for Claim 2 Containment Head Document Summary | 2019-04-05 | 2019-05-29 | 35 | 0 | 35 | 54 | 100% | 0.64815 | 1 | Completed
ER6370LT | W201 | ER6370.A10290 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Prepare Specification for Tech Specs HEAD DOCUMENT Report | 2019-04-08 | 2019-05-02 | 17 | 0 | 16 | 24 | 100% | 0.70833 | 1 | Completed
ER6370LT | W201 | ER6370.A10285 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Specification for Tech Specs HEAD DOCUMENT Report Summary | 2019-04-08 | 2019-07-25 | 75 | 0 | 74 | 108 | 100% | 0.69444 | 1 | Completed
ER6370LT | W201 | ER6370.A13270 | HNB Reactors Shutdown Essential Safety Cases | ALARP Strategy Document EAN TR Completed and uploaded to CDMS | 2019-04-08 | 2019-04-23 | 10 | 0 | 9 | 15 | 100% | 0.66667 | 1 | Completed
ER6370LT | W201 | ER6370.A11320 | HNB Reactors Shutdown Essential Safety Cases | Stress Test EAN Version 0 Upload to CDMS | 2019-04-08 | 2019-04-12 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A14650 | HNB Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Based Faults) - Supplier prepare and issue Offer | 2019-04-08 | 2019-04-23 | 10 | 0 | 9 | 15 | 100% | 0.66667 | 1 | Completed
ER6370LT | W201 | ER6370.A14700 | HNB Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Hazards) - Supplier prepare and issue Offer | 2019-04-08 | 2019-04-23 | 10 | 0 | 9 | 15 | 100% | 0.66667 | 1 | Completed
ER6370LT | W201 | ER6370.A15100 | HNB Reactors Shutdown Essential Safety Cases | HF Compliance Assessment for Shutdown Margin - Supplier prepare and issue Offer | 2019-04-08 | 2019-04-15 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6370LT | W201 | ER6370.A15150 | HNB Reactors Shutdown Essential Safety Cases | HF Compliance / Tech Spec As'ment for Core Cooling - Supplier prepare and issue Offer | 2019-04-08 | 2019-04-15 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6370LT | W201 | ER6370.A15850 | HNB Reactors Shutdown Essential Safety Cases | Summary of Compliance with NSPs - Supplier prepare and issue Offer | 2019-04-08 | 2019-04-12 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A16030 | HNB Reactors Shutdown Essential Safety Cases | ALARP Framework Support for ALARP/BAT/BPM Report Version 0 Upload to CDMS | 2019-04-08 | 2019-04-12 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A14390 | HNB Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals - Draft and issue RFS | 2019-04-09 | 2019-04-15 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A14385 | HNB Reactors Shutdown Essential Safety Cases | RFS - Specification for Pressure Boundary Seals Summary | 2019-04-09 | 2019-05-17 | 26 | 0 | 26 | 38 | 100% | 0.68421 | 1 | Completed
ER6370LT | W201 | ER6370.A15360 | HNB Reactors Shutdown Essential Safety Cases | HF Risk Assessment Draft Report - Review Offer, prepare and issue CI | 2019-04-09 | 2019-04-10 | 2 | 0 | 1 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | ER6370.A15370 | HNB Reactors Shutdown Essential Safety Cases | HF Risk Assessment Draft Report - Supplier mobilisation time | 2019-04-11 | 2019-04-11 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A15790 | HNB Reactors Shutdown Essential Safety Cases | Boilers and Gas Circulator Performance - Draft and issue RFS | 2019-04-11 | 2019-04-17 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A4970 | HNB Reactors Shutdown Essential Safety Cases | C&I Review Authoring Completed and Issued | 2019-04-12 | 2019-04-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A15380 | HNB Reactors Shutdown Essential Safety Cases | HF Risk Assessment Draft Report - Pre Job Brief | 2019-04-12 | 2019-04-12 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A13100.E0 | REGION 1 Reactors Shutdown Safety Cases Programme | Draft NSRS Produced - HPB and HNB | 2019-04-15 | 2019-04-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A13110.E0 | REGION 1 Reactors Shutdown Safety Cases Programme | Draft NSRS Produced - HRA and HYA | 2019-04-15 | 2019-04-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3710 | HNB Reactors Shutdown Essential Safety Cases | Develop Defuelling Dataset Part 1 Completed | 2019-04-15 | 2019-04-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3870 | HNB Reactors Shutdown Essential Safety Cases | Model and Datasets Part 1 Completed | 2019-04-15 | 2019-04-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A10530 | HNB Reactors Shutdown Essential Safety Cases | Prepare ALARP / BAT/ BPM Draft Report | 2019-04-15 | 2019-07-16 | 63 | 0 | 62 | 92 | 100% | 0.68478 | 1 | Completed
ER6370LT | W201 | ER6370.A13990 | HNB Reactors Shutdown Essential Safety Cases | Component Life Assessment - Supplier prepare and issue Offer | 2019-04-15 | 2019-04-25 | 7 | 0 | 7 | 10 | 100% | 0.7 | 1 | Completed
ER6370LT | W201 | ER6370.A14100 | HNB Reactors Shutdown Essential Safety Cases | Specification for Standpipe and Guide Tube Integrity Assessment - Supplier prepare and issue Offer | 2019-04-15 | 2019-04-25 | 7 | 0 | 6 | 10 | 100% | 0.7 | 1 | Completed
ER6370LT | W201 | ER6370.A14200 | HNB Reactors Shutdown Essential Safety Cases | Specification for Degradation of Boilers - Supplier prepare and issue Offer | 2019-04-15 | 2019-04-26 | 8 | 0 | 7 | 11 | 100% | 0.72727 | 1 | Completed
ER6370LT | W201 | ER6370.A14300 | HNB Reactors Shutdown Essential Safety Cases | Specification for Reactor Internals - Supplier prepare and issue Offer | 2019-04-15 | 2019-05-06 | 13 | 0 | 13 | 21 | 100% | 0.61905 | 1 | Completed
ER6370LT | W201 | ER6370.A14550 | HNB Reactors Shutdown Essential Safety Cases | Claim 2 Containment Head Document - Supplier prepare and issue Offer | 2019-04-15 | 2019-05-03 | 13 | 0 | 12 | 18 | 100% | 0.72222 | 1 | Completed
ER6370LT | W201 | ER6370.A15860 | HNB Reactors Shutdown Essential Safety Cases | Summary of Compliance with NSPs - Review Offer, prepare and issue CI | 2019-04-15 | 2019-04-16 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | ER6370.A15960 | HNB Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity - Review Offer, prepare and issue CI | 2019-04-15 | 2019-04-16 | 2 | 0 | 1 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | ER6370.A10780 | HNB Reactors Shutdown Essential Safety Cases | Current Code Applicability Range TR Completed and uploaded to CDMS | 2019-04-16 | 2019-04-30 | 9 | 0 | 8 | 14 | 100% | 0.64286 | 1 | Completed
ER6370LT | W201 | ER6370.A12265 | HNB Reactors Shutdown Essential Safety Cases | Verified EPRI Tool Issued to Station for Review - HNB | 2019-04-16 | 2019-04-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14400 | HNB Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals - Supplier prepare and issue Offer | 2019-04-16 | 2019-04-22 | 3 | 0 | 3 | 6 | 100% | 0.5 | 1 | Completed
ER6370LT | W201 | ER6370.A15110 | HNB Reactors Shutdown Essential Safety Cases | HF Compliance Assessment for Shutdown Margin - Review Offer, prepare and issue CI | 2019-04-16 | 2019-04-17 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | ER6370.A15160 | HNB Reactors Shutdown Essential Safety Cases | HF Compliance / Tech Spec As'ment for Core Cooling - Review Offer, prepare and issue CI | 2019-04-16 | 2019-04-17 | 2 | 0 | 1 | 1 | 100% | 2 | 1 | Completed
ER6243LT | W200 | A10290 | REGION 1 Reactors Shutdown Safety Cases Programme | DA & SRD agree NSRS (for authorised designers-NSRS must be reviewed by DA) (HYA, HAR) | 2019-04-17 | 2019-04-30 | 10 | 0 | 7 | 13 | 100% | 0.76923 | 1 | Completed
ER6370LT | W201 | ER6370.A12275 | HNB Reactors Shutdown Essential Safety Cases | EPRI Tool Reviewed by Station - HNB | 2019-04-17 | 2019-04-26 | 6 | 0 | 5 | 9 | 100% | 0.66667 | 1 | Completed
ER6370LT | W201 | ER6370.A15870 | HNB Reactors Shutdown Essential Safety Cases | Summary of Compliance with NSPs - Supplier mobilisation time | 2019-04-17 | 2019-04-23 | 3 | 0 | 2 | 6 | 100% | 0.5 | 1 | Completed
ER6370LT | W201 | ER6370.A15970 | HNB Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity - Supplier mobilisation time | 2019-04-17 | 2019-04-18 | 2 | 0 | 1 | 1 | 100% | 2 | 1 | Completed
ER6243LT | W200 | A10150 | REGION 1 Reactors Shutdown Safety Cases Programme | DA & SRD agree NSRS (for authorised designers-NSRS must be reviewed by DA) (HPB, HNB) | 2019-04-17 | 2019-04-30 | 10 | 0 | 7 | 13 | 100% | 0.76923 | 1 | Completed
ER6370LT | W201 | ER6370.A3880 | HNB Reactors Shutdown Essential Safety Cases | Validate Model and Datasets Part 2 (See Steps) | 2019-04-18 | 2019-07-12 | 58 | 0 | 57 | 85 | 100% | 0.68235 | 1 | Completed
ER6370LT | W201 | ER6370.A3875 | HNB Reactors Shutdown Essential Safety Cases | Validate Model and Datasets Part 2 Summary | 2019-04-18 | 2019-11-29 | 156 | 0 | 156 | 225 | 100% | 0.69333 | 1 | Completed
ER6370LT | W201 | ER6370.A15120 | HNB Reactors Shutdown Essential Safety Cases | HF Compliance Assessment for Shutdown Margin - Supplier mobilisation time | 2019-04-18 | 2019-04-29 | 6 | 0 | 5 | 11 | 100% | 0.54545 | 1 | Completed
ER6370LT | W201 | ER6370.A15800 | HNB Reactors Shutdown Essential Safety Cases | Boilers and Gas Circulator Performance - Supplier prepare and issue Offer | 2019-04-18 | 2019-05-10 | 14 | 0 | 13 | 22 | 100% | 0.63636 | 1 | Completed
ER6370LT | W201 | ER6370.A15170 | HNB Reactors Shutdown Essential Safety Cases | HF Compliance / Tech Spec As'ment for Core Cooling - Supplier mobilisation time | 2019-04-18 | 2019-04-29 | 6 | 0 | 5 | 11 | 100% | 0.54545 | 1 | Completed
ER6370LT | W201 | ER6370.A10330 | HNB Reactors Shutdown Essential Safety Cases | Prepare Structures and Equipment Integrity Draft Report | 2019-04-19 | 2019-07-05 | 52 | 0 | 51 | 77 | 100% | 0.67532 | 1 | Completed
ER6370LT | W201 | ER6370.A10325 | HNB Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity Summary | 2019-04-19 | 2019-10-21 | 126 | 0 | 126 | 185 | 100% | 0.68108 | 1 | Completed
ER6370LT | W201 | ER6370.A15980 | HNB Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity - Pre Job Brief | 2019-04-19 | 2019-04-19 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A5560 | HNB Reactors Shutdown Essential Safety Cases | Prepare HF Risk Assessment Draft Report | 2019-04-23 | 2019-09-09 | 97 | 0 | 96 | 139 | 100% | 0.69784 | 1 | Completed
ER6370LT | W201 | ER6370.A5555 | HNB Reactors Shutdown Essential Safety Cases | HF Risk Assessment Summary | 2019-04-23 | 2019-11-01 | 136 | 0 | 136 | 192 | 100% | 0.70833 | 1 | Completed
ER6370LT | W201 | ER6370.A13280 | HNB Reactors Shutdown Essential Safety Cases | ALARP Strategy Document EAN Completed | 2019-04-23 | 2019-04-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14410 | HNB Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals - Review Offer, prepare and issue CI | 2019-04-23 | 2019-04-26 | 4 | 0 | 3 | 3 | 100% | 1.3333 | 1 | Completed
ER6370LT | W201 | ER6370.A14660 | HNB Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Based Faults) - Review Offer, prepare and issue CI | 2019-04-24 | 2019-05-01 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6370LT | W201 | ER6370.A14710 | HNB Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Hazards) - Review Offer, prepare and issue CI | 2019-04-24 | 2019-05-01 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6370LT | W201 | ER6370.A15880 | HNB Reactors Shutdown Essential Safety Cases | Summary of Compliance with NSPs - Pre Job Brief | 2019-04-24 | 2019-04-24 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A10960 | HNB Reactors Shutdown Essential Safety Cases | Issued Scope Additional SDM Calcs Draft Report to EDF for Review. | 2019-04-26 | 2019-04-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A10970 | HNB Reactors Shutdown Essential Safety Cases | Scope Additional SDM Calcs Draft Report Reviewed by EDF SQEP | 2019-04-26 | 2019-05-17 | 15 | 0 | 15 | 21 | 100% | 0.71429 | 1 | Completed
ER6370LT | W201 | ER6370.A14110 | HNB Reactors Shutdown Essential Safety Cases | Specification for Standpipe and Guide Tube Integrity Assessment - Review Offer, prepare and issue CI | 2019-04-26 | 2019-05-06 | 6 | 0 | 6 | 10 | 100% | 0.6 | 1 | Completed
ER6370LT | W201 | ER6370.A13520 | HNB Reactors Shutdown Essential Safety Cases | SDM Assessments with Uncertainties - Pre Job Brief | 2019-04-29 | 2019-04-29 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13840 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Margin Head Document - Supplier prepare and issue Offer (Not Req'd) | 2019-04-29 | 2019-04-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13850 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Margin Head Document - Review Offer, prepare and issue CI (Not Req'd) | 2019-04-29 | 2019-04-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13860 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Margin Head Document - Supplier mobilisation time (Not Req'd) | 2019-04-29 | 2019-04-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14000 | HNB Reactors Shutdown Essential Safety Cases | Component Life Assessment - Review Offer, prepare and issue CI | 2019-04-29 | 2019-05-06 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6370LT | W201 | ER6370.A14210 | HNB Reactors Shutdown Essential Safety Cases | Specification for Degradation of Boilers - Review Offer, prepare and issue CI | 2019-04-29 | 2019-05-06 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6370LT | W201 | ER6370.A14420 | HNB Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals - Supplier mobilisation time | 2019-04-29 | 2019-05-16 | 13 | 0 | 12 | 17 | 100% | 0.76471 | 1 | Completed
ER6243LT | W200 | A10130 | REGION 1 Reactors Shutdown Safety Cases Programme | Issue final NSRS (HPB, HNB) | 2019-04-30 | 2019-04-30 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A10230 | REGION 1 Reactors Shutdown Safety Cases Programme | Issue final NSRS (HYA, HAR) | 2019-04-30 | 2019-04-30 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7280 | HNB Reactors Shutdown Essential Safety Cases | Issue Final Code Validation from Operational Reactor Report | 2019-04-30 | 2019-04-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7460 | HNB Reactors Shutdown Essential Safety Cases | Issued Flux Detection Scoping Draft Report to EDF for Review. | 2019-04-30 | 2019-04-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7590 | HNB Reactors Shutdown Essential Safety Cases | Prepare SDM Assessments with uncertainties / sensitivity studies Draft Report | 2019-04-30 | 2019-07-02 | 44 | 0 | 43 | 63 | 100% | 0.69841 | 1 | Completed
ER6370LT | W201 | ER6370.A8400 | HNB Reactors Shutdown Essential Safety Cases | Issue Final Pressure Boundary Seals Specification | 2019-04-30 | 2019-04-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A10790 | HNB Reactors Shutdown Essential Safety Cases | Current Code Applicability Range Completed | 2019-04-30 | 2019-04-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A11030 | HNB Reactors Shutdown Essential Safety Cases | Issue Final SDM Assumptions Document Report Report | 2019-04-30 | 2019-04-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7585 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 1) Summary | 2019-04-30 | 2019-11-14 | 139 | 0 | 139 | 198 | 100% | 0.70202 | 1 | Completed
ER6370LT | W201 | ER6370.A14280 | HNB Reactors Shutdown Essential Safety Cases | Ass'ment of Graphite behaviour for Shutdown Defuelling - Pre Job Brief | 2019-04-30 | 2019-04-30 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A15130 | HNB Reactors Shutdown Essential Safety Cases | HF Compliance Assessment for Shutdown Margin - Pre Job Brief | 2019-04-30 | 2019-04-30 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A15180 | HNB Reactors Shutdown Essential Safety Cases | HF Compliance / Tech Spec As'ment for Core Cooling - Pre Job Brief | 2019-04-30 | 2019-04-30 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3320 | HNB Reactors Shutdown Essential Safety Cases | Prepare Ass'ment of Graphite behaviour for Shutdown Defuelling Draft Report | 2019-05-01 | 2019-05-30 | 20 | 0 | 20 | 29 | 100% | 0.68966 | 1 | Completed
ER6370LT | W201 | ER6370.A3500 | HNB Reactors Shutdown Essential Safety Cases | Issue MACE code v3.2.2 defuelling prototype model Issued to EDF for Review. | 2019-05-01 | 2019-05-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3720 | HNB Reactors Shutdown Essential Safety Cases | Prepare Defuelling Dataset QA Grade 2 Part 2 Report | 2019-05-01 | 2019-12-20 | 165 | 0 | 164 | 233 | 100% | 0.70815 | 1 | Completed
ER6370LT | W201 | ER6370.A7290 | HNB Reactors Shutdown Essential Safety Cases | Code Validation from Operational Reactor Report Completed and Uploaded to CDMS | 2019-05-01 | 2019-06-28 | 41 | 0 | 40 | 58 | 100% | 0.7069 | 1 | Completed
ER6370LT | W201 | ER6370.A7470 | HNB Reactors Shutdown Essential Safety Cases | Flux Detection Scoping Draft Report Reviewed by EDF SQEP | 2019-05-01 | 2019-05-31 | 21 | 0 | 20 | 30 | 100% | 0.7 | 1 | Completed
ER6370LT | W201 | ER6370.A8040 | HNB Reactors Shutdown Essential Safety Cases | Specifications for RADCONs Completed | 2019-05-01 | 2019-05-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8050 | HNB Reactors Shutdown Essential Safety Cases | Specifications for Fault Schedule Review Completed | 2019-05-01 | 2019-05-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8410 | HNB Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals Specification Completed and uploaded to CDMS | 2019-05-01 | 2019-05-31 | 21 | 0 | 20 | 30 | 100% | 0.7 | 1 | Completed
ER6370LT | W201 | ER6370.A10610 | HNB Reactors Shutdown Essential Safety Cases | Prepare In Reactor NSP Compliance and Risk Draft Report | 2019-05-01 | 2019-07-19 | 56 | 0 | 55 | 79 | 100% | 0.70886 | 1 | Completed
ER6370LT | W201 | ER6370.A3315 | HNB Reactors Shutdown Essential Safety Cases | Assessment of Graphite behaviour for Shutdown Defuelling Summary | 2019-05-01 | 2019-09-02 | 85 | 0 | 85 | 124 | 100% | 0.68548 | 1 | Completed
ER6370LT | W201 | ER6370.A3715 | HNB Reactors Shutdown Essential Safety Cases | Develop Defuelling Dataset Part 2 Summary | 2019-05-01 | 2020-03-27 | 232 | 0 | 231 | 331 | 100% | 0.70091 | 1 | Completed
ER6370LT | W201 | ER6370.A10605 | HNB Reactors Shutdown Essential Safety Cases | In Reactor NSP Compliance and Risk Report Summary | 2019-05-01 | 2019-11-15 | 139 | 0 | 139 | 198 | 100% | 0.70202 | 1 | Completed
ER6370LT | W201 | ER6370.A3475 | HNB Reactors Shutdown Essential Safety Cases | MACE Develop Code Summary | 2019-05-01 | 2019-05-24 | 17 | 0 | 17 | 23 | 100% | 0.73913 | 1 | Completed
ER6370LT | W201 | ER6370.A12285 | HNB Reactors Shutdown Essential Safety Cases | Address Station Comments on EPRI Tool - HNB | 2019-05-01 | 2019-05-15 | 10 | 0 | 10 | 14 | 100% | 0.71429 | 1 | Completed
ER6370LT | W201 | ER6370.A16050 | HNB Reactors Shutdown Essential Safety Cases | Prepare Impacts for the Order of Defuelling Draft EAN | 2019-05-01 | 2019-05-21 | 14 | 0 | 13 | 20 | 100% | 0.7 | 1 | Completed
ER6370LT | W201 | ER6370.A16040 | HNB Reactors Shutdown Essential Safety Cases | Impacts for the Order of Defuelling Summary | 2019-05-01 | 2019-08-27 | 81 | 0 | 81 | 118 | 100% | 0.68644 | 1 | Completed
ER6378LT | W222 | W222.A14060 | HRA Fuel Handling Essential Safety Case | Project Definition Document (PDD) | 2019-05-01 | 2019-09-02 | 86 | 0 | 86 | 124 | 100% | 0.69355 | 1 | Completed
ER6378LT | W222 | W222.A14050 | HRA Fuel Handling Essential Safety Case | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 2019-05-01 | 2019-09-02 | 86 | 0 | 86 | 124 | 100% | 0.69355 | 1 | Completed
ER6650LT | W226 | W226.A14050 | HYA Fuel Handling Essential Safety Case | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 2019-05-01 | 2019-09-02 | 86 | 0 | 86 | 124 | 100% | 0.69355 | 1 | Completed
ER6650LT | W226 | W226.A14060 | HYA Fuel Handling Essential Safety Case | Project Definition Document (PDD) | 2019-05-01 | 2019-09-02 | 86 | 0 | 86 | 124 | 100% | 0.69355 | 1 | Completed
ER6370LT | W201 | ER6370.A3510 | HNB Reactors Shutdown Essential Safety Cases | Verify MACE code v3.2.2 defuelling prototype model Reviewed by EDF SQEP | 2019-05-01 | 2019-05-15 | 10 | 0 | 10 | 14 | 100% | 0.71429 | 1 | Completed
ER6243LT | W200 | A10340 | REGION 1 Reactors Shutdown Safety Cases Programme | NSRS agreed by stakeholders EC 363682 & 363676 <NSRS SC Approach & Outline> (Cat 1 Milestone) (HYA, HAR) | 2019-05-02 | 2019-05-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A10370 | REGION 1 Reactors Shutdown Safety Cases Programme | NSRS Presented to NSC (for complex CAT 1 cases) (HYA, HAR) | 2019-05-02 | 2019-05-03 | 1 | 0 | 1 | 1 | 100% | 1 | 1 | Completed
ER6243LT | W200 | A17240 | REGION 1 Reactors Shutdown Safety Cases Programme | NSRS agreed by stakeholders EC 363682 & 363676 <NSRS SC Approach & Outline> (Cat 1 Milestone) (HYA, HAR) | 2019-05-02 | 2019-05-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14670 | HNB Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Based Faults) - Supplier mobilisation time | 2019-05-02 | 2019-05-16 | 10 | 0 | 9 | 14 | 100% | 0.71429 | 1 | Completed
ER6370LT | W201 | ER6370.A14720 | HNB Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Hazards) - Supplier mobilisation time | 2019-05-02 | 2019-05-16 | 10 | 0 | 10 | 14 | 100% | 0.71429 | 1 | Completed
ER6370LT | W201 | ER6370.A14950 | HNB Reactors Shutdown Essential Safety Cases | Boiler Control and Protection Draft Report - Supplier prepare and issue Offer | 2019-05-02 | 2019-05-14 | 8 | 0 | 7 | 12 | 100% | 0.66667 | 1 | Completed
ER6370LT | W201 | ER6370.A15000 | HNB Reactors Shutdown Essential Safety Cases | Reactor Cooling Systems Draft Report - Supplier prepare and issue Offer | 2019-05-02 | 2019-05-14 | 8 | 0 | 7 | 12 | 100% | 0.66667 | 1 | Completed
ER6243LT | W200 | A10250 | REGION 1 Reactors Shutdown Safety Cases Programme | Circulate NSRS for Relevant Stakeholders (HYA, HAR) | 2019-05-03 | 2019-05-13 | 5 | 0 | 5 | 10 | 100% | 0.5 | 1 | Completed
ER6370LT | W201 | ER6370.A15590 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Tech Specs HEAD DOCUMENT Report - Draft and issue RFS | 2019-05-03 | 2019-05-10 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6370LT | W201 | ER6370.A14010 | HNB Reactors Shutdown Essential Safety Cases | Component Life Assessment - Supplier mobilisation time | 2019-05-07 | 2019-05-21 | 11 | 0 | 10 | 14 | 100% | 0.78571 | 1 | Completed
ER6370LT | W201 | ER6370.A14120 | HNB Reactors Shutdown Essential Safety Cases | Specification for Standpipe and Guide Tube Integrity Assessment - Supplier mobilisation time | 2019-05-07 | 2019-05-21 | 11 | 0 | 10 | 14 | 100% | 0.78571 | 1 | Completed
ER6370LT | W201 | ER6370.A14220 | HNB Reactors Shutdown Essential Safety Cases | Specification for Degradation of Boilers - Supplier mobilisation time | 2019-05-07 | 2019-05-21 | 11 | 0 | 10 | 14 | 100% | 0.78571 | 1 | Completed
ER6370LT | W201 | ER6370.A14310 | HNB Reactors Shutdown Essential Safety Cases | Specification for Reactor Internals - Review Offer, prepare and issue CI | 2019-05-07 | 2019-05-14 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6370LT | W201 | ER6370.A14560 | HNB Reactors Shutdown Essential Safety Cases | Claim 2 Containment Head Document - Review Offer, prepare and issue CI | 2019-05-07 | 2019-05-13 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6243LT | W200 | A1130 | REGION 1 Reactors Shutdown Safety Cases Programme | NSRS Complete - HPB and HNB | 2019-05-08 | 2019-05-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A1140 | REGION 1 Reactors Shutdown Safety Cases Programme | NSRS Complete - HRA and HYA | 2019-05-08 | 2019-05-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A1150.E0 | REGION 1 Reactors Shutdown Safety Cases Programme | Safety Case Submitted (Including Submission to INSA, NSC and ONR if required) HPB and HNB | 2019-05-08 | 2019-05-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A1160.E0 | REGION 1 Reactors Shutdown Safety Cases Programme | Safety Case Submitted (Including Submission to INSA, NSC and ONR if required) HRA and HYA | 2019-05-08 | 2019-05-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A1170 | REGION 1 Reactors Shutdown Safety Cases Programme | First Reactor Implementation plan Complete & close-out (One for each of HPB and HNB) | 2019-05-08 | 2019-05-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A10170 | REGION 1 Reactors Shutdown Safety Cases Programme | NSRS agreed by stakeholders EC 363701 & 364023 <NSRS SC Approach & Outline> (Cat 1 Milestone) (HPB, HNB) | 2019-05-08 | 2019-05-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A13090 | REGION 1 Reactors Shutdown Safety Cases Programme | NSRS Agreed by Stakeholders - HPB and HNB | 2019-05-08 | 2019-05-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A13120 | REGION 1 Reactors Shutdown Safety Cases Programme | NSRS Agreed by Stakeholders - HRA and HYA | 2019-05-08 | 2019-05-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A17230 | REGION 1 Reactors Shutdown Safety Cases Programme | NSRS agreed by stakeholders EC 363701 & 364023 <NSRS SC Approach & Outline> (Cat 1 Milestone) (HPB, HNB) | 2019-05-08 | 2019-05-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7320 | HNB Reactors Shutdown Essential Safety Cases | Issued DNB Commissiong Core Validation Scoping Draft Report to EDF for Review. | 2019-05-08 | 2019-05-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7330 | HNB Reactors Shutdown Essential Safety Cases | DNB Commissiong Core Validation Scoping Draft Report Reviewed by EDF SQEP | 2019-05-09 | 2020-02-07 | 192 | 0 | 191 | 274 | 100% | 0.70073 | 1 | Completed
ER6243LT | W200 | A1220 | REGION 1 Reactors Shutdown Safety Cases Programme | NSRS Presented to NSC (for complex CAT 1 cases) (HPB, HNB) | 2019-05-09 | 2019-05-09 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A10180 | REGION 1 Reactors Shutdown Safety Cases Programme | Circulate NSRS for Relevant Stakeholders (HPB, HNB) | 2019-05-10 | 2019-05-13 | 5 | 0 | 2 | 3 | 100% | 1.6667 | 1 | Completed
ER6370LT | W201 | ER6370.A11350 | HNB Reactors Shutdown Essential Safety Cases | ALARP Strategy Note | 2019-05-10 | 2019-05-31 | 15 | 0 | 14 | 21 | 100% | 0.71429 | 1 | Completed
ER6370LT | W201 | ER6370.A3240 | HNB Reactors Shutdown Essential Safety Cases | Prepare Gas Chemistry Assessment Draft Report | 2019-05-13 | 2019-08-23 | 74 | 0 | 73 | 102 | 100% | 0.72549 | 1 | Completed
ER6370LT | W201 | ER6370.A3235 | HNB Reactors Shutdown Essential Safety Cases | Gas Chemistry Assessment Summary | 2019-05-13 | 2019-11-29 | 142 | 0 | 142 | 200 | 100% | 0.71 | 1 | Completed
ER6370LT | W201 | ER6370.A15600 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Tech Specs HEAD DOCUMENT Report - Supplier prepare and issue Offer | 2019-05-13 | 2019-05-17 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A15810 | HNB Reactors Shutdown Essential Safety Cases | Boilers and Gas Circulator Performance - Review Offer, prepare and issue CI | 2019-05-13 | 2019-05-17 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6243LT | W200 | A1190 | REGION 1 Reactors Shutdown Safety Cases Programme | Send NSRS to ONR to determine level of review required (Acknowledgement or Agreement) (HPB, HNB) | 2019-05-14 | 2019-05-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A10360 | REGION 1 Reactors Shutdown Safety Cases Programme | Send NSRS to ONR to determine level of review required (Acknowledgement or Agreement) (HYA, HAR) | 2019-05-14 | 2019-05-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7000 | HNB Reactors Shutdown Essential Safety Cases | Prepare Boiler Supporting Systems Draft EAN | 2019-05-14 | 2019-08-27 | 74 | 0 | 73 | 105 | 100% | 0.70476 | 1 | Completed
ER6370LT | W201 | ER6370.A14570 | HNB Reactors Shutdown Essential Safety Cases | Claim 2 Containment Head Document - Supplier mobilisation time | 2019-05-14 | 2019-05-28 | 10 | 0 | 10 | 14 | 100% | 0.71429 | 1 | Completed
ER6370LT | W201 | ER6370.A12295 | HNB Reactors Shutdown Essential Safety Cases | Issue EPRI Tool for functional use - HNB | 2019-05-15 | 2019-05-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13320 | HNB Reactors Shutdown Essential Safety Cases | Verified Implementation Strategy Document Draft EAN Issued to EDF for Technical Review. | 2019-05-15 | 2019-05-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14320 | HNB Reactors Shutdown Essential Safety Cases | Specification for Reactor Internals - Supplier mobilisation time | 2019-05-15 | 2019-05-21 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A14960 | HNB Reactors Shutdown Essential Safety Cases | Boiler Control and Protection Draft Report - Review Offer, prepare and issue CI | 2019-05-15 | 2019-05-20 | 4 | 0 | 3 | 5 | 100% | 0.8 | 1 | Completed
ER6370LT | W201 | ER6370.A15010 | HNB Reactors Shutdown Essential Safety Cases | Reactor Cooling Systems Draft Report - Review Offer, prepare and issue CI | 2019-05-15 | 2019-05-20 | 4 | 0 | 3 | 5 | 100% | 0.8 | 1 | Completed
ER6370LT | W201 | ER6370.A3520 | HNB Reactors Shutdown Essential Safety Cases | Address Comments from EDF Review on MACE code v3.2.2 defuelling prototype model | 2019-05-16 | 2019-05-22 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A13330 | HNB Reactors Shutdown Essential Safety Cases | Implementation Strategy Document Draft EAN Technically Reviewed by EDF SQEP | 2019-05-16 | 2019-05-17 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6243LT | W200 | ER6243.A1490 | REGION 1 Reactors Shutdown Safety Cases Programme | Confirm Objectives to be Delivered at Gate B | 2019-05-17 | 2019-05-23 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A10980 | HNB Reactors Shutdown Essential Safety Cases | Issue Findings on Scope Additional SDM Calcs | 2019-05-17 | 2019-05-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13420 | HNB Reactors Shutdown Essential Safety Cases | Safety Rod Insertion Scoping - Pre Job Brief | 2019-05-17 | 2019-05-17 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14430 | HNB Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals - Pre Job Brief | 2019-05-17 | 2019-05-17 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14680 | HNB Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Based Faults) - Pre Job Brief | 2019-05-17 | 2019-05-17 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14730 | HNB Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Hazards) - Pre Job Brief | 2019-05-17 | 2019-05-17 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3160 | HNB Reactors Shutdown Essential Safety Cases | Prepare Pressure Boundary Seals Draft Report | 2019-05-20 | 2019-07-12 | 39 | 0 | 38 | 53 | 100% | 0.73585 | 1 | Completed
ER6370LT | W201 | ER6370.A4360 | HNB Reactors Shutdown Essential Safety Cases | Prepare Fault Schedule Review (Plant Based Faults) Draft Report | 2019-05-20 | 2019-06-24 | 25 | 0 | 24 | 35 | 100% | 0.71429 | 1 | Completed
ER6370LT | W201 | ER6370.A4440 | HNB Reactors Shutdown Essential Safety Cases | Prepare Fault Schedule Review (Harzards) Draft Report | 2019-05-20 | 2019-06-24 | 25 | 0 | 24 | 35 | 100% | 0.71429 | 1 | Completed
ER6370LT | W201 | ER6370.A3155 | HNB Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals Summary | 2019-05-20 | 2019-09-13 | 82 | 0 | 82 | 116 | 100% | 0.7069 | 1 | Completed
ER6370LT | W201 | ER6370.A4355 | HNB Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Based Faults) Summary | 2019-05-20 | 2019-12-23 | 153 | 0 | 153 | 217 | 100% | 0.70507 | 1 | Completed
ER6370LT | W201 | ER6370.A4435 | HNB Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Harzards) Summary | 2019-05-20 | 2019-12-23 | 153 | 0 | 153 | 217 | 100% | 0.70507 | 1 | Completed
ER6370LT | W201 | ER6370.A13340 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Implementation Strategy Document Draft EAN | 2019-05-20 | 2019-05-22 | 3 | 0 | 2 | 2 | 100% | 1.5 | 1 | Completed
ER6370LT | W201 | ER6370.A13430 | HNB Reactors Shutdown Essential Safety Cases | Uncertainty in SDM Calculations - Task Control Sheet | 2019-05-20 | 2019-06-07 | 14 | 0 | 14 | 18 | 100% | 0.77778 | 1 | Completed
ER6370LT | W201 | ER6370.A13425 | HNB Reactors Shutdown Essential Safety Cases | Task Control Sheet - Uncertainty in SDM Calculations Summary | 2019-05-20 | 2019-06-07 | 14 | 0 | 14 | 18 | 100% | 0.77778 | 1 | Completed
ER6370LT | W201 | ER6370.A15610 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Tech Specs HEAD DOCUMENT Report - Review Offer, prepare and issue CI | 2019-05-20 | 2019-05-21 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | ER6370.A15820 | HNB Reactors Shutdown Essential Safety Cases | Boilers and Gas Circulator Performance - Supplier mobilisation time | 2019-05-20 | 2019-05-22 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6370LT | W201 | ER6370.A14970 | HNB Reactors Shutdown Essential Safety Cases | Boiler Control and Protection Draft Report - Supplier mobilisation time | 2019-05-21 | 2019-05-22 | 2 | 0 | 1 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | ER6370.A15020 | HNB Reactors Shutdown Essential Safety Cases | Reactor Cooling Systems Draft Report - Supplier mobilisation time | 2019-05-21 | 2019-05-22 | 2 | 0 | 1 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | ER6370.A3530 | HNB Reactors Shutdown Essential Safety Cases | Issue Final Validated MACE code v3.2.2 defuelling prototype model | 2019-05-22 | 2019-05-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13350 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Implementation Strategy Document EAN | 2019-05-22 | 2019-05-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14020 | HNB Reactors Shutdown Essential Safety Cases | Component Life Assessment - Pre Job Brief | 2019-05-22 | 2019-05-22 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14130 | HNB Reactors Shutdown Essential Safety Cases | Specification for Standpipe and Guide Tube Integrity Assessment - Pre Job Brief | 2019-05-22 | 2019-05-22 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14230 | HNB Reactors Shutdown Essential Safety Cases | Specification for Degradation of Boilers - Pre Job Brief | 2019-05-22 | 2019-05-22 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14330 | HNB Reactors Shutdown Essential Safety Cases | Specification for Reactor Internals - Pre Job Brief | 2019-05-22 | 2019-05-22 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A15620 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Tech Specs HEAD DOCUMENT Report - Supplier mobilisation time | 2019-05-22 | 2019-05-29 | 5 | 0 | 4 | 7 | 100% | 0.71429 | 1 | Completed
ER6370LT | W201 | ER6370.A16060 | HNB Reactors Shutdown Essential Safety Cases | Impacts for the Order of Defuelling Draft EAN Verified by TSA | 2019-05-22 | 2019-06-04 | 9 | 0 | 9 | 13 | 100% | 0.69231 | 1 | Completed
ER6370LT | W201 | ER6370.A3540 | HNB Reactors Shutdown Essential Safety Cases | Validated MACE code v3.2.2 defuelling prototype model Completed and uploaded to CDMS | 2019-05-23 | 2019-05-24 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | ER6370.A8140 | HNB Reactors Shutdown Essential Safety Cases | Prepare Component Life Assessment Specification | 2019-05-23 | 2019-05-27 | 2 | 0 | 2 | 4 | 100% | 0.5 | 1 | Completed
ER6370LT | W201 | ER6370.A8220 | HNB Reactors Shutdown Essential Safety Cases | Prepare Standpipe and Guide Tube Integrity Assessment Specification | 2019-05-23 | 2019-05-27 | 2 | 0 | 2 | 4 | 100% | 0.5 | 1 | Completed
ER6370LT | W201 | ER6370.A8290 | HNB Reactors Shutdown Essential Safety Cases | Prepare Degradation of Boilers Specification | 2019-05-23 | 2019-05-27 | 2 | 0 | 2 | 4 | 100% | 0.5 | 1 | Completed
ER6370LT | W201 | ER6370.A11040 | HNB Reactors Shutdown Essential Safety Cases | SDM Assumptions Document Report Completed and Uploaded to CDMS | 2019-05-23 | 2019-05-31 | 6 | 0 | 5 | 8 | 100% | 0.75 | 1 | Completed
ER6370LT | W201 | ER6370.A11090 | HNB Reactors Shutdown Essential Safety Cases | Standpipe and Guide Tube Integrity Assessment Specification Summary | 2019-05-23 | 2019-05-31 | 6 | 0 | 6 | 8 | 100% | 0.75 | 1 | Completed
ER6370LT | W201 | ER6370.A8285 | HNB Reactors Shutdown Essential Safety Cases | Degradation of Boilers Specification Summary | 2019-05-23 | 2019-05-31 | 5 | 0 | 5 | 8 | 100% | 0.625 | 1 | Completed
ER6370LT | W201 | ER6370.A8135 | HNB Reactors Shutdown Essential Safety Cases | Component Life Assessment Specification Summary | 2019-05-23 | 2019-05-31 | 5 | 0 | 5 | 8 | 100% | 0.625 | 1 | Completed
ER6370LT | W201 | ER6370.A13360 | HNB Reactors Shutdown Essential Safety Cases | Implementation Strategy Document EAN TR Completed and uploaded to CDMS | 2019-05-23 | 2019-05-31 | 6 | 0 | 5 | 8 | 100% | 0.75 | 1 | Completed
ER6370LT | W201 | ER6370.A14980 | HNB Reactors Shutdown Essential Safety Cases | Boiler Control and Protection Draft Report - Pre Job Brief | 2019-05-23 | 2019-05-23 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A15030 | HNB Reactors Shutdown Essential Safety Cases | Reactor Cooling Systems Draft Report - Pre Job Brief | 2019-05-23 | 2019-05-23 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1070 | HRA Reactors Shutdown Essential Safety Cases | Phase 2 Project Start [FEEDS TO SUMMARY SCHEDULE] | 2019-05-23 | 2019-05-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1000 | HRA Reactors Shutdown Essential Safety Cases | Confirm Objectives to be Delivered at Gate B (FEEDS TO SUMMARY SCHEDULE) | 2019-05-23 | 2019-05-24 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6371LT | W202 | W202.A1080 | HRA Reactors Shutdown Essential Safety Cases | Actuals (PS - 29-Feb-2020) | 2019-05-23 | 2020-02-29 | 197 | 0 | 197 | 282 | 100% | 0.69858 | 1 | Completed
ER6661LT | W206 | W206.A1070 | HYA Reactors Shutdown Essential Safety Cases | Phase 2 Project Start [FEEDS TO SUMMARY SCHEDULE] | 2019-05-23 | 2019-05-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1000 | HYA Reactors Shutdown Essential Safety Cases | Confirm Objectives to be Delivered at Gate B [FEEDS TO SUMMARY SCHEDULE] | 2019-05-23 | 2019-05-24 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6661LT | W206 | W206.A1080 | HYA Reactors Shutdown Essential Safety Cases | Actuals (PS - 29-Feb-2020) | 2019-05-23 | 2020-02-29 | 197 | 0 | 197 | 282 | 100% | 0.69858 | 1 | Completed
ER6371LT | W202 | W202.A10101 | HRA Reactors Shutdown Essential Safety Cases | Summary for HRA Reactors Shutdown Essential Safety Cases W202 | 2019-05-23 | 2025-02-07 | 1 | 0 | 1445 | 2087 | 100% | 0.00047916 | 1 | Completed
ER6661LT | W206 | W202.A1010 | HYA Reactors Shutdown Essential Safety Cases | Summary for HYA Reactors Shutdown Essential Safety Cases W206 | 2019-05-23 | 2025-02-07 | 1 | 0 | 1445 | 2087 | 100% | 0.00047916 | 1 | Completed
ER6661LT | W206 | W206.A2206740 | HYA Reactors Shutdown Essential Safety Cases | Actuals (PS - 31-Mar-2023) | 2019-05-23 | 2023-03-31 | 197 | 0 | 976 | 1408 | 100% | 0.13991 | 1 | Completed
ER6370LT | W201 | ER6370.A15830 | HNB Reactors Shutdown Essential Safety Cases | Boilers and Gas Circulator Performance - Pre Job Brief | 2019-05-23 | 2019-05-23 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206740 | HRA Reactors Shutdown Essential Safety Cases | Actuals (PS - 31-Mar-2023) | 2019-05-23 | 2023-03-31 | 977 | 0 | 977 | 1408 | 100% | 0.69389 | 1 | Completed
ER6244LT | W220 | A8180.E0 | REGION 1 Defuelling Programme Fuel Handling Safety Case | [PR KDM] NSRS for HPB and HNB agreed by stakeholders - Defuelling Prog FH SC (Cat 1 ECs HPB 363993 & HNB 363991) | 2019-05-24 | 2019-05-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A8190.E0 | REGION 1 Defuelling Programme Fuel Handling Safety Case | [PR KDM] NSRS for HYA and HRA agreed by stakeholders - Defuelling Prog FH SC (Cat 1 ECs HRA 363839 & HYA 363840) | 2019-05-24 | 2019-05-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1500 | REGION 1 Reactors Shutdown Safety Cases Programme | Initial high level scope of programme | 2019-05-24 | 2019-05-31 | 5 | 0 | 4 | 7 | 100% | 0.71429 | 1 | Completed
ER6370LT | W201 | ER6370.A3550 | HNB Reactors Shutdown Essential Safety Cases | Validated MACE code v3.2.2 defuelling prototype model Completed | 2019-05-24 | 2019-05-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A3260 | HRA Fuel Handling Essential Safety Case | Issue final NSRS | 2019-05-24 | 2019-05-24 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A1140 | HRA Fuel Handling Essential Safety Case | Station agree NSRS | 2019-05-24 | 2019-05-24 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A3310 | HRA Fuel Handling Essential Safety Case | Circulate NSRS for Relevant Stakeholders | 2019-05-24 | 2019-05-24 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A3270 | HRA Fuel Handling Essential Safety Case | DA & INA agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2019-05-24 | 2019-05-24 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A3290 | HRA Fuel Handling Essential Safety Case | NSRS for HRA/HYA agreed by stakeholders Offload Depressurised Defuelling (Cat 1 Milestone) | 2019-05-24 | 2019-05-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A3290 | HYA Fuel Handling Essential Safety Case | NSRS for HYA/HYA agreed by stakeholders Offload Depressurised Defuelling (Cat 1 Milestone) | 2019-05-24 | 2019-05-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A3270 | HYA Fuel Handling Essential Safety Case | DA & INA agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2019-05-24 | 2019-05-24 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A3310 | HYA Fuel Handling Essential Safety Case | Circulate NSRS for Relevant Stakeholders | 2019-05-24 | 2019-05-24 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A1140 | HYA Fuel Handling Essential Safety Case | Station agree NSRS | 2019-05-24 | 2019-05-24 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A3260 | HYA Fuel Handling Essential Safety Case | Issue final NSRS | 2019-05-24 | 2019-05-24 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A6920 | HNB Reactors Shutdown Essential Safety Cases | Prepare Boilers and Gas Circulator Performance Draft EAN | 2019-05-27 | 2019-08-27 | 65 | 0 | 64 | 92 | 100% | 0.70652 | 1 | Completed
ER6370LT | W201 | ER6370.A8160 | HNB Reactors Shutdown Essential Safety Cases | Issue Component Life Assessment Specification to EDF Review. | 2019-05-27 | 2019-05-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8230 | HNB Reactors Shutdown Essential Safety Cases | Issue Standpipe and Guide Tube Integrity Assessment Specification to EDF Review. | 2019-05-27 | 2019-05-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8300 | HNB Reactors Shutdown Essential Safety Cases | Issue Degradation of Boilers Specification to EDF Review. | 2019-05-27 | 2019-05-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A3320 | HRA Fuel Handling Essential Safety Case | Send NSRS to ONR to determine level of review required (Acknowledgement or Agreement) | 2019-05-27 | 2019-12-02 | 134 | 0 | 134 | 189 | 100% | 0.70899 | 1 | Completed
ER6650LT | W226 | W226.A3320 | HYA Fuel Handling Essential Safety Case | Send NSRS to ONR to determine level of review required (Acknowledgement or Agreement) | 2019-05-27 | 2019-12-02 | 134 | 0 | 134 | 189 | 100% | 0.70899 | 1 | Completed
ER6370LT | W201 | ER6370.A8240 | HNB Reactors Shutdown Essential Safety Cases | Standpipe and Guide Tube Integrity Assessment Specification Reviewed by EDF SQEP | 2019-05-28 | 2019-05-29 | 2 | 0 | 1 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | ER6370.A8310 | HNB Reactors Shutdown Essential Safety Cases | Degradation of Boilers Specification Reviewed by EDF SQEP | 2019-05-28 | 2019-05-29 | 2 | 0 | 1 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | ER6370.A2010 | HNB Reactors Shutdown Essential Safety Cases | Validate codes and methods against logged flux detector response | 2019-05-28 | 2019-08-01 | 48 | 0 | 48 | 65 | 100% | 0.73846 | 1 | Completed
ER6371LT | W202 | W202.A1110 | HRA Reactors Shutdown Essential Safety Cases | Initial high level scope of programme | 2019-05-28 | 2019-05-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1110 | HYA Reactors Shutdown Essential Safety Cases | Initial high level scope of programme | 2019-05-28 | 2019-05-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14890 | HNB Reactors Shutdown Essential Safety Cases | Review of/Changes to Emergency Arrangements - Draft and issue RFS (Not Req'd 28.05.19 GW) | 2019-05-28 | 2019-05-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14900 | HNB Reactors Shutdown Essential Safety Cases | Review of/Changes to Emergency Arrangements - Supplier prepare and issue Offer (Not Req'd 28.05.19 GW) | 2019-05-28 | 2019-05-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14910 | HNB Reactors Shutdown Essential Safety Cases | Review of/Changes to Emergency Arrangements - Review Offer, prepare and issue CI (Not Req'd 28.05.19 GW) | 2019-05-28 | 2019-05-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14920 | HNB Reactors Shutdown Essential Safety Cases | Review of/Changes to Emergency Arrangements - Supplier mobilisation time (Not Req'd 28.05.19 GW) | 2019-05-28 | 2019-05-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14885 | HNB Reactors Shutdown Essential Safety Cases | RFS - Review of/Changes to Emergency Arrangements Summary (Not Req'd 28.05.19 GW) | 2019-05-28 | 2019-07-29 | 45 | 0 | 45 | 62 | 100% | 0.72581 | 1 | Completed
ER6244LT | W220 | A3260 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Issue final NSRS | 2019-05-29 | 2019-05-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A1140 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Station agree NSRS | 2019-05-29 | 2019-05-29 | 14 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A3270 | REGION 1 Defuelling Programme Fuel Handling Safety Case | DA & INA agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2019-05-29 | 2019-05-29 | 14 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A3290 | REGION 1 Defuelling Programme Fuel Handling Safety Case | NSRS for HPB and HNB agreed by stakeholders EC NNNNN <Enter Paper Title Here> (Cat 1 Milestone) | 2019-05-29 | 2019-05-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1120 | HRA Reactors Shutdown Essential Safety Cases | Define Project Control Structures (WBS/CBS/OBS/PBS) | 2019-05-29 | 2019-05-30 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6371LT | W202 | W202.A1130 | HRA Reactors Shutdown Essential Safety Cases | Prepare Draft Project Definition Document (PDD) | 2019-05-29 | 2019-05-31 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6661LT | W206 | W206.A1120 | HYA Reactors Shutdown Essential Safety Cases | Define Project Control Structures (WBS/CBS/OBS/PBS) | 2019-05-29 | 2019-05-30 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6661LT | W206 | W206.A1130 | HYA Reactors Shutdown Essential Safety Cases | Prepare Draft Project Definition Document (PDD) | 2019-05-29 | 2019-05-31 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6370LT | W201 | ER6370.A8170 | HNB Reactors Shutdown Essential Safety Cases | Component Life Assessment Specification Reviewed by EDF SQEP | 2019-05-29 | 2019-05-29 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14580 | HNB Reactors Shutdown Essential Safety Cases | Claim 2 Containment Head Document - Pre Job Brief | 2019-05-29 | 2019-05-29 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A3310 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Circulate NSRS for Relevant Stakeholders | 2019-05-30 | 2019-06-27 | 15 | 0 | 20 | 28 | 100% | 0.53571 | 1 | Completed
ER6370LT | W201 | ER6370.A3400 | HNB Reactors Shutdown Essential Safety Cases | Prepare Reactor Internals Draft Report | 2019-05-30 | 2019-06-28 | 22 | 0 | 21 | 29 | 100% | 0.75862 | 1 | Completed
ER6370LT | W201 | ER6370.A8180 | HNB Reactors Shutdown Essential Safety Cases | Address Comments on Reviewed Component Life Assessment Specification | 2019-05-30 | 2019-05-30 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8190 | HNB Reactors Shutdown Essential Safety Cases | Issue Final Component Life Assessment Specification | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8250 | HNB Reactors Shutdown Essential Safety Cases | Address Comments on Reviewed Standpipe and Guide Tube Integrity Assessment Specification | 2019-05-30 | 2019-05-30 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8260 | HNB Reactors Shutdown Essential Safety Cases | Issue Final Standpipe and Guide Tube Integrity Assessment Specification | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8320 | HNB Reactors Shutdown Essential Safety Cases | Address Comments on Reviewed Degradation of Boilers Specification | 2019-05-30 | 2019-05-30 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8330 | HNB Reactors Shutdown Essential Safety Cases | Issue Final Degradation of Boilers Specification | 2019-05-30 | 2019-05-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3395 | HNB Reactors Shutdown Essential Safety Cases | Reactor Internals Summary | 2019-05-30 | 2019-10-22 | 102 | 0 | 102 | 145 | 100% | 0.70345 | 1 | Completed
ER6370LT | W201 | ER6370.A15630 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Tech Specs HEAD DOCUMENT Report - Pre Job Brief | 2019-05-30 | 2019-05-30 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3330 | HNB Reactors Shutdown Essential Safety Cases | Ass'ment of Graphite behaviour for Shutdown Defuelling Draft Report Verified by TSA | 2019-05-31 | 2019-07-12 | 31 | 0 | 30 | 42 | 100% | 0.7381 | 1 | Completed
ER6370LT | W201 | ER6370.A8200 | HNB Reactors Shutdown Essential Safety Cases | Component Life Assessment Specification Completed and uploaded to CDMS | 2019-05-31 | 2019-05-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8210 | HNB Reactors Shutdown Essential Safety Cases | Component Life Assessment Specification Completed | 2019-05-31 | 2019-05-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8270 | HNB Reactors Shutdown Essential Safety Cases | Standpipe and Guide Tube Integrity Assessment Specification Completed and uploaded to CDMS | 2019-05-31 | 2019-05-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8280 | HNB Reactors Shutdown Essential Safety Cases | Standpipe and Guide Tube Integrity Assessment Specification Completed | 2019-05-31 | 2019-05-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8340 | HNB Reactors Shutdown Essential Safety Cases | Degradation of Boilers Specification Completed and uploaded to CDMS | 2019-05-31 | 2019-05-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8350 | HNB Reactors Shutdown Essential Safety Cases | Degradation of Boilers Specification Completed | 2019-05-31 | 2019-05-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8420 | HNB Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals Specification Completed | 2019-05-31 | 2019-05-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13370 | HNB Reactors Shutdown Essential Safety Cases | Implementation Strategy Document EAN Completed | 2019-05-31 | 2019-05-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13530 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) - Draft and issue RFS | 2019-05-31 | 2019-05-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13525 | HNB Reactors Shutdown Essential Safety Cases | RFS - Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) Summary | 2019-05-31 | 2019-07-29 | 42 | 0 | 42 | 59 | 100% | 0.71186 | 1 | Completed
ER6370LT | W201 | ER6370.A6120 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Prepare Tech Specs HEAD DOCUMENT Draft Report | 2019-05-31 | 2019-07-25 | 40 | 0 | 39 | 55 | 100% | 0.72727 | 1 | Completed
ER6370LT | W201 | ER6370.A2920 | HNB Reactors Shutdown Essential Safety Cases | Prepare Component Life Assessment Draft Report | 2019-06-03 | 2019-06-28 | 20 | 0 | 19 | 25 | 100% | 0.8 | 1 | Completed
ER6370LT | W201 | ER6370.A3000 | HNB Reactors Shutdown Essential Safety Cases | Prepare Standpipe and Guide Tube Integrity Assessment Draft Report | 2019-06-03 | 2019-06-28 | 20 | 0 | 19 | 25 | 100% | 0.8 | 1 | Completed
ER6370LT | W201 | ER6370.A3080 | HNB Reactors Shutdown Essential Safety Cases | Prepare Degradation of Boilers Draft Report | 2019-06-03 | 2019-06-28 | 20 | 0 | 19 | 25 | 100% | 0.8 | 1 | Completed
ER6370LT | W201 | ER6370.A3560 | HNB Reactors Shutdown Essential Safety Cases | Prepare MACE Dataset Development and Analysis for Minimum Temperature Issue | 2019-06-03 | 2019-09-06 | 69 | 0 | 68 | 95 | 100% | 0.72632 | 1 | Completed
ER6370LT | W201 | ER6370.A7480 | HNB Reactors Shutdown Essential Safety Cases | Address Comments from EDF Review on Flux Detection Scoping Draft Report | 2019-06-03 | 2019-07-05 | 25 | 0 | 24 | 32 | 100% | 0.78125 | 1 | Completed
ER6370LT | W201 | ER6370.A11050 | HNB Reactors Shutdown Essential Safety Cases | SDM Assumptions Document Report Completed | 2019-06-03 | 2019-06-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A2915 | HNB Reactors Shutdown Essential Safety Cases | Component Life Assessment Summary | 2019-06-03 | 2019-10-22 | 100 | 0 | 100 | 141 | 100% | 0.70922 | 1 | Completed
ER6370LT | W201 | ER6370.A2995 | HNB Reactors Shutdown Essential Safety Cases | Standpipe and Guide Tube Integrity Assessment Summary | 2019-06-03 | 2019-10-22 | 100 | 0 | 100 | 141 | 100% | 0.70922 | 1 | Completed
ER6370LT | W201 | ER6370.A3075 | HNB Reactors Shutdown Essential Safety Cases | Degradation of Boilers Summary | 2019-06-03 | 2019-10-22 | 100 | 0 | 100 | 141 | 100% | 0.70922 | 1 | Completed
ER6370LT | W201 | ER6370.A3555 | HNB Reactors Shutdown Essential Safety Cases | MACE Dataset Development and Analysis Summary | 2019-06-03 | 2019-09-06 | 68 | 0 | 68 | 95 | 100% | 0.71579 | 1 | Completed
ER6370LT | W201 | ER6370.A13540 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) - Supplier prepare and issue Offer | 2019-06-03 | 2019-06-07 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A14500 | HNB Reactors Shutdown Essential Safety Cases | Reactor Coolant Chemistry Conditions - Supplier prepare and issue Offer | 2019-06-03 | 2019-06-14 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A15040 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Operator Display Requirements Draft Report - Draft and issue RFS | 2019-06-03 | 2019-06-07 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A15035 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - RFS - Operator Display Requirements Draft Report Summary | 2019-06-03 | 2019-07-25 | 38 | 0 | 38 | 52 | 100% | 0.73077 | 1 | Completed
ER6370LT | W201 | ER6370.A15640 | HNB Reactors Shutdown Essential Safety Cases | LSD Strategy Draft Report - Draft and issue RFS | 2019-06-04 | 2019-06-07 | 4 | 0 | 3 | 3 | 100% | 1.3333 | 1 | Completed
ER6370LT | W201 | ER6370.A16070 | HNB Reactors Shutdown Essential Safety Cases | Verified Impacts for the Order of Defuelling Draft EAN Issued to EDF for Technical Review. | 2019-06-04 | 2019-06-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16080 | HNB Reactors Shutdown Essential Safety Cases | Impacts for the Order of Defuelling Draft EAN Technically Reviewed by EDF SQEP | 2019-06-05 | 2019-06-17 | 9 | 0 | 9 | 12 | 100% | 0.75 | 1 | Completed
ER6371LT | W202 | W202.A1140 | HRA Reactors Shutdown Essential Safety Cases | Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 2019-06-05 | 2019-06-06 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6371LT | W202 | W202.A1150 | HRA Reactors Shutdown Essential Safety Cases | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 2019-06-05 | 2019-06-06 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6371LT | W202 | W202.A1160 | HRA Reactors Shutdown Essential Safety Cases | Workshop to agree scope, effort and links | 2019-06-05 | 2019-06-06 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6661LT | W206 | W206.A1140 | HYA Reactors Shutdown Essential Safety Cases | Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 2019-06-05 | 2019-06-06 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6661LT | W206 | W206.A1150 | HYA Reactors Shutdown Essential Safety Cases | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 2019-06-05 | 2019-06-06 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6661LT | W206 | W206.A1160 | HYA Reactors Shutdown Essential Safety Cases | Workshop to agree scope, effort and links | 2019-06-05 | 2019-06-06 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | ER6370.A14840 | HNB Reactors Shutdown Essential Safety Cases | Worker Dose and Risks from Faults Draft Report - Draft and issue RFS | 2019-06-06 | 2019-06-13 | 6 | 0 | 6 | 7 | 100% | 0.85714 | 1 | Completed
ER6370LT | W201 | ER6370.A14835 | HNB Reactors Shutdown Essential Safety Cases | RFS - Worker Dose and Risks from Faults Draft Report Summary | 2019-06-06 | 2019-07-30 | 39 | 0 | 39 | 54 | 100% | 0.72222 | 1 | Completed
ER6371LT | W202 | W202.A1170 | HRA Reactors Shutdown Essential Safety Cases | Ensure Alignment of Schedule & Estimate | 2019-06-07 | 2019-06-10 | 2 | 0 | 2 | 3 | 100% | 0.66667 | 1 | Completed
ER6371LT | W202 | W202.A1180 | HRA Reactors Shutdown Essential Safety Cases | Hold Risk Workshop | 2019-06-07 | 2019-06-07 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1170 | HYA Reactors Shutdown Essential Safety Cases | Ensure Alignment of Schedule & Estimate | 2019-06-07 | 2019-06-10 | 2 | 0 | 2 | 3 | 100% | 0.66667 | 1 | Completed
ER6661LT | W206 | W206.A1180 | HYA Reactors Shutdown Essential Safety Cases | Hold Risk Workshop | 2019-06-07 | 2019-06-07 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A10880 | HNB Reactors Shutdown Essential Safety Cases | Prepare Uncertainty in SDM Calculations Draft Report | 2019-06-10 | 2019-08-30 | 59 | 0 | 58 | 81 | 100% | 0.7284 | 1 | Completed
ER6370LT | W201 | ER6370.A10875 | HNB Reactors Shutdown Essential Safety Cases | Uncertainty in SDM Calculations Summary | 2019-06-10 | 2020-05-08 | 252 | 0 | 233 | 333 | 100% | 0.75676 | 1 | Completed
ER6370LT | W201 | ER6370.A13550 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) - Review Offer, prepare and issue CI | 2019-06-10 | 2019-06-14 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A15050 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Operator Display Requirements Draft Report - Supplier prepare and issue Offer | 2019-06-10 | 2019-06-21 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A15650 | HNB Reactors Shutdown Essential Safety Cases | LSD Strategy Draft Report - Supplier prepare and issue Offer | 2019-06-10 | 2019-06-21 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6371LT | W202 | W202.A1190 | HRA Reactors Shutdown Essential Safety Cases | Complete Risk Log with Estimates | 2019-06-10 | 2019-06-11 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6661LT | W206 | W206.A1190 | HYA Reactors Shutdown Essential Safety Cases | Complete Risk Log with Estimates | 2019-06-10 | 2019-06-11 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6243LT | W200 | ER6243.A1300 | REGION 1 Reactors Shutdown Safety Cases Programme | Hold Risk Workshop | 2019-06-11 | 2019-06-11 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1200 | HRA Reactors Shutdown Essential Safety Cases | Update Schedule/Estimate from Risk Log & Add Provisions | 2019-06-12 | 2019-07-12 | 23 | 0 | 23 | 30 | 100% | 0.76667 | 1 | Completed
ER6661LT | W206 | W206.A1200 | HYA Reactors Shutdown Essential Safety Cases | Update Schedule/Estimate from Risk Log & Add Provisions | 2019-06-12 | 2019-07-12 | 23 | 0 | 23 | 30 | 100% | 0.76667 | 1 | Completed
ER6370LT | W201 | ER6370.A14790 | HNB Reactors Shutdown Essential Safety Cases | Requirements for Severe Accidents Draft Report - Draft and issue RFS | 2019-06-13 | 2019-07-05 | 17 | 0 | 16 | 22 | 100% | 0.77273 | 1 | Completed
ER6370LT | W201 | ER6370.A14785 | HNB Reactors Shutdown Essential Safety Cases | RFS - Requirements for Severe Accidents Draft Report Summary | 2019-06-13 | 2019-07-31 | 35 | 0 | 35 | 48 | 100% | 0.72917 | 1 | Completed
ER6243LT | W200 | A1290 | REGION 1 Reactors Shutdown Safety Cases Programme | Develop & resource mandatory template (HPB, HNB) | 2019-06-14 | 2019-06-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14850 | HNB Reactors Shutdown Essential Safety Cases | Worker Dose and Risks from Faults Draft Report - Supplier prepare and issue Offer | 2019-06-14 | 2019-06-27 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6243LT | W200 | A1320 | REGION 1 Reactors Shutdown Safety Cases Programme | Baseline Plan to Verification Commenced (T-11) (HPB, HNB) | 2019-06-17 | 2019-06-17 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13560 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) - Supplier mobilisation time | 2019-06-17 | 2019-06-28 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A14510 | HNB Reactors Shutdown Essential Safety Cases | Reactor Coolant Chemistry Conditions - Review Offer, prepare and issue CI | 2019-06-17 | 2019-06-21 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6243LT | W200 | ER6243.A1350 | REGION 1 Reactors Shutdown Safety Cases Programme | Prepare Draft Project Definition Document (PDD) | 2019-06-18 | 2019-07-17 | 15 | 0 | 21 | 29 | 100% | 0.51724 | 1 | Completed
ER6370LT | W201 | ER6370.A16090 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Impacts for the Order of Defuelling Draft EAN | 2019-06-18 | 2019-07-30 | 31 | 0 | 30 | 42 | 100% | 0.7381 | 1 | Completed
ER6243LT | W200 | ER6243.A1260 | REGION 1 Reactors Shutdown Safety Cases Programme | Define Project Control Structures (WBS/CBS/OBS/PBS) | 2019-06-18 | 2019-06-26 | 5 | 0 | 6 | 8 | 100% | 0.625 | 1 | Completed
ER6370LT | W201 | ER6370.A13630 | HNB Reactors Shutdown Essential Safety Cases | Compliance Scoping - Draft Task Sheet | 2019-06-24 | 2019-06-28 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A13625 | HNB Reactors Shutdown Essential Safety Cases | RFS - Compliance Scoping Summary | 2019-06-24 | 2019-07-01 | 6 | 0 | 6 | 7 | 100% | 0.85714 | 1 | Completed
ER6370LT | W201 | ER6370.A14520 | HNB Reactors Shutdown Essential Safety Cases | Reactor Coolant Chemistry Conditions - Supplier mobilisation time | 2019-06-24 | 2019-07-05 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A15060 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Operator Display Requirements Draft Report - Review Offer, prepare and issue CI | 2019-06-24 | 2019-06-28 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A15660 | HNB Reactors Shutdown Essential Safety Cases | LSD Strategy Draft Report - Review Offer, prepare and issue CI | 2019-06-24 | 2019-06-28 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6243LT | W200 | ER6243.A1270 | REGION 1 Reactors Shutdown Safety Cases Programme | Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 2019-06-25 | 2019-07-17 | 10 | 0 | 16 | 22 | 100% | 0.45455 | 1 | Completed
ER6243LT | W200 | ER6243.A1280 | REGION 1 Reactors Shutdown Safety Cases Programme | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 2019-06-25 | 2019-07-17 | 10 | 0 | 16 | 22 | 100% | 0.45455 | 1 | Completed
ER6243LT | W200 | ER6243.A1510 | REGION 1 Reactors Shutdown Safety Cases Programme | Workshop to agree scope, effort and links | 2019-06-25 | 2019-06-25 | 10 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4370 | HNB Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Based Faults) Draft Report Verified by TSA | 2019-06-25 | 2019-07-19 | 19 | 0 | 18 | 24 | 100% | 0.79167 | 1 | Completed
ER6370LT | W201 | ER6370.A4450 | HNB Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Harzards) Draft Report Verified by TSA | 2019-06-25 | 2019-07-19 | 19 | 0 | 18 | 24 | 100% | 0.79167 | 1 | Completed
ER6370LT | W201 | ER6370.A4520 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Prepare RADCONs Draft Report | 2019-06-25 | 2019-06-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4530 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - RADCONs Draft Report Verified by TSA | 2019-06-25 | 2019-06-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4540 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Verified RADCONs Draft Report Issued to EDF for Technical Review. | 2019-06-25 | 2019-06-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4550 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - RADCONs Draft Report Technically Reviewed by EDF SQEP | 2019-06-25 | 2019-06-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4560 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - TSA Address Comments on TR'd RADCONs Draft Report | 2019-06-25 | 2019-06-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4570 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - TSA Issue Final RADCONs Report | 2019-06-25 | 2019-06-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4580 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - RADCONs Report TR Completed and uploaded to CDMS | 2019-06-25 | 2019-06-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4590 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - RADCONs Report Completed | 2019-06-25 | 2019-06-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4620 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Verified Removal of Claims on 2nd and 3rd Shutdown/Holdown Sys Draft Report Issued to EDF for TR | 2019-06-25 | 2019-06-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4630 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Removal of Claims on 2nd and 3rd Shutdown/Holdown Sys Draft Report TR'd by EDF SQEP | 2019-06-25 | 2019-06-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4640 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - TSA Address Comments on TR'd Removal of Claims on 2nd and 3rd Shutdown/Holdown Sys Draft Report | 2019-06-25 | 2019-06-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4650 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - TSA Issue Final Removal of Claims on Secondary and Tertiary Shutdown/Holdown Sys Report | 2019-06-25 | 2019-06-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4660 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Removal of Claims on 2nd and 3rd Shutdown/Holdown Sys Report TR Completed and uploaded to CDMS | 2019-06-25 | 2019-06-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4670 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Removal of Claims on Secondary and Tertiary Shutdown/Holdown Sys Report Completed | 2019-06-25 | 2019-06-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A9460 | HNB Reactors Shutdown Essential Safety Cases | Prepare Boiler Control and Protection Draft Report | 2019-06-25 | 2019-08-27 | 45 | 0 | 44 | 63 | 100% | 0.71429 | 1 | Completed
ER6370LT | W201 | ER6370.A9540 | HNB Reactors Shutdown Essential Safety Cases | Prepare Reactor Cooling Systems Draft Report | 2019-06-25 | 2019-08-27 | 45 | 0 | 44 | 63 | 100% | 0.71429 | 1 | Completed
ER6370LT | W201 | ER6370.A10690 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Impact on Decommissioning Plans - (Scope Removed) | 2019-06-25 | 2019-06-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A10700 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Nuclear Liabilities - (Scope Removed) | 2019-06-25 | 2019-06-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4515 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - RADCONs Summary | 2019-06-25 | 2019-06-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4595 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Removal of Claims on the Secondary and Tertiary Shutdown / Holdown Systems Summary | 2019-06-25 | 2019-06-25 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A9455 | HNB Reactors Shutdown Essential Safety Cases | Boiler Control and Protection Summary | 2019-06-25 | 2019-12-06 | 117 | 0 | 117 | 164 | 100% | 0.71341 | 1 | Completed
ER6370LT | W201 | ER6370.A9535 | HNB Reactors Shutdown Essential Safety Cases | Reactor Cooling Systems Summary | 2019-06-25 | 2019-12-06 | 118 | 0 | 118 | 164 | 100% | 0.71951 | 1 | Completed
ER6370LT | W201 | ER6370.A14590 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - RADCONs - Draft and issue RFS | 2019-06-25 | 2019-06-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14600 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - RADCONs - Supplier prepare and issue Offer | 2019-06-25 | 2019-06-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14610 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - RADCONs - Review Offer, prepare and issue CI | 2019-06-25 | 2019-06-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14620 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - RADCONs - Supplier mobilisation time | 2019-06-25 | 2019-06-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14630 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - RADCONs - Pre Job Brief | 2019-06-25 | 2019-06-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14585 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - RFS - RADCONs Summary | 2019-06-25 | 2019-06-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14740 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Removal of Claims on the 2nd and 3rd Shutdown / Holdown Systems - Draft and issue RFS | 2019-06-25 | 2019-06-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14750 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Removal of Claims on the 2nd and 3rd Shutdown / Holdown Systems - Supplier prepare and issue Offer | 2019-06-25 | 2019-06-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14735 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - RFS - Removal of Claims on the 2nd and 3rd Shutdown / Holdown Systems Summary | 2019-06-25 | 2019-06-25 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4600 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Prepare Removal of Claims on the Secondary and Tertiary Shutdown / Holdown Systems Draft Report | 2019-06-25 | 2019-06-25 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4610 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Removal of Claims on Secondary and Tertiary Shutdown/Holdown Sys Draft Report Verified by TSA | 2019-06-25 | 2019-06-25 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14760 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Removal of Claims on the 2nd and 3rd Shutdown / Holdown Systems - Review Offer, prepare and issue CI | 2019-06-25 | 2019-06-25 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14770 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Removal of Claims on the 2nd and 3rd Shutdown / Holdown Systems - Supplier mobilisation time | 2019-06-25 | 2019-06-25 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14780 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Removal of Claims on the 2nd and 3rd Shutdown / Holdown Systems - Pre Job Brief | 2019-06-25 | 2019-06-25 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A3090 | REGION 1 Defuelling Programme Fuel Handling Safety Case | NSRS Complete - HPB and HNB | 2019-06-27 | 2019-06-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A3100 | REGION 1 Defuelling Programme Fuel Handling Safety Case | NSRS Complete - HRA and HYA | 2019-06-27 | 2019-06-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A3320 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Send NSRS to ONR to determine level of review required (Acknowledgement or Agreement) | 2019-06-27 | 2019-06-27 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A3360 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Issue final NSRS | 2019-06-27 | 2019-06-27 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A3370 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Station agree NSRS | 2019-06-27 | 2019-06-27 | 50 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A3380 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Circulate NSRS for Relevant Stakeholders | 2019-06-27 | 2019-06-27 | 15 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A3390 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Incorporate INA, Station, DA (peer) comments | 2019-06-27 | 2019-06-27 | 15 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A3400 | REGION 1 Defuelling Programme Fuel Handling Safety Case | DA & INA agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2019-06-27 | 2019-06-27 | 50 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A3420 | REGION 1 Defuelling Programme Fuel Handling Safety Case | NSRS for HYA and HRA agreed by stakeholders EC NNNNN <Enter Paper Title Here> (Cat 1 Milestone) | 2019-06-27 | 2019-06-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A3430 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Send NSRS to ONR to determine level of review required (Acknowledgement or Agreement) | 2019-06-27 | 2019-06-27 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A3440 | REGION 1 Defuelling Programme Fuel Handling Safety Case | NSRS Presented to NSC (for complex CAT 1 cases) | 2019-06-27 | 2019-06-27 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A3450 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Hold Case Conference as Appropriate | 2019-06-27 | 2019-06-27 | 3 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A2020 | HNB Reactors Shutdown Essential Safety Cases | Issue Establish Codes and Methods for Safety Case Draft Report to EDF for Review. | 2019-06-28 | 2019-06-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A2930 | HNB Reactors Shutdown Essential Safety Cases | Component Life Assessment Draft Report Verified by TSA | 2019-06-28 | 2019-07-12 | 11 | 0 | 10 | 14 | 100% | 0.78571 | 1 | Completed
ER6370LT | W201 | ER6370.A3010 | HNB Reactors Shutdown Essential Safety Cases | Standpipe and Guide Tube Integrity Assessment Draft Report Verified by TSA | 2019-06-28 | 2019-07-12 | 11 | 0 | 10 | 14 | 100% | 0.78571 | 1 | Completed
ER6370LT | W201 | ER6370.A3090 | HNB Reactors Shutdown Essential Safety Cases | Degradation of Boilers Draft Report Verified by TSA | 2019-06-28 | 2019-07-12 | 11 | 0 | 10 | 14 | 100% | 0.78571 | 1 | Completed
ER6370LT | W201 | ER6370.A3410 | HNB Reactors Shutdown Essential Safety Cases | Reactor Internals Draft Report Verified by TSA | 2019-06-28 | 2019-07-12 | 11 | 0 | 10 | 14 | 100% | 0.78571 | 1 | Completed
ER6370LT | W201 | ER6370.A7300 | HNB Reactors Shutdown Essential Safety Cases | Code Validation from Operational Reactor Report Completed | 2019-06-28 | 2019-06-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14860 | HNB Reactors Shutdown Essential Safety Cases | Worker Dose and Risks from Faults Draft Report - Review Offer, prepare and issue CI | 2019-06-28 | 2019-07-05 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6370LT | W201 | ER6370.A15670 | HNB Reactors Shutdown Essential Safety Cases | LSD Strategy Draft Report - Supplier mobilisation time | 2019-06-28 | 2019-07-22 | 17 | 0 | 17 | 24 | 100% | 0.70833 | 1 | Completed
ER6370LT | W201 | ER6370.A2030 | HNB Reactors Shutdown Essential Safety Cases | Establish Codes and Methods for Safety Case Draft Report Reviewed by EDF SQEP | 2019-07-01 | 2019-08-02 | 25 | 0 | 24 | 32 | 100% | 0.78125 | 1 | Completed
ER6370LT | W201 | ER6370.A7520 | HNB Reactors Shutdown Essential Safety Cases | Prepare Safety Rod Insertion Scoping Draft Report | 2019-07-01 | 2019-07-12 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A7515 | HNB Reactors Shutdown Essential Safety Cases | Safety Rod Insertion Scoping Summary | 2019-07-01 | 2019-07-18 | 13 | 0 | 13 | 17 | 100% | 0.76471 | 1 | Completed
ER6370LT | W201 | ER6370.A13640 | HNB Reactors Shutdown Essential Safety Cases | Compliance Scoping - Supplier prepare and issue Offer (Remove from Scope) | 2019-07-01 | 2019-07-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13650 | HNB Reactors Shutdown Essential Safety Cases | Compliance Scoping - Review Offer, prepare and issue CI (Remove from Scope) | 2019-07-01 | 2019-07-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13660 | HNB Reactors Shutdown Essential Safety Cases | Compliance Scoping - Supplier mobilisation time (Remove from Scope) | 2019-07-01 | 2019-07-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13670 | HNB Reactors Shutdown Essential Safety Cases | Compliance Scoping - Pre Job Brief | 2019-07-01 | 2019-07-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A15890 | HNB Reactors Shutdown Essential Safety Cases | Summary of Compliance with RADWASTE - Draft and issue RFS | 2019-07-01 | 2019-07-05 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A15885 | HNB Reactors Shutdown Essential Safety Cases | RFS - Summary of Compliance with RADWASTE Summary | 2019-07-01 | 2019-07-31 | 23 | 0 | 23 | 30 | 100% | 0.76667 | 1 | Completed
ER6370LT | W201 | ER6370.A16140 | HNB Reactors Shutdown Essential Safety Cases | Phase 2: Programme 6.1 Station Documentation and Implementation Strategy | 2019-07-01 | 2020-01-31 | 151 | 0 | 150 | 214 | 100% | 0.70561 | 1 | Completed
ER6370LT | W201 | ER6370.A11360 | HNB Reactors Shutdown Essential Safety Cases | Optioneering Report | 2019-07-01 | 2019-08-21 | 38 | 0 | 37 | 51 | 100% | 0.7451 | 1 | Completed
ER6370LT | W201 | ER6370.A7600 | HNB Reactors Shutdown Essential Safety Cases | Issued SDM Assessments with uncertainties / sensitivity studies Draft Report to EDF for Review. | 2019-07-02 | 2019-07-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7610 | HNB Reactors Shutdown Essential Safety Cases | SDM Assessments with uncertainties / sensitivity studies Draft Report Reviewed by EDF SQEP | 2019-07-03 | 2019-08-01 | 22 | 0 | 21 | 29 | 100% | 0.75862 | 1 | Completed
ER6370LT | W201 | ER6370.A7490 | HNB Reactors Shutdown Essential Safety Cases | Issue Final Flux Detection Scoping Report | 2019-07-05 | 2019-07-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7500 | HNB Reactors Shutdown Essential Safety Cases | Flux Detection Scoping Report Completed and Uploaded to CDMS | 2019-07-08 | 2019-07-19 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A10340 | HNB Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity Draft Report Verified by TSA | 2019-07-08 | 2019-07-19 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A14800 | HNB Reactors Shutdown Essential Safety Cases | Requirements for Severe Accidents Draft Report - Supplier prepare and issue Offer | 2019-07-08 | 2019-07-19 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A14870 | HNB Reactors Shutdown Essential Safety Cases | Worker Dose and Risks from Faults Draft Report - Supplier mobilisation time | 2019-07-08 | 2019-07-29 | 16 | 0 | 15 | 21 | 100% | 0.7619 | 1 | Completed
ER6370LT | W201 | ER6370.A15900 | HNB Reactors Shutdown Essential Safety Cases | Summary of Compliance with RADWASTE - Supplier prepare and issue Offer | 2019-07-08 | 2019-07-19 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A8430 | HNB Reactors Shutdown Essential Safety Cases | Prepare Reactor Coolant Chemistry Conditions Draft Report | 2019-07-09 | 2019-09-18 | 51 | 0 | 50 | 71 | 100% | 0.71831 | 1 | Completed
ER6370LT | W201 | ER6370.A11230 | HNB Reactors Shutdown Essential Safety Cases | Reactor Coolant Chemistry Conditions Summary | 2019-07-09 | 2020-01-02 | 123 | 0 | 123 | 177 | 100% | 0.69492 | 1 | Completed
ER6370LT | W201 | ER6370.A10540 | HNB Reactors Shutdown Essential Safety Cases | ALARP / BAT/ BPM Draft Report Verified by TSA | 2019-07-11 | 2019-08-30 | 36 | 0 | 35 | 50 | 100% | 0.72 | 1 | Completed
ER6370LT | W201 | ER6370.A2940 | HNB Reactors Shutdown Essential Safety Cases | Verified Component Life Assessment Draft Report Issued to EDF for Technical Review. | 2019-07-12 | 2019-07-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3020 | HNB Reactors Shutdown Essential Safety Cases | Verified Standpipe and Guide Tube Integrity Assessment Draft Report Issued to EDF for Technical Review. | 2019-07-12 | 2019-07-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3100 | HNB Reactors Shutdown Essential Safety Cases | Verified Degradation of Boilers Draft Report Issued to EDF for Technical Review. | 2019-07-12 | 2019-07-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3340 | HNB Reactors Shutdown Essential Safety Cases | Verified Ass'ment of Graphite behaviour for Shutdown Defuelling Draft Report Issued to EDF for Technical Review. | 2019-07-12 | 2019-07-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3420 | HNB Reactors Shutdown Essential Safety Cases | Verified Reactor Internals Draft Report Issued to EDF for Technical Review. | 2019-07-12 | 2019-07-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7530 | HNB Reactors Shutdown Essential Safety Cases | Issued Safety Rod Insertion Scoping Draft Report to EDF for Review. | 2019-07-12 | 2019-07-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14530 | HNB Reactors Shutdown Essential Safety Cases | Reactor Coolant Chemistry Conditions - Pre Job Brief | 2019-07-12 | 2019-07-12 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A2950 | HNB Reactors Shutdown Essential Safety Cases | Component Life Assessment Draft Report Technically Reviewed by EDF SQEP | 2019-07-15 | 2019-08-23 | 30 | 0 | 29 | 39 | 100% | 0.76923 | 1 | Completed
ER6370LT | W201 | ER6370.A3030 | HNB Reactors Shutdown Essential Safety Cases | Standpipe and Guide Tube Integrity Assessment Draft Report Technically Reviewed by EDF SQEP | 2019-07-15 | 2019-08-23 | 30 | 0 | 29 | 39 | 100% | 0.76923 | 1 | Completed
ER6370LT | W201 | ER6370.A3110 | HNB Reactors Shutdown Essential Safety Cases | Degradation of Boilers Draft Report Technically Reviewed by EDF SQEP | 2019-07-15 | 2019-08-23 | 30 | 0 | 29 | 39 | 100% | 0.76923 | 1 | Completed
ER6370LT | W201 | ER6370.A3170 | HNB Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals Draft Report Verified by TSA | 2019-07-15 | 2019-08-08 | 19 | 0 | 18 | 24 | 100% | 0.79167 | 1 | Completed
ER6370LT | W201 | ER6370.A3350 | HNB Reactors Shutdown Essential Safety Cases | Ass'ment of Graphite behaviour for Shutdown Defuelling Draft Report Technically Reviewed by EDF SQEP | 2019-07-15 | 2019-08-01 | 14 | 0 | 13 | 17 | 100% | 0.82353 | 1 | Completed
ER6370LT | W201 | ER6370.A3430 | HNB Reactors Shutdown Essential Safety Cases | Reactor Internals Draft Report Technically Reviewed by EDF SQEP | 2019-07-15 | 2019-08-23 | 30 | 0 | 29 | 39 | 100% | 0.76923 | 1 | Completed
ER6370LT | W201 | ER6370.A3890 | HNB Reactors Shutdown Essential Safety Cases | Model and Datasets Part 2 Reports Verified by TSA | 2019-07-15 | 2019-09-27 | 54 | 0 | 53 | 74 | 100% | 0.72973 | 1 | Completed
ER6370LT | W201 | ER6370.A7570 | HNB Reactors Shutdown Essential Safety Cases | Safety Rod Insertion Scoping Report Completed and Uploaded to CDMS | 2019-07-15 | 2019-07-18 | 4 | 0 | 3 | 3 | 100% | 1.3333 | 1 | Completed
ER6371LT | W202 | W202.A1210 | HRA Reactors Shutdown Essential Safety Cases | Add Data to IRM Paper | 2019-07-15 | 2019-07-16 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6661LT | W206 | W206.A1210 | HYA Reactors Shutdown Essential Safety Cases | Add Data to IRM Paper | 2019-07-15 | 2019-07-16 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6243LT | W200 | ER6243.A1290 | REGION 1 Reactors Shutdown Safety Cases Programme | Ensure Alignment of Schedule & Estimate | 2019-07-15 | 2019-07-16 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6243LT | W200 | ER6243.A1310 | REGION 1 Reactors Shutdown Safety Cases Programme | Complete Risk Log with Estimates | 2019-07-15 | 2019-07-16 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | ER6370.A2860 | HNB Reactors Shutdown Essential Safety Cases | Issue Civil Integrity Overview Draft EAN to EDF for Review. | 2019-07-17 | 2019-07-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13870 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Margin Head Document - Pre Job Brief | 2019-07-17 | 2019-07-17 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1220 | HRA Reactors Shutdown Essential Safety Cases | PCL Validate & Approve Baseline Package for PRC Submission | 2019-07-17 | 2019-07-19 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6661LT | W206 | W206.A1220 | HYA Reactors Shutdown Essential Safety Cases | PCL Validate & Approve Baseline Package for PRC Submission | 2019-07-17 | 2019-07-19 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6243LT | W200 | ER6243.A1320 | REGION 1 Reactors Shutdown Safety Cases Programme | Update Schedule/Estimate from Risk Log & Add Provisions | 2019-07-17 | 2019-07-18 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | ER6370.A2870 | HNB Reactors Shutdown Essential Safety Cases | Civil Integrity Overview Draft EAN Reviewed by EDF SQEP | 2019-07-18 | 2019-08-01 | 11 | 0 | 10 | 14 | 100% | 0.78571 | 1 | Completed
ER6370LT | W201 | ER6370.A7540 | HNB Reactors Shutdown Essential Safety Cases | Safety Rod Insertion Scoping Draft Report Reviewed by EDF SQEP (Remove from Scope) | 2019-07-18 | 2019-07-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7550 | HNB Reactors Shutdown Essential Safety Cases | Address Comments from EDF Review on Safety Rod Insertion Scoping Draft Report (Remove from Scope) | 2019-07-18 | 2019-07-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7560 | HNB Reactors Shutdown Essential Safety Cases | Issue Final Safety Rod Insertion Scoping Report Report (Remove from Scope) | 2019-07-18 | 2019-07-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7580 | HNB Reactors Shutdown Essential Safety Cases | Safety Rod Insertion Scoping Report Completed | 2019-07-18 | 2019-07-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4380 | HNB Reactors Shutdown Essential Safety Cases | Verified Fault Schedule Review (Plant Based Faults) Draft Report Issued to EDF for Technical Review. | 2019-07-19 | 2019-07-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4460 | HNB Reactors Shutdown Essential Safety Cases | Verified Fault Schedule Review (Harzards) Draft Report Issued to EDF for Technical Review. | 2019-07-19 | 2019-07-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7510 | HNB Reactors Shutdown Essential Safety Cases | Flux Detection Scoping Report Completed | 2019-07-19 | 2019-07-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A10350 | HNB Reactors Shutdown Essential Safety Cases | Verified Structures and Equipment Integrity Draft Report Issued to EDF for Technical Review. | 2019-07-19 | 2019-07-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1330 | REGION 1 Reactors Shutdown Safety Cases Programme | Add Data to IRM Paper | 2019-07-19 | 2019-07-22 | 2 | 0 | 2 | 3 | 100% | 0.66667 | 1 | Completed
ER6370LT | W201 | ER6370.A4390 | HNB Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Based Faults) Draft Report Technically Reviewed by EDF SQEP | 2019-07-22 | 2019-09-27 | 49 | 0 | 48 | 67 | 100% | 0.73134 | 1 | Completed
ER6370LT | W201 | ER6370.A4470 | HNB Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Harzards) Draft Report Technically Reviewed by EDF SQEP | 2019-07-22 | 2019-09-27 | 49 | 0 | 48 | 67 | 100% | 0.73134 | 1 | Completed
ER6370LT | W201 | ER6370.A7790 | HNB Reactors Shutdown Essential Safety Cases | Prepare Shutdown Margin Head Document | 2019-07-22 | 2019-10-31 | 73 | 0 | 72 | 101 | 100% | 0.72277 | 1 | Completed
ER6370LT | W201 | ER6370.A10360 | HNB Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity Draft Report Technically Reviewed by EDF SQEP | 2019-07-22 | 2019-08-23 | 25 | 0 | 24 | 32 | 100% | 0.78125 | 1 | Completed
ER6370LT | W201 | ER6370.A10620 | HNB Reactors Shutdown Essential Safety Cases | In Reactor NSP Compliance and Risk Report - Draft Report Verified by TSA | 2019-07-22 | 2019-08-30 | 29 | 0 | 28 | 39 | 100% | 0.74359 | 1 | Completed
ER6370LT | W201 | ER6370.A7785 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Margin Head Document Summary | 2019-07-22 | 2020-06-26 | 223 | 0 | 236 | 340 | 100% | 0.65588 | 1 | Completed
ER6370LT | W201 | ER6370.A14810 | HNB Reactors Shutdown Essential Safety Cases | Requirements for Severe Accidents Draft Report - Review Offer, prepare and issue CI | 2019-07-22 | 2019-07-24 | 3 | 0 | 2 | 2 | 100% | 1.5 | 1 | Completed
ER6370LT | W201 | ER6370.A15910 | HNB Reactors Shutdown Essential Safety Cases | Summary of Compliance with RADWASTE - Review Offer, prepare and issue CI | 2019-07-22 | 2019-07-26 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6243LT | W200 | A16210 | REGION 1 Reactors Shutdown Safety Cases Programme | Support System Report Issued to CDMS (HYA, HAR) | 2019-07-23 | 2019-07-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A16770 | REGION 1 Reactors Shutdown Safety Cases Programme | Support System Report Review and Acceptance (HYA, HAR) | 2019-07-23 | 2019-07-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7660 | HNB Reactors Shutdown Essential Safety Cases | Hold Meeting for Optioneering of timing of safety group insertion | 2019-07-23 | 2019-07-23 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7680 | HNB Reactors Shutdown Essential Safety Cases | Hold Meeting for Optioneering pattern of defuelling | 2019-07-23 | 2019-07-23 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13680 | HNB Reactors Shutdown Essential Safety Cases | Compliance Sensitivities Study - Draft Task Sheet | 2019-07-23 | 2019-07-29 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A13675 | HNB Reactors Shutdown Essential Safety Cases | RFS - Compliance Sensitivities Study Summary | 2019-07-23 | 2019-07-30 | 6 | 0 | 6 | 7 | 100% | 0.85714 | 1 | Completed
ER6370LT | W201 | ER6370.A15680 | HNB Reactors Shutdown Essential Safety Cases | LSD Strategy Draft Report - Pre Job Brief | 2019-07-23 | 2019-07-23 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16640 | HNB Reactors Shutdown Essential Safety Cases | Thermal Analysis of FPU - FEAT - Draft and issue RFS | 2019-07-23 | 2019-07-23 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16650 | HNB Reactors Shutdown Essential Safety Cases | Thermal Analysis of FPU - FEAT - Supplier prepare and issue Offer | 2019-07-23 | 2019-07-23 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16660 | HNB Reactors Shutdown Essential Safety Cases | Thermal Analysis of FPU - FEAT - Review Offer, prepare and issue CI | 2019-07-23 | 2019-07-23 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16670 | HNB Reactors Shutdown Essential Safety Cases | Thermal Analysis of FPU - FEAT - Supplier mobilisation time | 2019-07-23 | 2019-07-23 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16680 | HNB Reactors Shutdown Essential Safety Cases | Thermal Analysis of FPU - FEAT - Pre Job Brief | 2019-07-23 | 2019-07-23 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16690 | HNB Reactors Shutdown Essential Safety Cases | RFS - Thermal Analysis of FPU - FEAT Summary | 2019-07-23 | 2019-07-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1340 | REGION 1 Reactors Shutdown Safety Cases Programme | PCL Validate & Approve Baseline Package for PRC Submission | 2019-07-23 | 2019-07-25 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6370LT | W201 | ER6370.A6200 | HNB Reactors Shutdown Essential Safety Cases | Prepare LSD Strategy Draft Report | 2019-07-24 | 2019-07-31 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6370LT | W201 | ER6370.A8060 | HNB Reactors Shutdown Essential Safety Cases | Prepare Optioneering of Timing Meeting Minutes | 2019-07-24 | 2019-10-11 | 57 | 0 | 56 | 79 | 100% | 0.72152 | 1 | Completed
ER6370LT | W201 | ER6370.A8080 | HNB Reactors Shutdown Essential Safety Cases | Prepare Optioneering Pattern of Defuelling Meeting Minutes | 2019-07-24 | 2019-10-11 | 57 | 0 | 56 | 79 | 100% | 0.72152 | 1 | Completed
ER6370LT | W201 | ER6370.A16510 | HNB Reactors Shutdown Essential Safety Cases | ability of the PCPV to satisfy support in-resident FPUs - Draft and issue RFS | 2019-07-24 | 2019-07-24 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16520 | HNB Reactors Shutdown Essential Safety Cases | ability of the PCPV to satisfy support in-resident FPUs - Supplier prepare and issue Offer | 2019-07-24 | 2019-07-24 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16530 | HNB Reactors Shutdown Essential Safety Cases | ability of the PCPV to satisfy support in-resident FPUs - Review Offer, prepare and issue CI | 2019-07-24 | 2019-07-24 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16540 | HNB Reactors Shutdown Essential Safety Cases | ability of the PCPV to satisfy support in-resident FPUs - Supplier mobilisation time | 2019-07-24 | 2019-07-24 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16550 | HNB Reactors Shutdown Essential Safety Cases | ability of the PCPV to satisfy support in-resident FPUs - Pre Job Brief | 2019-07-24 | 2019-07-24 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16465 | HNB Reactors Shutdown Essential Safety Cases | RFS - ability of the PCPV to satisfy support in-resident FPUs Summary | 2019-07-24 | 2019-07-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16560 | HNB Reactors Shutdown Essential Safety Cases | Prepare Thermal Analysis of FPU - FEAT - Report - QA Grade 2 | 2019-07-24 | 2019-08-05 | 9 | 0 | 8 | 12 | 100% | 0.75 | 1 | Completed
ER6370LT | W201 | ER6370.A16385 | HNB Reactors Shutdown Essential Safety Cases | Thermal Analysis of FPU - FEAT - Report - QA Grade 2 Summary | 2019-07-24 | 2019-09-23 | 42 | 0 | 42 | 61 | 100% | 0.68852 | 1 | Completed
ER6370LT | W201 | ER6370.A6130 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Tech Specs HEAD DOCUMENT Draft Report Verified by TSA | 2019-07-25 | 2019-07-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A6140 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Verified Tech Specs HEAD DOCUMENT Draft Report Issued to EDF for Technical Review. | 2019-07-25 | 2019-07-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A6150 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Tech Specs HEAD DOCUMENT Draft Report Technically Reviewed by EDF SQEP | 2019-07-25 | 2019-07-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A6160 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - TSA Address Comments on TR'd Tech Specs HEAD DOCUMENT Draft Report | 2019-07-25 | 2019-07-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A6170 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - TSA Issue Final Tech Specs HEAD DOCUMENT Report | 2019-07-25 | 2019-07-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A6180 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Tech Specs HEAD DOCUMENT Report TR Completed and uploaded to CDMS (Not Req'd 28.05.19 GW) | 2019-07-25 | 2019-07-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A6190 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Tech Specs HEAD DOCUMENT Report Completed | 2019-07-25 | 2019-07-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A9620 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Prepare Operator Display Requirements Draft Report | 2019-07-25 | 2019-07-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A9630 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Operator Display Requirements Draft Report Verified by TSA | 2019-07-25 | 2019-07-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A9640 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Verified Operator Display Requirements Draft Report Issued to EDF for Technical Review. | 2019-07-25 | 2019-07-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A9650 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Operator Display Requirements Draft Report Technically Reviewed by EDF SQEP | 2019-07-25 | 2019-07-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A9660 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - TSA Address Comments on TR'd Operator Display Requirements Draft Report | 2019-07-25 | 2019-07-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A9670 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - TSA Issue Final Operator Display Requirements Report | 2019-07-25 | 2019-07-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A9680 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Operator Display Requirements Report TR Completed and uploaded to CDMS | 2019-07-25 | 2019-07-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A9690 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Operator Display Requirements Report Completed | 2019-07-25 | 2019-07-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A9615 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Operator Display Requirements Summary | 2019-07-25 | 2019-07-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14820 | HNB Reactors Shutdown Essential Safety Cases | Requirements for Severe Accidents Draft Report - Supplier mobilisation time | 2019-07-25 | 2019-07-30 | 4 | 0 | 3 | 5 | 100% | 0.8 | 1 | Completed
ER6370LT | W201 | ER6370.A15070 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Operator Display Requirements Draft Report - Supplier mobilisation time | 2019-07-25 | 2019-07-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A15080 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Operator Display Requirements Draft Report - Pre Job Brief | 2019-07-25 | 2019-07-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16430 | HNB Reactors Shutdown Essential Safety Cases | Prepare Consideration of the ability of the PCPV to satisfactorily support in- resident FPUs - EAN - QA Grade 2 | 2019-07-25 | 2019-08-30 | 26 | 0 | 25 | 36 | 100% | 0.72222 | 1 | Completed
ER6370LT | W201 | ER6370.A16225 | HNB Reactors Shutdown Essential Safety Cases | Consideration of the ability of the PCPV to satisfactorily support in- resident FPUs - EAN - QA Grade 2 Summary | 2019-07-25 | 2019-10-16 | 58 | 0 | 58 | 83 | 100% | 0.6988 | 1 | Completed
ER6370LT | W201 | ER6370.A7670 | HNB Reactors Shutdown Essential Safety Cases | Hold Meeting for SDM - optioneering of confidence required | 2019-07-29 | 2019-07-29 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13570 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) - Pre Job Brief | 2019-07-29 | 2019-07-29 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13690 | HNB Reactors Shutdown Essential Safety Cases | Compliance Sensitivities Study - Supplier prepare and issue Offer (Remove from Scope) | 2019-07-29 | 2019-07-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13700 | HNB Reactors Shutdown Essential Safety Cases | Compliance Sensitivities Study - Review Offer, prepare and issue CI (Remove from Scope) | 2019-07-29 | 2019-07-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13710 | HNB Reactors Shutdown Essential Safety Cases | Compliance Sensitivities Study - Supplier mobilisation time (Remove from Scope) | 2019-07-29 | 2019-07-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14930 | HNB Reactors Shutdown Essential Safety Cases | Review of/Changes to Emergency Arrangements - Pre Job Brief | 2019-07-29 | 2019-07-29 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A15920 | HNB Reactors Shutdown Essential Safety Cases | Summary of Compliance with RADWASTE - Supplier mobilisation time | 2019-07-29 | 2019-07-30 | 2 | 0 | 1 | 1 | 100% | 2 | 1 | Completed
ER6378LT | W222 | W222.A14090 | HRA Fuel Handling Essential Safety Case | Complete Risk Log with Estimates | 2019-07-29 | 2019-07-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A14080 | HRA Fuel Handling Essential Safety Case | Hold Risk Workshop | 2019-07-29 | 2019-07-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A14080 | HYA Fuel Handling Essential Safety Case | Hold Risk Workshop | 2019-07-29 | 2019-07-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A14090 | HYA Fuel Handling Essential Safety Case | Complete Risk Log with Estimates | 2019-07-29 | 2019-07-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4840 | HNB Reactors Shutdown Essential Safety Cases | Prepare Review of/Changes to Emergency Arrangements Draft Report | 2019-07-30 | 2019-09-10 | 30 | 0 | 29 | 42 | 100% | 0.71429 | 1 | Completed
ER6370LT | W201 | ER6370.A4835 | HNB Reactors Shutdown Essential Safety Cases | Review of/Changes to Emergency Arrangements Summary | 2019-07-30 | 2019-10-11 | 53 | 0 | 53 | 73 | 100% | 0.72603 | 1 | Completed
ER6370LT | W201 | ER6370.A13720 | HNB Reactors Shutdown Essential Safety Cases | Compliance Sensitivities Study - Pre Job Brief | 2019-07-30 | 2019-07-30 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14880 | HNB Reactors Shutdown Essential Safety Cases | Worker Dose and Risks from Faults Draft Report - Pre Job Brief | 2019-07-30 | 2019-07-30 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16100 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Impacts for the Order of Defuelling EAN | 2019-07-30 | 2019-07-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8070 | HNB Reactors Shutdown Essential Safety Cases | Prepare SDM Meeting Minutes | 2019-07-30 | 2019-10-11 | 53 | 0 | 52 | 73 | 100% | 0.72603 | 1 | Completed
ER6243LT | W200 | A10750 | REGION 1 Reactors Shutdown Safety Cases Programme | Estimating Uncertainty - 2018 | 2019-07-31 | 2019-07-31 | 45 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A14830 | HNB Reactors Shutdown Essential Safety Cases | Requirements for Severe Accidents Draft Report - Pre Job Brief | 2019-07-31 | 2019-07-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1230 | HRA Reactors Shutdown Essential Safety Cases | Gate B PRC Paper Submission | 2019-07-31 | 2019-07-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1240 | HRA Reactors Shutdown Essential Safety Cases | PRC Members Review IRM Documentation | 2019-07-31 | 2019-08-06 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | W206.A1230 | HYA Reactors Shutdown Essential Safety Cases | Gate B PRC Paper Submission | 2019-07-31 | 2019-07-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1240 | HYA Reactors Shutdown Essential Safety Cases | PRC Members Review IRM Documentation | 2019-07-31 | 2019-08-06 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6243LT | W200 | ER6243.A1240 | REGION 1 Reactors Shutdown Safety Cases Programme | Gate B PRC Paper Submission | 2019-07-31 | 2019-07-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A15930 | HNB Reactors Shutdown Essential Safety Cases | Summary of Compliance with RADWASTE - Pre Job Brief | 2019-07-31 | 2019-07-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A5400 | HNB Reactors Shutdown Essential Safety Cases | Prepare HF Compliance Assessment for Shutdown Margin Draft EAN | 2019-08-01 | 2020-04-01 | 171 | 0 | 170 | 244 | 100% | 0.70082 | 1 | Completed
ER6370LT | W201 | ER6370.A5480 | HNB Reactors Shutdown Essential Safety Cases | Prepare HF Compliance / Tech Spec As'ment for Core Cooling Draft EAN | 2019-08-01 | 2020-04-01 | 171 | 0 | 170 | 244 | 100% | 0.70082 | 1 | Completed
ER6370LT | W201 | ER6370.A6210 | HNB Reactors Shutdown Essential Safety Cases | LSD Strategy Draft Report Verified by TSA | 2019-08-01 | 2019-08-23 | 17 | 0 | 16 | 22 | 100% | 0.77273 | 1 | Completed
ER6370LT | W201 | ER6370.A6760 | HNB Reactors Shutdown Essential Safety Cases | Prepare Summary of Compliance with RADWASTE Assessment Principles Draft EAN | 2019-08-01 | 2019-08-30 | 21 | 0 | 20 | 29 | 100% | 0.72414 | 1 | Completed
ER6370LT | W201 | ER6370.A5395 | HNB Reactors Shutdown Essential Safety Cases | HF Compliance Assessment for Shutdown Margin Summary | 2019-08-01 | 2020-04-30 | 190 | 0 | 189 | 273 | 100% | 0.69597 | 1 | Completed
ER6370LT | W201 | ER6370.A5475 | HNB Reactors Shutdown Essential Safety Cases | HF Compliance / Tech Spec As'ment for Core Cooling Summary | 2019-08-01 | 2020-04-30 | 190 | 0 | 189 | 273 | 100% | 0.69597 | 1 | Completed
ER6370LT | W201 | ER6370.A6755 | HNB Reactors Shutdown Essential Safety Cases | Summary of Compliance with RADWASTE Assessment Principles Summary | 2019-08-01 | 2019-10-20 | 56 | 0 | 56 | 80 | 100% | 0.7 | 1 | Completed
ER6370LT | W201 | ER6370.A16110 | HNB Reactors Shutdown Essential Safety Cases | Impacts for the Order of Defuelling EAN TR Completed and uploaded to CDMS | 2019-08-01 | 2019-08-27 | 18 | 0 | 17 | 26 | 100% | 0.69231 | 1 | Completed
ER6370LT | W201 | ER6370.A16350 | HNB Reactors Shutdown Essential Safety Cases | Prepare PVCW Calculations - Dropped FPU Fault - EAN - QA Grade 2 | 2019-08-01 | 2019-08-30 | 21 | 0 | 20 | 29 | 100% | 0.72414 | 1 | Completed
ER6370LT | W201 | ER6370.A16145 | HNB Reactors Shutdown Essential Safety Cases | PVCW Calculations - Dropped FPU Fault - EAN - QA Grade 2 Summary | 2019-08-01 | 2019-10-11 | 50 | 0 | 50 | 71 | 100% | 0.70423 | 1 | Completed
ER6370LT | W201 | ER6370.A16700 | HNB Reactors Shutdown Essential Safety Cases | Prepare Summary Conditions Report - EAN - QA Grade 2 | 2019-08-01 | 2019-10-23 | 59 | 0 | 58 | 83 | 100% | 0.71084 | 1 | Completed
ER6370LT | W201 | ER6370.A16305 | HNB Reactors Shutdown Essential Safety Cases | Summary Conditions Report - EAN - QA Grade 2 Summary | 2019-08-01 | 2020-01-15 | 115 | 0 | 115 | 167 | 100% | 0.68862 | 1 | Completed
ER6378LT | W222 | W222.A14100 | HRA Fuel Handling Essential Safety Case | Update Schedule/Estimate from Risk Log & Add Provisions | 2019-08-01 | 2019-09-02 | 22 | 0 | 22 | 32 | 100% | 0.6875 | 1 | Completed
ER6650LT | W226 | W226.A14100 | HYA Fuel Handling Essential Safety Case | Update Schedule/Estimate from Risk Log & Add Provisions | 2019-08-01 | 2019-09-02 | 22 | 0 | 22 | 32 | 100% | 0.6875 | 1 | Completed
ER6243LT | W200 | ER6243.A1390 | REGION 1 Reactors Shutdown Safety Cases Programme | PRC Members Review IRM Documentation | 2019-08-01 | 2019-08-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A1920 | HNB Reactors Shutdown Essential Safety Cases | Prepare Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) | 2019-08-02 | 2019-10-14 | 51 | 0 | 50 | 73 | 100% | 0.69863 | 1 | Completed
ER6370LT | W201 | ER6370.A2880 | HNB Reactors Shutdown Essential Safety Cases | Address Comments from EDF Review on Civil Integrity Overview Draft EAN | 2019-08-02 | 2019-08-09 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6370LT | W201 | ER6370.A3360 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Ass'ment of Graphite behaviour for Shutdown Defuelling Draft Report | 2019-08-02 | 2019-08-09 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6370LT | W201 | ER6370.A7620 | HNB Reactors Shutdown Essential Safety Cases | Address Comments from EDF Review on SDM Assessments with uncertainties / sensitivity studies Draft Report | 2019-08-02 | 2019-08-23 | 16 | 0 | 15 | 21 | 100% | 0.7619 | 1 | Completed
ER6370LT | W201 | ER6370.A1915 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) Summary | 2019-08-02 | 2020-03-27 | 166 | 0 | 166 | 238 | 100% | 0.69748 | 1 | Completed
ER6370LT | W201 | ER6370.A2040 | HNB Reactors Shutdown Essential Safety Cases | Address Comments from EDF Review on Establish Codes and Methods for Safety Case Draft Report | 2019-08-05 | 2019-08-30 | 19 | 0 | 18 | 25 | 100% | 0.76 | 1 | Completed
ER6370LT | W201 | ER6370.A16570 | HNB Reactors Shutdown Essential Safety Cases | Thermal Analysis of FPU - FEAT - Report - QA Grade 2 Verified by TSA | 2019-08-06 | 2019-08-26 | 14 | 0 | 14 | 20 | 100% | 0.7 | 1 | Completed
ER6371LT | W202 | W202.A1250 | HRA Reactors Shutdown Essential Safety Cases | Hold PRC Meeting | 2019-08-08 | 2019-08-08 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1260 | HRA Reactors Shutdown Essential Safety Cases | Gate B PRC Paper Approval | 2019-08-08 | 2019-08-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1250 | HYA Reactors Shutdown Essential Safety Cases | Hold PRC Meeting | 2019-08-08 | 2019-08-08 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1260 | HYA Reactors Shutdown Essential Safety Cases | Gate B PRC Paper Approval | 2019-08-08 | 2019-08-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1360 | REGION 1 Reactors Shutdown Safety Cases Programme | Hold PRC Meeting | 2019-08-08 | 2019-08-08 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1440 | REGION 1 Reactors Shutdown Safety Cases Programme | Gate B PRC Paper Approval | 2019-08-08 | 2019-08-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A2890 | HNB Reactors Shutdown Essential Safety Cases | Issue Civil Integrity Overview Final EAN | 2019-08-09 | 2019-08-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3370 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Ass'ment of Graphite behaviour for Shutdown Defuelling Report | 2019-08-09 | 2019-08-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4040 | HNB Reactors Shutdown Essential Safety Cases | Prepare Specification for Analysis Draft Report | 2019-08-09 | 2019-08-23 | 11 | 0 | 10 | 14 | 100% | 0.78571 | 1 | Completed
ER6370LT | W201 | ER6370.A4035 | HNB Reactors Shutdown Essential Safety Cases | Specification for Analysis Summary | 2019-08-09 | 2019-08-30 | 15 | 0 | 14 | 21 | 100% | 0.71429 | 1 | Completed
ER6371LT | W202 | W202.A1270 | HRA Reactors Shutdown Essential Safety Cases | Modify Estimate, Schedule & Risk Log as Required | 2019-08-09 | 2019-08-12 | 2 | 0 | 1 | 3 | 100% | 0.66667 | 1 | Completed
ER6661LT | W206 | W206.A1270 | HYA Reactors Shutdown Essential Safety Cases | Modify Estimate, Schedule & Risk Log as Required | 2019-08-09 | 2019-08-12 | 6 | 0 | 1 | 3 | 100% | 2 | 1 | Completed
ER6243LT | W200 | ER6243.A1370 | REGION 1 Reactors Shutdown Safety Cases Programme | Modify Estimate, Schedule & Risk Log as Required | 2019-08-09 | 2019-08-09 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A2900 | HNB Reactors Shutdown Essential Safety Cases | Civil Integrity Overview EAN Completed and uploaded to CDMS | 2019-08-12 | 2019-08-19 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6370LT | W201 | ER6370.A3380 | HNB Reactors Shutdown Essential Safety Cases | Ass'ment of Graphite behaviour for Shutdown Defuelling Report TR Completed and uploaded to CDMS | 2019-08-12 | 2019-08-19 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6243LT | W200 | ER6243.A1380 | REGION 1 Reactors Shutdown Safety Cases Programme | Modify IRM Paper as Required | 2019-08-12 | 2019-08-12 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1290 | HRA Reactors Shutdown Essential Safety Cases | Gate B MS PRC Paper Submission | 2019-08-13 | 2019-08-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1280 | HRA Reactors Shutdown Essential Safety Cases | Modify IRM Paper as Required | 2019-08-13 | 2019-08-13 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1290 | HYA Reactors Shutdown Essential Safety Cases | Gate B MS PRC Paper Submission | 2019-08-13 | 2019-08-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1280 | HYA Reactors Shutdown Essential Safety Cases | Modify IRM Paper as Required | 2019-08-13 | 2019-08-13 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1250 | REGION 1 Reactors Shutdown Safety Cases Programme | Gate B MS PRC Paper Submission | 2019-08-13 | 2019-08-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1410 | REGION 1 Reactors Shutdown Safety Cases Programme | Modify Estimate, Schedule, Cost Tool & Risk Log as Required | 2019-08-13 | 2019-08-13 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1420 | REGION 1 Reactors Shutdown Safety Cases Programme | Update Cost Management Tool | 2019-08-13 | 2019-08-19 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6243LT | W200 | ER6243.A1430 | REGION 1 Reactors Shutdown Safety Cases Programme | IRM Members Review IRM Documentation | 2019-08-13 | 2019-08-19 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A1300 | HRA Reactors Shutdown Essential Safety Cases | Modify Estimate, Schedule, Cost Tool & Risk Log as Required | 2019-08-14 | 2019-08-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1310 | HRA Reactors Shutdown Essential Safety Cases | Update Cost Management Tool | 2019-08-14 | 2019-08-14 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1320 | HRA Reactors Shutdown Essential Safety Cases | IRM Members Review IRM Documentation | 2019-08-14 | 2019-08-16 | 3 | 0 | 2 | 2 | 100% | 1.5 | 1 | Completed
ER6661LT | W206 | W206.A1300 | HYA Reactors Shutdown Essential Safety Cases | Modify Estimate, Schedule, Cost Tool & Risk Log as Required | 2019-08-14 | 2019-08-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1310 | HYA Reactors Shutdown Essential Safety Cases | Update Cost Management Tool | 2019-08-14 | 2019-08-14 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1320 | HYA Reactors Shutdown Essential Safety Cases | IRM Members Review IRM Documentation | 2019-08-14 | 2019-08-16 | 3 | 0 | 2 | 2 | 100% | 1.5 | 1 | Completed
ER6370LT | W201 | ER6370.A2910 | HNB Reactors Shutdown Essential Safety Cases | Civil Integrity Overview EAN Completed | 2019-08-19 | 2019-08-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1330 | HRA Reactors Shutdown Essential Safety Cases | Hold MS PRC | 2019-08-20 | 2019-08-20 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1340 | HRA Reactors Shutdown Essential Safety Cases | Gate B MS PRC Approval | 2019-08-20 | 2019-08-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1330 | HYA Reactors Shutdown Essential Safety Cases | Hold MS PRC | 2019-08-20 | 2019-08-20 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1340 | HYA Reactors Shutdown Essential Safety Cases | Gate B MS PRC Approval | 2019-08-20 | 2019-08-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1350 | HYA Reactors Shutdown Essential Safety Cases | Update IRM paper with MS PRC Recommendations | 2019-08-21 | 2019-08-30 | 1 | 0 | 1 | 9 | 100% | 0.11111 | 1 | Completed
ER6243LT | W200 | ER6243.A1400 | REGION 1 Reactors Shutdown Safety Cases Programme | Hold MS PRC | 2019-08-21 | 2019-08-21 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1450 | REGION 1 Reactors Shutdown Safety Cases Programme | Gate B MS PRC Approval | 2019-08-21 | 2019-08-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3180 | HNB Reactors Shutdown Essential Safety Cases | Verified Pressure Boundary Seals Draft Report Issued to EDF for Technical Review. | 2019-08-23 | 2019-08-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3190 | HNB Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals Draft Report Technically Reviewed by EDF SQEP | 2019-08-23 | 2019-08-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3210 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Pressure Boundary Seals Report | 2019-08-23 | 2019-08-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4060 | HNB Reactors Shutdown Essential Safety Cases | Verified Specification for Analysis Draft Report Issued to EDF for Review. | 2019-08-23 | 2019-08-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A6220 | HNB Reactors Shutdown Essential Safety Cases | Verified LSD Strategy Draft Report Issued to EDF for Technical Review. | 2019-08-23 | 2019-08-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7630 | HNB Reactors Shutdown Essential Safety Cases | Issue Final SDM Assessments with uncertainties / sensitivity studies Report Report | 2019-08-23 | 2019-08-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8500 | HNB Reactors Shutdown Essential Safety Cases | Prepare Containment Head Document Draft Report | 2019-08-23 | 2019-10-18 | 40 | 0 | 39 | 56 | 100% | 0.71429 | 1 | Completed
ER6370LT | W201 | ER6370.A8495 | HNB Reactors Shutdown Essential Safety Cases | Claim 2 Containment Head Document Summary | 2019-08-23 | 2020-09-15 | 269 | 0 | 269 | 389 | 100% | 0.69152 | 1 | Completed
ER6370LT | W201 | ER6370.A3200 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Pressure Boundary Seals Draft Report | 2019-08-23 | 2019-08-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A2960 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Component Life Assessment Draft Report | 2019-08-26 | 2019-09-09 | 10 | 0 | 9 | 14 | 100% | 0.71429 | 1 | Completed
ER6370LT | W201 | ER6370.A3040 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Standpipe and Guide Tube Integrity Assessment Draft Report | 2019-08-26 | 2019-09-09 | 10 | 0 | 9 | 14 | 100% | 0.71429 | 1 | Completed
ER6370LT | W201 | ER6370.A3120 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Degradation of Boilers Draft Report | 2019-08-26 | 2019-09-09 | 10 | 0 | 9 | 14 | 100% | 0.71429 | 1 | Completed
ER6370LT | W201 | ER6370.A3440 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Reactor Internals Draft Report | 2019-08-26 | 2019-09-09 | 10 | 0 | 9 | 14 | 100% | 0.71429 | 1 | Completed
ER6370LT | W201 | ER6370.A4070 | HNB Reactors Shutdown Essential Safety Cases | Specification for Analysis Draft Report Reviewed by EDF SQEP | 2019-08-26 | 2019-08-30 | 4 | 0 | 3 | 4 | 100% | 1 | 1 | Completed
ER6370LT | W201 | ER6370.A16580 | HNB Reactors Shutdown Essential Safety Cases | Verified Thermal Analysis of FPU - FEAT - Report - QA Grade 2 Issued to EDF for Technical Review. | 2019-08-26 | 2019-08-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16120 | HNB Reactors Shutdown Essential Safety Cases | Impacts for the Order of Defuelling EAN Completed | 2019-08-27 | 2019-08-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A2050 | HNB Reactors Shutdown Essential Safety Cases | Issue Final Establish Codes and Methods for Safety Case Report | 2019-08-30 | 2019-08-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4110 | HNB Reactors Shutdown Essential Safety Cases | Specification for Analysis Report Completed | 2019-08-30 | 2019-08-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A10550 | HNB Reactors Shutdown Essential Safety Cases | Verified ALARP / BAT/ BPM Draft Report Issued to EDF for Technical Review. | 2019-08-30 | 2019-08-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A10890 | HNB Reactors Shutdown Essential Safety Cases | Issued Uncertainty in SDM Calculations Draft Report to EDF for Review. | 2019-08-30 | 2019-08-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13190 | HNB Reactors Shutdown Essential Safety Cases | Discovery Milestone: Scope confirmation following ONR advice on NSRS (HNB) | 2019-08-30 | 2019-08-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1360 | HRA Reactors Shutdown Essential Safety Cases | Gate B IRM Paper Submission | 2019-08-30 | 2019-08-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1350 | HRA Reactors Shutdown Essential Safety Cases | Update IRM paper with MS PRC Recommendations | 2019-08-30 | 2019-08-30 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1360 | HYA Reactors Shutdown Essential Safety Cases | Gate B IRM Paper Submission | 2019-08-30 | 2019-08-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1480 | REGION 1 Reactors Shutdown Safety Cases Programme | Gate B IRM Paper Submission | 2019-08-30 | 2019-08-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3220 | HNB Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals Report TR Completed and uploaded to CDMS | 2019-09-02 | 2019-09-13 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A3250 | HNB Reactors Shutdown Essential Safety Cases | Gas Chemistry Assessment Draft Report Verified by EDF | 2019-09-02 | 2019-10-31 | 44 | 0 | 43 | 59 | 100% | 0.74576 | 1 | Completed
ER6370LT | W201 | ER6370.A3390 | HNB Reactors Shutdown Essential Safety Cases | Ass'ment of Graphite behaviour for Shutdown Defuelling Report Completed | 2019-09-02 | 2019-09-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A6230 | HNB Reactors Shutdown Essential Safety Cases | LSD Strategy Draft Report Technically Reviewed by EDF SQEP | 2019-09-02 | 2019-09-13 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A6770 | HNB Reactors Shutdown Essential Safety Cases | Summary of Compliance with RADWASTE Assessment Principles Draft EAN Verified by TSA | 2019-09-02 | 2019-10-04 | 25 | 0 | 24 | 32 | 100% | 0.78125 | 1 | Completed
ER6370LT | W201 | ER6370.A7960 | HNB Reactors Shutdown Essential Safety Cases | Prepare Requirements for Severe Accidents Draft Report | 2019-09-02 | 2019-09-13 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A10370 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Structures and Equipment Integrity Draft Report | 2019-09-02 | 2019-09-27 | 20 | 0 | 19 | 25 | 100% | 0.8 | 1 | Completed
ER6370LT | W201 | ER6370.A10560 | HNB Reactors Shutdown Essential Safety Cases | ALARP / BAT/ BPM Draft Report Technically Reviewed by EDF SQEP | 2019-09-02 | 2019-09-20 | 15 | 0 | 14 | 18 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A10630 | HNB Reactors Shutdown Essential Safety Cases | Verified SIn Reactor NSP Compliance and Risk Report - Draft Report Issued to EDF for Technical Review. | 2019-09-02 | 2019-09-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A10640 | HNB Reactors Shutdown Essential Safety Cases | In Reactor NSP Compliance and Risk Report - Draft Report Technically Reviewed by EDF SQEP | 2019-09-02 | 2019-09-13 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A10900 | HNB Reactors Shutdown Essential Safety Cases | Uncertainty in SDM Calculations Draft Report Reviewed by EDF SQEP | 2019-09-02 | 2020-02-07 | 112 | 0 | 111 | 158 | 100% | 0.70886 | 1 | Completed
ER6370LT | W201 | ER6370.A7955 | HNB Reactors Shutdown Essential Safety Cases | Requirements for Severe Accidents Summary | 2019-09-02 | 2019-10-24 | 39 | 0 | 39 | 52 | 100% | 0.75 | 1 | Completed
ER6370LT | W201 | ER6370.A11340 | HNB Reactors Shutdown Essential Safety Cases | Prepare Scope Additional SDM Calcs Report (Phase 2) | 2019-09-02 | 2019-09-20 | 15 | 0 | 14 | 18 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A16360 | HNB Reactors Shutdown Essential Safety Cases | PVCW Calculations - Dropped FPU Fault - EAN - QA Grade 2 Verified by TSA | 2019-09-02 | 2019-09-12 | 9 | 0 | 8 | 10 | 100% | 0.9 | 1 | Completed
ER6370LT | W201 | ER6370.A16440 | HNB Reactors Shutdown Essential Safety Cases | Consideration of the ability of the PCPV to satisfy support in-resident FPUs - EAN - QA Grade 2 Verified by TSA | 2019-09-02 | 2019-09-06 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A16590 | HNB Reactors Shutdown Essential Safety Cases | Thermal Analysis of FPU - FEAT - Report - QA Grade 2 Technically Reviewed by EDF SQEP | 2019-09-02 | 2019-09-06 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6378LT | W222 | W222.A14010 | HRA Fuel Handling Essential Safety Case | PCL Validate & Approve Baseline Package for PRC Submission | 2019-09-02 | 2019-09-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A14000 | HRA Fuel Handling Essential Safety Case | Add Data to Scheme Paper | 2019-09-02 | 2019-09-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A14070 | HRA Fuel Handling Essential Safety Case | Ensure Alignment of Schedule & Estimate | 2019-09-02 | 2019-09-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A14070 | HYA Fuel Handling Essential Safety Case | Ensure Alignment of Schedule & Estimate | 2019-09-02 | 2019-09-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A14000 | HYA Fuel Handling Essential Safety Case | Add Data to Scheme Paper | 2019-09-02 | 2019-09-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A14010 | HYA Fuel Handling Essential Safety Case | PCL Validate & Approve Baseline Package for PRC Submission | 2019-09-02 | 2019-09-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3620 | HNB Reactors Shutdown Essential Safety Cases | MACE Dataset Development and Analysis for Minimum Temperature Issue TR Completed and uploaded to CDMS | 2019-09-03 | 2019-09-06 | 4 | 0 | 3 | 3 | 100% | 1.3333 | 1 | Completed
ER6378LT | W222 | W222.A14120 | HRA Fuel Handling Essential Safety Case | PRC Members Review Scheme Documentation | 2019-09-04 | 2019-09-10 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6378LT | W222 | W222.A14020 | HRA Fuel Handling Essential Safety Case | Issue Scheme Paper to PRC Members | 2019-09-04 | 2019-09-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A14020 | HYA Fuel Handling Essential Safety Case | Issue Scheme Paper to PRC Members | 2019-09-04 | 2019-09-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A14120 | HYA Fuel Handling Essential Safety Case | PRC Members Review Scheme Documentation | 2019-09-04 | 2019-09-10 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A3630 | HNB Reactors Shutdown Essential Safety Cases | MACE Dataset Development and Analysis for Minimum Temperature Issue Completed | 2019-09-06 | 2019-09-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16450 | HNB Reactors Shutdown Essential Safety Cases | Verified ability of the PCPV to satisfy support in-resident FPUs - EAN - QA Grade 2 Issued to EDF for TR. | 2019-09-06 | 2019-09-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1660 | HNB Reactors Shutdown Essential Safety Cases | Define Project Control Structures (WBS/CBS/OBS/PBS) | 2019-09-09 | 2019-09-27 | 15 | 0 | 14 | 18 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A2970 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Component Life Assessment Report | 2019-09-09 | 2019-09-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3050 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Standpipe and Guide Tube Integrity Assessment Report | 2019-09-09 | 2019-09-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3130 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Degradation of Boilers Report | 2019-09-09 | 2019-09-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3450 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Reactor Internals Report | 2019-09-09 | 2019-09-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16460 | HNB Reactors Shutdown Essential Safety Cases | ability of the PCPV to satisfy support in-resident FPUs - EAN - QA Grade 2 Technically Reviewed by EDF SQEP | 2019-09-09 | 2019-10-02 | 18 | 0 | 17 | 23 | 100% | 0.78261 | 1 | Completed
ER6370LT | W201 | ER6370.A16600 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Thermal Analysis of FPU - FEAT - Report - QA Grade 2 | 2019-09-09 | 2019-09-13 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A1680 | HNB Reactors Shutdown Essential Safety Cases | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 2019-09-09 | 2019-10-18 | 30 | 0 | 29 | 39 | 100% | 0.76923 | 1 | Completed
ER6370LT | W201 | ER6370.A2980 | HNB Reactors Shutdown Essential Safety Cases | Component Life Assessment Report TR Completed and uploaded to CDMS | 2019-09-10 | 2019-10-22 | 31 | 0 | 30 | 42 | 100% | 0.7381 | 1 | Completed
ER6370LT | W201 | ER6370.A3060 | HNB Reactors Shutdown Essential Safety Cases | Standpipe and Guide Tube Integrity Assessment Report TR Completed and uploaded to CDMS | 2019-09-10 | 2019-10-22 | 31 | 0 | 30 | 42 | 100% | 0.7381 | 1 | Completed
ER6370LT | W201 | ER6370.A3140 | HNB Reactors Shutdown Essential Safety Cases | Degradation of Boilers Report TR Completed and uploaded to CDMS | 2019-09-10 | 2019-10-22 | 31 | 0 | 30 | 42 | 100% | 0.7381 | 1 | Completed
ER6370LT | W201 | ER6370.A3460 | HNB Reactors Shutdown Essential Safety Cases | Reactor Internals Report TR Completed and uploaded to CDMS | 2019-09-10 | 2019-10-22 | 31 | 0 | 30 | 42 | 100% | 0.7381 | 1 | Completed
ER6370LT | W201 | ER6370.A5570 | HNB Reactors Shutdown Essential Safety Cases | HF Risk Assessment Draft Report Verified by TSA | 2019-09-10 | 2019-09-27 | 14 | 0 | 13 | 17 | 100% | 0.82353 | 1 | Completed
ER6370LT | W201 | ER6370.A4850 | HNB Reactors Shutdown Essential Safety Cases | Review of/Changes to Emergency Arrangements Draft Report Verified by TSA | 2019-09-11 | 2019-09-24 | 10 | 0 | 9 | 13 | 100% | 0.76923 | 1 | Completed
ER6370LT | W201 | ER6370.A16370 | HNB Reactors Shutdown Essential Safety Cases | Verified PVCW Calculations - Dropped FPU Fault - EAN - QA Grade 2 Issued to EDF for Technical Review. | 2019-09-12 | 2019-09-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3230 | HNB Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals Report Completed | 2019-09-13 | 2019-09-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16380 | HNB Reactors Shutdown Essential Safety Cases | PVCW Calculations - Dropped FPU Fault - EAN - QA Grade 2 Technically Reviewed by EDF SQEP | 2019-09-13 | 2019-09-19 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A16610 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Thermal Analysis of FPU - FEAT - Report - QA Grade 2 | 2019-09-13 | 2019-09-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A17390 | HNB Reactors Shutdown Essential Safety Cases | >>>INCOMING ENABLER (W221.A9570) Criticality Assessment for Dropped FPU at Reactor (DRY Condition) EAN Available | 2019-09-13 | 2019-09-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A17410 | HNB Reactors Shutdown Essential Safety Cases | >>>MIRROR OF INCOMING ENABLER (W221.A9570) Criticality Assessment for Dropped FPU at Reactor (DRY Con) EAN Available | 2019-09-13 | 2019-09-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1520 | REGION 1 Reactors Shutdown Safety Cases Programme | Gate B - 6.1 Reactors Shutdown Safety Cases Programme HAR/HYA | 2019-09-16 | 2019-09-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4200 | HNB Reactors Shutdown Essential Safety Cases | Prepare Core Cooling Head Document Draft Report | 2019-09-16 | 2020-06-11 | 187 | 0 | 186 | 269 | 100% | 0.69517 | 1 | Completed
ER6370LT | W201 | ER6370.A6240 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd LSD Strategy Draft Report | 2019-09-16 | 2019-09-23 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6370LT | W201 | ER6370.A7970 | HNB Reactors Shutdown Essential Safety Cases | Requirements for Severe Accidents Draft Report Verified by TSA | 2019-09-16 | 2019-09-20 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A10650 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd In Reactor NSP Compliance and Risk Report | 2019-09-16 | 2019-09-27 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A4195 | HNB Reactors Shutdown Essential Safety Cases | Core Cooling Head Document Summary | 2019-09-16 | 2020-10-09 | 276 | 0 | 271 | 389 | 100% | 0.70951 | 1 | Completed
ER6370LT | W201 | ER6370.A16620 | HNB Reactors Shutdown Essential Safety Cases | Thermal Analysis of FPU - FEAT - Report - QA Grade 2 TR Completed and uploaded to CDMS | 2019-09-16 | 2019-09-23 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6371LT | W202 | W202.A1370 | HRA Reactors Shutdown Essential Safety Cases | Gate B IRM Paper Approval | 2019-09-16 | 2019-09-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1370 | HYA Reactors Shutdown Essential Safety Cases | Gate B IRM Paper Approval | 2019-09-16 | 2019-09-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1470 | REGION 1 Reactors Shutdown Safety Cases Programme | Hold IRM | 2019-09-16 | 2019-09-16 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1380 | HRA Reactors Shutdown Essential Safety Cases | Hold IRM | 2019-09-16 | 2019-09-16 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1380 | HYA Reactors Shutdown Essential Safety Cases | Hold IRM | 2019-09-16 | 2019-09-16 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | ER6243.A1460 | REGION 1 Reactors Shutdown Safety Cases Programme | Gate B IRM Paper Approval - HYA And HRA | 2019-09-16 | 2019-09-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A14160 | HRA Fuel Handling Essential Safety Case | Issue Scheme Paper to Major Schemes PRC Members | 2019-09-17 | 2019-09-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A14160 | HYA Fuel Handling Essential Safety Case | Issue Scheme Paper to Major Schemes PRC Members | 2019-09-17 | 2019-09-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8440 | HNB Reactors Shutdown Essential Safety Cases | Issue Reactor Coolant Chemistry Conditions Draft Report to EDF for Review. | 2019-09-18 | 2019-09-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A14130 | HRA Fuel Handling Essential Safety Case | Hold PRC Meeting | 2019-09-18 | 2019-09-18 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A14130 | HYA Fuel Handling Essential Safety Case | Hold PRC Meeting | 2019-09-18 | 2019-09-18 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8450 | HNB Reactors Shutdown Essential Safety Cases | Reactor Coolant Chemistry Conditions Draft Report Reviewed by EDF SQEP | 2019-09-19 | 2019-10-31 | 31 | 0 | 30 | 42 | 100% | 0.7381 | 1 | Completed
ER6378LT | W222 | W222.A14140 | HRA Fuel Handling Essential Safety Case | Modify Estimate, Schedule & Risk Log as Required | 2019-09-19 | 2019-09-20 | 2 | 0 | 1 | 1 | 100% | 2 | 1 | Completed
ER6650LT | W226 | W226.A14140 | HYA Fuel Handling Essential Safety Case | Modify Estimate, Schedule & Risk Log as Required | 2019-09-19 | 2019-09-20 | 2 | 0 | 1 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | ER6370.A7980 | HNB Reactors Shutdown Essential Safety Cases | Verified Requirements for Severe Accidents Draft Report Issued to EDF for Technical Review. | 2019-09-20 | 2019-09-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13730 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Margin Compliance Report - Draft and issue RFS | 2019-09-20 | 2019-09-20 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13740 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Margin Compliance Report - Supplier prepare and issue Offer | 2019-09-20 | 2019-09-20 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13750 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Margin Compliance Report - Review Offer, prepare and issue CI | 2019-09-20 | 2019-09-20 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13760 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Margin Compliance Report - Supplier mobilisation time | 2019-09-20 | 2019-09-20 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13770 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Margin Compliance Report - Pre Job Brief | 2019-09-20 | 2019-09-20 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13725 | HNB Reactors Shutdown Essential Safety Cases | RFS - Shutdown Margin Compliance Report Summary | 2019-09-20 | 2019-09-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16390 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd PVCW Calculations - Dropped FPU Fault - EAN - QA Grade 2 | 2019-09-20 | 2019-09-26 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6378LT | W222 | W222.A14150 | HRA Fuel Handling Essential Safety Case | Modify Scheme Paper as Required | 2019-09-20 | 2019-09-20 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A14150 | HYA Fuel Handling Essential Safety Case | Modify Scheme Paper as Required | 2019-09-20 | 2019-09-20 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4760 | HNB Reactors Shutdown Essential Safety Cases | Prepare Worker Dose and Risks from Faults Draft Report | 2019-09-23 | 2019-11-22 | 45 | 0 | 44 | 60 | 100% | 0.75 | 1 | Completed
ER6370LT | W201 | ER6370.A6250 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final LSD Strategy Report | 2019-09-23 | 2019-09-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7990 | HNB Reactors Shutdown Essential Safety Cases | Requirements for Severe Accidents Draft Report Technically Reviewed by EDF SQEP | 2019-09-23 | 2019-09-27 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A10570 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd ALARP / BAT/ BPM Draft Report | 2019-09-23 | 2019-09-30 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6370LT | W201 | ER6370.A4755 | HNB Reactors Shutdown Essential Safety Cases | Worker Dose and Risks from Faults Summary | 2019-09-23 | 2020-02-28 | 111 | 0 | 111 | 158 | 100% | 0.70253 | 1 | Completed
ER6370LT | W201 | ER6370.A16630 | HNB Reactors Shutdown Essential Safety Cases | Thermal Analysis of FPU - FEAT - Report - QA Grade 2 Completed | 2019-09-23 | 2019-09-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A14460 | HRA Fuel Handling Essential Safety Case | Modify Estimate, Schedule & Risk Log as Required | 2019-09-23 | 2019-09-30 | 6 | 0 | 6 | 7 | 100% | 0.85714 | 1 | Completed
ER6650LT | W226 | W226.A14460 | HYA Fuel Handling Essential Safety Case | Modify Estimate, Schedule & Risk Log as Required | 2019-09-23 | 2019-09-30 | 6 | 0 | 6 | 7 | 100% | 0.85714 | 1 | Completed
ER6370LT | W201 | ER6370.A4860 | HNB Reactors Shutdown Essential Safety Cases | Verified Review of/Changes to Emergency Arrangements Draft Report Issued to EDF for Technical Review. | 2019-09-24 | 2019-09-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A6260 | HNB Reactors Shutdown Essential Safety Cases | LSD Strategy Report TR Completed and uploaded to CDMS | 2019-09-24 | 2019-10-04 | 9 | 0 | 8 | 10 | 100% | 0.9 | 1 | Completed
ER6370LT | W201 | ER6370.A4870 | HNB Reactors Shutdown Essential Safety Cases | Review of/Changes to Emergency Arrangements Draft Report Technically Reviewed by EDF SQEP | 2019-09-25 | 2019-09-27 | 3 | 0 | 2 | 2 | 100% | 1.5 | 1 | Completed
ER6370LT | W201 | ER6370.A16400 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final PVCW Calculations - Dropped FPU Fault - EAN - QA Grade 2 | 2019-09-26 | 2019-09-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1750 | HNB Reactors Shutdown Essential Safety Cases | Prepare Draft Project Definition Document (PDD) | 2019-09-27 | 2019-10-23 | 19 | 0 | 18 | 26 | 100% | 0.73077 | 1 | Completed
ER6370LT | W201 | ER6370.A1890 | HNB Reactors Shutdown Essential Safety Cases | Confirm Objectives to be Delivered at Gate C | 2019-09-27 | 2019-10-23 | 19 | 0 | 19 | 26 | 100% | 0.73077 | 1 | Completed
ER6370LT | W201 | ER6370.A1900 | HNB Reactors Shutdown Essential Safety Cases | Initial high level scope of programme | 2019-09-27 | 2019-10-23 | 19 | 0 | 19 | 26 | 100% | 0.73077 | 1 | Completed
ER6370LT | W201 | ER6370.A3900 | HNB Reactors Shutdown Essential Safety Cases | Verified Model and Datasets Part 2 Draft Reports Issued to EDF for Technical Review. | 2019-09-27 | 2019-09-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A5580 | HNB Reactors Shutdown Essential Safety Cases | Verified HF Risk Assessment Draft Report Issued to EDF for Technical Review. | 2019-09-27 | 2019-09-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A10380 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Structures and Equipment Integrity Report | 2019-09-27 | 2019-09-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A10660 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final In Reactor NSP Compliance and Risk Report | 2019-09-27 | 2019-09-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16410 | HNB Reactors Shutdown Essential Safety Cases | PVCW Calculations - Dropped FPU Fault - EAN - QA Grade 2 TR Completed and uploaded to CDMS | 2019-09-27 | 2019-10-11 | 11 | 0 | 10 | 14 | 100% | 0.78571 | 1 | Completed
ER6370LT | W201 | ER6370.A4120 | HNB Reactors Shutdown Essential Safety Cases | Prepare Shutdown Cooling Analysis Draft Report | 2019-09-30 | 2020-01-31 | 87 | 0 | 86 | 123 | 100% | 0.70732 | 1 | Completed
ER6370LT | W201 | ER6370.A4880 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Review of/Changes to Emergency Arrangements Draft Report | 2019-09-30 | 2019-10-04 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A5590 | HNB Reactors Shutdown Essential Safety Cases | HF Risk Assessment Draft Report Technically Reviewed by EDF SQEP | 2019-09-30 | 2019-10-10 | 9 | 0 | 8 | 10 | 100% | 0.9 | 1 | Completed
ER6370LT | W201 | ER6370.A7700 | HNB Reactors Shutdown Essential Safety Cases | ALARP input to/from Claim 5 | 2019-09-30 | 2019-11-29 | 45 | 0 | 44 | 60 | 100% | 0.75 | 1 | Completed
ER6370LT | W201 | ER6370.A8000 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Requirements for Severe Accidents Draft Report | 2019-09-30 | 2019-10-17 | 14 | 0 | 13 | 17 | 100% | 0.82353 | 1 | Completed
ER6370LT | W201 | ER6370.A10580 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final ALARP / BAT/ BPM Report | 2019-09-30 | 2019-09-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A10600 | HNB Reactors Shutdown Essential Safety Cases | ALARP / BAT/ BPM Report Completed | 2019-09-30 | 2019-09-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A10670 | HNB Reactors Shutdown Essential Safety Cases | In Reactor NSP Compliance and Risk Report TR Completed and uploaded to CDMS | 2019-09-30 | 2019-11-15 | 35 | 0 | 34 | 46 | 100% | 0.76087 | 1 | Completed
ER6370LT | W201 | ER6370.A4115 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Cooling Analysis Summary | 2019-09-30 | 2020-04-28 | 147 | 0 | 147 | 211 | 100% | 0.69668 | 1 | Completed
ER6370LT | W201 | ER6370.A17340 | HNB Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W221) ALARP / BAT/ BPM Report Completed | 2019-09-30 | 2019-09-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A17350 | HNB Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W221) Pressure Boundary Seals Report Completed | 2019-09-30 | 2019-09-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A10590 | HNB Reactors Shutdown Essential Safety Cases | ALARP / BAT/ BPM Report TR Completed and uploaded to CDMS | 2019-09-30 | 2019-09-30 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3910 | HNB Reactors Shutdown Essential Safety Cases | Model and Datasets Part 2 Draft Reports Technically Reviewed by EDF SQEP | 2019-10-01 | 2019-10-25 | 19 | 0 | 18 | 24 | 100% | 0.79167 | 1 | Completed
ER6370LT | W201 | ER6370.A4400 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Fault Schedule Review (Plant Based Faults) Draft Report | 2019-10-01 | 2019-11-29 | 44 | 0 | 43 | 59 | 100% | 0.74576 | 1 | Completed
ER6370LT | W201 | ER6370.A4480 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Fault Schedule Review (Harzards) Draft Report | 2019-10-01 | 2019-11-29 | 44 | 0 | 43 | 59 | 100% | 0.74576 | 1 | Completed
ER6370LT | W201 | ER6370.A6930 | HNB Reactors Shutdown Essential Safety Cases | Boilers and Gas Circulator Performance Draft EAN Verified by TSA | 2019-10-01 | 2019-12-20 | 59 | 0 | 58 | 80 | 100% | 0.7375 | 1 | Completed
ER6370LT | W201 | ER6370.A7010 | HNB Reactors Shutdown Essential Safety Cases | Boiler Supporting Systems Draft EAN Verified by TSA | 2019-10-01 | 2019-11-20 | 37 | 0 | 36 | 50 | 100% | 0.74 | 1 | Completed
ER6370LT | W201 | ER6370.A7640 | HNB Reactors Shutdown Essential Safety Cases | SDM Assessments with uncertainties / sensitivity studies Report Completed and Uploaded to CDMS | 2019-10-01 | 2019-11-14 | 33 | 0 | 32 | 44 | 100% | 0.75 | 1 | Completed
ER6370LT | W201 | ER6370.A9470 | HNB Reactors Shutdown Essential Safety Cases | Boiler Control and Protection Draft Report Verified by TSA | 2019-10-01 | 2019-10-18 | 14 | 0 | 14 | 17 | 100% | 0.82353 | 1 | Completed
ER6370LT | W201 | ER6370.A9550 | HNB Reactors Shutdown Essential Safety Cases | Reactor Cooling Systems Draft Report Verified by TSA | 2019-10-01 | 2019-10-18 | 14 | 0 | 14 | 17 | 100% | 0.82353 | 1 | Completed
ER6370LT | W201 | ER6370.A10390 | HNB Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity Report TR Completed and uploaded to CDMS | 2019-10-01 | 2019-10-21 | 15 | 0 | 14 | 20 | 100% | 0.75 | 1 | Completed
ER6378LT | W222 | W222.A14470 | HRA Fuel Handling Essential Safety Case | Modify Scheme Paper as Required | 2019-10-01 | 2019-10-04 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6650LT | W226 | W226.A14470 | HYA Fuel Handling Essential Safety Case | Modify Scheme Paper as Required | 2019-10-01 | 2019-10-04 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6370LT | W201 | ER6370.A16470 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd ability of the PCPV to satisfy support in-resident FPUs - EAN - QA Grade 2 | 2019-10-03 | 2019-10-09 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A4890 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Review of/Changes to Emergency Arrangements Report | 2019-10-04 | 2019-10-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A6270 | HNB Reactors Shutdown Essential Safety Cases | LSD Strategy Report Completed | 2019-10-04 | 2019-10-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A6780 | HNB Reactors Shutdown Essential Safety Cases | Verified Summary of Compliance with RADWASTE Assessment Principles Draft EAN Issued to EDF for Technical Review. | 2019-10-04 | 2019-10-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A14440 | HRA Fuel Handling Essential Safety Case | Issue Scheme Paper to IRM Members | 2019-10-04 | 2019-10-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A14440 | HYA Fuel Handling Essential Safety Case | Issue Scheme Paper to IRM Members | 2019-10-04 | 2019-10-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4900 | HNB Reactors Shutdown Essential Safety Cases | Review of/Changes to Emergency Arrangements Report TR Completed and uploaded to CDMS | 2019-10-07 | 2019-10-11 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A6790 | HNB Reactors Shutdown Essential Safety Cases | Summary of Compliance with RADWASTE Assessment Principles Draft EAN Technically Reviewed by EDF SQEP | 2019-10-07 | 2019-10-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A6800 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Summary of Compliance with RADWASTE Assessment Principles Draft EAN | 2019-10-07 | 2019-10-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A6810 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Summary of Compliance with RADWASTE Assessment Principles EAN | 2019-10-07 | 2019-10-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A6820 | HNB Reactors Shutdown Essential Safety Cases | Summary of Compliance with RADWASTE Assessment Principles EAN TR Completed and uploaded to CDMS | 2019-10-07 | 2019-10-20 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6371LT | W202 | W202.A1420 | HRA Reactors Shutdown Essential Safety Cases | Phase 2 Project Management - Gate B - C | 2019-10-07 | 2021-09-01 | 518 | 0 | 481 | 695 | 100% | 0.74532 | 1 | Completed
ER6371LT | W202 | W202.A1410 | HRA Reactors Shutdown Essential Safety Cases | Commence Supporting References or Supporting EC's (HRA) | 2019-10-07 | 2019-10-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1420 | HYA Reactors Shutdown Essential Safety Cases | Phase 2 Project Management - Gate B - C | 2019-10-07 | 2021-09-01 | 772 | 0 | 481 | 695 | 100% | 1.1108 | 1 | Completed
ER6661LT | W206 | W206.A1410 | HYA Reactors Shutdown Essential Safety Cases | Commence Supporting References or Supporting EC's (HYA) | 2019-10-07 | 2019-10-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A14180 | HRA Fuel Handling Essential Safety Case | IRM Members Review Sceme Paper Documentation | 2019-10-07 | 2019-10-11 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6650LT | W226 | W226.A14180 | HYA Fuel Handling Essential Safety Case | IRM Members Review Sceme Paper Documentation | 2019-10-07 | 2019-10-11 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A16480 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final PVCW Calculations - Dropped FPU Fault - EAN - QA Grade 2 | 2019-10-09 | 2019-10-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16490 | HNB Reactors Shutdown Essential Safety Cases | ability of the PCPV to satisfy support in-resident FPUs - EAN - QA Grade 2 TR Completed and uploaded to CDMS | 2019-10-10 | 2019-10-16 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6243LT | W200 | A1300 | REGION 1 Reactors Shutdown Safety Cases Programme | Gate EC2 completed EC 363701 & 364023 <NSRS SC Approach & Outline> (Cat 1 Milestone) (HPB, HNB) | 2019-10-11 | 2019-10-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4910 | HNB Reactors Shutdown Essential Safety Cases | Review of/Changes to Emergency Arrangements Report Completed | 2019-10-11 | 2019-10-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A5600 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd HF Risk Assessment Draft Report | 2019-10-11 | 2019-10-18 | 6 | 0 | 6 | 7 | 100% | 0.85714 | 1 | Completed
ER6370LT | W201 | ER6243.A1100 | HNB Reactors Shutdown Essential Safety Cases | Gate EC2 completed EC 364023 <NSRS SC Approach & Outline> (Cat 1 Milestone) (HNB) | 2019-10-11 | 2019-10-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16420 | HNB Reactors Shutdown Essential Safety Cases | PVCW Calculations - Dropped FPU Fault - EAN - QA Grade 2 Completed | 2019-10-11 | 2019-10-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1930 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) Verified by TSA | 2019-10-15 | 2019-10-21 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A8190.E10 | REGION 1 Defuelling Programme Fuel Handling Safety Case | [PR KDM] Gate B for HRA HYA Station Fuel Handling Safety Case Programme | 2019-10-16 | 2019-10-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1700 | HNB Reactors Shutdown Essential Safety Cases | Hold Risk Workshop | 2019-10-16 | 2019-10-16 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16500 | HNB Reactors Shutdown Essential Safety Cases | ability of the PCPV to satisfy support in-resident FPUs - EAN - QA Grade 2 Completed | 2019-10-16 | 2019-10-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25950 | HRA Fuel Handling Essential Safety Case | Basis of Analysis Report ##(Cost Summary)## (NEW) (C5) | 2019-10-16 | 2021-04-06 | 377 | 0 | 371 | 538 | 100% | 0.70074 | 1 | Completed
ER6378LT | W222 | W222.A23170 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Basis of Analysis Report EAN (REV 000) | 2019-10-16 | 2019-10-16 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23170 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Basis of Analysis Report EAN (REV 000) | 2019-10-16 | 2019-10-16 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25950 | HYA Fuel Handling Essential Safety Case | Basis of Analysis Report ##(Cost Summary)## (NEW) (C5) | 2019-10-16 | 2021-04-06 | 377 | 0 | 371 | 538 | 100% | 0.70074 | 1 | Completed
ER6378LT | W222 | W222.A14190 | HRA Fuel Handling Essential Safety Case | Hold IRM Meeting | 2019-10-16 | 2019-10-16 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A14190 | HYA Fuel Handling Essential Safety Case | Hold IRM Meeting | 2019-10-16 | 2019-10-16 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A13290 | HRA Fuel Handling Essential Safety Case | Gate B for Region 1 - HYA HRA Defuelling Fuel Handling Essential Safety Case | 2019-10-16 | 2019-10-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A16690 | HRA Fuel Handling Essential Safety Case | Gate B IRM Approval | 2019-10-16 | 2019-10-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A16690 | HYA Fuel Handling Essential Safety Case | Gate B IRM Approval | 2019-10-16 | 2019-10-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A13290 | HYA Fuel Handling Essential Safety Case | Gate B for Region 1 - HYA Defuelling Fuel Handling Essential Safety Case | 2019-10-16 | 2019-10-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1710 | HNB Reactors Shutdown Essential Safety Cases | Complete Risk Log with Estimates | 2019-10-17 | 2019-10-18 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | ER6370.A8010 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Requirements for Severe Accidents Report | 2019-10-17 | 2019-10-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A23180 | HRA Fuel Handling Essential Safety Case | Draft Basis of Analysis Report EAN (REV 000) | 2019-10-17 | 2020-04-15 | 125 | 0 | 124 | 181 | 100% | 0.69061 | 1 | Completed
ER6650LT | W226 | W226.A23180 | HYA Fuel Handling Essential Safety Case | Draft Basis of Analysis Report EAN (REV 000) | 2019-10-17 | 2020-04-15 | 125 | 0 | 124 | 181 | 100% | 0.69061 | 1 | Completed
ER6370LT | W201 | ER6370.A5610 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final HF Risk Assessment Report | 2019-10-18 | 2019-10-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8020 | HNB Reactors Shutdown Essential Safety Cases | Requirements for Severe AccidentsReport TR Completed and uploaded to CDMS | 2019-10-18 | 2019-10-24 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A9480 | HNB Reactors Shutdown Essential Safety Cases | Verified Boiler Control and Protection Draft Report Issued to EDF for Technical Review. | 2019-10-18 | 2019-10-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A9560 | HNB Reactors Shutdown Essential Safety Cases | Verified Reactor Cooling Systems Draft Report Issued to EDF for Technical Review. | 2019-10-18 | 2019-10-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A6830 | HNB Reactors Shutdown Essential Safety Cases | Summary of Compliance with RADWASTE Assessment Principles EAN Completed | 2019-10-20 | 2019-10-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1940 | HNB Reactors Shutdown Essential Safety Cases | Verified Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) Issued to EDF for Technical Revi | 2019-10-21 | 2019-10-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A5620 | HNB Reactors Shutdown Essential Safety Cases | HF Risk Assessment Report TR Completed and uploaded to CDMS | 2019-10-21 | 2019-11-01 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A8510 | HNB Reactors Shutdown Essential Safety Cases | Containment Head Document Draft Report Verified by TSA | 2019-10-21 | 2020-01-31 | 72 | 0 | 71 | 102 | 100% | 0.70588 | 1 | Completed
ER6370LT | W201 | ER6370.A9490 | HNB Reactors Shutdown Essential Safety Cases | Boiler Control and Protection Draft Report Technically Reviewed by EDF SQEP | 2019-10-21 | 2019-11-08 | 15 | 0 | 14 | 18 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A9570 | HNB Reactors Shutdown Essential Safety Cases | Reactor Cooling Systems Draft Report Technically Reviewed by EDF SQEP | 2019-10-21 | 2019-11-08 | 15 | 0 | 14 | 18 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A10400 | HNB Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity Report Completed | 2019-10-21 | 2019-10-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1910 | HNB Reactors Shutdown Essential Safety Cases | Workshop to agree scope, effort and links | 2019-10-21 | 2019-10-31 | 9 | 0 | 8 | 10 | 100% | 0.9 | 1 | Completed
ER6370LT | W201 | ER6370.A1950 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) Technically Reviewed by EDF SQEP | 2019-10-22 | 2019-11-29 | 29 | 0 | 28 | 38 | 100% | 0.76316 | 1 | Completed
ER6370LT | W201 | ER6370.A2990 | HNB Reactors Shutdown Essential Safety Cases | Component Life Assessment Report Completed | 2019-10-22 | 2019-10-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3070 | HNB Reactors Shutdown Essential Safety Cases | Standpipe and Guide Tube Integrity Assessment Report Completed | 2019-10-22 | 2019-10-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3150 | HNB Reactors Shutdown Essential Safety Cases | Degradation of Boilers Report Completed | 2019-10-22 | 2019-10-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3470 | HNB Reactors Shutdown Essential Safety Cases | Reactor Internals Report Completed | 2019-10-22 | 2019-10-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16710 | HNB Reactors Shutdown Essential Safety Cases | Summary Conditions Report - EAN - QA Grade 2 Verified by TSA | 2019-10-23 | 2019-11-29 | 28 | 0 | 27 | 37 | 100% | 0.75676 | 1 | Completed
ER6370LT | W201 | ER6370.A1670 | HNB Reactors Shutdown Essential Safety Cases | Plan Scope in Primavera (Level 2 C-D & Level 1 Lifecycle) | 2019-10-24 | 2019-11-18 | 18 | 0 | 17 | 25 | 100% | 0.72 | 1 | Completed
ER6370LT | W201 | ER6370.A8030 | HNB Reactors Shutdown Essential Safety Cases | Requirements for Severe Accidents Report Completed | 2019-10-24 | 2019-10-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A2060 | HNB Reactors Shutdown Essential Safety Cases | Establish Codes and Methods for Safety Case Report Completed and Uploaded to CDMS | 2019-10-25 | 2019-11-08 | 11 | 0 | 10 | 14 | 100% | 0.78571 | 1 | Completed
ER6370LT | W201 | ER6370.A3920 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Model and Datasets Part 2 Draft Report | 2019-10-25 | 2019-10-31 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A3260 | HNB Reactors Shutdown Essential Safety Cases | Verified Gas Chemistry Assessment Draft Report Issued to EDF for Technical Review. | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3270 | HNB Reactors Shutdown Essential Safety Cases | Gas Chemistry Assessment Draft Report Technically Reviewed by EDF SQEP | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3280 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Gas Chemistry Assessment Draft Report | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3290 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Gas Chemistry Assessment Report | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3930 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Model and Datasets Part 2 Reports | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A5630 | HNB Reactors Shutdown Essential Safety Cases | HF Risk Assessment Report Completed | 2019-10-31 | 2019-10-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3940 | HNB Reactors Shutdown Essential Safety Cases | Model and Datasets Part 2 Reports TR Completed and uploaded to CDMS | 2019-11-01 | 2019-11-29 | 21 | 0 | 20 | 28 | 100% | 0.75 | 1 | Completed
ER6370LT | W201 | ER6370.A7800 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Margin Head Document Verified by TSA | 2019-11-01 | 2019-12-06 | 26 | 0 | 25 | 35 | 100% | 0.74286 | 1 | Completed
ER6370LT | W201 | ER6370.A8460 | HNB Reactors Shutdown Essential Safety Cases | Address Comments on Reviwed Reactor Coolant Chemistry Conditions Draft Report | 2019-11-01 | 2019-11-29 | 21 | 0 | 20 | 28 | 100% | 0.75 | 1 | Completed
ER6370LT | W201 | ER6370.A3300 | HNB Reactors Shutdown Essential Safety Cases | Gas Chemistry Assessment Report TR Completed and uploaded to CDMS | 2019-11-04 | 2019-11-29 | 20 | 0 | 19 | 25 | 100% | 0.8 | 1 | Completed
ER6370LT | W201 | ER6370.A2070 | HNB Reactors Shutdown Essential Safety Cases | Establish Codes and Methods for Safety Case Report Completed | 2019-11-08 | 2019-11-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13020 | HNB Reactors Shutdown Essential Safety Cases | KDM Shutdown Margins – Codes and Method for Safety Case Report Complete (HNB) | 2019-11-08 | 2019-11-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A9500 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Boiler Control and Protection Draft Report | 2019-11-11 | 2019-11-22 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A9580 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Reactor Cooling Systems Draft Report | 2019-11-11 | 2019-11-22 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A1310 | HNB Reactors Shutdown Essential Safety Cases | Produce verification plan (HNB) | 2019-11-14 | 2019-11-15 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | ER6370.A7650 | HNB Reactors Shutdown Essential Safety Cases | SDM Assessments with uncertainties / sensitivity studies Report Completed | 2019-11-14 | 2019-11-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A10680 | HNB Reactors Shutdown Essential Safety Cases | In Reactor NSP Compliance and Risk Report Completed | 2019-11-15 | 2019-11-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16340 | HNB Reactors Shutdown Essential Safety Cases | All Supporting Technical References Complete - Claim 5 ALARP | 2019-11-15 | 2019-11-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7020 | HNB Reactors Shutdown Essential Safety Cases | Verified Boiler Supporting Systems Draft EAN Issued to EDF for Technical Review. | 2019-11-20 | 2019-11-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A9510 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Boiler Control and Protection Report | 2019-11-22 | 2019-11-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A9590 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Reactor Cooling Systems Report | 2019-11-22 | 2019-11-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4770 | HNB Reactors Shutdown Essential Safety Cases | Worker Dose and Risks from Faults Draft Report Verified by TSA | 2019-11-25 | 2020-02-07 | 52 | 0 | 51 | 74 | 100% | 0.7027 | 1 | Completed
ER6370LT | W201 | ER6370.A9520 | HNB Reactors Shutdown Essential Safety Cases | Boiler Control and Protection Report TR Completed and uploaded to CDMS | 2019-11-25 | 2019-12-06 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A9600 | HNB Reactors Shutdown Essential Safety Cases | Reactor Cooling Systems Report TR Completed and uploaded to CDMS | 2019-11-25 | 2019-12-06 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A3310 | HNB Reactors Shutdown Essential Safety Cases | Gas Chemistry Assessment Report Completed | 2019-11-29 | 2019-11-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3950 | HNB Reactors Shutdown Essential Safety Cases | Model and Datasets Part 2 Reports Completed | 2019-11-29 | 2019-11-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4410 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Fault Schedule Review (Plant Based Faults) Report | 2019-11-29 | 2019-11-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4490 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Fault Schedule Review (Harzards) Report | 2019-11-29 | 2019-11-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8470 | HNB Reactors Shutdown Essential Safety Cases | Issue Reactor Coolant Chemistry Conditions Final Report | 2019-11-29 | 2019-11-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16720 | HNB Reactors Shutdown Essential Safety Cases | Verified Summary Conditions Report - EAN - QA Grade 2 Issued to EDF for Technical Review. | 2019-11-29 | 2019-11-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1960 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) | 2019-12-02 | 2019-12-20 | 15 | 0 | 14 | 18 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A4420 | HNB Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Based Faults) Report TR Completed and uploaded to CDMS | 2019-12-02 | 2019-12-23 | 16 | 0 | 15 | 21 | 100% | 0.7619 | 1 | Completed
ER6370LT | W201 | ER6370.A4500 | HNB Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Harzards) Report TR Completed and uploaded to CDMS | 2019-12-02 | 2019-12-23 | 16 | 0 | 15 | 21 | 100% | 0.7619 | 1 | Completed
ER6370LT | W201 | ER6370.A8480 | HNB Reactors Shutdown Essential Safety Cases | Reactor Coolant Chemistry Conditions Final Report Completed and uploaded to CDMS | 2019-12-02 | 2020-01-02 | 21 | 0 | 20 | 31 | 100% | 0.67742 | 1 | Completed
ER6370LT | W201 | ER6370.A11200 | HNB Reactors Shutdown Essential Safety Cases | <SCOPE DELETED 13.10.2020> Scoping of Implementation ECs C-D | 2019-12-02 | 2020-10-12 | 257 | 0 | 217 | 315 | 100% | 0.81587 | 1 | Completed
ER6370LT | W201 | ER6370.A16730 | HNB Reactors Shutdown Essential Safety Cases | Summary Conditions Report - EAN - QA Grade 2 Technically Reviewed by EDF SQEP | 2019-12-02 | 2019-12-20 | 15 | 0 | 14 | 18 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A7810 | HNB Reactors Shutdown Essential Safety Cases | Verified Shutdown Margin Head Document Issued to EDF for Technical Review. | 2019-12-06 | 2019-12-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A9530 | HNB Reactors Shutdown Essential Safety Cases | Boiler Control and Protection Report Completed | 2019-12-06 | 2019-12-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A9610 | HNB Reactors Shutdown Essential Safety Cases | Reactor Cooling Systems Report Completed | 2019-12-06 | 2019-12-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7820 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Margin Head Document Technically Reviewed by EDF SQEP | 2019-12-09 | 2020-02-14 | 47 | 0 | 46 | 67 | 100% | 0.70149 | 1 | Completed
ER6370LT | W201 | ER6370.A17500 | HNB Reactors Shutdown Essential Safety Cases | >>>MIRROR OF INCOMING ENABLER (W282.A3100) SC Implementation and Rationalisation of Tech Specand SOI Documentation | 2019-12-12 | 2019-12-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A17490 | HNB Reactors Shutdown Essential Safety Cases | >>>INCOMING ENABLER (W282.A3100) SC Implementation and Rationalisation of Tech Specand SOI Documentation - Strategy Appr | 2019-12-12 | 2019-12-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A17510 | HNB Reactors Shutdown Essential Safety Cases | INTERFACE MILESTONE - STN Implementation Tech Spec & POI - (W282 Station Defuelling Deployment (Centre) (HNB) | 2019-12-12 | 2019-12-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1440 | HRA Reactors Shutdown Essential Safety Cases | Review of HRA Defuelling Case against the NSPs Summary | 2019-12-16 | 2020-10-09 | 209 | 0 | 206 | 298 | 100% | 0.70134 | 1 | Completed
ER6371LT | W202 | W202.A1430 | HRA Reactors Shutdown Essential Safety Cases | SC - Safety Case development - tech oversight Cat 1 - Claim 5 - HRA - B-C - STN | 2019-12-16 | 2021-09-01 | 468 | 0 | 431 | 625 | 100% | 0.7488 | 1 | Completed
ER6371LT | W202 | W202.A1450 | HRA Reactors Shutdown Essential Safety Cases | Review of HRA Defuelling Case against the NSPs - Pre Job Brief | 2019-12-16 | 2019-12-16 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1440 | HYA Reactors Shutdown Essential Safety Cases | Review of HYA Defuelling Case against the NSPs Summary | 2019-12-16 | 2020-10-09 | 207 | 0 | 206 | 298 | 100% | 0.69463 | 1 | Completed
ER6661LT | W206 | W206.A1430 | HYA Reactors Shutdown Essential Safety Cases | SC - Safety Case development - tech oversight Cat 1 - Claim 5 - HYA - B-C - STN | 2019-12-16 | 2021-09-01 | 468 | 0 | 431 | 625 | 100% | 0.7488 | 1 | Completed
ER6661LT | W206 | W206.A1450 | HYA Reactors Shutdown Essential Safety Cases | Review of HYA Defuelling Case against the NSPs - Pre Job Brief | 2019-12-16 | 2019-12-16 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A5570 | HRA Reactors Shutdown Essential Safety Cases | Early Claim Lead and Deputy Case Office | 2019-12-16 | 2021-02-26 | 229 | 0 | 304 | 438 | 100% | 0.52283 | 1 | Completed
ER6661LT | W206 | W206.A5580 | HYA Reactors Shutdown Essential Safety Cases | Early Claim Lead and Deputy Case Officer | 2019-12-16 | 2021-02-25 | 251 | 0 | 303 | 437 | 100% | 0.57437 | 1 | Completed
ER6370LT | W201 | ER6370.A1970 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) | 2019-12-20 | 2019-12-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A6940 | HNB Reactors Shutdown Essential Safety Cases | Verified Boilers and Gas Circulator Performance Draft EAN Issued to EDF for Technical Review. | 2019-12-20 | 2019-12-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4430 | HNB Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Based Faults) Report Completed | 2019-12-23 | 2019-12-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4510 | HNB Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Harzards) Report Completed | 2019-12-23 | 2019-12-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3730 | HNB Reactors Shutdown Essential Safety Cases | Defuelling Dataset QA Grade 2 Part 2 Report Verified by TSA | 2020-01-02 | 2020-01-22 | 15 | 0 | 14 | 20 | 100% | 0.75 | 1 | Completed
ER6370LT | W201 | ER6370.A6950 | HNB Reactors Shutdown Essential Safety Cases | Boilers and Gas Circulator Performance Draft EAN Technically Reviewed by EDF SQEP | 2020-01-02 | 2020-03-06 | 47 | 0 | 46 | 64 | 100% | 0.73438 | 1 | Completed
ER6370LT | W201 | ER6370.A7030 | HNB Reactors Shutdown Essential Safety Cases | Boiler Supporting Systems Draft EAN Technically Reviewed by EDF SQEP | 2020-01-02 | 2020-04-03 | 67 | 0 | 66 | 92 | 100% | 0.72826 | 1 | Completed
ER6370LT | W201 | ER6370.A8490 | HNB Reactors Shutdown Essential Safety Cases | Reactor Coolant Chemistry Conditions Report Completed | 2020-01-02 | 2020-01-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16310 | HNB Reactors Shutdown Essential Safety Cases | All Supporting Technical References Complete - Claim 2 Containment | 2020-01-02 | 2020-01-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16740 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Summary Conditions Report - EAN - QA Grade 2 | 2020-01-02 | 2020-01-08 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A1490 | HRA Reactors Shutdown Essential Safety Cases | Prepare Review of HRA Defuelling Case Against the NSPs Draft Report | 2020-01-02 | 2020-04-13 | 67 | 0 | 71 | 102 | 100% | 0.65686 | 1 | Completed
ER6371LT | W202 | W202.A1470 | HRA Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Base Faults and Hazards) - Draft and issue RFS | 2020-01-02 | 2020-01-06 | 3 | 0 | 2 | 4 | 100% | 0.75 | 1 | Completed
ER6371LT | W202 | W202.A1460 | HRA Reactors Shutdown Essential Safety Cases | RFS - Fault Schedule Review (Plant Base Faults and Hazards) Summary | 2020-01-02 | 2020-02-26 | 40 | 0 | 40 | 55 | 100% | 0.72727 | 1 | Completed
ER6661LT | W206 | W206.A1490 | HYA Reactors Shutdown Essential Safety Cases | Prepare Review of HYA Defuelling Case Against the NSPs Draft Report | 2020-01-02 | 2020-04-13 | 71 | 0 | 71 | 102 | 100% | 0.69608 | 1 | Completed
ER6661LT | W206 | W206.A1470 | HYA Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Base Faults and Hazards) - Draft and issue RFS | 2020-01-02 | 2020-01-06 | 3 | 0 | 2 | 4 | 100% | 0.75 | 1 | Completed
ER6661LT | W206 | W206.A1460 | HYA Reactors Shutdown Essential Safety Cases | RFS - Fault Schedule Review (Plant Base Faults and Hazards) Summary | 2020-01-02 | 2020-02-26 | 40 | 0 | 40 | 55 | 100% | 0.72727 | 1 | Completed
ER6370LT | W201 | ER6370.A16750 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Summary Conditions Report - EAN - QA Grade 2 | 2020-01-08 | 2020-01-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16760 | HNB Reactors Shutdown Essential Safety Cases | Summary Conditions Report - EAN - QA Grade 2 TR Completed and uploaded to CDMS | 2020-01-09 | 2020-01-15 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A8590 | HNB Reactors Shutdown Essential Safety Cases | INTERFACE MILESTONE -Criticality Asse'ment for Dropped FPU at Reactor - (W221 Fuel Handling Essential Safety Cases (HNB) | 2020-01-09 | 2020-01-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1500 | HRA Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Base Faults and Hazards) - Supplier prepare and issue Offer | 2020-01-09 | 2020-02-04 | 19 | 0 | 18 | 26 | 100% | 0.73077 | 1 | Completed
ER6661LT | W206 | W206.A1500 | HYA Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Base Faults and Hazards) - Supplier prepare and issue Offer | 2020-01-09 | 2020-02-04 | 19 | 0 | 18 | 26 | 100% | 0.73077 | 1 | Completed
ER6370LT | W201 | ER6370.A17400 | HNB Reactors Shutdown Essential Safety Cases | >>>INCOMING ENABLER (W221.A19600) Criticality Assessment for Dropped FPU at Reactor (WET Condition) EAN Available | 2020-01-09 | 2020-01-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A17420 | HNB Reactors Shutdown Essential Safety Cases | >>>MIRROR OF INCOMING ENABLER (W221.A19600) Criticality Assessment for Dropped FPU at Reactor (WET Con) EAN Available | 2020-01-09 | 2020-01-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A17250 | REGION 1 Reactors Shutdown Safety Cases Programme | Project Close Out | 2020-01-15 | 2020-04-15 | 0 | 0 | 63 | 91 | 100% | 0 | 1 | Completed
ER6370LT | W201 | ER6370.A16770 | HNB Reactors Shutdown Essential Safety Cases | Summary Conditions Report - EAN - QA Grade 2 Completed | 2020-01-15 | 2020-01-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3740 | HNB Reactors Shutdown Essential Safety Cases | Verified Defuelling Dataset QA Grade 2 Part 2 Report Issued to EDF for Technical Review. | 2020-01-22 | 2020-01-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3750 | HNB Reactors Shutdown Essential Safety Cases | Defuelling Dataset QA Grade 2 Part 2 Report Technically Reviewed by EDF SQEP | 2020-01-23 | 2020-02-07 | 12 | 0 | 11 | 15 | 100% | 0.8 | 1 | Completed
ER6370LT | W201 | ER6370.A17470 | HNB Reactors Shutdown Essential Safety Cases | >>>INCOMING ENABLER (W221.A11520) HF Assessment of Fuel Free Verification EAN Available | 2020-01-24 | 2020-01-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A17480 | HNB Reactors Shutdown Essential Safety Cases | >>>MIRROR OF INCOMING ENABLER (W221.A11520) HF Assessment of Fuel Free Verification EAN Available | 2020-01-24 | 2020-01-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A11280 | HNB Reactors Shutdown Essential Safety Cases | INTERFACE MILESTONE - HF Assessment of FFV EAN Available - (W221 Fuel Handling Essential Safety Cases (HNB) | 2020-01-24 | 2020-01-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1530 | HRA Reactors Shutdown Essential Safety Cases | Prepare Pressure Boundary Seals Specification | 2020-01-27 | 2020-02-14 | 15 | 0 | 14 | 18 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A1520 | HRA Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals Specification Summary | 2020-01-27 | 2020-08-28 | 136 | 0 | 150 | 214 | 100% | 0.63551 | 1 | Completed
ER6661LT | W206 | W206.A1530 | HYA Reactors Shutdown Essential Safety Cases | Prepare Pressure Boundary Seals Specification | 2020-01-27 | 2020-02-14 | 15 | 0 | 14 | 18 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | W206.A1520 | HYA Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals Specification Summary | 2020-01-27 | 2020-08-28 | 136 | 0 | 150 | 214 | 100% | 0.63551 | 1 | Completed
ER6370LT | W201 | ER6370.A2680 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Prepare Compliance Scoping Draft Report | 2020-01-29 | 2020-01-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A2690 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Compliance Scoping Draft Report Verified by TSA | 2020-01-29 | 2020-01-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A2700 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Verified Compliance Scoping Draft Report Issued to EDF for Technical Review. | 2020-01-29 | 2020-01-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A2710 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Compliance Scoping Draft Report Technically Reviewed by EDF SQEP | 2020-01-29 | 2020-01-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A2720 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - TSA Address Comments on TR'd Compliance Scoping Draft Report | 2020-01-29 | 2020-01-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A2730 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - TSA Issue Final Compliance Scoping Report | 2020-01-29 | 2020-01-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A2740 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Compliance Scoping Report TR Completed and uploaded to CDMS | 2020-01-29 | 2020-01-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A2750 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Compliance Scoping Report Completed | 2020-01-29 | 2020-01-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7870 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Prepare Compliance Sensitivities Study Draft Report | 2020-01-29 | 2020-01-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7880 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Compliance Sensitivities Study Draft Report Verified by TSA | 2020-01-29 | 2020-01-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7890 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Verified Compliance Sensitivities Study Draft Report Issued to EDF for Technical Review. | 2020-01-29 | 2020-01-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7900 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Compliance Sensitivities Study Draft Report Technically Reviewed by EDF SQEP | 2020-01-29 | 2020-01-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7910 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - TSA Address Comments on TR'd Compliance Sensitivities Study Draft Report | 2020-01-29 | 2020-01-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7920 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - TSA Issue Final Compliance Sensitivities Study Report | 2020-01-29 | 2020-01-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7930 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Compliance Sensitivities Study Report TR Completed and uploaded to CDMS | 2020-01-29 | 2020-01-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7940 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Compliance Sensitivities Study Report Completed | 2020-01-29 | 2020-01-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A2675 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Compliance Scoping Summary | 2020-01-29 | 2020-01-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A11080 | HNB Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Compliance Sensitivities Study Summary | 2020-01-29 | 2020-01-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8520 | HNB Reactors Shutdown Essential Safety Cases | Verified Containment Head Document Draft Report Issued to EDF for Technical Review. | 2020-01-31 | 2020-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16790 | HNB Reactors Shutdown Essential Safety Cases | Confirm Implementation plans are in line with Cat 1 Safety Case | 2020-01-31 | 2020-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16820 | HNB Reactors Shutdown Essential Safety Cases | Agree Items going into Local Station Documentation EC - HNB | 2020-01-31 | 2020-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1980 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) TR Completed and uploaded to CDMS | 2020-02-03 | 2020-03-27 | 40 | 0 | 39 | 53 | 100% | 0.75472 | 1 | Completed
ER6370LT | W201 | ER6370.A2600 | HNB Reactors Shutdown Essential Safety Cases | Prepare Shutdown margin compliance summary Draft Report | 2020-02-03 | 2020-02-20 | 14 | 0 | 13 | 17 | 100% | 0.82353 | 1 | Completed
ER6370LT | W201 | ER6370.A4130 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Cooling Analysis Draft Report Verified by TSA | 2020-02-03 | 2020-03-27 | 40 | 0 | 39 | 53 | 100% | 0.75472 | 1 | Completed
ER6370LT | W201 | ER6370.A8530 | HNB Reactors Shutdown Essential Safety Cases | Containment Head Document Draft Report Technically Reviewed by EDF SQEP | 2020-02-03 | 2020-03-20 | 35 | 0 | 34 | 46 | 100% | 0.76087 | 1 | Completed
ER6370LT | W201 | ER6370.A2595 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Margin Compliance Report Summary - HNB | 2020-02-03 | 2020-06-26 | 87 | 0 | 100 | 144 | 100% | 0.60417 | 1 | Completed
ER6370LT | W201 | ER6370.P1000 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - ALARP Report - Summary | 2020-02-03 | 2020-05-28 | 90 | 0 | 79 | 115 | 100% | 0.78261 | 1 | Completed
ER6370LT | W201 | ER6370.P1010 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - ALARP Report - Prepare Draft Report | 2020-02-03 | 2020-03-13 | 30 | 0 | 30 | 39 | 100% | 0.76923 | 1 | Completed
ER6370LT | W201 | ER6370.P1060 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Definition of Faults for PCPV Integrity - Summary | 2020-02-03 | 2020-05-15 | 90 | 0 | 72 | 102 | 100% | 0.88235 | 1 | Completed
ER6370LT | W201 | ER6370.P1070 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Definition of Faults for PCPV Integrity - Prepare Draft Report | 2020-02-03 | 2020-02-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.P1080 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Definition of Faults for PCPV Integrity - Prepare Final Report | 2020-02-03 | 2020-03-27 | 40 | 0 | 39 | 53 | 100% | 0.75472 | 1 | Completed
ER6370LT | W201 | ER6370.P1110 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Thermal Analysis - Prepare Report | 2020-02-03 | 2020-02-21 | 15 | 0 | 14 | 18 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.P1105 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Thermal Analysis Report - Summary | 2020-02-03 | 2020-03-27 | 40 | 0 | 40 | 53 | 100% | 0.75472 | 1 | Completed
ER6370LT | W201 | ER6370.P17100 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Additional SC Authoring Effort | 2020-02-03 | 2020-09-07 | 144 | 0 | 150 | 217 | 100% | 0.66359 | 1 | Completed
ER6371LT | W202 | W202.A1540 | HRA Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Base Faults and Hazards) - Review Offer, prepare and issue CI | 2020-02-05 | 2020-02-11 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | W206.A1540 | HYA Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Base Faults and Hazards) - Review Offer, prepare and issue CI | 2020-02-05 | 2020-02-11 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6378LT | W222 | W222.A25630 | HRA Fuel Handling Essential Safety Case | FPU Lifting Integrity while Handling at the Reactor ##(Cost Summary)## ### (C3) | 2020-02-05 | 2021-04-09 | 307 | 0 | 297 | 429 | 100% | 0.71562 | 1 | Completed
ER6378LT | W222 | W222.A8860 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for FPU Lifting Integrity while Handling at the Reactor EAN | 2020-02-05 | 2020-02-05 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A8860 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for FPU Lifting Integrity while Handling at the Reactor EAN | 2020-02-05 | 2020-02-05 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25630 | HYA Fuel Handling Essential Safety Case | FPU Lifting Integrity while Handling at the Reactor ##(Cost Summary)## ### (C3) | 2020-02-05 | 2021-04-09 | 307 | 0 | 297 | 429 | 100% | 0.71562 | 1 | Completed
ER6378LT | W222 | W222.A8870 | HRA Fuel Handling Essential Safety Case | Draft FPU Lifting Integrity while Handling at the Reactor EAN | 2020-02-06 | 2020-11-16 | 30 | 0 | 197 | 284 | 100% | 0.10563 | 1 | Completed
ER6650LT | W226 | W226.A8870 | HYA Fuel Handling Essential Safety Case | Draft FPU Lifting Integrity while Handling at the Reactor EAN | 2020-02-06 | 2020-11-16 | 30 | 0 | 197 | 284 | 100% | 0.10563 | 1 | Completed
ER6370LT | W201 | ER6370.A4780 | HNB Reactors Shutdown Essential Safety Cases | Verified Worker Dose and Risks from Faults Draft Report Issued to EDF for Technical Review. | 2020-02-07 | 2020-02-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7350 | HNB Reactors Shutdown Essential Safety Cases | Issue Findings on DNB Commissiong Core Validation Scoping | 2020-02-07 | 2020-02-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3760 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Defuelling Dataset QA Grade 2 Part 2 Report | 2020-02-10 | 2020-03-13 | 25 | 0 | 24 | 32 | 100% | 0.78125 | 1 | Completed
ER6370LT | W201 | ER6370.A4790 | HNB Reactors Shutdown Essential Safety Cases | Worker Dose and Risks from Faults Draft Report Technically Reviewed by EDF SQEP | 2020-02-10 | 2020-02-14 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A10910 | HNB Reactors Shutdown Essential Safety Cases | Address Comments from EDF Review on Uncertainty in SDM Calculations Draft Report | 2020-02-10 | 2020-02-21 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.P1200 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Head Document (PVCW) - Summary | 2020-02-10 | 2020-09-07 | 139 | 0 | 145 | 210 | 100% | 0.6619 | 1 | Completed
ER6370LT | W201 | ER6370.P1290 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Head Document (PVCW) - Draft and issue RFS | 2020-02-10 | 2020-02-12 | 3 | 0 | 2 | 2 | 100% | 1.5 | 1 | Completed
ER6371LT | W202 | W202.A1550 | HRA Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Base Faults and Hazards) - Supplier mobilisation time | 2020-02-12 | 2020-02-25 | 10 | 0 | 9 | 13 | 100% | 0.76923 | 1 | Completed
ER6661LT | W206 | W206.A1550 | HYA Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Base Faults and Hazards) - Supplier mobilisation time | 2020-02-12 | 2020-02-25 | 10 | 0 | 9 | 13 | 100% | 0.76923 | 1 | Completed
ER6370LT | W201 | ER6370.P1300 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Head Document (PVCW) - Supplier prepare and issue Offer | 2020-02-13 | 2020-02-19 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A1560 | HRA Reactors Shutdown Essential Safety Cases | Issue Pressure Boundary Seals Specification to EDF Review. | 2020-02-14 | 2020-02-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1560 | HYA Reactors Shutdown Essential Safety Cases | Issue Pressure Boundary Seals Specification to EDF Review. | 2020-02-14 | 2020-02-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4800 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Worker Dose and Risks from Faults Draft Report | 2020-02-17 | 2020-02-21 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A7830 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Shutdown Margin Head Document | 2020-02-17 | 2020-03-27 | 30 | 0 | 29 | 39 | 100% | 0.76923 | 1 | Completed
ER6371LT | W202 | W202.A1570 | HRA Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals Specification Reviewed by EDF SQEP | 2020-02-17 | 2020-02-21 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6661LT | W206 | W206.A1570 | HYA Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals Specification Reviewed by EDF SQEP | 2020-02-17 | 2020-02-21 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.P1310 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Head Document (PVCW) - Review Offer, prepare and issue CI | 2020-02-20 | 2020-02-21 | 2 | 0 | 1 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | ER6370.A2610 | HNB Reactors Shutdown Essential Safety Cases | Shutdown margin compliance summary Draft Report Verified by TSA | 2020-02-21 | 2020-02-28 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6370LT | W201 | ER6370.A4810 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Worker Dose and Risks from Faults Report | 2020-02-21 | 2020-02-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1580 | HRA Reactors Shutdown Essential Safety Cases | Review of HRA Defuelling Case against the NSPs - Mid-Job Brief | 2020-02-21 | 2020-02-21 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1580 | HYA Reactors Shutdown Essential Safety Cases | Review of HYA Defuelling Case against the NSPs - Mid-Job Brief | 2020-02-21 | 2020-02-21 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4280 | HNB Reactors Shutdown Essential Safety Cases | Prepare Core Cooling Compliance Summary Draft Report | 2020-02-24 | 2020-06-12 | 57 | 0 | 75 | 109 | 100% | 0.52294 | 1 | Completed
ER6370LT | W201 | ER6370.A4820 | HNB Reactors Shutdown Essential Safety Cases | Worker Dose and Risks from Faults Report TR Completed and uploaded to CDMS | 2020-02-24 | 2020-02-28 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A4275 | HNB Reactors Shutdown Essential Safety Cases | Core Cooling Compliance Summary | 2020-02-24 | 2020-07-14 | 109 | 0 | 97 | 141 | 100% | 0.77305 | 1 | Completed
ER6370LT | W201 | ER6370.P1120 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Thermal Analysis - Verification and Address Comments of Report | 2020-02-24 | 2020-03-03 | 7 | 0 | 6 | 8 | 100% | 0.875 | 1 | Completed
ER6370LT | W201 | ER6370.P1320 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Head Document (PVCW) - Supplier mobilisation time | 2020-02-24 | 2020-02-28 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6371LT | W202 | W202.A1590 | HRA Reactors Shutdown Essential Safety Cases | Address Comments on Reviewed Pressure Boundary Seals Specification | 2020-02-24 | 2020-02-28 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6661LT | W206 | W206.A1590 | HYA Reactors Shutdown Essential Safety Cases | Address Comments on Reviewed Pressure Boundary Seals Specification | 2020-02-24 | 2020-02-28 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6378LT | W222 | W222.A26300 | HRA Fuel Handling Essential Safety Case | Shock Absorbers Feasibility Study ##(Cost Summary)## (C5) (NEW) | 2020-02-25 | 2021-04-26 | 352 | 0 | 294 | 426 | 100% | 0.82629 | 1 | Completed
ER6378LT | W222 | W222.A23730 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Shock Absorbers Feasibility Study EAN | 2020-02-25 | 2020-02-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23730 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Shock Absorbers Feasibility Study EAN | 2020-02-25 | 2020-02-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26300 | HYA Fuel Handling Essential Safety Case | Shock Absorbers Feasibility Study ##(Cost Summary)## (C5) (NEW) | 2020-02-25 | 2021-04-26 | 352 | 0 | 294 | 426 | 100% | 0.82629 | 1 | Completed
ER6371LT | W202 | W202.A1610 | HRA Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Base Faults and Hazards) - Pre Job Brief | 2020-02-26 | 2020-02-26 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1610 | HYA Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Base Faults and Hazards) - Pre Job Brief | 2020-02-26 | 2020-02-26 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A23740 | HRA Fuel Handling Essential Safety Case | Draft Shock Absorbers Feasibility Study EAN | 2020-02-26 | 2020-05-29 | 64 | 0 | 63 | 93 | 100% | 0.68817 | 1 | Completed
ER6650LT | W226 | W226.A23740 | HYA Fuel Handling Essential Safety Case | Draft Shock Absorbers Feasibility Study EAN | 2020-02-26 | 2020-05-29 | 64 | 0 | 63 | 93 | 100% | 0.68817 | 1 | Completed
ER6370LT | W201 | ER6370.P1140 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Civils Integrity Report - Prepare Report | 2020-02-27 | 2020-05-22 | 45 | 0 | 58 | 85 | 100% | 0.52941 | 1 | Completed
ER6370LT | W201 | ER6370.P1135 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Civils Integrity Report - Summary | 2020-02-27 | 2020-06-12 | 88 | 0 | 72 | 106 | 100% | 0.83019 | 1 | Completed
ER6370LT | W201 | ER6370.A2620 | HNB Reactors Shutdown Essential Safety Cases | Verified Shutdown margin compliance summary Draft Report Issued to EDF for Technical Review. | 2020-02-28 | 2020-02-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4830 | HNB Reactors Shutdown Essential Safety Cases | Worker Dose and Risks from Faults Report Completed | 2020-02-28 | 2020-02-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1620 | HRA Reactors Shutdown Essential Safety Cases | Issue Final Pressure Boundary Seals Specification | 2020-02-28 | 2020-02-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1620 | HYA Reactors Shutdown Essential Safety Cases | Issue Final Pressure Boundary Seals Specification | 2020-02-28 | 2020-02-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1290 | HNB Reactors Shutdown Essential Safety Cases | Prepare the Safety Case Proposal (HNB) | 2020-03-02 | 2020-10-09 | 281 | 0 | 155 | 221 | 100% | 1.2715 | 1 | Completed
ER6370LT | W201 | ER6370.A11060 | HNB Reactors Shutdown Essential Safety Cases | RAWG Endorsement of Methods | 2020-03-02 | 2020-07-28 | 272 | 0 | 103 | 148 | 100% | 1.8378 | 1 | Completed
ER6370LT | W201 | ER6370.A11100 | HNB Reactors Shutdown Essential Safety Cases | SC - Safety Case development - tech oversight Cat 1 - Claim 1 - HNB - B-C - STN | 2020-03-02 | 2020-07-28 | 399 | 0 | 102 | 148 | 100% | 2.6959 | 1 | Completed
ER6370LT | W201 | ER6370.A11120 | HNB Reactors Shutdown Essential Safety Cases | SC - Safety Case development - tech oversight Cat 1 - Claim 2 - HNB - B-C - STN | 2020-03-02 | 2020-09-15 | 377 | 0 | 136 | 197 | 100% | 1.9137 | 1 | Completed
ER6370LT | W201 | ER6370.A11140 | HNB Reactors Shutdown Essential Safety Cases | SC - Safety Case development - tech oversight Cat 1 - Claim 3 - HNB - B-C - STN | 2020-03-02 | 2020-10-09 | 399 | 0 | 154 | 221 | 100% | 1.8054 | 1 | Completed
ER6370LT | W201 | ER6370.A11160 | HNB Reactors Shutdown Essential Safety Cases | SC - Safety Case development - tech oversight Cat 1 - Claim 4 - HNB - B-C - STN | 2020-03-02 | 2020-06-30 | 381 | 0 | 82 | 120 | 100% | 3.175 | 1 | Completed
ER6370LT | W201 | ER6370.A11190 | HNB Reactors Shutdown Essential Safety Cases | SC - Safety Case development - tech oversight Cat 1 - Claim 5 - HNB - B-C - STN | 2020-03-02 | 2020-06-30 | 399 | 0 | 82 | 120 | 100% | 3.325 | 1 | Completed
ER6370LT | W201 | ER6370.A11210 | HNB Reactors Shutdown Essential Safety Cases | SC - Safety Case development - Stakeholder comms Cat 1 - HNB - B-C - INA | 2020-03-02 | 2020-10-09 | 235 | 0 | 155 | 221 | 100% | 1.0633 | 1 | Completed
ER6370LT | W201 | ER6370.P1340 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Case Conferences - Summary | 2020-03-02 | 2020-03-20 | 15 | 0 | 14 | 18 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.P1350 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Case Conferences | 2020-03-02 | 2020-03-20 | 15 | 0 | 14 | 18 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A1510 | HRA Reactors Shutdown Essential Safety Cases | SC - Safety Case development - tech oversight Cat 1 - Claim 2 - HRA - B-C - STN | 2020-03-02 | 2021-09-01 | 455 | 0 | 379 | 548 | 100% | 0.83029 | 1 | Completed
ER6371LT | W202 | W202.A1600 | HRA Reactors Shutdown Essential Safety Cases | SC - Safety Case development - tech oversight Cat 1 - Claim 3 - HRA - B-C - STN | 2020-03-02 | 2021-09-01 | 433 | 0 | 379 | 548 | 100% | 0.79015 | 1 | Completed
ER6661LT | W206 | W206.A1510 | HYA Reactors Shutdown Essential Safety Cases | SC - Safety Case development - tech oversight Cat 1 - Claim 2 - HYA - B-C - STN | 2020-03-02 | 2021-09-01 | 455 | 0 | 379 | 548 | 100% | 0.83029 | 1 | Completed
ER6661LT | W206 | W206.A1600 | HYA Reactors Shutdown Essential Safety Cases | SC - Safety Case development - tech oversight Cat 1 - Claim 3 - HYA - B-C - STN | 2020-03-02 | 2021-09-01 | 433 | 0 | 379 | 548 | 100% | 0.79015 | 1 | Completed
ER6378LT | W222 | W222.A25960 | HRA Fuel Handling Essential Safety Case | Update Core Support Plate Properties Tensile ##(Cost Summary)## (C5) (NEW) | 2020-03-02 | 2020-05-01 | 43 | 0 | 42 | 60 | 100% | 0.71667 | 1 | Completed
ER6378LT | W222 | W222.A23240 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Update Core Support Plate Properties Tensile EAN | 2020-03-02 | 2020-03-02 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A9900 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Update to Failed Fuel EAN | 2020-03-02 | 2020-03-02 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A19440 | HRA Fuel Handling Essential Safety Case | Failed Fuel ##(Cost Summary)## ### (C1) | 2020-03-02 | 2020-09-09 | 152 | 0 | 132 | 191 | 100% | 0.79581 | 1 | Completed
ER6378LT | W222 | W222.A22240 | HRA Fuel Handling Essential Safety Case | EAC (02-Mar-2020 - 28-Aug-2020) ##(Cost Summary)## | 2020-03-02 | 2020-08-28 | 126 | 0 | 125 | 179 | 100% | 0.70391 | 1 | Completed
ER6650LT | W226 | W226.A22240 | HYA Fuel Handling Essential Safety Case | EAC (02-Mar-2020 - 28-Aug-2020) ##(Cost Summary)## | 2020-03-02 | 2020-08-28 | 126 | 0 | 125 | 179 | 100% | 0.70391 | 1 | Completed
ER6650LT | W226 | W226.A19440 | HYA Fuel Handling Essential Safety Case | Failed Fuel ##(Cost Summary)## ### (C1) | 2020-03-02 | 2020-09-09 | 152 | 0 | 132 | 191 | 100% | 0.79581 | 1 | Completed
ER6650LT | W226 | W226.A9900 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Update to Failed Fuel EAN | 2020-03-02 | 2020-03-02 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23240 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Update Core Support Plate Properties Tensile EAN | 2020-03-02 | 2020-03-02 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25960 | HYA Fuel Handling Essential Safety Case | Update Core Support Plate Properties Tensile ##(Cost Summary)## (C5) (NEW) | 2020-03-02 | 2020-05-01 | 43 | 0 | 42 | 60 | 100% | 0.71667 | 1 | Completed
ER6370LT | W201 | ER6370.A2630 | HNB Reactors Shutdown Essential Safety Cases | Shutdown margin compliance summary Draft Report Technically Reviewed by EDF SQEP | 2020-03-03 | 2020-03-13 | 9 | 0 | 8 | 10 | 100% | 0.9 | 1 | Completed
ER6378LT | W222 | W222.A23250 | HRA Fuel Handling Essential Safety Case | Draft Update Core Support Plate Properties Tensile EAN | 2020-03-03 | 2020-03-31 | 21 | 0 | 20 | 28 | 100% | 0.75 | 1 | Completed
ER6378LT | W222 | W222.A9910 | HRA Fuel Handling Essential Safety Case | Draft Update to Failed Fuel EAN | 2020-03-03 | 2020-05-26 | 18 | 0 | 56 | 84 | 100% | 0.21429 | 1 | Completed
ER6650LT | W226 | W226.A9910 | HYA Fuel Handling Essential Safety Case | Draft Update to Failed Fuel EAN | 2020-03-03 | 2020-05-26 | 18 | 0 | 56 | 84 | 100% | 0.21429 | 1 | Completed
ER6650LT | W226 | W226.A23250 | HYA Fuel Handling Essential Safety Case | Draft Update Core Support Plate Properties Tensile EAN | 2020-03-03 | 2020-03-31 | 21 | 0 | 20 | 28 | 100% | 0.75 | 1 | Completed
ER6370LT | W201 | ER6370.A6960 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Boilers and Gas Circulator Performance Draft EAN | 2020-03-09 | 2020-03-17 | 7 | 0 | 6 | 8 | 100% | 0.875 | 1 | Completed
ER6370LT | W201 | ER6370.A3770 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Defuelling Dataset QA Grade 2 Part 2 Report | 2020-03-13 | 2020-03-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A2640 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Shutdown margin compliance summary Draft Report | 2020-03-16 | 2020-03-27 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A3780 | HNB Reactors Shutdown Essential Safety Cases | Defuelling Dataset QA Grade 2 Part 2 Report TR Completed and uploaded to CDMS | 2020-03-16 | 2020-03-27 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.P1020 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - ALARP Report - Draft Report Reviewed by SQEP | 2020-03-16 | 2020-03-20 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.P1030 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - ALARP Report - Verification of Draft Report | 2020-03-16 | 2020-05-20 | 14 | 0 | 44 | 65 | 100% | 0.21538 | 1 | Completed
ER6370LT | W201 | ER6370.P1330 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Head Document (PVCW) - Pre Job Brief | 2020-03-16 | 2020-03-16 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1630 | HRA Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals Specification Completed and uploaded to CDMS | 2020-03-16 | 2020-08-28 | 101 | 0 | 115 | 165 | 100% | 0.61212 | 1 | Completed
ER6371LT | W202 | W202.A44580 | HRA Reactors Shutdown Essential Safety Cases | Opex Capture from HPB / HNB | 2020-03-16 | 2020-09-15 | 66 | 0 | 127 | 183 | 100% | 0.36066 | 1 | Completed
ER6661LT | W206 | W206.A1630 | HYA Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals Specification Completed and uploaded to CDMS | 2020-03-16 | 2020-08-28 | 101 | 0 | 115 | 165 | 100% | 0.61212 | 1 | Completed
ER6378LT | W222 | W222.A26070 | HRA Fuel Handling Essential Safety Case | Fuel Route Operational Sequence/Process for Defuelling ##(Cost Summary)## (C6) (NEW) | 2020-03-16 | 2021-02-03 | 225 | 0 | 225 | 324 | 100% | 0.69444 | 1 | Completed
ER6378LT | W222 | W222.A24360 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Fuel Route Operational Sequence/Process for Defuelling EAN (REV 000) | 2020-03-16 | 2020-03-16 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24360 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Fuel Route Operational Sequence/Process for Defuelling EAN (REV 000) | 2020-03-16 | 2020-03-16 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26070 | HYA Fuel Handling Essential Safety Case | Fuel Route Operational Sequence/Process for Defuelling ##(Cost Summary)## (C6) (NEW) | 2020-03-16 | 2021-02-03 | 225 | 0 | 225 | 324 | 100% | 0.69444 | 1 | Completed
ER6661LT | W206 | W206.A44580 | HYA Reactors Shutdown Essential Safety Cases | Opex Capture from HPB / HNB | 2020-03-16 | 2020-09-15 | 117 | 0 | 127 | 183 | 100% | 0.63934 | 1 | Completed
ER6370LT | W201 | ER6370.A6970 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Boilers and Gas Circulator Performance EAN | 2020-03-17 | 2020-03-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.P1280 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Head Document (PVCW) - Identify and Address Gaps in Head Document | 2020-03-17 | 2020-03-23 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6378LT | W222 | W222.A24370 | HRA Fuel Handling Essential Safety Case | Draft Fuel Route Operational Sequence/Process for Defuelling EAN (REV 000) | 2020-03-17 | 2020-04-14 | 19 | 0 | 18 | 28 | 100% | 0.67857 | 1 | Completed
ER6650LT | W226 | W226.A24370 | HYA Fuel Handling Essential Safety Case | Draft Fuel Route Operational Sequence/Process for Defuelling EAN (REV 000) | 2020-03-17 | 2020-04-14 | 19 | 0 | 18 | 28 | 100% | 0.67857 | 1 | Completed
ER6370LT | W201 | ER6370.A6980 | HNB Reactors Shutdown Essential Safety Cases | Boilers and Gas Circulator Performance EAN TR Completed and uploaded to CDMS | 2020-03-18 | 2020-03-27 | 8 | 0 | 7 | 9 | 100% | 0.88889 | 1 | Completed
ER6370LT | W201 | ER6370.P1360 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - DIscovery MS - Confirm Impact of PVCW Isolation on existing Technical References and Head Documents | 2020-03-20 | 2020-03-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1670 | HRA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HRA - Draft and issue RFS | 2020-03-20 | 2020-03-26 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A1660 | HRA Reactors Shutdown Essential Safety Cases | RFS - Dropped FPU Strategy Development HRA - Summary | 2020-03-20 | 2020-06-01 | 25 | 0 | 48 | 73 | 100% | 0.34247 | 1 | Completed
ER6661LT | W206 | W206.A1670 | HYA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HYA - Draft and issue RFS | 2020-03-20 | 2020-03-26 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | W206.A1660 | HYA Reactors Shutdown Essential Safety Cases | RFS - Dropped FPU Strategy Development HYA - Summary | 2020-03-20 | 2020-06-01 | 31 | 0 | 48 | 73 | 100% | 0.42466 | 1 | Completed
ER6370LT | W201 | ER6370.A8540 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Containment Head Document Draft Report | 2020-03-23 | 2020-06-12 | 56 | 0 | 55 | 81 | 100% | 0.69136 | 1 | Completed
ER6370LT | W201 | ER6370.P1130 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Thermal Analysis - Issue Report and upload to CDMS | 2020-03-23 | 2020-03-27 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6371LT | W202 | W202.A1680 | HRA Reactors Shutdown Essential Safety Cases | Assumptions EAN - Summary | 2020-03-23 | 2020-06-15 | 59 | 0 | 57 | 84 | 100% | 0.70238 | 1 | Completed
ER6371LT | W202 | W202.A1690 | HRA Reactors Shutdown Essential Safety Cases | Assumptions EAN - Pre-Job Brief | 2020-03-23 | 2020-03-23 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1680 | HYA Reactors Shutdown Essential Safety Cases | Assumptions EAN - Summary | 2020-03-23 | 2020-06-15 | 77 | 0 | 57 | 84 | 100% | 0.91667 | 1 | Completed
ER6661LT | W206 | W206.A1690 | HYA Reactors Shutdown Essential Safety Cases | Assumptions EAN - Pre-Job Brief | 2020-03-23 | 2020-03-23 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1710 | HRA Reactors Shutdown Essential Safety Cases | Assumptions EAN - Prepare Draft Report | 2020-03-24 | 2020-04-20 | 18 | 0 | 17 | 27 | 100% | 0.66667 | 1 | Completed
ER6661LT | W206 | W206.A1710 | HYA Reactors Shutdown Essential Safety Cases | Assumptions EAN - Prepare Draft Report | 2020-03-24 | 2020-04-20 | 18 | 0 | 17 | 27 | 100% | 0.66667 | 1 | Completed
ER6370LT | W201 | ER6370.A1990 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) Completed | 2020-03-27 | 2020-03-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A2650 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Shutdown margin compliance summary Report | 2020-03-27 | 2020-03-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A3790 | HNB Reactors Shutdown Essential Safety Cases | Defuelling Dataset QA Grade 2 Part 2 Report Completed | 2020-03-27 | 2020-03-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4140 | HNB Reactors Shutdown Essential Safety Cases | Verified Shutdown Cooling Analysis Draft Report Issued to EDF for Technical Review. | 2020-03-27 | 2020-03-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A6990 | HNB Reactors Shutdown Essential Safety Cases | Boilers and Gas Circulator Performance EAN Completed | 2020-03-27 | 2020-03-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13030 | HNB Reactors Shutdown Essential Safety Cases | KDM MACE – Dataset and Validation Complete (HNB) | 2020-03-27 | 2020-03-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7840 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Shutdown Margin Head Document | 2020-03-27 | 2020-03-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A10920 | HNB Reactors Shutdown Essential Safety Cases | Issue Final Uncertainty in SDM Calculations Report Report | 2020-03-27 | 2020-03-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A17360 | HNB Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W221) Defuelling Dataset QA Grade 2 Part 2 Report Completed | 2020-03-27 | 2020-03-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A17430 | HNB Reactors Shutdown Essential Safety Cases | >>>INCOMING ENABLER (W221.A20230) Dropped FPU Characterisation EAN Available | 2020-03-27 | 2020-03-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A17440 | HNB Reactors Shutdown Essential Safety Cases | >>>MIRROR OF INCOMING ENABLER (W221.A20230) Dropped FPU Characterisation EAN Available | 2020-03-27 | 2020-03-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8090 | HNB Reactors Shutdown Essential Safety Cases | INTERFACE MILESTONE - Dropped FPU Characterisation EAN Available - (W221 Fuel Handling Essential Safety Cases (HNB)) | 2020-03-27 | 2020-03-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1700 | HRA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HRA - Supplier prepare and issue Offer | 2020-03-27 | 2020-04-09 | 10 | 0 | 9 | 13 | 100% | 0.76923 | 1 | Completed
ER6661LT | W206 | W206.A1700 | HYA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HYA - Supplier prepare and issue Offer | 2020-03-27 | 2020-04-09 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6370LT | W201 | ER6370.A4150 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Cooling Analysis Draft Report Technically Reviewed by EDF SQEP | 2020-03-30 | 2020-04-14 | 10 | 0 | 10 | 15 | 100% | 0.66667 | 1 | Completed
ER6370LT | W201 | ER6370.A7850 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Margin Head Document TR Completed and uploaded to CDMS | 2020-03-30 | 2020-06-26 | 30 | 0 | 60 | 88 | 100% | 0.34091 | 1 | Completed
ER6370LT | W201 | ER6370.P1090 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Definition of Faults for PCPV Integrity - Verification and Address Comments of Final Report | 2020-03-30 | 2020-05-08 | 24 | 0 | 27 | 39 | 100% | 0.61538 | 1 | Completed
ER6370LT | W201 | ER6370.P1210 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Head Document (PVCW) - Prepare Draft Head Document | 2020-03-30 | 2020-06-17 | 33 | 0 | 53 | 79 | 100% | 0.41772 | 1 | Completed
ER6370LT | W201 | ER6370.A17450 | HNB Reactors Shutdown Essential Safety Cases | >>>INCOMING ENABLER (W221.A16210) Structural Integrity Analysis for Dropped FPU EAN Available | 2020-03-30 | 2020-03-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A17460 | HNB Reactors Shutdown Essential Safety Cases | >>>MIRROR OF INCOMING ENABLER (W221.A16210) Structural Integrity Analysis for Dropped FPU EAN Available | 2020-03-30 | 2020-03-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8600 | HNB Reactors Shutdown Essential Safety Cases | INTERFACE MILESTONE -Structural Integrity Analysis for Dropped FPU EAN- (W221 Fuel Handling Essential Safety Cases (HNB) | 2020-03-30 | 2020-03-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7080 | HNB Reactors Shutdown Essential Safety Cases | Boilers and Gas Circulator Performance - Reworked Draft EAN | 2020-03-30 | 2020-04-24 | 18 | 0 | 17 | 25 | 100% | 0.72 | 1 | Completed
ER6370LT | W201 | ER6370.A10930 | HNB Reactors Shutdown Essential Safety Cases | Uncertainty in SDM Calculations Report Completed and Uploaded to CDMS | 2020-03-30 | 2020-05-08 | 27 | 0 | 27 | 39 | 100% | 0.69231 | 1 | Completed
ER6371LT | W202 | W202.A859010 | HRA Reactors Shutdown Essential Safety Cases | Prepare Shutdown margin compliance summary Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A886010 | HRA Reactors Shutdown Essential Safety Cases | Prepare Core Cooling Compliance Summary Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A908010 | HRA Reactors Shutdown Essential Safety Cases | Issue Core Cooling Compliance Summary Draft Report to EDF for Review. - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A911010 | HRA Reactors Shutdown Essential Safety Cases | Core Cooling Compliance Summary Draft Report Reviewed by EDF SQEP - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A932010 | HRA Reactors Shutdown Essential Safety Cases | Address Comments from EDF's Review of Core Cooling Compliance Summary Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A950010 | HRA Reactors Shutdown Essential Safety Cases | Issue Final Core Cooling Compliance Summary Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A952010 | HRA Reactors Shutdown Essential Safety Cases | Core Cooling Compliance Summary Report Completed and uploaded to CDMS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A965010 | HRA Reactors Shutdown Essential Safety Cases | Core Cooling Compliance Summary Report Completed - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A863010 | HRA Reactors Shutdown Essential Safety Cases | Prepare Shutdown margin compliance summary Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A805010 | HRA Reactors Shutdown Essential Safety Cases | Prepare Requirements for Severe Accidents Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A858010 | HRA Reactors Shutdown Essential Safety Cases | Shutdown Margin Compliance Report Summary - HYA - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A862010 | HRA Reactors Shutdown Essential Safety Cases | Shutdown Margin Compliance Report Summary - HAR - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A804010 | HRA Reactors Shutdown Essential Safety Cases | Requirements for Severe Accidents Summary - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1190510 | HRA Reactors Shutdown Essential Safety Cases | Review of / Changes to Emergency Arrangements Summary - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A885010 | HRA Reactors Shutdown Essential Safety Cases | Core Cooling Compliance Summary - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A743010 | HRA Reactors Shutdown Essential Safety Cases | Shutdown Margin Compliance Report - Draft and issue RFS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A742010 | HRA Reactors Shutdown Essential Safety Cases | RFS - Shutdown Margin Compliance Report Summary - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A219010 | HRA Reactors Shutdown Essential Safety Cases | Reactor Coolant Chemistry Conditions - Draft and issue RFS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A218010 | HRA Reactors Shutdown Essential Safety Cases | RFS - Reactor Coolant Chemistry Conditions Summary - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A497010 | HRA Reactors Shutdown Essential Safety Cases | LSD Strategy Draft Report - Draft and issue RFS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A229010 | HRA Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity - Draft and issue RFS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A228010 | HRA Reactors Shutdown Essential Safety Cases | RFS - Structures and Equipment Integrity Summary - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2203010 | HRA Reactors Shutdown Essential Safety Cases | SDM Assessments - Data / sensitivity studies Draft Report Reviewed by EDF SQEP - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2204010 | HRA Reactors Shutdown Essential Safety Cases | Address Comments from EDF Review on SDM Assessments - Data / sensitivity studies Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2205010 | HRA Reactors Shutdown Essential Safety Cases | Issue Final SDM Assessments - Data / sensitivity studies Report Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206010 | HRA Reactors Shutdown Essential Safety Cases | SDM Assessments - Data / sensitivity studies Report Completed and Uploaded to CDMS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1092010 | HRA Reactors Shutdown Essential Safety Cases | Programme 6.1 Station Documentation and Implementation Strategy - Draft and issue RFS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1191010 | HRA Reactors Shutdown Essential Safety Cases | Prepare Review of / Changes to Emergency Arrangements Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A859010 | HYA Reactors Shutdown Essential Safety Cases | Prepare Shutdown margin compliance summary Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A886010 | HYA Reactors Shutdown Essential Safety Cases | Prepare Core Cooling Compliance Summary Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A908010 | HYA Reactors Shutdown Essential Safety Cases | Issue Core Cooling Compliance Summary Draft Report to EDF for Review. - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A911010 | HYA Reactors Shutdown Essential Safety Cases | Core Cooling Compliance Summary Draft Report Reviewed by EDF SQEP - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A932010 | HYA Reactors Shutdown Essential Safety Cases | Address Comments from EDF's Review of Core Cooling Compliance Summary Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A950010 | HYA Reactors Shutdown Essential Safety Cases | Issue Final Core Cooling Compliance Summary Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A952010 | HYA Reactors Shutdown Essential Safety Cases | Core Cooling Compliance Summary Report Completed and uploaded to CDMS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A965010 | HYA Reactors Shutdown Essential Safety Cases | Core Cooling Compliance Summary Report Completed - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A863010 | HYA Reactors Shutdown Essential Safety Cases | Prepare Shutdown margin compliance summary Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A805010 | HYA Reactors Shutdown Essential Safety Cases | Prepare Requirements for Severe Accidents Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A858010 | HYA Reactors Shutdown Essential Safety Cases | Shutdown Margin Compliance Report Summary - HYA - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A862010 | HYA Reactors Shutdown Essential Safety Cases | Shutdown Margin Compliance Report Summary - HAR - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A804010 | HYA Reactors Shutdown Essential Safety Cases | Requirements for Severe Accidents Summary - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1190510 | HYA Reactors Shutdown Essential Safety Cases | Review of / Changes to Emergency Arrangements Summary - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A885010 | HYA Reactors Shutdown Essential Safety Cases | Core Cooling Compliance Summary - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A743010 | HYA Reactors Shutdown Essential Safety Cases | Shutdown Margin Compliance Report - Draft and issue RFS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A742010 | HYA Reactors Shutdown Essential Safety Cases | RFS - Shutdown Margin Compliance Report Summary - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A219010 | HYA Reactors Shutdown Essential Safety Cases | Reactor Coolant Chemistry Conditions - Draft and issue RFS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A218010 | HYA Reactors Shutdown Essential Safety Cases | RFS - Reactor Coolant Chemistry Conditions Summary - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A497010 | HYA Reactors Shutdown Essential Safety Cases | LSD Strategy Draft Report - Draft and issue RFS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A229010 | HYA Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity - Draft and issue RFS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A228010 | HYA Reactors Shutdown Essential Safety Cases | RFS - Structures and Equipment Integrity Summary - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2203010 | HYA Reactors Shutdown Essential Safety Cases | SDM Assessments - Data / sensitivity studies Draft Report Reviewed by EDF SQEP - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2204010 | HYA Reactors Shutdown Essential Safety Cases | Address Comments from EDF Review on SDM Assessments - Data / sensitivity studies Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2205010 | HYA Reactors Shutdown Essential Safety Cases | Issue Final SDM Assessments - Data / sensitivity studies Report Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206010 | HYA Reactors Shutdown Essential Safety Cases | SDM Assessments - Data / sensitivity studies Report Completed and Uploaded to CDMS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1092010 | HYA Reactors Shutdown Essential Safety Cases | Programme 6.1 Station Documentation and Implementation Strategy - Draft and issue RFS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1191010 | HYA Reactors Shutdown Essential Safety Cases | Prepare Review of / Changes to Emergency Arrangements Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A898010 | HRA Reactors Shutdown Essential Safety Cases | Shutdown margin compliance summary Draft Report Verified by TSA - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A918010 | HRA Reactors Shutdown Essential Safety Cases | Shutdown margin compliance summary Draft Report Technically Reviewed by EDF SQEP - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A942010 | HRA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Shutdown margin compliance summary Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A956010 | HRA Reactors Shutdown Essential Safety Cases | Shutdown margin compliance summary Report TR Completed and uploaded to CDMS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A642010 | HRA Reactors Shutdown Essential Safety Cases | Prepare LSD Strategy Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A729010 | HRA Reactors Shutdown Essential Safety Cases | LSD Strategy Draft Report Verified by TSA - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A783010 | HRA Reactors Shutdown Essential Safety Cases | LSD Strategy Draft Report Technically Reviewed by EDF SQEP - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A813010 | HRA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd LSD Strategy Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A844010 | HRA Reactors Shutdown Essential Safety Cases | LSD Strategy Report TR Completed and uploaded to CDMS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A901010 | HRA Reactors Shutdown Essential Safety Cases | Shutdown margin compliance summary Draft Report Verified by TSA - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A921010 | HRA Reactors Shutdown Essential Safety Cases | Shutdown margin compliance summary Draft Report Technically Reviewed by EDF SQEP - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A943010 | HRA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Shutdown margin compliance summary Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A957010 | HRA Reactors Shutdown Essential Safety Cases | Shutdown margin compliance summary Report TR Completed and uploaded to CDMS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A866010 | HRA Reactors Shutdown Essential Safety Cases | Requirements for Severe AccidentsDraft Report Verified by TSA - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A892010 | HRA Reactors Shutdown Essential Safety Cases | Requirements for Severe AccidentsDraft Report Technically Reviewed by EDF SQEP - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A903010 | HRA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Requirements for Severe AccidentsDraft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A923010 | HRA Reactors Shutdown Essential Safety Cases | Requirements for Severe AccidentsReport TR Completed and uploaded to CDMS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A409010 | HRA Reactors Shutdown Essential Safety Cases | Prepare Reactor Coolant Chemistry Conditions Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A459010 | HRA Reactors Shutdown Essential Safety Cases | Reactor Coolant Chemistry Conditions Draft Report Reviewed by EDF SQEP - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A484010 | HRA Reactors Shutdown Essential Safety Cases | Address Comments on Reviwed Reactor Coolant Chemistry Conditions Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A510010 | HRA Reactors Shutdown Essential Safety Cases | Reactor Coolant Chemistry Conditions Final Report Completed and uploaded to CDMS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A412010 | HRA Reactors Shutdown Essential Safety Cases | Prepare Structures and Equipment Integrity Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A578010 | HRA Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity Draft Report Verified by TSA - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A626010 | HRA Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity Draft Report Technically Reviewed by EDF SQEP - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A674010 | HRA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Structures and Equipment Integrity Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A719010 | HRA Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity Report TR Completed and uploaded to CDMS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A271010 | HRA Reactors Shutdown Essential Safety Cases | Specification for LSD Strategy Draft Report Summary - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A411010 | HRA Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity Summary - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A395010 | HRA Reactors Shutdown Essential Safety Cases | Reactor Coolant Chemistry Conditions Summary - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A769010 | HRA Reactors Shutdown Essential Safety Cases | Shutdown Margin Compliance Report - Supplier prepare and issue Offer - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A808010 | HRA Reactors Shutdown Essential Safety Cases | Shutdown Margin Compliance Report - Review Offer, prepare and issue CI - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A826010 | HRA Reactors Shutdown Essential Safety Cases | Shutdown Margin Compliance Report - Supplier mobilisation time - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A851010 | HRA Reactors Shutdown Essential Safety Cases | Shutdown Margin Compliance Report - Pre Job Brief - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A246010 | HRA Reactors Shutdown Essential Safety Cases | Reactor Coolant Chemistry Conditions - Supplier prepare and issue Offer - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A305010 | HRA Reactors Shutdown Essential Safety Cases | Reactor Coolant Chemistry Conditions - Review Offer, prepare and issue CI - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A332010 | HRA Reactors Shutdown Essential Safety Cases | Reactor Coolant Chemistry Conditions - Supplier mobilisation time - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A382010 | HRA Reactors Shutdown Essential Safety Cases | Reactor Coolant Chemistry Conditions - Pre Job Brief - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A528010 | HRA Reactors Shutdown Essential Safety Cases | LSD Strategy Draft Report - Supplier prepare and issue Offer - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A568010 | HRA Reactors Shutdown Essential Safety Cases | LSD Strategy Draft Report - Review Offer, prepare and issue CI - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A581010 | HRA Reactors Shutdown Essential Safety Cases | LSD Strategy Draft Report - Supplier mobilisation time - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A629010 | HRA Reactors Shutdown Essential Safety Cases | LSD Strategy Draft Report - Pre Job Brief - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A255010 | HRA Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity - Supplier prepare and issue Offer - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A316010 | HRA Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity - Review Offer, prepare and issue CI - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A348010 | HRA Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity - Supplier mobilisation time - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A401010 | HRA Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity - Pre Job Brief - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1084010 | HRA Reactors Shutdown Essential Safety Cases | Prepare Programme 6.1 Station Documentation and Implementation Strategy - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1085010 | HRA Reactors Shutdown Essential Safety Cases | Programme 6.1 Station Documentation and Implementation Strategy Verified by TSA - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1087010 | HRA Reactors Shutdown Essential Safety Cases | Programme 6.1 Station Documentation and Implementation Strategy Technically Reviewed by EDF SQEP - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1088010 | HRA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Programme 6.1 Station Documentation and Implementation Strategy - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1090010 | HRA Reactors Shutdown Essential Safety Cases | Programme 6.1 Station Documentation and Implementation Strategy TR Completed and uploaded to CDMS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1093010 | HRA Reactors Shutdown Essential Safety Cases | Programme 6.1 Station Documentation and Implementation Strategy - Supplier prepare and issue Offer - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1094010 | HRA Reactors Shutdown Essential Safety Cases | Programme 6.1 Station Documentation and Implementation Strategy - Review Offer, prepare and issue CI - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1095010 | HRA Reactors Shutdown Essential Safety Cases | Programme 6.1 Station Documentation and Implementation Strategy - Supplier mobilisation time - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1096010 | HRA Reactors Shutdown Essential Safety Cases | Programme 6.1 Station Documentation and Implementation Strategy - Pre Job Brief - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1193010 | HRA Reactors Shutdown Essential Safety Cases | Review of / Changes to Emergency Arrangements Report Reviewed by EDF SQEP - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1194010 | HRA Reactors Shutdown Essential Safety Cases | Address Comments on Reviewed Review of / Changes to Emergency Arrangements Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1196010 | HRA Reactors Shutdown Essential Safety Cases | Review of / Changes to Emergency Arrangements Report Completed and uploaded to CDMS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1198010 | HRA Reactors Shutdown Essential Safety Cases | Develop Boundary Conditions Summary - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1199010 | HRA Reactors Shutdown Essential Safety Cases | Prepare Boundary ConditionsReport - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1200010 | HRA Reactors Shutdown Essential Safety Cases | Boundary Conditions Report Verified by TSA - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1202010 | HRA Reactors Shutdown Essential Safety Cases | Boundary Conditions Report Technically Reviewed by EDF SQEP - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1203010 | HRA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Boundary Conditions Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1205010 | HRA Reactors Shutdown Essential Safety Cases | Boundary Conditions Report TR Completed and uploaded to CDMS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1083510 | HRA Reactors Shutdown Essential Safety Cases | Programme 6.1 Station Documentation and Implementation Strategy Summary - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A898010 | HYA Reactors Shutdown Essential Safety Cases | Shutdown margin compliance summary Draft Report Verified by TSA - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A918010 | HYA Reactors Shutdown Essential Safety Cases | Shutdown margin compliance summary Draft Report Technically Reviewed by EDF SQEP - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A942010 | HYA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Shutdown margin compliance summary Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A956010 | HYA Reactors Shutdown Essential Safety Cases | Shutdown margin compliance summary Report TR Completed and uploaded to CDMS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A642010 | HYA Reactors Shutdown Essential Safety Cases | Prepare LSD Strategy Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A729010 | HYA Reactors Shutdown Essential Safety Cases | LSD Strategy Draft Report Verified by TSA - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A783010 | HYA Reactors Shutdown Essential Safety Cases | LSD Strategy Draft Report Technically Reviewed by EDF SQEP - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A813010 | HYA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd LSD Strategy Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A844010 | HYA Reactors Shutdown Essential Safety Cases | LSD Strategy Report TR Completed and uploaded to CDMS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A901010 | HYA Reactors Shutdown Essential Safety Cases | Shutdown margin compliance summary Draft Report Verified by TSA - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A921010 | HYA Reactors Shutdown Essential Safety Cases | Shutdown margin compliance summary Draft Report Technically Reviewed by EDF SQEP - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A943010 | HYA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Shutdown margin compliance summary Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A957010 | HYA Reactors Shutdown Essential Safety Cases | Shutdown margin compliance summary Report TR Completed and uploaded to CDMS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A866010 | HYA Reactors Shutdown Essential Safety Cases | Requirements for Severe AccidentsDraft Report Verified by TSA - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A892010 | HYA Reactors Shutdown Essential Safety Cases | Requirements for Severe AccidentsDraft Report Technically Reviewed by EDF SQEP - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A903010 | HYA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Requirements for Severe AccidentsDraft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A923010 | HYA Reactors Shutdown Essential Safety Cases | Requirements for Severe AccidentsReport TR Completed and uploaded to CDMS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A409010 | HYA Reactors Shutdown Essential Safety Cases | Prepare Reactor Coolant Chemistry Conditions Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A459010 | HYA Reactors Shutdown Essential Safety Cases | Reactor Coolant Chemistry Conditions Draft Report Reviewed by EDF SQEP - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A484010 | HYA Reactors Shutdown Essential Safety Cases | Address Comments on Reviwed Reactor Coolant Chemistry Conditions Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A510010 | HYA Reactors Shutdown Essential Safety Cases | Reactor Coolant Chemistry Conditions Final Report Completed and uploaded to CDMS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A412010 | HYA Reactors Shutdown Essential Safety Cases | Prepare Structures and Equipment Integrity Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A578010 | HYA Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity Draft Report Verified by TSA - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A626010 | HYA Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity Draft Report Technically Reviewed by EDF SQEP - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A674010 | HYA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Structures and Equipment Integrity Draft Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A719010 | HYA Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity Report TR Completed and uploaded to CDMS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A271010 | HYA Reactors Shutdown Essential Safety Cases | Specification for LSD Strategy Draft Report Summary - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A411010 | HYA Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity Summary - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A395010 | HYA Reactors Shutdown Essential Safety Cases | Reactor Coolant Chemistry Conditions Summary - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A769010 | HYA Reactors Shutdown Essential Safety Cases | Shutdown Margin Compliance Report - Supplier prepare and issue Offer - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A808010 | HYA Reactors Shutdown Essential Safety Cases | Shutdown Margin Compliance Report - Review Offer, prepare and issue CI - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A826010 | HYA Reactors Shutdown Essential Safety Cases | Shutdown Margin Compliance Report - Supplier mobilisation time - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A851010 | HYA Reactors Shutdown Essential Safety Cases | Shutdown Margin Compliance Report - Pre Job Brief - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A246010 | HYA Reactors Shutdown Essential Safety Cases | Reactor Coolant Chemistry Conditions - Supplier prepare and issue Offer - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A305010 | HYA Reactors Shutdown Essential Safety Cases | Reactor Coolant Chemistry Conditions - Review Offer, prepare and issue CI - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A332010 | HYA Reactors Shutdown Essential Safety Cases | Reactor Coolant Chemistry Conditions - Supplier mobilisation time - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A382010 | HYA Reactors Shutdown Essential Safety Cases | Reactor Coolant Chemistry Conditions - Pre Job Brief - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A528010 | HYA Reactors Shutdown Essential Safety Cases | LSD Strategy Draft Report - Supplier prepare and issue Offer - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A568010 | HYA Reactors Shutdown Essential Safety Cases | LSD Strategy Draft Report - Review Offer, prepare and issue CI - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A581010 | HYA Reactors Shutdown Essential Safety Cases | LSD Strategy Draft Report - Supplier mobilisation time - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A629010 | HYA Reactors Shutdown Essential Safety Cases | LSD Strategy Draft Report - Pre Job Brief - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A255010 | HYA Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity - Supplier prepare and issue Offer - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A316010 | HYA Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity - Review Offer, prepare and issue CI - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A348010 | HYA Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity - Supplier mobilisation time - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A401010 | HYA Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity - Pre Job Brief - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A10840 | HYA Reactors Shutdown Essential Safety Cases | Prepare Programme 6.1 Station Documentation and Implementation Strategy - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A10850 | HYA Reactors Shutdown Essential Safety Cases | Programme 6.1 Station Documentation and Implementation Strategy Verified by TSA - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A10870 | HYA Reactors Shutdown Essential Safety Cases | Programme 6.1 Station Documentation and Implementation Strategy Technically Reviewed by EDF SQEP - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A10880 | HYA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Programme 6.1 Station Documentation and Implementation Strategy - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A10900 | HYA Reactors Shutdown Essential Safety Cases | Programme 6.1 Station Documentation and Implementation Strategy TR Completed and uploaded to CDMS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A10930 | HYA Reactors Shutdown Essential Safety Cases | Programme 6.1 Station Documentation and Implementation Strategy - Supplier prepare and issue Offer - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A10940 | HYA Reactors Shutdown Essential Safety Cases | Programme 6.1 Station Documentation and Implementation Strategy - Review Offer, prepare and issue CI - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A10950 | HYA Reactors Shutdown Essential Safety Cases | Programme 6.1 Station Documentation and Implementation Strategy - Supplier mobilisation time - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A10960 | HYA Reactors Shutdown Essential Safety Cases | Programme 6.1 Station Documentation and Implementation Strategy - Pre Job Brief - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1193010 | HYA Reactors Shutdown Essential Safety Cases | Review of / Changes to Emergency Arrangements Report Reviewed by EDF SQEP - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1194010 | HYA Reactors Shutdown Essential Safety Cases | Address Comments on Reviewed Review of / Changes to Emergency Arrangements Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1196010 | HYA Reactors Shutdown Essential Safety Cases | Review of / Changes to Emergency Arrangements Report Completed and uploaded to CDMS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1198010 | HYA Reactors Shutdown Essential Safety Cases | Develop Boundary Conditions Summary - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1199010 | HYA Reactors Shutdown Essential Safety Cases | Prepare Boundary ConditionsReport - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1200010 | HYA Reactors Shutdown Essential Safety Cases | Boundary Conditions Report Verified by TSA - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1202010 | HYA Reactors Shutdown Essential Safety Cases | Boundary Conditions Report Technically Reviewed by EDF SQEP - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1203010 | HYA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Boundary Conditions Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1205010 | HYA Reactors Shutdown Essential Safety Cases | Boundary Conditions Report TR Completed and uploaded to CDMS - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A10835 | HYA Reactors Shutdown Essential Safety Cases | Programme 6.1 Station Documentation and Implementation Strategy Summary - (Scope Removed) | 2020-03-31 | 2020-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A912010 | HRA Reactors Shutdown Essential Safety Cases | Verified Shutdown margin compliance summary Draft Report Issued to EDF for Technical Review. - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A953010 | HRA Reactors Shutdown Essential Safety Cases | TSA Issue Final Shutdown margin compliance summary Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A967010 | HRA Reactors Shutdown Essential Safety Cases | Shutdown margin compliance summary Report Completed - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A775010 | HRA Reactors Shutdown Essential Safety Cases | Verified LSD Strategy Draft Report Issued to EDF for Technical Review. - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A841010 | HRA Reactors Shutdown Essential Safety Cases | TSA Issue Final LSD Strategy Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A870010 | HRA Reactors Shutdown Essential Safety Cases | LSD Strategy Report Completed - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A915010 | HRA Reactors Shutdown Essential Safety Cases | Verified Shutdown margin compliance summary Draft Report Issued to EDF for Technical Review. - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A954010 | HRA Reactors Shutdown Essential Safety Cases | TSA Issue Final Shutdown margin compliance summary Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A968010 | HRA Reactors Shutdown Essential Safety Cases | Shutdown margin compliance summary Report Completed - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A889010 | HRA Reactors Shutdown Essential Safety Cases | Verified Requirements for Severe AccidentsDraft Report Issued to EDF for Technical Review. - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A917010 | HRA Reactors Shutdown Essential Safety Cases | TSA Issue Final Requirements for Severe AccidentsReport - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A937010 | HRA Reactors Shutdown Essential Safety Cases | Requirements for Severe AccidentsReport Completed - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A448010 | HRA Reactors Shutdown Essential Safety Cases | Issue Reactor Coolant Chemistry Conditions Draft Report to EDF for Review. - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A503010 | HRA Reactors Shutdown Essential Safety Cases | Issue Reactor Coolant Chemistry Conditions Final Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A530010 | HRA Reactors Shutdown Essential Safety Cases | Reactor Coolant Chemistry Conditions Report Completed - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A623010 | HRA Reactors Shutdown Essential Safety Cases | Verified Structures and Equipment Integrity Draft Report Issued to EDF for Technical Review. - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A717010 | HRA Reactors Shutdown Essential Safety Cases | TSA Issue Final Structures and Equipment Integrity Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A767010 | HRA Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity Report Completed - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1086010 | HRA Reactors Shutdown Essential Safety Cases | Verified Programme 6.1 Station Documentation and Implementation Strategy Issued to EDF for TR. - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1089010 | HRA Reactors Shutdown Essential Safety Cases | TSA Issue Final Programme 6.1 Station Documentation and Implementation Strategy - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1091010 | HRA Reactors Shutdown Essential Safety Cases | Programme 6.1 Station Documentation and Implementation Strategy Completed - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1192010 | HRA Reactors Shutdown Essential Safety Cases | Issue Review of / Changes to Emergency Arrangements Report to EDF Review. - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1195010 | HRA Reactors Shutdown Essential Safety Cases | Issue Final Review of / Changes to Emergency Arrangements Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1197010 | HRA Reactors Shutdown Essential Safety Cases | Review of / Changes to Emergency Arrangements Report Completed - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1201010 | HRA Reactors Shutdown Essential Safety Cases | Verified Boundary Conditions Report Issued to EDF for Technical Review. - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1204010 | HRA Reactors Shutdown Essential Safety Cases | TSA Issue Final Boundary Conditions Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1206010 | HRA Reactors Shutdown Essential Safety Cases | Boundary Conditions Report Completed - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A912010 | HYA Reactors Shutdown Essential Safety Cases | Verified Shutdown margin compliance summary Draft Report Issued to EDF for Technical Review. - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A953010 | HYA Reactors Shutdown Essential Safety Cases | TSA Issue Final Shutdown margin compliance summary Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A967010 | HYA Reactors Shutdown Essential Safety Cases | Shutdown margin compliance summary Report Completed - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A775010 | HYA Reactors Shutdown Essential Safety Cases | Verified LSD Strategy Draft Report Issued to EDF for Technical Review. - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A841010 | HYA Reactors Shutdown Essential Safety Cases | TSA Issue Final LSD Strategy Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A870010 | HYA Reactors Shutdown Essential Safety Cases | LSD Strategy Report Completed - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A915010 | HYA Reactors Shutdown Essential Safety Cases | Verified Shutdown margin compliance summary Draft Report Issued to EDF for Technical Review. - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A954010 | HYA Reactors Shutdown Essential Safety Cases | TSA Issue Final Shutdown margin compliance summary Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A968010 | HYA Reactors Shutdown Essential Safety Cases | Shutdown margin compliance summary Report Completed - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A889010 | HYA Reactors Shutdown Essential Safety Cases | Verified Requirements for Severe AccidentsDraft Report Issued to EDF for Technical Review. - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A917010 | HYA Reactors Shutdown Essential Safety Cases | TSA Issue Final Requirements for Severe AccidentsReport - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A937010 | HYA Reactors Shutdown Essential Safety Cases | Requirements for Severe AccidentsReport Completed - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A448010 | HYA Reactors Shutdown Essential Safety Cases | Issue Reactor Coolant Chemistry Conditions Draft Report to EDF for Review. - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A503010 | HYA Reactors Shutdown Essential Safety Cases | Issue Reactor Coolant Chemistry Conditions Final Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A530010 | HYA Reactors Shutdown Essential Safety Cases | Reactor Coolant Chemistry Conditions Report Completed - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A623010 | HYA Reactors Shutdown Essential Safety Cases | Verified Structures and Equipment Integrity Draft Report Issued to EDF for Technical Review. - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A717010 | HYA Reactors Shutdown Essential Safety Cases | TSA Issue Final Structures and Equipment Integrity Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A767010 | HYA Reactors Shutdown Essential Safety Cases | Structures and Equipment Integrity Report Completed - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A10860 | HYA Reactors Shutdown Essential Safety Cases | Verified Programme 6.1 Station Documentation and Implementation Strategy Issued to EDF for TR. - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A10890 | HYA Reactors Shutdown Essential Safety Cases | TSA Issue Final Programme 6.1 Station Documentation and Implementation Strategy - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A10910 | HYA Reactors Shutdown Essential Safety Cases | Programme 6.1 Station Documentation and Implementation Strategy Completed - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1192010 | HYA Reactors Shutdown Essential Safety Cases | Issue Review of / Changes to Emergency Arrangements Report to EDF Review. - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1195010 | HYA Reactors Shutdown Essential Safety Cases | Issue Final Review of / Changes to Emergency Arrangements Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1197010 | HYA Reactors Shutdown Essential Safety Cases | Review of / Changes to Emergency Arrangements Report Completed - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1201010 | HYA Reactors Shutdown Essential Safety Cases | Verified Boundary Conditions Report Issued to EDF for Technical Review. - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1204010 | HYA Reactors Shutdown Essential Safety Cases | TSA Issue Final Boundary Conditions Report - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1206010 | HYA Reactors Shutdown Essential Safety Cases | Boundary Conditions Report Completed - (Scope Removed) | 2020-03-31 | 2020-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.P1170 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Pressure Vessel Integrity Report - Prepare Report | 2020-04-01 | 2020-05-08 | 25 | 0 | 25 | 37 | 100% | 0.67568 | 1 | Completed
ER6370LT | W201 | ER6370.P1165 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Pressure Vessel Integrity Report - Summary | 2020-04-01 | 2020-06-10 | 69 | 0 | 46 | 70 | 100% | 0.98571 | 1 | Completed
ER6370LT | W201 | ER6370.A11240 | HNB Reactors Shutdown Essential Safety Cases | Phase 2 Programme Management | 2020-04-01 | 2021-03-31 | 233 | 0 | 252 | 364 | 100% | 0.64011 | 1 | Completed
ER6370LT | W201 | ER6370.A17380 | HNB Reactors Shutdown Essential Safety Cases | Programme Management - Start MS | 2020-04-01 | 2020-04-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A23260 | HRA Fuel Handling Essential Safety Case | Verify Update Core Support Plate Properties Tensile and Issue for Technical Review | 2020-04-01 | 2020-04-08 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6650LT | W226 | W226.A23260 | HYA Fuel Handling Essential Safety Case | Verify Update Core Support Plate Properties Tensile and Issue for Technical Review | 2020-04-01 | 2020-04-08 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6372LT | W203 | W203.A1060 | HNB Enhanced Defuelling Safety Cases | Phase 2 Project Start [FEEDS TO SUMMARY SCHEDULE] | 2020-04-01 | 2020-04-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1020 | HNB Enhanced Defuelling Safety Cases | (HNB) Gate A planning | 2020-04-01 | 2020-11-11 | 156 | 0 | 156 | 224 | 100% | 0.69643 | 1 | Completed
ER6372LT | W203 | W203.A1070 | HNB Enhanced Defuelling Safety Cases | Project Management Gate A - B | 2020-04-01 | 2021-09-22 | 459 | 0 | 373 | 539 | 100% | 0.85158 | 1 | Completed
ER6372LT | W203 | W203.A1080 | HNB Enhanced Defuelling Safety Cases | Technical Oversight Gate A - B | 2020-04-01 | 2021-09-22 | 459 | 0 | 373 | 539 | 100% | 0.85158 | 1 | Completed
ER6372LT | W203 | W203.A1090 | HNB Enhanced Defuelling Safety Cases | Station Oversight Gate A - B | 2020-04-01 | 2021-09-22 | 459 | 0 | 373 | 539 | 100% | 0.85158 | 1 | Completed
ER6372LT | W203 | W203.A2455 | HNB Enhanced Defuelling Safety Cases | Scoping Report - Prepare Draft Report | 2020-04-01 | 2020-08-14 | 94 | 0 | 94 | 135 | 100% | 0.6963 | 1 | Completed
ER6372LT | W203 | W203.A2540 | HNB Enhanced Defuelling Safety Cases | Confirm Objectives to be Delivered at Gate A | 2020-04-01 | 2020-04-30 | 20 | 0 | 20 | 29 | 100% | 0.68966 | 1 | Completed
ER6370LT | W201 | ER6370.A5410 | HNB Reactors Shutdown Essential Safety Cases | HF Compliance Assessment for Shutdown Margin Draft EAN Verified by TSA | 2020-04-02 | 2020-04-08 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A5490 | HNB Reactors Shutdown Essential Safety Cases | HF Compliance / Tech Spec As'ment for Core Cooling Draft EAN Verified by TSA | 2020-04-02 | 2020-04-08 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6244LT | W220 | A11090 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Develop HRA HYA Detailed Costing and Schedules for Future Phases (Post Gate B) | 2020-04-03 | 2020-04-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7040 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Boiler Supporting Systems Draft EAN | 2020-04-06 | 2020-04-21 | 10 | 0 | 9 | 15 | 100% | 0.66667 | 1 | Completed
ER6371LT | W202 | W202.A1780 | HRA Reactors Shutdown Essential Safety Cases | Seismic Assessment of FPU within Reactor - Draft and issue RFS | 2020-04-06 | 2020-04-13 | 5 | 0 | 4 | 7 | 100% | 0.71429 | 1 | Completed
ER6371LT | W202 | W202.A1770 | HRA Reactors Shutdown Essential Safety Cases | RFS - Seismic Assessment of FPU within Reactor Summary | 2020-04-06 | 2020-06-10 | 25 | 0 | 44 | 65 | 100% | 0.38462 | 1 | Completed
ER6661LT | W206 | W206.A1780 | HYA Reactors Shutdown Essential Safety Cases | Seismic Assessment of FPU within Reactor - Draft and issue RFS | 2020-04-06 | 2020-04-13 | 5 | 0 | 4 | 7 | 100% | 0.71429 | 1 | Completed
ER6661LT | W206 | W206.A1770 | HYA Reactors Shutdown Essential Safety Cases | RFS - Seismic Assessment of FPU within Reactor Summary | 2020-04-06 | 2020-06-10 | 31 | 0 | 43 | 65 | 100% | 0.47692 | 1 | Completed
ER6370LT | W201 | ER6370.A5420 | HNB Reactors Shutdown Essential Safety Cases | Verified HF Compliance Assessment for Shutdown Margin Draft EAN Issued to EDF for Technical Review. | 2020-04-08 | 2020-04-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A5500 | HNB Reactors Shutdown Essential Safety Cases | Verified HF Compliance / Tech Spec As'ment for Core Cooling Draft EAN Issued to EDF for Technical Review. | 2020-04-08 | 2020-04-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A2660 | HNB Reactors Shutdown Essential Safety Cases | Shutdown margin compliance summary Report TR Completed and uploaded to CDMS | 2020-04-09 | 2020-06-26 | 5 | 0 | 52 | 78 | 100% | 0.064103 | 1 | Completed
ER6370LT | W201 | ER6370.A5430 | HNB Reactors Shutdown Essential Safety Cases | HF Compliance Assessment for Shutdown Margin Draft EAN Technically Reviewed by EDF SQEP | 2020-04-09 | 2020-04-17 | 5 | 0 | 4 | 8 | 100% | 0.625 | 1 | Completed
ER6370LT | W201 | ER6370.A5510 | HNB Reactors Shutdown Essential Safety Cases | HF Compliance / Tech Spec As'ment for Core Cooling Draft EAN Technically Reviewed by EDF SQEP | 2020-04-09 | 2020-04-17 | 5 | 0 | 5 | 8 | 100% | 0.625 | 1 | Completed
ER6378LT | W222 | W222.A23270 | HRA Fuel Handling Essential Safety Case | Technical Review of Update Core Support Plate Properties Tensile EAN | 2020-04-09 | 2020-04-16 | 4 | 0 | 3 | 7 | 100% | 0.57143 | 1 | Completed
ER6650LT | W226 | W226.A23270 | HYA Fuel Handling Essential Safety Case | Technical Review of Update Core Support Plate Properties Tensile EAN | 2020-04-09 | 2020-04-16 | 4 | 0 | 3 | 7 | 100% | 0.57143 | 1 | Completed
ER6371LT | W202 | W202.A1720 | HRA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HRA - Review Offer, prepare and issue CI | 2020-04-10 | 2020-04-20 | 5 | 0 | 4 | 10 | 100% | 0.5 | 1 | Completed
ER6661LT | W206 | W206.A1720 | HYA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HYA - Review Offer, prepare and issue CI | 2020-04-10 | 2020-04-20 | 5 | 0 | 5 | 10 | 100% | 0.5 | 1 | Completed
ER6371LT | W202 | W202.A1800 | HRA Reactors Shutdown Essential Safety Cases | Review of HRA Defuelling Case against the NSPs Internally Verified by TSA | 2020-04-14 | 2020-04-27 | 10 | 0 | 9 | 13 | 100% | 0.76923 | 1 | Completed
ER6371LT | W202 | W202.A1820 | HRA Reactors Shutdown Essential Safety Cases | Seismic Assessment of FPU within Reactor - Supplier prepare and issue Offer | 2020-04-14 | 2020-04-28 | 10 | 0 | 10 | 14 | 100% | 0.71429 | 1 | Completed
ER6661LT | W206 | W206.A1800 | HYA Reactors Shutdown Essential Safety Cases | Review of HYA Defuelling Case against the NSPs Internally Verified by TSA | 2020-04-14 | 2020-04-27 | 10 | 0 | 9 | 13 | 100% | 0.76923 | 1 | Completed
ER6661LT | W206 | W206.A1820 | HYA Reactors Shutdown Essential Safety Cases | Seismic Assessment of FPU within Reactor - Supplier prepare and issue Offer | 2020-04-14 | 2020-04-28 | 10 | 0 | 10 | 14 | 100% | 0.71429 | 1 | Completed
ER6243LT | W200 | ER6243.A1580 | REGION 1 Reactors Shutdown Safety Cases Programme | Gate D IRM - 6.1 W200 Reactors Shutdown Safety Cases Programme [FEEDS TO SUMMARY SCHEDULE] | 2020-04-15 | 2020-04-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4160 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Shutdown Cooling Analysis Draft Report | 2020-04-15 | 2020-04-21 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6378LT | W222 | W222.A26020 | HRA Fuel Handling Essential Safety Case | Confirm Acceptability of CSP Pillars ##(Cost Summary)## (C5) (NEW) | 2020-04-15 | 2020-12-01 | 162 | 0 | 162 | 230 | 100% | 0.70435 | 1 | Completed
ER6378LT | W222 | W222.A24380 | HRA Fuel Handling Essential Safety Case | Verify Fuel Route Operational Sequence/Process for Defuelling EAN and Issue for Technical Review (REV 000) | 2020-04-15 | 2020-04-29 | 11 | 0 | 10 | 14 | 100% | 0.78571 | 1 | Completed
ER6378LT | W222 | W222.A23660 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Confirm Acceptability of CSP Pillars EAN | 2020-04-15 | 2020-04-15 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23660 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Confirm Acceptability of CSP Pillars EAN | 2020-04-15 | 2020-04-15 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24380 | HYA Fuel Handling Essential Safety Case | Verify Fuel Route Operational Sequence/Process for Defuelling EAN and Issue for Technical Review (REV 000) | 2020-04-15 | 2020-04-29 | 11 | 0 | 10 | 14 | 100% | 0.78571 | 1 | Completed
ER6650LT | W226 | W226.A26020 | HYA Fuel Handling Essential Safety Case | Confirm Acceptability of CSP Pillars ##(Cost Summary)## (C5) (NEW) | 2020-04-15 | 2020-12-01 | 162 | 0 | 162 | 230 | 100% | 0.70435 | 1 | Completed
ER6243LT | W200 | RSSC.PM.A170 | REGION 1 Reactors Shutdown Safety Cases Programme | Project Closeout | 2020-04-15 | 2020-04-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6243LT | W200 | A3010 | REGION 1 Reactors Shutdown Safety Cases Programme | Project Finish Date | 2020-04-15 | 2020-04-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6244LT | W220 | A13080 | REGION 1 Defuelling Programme Fuel Handling Safety Case | Gate D For HPB HNB Station Fuel Handling Safety Case Programme [FEEDS TO SUMMARY SCHEDULE] | 2020-04-15 | 2020-04-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A23670 | HRA Fuel Handling Essential Safety Case | Draft Confirm Acceptability of CSP Pillars EAN | 2020-04-16 | 2020-05-14 | 20 | 0 | 19 | 28 | 100% | 0.71429 | 1 | Completed
ER6378LT | W222 | W222.A23190 | HRA Fuel Handling Essential Safety Case | Verify Basis of Analysis Report EAN and Issue for Technical Review (REV 000) | 2020-04-16 | 2020-05-07 | 16 | 0 | 15 | 21 | 100% | 0.7619 | 1 | Completed
ER6650LT | W226 | W226.A23190 | HYA Fuel Handling Essential Safety Case | Verify Basis of Analysis Report EAN and Issue for Technical Review (REV 000) | 2020-04-16 | 2020-05-07 | 16 | 0 | 15 | 21 | 100% | 0.7619 | 1 | Completed
ER6650LT | W226 | W226.A23670 | HYA Fuel Handling Essential Safety Case | Draft Confirm Acceptability of CSP Pillars EAN | 2020-04-16 | 2020-05-14 | 20 | 0 | 19 | 28 | 100% | 0.71429 | 1 | Completed
ER6378LT | W222 | W222.A23280 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Update Core Support Plate Properties Tensile EAN | 2020-04-17 | 2020-04-24 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6650LT | W226 | W226.A23280 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Update Core Support Plate Properties Tensile EAN | 2020-04-17 | 2020-04-24 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6370LT | W201 | ER6370.A5440 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd HF Compliance Assessment for Shutdown Margin Draft EAN | 2020-04-20 | 2020-04-24 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A5520 | HNB Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd HF Compliance / Tech Spec As'ment for Core Cooling Draft EAN | 2020-04-20 | 2020-04-24 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A4170 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Shutdown Cooling Analysis Report | 2020-04-21 | 2020-04-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7050 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Boiler Supporting Systems EAN | 2020-04-21 | 2020-04-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2960 | HRA Reactors Shutdown Essential Safety Cases | Prepare Worker Dose Report | 2020-04-21 | 2020-06-29 | 48 | 0 | 47 | 69 | 100% | 0.69565 | 1 | Completed
ER6371LT | W202 | W202.A2950 | HRA Reactors Shutdown Essential Safety Cases | Worker Dose Report Summary | 2020-04-21 | 2020-10-20 | 130 | 0 | 127 | 182 | 100% | 0.71429 | 1 | Completed
ER6371LT | W202 | W202.A1790 | HRA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HRA - Supplier mobilisation time | 2020-04-21 | 2020-05-15 | 10 | 0 | 17 | 24 | 100% | 0.41667 | 1 | Completed
ER6661LT | W206 | W206.A2960 | HYA Reactors Shutdown Essential Safety Cases | Prepare Worker Dose Report | 2020-04-21 | 2020-06-29 | 48 | 0 | 47 | 69 | 100% | 0.69565 | 1 | Completed
ER6661LT | W206 | W206.A2950 | HYA Reactors Shutdown Essential Safety Cases | Worker Dose Report Summary | 2020-04-21 | 2020-10-26 | 130 | 0 | 131 | 188 | 100% | 0.69149 | 1 | Completed
ER6661LT | W206 | W206.A1790 | HYA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HYA - Supplier mobilisation time | 2020-04-21 | 2020-05-15 | 10 | 0 | 18 | 24 | 100% | 0.41667 | 1 | Completed
ER6370LT | W201 | ER6370.A4180 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Cooling Analysis Report TR Completed and uploaded to CDMS | 2020-04-22 | 2020-04-28 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A7060 | HNB Reactors Shutdown Essential Safety Cases | Boiler Supporting Systems EAN TR Completed and uploaded to CDMS | 2020-04-22 | 2020-04-24 | 3 | 0 | 2 | 2 | 100% | 1.5 | 1 | Completed
ER6378LT | W222 | W222.A25910 | HRA Fuel Handling Essential Safety Case | Interpretation of MACE for Fuel Route ##(Cost Summary)## (NEW) (C4) | 2020-04-23 | 2020-11-18 | 140 | 0 | 146 | 209 | 100% | 0.66986 | 1 | Completed
ER6378LT | W222 | W222.A22960 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Interpretation of MACE for Fuel Route EAN | 2020-04-23 | 2020-04-23 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A22960 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Interpretation of MACE for Fuel Route EAN | 2020-04-23 | 2020-04-23 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25910 | HYA Fuel Handling Essential Safety Case | Interpretation of MACE for Fuel Route ##(Cost Summary)## (NEW) (C4) | 2020-04-23 | 2020-11-18 | 139 | 0 | 146 | 209 | 100% | 0.66507 | 1 | Completed
ER6370LT | W201 | ER6370.A5450 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final HF Compliance Assessment for Shutdown Margin EAN | 2020-04-24 | 2020-04-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A5530 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final HF Compliance / Tech Spec As'ment for Core Cooling EAN | 2020-04-24 | 2020-04-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7070 | HNB Reactors Shutdown Essential Safety Cases | Boiler Supporting Systems EAN Completed | 2020-04-24 | 2020-04-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7090 | HNB Reactors Shutdown Essential Safety Cases | Boilers and Gas Circulator Performance - Reworked Draft EAN Complete Available for Verification | 2020-04-24 | 2020-04-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25930 | HRA Fuel Handling Essential Safety Case | Damage and Thermal Analysis Dropped Fuel ##(Cost Summary)## (C5) (NEW) | 2020-04-24 | 2020-12-10 | 172 | 0 | 162 | 230 | 100% | 0.74783 | 1 | Completed
ER6378LT | W222 | W222.A25820 | HRA Fuel Handling Essential Safety Case | Hazop Study of Defuelling Process (REV 000) ##(Cost Summary)## (C2) (NEW) | 2020-04-24 | 2020-10-09 | 122 | 0 | 117 | 168 | 100% | 0.72619 | 1 | Completed
ER6378LT | W222 | W222.A25720 | HRA Fuel Handling Essential Safety Case | Update to Fault Schedule/PSA ##(Cost Summary)## ### (C6) | 2020-04-24 | 2021-07-22 | 315 | 0 | 315 | 454 | 100% | 0.69383 | 1 | Completed
ER6378LT | W222 | W222.A24150 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Hazop Study of Defuelling Process EAN (REV 000) | 2020-04-24 | 2020-04-24 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A22970 | HRA Fuel Handling Essential Safety Case | Draft Interpretation of MACE for Fuel Route EAN | 2020-04-24 | 2020-06-05 | 29 | 0 | 28 | 42 | 100% | 0.69048 | 1 | Completed
ER6378LT | W222 | W222.A22900 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Damage and Thermal Analysis Dropped Fuel EAN | 2020-04-24 | 2020-04-24 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A22900 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Damage and Thermal Analysis Dropped Fuel EAN | 2020-04-24 | 2020-04-24 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A22970 | HYA Fuel Handling Essential Safety Case | Draft Interpretation of MACE for Fuel Route EAN | 2020-04-24 | 2020-06-05 | 29 | 0 | 28 | 42 | 100% | 0.69048 | 1 | Completed
ER6650LT | W226 | W226.A24150 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Hazop Study of Defuelling Process EAN (REV 000) | 2020-04-24 | 2020-04-24 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25720 | HYA Fuel Handling Essential Safety Case | Update to Fault Schedule/PSA ##(Cost Summary)## ### (C6) | 2020-04-24 | 2021-07-22 | 305 | 0 | 314 | 454 | 100% | 0.67181 | 1 | Completed
ER6650LT | W226 | W226.A25820 | HYA Fuel Handling Essential Safety Case | Hazop Study of Defuelling Process (REV 000) ##(Cost Summary)## (C2) (NEW) | 2020-04-24 | 2020-10-09 | 122 | 0 | 117 | 168 | 100% | 0.72619 | 1 | Completed
ER6650LT | W226 | W226.A25930 | HYA Fuel Handling Essential Safety Case | Damage and Thermal Analysis Dropped Fuel ##(Cost Summary)## (C5) (NEW) | 2020-04-24 | 2020-12-10 | 172 | 0 | 162 | 230 | 100% | 0.74783 | 1 | Completed
ER6370LT | W201 | ER6370.A5460 | HNB Reactors Shutdown Essential Safety Cases | HF Compliance Assessment for Shutdown Margin EAN TR Completed and uploaded to CDMS | 2020-04-27 | 2020-04-30 | 4 | 0 | 3 | 3 | 100% | 1.3333 | 1 | Completed
ER6370LT | W201 | ER6370.A5540 | HNB Reactors Shutdown Essential Safety Cases | HF Compliance / Tech Spec As'ment for Core Cooling EAN TR Completed and uploaded to CDMS | 2020-04-27 | 2020-04-30 | 4 | 0 | 3 | 3 | 100% | 1.3333 | 1 | Completed
ER6370LT | W201 | ER6370.A7100 | HNB Reactors Shutdown Essential Safety Cases | Boilers and Gas Circulator Performance - EDF Internal Verification of Reworked Draft EAN | 2020-04-27 | 2020-07-17 | 5 | 0 | 58 | 81 | 100% | 0.061728 | 1 | Completed
ER6371LT | W202 | W202.A1870 | HRA Reactors Shutdown Essential Safety Cases | Review of HRA Defuelling Case against the NSPs Draft Report Issued to EDF for Verification | 2020-04-27 | 2020-04-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1870 | HYA Reactors Shutdown Essential Safety Cases | Review of HYA Defuelling Case against the NSPs Draft Report Issued to EDF for Verification | 2020-04-27 | 2020-04-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24160 | HRA Fuel Handling Essential Safety Case | Draft Review of Hazop Study of Defuelling Process (REV 000) | 2020-04-27 | 2020-06-19 | 38 | 0 | 37 | 53 | 100% | 0.71698 | 1 | Completed
ER6378LT | W222 | W222.A23290 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Update Core Support Plate Properties Tensile EAN to CDMS | 2020-04-27 | 2020-05-01 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6378LT | W222 | W222.A22890 | HRA Fuel Handling Essential Safety Case | Draft Damage and Thermal Analysis Dropped Fuel EAN | 2020-04-27 | 2020-05-25 | 19 | 0 | 19 | 28 | 100% | 0.67857 | 1 | Completed
ER6650LT | W226 | W226.A22890 | HYA Fuel Handling Essential Safety Case | Draft Damage and Thermal Analysis Dropped Fuel EAN | 2020-04-27 | 2020-05-25 | 19 | 0 | 19 | 28 | 100% | 0.67857 | 1 | Completed
ER6650LT | W226 | W226.A23290 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Update Core Support Plate Properties Tensile EAN to CDMS | 2020-04-27 | 2020-05-01 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6650LT | W226 | W226.A24160 | HYA Fuel Handling Essential Safety Case | Draft Review of Hazop Study of Defuelling Process (REV 000) | 2020-04-27 | 2020-06-19 | 38 | 0 | 37 | 53 | 100% | 0.71698 | 1 | Completed
ER6370LT | W201 | ER6370.A4190 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Cooling Analysis Report Completed | 2020-04-28 | 2020-04-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16320 | HNB Reactors Shutdown Essential Safety Cases | All Supporting Technical References Complete - Claim 3 Cooling | 2020-04-28 | 2020-04-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A17370 | HNB Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W221) Shutdown Cooling Analysis Report Completed | 2020-04-28 | 2020-04-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A5470 | HNB Reactors Shutdown Essential Safety Cases | HF Compliance Assessment for Shutdown Margin EAN Completed | 2020-04-30 | 2020-04-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A5550 | HNB Reactors Shutdown Essential Safety Cases | HF Compliance / Tech Spec As'ment for Core Cooling EAN Completed | 2020-04-30 | 2020-04-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24390 | HRA Fuel Handling Essential Safety Case | Technical Review of Fuel Route Operational Sequence/Process for Defuelling EAN (REV 000) | 2020-04-30 | 2020-05-14 | 10 | 0 | 9 | 14 | 100% | 0.71429 | 1 | Completed
ER6650LT | W226 | W226.A24390 | HYA Fuel Handling Essential Safety Case | Technical Review of Fuel Route Operational Sequence/Process for Defuelling EAN (REV 000) | 2020-04-30 | 2020-05-14 | 10 | 0 | 9 | 14 | 100% | 0.71429 | 1 | Completed
ER6371LT | W202 | W202.A1890 | HRA Reactors Shutdown Essential Safety Cases | Review of HRA Defuelling Case against the NSPs Draft Report Verified by EDF SQEP | 2020-05-01 | 2020-07-31 | 25 | 0 | 63 | 91 | 100% | 0.27473 | 1 | Completed
ER6371LT | W202 | W202.A1970 | HRA Reactors Shutdown Essential Safety Cases | Seismic Assessment of FPU within Reactor - Review Offer, prepare and issue CI | 2020-05-01 | 2020-05-07 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A1830 | HRA Reactors Shutdown Essential Safety Cases | Assumptions EAN - Issue Draft Report to EDF Energy for Verification | 2020-05-01 | 2020-05-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1740 | HRA Reactors Shutdown Essential Safety Cases | Prepare Fault Schedule Review (Plant Base Faults and Hazards) Draft Report - (HRA) | 2020-05-01 | 2020-07-13 | 54 | 0 | 49 | 73 | 100% | 0.73973 | 1 | Completed
ER6371LT | W202 | W202.A1730 | HRA Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Base Faults and Hazards) Summary - (HRA) | 2020-05-01 | 2020-09-29 | 105 | 0 | 105 | 151 | 100% | 0.69536 | 1 | Completed
ER6661LT | W206 | W206.A1890 | HYA Reactors Shutdown Essential Safety Cases | Review of HYA Defuelling Case against the NSPs Draft Report Verified by EDF SQEP | 2020-05-01 | 2020-07-31 | 64 | 0 | 63 | 91 | 100% | 0.7033 | 1 | Completed
ER6661LT | W206 | W206.A1970 | HYA Reactors Shutdown Essential Safety Cases | Seismic Assessment of FPU within Reactor - Review Offer, prepare and issue CI | 2020-05-01 | 2020-05-07 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | W206.A1830 | HYA Reactors Shutdown Essential Safety Cases | Assumptions EAN - Issue Draft Report to EDF Energy for Verification | 2020-05-01 | 2020-05-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1740 | HYA Reactors Shutdown Essential Safety Cases | Prepare Fault Schedule Review (Plant Base Faults and Hazards) Draft Report - (HYA) | 2020-05-01 | 2020-06-12 | 54 | 0 | 28 | 42 | 100% | 1.2857 | 1 | Completed
ER6661LT | W206 | W206.A1730 | HYA Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Base Faults and Hazards) Summary - (HYA) | 2020-05-01 | 2020-09-14 | 114 | 0 | 94 | 136 | 100% | 0.83824 | 1 | Completed
ER6378LT | W222 | W222.A25770 | HRA Fuel Handling Essential Safety Case | HF Assessment of Fuel Free Verification ##(Cost Summary)## ### (C2) | 2020-05-01 | 2020-10-07 | 107 | 0 | 110 | 159 | 100% | 0.67296 | 1 | Completed
ER6378LT | W222 | W222.A23300 | HRA Fuel Handling Essential Safety Case | Update Core Support Plate Properties Tensile EAN Available | 2020-05-01 | 2020-05-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A11460 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for HF Assessment of Fuel Free Verification EAN (System) | 2020-05-01 | 2020-05-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A11460 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for HF Assessment of Fuel Free Verification EAN (System) | 2020-05-01 | 2020-05-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23300 | HYA Fuel Handling Essential Safety Case | Update Core Support Plate Properties Tensile EAN Available | 2020-05-01 | 2020-05-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25770 | HYA Fuel Handling Essential Safety Case | HF Assessment of Fuel Free Verification ##(Cost Summary)## ### (C2) | 2020-05-01 | 2020-10-07 | 107 | 0 | 110 | 159 | 100% | 0.67296 | 1 | Completed
ER6370LT | W201 | ER6370.A1690 | HNB Reactors Shutdown Essential Safety Cases | Ensure Alignment of Schedule & Estimate | 2020-05-01 | 2020-05-11 | 1 | 0 | 5 | 10 | 100% | 0.1 | 1 | Completed
ER6372LT | W203 | W203.A2550 | HNB Enhanced Defuelling Safety Cases | Initial high level scope of programme | 2020-05-01 | 2020-05-15 | 10 | 0 | 10 | 14 | 100% | 0.71429 | 1 | Completed
ER6371LT | W202 | W202.A1840 | HRA Reactors Shutdown Essential Safety Cases | Assumptions EAN - Draft Report Verified by EDF Energy | 2020-05-04 | 2020-05-13 | 7 | 0 | 6 | 9 | 100% | 0.77778 | 1 | Completed
ER6661LT | W206 | W206.A1840 | HYA Reactors Shutdown Essential Safety Cases | Assumptions EAN - Draft Report Verified by EDF Energy | 2020-05-04 | 2020-05-13 | 7 | 0 | 6 | 9 | 100% | 0.77778 | 1 | Completed
ER6378LT | W222 | W222.A17660 | HRA Fuel Handling Essential Safety Case | Draft HF Assessment of Fuel Free Verification EAN (System) | 2020-05-04 | 2020-06-01 | 19 | 0 | 18 | 28 | 100% | 0.67857 | 1 | Completed
ER6650LT | W226 | W226.A17660 | HYA Fuel Handling Essential Safety Case | Draft HF Assessment of Fuel Free Verification EAN (System) | 2020-05-04 | 2020-06-01 | 19 | 0 | 18 | 28 | 100% | 0.67857 | 1 | Completed
ER6378LT | W222 | W222.A25980 | HRA Fuel Handling Essential Safety Case | CSP Model and Static Analysis ##(Cost Summary)## (C5) (NEW) | 2020-05-06 | 2021-02-26 | 207 | 0 | 206 | 296 | 100% | 0.69932 | 1 | Completed
ER6378LT | W222 | W222.A23380 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for CSP Model and Static Analysis EAN | 2020-05-06 | 2020-05-06 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23380 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for CSP Model and Static Analysis EAN | 2020-05-06 | 2020-05-06 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25980 | HYA Fuel Handling Essential Safety Case | CSP Model and Static Analysis ##(Cost Summary)## (C5) (NEW) | 2020-05-06 | 2021-02-26 | 232 | 0 | 206 | 296 | 100% | 0.78378 | 1 | Completed
ER6378LT | W222 | W222.A23390 | HRA Fuel Handling Essential Safety Case | Draft CSP Model and Static Analysis EAN | 2020-05-07 | 2020-08-07 | 65 | 0 | 64 | 92 | 100% | 0.70652 | 1 | Completed
ER6650LT | W226 | W226.A23390 | HYA Fuel Handling Essential Safety Case | Draft CSP Model and Static Analysis EAN | 2020-05-07 | 2020-08-07 | 65 | 0 | 64 | 92 | 100% | 0.70652 | 1 | Completed
ER6370LT | W201 | ER6370.A10940 | HNB Reactors Shutdown Essential Safety Cases | Uncertainty in SDM Calculations Report Completed | 2020-05-08 | 2020-05-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16300 | HNB Reactors Shutdown Essential Safety Cases | All Supporting Technical References Complete - Claim 1 Shutdown Margins | 2020-05-08 | 2020-05-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A23200 | HRA Fuel Handling Essential Safety Case | Technical Review of Basis of Analysis Report EAN (REV 000) | 2020-05-08 | 2020-05-22 | 10 | 0 | 9 | 14 | 100% | 0.71429 | 1 | Completed
ER6650LT | W226 | W226.A23200 | HYA Fuel Handling Essential Safety Case | Technical Review of Basis of Analysis Report EAN (REV 000) | 2020-05-08 | 2020-05-22 | 10 | 0 | 9 | 14 | 100% | 0.71429 | 1 | Completed
ER6370LT | W201 | ER6370.A1720 | HNB Reactors Shutdown Essential Safety Cases | Update Schedule/Estimate from Risk Log & Add Provisions | 2020-05-11 | 2020-05-13 | 2 | 0 | 2 | 2 | 100% | 1 | 1 | Completed
ER6370LT | W201 | ER6370.P1100 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Definition of Faults for PCPV Integrity - Issue Report and upload to CDMS | 2020-05-11 | 2020-05-15 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.P1180 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Pressure Vessel Integrity Report - Verification and Address Comments of Report | 2020-05-11 | 2020-06-05 | 10 | 0 | 18 | 25 | 100% | 0.4 | 1 | Completed
ER6371LT | W202 | W202.A2030 | HRA Reactors Shutdown Essential Safety Cases | Seismic Assessment of FPU within Reactor - Supplier mobilisation time | 2020-05-11 | 2020-06-04 | 10 | 0 | 18 | 24 | 100% | 0.41667 | 1 | Completed
ER6661LT | W206 | W206.A2030 | HYA Reactors Shutdown Essential Safety Cases | Seismic Assessment of FPU within Reactor - Supplier mobilisation time | 2020-05-11 | 2020-06-04 | 10 | 0 | 17 | 24 | 100% | 0.41667 | 1 | Completed
ER6370LT | W201 | ER6370.A1730 | HNB Reactors Shutdown Essential Safety Cases | Add Data to IRM Paper | 2020-05-14 | 2020-05-15 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6371LT | W202 | W202.A1960 | HRA Reactors Shutdown Essential Safety Cases | Assumptions EAN - TSA Address Verification Comments from EDF Energy | 2020-05-14 | 2020-06-02 | 2 | 0 | 13 | 19 | 100% | 0.10526 | 1 | Completed
ER6661LT | W206 | W206.A1960 | HYA Reactors Shutdown Essential Safety Cases | Assumptions EAN - TSA Address Verification Comments from EDF Energy | 2020-05-14 | 2020-06-02 | 2 | 0 | 13 | 19 | 100% | 0.10526 | 1 | Completed
ER6378LT | W222 | W222.A25830 | HRA Fuel Handling Essential Safety Case | Human Reliability Baseline Report ##(Cost Summary)## (C2) (NEW) | 2020-05-15 | 2021-07-29 | 306 | 0 | 306 | 440 | 100% | 0.69545 | 1 | Completed
ER6378LT | W222 | W222.A24570 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Human Reliability Baseline Report EAN | 2020-05-15 | 2020-05-15 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24400 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Fuel Route Operational Sequence/Process for Defuelling EAN (REV 000) | 2020-05-15 | 2020-05-22 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6378LT | W222 | W222.A23680 | HRA Fuel Handling Essential Safety Case | Verify Confirm Acceptability of CSP PillarsEAN and Issue for Technical Review | 2020-05-15 | 2020-09-16 | 87 | 0 | 87 | 124 | 100% | 0.70161 | 1 | Completed
ER6650LT | W226 | W226.A23680 | HYA Fuel Handling Essential Safety Case | Verify Confirm Acceptability of CSP PillarsEAN and Issue for Technical Review | 2020-05-15 | 2020-09-16 | 87 | 0 | 87 | 124 | 100% | 0.70161 | 1 | Completed
ER6650LT | W226 | W226.A24400 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Fuel Route Operational Sequence/Process for Defuelling EAN (REV 000) | 2020-05-15 | 2020-05-22 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6650LT | W226 | W226.A24570 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Human Reliability Baseline Report EAN | 2020-05-15 | 2020-05-15 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25830 | HYA Fuel Handling Essential Safety Case | Human Reliability Baseline Report ##(Cost Summary)## (C2) (NEW) | 2020-05-15 | 2021-07-29 | 306 | 0 | 306 | 440 | 100% | 0.69545 | 1 | Completed
ER6370LT | W201 | ER6370.A1740 | HNB Reactors Shutdown Essential Safety Cases | PCL Validate & Approve Baseline Package for PRC Submission | 2020-05-18 | 2020-05-22 | 3 | 0 | 4 | 4 | 100% | 0.75 | 1 | Completed
ER6378LT | W222 | W222.A24580 | HRA Fuel Handling Essential Safety Case | Draft Review of Human Reliability Baseline Report EAN | 2020-05-18 | 2020-12-09 | 83 | 0 | 145 | 205 | 100% | 0.40488 | 1 | Completed
ER6378LT | W222 | W222.A24410 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Fuel Route Operational Sequence/Process for Defuelling EAN to CDMS (PROCESS DOCUMENT) (REV 000) | 2020-05-18 | 2020-07-20 | 45 | 0 | 44 | 63 | 100% | 0.71429 | 1 | Completed
ER6650LT | W226 | W226.A24410 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Fuel Route Operational Sequence/Process for Defuelling EAN to CDMS (PROCESS DOCUMENT) (REV 000) | 2020-05-18 | 2020-07-20 | 45 | 0 | 44 | 63 | 100% | 0.71429 | 1 | Completed
ER6650LT | W226 | W226.A24580 | HYA Fuel Handling Essential Safety Case | Draft Review of Human Reliability Baseline Report EAN | 2020-05-18 | 2020-12-09 | 83 | 0 | 145 | 205 | 100% | 0.40488 | 1 | Completed
ER6372LT | W203 | W203.A2560 | HNB Enhanced Defuelling Safety Cases | Define Project Control Structures (WBS/CBS/OBS/PBS) | 2020-05-18 | 2020-05-22 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6372LT | W203 | W203.A2570 | HNB Enhanced Defuelling Safety Cases | Prepare Draft Project Definition Document (PDD) | 2020-05-18 | 2020-07-13 | 40 | 0 | 40 | 56 | 100% | 0.71429 | 1 | Completed
ER6370LT | W201 | ER6370.P1050 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - ALARP Report - Issue Report | 2020-05-21 | 2020-05-28 | 5 | 0 | 4 | 7 | 100% | 0.71429 | 1 | Completed
ER6370LT | W201 | ER6370.P1040 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - ALARP Report - Presented to DSCOG | 2020-05-22 | 2020-05-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.P1150 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Civils Integrity Report - Verification and Address Comments of Report | 2020-05-25 | 2020-05-29 | 5 | 0 | 3 | 4 | 100% | 1.25 | 1 | Completed
ER6378LT | W222 | W222.A23210 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Basis of Analysis Report EAN (REV 000) | 2020-05-25 | 2020-06-01 | 5 | 0 | 4 | 7 | 100% | 0.71429 | 1 | Completed
ER6650LT | W226 | W226.A23210 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Basis of Analysis Report EAN (REV 000) | 2020-05-25 | 2020-06-01 | 5 | 0 | 4 | 7 | 100% | 0.71429 | 1 | Completed
ER6371LT | W202 | W202.A1760 | HRA Reactors Shutdown Essential Safety Cases | Thermal Analysis (FEAT) of FPU Fully Extended - Draft and issue RFS | 2020-05-26 | 2020-06-05 | 9 | 0 | 9 | 10 | 100% | 0.9 | 1 | Completed
ER6371LT | W202 | W202.A1750 | HRA Reactors Shutdown Essential Safety Cases | RFS - Thermal Analysis (FEAT) of FPU Fully Extended Summary | 2020-05-26 | 2020-07-06 | 37 | 0 | 29 | 41 | 100% | 0.90244 | 1 | Completed
ER6378LT | W222 | W222.A22910 | HRA Fuel Handling Essential Safety Case | Verify Damage and Thermal Analysis Dropped Fuel EAN and Issue for Technical Review | 2020-05-26 | 2020-06-23 | 21 | 0 | 20 | 28 | 100% | 0.75 | 1 | Completed
ER6650LT | W226 | W226.A22910 | HYA Fuel Handling Essential Safety Case | Verify Damage and Thermal Analysis Dropped Fuel EAN and Issue for Technical Review | 2020-05-26 | 2020-06-23 | 21 | 0 | 20 | 28 | 100% | 0.75 | 1 | Completed
ER6378LT | W222 | W222.A9920 | HRA Fuel Handling Essential Safety Case | Verify Update to Failed Fuel EAN and Issue for Technical Review | 2020-05-27 | 2020-06-17 | 16 | 0 | 15 | 21 | 100% | 0.7619 | 1 | Completed
ER6650LT | W226 | W226.A9920 | HYA Fuel Handling Essential Safety Case | Verify Update to Failed Fuel EAN and Issue for Technical Review | 2020-05-27 | 2020-06-17 | 16 | 0 | 15 | 21 | 100% | 0.7619 | 1 | Completed
ER6370LT | W201 | ER6370.P1160 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Civils Integrity Report - Issue Report and upload to CDMS | 2020-06-01 | 2020-06-12 | 3 | 0 | 9 | 11 | 100% | 0.27273 | 1 | Completed
ER6378LT | W222 | W222.A25870 | HRA Fuel Handling Essential Safety Case | Human Factors Risk Assessment for Defuelling ##(Cost Summary)## (C2) (NEW) | 2020-06-01 | 2020-06-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25800 | HRA Fuel Handling Essential Safety Case | Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN ##(Cost Summary)## (C2) (NEW) | 2020-06-01 | 2020-09-01 | 66 | 0 | 66 | 92 | 100% | 0.71739 | 1 | Completed
ER6378LT | W222 | W222.A25760 | HRA Fuel Handling Essential Safety Case | Human Factors Integration Plan ##(Cost Summary)## ### (C2) | 2020-06-01 | 2021-07-29 | 274 | 0 | 296 | 423 | 100% | 0.64775 | 1 | Completed
ER6378LT | W222 | W222.A24850 | HRA Fuel Handling Essential Safety Case | Confirm R1 Document is Appropriate (Human Factors Risk Assessment for Defuelling EAN) | 2020-06-01 | 2020-06-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24900 | HRA Fuel Handling Essential Safety Case | Complete Review of Human Factors Risk Assessment for Defuelling EAN to CDMS | 2020-06-01 | 2020-06-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24910 | HRA Fuel Handling Essential Safety Case | Human Factors Risk Assessment for Defuelling EAN Available | 2020-06-01 | 2020-06-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24430 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN | 2020-06-01 | 2020-06-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A23750 | HRA Fuel Handling Essential Safety Case | Verify Shock Absorbers Feasibility Study EAN for Technical Review | 2020-06-01 | 2020-06-15 | 11 | 0 | 10 | 14 | 100% | 0.78571 | 1 | Completed
ER6378LT | W222 | W222.A17550 | HRA Fuel Handling Essential Safety Case | Findings of PSA Quick Look Activities (File Note) | 2020-06-01 | 2020-06-30 | 22 | 0 | 21 | 29 | 100% | 0.75862 | 1 | Completed
ER6378LT | W222 | W222.A11590 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Human Factors Integration Plan EAN (REV 000) | 2020-06-01 | 2020-06-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A11590 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Human Factors Integration Plan EAN (REV 000) | 2020-06-01 | 2020-06-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A17550 | HYA Fuel Handling Essential Safety Case | Findings of PSA Quick Look Activities (File Note) | 2020-06-01 | 2020-06-30 | 22 | 0 | 21 | 29 | 100% | 0.75862 | 1 | Completed
ER6650LT | W226 | W226.A23750 | HYA Fuel Handling Essential Safety Case | Verify Shock Absorbers Feasibility Study EAN for Technical Review | 2020-06-01 | 2020-06-15 | 11 | 0 | 10 | 14 | 100% | 0.78571 | 1 | Completed
ER6650LT | W226 | W226.A24430 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN | 2020-06-01 | 2020-06-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24910 | HYA Fuel Handling Essential Safety Case | Human Factors Risk Assessment for Defuelling EAN Available | 2020-06-01 | 2020-06-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24900 | HYA Fuel Handling Essential Safety Case | Complete Review of Human Factors Risk Assessment for Defuelling EAN to CDMS | 2020-06-01 | 2020-06-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24850 | HYA Fuel Handling Essential Safety Case | Confirm R1 Document is Appropriate (Human Factors Risk Assessment for Defuelling EAN) | 2020-06-01 | 2020-06-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25760 | HYA Fuel Handling Essential Safety Case | Human Factors Integration Plan ##(Cost Summary)## ### (C2) | 2020-06-01 | 2021-07-29 | 274 | 0 | 296 | 423 | 100% | 0.64775 | 1 | Completed
ER6650LT | W226 | W226.A25800 | HYA Fuel Handling Essential Safety Case | Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN ##(Cost Summary)## (C2) (NEW) | 2020-06-01 | 2020-09-01 | 66 | 0 | 66 | 92 | 100% | 0.71739 | 1 | Completed
ER6650LT | W226 | W226.A25870 | HYA Fuel Handling Essential Safety Case | Human Factors Risk Assessment for Defuelling ##(Cost Summary)## (C2) (NEW) | 2020-06-01 | 2020-06-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2010 | HRA Reactors Shutdown Essential Safety Cases | Prepare Gas Chemistry Assessment Draft Report | 2020-06-01 | 2020-06-30 | 30 | 0 | 21 | 29 | 100% | 1.0345 | 1 | Completed
ER6371LT | W202 | W202.A2000 | HRA Reactors Shutdown Essential Safety Cases | Gas Chemistry Assessment Summary | 2020-06-01 | 2020-10-26 | 100 | 0 | 104 | 147 | 100% | 0.68027 | 1 | Completed
ER6371LT | W202 | W202.A1880 | HRA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HRA - Pre Job Brief | 2020-06-01 | 2020-06-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2010 | HYA Reactors Shutdown Essential Safety Cases | Prepare Gas Chemistry Assessment Draft Report | 2020-06-01 | 2020-06-30 | 30 | 0 | 21 | 29 | 100% | 1.0345 | 1 | Completed
ER6661LT | W206 | W206.A2000 | HYA Reactors Shutdown Essential Safety Cases | Gas Chemistry Assessment Summary | 2020-06-01 | 2020-10-26 | 100 | 0 | 104 | 147 | 100% | 0.68027 | 1 | Completed
ER6661LT | W206 | W206.A1760 | HYA Reactors Shutdown Essential Safety Cases | Thermal Analysis (FEAT) of FPU Fully Extended - Draft and issue RFS | 2020-06-01 | 2020-06-05 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6661LT | W206 | W206.A1750 | HYA Reactors Shutdown Essential Safety Cases | RFS - Thermal Analysis (FEAT) of FPU Fully Extended Summary | 2020-06-01 | 2020-07-06 | 33 | 0 | 26 | 35 | 100% | 0.94286 | 1 | Completed
ER6661LT | W206 | W206.A1880 | HYA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HYA - Pre Job Brief | 2020-06-01 | 2020-06-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1860 | HRA Reactors Shutdown Essential Safety Cases | HF - Oversight of Work / HF Risk / HFIP - Draft and issue RFS | 2020-06-02 | 2020-06-09 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6371LT | W202 | W202.A1850 | HRA Reactors Shutdown Essential Safety Cases | RFS - HF - Oversight of Work / HF Risk / HFIP Summary | 2020-06-02 | 2020-08-28 | 51 | 0 | 64 | 87 | 100% | 0.58621 | 1 | Completed
ER6661LT | W206 | W206.A1860 | HYA Reactors Shutdown Essential Safety Cases | HF - Oversight of Work / HF Risk / HFIP - Draft and issue RFS | 2020-06-02 | 2020-06-09 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6661LT | W206 | W206.A1850 | HYA Reactors Shutdown Essential Safety Cases | RFS - HF - Oversight of Work / HF Risk / HFIP Summary | 2020-06-02 | 2020-08-28 | 64 | 0 | 64 | 87 | 100% | 0.73563 | 1 | Completed
ER6378LT | W222 | W222.A24440 | HRA Fuel Handling Essential Safety Case | Draft Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN | 2020-06-02 | 2020-06-30 | 21 | 0 | 20 | 28 | 100% | 0.75 | 1 | Completed
ER6378LT | W222 | W222.A23220 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Basis of Analysis Report EAN to CDMS (REV 000) | 2020-06-02 | 2020-06-05 | 4 | 0 | 3 | 3 | 100% | 1.3333 | 1 | Completed
ER6378LT | W222 | W222.A11480 | HRA Fuel Handling Essential Safety Case | Verify HF Assessment of Fuel Free Verification EAN and Issue for Technical Review (System) | 2020-06-02 | 2020-06-22 | 15 | 0 | 14 | 20 | 100% | 0.75 | 1 | Completed
ER6378LT | W222 | W222.A11600 | HRA Fuel Handling Essential Safety Case | Draft Human Factors Integration Plan EAN (REV 000) | 2020-06-02 | 2020-08-07 | 27 | 0 | 48 | 66 | 100% | 0.40909 | 1 | Completed
ER6650LT | W226 | W226.A11600 | HYA Fuel Handling Essential Safety Case | Draft Human Factors Integration Plan EAN (REV 000) | 2020-06-02 | 2020-08-07 | 27 | 0 | 48 | 66 | 100% | 0.40909 | 1 | Completed
ER6650LT | W226 | W226.A11480 | HYA Fuel Handling Essential Safety Case | Verify HF Assessment of Fuel Free Verification EAN and Issue for Technical Review (System) | 2020-06-02 | 2020-06-22 | 15 | 0 | 14 | 20 | 100% | 0.75 | 1 | Completed
ER6650LT | W226 | W226.A23220 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Basis of Analysis Report EAN to CDMS (REV 000) | 2020-06-02 | 2020-06-05 | 4 | 0 | 3 | 3 | 100% | 1.3333 | 1 | Completed
ER6650LT | W226 | W226.A24440 | HYA Fuel Handling Essential Safety Case | Draft Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN | 2020-06-02 | 2020-06-30 | 21 | 0 | 20 | 28 | 100% | 0.75 | 1 | Completed
ER6370LT | W201 | ER6370.A1640 | HNB Reactors Shutdown Essential Safety Cases | Gate C PRC Paper Submission | 2020-06-03 | 2020-06-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1790 | HNB Reactors Shutdown Essential Safety Cases | PRC Members Review IRM Documentation | 2020-06-03 | 2020-06-09 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A1980 | HRA Reactors Shutdown Essential Safety Cases | Assumptions EAN - EDF Energy Approve Final Report | 2020-06-03 | 2020-06-05 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6661LT | W206 | W206.A1980 | HYA Reactors Shutdown Essential Safety Cases | Assumptions EAN - EDF Energy Approve Final Report | 2020-06-03 | 2020-06-05 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6378LT | W222 | W222.A23230 | HRA Fuel Handling Essential Safety Case | Basis of Analysis Report EAN Available (REV 000) | 2020-06-05 | 2020-06-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23230 | HYA Fuel Handling Essential Safety Case | Basis of Analysis Report EAN Available (REV 000) | 2020-06-05 | 2020-06-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.P1190 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Pressure Vessel Integrity Report - Issue Report and upload to CDMS | 2020-06-08 | 2020-06-10 | 3 | 0 | 2 | 2 | 100% | 1.5 | 1 | Completed
ER6378LT | W222 | W222.A22980 | HRA Fuel Handling Essential Safety Case | Verify Interpretation of MACE for Fuel Route EAN and Issue for Technical Review | 2020-06-08 | 2020-08-10 | 46 | 0 | 45 | 63 | 100% | 0.73016 | 1 | Completed
ER6650LT | W226 | W226.A22980 | HYA Fuel Handling Essential Safety Case | Verify Interpretation of MACE for Fuel Route EAN and Issue for Technical Review | 2020-06-08 | 2020-08-10 | 46 | 0 | 45 | 63 | 100% | 0.73016 | 1 | Completed
ER6371LT | W202 | W202.A1810 | HRA Reactors Shutdown Essential Safety Cases | Thermal Analysis (FEAT) of FPU Fully Extended - Supplier prepare and issue Offer | 2020-06-08 | 2020-06-19 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6371LT | W202 | W202.A2020 | HRA Reactors Shutdown Essential Safety Cases | Assumptions EAN - TSA Issue Final Report | 2020-06-08 | 2020-06-08 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1810 | HYA Reactors Shutdown Essential Safety Cases | Thermal Analysis (FEAT) of FPU Fully Extended - Supplier prepare and issue Offer | 2020-06-08 | 2020-06-19 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6661LT | W206 | W206.A2020 | HYA Reactors Shutdown Essential Safety Cases | Assumptions EAN - TSA Issue Final Report | 2020-06-08 | 2020-06-08 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2070 | HRA Reactors Shutdown Essential Safety Cases | Assumptions EAN - Post Job De-Brief | 2020-06-09 | 2020-06-11 | 2 | 0 | 2 | 2 | 100% | 1 | 1 | Completed
ER6371LT | W202 | W202.A2040 | HRA Reactors Shutdown Essential Safety Cases | Assumptions EAN - TR Completed and Final Report Uploaded to CDMS | 2020-06-09 | 2020-06-15 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | W206.A2040 | HYA Reactors Shutdown Essential Safety Cases | Assumptions EAN - TR Completed and Final Report Uploaded to CDMS | 2020-06-09 | 2020-06-15 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A13075 | HNB Reactors Shutdown Essential Safety Cases | PVCW Key Technical References Complete | 2020-06-10 | 2020-06-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1950 | HRA Reactors Shutdown Essential Safety Cases | HF - Oversight of Work / HF Risk / HFIP - Supplier prepare and issue Offer | 2020-06-10 | 2020-06-12 | 10 | 0 | 2 | 2 | 100% | 5 | 1 | Completed
ER6371LT | W202 | W202.A2140 | HRA Reactors Shutdown Essential Safety Cases | Seismic Assessment of FPU within Reactor - Pre Job Brief | 2020-06-10 | 2020-06-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1950 | HYA Reactors Shutdown Essential Safety Cases | HF - Oversight of Work / HF Risk / HFIP - Supplier prepare and issue Offer | 2020-06-10 | 2020-06-12 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6661LT | W206 | W206.A2140 | HYA Reactors Shutdown Essential Safety Cases | Seismic Assessment of FPU within Reactor - Pre Job Brief | 2020-06-10 | 2020-06-10 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2070 | HYA Reactors Shutdown Essential Safety Cases | Assumptions EAN - Post Job De-Brief | 2020-06-10 | 2020-06-11 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | ER6370.A1760 | HNB Reactors Shutdown Essential Safety Cases | Hold PRC Meeting | 2020-06-11 | 2020-06-11 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1840 | HNB Reactors Shutdown Essential Safety Cases | Gate C PRC Paper Approval | 2020-06-11 | 2020-06-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1770 | HNB Reactors Shutdown Essential Safety Cases | Modify Estimate, Schedule & Risk Log as Required | 2020-06-12 | 2020-06-12 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4300 | HNB Reactors Shutdown Essential Safety Cases | Issue Core Cooling Compliance Summary Draft Report to EDF for Review. | 2020-06-12 | 2020-06-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8550 | HNB Reactors Shutdown Essential Safety Cases | TSA Issue Final Containment Head Document Report | 2020-06-12 | 2020-06-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8580 | HNB Reactors Shutdown Essential Safety Cases | Containment Implementation Workshop | 2020-06-12 | 2020-06-12 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A17310 | HNB Reactors Shutdown Essential Safety Cases | Cooling Workshop | 2020-06-12 | 2020-06-12 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1650 | HNB Reactors Shutdown Essential Safety Cases | Gate C MS PRC Paper Submission | 2020-06-15 | 2020-06-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1780 | HNB Reactors Shutdown Essential Safety Cases | Modify IRM Paper as Required | 2020-06-15 | 2020-06-15 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4310 | HNB Reactors Shutdown Essential Safety Cases | Core Cooling Compliance Summary Draft Report Reviewed by EDF SQEP | 2020-06-15 | 2020-07-01 | 10 | 0 | 12 | 16 | 100% | 0.625 | 1 | Completed
ER6370LT | W201 | ER6370.A8560 | HNB Reactors Shutdown Essential Safety Cases | Containment Head Document Report TR Completed and uploaded to CDMS | 2020-06-15 | 2020-09-15 | 10 | 0 | 65 | 92 | 100% | 0.1087 | 1 | Completed
ER6371LT | W202 | W202.A2060 | HRA Reactors Shutdown Essential Safety Cases | HF - Oversight of Work / HF Risk / HFIP - Review Offer, prepare and issue CI | 2020-06-15 | 2020-06-15 | 5 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2060 | HYA Reactors Shutdown Essential Safety Cases | HF - Oversight of Work / HF Risk / HFIP - Review Offer, prepare and issue CI | 2020-06-15 | 2020-06-15 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A16400 | HRA Fuel Handling Essential Safety Case | Draft Update to Defuelling Programme Assumptions EAN | 2020-06-15 | 2020-06-15 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A16390 | HRA Fuel Handling Essential Safety Case | Draft Update to Defuelling Programme Assumptions EAN Verified and Issued for Verification | 2020-06-15 | 2020-06-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A16410 | HRA Fuel Handling Essential Safety Case | Verification of Update to Defuelling Programme Assumptions EAN | 2020-06-15 | 2020-06-15 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A16420 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Update to Defuelling Programme Assumptions EAN | 2020-06-15 | 2020-06-15 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A16440 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Update to Defuelling Programme Assumptions EAN to CDMS | 2020-06-15 | 2020-06-15 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A16430 | HRA Fuel Handling Essential Safety Case | Update to Defuelling Programme Assumptions EAN Available | 2020-06-15 | 2020-06-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A16380 | HRA Fuel Handling Essential Safety Case | Update to Defuelling Programme Assumptions ##(Cost Summary)## | 2020-06-15 | 2020-06-15 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A16380 | HYA Fuel Handling Essential Safety Case | Update to Defuelling Programme Assumptions ##(Cost Summary)## | 2020-06-15 | 2020-06-15 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A16430 | HYA Fuel Handling Essential Safety Case | Update to Defuelling Programme Assumptions EAN Available | 2020-06-15 | 2020-06-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A16440 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Update to Defuelling Programme Assumptions EAN to CDMS | 2020-06-15 | 2020-06-15 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A16420 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Update to Defuelling Programme Assumptions EAN | 2020-06-15 | 2020-06-15 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A16410 | HYA Fuel Handling Essential Safety Case | Verification of Update to Defuelling Programme Assumptions EAN | 2020-06-15 | 2020-06-15 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A16390 | HYA Fuel Handling Essential Safety Case | Draft Update to Defuelling Programme Assumptions EAN Verified and Issued for Verification | 2020-06-15 | 2020-06-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A16400 | HYA Fuel Handling Essential Safety Case | Draft Update to Defuelling Programme Assumptions EAN | 2020-06-15 | 2020-06-15 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1810 | HNB Reactors Shutdown Essential Safety Cases | Modify Estimate, Schedule, Cost Tool & Risk Log as Required | 2020-06-16 | 2020-06-16 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1820 | HNB Reactors Shutdown Essential Safety Cases | Update Cost Management Tool | 2020-06-16 | 2020-06-22 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6378LT | W222 | W222.A23760 | HRA Fuel Handling Essential Safety Case | Technical Review of Shock Absorbers Feasibility Study EAN | 2020-06-16 | 2020-06-23 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6650LT | W226 | W226.A23760 | HYA Fuel Handling Essential Safety Case | Technical Review of Shock Absorbers Feasibility Study EAN | 2020-06-16 | 2020-06-23 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6370LT | W201 | ER6370.A4210 | HNB Reactors Shutdown Essential Safety Cases | Core Cooling Head Document Draft Report Verified by all Verifiers | 2020-06-17 | 2020-07-17 | 10 | 0 | 22 | 30 | 100% | 0.33333 | 1 | Completed
ER6370LT | W201 | ER6370.P1220 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Head Document (PVCW) - First Round Verification and Address Comments of Head Document | 2020-06-18 | 2020-07-13 | 8 | 0 | 18 | 25 | 100% | 0.32 | 1 | Completed
ER6378LT | W222 | W222.A9930 | HRA Fuel Handling Essential Safety Case | Technical Review of Update to Failed Fuel EAN | 2020-06-18 | 2020-09-01 | 53 | 0 | 52 | 75 | 100% | 0.70667 | 1 | Completed
ER6650LT | W226 | W226.A9930 | HYA Fuel Handling Essential Safety Case | Technical Review of Update to Failed Fuel EAN | 2020-06-18 | 2020-09-01 | 53 | 0 | 52 | 75 | 100% | 0.70667 | 1 | Completed
ER6378LT | W222 | W222.A24170 | HRA Fuel Handling Essential Safety Case | Verify Review of Hazop Study of Defuelling Process EAN and Issue for Technical Review (REV 000) | 2020-06-22 | 2020-09-10 | 15 | 0 | 58 | 80 | 100% | 0.1875 | 1 | Completed
ER6650LT | W226 | W226.A24170 | HYA Fuel Handling Essential Safety Case | Verify Review of Hazop Study of Defuelling Process EAN and Issue for Technical Review (REV 000) | 2020-06-22 | 2020-09-10 | 15 | 0 | 58 | 80 | 100% | 0.1875 | 1 | Completed
ER6371LT | W202 | W202.A1940 | HRA Reactors Shutdown Essential Safety Cases | Thermal Analysis (FEAT) of FPU Fully Extended - Review Offer, prepare and issue CI | 2020-06-22 | 2020-06-26 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6661LT | W206 | W206.A1940 | HYA Reactors Shutdown Essential Safety Cases | Thermal Analysis (FEAT) of FPU Fully Extended - Review Offer, prepare and issue CI | 2020-06-22 | 2020-06-26 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6378LT | W222 | W222.A11490 | HRA Fuel Handling Essential Safety Case | Technical Review of HF Assessment of Fuel Free Verification EAN (System) | 2020-06-23 | 2020-09-11 | 58 | 0 | 58 | 80 | 100% | 0.725 | 1 | Completed
ER6650LT | W226 | W226.A11490 | HYA Fuel Handling Essential Safety Case | Technical Review of HF Assessment of Fuel Free Verification EAN (System) | 2020-06-23 | 2020-09-11 | 58 | 0 | 58 | 80 | 100% | 0.725 | 1 | Completed
ER6378LT | W222 | W222.A23770 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Shock Absorbers Feasibility Study EAN | 2020-06-24 | 2020-06-24 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A22920 | HRA Fuel Handling Essential Safety Case | Technical Review of Damage and Thermal Analysis Dropped Fuelr EAN | 2020-06-24 | 2020-12-10 | 23 | 0 | 120 | 169 | 100% | 0.13609 | 1 | Completed
ER6650LT | W226 | W226.A22920 | HYA Fuel Handling Essential Safety Case | Technical Review of Damage and Thermal Analysis Dropped Fuelr EAN | 2020-06-24 | 2020-12-10 | 23 | 0 | 120 | 169 | 100% | 0.13609 | 1 | Completed
ER6650LT | W226 | W226.A23770 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Shock Absorbers Feasibility Study EAN | 2020-06-24 | 2020-06-24 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A23780 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Shock Absorbers Feasibility Study EAN to CDMS | 2020-06-25 | 2020-10-02 | 66 | 0 | 71 | 99 | 100% | 0.66667 | 1 | Completed
ER6378LT | W222 | W222.A18150 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for P6.6 Handover Document | 2020-06-25 | 2020-06-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A18250 | HRA Fuel Handling Essential Safety Case | HH1 EoG Strategy for Implementation of Doc Changes for Essen Fuel/non Fuel Handling SC Handover Doc ##(Cost Summary)## | 2020-06-25 | 2021-02-26 | 208 | 0 | 172 | 246 | 100% | 0.84553 | 1 | Completed
ER6650LT | W226 | W226.A18250 | HYA Fuel Handling Essential Safety Case | HH1 EoG Strategy for Implementation of Doc Changes for Essen Fuel/non Fuel Handling SC Handover Doc ##(Cost Summary)## | 2020-06-25 | 2021-02-26 | 208 | 0 | 172 | 246 | 100% | 0.84553 | 1 | Completed
ER6650LT | W226 | W226.A18150 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for P6.6 Handover Document | 2020-06-25 | 2020-06-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23780 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Shock Absorbers Feasibility Study EAN to CDMS | 2020-06-25 | 2020-10-02 | 66 | 0 | 71 | 99 | 100% | 0.66667 | 1 | Completed
ER6370LT | W201 | ER6370.A1830 | HNB Reactors Shutdown Essential Safety Cases | IRM Members Review IRM Documentation | 2020-06-26 | 2020-07-01 | 5 | 0 | 3 | 5 | 100% | 1 | 1 | Completed
ER6370LT | W201 | ER6370.A2670 | HNB Reactors Shutdown Essential Safety Cases | Shutdown margin compliance summary Report Completed | 2020-06-26 | 2020-06-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A7860 | HNB Reactors Shutdown Essential Safety Cases | Shutdown Margin Head Document Completed | 2020-06-26 | 2020-06-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A17520 | HNB Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (D414) Shutdown Margin Head Document Completed | 2020-06-26 | 2020-06-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A18160 | HRA Fuel Handling Essential Safety Case | Draft P6.6 Handover Document | 2020-06-26 | 2020-10-28 | 88 | 0 | 87 | 124 | 100% | 0.70968 | 1 | Completed
ER6650LT | W226 | W226.A18160 | HYA Fuel Handling Essential Safety Case | Draft P6.6 Handover Document | 2020-06-26 | 2020-10-28 | 88 | 0 | 87 | 124 | 100% | 0.70968 | 1 | Completed
ER6371LT | W202 | W202.A3240 | HRA Reactors Shutdown Essential Safety Cases | Issue Worker Dose Report to EDF Review. | 2020-06-29 | 2020-06-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3240 | HYA Reactors Shutdown Essential Safety Cases | Issue Worker Dose Report to EDF Review. | 2020-06-29 | 2020-06-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26010 | HRA Fuel Handling Essential Safety Case | Quality of Build Considerations ##(Cost Summary)## (C5) (NEW) | 2020-06-29 | 2020-12-02 | 112 | 0 | 112 | 156 | 100% | 0.71795 | 1 | Completed
ER6378LT | W222 | W222.A25730 | HRA Fuel Handling Essential Safety Case | Worker Dose Assessment ##(Cost Summary)## ### (C6) | 2020-06-29 | 2023-11-02 | 889 | 0 | 846 | 1221 | 100% | 0.72809 | 1 | Completed
ER6378LT | W222 | W222.A23590 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Quality of Build Considerations (Task File Note) | 2020-06-29 | 2020-06-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A10550 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Worker Dose Assessment (SKELETON) EAN | 2020-06-29 | 2020-06-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A10550 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Worker Dose Assessment (SKELETON) EAN | 2020-06-29 | 2020-06-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23590 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Quality of Build Considerations (Task File Note) | 2020-06-29 | 2020-06-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25730 | HYA Fuel Handling Essential Safety Case | Worker Dose Assessment ##(Cost Summary)## ### (C6) | 2020-06-29 | 2023-11-02 | 847 | 0 | 847 | 1221 | 100% | 0.69369 | 1 | Completed
ER6650LT | W226 | W226.A26010 | HYA Fuel Handling Essential Safety Case | Quality of Build Considerations ##(Cost Summary)## (C5) (NEW) | 2020-06-29 | 2020-12-02 | 112 | 0 | 112 | 156 | 100% | 0.71795 | 1 | Completed
ER6378LT | W222 | W222.A23600 | HRA Fuel Handling Essential Safety Case | Draft Quality of Build Considerations (Task File Note) | 2020-06-30 | 2020-10-13 | 56 | 0 | 75 | 105 | 100% | 0.53333 | 1 | Completed
ER6378LT | W222 | W222.A10560 | HRA Fuel Handling Essential Safety Case | Draft Worker Dose Assessment (SKELETON) EAN | 2020-06-30 | 2021-02-01 | 73 | 0 | 151 | 216 | 100% | 0.33796 | 1 | Completed
ER6650LT | W226 | W226.A10560 | HYA Fuel Handling Essential Safety Case | Draft Worker Dose Assessment (SKELETON) EAN | 2020-06-30 | 2021-02-01 | 73 | 0 | 151 | 216 | 100% | 0.33796 | 1 | Completed
ER6650LT | W226 | W226.A23600 | HYA Fuel Handling Essential Safety Case | Draft Quality of Build Considerations (Task File Note) | 2020-06-30 | 2020-10-13 | 56 | 0 | 75 | 105 | 100% | 0.53333 | 1 | Completed
ER6370LT | W201 | ER6370.A1800 | HNB Reactors Shutdown Essential Safety Cases | Hold MS PRC | 2020-07-01 | 2020-07-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1850 | HNB Reactors Shutdown Essential Safety Cases | Gate C MS PRC Approval | 2020-07-01 | 2020-07-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2130 | HRA Reactors Shutdown Essential Safety Cases | Prepare Pressure Boundary Seals Draft Report | 2020-07-01 | 2020-07-17 | 13 | 0 | 12 | 16 | 100% | 0.8125 | 1 | Completed
ER6371LT | W202 | W202.A2120 | HRA Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals Summary | 2020-07-01 | 2020-11-23 | 125 | 0 | 102 | 145 | 100% | 0.86207 | 1 | Completed
ER6661LT | W206 | W206.A2350 | HYA Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals Draft Report Verified by TSA | 2020-07-01 | 2020-08-28 | 43 | 0 | 42 | 58 | 100% | 0.74138 | 1 | Completed
ER6661LT | W206 | W206.A2120 | HYA Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals Summary | 2020-07-01 | 2020-11-23 | 117 | 0 | 102 | 145 | 100% | 0.8069 | 1 | Completed
ER6378LT | W222 | W222.A24450 | HRA Fuel Handling Essential Safety Case | Verify Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN & Issue for Technical Review | 2020-07-01 | 2020-07-02 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | A1040 | HNB Reactors Shutdown Essential Safety Cases | 4 – Resolution of SC Shortfalls and Key NS Issues - Summary | 2020-07-01 | 2020-07-30 | 22 | 0 | 22 | 29 | 100% | 0.75862 | 1 | Completed
ER6370LT | W201 | A1050 | HNB Reactors Shutdown Essential Safety Cases | 5 – Description of Updated SC - Summary | 2020-07-01 | 2020-08-05 | 24 | 0 | 25 | 35 | 100% | 0.68571 | 1 | Completed
ER6370LT | W201 | A1060 | HNB Reactors Shutdown Essential Safety Cases | 5.0 Claim 0 - Summary | 2020-07-01 | 2020-08-14 | 18 | 0 | 33 | 44 | 100% | 0.40909 | 1 | Completed
ER6370LT | W201 | A1070 | HNB Reactors Shutdown Essential Safety Cases | 5.1 Claim 1 - Summary | 2020-07-01 | 2020-08-06 | 16 | 0 | 27 | 36 | 100% | 0.44444 | 1 | Completed
ER6370LT | W201 | A1080 | HNB Reactors Shutdown Essential Safety Cases | 5.2 Claim 2 - Summary | 2020-07-01 | 2020-08-28 | 30 | 0 | 42 | 58 | 100% | 0.51724 | 1 | Completed
ER6370LT | W201 | A1130 | HNB Reactors Shutdown Essential Safety Cases | 7 – QA - Summary | 2020-07-01 | 2020-10-09 | 59 | 0 | 72 | 100 | 100% | 0.59 | 1 | Completed
ER6370LT | W201 | A1140 | HNB Reactors Shutdown Essential Safety Cases | 8 – Implementation Programme - Summary | 2020-07-01 | 2020-10-09 | 61 | 0 | 72 | 100 | 100% | 0.61 | 1 | Completed
ER6370LT | W201 | A1150 | HNB Reactors Shutdown Essential Safety Cases | 9 – INSA - Summary | 2020-07-01 | 2020-09-25 | 49 | 0 | 62 | 86 | 100% | 0.56977 | 1 | Completed
ER6370LT | W201 | A1440 | HNB Reactors Shutdown Essential Safety Cases | Resolution of SC Shortfalls and Key NS Issues - Early Draft | 2020-07-01 | 2020-07-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1490 | HNB Reactors Shutdown Essential Safety Cases | Description of Updated SC - Early Draft | 2020-07-01 | 2020-07-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1540 | HNB Reactors Shutdown Essential Safety Cases | Claim 0 - Early Draft | 2020-07-01 | 2020-07-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1590 | HNB Reactors Shutdown Essential Safety Cases | Claim 1 - Early Draft | 2020-07-01 | 2020-07-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1640 | HNB Reactors Shutdown Essential Safety Cases | Claim 2 - Early Draft | 2020-07-01 | 2020-07-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1890 | HNB Reactors Shutdown Essential Safety Cases | QA - Early Draft | 2020-07-01 | 2020-07-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1940 | HNB Reactors Shutdown Essential Safety Cases | Implementation Programme - Early Draft | 2020-07-01 | 2020-07-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A2020 | HNB Reactors Shutdown Essential Safety Cases | INSA - Peer Review | 2020-07-01 | 2020-07-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A2745 | HNB Reactors Shutdown Essential Safety Cases | Safety Case Authoring Start | 2020-07-01 | 2020-07-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A2741 | HNB Reactors Shutdown Essential Safety Cases | Safety Case Authoring - Summary | 2020-07-01 | 2020-10-09 | 74 | 0 | 72 | 100 | 100% | 0.74 | 1 | Completed
ER6378LT | W222 | W222.A26940 | HRA Fuel Handling Essential Safety Case | Update Project Definition Document (PDD) | 2020-07-01 | 2020-09-21 | 1 | 0 | 57 | 82 | 100% | 0.012195 | 1 | Completed
ER6378LT | W222 | W222.A27020 | HRA Fuel Handling Essential Safety Case | Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 2020-07-01 | 2020-09-18 | 57 | 0 | 57 | 79 | 100% | 0.72152 | 1 | Completed
ER6378LT | W222 | W222.A27030 | HRA Fuel Handling Essential Safety Case | Define Project Control Structures (WBS/CBS/OBS/PBS) (FEEDS TO SUMMARY SCHEDULE) | 2020-07-01 | 2020-09-18 | 57 | 0 | 57 | 79 | 100% | 0.72152 | 1 | Completed
ER6650LT | W226 | W226.A27030 | HYA Fuel Handling Essential Safety Case | Define Project Control Structures (WBS/CBS/OBS/PBS) | 2020-07-01 | 2020-09-18 | 57 | 0 | 57 | 79 | 100% | 0.72152 | 1 | Completed
ER6650LT | W226 | W226.A27020 | HYA Fuel Handling Essential Safety Case | Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 2020-07-01 | 2020-09-18 | 57 | 0 | 57 | 79 | 100% | 0.72152 | 1 | Completed
ER6650LT | W226 | W226.A26940 | HYA Fuel Handling Essential Safety Case | Update Project Definition Document (PDD) | 2020-07-01 | 2020-09-21 | 1 | 0 | 57 | 82 | 100% | 0.012195 | 1 | Completed
ER6650LT | W226 | W226.A24450 | HYA Fuel Handling Essential Safety Case | Verify Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN & Issue for Technical Review | 2020-07-01 | 2020-07-02 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6371LT | W202 | W202.A2290 | HRA Reactors Shutdown Essential Safety Cases | Gas Chemistry Assessment Draft Report Verified by TSA | 2020-07-01 | 2020-07-06 | 15 | 0 | 3 | 5 | 100% | 3 | 1 | Completed
ER6371LT | W202 | W202.A2170 | HRA Reactors Shutdown Essential Safety Cases | Prepare Seismic Assessment of FPU within Reactor Report | 2020-07-01 | 2020-09-14 | 53 | 0 | 53 | 75 | 100% | 0.70667 | 1 | Completed
ER6371LT | W202 | W202.A2160 | HRA Reactors Shutdown Essential Safety Cases | Seismic Assessment of FPU within Reactor Report Summary | 2020-07-01 | 2020-11-20 | 92 | 0 | 101 | 142 | 100% | 0.64789 | 1 | Completed
ER6371LT | W202 | W202.A1990 | HRA Reactors Shutdown Essential Safety Cases | Thermal Analysis (FEAT) of FPU Fully Extended - Supplier mobilisation time | 2020-07-01 | 2020-07-02 | 10 | 0 | 2 | 1 | 100% | 10 | 1 | Completed
ER6371LT | W202 | W202.A2340 | HRA Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Station Documentation Update Strategy Report - Draft and issue RFS | 2020-07-01 | 2020-07-02 | 0 | 0 | 1 | 1 | 100% | 0 | 1 | Completed
ER6371LT | W202 | W202.A2400 | HRA Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Station Documentation Update Strategy Report - Supplier prepare and issue Offer | 2020-07-01 | 2020-07-02 | 0 | 0 | 1 | 1 | 100% | 0 | 1 | Completed
ER6371LT | W202 | W202.A2580 | HRA Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Station Documentation Update Strategy Report - Review Offer, prepare and issue CI | 2020-07-01 | 2020-07-02 | 0 | 0 | 1 | 1 | 100% | 0 | 1 | Completed
ER6371LT | W202 | W202.A2600 | HRA Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Station Documentation Update Strategy Report - Supplier mobilisation time | 2020-07-01 | 2020-07-02 | 0 | 0 | 1 | 1 | 100% | 0 | 1 | Completed
ER6371LT | W202 | W202.A2800 | HRA Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Station Documentation Update Strategy Report - Pre Job Brief | 2020-07-01 | 2020-07-02 | 0 | 0 | 1 | 1 | 100% | 0 | 1 | Completed
ER6371LT | W202 | W202.A3250 | HRA Reactors Shutdown Essential Safety Cases | Worker Dose Report Reviewed by EDF SQEP | 2020-07-01 | 2020-07-31 | 10 | 0 | 22 | 30 | 100% | 0.33333 | 1 | Completed
ER6661LT | W206 | W206.A2290 | HYA Reactors Shutdown Essential Safety Cases | Gas Chemistry Assessment Draft Report Verified by TSA | 2020-07-01 | 2020-07-06 | 15 | 0 | 3 | 5 | 100% | 3 | 1 | Completed
ER6661LT | W206 | W206.A2170 | HYA Reactors Shutdown Essential Safety Cases | Prepare Seismic Assessment of FPU within Reactor Report | 2020-07-01 | 2020-09-14 | 53 | 0 | 53 | 75 | 100% | 0.70667 | 1 | Completed
ER6661LT | W206 | W206.A2160 | HYA Reactors Shutdown Essential Safety Cases | Seismic Assessment of FPU within Reactor Report Summary | 2020-07-01 | 2020-11-20 | 92 | 0 | 101 | 142 | 100% | 0.64789 | 1 | Completed
ER6661LT | W206 | W206.A1990 | HYA Reactors Shutdown Essential Safety Cases | Thermal Analysis (FEAT) of FPU Fully Extended - Supplier mobilisation time | 2020-07-01 | 2020-07-02 | 10 | 0 | 2 | 1 | 100% | 10 | 1 | Completed
ER6661LT | W206 | W206.A2340 | HYA Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Station Documentation Update Strategy Report - Draft and issue RFS | 2020-07-01 | 2020-07-02 | 5 | 0 | 1 | 1 | 100% | 5 | 1 | Completed
ER6661LT | W206 | W206.A2400 | HYA Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Station Documentation Update Strategy Report - Supplier prepare and issue Offer | 2020-07-01 | 2020-07-02 | 10 | 0 | 1 | 1 | 100% | 10 | 1 | Completed
ER6661LT | W206 | W206.A2580 | HYA Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Station Documentation Update Strategy Report - Review Offer, prepare and issue CI | 2020-07-01 | 2020-07-02 | 5 | 0 | 1 | 1 | 100% | 5 | 1 | Completed
ER6661LT | W206 | W206.A2600 | HYA Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Station Documentation Update Strategy Report - Supplier mobilisation time | 2020-07-01 | 2020-07-02 | 10 | 0 | 1 | 1 | 100% | 10 | 1 | Completed
ER6661LT | W206 | W206.A2800 | HYA Reactors Shutdown Essential Safety Cases | (SCOPE REMOVED) - Station Documentation Update Strategy Report - Pre Job Brief | 2020-07-01 | 2020-07-02 | 1 | 0 | 1 | 1 | 100% | 1 | 1 | Completed
ER6661LT | W206 | W206.A3250 | HYA Reactors Shutdown Essential Safety Cases | Worker Dose Report Reviewed by EDF SQEP | 2020-07-01 | 2020-07-31 | 23 | 0 | 22 | 30 | 100% | 0.76667 | 1 | Completed
ER6661LT | W206 | W206.A2310 | HYA Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Base Faults and Hazards) Draft Report Verified by TSA - (HYA) | 2020-07-01 | 2020-07-14 | 10 | 0 | 9 | 13 | 100% | 0.76923 | 1 | Completed
ER6370LT | W201 | ER6370.A8610 | HNB Reactors Shutdown Essential Safety Cases | Containment Head Document - Resolution of verification comments | 2020-07-01 | 2020-08-05 | 13 | 0 | 26 | 35 | 100% | 0.37143 | 1 | Completed
ER6378LT | W222 | W222.A25940 | HRA Fuel Handling Essential Safety Case | Breached PVCW Assessment ##(Cost Summary)## (C5) | 2020-07-01 | 2020-09-18 | 57 | 0 | 57 | 79 | 100% | 0.72152 | 1 | Completed
ER6378LT | W222 | W222.A23030 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Breached PVCW Assessment EAN | 2020-07-01 | 2020-07-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1000 | HNB Reactors Shutdown Essential Safety Cases | 1 – Introduction - Summary | 2020-07-01 | 2020-07-27 | 19 | 0 | 19 | 26 | 100% | 0.73077 | 1 | Completed
ER6370LT | W201 | A1020 | HNB Reactors Shutdown Essential Safety Cases | 2 – Existing Safety Case - Summary | 2020-07-01 | 2020-07-28 | 20 | 0 | 20 | 27 | 100% | 0.74074 | 1 | Completed
ER6370LT | W201 | A1030 | HNB Reactors Shutdown Essential Safety Cases | 3 – Description of Essential Defuelling Process - Summary | 2020-07-01 | 2020-07-29 | 21 | 0 | 21 | 28 | 100% | 0.75 | 1 | Completed
ER6370LT | W201 | A1290 | HNB Reactors Shutdown Essential Safety Cases | Introduction - Early Draft | 2020-07-01 | 2020-07-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1340 | HNB Reactors Shutdown Essential Safety Cases | Existing Safety Case - Early Draft | 2020-07-01 | 2020-07-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1390 | HNB Reactors Shutdown Essential Safety Cases | Description of Essential Defuelling Process - Early Draft | 2020-07-01 | 2020-07-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23030 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Breached PVCW Assessment EAN | 2020-07-01 | 2020-07-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25940 | HYA Fuel Handling Essential Safety Case | Breached PVCW Assessment ##(Cost Summary)## (C5) | 2020-07-01 | 2020-09-18 | 57 | 0 | 57 | 79 | 100% | 0.72152 | 1 | Completed
ER6370LT | W201 | ER6370.A4320 | HNB Reactors Shutdown Essential Safety Cases | Address Comments from EDF's Review of Core Cooling Compliance Summary Draft Report | 2020-07-02 | 2020-07-08 | 8 | 0 | 4 | 6 | 100% | 1.3333 | 1 | Completed
ER6370LT | W201 | A1100 | HNB Reactors Shutdown Essential Safety Cases | 5.4 Claim 4 - Summary | 2020-07-02 | 2020-09-25 | 44 | 0 | 61 | 85 | 100% | 0.51765 | 1 | Completed
ER6370LT | W201 | A1450 | HNB Reactors Shutdown Essential Safety Cases | Resolution of SC Shortfalls and Key NS Issues - CO and co-author review | 2020-07-02 | 2020-07-02 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1500 | HNB Reactors Shutdown Essential Safety Cases | Description of Updated SC - CO and co-author review | 2020-07-02 | 2020-07-02 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1550 | HNB Reactors Shutdown Essential Safety Cases | Claim 0 - CO and co-author review | 2020-07-02 | 2020-07-02 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1600 | HNB Reactors Shutdown Essential Safety Cases | Claim 1 - CO and co-author review | 2020-07-02 | 2020-07-02 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1650 | HNB Reactors Shutdown Essential Safety Cases | Claim 2 - CO and co-author review | 2020-07-02 | 2020-07-02 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1750 | HNB Reactors Shutdown Essential Safety Cases | Claim 4 - CO and co-author review | 2020-07-02 | 2020-07-02 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A23040 | HRA Fuel Handling Essential Safety Case | Draft Breached PVCW Assessmen EAN | 2020-07-02 | 2020-09-07 | 30 | 0 | 47 | 67 | 100% | 0.44776 | 1 | Completed
ER6370LT | W201 | A1300 | HNB Reactors Shutdown Essential Safety Cases | Introduction - CO and co-author review | 2020-07-02 | 2020-07-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1350 | HNB Reactors Shutdown Essential Safety Cases | Existing Safety Case - CO and co-author review | 2020-07-02 | 2020-07-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1400 | HNB Reactors Shutdown Essential Safety Cases | Description of Essential Defuelling Process - CO and co-author review | 2020-07-02 | 2020-07-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23040 | HYA Fuel Handling Essential Safety Case | Draft Breached PVCW Assessmen EAN | 2020-07-02 | 2020-09-07 | 30 | 0 | 47 | 67 | 100% | 0.44776 | 1 | Completed
ER6370LT | W201 | ER6370.A1880 | HNB Reactors Shutdown Essential Safety Cases | Gate C IRM Paper Submission | 2020-07-03 | 2020-07-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2080 | HRA Reactors Shutdown Essential Safety Cases | Thermal Analysis (FEAT) of FPU Fully Extended - Pre Job Brief | 2020-07-03 | 2020-07-06 | 1 | 0 | 1 | 3 | 100% | 0.33333 | 1 | Completed
ER6370LT | W201 | A1460 | HNB Reactors Shutdown Essential Safety Cases | Resolution of SC Shortfalls and Key NS Issues - Mature Draft | 2020-07-03 | 2020-07-03 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1510 | HNB Reactors Shutdown Essential Safety Cases | Description of Updated SC - Mature Draft | 2020-07-03 | 2020-07-03 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1560 | HNB Reactors Shutdown Essential Safety Cases | Claim 0 - Mature Draft | 2020-07-03 | 2020-07-03 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1610 | HNB Reactors Shutdown Essential Safety Cases | Claim 1 - Mature Draft | 2020-07-03 | 2020-07-03 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1660 | HNB Reactors Shutdown Essential Safety Cases | Claim 2 - Mature Draft | 2020-07-03 | 2020-07-03 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24460 | HRA Fuel Handling Essential Safety Case | Technical Review of Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN | 2020-07-03 | 2020-07-06 | 2 | 0 | 2 | 3 | 100% | 0.66667 | 1 | Completed
ER6370LT | W201 | A1310 | HNB Reactors Shutdown Essential Safety Cases | Introduction - Mature Draft | 2020-07-03 | 2020-07-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1360 | HNB Reactors Shutdown Essential Safety Cases | Existing Safety Case - Mature Draft | 2020-07-03 | 2020-07-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1410 | HNB Reactors Shutdown Essential Safety Cases | Description of Essential Defuelling Process - Mature Draft | 2020-07-03 | 2020-07-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24460 | HYA Fuel Handling Essential Safety Case | Technical Review of Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN | 2020-07-03 | 2020-07-06 | 2 | 0 | 2 | 3 | 100% | 0.66667 | 1 | Completed
ER6371LT | W202 | W202.A2390 | HRA Reactors Shutdown Essential Safety Cases | Verified Gas Chemistry Assessment Draft Report Issued to EDF for Technical Review. | 2020-07-06 | 2020-07-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2080 | HYA Reactors Shutdown Essential Safety Cases | Thermal Analysis (FEAT) of FPU Fully Extended - Pre Job Brief | 2020-07-06 | 2020-07-06 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26330 | HRA Fuel Handling Essential Safety Case | The Grab Extend FPU Ledge/ Fault and Associated Protection Needs ##(Cost Summary)## (C2) (NEW) | 2020-07-06 | 2021-06-11 | 235 | 0 | 236 | 340 | 100% | 0.69118 | 1 | Completed
ER6378LT | W222 | W222.A26320 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for The Grab Extend FPU Ledge/ Fault and Associated Protection Needs EAN | 2020-07-06 | 2020-07-06 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1470 | HNB Reactors Shutdown Essential Safety Cases | Resolution of SC Shortfalls and Key NS Issues - Peer Review | 2020-07-06 | 2020-07-24 | 15 | 0 | 15 | 18 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | A1520 | HNB Reactors Shutdown Essential Safety Cases | Description of Updated SC - Peer Review | 2020-07-06 | 2020-07-27 | 15 | 0 | 16 | 21 | 100% | 0.71429 | 1 | Completed
ER6650LT | W226 | W226.A26320 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for The Grab Extend FPU Ledge/ Fault and Associated Protection Needs EAN | 2020-07-06 | 2020-07-06 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26330 | HYA Fuel Handling Essential Safety Case | The Grab Extend FPU Ledge/ Fault and Associated Protection Needs ##(Cost Summary)## (C2) (NEW) | 2020-07-06 | 2021-06-11 | 235 | 0 | 236 | 340 | 100% | 0.69118 | 1 | Completed
ER6370LT | W201 | A1320 | HNB Reactors Shutdown Essential Safety Cases | Introduction - Peer Review | 2020-07-06 | 2020-07-24 | 15 | 0 | 15 | 18 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | A1370 | HNB Reactors Shutdown Essential Safety Cases | Existing Safety Case - Peer Review | 2020-07-06 | 2020-07-24 | 1 | 0 | 15 | 18 | 100% | 0.055556 | 1 | Completed
ER6370LT | W201 | A1420 | HNB Reactors Shutdown Essential Safety Cases | Description of Essential Defuelling Process - Peer Review | 2020-07-06 | 2020-07-24 | 1 | 0 | 15 | 18 | 100% | 0.055556 | 1 | Completed
ER6378LT | W222 | W222.A26340 | HRA Fuel Handling Essential Safety Case | Draft The Grab Extend FPU Ledge/ Fault and Associated Protection Needs EAN | 2020-07-07 | 2021-02-12 | 75 | 0 | 155 | 220 | 100% | 0.34091 | 1 | Completed
ER6378LT | W222 | W222.A25890 | HRA Fuel Handling Essential Safety Case | Grab Engagement for Low Burn-up Fuel##(Cost Summary)## (NEW) (C3) | 2020-07-07 | 2020-11-10 | 90 | 0 | 90 | 126 | 100% | 0.71429 | 1 | Completed
ER6378LT | W222 | W222.A22820 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Grab Engagement for Low Burn-up Fuel EAN | 2020-07-07 | 2020-07-07 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A22820 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Grab Engagement for Low Burn-up Fuel EAN | 2020-07-07 | 2020-07-07 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25890 | HYA Fuel Handling Essential Safety Case | Grab Engagement for Low Burn-up Fuel##(Cost Summary)## (NEW) (C3) | 2020-07-07 | 2020-11-10 | 90 | 0 | 90 | 126 | 100% | 0.71429 | 1 | Completed
ER6650LT | W226 | W226.A26340 | HYA Fuel Handling Essential Safety Case | Draft The Grab Extend FPU Ledge/ Fault and Associated Protection Needs EAN | 2020-07-07 | 2021-02-12 | 75 | 0 | 155 | 220 | 100% | 0.34091 | 1 | Completed
ER6378LT | W222 | W222.A24470 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN | 2020-07-07 | 2020-07-08 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6650LT | W226 | W226.A24470 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN | 2020-07-07 | 2020-07-08 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | ER6370.A4330 | HNB Reactors Shutdown Essential Safety Cases | Issue Final Core Cooling Compliance Summary Report | 2020-07-08 | 2020-07-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25970 | HRA Fuel Handling Essential Safety Case | Update Core Support Plate Properties Methodology & Toughness Properties ##(Cost Summary)## (C5) (NEW) | 2020-07-08 | 2021-05-04 | 208 | 0 | 208 | 300 | 100% | 0.69333 | 1 | Completed
ER6378LT | W222 | W222.A23310 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Update Core Support Plate Properties Methodology & Toughness Properties EAN | 2020-07-08 | 2020-07-08 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A22830 | HRA Fuel Handling Essential Safety Case | Draft Grab Engagement for Low Burn-up Fuel EAN | 2020-07-08 | 2020-08-07 | 23 | 0 | 22 | 30 | 100% | 0.76667 | 1 | Completed
ER6650LT | W226 | W226.A22830 | HYA Fuel Handling Essential Safety Case | Draft Grab Engagement for Low Burn-up Fuel EAN | 2020-07-08 | 2020-08-07 | 23 | 0 | 22 | 30 | 100% | 0.76667 | 1 | Completed
ER6650LT | W226 | W226.A23310 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Update Core Support Plate Properties Methodology & Toughness Properties EAN | 2020-07-08 | 2020-07-08 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25970 | HYA Fuel Handling Essential Safety Case | Update Core Support Plate Properties Methodology & Toughness Properties ##(Cost Summary)## (C5) (NEW) | 2020-07-08 | 2021-05-04 | 208 | 0 | 208 | 300 | 100% | 0.69333 | 1 | Completed
ER6370LT | W201 | ER6370.A4340 | HNB Reactors Shutdown Essential Safety Cases | Core Cooling Compliance Summary Report Completed and uploaded to CDMS | 2020-07-09 | 2020-07-14 | 3 | 0 | 3 | 5 | 100% | 0.6 | 1 | Completed
ER6661LT | W206 | W206.A2190 | HYA Reactors Shutdown Essential Safety Cases | TSA Address Comments on HYA Defuelling Case against the NSPs Draft Report | 2020-07-09 | 2020-08-14 | 27 | 0 | 26 | 36 | 100% | 0.75 | 1 | Completed
ER6378LT | W222 | W222.A24480 | HRA Fuel Handling Essential Safety Case | Complete Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN to CDMS | 2020-07-09 | 2020-07-10 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6650LT | W226 | W226.A24480 | HYA Fuel Handling Essential Safety Case | Complete Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN to CDMS | 2020-07-09 | 2020-07-10 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6378LT | W222 | W222.A24490 | HRA Fuel Handling Essential Safety Case | Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN Available | 2020-07-10 | 2020-07-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24490 | HYA Fuel Handling Essential Safety Case | Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN Available | 2020-07-10 | 2020-07-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1910 | HRA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HRA - TSA Prepare Draft Report | 2020-07-13 | 2020-07-14 | 2 | 0 | 1 | 1 | 100% | 2 | 1 | Completed
ER6371LT | W202 | W202.A1900 | HRA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HRA - Summary | 2020-07-13 | 2021-05-28 | 223 | 0 | 223 | 319 | 100% | 0.69906 | 1 | Completed
ER6370LT | W201 | A1170 | HNB Reactors Shutdown Essential Safety Cases | 11 – NSC Request for Consideration and Advice - Summary | 2020-07-13 | 2020-10-02 | 49 | 0 | 59 | 81 | 100% | 0.60494 | 1 | Completed
ER6370LT | W201 | A1180 | HNB Reactors Shutdown Essential Safety Cases | Appendix – Description of Existing Safety Case - Summary | 2020-07-13 | 2020-10-09 | 59 | 0 | 64 | 88 | 100% | 0.67045 | 1 | Completed
ER6370LT | W201 | A1270 | HNB Reactors Shutdown Essential Safety Cases | Appendix F – Previous Advice from NSC - Summary | 2020-07-13 | 2020-10-09 | 54 | 0 | 63 | 88 | 100% | 0.61364 | 1 | Completed
ER6370LT | W201 | A1990 | HNB Reactors Shutdown Essential Safety Cases | INSA - Early Draft | 2020-07-13 | 2020-07-13 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A2000 | HNB Reactors Shutdown Essential Safety Cases | INSA - CO and co-author review | 2020-07-13 | 2020-07-13 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A2010 | HNB Reactors Shutdown Essential Safety Cases | INSA - Mature Draft | 2020-07-13 | 2020-07-13 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A2090 | HNB Reactors Shutdown Essential Safety Cases | NSC Request for Consideration and Advice - Early Draft | 2020-07-13 | 2020-07-13 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A2100 | HNB Reactors Shutdown Essential Safety Cases | NSC Request for Consideration and Advice - CO and co-author review | 2020-07-13 | 2020-07-13 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A2110 | HNB Reactors Shutdown Essential Safety Cases | NSC Request for Consideration and Advice - Mature Draft | 2020-07-13 | 2020-07-13 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A2140 | HNB Reactors Shutdown Essential Safety Cases | Appendix – Description of Existing Safety Case - Early Draft | 2020-07-13 | 2020-07-13 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A2640 | HNB Reactors Shutdown Essential Safety Cases | Appendix F – Previous Advice from NSC - Early Draft | 2020-07-13 | 2020-07-13 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A2650 | HNB Reactors Shutdown Essential Safety Cases | Appendix F – Previous Advice from NSC - CO and co-author review | 2020-07-13 | 2020-07-13 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A2660 | HNB Reactors Shutdown Essential Safety Cases | Appendix F – Previous Advice from NSC - Mature Draft | 2020-07-13 | 2020-07-13 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1930 | HRA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HRA - Draft Report Reviewed by EDF SQEP | 2020-07-13 | 2020-07-14 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6371LT | W202 | W202.A2050 | HRA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HRA - TSA Address Comments on Draft Report | 2020-07-13 | 2020-07-14 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6371LT | W202 | W202.A2180 | HRA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HRA - Final Report Completed and uploaded to CDMS | 2020-07-13 | 2020-07-14 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6661LT | W206 | W206.A1910 | HYA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HYA - TSA Prepare Draft Report | 2020-07-13 | 2020-07-14 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6661LT | W206 | W206.A1930 | HYA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HYA - Draft Report Reviewed by EDF SQEP | 2020-07-13 | 2020-07-14 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6661LT | W206 | W206.A2050 | HYA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HYA - TSA Address Comments on Draft Report | 2020-07-13 | 2020-07-14 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6661LT | W206 | W206.A2180 | HYA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HYA - Final Report Completed and uploaded to CDMS | 2020-07-13 | 2020-07-14 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6661LT | W206 | W206.A1900 | HYA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HYA - Summary | 2020-07-13 | 2021-05-28 | 223 | 0 | 222 | 319 | 100% | 0.69906 | 1 | Completed
ER6370LT | W201 | ER6370.A4350 | HNB Reactors Shutdown Essential Safety Cases | Core Cooling Compliance Summary Report Completed | 2020-07-14 | 2020-07-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2310 | HRA Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Base Faults and Hazards) Draft Report Verified by TSA - (HRA) | 2020-07-14 | 2020-07-31 | 10 | 0 | 13 | 17 | 100% | 0.58824 | 1 | Completed
ER6370LT | W201 | ER6370.P1230 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Head Document (PVCW) - Second Round Comments Received | 2020-07-14 | 2020-07-22 | 5 | 0 | 7 | 8 | 100% | 0.625 | 1 | Completed
ER6372LT | W203 | W203.A1030 | HNB Enhanced Defuelling Safety Cases | Prepare Schedule | 2020-07-14 | 2020-08-21 | 29 | 0 | 29 | 38 | 100% | 0.76316 | 1 | Completed
ER6372LT | W203 | W203.A1040 | HNB Enhanced Defuelling Safety Cases | Prepare Cost Estimates +/- 10% B-C & +/- 30% Lifecycle | 2020-07-14 | 2020-08-21 | 29 | 0 | 29 | 38 | 100% | 0.76316 | 1 | Completed
ER6371LT | W202 | W202.A1920 | HRA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HRA - TSA Issue Draft Report to EDF for Review. | 2020-07-14 | 2020-07-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2150 | HRA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HRA - TSA Issue Final Report | 2020-07-14 | 2020-07-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2270 | HRA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HRA - Report Completed | 2020-07-14 | 2020-07-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2280 | HRA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HRA - Discovery MS Strategy Agreed | 2020-07-14 | 2020-07-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1920 | HYA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HYA - TSA Issue Draft Report to EDF for Review. | 2020-07-14 | 2020-07-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2150 | HYA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HYA - TSA Issue Final Report | 2020-07-14 | 2020-07-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2270 | HYA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HYA - Report Completed | 2020-07-14 | 2020-07-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2280 | HYA Reactors Shutdown Essential Safety Cases | Dropped FPU Strategy Development HYA - Discovery MS Strategy Agreed | 2020-07-14 | 2020-07-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2370 | HYA Reactors Shutdown Essential Safety Cases | Verified Fault Schedule Review (Plant Base Faults and Hazards) Draft Report Issued to EDF for Technical Review. - (HYA) | 2020-07-14 | 2020-07-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2380 | HYA Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Base Faults and Hazards) Draft Report Technically Reviewed by EDF SQEP - (HYA) | 2020-07-15 | 2020-07-28 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6370LT | W201 | ER6370.A1860 | HNB Reactors Shutdown Essential Safety Cases | Gate C IRM Paper Approval - HNB | 2020-07-16 | 2020-07-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1870 | HNB Reactors Shutdown Essential Safety Cases | Hold IRM | 2020-07-16 | 2020-07-16 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13060 | HNB Reactors Shutdown Essential Safety Cases | Gate C IRM Paper Approval (HNB) | 2020-07-16 | 2020-07-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2110 | HRA Reactors Shutdown Essential Safety Cases | Prepare Thermal Analysis (FEAT) of FPU Fully Extended Report | 2020-07-16 | 2020-08-07 | 40 | 0 | 16 | 22 | 100% | 1.8182 | 1 | Completed
ER6371LT | W202 | W202.A2100 | HRA Reactors Shutdown Essential Safety Cases | Thermal Analysis (FEAT) of FPU Fully Extended Report Summary | 2020-07-16 | 2021-02-12 | 148 | 0 | 148 | 211 | 100% | 0.70142 | 1 | Completed
ER6661LT | W206 | W206.A2130 | HYA Reactors Shutdown Essential Safety Cases | Prepare Pressure Boundary Seals Draft Report | 2020-07-16 | 2020-07-17 | 30 | 0 | 1 | 1 | 100% | 30 | 1 | Completed
ER6661LT | W206 | W206.A2110 | HYA Reactors Shutdown Essential Safety Cases | Prepare Thermal Analysis (FEAT) of FPU Fully Extended Report | 2020-07-16 | 2020-08-07 | 40 | 0 | 16 | 22 | 100% | 1.8182 | 1 | Completed
ER6661LT | W206 | W206.A2100 | HYA Reactors Shutdown Essential Safety Cases | Thermal Analysis (FEAT) of FPU Fully Extended Report Summary | 2020-07-16 | 2021-02-12 | 148 | 0 | 148 | 211 | 100% | 0.70142 | 1 | Completed
ER6370LT | W201 | ER6370.A4220 | HNB Reactors Shutdown Essential Safety Cases | Core Cooling Head Document Draft Report - Comments returned from all verifiers | 2020-07-17 | 2020-07-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2510 | HRA Reactors Shutdown Essential Safety Cases | SC - Safety Case development - tech oversight Cat 1 - Claim 1 - HRA - B-C - STN | 2020-07-17 | 2021-09-01 | 335 | 0 | 284 | 411 | 100% | 0.81509 | 1 | Completed
ER6371LT | W202 | W202.A2530 | HRA Reactors Shutdown Essential Safety Cases | Shutdown Margin Workshop - Identify / Address any Shortfalls | 2020-07-17 | 2020-07-20 | 2 | 0 | 2 | 3 | 100% | 0.66667 | 1 | Completed
ER6371LT | W202 | W202.A2520 | HRA Reactors Shutdown Essential Safety Cases | Shutdown Margin Workshop Summary | 2020-07-17 | 2021-08-20 | 118 | 0 | 277 | 399 | 100% | 0.29574 | 1 | Completed
ER6371LT | W202 | W202.A2500 | HRA Reactors Shutdown Essential Safety Cases | Safety Case Dev Cat 1 - Station Oversight of tech work & SC - HRA - B-C - T&S NS | 2020-07-17 | 2021-09-01 | 335 | 0 | 284 | 411 | 100% | 0.81509 | 1 | Completed
ER6661LT | W206 | W206.A2510 | HYA Reactors Shutdown Essential Safety Cases | SC - Safety Case development - tech oversight Cat 1 - Claim 1 - HYA - B-C - STN | 2020-07-17 | 2021-09-01 | 335 | 0 | 284 | 411 | 100% | 0.81509 | 1 | Completed
ER6661LT | W206 | W206.A2530 | HYA Reactors Shutdown Essential Safety Cases | Shutdown Margin Workshop - Identify / Address any Shortfalls | 2020-07-17 | 2020-07-20 | 2 | 0 | 1 | 3 | 100% | 0.66667 | 1 | Completed
ER6661LT | W206 | W206.A2520 | HYA Reactors Shutdown Essential Safety Cases | Shutdown Margin Workshop Summary | 2020-07-17 | 2021-08-20 | 118 | 0 | 277 | 399 | 100% | 0.29574 | 1 | Completed
ER6661LT | W206 | W206.A2500 | HYA Reactors Shutdown Essential Safety Cases | Safety Case Dev Cat 1 - Station Oversight of tech work & SC - HYA - B-C - T&S NS | 2020-07-17 | 2021-09-01 | 335 | 0 | 284 | 411 | 100% | 0.81509 | 1 | Completed
ER6370LT | W201 | ER6370.A7110 | HNB Reactors Shutdown Essential Safety Cases | Boilers and Gas Circulator Performance - EDF Internal Verification of Reworked Draft EAN Complete | 2020-07-17 | 2020-07-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24420 | HRA Fuel Handling Essential Safety Case | Fuel Route Operational Sequence/Process for Defuelling EAN Available (REV 000) | 2020-07-20 | 2020-07-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24420 | HYA Fuel Handling Essential Safety Case | Fuel Route Operational Sequence/Process for Defuelling EAN Available (REV 000) | 2020-07-20 | 2020-07-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4230 | HNB Reactors Shutdown Essential Safety Cases | Core Cooling Head Document Draft Report - Lead verifier collation of comments | 2020-07-20 | 2020-07-27 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6370LT | W201 | ER6370.A17540 | HNB Reactors Shutdown Essential Safety Cases | Boilers and Gas Circulator Performance - Verified Reworked Draft EAN Completed and uploaded to CDMS | 2020-07-20 | 2020-07-28 | 5 | 0 | 6 | 8 | 100% | 0.625 | 1 | Completed
ER6371LT | W202 | W202.A2570 | HRA Reactors Shutdown Essential Safety Cases | Shutdown Margin Workshop - Production of Meeting Notes | 2020-07-21 | 2020-09-25 | 14 | 0 | 47 | 66 | 100% | 0.21212 | 1 | Completed
ER6661LT | W206 | W206.A2570 | HYA Reactors Shutdown Essential Safety Cases | Shutdown Margin Workshop - Production of Meeting Notes | 2020-07-21 | 2020-09-25 | 14 | 0 | 47 | 66 | 100% | 0.21212 | 1 | Completed
ER6371LT | W202 | W202.A2410 | HRA Reactors Shutdown Essential Safety Cases | Gas Chemistry Assessment Draft Report Technically Reviewed by EDF SQEP | 2020-07-22 | 2020-08-28 | 15 | 0 | 27 | 37 | 100% | 0.40541 | 1 | Completed
ER6661LT | W206 | W206.A2410 | HYA Reactors Shutdown Essential Safety Cases | Gas Chemistry Assessment Draft Report Technically Reviewed by EDF SQEP | 2020-07-22 | 2020-08-28 | 15 | 0 | 27 | 37 | 100% | 0.40541 | 1 | Completed
ER6370LT | W201 | ER6370.P1240 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Head Document (PVCW) - Hold Point to Re-confirm Delivery Dates | 2020-07-23 | 2020-07-23 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.P1250 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Head Document (PVCW) - Author Address Second Round Comments and Re-circulate Draft | 2020-07-24 | 2020-07-29 | 4 | 0 | 4 | 5 | 100% | 0.8 | 1 | Completed
ER6370LT | W201 | A1090 | HNB Reactors Shutdown Essential Safety Cases | 5.3 Claim 3 - Summary | 2020-07-27 | 2020-10-09 | 54 | 0 | 54 | 74 | 100% | 0.72973 | 1 | Completed
ER6370LT | W201 | A1690 | HNB Reactors Shutdown Essential Safety Cases | Claim 3 - Early Draft | 2020-07-27 | 2020-09-25 | 37 | 0 | 44 | 60 | 100% | 0.61667 | 1 | Completed
ER6370LT | W201 | A1110 | HNB Reactors Shutdown Essential Safety Cases | 5.5 Claim 5 - Summary | 2020-07-27 | 2020-10-07 | 49 | 0 | 52 | 72 | 100% | 0.68056 | 1 | Completed
ER6370LT | W201 | A1330 | HNB Reactors Shutdown Essential Safety Cases | Introduction - Draft Complete | 2020-07-27 | 2020-07-27 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1570 | HNB Reactors Shutdown Essential Safety Cases | Claim 0 - Peer Review | 2020-07-27 | 2020-08-06 | 2 | 0 | 8 | 10 | 100% | 0.2 | 1 | Completed
ER6370LT | W201 | A1740 | HNB Reactors Shutdown Essential Safety Cases | Claim 4 - Early Draft | 2020-07-27 | 2020-07-27 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1790 | HNB Reactors Shutdown Essential Safety Cases | Claim 5 - Early Draft | 2020-07-27 | 2020-08-26 | 15 | 0 | 22 | 30 | 100% | 0.5 | 1 | Completed
ER6370LT | W201 | ER6370.A1480 | HNB Reactors Shutdown Essential Safety Cases | All supporting references Approved and Issued (HNB) | 2020-07-28 | 2020-07-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13040 | HNB Reactors Shutdown Essential Safety Cases | All Key Supporting Technical References Completed for Hunterston Essential Safety Case (HNB) | 2020-07-28 | 2020-07-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16330 | HNB Reactors Shutdown Essential Safety Cases | All Supporting Technical References Complete - Claim 4 Configuration | 2020-07-28 | 2020-07-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A17550 | HNB Reactors Shutdown Essential Safety Cases | Boilers and Gas Circulator Performance - Reworked Draft EAN Completed | 2020-07-28 | 2020-07-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1640 | HRA Reactors Shutdown Essential Safety Cases | HPB / HNB All Key References Produced | 2020-07-28 | 2020-07-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1640 | HYA Reactors Shutdown Essential Safety Cases | HPB / HNB All Key References Produced | 2020-07-28 | 2020-07-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1380 | HNB Reactors Shutdown Essential Safety Cases | Existing Safety Case - Draft Complete | 2020-07-28 | 2020-07-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2560 | HYA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Fault Schedule Review (Plant Base Faults and Hazards) Draft Report - (HYA) | 2020-07-29 | 2020-08-26 | 10 | 0 | 20 | 28 | 100% | 0.35714 | 1 | Completed
ER6370LT | W201 | A1430 | HNB Reactors Shutdown Essential Safety Cases | Description of Essential Defuelling Process - Draft Complete | 2020-07-29 | 2020-07-29 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1760 | HNB Reactors Shutdown Essential Safety Cases | Claim 4 - Mature Draft | 2020-07-29 | 2020-08-06 | 1 | 0 | 6 | 8 | 100% | 0.125 | 1 | Completed
ER6370LT | W201 | ER6370.A4250 | HNB Reactors Shutdown Essential Safety Cases | Core Cooling Head Document Report - HOLD POINT - REVIEW COMMENTS AND RE-FORECAST | 2020-07-29 | 2020-07-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2190 | HRA Reactors Shutdown Essential Safety Cases | TSA Address Comments on HRA Defuelling Case against the NSPs Draft Report | 2020-07-30 | 2020-08-14 | 17 | 0 | 11 | 15 | 100% | 1.1333 | 1 | Completed
ER6370LT | W201 | ER6370.A4290 | HNB Reactors Shutdown Essential Safety Cases | Core Cooling Head Document Draft Report - Author respond to comments and update draft | 2020-07-30 | 2020-08-20 | 9 | 0 | 15 | 21 | 100% | 0.42857 | 1 | Completed
ER6370LT | W201 | ER6370.P17110 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Head Document (PVCW) - Third Round Comments Received | 2020-07-30 | 2020-07-30 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1480 | HNB Reactors Shutdown Essential Safety Cases | Resolution of SC Shortfalls and Key NS Issues - Draft Complete | 2020-07-30 | 2020-07-30 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2390 | HYA Reactors Shutdown Essential Safety Cases | Verified Gas Chemistry Assessment Draft Report Issued to EDF for Technical Review. | 2020-07-31 | 2020-07-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.P1260 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Head Document (PVCW) - Verifiers Sign-Off and Produce Verification Statement | 2020-07-31 | 2020-08-26 | 5 | 0 | 18 | 26 | 100% | 0.19231 | 1 | Completed
ER6371LT | W202 | W202.A2370 | HRA Reactors Shutdown Essential Safety Cases | Verified Fault Schedule Review (Plant Base Faults and Hazards) Draft Report Issued to EDF for Technical Review. - (HRA) | 2020-07-31 | 2020-07-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25750 | HRA Fuel Handling Essential Safety Case | Management Strategy for Pond Water Treatment Arisings ##(Cost Summary)## ### (C6) | 2020-08-03 | 2021-03-05 | 131 | 0 | 151 | 214 | 100% | 0.61215 | 1 | Completed
ER6378LT | W222 | W222.A25650 | HRA Fuel Handling Essential Safety Case | Defuelling Cooling and Match Analysis ##(Cost Summary)## ### (C4) | 2020-08-03 | 2021-03-16 | 122 | 0 | 158 | 225 | 100% | 0.54222 | 1 | Completed
ER6378LT | W222 | W222.A8210 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Defuelling Cooling and Match Analysis (Task FIle Note) | 2020-08-03 | 2020-08-03 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A12500 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Management Strategy for Pond Water Treatment Arisings EAN | 2020-08-03 | 2020-08-03 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1770 | HNB Reactors Shutdown Essential Safety Cases | Claim 4 - Peer Review 1 | 2020-08-03 | 2020-08-31 | 2 | 0 | 20 | 28 | 100% | 0.071429 | 1 | Completed
ER6370LT | W201 | A2740 | HNB Reactors Shutdown Essential Safety Cases | Claim 0 - Peer Review | 2020-08-03 | 2020-08-06 | 1 | 0 | 3 | 3 | 100% | 0.33333 | 1 | Completed
ER6650LT | W226 | W226.A12500 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Management Strategy for Pond Water Treatment Arisings EAN | 2020-08-03 | 2020-08-03 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A8210 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Defuelling Cooling and Match Analysis (Task FIle Note) | 2020-08-03 | 2020-08-03 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25650 | HYA Fuel Handling Essential Safety Case | Defuelling Cooling and Match Analysis ##(Cost Summary)## ### (C4) | 2020-08-03 | 2021-03-16 | 122 | 0 | 158 | 225 | 100% | 0.54222 | 1 | Completed
ER6650LT | W226 | W226.A25750 | HYA Fuel Handling Essential Safety Case | Management Strategy for Pond Water Treatment Arisings ##(Cost Summary)## ### (C6) | 2020-08-03 | 2021-03-05 | 131 | 0 | 151 | 214 | 100% | 0.61215 | 1 | Completed
ER6371LT | W202 | W202.A2350 | HRA Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals Draft Report Verified by TSA | 2020-08-03 | 2020-08-28 | 20 | 0 | 20 | 25 | 100% | 0.8 | 1 | Completed
ER6371LT | W202 | W202.A2090 | HRA Reactors Shutdown Essential Safety Cases | HF - Oversight of Work / HF Risk / HFIP - Supplier mobilisation time | 2020-08-03 | 2020-08-27 | 19 | 0 | 19 | 24 | 100% | 0.79167 | 1 | Completed
ER6371LT | W202 | W202.A2380 | HRA Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Base Faults and Hazards) Draft Report Technically Reviewed by EDF SQEP - (HRA) | 2020-08-03 | 2020-08-28 | 10 | 0 | 19 | 25 | 100% | 0.4 | 1 | Completed
ER6661LT | W206 | W206.A2090 | HYA Reactors Shutdown Essential Safety Cases | HF - Oversight of Work / HF Risk / HFIP - Supplier mobilisation time | 2020-08-03 | 2020-08-27 | 19 | 0 | 19 | 24 | 100% | 0.79167 | 1 | Completed
ER6370LT | W201 | ER6370.A8620 | HNB Reactors Shutdown Essential Safety Cases | Containment Head Document - Provision of verification statement | 2020-08-03 | 2020-09-11 | 3 | 0 | 29 | 39 | 100% | 0.076923 | 1 | Completed
ER6370LT | W201 | A1530 | HNB Reactors Shutdown Essential Safety Cases | Description of Updated SC - Draft Complete | 2020-08-03 | 2020-08-05 | 1 | 0 | 2 | 2 | 100% | 0.5 | 1 | Completed
ER6378LT | W222 | W222.A25640 | HRA Fuel Handling Essential Safety Case | Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment ##(Cost Summary)## ### (C3) | 2020-08-04 | 2021-05-28 | 212 | 0 | 207 | 297 | 100% | 0.7138 | 1 | Completed
ER6378LT | W222 | W222.A8220 | HRA Fuel Handling Essential Safety Case | Draft Defuelling Cooling and Match Analysis (Task FIle Note) | 2020-08-04 | 2020-08-28 | 5 | 0 | 18 | 24 | 100% | 0.20833 | 1 | Completed
ER6378LT | W222 | W222.A8990 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN | 2020-08-04 | 2020-08-04 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A12510 | HRA Fuel Handling Essential Safety Case | Draft Management Strategy for Pond Water Treatment Arisings EAN | 2020-08-04 | 2020-11-30 | 28 | 0 | 83 | 118 | 100% | 0.23729 | 1 | Completed
ER6370LT | W201 | A1580 | HNB Reactors Shutdown Essential Safety Cases | Claim 0 - Draft Complete | 2020-08-04 | 2020-08-14 | 2 | 0 | 9 | 10 | 100% | 0.2 | 1 | Completed
ER6650LT | W226 | W226.A12510 | HYA Fuel Handling Essential Safety Case | Draft Management Strategy for Pond Water Treatment Arisings EAN | 2020-08-04 | 2020-11-30 | 28 | 0 | 83 | 118 | 100% | 0.23729 | 1 | Completed
ER6650LT | W226 | W226.A8990 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN | 2020-08-04 | 2020-08-04 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A8220 | HYA Fuel Handling Essential Safety Case | Draft Defuelling Cooling and Match Analysis (Task FIle Note) | 2020-08-04 | 2020-08-28 | 10 | 0 | 18 | 24 | 100% | 0.41667 | 1 | Completed
ER6650LT | W226 | W226.A25640 | HYA Fuel Handling Essential Safety Case | Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment ##(Cost Summary)## ### (C3) | 2020-08-04 | 2021-05-28 | 217 | 0 | 207 | 297 | 100% | 0.73064 | 1 | Completed
ER6370LT | W201 | A1620 | HNB Reactors Shutdown Essential Safety Cases | Claim 1 - Peer Review | 2020-08-04 | 2020-08-06 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6370LT | W201 | A1630 | HNB Reactors Shutdown Essential Safety Cases | Claim 1 - Draft Complete | 2020-08-05 | 2020-08-06 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6371LT | W202 | W202.A2450 | HRA Reactors Shutdown Essential Safety Cases | Issue Thermal Analysis (FEAT) of FPU Fully Extended Report to EDF Review. | 2020-08-07 | 2020-08-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2450 | HYA Reactors Shutdown Essential Safety Cases | Issue Thermal Analysis (FEAT) of FPU Fully Extended Report to EDF Review. | 2020-08-07 | 2020-08-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A9000 | HRA Fuel Handling Essential Safety Case | Draft Impact on Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN | 2020-08-07 | 2021-04-20 | 65 | 0 | 177 | 256 | 100% | 0.25391 | 1 | Completed
ER6650LT | W226 | W226.A9000 | HYA Fuel Handling Essential Safety Case | Draft Impact on Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN | 2020-08-07 | 2021-04-20 | 65 | 0 | 176 | 256 | 100% | 0.25391 | 1 | Completed
ER6370LT | W201 | A1670 | HNB Reactors Shutdown Essential Safety Cases | Claim 2 - Peer Review | 2020-08-07 | 2020-08-28 | 3 | 0 | 15 | 21 | 100% | 0.14286 | 1 | Completed
ER6371LT | W202 | W202.A2470 | HRA Reactors Shutdown Essential Safety Cases | Thermal Analysis (FEAT) of FPU Fully Extended Report Reviewed by EDF SQEP | 2020-08-10 | 2020-08-28 | 10 | 0 | 14 | 18 | 100% | 0.55556 | 1 | Completed
ER6378LT | W222 | W222.A23400 | HRA Fuel Handling Essential Safety Case | Verify CSP Model and Static Analysis and Isuue for Technical Review | 2020-08-10 | 2020-09-18 | 29 | 0 | 29 | 39 | 100% | 0.74359 | 1 | Completed
ER6378LT | W222 | W222.A22840 | HRA Fuel Handling Essential Safety Case | Verification of Grab Engagement for Low Burn-up Fuel EAN | 2020-08-10 | 2020-10-14 | 29 | 0 | 47 | 65 | 100% | 0.44615 | 1 | Completed
ER6378LT | W222 | W222.A11610 | HRA Fuel Handling Essential Safety Case | Verify Human Factors Integration Plan EAN and Issue for Technical Review (REV 000) | 2020-08-10 | 2020-08-14 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6378LT | W222 | W222.A26950 | HRA Fuel Handling Essential Safety Case | PCL Validate & Approve Baseline Package for PRC Submission | 2020-08-10 | 2020-09-22 | 31 | 0 | 30 | 43 | 100% | 0.72093 | 1 | Completed
ER6378LT | W222 | W222.A26960 | HRA Fuel Handling Essential Safety Case | Add Data to Scheme Paper | 2020-08-10 | 2020-09-22 | 31 | 0 | 30 | 43 | 100% | 0.72093 | 1 | Completed
ER6378LT | W222 | W222.A26970 | HRA Fuel Handling Essential Safety Case | Update Schedule/Estimate from Risk Log & Add Provisions | 2020-08-10 | 2020-09-22 | 31 | 0 | 30 | 43 | 100% | 0.72093 | 1 | Completed
ER6378LT | W222 | W222.A26980 | HRA Fuel Handling Essential Safety Case | Complete Risk Log with Estimates | 2020-08-10 | 2020-09-22 | 31 | 0 | 30 | 43 | 100% | 0.72093 | 1 | Completed
ER6378LT | W222 | W222.A27000 | HRA Fuel Handling Essential Safety Case | Ensure Alignment of Schedule & Estimate | 2020-08-10 | 2020-09-21 | 30 | 0 | 30 | 42 | 100% | 0.71429 | 1 | Completed
ER6378LT | W222 | W222.A27010 | HRA Fuel Handling Essential Safety Case | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 2020-08-10 | 2020-09-21 | 30 | 0 | 30 | 42 | 100% | 0.71429 | 1 | Completed
ER6650LT | W226 | W226.A27010 | HYA Fuel Handling Essential Safety Case | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 2020-08-10 | 2020-09-21 | 30 | 0 | 30 | 42 | 100% | 0.71429 | 1 | Completed
ER6650LT | W226 | W226.A27000 | HYA Fuel Handling Essential Safety Case | Ensure Alignment of Schedule & Estimate | 2020-08-10 | 2020-09-21 | 30 | 0 | 30 | 42 | 100% | 0.71429 | 1 | Completed
ER6650LT | W226 | W226.A26980 | HYA Fuel Handling Essential Safety Case | Complete Risk Log with Estimates | 2020-08-10 | 2020-09-22 | 31 | 0 | 30 | 43 | 100% | 0.72093 | 1 | Completed
ER6650LT | W226 | W226.A26970 | HYA Fuel Handling Essential Safety Case | Update Schedule/Estimate from Risk Log & Add Provisions | 2020-08-10 | 2020-09-22 | 31 | 0 | 30 | 43 | 100% | 0.72093 | 1 | Completed
ER6650LT | W226 | W226.A26960 | HYA Fuel Handling Essential Safety Case | Add Data to Scheme Paper | 2020-08-10 | 2020-09-22 | 31 | 0 | 30 | 43 | 100% | 0.72093 | 1 | Completed
ER6650LT | W226 | W226.A26950 | HYA Fuel Handling Essential Safety Case | PCL Validate & Approve Baseline Package for PRC Submission | 2020-08-10 | 2020-09-22 | 31 | 0 | 30 | 43 | 100% | 0.72093 | 1 | Completed
ER6650LT | W226 | W226.A11610 | HYA Fuel Handling Essential Safety Case | Verify Human Factors Integration Plan EAN and Issue for Technical Review (REV 000) | 2020-08-10 | 2020-08-14 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6650LT | W226 | W226.A22840 | HYA Fuel Handling Essential Safety Case | Verification of Grab Engagement for Low Burn-up Fuel EAN | 2020-08-10 | 2020-10-14 | 29 | 0 | 47 | 65 | 100% | 0.44615 | 1 | Completed
ER6650LT | W226 | W226.A23400 | HYA Fuel Handling Essential Safety Case | Verify CSP Model and Static Analysis and Isuue for Technical Review | 2020-08-10 | 2020-09-18 | 29 | 0 | 29 | 39 | 100% | 0.74359 | 1 | Completed
ER6370LT | W201 | A1120 | HNB Reactors Shutdown Essential Safety Cases | 6 – SC Margins, Judgements and Challenges - Summary | 2020-08-10 | 2020-10-06 | 41 | 0 | 41 | 57 | 100% | 0.7193 | 1 | Completed
ER6370LT | W201 | A1840 | HNB Reactors Shutdown Essential Safety Cases | SC Margins, Judgements and Challenges - Early Draft | 2020-08-10 | 2020-09-07 | 22 | 0 | 19 | 28 | 100% | 0.78571 | 1 | Completed
ER6378LT | W222 | W222.A22990 | HRA Fuel Handling Essential Safety Case | Technical Review of Interpretation of MACE for Fuel Route EAN | 2020-08-11 | 2020-10-30 | 28 | 0 | 57 | 80 | 100% | 0.35 | 1 | Completed
ER6370LT | W201 | A1950 | HNB Reactors Shutdown Essential Safety Cases | Implementation Programme - CO and co-author review | 2020-08-11 | 2020-08-28 | 1 | 0 | 13 | 17 | 100% | 0.058824 | 1 | Completed
ER6650LT | W226 | W226.A22990 | HYA Fuel Handling Essential Safety Case | Technical Review of Interpretation of MACE for Fuel Route EAN | 2020-08-11 | 2020-10-30 | 28 | 0 | 57 | 80 | 100% | 0.35 | 1 | Completed
ER6370LT | W201 | A2150 | HNB Reactors Shutdown Essential Safety Cases | Appendix – Description of Existing Safety Case - CO and co-author review | 2020-08-11 | 2020-08-28 | 4 | 0 | 13 | 17 | 100% | 0.23529 | 1 | Completed
ER6378LT | W222 | W222.A25900 | HRA Fuel Handling Essential Safety Case | Lifting Integrity Life Limits ##(Cost Summary)## (NEW) (C3) | 2020-08-13 | 2020-12-18 | 93 | 0 | 91 | 127 | 100% | 0.73228 | 1 | Completed
ER6378LT | W222 | W222.A22750 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Lifting Integrity Life Limits EAN | 2020-08-13 | 2020-08-13 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A22750 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Lifting Integrity Life Limits EAN | 2020-08-13 | 2020-08-13 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25900 | HYA Fuel Handling Essential Safety Case | Lifting Integrity Life Limits ##(Cost Summary)## (NEW) (C3) | 2020-08-13 | 2020-12-18 | 93 | 0 | 90 | 127 | 100% | 0.73228 | 1 | Completed
ER6661LT | W206 | W206.A2300 | HYA Reactors Shutdown Essential Safety Cases | EDF Energy Issue HYA Defuelling Case against the NSPs Final Report | 2020-08-14 | 2020-08-21 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6378LT | W222 | W222.A22760 | HRA Fuel Handling Essential Safety Case | Draft Lifting Integrity Life Limits EAN | 2020-08-14 | 2020-10-12 | 40 | 0 | 40 | 59 | 100% | 0.67797 | 1 | Completed
ER6650LT | W226 | W226.A22760 | HYA Fuel Handling Essential Safety Case | Draft Lifting Integrity Life Limits EAN | 2020-08-14 | 2020-10-12 | 40 | 0 | 40 | 59 | 100% | 0.67797 | 1 | Completed
ER6372LT | W203 | W203.1000 | HNB Enhanced Defuelling Safety Cases | Scoping Report - Summary | 2020-08-14 | 2021-08-10 | 272 | 0 | 248 | 361 | 100% | 0.75346 | 1 | Completed
ER6372LT | W203 | W203.A2465 | HNB Enhanced Defuelling Safety Cases | Scoping Report - Issue Draft Repot for Technical Review | 2020-08-14 | 2020-08-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2300 | HRA Reactors Shutdown Essential Safety Cases | EDF Energy Issue HRA Defuelling Case against the NSPs Final Report | 2020-08-17 | 2020-08-21 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6661LT | W206 | W206.A3340 | HYA Reactors Shutdown Essential Safety Cases | Reactor Internals and Structural Integrity during Defuelling - Draft and issue RFS | 2020-08-17 | 2020-08-20 | 3 | 0 | 3 | 3 | 100% | 1 | 1 | Completed
ER6661LT | W206 | W206.A3330 | HYA Reactors Shutdown Essential Safety Cases | RFS - Reactor Internals and Structural Integrity during Defuelling Summary | 2020-08-17 | 2020-10-02 | 25 | 0 | 33 | 46 | 100% | 0.54348 | 1 | Completed
ER6661LT | W206 | W206.A2470 | HYA Reactors Shutdown Essential Safety Cases | Thermal Analysis (FEAT) of FPU Fully Extended Report Reviewed by EDF SQEP | 2020-08-17 | 2020-08-28 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6378LT | W222 | W222.A11630 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Human Factors Integration Plan EAN (REV 000) | 2020-08-17 | 2020-08-21 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6650LT | W226 | W226.A11630 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Human Factors Integration Plan EAN (REV 000) | 2020-08-17 | 2020-08-21 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A13170 | HNB Reactors Shutdown Essential Safety Cases | SC - Safety Case development - INSA - HNB - B-C | 2020-08-17 | 2021-05-07 | 89 | 0 | 182 | 263 | 100% | 0.3384 | 1 | Completed
ER6370LT | W201 | ER6370.A18120 | HNB Reactors Shutdown Essential Safety Cases | Initial review of available Head Documents (Claims 0, 1 and 2) | 2020-08-17 | 2020-09-21 | 17 | 0 | 24 | 35 | 100% | 0.48571 | 1 | Completed
ER6370LT | W201 | A1190 | HNB Reactors Shutdown Essential Safety Cases | Appendix – OPEX - Summary | 2020-08-17 | 2020-10-07 | 37 | 0 | 37 | 51 | 100% | 0.72549 | 1 | Completed
ER6370LT | W201 | A1800 | HNB Reactors Shutdown Essential Safety Cases | Claim 5 - CO and co-author review | 2020-08-17 | 2020-09-01 | 10 | 0 | 10 | 15 | 100% | 0.66667 | 1 | Completed
ER6370LT | W201 | A2190 | HNB Reactors Shutdown Essential Safety Cases | Appendix – OPEX - Early Draft | 2020-08-17 | 2020-09-11 | 10 | 0 | 19 | 25 | 100% | 0.4 | 1 | Completed
ER6370LT | W201 | ER6370.A4680 | HNB Reactors Shutdown Essential Safety Cases | Core Cooling Head Document Draft Report - Revised draft issued to verifiers | 2020-08-20 | 2020-08-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2320 | HRA Reactors Shutdown Essential Safety Cases | TSA Issue HRA Defuelling Case against the NSPs Final Report | 2020-08-21 | 2020-08-28 | 10 | 0 | 5 | 7 | 100% | 1.4286 | 1 | Completed
ER6661LT | W206 | W206.A2320 | HYA Reactors Shutdown Essential Safety Cases | TSA Issue HYA Defuelling Case against the NSPs Final Report | 2020-08-21 | 2020-08-28 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6370LT | W201 | ER6370.A4690 | HNB Reactors Shutdown Essential Safety Cases | Core Cooling Head Document Draft Report - Verifiers provide second round comments | 2020-08-21 | 2020-09-14 | 16 | 0 | 16 | 24 | 100% | 0.66667 | 1 | Completed
ER6378LT | W222 | W222.A11640 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Human Factors Integration Plan EAN to CDMS (REV 000) | 2020-08-24 | 2020-09-24 | 19 | 0 | 22 | 31 | 100% | 0.6129 | 1 | Completed
ER6650LT | W226 | W226.A11640 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Human Factors Integration Plan EAN to CDMS (REV 000) | 2020-08-24 | 2020-09-24 | 19 | 0 | 22 | 31 | 100% | 0.6129 | 1 | Completed
ER6372LT | W203 | W203.A1050 | HNB Enhanced Defuelling Safety Cases | Write IRM Paper | 2020-08-24 | 2020-09-07 | 10 | 0 | 10 | 14 | 100% | 0.71429 | 1 | Completed
ER6371LT | W202 | W202.A3340 | HRA Reactors Shutdown Essential Safety Cases | Reactor Internals and Structural Integrity during Defuelling - Draft and issue RFS | 2020-08-25 | 2020-08-28 | 3 | 0 | 3 | 3 | 100% | 1 | 1 | Completed
ER6371LT | W202 | W202.A3330 | HRA Reactors Shutdown Essential Safety Cases | RFS - Reactor Internals and Structural Integrity during Defuelling Summary | 2020-08-25 | 2020-10-02 | 25 | 0 | 27 | 38 | 100% | 0.65789 | 1 | Completed
ER6370LT | W201 | A1680 | HNB Reactors Shutdown Essential Safety Cases | Claim 2 - Draft Complete | 2020-08-26 | 2020-08-28 | 5 | 0 | 2 | 2 | 100% | 2.5 | 1 | Completed
ER6370LT | W201 | ER6370.P1270 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE> - Head Document (PVCW) - Issue Head Document and upload to CDMS | 2020-08-27 | 2020-09-07 | 5 | 0 | 6 | 11 | 100% | 0.45455 | 1 | Completed
ER6378LT | W222 | W222.A16310 | HRA Fuel Handling Essential Safety Case | Defuelling Safety Case Head Documents ##(Cost Summary)## | 2020-08-27 | 2021-12-24 | 336 | 0 | 338 | 484 | 100% | 0.69421 | 1 | Completed
ER6378LT | W222 | W222.A11330 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Justification for Pressure Boundary EAN | 2020-08-27 | 2020-08-27 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A16910 | HRA Fuel Handling Essential Safety Case | Pre-job Brief | 2020-08-27 | 2020-08-27 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A19400 | HRA Fuel Handling Essential Safety Case | Pressure Boundary ##(Cost Summary)## (C3) (NEW) | 2020-08-27 | 2021-03-19 | 119 | 0 | 143 | 204 | 100% | 0.58333 | 1 | Completed
ER6650LT | W226 | W226.A19400 | HYA Fuel Handling Essential Safety Case | Pressure Boundary ##(Cost Summary)## (C3) (NEW) | 2020-08-27 | 2021-03-19 | 119 | 0 | 143 | 204 | 100% | 0.58333 | 1 | Completed
ER6650LT | W226 | W226.A11330 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Justification for Pressure Boundary EAN | 2020-08-27 | 2020-08-27 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1650 | HRA Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals Specification Completed | 2020-08-28 | 2020-08-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1650 | HYA Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals Specification Completed | 2020-08-28 | 2020-08-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206020 | HRA Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W222.A22450) Pressure Boundary Seals Report Completed | 2020-08-28 | 2020-08-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206020 | HYA Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W222.A22450) Pressure Boundary Seals Report Completed | 2020-08-28 | 2020-08-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206160 | HYA Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W226) Pressure Boundary Seals Report Completed | 2020-08-28 | 2020-08-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A17630 | HRA Fuel Handling Essential Safety Case | Draft and Verify Justification for Pressure Boundary EAN | 2020-08-28 | 2020-12-11 | 60 | 0 | 75 | 105 | 100% | 0.57143 | 1 | Completed
ER6378LT | W222 | W222.A16920 | HRA Fuel Handling Essential Safety Case | Proposed Contents Page Shared with EDF Energy | 2020-08-28 | 2020-12-01 | 30 | 0 | 67 | 95 | 100% | 0.31579 | 1 | Completed
ER6378LT | W222 | W222.A22450 | HRA Fuel Handling Essential Safety Case | >>>INCOMING ENABLER (W202.A2206020) Pressure Boundary Seals Report Completed | 2020-08-28 | 2020-08-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A22550 | HRA Fuel Handling Essential Safety Case | >>>MIRROR OF INCOMING ENABLER (W202.A2206020) Pressure Boundary Seals Report Completed | 2020-08-28 | 2020-08-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A22650 | HRA Fuel Handling Essential Safety Case | INTERFACE MILESTONE - Pressure Boundary Seals Report Completed - (W206 Reactors Shutdown Essential Safety Cases (HRA)) | 2020-08-28 | 2020-08-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A2120 | HNB Reactors Shutdown Essential Safety Cases | NSC Request for Consideration and Advice - Peer Review | 2020-08-28 | 2020-08-28 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A22650 | HYA Fuel Handling Essential Safety Case | INTERFACE MILESTONE - Pressure Boundary Seals Report Completed - (W206 Reactors Shutdown Essential Safety Cases (HYA)) | 2020-08-28 | 2020-08-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A22550 | HYA Fuel Handling Essential Safety Case | >>>MIRROR OF INCOMING ENABLER (W202.A2206020) Pressure Boundary Seals Report Completed | 2020-08-28 | 2020-08-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A16920 | HYA Fuel Handling Essential Safety Case | Proposed Contents Page Shared with EDF Energy | 2020-08-28 | 2020-12-01 | 30 | 0 | 67 | 95 | 100% | 0.31579 | 1 | Completed
ER6650LT | W226 | W226.A17630 | HYA Fuel Handling Essential Safety Case | Draft Justification for Pressure Boundary EAN | 2020-08-28 | 2020-12-11 | 60 | 0 | 75 | 105 | 100% | 0.57143 | 1 | Completed
ER6650LT | W226 | W226.A16310 | HYA Fuel Handling Essential Safety Case | Defuelling Safety Case Head Documents ##(Cost Summary)## | 2020-08-28 | 2021-12-24 | 321 | 0 | 336 | 483 | 100% | 0.6646 | 1 | Completed
ER6650LT | W226 | W226.A27190 | HYA Fuel Handling Essential Safety Case | >>>INCOMING ENABLER (W206.A2206020) Pressure Boundary Seals Report Completed | 2020-08-28 | 2020-08-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2220 | HRA Reactors Shutdown Essential Safety Cases | HF - Oversight of Work / HF Risk / HFIP - Pre Job Brief | 2020-08-28 | 2020-08-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2220 | HYA Reactors Shutdown Essential Safety Cases | HF - Oversight of Work / HF Risk / HFIP - Pre Job Brief | 2020-08-28 | 2020-08-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A12370 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Confirm Adequate Capacity for Solid Waste Arisings from Stringer Dismantling EAN | 2020-08-31 | 2020-10-01 | 0 | 0 | 23 | 31 | 100% | 0 | 1 | Completed
ER6370LT | W201 | A1960 | HNB Reactors Shutdown Essential Safety Cases | Implementation Programme - Mature Draft | 2020-08-31 | 2020-10-08 | 1 | 0 | 28 | 38 | 100% | 0.026316 | 1 | Completed
ER6370LT | W201 | A2160 | HNB Reactors Shutdown Essential Safety Cases | Appendix – Description of Existing Safety Case - Mature Draft | 2020-08-31 | 2020-08-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A12370 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Confirm Adequate Capacity for Solid Waste Arisings from Stringer Dismantling EAN | 2020-08-31 | 2020-10-01 | 0 | 0 | 22 | 31 | 100% | 0 | 1 | Completed
ER6661LT | W206 | W206.A2240 | HYA Reactors Shutdown Essential Safety Cases | Prepare General HF Oversight and HFIP Updates and Revisions Draft EAN | 2020-09-01 | 2020-10-05 | 25 | 0 | 25 | 34 | 100% | 0.73529 | 1 | Completed
ER6661LT | W206 | W206.A2230 | HYA Reactors Shutdown Essential Safety Cases | General HF Oversight and HFIP Updates and Revisions Summary | 2020-09-01 | 2020-11-23 | 74 | 0 | 59 | 83 | 100% | 0.89157 | 1 | Completed
ER6661LT | W206 | W206.A2810 | HYA Reactors Shutdown Essential Safety Cases | SC - Safety Case development - tech oversight Cat 1 - Claim 4 - HYA - B-C - STN | 2020-09-01 | 2021-08-24 | 283 | 0 | 248 | 357 | 100% | 0.79272 | 1 | Completed
ER6378LT | W222 | W222.A8230 | HRA Fuel Handling Essential Safety Case | Verify Defuelling Cooling and Match Analysis (Task FIle Note) and Issue for Technical Review | 2020-09-01 | 2020-12-17 | 27 | 0 | 77 | 107 | 100% | 0.25234 | 1 | Completed
ER6378LT | W222 | W222.A12890 | HRA Fuel Handling Essential Safety Case | Safety Case Development - ##(Cost Summary)## (B to C) | 2020-09-01 | 2021-12-13 | 187 | 0 | 326 | 468 | 100% | 0.39957 | 1 | Completed
ER6378LT | W222 | W222.A13260 | HRA Fuel Handling Essential Safety Case | Project Management Costs (B to C) ##(Cost Summary)## | 2020-09-01 | 2021-12-13 | 187 | 0 | 326 | 468 | 100% | 0.39957 | 1 | Completed
ER6370LT | W201 | A1260 | HNB Reactors Shutdown Essential Safety Cases | Appendix E – Detailed Description of Changes to Documentation - Summary | 2020-09-01 | 2020-09-15 | 7 | 0 | 11 | 14 | 100% | 0.5 | 1 | Completed
ER6370LT | W201 | A2590 | HNB Reactors Shutdown Essential Safety Cases | Appendix E – Detailed Description of Changes to Documentation - Early Draft | 2020-09-01 | 2020-09-03 | 3 | 0 | 2 | 2 | 100% | 1.5 | 1 | Completed
ER6378LT | W222 | W222.A27090 | HRA Fuel Handling Essential Safety Case | Gate B+ PM Costs START MILESTONE | 2020-09-01 | 2020-09-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A27110 | HRA Fuel Handling Essential Safety Case | Gate B+ Safety Case Costs START MILESTONE | 2020-09-01 | 2020-09-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27110 | HYA Fuel Handling Essential Safety Case | Gate B+ Safety Case Costs START MILESTONE | 2020-09-01 | 2020-09-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27090 | HYA Fuel Handling Essential Safety Case | Gate B+ PM Costs START MILESTONE | 2020-09-01 | 2020-09-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A13260 | HYA Fuel Handling Essential Safety Case | Project Management Costs (B to C) ##(Cost Summary)## | 2020-09-01 | 2021-12-13 | 187 | 0 | 326 | 468 | 100% | 0.39957 | 1 | Completed
ER6650LT | W226 | W226.A12890 | HYA Fuel Handling Essential Safety Case | Safety Case Development - ##(Cost Summary)## (B to C) | 2020-09-01 | 2021-12-13 | 187 | 0 | 326 | 468 | 100% | 0.39957 | 1 | Completed
ER6650LT | W226 | W226.A8230 | HYA Fuel Handling Essential Safety Case | Verify Defuelling Cooling and Match Analysis (Task FIle Note) and Issue for Technical Review | 2020-09-01 | 2020-12-17 | 20 | 0 | 77 | 107 | 100% | 0.18692 | 1 | Completed
ER6650LT | W226 | W226.A27430 | HYA Fuel Handling Essential Safety Case | 2020-2023 Reconciliation Sunk Line | 2020-09-01 | 2023-04-28 | 798 | 0 | 671 | 969 | 100% | 0.82353 | 1 | Completed
ER6378LT | W222 | W222.A27435 | HRA Fuel Handling Essential Safety Case | 2020-2023 Reconciliation Sunk Line | 2020-09-01 | 2023-04-28 | 798 | 0 | 671 | 969 | 100% | 0.82353 | 1 | Completed
ER6371LT | W202 | W202.A2610 | HRA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Gas Chemistry Assessment Draft Report | 2020-09-01 | 2020-10-19 | 15 | 0 | 34 | 48 | 100% | 0.3125 | 1 | Completed
ER6371LT | W202 | W202.A2240 | HRA Reactors Shutdown Essential Safety Cases | Prepare General HF Oversight and HFIP Updates and Revisions Draft EAN | 2020-09-01 | 2020-10-05 | 25 | 0 | 25 | 34 | 100% | 0.73529 | 1 | Completed
ER6371LT | W202 | W202.A2420 | HRA Reactors Shutdown Essential Safety Cases | Review of HRA Defuelling Case against the NSPs TR Completed and uploaded to CDMS | 2020-09-01 | 2020-09-02 | 31 | 0 | 1 | 1 | 100% | 31 | 1 | Completed
ER6371LT | W202 | W202.A2230 | HRA Reactors Shutdown Essential Safety Cases | General HF Oversight and HFIP Updates and Revisions Summary | 2020-09-01 | 2020-11-27 | 95 | 0 | 63 | 87 | 100% | 1.092 | 1 | Completed
ER6371LT | W202 | W202.A2810 | HRA Reactors Shutdown Essential Safety Cases | SC - Safety Case development - tech oversight Cat 1 - Claim 4 - HRA - B-C - STN | 2020-09-01 | 2021-08-24 | 290 | 0 | 248 | 357 | 100% | 0.81232 | 1 | Completed
ER6371LT | W202 | W202.A3390 | HRA Reactors Shutdown Essential Safety Cases | Reactor Internals and Structural Integrity during Defuelling - Supplier prepare and issue Offer | 2020-09-01 | 2020-09-14 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6371LT | W202 | W202.A2640 | HRA Reactors Shutdown Essential Safety Cases | Address Comments on Reviewed Thermal Analysis (FEAT) of FPU Fully Extended Report | 2020-09-01 | 2020-12-31 | 10 | 0 | 85 | 121 | 100% | 0.082645 | 1 | Completed
ER6371LT | W202 | W202.A3480 | HRA Reactors Shutdown Essential Safety Cases | Address Comments on Reviewed Worker Dose Report | 2020-09-01 | 2020-10-15 | 10 | 0 | 33 | 44 | 100% | 0.22727 | 1 | Completed
ER6661LT | W206 | W206.A2610 | HYA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Gas Chemistry Assessment Draft Report | 2020-09-01 | 2020-10-19 | 15 | 0 | 34 | 48 | 100% | 0.3125 | 1 | Completed
ER6661LT | W206 | W206.A2420 | HYA Reactors Shutdown Essential Safety Cases | Review of HYA Defuelling Case against the NSPs TR Completed and uploaded to CDMS | 2020-09-01 | 2020-09-02 | 2 | 0 | 1 | 1 | 100% | 2 | 1 | Completed
ER6661LT | W206 | W206.A3390 | HYA Reactors Shutdown Essential Safety Cases | Reactor Internals and Structural Integrity during Defuelling - Supplier prepare and issue Offer | 2020-09-01 | 2020-09-14 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6661LT | W206 | W206.A2640 | HYA Reactors Shutdown Essential Safety Cases | Address Comments on Reviewed Thermal Analysis (FEAT) of FPU Fully Extended Report | 2020-09-01 | 2020-12-31 | 10 | 0 | 85 | 121 | 100% | 0.082645 | 1 | Completed
ER6661LT | W206 | W206.A2680 | HYA Reactors Shutdown Essential Safety Cases | TSA Issue Final Fault Schedule Review (Plant Base Faults and Hazards) Report - (HYA) | 2020-09-01 | 2020-09-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2700 | HYA Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Base Faults and Hazards) Report TR Completed and uploaded to CDMS - (HYA) | 2020-09-01 | 2020-09-14 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6378LT | W222 | W222.A26750 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Fuel Route Operational Sequence/Process for Defuelling EAN (REV 001) | 2020-09-01 | 2020-09-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26490 | HRA Fuel Handling Essential Safety Case | LVDT Weight Sensing System matters arising from Review of HH1 FM Protection ##(Cost Summary)## (C2) (NEW) | 2020-09-01 | 2021-04-15 | 158 | 0 | 158 | 226 | 100% | 0.69912 | 1 | Completed
ER6378LT | W222 | W222.A26480 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for LVDT Weight Sensing System matters arising from Review of HH1 FM Protection | 2020-09-01 | 2020-09-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26410 | HRA Fuel Handling Essential Safety Case | Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection ##(Cost Summary)## (C2) (NEW) | 2020-09-01 | 2021-05-26 | 170 | 0 | 185 | 267 | 100% | 0.6367 | 1 | Completed
ER6378LT | W222 | W222.A26400 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection | 2020-09-01 | 2020-09-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26100 | HRA Fuel Handling Essential Safety Case | HAZOP updates resulting from defuelling process changes (REV 001) ##(Cost Summary)## (C2) (NEW) | 2020-09-01 | 2021-02-11 | 115 | 0 | 115 | 163 | 100% | 0.70552 | 1 | Completed
ER6378LT | W222 | W222.A26090 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for HAZOP updates resulting from defuelling process changes (REV 001) | 2020-09-01 | 2020-09-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26030 | HRA Fuel Handling Essential Safety Case | Detailed Option Investigation ##(Cost Summary)## (C5) (NEW) | 2020-09-01 | 2020-11-20 | 59 | 0 | 59 | 80 | 100% | 0.7375 | 1 | Completed
ER6378LT | W222 | W222.A25810 | HRA Fuel Handling Essential Safety Case | Review of Interlock Maintenance Review EAN ##(Cost Summary)## (DRAFT) (C2) (NEW) (Claim 2 & 6 Impact Summary) | 2020-09-01 | 2021-09-14 | 263 | 0 | 263 | 378 | 100% | 0.69577 | 1 | Completed
ER6378LT | W222 | W222.A25780 | HRA Fuel Handling Essential Safety Case | Hazards Review ##(Cost Summary)## (C1) (NEW) | 2020-09-01 | 2021-04-19 | 161 | 0 | 159 | 230 | 100% | 0.7 | 1 | Completed
ER6378LT | W222 | W222.A25130 | HRA Fuel Handling Essential Safety Case | Update Basis of Analysis for Dropped FPU to (UPDATE) (REV 001) | 2020-09-01 | 2021-02-05 | 13 | 0 | 111 | 157 | 100% | 0.082803 | 1 | Completed
ER6378LT | W222 | W222.A24500 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Review of Interlock Maintenance Review EAN (DRAFT) | 2020-09-01 | 2020-09-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24220 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Hazards Review EAN | 2020-09-01 | 2020-09-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A23800 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Detailed Option Investigation EAN | 2020-09-01 | 2020-09-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A6010 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Panther Sensitivity Studies - Draft and issue RFS | 2020-09-01 | 2020-09-02 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6371LT | W202 | W202.A6000 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> RFS - Panther Sensitivity Studies Summary | 2020-09-01 | 2020-09-18 | 14 | 0 | 14 | 17 | 100% | 0.82353 | 1 | Completed
ER6371LT | W202 | W202.A6310 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Consequences EAN - Draft and issue RFS | 2020-09-01 | 2020-09-02 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6371LT | W202 | W202.A6300 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> RFS - Consequences EAN Summary | 2020-09-01 | 2020-09-16 | 12 | 0 | 12 | 15 | 100% | 0.8 | 1 | Completed
ER6371LT | W202 | W202.A6800 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Specified Flows - Draft and issue RFS | 2020-09-01 | 2020-09-02 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6371LT | W202 | W202.A6790 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> RFS - Specified Flows Summary | 2020-09-01 | 2020-09-18 | 14 | 0 | 14 | 17 | 100% | 0.82353 | 1 | Completed
ER6371LT | W202 | W202.A6950 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Determination of Cliff Edge - Draft and issue RFS | 2020-09-01 | 2020-09-02 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6371LT | W202 | W202.A6940 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> RFS - Determination of Cliff Edge Summary | 2020-09-01 | 2020-09-18 | 14 | 0 | 14 | 17 | 100% | 0.82353 | 1 | Completed
ER6661LT | W206 | W206.A6010 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Panther Sensitivity Studies - Draft and issue RFS | 2020-09-01 | 2020-09-02 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6661LT | W206 | W206.A6000 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> RFS - Panther Sensitivity Studies Summary | 2020-09-01 | 2020-09-18 | 14 | 0 | 14 | 17 | 100% | 0.82353 | 1 | Completed
ER6661LT | W206 | W206.A6310 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Consequences EAN - Draft and issue RFS | 2020-09-01 | 2020-09-02 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6661LT | W206 | W206.A6300 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> RFS - Consequences EAN Summary | 2020-09-01 | 2020-09-16 | 12 | 0 | 12 | 15 | 100% | 0.8 | 1 | Completed
ER6661LT | W206 | W206.A6800 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Specified Flows - Draft and issue RFS | 2020-09-01 | 2020-09-02 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6661LT | W206 | W206.A6790 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> RFS - Specified Flows Summary | 2020-09-01 | 2020-09-18 | 14 | 0 | 14 | 17 | 100% | 0.82353 | 1 | Completed
ER6661LT | W206 | W206.A6950 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Determination of Cliff Edge - Draft and issue RFS | 2020-09-01 | 2020-09-02 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6661LT | W206 | W206.A6940 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> RFS - Determination of Cliff Edge Summary | 2020-09-01 | 2020-09-18 | 14 | 0 | 14 | 17 | 100% | 0.82353 | 1 | Completed
ER6650LT | W226 | W226.A16910 | HYA Fuel Handling Essential Safety Case | Pre-job Brief | 2020-09-01 | 2020-09-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23800 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Detailed Option Investigation EAN | 2020-09-01 | 2020-09-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24220 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Hazards Review EAN | 2020-09-01 | 2020-09-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24500 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Review of Interlock Maintenance Review EAN (DRAFT) | 2020-09-01 | 2020-09-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25130 | HYA Fuel Handling Essential Safety Case | Update Basis of Analysis fro Dropped FPU to (UPDATE) (REV 001) | 2020-09-01 | 2021-02-05 | 13 | 0 | 111 | 157 | 100% | 0.082803 | 1 | Completed
ER6650LT | W226 | W226.A25780 | HYA Fuel Handling Essential Safety Case | Hazards Review ##(Cost Summary)## (C1) (NEW) | 2020-09-01 | 2021-04-19 | 161 | 0 | 159 | 230 | 100% | 0.7 | 1 | Completed
ER6650LT | W226 | W226.A25810 | HYA Fuel Handling Essential Safety Case | Review of Interlock Maintenance Review EAN ##(Cost Summary)## (DRAFT) (C2) (NEW) | 2020-09-01 | 2021-09-14 | 263 | 0 | 263 | 378 | 100% | 0.69577 | 1 | Completed
ER6650LT | W226 | W226.A26030 | HYA Fuel Handling Essential Safety Case | Detailed Option Investigation ##(Cost Summary)## (C5) (NEW) | 2020-09-01 | 2020-11-20 | 59 | 0 | 59 | 80 | 100% | 0.7375 | 1 | Completed
ER6650LT | W226 | W226.A26090 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for HAZOP updates resulting from defuelling process changes (REV 001) | 2020-09-01 | 2020-09-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26100 | HYA Fuel Handling Essential Safety Case | HAZOP updates resulting from defuelling process changes (REV 001) ##(Cost Summary)## (C2) (NEW) | 2020-09-01 | 2021-02-11 | 116 | 0 | 114 | 163 | 100% | 0.71166 | 1 | Completed
ER6650LT | W226 | W226.A26400 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection | 2020-09-01 | 2020-09-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26410 | HYA Fuel Handling Essential Safety Case | Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection ##(Cost Summary)## (C2) (NEW) | 2020-09-01 | 2021-05-26 | 170 | 0 | 185 | 267 | 100% | 0.6367 | 1 | Completed
ER6650LT | W226 | W226.A26480 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for LVDT Weight Sensing System matters arising from Review of HH1 FM Protection | 2020-09-01 | 2020-09-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26490 | HYA Fuel Handling Essential Safety Case | LVDT Weight Sensing System matters arising from Review of HH1 FM Protection ##(Cost Summary)## (C2) (NEW) | 2020-09-01 | 2021-04-15 | 158 | 0 | 158 | 226 | 100% | 0.69912 | 1 | Completed
ER6650LT | W226 | W226.A26750 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Fuel Route Operational Sequence/Process for Defuelling EAN (REV 001) | 2020-09-01 | 2020-09-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A27260 | HRA Fuel Handling Essential Safety Case | Post Reference Query | 2020-09-01 | 2020-09-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W222.A27260 | HYA Fuel Handling Essential Safety Case | Post Reference Query | 2020-09-01 | 2020-09-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A9940 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Update to Failed Fuel EAN | 2020-09-02 | 2020-09-07 | 4 | 0 | 3 | 5 | 100% | 0.8 | 1 | Completed
ER6650LT | W226 | W226.A9940 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Update to Failed Fuel EAN | 2020-09-02 | 2020-09-07 | 4 | 0 | 3 | 5 | 100% | 0.8 | 1 | Completed
ER6371LT | W202 | W202.A2560 | HRA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Fault Schedule Review (Plant Base Faults and Hazards) Draft Report - (HRA) | 2020-09-02 | 2020-09-15 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6661LT | W206 | W206.A3480 | HYA Reactors Shutdown Essential Safety Cases | Address Comments on Reviewed Worker Dose Report | 2020-09-02 | 2020-10-15 | 10 | 0 | 32 | 43 | 100% | 0.23256 | 1 | Completed
ER6378LT | W222 | W222.A26760 | HRA Fuel Handling Essential Safety Case | Draft Fuel Route Operational Sequence/Process for Defuelling EAN (REV 001) | 2020-09-02 | 2020-09-11 | 8 | 0 | 8 | 9 | 100% | 0.88889 | 1 | Completed
ER6378LT | W222 | W222.A26500 | HRA Fuel Handling Essential Safety Case | Draft LVDT Weight Sensing System matters arising from Review of HH1 FM Protection | 2020-09-02 | 2021-04-01 | 10 | 0 | 149 | 211 | 100% | 0.047393 | 1 | Completed
ER6378LT | W222 | W222.A26420 | HRA Fuel Handling Essential Safety Case | Draft Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection | 2020-09-02 | 2020-09-16 | 10 | 0 | 10 | 14 | 100% | 0.71429 | 1 | Completed
ER6378LT | W222 | W222.A26110 | HRA Fuel Handling Essential Safety Case | Draft HAZOP updates resulting from defuelling process changes (REV 001) | 2020-09-02 | 2020-10-09 | 15 | 0 | 28 | 37 | 100% | 0.40541 | 1 | Completed
ER6378LT | W222 | W222.A24510 | HRA Fuel Handling Essential Safety Case | Draft Review of Interlock Maintenance Review EAN (DRAFT) | 2020-09-02 | 2020-10-16 | 33 | 0 | 33 | 44 | 100% | 0.75 | 1 | Completed
ER6378LT | W222 | W222.A24230 | HRA Fuel Handling Essential Safety Case | Draft Hazards Review EAN | 2020-09-02 | 2020-11-02 | 15 | 0 | 44 | 61 | 100% | 0.2459 | 1 | Completed
ER6378LT | W222 | W222.A23810 | HRA Fuel Handling Essential Safety Case | Draft Detailed Option Investigation EAN | 2020-09-02 | 2020-10-02 | 20 | 0 | 23 | 30 | 100% | 0.66667 | 1 | Completed
ER6370LT | W201 | A1810 | HNB Reactors Shutdown Essential Safety Cases | Claim 5 - Mature Draft | 2020-09-02 | 2020-09-04 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6370LT | W201 | A2760 | HNB Reactors Shutdown Essential Safety Cases | Claim 4 - Peer Review 2 | 2020-09-02 | 2020-09-22 | 7 | 0 | 15 | 20 | 100% | 0.35 | 1 | Completed
ER6650LT | W226 | W226.A23810 | HYA Fuel Handling Essential Safety Case | Draft Detailed Option Investigation EAN | 2020-09-02 | 2020-10-02 | 20 | 0 | 23 | 30 | 100% | 0.66667 | 1 | Completed
ER6650LT | W226 | W226.A24230 | HYA Fuel Handling Essential Safety Case | Draft Hazards Review EAN | 2020-09-02 | 2020-11-02 | 15 | 0 | 44 | 61 | 100% | 0.2459 | 1 | Completed
ER6650LT | W226 | W226.A24510 | HYA Fuel Handling Essential Safety Case | Draft Review of Interlock Maintenance Review EAN (DRAFT) | 2020-09-02 | 2020-10-16 | 33 | 0 | 33 | 44 | 100% | 0.75 | 1 | Completed
ER6650LT | W226 | W226.A26110 | HYA Fuel Handling Essential Safety Case | Draft HAZOP updates resulting from defuelling process changes (REV 001) | 2020-09-02 | 2020-10-09 | 15 | 0 | 28 | 37 | 100% | 0.40541 | 1 | Completed
ER6650LT | W226 | W226.A26420 | HYA Fuel Handling Essential Safety Case | Draft Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection | 2020-09-02 | 2020-09-16 | 10 | 0 | 10 | 14 | 100% | 0.71429 | 1 | Completed
ER6650LT | W226 | W226.A26500 | HYA Fuel Handling Essential Safety Case | Draft LVDT Weight Sensing System matters arising from Review of HH1 FM Protection | 2020-09-02 | 2021-04-01 | 10 | 0 | 149 | 211 | 100% | 0.047393 | 1 | Completed
ER6650LT | W226 | W226.A26760 | HYA Fuel Handling Essential Safety Case | Draft Fuel Route Operational Sequence/Process for Defuelling EAN (REV 001) | 2020-09-02 | 2020-09-11 | 8 | 0 | 8 | 9 | 100% | 0.88889 | 1 | Completed
ER6371LT | W202 | W202.A6020 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Panther Sensitivity Studies - Supplier prepare and issue Offer | 2020-09-03 | 2020-09-09 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A6320 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Consequences EAN - Supplier prepare and issue Offer | 2020-09-03 | 2020-09-09 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A6810 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Specified Flows - Supplier prepare and issue Offer | 2020-09-03 | 2020-09-09 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A6960 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Determination of Cliff Edge - Supplier prepare and issue Offer | 2020-09-03 | 2020-09-09 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | W206.A6020 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Panther Sensitivity Studies - Supplier prepare and issue Offer | 2020-09-03 | 2020-09-09 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | W206.A6320 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Consequences EAN - Supplier prepare and issue Offer | 2020-09-03 | 2020-09-09 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | W206.A6810 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Specified Flows - Supplier prepare and issue Offer | 2020-09-03 | 2020-09-09 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | W206.A6960 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Determination of Cliff Edge - Supplier prepare and issue Offer | 2020-09-03 | 2020-09-09 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A17660 | HNB Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W283) PVCW Head Document Complete | 2020-09-07 | 2020-09-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A2600 | HNB Reactors Shutdown Essential Safety Cases | Appendix E – Detailed Description of Changes to Documentation - CO and co-author review | 2020-09-07 | 2020-09-08 | 2 | 0 | 1 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | A2690 | HNB Reactors Shutdown Essential Safety Cases | Summary - Early Draft | 2020-09-07 | 2020-09-18 | 5 | 0 | 10 | 11 | 100% | 0.45455 | 1 | Completed
ER6378LT | W222 | W222.A9950 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Update to Failed Fuel EAN to CDMS | 2020-09-08 | 2020-09-09 | 2 | 0 | 1 | 1 | 100% | 2 | 1 | Completed
ER6650LT | W226 | W226.A9950 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Update to Failed Fuel EAN to CDMS | 2020-09-08 | 2020-09-09 | 2 | 0 | 1 | 1 | 100% | 2 | 1 | Completed
ER6378LT | W222 | W222.A23050 | HRA Fuel Handling Essential Safety Case | Verify Breached PVCW Assessmen and Issue EAN for Technical Review | 2020-09-08 | 2020-09-08 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1100 | HNB Enhanced Defuelling Safety Cases | IRM Paper stakeholder sign off | 2020-09-08 | 2020-09-14 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6650LT | W226 | W226.A23050 | HYA Fuel Handling Essential Safety Case | Verify Breached PVCW Assessmen and Issue EAN for Technical Review | 2020-09-08 | 2020-09-08 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A9960 | HRA Fuel Handling Essential Safety Case | Update to Failed Fuel EAN Available | 2020-09-09 | 2020-09-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A9960 | HYA Fuel Handling Essential Safety Case | Update to Failed Fuel EAN Available | 2020-09-09 | 2020-09-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A23060 | HRA Fuel Handling Essential Safety Case | Technical Review of Breached PVCW Assessmen EAN | 2020-09-09 | 2020-09-10 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | A2610 | HNB Reactors Shutdown Essential Safety Cases | Appendix E – Detailed Description of Changes to Documentation - Mature Draft | 2020-09-09 | 2020-09-10 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6650LT | W226 | W226.A23060 | HYA Fuel Handling Essential Safety Case | Technical Review of Breached PVCW Assessmen EAN | 2020-09-09 | 2020-09-10 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6371LT | W202 | W202.A2750 | HRA Reactors Shutdown Essential Safety Cases | Prepare Shutdown Margin Head Document | 2020-09-10 | 2020-10-09 | 20 | 0 | 21 | 29 | 100% | 0.68966 | 1 | Completed
ER6371LT | W202 | W202.A2740 | HRA Reactors Shutdown Essential Safety Cases | Shutdown Margin Head Document Summary | 2020-09-10 | 2021-08-20 | 198 | 0 | 240 | 344 | 100% | 0.57558 | 1 | Completed
ER6661LT | W206 | W206.A2750 | HYA Reactors Shutdown Essential Safety Cases | Prepare Shutdown Margin Head Document | 2020-09-10 | 2020-10-09 | 20 | 0 | 21 | 29 | 100% | 0.68966 | 1 | Completed
ER6661LT | W206 | W206.A2740 | HYA Reactors Shutdown Essential Safety Cases | Shutdown Margin Head Document Summary | 2020-09-10 | 2021-08-20 | 198 | 0 | 240 | 344 | 100% | 0.57558 | 1 | Completed
ER6371LT | W202 | W202.A2770 | HRA Reactors Shutdown Essential Safety Cases | Summary of Compliance with NSPs - Draft and issue RFS | 2020-09-10 | 2020-10-01 | 5 | 0 | 15 | 21 | 100% | 0.2381 | 1 | Completed
ER6371LT | W202 | W202.A2760 | HRA Reactors Shutdown Essential Safety Cases | RFS - Summary of Compliance with NSPs Summary | 2020-09-10 | 2020-10-08 | 44 | 0 | 21 | 28 | 100% | 1.5714 | 1 | Completed
ER6661LT | W206 | W206.A2770 | HYA Reactors Shutdown Essential Safety Cases | Summary of Compliance with NSPs - Draft and issue RFS | 2020-09-10 | 2020-10-01 | 5 | 0 | 15 | 21 | 100% | 0.2381 | 1 | Completed
ER6661LT | W206 | W206.A2760 | HYA Reactors Shutdown Essential Safety Cases | RFS - Summary of Compliance with NSPs Summary | 2020-09-10 | 2020-10-08 | 44 | 0 | 21 | 28 | 100% | 1.5714 | 1 | Completed
ER6371LT | W202 | W202.A6030 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Panther Sensitivity Studies - Review Offer, prepare and issue CI | 2020-09-10 | 2020-09-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A6330 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Consequences EAN - Review Offer, prepare and issue CI | 2020-09-10 | 2020-09-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A6820 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Specified Flows - Review Offer, prepare and issue CI | 2020-09-10 | 2020-09-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A6970 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Determination of Cliff Edge - Review Offer, prepare and issue CI | 2020-09-10 | 2020-09-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A6030 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Panther Sensitivity Studies - Review Offer, prepare and issue CI | 2020-09-10 | 2020-09-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A6330 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Consequences EAN - Review Offer, prepare and issue CI | 2020-09-10 | 2020-09-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A6820 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Specified Flows - Review Offer, prepare and issue CI | 2020-09-10 | 2020-09-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A6970 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Determination of Cliff Edge - Review Offer, prepare and issue CI | 2020-09-10 | 2020-09-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A17650 | HNB Reactors Shutdown Essential Safety Cases | Core Cooling Head Document Draft Report - Second round comments/customer review | 2020-09-11 | 2020-09-14 | 2 | 0 | 2 | 3 | 100% | 0.66667 | 1 | Completed
ER6378LT | W222 | W222.A24190 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Review of Hazop Study of Defuelling Process EAN (REV 000) | 2020-09-11 | 2020-09-17 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6378LT | W222 | W222.A23070 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Breached PVCW Assessmen EAN | 2020-09-11 | 2020-09-11 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A2620 | HNB Reactors Shutdown Essential Safety Cases | Appendix E – Detailed Description of Changes to Documentation - Peer Review | 2020-09-11 | 2020-09-14 | 2 | 0 | 2 | 3 | 100% | 0.66667 | 1 | Completed
ER6371LT | W202 | W202.A6040 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Panther Sensitivity Studies - Supplier mobilisation time | 2020-09-11 | 2020-09-17 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A6340 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Consequences EAN - Supplier mobilisation time | 2020-09-11 | 2020-09-15 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6371LT | W202 | W202.A6830 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Specified Flows - Supplier mobilisation time | 2020-09-11 | 2020-09-17 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A6980 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Determination of Cliff Edge - Supplier mobilisation time | 2020-09-11 | 2020-09-17 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | W206.A6040 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Panther Sensitivity Studies - Supplier mobilisation time | 2020-09-11 | 2020-09-17 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | W206.A6340 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Consequences EAN - Supplier mobilisation time | 2020-09-11 | 2020-09-15 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6661LT | W206 | W206.A6830 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Specified Flows - Supplier mobilisation time | 2020-09-11 | 2020-09-17 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | W206.A6980 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Determination of Cliff Edge - Supplier mobilisation time | 2020-09-11 | 2020-09-17 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6650LT | W226 | W226.A23070 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Breached PVCW Assessmen EAN | 2020-09-11 | 2020-09-11 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24190 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Review of Hazop Study of Defuelling Process EAN (REV 000) | 2020-09-11 | 2020-09-17 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A8630 | HNB Reactors Shutdown Essential Safety Cases | Containment Head Document - Final sign-off of verification | 2020-09-14 | 2020-09-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26770 | HRA Fuel Handling Essential Safety Case | Verify Fuel Route Operational Sequence/Process for Defuelling EAN and Issue for Technical Review (REV 001) | 2020-09-14 | 2020-10-15 | 5 | 0 | 24 | 31 | 100% | 0.16129 | 1 | Completed
ER6378LT | W222 | W222.A23080 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Breached PVCW Assessmen EAN to CDMS | 2020-09-14 | 2020-09-18 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6378LT | W222 | W222.A11500 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue HF Assessment of Fuel Free Verification EAN (System) | 2020-09-14 | 2020-09-18 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | A1160 | HNB Reactors Shutdown Essential Safety Cases | 10 – Conclusions - Summary | 2020-09-14 | 2020-10-09 | 20 | 0 | 20 | 25 | 100% | 0.8 | 1 | Completed
ER6370LT | W201 | A1900 | HNB Reactors Shutdown Essential Safety Cases | QA - CO and co-author review | 2020-09-14 | 2020-09-16 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6370LT | W201 | A1970 | HNB Reactors Shutdown Essential Safety Cases | Implementation Programme - Peer Review | 2020-09-14 | 2020-10-09 | 1 | 0 | 19 | 25 | 100% | 0.04 | 1 | Completed
ER6370LT | W201 | A2040 | HNB Reactors Shutdown Essential Safety Cases | Conclusions - Early Draft | 2020-09-14 | 2020-09-25 | 5 | 0 | 10 | 11 | 100% | 0.45455 | 1 | Completed
ER6650LT | W226 | W226.A11500 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue HF Assessment of Fuel Free Verification EAN (System) | 2020-09-14 | 2020-09-18 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6650LT | W226 | W226.A23080 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Breached PVCW Assessmen EAN to CDMS | 2020-09-14 | 2020-09-18 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6650LT | W226 | W226.A26770 | HYA Fuel Handling Essential Safety Case | Verify Fuel Route Operational Sequence/Process for Defuelling EAN and Issue for Technical Review (REV 001) | 2020-09-14 | 2020-10-15 | 5 | 0 | 24 | 31 | 100% | 0.16129 | 1 | Completed
ER6371LT | W202 | W202.A2540 | HRA Reactors Shutdown Essential Safety Cases | Issue Seismic Assessment of FPU within Reactor Report to EDF Review. | 2020-09-14 | 2020-09-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2540 | HYA Reactors Shutdown Essential Safety Cases | Issue Seismic Assessment of FPU within Reactor Report to EDF Review. | 2020-09-14 | 2020-09-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2930 | HYA Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Base Faults and Hazards) Report Completed - (HYA) | 2020-09-14 | 2020-09-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A27140 | HRA Fuel Handling Essential Safety Case | >>>INCOMING ENABLER (W202.A2206170) Confirm Requirements for Core Cooling Analysis | 2020-09-15 | 2020-09-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A27150 | HRA Fuel Handling Essential Safety Case | >>>MIRROR OF INCOMING ENABLER (W202) Confirm Requirements for Core Cooling Analysis | 2020-09-15 | 2020-09-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206170 | HRA Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W222.A27140) Confirm Requirements for Core Cooling Analysis | 2020-09-15 | 2020-09-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A27160 | HRA Fuel Handling Essential Safety Case | INTERFACE MILESTONE - (W202) Confirm Requirements for Core Cooling Analysis | 2020-09-15 | 2020-09-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27160 | HYA Fuel Handling Essential Safety Case | INTERFACE MILESTONE - (W202) Confirm Requirements for Core Cooling Analysis | 2020-09-15 | 2020-09-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27150 | HYA Fuel Handling Essential Safety Case | >>>MIRROR OF INCOMING ENABLER (W206) Confirm Requirements for Core Cooling Analysis | 2020-09-15 | 2020-09-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27140 | HYA Fuel Handling Essential Safety Case | >>>INCOMING ENABLER (W206) Confirm Requirements for Core Cooling Analysis | 2020-09-15 | 2020-09-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W226.A2206165 | HYA Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W226) Confirm Requirements for Core Cooling Analysis | 2020-09-15 | 2020-09-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3510 | HRA Reactors Shutdown Essential Safety Cases | Reactor Internals and Structural Integrity during Defuelling - Review Offer, prepare and issue CI | 2020-09-15 | 2020-09-21 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A2550 | HRA Reactors Shutdown Essential Safety Cases | Seismic Assessment of FPU within Reactor Report Reviewed by EDF SQEP | 2020-09-15 | 2020-09-28 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6661LT | W206 | W206.A3510 | HYA Reactors Shutdown Essential Safety Cases | Reactor Internals and Structural Integrity during Defuelling - Review Offer, prepare and issue CI | 2020-09-15 | 2020-09-21 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | W206.A2550 | HYA Reactors Shutdown Essential Safety Cases | Seismic Assessment of FPU within Reactor Report Reviewed by EDF SQEP | 2020-09-15 | 2020-09-28 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6370LT | W201 | ER6370.A4700 | HNB Reactors Shutdown Essential Safety Cases | Core Cooling Head Document Draft Report - Resolution Meeting | 2020-09-15 | 2020-09-15 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A2630 | HNB Reactors Shutdown Essential Safety Cases | Appendix E – Detailed Description of Changes to Documentation - Draft Complete | 2020-09-15 | 2020-09-15 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A8570 | HNB Reactors Shutdown Essential Safety Cases | Containment Head Document Report Completed | 2020-09-15 | 2020-09-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2680 | HRA Reactors Shutdown Essential Safety Cases | TSA Issue Final Fault Schedule Review (Plant Base Faults and Hazards) Report - (HRA) | 2020-09-15 | 2020-09-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A44590 | HRA Reactors Shutdown Essential Safety Cases | Confirm Requirements for Core Cooling Analysis | 2020-09-15 | 2020-09-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A44590 | HYA Reactors Shutdown Essential Safety Cases | Confirm Requirements for Core Cooling Analysis | 2020-09-15 | 2020-09-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4720 | HNB Reactors Shutdown Essential Safety Cases | Core Cooling Head Document Report - HOLD POINT - REVIEW COMMENTS AND RE-FORECAST | 2020-09-15 | 2020-09-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2700 | HRA Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Base Faults and Hazards) Report TR Completed and uploaded to CDMS - (HRA) | 2020-09-16 | 2020-09-29 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6371LT | W202 | W202.A3270 | HRA Reactors Shutdown Essential Safety Cases | Review of HHB LSD Strategy Deliverable | 2020-09-16 | 2020-10-16 | 20 | 0 | 22 | 30 | 100% | 0.66667 | 1 | Completed
ER6661LT | W206 | W206.A3270 | HYA Reactors Shutdown Essential Safety Cases | Review of HHB LSD Strategy Deliverable | 2020-09-16 | 2020-10-16 | 20 | 0 | 22 | 30 | 100% | 0.66667 | 1 | Completed
ER6370LT | W201 | ER6370.A4710 | HNB Reactors Shutdown Essential Safety Cases | Core Cooling Head Document Draft Report - Author Update Draft | 2020-09-16 | 2020-09-24 | 5 | 0 | 6 | 8 | 100% | 0.625 | 1 | Completed
ER6378LT | W222 | W222.A26430 | HRA Fuel Handling Essential Safety Case | Verify Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection & Issue for Technical Review | 2020-09-16 | 2020-10-12 | 5 | 0 | 18 | 26 | 100% | 0.19231 | 1 | Completed
ER6371LT | W202 | W202.A6350 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Consequences EAN - Pre Job Brief | 2020-09-16 | 2020-09-16 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A6350 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Consequences EAN - Pre Job Brief | 2020-09-16 | 2020-09-16 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26430 | HYA Fuel Handling Essential Safety Case | Verify Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection & Issue for Technical Review | 2020-09-16 | 2020-10-12 | 5 | 0 | 18 | 26 | 100% | 0.19231 | 1 | Completed
ER6378LT | W222 | W222.A23700 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Confirm Acceptability of CSP Pillars EAN | 2020-09-17 | 2020-09-23 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | A1910 | HNB Reactors Shutdown Essential Safety Cases | QA - Mature Draft | 2020-09-17 | 2020-09-18 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6650LT | W226 | W226.A23700 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Confirm Acceptability of CSP Pillars EAN | 2020-09-17 | 2020-09-23 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A6050 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Panther Sensitivity Studies - Pre Job Brief | 2020-09-18 | 2020-09-18 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A6840 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Specified Flows - Pre Job Brief | 2020-09-18 | 2020-09-18 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A6990 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Determination of Cliff Edge - Pre Job Brief | 2020-09-18 | 2020-09-18 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A6050 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Panther Sensitivity Studies - Pre Job Brief | 2020-09-18 | 2020-09-18 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A6840 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Specified Flows - Pre Job Brief | 2020-09-18 | 2020-09-18 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A6990 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Determination of Cliff Edge - Pre Job Brief | 2020-09-18 | 2020-09-18 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A23090 | HRA Fuel Handling Essential Safety Case | Criticality Assessment for Breached PVCW Assessmen EAN Available | 2020-09-18 | 2020-09-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23090 | HYA Fuel Handling Essential Safety Case | Criticality Assessment for Breached PVCW Assessmen EAN Available | 2020-09-18 | 2020-09-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A23420 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue CSP Model and Static Analysis EAN | 2020-09-21 | 2021-01-05 | 5 | 0 | 73 | 106 | 100% | 0.04717 | 1 | Completed
ER6378LT | W222 | W222.A11510 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload HF Assessment of Fuel Free Verification EAN to CDMS (System) | 2020-09-21 | 2020-10-07 | 5 | 0 | 12 | 16 | 100% | 0.3125 | 1 | Completed
ER6370LT | W201 | A1820 | HNB Reactors Shutdown Essential Safety Cases | Claim 5 - Peer Review | 2020-09-21 | 2020-09-25 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | A1850 | HNB Reactors Shutdown Essential Safety Cases | SC Margins, Judgements and Challenges - CO and co-author review | 2020-09-21 | 2020-09-23 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6370LT | W201 | A1920 | HNB Reactors Shutdown Essential Safety Cases | QA - Peer Review | 2020-09-21 | 2020-10-09 | 5 | 0 | 15 | 18 | 100% | 0.27778 | 1 | Completed
ER6370LT | W201 | A2030 | HNB Reactors Shutdown Essential Safety Cases | INSA - Draft Complete | 2020-09-21 | 2020-09-25 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | A2130 | HNB Reactors Shutdown Essential Safety Cases | NSC Request for Consideration and Advice - Draft Complete | 2020-09-21 | 2020-10-02 | 5 | 0 | 10 | 11 | 100% | 0.45455 | 1 | Completed
ER6370LT | W201 | A2170 | HNB Reactors Shutdown Essential Safety Cases | Appendix – Description of Existing Safety Case - Peer Review | 2020-09-21 | 2020-09-23 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6370LT | W201 | A2200 | HNB Reactors Shutdown Essential Safety Cases | Appendix – OPEX - CO and co-author review | 2020-09-21 | 2020-09-25 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | A2700 | HNB Reactors Shutdown Essential Safety Cases | Summary - CO and co-author review | 2020-09-21 | 2020-09-25 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6371LT | W202 | W202.A6070 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Prepare Panther Sensitivity Studies Draft Report | 2020-09-21 | 2020-10-16 | 20 | 0 | 20 | 25 | 100% | 0.8 | 1 | Completed
ER6371LT | W202 | W202.A6060 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Panther Sensitivity Studies Summary | 2020-09-21 | 2021-01-15 | 82 | 0 | 82 | 116 | 100% | 0.7069 | 1 | Completed
ER6371LT | W202 | W202.A6710 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Prepare Specified Flows Draft Report | 2020-09-21 | 2020-11-20 | 20 | 0 | 45 | 60 | 100% | 0.33333 | 1 | Completed
ER6371LT | W202 | W202.A6700 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Specified Flows Summary | 2020-09-21 | 2021-02-12 | 102 | 0 | 102 | 144 | 100% | 0.70833 | 1 | Completed
ER6371LT | W202 | W202.A6860 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Prepare Determination of Cliff Edge Draft Report | 2020-09-21 | 2020-10-23 | 20 | 0 | 24 | 32 | 100% | 0.625 | 1 | Completed
ER6371LT | W202 | W202.A6850 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Determination of Cliff Edge Summary | 2020-09-21 | 2021-01-20 | 85 | 0 | 85 | 121 | 100% | 0.70248 | 1 | Completed
ER6661LT | W206 | W206.A6070 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Prepare Panther Sensitivity Studies Draft Report | 2020-09-21 | 2020-10-16 | 20 | 0 | 20 | 25 | 100% | 0.8 | 1 | Completed
ER6661LT | W206 | W206.A6060 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Panther Sensitivity Studies Summary | 2020-09-21 | 2021-01-15 | 82 | 0 | 82 | 116 | 100% | 0.7069 | 1 | Completed
ER6661LT | W206 | W206.A6710 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Prepare Specified Flows Draft Report | 2020-09-21 | 2020-11-20 | 20 | 0 | 45 | 60 | 100% | 0.33333 | 1 | Completed
ER6661LT | W206 | W206.A6700 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Specified Flows Summary | 2020-09-21 | 2021-02-12 | 102 | 0 | 102 | 144 | 100% | 0.70833 | 1 | Completed
ER6661LT | W206 | W206.A6860 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Prepare Determination of Cliff Edge Draft Report | 2020-09-21 | 2020-10-23 | 20 | 0 | 24 | 32 | 100% | 0.625 | 1 | Completed
ER6661LT | W206 | W206.A6850 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Determination of Cliff Edge Summary | 2020-09-21 | 2021-01-20 | 85 | 0 | 85 | 121 | 100% | 0.70248 | 1 | Completed
ER6650LT | W226 | W226.A11510 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload HF Assessment of Fuel Free Verification EAN to CDMS (System) | 2020-09-21 | 2020-10-07 | 5 | 0 | 12 | 16 | 100% | 0.3125 | 1 | Completed
ER6650LT | W226 | W226.A23420 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue CSP Model and Static Analysis EAN | 2020-09-21 | 2021-01-05 | 5 | 0 | 73 | 106 | 100% | 0.04717 | 1 | Completed
ER6370LT | W201 | ER6370.A18270 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 187> - RFS - OPEX/ Literature Review - Draft and issue RFS | 2020-09-21 | 2020-09-30 | 8 | 0 | 8 | 9 | 100% | 0.88889 | 1 | Completed
ER6370LT | W201 | ER6370.A18195 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 187> - RFS - OPEX/ Literature Review Summary | 2020-09-21 | 2020-11-16 | 41 | 0 | 41 | 56 | 100% | 0.73214 | 1 | Completed
ER6371LT | W202 | W202.A3560 | HRA Reactors Shutdown Essential Safety Cases | Reactor Internals and Structural Integrity during Defuelling - Supplier mobilisation time | 2020-09-22 | 2020-09-30 | 10 | 0 | 6 | 8 | 100% | 1.25 | 1 | Completed
ER6661LT | W206 | W206.A3560 | HYA Reactors Shutdown Essential Safety Cases | Reactor Internals and Structural Integrity during Defuelling - Supplier mobilisation time | 2020-09-22 | 2020-09-30 | 10 | 0 | 6 | 8 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | A2050 | HNB Reactors Shutdown Essential Safety Cases | Conclusions - CO and co-author review | 2020-09-22 | 2020-10-02 | 4 | 0 | 9 | 10 | 100% | 0.4 | 1 | Completed
ER6378LT | W222 | W222.A26990 | HRA Fuel Handling Essential Safety Case | Hold Risk Workshop | 2020-09-22 | 2020-09-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26990 | HYA Fuel Handling Essential Safety Case | Hold Risk Workshop | 2020-09-22 | 2020-09-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1780 | HNB Reactors Shutdown Essential Safety Cases | Claim 4 - Draft Complete | 2020-09-23 | 2020-09-25 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6370LT | W201 | ER6370.A17630 | HNB Reactors Shutdown Essential Safety Cases | Core Cooling Head Document Report - Verifiers sign-off and provide verification statement | 2020-09-24 | 2020-10-07 | 3 | 0 | 9 | 13 | 100% | 0.23077 | 1 | Completed
ER6378LT | W222 | W222.A11650 | HRA Fuel Handling Essential Safety Case | Human Factors Integration Plan EAN Available (REV 000) | 2020-09-24 | 2020-09-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A11650 | HYA Fuel Handling Essential Safety Case | Human Factors Integration Plan EAN Available (REV 000) | 2020-09-24 | 2020-09-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24200 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Hazop Study of Defuelling Process EAN to CDMS (REV 000) | 2020-09-24 | 2020-10-09 | 5 | 0 | 11 | 15 | 100% | 0.33333 | 1 | Completed
ER6378LT | W222 | W222.A23710 | HRA Fuel Handling Essential Safety Case | Complete and Upload Confirm Acceptability of CSP Pillars EAN to CDMS | 2020-09-24 | 2020-12-01 | 5 | 0 | 49 | 68 | 100% | 0.073529 | 1 | Completed
ER6650LT | W226 | W226.A23710 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Confirm Acceptability of CSP Pillars EAN to CDMS | 2020-09-24 | 2020-12-01 | 5 | 0 | 49 | 68 | 100% | 0.073529 | 1 | Completed
ER6650LT | W226 | W226.A24200 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Hazop Study of Defuelling Process EAN to CDMS (REV 000) | 2020-09-24 | 2020-10-09 | 5 | 0 | 11 | 15 | 100% | 0.33333 | 1 | Completed
ER6370LT | W201 | ER6370.A18150 | HNB Reactors Shutdown Essential Safety Cases | Prepare for Verification Pre-job Brief | 2020-09-25 | 2020-09-30 | 4 | 0 | 4 | 5 | 100% | 0.8 | 1 | Completed
ER6378LT | W222 | W222.A25990 | HRA Fuel Handling Essential Safety Case | Complex FEA (Dynamic R3 Analysis) ##(Cost Summary)## (C5) (NEW) | 2020-09-28 | 2021-05-28 | 188 | 0 | 169 | 242 | 100% | 0.77686 | 1 | Completed
ER6378LT | W222 | W222.A23450 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Complex FEA (Dynamic R3 Analysis) EAN | 2020-09-28 | 2020-09-28 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1860 | HNB Reactors Shutdown Essential Safety Cases | SC Margins, Judgements and Challenges - Mature Draft | 2020-09-28 | 2020-09-30 | 2 | 0 | 2 | 2 | 100% | 1 | 1 | Completed
ER6378LT | W222 | W222.A26900 | HRA Fuel Handling Essential Safety Case | PRC Members Review Scheme Documentation | 2020-09-28 | 2020-10-05 | 5 | 0 | 6 | 7 | 100% | 0.71429 | 1 | Completed
ER6650LT | W226 | W226.A23450 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Complex FEA (Dynamic R3 Analysis) EAN | 2020-09-28 | 2020-09-29 | 1 | 0 | 1 | 1 | 100% | 1 | 1 | Completed
ER6650LT | W226 | W226.A25990 | HYA Fuel Handling Essential Safety Case | Complex FEA (Dynamic R3 Analysis) ##(Cost Summary)## (C5) (NEW) | 2020-09-28 | 2021-05-28 | 188 | 0 | 169 | 242 | 100% | 0.77686 | 1 | Completed
ER6370LT | W201 | A2770 | HNB Reactors Shutdown Essential Safety Cases | Appendix F – TIDYING AND EDITORIAL STUFF, Responding to Station Comments | 2020-09-28 | 2020-10-09 | 1 | 0 | 9 | 11 | 100% | 0.090909 | 1 | Completed
ER6370LT | W201 | ER6370.A2160 | HNB Reactors Shutdown Essential Safety Cases | Lead Verifier Familiarisation | 2020-09-28 | 2020-10-09 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | A1700 | HNB Reactors Shutdown Essential Safety Cases | Claim 3 - CO and co-author review | 2020-09-28 | 2020-09-29 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | A1830 | HNB Reactors Shutdown Essential Safety Cases | Claim 5 - Draft Complete | 2020-09-28 | 2020-10-07 | 5 | 0 | 8 | 9 | 100% | 0.55556 | 1 | Completed
ER6370LT | W201 | A2210 | HNB Reactors Shutdown Essential Safety Cases | Appendix – OPEX - Mature Draft | 2020-09-28 | 2020-09-30 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6370LT | W201 | A2670 | HNB Reactors Shutdown Essential Safety Cases | Appendix F – Previous Advice from NSC - Peer Review | 2020-09-28 | 2020-09-30 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6370LT | W201 | A2710 | HNB Reactors Shutdown Essential Safety Cases | Summary - Mature Draft | 2020-09-28 | 2020-09-30 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6372LT | W203 | W203.A1130 | HNB Enhanced Defuelling Safety Cases | Gate A PRC Paper Submission | 2020-09-28 | 2020-09-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A27050 | HRA Fuel Handling Essential Safety Case | Issue Scheme Paper to PRC Members | 2020-09-28 | 2020-09-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27050 | HYA Fuel Handling Essential Safety Case | Issue Scheme Paper to PRC Members | 2020-09-28 | 2020-09-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26900 | HYA Fuel Handling Essential Safety Case | PRC Members Review Scheme Documentation | 2020-09-28 | 2020-10-05 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6378LT | W222 | W222.A25710 | HRA Fuel Handling Essential Safety Case | Production of Hazard and Interlock Schedule ##(Cost Summary)## ### (C2) | 2020-09-29 | 2021-07-14 | 205 | 0 | 199 | 288 | 100% | 0.71181 | 1 | Completed
ER6378LT | W222 | W222.A25200 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Hazard and Interlock Schedule (REV 000) EAN | 2020-09-29 | 2020-09-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A23460 | HRA Fuel Handling Essential Safety Case | Draft Complex FEA (Dynamic R3 Analysis) EAN | 2020-09-29 | 2021-04-01 | 13 | 0 | 130 | 184 | 100% | 0.070652 | 1 | Completed
ER6650LT | W226 | W226.A23460 | HYA Fuel Handling Essential Safety Case | Draft Complex FEA (Dynamic R3 Analysis) EAN | 2020-09-29 | 2021-04-01 | 13 | 0 | 130 | 184 | 100% | 0.070652 | 1 | Completed
ER6650LT | W226 | W226.A25200 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Hazard and Interlock Schedule (REV 000) EAN | 2020-09-29 | 2020-09-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25710 | HYA Fuel Handling Essential Safety Case | Production of Hazard and Interlock Schedule ##(Cost Summary)## ### (C2) | 2020-09-29 | 2021-07-14 | 205 | 0 | 200 | 288 | 100% | 0.71181 | 1 | Completed
ER6371LT | W202 | W202.A2690 | HRA Reactors Shutdown Essential Safety Cases | Address Comments on Reviewed Seismic Assessment of FPU within Reactor Report | 2020-09-29 | 2020-10-26 | 10 | 0 | 19 | 27 | 100% | 0.37037 | 1 | Completed
ER6661LT | W206 | W206.A2690 | HYA Reactors Shutdown Essential Safety Cases | Address Comments on Reviewed Seismic Assessment of FPU within Reactor Report | 2020-09-29 | 2020-10-26 | 10 | 0 | 19 | 27 | 100% | 0.37037 | 1 | Completed
ER6372LT | W203 | W203.A1240 | HNB Enhanced Defuelling Safety Cases | Effect of air admission on reactor containment (Coolant conditions CO2) EAN up Rev - Prepare Draft Report | 2020-09-29 | 2020-12-18 | 10 | 0 | 59 | 80 | 100% | 0.125 | 1 | Completed
ER6372LT | W203 | W203.A1230 | HNB Enhanced Defuelling Safety Cases | Effect of air admission on reactor containment (Coolant conditions CO2) EAN up Rev - Summary | 2020-09-29 | 2021-06-28 | 188 | 0 | 188 | 272 | 100% | 0.69118 | 1 | Completed
ER6371LT | W202 | W202.A2930 | HRA Reactors Shutdown Essential Safety Cases | Fault Schedule Review (Plant Base Faults and Hazards) Report Completed - (HRA) | 2020-09-29 | 2020-09-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1870 | HNB Reactors Shutdown Essential Safety Cases | SC Margins, Judgements and Challenges - Peer Review | 2020-09-30 | 2020-10-02 | 2 | 0 | 3 | 2 | 100% | 1 | 1 | Completed
ER6370LT | W201 | A1710 | HNB Reactors Shutdown Essential Safety Cases | Claim 3 - Mature Draft | 2020-09-30 | 2020-10-02 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6370LT | W201 | ER6370.A2170 | HNB Reactors Shutdown Essential Safety Cases | Verification Pre-job Brief | 2020-09-30 | 2020-09-30 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2360 | HRA Reactors Shutdown Essential Safety Cases | HF Risk Assessment Draft Report Verified by TSA | 2020-10-01 | 2020-10-01 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2460 | HRA Reactors Shutdown Essential Safety Cases | Verified HF Risk Assessment Draft Report Issued to EDF for Technical Review. | 2020-10-01 | 2020-10-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2490 | HRA Reactors Shutdown Essential Safety Cases | HF Risk Assessment Draft Report Technically Reviewed by EDF SQEP | 2020-10-01 | 2020-10-01 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2670 | HRA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd HF Risk Assessment Draft Report | 2020-10-01 | 2020-10-01 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2830 | HRA Reactors Shutdown Essential Safety Cases | TSA Issue Final HF Risk Assessment Report | 2020-10-01 | 2020-10-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2910 | HRA Reactors Shutdown Essential Safety Cases | HF Risk Assessment Report TR Completed and uploaded to CDMS | 2020-10-01 | 2020-10-01 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3090 | HRA Reactors Shutdown Essential Safety Cases | HF Risk Assessment Report Completed | 2020-10-01 | 2020-10-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2250 | HRA Reactors Shutdown Essential Safety Cases | HF Risk Assessment Summary | 2020-10-01 | 2020-10-02 | 60 | 0 | 1 | 1 | 100% | 60 | 1 | Completed
ER6371LT | W202 | W202.A2890 | HRA Reactors Shutdown Essential Safety Cases | Summary of Compliance with NSPs - Supplier prepare and issue Offer | 2020-10-01 | 2020-10-01 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3100 | HRA Reactors Shutdown Essential Safety Cases | Summary of Compliance with NSPs - Review Offer, prepare and issue CI | 2020-10-01 | 2020-10-01 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3170 | HRA Reactors Shutdown Essential Safety Cases | Summary of Compliance with NSPs - Supplier mobilisation time | 2020-10-01 | 2020-10-01 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2360 | HYA Reactors Shutdown Essential Safety Cases | HF Risk Assessment Draft Report Verified by TSA | 2020-10-01 | 2020-10-01 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2460 | HYA Reactors Shutdown Essential Safety Cases | Verified HF Risk Assessment Draft Report Issued to EDF for Technical Review. | 2020-10-01 | 2020-10-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2490 | HYA Reactors Shutdown Essential Safety Cases | HF Risk Assessment Draft Report Technically Reviewed by EDF SQEP | 2020-10-01 | 2020-10-01 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2670 | HYA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd HF Risk Assessment Draft Report | 2020-10-01 | 2020-10-01 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2830 | HYA Reactors Shutdown Essential Safety Cases | TSA Issue Final HF Risk Assessment Report | 2020-10-01 | 2020-10-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2910 | HYA Reactors Shutdown Essential Safety Cases | HF Risk Assessment Report TR Completed and uploaded to CDMS | 2020-10-01 | 2020-10-01 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2250 | HYA Reactors Shutdown Essential Safety Cases | HF Risk Assessment Summary | 2020-10-01 | 2020-10-02 | 60 | 0 | 1 | 1 | 100% | 60 | 1 | Completed
ER6661LT | W206 | W206.A2890 | HYA Reactors Shutdown Essential Safety Cases | Summary of Compliance with NSPs - Supplier prepare and issue Offer | 2020-10-01 | 2020-10-01 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3100 | HYA Reactors Shutdown Essential Safety Cases | Summary of Compliance with NSPs - Review Offer, prepare and issue CI | 2020-10-01 | 2020-10-01 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3170 | HYA Reactors Shutdown Essential Safety Cases | Summary of Compliance with NSPs - Supplier mobilisation time | 2020-10-01 | 2020-10-01 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2260 | HRA Reactors Shutdown Essential Safety Cases | Prepare HF Risk Assessment Draft Report | 2020-10-01 | 2020-10-02 | 20 | 0 | 1 | 1 | 100% | 20 | 1 | Completed
ER6371LT | W202 | W202.A3680 | HRA Reactors Shutdown Essential Safety Cases | Reactor Internals and Structural Integrity during Defuelling - Pre Job Brief | 2020-10-01 | 2020-10-02 | 1 | 0 | 1 | 1 | 100% | 1 | 1 | Completed
ER6371LT | W202 | W202.A3130 | HRA Reactors Shutdown Essential Safety Cases | Containment Head Document - Draft and issue RFS | 2020-10-01 | 2020-10-30 | 5 | 0 | 21 | 29 | 100% | 0.17241 | 1 | Completed
ER6371LT | W202 | W202.A3120 | HRA Reactors Shutdown Essential Safety Cases | RFS - Specification for Pressure Boundary Seals Summary | 2020-10-01 | 2021-01-07 | 66 | 0 | 67 | 98 | 100% | 0.67347 | 1 | Completed
ER6371LT | W202 | W202.A2880 | HRA Reactors Shutdown Essential Safety Cases | Supporting Plant - Draft and issue RFS | 2020-10-01 | 2020-10-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A2870 | HRA Reactors Shutdown Essential Safety Cases | RFS - Supporting Plant Summary | 2020-10-01 | 2020-11-19 | 33 | 0 | 35 | 49 | 100% | 0.67347 | 1 | Completed
ER6371LT | W202 | W202.A3300 | HRA Reactors Shutdown Essential Safety Cases | ALARP Report - Draft and issue RFS | 2020-10-01 | 2020-10-15 | 11 | 0 | 11 | 14 | 100% | 0.78571 | 1 | Completed
ER6371LT | W202 | W202.A3290 | HRA Reactors Shutdown Essential Safety Cases | RFS - ALARP Report Summary | 2020-10-01 | 2020-10-30 | 37 | 0 | 22 | 29 | 100% | 1.2759 | 1 | Completed
ER6661LT | W206 | W206.A2260 | HYA Reactors Shutdown Essential Safety Cases | Prepare HF Risk Assessment Draft Report | 2020-10-01 | 2020-10-02 | 20 | 0 | 1 | 1 | 100% | 20 | 1 | Completed
ER6661LT | W206 | W206.A3680 | HYA Reactors Shutdown Essential Safety Cases | Reactor Internals and Structural Integrity during Defuelling - Pre Job Brief | 2020-10-01 | 2020-10-02 | 1 | 0 | 1 | 1 | 100% | 1 | 1 | Completed
ER6661LT | W206 | W206.A3130 | HYA Reactors Shutdown Essential Safety Cases | Containment Head Document - Draft and issue RFS | 2020-10-01 | 2020-10-30 | 5 | 0 | 21 | 29 | 100% | 0.17241 | 1 | Completed
ER6661LT | W206 | W206.A3120 | HYA Reactors Shutdown Essential Safety Cases | RFS - Specification for Pressure Boundary Seals Summary | 2020-10-01 | 2021-01-07 | 74 | 0 | 67 | 98 | 100% | 0.7551 | 1 | Completed
ER6661LT | W206 | W206.A2880 | HYA Reactors Shutdown Essential Safety Cases | Supporting Plant - Draft and issue RFS | 2020-10-01 | 2020-10-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | W206.A2870 | HYA Reactors Shutdown Essential Safety Cases | RFS - Supporting Plant Summary | 2020-10-01 | 2020-11-19 | 33 | 0 | 35 | 49 | 100% | 0.67347 | 1 | Completed
ER6661LT | W206 | W206.A3300 | HYA Reactors Shutdown Essential Safety Cases | ALARP Report - Draft and issue RFS | 2020-10-01 | 2020-10-15 | 11 | 0 | 11 | 14 | 100% | 0.78571 | 1 | Completed
ER6661LT | W206 | W206.A3290 | HYA Reactors Shutdown Essential Safety Cases | RFS - ALARP Report Summary | 2020-10-01 | 2020-10-30 | 37 | 0 | 21 | 29 | 100% | 1.2759 | 1 | Completed
ER6378LT | W222 | W222.A25690 | HRA Fuel Handling Essential Safety Case | Criticality Assessment for Dropped FPU at Reactor ##(Cost Summary)## ### (C5) | 2020-10-01 | 2021-04-26 | 160 | 0 | 143 | 207 | 100% | 0.77295 | 1 | Completed
ER6378LT | W222 | W222.A25680 | HRA Fuel Handling Essential Safety Case | Adjacent Fuel Assembly Drop Assessment & Associated Radcons ##(Cost Summary)## ### (C5) | 2020-10-01 | 2021-04-28 | 147 | 0 | 144 | 209 | 100% | 0.70335 | 1 | Completed
ER6378LT | W222 | W222.A25340 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Update to Fault Schedule/PSA (REV 000) EAN | 2020-10-01 | 2020-10-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A9510 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Criticality Assessment for Dropped FPU at Reactor EAN | 2020-10-01 | 2020-10-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A9770 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN | 2020-10-01 | 2020-10-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A2220 | HNB Reactors Shutdown Essential Safety Cases | Appendix – OPEX - Peer Review | 2020-10-01 | 2020-10-02 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | A2680 | HNB Reactors Shutdown Essential Safety Cases | Appendix F – Previous Advice from NSC - Draft Complete | 2020-10-01 | 2020-10-02 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | A2720 | HNB Reactors Shutdown Essential Safety Cases | Summary - Peer Review | 2020-10-01 | 2020-10-02 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6371LT | W202 | W202.A6210 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> PVCW Management - Technical Lead | 2020-10-01 | 2021-02-01 | 65 | 0 | 84 | 123 | 100% | 0.52846 | 1 | Completed
ER6371LT | W202 | W202.A6200 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> PVCW Management Summary | 2020-10-01 | 2021-02-01 | 84 | 0 | 84 | 123 | 100% | 0.68293 | 1 | Completed
ER6371LT | W202 | W202.A6370 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Prepare Consequences EAN Draft Report | 2020-10-01 | 2020-10-26 | 32 | 0 | 17 | 25 | 100% | 1.28 | 1 | Completed
ER6371LT | W202 | W202.A6360 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Consequences EAN Summary | 2020-10-01 | 2021-01-13 | 67 | 0 | 71 | 104 | 100% | 0.64423 | 1 | Completed
ER6371LT | W202 | W202.A6510 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Prepare Optioneering EAN Draft Report | 2020-10-01 | 2020-11-02 | 32 | 0 | 23 | 32 | 100% | 1 | 1 | Completed
ER6371LT | W202 | W202.A6500 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Optioneering EAN Summary | 2020-10-01 | 2021-01-29 | 89 | 0 | 83 | 120 | 100% | 0.74167 | 1 | Completed
ER6661LT | W206 | W206.A6210 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> PVCW Management - Technical Lead | 2020-10-01 | 2021-02-01 | 74 | 0 | 84 | 123 | 100% | 0.60163 | 1 | Completed
ER6661LT | W206 | W206.A6200 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> PVCW Management Summary | 2020-10-01 | 2021-02-01 | 84 | 0 | 84 | 123 | 100% | 0.68293 | 1 | Completed
ER6661LT | W206 | W206.A6370 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Prepare Consequences EAN Draft Report | 2020-10-01 | 2020-10-26 | 32 | 0 | 17 | 25 | 100% | 1.28 | 1 | Completed
ER6661LT | W206 | W206.A6360 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Consequences EAN Summary | 2020-10-01 | 2021-01-13 | 84 | 0 | 71 | 104 | 100% | 0.80769 | 1 | Completed
ER6661LT | W206 | W206.A6510 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Prepare Optioneering EAN Draft Report | 2020-10-01 | 2020-11-02 | 32 | 0 | 23 | 32 | 100% | 1 | 1 | Completed
ER6661LT | W206 | W206.A6500 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Optioneering EAN Summary | 2020-10-01 | 2021-01-29 | 89 | 0 | 83 | 120 | 100% | 0.74167 | 1 | Completed
ER6650LT | W226 | W226.A9770 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN | 2020-10-01 | 2020-10-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A9510 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Criticality Assessment for Dropped FPU at Reactor EAN | 2020-10-01 | 2020-10-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25340 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Update to Fault Schedule/PSA (REV 000) EAN | 2020-10-01 | 2020-10-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25680 | HYA Fuel Handling Essential Safety Case | Adjacent Fuel Assembly Drop Assessment & Associated Radcons ##(Cost Summary)## ### (C5) | 2020-10-01 | 2021-04-28 | 147 | 0 | 144 | 209 | 100% | 0.70335 | 1 | Completed
ER6650LT | W226 | W226.A25690 | HYA Fuel Handling Essential Safety Case | Criticality Assessment for Dropped FPU at Reactor ##(Cost Summary)## ### (C5) | 2020-10-01 | 2021-04-26 | 160 | 0 | 143 | 207 | 100% | 0.77295 | 1 | Completed
ER6370LT | W201 | ER6370.A18280 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 187> - RFS - OPEX/ Literature Review - Supplier prepare and issue Offer | 2020-10-01 | 2020-10-14 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6378LT | W222 | W222.A27205 | HRA Fuel Handling Essential Safety Case | Produce H&I Schedules for All Facilities (FM/Ponds etc) | 2020-10-01 | 2021-03-02 | 1 | 0 | 106 | 152 | 100% | 0.0065789 | 1 | Completed
ER6650LT | W226 | W226.A27205 | HYA Fuel Handling Essential Safety Case | Produce H&I Schedules for All Facilities | 2020-10-01 | 2021-03-02 | 1 | 0 | 106 | 152 | 100% | 0.0065789 | 1 | Completed
ER6371LT | W202 | W202.A3020 | HRA Reactors Shutdown Essential Safety Cases | Review of HRA Defuelling Case against the NSPs Report Completed | 2020-10-02 | 2020-10-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3070 | HRA Reactors Shutdown Essential Safety Cases | Review of HRA Defuelling Case against the NSPs - PJDB | 2020-10-02 | 2020-10-09 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6661LT | W206 | W206.A3090 | HYA Reactors Shutdown Essential Safety Cases | HF Risk Assessment Report Completed | 2020-10-02 | 2020-10-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3020 | HYA Reactors Shutdown Essential Safety Cases | Review of HYA Defuelling Case against the NSPs Report Completed | 2020-10-02 | 2020-10-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3070 | HYA Reactors Shutdown Essential Safety Cases | Review of HYA Defuelling Case against the NSPs - PJDB | 2020-10-02 | 2020-10-09 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6650LT | W226 | W226.A12380 | HYA Fuel Handling Essential Safety Case | Draft Confirm Adequate Capacity for Solid Waste Arisings from Stringer Dismantling EAN | 2020-10-02 | 2020-10-08 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A3710 | HRA Reactors Shutdown Essential Safety Cases | Prepare Reactor Internals and Structural Integrity during Defuelling Report | 2020-10-02 | 2020-11-27 | 50 | 0 | 41 | 56 | 100% | 0.89286 | 1 | Completed
ER6371LT | W202 | W202.A3700 | HRA Reactors Shutdown Essential Safety Cases | Reactor Internals and Structural Integrity during Defuelling Report Summary | 2020-10-02 | 2021-01-27 | 88 | 0 | 80 | 117 | 100% | 0.75214 | 1 | Completed
ER6661LT | W206 | W206.A3710 | HYA Reactors Shutdown Essential Safety Cases | Prepare Reactor Internals and Structural Integrity during Defuelling Report | 2020-10-02 | 2020-11-27 | 50 | 0 | 41 | 56 | 100% | 0.89286 | 1 | Completed
ER6661LT | W206 | W206.A3700 | HYA Reactors Shutdown Essential Safety Cases | Reactor Internals and Structural Integrity during Defuelling Report Summary | 2020-10-02 | 2021-01-27 | 88 | 0 | 80 | 117 | 100% | 0.75214 | 1 | Completed
ER6378LT | W222 | W222.A9520 | HRA Fuel Handling Essential Safety Case | Draft Criticality Assessment for Dropped FPU at Reactor EAN | 2020-10-02 | 2021-04-26 | 20 | 0 | 142 | 206 | 100% | 0.097087 | 1 | Completed
ER6378LT | W222 | W222.A9780 | HRA Fuel Handling Essential Safety Case | Draft Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN | 2020-10-02 | 2020-10-30 | 21 | 0 | 21 | 28 | 100% | 0.75 | 1 | Completed
ER6378LT | W222 | W222.A12380 | HRA Fuel Handling Essential Safety Case | Draft Confirm Adequate Capacity for Solid Waste Arisings from Stringer Dismantling EAN | 2020-10-02 | 2020-10-08 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6650LT | W226 | W226.A9780 | HYA Fuel Handling Essential Safety Case | Draft Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN | 2020-10-02 | 2020-10-30 | 21 | 0 | 21 | 28 | 100% | 0.75 | 1 | Completed
ER6650LT | W226 | W226.A9520 | HYA Fuel Handling Essential Safety Case | Draft Criticality Assessment for Dropped FPU at Reactor EAN | 2020-10-02 | 2021-04-26 | 20 | 0 | 142 | 206 | 100% | 0.097087 | 1 | Completed
ER6378LT | W222 | W222.A27230 | HRA Fuel Handling Essential Safety Case | PSA Modelling | 2020-10-02 | 2021-03-30 | 56 | 0 | 124 | 179 | 100% | 0.31285 | 1 | Completed
ER6650LT | W226 | W226.A27230 | HYA Fuel Handling Essential Safety Case | PSA Modelling | 2020-10-02 | 2021-03-30 | 56 | 0 | 124 | 179 | 100% | 0.31285 | 1 | Completed
ER6378LT | W222 | W222.A23790 | HRA Fuel Handling Essential Safety Case | Shock Absorbers Feasibility Study EAN Available | 2020-10-02 | 2020-10-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23790 | HYA Fuel Handling Essential Safety Case | Shock Absorbers Feasibility Study EAN Available | 2020-10-02 | 2020-10-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1280 | HNB Reactors Shutdown Essential Safety Cases | Obtain peer review (if required) (HNB) | 2020-10-05 | 2020-10-09 | 4 | 0 | 5 | 4 | 100% | 1 | 1 | Completed
ER6370LT | W201 | ER6370.A1360 | HNB Reactors Shutdown Essential Safety Cases | SC - Safety Case development - Cat 1 Case verification & SA - HNB - B-C | 2020-10-05 | 2021-05-05 | 56 | 0 | 147 | 212 | 100% | 0.26415 | 1 | Completed
ER6371LT | W202 | W202.A2710 | HRA Reactors Shutdown Essential Safety Cases | Shutdown Margin Workshop - Discovery MS - Confirm no Further SDM Analysis Required | 2020-10-05 | 2020-10-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3760 | HRA Reactors Shutdown Essential Safety Cases | Prepare ALARP Strategy - Confirm HHB Strategy Applicable to HRA Report | 2020-10-05 | 2020-10-09 | 25 | 0 | 4 | 4 | 100% | 6.25 | 1 | Completed
ER6371LT | W202 | W202.A3750 | HRA Reactors Shutdown Essential Safety Cases | ALARP Strategy - Confirm HHB Strategy Applicable to HRA Report Summary | 2020-10-05 | 2020-10-20 | 80 | 0 | 11 | 15 | 100% | 5.3333 | 1 | Completed
ER6661LT | W206 | W206.A2710 | HYA Reactors Shutdown Essential Safety Cases | Shutdown Margin Workshop - Discovery MS - Confirm no Further SDM Analysis Required | 2020-10-05 | 2020-10-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3760 | HYA Reactors Shutdown Essential Safety Cases | Prepare ALARP Strategy - Confirm HHB Strategy Applicable to HYA Report | 2020-10-05 | 2020-10-09 | 25 | 0 | 4 | 4 | 100% | 6.25 | 1 | Completed
ER6661LT | W206 | W206.A3750 | HYA Reactors Shutdown Essential Safety Cases | ALARP Strategy - Confirm HHB Strategy Applicable to HYA Report Summary | 2020-10-05 | 2020-10-20 | 80 | 0 | 11 | 15 | 100% | 5.3333 | 1 | Completed
ER6378LT | W222 | W222.A23820 | HRA Fuel Handling Essential Safety Case | Verify Detailed Option Investigation EAN for Technical Review | 2020-10-05 | 2020-10-16 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | A1880 | HNB Reactors Shutdown Essential Safety Cases | SC Margins, Judgements and Challenges - Draft Complete | 2020-10-05 | 2020-10-06 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | A2060 | HNB Reactors Shutdown Essential Safety Cases | Conclusions - Mature Draft | 2020-10-05 | 2020-10-06 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | A2230 | HNB Reactors Shutdown Essential Safety Cases | Appendix – OPEX - Draft Complete | 2020-10-05 | 2020-10-07 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6650LT | W226 | W226.A23820 | HYA Fuel Handling Essential Safety Case | Verify Detailed Option Investigation EAN for Technical Review | 2020-10-05 | 2020-10-16 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6650LT | W226 | W226.A26930 | HYA Fuel Handling Essential Safety Case | Hold PRC Meeting | 2020-10-06 | 2020-10-06 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2480 | HRA Reactors Shutdown Essential Safety Cases | General HF Oversight and HFIP Updates and Revisions Draft EAN Verified by TSA | 2020-10-06 | 2020-10-26 | 10 | 0 | 14 | 20 | 100% | 0.5 | 1 | Completed
ER6661LT | W206 | W206.A2480 | HYA Reactors Shutdown Essential Safety Cases | General HF Oversight and HFIP Updates and Revisions Draft EAN Verified by TSA | 2020-10-06 | 2020-10-26 | 10 | 0 | 14 | 20 | 100% | 0.5 | 1 | Completed
ER6370LT | W201 | A2730 | HNB Reactors Shutdown Essential Safety Cases | Summary - Draft Complete | 2020-10-06 | 2020-10-07 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6372LT | W203 | W203.A1140 | HNB Enhanced Defuelling Safety Cases | Hold PRC | 2020-10-06 | 2020-10-06 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26930 | HRA Fuel Handling Essential Safety Case | Hold PRC Meeting | 2020-10-06 | 2020-10-06 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1150 | HNB Enhanced Defuelling Safety Cases | Gate A PRC Paper Approval | 2020-10-06 | 2020-10-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4260 | HNB Reactors Shutdown Essential Safety Cases | Core Cooling Head Document Report Verification Completed and uploaded to CDMS | 2020-10-07 | 2020-10-07 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206110 | HRA Reactors Shutdown Essential Safety Cases | >>>INCOMING ENABLER (W202.A22350) HF Assessment of Fuel Free Verification EAN Available(TO BE DELETED) | 2020-10-07 | 2020-10-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A11520 | HRA Fuel Handling Essential Safety Case | HF Assessment of Fuel Free Verification EAN Available (System) | 2020-10-07 | 2020-10-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A22350 | HRA Fuel Handling Essential Safety Case | >>>OUTGOING ENABLER (W202.A1320?) HF Assessment of Fuel Free Verification EAN Available | 2020-10-07 | 2020-10-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26920 | HYA Fuel Handling Essential Safety Case | Modify Estimate, Schedule & Risk Log as Required | 2020-10-07 | 2020-10-08 | 2 | 0 | 1 | 1 | 100% | 2 | 1 | Completed
ER6650LT | W226 | W226.A11520 | HYA Fuel Handling Essential Safety Case | HF Assessment of Fuel Free Verification EAN Available (System) | 2020-10-07 | 2020-10-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27210 | HYA Fuel Handling Essential Safety Case | >>>OUTGOING ENABLER (W206.A1320?) HF Assessment of Fuel Free Verification EAN Available | 2020-10-07 | 2020-10-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A1720 | HNB Reactors Shutdown Essential Safety Cases | Claim 3 - Peer Review | 2020-10-07 | 2020-10-07 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A2070 | HNB Reactors Shutdown Essential Safety Cases | Conclusions - Peer Review | 2020-10-07 | 2020-10-09 | 1 | 0 | 3 | 2 | 100% | 0.5 | 1 | Completed
ER6378LT | W222 | W222.A26920 | HRA Fuel Handling Essential Safety Case | Modify Estimate, Schedule & Risk Log as Required | 2020-10-07 | 2020-10-08 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6371LT | W202 | W202.A3350 | HRA Reactors Shutdown Essential Safety Cases | Summary of Compliance with NSPs - Pre Job Brief | 2020-10-08 | 2020-10-08 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3350 | HYA Reactors Shutdown Essential Safety Cases | Summary of Compliance with NSPs - Pre Job Brief | 2020-10-08 | 2020-10-08 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A17640 | HNB Reactors Shutdown Essential Safety Cases | Core Cooling Head Document Report - CDMS route list approval | 2020-10-08 | 2020-10-09 | 3 | 0 | 1 | 1 | 100% | 3 | 1 | Completed
ER6371LT | W202 | W202.A3000 | HRA Reactors Shutdown Essential Safety Cases | Supporting Plant - Supplier prepare and issue Offer | 2020-10-08 | 2020-10-21 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6661LT | W206 | W206.A3000 | HYA Reactors Shutdown Essential Safety Cases | Supporting Plant - Supplier prepare and issue Offer | 2020-10-08 | 2020-10-21 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6370LT | W201 | A1730 | HNB Reactors Shutdown Essential Safety Cases | Claim 3 - Draft Complete | 2020-10-08 | 2020-10-09 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | A1930 | HNB Reactors Shutdown Essential Safety Cases | QA - Draft Complete | 2020-10-08 | 2020-10-09 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | A2080 | HNB Reactors Shutdown Essential Safety Cases | Conclusions - Draft Complete | 2020-10-08 | 2020-10-09 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | A2180 | HNB Reactors Shutdown Essential Safety Cases | Appendix – Description of Existing Safety Case - Draft Complete | 2020-10-08 | 2020-10-09 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | ER6370.A1630 | HNB Reactors Shutdown Essential Safety Cases | Verification Commenced (T-11) (HNB) | 2020-10-09 | 2020-10-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A4270 | HNB Reactors Shutdown Essential Safety Cases | Core Cooling Head Document Report Completed | 2020-10-09 | 2020-10-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16150 | HNB Reactors Shutdown Essential Safety Cases | Safety Case Proposal Authoring Draft Complete EC 364023 <NSRS SC Approach & Outline>(Cat 1 KDM) (HNB) RS Essential SC | 2020-10-09 | 2020-10-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16810 | HNB Reactors Shutdown Essential Safety Cases | Completion of Head Documents (Reactor Shutdown Essential SC) | 2020-10-09 | 2020-10-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A17530 | HNB Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (D414) Cooling Head Document Completed | 2020-10-09 | 2020-10-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3980 | HRA Reactors Shutdown Essential Safety Cases | ALARP Strategy - Confirm HHB Strategy Applicable to HRA Report Verified by TSA | 2020-10-09 | 2020-10-12 | 15 | 0 | 1 | 3 | 100% | 5 | 1 | Completed
ER6661LT | W206 | W206.A3980 | HYA Reactors Shutdown Essential Safety Cases | ALARP Strategy - Confirm HHB Strategy Applicable to HYA Report Verified by TSA | 2020-10-09 | 2020-10-12 | 15 | 0 | 1 | 3 | 100% | 5 | 1 | Completed
ER6370LT | W201 | ER6370.A17670 | HNB Reactors Shutdown Essential Safety Cases | First Round of Verification - Richard James | 2020-10-09 | 2020-10-10 | 5 | 0 | 1 | 1 | 100% | 5 | 1 | Completed
ER6370LT | W201 | ER6370.A17720 | HNB Reactors Shutdown Essential Safety Cases | First Round of Verification - Martin Kearns | 2020-10-09 | 2020-10-11 | 5 | 0 | 1 | 2 | 100% | 2.5 | 1 | Completed
ER6378LT | W222 | W222.A24210 | HRA Fuel Handling Essential Safety Case | Hazop Study of Defuelling Process EAN Available (REV 000) | 2020-10-09 | 2020-10-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | A2750 | HNB Reactors Shutdown Essential Safety Cases | Safety Case Authoring Complete | 2020-10-09 | 2020-10-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26910 | HYA Fuel Handling Essential Safety Case | Modify Scheme Paper as Required | 2020-10-09 | 2020-10-12 | 2 | 0 | 1 | 3 | 100% | 0.66667 | 1 | Completed
ER6650LT | W226 | W226.A12390 | HYA Fuel Handling Essential Safety Case | Verify Adequate Capacity for Solida Waste Arisings EAN and Issue for Technical Review | 2020-10-09 | 2020-10-15 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6650LT | W226 | W226.A24210 | HYA Fuel Handling Essential Safety Case | Hazop Study of Defuelling Process EAN Available (REV 000) | 2020-10-09 | 2020-10-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A12390 | HRA Fuel Handling Essential Safety Case | Verify Adequate Capacity for Solida Waste Arisings EAN and Issue for Technical Review | 2020-10-09 | 2020-10-15 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | A1980 | HNB Reactors Shutdown Essential Safety Cases | Implementation Programme - Draft Complete | 2020-10-09 | 2020-10-09 | 3 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26910 | HRA Fuel Handling Essential Safety Case | Modify Scheme Paper as Required | 2020-10-09 | 2020-10-12 | 2 | 0 | 2 | 3 | 100% | 0.66667 | 1 | Completed
ER6371LT | W202 | W202.A4110 | HRA Reactors Shutdown Essential Safety Cases | Verified ALARP Strategy - Confirm HHB Strategy Applicable to HRA Report Issued to EDF for Technical Review. | 2020-10-12 | 2020-10-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4110 | HYA Reactors Shutdown Essential Safety Cases | Verified ALARP Strategy - Confirm HHB Strategy Applicable to HYA Report Issued to EDF for Technical Review. | 2020-10-12 | 2020-10-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27040 | HYA Fuel Handling Essential Safety Case | Issue Scheme Paper to Major Schemes PRC Members | 2020-10-12 | 2020-10-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1365 | HNB Reactors Shutdown Essential Safety Cases | SQEP verification (1st round review) (HNB) (Driver to Start EC's on ER6602) Summary | 2020-10-12 | 2020-10-23 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A1570 | HNB Reactors Shutdown Essential Safety Cases | Specialist Assessments if Necessary (HNB) - Summary | 2020-10-12 | 2020-10-30 | 15 | 0 | 15 | 18 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A1600 | HNB Reactors Shutdown Essential Safety Cases | Prepare and Populate Affected Documents List (HNB) | 2020-10-12 | 2020-10-30 | 10 | 0 | 14 | 18 | 100% | 0.55556 | 1 | Completed
ER6370LT | W201 | ER6370.A1610 | HNB Reactors Shutdown Essential Safety Cases | Nuclear Safety | 2020-10-12 | 2020-10-30 | 15 | 0 | 15 | 18 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A2080 | HNB Reactors Shutdown Essential Safety Cases | Ops & PSSR | 2020-10-12 | 2020-10-30 | 15 | 0 | 15 | 18 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A2090 | HNB Reactors Shutdown Essential Safety Cases | Civils | 2020-10-12 | 2020-10-30 | 15 | 0 | 15 | 18 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A2100 | HNB Reactors Shutdown Essential Safety Cases | Emergency Arrangements | 2020-10-12 | 2020-10-30 | 15 | 0 | 15 | 18 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A2110 | HNB Reactors Shutdown Essential Safety Cases | Nuclear Liabilities | 2020-10-12 | 2020-10-30 | 15 | 0 | 15 | 18 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A2120 | HNB Reactors Shutdown Essential Safety Cases | Decommissioning | 2020-10-12 | 2020-10-30 | 15 | 0 | 15 | 18 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A1375 | HNB Reactors Shutdown Essential Safety Cases | First Round of Verification - David Powada | 2020-10-12 | 2020-10-23 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6370LT | W201 | ER6370.A17690 | HNB Reactors Shutdown Essential Safety Cases | First Round of Verification - Sarah Penny | 2020-10-12 | 2020-10-14 | 5 | 0 | 2 | 2 | 100% | 2.5 | 1 | Completed
ER6370LT | W201 | ER6370.A17710 | HNB Reactors Shutdown Essential Safety Cases | First Round of Verification - Rob Cotterill | 2020-10-12 | 2020-10-16 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A17750 | HNB Reactors Shutdown Essential Safety Cases | First Round of Verification - Phil Hurst / Lorna Stevens | 2020-10-12 | 2020-10-16 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A17770 | HNB Reactors Shutdown Essential Safety Cases | First Round of Verification - Maria Mak | 2020-10-12 | 2020-10-16 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A17780 | HNB Reactors Shutdown Essential Safety Cases | First Round of Verification - Beth Gaston | 2020-10-12 | 2020-10-21 | 5 | 0 | 7 | 9 | 100% | 0.55556 | 1 | Completed
ER6370LT | W201 | ER6370.A17790 | HNB Reactors Shutdown Essential Safety Cases | First Round of Verification - Jason Satchell | 2020-10-12 | 2020-10-14 | 5 | 0 | 2 | 2 | 100% | 2.5 | 1 | Completed
ER6370LT | W201 | ER6370.A17800 | HNB Reactors Shutdown Essential Safety Cases | First Round of Verification - Allison Adamson | 2020-10-12 | 2020-10-21 | 5 | 0 | 7 | 9 | 100% | 0.55556 | 1 | Completed
ER6370LT | W201 | ER6370.A17810 | HNB Reactors Shutdown Essential Safety Cases | First Round of Verification - Jim Kershaw | 2020-10-12 | 2020-10-13 | 5 | 0 | 1 | 1 | 100% | 5 | 1 | Completed
ER6370LT | W201 | ER6370.A18110 | HNB Reactors Shutdown Essential Safety Cases | Environment/Rad Protection | 2020-10-12 | 2020-10-30 | 15 | 0 | 15 | 18 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A2150 | HNB Reactors Shutdown Essential Safety Cases | Confirm Specialist Assessments Required | 2020-10-12 | 2020-10-14 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6378LT | W222 | W222.A26120 | HRA Fuel Handling Essential Safety Case | Verify HAZOP updates resulting from defuelling process changes & Issue for Technical Review (REV 001) | 2020-10-12 | 2020-10-16 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A17665 | HNB Reactors Shutdown Essential Safety Cases | First Round of Verification - Georgia Pawson | 2020-10-12 | 2020-10-23 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6650LT | W226 | W226.A22770 | HYA Fuel Handling Essential Safety Case | Verification of Lifting Integrity Life Limits EAN | 2020-10-12 | 2020-11-19 | 15 | 0 | 28 | 38 | 100% | 0.39474 | 1 | Completed
ER6650LT | W226 | W226.A26120 | HYA Fuel Handling Essential Safety Case | Verify HAZOP updates resulting from defuelling process changes & Issue for Technical Review (REV 001) | 2020-10-12 | 2020-10-16 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6378LT | W222 | W222.A27040 | HRA Fuel Handling Essential Safety Case | Issue Scheme Paper to Major Schemes PRC Members | 2020-10-12 | 2020-10-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4120 | HRA Reactors Shutdown Essential Safety Cases | ALARP Strategy - Confirm HHB Strategy Applicable to HRA Report Technically Reviewed by EDF SQEP | 2020-10-13 | 2020-10-14 | 15 | 0 | 1 | 1 | 100% | 15 | 1 | Completed
ER6661LT | W206 | W206.A4120 | HYA Reactors Shutdown Essential Safety Cases | ALARP Strategy - Confirm HHB Strategy Applicable to HYA Report Technically Reviewed by EDF SQEP | 2020-10-13 | 2020-10-14 | 15 | 0 | 1 | 1 | 100% | 15 | 1 | Completed
ER6378LT | W222 | W222.A26440 | HRA Fuel Handling Essential Safety Case | Technical Review of Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection | 2020-10-13 | 2020-10-19 | 4 | 0 | 4 | 6 | 100% | 0.66667 | 1 | Completed
ER6378LT | W222 | W222.A22770 | HRA Fuel Handling Essential Safety Case | Verification of Lifting Integrity Life Limits EAN | 2020-10-13 | 2020-11-19 | 15 | 0 | 27 | 37 | 100% | 0.40541 | 1 | Completed
ER6650LT | W226 | W226.A27070 | HYA Fuel Handling Essential Safety Case | Major Schemes PRC Members Review IRM Documentation | 2020-10-13 | 2020-10-19 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6650LT | W226 | W226.A26440 | HYA Fuel Handling Essential Safety Case | Technical Review of Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection | 2020-10-13 | 2020-10-19 | 4 | 0 | 4 | 6 | 100% | 0.66667 | 1 | Completed
ER6378LT | W222 | W222.A27070 | HRA Fuel Handling Essential Safety Case | Major Schemes PRC Members Review IRM Documentation | 2020-10-13 | 2020-10-19 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A11070 | HNB Reactors Shutdown Essential Safety Cases | Phase 2 Project Management - Gate C - D | 2020-10-14 | 2022-08-31 | 208 | 0 | 474 | 686 | 100% | 0.30321 | 1 | Completed
ER6370LT | W201 | ER6370.A11110 | HNB Reactors Shutdown Essential Safety Cases | SC - Safety Case development - tech oversight Cat 1 - Claim 1 - HNB - C-D - STN | 2020-10-14 | 2022-08-10 | 197 | 0 | 459 | 665 | 100% | 0.29624 | 1 | Completed
ER6370LT | W201 | ER6370.A11130 | HNB Reactors Shutdown Essential Safety Cases | SC - Safety Case development - tech oversight Cat 1 - Claim 2 - HNB - C-D - STN | 2020-10-14 | 2020-12-31 | 56 | 0 | 54 | 78 | 100% | 0.71795 | 1 | Completed
ER6370LT | W201 | ER6370.A11150 | HNB Reactors Shutdown Essential Safety Cases | SC - Safety Case development - tech oversight Cat 1 - Claim 3 - HNB - C-D - STN | 2020-10-14 | 2022-04-27 | 197 | 0 | 387 | 560 | 100% | 0.35179 | 1 | Completed
ER6370LT | W201 | ER6370.A11170 | HNB Reactors Shutdown Essential Safety Cases | SC - Safety Case development - tech oversight Cat 1 - Claim 4 - HNB - C-D - STN | 2020-10-14 | 2022-04-27 | 197 | 0 | 387 | 560 | 100% | 0.35179 | 1 | Completed
ER6370LT | W201 | ER6370.A11180 | HNB Reactors Shutdown Essential Safety Cases | SC - Safety Case development - tech oversight Cat 1 - Claim 5- HNB - C-D - STN | 2020-10-14 | 2022-04-27 | 197 | 0 | 387 | 560 | 100% | 0.35179 | 1 | Completed
ER6370LT | W201 | ER6370.A11220 | HNB Reactors Shutdown Essential Safety Cases | SC - Safety Case development - Stakeholder comms Cat 1 - HNB - C-D | 2020-10-14 | 2022-04-28 | 197 | 0 | 388 | 561 | 100% | 0.35116 | 1 | Completed
ER6370LT | W201 | ER6370.A16160 | HNB Reactors Shutdown Essential Safety Cases | Gate EC3 Completed 364023 (HNB) | 2020-10-14 | 2020-10-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A23610 | HRA Fuel Handling Essential Safety Case | Verify Quality of Build Considerations (Task File Note) for Technical Review | 2020-10-14 | 2020-12-01 | 8 | 0 | 35 | 48 | 100% | 0.16667 | 1 | Completed
ER6650LT | W226 | W226.A23610 | HYA Fuel Handling Essential Safety Case | Verify Quality of Build Considerations (Task File Note) for Technical Review | 2020-10-14 | 2020-12-01 | 8 | 0 | 35 | 48 | 100% | 0.16667 | 1 | Completed
ER6371LT | W202 | W202.A4200 | HRA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd ALARP Strategy - Confirm HHB Strategy Applicable to HRA Report | 2020-10-15 | 2020-10-16 | 15 | 0 | 1 | 1 | 100% | 15 | 1 | Completed
ER6661LT | W206 | W206.A4200 | HYA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd ALARP Strategy - Confirm HHB Strategy Applicable to HYA Report | 2020-10-15 | 2020-10-16 | 15 | 0 | 1 | 1 | 100% | 15 | 1 | Completed
ER6378LT | W222 | W222.A22850 | HRA Fuel Handling Essential Safety Case | Technical Review of Grab Engagement for Low Burn-up Fuel EAN | 2020-10-15 | 2020-10-27 | 9 | 0 | 9 | 12 | 100% | 0.75 | 1 | Completed
ER6650LT | W226 | W226.A22850 | HYA Fuel Handling Essential Safety Case | Technical Review of Grab Engagement for Low Burn-up Fuel EAN | 2020-10-15 | 2020-10-27 | 9 | 0 | 9 | 12 | 100% | 0.75 | 1 | Completed
ER6370LT | W201 | ER6370.A18220 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 187> - RFS - OPEX/ Literature Review - Review Offer, prepare and issue CI | 2020-10-15 | 2020-11-06 | 5 | 0 | 17 | 22 | 100% | 0.22727 | 1 | Completed
ER6371LT | W202 | W202.A3540 | HRA Reactors Shutdown Essential Safety Cases | Issue Final Worker Dose Report | 2020-10-15 | 2020-10-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3540 | HYA Reactors Shutdown Essential Safety Cases | Issue Final Worker Dose Report | 2020-10-15 | 2020-10-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4250 | HRA Reactors Shutdown Essential Safety Cases | TSA Issue Final ALARP Strategy - Confirm HHB Strategy Applicable to HRA Report | 2020-10-16 | 2020-10-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3580 | HRA Reactors Shutdown Essential Safety Cases | Confirm Applicability to HRA | 2020-10-16 | 2020-10-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4250 | HYA Reactors Shutdown Essential Safety Cases | TSA Issue Final ALARP Strategy - Confirm HHB Strategy Applicable to HYA Report | 2020-10-16 | 2020-10-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3580 | HYA Reactors Shutdown Essential Safety Cases | Confirm Applicability to HYA | 2020-10-16 | 2020-10-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A12400 | HYA Fuel Handling Essential Safety Case | Technical Review of Confirm Adequate Capacity for Solid Waste Arisings from Stringer Dismantling EAN | 2020-10-16 | 2020-10-22 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A3440 | HRA Reactors Shutdown Essential Safety Cases | ALARP Report - Supplier prepare and issue Offer | 2020-10-16 | 2020-10-29 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6371LT | W202 | W202.A3550 | HRA Reactors Shutdown Essential Safety Cases | Worker Dose Report Completed and uploaded to CDMS | 2020-10-16 | 2020-10-20 | 5 | 0 | 2 | 4 | 100% | 1.25 | 1 | Completed
ER6661LT | W206 | W206.A3440 | HYA Reactors Shutdown Essential Safety Cases | ALARP Report - Supplier prepare and issue Offer | 2020-10-16 | 2020-10-29 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6661LT | W206 | W206.A3550 | HYA Reactors Shutdown Essential Safety Cases | Worker Dose Report Completed and uploaded to CDMS | 2020-10-16 | 2020-10-26 | 5 | 0 | 6 | 10 | 100% | 0.5 | 1 | Completed
ER6378LT | W222 | W222.A26780 | HRA Fuel Handling Essential Safety Case | Technical Review of Fuel Route Operational Sequence/Process for Defuelling EAN (REV 001) | 2020-10-16 | 2020-10-26 | 7 | 0 | 7 | 10 | 100% | 0.7 | 1 | Completed
ER6378LT | W222 | W222.A12400 | HRA Fuel Handling Essential Safety Case | Technical Review of Confirm Adequate Capacity for Solid Waste Arisings from Stringer Dismantling EAN | 2020-10-16 | 2020-10-22 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A7000 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Corroborated Approach Summary | 2020-10-16 | 2021-01-29 | 78 | 0 | 72 | 105 | 100% | 0.74286 | 1 | Completed
ER6371LT | W202 | W202.A7010 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Corroborated Approach Pre-Job Brief | 2020-10-16 | 2020-10-16 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A7000 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Corroborated Approach Summary | 2020-10-16 | 2021-01-29 | 78 | 0 | 72 | 105 | 100% | 0.74286 | 1 | Completed
ER6661LT | W206 | W206.A7010 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Corroborated Approach Pre-Job Brief | 2020-10-16 | 2020-10-16 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26780 | HYA Fuel Handling Essential Safety Case | Technical Review of Fuel Route Operational Sequence/Process for Defuelling EAN (REV 001) | 2020-10-16 | 2020-10-26 | 7 | 0 | 7 | 10 | 100% | 0.7 | 1 | Completed
ER6371LT | W202 | W202.A2630 | HRA Reactors Shutdown Essential Safety Cases | Verified Pressure Boundary Seals Draft Report Issued to EDF for Technical Review. | 2020-10-19 | 2020-10-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2660 | HRA Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals Draft Report Technically Reviewed by EDF SQEP | 2020-10-19 | 2020-11-06 | 15 | 0 | 15 | 18 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A2970 | HRA Reactors Shutdown Essential Safety Cases | TSA Issue Final Gas Chemistry Assessment Report | 2020-10-19 | 2020-10-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2980 | HRA Reactors Shutdown Essential Safety Cases | Gas Chemistry Assessment Report TR Completed and uploaded to CDMS | 2020-10-19 | 2020-10-26 | 10 | 0 | 5 | 7 | 100% | 1.4286 | 1 | Completed
ER6371LT | W202 | W202.A4260 | HRA Reactors Shutdown Essential Safety Cases | ALARP Strategy - Confirm HHB Strategy Applicable to HRA Report TR Completed and uploaded to CDMS | 2020-10-19 | 2020-10-20 | 10 | 0 | 1 | 1 | 100% | 10 | 1 | Completed
ER6661LT | W206 | W206.A2630 | HYA Reactors Shutdown Essential Safety Cases | Verified Pressure Boundary Seals Draft Report Issued to EDF for Technical Review. | 2020-10-19 | 2020-10-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2970 | HYA Reactors Shutdown Essential Safety Cases | TSA Issue Final Gas Chemistry Assessment Report | 2020-10-19 | 2020-10-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2980 | HYA Reactors Shutdown Essential Safety Cases | Gas Chemistry Assessment Report TR Completed and uploaded to CDMS | 2020-10-19 | 2020-10-26 | 10 | 0 | 5 | 7 | 100% | 1.4286 | 1 | Completed
ER6661LT | W206 | W206.A4260 | HYA Reactors Shutdown Essential Safety Cases | ALARP Strategy - Confirm HHB Strategy Applicable to HYA Report TR Completed and uploaded to CDMS | 2020-10-19 | 2020-10-20 | 10 | 0 | 1 | 1 | 100% | 10 | 1 | Completed
ER6378LT | W222 | W222.A26130 | HRA Fuel Handling Essential Safety Case | Technical Review of HAZOP updates resulting from defuelling process changes EAN (REV 001) | 2020-10-19 | 2021-02-04 | 4 | 0 | 76 | 108 | 100% | 0.037037 | 1 | Completed
ER6650LT | W226 | W226.A26130 | HYA Fuel Handling Essential Safety Case | Technical Review of HAZOP updates resulting from defuelling process changes EAN (REV 001) | 2020-10-19 | 2021-02-04 | 4 | 0 | 76 | 108 | 100% | 0.037037 | 1 | Completed
ER6370LT | W201 | ER6370.A17680 | HNB Reactors Shutdown Essential Safety Cases | First Round of Verification - Ruth Aldred | 2020-10-19 | 2020-10-23 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6378LT | W222 | W222.A24520 | HRA Fuel Handling Essential Safety Case | Verify Review of Interlock Maintenance Review EAN & Issue for Technical Review (DRAFT) | 2020-10-19 | 2020-12-11 | 15 | 0 | 39 | 53 | 100% | 0.28302 | 1 | Completed
ER6378LT | W222 | W222.A23830 | HRA Fuel Handling Essential Safety Case | Technical Review of Detailed Option Investigation EAN | 2020-10-19 | 2020-11-13 | 10 | 0 | 19 | 25 | 100% | 0.4 | 1 | Completed
ER6371LT | W202 | W202.A6080 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Panther Sensitivity Studies Draft Report Verified by TSA | 2020-10-19 | 2020-10-23 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6371LT | W202 | W202.A7020 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Prepare Corroborated Approach Draft Report | 2020-10-19 | 2020-10-23 | 11 | 0 | 4 | 4 | 100% | 2.75 | 1 | Completed
ER6661LT | W206 | W206.A6080 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Panther Sensitivity Studies Draft Report Verified by TSA | 2020-10-19 | 2020-10-23 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6661LT | W206 | W206.A7020 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Prepare Corroborated Approach Draft Report | 2020-10-19 | 2020-10-23 | 11 | 0 | 4 | 4 | 100% | 2.75 | 1 | Completed
ER6650LT | W226 | W226.A23830 | HYA Fuel Handling Essential Safety Case | Technical Review of Detailed Option Investigation EAN | 2020-10-19 | 2020-11-13 | 10 | 0 | 19 | 25 | 100% | 0.4 | 1 | Completed
ER6650LT | W226 | W226.A24520 | HYA Fuel Handling Essential Safety Case | Verify Review of Interlock Maintenance Review EAN & Issue for Technical Review (DRAFT) | 2020-10-19 | 2020-12-11 | 15 | 0 | 39 | 53 | 100% | 0.28302 | 1 | Completed
ER6371LT | W202 | W202.A4320 | HRA Reactors Shutdown Essential Safety Cases | ALARP Strategy - Confirm HHB Strategy Applicable to HRA Report Completed | 2020-10-20 | 2020-10-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3620 | HRA Reactors Shutdown Essential Safety Cases | Worker Dose Report Completed | 2020-10-20 | 2020-10-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2660 | HYA Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals Draft Report Technically Reviewed by EDF SQEP | 2020-10-20 | 2020-11-06 | 15 | 0 | 14 | 17 | 100% | 0.88235 | 1 | Completed
ER6661LT | W206 | W206.A4320 | HYA Reactors Shutdown Essential Safety Cases | ALARP Strategy - Confirm HHB Strategy Applicable to HYA Report Completed | 2020-10-20 | 2020-10-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206150 | HRA Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W206) ALARP / BAT/ BPM Report Completed | 2020-10-20 | 2020-10-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26450 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protections | 2020-10-20 | 2020-10-20 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A22440 | HRA Fuel Handling Essential Safety Case | >>>INCOMING ENABLER (W202.A10600?) ALARP / BAT/ BPM Report Completed | 2020-10-20 | 2020-10-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A22540 | HRA Fuel Handling Essential Safety Case | >>>MIRROR OF INCOMING ENABLER (W202.A10600?) ALARP / BAT/ BPM Report Completed | 2020-10-20 | 2020-10-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A22640 | HRA Fuel Handling Essential Safety Case | INTERFACE MILESTONE - ALARP / BAT/ BPM Report Completed - (W202 Reactors Shutdown Essential Safety Cases (HRA)) | 2020-10-20 | 2020-10-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A22640 | HYA Fuel Handling Essential Safety Case | INTERFACE MILESTONE - ALARP / BAT/ BPM Report Completed - (W202 Reactors Shutdown Essential Safety Cases (HYA)) | 2020-10-20 | 2020-10-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A22540 | HYA Fuel Handling Essential Safety Case | >>>MIRROR OF INCOMING ENABLER (W206) ALARP / BAT/ BPM Report Completed | 2020-10-20 | 2020-10-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A22440 | HYA Fuel Handling Essential Safety Case | >>>INCOMING ENABLER (W206) ALARP / BAT/ BPM Report Completed | 2020-10-20 | 2020-10-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26450 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protections | 2020-10-20 | 2020-10-20 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206165 | HYA Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W226) ALARP / BAT/ BPM Report Completed | 2020-10-20 | 2020-10-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26460 | HRA Fuel Handling Essential Safety Case | Complete Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection to CDMS | 2020-10-21 | 2021-05-26 | 1 | 0 | 149 | 217 | 100% | 0.0046083 | 1 | Completed
ER6650LT | W226 | W226.A27080 | HYA Fuel Handling Essential Safety Case | Hold Major Schemes PRC Meeting | 2020-10-21 | 2020-10-21 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26460 | HYA Fuel Handling Essential Safety Case | Complete Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection to CDMS | 2020-10-21 | 2021-05-26 | 1 | 0 | 149 | 217 | 100% | 0.0046083 | 1 | Completed
ER6378LT | W222 | W222.A27080 | HRA Fuel Handling Essential Safety Case | Hold Major Schemes PRC Meeting | 2020-10-21 | 2020-10-21 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26860 | HYA Fuel Handling Essential Safety Case | Modify Estimate, Schedule & Risk Log as Required | 2020-10-22 | 2020-10-26 | 3 | 0 | 2 | 4 | 100% | 0.75 | 1 | Completed
ER6371LT | W202 | W202.A3160 | HRA Reactors Shutdown Essential Safety Cases | Supporting Plant - Review Offer, prepare and issue CI | 2020-10-22 | 2020-10-28 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | W206.A3160 | HYA Reactors Shutdown Essential Safety Cases | Supporting Plant - Review Offer, prepare and issue CI | 2020-10-22 | 2020-10-28 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6378LT | W222 | W222.A26860 | HRA Fuel Handling Essential Safety Case | Modify Estimate, Schedule & Risk Log as Required | 2020-10-22 | 2020-10-26 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6370LT | W201 | ER6370.A16850 | HNB Reactors Shutdown Essential Safety Cases | Review Comment Response to INSA and Verification - HNB | 2020-10-23 | 2020-10-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A12410 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Confirm Adequate Capacity for Solid Waste Arisings from Stringer Dismantling EAN | 2020-10-23 | 2020-10-27 | 3 | 0 | 2 | 4 | 100% | 0.75 | 1 | Completed
ER6378LT | W222 | W222.A12410 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Confirm Adequate Capacity for Solid Waste Arisings from Stringer Dismantling EAN | 2020-10-23 | 2020-10-27 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6370LT | W201 | ER6370.A1410 | HNB Reactors Shutdown Essential Safety Cases | First round verification comments received (HNB) | 2020-10-23 | 2020-10-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A6090 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Verified Panther Sensitivity Studies Draft Report Issued to EDF for Technical Review. | 2020-10-23 | 2020-10-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A6090 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Verified Panther Sensitivity Studies Draft Report Issued to EDF for Technical Review. | 2020-10-23 | 2020-10-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3150 | HRA Reactors Shutdown Essential Safety Cases | Gas Chemistry Assessment Report Completed | 2020-10-26 | 2020-10-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2620 | HRA Reactors Shutdown Essential Safety Cases | Verified General HF Oversight and HFIP Updates and Revisions Draft EAN Issued to EDF for Technical Review. | 2020-10-26 | 2020-10-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2920 | HRA Reactors Shutdown Essential Safety Cases | Issue Final Seismic Assessment of FPU within Reactor Report | 2020-10-26 | 2020-10-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3150 | HYA Reactors Shutdown Essential Safety Cases | Gas Chemistry Assessment Report Completed | 2020-10-26 | 2020-10-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2620 | HYA Reactors Shutdown Essential Safety Cases | Verified General HF Oversight and HFIP Updates and Revisions Draft EAN Issued to EDF for Technical Review. | 2020-10-26 | 2020-10-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2920 | HYA Reactors Shutdown Essential Safety Cases | Issue Final Seismic Assessment of FPU within Reactor Report | 2020-10-26 | 2020-10-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3620 | HYA Reactors Shutdown Essential Safety Cases | Worker Dose Report Completed | 2020-10-26 | 2020-10-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A7030 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Corroborated Approach Draft Report Verified by TSA | 2020-10-26 | 2020-11-30 | 4 | 0 | 25 | 35 | 100% | 0.11429 | 1 | Completed
ER6661LT | W206 | W206.A7030 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Corroborated Approach Draft Report Verified by TSA | 2020-10-26 | 2020-11-30 | 4 | 0 | 25 | 35 | 100% | 0.11429 | 1 | Completed
ER6370LT | W201 | ER6370.A1520 | HNB Reactors Shutdown Essential Safety Cases | Case Author address first round verification comments | 2020-10-26 | 2020-11-16 | 15 | 0 | 15 | 21 | 100% | 0.71429 | 1 | Completed
ER6371LT | W202 | W202.A6100 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Panther Sensitivity Studies Draft Report Technically Reviewed by EDF SQEP | 2020-10-26 | 2020-11-16 | 10 | 0 | 16 | 21 | 100% | 0.47619 | 1 | Completed
ER6378LT | W222 | W222.A22860 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Grab Engagement for Low Burn-up Fuel EAN | 2020-10-27 | 2020-10-27 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26850 | HYA Fuel Handling Essential Safety Case | Modify Scheme Paper as Required | 2020-10-27 | 2020-12-04 | 3 | 0 | 29 | 38 | 100% | 0.078947 | 1 | Completed
ER6650LT | W226 | W226.A22860 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Grab Engagement for Low Burn-up Fuel EAN | 2020-10-27 | 2020-10-27 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26790 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Fuel Route Operational Sequence/Process for Defuelling EAN (REV 001) | 2020-10-27 | 2021-02-01 | 2 | 0 | 67 | 97 | 100% | 0.020619 | 1 | Completed
ER6378LT | W222 | W222.A26850 | HRA Fuel Handling Essential Safety Case | Modify Scheme Paper as Required | 2020-10-27 | 2020-12-04 | 3 | 0 | 29 | 38 | 100% | 0.078947 | 1 | Completed
ER6650LT | W226 | W226.A26790 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Fuel Route Operational Sequence/Process for Defuelling EAN (REV 001) | 2020-10-27 | 2021-02-01 | 2 | 0 | 67 | 97 | 100% | 0.020619 | 1 | Completed
ER6378LT | W222 | W222.A22870 | HRA Fuel Handling Essential Safety Case | Complete TR Form & Upload Grab Engagement for Low Burn-up Fuel EAN to CDMS | 2020-10-28 | 2020-11-10 | 5 | 0 | 10 | 13 | 100% | 0.38462 | 1 | Completed
ER6650LT | W226 | W226.A12420 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Confirm Adequate Capacity for Solid Waste Arisings from Stringer Dismantling EAN to CDMS | 2020-10-28 | 2020-10-30 | 3 | 0 | 2 | 2 | 100% | 1.5 | 1 | Completed
ER6650LT | W226 | W226.A22870 | HYA Fuel Handling Essential Safety Case | Complete TR Form & Upload Grab Engagement for Low Burn-up Fuel EAN to CDMS | 2020-10-28 | 2020-11-10 | 5 | 0 | 10 | 13 | 100% | 0.38462 | 1 | Completed
ER6378LT | W222 | W222.A12420 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Confirm Adequate Capacity for Solid Waste Arisings from Stringer Dismantling EAN to CDMS | 2020-10-28 | 2020-10-30 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6371LT | W202 | W202.A3530 | HRA Reactors Shutdown Essential Safety Cases | ALARP Report - Review Offer, prepare and issue CI | 2020-10-29 | 2020-10-30 | 5 | 0 | 1 | 1 | 100% | 5 | 1 | Completed
ER6661LT | W206 | W206.A3530 | HYA Reactors Shutdown Essential Safety Cases | ALARP Report - Review Offer, prepare and issue CI | 2020-10-29 | 2020-10-30 | 5 | 0 | 1 | 1 | 100% | 5 | 1 | Completed
ER6378LT | W222 | W222.A18170 | HRA Fuel Handling Essential Safety Case | Verification of P6.6 Handover Document | 2020-10-29 | 2020-11-13 | 10 | 0 | 12 | 15 | 100% | 0.66667 | 1 | Completed
ER6650LT | W226 | W226.A18170 | HYA Fuel Handling Essential Safety Case | Verification of P6.6 Handover Document | 2020-10-29 | 2020-11-13 | 10 | 0 | 12 | 15 | 100% | 0.66667 | 1 | Completed
ER6370LT | W201 | ER6370.A2140 | HNB Reactors Shutdown Essential Safety Cases | Programme Review | 2020-10-29 | 2020-10-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A17010 | HNB Reactors Shutdown Essential Safety Cases | Specialist Assessments of Safety Case - HNB | 2020-10-30 | 2020-10-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3610 | HRA Reactors Shutdown Essential Safety Cases | ALARP Report - Supplier mobilisation time | 2020-10-30 | 2020-10-30 | 10 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3740 | HRA Reactors Shutdown Essential Safety Cases | ALARP Report - Pre Job Brief | 2020-10-30 | 2020-10-30 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3610 | HYA Reactors Shutdown Essential Safety Cases | ALARP Report - Supplier mobilisation time | 2020-10-30 | 2020-10-30 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3740 | HYA Reactors Shutdown Essential Safety Cases | ALARP Report - Pre Job Brief | 2020-10-30 | 2020-10-30 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A9790 | HRA Fuel Handling Essential Safety Case | Verify Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN and Issue for Technical Review | 2020-10-30 | 2020-12-02 | 5 | 0 | 23 | 33 | 100% | 0.15152 | 1 | Completed
ER6650LT | W226 | W226.A12430 | HYA Fuel Handling Essential Safety Case | Confirm Adequate Capacity for Solid Waste Arisings from Stringer Dismantling EAN Available | 2020-10-30 | 2020-10-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A9790 | HYA Fuel Handling Essential Safety Case | Verify Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN and Issue for Technical Review | 2020-10-30 | 2020-12-02 | 10 | 0 | 23 | 33 | 100% | 0.30303 | 1 | Completed
ER6372LT | W203 | W203.A1160 | HNB Enhanced Defuelling Safety Cases | Gate A IRM Paper Submission | 2020-10-30 | 2020-10-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A12430 | HRA Fuel Handling Essential Safety Case | Confirm Adequate Capacity for Solid Waste Arisings from Stringer Dismantling EAN Available | 2020-10-30 | 2020-10-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2650 | HRA Reactors Shutdown Essential Safety Cases | General HF Oversight and HFIP Updates and Revisions Draft EAN Technically Reviewed by EDF SQEP | 2020-11-02 | 2020-11-13 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6378LT | W222 | W222.A23000 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Interpretation of MACE for Fuel Route EAN | 2020-11-02 | 2020-11-03 | 2 | 0 | 1 | 1 | 100% | 2 | 1 | Completed
ER6650LT | W226 | W226.A23000 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Interpretation of MACE for Fuel Route EAN | 2020-11-02 | 2020-11-03 | 1 | 0 | 2 | 1 | 100% | 1 | 1 | Completed
ER6371LT | W202 | W202.A3180 | HRA Reactors Shutdown Essential Safety Cases | Containment Head Document - Supplier prepare and issue Offer | 2020-11-02 | 2020-11-23 | 10 | 0 | 15 | 21 | 100% | 0.47619 | 1 | Completed
ER6371LT | W202 | W202.A3220 | HRA Reactors Shutdown Essential Safety Cases | Supporting Plant - Supplier mobilisation time | 2020-11-02 | 2020-11-13 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6371LT | W202 | W202.A2940 | HRA Reactors Shutdown Essential Safety Cases | Seismic Assessment of FPU within Reactor Report Completed and uploaded to CDMS | 2020-11-02 | 2020-11-20 | 5 | 0 | 14 | 18 | 100% | 0.27778 | 1 | Completed
ER6371LT | W202 | W202.A2860 | HRA Reactors Shutdown Essential Safety Cases | Prepare Station Documentation Update Strategy Report | 2020-11-02 | 2020-12-04 | 20 | 0 | 24 | 32 | 100% | 0.625 | 1 | Completed
ER6371LT | W202 | W202.A2850 | HRA Reactors Shutdown Essential Safety Cases | Station Documentation Update Strategy Report Summary | 2020-11-02 | 2021-02-03 | 72 | 0 | 64 | 93 | 100% | 0.77419 | 1 | Completed
ER6661LT | W206 | W206.A2650 | HYA Reactors Shutdown Essential Safety Cases | General HF Oversight and HFIP Updates and Revisions Draft EAN Technically Reviewed by EDF SQEP | 2020-11-02 | 2020-11-13 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6661LT | W206 | W206.A3180 | HYA Reactors Shutdown Essential Safety Cases | Containment Head Document - Supplier prepare and issue Offer | 2020-11-02 | 2020-11-23 | 10 | 0 | 15 | 21 | 100% | 0.47619 | 1 | Completed
ER6661LT | W206 | W206.A3220 | HYA Reactors Shutdown Essential Safety Cases | Supporting Plant - Supplier mobilisation time | 2020-11-02 | 2020-11-13 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6661LT | W206 | W206.A2940 | HYA Reactors Shutdown Essential Safety Cases | Seismic Assessment of FPU within Reactor Report Completed and uploaded to CDMS | 2020-11-02 | 2020-11-20 | 5 | 0 | 14 | 18 | 100% | 0.27778 | 1 | Completed
ER6661LT | W206 | W206.A2860 | HYA Reactors Shutdown Essential Safety Cases | Prepare Station Documentation Update Strategy Report | 2020-11-02 | 2020-12-04 | 20 | 0 | 24 | 32 | 100% | 0.625 | 1 | Completed
ER6661LT | W206 | W206.A2850 | HYA Reactors Shutdown Essential Safety Cases | Station Documentation Update Strategy Report Summary | 2020-11-02 | 2021-02-03 | 72 | 0 | 64 | 93 | 100% | 0.77419 | 1 | Completed
ER6370LT | W201 | ER6370.A18115 | HNB Reactors Shutdown Essential Safety Cases | Formal Review of Head Documents and Head Document Integration | 2020-11-02 | 2020-12-23 | 20 | 0 | 37 | 51 | 100% | 0.39216 | 1 | Completed
ER6378LT | W222 | W222.A25860 | HRA Fuel Handling Essential Safety Case | Review of Human Factors Assessment of FM Movements during Defuelling Operations ##(Cost Summary)## (C2) (NEW) | 2020-11-02 | 2021-07-28 | 186 | 0 | 186 | 268 | 100% | 0.69403 | 1 | Completed
ER6378LT | W222 | W222.A24780 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Human Factors Assessment of FM Movements during Defuelling Operations EAN | 2020-11-02 | 2020-11-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A23320 | HRA Fuel Handling Essential Safety Case | Draft Update Core Support Plate Properties Methodology & Toughness Properties EAN | 2020-11-02 | 2021-02-01 | 42 | 0 | 63 | 91 | 100% | 0.46154 | 1 | Completed
ER6371LT | W202 | W202.A6380 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Consequences EAN Draft Report Verified by TSA | 2020-11-02 | 2020-11-17 | 5 | 0 | 11 | 15 | 100% | 0.33333 | 1 | Completed
ER6371LT | W202 | W202.A6870 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Determination of Cliff Edge Draft Report Verified by TSA | 2020-11-02 | 2020-11-16 | 10 | 0 | 10 | 14 | 100% | 0.71429 | 1 | Completed
ER6371LT | W202 | W202.A7100 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Specification of Multi-Channel MACE Model Summary | 2020-11-02 | 2021-02-15 | 73 | 0 | 73 | 105 | 100% | 0.69524 | 1 | Completed
ER6371LT | W202 | W202.A7110 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Specification of Multi-Channel MACE Model Pre-Job Brief | 2020-11-02 | 2020-11-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A6100 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Panther Sensitivity Studies Draft Report Technically Reviewed by EDF SQEP | 2020-11-02 | 2020-11-13 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6661LT | W206 | W206.A6380 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Consequences EAN Draft Report Verified by TSA | 2020-11-02 | 2020-11-17 | 5 | 0 | 11 | 15 | 100% | 0.33333 | 1 | Completed
ER6661LT | W206 | W206.A6870 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Determination of Cliff Edge Draft Report Verified by TSA | 2020-11-02 | 2020-11-16 | 10 | 0 | 10 | 14 | 100% | 0.71429 | 1 | Completed
ER6661LT | W206 | W206.A7100 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Specification of Multi-Channel MACE Model Summary | 2020-11-02 | 2021-02-22 | 73 | 0 | 77 | 112 | 100% | 0.65179 | 1 | Completed
ER6661LT | W206 | W206.A7110 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Specification of Multi-Channel MACE Model Pre-Job Brief | 2020-11-02 | 2020-11-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23320 | HYA Fuel Handling Essential Safety Case | Draft Update Core Support Plate Properties Methodology & Toughness Properties EAN | 2020-11-02 | 2021-02-01 | 42 | 0 | 63 | 91 | 100% | 0.46154 | 1 | Completed
ER6650LT | W226 | W226.A24780 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Human Factors Assessment of FM Movements during Defuelling Operations EAN | 2020-11-02 | 2020-11-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25860 | HYA Fuel Handling Essential Safety Case | Review of Human Factors Assessment of FM Movements during Defuelling Operations ##(Cost Summary)## (C2) (NEW) | 2020-11-02 | 2021-07-28 | 186 | 0 | 186 | 268 | 100% | 0.69403 | 1 | Completed
ER6378LT | W222 | W222.A24790 | HRA Fuel Handling Essential Safety Case | Draft Review of Human Factors Assessment of FM Movements during Defuelling Operations EAN | 2020-11-03 | 2020-11-23 | 15 | 0 | 14 | 20 | 100% | 0.75 | 1 | Completed
ER6378LT | W222 | W222.A24240 | HRA Fuel Handling Essential Safety Case | Verify Hazards Review EAN and Issue for Technical Review | 2020-11-03 | 2020-11-20 | 9 | 0 | 13 | 17 | 100% | 0.52941 | 1 | Completed
ER6371LT | W202 | W202.A6520 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Optioneering EAN Draft Report Verified by TSA | 2020-11-03 | 2020-11-27 | 5 | 0 | 18 | 24 | 100% | 0.20833 | 1 | Completed
ER6371LT | W202 | W202.A7120 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Prepare Specification of Multi-Channel MACE Model Draft Report | 2020-11-03 | 2020-11-27 | 10 | 0 | 18 | 24 | 100% | 0.41667 | 1 | Completed
ER6661LT | W206 | W206.A6520 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Optioneering EAN Draft Report Verified by TSA | 2020-11-03 | 2020-11-27 | 5 | 0 | 18 | 24 | 100% | 0.20833 | 1 | Completed
ER6661LT | W206 | W206.A7120 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Prepare Specification of Multi-Channel MACE Model Draft Report | 2020-11-03 | 2020-11-27 | 10 | 0 | 18 | 24 | 100% | 0.41667 | 1 | Completed
ER6650LT | W226 | W226.A24240 | HYA Fuel Handling Essential Safety Case | Verify Hazards Review EAN and Issue for Technical Review | 2020-11-03 | 2020-11-20 | 9 | 0 | 13 | 17 | 100% | 0.52941 | 1 | Completed
ER6650LT | W226 | W226.A24790 | HYA Fuel Handling Essential Safety Case | Draft Review of Human Factors Assessment of FM Movements during Defuelling Operations EAN | 2020-11-03 | 2020-11-23 | 15 | 0 | 14 | 20 | 100% | 0.75 | 1 | Completed
ER6371LT | W202 | W202.A4470 | HRA Reactors Shutdown Essential Safety Cases | Core Cooling Head Document Summary | 2020-11-04 | 2021-08-10 | 193 | 0 | 193 | 279 | 100% | 0.69176 | 1 | Completed
ER6371LT | W202 | W202.A4480 | HRA Reactors Shutdown Essential Safety Cases | Core Cooling Workshop | 2020-11-04 | 2021-01-06 | 20 | 0 | 42 | 63 | 100% | 0.31746 | 1 | Completed
ER6661LT | W206 | W206.A4470 | HYA Reactors Shutdown Essential Safety Cases | Core Cooling Head Document Summary | 2020-11-04 | 2021-08-09 | 192 | 0 | 192 | 278 | 100% | 0.69065 | 1 | Completed
ER6661LT | W206 | W206.A4480 | HYA Reactors Shutdown Essential Safety Cases | Core Cooling Workshop | 2020-11-04 | 2021-01-06 | 20 | 0 | 43 | 63 | 100% | 0.31746 | 1 | Completed
ER6650LT | W226 | W226.A23010 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Interpretation of MACE for Fuel Route EAN to CDMS | 2020-11-05 | 2020-11-18 | 3 | 0 | 9 | 13 | 100% | 0.23077 | 1 | Completed
ER6378LT | W222 | W222.A23010 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Interpretation of MACE for Fuel Route EAN to CDMS | 2020-11-05 | 2020-11-18 | 3 | 0 | 9 | 13 | 100% | 0.23077 | 1 | Completed
ER6371LT | W202 | W202.A3010 | HRA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Pressure Boundary Seals Draft Report | 2020-11-09 | 2020-11-18 | 15 | 0 | 7 | 9 | 100% | 1.6667 | 1 | Completed
ER6661LT | W206 | W206.A3010 | HYA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Pressure Boundary Seals Draft Report | 2020-11-09 | 2020-11-18 | 15 | 0 | 7 | 9 | 100% | 1.6667 | 1 | Completed
ER6378LT | W222 | W222.A23840 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Detailed Option Investigation EAN | 2020-11-09 | 2020-11-13 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6650LT | W226 | W226.A23840 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Detailed Option Investigation EAN | 2020-11-09 | 2020-11-13 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A18230 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 187> - RFS - OPEX/ Literature Review - Supplier mobilisation time | 2020-11-09 | 2020-11-13 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6378LT | W222 | W222.A22880 | HRA Fuel Handling Essential Safety Case | Grab Engagement for Low Burn-up Fuel EAN Available | 2020-11-10 | 2020-11-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A22880 | HYA Fuel Handling Essential Safety Case | Grab Engagement for Low Burn-up Fuel EAN Available | 2020-11-10 | 2020-11-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1180 | HNB Enhanced Defuelling Safety Cases | Gate A IRM Paper Approval | 2020-11-11 | 2020-11-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1170 | HNB Enhanced Defuelling Safety Cases | Hold IRM (FEEDS TO SUMMARY SCHEDULE) | 2020-11-11 | 2020-11-11 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A18180 | HRA Fuel Handling Essential Safety Case | Technical Review of P6.6 Handover Document | 2020-11-13 | 2020-11-13 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A18190 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue P6.6 Handover Document | 2020-11-13 | 2020-11-13 | 2 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A18200 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload P6.6 Handover Document to CDMS | 2020-11-13 | 2021-02-26 | 2 | 0 | 72 | 105 | 100% | 0.019048 | 1 | Completed
ER6650LT | W226 | W226.A18200 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload P6.6 Handover Document to CDMS | 2020-11-13 | 2021-02-26 | 2 | 0 | 72 | 105 | 100% | 0.019048 | 1 | Completed
ER6650LT | W226 | W226.A18190 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue P6.6 Handover Document | 2020-11-13 | 2020-11-13 | 2 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A18180 | HYA Fuel Handling Essential Safety Case | Technical Review of P6.6 Handover Document | 2020-11-13 | 2020-11-13 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2900 | HRA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd General HF Oversight and HFIP Updates and Revisions Draft EAN | 2020-11-16 | 2020-11-20 | 10 | 0 | 4 | 4 | 100% | 2.5 | 1 | Completed
ER6378LT | W222 | W222.A8880 | HRA Fuel Handling Essential Safety Case | Verification of FPU Lifting Integrity while Handling at the Reactor EAN | 2020-11-16 | 2021-02-12 | 20 | 0 | 62 | 88 | 100% | 0.22727 | 1 | Completed
ER6371LT | W202 | W202.A6880 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Verified Determination of Cliff Edge Draft Report Issued to EDF for Technical Review. | 2020-11-16 | 2020-11-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A6880 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Verified Determination of Cliff Edge Draft Report Issued to EDF for Technical Review. | 2020-11-16 | 2020-11-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A8880 | HYA Fuel Handling Essential Safety Case | Verification of FPU Lifting Integrity while Handling at the Reactor EAN | 2020-11-16 | 2021-02-12 | 20 | 0 | 62 | 88 | 100% | 0.22727 | 1 | Completed
ER6371LT | W202 | W202.A3450 | HRA Reactors Shutdown Essential Safety Cases | Supporting Plant - Pre Job Brief | 2020-11-16 | 2020-11-19 | 1 | 0 | 3 | 3 | 100% | 0.33333 | 1 | Completed
ER6661LT | W206 | W206.A2900 | HYA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd General HF Oversight and HFIP Updates and Revisions Draft EAN | 2020-11-16 | 2020-11-18 | 10 | 0 | 2 | 2 | 100% | 5 | 1 | Completed
ER6661LT | W206 | W206.A3450 | HYA Reactors Shutdown Essential Safety Cases | Supporting Plant - Pre Job Brief | 2020-11-16 | 2020-11-19 | 1 | 0 | 3 | 3 | 100% | 0.33333 | 1 | Completed
ER6370LT | W201 | ER6370.A1540 | HNB Reactors Shutdown Essential Safety Cases | SQEP verification (2nd/3rd/4th/5th round review) Summary | 2020-11-16 | 2021-05-05 | 82 | 0 | 117 | 170 | 100% | 0.48235 | 1 | Completed
ER6370LT | W201 | ER6370.A17880 | HNB Reactors Shutdown Essential Safety Cases | Second Round of Verification - David Powada | 2020-11-16 | 2020-11-27 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6378LT | W222 | W222.A23850 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Detailed Option Investigation EAN to CDMS | 2020-11-16 | 2020-11-20 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6371LT | W202 | W202.A6890 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Determination of Cliff Edge Draft Report Technically Reviewed by EDF SQEP | 2020-11-16 | 2020-12-18 | 10 | 0 | 24 | 32 | 100% | 0.3125 | 1 | Completed
ER6661LT | W206 | W206.A6110 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> TSA Address Comments on TR'd Panther Sensitivity Studies Draft Report | 2020-11-16 | 2020-11-30 | 10 | 0 | 10 | 14 | 100% | 0.71429 | 1 | Completed
ER6650LT | W226 | W226.A23850 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Detailed Option Investigation EAN to CDMS | 2020-11-16 | 2020-11-20 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A18240 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 187> - RFS - OPEX/ Literature Review - Pre Job Brief | 2020-11-16 | 2020-11-16 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A6890 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Determination of Cliff Edge Draft Report Technically Reviewed by EDF SQEP | 2020-11-17 | 2020-12-18 | 10 | 0 | 23 | 31 | 100% | 0.32258 | 1 | Completed
ER6661LT | W206 | W206.A3470 | HYA Reactors Shutdown Essential Safety Cases | Prepare Supporting Plant | 2020-11-17 | 2020-12-18 | 20 | 0 | 23 | 31 | 100% | 0.64516 | 1 | Completed
ER6661LT | W206 | W206.A3460 | HYA Reactors Shutdown Essential Safety Cases | Boiler Control and Protection Summary | 2020-11-17 | 2021-04-26 | 110 | 0 | 110 | 160 | 100% | 0.6875 | 1 | Completed
ER6371LT | W202 | W202.A6110 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> TSA Address Comments on TR'd Panther Sensitivity Studies Draft Report | 2020-11-17 | 2020-11-30 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6370LT | W201 | ER6370.A18250 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 187> - OPEX/ Literature Review - Summary | 2020-11-17 | 2021-02-26 | 84 | 0 | 70 | 101 | 100% | 0.83168 | 1 | Completed
ER6370LT | W201 | ER6370.A18290 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 187> - OPEX/ Literature Review - Prepare Draft EAN | 2020-11-17 | 2021-02-02 | 20 | 0 | 52 | 77 | 100% | 0.25974 | 1 | Completed
ER6371LT | W202 | W202.A3200 | HRA Reactors Shutdown Essential Safety Cases | TSA Issue Final Pressure Boundary Seals Report | 2020-11-18 | 2020-11-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3200 | HYA Reactors Shutdown Essential Safety Cases | TSA Issue Final Pressure Boundary Seals Report | 2020-11-18 | 2020-11-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3080 | HYA Reactors Shutdown Essential Safety Cases | TSA Issue Final General HF Oversight and HFIP Updates and Revisions EAN | 2020-11-18 | 2020-11-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A2130 | HNB Reactors Shutdown Essential Safety Cases | First round comments addressed and revised draft re-circulated | 2020-11-18 | 2020-11-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A23020 | HRA Fuel Handling Essential Safety Case | Interpretation of MACE for Fuel Route EAN Available | 2020-11-18 | 2020-11-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23020 | HYA Fuel Handling Essential Safety Case | Interpretation of MACE for Fuel Route EAN Available | 2020-11-18 | 2020-11-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26560 | HRA Fuel Handling Essential Safety Case | Draft Human Factors Integration Plan EAN (REV 001) | 2020-11-18 | 2021-07-08 | 10 | 0 | 160 | 232 | 100% | 0.043103 | 1 | Completed
ER6650LT | W226 | W226.A26560 | HYA Fuel Handling Essential Safety Case | Draft Human Factors Integration Plan EAN (REV 001) | 2020-11-18 | 2021-07-08 | 10 | 0 | 160 | 232 | 100% | 0.043103 | 1 | Completed
ER6371LT | W202 | W202.A3230 | HRA Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals Report TR Completed and uploaded to CDMS | 2020-11-19 | 2020-11-23 | 10 | 0 | 2 | 4 | 100% | 2.5 | 1 | Completed
ER6661LT | W206 | W206.A3230 | HYA Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals Report TR Completed and uploaded to CDMS | 2020-11-19 | 2020-11-23 | 10 | 0 | 2 | 4 | 100% | 2.5 | 1 | Completed
ER6661LT | W206 | W206.A3110 | HYA Reactors Shutdown Essential Safety Cases | General HF Oversight and HFIP Updates and Revisions EAN TR Completed and uploaded to CDMS | 2020-11-19 | 2020-11-23 | 10 | 0 | 2 | 4 | 100% | 2.5 | 1 | Completed
ER6371LT | W202 | W202.A3110 | HRA Reactors Shutdown Essential Safety Cases | General HF Oversight and HFIP Updates and Revisions EAN TR Completed and uploaded to CDMS | 2020-11-20 | 2020-11-23 | 10 | 0 | 1 | 3 | 100% | 3.3333 | 1 | Completed
ER6371LT | W202 | W202.A3470 | HRA Reactors Shutdown Essential Safety Cases | Prepare Supporting Plant | 2020-11-20 | 2020-12-18 | 20 | 0 | 20 | 28 | 100% | 0.71429 | 1 | Completed
ER6371LT | W202 | W202.A3460 | HRA Reactors Shutdown Essential Safety Cases | Boiler Control and Protection Summary | 2020-11-20 | 2021-04-26 | 110 | 0 | 107 | 157 | 100% | 0.70064 | 1 | Completed
ER6371LT | W202 | W202.A3030 | HRA Reactors Shutdown Essential Safety Cases | Seismic Assessment of FPU within Reactor Report Completed | 2020-11-20 | 2020-11-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3030 | HYA Reactors Shutdown Essential Safety Cases | Seismic Assessment of FPU within Reactor Report Completed | 2020-11-20 | 2020-11-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A22780 | HRA Fuel Handling Essential Safety Case | Technical Review of Lifting Integrity Life Limits EAN | 2020-11-20 | 2020-12-04 | 15 | 0 | 11 | 14 | 100% | 1.0714 | 1 | Completed
ER6650LT | W226 | W226.A22780 | HYA Fuel Handling Essential Safety Case | Technical Review of Lifting Integrity Life Limits EAN | 2020-11-20 | 2020-12-04 | 15 | 0 | 11 | 14 | 100% | 1.0714 | 1 | Completed
ER6378LT | W222 | W222.A23860 | HRA Fuel Handling Essential Safety Case | Detailed Option Investigation EAN Available | 2020-11-20 | 2020-11-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23860 | HYA Fuel Handling Essential Safety Case | Detailed Option Investigation EAN Available | 2020-11-20 | 2020-11-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3420 | HRA Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals Report Completed | 2020-11-23 | 2020-11-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3190 | HRA Reactors Shutdown Essential Safety Cases | General HF Oversight and HFIP EAN Completed | 2020-11-23 | 2020-11-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3420 | HYA Reactors Shutdown Essential Safety Cases | Pressure Boundary Seals Report Completed | 2020-11-23 | 2020-11-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3190 | HYA Reactors Shutdown Essential Safety Cases | General HF Oversight and HFIP EAN Completed | 2020-11-23 | 2020-11-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24250 | HRA Fuel Handling Essential Safety Case | Technical Review of Hazards Review EAN | 2020-11-23 | 2021-04-06 | 10 | 0 | 92 | 134 | 100% | 0.074627 | 1 | Completed
ER6371LT | W202 | W202.A6390 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Verified Consequences EAN Draft Report Issued to EDF for Technical Review. | 2020-11-23 | 2020-11-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A6390 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Verified Consequences EAN Draft Report Issued to EDF for Technical Review. | 2020-11-23 | 2020-11-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24250 | HYA Fuel Handling Essential Safety Case | Technical Review of Hazards Review EAN | 2020-11-23 | 2021-04-06 | 10 | 0 | 92 | 134 | 100% | 0.074627 | 1 | Completed
ER6371LT | W202 | W202.A6720 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Specified Flows Draft Report Verified by TSA | 2020-11-23 | 2020-12-14 | 10 | 0 | 15 | 21 | 100% | 0.47619 | 1 | Completed
ER6661LT | W206 | W206.A6720 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Specified Flows Draft Report Verified by TSA | 2020-11-23 | 2020-12-14 | 10 | 0 | 15 | 21 | 100% | 0.47619 | 1 | Completed
ER6371LT | W202 | W202.A3400 | HRA Reactors Shutdown Essential Safety Cases | Containment Head Document - Review Offer, prepare and issue CI | 2020-11-24 | 2020-12-17 | 5 | 0 | 18 | 23 | 100% | 0.21739 | 1 | Completed
ER6661LT | W206 | W206.A3400 | HYA Reactors Shutdown Essential Safety Cases | Containment Head Document - Review Offer, prepare and issue CI | 2020-11-24 | 2020-12-17 | 5 | 0 | 17 | 23 | 100% | 0.21739 | 1 | Completed
ER6378LT | W222 | W222.A24800 | HRA Fuel Handling Essential Safety Case | Verify Human Factors Assessment of FM Movements during Defuelling Operations EAN & Issue for Technical Review | 2020-11-24 | 2021-05-26 | 15 | 0 | 125 | 183 | 100% | 0.081967 | 1 | Completed
ER6371LT | W202 | W202.A6400 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Consequences EAN Draft Report Technically Reviewed by EDF SQEP | 2020-11-24 | 2020-12-04 | 10 | 0 | 9 | 10 | 100% | 1 | 1 | Completed
ER6661LT | W206 | W206.A6400 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Consequences EAN Draft Report Technically Reviewed by EDF SQEP | 2020-11-24 | 2020-12-04 | 10 | 0 | 8 | 10 | 100% | 1 | 1 | Completed
ER6650LT | W226 | W226.A24800 | HYA Fuel Handling Essential Safety Case | Verify Human Factors Assessment of FM Movements during Defuelling Operations EAN & Issue for Technical Review | 2020-11-24 | 2021-05-26 | 15 | 0 | 125 | 183 | 100% | 0.081967 | 1 | Completed
ER6371LT | W202 | W202.A3080 | HRA Reactors Shutdown Essential Safety Cases | TSA Issue Final General HF Oversight and HFIP Updates and Revisions EAN | 2020-11-27 | 2020-11-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A6530 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Verified Optioneering EAN Draft Report Issued to EDF for Technical Review. | 2020-11-27 | 2020-11-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A6530 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Verified Optioneering EAN Draft Report Issued to EDF for Technical Review. | 2020-11-27 | 2020-11-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4150 | HRA Reactors Shutdown Essential Safety Cases | Issue Reactor Internals and Structural Integrity during Defuelling Report to EDF Review. | 2020-11-27 | 2020-11-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4150 | HYA Reactors Shutdown Essential Safety Cases | Issue Reactor Internals and Structural Integrity during Defuelling Report to EDF Review. | 2020-11-27 | 2020-11-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4340 | HRA Reactors Shutdown Essential Safety Cases | Prepare Optioneering Forming Report | 2020-11-30 | 2020-12-18 | 14 | 0 | 14 | 18 | 100% | 0.77778 | 1 | Completed
ER6371LT | W202 | W202.A4330 | HRA Reactors Shutdown Essential Safety Cases | Optioneering Forming Report Summary | 2020-11-30 | 2021-02-09 | 52 | 0 | 49 | 71 | 100% | 0.73239 | 1 | Completed
ER6661LT | W206 | W206.A4340 | HYA Reactors Shutdown Essential Safety Cases | Prepare Optioneering Forming Report | 2020-11-30 | 2020-12-18 | 14 | 0 | 14 | 18 | 100% | 0.77778 | 1 | Completed
ER6661LT | W206 | W206.A4330 | HYA Reactors Shutdown Essential Safety Cases | Optioneering Forming Report Summary | 2020-11-30 | 2021-02-09 | 52 | 0 | 49 | 71 | 100% | 0.73239 | 1 | Completed
ER6371LT | W202 | W202.A6540 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Optioneering EAN Draft Report Technically Reviewed by EDF SQEP | 2020-11-30 | 2020-12-08 | 10 | 0 | 6 | 8 | 100% | 1.25 | 1 | Completed
ER6371LT | W202 | W202.A7040 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Verified Corroborated Approach Draft Report Issued to EDF for Technical Review. | 2020-11-30 | 2020-11-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A6120 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> TSA Issue Final Panther Sensitivity Studies Report | 2020-11-30 | 2020-11-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A6540 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Optioneering EAN Draft Report Technically Reviewed by EDF SQEP | 2020-11-30 | 2020-12-08 | 10 | 0 | 6 | 8 | 100% | 1.25 | 1 | Completed
ER6661LT | W206 | W206.A7040 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Verified Corroborated Approach Draft Report Issued to EDF for Technical Review. | 2020-11-30 | 2020-11-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4160 | HRA Reactors Shutdown Essential Safety Cases | Reactor Internals and Structural Integrity during Defuelling Report Reviewed by EDF SQEP | 2020-11-30 | 2020-12-18 | 10 | 0 | 15 | 18 | 100% | 0.55556 | 1 | Completed
ER6661LT | W206 | W206.A4160 | HYA Reactors Shutdown Essential Safety Cases | Reactor Internals and Structural Integrity during Defuelling Report Reviewed by EDF SQEP | 2020-11-30 | 2020-12-18 | 10 | 0 | 14 | 18 | 100% | 0.55556 | 1 | Completed
ER6370LT | W201 | ER6370.A1550 | HNB Reactors Shutdown Essential Safety Cases | Resolution meeting held | 2020-11-30 | 2020-11-30 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A6120 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> TSA Issue Final Panther Sensitivity Studies Report | 2020-11-30 | 2020-11-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3380 | HRA Reactors Shutdown Essential Safety Cases | Prepare Summary of Compliance with RADWASTE Assessment Principles Draft EAN | 2020-12-01 | 2021-01-07 | 25 | 0 | 25 | 37 | 100% | 0.67568 | 1 | Completed
ER6371LT | W202 | W202.A3360 | HRA Reactors Shutdown Essential Safety Cases | Environmental Permitting and Permissioing Scoping and Stakeholder Engagement | 2020-12-01 | 2021-02-11 | 65 | 0 | 50 | 72 | 100% | 0.90278 | 1 | Completed
ER6371LT | W202 | W202.A3370 | HRA Reactors Shutdown Essential Safety Cases | Summary of Compliance with RADWASTE Assessment Principles Summary | 2020-12-01 | 2021-02-11 | 50 | 0 | 50 | 72 | 100% | 0.69444 | 1 | Completed
ER6371LT | W202 | W202.A3840 | HRA Reactors Shutdown Essential Safety Cases | RAWG Endorsement | 2020-12-01 | 2021-08-20 | 2 | 0 | 181 | 262 | 100% | 0.0076336 | 1 | Completed
ER6661LT | W206 | W206.A3380 | HYA Reactors Shutdown Essential Safety Cases | Prepare Summary of Compliance with RADWASTE Assessment Principles Draft EAN | 2020-12-01 | 2021-01-07 | 25 | 0 | 25 | 37 | 100% | 0.67568 | 1 | Completed
ER6661LT | W206 | W206.A3360 | HYA Reactors Shutdown Essential Safety Cases | Environmental Permitting and Permissioing Scoping and Stakeholder Engagement | 2020-12-01 | 2021-02-11 | 44 | 0 | 50 | 72 | 100% | 0.61111 | 1 | Completed
ER6661LT | W206 | W206.A3370 | HYA Reactors Shutdown Essential Safety Cases | Summary of Compliance with RADWASTE Assessment Principles Summary | 2020-12-01 | 2021-02-11 | 50 | 0 | 50 | 72 | 100% | 0.69444 | 1 | Completed
ER6661LT | W206 | W206.A3840 | HYA Reactors Shutdown Essential Safety Cases | RAWG Endorsement | 2020-12-01 | 2021-08-20 | 2 | 0 | 181 | 262 | 100% | 0.0076336 | 1 | Completed
ER6378LT | W222 | W222.A12520 | HRA Fuel Handling Essential Safety Case | Verify Management Strategy for Pond Water Treatment Arisings EAN and Issue for Technical Review | 2020-12-01 | 2021-01-04 | 10 | 0 | 21 | 34 | 100% | 0.29412 | 1 | Completed
ER6378LT | W222 | W222.AXXX01 | HRA Fuel Handling Essential Safety Case | Programme Manager ##(Cost Summary)## | 2020-12-01 | 2021-09-30 | 365 | 0 | 209 | 303 | 100% | 1.2046 | 1 | Completed
ER6371LT | W202 | W202.A7050 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Corroborated Approach Draft Report Technically Reviewed by EDF SQEP | 2020-12-01 | 2020-12-31 | 21 | 0 | 20 | 30 | 100% | 0.7 | 1 | Completed
ER6661LT | W206 | W206.A7050 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Corroborated Approach Draft Report Technically Reviewed by EDF SQEP | 2020-12-01 | 2020-12-31 | 21 | 0 | 20 | 30 | 100% | 0.7 | 1 | Completed
ER6378LT | W222 | W222.A27100 | HRA Fuel Handling Essential Safety Case | External Programme Manager START MILESTONE | 2020-12-01 | 2020-12-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27100 | HYA Fuel Handling Essential Safety Case | External Programme Manager START MILESTONE | 2020-12-01 | 2020-12-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.AXXX01 | HYA Fuel Handling Essential Safety Case | Programme Manager ##(Cost Summary)## | 2020-12-01 | 2021-09-30 | 365 | 0 | 209 | 303 | 100% | 1.2046 | 1 | Completed
ER6650LT | W226 | W226.A12520 | HYA Fuel Handling Essential Safety Case | Verify Management Strategy for Pond Water Treatment Arisings EAN and Issue for Technical Review | 2020-12-01 | 2021-01-04 | 10 | 0 | 21 | 34 | 100% | 0.29412 | 1 | Completed
ER6650LT | W226 | W226.A25350 | HYA Fuel Handling Essential Safety Case | Draft Update to Fault Schedule/PSA (REV 000) EAN | 2020-12-01 | 2021-06-02 | 11 | 0 | 125 | 183 | 100% | 0.060109 | 1 | Completed
ER6370LT | W201 | ER6370.A1560 | HNB Reactors Shutdown Essential Safety Cases | Second/Third round comments addressed (author) | 2020-12-01 | 2021-01-22 | 10 | 0 | 35 | 52 | 100% | 0.19231 | 1 | Completed
ER6378LT | W222 | W222.A25350 | HRA Fuel Handling Essential Safety Case | Draft Update to Fault Schedule/PSA (REV 000) EAN | 2020-12-01 | 2021-06-02 | 49 | 0 | 125 | 183 | 100% | 0.26776 | 1 | Completed
ER6378LT | W222 | W222.A23720 | HRA Fuel Handling Essential Safety Case | Confirm Acceptability of CSP Pillars EAN Available | 2020-12-01 | 2020-12-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23720 | HYA Fuel Handling Essential Safety Case | Confirm Acceptability of CSP Pillars EAN Available | 2020-12-01 | 2020-12-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25850 | HRA Fuel Handling Essential Safety Case | Human Factors Assessment of Dropped FPU Fault Sequences ##(Cost Summary)## (C2) (NEW) | 2020-12-02 | 2021-06-25 | 142 | 0 | 141 | 205 | 100% | 0.69268 | 1 | Completed
ER6378LT | W222 | W222.A24710 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Human Factors Assessment of Dropped FPU Fault Sequences EAN | 2020-12-02 | 2020-12-02 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24710 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Human Factors Assessment of Dropped FPU Fault Sequences EAN | 2020-12-02 | 2020-12-02 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25850 | HYA Fuel Handling Essential Safety Case | Human Factors Assessment of Dropped FPU Fault Sequences ##(Cost Summary)## (C2) (NEW) | 2020-12-02 | 2021-06-25 | 142 | 0 | 141 | 205 | 100% | 0.69268 | 1 | Completed
ER6378LT | W222 | W222.A23640 | HRA Fuel Handling Essential Safety Case | Complete and Upload Quality of Build Considerations (Task File Note) | 2020-12-02 | 2020-12-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A16930 | HRA Fuel Handling Essential Safety Case | Unverified Skeleton Road Map Shared with EDF Energy | 2020-12-02 | 2020-12-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A16930 | HYA Fuel Handling Essential Safety Case | Unverified Skeleton Road Map Shared with EDF Energy | 2020-12-02 | 2020-12-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23640 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Quality of Build Considerations (Task File Note) | 2020-12-02 | 2020-12-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A23650 | HRA Fuel Handling Essential Safety Case | Quality of Build Considerations (Task File Note) Available | 2020-12-02 | 2020-12-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23650 | HYA Fuel Handling Essential Safety Case | Quality of Build Considerations (Task File Note) Available | 2020-12-02 | 2020-12-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24720 | HRA Fuel Handling Essential Safety Case | Draft Review of Human Factors Assessment of Dropped FPU Fault Sequences EAN | 2020-12-03 | 2021-02-01 | 15 | 0 | 40 | 60 | 100% | 0.25 | 1 | Completed
ER6378LT | W222 | W222.A9800 | HRA Fuel Handling Essential Safety Case | Technical Review of Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN | 2020-12-03 | 2021-03-25 | 11 | 0 | 77 | 112 | 100% | 0.098214 | 1 | Completed
ER6650LT | W226 | W226.A9800 | HYA Fuel Handling Essential Safety Case | Technical Review of Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN | 2020-12-03 | 2021-03-25 | 11 | 0 | 77 | 112 | 100% | 0.098214 | 1 | Completed
ER6650LT | W226 | W226.A24720 | HYA Fuel Handling Essential Safety Case | Draft Review of Human Factors Assessment of Dropped FPU Fault Sequences EAN | 2020-12-03 | 2021-02-01 | 15 | 0 | 40 | 60 | 100% | 0.25 | 1 | Completed
ER6370LT | W201 | W201.1000 | HNB Reactors Shutdown Essential Safety Cases | CAT 1 SC Proposal Revised Draft | 2020-12-04 | 2020-12-23 | 14 | 0 | 14 | 19 | 100% | 0.73684 | 1 | Completed
ER6370LT | W201 | W201.1010 | HNB Reactors Shutdown Essential Safety Cases | Prepare Verified Task File Notes | 2020-12-04 | 2020-12-16 | 9 | 0 | 9 | 12 | 100% | 0.75 | 1 | Completed
ER6370LT | W201 | W201.1030 | HNB Reactors Shutdown Essential Safety Cases | Prepare FPU Slot Modelling Technical Reference | 2020-12-04 | 2020-12-30 | 17 | 0 | 17 | 26 | 100% | 0.65385 | 1 | Completed
ER6370LT | W201 | W201.1070 | HNB Reactors Shutdown Essential Safety Cases | Prepare changes to PVCW Isolation Paper | 2020-12-04 | 2020-12-23 | 14 | 0 | 14 | 19 | 100% | 0.73684 | 1 | Completed
ER6370LT | W201 | W201.1080 | HNB Reactors Shutdown Essential Safety Cases | Address minor residual comments | 2020-12-04 | 2020-12-23 | 14 | 0 | 14 | 19 | 100% | 0.73684 | 1 | Completed
ER6378LT | W222 | W222.A26870 | HRA Fuel Handling Essential Safety Case | Issue Scheme Paper to IRM Members | 2020-12-04 | 2020-12-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26870 | HYA Fuel Handling Essential Safety Case | Issue Scheme Paper to IRM Members | 2020-12-04 | 2020-12-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3210 | HRA Reactors Shutdown Essential Safety Cases | Station Documentation Update Strategy Report Verified by TSA | 2020-12-07 | 2020-12-18 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6661LT | W206 | W206.A3210 | HYA Reactors Shutdown Essential Safety Cases | Station Documentation Update Strategy Report Verified by TSA | 2020-12-07 | 2020-12-18 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6661LT | W206 | W206.A6410 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> TSA Address Comments on TR'd Consequences EAN Draft Report | 2020-12-07 | 2020-12-18 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6378LT | W222 | W222.A22790 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Lifting Integrity Life Limits EAN | 2020-12-07 | 2020-12-11 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6371LT | W202 | W202.A6410 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> TSA Address Comments on TR'd Consequences EAN Draft Report | 2020-12-07 | 2020-12-18 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6378LT | W222 | W222.A26880 | HRA Fuel Handling Essential Safety Case | IRM Members Review Sceme Paper Documentation | 2020-12-07 | 2020-12-11 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6650LT | W226 | W226.A26880 | HYA Fuel Handling Essential Safety Case | IRM Members Review Sceme Paper Documentation | 2020-12-07 | 2020-12-11 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6650LT | W226 | W226.A22790 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Lifting Integrity Life Limits EAN | 2020-12-07 | 2020-12-11 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | ER6370.A18100 | HNB Reactors Shutdown Essential Safety Cases | Programme Review | 2020-12-09 | 2020-12-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A22930 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Damage and Thermal Analysis Dropped Fuel EAN | 2020-12-10 | 2020-12-10 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A22940 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Damage and Thermal Analysis Dropped Fuel EAN to CDMS | 2020-12-10 | 2020-12-10 | 5 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A22940 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Damage and Thermal Analysis Dropped Fuel EAN to CDMS | 2020-12-10 | 2020-12-10 | 5 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A22930 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Damage and Thermal Analysis Dropped Fuel EAN | 2020-12-10 | 2020-12-10 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24740 | HRA Fuel Handling Essential Safety Case | EDF review draft & scope Human Reliability Assessment of Unsubstantiated Claims | 2020-12-10 | 2021-02-02 | 1 | 0 | 36 | 54 | 100% | 0.018519 | 1 | Completed
ER6650LT | W226 | W226.A24740 | HYA Fuel Handling Essential Safety Case | EDF review draft & scope Human Reliability Assessment of Unsubstantiated Claims | 2020-12-10 | 2021-02-02 | 36 | 0 | 36 | 54 | 100% | 0.66667 | 1 | Completed
ER6370LT | W201 | W201.1050 | HNB Reactors Shutdown Essential Safety Cases | Implementation Meeting | 2020-12-10 | 2020-12-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A22950 | HRA Fuel Handling Essential Safety Case | Damage and Thermal Analysis Dropped Fuel EAN Available | 2020-12-10 | 2020-12-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A22950 | HYA Fuel Handling Essential Safety Case | Damage and Thermal Analysis Dropped Fuel EAN Available | 2020-12-10 | 2020-12-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24530 | HRA Fuel Handling Essential Safety Case | Technical Review of Review of Interlock Maintenance Review EAN (DRAFT) | 2020-12-11 | 2020-12-11 | 15 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24540 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Review of Interlock Maintenance Review EAN (DRAFT) | 2020-12-11 | 2020-12-11 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24550 | HRA Fuel Handling Essential Safety Case | Complete Review of Interlock Maintenance Review EAN to CDMS (DRAFT) | 2020-12-11 | 2020-12-11 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24560 | HRA Fuel Handling Essential Safety Case | Review of Interlock Maintenance Review EAN Available (DRAFT) | 2020-12-11 | 2020-12-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24560 | HYA Fuel Handling Essential Safety Case | Review of Interlock Maintenance Review EAN Available (DRAFT) | 2020-12-11 | 2020-12-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24550 | HYA Fuel Handling Essential Safety Case | Complete Review of Interlock Maintenance Review EAN to CDMS (DRAFT) | 2020-12-11 | 2020-12-11 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24540 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Review of Interlock Maintenance Review EAN (DRAFT) | 2020-12-11 | 2020-12-11 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24530 | HYA Fuel Handling Essential Safety Case | Technical Review of Review of Interlock Maintenance Review EAN (DRAFT) | 2020-12-11 | 2020-12-11 | 15 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A22800 | HRA Fuel Handling Essential Safety Case | Complete TR Form & Upload Lifting Integrity Life Limits EAN to CDMS | 2020-12-11 | 2020-12-18 | 1 | 0 | 6 | 7 | 100% | 0.14286 | 1 | Completed
ER6650LT | W226 | W226.A22800 | HYA Fuel Handling Essential Safety Case | Complete TR Form & Upload Lifting Integrity Life Limits EAN to CDMS | 2020-12-11 | 2020-12-18 | 1 | 0 | 5 | 7 | 100% | 0.14286 | 1 | Completed
ER6370LT | W201 | W201.1060 | HNB Reactors Shutdown Essential Safety Cases | Revise Implementation Appendix | 2020-12-11 | 2020-12-23 | 9 | 0 | 9 | 12 | 100% | 0.75 | 1 | Completed
ER6371LT | W202 | W202.A6730 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Verified Specified Flows Draft Report Issued to EDF for Technical Review. | 2020-12-14 | 2020-12-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A6730 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Verified Specified Flows Draft Report Issued to EDF for Technical Review. | 2020-12-14 | 2020-12-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A11360 | HRA Fuel Handling Essential Safety Case | Technical Review of Justification for Pressure Boundary EAN | 2020-12-14 | 2021-01-25 | 22 | 0 | 28 | 42 | 100% | 0.52381 | 1 | Completed
ER6650LT | W226 | W226.A11360 | HYA Fuel Handling Essential Safety Case | Technical Review of Justification for Pressure Boundary EAN | 2020-12-14 | 2021-01-25 | 22 | 0 | 27 | 42 | 100% | 0.52381 | 1 | Completed
ER6371LT | W202 | W202.A6740 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Specified Flows Draft Report Technically Reviewed by EDF SQEP | 2020-12-15 | 2021-01-15 | 10 | 0 | 21 | 31 | 100% | 0.32258 | 1 | Completed
ER6661LT | W206 | W206.A6740 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Specified Flows Draft Report Technically Reviewed by EDF SQEP | 2020-12-15 | 2021-01-15 | 10 | 0 | 21 | 31 | 100% | 0.32258 | 1 | Completed
ER6371LT | W202 | W202.A3140 | HRA Reactors Shutdown Essential Safety Cases | Shutdown Margin Head Document Verified by TSA | 2020-12-15 | 2020-12-30 | 10 | 0 | 10 | 15 | 100% | 0.66667 | 1 | Completed
ER6661LT | W206 | W206.A3140 | HYA Reactors Shutdown Essential Safety Cases | Shutdown Margin Head Document Verified by TSA | 2020-12-15 | 2020-12-30 | 10 | 0 | 10 | 15 | 100% | 0.66667 | 1 | Completed
ER6378LT | W222 | W222.A26840 | HRA Fuel Handling Essential Safety Case | Gate B+ for Region 1 - HYA HRA Defuelling Fuel Handling Essential Safety Case | 2020-12-15 | 2020-12-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26890 | HRA Fuel Handling Essential Safety Case | Hold IRM Meeting | 2020-12-15 | 2020-12-15 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26890 | HYA Fuel Handling Essential Safety Case | Hold IRM Meeting | 2020-12-15 | 2020-12-15 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A18260 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 187> - Prepare Vibration in the FPU Report | 2020-12-15 | 2021-03-22 | 15 | 0 | 66 | 97 | 100% | 0.15464 | 1 | Completed
ER6370LT | W201 | ER6370.A18255 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 187> - Vibration in the FPU Report - Summary | 2020-12-15 | 2021-05-05 | 99 | 0 | 96 | 141 | 100% | 0.70213 | 1 | Completed
ER6378LT | W222 | W222.A27060 | HRA Fuel Handling Essential Safety Case | Gate B IRM Approval | 2020-12-15 | 2020-12-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27060 | HYA Fuel Handling Essential Safety Case | Gate B IRM Approval | 2020-12-15 | 2020-12-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26840 | HYA Fuel Handling Essential Safety Case | Gate B+ for Region 1 - HYA HRA Defuelling Fuel Handling Essential Safety Case | 2020-12-15 | 2020-12-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A8240 | HRA Fuel Handling Essential Safety Case | Technical Review of Defuelling Cooling and Match Analysis (Task FIle Note) | 2020-12-16 | 2021-01-22 | 10 | 0 | 25 | 37 | 100% | 0.27027 | 1 | Completed
ER6650LT | W226 | W226.A8240 | HYA Fuel Handling Essential Safety Case | Technical Review of Defuelling Cooling and Match Analysis (Task FIle Note) | 2020-12-16 | 2021-01-22 | 10 | 0 | 25 | 37 | 100% | 0.27027 | 1 | Completed
ER6370LT | W201 | W201.1020 | HNB Reactors Shutdown Essential Safety Cases | Summary Text fir CAT 1 Paper | 2020-12-17 | 2020-12-23 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A3490 | HRA Reactors Shutdown Essential Safety Cases | Containment Head Document - Supplier mobilisation time | 2020-12-18 | 2021-01-04 | 10 | 0 | 8 | 17 | 100% | 0.58824 | 1 | Completed
ER6371LT | W202 | W202.A3410 | HRA Reactors Shutdown Essential Safety Cases | Verified Station Documentation Update Strategy Report Issued to EDF for Technical Review. | 2020-12-18 | 2020-12-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3430 | HRA Reactors Shutdown Essential Safety Cases | Station Documentation Update Strategy Report Technically Reviewed by EDF SQEP | 2020-12-18 | 2021-01-29 | 18 | 0 | 27 | 42 | 100% | 0.42857 | 1 | Completed
ER6661LT | W206 | W206.A4430 | HYA Reactors Shutdown Essential Safety Cases | Optioneering Forming Report Verified by TSA | 2020-12-18 | 2021-01-06 | 15 | 0 | 11 | 19 | 100% | 0.78947 | 1 | Completed
ER6661LT | W206 | W206.A3490 | HYA Reactors Shutdown Essential Safety Cases | Containment Head Document - Supplier mobilisation time | 2020-12-18 | 2021-01-04 | 10 | 0 | 9 | 17 | 100% | 0.58824 | 1 | Completed
ER6661LT | W206 | W206.A3410 | HYA Reactors Shutdown Essential Safety Cases | Verified Station Documentation Update Strategy Report Issued to EDF for Technical Review. | 2020-12-18 | 2020-12-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3430 | HYA Reactors Shutdown Essential Safety Cases | Station Documentation Update Strategy Report Technically Reviewed by EDF SQEP | 2020-12-18 | 2021-01-29 | 10 | 0 | 27 | 42 | 100% | 0.2381 | 1 | Completed
ER6661LT | W206 | W206.A6420 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> TSA Issue Final Consequences EAN Report | 2020-12-18 | 2020-12-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A22810 | HYA Fuel Handling Essential Safety Case | Lifting Integrity Life Limits EAN Available | 2020-12-18 | 2020-12-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A22810 | HRA Fuel Handling Essential Safety Case | Lifting Integrity Life Limits EAN Available | 2020-12-18 | 2020-12-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1370 | HNB Enhanced Defuelling Safety Cases | Effect of air admission on reactor containment (Coolant conditions CO2) EAN up Rev - Issued Draft Report to EDF for Revi | 2020-12-18 | 2020-12-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A6420 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> TSA Issue Final Consequences EAN Report | 2020-12-18 | 2020-12-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A6900 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> TSA Address Comments on TR'd Determination of Cliff Edge Draft Report | 2020-12-19 | 2021-01-06 | 10 | 0 | 10 | 18 | 100% | 0.55556 | 1 | Completed
ER6371LT | W202 | W202.A3650 | HRA Reactors Shutdown Essential Safety Cases | Supporting Plant Verified by TSA | 2020-12-21 | 2021-02-26 | 10 | 0 | 46 | 67 | 100% | 0.14925 | 1 | Completed
ER6371LT | W202 | W202.A4430 | HRA Reactors Shutdown Essential Safety Cases | Optioneering Forming Report Verified by TSA | 2020-12-21 | 2021-01-06 | 10 | 0 | 10 | 16 | 100% | 0.625 | 1 | Completed
ER6661LT | W206 | W206.A4210 | HYA Reactors Shutdown Essential Safety Cases | Address Comments on Reviewed Reactor Internals and Structural Integrity during Defuelling Report | 2020-12-21 | 2021-01-25 | 10 | 0 | 22 | 35 | 100% | 0.28571 | 1 | Completed
ER6661LT | W206 | W206.A3650 | HYA Reactors Shutdown Essential Safety Cases | Supporting Plant Verified by TSA | 2020-12-21 | 2021-02-26 | 10 | 0 | 46 | 67 | 100% | 0.14925 | 1 | Completed
ER6661LT | W206 | W206.A6430 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Consequences EAN Report TR Completed and uploaded to CDMS | 2020-12-21 | 2021-01-13 | 10 | 0 | 14 | 23 | 100% | 0.43478 | 1 | Completed
ER6661LT | W206 | W206.A6570 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Optioneering EAN Report TR Completed and uploaded to CDMS | 2020-12-21 | 2021-01-29 | 10 | 0 | 26 | 39 | 100% | 0.25641 | 1 | Completed
ER6661LT | W206 | W206.A6900 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> TSA Address Comments on TR'd Determination of Cliff Edge Draft Report | 2020-12-21 | 2021-01-06 | 10 | 0 | 10 | 16 | 100% | 0.625 | 1 | Completed
ER6371LT | W202 | W202.A4210 | HRA Reactors Shutdown Essential Safety Cases | Address Comments on Reviewed Reactor Internals and Structural Integrity during Defuelling Report | 2020-12-21 | 2021-01-25 | 10 | 0 | 22 | 35 | 100% | 0.28571 | 1 | Completed
ER6371LT | W202 | W202.A6430 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Consequences EAN Report TR Completed and uploaded to CDMS | 2020-12-21 | 2021-01-13 | 10 | 0 | 14 | 23 | 100% | 0.43478 | 1 | Completed
ER6371LT | W202 | W202.A6570 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Optioneering EAN Report TR Completed and uploaded to CDMS | 2020-12-21 | 2021-01-29 | 10 | 0 | 26 | 39 | 100% | 0.25641 | 1 | Completed
ER6371LT | W202 | W202.A3260 | HRA Reactors Shutdown Essential Safety Cases | Verified Shutdown Margin Head Document Issued to EDF for Technical Review. | 2020-12-30 | 2020-12-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3260 | HYA Reactors Shutdown Essential Safety Cases | Verified Shutdown Margin Head Document Issued to EDF for Technical Review. | 2020-12-30 | 2020-12-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16131 | HNB Reactors Shutdown Essential Safety Cases | SC - Safety Case development - tech oversight Cat 1 - Claim 2 -HNB - C-D - STN | 2020-12-31 | 2022-04-27 | 143 | 0 | 333 | 482 | 100% | 0.29668 | 1 | Completed
ER6370LT | W201 | ER6370.A11330 | HNB Reactors Shutdown Essential Safety Cases | Claim 2 MS 12/2020 | 2020-12-31 | 2020-12-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2820 | HRA Reactors Shutdown Essential Safety Cases | Issue Final Thermal Analysis (FEAT) of FPU Fully Extended Report | 2020-12-31 | 2020-12-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2820 | HYA Reactors Shutdown Essential Safety Cases | Issue Final Thermal Analysis (FEAT) of FPU Fully Extended Report | 2020-12-31 | 2020-12-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | W201.1040 | HNB Reactors Shutdown Essential Safety Cases | Update Head Document | 2020-12-31 | 2021-02-16 | 6 | 0 | 32 | 47 | 100% | 0.12766 | 1 | Completed
ER6650LT | W226 | W226.A25210 | HYA Fuel Handling Essential Safety Case | Draft Hazard and Interlock Schedule EAN (REV 000) EAN | 2021-01-04 | 2021-06-18 | 10 | 0 | 116 | 165 | 100% | 0.060606 | 1 | Completed
ER6371LT | W202 | W202.A2840 | HRA Reactors Shutdown Essential Safety Cases | Thermal Analysis (FEAT) of FPU Fully Extended Report Completed and uploaded to CDMS | 2021-01-04 | 2021-02-12 | 10 | 0 | 30 | 39 | 100% | 0.25641 | 1 | Completed
ER6661LT | W206 | W206.A2840 | HYA Reactors Shutdown Essential Safety Cases | Thermal Analysis (FEAT) of FPU Fully Extended Report Completed and uploaded to CDMS | 2021-01-04 | 2021-02-12 | 10 | 0 | 30 | 39 | 100% | 0.25641 | 1 | Completed
ER6378LT | W222 | W222.A26000 | HRA Fuel Handling Essential Safety Case | Fast Fracture R6 Analysis ##(Cost Summary)## (C5) (NEW) | 2021-01-04 | 2021-05-21 | 102 | 0 | 96 | 137 | 100% | 0.74453 | 1 | Completed
ER6378LT | W222 | W222.A25210 | HRA Fuel Handling Essential Safety Case | Draft Hazard and Interlock Schedule EAN (REV 000) | 2021-01-04 | 2021-06-18 | 10 | 0 | 116 | 165 | 100% | 0.060606 | 1 | Completed
ER6378LT | W222 | W222.A23520 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Fast Fracture R6 Analysis EAN | 2021-01-04 | 2021-01-05 | 1 | 0 | 1 | 1 | 100% | 1 | 1 | Completed
ER6372LT | W203 | W203.A1420 | HNB Enhanced Defuelling Safety Cases | Effect of air admission on reactor containment (Coolant conditions CO2) EAN up Rev - Reviewed by EDF SQEP | 2021-01-04 | 2021-05-24 | 10 | 0 | 97 | 140 | 100% | 0.071429 | 1 | Completed
ER6371LT | W202 | W202.A6130 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Panther Sensitivity Studies Report TR Completed and uploaded to CDMS | 2021-01-04 | 2021-01-15 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6371LT | W202 | W202.A7060 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> TSA Address Comments on TR'd Corroborated Approach Draft Report | 2021-01-04 | 2021-01-15 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6371LT | W202 | W202.A7130 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Specification of Multi-Channel MACE Model Draft Report Verified by TSA | 2021-01-04 | 2021-01-07 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6661LT | W206 | W206.A6130 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Panther Sensitivity Studies Report TR Completed and uploaded to CDMS | 2021-01-04 | 2021-01-15 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6661LT | W206 | W206.A7060 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> TSA Address Comments on TR'd Corroborated Approach Draft Report | 2021-01-04 | 2021-01-15 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6661LT | W206 | W206.A7130 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Specification of Multi-Channel MACE Model Draft Report Verified by TSA | 2021-01-04 | 2021-01-07 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6650LT | W226 | W226.A23520 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Fast Fracture R6 Analysis EAN | 2021-01-04 | 2021-01-05 | 1 | 0 | 1 | 1 | 100% | 1 | 1 | Completed
ER6650LT | W226 | W226.A26000 | HYA Fuel Handling Essential Safety Case | Fast Fracture R6 Analysis ##(Cost Summary)## (C5) (NEW) | 2021-01-04 | 2021-05-21 | 97 | 0 | 97 | 137 | 100% | 0.70803 | 1 | Completed
ER6378LT | W222 | W222.A23530 | HRA Fuel Handling Essential Safety Case | Draft Fast Fracture R6 Analysis EAN | 2021-01-05 | 2021-04-12 | 5 | 0 | 67 | 97 | 100% | 0.051546 | 1 | Completed
ER6378LT | W222 | W222.A12530 | HRA Fuel Handling Essential Safety Case | Address Verification Comments of Management Strategy for Pond Water Treatment Arisings EAN | 2021-01-05 | 2021-01-22 | 5 | 0 | 13 | 17 | 100% | 0.29412 | 1 | Completed
ER6650LT | W226 | W226.A12530 | HYA Fuel Handling Essential Safety Case | Address Verification Comments of Management Strategy for Pond Water Treatment Arisings EAN | 2021-01-05 | 2021-01-22 | 5 | 0 | 13 | 17 | 100% | 0.29412 | 1 | Completed
ER6650LT | W226 | W226.A23530 | HYA Fuel Handling Essential Safety Case | Draft Fast Fracture R6 Analysis EAN | 2021-01-05 | 2021-04-12 | 5 | 0 | 67 | 97 | 100% | 0.051546 | 1 | Completed
ER6371LT | W202 | W202.A3570 | HRA Reactors Shutdown Essential Safety Cases | Containment Head Document - Pre Job Brief | 2021-01-05 | 2021-01-07 | 1 | 0 | 2 | 2 | 100% | 0.5 | 1 | Completed
ER6661LT | W206 | W206.A3570 | HYA Reactors Shutdown Essential Safety Cases | Containment Head Document - Pre Job Brief | 2021-01-05 | 2021-01-07 | 1 | 0 | 2 | 2 | 100% | 0.5 | 1 | Completed
ER6378LT | W222 | W222.A23430 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload CSP Model and Static Analysis EAN to CDMS | 2021-01-05 | 2021-02-26 | 4 | 0 | 38 | 52 | 100% | 0.076923 | 1 | Completed
ER6650LT | W226 | W226.A23430 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload CSP Model and Static Analysis EAN to CDMS | 2021-01-05 | 2021-02-26 | 4 | 0 | 38 | 52 | 100% | 0.076923 | 1 | Completed
ER6371LT | W202 | W202.A4510 | HRA Reactors Shutdown Essential Safety Cases | Verified Optioneering Forming Report Issued to EDF for Technical Review. | 2021-01-06 | 2021-01-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4510 | HYA Reactors Shutdown Essential Safety Cases | Verified Optioneering Forming Report Issued to EDF for Technical Review. | 2021-01-06 | 2021-01-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A6910 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> TSA Issue Final Determination of Cliff Edge Report | 2021-01-06 | 2021-01-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A6910 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> TSA Issue Final Determination of Cliff Edge Report | 2021-01-06 | 2021-01-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4520 | HRA Reactors Shutdown Essential Safety Cases | Optioneering Forming Report Technically Reviewed by EDF SQEP | 2021-01-07 | 2021-01-29 | 17 | 0 | 17 | 22 | 100% | 0.77273 | 1 | Completed
ER6661LT | W206 | W206.A4520 | HYA Reactors Shutdown Essential Safety Cases | Optioneering Forming Report Technically Reviewed by EDF SQEP | 2021-01-07 | 2021-01-29 | 17 | 0 | 17 | 22 | 100% | 0.77273 | 1 | Completed
ER6378LT | W222 | W222.A26060 | HRA Fuel Handling Essential Safety Case | Dropped FPU Optioneering Documents ##(Cost Summary)## (C5) (NEW) | 2021-01-07 | 2021-06-11 | 108 | 0 | 108 | 155 | 100% | 0.69677 | 1 | Completed
ER6378LT | W222 | W222.A24010 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Dropped FPU Optioneering Documents EAN | 2021-01-07 | 2021-01-07 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A6920 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Determination of Cliff Edge Report TR Completed and uploaded to CDMS | 2021-01-07 | 2021-01-20 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6661LT | W206 | W206.A6920 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Determination of Cliff Edge Report TR Completed and uploaded to CDMS | 2021-01-07 | 2021-01-20 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6650LT | W226 | W226.A24010 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Dropped FPU Optioneering Documents EAN | 2021-01-07 | 2021-01-07 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26060 | HYA Fuel Handling Essential Safety Case | Dropped FPU Optioneering Documents ##(Cost Summary)## (C5) (NEW) | 2021-01-07 | 2021-06-11 | 108 | 0 | 108 | 155 | 100% | 0.69677 | 1 | Completed
ER6371LT | W202 | W202.A7140 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Verified Specification of Multi-Channel MACE Model Draft Report Issued to EDF for Technical Revie | 2021-01-07 | 2021-01-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A7140 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Verified Specification of Multi-Channel MACE Model Draft Report Issued to EDF for Technical Revie | 2021-01-07 | 2021-01-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4050 | HRA Reactors Shutdown Essential Safety Cases | Prepare Containment Head Document Draft Report | 2021-01-08 | 2021-03-24 | 37 | 0 | 53 | 75 | 100% | 0.49333 | 1 | Completed
ER6371LT | W202 | W202.A4040 | HRA Reactors Shutdown Essential Safety Cases | Claim 2 Containment Head Document Summary | 2021-01-08 | 2021-08-24 | 159 | 0 | 159 | 228 | 100% | 0.69737 | 1 | Completed
ER6661LT | W206 | W206.A4050 | HYA Reactors Shutdown Essential Safety Cases | Prepare Containment Head Document Draft Report | 2021-01-08 | 2021-03-24 | 37 | 0 | 54 | 75 | 100% | 0.49333 | 1 | Completed
ER6661LT | W206 | W206.A4040 | HYA Reactors Shutdown Essential Safety Cases | Claim 2 Containment Head Document Summary | 2021-01-08 | 2021-08-24 | 159 | 0 | 159 | 228 | 100% | 0.69737 | 1 | Completed
ER6371LT | W202 | W202.A3660 | HRA Reactors Shutdown Essential Safety Cases | Summary of Compliance with RADWASTE Assessment Principles Draft EAN Verified by TSA | 2021-01-08 | 2021-01-21 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6661LT | W206 | W206.A3660 | HYA Reactors Shutdown Essential Safety Cases | Summary of Compliance with RADWASTE Assessment Principles Draft EAN Verified by TSA | 2021-01-08 | 2021-01-21 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6378LT | W222 | W222.A24020 | HRA Fuel Handling Essential Safety Case | Draft Dropped FPU Optioneering Documents EAN | 2021-01-08 | 2021-04-23 | 12 | 0 | 74 | 105 | 100% | 0.11429 | 1 | Completed
ER6371LT | W202 | W202.A7150 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Specification of Multi-Channel MACE Model Draft Report Technically Reviewed by EDF SQEP | 2021-01-08 | 2021-01-21 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6661LT | W206 | W206.A7150 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Specification of Multi-Channel MACE Model Draft Report Technically Reviewed by EDF SQEP | 2021-01-08 | 2021-01-21 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6650LT | W226 | W226.A24020 | HYA Fuel Handling Essential Safety Case | Draft Dropped FPU Optioneering Documents EAN | 2021-01-08 | 2021-04-23 | 12 | 0 | 73 | 105 | 100% | 0.11429 | 1 | Completed
ER6371LT | W202 | W202.A6440 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Consequences EAN Report Completed | 2021-01-13 | 2021-01-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A6440 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Consequences EAN Report Completed | 2021-01-13 | 2021-01-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2720 | HRA Reactors Shutdown Essential Safety Cases | All Supporting Technical References Complete - Claim 1 Shutdown Margins | 2021-01-15 | 2021-01-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2720 | HYA Reactors Shutdown Essential Safety Cases | All Supporting Technical References Complete - Claim 1 Shutdown Margins | 2021-01-15 | 2021-01-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26080 | HRA Fuel Handling Essential Safety Case | Assessment of Worker Risk ##(Cost Summary)## (C6) (NEW) | 2021-01-15 | 2021-07-19 | 140 | 0 | 127 | 185 | 100% | 0.75676 | 1 | Completed
ER6378LT | W222 | W222.A25490 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Assessment of Worker Risk (REV 000) EAN | 2021-01-15 | 2021-01-15 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25490 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Assessment of Worker Risk (REV 000) EAN | 2021-01-15 | 2021-01-15 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26080 | HYA Fuel Handling Essential Safety Case | Assessment of Worker Risk ##(Cost Summary)## (C6) (NEW) | 2021-01-15 | 2021-07-19 | 139 | 0 | 127 | 185 | 100% | 0.75135 | 1 | Completed
ER6371LT | W202 | W202.A6140 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Panther Sensitivity Studies Report Completed | 2021-01-15 | 2021-01-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A7070 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> TSA Issue Final Corroborated Approach Report | 2021-01-15 | 2021-01-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A6140 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Panther Sensitivity Studies Report Completed | 2021-01-15 | 2021-01-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A7070 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> TSA Issue Final Corroborated Approach Report | 2021-01-15 | 2021-01-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25500 | HRA Fuel Handling Essential Safety Case | Draft Assessment of Worker Risk (REV 000) EAN | 2021-01-18 | 2021-06-21 | 20 | 0 | 106 | 154 | 100% | 0.12987 | 1 | Completed
ER6650LT | W226 | W226.A25500 | HYA Fuel Handling Essential Safety Case | Draft Assessment of Worker Risk (REV 000) EAN | 2021-01-18 | 2021-06-21 | 20 | 0 | 107 | 154 | 100% | 0.12987 | 1 | Completed
ER6370LT | W201 | W201.1090 | HNB Reactors Shutdown Essential Safety Cases | CAT 1 SC Proposal Revised Draft 4 | 2021-01-18 | 2021-02-15 | 1 | 0 | 20 | 28 | 100% | 0.035714 | 1 | Completed
ER6371LT | W202 | W202.A3320 | HRA Reactors Shutdown Essential Safety Cases | Prepare Civil Integrity Overview Draft EAN | 2021-01-18 | 2021-02-12 | 30 | 0 | 20 | 25 | 100% | 1.2 | 1 | Completed
ER6371LT | W202 | W202.A3280 | HRA Reactors Shutdown Essential Safety Cases | Shutdown Margin Head Document Technically Reviewed by EDF SQEP | 2021-01-18 | 2021-02-12 | 21 | 0 | 20 | 25 | 100% | 0.84 | 1 | Completed
ER6371LT | W202 | W202.A3310 | HRA Reactors Shutdown Essential Safety Cases | Civil Integrity Overview Summary | 2021-01-18 | 2021-03-24 | 48 | 0 | 48 | 65 | 100% | 0.73846 | 1 | Completed
ER6661LT | W206 | W206.A3320 | HYA Reactors Shutdown Essential Safety Cases | Prepare Civil Integrity Overview Draft EAN | 2021-01-18 | 2021-02-12 | 30 | 0 | 20 | 25 | 100% | 1.2 | 1 | Completed
ER6661LT | W206 | W206.A3280 | HYA Reactors Shutdown Essential Safety Cases | Shutdown Margin Head Document Technically Reviewed by EDF SQEP | 2021-01-18 | 2021-02-12 | 21 | 0 | 20 | 25 | 100% | 0.84 | 1 | Completed
ER6661LT | W206 | W206.A3310 | HYA Reactors Shutdown Essential Safety Cases | Civil Integrity Overview Summary | 2021-01-18 | 2021-03-24 | 48 | 0 | 48 | 65 | 100% | 0.73846 | 1 | Completed
ER6370LT | W201 | ER6370.A1590 | HNB Reactors Shutdown Essential Safety Cases | SQEP sign off of verification | 2021-01-18 | 2021-05-05 | 5 | 0 | 75 | 107 | 100% | 0.046729 | 1 | Completed
ER6371LT | W202 | W202.A6750 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> TSA Address Comments on TR'd Specified Flows Draft Report | 2021-01-18 | 2021-01-29 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6371LT | W202 | W202.A7080 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Corroborated Approach Report TR Completed and uploaded to CDMS | 2021-01-18 | 2021-01-29 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6661LT | W206 | W206.A6750 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> TSA Address Comments on TR'd Specified Flows Draft Report | 2021-01-18 | 2021-01-29 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6661LT | W206 | W206.A7080 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Corroborated Approach Report TR Completed and uploaded to CDMS | 2021-01-18 | 2021-01-29 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
ER6371LT | W202 | W202.A6930 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Determination of Cliff Edge Report Completed | 2021-01-20 | 2021-01-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A6930 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Determination of Cliff Edge Report Completed | 2021-01-20 | 2021-01-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3830 | HRA Reactors Shutdown Essential Safety Cases | Verified Summary of Compliance with RADWASTE Assessment Principles Draft EAN Issued to EDF for Technical Review. | 2021-01-21 | 2021-01-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3830 | HYA Reactors Shutdown Essential Safety Cases | Verified Summary of Compliance with RADWASTE Assessment Principles Draft EAN Issued to EDF for Technical Review. | 2021-01-21 | 2021-01-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3860 | HRA Reactors Shutdown Essential Safety Cases | Summary of Compliance with RADWASTE Assessment Principles Draft EAN Technically Reviewed by EDF SQEP | 2021-01-22 | 2021-02-04 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6661LT | W206 | W206.A3860 | HYA Reactors Shutdown Essential Safety Cases | Summary of Compliance with RADWASTE Assessment Principles Draft EAN Technically Reviewed by EDF SQEP | 2021-01-22 | 2021-02-04 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6371LT | W202 | W202.A7160 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> TSA Address Comments on TR'd Specification of Multi-Channel MACE Model Draft Report | 2021-01-22 | 2021-02-15 | 10 | 0 | 17 | 24 | 100% | 0.41667 | 1 | Completed
ER6661LT | W206 | W206.A7160 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> TSA Address Comments on TR'd Specification of Multi-Channel MACE Model Draft Report | 2021-01-22 | 2021-02-22 | 10 | 0 | 21 | 31 | 100% | 0.32258 | 1 | Completed
ER6371LT | W202 | W202.A4230 | HRA Reactors Shutdown Essential Safety Cases | Issue Final Reactor Internals and Structural Integrity during Defuelling Report | 2021-01-25 | 2021-01-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4230 | HYA Reactors Shutdown Essential Safety Cases | Issue Final Reactor Internals and Structural Integrity during Defuelling Report | 2021-01-25 | 2021-01-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A8250 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Defuelling Cooling and Match Analysis (Task FIle Note) | 2021-01-25 | 2021-02-25 | 3 | 0 | 23 | 31 | 100% | 0.096774 | 1 | Completed
ER6378LT | W222 | W222.A12540 | HRA Fuel Handling Essential Safety Case | Confirm Verification Comments for Pond Water Treatment Arisings EAN | 2021-01-25 | 2021-01-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A6590 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Scope Defined to Support Preferred Option | 2021-01-25 | 2021-01-29 | 7 | 0 | 4 | 4 | 100% | 1.75 | 1 | Completed
ER6661LT | W206 | W206.A6590 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Scope Defined to Support Preferred Option | 2021-01-25 | 2021-01-29 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6650LT | W226 | W226.A12540 | HYA Fuel Handling Essential Safety Case | Confirm Verification Comments for Pond Water Treatment Arisings EAN | 2021-01-25 | 2021-01-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A8250 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Defuelling Cooling and Match Analysis (Task FIle Note) | 2021-01-25 | 2021-02-25 | 3 | 0 | 23 | 31 | 100% | 0.096774 | 1 | Completed
ER6371LT | W202 | W202.A4240 | HRA Reactors Shutdown Essential Safety Cases | Reactor Internals and Structural Integrity during Defuelling Report Completed and uploaded to CDMS | 2021-01-26 | 2021-01-27 | 5 | 0 | 1 | 1 | 100% | 5 | 1 | Completed
ER6661LT | W206 | W206.A4240 | HYA Reactors Shutdown Essential Safety Cases | Reactor Internals and Structural Integrity during Defuelling Report Completed and uploaded to CDMS | 2021-01-26 | 2021-01-27 | 5 | 0 | 1 | 1 | 100% | 5 | 1 | Completed
ER6378LT | W222 | W222.A11370 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Justification for Pressure Boundary EAN | 2021-01-26 | 2021-02-25 | 10 | 0 | 22 | 30 | 100% | 0.33333 | 1 | Completed
ER6378LT | W222 | W222.A12550 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Management Strategy for Pond Water Treatment Arisings EAN to CDMS | 2021-01-26 | 2021-03-05 | 4 | 0 | 29 | 38 | 100% | 0.10526 | 1 | Completed
ER6650LT | W226 | W226.A12550 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Management Strategy for Pond Water Treatment Arisings EAN to CDMS | 2021-01-26 | 2021-03-05 | 4 | 0 | 29 | 38 | 100% | 0.10526 | 1 | Completed
ER6650LT | W226 | W226.A11370 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Justification for Pressure Boundary EAN | 2021-01-26 | 2021-02-25 | 10 | 0 | 22 | 30 | 100% | 0.33333 | 1 | Completed
ER6650LT | W226 | W226.A24920 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Human Factors Defuelling Issues Management Report EAN | 2021-01-26 | 2021-01-26 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25880 | HYA Fuel Handling Essential Safety Case | Human Factors Defuelling Issues Management Report ##(Cost Summary)## (C2) (NEW) | 2021-01-26 | 2021-06-16 | 109 | 0 | 98 | 141 | 100% | 0.77305 | 1 | Completed
ER6378LT | W222 | W222.A25880 | HRA Fuel Handling Essential Safety Case | Human Factors Defuelling Issues Management Report ##(Cost Summary)## (C2) (NEW) | 2021-01-26 | 2021-06-16 | 103 | 0 | 98 | 141 | 100% | 0.7305 | 1 | Completed
ER6378LT | W222 | W222.A24920 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Human Factors Defuelling Issues Management Report EAN | 2021-01-26 | 2021-01-26 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4290 | HRA Reactors Shutdown Essential Safety Cases | Reactor Internals and Structural Integrity during Defuelling Report Completed | 2021-01-27 | 2021-01-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4290 | HYA Reactors Shutdown Essential Safety Cases | Reactor Internals and Structural Integrity during Defuelling Report Completed | 2021-01-27 | 2021-01-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24930 | HYA Fuel Handling Essential Safety Case | Draft Review of Human Factors Defuelling Issues Management Report EAN | 2021-01-27 | 2021-04-30 | 17 | 0 | 66 | 93 | 100% | 0.1828 | 1 | Completed
ER6378LT | W222 | W222.A24930 | HRA Fuel Handling Essential Safety Case | Draft Review of Human Factors Defuelling Issues Management Report EAN | 2021-01-27 | 2021-04-30 | 22 | 0 | 66 | 93 | 100% | 0.23656 | 1 | Completed
ER6371LT | W202 | W202.A4550 | HRA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Optioneering Forming Report | 2021-01-29 | 2021-02-02 | 11 | 0 | 3 | 4 | 100% | 2.75 | 1 | Completed
ER6371LT | W202 | W202.A3520 | HRA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Station Documentation Update Strategy Report | 2021-01-29 | 2021-02-02 | 0 | 0 | 3 | 4 | 100% | 0 | 1 | Completed
ER6661LT | W206 | W206.A4550 | HYA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Optioneering Forming Report | 2021-01-29 | 2021-02-02 | 11 | 0 | 3 | 4 | 100% | 2.75 | 1 | Completed
ER6661LT | W206 | W206.A3520 | HYA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Station Documentation Update Strategy Report | 2021-01-29 | 2021-02-02 | 10 | 0 | 3 | 4 | 100% | 2.5 | 1 | Completed
ER6378LT | W222 | W222.A25740 | HRA Fuel Handling Essential Safety Case | Development of Fuel Free Verification Methods ##(Cost Summary)## ### (C1) | 2021-01-29 | 2021-06-08 | 86 | 0 | 88 | 130 | 100% | 0.66154 | 1 | Completed
ER6378LT | W222 | W222.A12630 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Development of Fuel Free Verification Methods (File Note) | 2021-01-29 | 2021-01-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A6580 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Optioneering EAN Report Completed | 2021-01-29 | 2021-01-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A7090 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Corroborated Approach Report Completed | 2021-01-29 | 2021-01-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A6580 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Optioneering EAN Report Completed | 2021-01-29 | 2021-01-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A7090 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Corroborated Approach Report Completed | 2021-01-29 | 2021-01-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A12630 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Development of Fuel Free Verification Methods (File Note) | 2021-01-29 | 2021-01-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25740 | HYA Fuel Handling Essential Safety Case | Development of Fuel Free Verification Methods ##(Cost Summary)## ### (C1) | 2021-01-29 | 2021-06-08 | 92 | 0 | 88 | 130 | 100% | 0.70769 | 1 | Completed
ER6371LT | W202 | W202.A6760 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> TSA Issue Final Specified Flows Report | 2021-01-29 | 2021-01-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A6760 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> TSA Issue Final Specified Flows Report | 2021-01-29 | 2021-01-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206030 | HRA Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W222.A22460) Defuelling Dataset QA Grade 2 Part 2 Report Completed <SCOPE DELETED CR220> | 2021-02-01 | 2021-02-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206030 | HYA Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W222.A22460) Defuelling Dataset QA Grade 2 Part 2 Report Completed (SCOPE DELETED CR221) | 2021-02-01 | 2021-02-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206170 | HYA Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W226) Defuelling Dataset QA Grade 2 Part 2 Report Completed (SCOPE DELETED CR221) | 2021-02-01 | 2021-02-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A12640 | HRA Fuel Handling Essential Safety Case | Draft Development of Fuel Free Verification Methods (File Note) | 2021-02-01 | 2021-04-23 | 30 | 0 | 58 | 81 | 100% | 0.37037 | 1 | Completed
ER6378LT | W222 | W222.A22460 | HRA Fuel Handling Essential Safety Case | >>>INCOMING ENABLER (W202.A2206030) Defuelling Dataset QA Grade 2 Part 2 Report Completed ?? CATCH ALL RADCONS ASSESS | 2021-02-01 | 2021-02-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A12640 | HYA Fuel Handling Essential Safety Case | Draft Development of Fuel Free Verification Methods (File Note) | 2021-02-01 | 2021-04-23 | 30 | 0 | 58 | 81 | 100% | 0.37037 | 1 | Completed
ER6650LT | W226 | W226.A26050 | HYA Fuel Handling Essential Safety Case | Dropped FPU Fault Definition Document ##(Cost Summary)## (C5) (NEW) | 2021-02-01 | 2023-10-12 | 697 | 0 | 680 | 983 | 100% | 0.70905 | 1 | Completed
ER6650LT | W226 | W226.A26140 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue HAZOP updates resulting from defuelling process changes EAN (REV 001) | 2021-02-01 | 2021-02-08 | 3 | 0 | 5 | 7 | 100% | 0.42857 | 1 | Completed
ER6650LT | W226 | W226.A26260 | HYA Fuel Handling Essential Safety Case | Draft Dropped FPU Fault Definition Document (FDD) (REV 001) EAN | 2021-02-01 | 2021-05-14 | 10 | 0 | 72 | 102 | 100% | 0.098039 | 1 | Completed
ER6378LT | W222 | W222.A26260 | HRA Fuel Handling Essential Safety Case | Draft Dropped FPU Fault Definition Document (FDD) (REV 001) EAN | 2021-02-01 | 2021-05-14 | 10 | 0 | 72 | 102 | 100% | 0.098039 | 1 | Completed
ER6378LT | W222 | W222.A26140 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue HAZOP updates resulting from defuelling process changes EAN (REV 001) | 2021-02-01 | 2021-02-08 | 2 | 0 | 5 | 7 | 100% | 0.28571 | 1 | Completed
ER6378LT | W222 | W222.A26050 | HRA Fuel Handling Essential Safety Case | Dropped FPU Fault Definition Document ##(Cost Summary)## (C5) (NEW) | 2021-02-01 | 2023-10-12 | 717 | 0 | 680 | 983 | 100% | 0.7294 | 1 | Completed
ER6378LT | W222 | W222.A12650 | HRA Fuel Handling Essential Safety Case | Work with Stations to develop Fuel Free Verification Quality Plan (File Note) | 2021-02-01 | 2021-05-26 | 41 | 0 | 79 | 114 | 100% | 0.35965 | 1 | Completed
ER6378LT | W222 | W222.A22560 | HRA Fuel Handling Essential Safety Case | >>>MIRROR OF INCOMING ENABLER (W202.A2206030) Defuelling Dataset QA Grade 2 Part 2 Report Completed ?? | 2021-02-01 | 2021-02-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A16470 | HRA Fuel Handling Essential Safety Case | INTERFACE MILESTONE - Defuelling Dataset QA Grade 2Part2 Report - (W202 Reactors Shutdown Essential Safety Cases (HRA)) | 2021-02-01 | 2021-02-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A6220 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> PVCW Management - Discovery Milestone | 2021-02-01 | 2021-02-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A6770 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Specified Flows Report TR Completed and uploaded to CDMS | 2021-02-01 | 2021-02-12 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6661LT | W206 | W206.A6220 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> PVCW Management - Discovery Milestone | 2021-02-01 | 2021-02-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A6770 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Specified Flows Report TR Completed and uploaded to CDMS | 2021-02-01 | 2021-02-12 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6650LT | W226 | W226.A16470 | HYA Fuel Handling Essential Safety Case | INTERFACE MILESTONE - Defuelling Dataset QA Grade 2Part2 Report - (W202 Reactors Shutdown Essential Safety Cases (HYA)) | 2021-02-01 | 2021-02-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A22560 | HYA Fuel Handling Essential Safety Case | >>>MIRROR OF INCOMING ENABLER (W202.A2206030) Defuelling Dataset QA Grade 2 Part 2 Report Completed | 2021-02-01 | 2021-02-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A12650 | HYA Fuel Handling Essential Safety Case | Work with Stations to develop Fuel Free Verification Quality Plan (File Note) | 2021-02-01 | 2021-05-26 | 41 | 0 | 79 | 114 | 100% | 0.35965 | 1 | Completed
ER6650LT | W226 | W226.A27200 | HYA Fuel Handling Essential Safety Case | >>>INCOMING ENABLER (W206.A2206030) Defuelling Dataset QA Grade 2 Part 2 Report Completed CATCH ALL RADCONS ASSESS | 2021-02-01 | 2021-02-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A10590 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Worker Dose Assessment (SKELETON) EAN | 2021-02-02 | 2021-02-26 | 10 | 0 | 18 | 24 | 100% | 0.41667 | 1 | Completed
ER6370LT | W201 | ER6370.A18300 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 187> - OPEX/ Literature Review - Issue Draft EAN to EDF for Review. | 2021-02-02 | 2021-02-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26800 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Fuel Route Operational Sequence/Process for Defuelling EAN to CDMS (PROCESS DOCUMENT) (REV 001) | 2021-02-02 | 2021-02-03 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6378LT | W222 | W222.A24730 | HRA Fuel Handling Essential Safety Case | Verify Human Factors Assessment of Dropped FPU Fault Sequences EAN & Issue for Technical Review | 2021-02-02 | 2021-02-15 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6378LT | W222 | W222.A23330 | HRA Fuel Handling Essential Safety Case | Verify Update Core Support Plate Properties Methodology & Toughness Properties EAN and Issue for Technical Review | 2021-02-02 | 2021-04-01 | 19 | 0 | 43 | 58 | 100% | 0.32759 | 1 | Completed
ER6378LT | W222 | W222.A10570 | HRA Fuel Handling Essential Safety Case | Verify Worker Dose Assessment (SKELETON) EAN and Issue for Technical Review | 2021-02-02 | 2021-02-26 | 20 | 0 | 18 | 24 | 100% | 0.83333 | 1 | Completed
ER6650LT | W226 | W226.A10590 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Worker Dose Assessment (SKELETON) EAN | 2021-02-02 | 2021-02-26 | 10 | 0 | 18 | 24 | 100% | 0.41667 | 1 | Completed
ER6650LT | W226 | W226.A10570 | HYA Fuel Handling Essential Safety Case | Verify Worker Dose Assessment (SKELETON) EAN and Issue for Technical Review | 2021-02-02 | 2021-02-26 | 20 | 0 | 18 | 24 | 100% | 0.83333 | 1 | Completed
ER6650LT | W226 | W226.A23330 | HYA Fuel Handling Essential Safety Case | Verify Update Core Support Plate Properties Methodology & Toughness Properties EAN and Issue for Technical Review | 2021-02-02 | 2021-04-01 | 19 | 0 | 43 | 58 | 100% | 0.32759 | 1 | Completed
ER6650LT | W226 | W226.A24730 | HYA Fuel Handling Essential Safety Case | Verify Human Factors Assessment of Dropped FPU Fault Sequences EAN & Issue for Technical Review | 2021-02-02 | 2021-02-15 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6650LT | W226 | W226.A26800 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Fuel Route Operational Sequence/Process for Defuelling EAN to CDMS (PROCESS DOCUMENT) (REV 001) | 2021-02-02 | 2021-02-03 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6371LT | W202 | W202.A4570 | HRA Reactors Shutdown Essential Safety Cases | TSA Issue Final Optioneering Forming Report | 2021-02-02 | 2021-02-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3630 | HRA Reactors Shutdown Essential Safety Cases | TSA Issue Final Station Documentation Update Strategy Report | 2021-02-02 | 2021-02-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4570 | HYA Reactors Shutdown Essential Safety Cases | TSA Issue Final Optioneering Forming Report | 2021-02-02 | 2021-02-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3630 | HYA Reactors Shutdown Essential Safety Cases | TSA Issue Final Station Documentation Update Strategy Report | 2021-02-02 | 2021-02-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3790 | HRA Reactors Shutdown Essential Safety Cases | Confirm Implementation plans are in line with Cat 1 Safety Case - HRA | 2021-02-03 | 2021-02-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3800 | HRA Reactors Shutdown Essential Safety Cases | Agree in principle to changes to Tech Specs - HRA | 2021-02-03 | 2021-02-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3780 | HYA Reactors Shutdown Essential Safety Cases | All Supporting Technical References Complete - Claim 4 Configuration | 2021-02-03 | 2021-02-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3790 | HYA Reactors Shutdown Essential Safety Cases | Confirm Implementation plans are in line with Cat 1 Safety Case - HYA | 2021-02-03 | 2021-02-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206040 | HRA Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W222.A22470) Shutdown Cooling Analysis Report Completed <SCOPE DELETED CR220> | 2021-02-03 | 2021-02-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206040 | HYA Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W222.A22470) Shutdown Cooling Analysis Report Completed (SCOPE DELETED CR221) | 2021-02-03 | 2021-02-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206180 | HYA Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W226) Shutdown Cooling Analysis Report Completed (SCOPE DELETED CR221) | 2021-02-03 | 2021-02-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A18310 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 187> - OPEX/ Literature Review - Draft EAN Reviewed by EDF SQEP | 2021-02-03 | 2021-02-12 | 10 | 0 | 7 | 9 | 100% | 1.1111 | 1 | Completed
ER6371LT | W202 | W202.A4580 | HRA Reactors Shutdown Essential Safety Cases | Optioneering Forming Report TR Completed and uploaded to CDMS | 2021-02-03 | 2021-02-09 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A3640 | HRA Reactors Shutdown Essential Safety Cases | Station Documentation Update Strategy Report TR Completed and uploaded to CDMS | 2021-02-03 | 2021-02-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3770 | HRA Reactors Shutdown Essential Safety Cases | Station Documentation Update Strategy Report Completed | 2021-02-03 | 2021-02-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3780 | HRA Reactors Shutdown Essential Safety Cases | All Supporting Technical References Complete - Claim 4 Configuration | 2021-02-03 | 2021-02-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4580 | HYA Reactors Shutdown Essential Safety Cases | Optioneering Forming Report TR Completed and uploaded to CDMS | 2021-02-03 | 2021-02-09 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | W206.A3640 | HYA Reactors Shutdown Essential Safety Cases | Station Documentation Update Strategy Report TR Completed and uploaded to CDMS | 2021-02-03 | 2021-02-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3770 | HYA Reactors Shutdown Essential Safety Cases | Station Documentation Update Strategy Report Completed | 2021-02-03 | 2021-02-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24860 | HRA Fuel Handling Essential Safety Case | PJB for Phase 2 | 2021-02-03 | 2021-02-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24870 | HYA Fuel Handling Essential Safety Case | PJB for Phase 2 | 2021-02-03 | 2021-02-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26810 | HRA Fuel Handling Essential Safety Case | Fuel Route Operational Sequence/Process for Defuelling EAN Available (REV 001) | 2021-02-03 | 2021-02-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26810 | HYA Fuel Handling Essential Safety Case | Fuel Route Operational Sequence/Process for Defuelling EAN Available (REV 001) | 2021-02-03 | 2021-02-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25840 | HRA Fuel Handling Essential Safety Case | Human Reliability Assessment of Unsubstantaited Claims ##(Cost Summary)## (C2) (NEW) | 2021-02-04 | 2021-07-26 | 119 | 0 | 119 | 172 | 100% | 0.69186 | 1 | Completed
ER6378LT | W222 | W222.A24640 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Human Reliability Assessment of Unsubstantaited Claims EAN | 2021-02-04 | 2021-02-04 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24640 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Human Reliability Assessment of Unsubstantaited Claims EAN | 2021-02-04 | 2021-02-04 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25840 | HYA Fuel Handling Essential Safety Case | Human Reliability Assessment of Unsubstantaited Claims ##(Cost Summary)## (C2) (NEW) | 2021-02-04 | 2021-07-26 | 119 | 0 | 119 | 172 | 100% | 0.69186 | 1 | Completed
ER6378LT | W222 | W222.A24870 | HRA Fuel Handling Essential Safety Case | Review dataset in-line with updated H&I (Atkins Update Tables 1 to 4) | 2021-02-04 | 2021-06-15 | 9 | 0 | 90 | 131 | 100% | 0.068702 | 1 | Completed
ER6650LT | W226 | W226.A24880 | HYA Fuel Handling Essential Safety Case | Review dataset in-line with updated H&I (Atkins Update Tables 1 to 4) | 2021-02-04 | 2021-06-15 | 9 | 0 | 90 | 131 | 100% | 0.068702 | 1 | Completed
ER6371LT | W202 | W202.A4000 | HRA Reactors Shutdown Essential Safety Cases | Summary of Compliance with RADWASTE Assessment Principles EAN TR Completed and uploaded to CDMS | 2021-02-05 | 2021-02-11 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | W206.A3910 | HYA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Summary of Compliance with RADWASTE Assessment Principles Draft EAN | 2021-02-05 | 2021-02-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3970 | HYA Reactors Shutdown Essential Safety Cases | TSA Issue Final Summary of Compliance with RADWASTE Assessment Principles EAN | 2021-02-05 | 2021-02-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4000 | HYA Reactors Shutdown Essential Safety Cases | Summary of Compliance with RADWASTE Assessment Principles EAN TR Completed and uploaded to CDMS | 2021-02-05 | 2021-02-11 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6378LT | W222 | W222.A24650 | HRA Fuel Handling Essential Safety Case | Draft Human Reliability Assessment of Unsubstantaited Claims EAN | 2021-02-05 | 2021-07-02 | 20 | 0 | 102 | 147 | 100% | 0.13605 | 1 | Completed
ER6650LT | W226 | W226.A24650 | HYA Fuel Handling Essential Safety Case | Draft Human Reliability Assessment of Unsubstantaited Claims EAN | 2021-02-05 | 2021-07-02 | 20 | 0 | 102 | 147 | 100% | 0.13605 | 1 | Completed
ER6378LT | W222 | W222.A25140 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Basis of Analysis Report EAN to CDMS (UPDATE) (REV 001) | 2021-02-08 | 2021-04-06 | 6 | 0 | 39 | 57 | 100% | 0.10526 | 1 | Completed
ER6650LT | W226 | W226.A25140 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Basis of Analysis Report EAN to CDMS (UPDATE) (REV 001) | 2021-02-08 | 2021-04-06 | 6 | 0 | 39 | 57 | 100% | 0.10526 | 1 | Completed
ER6371LT | W202 | W202.A4610 | HRA Reactors Shutdown Essential Safety Cases | All Supporting Technical References Complete - Claim 5 ALARP | 2021-02-09 | 2021-02-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26150 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload HAZOP updates resulting from defuelling process changes EAN to CDMS (REV 001) | 2021-02-09 | 2021-02-11 | 3 | 0 | 2 | 2 | 100% | 1.5 | 1 | Completed
ER6378LT | W222 | W222.A26150 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload HAZOP updates resulting from defuelling process changes EAN to CDMS (REV 001) | 2021-02-09 | 2021-02-11 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6371LT | W202 | W202.A4660 | HRA Reactors Shutdown Essential Safety Cases | Optioneering Forming Report Completed | 2021-02-09 | 2021-02-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4660 | HYA Reactors Shutdown Essential Safety Cases | Optioneering Forming Report Completed | 2021-02-09 | 2021-02-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26160 | HYA Fuel Handling Essential Safety Case | HAZOP updates resulting from defuelling process changes EAN Available (REV 001) | 2021-02-11 | 2021-02-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4070 | HRA Reactors Shutdown Essential Safety Cases | Summary of Compliance with RADWASTE Assessment Principles EAN Completed | 2021-02-11 | 2021-02-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4070 | HYA Reactors Shutdown Essential Safety Cases | Summary of Compliance with RADWASTE Assessment Principles EAN Completed | 2021-02-11 | 2021-02-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4610 | HYA Reactors Shutdown Essential Safety Cases | All Supporting Technical References Complete - Claim 5 ALARP | 2021-02-11 | 2021-02-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26160 | HRA Fuel Handling Essential Safety Case | HAZOP updates resulting from defuelling process changes EAN Available (REV 001) | 2021-02-11 | 2021-02-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3720 | HRA Reactors Shutdown Essential Safety Cases | Issue Civil Integrity Overview Draft EAN to EDF for Review. | 2021-02-12 | 2021-02-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2990 | HRA Reactors Shutdown Essential Safety Cases | Thermal Analysis (FEAT) of FPU Fully Extended Report Completed | 2021-02-12 | 2021-02-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3720 | HYA Reactors Shutdown Essential Safety Cases | Issue Civil Integrity Overview Draft EAN to EDF for Review. | 2021-02-12 | 2021-02-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2990 | HYA Reactors Shutdown Essential Safety Cases | Thermal Analysis (FEAT) of FPU Fully Extended Report Completed | 2021-02-12 | 2021-02-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A6780 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Specified Flows Report Completed | 2021-02-12 | 2021-02-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A6780 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Specified Flows Report Completed | 2021-02-12 | 2021-02-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A18320 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 187> - OPEX/ Literature Review - Address Comments from EDF Review on Draft EAN | 2021-02-15 | 2021-02-17 | 10 | 0 | 2 | 2 | 100% | 5 | 1 | Completed
ER6371LT | W202 | W202.A3730 | HRA Reactors Shutdown Essential Safety Cases | Civil Integrity Overview Draft EAN Reviewed by EDF SQEP | 2021-02-15 | 2021-02-26 | 2 | 0 | 9 | 11 | 100% | 0.18182 | 1 | Completed
ER6371LT | W202 | W202.A4540 | HRA Reactors Shutdown Essential Safety Cases | Prepare Core Cooling Head Document Draft Report | 2021-02-15 | 2021-04-23 | 38 | 0 | 47 | 67 | 100% | 0.56716 | 1 | Completed
ER6371LT | W202 | W202.A3500 | HRA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Shutdown Margin Head Document | 2021-02-15 | 2021-02-26 | 5 | 0 | 9 | 11 | 100% | 0.45455 | 1 | Completed
ER6661LT | W206 | W206.A3730 | HYA Reactors Shutdown Essential Safety Cases | Civil Integrity Overview Draft EAN Reviewed by EDF SQEP | 2021-02-15 | 2021-02-26 | 2 | 0 | 9 | 11 | 100% | 0.18182 | 1 | Completed
ER6661LT | W206 | W206.A4540 | HYA Reactors Shutdown Essential Safety Cases | Prepare Core Cooling Head Document Draft Report | 2021-02-15 | 2021-04-23 | 38 | 0 | 47 | 67 | 100% | 0.56716 | 1 | Completed
ER6661LT | W206 | W206.A3500 | HYA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Shutdown Margin Head Document | 2021-02-15 | 2021-02-26 | 5 | 0 | 9 | 11 | 100% | 0.45455 | 1 | Completed
ER6378LT | W222 | W222.A26350 | HRA Fuel Handling Essential Safety Case | Verify The Grab Extend FPU Ledge/ Fault and Associated Protection Needs & Issue for Technical Review | 2021-02-15 | 2021-04-27 | 7 | 0 | 49 | 71 | 100% | 0.098592 | 1 | Completed
ER6378LT | W222 | W222.A8890 | HRA Fuel Handling Essential Safety Case | Technical Review of FPU Lifting Integrity while Handling at the Reactor EAN | 2021-02-15 | 2021-03-04 | 5 | 0 | 13 | 17 | 100% | 0.29412 | 1 | Completed
ER6650LT | W226 | W226.A8890 | HYA Fuel Handling Essential Safety Case | Technical Review of FPU Lifting Integrity while Handling at the Reactor EAN | 2021-02-15 | 2021-03-04 | 5 | 0 | 13 | 17 | 100% | 0.29412 | 1 | Completed
ER6650LT | W226 | W226.A26350 | HYA Fuel Handling Essential Safety Case | Verify The Grab Extend FPU Ledge/ Fault and Associated Protection Needs & Issue for Technical Review | 2021-02-15 | 2021-04-27 | 7 | 0 | 49 | 71 | 100% | 0.098592 | 1 | Completed
ER6371LT | W202 | W202.A7170 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> TSA Issue Final Specification of Multi-Channel MACE Model Report | 2021-02-15 | 2021-02-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A7190 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR220> Specification of Multi-Channel MACE Model Report Completed | 2021-02-15 | 2021-02-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24890 | HRA Fuel Handling Essential Safety Case | Technical Review of Human Factors Assessment of Dropped FPU Fault Sequences EAN | 2021-02-16 | 2021-05-05 | 10 | 0 | 53 | 78 | 100% | 0.12821 | 1 | Completed
ER6650LT | W226 | W226.A24890 | HYA Fuel Handling Essential Safety Case | Technical Review of Human Factors Assessment of Dropped FPU Fault Sequences EAN | 2021-02-16 | 2021-05-05 | 10 | 0 | 53 | 78 | 100% | 0.12821 | 1 | Completed
ER6370LT | W201 | ER6370.A18330 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 187> - OPEX/ Literature Review - Issue Final EAN | 2021-02-17 | 2021-02-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3890 | HRA Reactors Shutdown Essential Safety Cases | Address Comments from EDF Review on Civil Integrity Overview Draft EAN | 2021-02-17 | 2021-03-19 | 5 | 0 | 23 | 30 | 100% | 0.16667 | 1 | Completed
ER6370LT | W201 | ER6370.A18340 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 187> - OPEX/ Literature Review - EAN Completed and Uploaded to CDMS | 2021-02-18 | 2021-02-26 | 10 | 0 | 6 | 8 | 100% | 1.25 | 1 | Completed
ER6661LT | W206 | W206.A7170 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> TSA Issue Final Specification of Multi-Channel MACE Model Report | 2021-02-22 | 2021-02-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A7190 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 221> Specification of Multi-Channel MACE Model Report Completed | 2021-02-22 | 2021-02-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3590 | HRA Reactors Shutdown Essential Safety Cases | TSA Issue Final Shutdown Margin Head Document | 2021-02-26 | 2021-02-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3820 | HRA Reactors Shutdown Essential Safety Cases | Verified Supporting Plant Issued to EDF for Technical Review. | 2021-02-26 | 2021-02-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3590 | HYA Reactors Shutdown Essential Safety Cases | TSA Issue Final Shutdown Margin Head Document | 2021-02-26 | 2021-02-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3820 | HYA Reactors Shutdown Essential Safety Cases | Verified Supporting Plant Issued to EDF for Technical Review. | 2021-02-26 | 2021-02-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A23440 | HRA Fuel Handling Essential Safety Case | CSP Model and Static Analysis EAN Available | 2021-02-26 | 2021-02-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A10600 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Worker Dose Assessment (SKELETON) | 2021-02-26 | 2021-02-26 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A10610 | HRA Fuel Handling Essential Safety Case | Worker Dose Assessment (SKELETON COMPLETE) | 2021-02-26 | 2021-02-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A11380 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Justification for Pressure Boundary EAN to CDMS | 2021-02-26 | 2021-03-19 | 10 | 0 | 16 | 21 | 100% | 0.47619 | 1 | Completed
ER6378LT | W222 | W222.A18210 | HRA Fuel Handling Essential Safety Case | P6.6 Handover Document Available | 2021-02-26 | 2021-02-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A18210 | HYA Fuel Handling Essential Safety Case | P6.6 Handover Document Available | 2021-02-26 | 2021-02-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A11380 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Justification for Pressure Boundary EAN to CDMS | 2021-02-26 | 2021-03-19 | 10 | 0 | 16 | 21 | 100% | 0.47619 | 1 | Completed
ER6650LT | W226 | W226.A10610 | HYA Fuel Handling Essential Safety Case | Worker Dose Assessment (SKELETON COMPLETE) | 2021-02-26 | 2021-02-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A10600 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Worker Dose Assessment (SKELETON) | 2021-02-26 | 2021-02-26 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23440 | HYA Fuel Handling Essential Safety Case | CSP Model and Static Analysis EAN Available | 2021-02-26 | 2021-02-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A18350 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 187> - OPEX/ Literature Review - EAN Completed | 2021-02-26 | 2021-02-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A18390 | HNB Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W202) OPEX/ Literature Review - EAN Completed | 2021-02-26 | 2021-02-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3850 | HYA Reactors Shutdown Essential Safety Cases | Supporting Plant Technically Reviewed by EDF SQEP | 2021-03-01 | 2021-03-31 | 1 | 0 | 22 | 30 | 100% | 0.033333 | 1 | Completed
ER6378LT | W222 | W222.A25420 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Defuelling NSPs/SAGs (REV 000) EAN | 2021-03-01 | 2021-03-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A8260 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Defuelling Cooling and Match Analysis (Task FIle Note) | 2021-03-01 | 2021-03-16 | 2 | 0 | 12 | 15 | 100% | 0.13333 | 1 | Completed
ER6378LT | W222 | W222.A18260 | HRA Fuel Handling Essential Safety Case | Defuelling NSPs/SAGs ##(Cost Summary)## | 2021-03-01 | 2021-07-27 | 59 | 0 | 103 | 148 | 100% | 0.39865 | 1 | Completed
ER6650LT | W226 | W226.A18260 | HYA Fuel Handling Essential Safety Case | Defuelling NSPs/SAGs ##(Cost Summary)## | 2021-03-01 | 2021-07-27 | 59 | 0 | 103 | 148 | 100% | 0.39865 | 1 | Completed
ER6650LT | W226 | W226.A25420 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Defuelling NSPs/SAGs (REV 000) EAN | 2021-03-01 | 2021-03-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3850 | HRA Reactors Shutdown Essential Safety Cases | Supporting Plant Technically Reviewed by EDF SQEP | 2021-03-01 | 2021-03-31 | 1 | 0 | 22 | 30 | 100% | 0.033333 | 1 | Completed
ER6661LT | W206 | W206.A3890 | HYA Reactors Shutdown Essential Safety Cases | Address Comments from EDF Review on Civil Integrity Overview Draft EAN | 2021-03-01 | 2021-03-19 | 15 | 0 | 15 | 18 | 100% | 0.83333 | 1 | Completed
ER6378LT | W222 | W222.A25920 | HRA Fuel Handling Essential Safety Case | Dropped Fuel Head Document ##(Cost Summary)## (C5) (NEW) | 2021-03-01 | 2021-05-26 | 82 | 0 | 59 | 86 | 100% | 0.95349 | 1 | Completed
ER6378LT | W222 | W222.A24990 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Dropped Fuel Head Document EAN | 2021-03-01 | 2021-03-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A8260 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Defuelling Cooling and Match Analysis (Task FIle Note) | 2021-03-01 | 2021-03-16 | 2 | 0 | 12 | 15 | 100% | 0.13333 | 1 | Completed
ER6650LT | W226 | W226.A24990 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Dropped Fuel Head Document EAN | 2021-03-01 | 2021-03-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25920 | HYA Fuel Handling Essential Safety Case | Dropped Fuel Head Document ##(Cost Summary)## (C5) (NEW) | 2021-03-01 | 2021-05-26 | 64 | 0 | 59 | 86 | 100% | 0.74419 | 1 | Completed
ER6370LT | W201 | W201.1100 | HNB Reactors Shutdown Essential Safety Cases | Revise Implementation Appendix - Draft 5 | 2021-03-01 | 2021-03-05 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | W201.1110 | HNB Reactors Shutdown Essential Safety Cases | CAT 1 SC Proposal Revised Draft 5 | 2021-03-01 | 2021-03-15 | 10 | 0 | 10 | 14 | 100% | 0.71429 | 1 | Completed
ER6378LT | W222 | W222.A25430 | HRA Fuel Handling Essential Safety Case | Draft Defuelling NSPs/SAGs (REV 000) EAN | 2021-03-02 | 2021-06-04 | 18 | 0 | 65 | 94 | 100% | 0.19149 | 1 | Completed
ER6650LT | W226 | W226.A25430 | HYA Fuel Handling Essential Safety Case | Draft Defuelling NSPs/SAGs (REV 000) EAN | 2021-03-02 | 2021-06-04 | 18 | 0 | 65 | 94 | 100% | 0.19149 | 1 | Completed
ER6378LT | W222 | W222.A25000 | HRA Fuel Handling Essential Safety Case | Draft Damage and Dropped Fuel Head Document EAN | 2021-03-02 | 2021-05-26 | 20 | 0 | 58 | 85 | 100% | 0.23529 | 1 | Completed
ER6650LT | W226 | W226.A25000 | HYA Fuel Handling Essential Safety Case | Draft Damage and Dropped Fuel Head Document EAN | 2021-03-02 | 2021-05-26 | 20 | 0 | 58 | 85 | 100% | 0.23529 | 1 | Completed
ER6378LT | W222 | W222.A27215 | HRA Fuel Handling Essential Safety Case | Mid Job HOLD POINT | 2021-03-02 | 2021-03-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27215 | HYA Fuel Handling Essential Safety Case | Mid Job HOLD POINT | 2021-03-02 | 2021-03-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A27225 | HRA Fuel Handling Essential Safety Case | Verify H&I Scheudules for all Facilities | 2021-03-03 | 2021-04-12 | 17 | 0 | 26 | 40 | 100% | 0.425 | 1 | Completed
ER6650LT | W226 | W226.A27225 | HYA Fuel Handling Essential Safety Case | Verify H&I Scheudules for all Facilities | 2021-03-03 | 2021-04-12 | 17 | 0 | 26 | 40 | 100% | 0.425 | 1 | Completed
ER6378LT | W222 | W222.A8900 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue FPU Lifting Integrity while Handling at the Reactor EAN | 2021-03-05 | 2021-04-09 | 5 | 0 | 23 | 35 | 100% | 0.14286 | 1 | Completed
ER6650LT | W226 | W226.A8900 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue FPU Lifting Integrity while Handling at the Reactor EAN | 2021-03-05 | 2021-04-09 | 5 | 0 | 23 | 35 | 100% | 0.14286 | 1 | Completed
ER6378LT | W222 | W222.A12560 | HRA Fuel Handling Essential Safety Case | Management Strategy for Pond Water Treatment Arisings EAN Available | 2021-03-05 | 2021-03-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A12560 | HYA Fuel Handling Essential Safety Case | Management Strategy for Pond Water Treatment Arisings EAN Available | 2021-03-05 | 2021-03-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1340 | HNB Reactors Shutdown Essential Safety Cases | INSA review & iteration of comments (using BARRIER MODEL) (HNB) | 2021-03-15 | 2021-05-07 | 20 | 0 | 37 | 53 | 100% | 0.37736 | 1 | Completed
ER6370LT | W201 | ER6370.A1450 | HNB Reactors Shutdown Essential Safety Cases | SC - Safety Case development - INSA - HNB - C-D - INSA | 2021-03-15 | 2021-07-01 | 47 | 0 | 74 | 108 | 100% | 0.43519 | 1 | Completed
ER6378LT | W222 | W222.A18490 | HRA Fuel Handling Essential Safety Case | Claim 4 - P6.2 HRA/HYA Essential Defuelling SC - Defuelling Cooling Complete | 2021-03-16 | 2021-03-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A18760 | HRA Fuel Handling Essential Safety Case | Claim 4 - P6.2 HRA/HYA Essential Defuelling SC - Defuelling Cooling | 2021-03-16 | 2021-03-16 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A18760 | HYA Fuel Handling Essential Safety Case | Claim 4 - P6.2 HYA/HYA Essential Defuelling SC - Defuelling Cooling | 2021-03-16 | 2021-03-16 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A18490 | HYA Fuel Handling Essential Safety Case | Claim 4 - P6.2 HYA/HYA Essential Defuelling SC - Defuelling Cooling Complete | 2021-03-16 | 2021-03-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A8270 | HRA Fuel Handling Essential Safety Case | Defuelling Cooling and Match Analysis (Task FIle Note) Available | 2021-03-16 | 2021-03-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A8270 | HYA Fuel Handling Essential Safety Case | Defuelling Cooling and Match Analysis (Task FIle Note) Available | 2021-03-16 | 2021-03-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.1080 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - Vibration in the FPU - Summary | 2021-03-18 | 2021-04-15 | 25 | 0 | 19 | 28 | 100% | 0.89286 | 1 | Completed
ER6371LT | W202 | W202.1090 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - Vibration in the FPU - Draft and issue RFS | 2021-03-18 | 2021-03-18 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.1080 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - Vibration in the FPU - Summary | 2021-03-18 | 2021-04-15 | 25 | 0 | 19 | 28 | 100% | 0.89286 | 1 | Completed
ER6661LT | W206 | W206.1090 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - Vibration in the FPU - Draft and issue RFS | 2021-03-18 | 2021-03-18 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4690 | HYA Reactors Shutdown Essential Safety Cases | Prepare the Safety Case Proposal (HYA) | 2021-03-18 | 2021-08-27 | 81 | 0 | 113 | 162 | 100% | 0.5 | 1 | Completed
ER6661LT | W206 | W206.A4680 | HYA Reactors Shutdown Essential Safety Cases | SC - Safety Case development - Stakeholder comms Cat 1 - HYA - B-C - INA | 2021-03-18 | 2021-08-23 | 81 | 0 | 108 | 158 | 100% | 0.51266 | 1 | Completed
ER6371LT | W202 | W202.1100 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - Vibration in the FPU - Supplier prepare and issue Offer | 2021-03-19 | 2021-03-22 | 2 | 0 | 2 | 3 | 100% | 0.66667 | 1 | Completed
ER6661LT | W206 | W206.1100 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - Vibration in the FPU - Supplier prepare and issue Offer | 2021-03-19 | 2021-03-22 | 2 | 0 | 2 | 3 | 100% | 0.66667 | 1 | Completed
ER6371LT | W202 | W202.A4690 | HRA Reactors Shutdown Essential Safety Cases | Prepare the Safety Case Proposal (HRA) | 2021-03-19 | 2021-08-27 | 81 | 0 | 111 | 161 | 100% | 0.50311 | 1 | Completed
ER6371LT | W202 | W202.A4680 | HRA Reactors Shutdown Essential Safety Cases | SC - Safety Case development - Stakeholder comms Cat 1 - HRA - B-C - INA | 2021-03-19 | 2021-08-23 | 94 | 0 | 107 | 157 | 100% | 0.59873 | 1 | Completed
ER6371LT | W202 | W202.A3930 | HRA Reactors Shutdown Essential Safety Cases | Issue Civil Integrity Overview Final EAN | 2021-03-19 | 2021-03-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3930 | HYA Reactors Shutdown Essential Safety Cases | Issue Civil Integrity Overview Final EAN | 2021-03-19 | 2021-03-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A11390 | HRA Fuel Handling Essential Safety Case | Justification for Pressure Boundary EAN Available | 2021-03-19 | 2021-03-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A11390 | HYA Fuel Handling Essential Safety Case | Justification for Pressure Boundary EAN Available | 2021-03-19 | 2021-03-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | W201.1120 | HNB Reactors Shutdown Essential Safety Cases | CAT 1 SC Proposal Revised Draft 6 | 2021-03-22 | 2021-05-05 | 10 | 0 | 30 | 44 | 100% | 0.22727 | 1 | Completed
ER6370LT | W201 | W201.1130 | HNB Reactors Shutdown Essential Safety Cases | Revise Implementation Appendix - Draft 6 | 2021-03-22 | 2021-05-05 | 5 | 0 | 30 | 44 | 100% | 0.11364 | 1 | Completed
ER6371LT | W202 | W202.A3940 | HRA Reactors Shutdown Essential Safety Cases | Civil Integrity Overview EAN Completed and uploaded to CDMS | 2021-03-22 | 2021-03-24 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6661LT | W206 | W206.A3940 | HYA Reactors Shutdown Essential Safety Cases | Civil Integrity Overview EAN Completed and uploaded to CDMS | 2021-03-22 | 2021-03-24 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6370LT | W201 | ER6370.A18360 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 187> - Verify Vibration in the FPU Report | 2021-03-23 | 2021-04-28 | 10 | 0 | 24 | 36 | 100% | 0.27778 | 1 | Completed
ER6371LT | W202 | W202.A4030 | HRA Reactors Shutdown Essential Safety Cases | Civil Integrity Overview EAN Completed | 2021-03-24 | 2021-03-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4030 | HYA Reactors Shutdown Essential Safety Cases | Civil Integrity Overview EAN Completed | 2021-03-24 | 2021-03-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4310 | HRA Reactors Shutdown Essential Safety Cases | Containment Head Document Draft Report Verified by TSA | 2021-03-25 | 2021-06-21 | 19 | 0 | 59 | 88 | 100% | 0.21591 | 1 | Completed
ER6661LT | W206 | W206.A4310 | HYA Reactors Shutdown Essential Safety Cases | Containment Head Document Draft Report Verified by TSA | 2021-03-25 | 2021-06-21 | 19 | 0 | 59 | 88 | 100% | 0.21591 | 1 | Completed
ER6378LT | W222 | W222.A9810 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN | 2021-03-26 | 2021-04-23 | 2 | 0 | 19 | 28 | 100% | 0.071429 | 1 | Completed
ER6650LT | W226 | W226.A9810 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN | 2021-03-26 | 2021-04-23 | 2 | 0 | 19 | 28 | 100% | 0.071429 | 1 | Completed
ER6378LT | W222 | W222.A26680 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Review of Interlock Maintenance Review EAN (REV 000) | 2021-03-26 | 2021-03-26 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26680 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Review of Interlock Maintenance Review EAN (REV 000) | 2021-03-26 | 2021-03-26 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26690 | HRA Fuel Handling Essential Safety Case | Draft Review of Interlock Maintenance Review EAN (REV 000) | 2021-03-29 | 2021-09-01 | 20 | 0 | 108 | 156 | 100% | 0.12821 | 1 | Completed
ER6650LT | W226 | W226.A26690 | HYA Fuel Handling Essential Safety Case | Draft Review of Interlock Maintenance Review EAN (REV 000) | 2021-03-29 | 2021-09-01 | 20 | 0 | 108 | 156 | 100% | 0.12821 | 1 | Completed
ER6370LT | W201 | ER6370.A11270 | HNB Reactors Shutdown Essential Safety Cases | Programme Management - End MS | 2021-03-31 | 2021-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A27245 | HRA Fuel Handling Essential Safety Case | PSA Model Verification | 2021-03-31 | 2021-05-19 | 22 | 0 | 33 | 49 | 100% | 0.44898 | 1 | Completed
ER6650LT | W226 | W226.A27245 | HYA Fuel Handling Essential Safety Case | PSA Model Verification | 2021-03-31 | 2021-05-19 | 23 | 0 | 32 | 49 | 100% | 0.46939 | 1 | Completed
ER6371LT | W202 | W202.A3900 | HRA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Supporting Plant | 2021-04-01 | 2021-04-12 | 6 | 0 | 6 | 11 | 100% | 0.54545 | 1 | Completed
ER6661LT | W206 | W206.A3900 | HYA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Supporting Plant | 2021-04-01 | 2021-04-12 | 6 | 0 | 6 | 11 | 100% | 0.54545 | 1 | Completed
ER6378LT | W222 | W222.A26180 | HRA Fuel Handling Essential Safety Case | Additional Thermal and Rad Assessment of High Risk Areas##(Cost Summary)## ### (C5) | 2021-04-01 | 2021-04-26 | 28 | 0 | 16 | 25 | 100% | 1.12 | 1 | Completed
ER6378LT | W222 | W222.A26170 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Additional Thermal and Rad Assessment of High Risk Areas EAN | 2021-04-01 | 2021-04-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A18410 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Operator Training Handover Strategy Document (to P6.6) | 2021-04-01 | 2021-04-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A18370 | HRA Fuel Handling Essential Safety Case | Operator Training Handover Strategy Document ##(Cost Summary)## | 2021-04-01 | 2021-04-26 | 76 | 0 | 15 | 25 | 100% | 3.04 | 1 | Completed
ER6650LT | W226 | W226.A18370 | HYA Fuel Handling Essential Safety Case | Operator Training Handover Strategy Document ##(Cost Summary)## | 2021-04-01 | 2021-04-26 | 76 | 0 | 15 | 25 | 100% | 3.04 | 1 | Completed
ER6650LT | W226 | W226.A18410 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Operator Training Handover Strategy Document (to P6.6) | 2021-04-01 | 2021-04-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26170 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Additional Thermal and Rad Assessment of High Risk Areas EAN | 2021-04-01 | 2021-04-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26180 | HYA Fuel Handling Essential Safety Case | Additional Thermal and Rad Assessment of High Risk Areas##(Cost Summary)## ### (C5) | 2021-04-01 | 2021-04-26 | 28 | 0 | 16 | 25 | 100% | 1.12 | 1 | Completed
ER6371LT | W202 | W202.1000 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - Summary | 2021-04-01 | 2021-07-23 | 78 | 0 | 78 | 113 | 100% | 0.69027 | 1 | Completed
ER6371LT | W202 | W202.1010 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - Prepare Draft EAN | 2021-04-01 | 2021-05-28 | 39 | 0 | 39 | 57 | 100% | 0.68421 | 1 | Completed
ER6371LT | W202 | W202.1110 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - Vibration in the FPU - Review Offer, prepare and issue CI | 2021-04-01 | 2021-04-06 | 2 | 0 | 2 | 5 | 100% | 0.4 | 1 | Completed
ER6661LT | W206 | W206.1000 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - Summary | 2021-04-01 | 2021-07-23 | 78 | 0 | 78 | 113 | 100% | 0.69027 | 1 | Completed
ER6661LT | W206 | W206.1010 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - Prepare Draft EAN | 2021-04-01 | 2021-05-28 | 39 | 0 | 39 | 57 | 100% | 0.68421 | 1 | Completed
ER6661LT | W206 | W206.1110 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - Vibration in the FPU - Review Offer, prepare and issue CI | 2021-04-01 | 2021-04-06 | 2 | 0 | 2 | 5 | 100% | 0.4 | 1 | Completed
ER6378LT | W222 | W222.A25150 | HRA Fuel Handling Essential Safety Case | Basis of Analysis Report EAN Available (UPDATE) (REV 001) | 2021-04-06 | 2021-04-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25150 | HYA Fuel Handling Essential Safety Case | Basis of Analysis Report EAN Available (UPDATE) (REV 001) | 2021-04-06 | 2021-04-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26510 | HRA Fuel Handling Essential Safety Case | Verify LVDT Weight Sensing System matters arising from Review of HH1 FM Protection & Issue for Technical Review | 2021-04-06 | 2021-04-07 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6378LT | W222 | W222.A26190 | HRA Fuel Handling Essential Safety Case | Draft Additional Thermal and Rad Assessment of High Risk Areas EAN | 2021-04-06 | 2021-04-16 | 9 | 0 | 9 | 10 | 100% | 0.9 | 1 | Completed
ER6378LT | W222 | W222.A23470 | HRA Fuel Handling Essential Safety Case | Verify Complex FEA (Dynamic R3 Analysis) EAN and Issue for Technical Review | 2021-04-06 | 2021-04-14 | 7 | 0 | 7 | 8 | 100% | 0.875 | 1 | Completed
ER6378LT | W222 | W222.A23350 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Update Core Support Plate Properties Methodology & Toughness Properties EAN | 2021-04-06 | 2021-04-08 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6378LT | W222 | W222.A18420 | HRA Fuel Handling Essential Safety Case | Draft Operator Training Handover Strategy Document (to P6.6) | 2021-04-06 | 2021-04-26 | 20 | 0 | 14 | 20 | 100% | 1 | 1 | Completed
ER6650LT | W226 | W226.A18420 | HYA Fuel Handling Essential Safety Case | Draft Operator Training Handover Strategy Document (to P6.6) | 2021-04-06 | 2021-04-26 | 20 | 0 | 14 | 20 | 100% | 1 | 1 | Completed
ER6650LT | W226 | W226.A23350 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Update Core Support Plate Properties Methodology & Toughness Properties EAN | 2021-04-06 | 2021-04-08 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6650LT | W226 | W226.A23470 | HYA Fuel Handling Essential Safety Case | Verify Complex FEA (Dynamic R3 Analysis) EAN and Issue for Technical Review | 2021-04-06 | 2021-04-14 | 7 | 0 | 7 | 8 | 100% | 0.875 | 1 | Completed
ER6650LT | W226 | W226.A26190 | HYA Fuel Handling Essential Safety Case | Draft Additional Thermal and Rad Assessment of High Risk Areas EAN | 2021-04-06 | 2021-04-16 | 9 | 0 | 9 | 10 | 100% | 0.9 | 1 | Completed
ER6650LT | W226 | W226.A26510 | HYA Fuel Handling Essential Safety Case | Verify LVDT Weight Sensing System matters arising from Review of HH1 FM Protection & Issue for Technical Review | 2021-04-06 | 2021-04-07 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6378LT | W222 | W222.A24260 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Hazards Review EAN | 2021-04-07 | 2021-04-13 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6650LT | W226 | W226.A24260 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Hazards Review EAN | 2021-04-07 | 2021-04-13 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.1120 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - Vibration in the FPU - Supplier mobilisation time | 2021-04-07 | 2021-04-14 | 6 | 0 | 6 | 7 | 100% | 0.85714 | 1 | Completed
ER6661LT | W206 | W206.1120 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - Vibration in the FPU - Supplier mobilisation time | 2021-04-07 | 2021-04-14 | 6 | 0 | 6 | 7 | 100% | 0.85714 | 1 | Completed
ER6378LT | W222 | W222.A26520 | HRA Fuel Handling Essential Safety Case | Technical Review of LVDT Weight Sensing System matters arising from Review of HH1 FM Protection | 2021-04-08 | 2021-04-13 | 4 | 0 | 4 | 5 | 100% | 0.8 | 1 | Completed
ER6650LT | W226 | W226.A26520 | HYA Fuel Handling Essential Safety Case | Technical Review of LVDT Weight Sensing System matters arising from Review of HH1 FM Protection | 2021-04-08 | 2021-04-13 | 4 | 0 | 4 | 5 | 100% | 0.8 | 1 | Completed
ER6378LT | W222 | W222.A8910 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload FPU Lifting Integrity while Handling at the Reactor EAN to CDMS | 2021-04-09 | 2021-04-09 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A8920 | HRA Fuel Handling Essential Safety Case | FPU Lifting Integrity while Handling at the Reactor EAN Available | 2021-04-09 | 2021-04-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A8920 | HYA Fuel Handling Essential Safety Case | FPU Lifting Integrity while Handling at the Reactor EAN Available | 2021-04-09 | 2021-04-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A8910 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload FPU Lifting Integrity while Handling at the Reactor EAN to CDMS | 2021-04-09 | 2021-04-09 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A23360 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Update Core Support Plate Properties Methodology & Toughness Properties EAN to CDMS | 2021-04-09 | 2021-05-04 | 2 | 0 | 17 | 25 | 100% | 0.08 | 1 | Completed
ER6650LT | W226 | W226.A23360 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Update Core Support Plate Properties Methodology & Toughness Properties EAN to CDMS | 2021-04-09 | 2021-05-04 | 2 | 0 | 17 | 25 | 100% | 0.08 | 1 | Completed
ER6378LT | W222 | W222.A23540 | HRA Fuel Handling Essential Safety Case | Verify Fast Fracture R6 Analysis EAN and Issue for Technical Review | 2021-04-12 | 2021-04-30 | 10 | 0 | 14 | 18 | 100% | 0.55556 | 1 | Completed
ER6650LT | W226 | W226.A23540 | HYA Fuel Handling Essential Safety Case | Verify Fast Fracture R6 Analysis EAN and Issue for Technical Review | 2021-04-12 | 2021-04-30 | 10 | 0 | 14 | 18 | 100% | 0.55556 | 1 | Completed
ER6371LT | W202 | W202.A3960 | HRA Reactors Shutdown Essential Safety Cases | TSA Issue Final Supporting Plant Report | 2021-04-12 | 2021-04-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3960 | HYA Reactors Shutdown Essential Safety Cases | TSA Issue Final Supporting Plant Report | 2021-04-12 | 2021-04-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3990 | HRA Reactors Shutdown Essential Safety Cases | Supporting Plant Report TR Completed and uploaded to CDMS | 2021-04-13 | 2021-04-26 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6661LT | W206 | W206.A3990 | HYA Reactors Shutdown Essential Safety Cases | Supporting Plant Report TR Completed and uploaded to CDMS | 2021-04-13 | 2021-04-26 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6378LT | W222 | W222.A26530 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue LVDT Weight Sensing System matters arising from Review of HH1 FM Protection | 2021-04-14 | 2021-04-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24270 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Hazards Review EAN to CDMS | 2021-04-14 | 2021-04-19 | 5 | 0 | 3 | 5 | 100% | 1 | 1 | Completed
ER6650LT | W226 | W226.A24270 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Hazards Review EAN to CDMS | 2021-04-14 | 2021-04-19 | 5 | 0 | 3 | 5 | 100% | 1 | 1 | Completed
ER6650LT | W226 | W226.A26530 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue LVDT Weight Sensing System matters arising from Review of HH1 FM Protection | 2021-04-14 | 2021-04-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26540 | HRA Fuel Handling Essential Safety Case | Complete LVDT Weight Sensing System matters arising from Review of HH1 FM Protection to CDMS | 2021-04-15 | 2021-04-15 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26040 | HRA Fuel Handling Essential Safety Case | Concept Detail and Specification ##(Cost Summary)## (C5) (NEW) | 2021-04-15 | 2021-04-26 | 65 | 0 | 7 | 11 | 100% | 5.9091 | 1 | Completed
ER6378LT | W222 | W222.A23870 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Concept Detail and Specification EAN | 2021-04-15 | 2021-04-15 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A23490 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Complex FEA (Dynamic R3 Analysis) EAN | 2021-04-15 | 2021-05-21 | 5 | 0 | 26 | 36 | 100% | 0.13889 | 1 | Completed
ER6650LT | W226 | W226.A23490 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Complex FEA (Dynamic R3 Analysis) EAN | 2021-04-15 | 2021-05-21 | 5 | 0 | 26 | 36 | 100% | 0.13889 | 1 | Completed
ER6650LT | W226 | W226.A23870 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Concept Detail and Specification EAN | 2021-04-15 | 2021-04-15 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26040 | HYA Fuel Handling Essential Safety Case | Concept Detail and Specification ##(Cost Summary)## (C5) (NEW) | 2021-04-15 | 2021-04-26 | 65 | 0 | 7 | 11 | 100% | 5.9091 | 1 | Completed
ER6650LT | W226 | W226.A26540 | HYA Fuel Handling Essential Safety Case | Complete LVDT Weight Sensing System matters arising from Review of HH1 FM Protection to CDMS | 2021-04-15 | 2021-04-15 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.1130 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - Vibration in the FPU - Pre Job Brief | 2021-04-15 | 2021-04-15 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.1130 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - Vibration in the FPU - Pre Job Brief | 2021-04-15 | 2021-04-15 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26550 | HRA Fuel Handling Essential Safety Case | LVDT Weight Sensing System matters arising from Review of HH1 FM Protection Available | 2021-04-15 | 2021-04-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26550 | HYA Fuel Handling Essential Safety Case | LVDT Weight Sensing System matters arising from Review of HH1 FM Protection Available | 2021-04-15 | 2021-04-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A23880 | HRA Fuel Handling Essential Safety Case | Draft Concept Detail and Specification EAN | 2021-04-16 | 2021-04-26 | 35 | 0 | 6 | 10 | 100% | 3.5 | 1 | Completed
ER6650LT | W226 | W226.A23880 | HYA Fuel Handling Essential Safety Case | Draft Concept Detail and Specification EAN | 2021-04-16 | 2021-04-26 | 35 | 0 | 6 | 10 | 100% | 3.5 | 1 | Completed
ER6371LT | W202 | W202.A18260 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Prepare Vibration in the FPU EAN | 2021-04-16 | 2021-06-10 | 21 | 0 | 38 | 55 | 100% | 0.38182 | 1 | Completed
ER6371LT | W202 | W202.A18255 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Vibration in the FPU EAN - Summary | 2021-04-16 | 2021-07-30 | 74 | 0 | 74 | 105 | 100% | 0.70476 | 1 | Completed
ER6661LT | W206 | W206.A18260 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Prepare Vibration in the FPU Report | 2021-04-16 | 2021-06-10 | 21 | 0 | 38 | 55 | 100% | 0.38182 | 1 | Completed
ER6661LT | W206 | W206.A18255 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Vibration in the FPU Report - Summary | 2021-04-16 | 2021-07-30 | 74 | 0 | 74 | 105 | 100% | 0.70476 | 1 | Completed
ER6378LT | W222 | W222.A24280 | HRA Fuel Handling Essential Safety Case | Hazards Review EAN Available | 2021-04-19 | 2021-04-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24280 | HYA Fuel Handling Essential Safety Case | Hazards Review EAN Available | 2021-04-19 | 2021-04-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.1240 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - HF Assessment of Misloading Fault - Summary | 2021-04-19 | 2021-05-14 | 15 | 0 | 19 | 25 | 100% | 0.6 | 1 | Completed
ER6371LT | W202 | W202.1250 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - HF Assessment of Misloading Fault - Draft and issue RFS | 2021-04-19 | 2021-04-23 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6661LT | W206 | W206.1420 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - HF Assessment of Misloading Fault - Summary | 2021-04-19 | 2021-05-14 | 15 | 0 | 19 | 25 | 100% | 0.6 | 1 | Completed
ER6661LT | W206 | W206.1430 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - HF Assessment of Misloading Fault - Draft and issue RFS | 2021-04-19 | 2021-04-23 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6378LT | W222 | W222.A26200 | HRA Fuel Handling Essential Safety Case | Verify Additional Thermal and Rad Assessment of High Risk Areas and Issue for Technical Review | 2021-04-19 | 2021-04-21 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6650LT | W226 | W226.A26200 | HYA Fuel Handling Essential Safety Case | Verify Additional Thermal and Rad Assessment of High Risk Areas and Issue for Technical Review | 2021-04-19 | 2021-04-21 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6650LT | W226 | W226.A9010 | HYA Fuel Handling Essential Safety Case | Verification of Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN | 2021-04-21 | 2021-05-14 | 14 | 0 | 16 | 23 | 100% | 0.6087 | 1 | Completed
ER6378LT | W222 | W222.A9010 | HRA Fuel Handling Essential Safety Case | Verification of Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN | 2021-04-21 | 2021-05-14 | 14 | 0 | 17 | 23 | 100% | 0.6087 | 1 | Completed
ER6378LT | W222 | W222.A26210 | HRA Fuel Handling Essential Safety Case | Technical Review of Additional Thermal and Rad Assessment of High Risk AreasEAN | 2021-04-22 | 2021-04-26 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6650LT | W226 | W226.A26210 | HYA Fuel Handling Essential Safety Case | Technical Review of Additional Thermal and Rad Assessment of High Risk AreasEAN | 2021-04-22 | 2021-04-26 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6371LT | W202 | W202.A4560 | HRA Reactors Shutdown Essential Safety Cases | Core Cooling Head Document Draft Report Verified by TSA | 2021-04-23 | 2021-06-30 | 24 | 0 | 46 | 68 | 100% | 0.35294 | 1 | Completed
ER6661LT | W206 | W206.A4560 | HYA Reactors Shutdown Essential Safety Cases | Core Cooling Head Document Draft Report Verified by TSA | 2021-04-23 | 2021-06-30 | 24 | 0 | 46 | 68 | 100% | 0.35294 | 1 | Completed
ER6371LT | W202 | W202.1260 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - HF Assessment of Misloading Fault - Supplier prepare and issue Offer | 2021-04-23 | 2021-04-26 | 3 | 0 | 1 | 3 | 100% | 1 | 1 | Completed
ER6661LT | W206 | W206.1440 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - HF Assessment of Misloading Fault - Supplier prepare and issue Offer | 2021-04-23 | 2021-04-26 | 3 | 0 | 1 | 3 | 100% | 1 | 1 | Completed
ER6371LT | W202 | W202.A2206050 | HRA Reactors Shutdown Essential Safety Cases | >>>INCOMING ENABLER (W222.A22250) Criticality Assessment for Dropped FPU at Reactor (DRY Condition) EAN Available ????? | 2021-04-26 | 2021-04-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206070 | HRA Reactors Shutdown Essential Safety Cases | >>>MIRROR OF INCOMING ENABLER (W222.A22250)Criticality Assessment for Dropped FPU at Reactor(DRY Condition)EAN Available | 2021-04-26 | 2021-04-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206050 | HYA Reactors Shutdown Essential Safety Cases | >>>INCOMING ENABLER (W226) Criticality Assessment for Dropped FPU at Reactor (DRY Condition) EAN Available ????? | 2021-04-26 | 2021-04-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206070 | HYA Reactors Shutdown Essential Safety Cases | >>>MIRROR OF INCOMING ENABLER (W226)Criticality Assessment for Dropped FPU at Reactor(DRY Condition)EAN Available | 2021-04-26 | 2021-04-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3950 | HYA Reactors Shutdown Essential Safety Cases | INTERFACE MILESTONE - (W222.A22250, A22260)Criticality Assessment for Dropped FPU at Reactor(DRY Condition)EAN Available | 2021-04-26 | 2021-04-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A5580 | HRA Reactors Shutdown Essential Safety Cases | HRA References not Impacted by Core Support Plate/Shock Absorber Decision Complete | 2021-04-26 | 2021-04-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5560 | HYA Reactors Shutdown Essential Safety Cases | HYA References not Impacted by Core Support Plate/Shock Absorber Decision Complete | 2021-04-26 | 2021-04-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26220 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Additional Thermal and Rad Assessment of High Risk Areas EAN | 2021-04-26 | 2021-04-26 | 2 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26230 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Additional Thermal and Rad Assessment of High Risk Areas EAN to CDMS | 2021-04-26 | 2021-04-26 | 2 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26240 | HRA Fuel Handling Essential Safety Case | Additional Thermal and Rad Assessment of High Risk Areas EAN Available | 2021-04-26 | 2021-04-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A23890 | HRA Fuel Handling Essential Safety Case | Verify Concept Detail and Specification EAN for Technical Review | 2021-04-26 | 2021-04-26 | 19 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A23910 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Concept Detail and Specification EAN | 2021-04-26 | 2021-04-26 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A23920 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Concept Detail and Specification EAN to CDMS | 2021-04-26 | 2021-04-26 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A23930 | HRA Fuel Handling Essential Safety Case | Concept Detail and Specification EAN Available | 2021-04-26 | 2021-04-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A9530 | HRA Fuel Handling Essential Safety Case | Verify Criticality Assessment for Dropped FPU at Reactor EAN and Issue for Technical Review | 2021-04-26 | 2021-04-26 | 10 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A9540 | HRA Fuel Handling Essential Safety Case | Technical Review of Criticality Assessment for Dropped FPU at Reactor EAN | 2021-04-26 | 2021-04-26 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A9550 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Criticality Assessment for Dropped FPU at Reactor EAN | 2021-04-26 | 2021-04-26 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A9560 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Criticality Assessment for Dropped FPU at Reactor EAN to CDMS | 2021-04-26 | 2021-04-26 | 5 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A18430 | HRA Fuel Handling Essential Safety Case | Verification of Operator Training Handover Strategy Document (to P6.6) | 2021-04-26 | 2021-04-26 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A18440 | HRA Fuel Handling Essential Safety Case | Technical Review of Operator Training Handover Strategy Document (to P6.6) | 2021-04-26 | 2021-04-26 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A18450 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Operator Training Handover Strategy Document (to P6.6) | 2021-04-26 | 2021-04-26 | 2 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A18460 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Operator Training Handover Strategy Document (to P6.6) to CDMS | 2021-04-26 | 2021-04-26 | 2 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A18470 | HRA Fuel Handling Essential Safety Case | Operator Training Handover Strategy Document (to P6.6) Available | 2021-04-26 | 2021-04-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A22250 | HRA Fuel Handling Essential Safety Case | >>>OUTGOING ENABLER (W202.A2206050) Criticality Assessment for Dropped FPU at Reactor - EAN Available | 2021-04-26 | 2021-04-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A18470 | HYA Fuel Handling Essential Safety Case | Operator Training Handover Strategy Document (to P6.6) Available | 2021-04-26 | 2021-04-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A18460 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Operator Training Handover Strategy Document (to P6.6) to CDMS | 2021-04-26 | 2021-04-26 | 2 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A18450 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Operator Training Handover Strategy Document (to P6.6) | 2021-04-26 | 2021-04-26 | 2 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A18440 | HYA Fuel Handling Essential Safety Case | Technical Review of Operator Training Handover Strategy Document (to P6.6) | 2021-04-26 | 2021-04-26 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A18430 | HYA Fuel Handling Essential Safety Case | Verification of Operator Training Handover Strategy Document (to P6.6) | 2021-04-26 | 2021-04-26 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A9560 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Criticality Assessment for Dropped FPU at Reactor EAN to CDMS | 2021-04-26 | 2021-04-26 | 5 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A9550 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Criticality Assessment for Dropped FPU at Reactor EAN | 2021-04-26 | 2021-04-26 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A9540 | HYA Fuel Handling Essential Safety Case | Technical Review of Criticality Assessment for Dropped FPU at Reactor EAN | 2021-04-26 | 2021-04-26 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A9530 | HYA Fuel Handling Essential Safety Case | Verify Criticality Assessment for Dropped FPU at Reactor EAN and Issue for Technical Review | 2021-04-26 | 2021-04-26 | 10 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23930 | HYA Fuel Handling Essential Safety Case | Concept Detail and Specification EAN Available | 2021-04-26 | 2021-04-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23920 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Concept Detail and Specification EAN to CDMS | 2021-04-26 | 2021-04-26 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23910 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Concept Detail and Specification EAN | 2021-04-26 | 2021-04-26 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23890 | HYA Fuel Handling Essential Safety Case | Verify Concept Detail and Specification EAN for Technical Review | 2021-04-26 | 2021-04-26 | 19 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24030 | HYA Fuel Handling Essential Safety Case | Verify Dropped FPU Optioneering Documents EAN for Technical Review | 2021-04-26 | 2021-06-02 | 7 | 0 | 25 | 37 | 100% | 0.18919 | 1 | Completed
ER6650LT | W226 | W226.A26230 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Additional Thermal and Rad Assessment of High Risk Areas EAN to CDMS | 2021-04-26 | 2021-04-26 | 2 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26220 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Additional Thermal and Rad Assessment of High Risk Areas EAN | 2021-04-26 | 2021-04-26 | 2 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27220 | HYA Fuel Handling Essential Safety Case | >>>OUTGOING ENABLER (W206.A8500?) Criticality Assessment for Dropped FPU at Reactor (DRY Condition) | 2021-04-26 | 2021-04-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24030 | HRA Fuel Handling Essential Safety Case | Verify Dropped FPU Optioneering Documents EAN for Technical Review | 2021-04-26 | 2021-06-02 | 11 | 0 | 25 | 37 | 100% | 0.2973 | 1 | Completed
ER6378LT | W222 | W222.A9820 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN to CDMS | 2021-04-26 | 2021-04-28 | 5 | 0 | 2 | 2 | 100% | 2.5 | 1 | Completed
ER6650LT | W226 | W226.A9820 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN to CDMS | 2021-04-26 | 2021-04-28 | 5 | 0 | 2 | 2 | 100% | 2.5 | 1 | Completed
ER6371LT | W202 | W202.A4060 | HRA Reactors Shutdown Essential Safety Cases | Supporting Plant Report Completed | 2021-04-26 | 2021-04-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4440 | HRA Reactors Shutdown Essential Safety Cases | All Supporting Technical References Complete - Claim 3 Cooling | 2021-04-26 | 2021-04-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4060 | HYA Reactors Shutdown Essential Safety Cases | Supporting Plant Report Completed | 2021-04-26 | 2021-04-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4440 | HYA Reactors Shutdown Essential Safety Cases | All Supporting Technical References Complete - Claim 3 Cooling | 2021-04-26 | 2021-04-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3950 | HRA Reactors Shutdown Essential Safety Cases | INTERFACE MILESTONE - (W222.A22250, A22260)Criticality Assessment for Dropped FPU at Reactor(DRY Condition)EAN Available | 2021-04-26 | 2021-04-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A9570 | HRA Fuel Handling Essential Safety Case | Criticality Assessment for Dropped FPU at Reactor EAN Available | 2021-04-26 | 2021-04-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A9570 | HYA Fuel Handling Essential Safety Case | Criticality Assessment for Dropped FPU at Reactor EAN Available | 2021-04-26 | 2021-04-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26240 | HYA Fuel Handling Essential Safety Case | Additional Thermal and Rad Assessment of High Risk Areas EAN Available | 2021-04-26 | 2021-04-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.1270 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - HF Assessment of Misloading Fault - Review Offer, prepare and issue CI | 2021-04-27 | 2021-04-27 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.1450 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - HF Assessment of Misloading Fault - Review Offer, prepare and issue CI | 2021-04-27 | 2021-04-27 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1510 | HNB Reactors Shutdown Essential Safety Cases | CO Sign-off (HNB) | 2021-04-28 | 2021-05-05 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6378LT | W222 | W222.A26360 | HRA Fuel Handling Essential Safety Case | Technical Review of The Grab Extend FPU Ledge/ Fault and Associated Protection Needs EAN | 2021-04-28 | 2021-06-01 | 14 | 0 | 23 | 34 | 100% | 0.41176 | 1 | Completed
ER6378LT | W222 | W222.A9830 | HRA Fuel Handling Essential Safety Case | Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN Available | 2021-04-28 | 2021-04-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A9830 | HYA Fuel Handling Essential Safety Case | Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN Available | 2021-04-28 | 2021-04-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26360 | HYA Fuel Handling Essential Safety Case | Technical Review of The Grab Extend FPU Ledge/ Fault and Associated Protection Needs EAN | 2021-04-28 | 2021-06-01 | 14 | 0 | 23 | 34 | 100% | 0.41176 | 1 | Completed
ER6650LT | W226 | W226.A25110 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Environmental Permit Compliance EAN to CDMS | 2021-05-03 | 2021-05-04 | 44 | 0 | 0 | 1 | 100% | 44 | 1 | Completed
ER6378LT | W222 | W222.A23570 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Fast Fracture R6 Analysis EAN to CDMS | 2021-05-04 | 2021-05-21 | 5 | 0 | 13 | 17 | 100% | 0.29412 | 1 | Completed
ER6650LT | W226 | W226.A23570 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Fast Fracture R6 Analysis EAN to CDMS | 2021-05-04 | 2021-05-21 | 5 | 0 | 14 | 17 | 100% | 0.29412 | 1 | Completed
ER6650LT | W226 | W226.A25120 | HYA Fuel Handling Essential Safety Case | Environmental Permit Compliance EAN Available | 2021-05-04 | 2021-05-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3600 | HRA Reactors Shutdown Essential Safety Cases | Shutdown Margin Head Document TR Completed and uploaded to CDMS | 2021-05-04 | 2021-06-10 | 10 | 0 | 27 | 37 | 100% | 0.27027 | 1 | Completed
ER6661LT | W206 | W206.A3600 | HYA Reactors Shutdown Essential Safety Cases | Shutdown Margin Head Document TR Completed and uploaded to CDMS | 2021-05-04 | 2021-06-10 | 10 | 0 | 27 | 37 | 100% | 0.27027 | 1 | Completed
ER6378LT | W222 | W222.A25110 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Environmental Permit Compliance EAN to CDMS | 2021-05-04 | 2021-05-04 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24940 | HRA Fuel Handling Essential Safety Case | Verify Human Factors Defuelling Issues Management Report EAN & Issue for Technical Review | 2021-05-04 | 2021-06-16 | 15 | 0 | 31 | 43 | 100% | 0.34884 | 1 | Completed
ER6650LT | W226 | W226.A24940 | HYA Fuel Handling Essential Safety Case | Verify Human Factors Defuelling Issues Management Report EAN & Issue for Technical Review | 2021-05-04 | 2021-06-16 | 15 | 0 | 31 | 43 | 100% | 0.34884 | 1 | Completed
ER6370LT | W201 | ER6370.A18370 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 187> - Vibration in the FPU Report Completed and Uploaded to CDMS | 2021-05-04 | 2021-05-05 | 5 | 0 | 2 | 1 | 100% | 5 | 1 | Completed
ER6378LT | W222 | W222.A25120 | HRA Fuel Handling Essential Safety Case | Environmental Permit Compliance EAN Available | 2021-05-04 | 2021-05-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A23370 | HRA Fuel Handling Essential Safety Case | Update Core Support Plate Properties Methodology & Toughness Properties EAN Available | 2021-05-04 | 2021-05-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23370 | HYA Fuel Handling Essential Safety Case | Update Core Support Plate Properties Methodology & Toughness Properties EAN Available | 2021-05-04 | 2021-05-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1370 | HNB Reactors Shutdown Essential Safety Cases | Verification complete (HNB) | 2021-05-05 | 2021-05-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A18380 | HNB Reactors Shutdown Essential Safety Cases | <NEW SCOPE CR 187> - Vibration in the FPU Report Complete | 2021-05-05 | 2021-05-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24750 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Human Factors Assessment of Dropped FPU Fault Sequences EAN | 2021-05-06 | 2021-06-18 | 10 | 0 | 31 | 43 | 100% | 0.23256 | 1 | Completed
ER6650LT | W226 | W226.A24750 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Human Factors Assessment of Dropped FPU Fault Sequences EAN | 2021-05-06 | 2021-06-18 | 10 | 0 | 31 | 43 | 100% | 0.23256 | 1 | Completed
ER6370LT | W201 | ER6370.A1380 | HNB Reactors Shutdown Essential Safety Cases | DA (Authorised Designer) Approval of CAT1 Safety Case (HNB) | 2021-05-06 | 2021-05-12 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | W201.1140 | HNB Reactors Shutdown Essential Safety Cases | INSA of Main Proposal - DA review/respond to comments | 2021-05-06 | 2021-05-12 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | W201.1150 | HNB Reactors Shutdown Essential Safety Cases | Claim 0 - DA respond to comments | 2021-05-06 | 2021-05-12 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | W201.1180 | HNB Reactors Shutdown Essential Safety Cases | Claim 1 - Formal INSA | 2021-05-06 | 2021-05-19 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6370LT | W201 | W201.1200 | HNB Reactors Shutdown Essential Safety Cases | Claim 2 - DA respond to comments | 2021-05-06 | 2021-05-12 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | W201.1240 | HNB Reactors Shutdown Essential Safety Cases | Claim 3 - Formal INSA | 2021-05-06 | 2021-05-19 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6370LT | W201 | W201.1260 | HNB Reactors Shutdown Essential Safety Cases | Claim 4 - Formal INSA | 2021-05-06 | 2021-05-19 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6370LT | W201 | W201.1310 | HNB Reactors Shutdown Essential Safety Cases | INSA of Appendices | 2021-05-06 | 2021-05-12 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A16170 | HNB Reactors Shutdown Essential Safety Cases | Verified Draft Available for INSA (T-7) EC 364023 <NSRS SC Approach & Outline> (Cat 1 KDM) (HNB) RS Essential SC | 2021-05-07 | 2021-05-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.1280 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - HF Assessment of Misloading Fault - Supplier mobilisation time | 2021-05-12 | 2021-05-13 | 1 | 0 | 1 | 1 | 100% | 1 | 1 | Completed
ER6661LT | W206 | W206.1460 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - HF Assessment of Misloading Fault - Supplier mobilisation time | 2021-05-12 | 2021-05-13 | 1 | 0 | 1 | 1 | 100% | 1 | 1 | Completed
ER6370LT | W201 | ER6370.A1420 | HNB Reactors Shutdown Essential Safety Cases | Incorporate INSA comments (HNB) | 2021-05-13 | 2021-06-01 | 5 | 0 | 13 | 19 | 100% | 0.26316 | 1 | Completed
ER6370LT | W201 | W201.1160 | HNB Reactors Shutdown Essential Safety Cases | Claim 0 - Formal INSA | 2021-05-13 | 2021-05-19 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | W201.1210 | HNB Reactors Shutdown Essential Safety Cases | Claim 2 - Formal INSA | 2021-05-13 | 2021-05-26 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6370LT | W201 | W201.1320 | HNB Reactors Shutdown Essential Safety Cases | INSA of Appendices - DA respond to comments | 2021-05-13 | 2021-05-19 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.1290 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - HF Assessment of Misloading Fault - Pre Job Brief | 2021-05-14 | 2021-05-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.1470 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - HF Assessment of Misloading Fault - Pre Job Brief | 2021-05-14 | 2021-05-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A2600 | HNB Enhanced Defuelling Safety Cases | Flow Diversion EAN - Draft and issue RFS | 2021-05-14 | 2021-06-01 | 2 | 0 | 12 | 18 | 100% | 0.11111 | 1 | Completed
ER6372LT | W203 | W203.A2595 | HNB Enhanced Defuelling Safety Cases | RFS - Flow Diversion EAN - Summary | 2021-05-14 | 2021-06-01 | 38 | 0 | 12 | 18 | 100% | 2.1111 | 1 | Completed
ER6378LT | W222 | W222.A25790 | HRA Fuel Handling Essential Safety Case | Living Safety Document ##(Cost Summary)## (C1) (NEW) ** | 2021-05-17 | 2024-07-22 | 802 | 0 | 804 | 1162 | 100% | 0.69019 | 1 | Completed
ER6378LT | W222 | W222.A24290 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Living Safety Document EAN | 2021-05-17 | 2021-05-17 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A9020 | HYA Fuel Handling Essential Safety Case | Technical Review of Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN | 2021-05-17 | 2021-05-28 | 5 | 0 | 10 | 11 | 100% | 0.45455 | 1 | Completed
ER6650LT | W226 | W226.A24290 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Living Safety Document EAN | 2021-05-17 | 2021-05-17 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25790 | HYA Fuel Handling Essential Safety Case | Living Safety Document ##(Cost Summary)## (C1) (NEW) ** | 2021-05-17 | 2024-09-02 | 830 | 0 | 832 | 1204 | 100% | 0.68937 | 1 | Completed
ER6371LT | W202 | W202.A2206440 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Prepare HF Assessment of Misloading Fault EAN | 2021-05-17 | 2021-06-21 | 10 | 0 | 24 | 35 | 100% | 0.28571 | 1 | Completed
ER6371LT | W202 | W202.A2206435 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - HF Assessment of Misloading Fault EAN - Summary | 2021-05-17 | 2021-07-30 | 44 | 0 | 54 | 74 | 100% | 0.59459 | 1 | Completed
ER6661LT | W206 | W206.1370 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Prepare HF Assessment of Misloading Fault EAN | 2021-05-17 | 2021-06-21 | 10 | 0 | 24 | 35 | 100% | 0.28571 | 1 | Completed
ER6661LT | W206 | W206.1365 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - HF Assessment of Misloading Fault EAN - Summary | 2021-05-17 | 2021-07-21 | 37 | 0 | 47 | 65 | 100% | 0.56923 | 1 | Completed
ER6378LT | W222 | W222.A26270 | HRA Fuel Handling Essential Safety Case | Verify Dropped FPU Fault Definition Document (FDD) (REV 001) EAN for Technical Review | 2021-05-17 | 2021-06-04 | 5 | 0 | 14 | 18 | 100% | 0.27778 | 1 | Completed
ER6378LT | W222 | W222.A9020 | HRA Fuel Handling Essential Safety Case | Technical Review of Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN | 2021-05-17 | 2021-05-28 | 5 | 0 | 10 | 11 | 100% | 0.45455 | 1 | Completed
ER6650LT | W226 | W226.A26270 | HYA Fuel Handling Essential Safety Case | Verify Dropped FPU Fault Definition Document (FDD) (REV 001) EAN for Technical Review | 2021-05-17 | 2021-06-04 | 5 | 0 | 14 | 18 | 100% | 0.27778 | 1 | Completed
ER6370LT | W201 | W201.1280 | HNB Reactors Shutdown Essential Safety Cases | Claim 5 - Formal INSA | 2021-05-17 | 2021-05-28 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6378LT | W222 | W222.A24300 | HRA Fuel Handling Essential Safety Case | Draft Living Safety Document EAN | 2021-05-18 | 2021-12-03 | 40 | 0 | 142 | 199 | 100% | 0.20101 | 1 | Completed
ER6650LT | W226 | W226.A24300 | HYA Fuel Handling Essential Safety Case | Draft Living Safety Document EAN | 2021-05-18 | 2021-12-03 | 40 | 0 | 142 | 199 | 100% | 0.20101 | 1 | Completed
ER6371LT | W202 | W202.A4730 | HRA Reactors Shutdown Essential Safety Cases | Confirm Objectives to be Delivered at Gate C | 2021-05-18 | 2021-06-15 | 20 | 0 | 20 | 28 | 100% | 0.71429 | 1 | Completed
ER6371LT | W202 | W202.A4670 | HRA Reactors Shutdown Essential Safety Cases | Gate C Planning | 2021-05-18 | 2021-08-24 | 70 | 0 | 69 | 98 | 100% | 0.71429 | 1 | Completed
ER6661LT | W206 | W206.A4730 | HYA Reactors Shutdown Essential Safety Cases | Confirm Objectives to be Delivered at Gate C | 2021-05-18 | 2021-06-15 | 20 | 0 | 20 | 28 | 100% | 0.71429 | 1 | Completed
ER6661LT | W206 | W206.A4670 | HYA Reactors Shutdown Essential Safety Cases | Gate C Planning | 2021-05-18 | 2021-08-24 | 70 | 0 | 70 | 98 | 100% | 0.71429 | 1 | Completed
ER6650LT | W226 | W226.A27250 | HYA Fuel Handling Essential Safety Case | PSA Model TR | 2021-05-20 | 2021-05-27 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6378LT | W222 | W222.A27250 | HRA Fuel Handling Essential Safety Case | PSA Model TR | 2021-05-20 | 2021-05-27 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6370LT | W201 | W201.1170 | HNB Reactors Shutdown Essential Safety Cases | Claim 0 - DA respond to comments | 2021-05-20 | 2021-05-28 | 5 | 0 | 6 | 8 | 100% | 0.625 | 1 | Completed
ER6370LT | W201 | W201.1190 | HNB Reactors Shutdown Essential Safety Cases | Claim 1 - DA respond to comments | 2021-05-20 | 2021-05-28 | 5 | 0 | 6 | 8 | 100% | 0.625 | 1 | Completed
ER6370LT | W201 | W201.1250 | HNB Reactors Shutdown Essential Safety Cases | Claim 3 - DA respond to comments | 2021-05-20 | 2021-05-26 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | W201.1270 | HNB Reactors Shutdown Essential Safety Cases | Claim 4 - DA respond to comments | 2021-05-20 | 2021-05-26 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6378LT | W222 | W222.A23580 | HRA Fuel Handling Essential Safety Case | Fast Fracture R6 Analysis EAN Available | 2021-05-21 | 2021-05-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23580 | HYA Fuel Handling Essential Safety Case | Fast Fracture R6 Analysis EAN Available | 2021-05-21 | 2021-05-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | W201.1340 | HNB Reactors Shutdown Essential Safety Cases | Interactions with NP/SC 7786 - DA respond to comments | 2021-05-24 | 2021-05-28 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | W201.1380 | HNB Reactors Shutdown Essential Safety Cases | Update Cat 1 | 2021-05-24 | 2021-05-28 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6371LT | W202 | W202.A2206320 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> Optioneering - Draft and issue RFS | 2021-05-24 | 2021-05-28 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6371LT | W202 | W202.A2206310 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> Optioneering - Summary | 2021-05-24 | 2021-06-11 | 9 | 0 | 14 | 18 | 100% | 0.5 | 1 | Completed
ER6661LT | W206 | W206.1140 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> Optioneering - Draft and issue RFS | 2021-05-24 | 2021-05-28 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6661LT | W206 | W206.1135 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> Optioneering - Summary | 2021-05-24 | 2021-06-11 | 9 | 0 | 14 | 18 | 100% | 0.5 | 1 | Completed
ER6378LT | W222 | W222.A23500 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Complex FEA (Dynamic R3 Analysis) EAN to CDMS | 2021-05-24 | 2021-05-28 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6650LT | W226 | W226.A23500 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Complex FEA (Dynamic R3 Analysis) EAN to CDMS | 2021-05-24 | 2021-05-28 | 2 | 0 | 5 | 4 | 100% | 0.5 | 1 | Completed
ER6370LT | W201 | W201.1330 | HNB Reactors Shutdown Essential Safety Cases | Interactions with NP/SC 7786 | 2021-05-24 | 2021-05-28 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | W201.1350 | HNB Reactors Shutdown Essential Safety Cases | Consolidated Comments Issued | 2021-05-24 | 2021-05-27 | 5 | 0 | 3 | 3 | 100% | 1.6667 | 1 | Completed
ER6378LT | W222 | W222.A26470 | HRA Fuel Handling Essential Safety Case | Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection Available | 2021-05-26 | 2021-05-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25560 | HRA Fuel Handling Essential Safety Case | Pre Job Brief for Worker Dose Assessment (REV 000) EAN | 2021-05-26 | 2021-05-26 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25570 | HRA Fuel Handling Essential Safety Case | Draft Worker Dose Assessment (REV 000) EAN | 2021-05-26 | 2021-05-26 | 20 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25580 | HRA Fuel Handling Essential Safety Case | Verify Worker Dose Assessment (REV 000) EAN and Issue for Technical Review | 2021-05-26 | 2021-05-26 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25590 | HRA Fuel Handling Essential Safety Case | Technical Review of Worker Dose Assessment (REV 000) EAN | 2021-05-26 | 2021-05-26 | 3 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25600 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Worker Dose Assessment (REV 000) EAN | 2021-05-26 | 2021-05-26 | 3 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25610 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Worker Dose Assessment (REV 000) EAN to CDMS | 2021-05-26 | 2021-05-26 | 3 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25620 | HRA Fuel Handling Essential Safety Case | Worker Dose Assessment (REV 000) EAN Available | 2021-05-26 | 2021-05-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25010 | HRA Fuel Handling Essential Safety Case | Verify Dropped Fuel Head Document EAN and Issue for Technical Review | 2021-05-26 | 2021-05-26 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25020 | HRA Fuel Handling Essential Safety Case | Technical Review of Dropped Fuel Head Document EAN | 2021-05-26 | 2021-05-26 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25030 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Dropped Fuel Head Document EAN | 2021-05-26 | 2021-05-26 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25040 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Dropped Fuel Head Document EAN to CDMS | 2021-05-26 | 2021-05-26 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25050 | HRA Fuel Handling Essential Safety Case | Damage and Dropped Fuel Head Document EAN Available | 2021-05-26 | 2021-05-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25050 | HYA Fuel Handling Essential Safety Case | Damage and Dropped Fuel Head Document EAN Available | 2021-05-26 | 2021-05-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25040 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Dropped Fuel Head Document EAN to CDMS | 2021-05-26 | 2021-05-26 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25030 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Dropped Fuel Head Document EAN | 2021-05-26 | 2021-05-26 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25020 | HYA Fuel Handling Essential Safety Case | Technical Review of Dropped Fuel Head Document EAN | 2021-05-26 | 2021-05-26 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25010 | HYA Fuel Handling Essential Safety Case | Verify Dropped Fuel Head Document EAN and Issue for Technical Review | 2021-05-26 | 2021-05-26 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25620 | HYA Fuel Handling Essential Safety Case | Worker Dose Assessment (REV 000) EAN Available | 2021-05-26 | 2021-05-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25610 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Worker Dose Assessment (REV 000) EAN to CDMS | 2021-05-26 | 2021-05-26 | 3 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25600 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Worker Dose Assessment (REV 000) EAN | 2021-05-26 | 2021-05-26 | 3 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25590 | HYA Fuel Handling Essential Safety Case | Technical Review of Worker Dose Assessment (REV 000) EAN | 2021-05-26 | 2021-05-26 | 3 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25580 | HYA Fuel Handling Essential Safety Case | Verify Worker Dose Assessment (REV 000) EAN and Issue for Technical Review | 2021-05-26 | 2021-05-26 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25570 | HYA Fuel Handling Essential Safety Case | Draft Worker Dose Assessment (REV 000) EAN | 2021-05-26 | 2021-05-26 | 4 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25560 | HYA Fuel Handling Essential Safety Case | Pre Job Brief for Worker Dose Assessment (REV 000) EAN | 2021-05-26 | 2021-05-26 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26470 | HYA Fuel Handling Essential Safety Case | Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection Available | 2021-05-26 | 2021-05-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | W201.1230 | HNB Reactors Shutdown Essential Safety Cases | Discovery milestone - FPU vibration approach accepted | 2021-05-26 | 2021-05-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24810 | HRA Fuel Handling Essential Safety Case | Technical Review of Human Factors Assessment of FM Movements during Defuelling Operations EAN | 2021-05-27 | 2021-06-02 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6378LT | W222 | W222.A12680 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Development of Fuel Free Verification Methods (File Note) | 2021-05-27 | 2021-06-08 | 10 | 0 | 7 | 12 | 100% | 0.83333 | 1 | Completed
ER6650LT | W226 | W226.A12680 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Development of Fuel Free Verification Methods (File Note) | 2021-05-27 | 2021-06-08 | 10 | 0 | 7 | 12 | 100% | 0.83333 | 1 | Completed
ER6650LT | W226 | W226.A24810 | HYA Fuel Handling Essential Safety Case | Technical Review of Human Factors Assessment of FM Movements during Defuelling Operations EAN | 2021-05-27 | 2021-06-02 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | ER6370.A1350 | HNB Reactors Shutdown Essential Safety Cases | INA provision of full comments | 2021-05-27 | 2021-05-27 | 18 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | W201.1220 | HNB Reactors Shutdown Essential Safety Cases | Claim 2 - DA respond to comments | 2021-05-27 | 2021-06-01 | 5 | 0 | 3 | 5 | 100% | 1 | 1 | Completed
ER6371LT | W202 | W202.A2206130 | HRA Reactors Shutdown Essential Safety Cases | >>>INCOMING ENABLER (W222.A22270) Structural Integrity Analysis for Dropped FPU EAN Available | 2021-05-28 | 2021-05-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206140 | HRA Reactors Shutdown Essential Safety Cases | >>>MIRROR OF INCOMING ENABLER (W222.A22270) Structural Integrity Analysis for Dropped FPU EAN Available | 2021-05-28 | 2021-05-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206130 | HYA Reactors Shutdown Essential Safety Cases | >>>INCOMING ENABLER (W226) Structural Integrity Analysis for Dropped FPU EAN Available | 2021-05-28 | 2021-05-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206140 | HYA Reactors Shutdown Essential Safety Cases | >>>MIRROR OF INCOMING ENABLER (W226.A22270) Structural Integrity Analysis for Dropped FPU EAN Available | 2021-05-28 | 2021-05-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5550 | HYA Reactors Shutdown Essential Safety Cases | INTERFACE MILESTONE - (W222.A22270) Structural Integrity Analysis for Dropped FPU EAN Available | 2021-05-28 | 2021-05-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A17610 | HNB Reactors Shutdown Essential Safety Cases | >>>MIRROR of INCOMING ENABLER (W283) - LSD verification complete | 2021-05-28 | 2021-05-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1330 | HNB Reactors Shutdown Essential Safety Cases | INTERFACE MILESTONE - (W283) LSD verification complete | 2021-05-28 | 2021-05-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26820 | HRA Fuel Handling Essential Safety Case | HOLD POINT 2 - Confirm Technical Works on all Claims is Sufficient | 2021-05-28 | 2021-05-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A9030 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN | 2021-05-28 | 2021-05-28 | 5 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A9040 | HRA Fuel Handling Essential Safety Case | Complete TR Form & Upload Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN to CDMS | 2021-05-28 | 2021-05-28 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A9050 | HRA Fuel Handling Essential Safety Case | Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN Available | 2021-05-28 | 2021-05-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A17770 | HRA Fuel Handling Essential Safety Case | Claim 3 - P6.2 HRA/HYA Essential Defuelling SC - Lifting, Stringer & Pressure Boundary Integrity Complete | 2021-05-28 | 2021-05-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A18750 | HRA Fuel Handling Essential Safety Case | Claim 3 - P6.2 HRA/HYA Essential Defuelling SC - Lifting, Stringer & Pressure Boundary Integrity | 2021-05-28 | 2021-05-28 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A22270 | HRA Fuel Handling Essential Safety Case | >>>OUTGOING ENABLER (W202.A8500?) Structural Integrity Analysis for Dropped FPU EAN Available | 2021-05-28 | 2021-05-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26830 | HRA Fuel Handling Essential Safety Case | HRA References not impacted by core support plate/shock absorber decision complete (2020) | 2021-05-28 | 2021-05-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26830 | HYA Fuel Handling Essential Safety Case | HYA References not impacted by core support plate/shock absorber decision complete (2020) | 2021-05-28 | 2021-05-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A18750 | HYA Fuel Handling Essential Safety Case | Claim 3 - P6.2 HYA/HYA Essential Defuelling SC - Lifting, Stringer & Pressure Boundary Integrity | 2021-05-28 | 2021-05-28 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A17770 | HYA Fuel Handling Essential Safety Case | Claim 3 - P6.2 HYA/HYA Essential Defuelling SC - Lifting, Stringer & Pressure Boundary Integrity Complete | 2021-05-28 | 2021-05-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A9040 | HYA Fuel Handling Essential Safety Case | Complete TR Form & Upload Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN to CDMS | 2021-05-28 | 2021-05-28 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A9030 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN | 2021-05-28 | 2021-05-28 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27240 | HYA Fuel Handling Essential Safety Case | >>>OUTGOING ENABLER (W206.A8500?) Structural Integrity Analysis for Dropped FPU EAN Available | 2021-05-28 | 2021-05-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | W201.1290 | HNB Reactors Shutdown Essential Safety Cases | Claim 5 - DA respond to comments | 2021-05-28 | 2021-06-01 | 5 | 0 | 2 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | W201.1390 | HNB Reactors Shutdown Essential Safety Cases | Re- Verify | 2021-05-28 | 2021-06-02 | 5 | 0 | 3 | 5 | 100% | 1 | 1 | Completed
ER6370LT | W201 | W201.1370 | HNB Reactors Shutdown Essential Safety Cases | Responses Received | 2021-05-28 | 2021-06-01 | 10 | 0 | 2 | 4 | 100% | 2.5 | 1 | Completed
ER6371LT | W202 | W202.A5550 | HRA Reactors Shutdown Essential Safety Cases | INTERFACE MILESTONE - (W222.A22270) Structural Integrity Analysis for Dropped FPU EAN Available | 2021-05-28 | 2021-05-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A17600 | HNB Reactors Shutdown Essential Safety Cases | >>>INCOMING ENABLER (W283) - LSD verification complete | 2021-05-28 | 2021-05-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25190 | HRA Fuel Handling Essential Safety Case | HOLD POINT 1 - Core Support Plate (CSP) Qualification Milestone | 2021-05-28 | 2021-05-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A23510 | HRA Fuel Handling Essential Safety Case | Complex FEA (Dynamic R3 Analysis) EAN Available | 2021-05-28 | 2021-05-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A9050 | HYA Fuel Handling Essential Safety Case | Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN Available | 2021-05-28 | 2021-05-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A23510 | HYA Fuel Handling Essential Safety Case | Complex FEA (Dynamic R3 Analysis) EAN Available | 2021-05-28 | 2021-05-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25190 | HYA Fuel Handling Essential Safety Case | HOLD POINT 1 - Core Support Plate (CSP) Qualification Milestone | 2021-05-28 | 2021-05-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26820 | HYA Fuel Handling Essential Safety Case | HOLD POINT 2 - Confirm Technical Works on all Claims is Sufficient | 2021-05-28 | 2021-05-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.1020 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - Issue Draft EAN to EDF for Review. | 2021-05-28 | 2021-05-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.1020 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - Issue Draft EAN to EDF for Review. | 2021-05-28 | 2021-05-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | W201.1300 | HNB Reactors Shutdown Essential Safety Cases | Discovery milestone - Significant comments raised | 2021-05-28 | 2021-05-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | W201.1360 | HNB Reactors Shutdown Essential Safety Cases | Discovery milestone - Update to Cat 1 required | 2021-05-28 | 2021-05-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206330 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> Optioneering - Supplier prepare and issue Offer | 2021-05-31 | 2021-06-07 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6661LT | W206 | W206.1150 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> Optioneering - Supplier prepare and issue Offer | 2021-05-31 | 2021-06-07 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6372LT | W203 | W203.A1290 | HNB Enhanced Defuelling Safety Cases | Flow Diversion EAN - Summary | 2021-06-01 | 2021-09-22 | 59 | 0 | 81 | 113 | 100% | 0.52212 | 1 | Completed
ER6372LT | W203 | W203.A1300 | HNB Enhanced Defuelling Safety Cases | Flow Diversion EAN - Prepare Draft EAN | 2021-06-01 | 2021-06-25 | 20 | 0 | 18 | 24 | 100% | 0.83333 | 1 | Completed
ER6372LT | W203 | W203.A2610 | HNB Enhanced Defuelling Safety Cases | Flow Diversion EAN - Supplier prepare and issue Offer | 2021-06-01 | 2021-06-01 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A2620 | HNB Enhanced Defuelling Safety Cases | Flow Diversion EAN - Review Offer, prepare and issue CI | 2021-06-01 | 2021-06-01 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A2630 | HNB Enhanced Defuelling Safety Cases | Flow Diversion EAN - Supplier mobilisation time | 2021-06-01 | 2021-06-01 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A2640 | HNB Enhanced Defuelling Safety Cases | Flow Diversion EAN - Pre Job Brief | 2021-06-01 | 2021-06-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1430 | HNB Reactors Shutdown Essential Safety Cases | Prepare Station Director's Brief (HNB) | 2021-06-01 | 2021-06-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6372LT | W203 | W203.A1520 | HNB Enhanced Defuelling Safety Cases | Effect of air admission on reactor containment (Coolant conditions CO2) EAN up Rev - Address Comments from EDF Review | 2021-06-01 | 2021-06-14 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6371LT | W202 | W202.1030 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - Draft EAN Reviewed by EDF SQEP | 2021-06-01 | 2021-06-16 | 12 | 0 | 12 | 15 | 100% | 0.8 | 1 | Completed
ER6661LT | W206 | W206.1030 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - Draft EAN Reviewed by EDF SQEP | 2021-06-01 | 2021-06-16 | 12 | 0 | 12 | 15 | 100% | 0.8 | 1 | Completed
ER6371LT | W202 | W202.1170 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - Reactivity Assessment of Misloading Fault - Summary | 2021-06-01 | 2021-06-22 | 15 | 0 | 15 | 21 | 100% | 0.71429 | 1 | Completed
ER6371LT | W202 | W202.1180 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - Reactivity Assessment of Misloading Fault - Draft and issue RFS | 2021-06-01 | 2021-06-11 | 9 | 0 | 9 | 10 | 100% | 0.9 | 1 | Completed
ER6661LT | W206 | W206.1280 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - Reactivity Assessment of Misloading Fault - Summary | 2021-06-01 | 2021-06-22 | 15 | 0 | 15 | 21 | 100% | 0.71429 | 1 | Completed
ER6661LT | W206 | W206.1290 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - Reactivity Assessment of Misloading Fault - Draft and issue RFS | 2021-06-01 | 2021-06-11 | 9 | 0 | 9 | 10 | 100% | 0.9 | 1 | Completed
ER6378LT | W222 | W222.A26370 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue The Grab Extend FPU Ledge/ Fault and Associated Protection Needs EAN | 2021-06-02 | 2021-06-04 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6650LT | W226 | W226.A26370 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue The Grab Extend FPU Ledge/ Fault and Associated Protection Needs EAN | 2021-06-02 | 2021-06-04 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6378LT | W222 | W222.A24040 | HRA Fuel Handling Essential Safety Case | Technical Review of Dropped FPU Optioneering Documents EAN | 2021-06-03 | 2021-06-04 | 7 | 0 | 2 | 1 | 100% | 7 | 1 | Completed
ER6650LT | W226 | W226.A24040 | HYA Fuel Handling Essential Safety Case | Technical Review of Dropped FPU Optioneering Documents EAN | 2021-06-03 | 2021-06-04 | 7 | 0 | 2 | 1 | 100% | 7 | 1 | Completed
ER6378LT | W222 | W222.A25360 | HRA Fuel Handling Essential Safety Case | Verify Update to Fault Schedule/PSA (REV 000) EAN and Issue for Technical Review | 2021-06-03 | 2021-07-01 | 7 | 0 | 21 | 28 | 100% | 0.25 | 1 | Completed
ER6378LT | W222 | W222.A24820 | HRA Fuel Handling Essential Safety Case | Supplier Update and Human Factors Assessment of FM Movements during Defuelling Operations EAN | 2021-06-03 | 2021-07-07 | 5 | 0 | 25 | 34 | 100% | 0.14706 | 1 | Completed
ER6650LT | W226 | W226.A24820 | HYA Fuel Handling Essential Safety Case | Supplier Update and Human Factors Assessment of FM Movements during Defuelling Operations EAN | 2021-06-03 | 2021-07-07 | 5 | 0 | 25 | 34 | 100% | 0.14706 | 1 | Completed
ER6650LT | W226 | W226.A25360 | HYA Fuel Handling Essential Safety Case | Verify Update to Fault Schedule/PSA (REV 000) EAN and Issue for Technical Review | 2021-06-03 | 2021-07-01 | 7 | 0 | 21 | 28 | 100% | 0.25 | 1 | Completed
ER6370LT | W201 | W201.1410 | HNB Reactors Shutdown Essential Safety Cases | INSA Substantially Complete | 2021-06-03 | 2021-06-03 | 4 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16180 | HNB Reactors Shutdown Essential Safety Cases | INSA Assessment substantially comp (T - 3 weeks before NSC date) EC 364023 <NSRS SC Approach & Outline> (Cat 1 MS) (HNB) | 2021-06-03 | 2021-06-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A18420 | HNB Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W221, HNB Security Plan) INSA Assessment substantially comp (T - 3 weeks before NSC date) | 2021-06-03 | 2021-06-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26380 | HRA Fuel Handling Essential Safety Case | Complete The Grab Extend FPU Ledge/ Fault and Associated Protection Needs EAN to CDMS | 2021-06-07 | 2021-06-11 | 3 | 0 | 4 | 4 | 100% | 0.75 | 1 | Completed
ER6378LT | W222 | W222.A25440 | HRA Fuel Handling Essential Safety Case | Verification of Defuelling NSPs/SAGs (REV 000) EAN | 2021-06-07 | 2021-07-02 | 5 | 0 | 19 | 25 | 100% | 0.2 | 1 | Completed
ER6378LT | W222 | W222.A25170 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Dropped FPU Fault Definition Document (FDD) EAN to CDMS (REV 001) | 2021-06-07 | 2021-06-11 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6378LT | W222 | W222.A24050 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Dropped FPU Optioneering Documents EAN | 2021-06-07 | 2021-06-08 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6650LT | W226 | W226.A24050 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Dropped FPU Optioneering Documents EAN | 2021-06-07 | 2021-06-08 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6650LT | W226 | W226.A25170 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Dropped FPU Fault Definition Document (FDD) EAN to CDMS (REV 001) | 2021-06-07 | 2021-06-11 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6650LT | W226 | W226.A25440 | HYA Fuel Handling Essential Safety Case | Verification of Defuelling NSPs/SAGs (REV 000) EAN | 2021-06-07 | 2021-07-02 | 5 | 0 | 19 | 25 | 100% | 0.2 | 1 | Completed
ER6650LT | W226 | W226.A26380 | HYA Fuel Handling Essential Safety Case | Complete The Grab Extend FPU Ledge/ Fault and Associated Protection Needs EAN to CDMS | 2021-06-07 | 2021-06-11 | 3 | 0 | 4 | 4 | 100% | 0.75 | 1 | Completed
ER6378LT | W222 | W222.A12690 | HRA Fuel Handling Essential Safety Case | Development of Fuel Free Verification Methods (File Note) Available | 2021-06-08 | 2021-06-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A17750 | HRA Fuel Handling Essential Safety Case | Claim 1 - P6.2 HRA/HYA Essential Defuelling SC - Proposed Defuelling Strategy Complete | 2021-06-08 | 2021-06-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A18730 | HRA Fuel Handling Essential Safety Case | Claim 1 - P6.2 HRA/HYA Essential Defuelling SC - Proposed Defuelling Strategy | 2021-06-08 | 2021-06-08 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A18730 | HYA Fuel Handling Essential Safety Case | Claim 1 - P6.2 HYA/HYA Essential Defuelling SC - Proposed Defuelling Strategy | 2021-06-08 | 2021-06-08 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A17750 | HYA Fuel Handling Essential Safety Case | Claim 1 - P6.2 HYA/HYA Essential Defuelling SC - Proposed Defuelling Strategy Complete | 2021-06-08 | 2021-06-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A12690 | HYA Fuel Handling Essential Safety Case | Development of Fuel Free Verification Methods (File Note) Available | 2021-06-08 | 2021-06-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206340 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> Optioneering - Review Offer, prepare and issue CI | 2021-06-08 | 2021-06-09 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6661LT | W206 | W206.1160 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> Optioneering - Review Offer, prepare and issue CI | 2021-06-08 | 2021-06-09 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6378LT | W222 | W222.A24060 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Dropped FPU Optioneering Documents EAN to CDMS | 2021-06-09 | 2021-06-11 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6650LT | W226 | W226.A24060 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Dropped FPU Optioneering Documents EAN to CDMS | 2021-06-09 | 2021-06-11 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6371LT | W202 | W202.A2206350 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> Optioneering - Supplier mobilisation time | 2021-06-10 | 2021-06-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.1170 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> Optioneering - Supplier mobilisation time | 2021-06-10 | 2021-06-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16870 | HNB Reactors Shutdown Essential Safety Cases | Review NSC Presentation Paper and Brief Station Director - HNB | 2021-06-10 | 2021-06-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26390 | HRA Fuel Handling Essential Safety Case | The Grab Extend FPU Ledge/ Fault and Associated Protection Needs EAN Available | 2021-06-11 | 2021-06-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A18500 | HRA Fuel Handling Essential Safety Case | Claim 5 - P6.2 HRA/HYA Essential Defuelling SC - Dropped Fuel and Non-Fuel Complete | 2021-06-11 | 2021-06-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A18770 | HRA Fuel Handling Essential Safety Case | Claim 5 - P6.2 HRA/HYA Essential Defuelling SC - Dropped Fuel and Non-Fuel | 2021-06-11 | 2021-06-11 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A18770 | HYA Fuel Handling Essential Safety Case | Claim 5 - P6.2 HYA/HYA Essential Defuelling SC - Dropped Fuel and Non-Fuel | 2021-06-11 | 2021-06-11 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A18500 | HYA Fuel Handling Essential Safety Case | Claim 5 - P6.2 HYA/HYA Essential Defuelling SC - Dropped Fuel and Non-Fuel Complete | 2021-06-11 | 2021-06-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26390 | HYA Fuel Handling Essential Safety Case | The Grab Extend FPU Ledge/ Fault and Associated Protection Needs EAN Available | 2021-06-11 | 2021-06-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A18360 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Verify Vibration in the FPU EAN | 2021-06-11 | 2021-07-09 | 10 | 0 | 21 | 28 | 100% | 0.35714 | 1 | Completed
ER6661LT | W206 | W206.A18360 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Verify Vibration in the FPU Report | 2021-06-11 | 2021-07-09 | 10 | 0 | 21 | 28 | 100% | 0.35714 | 1 | Completed
ER6371LT | W202 | W202.A2206360 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> Optioneering - Pre Job Brief | 2021-06-11 | 2021-06-11 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.1180 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> Optioneering - Pre Job Brief | 2021-06-11 | 2021-06-11 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25180 | HRA Fuel Handling Essential Safety Case | Dropped FPU Fault Definition Document (FDD) EAN Available (REV 001) | 2021-06-11 | 2021-06-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24070 | HRA Fuel Handling Essential Safety Case | Dropped FPU Optioneering Documents EAN Available | 2021-06-11 | 2021-06-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24070 | HYA Fuel Handling Essential Safety Case | Dropped FPU Optioneering Documents EAN Available | 2021-06-11 | 2021-06-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25180 | HYA Fuel Handling Essential Safety Case | Dropped FPU Fault Definition Document (FDD) EAN Available (REV 001) | 2021-06-11 | 2021-06-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.1140 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> Optioneering - Develop Options for Workshop | 2021-06-14 | 2021-06-25 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6371LT | W202 | W202.1190 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - Reactivity Assessment of Misloading Fault - Supplier prepare and issue Offer | 2021-06-14 | 2021-06-16 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6371LT | W202 | W202.1135 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> Optioneering - Summary | 2021-06-14 | 2021-08-20 | 71 | 0 | 49 | 67 | 100% | 1.0597 | 1 | Completed
ER6661LT | W206 | W206.1200 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> Optioneering - Develop Options for Workshop | 2021-06-14 | 2021-06-25 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6661LT | W206 | W206.1300 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - Reactivity Assessment of Misloading Fault - Supplier prepare and issue Offer | 2021-06-14 | 2021-06-16 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6661LT | W206 | W206.1195 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> Optioneering - Summary | 2021-06-14 | 2021-08-20 | 50 | 0 | 49 | 67 | 100% | 0.74627 | 1 | Completed
ER6372LT | W203 | W203.A1580 | HNB Enhanced Defuelling Safety Cases | Effect of air admission on reactor containment (Coolant conditions CO2) EAN up Rev - Issue Final Report | 2021-06-14 | 2021-06-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1610 | HNB Enhanced Defuelling Safety Cases | Effect of air admission on reactor containment (Coolant conditions CO2) EAN up Rev - Completed and Uploaded to CDMS | 2021-06-15 | 2021-06-28 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6378LT | W222 | W222.A24970 | HRA Fuel Handling Essential Safety Case | Complete Review of Human Factors Defuelling Issues Management (DIM) Report EAN to CDMS | 2021-06-16 | 2021-06-16 | 5 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24970 | HYA Fuel Handling Essential Safety Case | Complete Review of Human Factors Defuelling Issues Management (DIM) Report EAN to CDMS | 2021-06-16 | 2021-06-16 | 5 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24880 | HRA Fuel Handling Essential Safety Case | Update DRAFT Human Reliability Baseline Report | 2021-06-16 | 2021-06-28 | 5 | 0 | 8 | 12 | 100% | 0.41667 | 1 | Completed
ER6650LT | W226 | W226.A27300 | HYA Fuel Handling Essential Safety Case | Update DRAFT Human Reliability Baseline Report | 2021-06-16 | 2021-06-28 | 5 | 0 | 9 | 12 | 100% | 0.41667 | 1 | Completed
ER6378LT | W222 | W222.A24980 | HRA Fuel Handling Essential Safety Case | Human Factors Defuelling Issues Management Report EAN Available | 2021-06-16 | 2021-06-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24980 | HYA Fuel Handling Essential Safety Case | Human Factors Defuelling Issues Management Report EAN Available | 2021-06-16 | 2021-06-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.1040 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - Address Comments from EDF Review on Draft EAN | 2021-06-17 | 2021-07-09 | 10 | 0 | 17 | 22 | 100% | 0.45455 | 1 | Completed
ER6661LT | W206 | W206.1040 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - Address Comments from EDF Review on Draft EAN | 2021-06-17 | 2021-07-09 | 10 | 0 | 17 | 22 | 100% | 0.45455 | 1 | Completed
ER6371LT | W202 | W202.1200 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - Reactivity Assessment of Misloading Fault - Review Offer, prepare and issue CI | 2021-06-17 | 2021-06-17 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.1310 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - Reactivity Assessment of Misloading Fault - Review Offer, prepare and issue CI | 2021-06-17 | 2021-06-17 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.1150 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> Optioneering - Peer Review | 2021-06-17 | 2021-06-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.1210 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> Optioneering - Peer Review | 2021-06-17 | 2021-06-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.1210 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - Reactivity Assessment of Misloading Fault - Supplier mobilisation time | 2021-06-18 | 2021-06-18 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.1320 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - Reactivity Assessment of Misloading Fault - Supplier mobilisation time | 2021-06-18 | 2021-06-18 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25510 | HRA Fuel Handling Essential Safety Case | Verify Assessment of Worker Risk (REV 000) EAN and Issue for Technical Review | 2021-06-21 | 2021-07-02 | 9 | 0 | 9 | 11 | 100% | 0.81818 | 1 | Completed
ER6650LT | W226 | W226.A25510 | HYA Fuel Handling Essential Safety Case | Verify Assessment of Worker Risk (REV 000) EAN and Issue for Technical Review | 2021-06-21 | 2021-07-02 | 9 | 0 | 9 | 11 | 100% | 0.81818 | 1 | Completed
ER6378LT | W222 | W222.A25220 | HRA Fuel Handling Essential Safety Case | Verify Hazard and Interlock Schedule EAN (REV 000) EAN and Issue for Technical Review | 2021-06-21 | 2021-06-30 | 5 | 0 | 8 | 9 | 100% | 0.55556 | 1 | Completed
ER6378LT | W222 | W222.A24760 | HRA Fuel Handling Essential Safety Case | Complete Review of Human Factors Assessment of Dropped FPU Fault Sequencess EAN to CDMS | 2021-06-21 | 2021-06-25 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6650LT | W226 | W226.A24760 | HYA Fuel Handling Essential Safety Case | Complete Review of Human Factors Assessment of Dropped FPU Fault Sequencess EAN to CDMS | 2021-06-21 | 2021-06-25 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6650LT | W226 | W226.A25220 | HYA Fuel Handling Essential Safety Case | Verify Hazard and Interlock Schedule EAN (REV 000) EAN and Issue for Technical Review | 2021-06-21 | 2021-06-30 | 5 | 0 | 7 | 9 | 100% | 0.55556 | 1 | Completed
ER6371LT | W202 | W202.1220 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - Reactivity Assessment of Misloading Fault - Pre Job Brief | 2021-06-21 | 2021-06-22 | 1 | 0 | 1 | 1 | 100% | 1 | 1 | Completed
ER6661LT | W206 | W206.1330 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - RFS - Reactivity Assessment of Misloading Fault - Pre Job Brief | 2021-06-21 | 2021-06-22 | 1 | 0 | 1 | 1 | 100% | 1 | 1 | Completed
ER6371LT | W202 | W202.A2206460 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Verify HF Assessment of Misloading Fault EAN | 2021-06-22 | 2021-07-09 | 5 | 0 | 14 | 17 | 100% | 0.29412 | 1 | Completed
ER6661LT | W206 | W206.1390 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Verify HF Assessment of Misloading Fault EAN | 2021-06-22 | 2021-07-09 | 5 | 0 | 14 | 17 | 100% | 0.29412 | 1 | Completed
ER6372LT | W203 | W203.A2660 | HNB Enhanced Defuelling Safety Cases | DISCOVERY MILESTONE: Scope of Technical References and Delivery Dates Agreed | 2021-06-23 | 2021-06-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16190 | HNB Reactors Shutdown Essential Safety Cases | NSC Presentation Date (T) EC (HNB-364023) Reactor Shutdown Essential Safety Case | 2021-06-24 | 2021-06-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A18180 | HNB Reactors Shutdown Essential Safety Cases | DA SC Support for NSC Presentation Date (T) EC (HNB-364023) | 2021-06-24 | 2021-06-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A18190 | HNB Reactors Shutdown Essential Safety Cases | INA SC Support for NSC Presentation Date (T) EC (HNB-364023) | 2021-06-24 | 2021-06-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24770 | HRA Fuel Handling Essential Safety Case | Human Factors Assessment of Dropped FPU Fault Sequences EAN Available | 2021-06-25 | 2021-06-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24770 | HYA Fuel Handling Essential Safety Case | Human Factors Assessment of Dropped FPU Fault Sequences EAN Available | 2021-06-25 | 2021-06-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.1160 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> Optioneering - Optioneering Workshop | 2021-06-25 | 2021-06-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.1220 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> Optioneering - Optioneering Workshop | 2021-06-25 | 2021-06-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24590 | HRA Fuel Handling Essential Safety Case | Verify Human Reliability Baseline Report EAN & Issue for Technical Review | 2021-06-28 | 2021-07-07 | 10 | 0 | 7 | 9 | 100% | 1.1111 | 1 | Completed
ER6650LT | W226 | W226.A24590 | HYA Fuel Handling Essential Safety Case | Verify Human Reliability Baseline Report EAN & Issue for Technical Review | 2021-06-28 | 2021-07-07 | 10 | 0 | 7 | 9 | 100% | 1.1111 | 1 | Completed
ER6371LT | W202 | W202.A2206370 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Prepare Reactivity Assessment of Misloading Fault EAN | 2021-06-28 | 2021-07-09 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6371LT | W202 | W202.A2206365 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Reactivity Assessment of Misloading Fault EAN - Summary | 2021-06-28 | 2021-07-22 | 23 | 0 | 19 | 24 | 100% | 0.95833 | 1 | Completed
ER6661LT | W206 | W206.1230 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Prepare Reactivity Assessment of Misloading Fault EAN | 2021-06-28 | 2021-07-09 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6661LT | W206 | W206.1225 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Reactivity Assessment of Misloading Fault EAN - Summary | 2021-06-28 | 2021-07-30 | 29 | 0 | 25 | 32 | 100% | 0.90625 | 1 | Completed
ER6370LT | W201 | ER6370.A1390 | HNB Reactors Shutdown Essential Safety Cases | NSC Consideration & advice to Station Director (HNB) | 2021-06-28 | 2021-06-30 | 5 | 0 | 2 | 2 | 100% | 2.5 | 1 | Completed
ER6372LT | W203 | W203.A1650 | HNB Enhanced Defuelling Safety Cases | Effect of air admission on reactor containment (Coolant conditions CO2) EAN up Rev - Report Completed | 2021-06-28 | 2021-06-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4590 | HRA Reactors Shutdown Essential Safety Cases | Verified Core Cooling Head Document Draft Report Issued to EDF for Technical Review. | 2021-06-30 | 2021-06-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4600 | HRA Reactors Shutdown Essential Safety Cases | Core Cooling Head Document Draft Report Technically Reviewed by EDF SQEP | 2021-06-30 | 2021-07-09 | 10 | 0 | 8 | 9 | 100% | 1.1111 | 1 | Completed
ER6661LT | W206 | W206.A4590 | HYA Reactors Shutdown Essential Safety Cases | Verified Core Cooling Head Document Draft Report Issued to EDF for Technical Review. | 2021-06-30 | 2021-06-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4600 | HYA Reactors Shutdown Essential Safety Cases | Core Cooling Head Document Draft Report Technically Reviewed by EDF SQEP | 2021-06-30 | 2021-07-09 | 10 | 0 | 8 | 9 | 100% | 1.1111 | 1 | Completed
ER6378LT | W222 | W222.A25230 | HRA Fuel Handling Essential Safety Case | Technical Review of Hazard and Interlock Schedule (REV 000) EAN | 2021-06-30 | 2021-07-02 | 10 | 0 | 2 | 2 | 100% | 5 | 1 | Completed
ER6650LT | W226 | W226.A25230 | HYA Fuel Handling Essential Safety Case | Technical Review of Hazard and Interlock Schedule (REV 000) EAN | 2021-06-30 | 2021-07-02 | 10 | 0 | 2 | 2 | 100% | 5 | 1 | Completed
ER6370LT | W201 | ER6370.A16200 | HNB Reactors Shutdown Essential Safety Cases | INSA Final Approval EC 364023 <NSRS SC Approach & Outline> (Cat 1 Milestone) (HNB) (Reactor Shutdown Essential SC) | 2021-07-01 | 2021-07-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A18410 | HNB Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W283) CAT 1 Reactors Shutdown SC INSA Approved | 2021-07-01 | 2021-07-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W520LT | W520 | W520.A1060 | FLEETWIDE CTO Defueling Safety Case Delivery | Confirm NSSB Board Availability | 2021-07-01 | 2021-07-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4700 | HRA Reactors Shutdown Essential Safety Cases | Produce verification plan (HRA,) | 2021-07-01 | 2021-08-02 | 2 | 0 | 22 | 32 | 100% | 0.0625 | 1 | Completed
ER6371LT | W202 | W202.A4710 | HRA Reactors Shutdown Essential Safety Cases | Define Project Control Structures (WBS/CBS/OBS/PBS) | 2021-07-01 | 2021-07-23 | 5 | 0 | 16 | 22 | 100% | 0.22727 | 1 | Completed
ER6371LT | W202 | W202.A4720 | HRA Reactors Shutdown Essential Safety Cases | Prepare Draft Project Definition Document (PDD) | 2021-07-01 | 2021-08-02 | 1 | 0 | 23 | 32 | 100% | 0.03125 | 1 | Completed
ER6371LT | W202 | W202.A4740 | HRA Reactors Shutdown Essential Safety Cases | Initial high level scope of programme | 2021-07-01 | 2021-07-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | W206.A4710 | HYA Reactors Shutdown Essential Safety Cases | Define Project Control Structures (WBS/CBS/OBS/PBS) | 2021-07-01 | 2021-07-23 | 5 | 0 | 16 | 22 | 100% | 0.22727 | 1 | Completed
ER6661LT | W206 | W206.A4720 | HYA Reactors Shutdown Essential Safety Cases | Prepare Draft Project Definition Document (PDD) | 2021-07-01 | 2021-08-02 | 1 | 0 | 23 | 32 | 100% | 0.03125 | 1 | Completed
ER6661LT | W206 | W206.A4740 | HYA Reactors Shutdown Essential Safety Cases | Initial high level scope of programme | 2021-07-01 | 2021-07-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6378LT | W222 | W222.A16330 | HRA Fuel Handling Essential Safety Case | Draft Defuelling Safety Case Head Documents EAN | 2021-07-01 | 2021-08-06 | 15 | 0 | 27 | 36 | 100% | 0.41667 | 1 | Completed
ER6372LT | W203 | W203.A1540 | HNB Enhanced Defuelling Safety Cases | Flow Diversion EAN - Review/Verification | 2021-07-01 | 2021-07-14 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6650LT | W226 | W226.A16330 | HYA Fuel Handling Essential Safety Case | Draft Defuelling Safety Case Head Documents EAN | 2021-07-01 | 2021-08-06 | 15 | 0 | 27 | 36 | 100% | 0.41667 | 1 | Completed
ER6378LT | W222 | W222.A25240 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Hazard and Interlock Schedule (REV 000) EAN | 2021-07-02 | 2021-07-02 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25240 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Hazard and Interlock Schedule (REV 000) EAN | 2021-07-02 | 2021-07-02 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4700 | HYA Reactors Shutdown Essential Safety Cases | Produce verification plan (HYA,) | 2021-07-02 | 2021-08-02 | 2 | 0 | 22 | 31 | 100% | 0.064516 | 1 | Completed
ER6378LT | W222 | W222.A25370 | HRA Fuel Handling Essential Safety Case | Technical Review of Update to Fault Schedule/PSA (REV 000) EAN | 2021-07-02 | 2021-07-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25370 | HYA Fuel Handling Essential Safety Case | Technical Review of Update to Fault Schedule/PSA (REV 000) EAN | 2021-07-02 | 2021-07-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A17090 | HNB Reactors Shutdown Essential Safety Cases | CAT 1 Satety Case Submitted to ONR - (Reactor Shutdown Essential SC) HNB | 2021-07-02 | 2021-07-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25450 | HRA Fuel Handling Essential Safety Case | Technical Review of Defuelling NSPs/SAGs (REV 000) EAN | 2021-07-05 | 2021-07-13 | 8 | 0 | 7 | 8 | 100% | 1 | 1 | Completed
ER6378LT | W222 | W222.A25250 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Hazard and Interlock Schedule (REV 000) EAN to CDMS (INITIAL H&I) | 2021-07-05 | 2021-07-14 | 5 | 0 | 7 | 9 | 100% | 0.55556 | 1 | Completed
ER6650LT | W226 | W226.A25250 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Hazard and Interlock Schedule (REV 000) EAN to CDMS (INITIAL H&I) | 2021-07-05 | 2021-07-14 | 5 | 0 | 8 | 9 | 100% | 0.55556 | 1 | Completed
ER6650LT | W226 | W226.A25450 | HYA Fuel Handling Essential Safety Case | Technical Review of Defuelling NSPs/SAGs (REV 000) EAN | 2021-07-05 | 2021-07-13 | 8 | 0 | 7 | 8 | 100% | 1 | 1 | Completed
ER6650LT | W226 | W226.A25520 | HYA Fuel Handling Essential Safety Case | Technical Review of Assessment of Worker Risk (REV 000) EAN | 2021-07-05 | 2021-07-07 | 5 | 0 | 2 | 2 | 100% | 2.5 | 1 | Completed
ER6378LT | W222 | W222.1050 | HRA Fuel Handling Essential Safety Case | Pre Job Brief Concept Definition of Elec Interlock for Prevention of F/Assembly Misloading in Defueling Reactors EAN | 2021-07-05 | 2021-07-05 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.1060 | HRA Fuel Handling Essential Safety Case | Draft Concept Definition of Elec Interlock for Prevention of F/Assembly Misloading in Defueling Reactors EAN | 2021-07-05 | 2021-07-20 | 1 | 0 | 11 | 15 | 100% | 0.066667 | 1 | Completed
ER6650LT | W226 | W226.1050 | HYA Fuel Handling Essential Safety Case | Pre Job Brief Concept Definition of Elec Interlock for Prevention of F/Assembly Misloading in Defueling Reactors EAN | 2021-07-05 | 2021-07-05 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.1060 | HYA Fuel Handling Essential Safety Case | Draft Concept Definition of Elec Interlock for Prevention of F/Assembly Misloading in Defueling Reactors EAN | 2021-07-05 | 2021-07-20 | 1 | 0 | 11 | 15 | 100% | 0.066667 | 1 | Completed
ER6370LT | W201 | ER6370.A16210 | HNB Reactors Shutdown Essential Safety Cases | ONR Approval of Safety Case EC 364023 <NSRS SC Approach & Outline> (Cat 1 Milestone) (HNB) (FEEDS TO SUMMARY SHEDULE) | 2021-07-05 | 2022-03-21 | 60 | 0 | 181 | 259 | 100% | 0.23166 | 1 | Completed
ER6378LT | W222 | W222.A25520 | HRA Fuel Handling Essential Safety Case | Technical Review of Assessment of Worker Risk (REV 000) EAN | 2021-07-05 | 2021-07-07 | 5 | 0 | 2 | 2 | 100% | 2.5 | 1 | Completed
ER6378LT | W222 | W222.A25380 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Update to Fault Schedule/PSA (REV 000) EAN | 2021-07-05 | 2021-07-05 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24660 | HRA Fuel Handling Essential Safety Case | Verify Human Reliability Assessment of Unsubstantaited Claims & Issue for Technical Review | 2021-07-05 | 2021-07-07 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6370LT | W201 | ER6370.A1400 | HNB Reactors Shutdown Essential Safety Cases | Progress Lessons Learned Review - INSA Final Approval EC 364023 <NSRS SC Approach & Outline> | 2021-07-05 | 2022-04-27 | 20 | 0 | 206 | 296 | 100% | 0.067568 | 1 | Completed
ER6650LT | W226 | W226.A24660 | HYA Fuel Handling Essential Safety Case | Verify Human Reliability Assessment of Unsubstantaited Claims & Issue for Technical Review | 2021-07-05 | 2021-07-07 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6650LT | W226 | W226.A25380 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Update to Fault Schedule/PSA (REV 000) EAN | 2021-07-05 | 2021-07-05 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25390 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Update to Fault Schedule/PSA (REV 000) EAN to CDMS | 2021-07-06 | 2021-07-22 | 3 | 0 | 12 | 16 | 100% | 0.1875 | 1 | Completed
ER6650LT | W226 | W226.A25390 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Update to Fault Schedule/PSA (REV 000) EAN to CDMS | 2021-07-06 | 2021-07-22 | 3 | 0 | 12 | 16 | 100% | 0.1875 | 1 | Completed
ER6378LT | W222 | W222.A24600 | HRA Fuel Handling Essential Safety Case | Technical Review of Human Reliability Baseline Report EAN | 2021-07-07 | 2021-07-15 | 7 | 0 | 7 | 8 | 100% | 0.875 | 1 | Completed
ER6650LT | W226 | W226.A24600 | HYA Fuel Handling Essential Safety Case | Technical Review of Human Reliability Baseline Report EAN | 2021-07-07 | 2021-07-15 | 7 | 0 | 7 | 8 | 100% | 0.875 | 1 | Completed
ER6378LT | W222 | W222.A25530 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Assessment of Worker Risk (REV 000) EAN | 2021-07-08 | 2021-07-14 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6650LT | W226 | W226.A25530 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Assessment of Worker Risk (REV 000) EAN | 2021-07-08 | 2021-07-14 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A4750 | HRA Reactors Shutdown Essential Safety Cases | Plan Scope in Primavera (Level 2 C-D & Level 1 Lifecycle) | 2021-07-08 | 2021-07-21 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6371LT | W202 | W202.A4760 | HRA Reactors Shutdown Essential Safety Cases | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 2021-07-08 | 2021-08-03 | 1 | 0 | 19 | 26 | 100% | 0.038462 | 1 | Completed
ER6371LT | W202 | W202.A4770 | HRA Reactors Shutdown Essential Safety Cases | Workshop to agree scope, effort and links | 2021-07-08 | 2021-07-23 | 10 | 0 | 11 | 15 | 100% | 0.66667 | 1 | Completed
ER6661LT | W206 | W206.A4750 | HYA Reactors Shutdown Essential Safety Cases | Plan Scope in Primavera (Level 2 C-D & Level 1 Lifecycle) | 2021-07-08 | 2021-07-21 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6661LT | W206 | W206.A4760 | HYA Reactors Shutdown Essential Safety Cases | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 2021-07-08 | 2021-08-03 | 1 | 0 | 19 | 26 | 100% | 0.038462 | 1 | Completed
ER6661LT | W206 | W206.A4770 | HYA Reactors Shutdown Essential Safety Cases | Workshop to agree scope, effort and links | 2021-07-08 | 2021-07-23 | 10 | 0 | 11 | 15 | 100% | 0.66667 | 1 | Completed
ER6378LT | W222 | W222.A24830 | HRA Fuel Handling Essential Safety Case | Complete Review of Human Factors Assessment of FM Movements during Defuelling Operations EAN to CDMS | 2021-07-08 | 2021-07-28 | 3 | 0 | 15 | 20 | 100% | 0.15 | 1 | Completed
ER6378LT | W222 | W222.A24670 | HRA Fuel Handling Essential Safety Case | Technical Review of Human Reliability Assessment of Unsubstantaited Claims EAN | 2021-07-08 | 2021-07-09 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6650LT | W226 | W226.A24670 | HYA Fuel Handling Essential Safety Case | Technical Review of Human Reliability Assessment of Unsubstantaited Claims EAN | 2021-07-08 | 2021-07-09 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6650LT | W226 | W226.A24830 | HYA Fuel Handling Essential Safety Case | Complete Review of Human Factors Assessment of FM Movements during Defuelling Operations EAN to CDMS | 2021-07-08 | 2021-07-28 | 3 | 0 | 15 | 20 | 100% | 0.15 | 1 | Completed
ER6378LT | W222 | W222.A26570 | HRA Fuel Handling Essential Safety Case | Verify Human Factors Integration Plan EAN and Issue for Technical Review (REV 001) | 2021-07-09 | 2021-07-22 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6650LT | W226 | W226.A26570 | HYA Fuel Handling Essential Safety Case | Verify Human Factors Integration Plan EAN and Issue for Technical Review (REV 001) | 2021-07-09 | 2021-07-22 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6371LT | W202 | W202.1050 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - Issue Final EAN | 2021-07-09 | 2021-07-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.1050 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - Issue Final EAN | 2021-07-09 | 2021-07-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4780 | HRA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Core Cooling Head Document Draft Report | 2021-07-12 | 2021-08-03 | 5 | 0 | 17 | 22 | 100% | 0.22727 | 1 | Completed
ER6661LT | W206 | W206.A4780 | HYA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Core Cooling Head Document Draft Report | 2021-07-12 | 2021-08-02 | 5 | 0 | 16 | 21 | 100% | 0.2381 | 1 | Completed
ER6378LT | W222 | W222.A24680 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Human Reliability Assessment of Unsubstantaited Claims EAN | 2021-07-12 | 2021-07-12 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24680 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Human Reliability Assessment of Unsubstantaited Claims EAN | 2021-07-12 | 2021-07-12 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.1060 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - EAN Completed and Uploaded to CDMS | 2021-07-12 | 2021-07-23 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6661LT | W206 | W206.1060 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - EAN Completed and Uploaded to CDMS | 2021-07-12 | 2021-07-23 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6371LT | W202 | W202.A18390 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Vibration in the FPU EAN Reviewed by EDF SQEP | 2021-07-12 | 2021-07-16 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6661LT | W206 | W206.A18390 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Vibration in the FPU EAN Reviewed by EDF SQEP | 2021-07-12 | 2021-07-16 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6371LT | W202 | W202.A2206390 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Verify Reactivity Assessment of Misloading Fault EAN | 2021-07-12 | 2021-07-14 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6371LT | W202 | W202.A2206490 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - HF Assessment of Misloading Fault EAN Reviewed by EDF SQEP | 2021-07-12 | 2021-07-19 | 6 | 0 | 6 | 7 | 100% | 0.85714 | 1 | Completed
ER6661LT | W206 | W206.1250 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Verify Reactivity Assessment of Misloading Fault EAN | 2021-07-12 | 2021-07-19 | 6 | 0 | 6 | 7 | 100% | 0.85714 | 1 | Completed
ER6661LT | W206 | W206.1480 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - HF Assessment of Misloading Fault EAN Reviewed by EDF SQEP | 2021-07-12 | 2021-07-15 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6378LT | W222 | W222.A24690 | HRA Fuel Handling Essential Safety Case | Complete Human Reliability Assessment of Unsubstantaited Claims EAN to CDMS | 2021-07-13 | 2021-07-26 | 5 | 0 | 10 | 13 | 100% | 0.38462 | 1 | Completed
ER6650LT | W226 | W226.A24690 | HYA Fuel Handling Essential Safety Case | Complete Human Reliability Assessment of Unsubstantaited Claims EAN to CDMS | 2021-07-13 | 2021-07-26 | 5 | 0 | 10 | 13 | 100% | 0.38462 | 1 | Completed
ER6378LT | W222 | W222.A25260 | HRA Fuel Handling Essential Safety Case | Hazard and Interlock Schedule (REV 000) EAN Available | 2021-07-14 | 2021-07-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25460 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Defuelling NSPs/SAGs (REV 000) EAN | 2021-07-14 | 2021-07-23 | 3 | 0 | 8 | 9 | 100% | 0.33333 | 1 | Completed
ER6650LT | W226 | W226.A25460 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Defuelling NSPs/SAGs (REV 000) EAN | 2021-07-14 | 2021-07-23 | 3 | 0 | 8 | 9 | 100% | 0.33333 | 1 | Completed
ER6650LT | W226 | W226.A25260 | HYA Fuel Handling Essential Safety Case | Hazard and Interlock Schedule (REV 000) EAN Available | 2021-07-14 | 2021-07-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1630 | HNB Enhanced Defuelling Safety Cases | Flow Diversion EAN - Address Comments | 2021-07-15 | 2021-09-10 | 19 | 0 | 41 | 57 | 100% | 0.33333 | 1 | Completed
ER6371LT | W202 | W202.A2206420 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Reactivity Assessment of Misloading Fault EAN Reviewed by EDF SQEP | 2021-07-15 | 2021-07-16 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6650LT | W226 | W226.A25540 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Assessment of Worker Risk (REV 000) EAN to CDMS | 2021-07-16 | 2021-07-19 | 5 | 0 | 1 | 3 | 100% | 1.6667 | 1 | Completed
W520LT | W520 | W520.A1070 | FLEETWIDE CTO Defueling Safety Case Delivery | Estimate Peer Review / Address Comments | 2021-07-16 | 2021-07-16 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W520LT | W520 | W520.A1080 | FLEETWIDE CTO Defueling Safety Case Delivery | Ensure Alignment of Schedule & Estimate (If Required) | 2021-07-16 | 2021-07-16 | 3 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W520LT | W520 | W520.A1090 | FLEETWIDE CTO Defueling Safety Case Delivery | Estimate Scope (If Required) | 2021-07-16 | 2021-07-16 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W520LT | W520 | W520.A1100 | FLEETWIDE CTO Defueling Safety Case Delivery | Plan Scope in Primavera (If Required) | 2021-07-16 | 2021-07-16 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25540 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Assessment of Worker Risk (REV 000) EAN to CDMS | 2021-07-16 | 2021-07-19 | 5 | 0 | 1 | 3 | 100% | 1.6667 | 1 | Completed
ER6378LT | W222 | W222.A24610 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Human Reliability Baseline Report EAN | 2021-07-16 | 2021-07-22 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6650LT | W226 | W226.A24610 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Human Reliability Baseline Report EAN | 2021-07-16 | 2021-07-22 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | W206.1490 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Address Comments from EDF Review on HF Assessment of Misloading Fault EAN | 2021-07-16 | 2021-07-19 | 2 | 0 | 2 | 3 | 100% | 0.66667 | 1 | Completed
ER6378LT | W222 | W222.A25550 | HRA Fuel Handling Essential Safety Case | Assessment of Worker Risk (REV 000) EAN Available | 2021-07-19 | 2021-07-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25550 | HYA Fuel Handling Essential Safety Case | Assessment of Worker Risk (REV 000) EAN Available | 2021-07-19 | 2021-07-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A18400 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Address Comments from EDF Review on Vibration in the FPU EAN | 2021-07-19 | 2021-07-23 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6661LT | W206 | W206.A18400 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Address Comments from EDF Review on Vibration in the FPU EAN | 2021-07-19 | 2021-07-23 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6371LT | W202 | W202.A2206430 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Address Comments from EDF Review on Reactivity Assessment of Misloading Fault EAN | 2021-07-19 | 2021-07-20 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6378LT | W222 | W222.1070 | HRA Fuel Handling Essential Safety Case | Verification of Concept Definition of Elec Interlock for Prevention of F/Assembly Misloading in Defueling Reactors EAN | 2021-07-20 | 2021-07-20 | 6 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.1080 | HRA Fuel Handling Essential Safety Case | Complete/Upload Concept Def of Elec Interlock for Prevention of F/Assembly Misloading in Defueling Reactors EAN to CDMS | 2021-07-20 | 2021-07-20 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.1090 | HRA Fuel Handling Essential Safety Case | Concept Definition of Elec Interlock for Prevention of F/Assembly Misloading in Defueling Reactors EAN Available | 2021-07-20 | 2021-07-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.1100 | HRA Fuel Handling Essential Safety Case | >>>OUTGOING ENABLER (W202) Concept Def of Elec Interlck for Prevntion of F/Assembly Misloading in Defing Rctrs EAN Avail | 2021-07-20 | 2021-07-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.1070 | HYA Fuel Handling Essential Safety Case | Verification of Concept Definition of Elec Interlock for Prevention of F/Assembly Misloading in Defueling Reactors EAN | 2021-07-20 | 2021-07-20 | 6 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.1080 | HYA Fuel Handling Essential Safety Case | Complete/Upload Concept Def of Elec Interlock for Prevention of F/Assembly Misloading in Defueling Reactors EAN to CDMS | 2021-07-20 | 2021-07-20 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.1090 | HYA Fuel Handling Essential Safety Case | Concept Definition of Elec Interlock for Prevention of F/Assembly Misloading in Defueling Reactors EAN Available | 2021-07-20 | 2021-07-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.1100 | HYA Fuel Handling Essential Safety Case | >>>OUTGOING ENABLER (W206) Concept Def of Elec Interlck for Prevntion of F/Assembly Misloading in Defing Rctrs EAN Avail | 2021-07-20 | 2021-07-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.1300 | HRA Reactors Shutdown Essential Safety Cases | >>>INCOMING ENABLER (W222) Concept Def of Elec Interlck for Prevntion of F/Assembly Misloading in Defing Rctrs EAN Avail | 2021-07-20 | 2021-07-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.1310 | HRA Reactors Shutdown Essential Safety Cases | >>>MIRROR of INCOMING ENABLER (W222) Concept Def of Elec Interlck for Prevntion of F/Assembly Misloading in Defing Rctrs | 2021-07-20 | 2021-07-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.1320 | HRA Reactors Shutdown Essential Safety Cases | >>>INTERFACE MS (W222) Concept Def of Elec Interlck for Prevntion of F/Assembly Misloading in Defing Rctrs EAN Avail | 2021-07-20 | 2021-07-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.13105 | HYA Reactors Shutdown Essential Safety Cases | >>>MIRROR of INCOMING ENABLER (W226) Concept Def of Elec Interlck for Prevntion of F/Assembly Misloading in Defing Rctrs | 2021-07-20 | 2021-07-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.13115 | HYA Reactors Shutdown Essential Safety Cases | >>>INTERFACE MS (W226) Concept Def of Elec Interlck for Prevntion of F/Assembly Misloading in Defing Rctrs EAN Avail | 2021-07-20 | 2021-07-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206500 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Address Comments from EDF Review on HF Assessment of Misloading Fault EAN | 2021-07-20 | 2021-07-26 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | W206.1340 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Reactivity Assessment of Misloading Fault EAN Reviewed by EDF SQEP | 2021-07-20 | 2021-07-21 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6661LT | W206 | W206.1400 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - HF Assessment of Misloading Fault EAN Completed and Uploaded to CDMS | 2021-07-20 | 2021-07-21 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6661LT | W206 | W206.13005 | HYA Reactors Shutdown Essential Safety Cases | >>>INCOMING ENABLER (W226) Concept Def of Elec Interlck for Prevntion of F/Assembly Misloading in Defing Rctrs EAN Avail | 2021-07-20 | 2021-07-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206400 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Reactivity Assessment of Misloading Fault EAN Completed and Uploaded to CDMS | 2021-07-21 | 2021-07-22 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6661LT | W206 | W206.1410 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - HF Assessment of Misloading Fault EAN Complete | 2021-07-21 | 2021-07-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A18510 | HRA Fuel Handling Essential Safety Case | Claim 6 - P6.2 HRA/HYA Essential Defuelling SC - NSPs and ALARP Complete | 2021-07-22 | 2021-07-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A18510 | HYA Fuel Handling Essential Safety Case | Claim 6 - P6.2 HYA/HYA Essential Defuelling SC - NSPs and ALARP Complete | 2021-07-22 | 2021-07-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25400 | HYA Fuel Handling Essential Safety Case | Update to Fault Schedule/PSA (REV 000) EAN Available | 2021-07-22 | 2021-07-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.1350 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Address Comments from EDF Review on Reactivity Assessment of Misloading Fault EAN | 2021-07-22 | 2021-07-26 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6378LT | W222 | W222.A25400 | HRA Fuel Handling Essential Safety Case | Update to Fault Schedule/PSA (REV 000) EAN Available | 2021-07-22 | 2021-07-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206410 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Reactivity Assessment of Misloading Fault EAN Complete | 2021-07-22 | 2021-07-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A26590 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Human Factors Integration Plan EAN to CDMS (REV 001) | 2021-07-23 | 2021-07-29 | 21 | 0 | 4 | 6 | 100% | 3.5 | 1 | Completed
ER6378LT | W222 | W222.A24620 | HRA Fuel Handling Essential Safety Case | Complete Review of Human Reliability Baseline Report EAN to CDMS | 2021-07-23 | 2021-07-29 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6650LT | W226 | W226.A24620 | HYA Fuel Handling Essential Safety Case | Complete Review of Human Reliability Baseline Report EAN to CDMS | 2021-07-23 | 2021-07-29 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6650LT | W226 | W226.A26590 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Human Factors Integration Plan EAN to CDMS (REV 001) | 2021-07-23 | 2021-07-29 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.1070 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - EAN Completed | 2021-07-23 | 2021-07-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.1070 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - EAN Completed | 2021-07-23 | 2021-07-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A3810 | HRA Reactors Shutdown Essential Safety Cases | Shutdown Margin Head Document - Update due to initial RAWG Commmnets | 2021-07-26 | 2021-08-20 | 1 | 0 | 20 | 25 | 100% | 0.04 | 1 | Completed
ER6661LT | W206 | W206.A3810 | HYA Reactors Shutdown Essential Safety Cases | Shutdown Margin Head Document - Update due to initial RAWG Commmnets | 2021-07-26 | 2021-08-20 | 1 | 0 | 20 | 25 | 100% | 0.04 | 1 | Completed
ER6378LT | W222 | W222.A25470 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Defuelling NSPs/SAGs (REV 000) EAN to CDMS | 2021-07-26 | 2021-07-27 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6650LT | W226 | W226.A25470 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Defuelling NSPs/SAGs (REV 000) EAN to CDMS | 2021-07-26 | 2021-07-27 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6371LT | W202 | W202.A18370 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Vibration in the FPU EAN Completed and Uploaded to CDMS | 2021-07-26 | 2021-07-30 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6661LT | W206 | W206.A18370 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Vibration in the FPU Report Completed and Uploaded to CDMS | 2021-07-26 | 2021-07-30 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6378LT | W222 | W222.A24700 | HRA Fuel Handling Essential Safety Case | Human Reliability Assessment of Unsubstantaited Claims EAN Available | 2021-07-26 | 2021-07-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24700 | HYA Fuel Handling Essential Safety Case | Human Reliability Assessment of Unsubstantaited Claims EAN Available | 2021-07-26 | 2021-07-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206470 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - HF Assessment of Misloading Fault EAN Completed and Uploaded to CDMS | 2021-07-27 | 2021-07-30 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6661LT | W206 | W206.1260 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Reactivity Assessment of Misloading Fault EAN Completed and Uploaded to CDMS | 2021-07-27 | 2021-07-30 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6378LT | W222 | W222.A25480 | HRA Fuel Handling Essential Safety Case | Defuelling NSPs/SAGs (REV 000) EAN Available | 2021-07-27 | 2021-07-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A25480 | HYA Fuel Handling Essential Safety Case | Defuelling NSPs/SAGs (REV 000) EAN Available | 2021-07-27 | 2021-07-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24840 | HRA Fuel Handling Essential Safety Case | Human Factors Assessment of FM Movements during Defuelling Operations EAN Available | 2021-07-28 | 2021-07-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24840 | HYA Fuel Handling Essential Safety Case | Human Factors Assessment of FM Movements during Defuelling Operations EAN Available | 2021-07-28 | 2021-07-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A4690 | HRA Fuel Handling Essential Safety Case | Produce verification plan | 2021-07-29 | 2021-08-18 | 2 | 0 | 14 | 20 | 100% | 0.1 | 1 | Completed
ER6378LT | W222 | W222.A4780 | HRA Fuel Handling Essential Safety Case | Prepare and Populate Affected Documents List | 2021-07-29 | 2023-09-15 | 10 | 0 | 538 | 778 | 100% | 0.012853 | 1 | Completed
ER6378LT | W222 | W222.A5080 | HRA Fuel Handling Essential Safety Case | All key supporting references complete | 2021-07-29 | 2021-07-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A17740 | HRA Fuel Handling Essential Safety Case | HAR Fuel Handling Essential Safety Case - Technical References Issued | 2021-07-29 | 2021-07-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A17760 | HRA Fuel Handling Essential Safety Case | Claim 2 - P6.2 HRA/HYA Essential Defuelling SC - Sufficient Protection is in Place Complete | 2021-07-29 | 2021-07-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A18740 | HRA Fuel Handling Essential Safety Case | Claim 2 - P6.2 HRA/HYA Essential Defuelling SC - Sufficient Protection is in Place | 2021-07-29 | 2021-07-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A18780 | HRA Fuel Handling Essential Safety Case | Claim 6 - P6.2 HRA/HYA Essential Defuelling SC - NSPs and ALARP | 2021-07-29 | 2021-07-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A18940 | HYA Fuel Handling Essential Safety Case | Prepare the Safety Case Proposal ##(Cost Summary)## | 2021-07-29 | 2021-12-10 | 60 | 0 | 96 | 134 | 100% | 0.44776 | 1 | Completed
ER6650LT | W226 | W226.A18780 | HYA Fuel Handling Essential Safety Case | Claim 6 - P6.2 HYA/HYA Essential Defuelling SC - NSPs and ALARP | 2021-07-29 | 2021-07-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A18740 | HYA Fuel Handling Essential Safety Case | Claim 2 - P6.2 HYA/HYA Essential Defuelling SC - Sufficient Protection is in Place | 2021-07-29 | 2021-07-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A17760 | HYA Fuel Handling Essential Safety Case | Claim 2 - P6.2 HYA/HYA Essential Defuelling SC - Sufficient Protection is in Place Complete | 2021-07-29 | 2021-07-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A17740 | HYA Fuel Handling Essential Safety Case | HYA Fuel Handling Essential Safety Case - Technical References Issued | 2021-07-29 | 2021-07-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A5080 | HYA Fuel Handling Essential Safety Case | All key supporting references complete | 2021-07-29 | 2021-07-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A4780 | HYA Fuel Handling Essential Safety Case | Prepare and Populate Affected Documents List | 2021-07-29 | 2023-09-15 | 10 | 0 | 537 | 778 | 100% | 0.012853 | 1 | Completed
ER6650LT | W226 | W226.A4690 | HYA Fuel Handling Essential Safety Case | Produce verification plan | 2021-07-29 | 2021-08-18 | 2 | 0 | 14 | 20 | 100% | 0.1 | 1 | Completed
ER6378LT | W222 | W222.A18940 | HRA Fuel Handling Essential Safety Case | Prepare the Safety Case Proposal ##(Cost Summary)## | 2021-07-29 | 2021-12-10 | 60 | 0 | 96 | 134 | 100% | 0.44776 | 1 | Completed
ER6378LT | W222 | W222.A26600 | HRA Fuel Handling Essential Safety Case | Human Factors Integration Plan EAN Available (REV 001) | 2021-07-29 | 2021-07-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24630 | HRA Fuel Handling Essential Safety Case | Human Reliability Baseline Report EAN Available | 2021-07-29 | 2021-07-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A24630 | HYA Fuel Handling Essential Safety Case | Human Reliability Baseline Report EAN Available | 2021-07-29 | 2021-07-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26600 | HYA Fuel Handling Essential Safety Case | Human Factors Integration Plan EAN Available (REV 001) | 2021-07-29 | 2021-07-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4650 | HRA Reactors Shutdown Essential Safety Cases | All supporting references Approved and Issued (HRA) | 2021-07-30 | 2021-07-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4640 | HRA Reactors Shutdown Essential Safety Cases | Supporting Technical References Completed for Hartlepool Essential Safety Case | 2021-07-30 | 2021-07-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4630 | HRA Reactors Shutdown Essential Safety Cases | HAR Shutdown Reactor Essential Safety Case - Technical References Issued | 2021-07-30 | 2021-07-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4650 | HYA Reactors Shutdown Essential Safety Cases | All supporting references Approved and Issued (HYA) | 2021-07-30 | 2021-07-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4640 | HYA Reactors Shutdown Essential Safety Cases | HYA Shutdown Reactor Essential Safety Case - Technical References Issued | 2021-07-30 | 2021-07-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4270 | HYA Reactors Shutdown Essential Safety Cases | All Supporting Technical References Complete - Claim 2 Containment | 2021-07-30 | 2021-07-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4630 | HYA Reactors Shutdown Essential Safety Cases | Essential Reactor Safety Case - Supporting Technical References Complete (HYA) | 2021-07-30 | 2021-07-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4270 | HRA Reactors Shutdown Essential Safety Cases | All Supporting Technical References Complete - Claim 2 Containment | 2021-07-30 | 2021-07-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A18380 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Vibration in the FPU EAN Complete | 2021-07-30 | 2021-07-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A18380 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Vibration in the FPU Report Complete | 2021-07-30 | 2021-07-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206480 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - HF Assessment of Misloading Fault EAN Complete | 2021-07-30 | 2021-07-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.1270 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> - Reactivity Assessment of Misloading Fault EAN Complete | 2021-07-30 | 2021-07-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W520LT | W520 | W520.A1000 | FLEETWIDE CTO Defueling Safety Case Delivery | 2021 Costs | 2021-08-01 | 2021-12-31 | 57 | 0 | 106 | 152 | 100% | 0.375 | 1 | Completed
ER6370LT | W201 | ER6370.A17560 | HNB Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (HNB Security Plan) Review SPPI File Against Issued Safety Cases (NOT REQUIRED) | 2021-08-02 | 2021-08-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.1230 | HRA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> Optioneering - Write-up Preferred Option | 2021-08-02 | 2021-08-20 | 15 | 0 | 14 | 18 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A4370 | HRA Reactors Shutdown Essential Safety Cases | Verified Containment Head Document Draft Report Issued to EDF for Technical Review. | 2021-08-02 | 2021-08-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4380 | HRA Reactors Shutdown Essential Safety Cases | Containment Head Document Draft Report Technically Reviewed by EDF SQEP | 2021-08-02 | 2021-08-06 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6661LT | W206 | W206.A4790 | HYA Reactors Shutdown Essential Safety Cases | Ensure Alignment of Schedule & Estimate | 2021-08-02 | 2021-08-03 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6661LT | W206 | W206.A4370 | HYA Reactors Shutdown Essential Safety Cases | Verified Containment Head Document Draft Report Issued to EDF for Technical Review. | 2021-08-02 | 2021-08-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4380 | HYA Reactors Shutdown Essential Safety Cases | Containment Head Document Draft Report Technically Reviewed by EDF SQEP | 2021-08-02 | 2021-08-06 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6661LT | W206 | W206.1360 | HYA Reactors Shutdown Essential Safety Cases | <NEW SCOPE PENDING CC> Optioneering - Write-up Preferred Option | 2021-08-02 | 2021-08-20 | 15 | 0 | 14 | 18 | 100% | 0.83333 | 1 | Completed
W520LT | W520 | W520.A1110 | FLEETWIDE CTO Defueling Safety Case Delivery | Plan Peer Review & SMART Check / Address Comments | 2021-08-02 | 2021-08-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W520LT | W520 | W520.A1120 | FLEETWIDE CTO Defueling Safety Case Delivery | Revise Project Definition Document (PDD) (If Required) | 2021-08-02 | 2021-08-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W520LT | W520 | W520.A1130 | FLEETWIDE CTO Defueling Safety Case Delivery | Complete Risk Log with Estimates (If Required) | 2021-08-02 | 2021-08-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4810 | HYA Reactors Shutdown Essential Safety Cases | TSA Issue Final Core Cooling Head Document Report | 2021-08-02 | 2021-08-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4790 | HRA Reactors Shutdown Essential Safety Cases | Ensure Alignment of Schedule & Estimate | 2021-08-03 | 2021-08-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4830 | HYA Reactors Shutdown Essential Safety Cases | Core Cooling Head Document Report TR Completed and uploaded to CDMS | 2021-08-03 | 2021-08-09 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
W520LT | W520 | W520.A1140 | FLEETWIDE CTO Defueling Safety Case Delivery | Update Schedule/Estimate from Risk Log & Add Provisions (If Required) | 2021-08-03 | 2021-08-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4810 | HRA Reactors Shutdown Essential Safety Cases | TSA Issue Final Core Cooling Head Document Report | 2021-08-03 | 2021-08-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4800 | HRA Reactors Shutdown Essential Safety Cases | Hold Risk Workshop | 2021-08-04 | 2021-08-04 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4830 | HRA Reactors Shutdown Essential Safety Cases | Core Cooling Head Document Report TR Completed and uploaded to CDMS | 2021-08-04 | 2021-08-10 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | W206.A4800 | HYA Reactors Shutdown Essential Safety Cases | Hold Risk Workshop | 2021-08-04 | 2021-08-04 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W520LT | W520 | W520.A1150 | FLEETWIDE CTO Defueling Safety Case Delivery | Update NSSB Paper | 2021-08-04 | 2021-08-05 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6371LT | W202 | W202.A4820 | HRA Reactors Shutdown Essential Safety Cases | Complete Risk Log with Estimates | 2021-08-05 | 2021-08-05 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4820 | HYA Reactors Shutdown Essential Safety Cases | Complete Risk Log with Estimates | 2021-08-05 | 2021-08-05 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4840 | HRA Reactors Shutdown Essential Safety Cases | Update Schedule/Estimate from Risk Log & Add Provisions | 2021-08-06 | 2021-08-06 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4840 | HYA Reactors Shutdown Essential Safety Cases | Update Schedule/Estimate from Risk Log & Add Provisions | 2021-08-06 | 2021-08-06 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W520LT | W520 | W520.A1160 | FLEETWIDE CTO Defueling Safety Case Delivery | PCL Validate & Approve Baseline Package for NSSB Submission | 2021-08-06 | 2021-09-13 | 2 | 0 | 26 | 38 | 100% | 0.052632 | 1 | Completed
ER6378LT | W222 | W222.A16320 | HRA Fuel Handling Essential Safety Case | Defuelling Safety Case Head Documents EAN Drafted and Issued for Verification | 2021-08-06 | 2021-08-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A16320 | HYA Fuel Handling Essential Safety Case | Defuelling Safety Case Head Documents EAN Drafted and Issued for Verification | 2021-08-06 | 2021-08-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4850 | HRA Reactors Shutdown Essential Safety Cases | Add Data to IAB Paper | 2021-08-09 | 2021-08-09 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4420 | HRA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Containment Head Document Draft Report | 2021-08-09 | 2021-08-17 | 7 | 0 | 7 | 8 | 100% | 0.875 | 1 | Completed
ER6661LT | W206 | W206.A4850 | HYA Reactors Shutdown Essential Safety Cases | Add Data to PRC Paper | 2021-08-09 | 2021-08-09 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4420 | HYA Reactors Shutdown Essential Safety Cases | TSA Address Comments on TR'd Containment Head Document Draft Report | 2021-08-09 | 2021-08-17 | 7 | 0 | 7 | 8 | 100% | 0.875 | 1 | Completed
ER6378LT | W222 | W222.A16340 | HRA Fuel Handling Essential Safety Case | Verification of Defuelling Safety Case Head Documents EAN | 2021-08-09 | 2021-11-26 | 38 | 0 | 79 | 109 | 100% | 0.34862 | 1 | Completed
ER6650LT | W226 | W226.A16340 | HYA Fuel Handling Essential Safety Case | Verification of Defuelling Safety Case Head Documents EAN | 2021-08-09 | 2021-11-26 | 38 | 0 | 79 | 109 | 100% | 0.34862 | 1 | Completed
ER6661LT | W206 | W206.A4880 | HYA Reactors Shutdown Essential Safety Cases | Core Cooling Head Document Report Completed | 2021-08-09 | 2021-08-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4860 | HRA Reactors Shutdown Essential Safety Cases | PCL Validate & Approve Baseline Package for PRC Submission | 2021-08-10 | 2021-08-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4860 | HYA Reactors Shutdown Essential Safety Cases | PCL Validate & Approve Baseline Package for PRC Submission | 2021-08-10 | 2021-08-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4880 | HRA Reactors Shutdown Essential Safety Cases | Core Cooling Head Document Report Completed | 2021-08-10 | 2021-08-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4900 | HRA Reactors Shutdown Essential Safety Cases | PRC Members Review PRC Documentation | 2021-08-11 | 2021-08-16 | 4 | 0 | 3 | 5 | 100% | 0.8 | 1 | Completed
ER6371LT | W202 | W202.A4890 | HRA Reactors Shutdown Essential Safety Cases | Gate C PRC Paper Submission | 2021-08-11 | 2021-08-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4890 | HYA Reactors Shutdown Essential Safety Cases | Gate C PRC Paper Submission | 2021-08-11 | 2021-08-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4900 | HYA Reactors Shutdown Essential Safety Cases | PRC Members Review PRC Documentation | 2021-08-11 | 2021-08-16 | 4 | 0 | 4 | 5 | 100% | 0.8 | 1 | Completed
ER6370LT | W201 | 970 | HNB Reactors Shutdown Essential Safety Cases | Review 6 impact areas with FH Case CO | 2021-08-16 | 2021-08-16 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | 960 | HNB Reactors Shutdown Essential Safety Cases | Review Cat 1 proposal, head doc and tech refs to identify changes (if any) | 2021-08-16 | 2021-08-16 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4490 | HRA Reactors Shutdown Essential Safety Cases | TSA Issue Final Containment Head Document Report | 2021-08-17 | 2021-08-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4490 | HYA Reactors Shutdown Essential Safety Cases | TSA Issue Final Containment Head Document Report | 2021-08-17 | 2021-08-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4500 | HRA Reactors Shutdown Essential Safety Cases | Containment Head Document Report TR Completed and uploaded to CDMS | 2021-08-18 | 2021-08-24 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | W206.A4500 | HYA Reactors Shutdown Essential Safety Cases | Containment Head Document Report TR Completed and uploaded to CDMS | 2021-08-18 | 2021-08-24 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A3690 | HRA Reactors Shutdown Essential Safety Cases | Shutdown Margin Head Document Completed | 2021-08-20 | 2021-08-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A3690 | HYA Reactors Shutdown Essential Safety Cases | Shutdown Margin Head Document Completed | 2021-08-20 | 2021-08-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A5050 | HRA Reactors Shutdown Essential Safety Cases | Obtain peer review (if required) (HRA) | 2021-08-23 | 2021-08-27 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6661LT | W206 | W206.A5050 | HYA Reactors Shutdown Essential Safety Cases | Obtain peer review (if required) (HYA) | 2021-08-23 | 2021-08-27 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | 1040 | HNB Reactors Shutdown Essential Safety Cases | Draft updates to Cat 1 Proposal (a Dropped FPU section, b ALARP section, c Fuel Handling discussions, d Interaction | 2021-08-23 | 2021-09-02 | 8 | 0 | 8 | 10 | 100% | 0.8 | 1 | Completed
ER6370LT | W201 | 1030 | HNB Reactors Shutdown Essential Safety Cases | Complete review of FNC Report | 2021-08-23 | 2021-08-24 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | 1020 | HNB Reactors Shutdown Essential Safety Cases | Review with INA | 2021-08-23 | 2021-08-24 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | 1010 | HNB Reactors Shutdown Essential Safety Cases | Review with Stn RE's | 2021-08-23 | 2021-08-24 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | 1000 | HNB Reactors Shutdown Essential Safety Cases | Review with CO | 2021-08-23 | 2021-08-24 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | 990 | HNB Reactors Shutdown Essential Safety Cases | NSC Strategy (matter arising tbc) | 2021-08-23 | 2021-09-09 | 13 | 0 | 12 | 17 | 100% | 0.76471 | 1 | Completed
ER6370LT | W201 | 980 | HNB Reactors Shutdown Essential Safety Cases | Finalise and constrain scope of changes to Reactor Case | 2021-08-23 | 2021-08-23 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4910 | HRA Reactors Shutdown Essential Safety Cases | Hold PRC Meeting | 2021-08-24 | 2021-08-24 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4920 | HRA Reactors Shutdown Essential Safety Cases | Gate C PRC Paper Approval | 2021-08-24 | 2021-08-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1090 | HRA Reactors Shutdown Essential Safety Cases | Phase 2 Project Management - Gate C - D | 2021-08-24 | 2025-02-21 | 253 | 0 | 883 | 1277 | 100% | 0.19812 | 1 | Completed
ER6371LT | W202 | W202.A1010 | HRA Reactors Shutdown Essential Safety Cases | SC - Safety Case development - tech oversight Cat 1 - HRA - C-D - STN | 2021-08-24 | 2024-10-02 | 290 | 0 | 785 | 1135 | 100% | 0.25551 | 1 | Completed
ER6371LT | W202 | W202.A5030 | HRA Reactors Shutdown Essential Safety Cases | Gate C PRC Paper Approval - Region 1 Essential Safety Case (HRA) | 2021-08-24 | 2021-08-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A1100 | HRA Reactors Shutdown Essential Safety Cases | Safety Case Dev Cat 1 - Station Oversight of tech work & SC - HRA - C-D - T&S NS | 2021-08-24 | 2025-02-21 | 254 | 0 | 883 | 1277 | 100% | 0.1989 | 1 | Completed
ER6371LT | W202 | W202.A5080 | HRA Reactors Shutdown Essential Safety Cases | Gate EC3 Completed 363682 (HRA) | 2021-08-24 | 2021-08-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4870 | HRA Reactors Shutdown Essential Safety Cases | Completion of Head Documents (Reactor Shutdown Essential SC) | 2021-08-24 | 2021-08-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A1090 | HYA Reactors Shutdown Essential Safety Cases | Phase 2 Project Management - Gate C - D | 2021-08-24 | 2025-02-21 | 257 | 0 | 883 | 1277 | 100% | 0.20125 | 1 | Completed
ER6661LT | W206 | W206.A1010 | HYA Reactors Shutdown Essential Safety Cases | SC - Safety Case development - tech oversight Cat 1 - HYA - C-D - STN | 2021-08-24 | 2024-10-10 | 291 | 0 | 790 | 1143 | 100% | 0.25459 | 1 | Completed
ER6661LT | W206 | W206.A1100 | HYA Reactors Shutdown Essential Safety Cases | Safety Case Dev Cat 1 - Station Oversight of tech work & SC - HYA - C-D - T&S NS | 2021-08-24 | 2025-02-21 | 258 | 0 | 883 | 1277 | 100% | 0.20204 | 1 | Completed
ER6661LT | W206 | W206.A5080 | HYA Reactors Shutdown Essential Safety Cases | Gate EC3 Completed 363676 (HYA) | 2021-08-24 | 2021-08-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4910 | HYA Reactors Shutdown Essential Safety Cases | Hold PRC Meeting | 2021-08-24 | 2021-08-24 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A4530 | HRA Reactors Shutdown Essential Safety Cases | Containment Head Document Report Completed | 2021-08-24 | 2021-08-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4920 | HYA Reactors Shutdown Essential Safety Cases | Gate C PRC Paper Approval | 2021-08-24 | 2021-08-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4530 | HYA Reactors Shutdown Essential Safety Cases | Containment Head Document Report Completed | 2021-08-24 | 2021-08-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5030 | HYA Reactors Shutdown Essential Safety Cases | Gate C PRC Paper Approval - Region 1 Essential Safety Case (HYA) | 2021-08-24 | 2021-08-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A5140 | HRA Reactors Shutdown Essential Safety Cases | Verification Commenced (T-11) (HRA) | 2021-08-25 | 2021-08-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5140 | HYA Reactors Shutdown Essential Safety Cases | Verification Commenced (T-11) (HYA) | 2021-08-25 | 2021-08-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A4870 | HYA Reactors Shutdown Essential Safety Cases | Completion of Head Documents (Reactor Shutdown Essential SC) | 2021-08-27 | 2021-08-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A5110 | HRA Reactors Shutdown Essential Safety Cases | First Round of Verification - Verifier Name | 2021-09-01 | 2021-09-15 | 11 | 0 | 11 | 14 | 100% | 0.78571 | 1 | Completed
ER6371LT | W202 | W202.A5130 | HRA Reactors Shutdown Essential Safety Cases | Specialist Assessments if Necessary (Expand as Required) (HRA) | 2021-09-01 | 2021-11-04 | 15 | 0 | 47 | 64 | 100% | 0.23438 | 1 | Completed
ER6371LT | W202 | W202.A5120 | HRA Reactors Shutdown Essential Safety Cases | SC - Safety Case development - Cat 1 Case verification & SA - HRA - C-D | 2021-09-01 | 2021-11-26 | 63 | 0 | 63 | 86 | 100% | 0.73256 | 1 | Completed
ER6371LT | W202 | W202.A5070 | HRA Reactors Shutdown Essential Safety Cases | Safety Case Proposal Authoring Complete EC 363682 <Reactor Shutdown Essential SC>(Cat 1 KDM) (HRA) | 2021-09-01 | 2021-09-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A5090 | HRA Reactors Shutdown Essential Safety Cases | Safety Case Proposal Authoring Complete EC 363682 <Reactor Shutdown Essential SC> (Cat 1 KDM) (HRA) | 2021-09-01 | 2021-09-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5110 | HYA Reactors Shutdown Essential Safety Cases | First Round of Verification - Verifier Name | 2021-09-01 | 2021-09-15 | 11 | 0 | 11 | 14 | 100% | 0.78571 | 1 | Completed
ER6661LT | W206 | W206.A5130 | HYA Reactors Shutdown Essential Safety Cases | Specialist Assessments if Necessary (Expand as Required) (HYA) | 2021-09-01 | 2021-11-04 | 15 | 0 | 47 | 64 | 100% | 0.23438 | 1 | Completed
ER6661LT | W206 | W206.A5120 | HYA Reactors Shutdown Essential Safety Cases | SC - Safety Case development - Cat 1 Case verification & SA - HYA - C-D | 2021-09-01 | 2021-11-26 | 58 | 0 | 63 | 86 | 100% | 0.67442 | 1 | Completed
ER6661LT | W206 | W206.A5070 | HYA Reactors Shutdown Essential Safety Cases | Safety Case Proposal Authoring Complete EC 363676 <Reactor Shutdown Essential SC>(Cat 1 KDM) (HYA) | 2021-09-01 | 2021-09-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5090 | HYA Reactors Shutdown Essential Safety Cases | Safety Case Proposal Authoring Complete EC 363676 <Reactor Shutdown Essential SC> (Cat 1 KDM) (HYA) | 2021-09-01 | 2021-09-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A14270 | HRA Fuel Handling Essential Safety Case | Revise Project Definition Document (PDD) | 2021-09-01 | 2021-09-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6378LT | W222 | W222.A14260 | HRA Fuel Handling Essential Safety Case | Estimate Scope +/- 10% Lifecycle | 2021-09-01 | 2021-09-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6378LT | W222 | W222.A14250 | HRA Fuel Handling Essential Safety Case | Plan Scope in Primavera Level 2 Lifecycle) | 2021-09-01 | 2021-09-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A14250 | HYA Fuel Handling Essential Safety Case | Plan Scope in Primavera Level 2 Lifecycle) | 2021-09-01 | 2021-09-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A14260 | HYA Fuel Handling Essential Safety Case | Estimate Scope +/- 10% Lifecycle | 2021-09-01 | 2021-09-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6650LT | W226 | W226.A14270 | HYA Fuel Handling Essential Safety Case | Revise Project Definition Document (PDD) | 2021-09-01 | 2021-09-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A5150 | HRA Reactors Shutdown Essential Safety Cases | Nuclear Safety | 2021-09-01 | 2021-09-21 | 15 | 0 | 15 | 20 | 100% | 0.75 | 1 | Completed
ER6371LT | W202 | W202.A5590 | HRA Reactors Shutdown Essential Safety Cases | Environment/Rad Protection | 2021-09-01 | 2021-11-04 | 15 | 0 | 47 | 64 | 100% | 0.23438 | 1 | Completed
ER6371LT | W202 | W202.A5600 | HRA Reactors Shutdown Essential Safety Cases | Ops & PSSR | 2021-09-01 | 2021-11-04 | 15 | 0 | 47 | 64 | 100% | 0.23438 | 1 | Completed
ER6371LT | W202 | W202.A5610 | HRA Reactors Shutdown Essential Safety Cases | Civils | 2021-09-01 | 2021-09-21 | 15 | 0 | 15 | 20 | 100% | 0.75 | 1 | Completed
ER6371LT | W202 | W202.A5620 | HRA Reactors Shutdown Essential Safety Cases | Emergency Arrangements | 2021-09-01 | 2021-10-11 | 15 | 0 | 29 | 40 | 100% | 0.375 | 1 | Completed
ER6371LT | W202 | W202.A5630 | HRA Reactors Shutdown Essential Safety Cases | Nuclear Liabilities | 2021-09-01 | 2021-09-21 | 15 | 0 | 15 | 20 | 100% | 0.75 | 1 | Completed
ER6371LT | W202 | W202.A5640 | HRA Reactors Shutdown Essential Safety Cases | Decommissioning | 2021-09-01 | 2021-09-21 | 15 | 0 | 15 | 20 | 100% | 0.75 | 1 | Completed
ER6371LT | W202 | W202.A5135 | HRA Reactors Shutdown Essential Safety Cases | Confirm Specialist Assessments Required | 2021-09-01 | 2021-09-03 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6661LT | W206 | W206.A5155 | HYA Reactors Shutdown Essential Safety Cases | Nuclear Safety | 2021-09-01 | 2021-09-21 | 15 | 0 | 15 | 20 | 100% | 0.75 | 1 | Completed
ER6661LT | W206 | W206.A5590 | HYA Reactors Shutdown Essential Safety Cases | Environment/Rad Protection | 2021-09-01 | 2021-11-04 | 15 | 0 | 47 | 64 | 100% | 0.23438 | 1 | Completed
ER6661LT | W206 | W206.A5600 | HYA Reactors Shutdown Essential Safety Cases | Ops & PSSR | 2021-09-01 | 2021-11-04 | 15 | 0 | 47 | 64 | 100% | 0.23438 | 1 | Completed
ER6661LT | W206 | W206.A5610 | HYA Reactors Shutdown Essential Safety Cases | Civils | 2021-09-01 | 2021-09-21 | 15 | 0 | 15 | 20 | 100% | 0.75 | 1 | Completed
ER6661LT | W206 | W206.A5620 | HYA Reactors Shutdown Essential Safety Cases | Emergency Arrangements | 2021-09-01 | 2021-10-11 | 15 | 0 | 29 | 40 | 100% | 0.375 | 1 | Completed
ER6661LT | W206 | W206.A5630 | HYA Reactors Shutdown Essential Safety Cases | Nuclear Liabilities | 2021-09-01 | 2021-09-21 | 15 | 0 | 15 | 20 | 100% | 0.75 | 1 | Completed
ER6661LT | W206 | W206.A5640 | HYA Reactors Shutdown Essential Safety Cases | Decommissioning | 2021-09-01 | 2021-09-21 | 15 | 0 | 15 | 20 | 100% | 0.75 | 1 | Completed
ER6661LT | W206 | W206.A5135 | HYA Reactors Shutdown Essential Safety Cases | Confirm Specialist Assessments Required | 2021-09-01 | 2021-09-03 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6370LT | W201 | 1050 | HNB Reactors Shutdown Essential Safety Cases | Early review updated Proposal by Tech Lead | 2021-09-01 | 2021-09-02 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6378LT | W222 | W222.A26700 | HRA Fuel Handling Essential Safety Case | Verify Review of Interlock Maintenance Review EAN & Issue for Technical Review (REV 000) | 2021-09-02 | 2021-09-08 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6650LT | W226 | W226.A26700 | HYA Fuel Handling Essential Safety Case | Verify Review of Interlock Maintenance Review EAN & Issue for Technical Review (REV 000) | 2021-09-02 | 2021-09-08 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6370LT | W201 | 1080 | HNB Reactors Shutdown Essential Safety Cases | Review updated Proposal by Station RE's | 2021-09-02 | 2021-09-03 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | 1120 | HNB Reactors Shutdown Essential Safety Cases | HPB LSD 2.14d Updates | 2021-09-06 | 2021-09-29 | 9 | 0 | 17 | 23 | 100% | 0.3913 | 1 | Completed
ER6370LT | W201 | 1110 | HNB Reactors Shutdown Essential Safety Cases | Agree with NSG to update LSDs in parallel with Verification | 2021-09-06 | 2021-09-07 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6370LT | W201 | 1090 | HNB Reactors Shutdown Essential Safety Cases | Incorporate review comments | 2021-09-06 | 2021-09-10 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | 1070 | HNB Reactors Shutdown Essential Safety Cases | Review | 2021-09-06 | 2021-09-06 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | 1060 | HNB Reactors Shutdown Essential Safety Cases | Review updated Proposal by Case Officer | 2021-09-07 | 2021-09-10 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6378LT | W222 | W222.A14280 | HRA Fuel Handling Essential Safety Case | Ensure Alignment of Schedule & Estimate | 2021-09-08 | 2021-09-10 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6650LT | W226 | W226.A14280 | HYA Fuel Handling Essential Safety Case | Ensure Alignment of Schedule & Estimate | 2021-09-08 | 2021-09-10 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6370LT | W201 | 1140 | HNB Reactors Shutdown Essential Safety Cases | Produce Verification Plan | 2021-09-08 | 2021-09-10 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6378LT | W222 | W222.A26730 | HRA Fuel Handling Essential Safety Case | Complete Review of Interlock Maintenance Review EAN to CDMS (REV 000) | 2021-09-09 | 2021-09-14 | 4 | 0 | 4 | 5 | 100% | 0.8 | 1 | Completed
ER6650LT | W226 | W226.A26730 | HYA Fuel Handling Essential Safety Case | Complete Review of Interlock Maintenance Review EAN to CDMS (REV 000) | 2021-09-09 | 2021-09-14 | 4 | 0 | 4 | 5 | 100% | 0.8 | 1 | Completed
ER6378LT | W222 | W222.A14290 | HRA Fuel Handling Essential Safety Case | Hold Risk Workshop | 2021-09-13 | 2021-09-13 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1680 | HNB Enhanced Defuelling Safety Cases | Flow Diversion EAN - Complete and Upload to CDMS | 2021-09-13 | 2021-09-22 | 8 | 0 | 8 | 9 | 100% | 0.88889 | 1 | Completed
ER6650LT | W226 | W226.A14290 | HYA Fuel Handling Essential Safety Case | Hold Risk Workshop | 2021-09-13 | 2021-09-13 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | 1180 | HNB Reactors Shutdown Essential Safety Cases | Nuclear Safety Specialist Assessment(s) | 2021-09-13 | 2021-09-21 | 5 | 0 | 6 | 8 | 100% | 0.625 | 1 | Completed
ER6370LT | W201 | 1170 | HNB Reactors Shutdown Essential Safety Cases | Sub-verifier(s) | 2021-09-13 | 2021-09-20 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6370LT | W201 | 1160 | HNB Reactors Shutdown Essential Safety Cases | Verification (Lead Verifier) | 2021-09-13 | 2021-09-23 | 4 | 0 | 8 | 10 | 100% | 0.4 | 1 | Completed
ER6370LT | W201 | 1150 | HNB Reactors Shutdown Essential Safety Cases | Verification PJB | 2021-09-13 | 2021-09-13 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A14300 | HRA Fuel Handling Essential Safety Case | Complete Risk Log with Estimates | 2021-09-14 | 2021-09-15 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6650LT | W226 | W226.A14300 | HYA Fuel Handling Essential Safety Case | Complete Risk Log with Estimates | 2021-09-14 | 2021-09-15 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
W520LT | W520 | W520.A1170 | FLEETWIDE CTO Defueling Safety Case Delivery | Obtain 'Pre-NSSB Signatures' | 2021-09-14 | 2021-09-20 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6378LT | W222 | W222.A26740 | HRA Fuel Handling Essential Safety Case | Review of Interlock Maintenance Review EAN Available (REV 000) | 2021-09-14 | 2021-09-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A26740 | HYA Fuel Handling Essential Safety Case | Review of Interlock Maintenance Review EAN Available (REV 000) | 2021-09-14 | 2021-09-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | 1100 | HNB Reactors Shutdown Essential Safety Cases | AMS Milestone - Ready for Review | 2021-09-14 | 2021-09-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | 1190 | HNB Reactors Shutdown Essential Safety Cases | Respond to Verification Comments and Updates | 2021-09-15 | 2021-09-21 | 4 | 0 | 4 | 6 | 100% | 0.66667 | 1 | Completed
ER6661LT | W206 | W206.A5150 | HYA Reactors Shutdown Essential Safety Cases | First round verification comments received (HYA) | 2021-09-15 | 2021-09-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A5170 | HRA Reactors Shutdown Essential Safety Cases | First round verification comments received (HRA) | 2021-09-15 | 2021-09-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5180 | HYA Reactors Shutdown Essential Safety Cases | Case Author address first round verification comments | 2021-09-16 | 2021-09-29 | 9 | 0 | 9 | 13 | 100% | 0.69231 | 1 | Completed
ER6378LT | W222 | W222.A14310 | HRA Fuel Handling Essential Safety Case | Update Schedule/Estimate from Risk Log & Add Provisions | 2021-09-16 | 2021-09-17 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6650LT | W226 | W226.A14310 | HYA Fuel Handling Essential Safety Case | Update Schedule/Estimate from Risk Log & Add Provisions | 2021-09-16 | 2021-09-17 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6371LT | W202 | W202.A5200 | HRA Reactors Shutdown Essential Safety Cases | Case Author address first round verification comments | 2021-09-16 | 2021-09-29 | 9 | 0 | 9 | 13 | 100% | 0.69231 | 1 | Completed
ER6370LT | W201 | 1210 | HNB Reactors Shutdown Essential Safety Cases | Stn RE Endorsed | 2021-09-20 | 2021-09-23 | 3 | 0 | 3 | 3 | 100% | 1 | 1 | Completed
ER6370LT | W201 | 1200 | HNB Reactors Shutdown Essential Safety Cases | CO Endorsed | 2021-09-20 | 2021-09-23 | 3 | 0 | 3 | 3 | 100% | 1 | 1 | Completed
ER6370LT | W201 | 930 | HNB Reactors Shutdown Essential Safety Cases | Draft HPB Formal ONR Letter/Review | 2021-09-20 | 2021-09-22 | 8 | 0 | 2 | 2 | 100% | 4 | 1 | Completed
ER6378LT | W222 | W222.A14320 | HRA Fuel Handling Essential Safety Case | Add Data to PRC Paper | 2021-09-20 | 2021-09-21 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6650LT | W226 | W226.A14320 | HYA Fuel Handling Essential Safety Case | Add Data to IRM Paper | 2021-09-20 | 2021-09-21 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
W520LT | W520 | W520.A1180 | FLEETWIDE CTO Defueling Safety Case Delivery | Issue Paper to NSSB Secretary | 2021-09-20 | 2021-09-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A5160 | HRA Reactors Shutdown Essential Safety Cases | Discovery Milestone - Confirm Verification Period | 2021-09-21 | 2021-09-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5160 | HYA Reactors Shutdown Essential Safety Cases | Discovery Milestone - Confirm Verification Period | 2021-09-21 | 2021-09-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5240 | HYA Reactors Shutdown Essential Safety Cases | Programme Review | 2021-09-21 | 2021-09-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A5240 | HRA Reactors Shutdown Essential Safety Cases | Programme Review | 2021-09-21 | 2021-09-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W520LT | W520 | W520.A1190 | FLEETWIDE CTO Defueling Safety Case Delivery | NSSB Members Review Documentation | 2021-09-21 | 2021-09-27 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6372LT | W203 | W203.A2430 | HNB Enhanced Defuelling Safety Cases | All key supporting technical references complete <SUSPENDED 22.09.2021> | 2021-09-22 | 2021-09-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A14230 | HRA Fuel Handling Essential Safety Case | PCL Validate & Approve Baseline Package for PRC Submission | 2021-09-22 | 2021-11-10 | 3 | 0 | 36 | 49 | 100% | 0.061224 | 1 | Completed
ER6650LT | W226 | W226.A14230 | HYA Fuel Handling Essential Safety Case | PCL Validate & Approve Baseline Package for PRC Submission | 2021-09-22 | 2021-11-10 | 3 | 0 | 36 | 49 | 100% | 0.061224 | 1 | Completed
ER6370LT | W201 | 1230 | HNB Reactors Shutdown Essential Safety Cases | Other INA assessor(s) | 2021-09-23 | 2021-10-11 | 5 | 0 | 12 | 18 | 100% | 0.27778 | 1 | Completed
ER6370LT | W201 | 1220 | HNB Reactors Shutdown Essential Safety Cases | Lead INA assessor | 2021-09-23 | 2021-10-11 | 5 | 0 | 12 | 18 | 100% | 0.27778 | 1 | Completed
W520LT | W520 | W520.A1200 | FLEETWIDE CTO Defueling Safety Case Delivery | Present Paper to NSSB | 2021-09-28 | 2021-09-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A5560 | HRA Reactors Shutdown Essential Safety Cases | First round comments addressed and revised draft re-circulated | 2021-09-29 | 2021-09-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5565 | HYA Reactors Shutdown Essential Safety Cases | First round comments addressed and revised draft re-circulated | 2021-09-29 | 2021-09-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | 1130 | HNB Reactors Shutdown Essential Safety Cases | Re-attach to HPB ADL | 2021-09-29 | 2021-09-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206210 | HRA Reactors Shutdown Essential Safety Cases | Second Round of Verification - Verifier Name | 2021-09-29 | 2021-10-15 | 13 | 0 | 13 | 16 | 100% | 0.8125 | 1 | Completed
ER6661LT | W206 | W206.A2206210 | HYA Reactors Shutdown Essential Safety Cases | Second Round of Verification - Verifier Name | 2021-09-29 | 2021-10-15 | 13 | 0 | 13 | 16 | 100% | 0.8125 | 1 | Completed
W520LT | W520 | W520.A1210 | FLEETWIDE CTO Defueling Safety Case Delivery | Address NSSB Comments | 2021-09-29 | 2021-10-05 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.1030 | HYB Essential Defueling Safety Case | Project Start | 2021-10-01 | 2021-10-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.3000 | HYB Essential Defueling Safety Case | Problem Statement - Summary | 2021-10-01 | 2021-11-05 | 26 | 0 | 26 | 35 | 100% | 0.74286 | 1 | Completed
ER6666LT | W209 | W209.3010 | HYB Essential Defueling Safety Case | Problem Statement - Prepare Problem Statement | 2021-10-01 | 2021-10-08 | 25 | 0 | 5 | 7 | 100% | 3.5714 | 1 | Completed
ER6666LT | W209 | W209.1855 | HYB Essential Defueling Safety Case | Technical Development / Project Management - Pre Gate A - (Cost Summary) ## | 2021-10-01 | 2022-02-23 | 106 | 0 | 100 | 145 | 100% | 0.73103 | 1 | Completed
ER6668LT | W213 | W213.1030 | TOR Essential Defueling Safety Case | Project Start | 2021-10-01 | 2021-10-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.3000 | TOR Essential Defueling Safety Case | Problem Statement - Summary | 2021-10-01 | 2021-11-05 | 26 | 0 | 26 | 35 | 100% | 0.74286 | 1 | Completed
ER6668LT | W213 | W213.3010 | TOR Essential Defueling Safety Case | Problem Statement - Prepare Problem Statement | 2021-10-01 | 2021-10-08 | 25 | 0 | 5 | 7 | 100% | 3.5714 | 1 | Completed
ER6668LT | W213 | W213.1855 | TOR Essential Defueling Safety Case | Technical Development / Project Management - Pre Gate A - (Cost Summary) ## | 2021-10-01 | 2022-02-23 | 106 | 0 | 100 | 145 | 100% | 0.73103 | 1 | Completed
W520LT | W520 | W520.A1220 | FLEETWIDE CTO Defueling Safety Case Delivery | Obtain 'Post-NSSB Meeting Signatures' | 2021-10-06 | 2021-10-07 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
W520LT | W520 | W520.A1230 | FLEETWIDE CTO Defueling Safety Case Delivery | Request Direction Sanction Approval | 2021-10-08 | 2021-10-11 | 2 | 0 | 2 | 3 | 100% | 0.66667 | 1 | Completed
ER6370LT | W201 | 1240 | HNB Reactors Shutdown Essential Safety Cases | Final INSA Approval | 2021-10-11 | 2021-10-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W520LT | W520 | W520.A1050 | FLEETWIDE CTO Defueling Safety Case Delivery | NSSB Sanction Approval | 2021-10-11 | 2021-10-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | 920 | HNB Reactors Shutdown Essential Safety Cases | Draft HNB Formal ONR Letter/Review | 2021-10-12 | 2021-10-29 | 8 | 0 | 13 | 17 | 100% | 0.47059 | 1 | Completed
W520LT | W520 | W520.A1240 | FLEETWIDE CTO Defueling Safety Case Delivery | Finance Shuffle Budgets | 2021-10-12 | 2021-10-25 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6371LT | W202 | W202.A2206220 | HRA Reactors Shutdown Essential Safety Cases | Second round verification comments received (HRA) | 2021-10-15 | 2021-10-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206225 | HYA Reactors Shutdown Essential Safety Cases | Second round verification comments received (HYA) | 2021-10-15 | 2021-10-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206230 | HRA Reactors Shutdown Essential Safety Cases | Case Author address Second round verification comments | 2021-10-18 | 2021-11-05 | 15 | 0 | 15 | 18 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | W206.A2206235 | HYA Reactors Shutdown Essential Safety Cases | Case Author address Second round verification comments | 2021-10-18 | 2021-11-05 | 15 | 0 | 15 | 18 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.3020 | HYB Essential Defueling Safety Case | Problem Statement - Issue Problem Statement for Comment. | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.3020 | TOR Essential Defueling Safety Case | Problem Statement - Issue Problem Statement for Comment. | 2021-10-29 | 2021-10-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A5060 | HRA Reactors Shutdown Essential Safety Cases | Prepare and Populate Affected Documents List (HRA) | 2021-11-01 | 2021-12-13 | 10 | 0 | 30 | 42 | 100% | 0.2381 | 1 | Completed
ER6661LT | W206 | W206.A5060 | HYA Reactors Shutdown Essential Safety Cases | Prepare and Populate Affected Documents List (HYA) | 2021-11-01 | 2021-12-13 | 10 | 0 | 30 | 42 | 100% | 0.2381 | 1 | Completed
ER6666LT | W209 | W209.3030 | HYB Essential Defueling Safety Case | Problem Statement - Agree Problem Statement | 2021-11-01 | 2021-11-05 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | 940 | HNB Reactors Shutdown Essential Safety Cases | Station Directors sign letters | 2021-11-01 | 2021-11-03 | 4 | 0 | 2 | 2 | 100% | 2 | 1 | Completed
ER6668LT | W213 | W213.3030 | TOR Essential Defueling Safety Case | Problem Statement - Agree Problem Statement | 2021-11-01 | 2021-11-05 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6370LT | W201 | W201.1550 | HNB Reactors Shutdown Essential Safety Cases | Event Recovery Milestone - Safety Case Submitted to the ONR | 2021-11-03 | 2021-11-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | 950 | HNB Reactors Shutdown Essential Safety Cases | Safety Case Submitted to the ONR | 2021-11-03 | 2021-11-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | W201.1560 | HNB Reactors Shutdown Essential Safety Cases | Event Recovery - ONR Assessment Period | 2021-11-05 | 2022-03-21 | 43 | 0 | 93 | 136 | 100% | 0.31618 | 1 | Completed
ER6666LT | W209 | W209.3050 | HYB Essential Defueling Safety Case | Problem Statement - Issue Problem Statement to Stakeholders | 2021-11-05 | 2021-11-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206250 | HRA Reactors Shutdown Essential Safety Cases | Second round comments addressed and revised draft re-circulated | 2021-11-05 | 2021-11-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206255 | HYA Reactors Shutdown Essential Safety Cases | Second round comments addressed and revised draft re-circulated | 2021-11-05 | 2021-11-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.3050 | TOR Essential Defueling Safety Case | Problem Statement - Issue Problem Statement to Stakeholders | 2021-11-05 | 2021-11-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206260 | HRA Reactors Shutdown Essential Safety Cases | Third Round of Verification - Verifier Name | 2021-11-08 | 2021-11-08 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206260 | HYA Reactors Shutdown Essential Safety Cases | Third Round of Verification - Verifier Name | 2021-11-08 | 2021-11-08 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206270 | HRA Reactors Shutdown Essential Safety Cases | Third round verification comments received (HRA) | 2021-11-08 | 2021-11-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206270 | HYA Reactors Shutdown Essential Safety Cases | Third round verification comments received (HYA) | 2021-11-08 | 2021-11-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206280 | HRA Reactors Shutdown Essential Safety Cases | Case Author address Third round verification comments | 2021-11-09 | 2021-11-09 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206280 | HYA Reactors Shutdown Essential Safety Cases | Case Author address Third round verification comments | 2021-11-09 | 2021-11-09 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206300 | HRA Reactors Shutdown Essential Safety Cases | Third round comments addressed and revised draft re-circulated | 2021-11-09 | 2021-11-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206300 | HYA Reactors Shutdown Essential Safety Cases | Third round comments addressed and revised draft re-circulated | 2021-11-09 | 2021-11-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A14240 | HRA Fuel Handling Essential Safety Case | Issue PRC Paper to R4 PRC Members | 2021-11-10 | 2021-11-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A14240 | HYA Fuel Handling Essential Safety Case | Issue IRM Paper to R4 PRC Members | 2021-11-10 | 2021-11-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A14330 | HRA Fuel Handling Essential Safety Case | PRC Members Review PRC Documentation | 2021-11-11 | 2021-11-17 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6650LT | W226 | W226.A14330 | HYA Fuel Handling Essential Safety Case | PRC Members Review IRM Documentation | 2021-11-11 | 2021-11-17 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A5180 | HRA Reactors Shutdown Essential Safety Cases | SQEP sign off of verification (HRA) | 2021-11-15 | 2021-11-19 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6661LT | W206 | W206.A2206230 | HYA Reactors Shutdown Essential Safety Cases | SQEP sign off of verification (HYA) | 2021-11-15 | 2021-11-19 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6371LT | W202 | W202.A5190 | HRA Reactors Shutdown Essential Safety Cases | CO Sign-off (HRA) | 2021-11-22 | 2021-11-26 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6661LT | W206 | W206.A5190 | HYA Reactors Shutdown Essential Safety Cases | CO Sign-off (HYA) | 2021-11-22 | 2021-11-26 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6378LT | W222 | W222.A13300 | HRA Fuel Handling Essential Safety Case | Gate C for Region 1 - HRA Defuelling Fuel Handling Essential Safety Case | 2021-11-23 | 2021-11-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A13300 | HYA Fuel Handling Essential Safety Case | Gate C for Region 1 - HYA Defuelling Fuel Handling Essential Safety Case | 2021-11-23 | 2021-11-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A14340 | HRA Fuel Handling Essential Safety Case | Hold R4 PRC Meeting | 2021-11-23 | 2021-11-23 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A14340 | HYA Fuel Handling Essential Safety Case | Hold R4 PRC Meeting | 2021-11-23 | 2021-11-23 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A14350 | HRA Fuel Handling Essential Safety Case | Modify Estimate, Schedule & Risk Log as Required | 2021-11-24 | 2021-11-25 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6650LT | W226 | W226.A14350 | HYA Fuel Handling Essential Safety Case | Modify Estimate, Schedule & Risk Log as Required | 2021-11-24 | 2021-11-25 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6378LT | W222 | W222.A14380 | HRA Fuel Handling Essential Safety Case | Update Cost Management Tool | 2021-11-26 | 2021-12-23 | 5 | 0 | 19 | 27 | 100% | 0.18519 | 1 | Completed
ER6650LT | W226 | W226.A14380 | HYA Fuel Handling Essential Safety Case | Update Cost Management Tool | 2021-11-26 | 2021-12-23 | 5 | 0 | 19 | 27 | 100% | 0.18519 | 1 | Completed
ER6371LT | W202 | W202.A5210 | HRA Reactors Shutdown Essential Safety Cases | Verified Draft Available for INSA (T-7) EC 363682 <Reactor Shutdown Essential SC> (Cat 1 KDM) (HRA) | 2021-11-26 | 2021-11-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A5220 | HRA Reactors Shutdown Essential Safety Cases | Verification complete (HRA) | 2021-11-26 | 2021-11-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A5230 | HRA Reactors Shutdown Essential Safety Cases | Verified Draft Available for INSA (T-7) EC 363682 <Reactor Shutdown Essential SC> (Cat 1 KDM) (HRA) | 2021-11-26 | 2021-11-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5210 | HYA Reactors Shutdown Essential Safety Cases | Verified Draft Available for INSA (T-7) EC 363676 <Reactor Shutdown Essential SC> (Cat 1 KDM) (HYA) | 2021-11-26 | 2021-11-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5220 | HYA Reactors Shutdown Essential Safety Cases | Verification complete (HYA) | 2021-11-26 | 2021-11-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5230 | HYA Reactors Shutdown Essential Safety Cases | Verified Draft Available for INSA (T-7) EC 363676 <Reactor Shutdown Essential SC> (Cat 1 KDM) (HYA) | 2021-11-26 | 2021-11-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A16370 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Defuelling Safety Case Head Documents EAN to CDMS | 2021-11-29 | 2021-12-24 | 5 | 0 | 20 | 25 | 100% | 0.2 | 1 | Completed
ER6650LT | W226 | W226.A16370 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Defuelling Safety Case Head Documents EAN to CDMS | 2021-11-29 | 2021-12-24 | 5 | 0 | 19 | 25 | 100% | 0.2 | 1 | Completed
ER6666LT | W209 | W209.1000 | HYB Essential Defueling Safety Case | Confirm Objectives to be Delivered at Gate A (FEEDS TO SUMMARY SCHEDULE) | 2021-12-01 | 2021-12-02 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6668LT | W213 | W213.1000 | TOR Essential Defueling Safety Case | Confirm Objectives to be Delivered at Gate A (FEEDS TO SUMMARY SCHEDULE) | 2021-12-01 | 2021-12-02 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6666LT | W209 | W209.1040 | HYB Essential Defueling Safety Case | Initial high level scope of programme | 2021-12-03 | 2021-12-06 | 2 | 0 | 2 | 3 | 100% | 0.66667 | 1 | Completed
ER6668LT | W213 | W213.1040 | TOR Essential Defueling Safety Case | Initial high level scope of programme | 2021-12-03 | 2021-12-06 | 2 | 0 | 2 | 3 | 100% | 0.66667 | 1 | Completed
ER6371LT | W202 | W202.A5250 | HRA Reactors Shutdown Essential Safety Cases | INSA review & iteration of comments (using BARRIER MODEL) (HRA) (Suspended for Event Recovery) | 2021-12-06 | 2022-02-01 | 40 | 0 | 38 | 57 | 100% | 0.70175 | 1 | Completed
ER6371LT | W202 | W202.A5260 | HRA Reactors Shutdown Essential Safety Cases | <NOT REQUIRED> DA (Authorised Designer) Approval of CAT1 Safety Case (HRA) | 2021-12-06 | 2021-12-06 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5250 | HYA Reactors Shutdown Essential Safety Cases | INSA review & iteration of comments (using BARRIER MODEL) (HYA) (Suspended for Event Recovery) | 2021-12-06 | 2022-02-01 | 40 | 0 | 38 | 57 | 100% | 0.70175 | 1 | Completed
ER6661LT | W206 | W206.A5260 | HYA Reactors Shutdown Essential Safety Cases | <NOT REQUIRED> DA (Authorised Designer) Approval of CAT1 Safety Case (HYA) | 2021-12-06 | 2021-12-06 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A24310 | HRA Fuel Handling Essential Safety Case | Verify Living Safety Document EAN and Issue for Technical Review | 2021-12-06 | 2022-02-17 | 10 | 0 | 51 | 73 | 100% | 0.13699 | 1 | Completed
ER6378LT | W222 | W222.A4660 | HRA Fuel Handling Essential Safety Case | Obtain peer review (if required) | 2021-12-06 | 2021-12-10 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6650LT | W226 | W226.A4660 | HYA Fuel Handling Essential Safety Case | Obtain peer review (if required) | 2021-12-06 | 2021-12-10 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6650LT | W226 | W226.A24310 | HYA Fuel Handling Essential Safety Case | Verify Living Safety Document EAN and Issue for Technical Review | 2021-12-06 | 2022-02-17 | 10 | 0 | 50 | 73 | 100% | 0.13699 | 1 | Completed
ER6666LT | W209 | W209.1050 | HYB Essential Defueling Safety Case | Prepare Draft Project Definition Document (PDD) | 2021-12-07 | 2021-12-13 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.1050 | TOR Essential Defueling Safety Case | Prepare Draft Project Definition Document (PDD) | 2021-12-07 | 2021-12-13 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6378LT | W222 | W222.1000 | HRA Fuel Handling Essential Safety Case | Discovery Milestone - Confirm Verification Period | 2021-12-07 | 2021-12-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.1000 | HYA Fuel Handling Essential Safety Case | Discovery Milestone - Confirm Verification Period | 2021-12-07 | 2021-12-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A4790 | HRA Fuel Handling Essential Safety Case | Safety Case Prop Authoring Complete ECs (HRA-363840) HRA Essential Fuel Handling Safety Case | 2021-12-10 | 2021-12-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A4790 | HYA Fuel Handling Essential Safety Case | Safety Case Prop Authoring Complete ECs (HYA-363839) HYA Essential Fuel Handling Safety Case | 2021-12-10 | 2021-12-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A4800 | HRA Fuel Handling Essential Safety Case | HRA HYA Essential Fuel Handling SC: Verification Commenced (T-11) | 2021-12-13 | 2021-12-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A4800 | HYA Fuel Handling Essential Safety Case | HYA HYA Essential Fuel Handling SC: Verification Commenced (T-11) | 2021-12-13 | 2021-12-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5320 | HYA Reactors Shutdown Essential Safety Cases | Discovery Milestone: Confirm INA Period | 2021-12-13 | 2021-12-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A13380 | HRA Fuel Handling Essential Safety Case | Safety Case Development - Costs - AR / CETS / Support to CO ##(Cost Summary)## (C to D) ** | 2021-12-13 | 2025-01-24 | 176 | 0 | 786 | 1138 | 100% | 0.15466 | 1 | Completed
ER6378LT | W222 | W222.A4700 | HRA Fuel Handling Essential Safety Case | Verification of the case (using BARRIER MODEL) | 2021-12-13 | 2022-02-21 | 40 | 0 | 47 | 70 | 100% | 0.57143 | 1 | Completed
ER6378LT | W222 | W222.A4770 | HRA Fuel Handling Essential Safety Case | Specialist Assessments if Necessary (Expand as Required) | 2021-12-13 | 2023-08-31 | 10 | 0 | 430 | 626 | 100% | 0.015974 | 1 | Completed
ER6650LT | W226 | W226.A4770 | HYA Fuel Handling Essential Safety Case | Specialist Assessments if Necessary (Expand as Required) | 2021-12-13 | 2023-08-31 | 10 | 0 | 430 | 626 | 100% | 0.015974 | 1 | Completed
ER6650LT | W226 | W226.A4700 | HYA Fuel Handling Essential Safety Case | Verification of the case (using BARRIER MODEL) | 2021-12-13 | 2022-02-21 | 40 | 0 | 47 | 70 | 100% | 0.57143 | 1 | Completed
ER6378LT | W222 | W222.1110 | HRA Fuel Handling Essential Safety Case | Project Management Costs - Verification Phase (C to D ) ##Cost Summary## ** | 2021-12-13 | 2024-07-17 | 70 | 0 | 653 | 947 | 100% | 0.073918 | 1 | Completed
ER6378LT | W222 | W222.1120 | HRA Fuel Handling Essential Safety Case | Safety Case Development Costs - Verification Phase (C to D ) ##Cost Summary## ** | 2021-12-13 | 2024-07-17 | 70 | 0 | 653 | 947 | 100% | 0.073918 | 1 | Completed
ER6650LT | W226 | W226.A13380 | HYA Fuel Handling Essential Safety Case | Safety Case Development - Costs - AR / CETS / Support to CO ##(Cost Summary)## (C to D) ** | 2021-12-13 | 2025-01-13 | 176 | 0 | 777 | 1127 | 100% | 0.15617 | 1 | Completed
ER6650LT | W226 | W226.1120 | HYA Fuel Handling Essential Safety Case | Safety Case Development Costs - Verification Phase (C to D ) ##Cost Summary## ** | 2021-12-13 | 2024-07-17 | 70 | 0 | 653 | 947 | 100% | 0.073918 | 1 | Completed
ER6650LT | W226 | W226.1110 | HYA Fuel Handling Essential Safety Case | Project Management Costs - Verification Phase (C to D ) ##Cost Summary## ** | 2021-12-13 | 2024-07-17 | 70 | 0 | 653 | 947 | 100% | 0.073918 | 1 | Completed
ER6371LT | W202 | W202.A5320 | HRA Reactors Shutdown Essential Safety Cases | Discovery Milestone: Confirm INA Period | 2021-12-13 | 2021-12-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1130 | HYB Essential Defueling Safety Case | Update Schedule/Estimate from Risk Log & Add Provisions | 2021-12-14 | 2022-01-28 | 5 | 0 | 31 | 45 | 100% | 0.11111 | 1 | Completed
ER6668LT | W213 | W213.1130 | TOR Essential Defueling Safety Case | Update Schedule/Estimate from Risk Log & Add Provisions | 2021-12-14 | 2022-01-28 | 5 | 0 | 31 | 45 | 100% | 0.11111 | 1 | Completed
ER6650LT | W226 | W226.A16360 | HYA Fuel Handling Essential Safety Case | Defuelling Safety Case Head Documents EAN Available | 2021-12-24 | 2021-12-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A16360 | HRA Fuel Handling Essential Safety Case | Defuelling Safety Case Head Documents EAN Available | 2021-12-24 | 2021-12-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1260 | HYB Essential Defueling Safety Case | Project Management - Gate A-B - (Cost Summary) ## | 2022-01-04 | 2022-07-14 | 282 | 0 | 133 | 191 | 100% | 1.4764 | 1 | Completed
ER6666LT | W209 | W209.1280 | HYB Essential Defueling Safety Case | SC - Oversight Support - A-B - (Cost Summary) ## | 2022-01-04 | 2022-07-14 | 282 | 0 | 133 | 191 | 100% | 1.4764 | 1 | Completed
ER6666LT | W209 | W209.3280 | HYB Essential Defueling Safety Case | Release and Receive Comments from Stakeholders | 2022-01-04 | 2022-02-04 | 10 | 0 | 24 | 31 | 100% | 0.32258 | 1 | Completed
ER6666LT | W209 | W209.3290 | HYB Essential Defueling Safety Case | Develop Optioneering Options | 2022-01-04 | 2022-02-04 | 5 | 0 | 24 | 31 | 100% | 0.16129 | 1 | Completed
ER6666LT | W209 | W209.4280 | HYB Essential Defueling Safety Case | Defueling Order / Fuel Management - (Cost Summary) ## | 2022-01-04 | 2022-05-13 | 84 | 0 | 91 | 129 | 100% | 0.65116 | 1 | Completed
ER6666LT | W209 | W209.4290 | HYB Essential Defueling Safety Case | Fuel Handling - (Cost Summary) ## | 2022-01-04 | 2022-07-13 | 282 | 0 | 132 | 190 | 100% | 1.4842 | 1 | Completed
ER6666LT | W209 | W209.5680 | HYB Essential Defueling Safety Case | Prepare Spec for Judgement Based Work Diversion EAN | 2022-01-04 | 2022-01-17 | 5 | 0 | 9 | 13 | 100% | 0.38462 | 1 | Completed
ER6666LT | W209 | W209.25960 | HYB Essential Defueling Safety Case | Technical Development / Project Management - Gate A - B - (Cost Summary) ## | 2022-01-04 | 2022-07-14 | 282 | 0 | 133 | 191 | 100% | 1.4764 | 1 | Completed
ER6668LT | W213 | W213.1260 | TOR Essential Defueling Safety Case | Project Management - Gate A-B - (Cost Summary) ## | 2022-01-04 | 2022-07-14 | 282 | 0 | 133 | 191 | 100% | 1.4764 | 1 | Completed
ER6668LT | W213 | W213.1280 | TOR Essential Defueling Safety Case | SC - Oversight Support - A-B - (Cost Summary) ## | 2022-01-04 | 2022-07-14 | 282 | 0 | 133 | 191 | 100% | 1.4764 | 1 | Completed
ER6668LT | W213 | W213.3280 | TOR Essential Defueling Safety Case | Release and Receive Comments from Stakeholders | 2022-01-04 | 2022-02-04 | 10 | 0 | 24 | 31 | 100% | 0.32258 | 1 | Completed
ER6668LT | W213 | W213.3290 | TOR Essential Defueling Safety Case | Develop Optioneering Options | 2022-01-04 | 2022-02-04 | 5 | 0 | 24 | 31 | 100% | 0.16129 | 1 | Completed
ER6668LT | W213 | W213.4280 | TOR Essential Defueling Safety Case | Defueling Order / Fuel Management - (Cost Summary) ## | 2022-01-04 | 2022-05-13 | 84 | 0 | 91 | 129 | 100% | 0.65116 | 1 | Completed
ER6668LT | W213 | W213.4290 | TOR Essential Defueling Safety Case | Fuel Handling - (Cost Summary) ## | 2022-01-04 | 2022-07-13 | 282 | 0 | 132 | 190 | 100% | 1.4842 | 1 | Completed
ER6668LT | W213 | W213.5680 | TOR Essential Defueling Safety Case | Prepare Spec for Judgement Based Work Diversion EAN | 2022-01-04 | 2022-01-17 | 5 | 0 | 9 | 13 | 100% | 0.38462 | 1 | Completed
ER6668LT | W213 | W213.25960 | TOR Essential Defueling Safety Case | Technical Development / Project Management - Gate A - B - (Cost Summary) ## | 2022-01-04 | 2022-07-14 | 282 | 0 | 133 | 191 | 100% | 1.4764 | 1 | Completed
W520LT | W520 | W520.A1010 | FLEETWIDE CTO Defueling Safety Case Delivery | 2022 Costs | 2022-01-04 | 2022-12-30 | 253 | 0 | 250 | 360 | 100% | 0.70278 | 1 | Completed
ER6666LT | W209 | W209.3260 | HYB Essential Defueling Safety Case | Develop Optioneering Question Set | 2022-01-04 | 2022-02-04 | 15 | 0 | 24 | 31 | 100% | 0.48387 | 1 | Completed
ER6666LT | W209 | W209.3270 | HYB Essential Defueling Safety Case | Develop Optioneering Criteria | 2022-01-04 | 2022-02-04 | 15 | 0 | 24 | 31 | 100% | 0.48387 | 1 | Completed
ER6666LT | W209 | W209.3580 | HYB Essential Defueling Safety Case | Specify Scope for Delivery | 2022-01-04 | 2022-01-24 | 9 | 0 | 14 | 20 | 100% | 0.45 | 1 | Completed
ER6666LT | W209 | W209.3890 | HYB Essential Defueling Safety Case | Develop Optioneering Question Set | 2022-01-04 | 2022-02-11 | 10 | 0 | 29 | 38 | 100% | 0.26316 | 1 | Completed
ER6666LT | W209 | W209.3900 | HYB Essential Defueling Safety Case | Develop Optioneering Criteria & Options | 2022-01-04 | 2022-02-11 | 10 | 0 | 29 | 38 | 100% | 0.26316 | 1 | Completed
ER6666LT | W209 | W209.3990 | HYB Essential Defueling Safety Case | Defueling PM OPEX | 2022-01-04 | 2022-04-27 | 40 | 0 | 79 | 113 | 100% | 0.35398 | 1 | Completed
ER6666LT | W209 | W209.4340 | HYB Essential Defueling Safety Case | Generate Draft Fuel Route Process Flow Commentary | 2022-01-04 | 2022-03-01 | 15 | 0 | 41 | 56 | 100% | 0.26786 | 1 | Completed
ER6666LT | W209 | W209.4440 | HYB Essential Defueling Safety Case | Generate RFS (A-B Phase) | 2022-01-04 | 2022-01-17 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6666LT | W209 | W209.4460 | HYB Essential Defueling Safety Case | Ratify HYB TOR Defueling Assumptions List with Station | 2022-01-04 | 2022-02-01 | 20 | 0 | 21 | 28 | 100% | 0.71429 | 1 | Completed
ER6666LT | W209 | W209.4490 | HYB Essential Defueling Safety Case | Lead & Learn Workstream - (Cost Summary) ## | 2022-01-04 | 2022-05-17 | 93 | 0 | 93 | 133 | 100% | 0.69925 | 1 | Completed
ER6666LT | W209 | W209.1085 | HYB Essential Defueling Safety Case | Produce draft NSRS (using BARRIER MODEL) | 2022-01-04 | 2022-04-01 | 40 | 0 | 64 | 87 | 100% | 0.45977 | 1 | Completed
ER6666LT | W209 | W209.4640 | HYB Essential Defueling Safety Case | Defueling Cooling Operations - (Cost Summary) ## | 2022-01-04 | 2022-07-01 | 106 | 0 | 124 | 178 | 100% | 0.59551 | 1 | Completed
ER6666LT | W209 | W209.4890 | HYB Essential Defueling Safety Case | Defueling Cooling Operations - De-risking Scope - (Cost Summary) ## | 2022-01-04 | 2022-07-13 | 132 | 0 | 132 | 190 | 100% | 0.69474 | 1 | Completed
ER6668LT | W213 | W213.3260 | TOR Essential Defueling Safety Case | Develop Optioneering Question Set | 2022-01-04 | 2022-02-04 | 15 | 0 | 24 | 31 | 100% | 0.48387 | 1 | Completed
ER6668LT | W213 | W213.3270 | TOR Essential Defueling Safety Case | Develop Optioneering Criteria | 2022-01-04 | 2022-02-04 | 15 | 0 | 24 | 31 | 100% | 0.48387 | 1 | Completed
ER6668LT | W213 | W213.3580 | TOR Essential Defueling Safety Case | Specify Scope for Delivery | 2022-01-04 | 2022-01-24 | 9 | 0 | 14 | 20 | 100% | 0.45 | 1 | Completed
ER6668LT | W213 | W213.3890 | TOR Essential Defueling Safety Case | Develop Optioneering Question Set | 2022-01-04 | 2022-02-11 | 10 | 0 | 29 | 38 | 100% | 0.26316 | 1 | Completed
ER6668LT | W213 | W213.3900 | TOR Essential Defueling Safety Case | Develop Optioneering Criteria & Options | 2022-01-04 | 2022-02-11 | 10 | 0 | 29 | 38 | 100% | 0.26316 | 1 | Completed
ER6668LT | W213 | W213.3990 | TOR Essential Defueling Safety Case | Defueling PM OPEX | 2022-01-04 | 2022-04-27 | 40 | 0 | 79 | 113 | 100% | 0.35398 | 1 | Completed
ER6668LT | W213 | W213.4340 | TOR Essential Defueling Safety Case | Generate Draft Fuel Route Process Flow Commentary | 2022-01-04 | 2022-03-01 | 15 | 0 | 41 | 56 | 100% | 0.26786 | 1 | Completed
ER6668LT | W213 | W213.4440 | TOR Essential Defueling Safety Case | Generate RFS (A-B Phase) | 2022-01-04 | 2022-01-17 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6668LT | W213 | W213.4460 | TOR Essential Defueling Safety Case | Ratify TOR TOR Defueling Assumptions List with Station | 2022-01-04 | 2022-02-01 | 20 | 0 | 21 | 28 | 100% | 0.71429 | 1 | Completed
ER6668LT | W213 | W213.4490 | TOR Essential Defueling Safety Case | Lead & Learn Workstream - (Cost Summary) ## | 2022-01-04 | 2022-05-17 | 93 | 0 | 93 | 133 | 100% | 0.69925 | 1 | Completed
ER6668LT | W213 | W213.1085 | TOR Essential Defueling Safety Case | Produce draft NSRS (using BARRIER MODEL) | 2022-01-04 | 2022-04-01 | 40 | 0 | 64 | 87 | 100% | 0.45977 | 1 | Completed
ER6668LT | W213 | W213.4640 | TOR Essential Defueling Safety Case | Defueling Cooling Operations - (Cost Summary) ## | 2022-01-04 | 2022-07-01 | 106 | 0 | 124 | 178 | 100% | 0.59551 | 1 | Completed
ER6668LT | W213 | W213.4890 | TOR Essential Defueling Safety Case | Defueling Cooling Operations - De-risking Scope - (Cost Summary) ## | 2022-01-04 | 2022-07-13 | 132 | 0 | 132 | 190 | 100% | 0.69474 | 1 | Completed
ER6666LT | W209 | W209.1005 | HYB Essential Defueling Safety Case | PM / CO and PCE Create Initial Plan of Work | 2022-01-04 | 2022-01-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1015 | HYB Essential Defueling Safety Case | Initial Categorisation by Station | 2022-01-04 | 2022-01-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1005 | TOR Essential Defueling Safety Case | PM / CO and PCE Create Initial Plan of Work | 2022-01-04 | 2022-01-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1015 | TOR Essential Defueling Safety Case | Initial Categorisation by Station | 2022-01-04 | 2022-01-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1035 | HYB Essential Defueling Safety Case | Appoint CO | 2022-01-05 | 2022-01-05 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1035 | TOR Essential Defueling Safety Case | Appoint CO | 2022-01-05 | 2022-01-05 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1025 | HYB Essential Defueling Safety Case | Commence NSRS | 2022-01-06 | 2022-01-06 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1025 | TOR Essential Defueling Safety Case | Commence NSRS | 2022-01-06 | 2022-01-06 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.4020 | HYB Essential Defueling Safety Case | SC Strategy Workshop | 2022-01-06 | 2022-01-06 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.4020 | TOR Essential Defueling Safety Case | SC Strategy Workshop | 2022-01-06 | 2022-01-06 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.4500 | HYB Essential Defueling Safety Case | Share Safety Case Strategy with Stakeholders (Central / Station / Regulatory) | 2022-01-07 | 2022-03-03 | 40 | 0 | 40 | 55 | 100% | 0.72727 | 1 | Completed
ER6668LT | W213 | W213.4500 | TOR Essential Defueling Safety Case | Share Safety Case Strategy with Stakeholders (Central / Station / Regulatory) | 2022-01-07 | 2022-03-03 | 40 | 0 | 40 | 55 | 100% | 0.72727 | 1 | Completed
ER6666LT | W209 | W209.4990 | HYB Essential Defueling Safety Case | Contract Instruction issues to Atkins by EDF Energy | 2022-01-10 | 2022-01-17 | 0 | 0 | 5 | 7 | 100% | 0 | 1 | Completed
ER6666LT | W209 | W209.5180 | HYB Essential Defueling Safety Case | Dropped FPU - Basis of Analysis - (Cost Summary) ## | 2022-01-10 | 2022-07-01 | 92 | 0 | 120 | 172 | 100% | 0.53488 | 1 | Completed
ER6666LT | W209 | W209.5190 | HYB Essential Defueling Safety Case | DE-RISKING SCOPE - Fuel Handling - (Cost Summary) ## | 2022-01-10 | 2022-07-13 | 69 | 0 | 128 | 184 | 100% | 0.375 | 1 | Completed
ER6666LT | W209 | W209.6580 | HYB Essential Defueling Safety Case | Prepare Spec for Radiological Consequences Following Failed CSP EAN | 2022-01-10 | 2022-01-14 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6668LT | W213 | W213.4990 | TOR Essential Defueling Safety Case | Contract Instruction issues to Atkins by EDF Energy | 2022-01-10 | 2022-01-17 | 0 | 0 | 5 | 7 | 100% | 0 | 1 | Completed
ER6668LT | W213 | W213.5180 | TOR Essential Defueling Safety Case | Dropped FPU - Basis of Analysis - (Cost Summary) ## | 2022-01-10 | 2022-07-01 | 92 | 0 | 120 | 172 | 100% | 0.53488 | 1 | Completed
ER6668LT | W213 | W213.5190 | TOR Essential Defueling Safety Case | DE-RISKING SCOPE - Fuel Handling - (Cost Summary) ## | 2022-01-10 | 2022-07-13 | 69 | 0 | 128 | 184 | 100% | 0.375 | 1 | Completed
ER6668LT | W213 | W213.6580 | TOR Essential Defueling Safety Case | Prepare Spec for Radiological Consequences Following Failed CSP EAN | 2022-01-10 | 2022-01-14 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6666LT | W209 | W209.5000 | HYB Essential Defueling Safety Case | PJB Held | 2022-01-17 | 2022-01-17 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.6590 | HYB Essential Defueling Safety Case | Prepare Task Sheet for Radiological Consequences Following Failed CSP EAN | 2022-01-17 | 2022-01-21 | 10 | 0 | 4 | 4 | 100% | 2.5 | 1 | Completed
ER6668LT | W213 | W213.5000 | TOR Essential Defueling Safety Case | PJB Held | 2022-01-17 | 2022-01-17 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.6590 | TOR Essential Defueling Safety Case | Prepare Task Sheet for Radiological Consequences Following Failed CSP EAN | 2022-01-17 | 2022-01-21 | 10 | 0 | 4 | 4 | 100% | 2.5 | 1 | Completed
ER6666LT | W209 | W209.4710 | HYB Essential Defueling Safety Case | Review Region 1 & Existing Fault Schedules | 2022-01-17 | 2022-01-21 | 10 | 0 | 4 | 4 | 100% | 2.5 | 1 | Completed
ER6668LT | W213 | W213.4710 | TOR Essential Defueling Safety Case | Review Region 1 & Existing Fault Schedules | 2022-01-17 | 2022-01-21 | 10 | 0 | 4 | 4 | 100% | 2.5 | 1 | Completed
ER6666LT | W209 | W209.5050 | HYB Essential Defueling Safety Case | Define Nuclear Safety Issues | 2022-01-18 | 2022-02-15 | 1 | 0 | 20 | 28 | 100% | 0.035714 | 1 | Completed
ER6666LT | W209 | W209.5690 | HYB Essential Defueling Safety Case | Prepare Task Sheet for Judgement Based Work Diversion EAN | 2022-01-18 | 2022-01-20 | 10 | 0 | 2 | 2 | 100% | 5 | 1 | Completed
ER6668LT | W213 | W213.5050 | TOR Essential Defueling Safety Case | Define Nuclear Safety Issues | 2022-01-18 | 2022-02-15 | 1 | 0 | 20 | 28 | 100% | 0.035714 | 1 | Completed
ER6668LT | W213 | W213.5690 | TOR Essential Defueling Safety Case | Prepare Task Sheet for Judgement Based Work Diversion EAN | 2022-01-18 | 2022-01-20 | 10 | 0 | 2 | 2 | 100% | 5 | 1 | Completed
ER6666LT | W209 | W209.4660 | HYB Essential Defueling Safety Case | Review & Approve RFS (A-B Phase) | 2022-01-18 | 2022-01-20 | 5 | 0 | 3 | 2 | 100% | 2.5 | 1 | Completed
ER6668LT | W213 | W213.4660 | TOR Essential Defueling Safety Case | Review & Approve RFS (A-B Phase) | 2022-01-18 | 2022-01-20 | 5 | 0 | 3 | 2 | 100% | 2.5 | 1 | Completed
ER6666LT | W209 | W209.5700 | HYB Essential Defueling Safety Case | Approve Task Sheet for Judgement Based Work Diversion EAN | 2022-01-21 | 2022-01-21 | 7 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.5700 | TOR Essential Defueling Safety Case | Approve Task Sheet for Judgement Based Work Diversion EAN | 2022-01-21 | 2022-01-21 | 7 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.4670 | HYB Essential Defueling Safety Case | Issue RFS (A-B Phase) | 2022-01-21 | 2022-01-21 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.4670 | TOR Essential Defueling Safety Case | Issue RFS (A-B Phase) | 2022-01-21 | 2022-01-21 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.3590 | HYB Essential Defueling Safety Case | TSA/EDF Best Athlete Review | 2022-01-24 | 2022-02-17 | 10 | 0 | 18 | 24 | 100% | 0.41667 | 1 | Completed
ER6666LT | W209 | W209.4720 | HYB Essential Defueling Safety Case | Defueling Safety Case Team Review | 2022-01-24 | 2022-03-01 | 10 | 0 | 27 | 36 | 100% | 0.27778 | 1 | Completed
ER6666LT | W209 | W209.6600 | HYB Essential Defueling Safety Case | Approve Task Sheet for Radiological Consequences Following Failed CSP EAN | 2022-01-24 | 2022-02-04 | 7 | 0 | 9 | 11 | 100% | 0.63636 | 1 | Completed
ER6668LT | W213 | W213.3590 | TOR Essential Defueling Safety Case | TSA/EDF Best Athlete Review | 2022-01-24 | 2022-02-17 | 10 | 0 | 18 | 24 | 100% | 0.41667 | 1 | Completed
ER6668LT | W213 | W213.4720 | TOR Essential Defueling Safety Case | Defueling Safety Case Team Review | 2022-01-24 | 2022-03-01 | 10 | 0 | 27 | 36 | 100% | 0.27778 | 1 | Completed
ER6668LT | W213 | W213.6600 | TOR Essential Defueling Safety Case | Approve Task Sheet for Radiological Consequences Following Failed CSP EAN | 2022-01-24 | 2022-02-04 | 7 | 0 | 9 | 11 | 100% | 0.63636 | 1 | Completed
ER6666LT | W209 | W209.4680 | HYB Essential Defueling Safety Case | Supplier Respond to RFS (A-B Phase) | 2022-01-24 | 2022-02-07 | 15 | 0 | 10 | 14 | 100% | 1.0714 | 1 | Completed
ER6668LT | W213 | W213.4680 | TOR Essential Defueling Safety Case | Supplier Respond to RFS (A-B Phase) | 2022-01-24 | 2022-02-07 | 15 | 0 | 10 | 14 | 100% | 1.0714 | 1 | Completed
ER6666LT | W209 | W209.5210 | HYB Essential Defueling Safety Case | De-Risking Scope - Consequences Assessment - (Cost Summary) ## | 2022-01-31 | 2022-05-06 | 26 | 0 | 66 | 95 | 100% | 0.27368 | 1 | Completed
ER6668LT | W213 | W213.5210 | TOR Essential Defueling Safety Case | De-Risking Scope - Consequences Assessment - (Cost Summary) ## | 2022-01-31 | 2022-05-06 | 26 | 0 | 66 | 95 | 100% | 0.27368 | 1 | Completed
ER6666LT | W209 | W209.1140 | HYB Essential Defueling Safety Case | Add Data to IAB Paper | 2022-01-31 | 2022-02-01 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6666LT | W209 | W209.3410 | HYB Essential Defueling Safety Case | Dropped FPU Scoping Workshop | 2022-01-31 | 2022-01-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1140 | TOR Essential Defueling Safety Case | Add Data to IAB Paper | 2022-01-31 | 2022-02-01 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6668LT | W213 | W213.3410 | TOR Essential Defueling Safety Case | Dropped FPU Scoping Workshop | 2022-01-31 | 2022-01-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.3430 | HYB Essential Defueling Safety Case | Develop Dropped FPU Substantiation De-risking scope | 2022-02-01 | 2022-04-20 | 10 | 0 | 55 | 78 | 100% | 0.12821 | 1 | Completed
ER6666LT | W209 | W209.3830 | HYB Essential Defueling Safety Case | Specify Seismic Assessment Scope for Delivery | 2022-02-01 | 2022-03-16 | 10 | 0 | 31 | 43 | 100% | 0.23256 | 1 | Completed
ER6668LT | W213 | W213.3430 | TOR Essential Defueling Safety Case | Develop Dropped FPU Substantiation De-risking scope | 2022-02-01 | 2022-04-20 | 10 | 0 | 55 | 78 | 100% | 0.12821 | 1 | Completed
ER6668LT | W213 | W213.3830 | TOR Essential Defueling Safety Case | Specify Seismic Assessment Scope for Delivery | 2022-02-01 | 2022-03-16 | 10 | 0 | 31 | 43 | 100% | 0.23256 | 1 | Completed
ER6666LT | W209 | W209.3780 | HYB Essential Defueling Safety Case | Specify PCPV Integrity Justification Scope for Delivery | 2022-02-01 | 2022-03-16 | 10 | 0 | 31 | 43 | 100% | 0.23256 | 1 | Completed
ER6668LT | W213 | W213.3780 | TOR Essential Defueling Safety Case | Specify PCPV Integrity Justification Scope for Delivery | 2022-02-01 | 2022-03-16 | 10 | 0 | 31 | 43 | 100% | 0.23256 | 1 | Completed
ER6666LT | W209 | W209.1150 | HYB Essential Defueling Safety Case | PCL Validate & Approve Baseline Package for PRC Submission | 2022-02-02 | 2022-02-08 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.4470 | HYB Essential Defueling Safety Case | Pre PSRG to Review and Approve Defueling Assumptions List | 2022-02-02 | 2022-03-01 | 5 | 0 | 20 | 27 | 100% | 0.18519 | 1 | Completed
ER6666LT | W209 | W209.5070 | HYB Essential Defueling Safety Case | Formal Pre Job Brief | 2022-02-02 | 2022-02-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1150 | TOR Essential Defueling Safety Case | PCL Validate & Approve Baseline Package for PRC Submission | 2022-02-02 | 2022-02-08 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.4470 | TOR Essential Defueling Safety Case | Pre PSRG to Review and Approve Defueling Assumptions List | 2022-02-02 | 2022-03-01 | 5 | 0 | 20 | 27 | 100% | 0.18519 | 1 | Completed
ER6668LT | W213 | W213.5070 | TOR Essential Defueling Safety Case | Formal Pre Job Brief | 2022-02-02 | 2022-02-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.5080 | HYB Essential Defueling Safety Case | Issue of QA Grade 4 Skeleton Document | 2022-02-03 | 2022-03-02 | 18 | 0 | 20 | 27 | 100% | 0.66667 | 1 | Completed
ER6668LT | W213 | W213.5080 | TOR Essential Defueling Safety Case | Issue of QA Grade 4 Skeleton Document | 2022-02-03 | 2022-03-02 | 18 | 0 | 20 | 27 | 100% | 0.66667 | 1 | Completed
ER6666LT | W209 | W209.3310 | HYB Essential Defueling Safety Case | PJB Workshop Attendees | 2022-02-04 | 2022-02-04 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.3310 | TOR Essential Defueling Safety Case | PJB Workshop Attendees | 2022-02-04 | 2022-02-04 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.3300 | HYB Essential Defueling Safety Case | Release Draft Optioneering Report for Workshop | 2022-02-04 | 2022-02-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.3300 | TOR Essential Defueling Safety Case | Release Draft Optioneering Report for Workshop | 2022-02-04 | 2022-02-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A25700 | HYB Essential Defueling Safety Case | Pre Job Brief for Judgement Based Work Diversion EAN | 2022-02-07 | 2022-02-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A28580 | HYB Essential Defueling Safety Case | Pre Job Brief for Radiological Consequences Following Failed CSP EAN | 2022-02-07 | 2022-02-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A25700 | TOR Essential Defueling Safety Case | Pre Job Brief for Judgement Based Work Diversion EAN | 2022-02-07 | 2022-02-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A28580 | TOR Essential Defueling Safety Case | Pre Job Brief for Radiological Consequences Following Failed CSP EAN | 2022-02-07 | 2022-02-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.4700 | HYB Essential Defueling Safety Case | Undertake Analysis (A-B Phase) | 2022-02-08 | 2022-07-01 | 69 | 0 | 99 | 143 | 100% | 0.48252 | 1 | Completed
ER6666LT | W209 | W209.A25710 | HYB Essential Defueling Safety Case | Draft Judgement Based Work Diversion EAN | 2022-02-08 | 2022-07-01 | 30 | 0 | 99 | 143 | 100% | 0.20979 | 1 | Completed
ER6666LT | W209 | W209.A28590 | HYB Essential Defueling Safety Case | Draft Radiological Consequences Following Failed CSP EAN | 2022-02-08 | 2022-07-01 | 30 | 0 | 99 | 143 | 100% | 0.20979 | 1 | Completed
ER6668LT | W213 | W213.4700 | TOR Essential Defueling Safety Case | Undertake Analysis (A-B Phase) | 2022-02-08 | 2022-07-01 | 69 | 0 | 99 | 143 | 100% | 0.48252 | 1 | Completed
ER6668LT | W213 | W213.A25710 | TOR Essential Defueling Safety Case | Draft Judgement Based Work Diversion EAN | 2022-02-08 | 2022-07-01 | 30 | 0 | 99 | 143 | 100% | 0.20979 | 1 | Completed
ER6668LT | W213 | W213.A28590 | TOR Essential Defueling Safety Case | Draft Radiological Consequences Following Failed CSP EAN | 2022-02-08 | 2022-07-01 | 30 | 0 | 99 | 143 | 100% | 0.20979 | 1 | Completed
ER6666LT | W209 | W209.1160 | HYB Essential Defueling Safety Case | Gate A PRC Paper Submission | 2022-02-09 | 2022-02-09 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1160 | TOR Essential Defueling Safety Case | Gate A PRC Paper Submission | 2022-02-09 | 2022-02-09 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.3320 | HYB Essential Defueling Safety Case | Hold Optioneering Workshop | 2022-02-10 | 2022-02-10 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.4150 | HYB Essential Defueling Safety Case | HF Workstream - (Cost Summary) ## | 2022-02-10 | 2022-07-13 | 106 | 0 | 105 | 153 | 100% | 0.69281 | 1 | Completed
ER6666LT | W209 | W209.5200 | HYB Essential Defueling Safety Case | Attend Defueling Order Optioneering Workshop | 2022-02-10 | 2022-02-10 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.3320 | TOR Essential Defueling Safety Case | Hold Optioneering Workshop | 2022-02-10 | 2022-02-10 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.4150 | TOR Essential Defueling Safety Case | HF Workstream - (Cost Summary) ## | 2022-02-10 | 2022-07-13 | 106 | 0 | 105 | 153 | 100% | 0.69281 | 1 | Completed
ER6668LT | W213 | W213.5200 | TOR Essential Defueling Safety Case | Attend Defueling Order Optioneering Workshop | 2022-02-10 | 2022-02-10 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1170 | HYB Essential Defueling Safety Case | PRC Members Review IAB Documentation | 2022-02-10 | 2022-02-16 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.1170 | TOR Essential Defueling Safety Case | PRC Members Review IAB Documentation | 2022-02-10 | 2022-02-16 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.3330 | HYB Essential Defueling Safety Case | Update Report Post Workshop | 2022-02-11 | 2022-02-24 | 10 | 0 | 9 | 13 | 100% | 0.76923 | 1 | Completed
ER6666LT | W209 | W209.3350 | HYB Essential Defueling Safety Case | Define Case Production Scope (RFS) | 2022-02-11 | 2022-02-24 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6666LT | W209 | W209.4110 | HYB Essential Defueling Safety Case | Review Existing Documentation | 2022-02-11 | 2022-04-01 | 5 | 0 | 36 | 49 | 100% | 0.10204 | 1 | Completed
ER6668LT | W213 | W213.3330 | TOR Essential Defueling Safety Case | Update Report Post Workshop | 2022-02-11 | 2022-02-24 | 10 | 0 | 9 | 13 | 100% | 0.76923 | 1 | Completed
ER6668LT | W213 | W213.3350 | TOR Essential Defueling Safety Case | Define Case Production Scope (RFS) | 2022-02-11 | 2022-02-24 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6668LT | W213 | W213.4110 | TOR Essential Defueling Safety Case | Review Existing Documentation | 2022-02-11 | 2022-04-01 | 5 | 0 | 36 | 49 | 100% | 0.10204 | 1 | Completed
ER6666LT | W209 | W209.3910 | HYB Essential Defueling Safety Case | Release and Respond to Comments | 2022-02-14 | 2022-02-18 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6668LT | W213 | W213.3910 | TOR Essential Defueling Safety Case | Release and Respond to Comments | 2022-02-14 | 2022-02-18 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6666LT | W209 | W209.5010 | HYB Essential Defueling Safety Case | HOLD POINT 1 - Nuclear Safety Issues Identified | 2022-02-15 | 2022-02-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.5010 | TOR Essential Defueling Safety Case | HOLD POINT 1 - Nuclear Safety Issues Identified | 2022-02-15 | 2022-02-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.3680 | HYB Essential Defueling Safety Case | Specify Flow Induced Vibration EAN Scope for Delivery | 2022-02-15 | 2022-03-01 | 10 | 0 | 11 | 14 | 100% | 0.71429 | 1 | Completed
ER6668LT | W213 | W213.3680 | TOR Essential Defueling Safety Case | Specify Flow Induced Vibration EAN Scope for Delivery | 2022-02-15 | 2022-03-01 | 10 | 0 | 11 | 14 | 100% | 0.71429 | 1 | Completed
ER6666LT | W209 | W209.5060 | HYB Essential Defueling Safety Case | Review Legacy Assessments & Determine Future Assessments Required | 2022-02-16 | 2022-04-01 | 43 | 0 | 32 | 44 | 100% | 0.97727 | 1 | Completed
ER6370LT | W201 | W201.1570 | HNB Reactors Shutdown Essential Safety Cases | Cat 1 Proposal Updates Authoring | 2022-02-16 | 2022-02-25 | 0 | 0 | 7 | 9 | 100% | 0 | 1 | Completed
ER6668LT | W213 | W213.5060 | TOR Essential Defueling Safety Case | Review Legacy Assessments & Determine Future Assessments Required | 2022-02-16 | 2022-04-01 | 43 | 0 | 32 | 44 | 100% | 0.97727 | 1 | Completed
ER6650LT | W226 | W226.A24320 | HYA Fuel Handling Essential Safety Case | Technical Review of Living Safety Document EAN | 2022-02-18 | 2024-03-25 | 3 | 0 | 528 | 766 | 100% | 0.0039164 | 1 | Completed
ER6378LT | W222 | W222.A24320 | HRA Fuel Handling Essential Safety Case | Technical Review of Living Safety Document EAN | 2022-02-18 | 2024-03-25 | 3 | 0 | 528 | 766 | 100% | 0.0039164 | 1 | Completed
ER6666LT | W209 | W209.5860 | HYB Essential Defueling Safety Case | Prepare Spec for Pressure Boundary Integrity of Seals Report EAN | 2022-02-21 | 2022-02-25 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6666LT | W209 | W209.6850 | HYB Essential Defueling Safety Case | Prepare Spec for Reactor Pressure Boundary Seals Integrity (Tech Report) | 2022-02-21 | 2022-02-25 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6668LT | W213 | W213.5860 | TOR Essential Defueling Safety Case | Prepare Spec for Pressure Boundary Integrity of Seals Report EAN | 2022-02-21 | 2022-02-25 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6668LT | W213 | W213.6850 | TOR Essential Defueling Safety Case | Prepare Spec for Reactor Pressure Boundary Seals Integrity (Tech Report) | 2022-02-21 | 2022-02-25 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6666LT | W209 | W209.5220 | HYB Essential Defueling Safety Case | Generate Schedule of Seals Tasksheet | 2022-02-21 | 2022-03-03 | 9 | 0 | 9 | 10 | 100% | 0.9 | 1 | Completed
ER6668LT | W213 | W213.5220 | TOR Essential Defueling Safety Case | Generate Schedule of Seals Tasksheet | 2022-02-21 | 2022-03-03 | 9 | 0 | 9 | 10 | 100% | 0.9 | 1 | Completed
ER6666LT | W209 | W209.1056 | HYB Essential Defueling Safety Case | Gate A - PRC Paper Approval (HYB) | 2022-02-22 | 2022-02-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1056 | TOR Essential Defueling Safety Case | Gate A - PRC Paper Approval (TOR) | 2022-02-22 | 2022-02-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1180 | HYB Essential Defueling Safety Case | Hold PRC Meeting | 2022-02-22 | 2022-02-22 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1180 | TOR Essential Defueling Safety Case | Hold PRC Meeting | 2022-02-22 | 2022-02-22 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1190 | HYB Essential Defueling Safety Case | Gate A PRC Paper Approval | 2022-02-22 | 2022-02-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1190 | TOR Essential Defueling Safety Case | Gate A PRC Paper Approval | 2022-02-22 | 2022-02-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1210 | HYB Essential Defueling Safety Case | Modify PRC Paper as Required | 2022-02-23 | 2022-02-23 | 22 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1200 | HYB Essential Defueling Safety Case | Modify Estimate, Schedule & Risk Log as Required | 2022-02-23 | 2022-02-23 | 22 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.3930 | HYB Essential Defueling Safety Case | PJB (All Attendees) | 2022-02-23 | 2022-02-23 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.5320 | HYB Essential Defueling Safety Case | Pre-Job Brief of Previous Lessons Learned (DNB) | 2022-02-23 | 2022-03-01 | 1 | 0 | 5 | 6 | 100% | 0.16667 | 1 | Completed
ER6668LT | W213 | W213.1210 | TOR Essential Defueling Safety Case | Modify PRC Paper as Required | 2022-02-23 | 2022-02-23 | 22 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1200 | TOR Essential Defueling Safety Case | Modify Estimate, Schedule & Risk Log as Required | 2022-02-23 | 2022-02-23 | 22 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.3930 | TOR Essential Defueling Safety Case | PJB (All Attendees) | 2022-02-23 | 2022-02-23 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.5320 | TOR Essential Defueling Safety Case | Pre-Job Brief of Previous Lessons Learned (DNB) | 2022-02-23 | 2022-03-01 | 1 | 0 | 5 | 6 | 100% | 0.16667 | 1 | Completed
ER6666LT | W209 | W209.3340 | HYB Essential Defueling Safety Case | Verify Report Post Workshop | 2022-02-25 | 2022-05-03 | 10 | 0 | 45 | 67 | 100% | 0.14925 | 1 | Completed
ER6370LT | W201 | W201.1580 | HNB Reactors Shutdown Essential Safety Cases | AMS Milestone - Ready for Review | 2022-02-25 | 2022-02-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.3340 | TOR Essential Defueling Safety Case | Verify Report Post Workshop | 2022-02-25 | 2022-05-03 | 10 | 0 | 45 | 67 | 100% | 0.14925 | 1 | Completed
ER6666LT | W209 | W209.4160 | HYB Essential Defueling Safety Case | Approve & Issue RFS / Task Sheet | 2022-02-25 | 2022-03-08 | 10 | 0 | 8 | 11 | 100% | 0.90909 | 1 | Completed
ER6668LT | W213 | W213.4160 | TOR Essential Defueling Safety Case | Approve & Issue RFS / Task Sheet | 2022-02-25 | 2022-03-08 | 10 | 0 | 8 | 11 | 100% | 0.90909 | 1 | Completed
ER6666LT | W209 | W209.5870 | HYB Essential Defueling Safety Case | Prepare Task Sheet for Pressure Boundary Integrity of Seals Report EAN | 2022-02-28 | 2022-03-03 | 10 | 0 | 3 | 3 | 100% | 3.3333 | 1 | Completed
ER6666LT | W209 | W209.6860 | HYB Essential Defueling Safety Case | Prepare Task Sheet for Reactor Pressure Boundary Seals Integrity (Tech Report) | 2022-02-28 | 2022-03-03 | 10 | 0 | 3 | 3 | 100% | 3.3333 | 1 | Completed
ER6370LT | W201 | W201.1590 | HNB Reactors Shutdown Essential Safety Cases | Verification (Lead Verifier) | 2022-02-28 | 2022-03-14 | 1 | 0 | 10 | 14 | 100% | 0.071429 | 1 | Completed
ER6668LT | W213 | W213.5870 | TOR Essential Defueling Safety Case | Prepare Task Sheet for Pressure Boundary Integrity of Seals Report EAN | 2022-02-28 | 2022-03-03 | 10 | 0 | 3 | 3 | 100% | 3.3333 | 1 | Completed
ER6668LT | W213 | W213.6860 | TOR Essential Defueling Safety Case | Prepare Task Sheet for Reactor Pressure Boundary Seals Integrity (Tech Report) | 2022-02-28 | 2022-03-03 | 10 | 0 | 3 | 3 | 100% | 3.3333 | 1 | Completed
ER6666LT | W209 | W209.4180 | HYB Essential Defueling Safety Case | Supplier Generates Task Sheet | 2022-03-01 | 2022-04-22 | 10 | 0 | 36 | 52 | 100% | 0.19231 | 1 | Completed
ER6666LT | W209 | W209.5170 | HYB Essential Defueling Safety Case | Defuelling Order / Fuel Management - De-risking scope - (Cost Summary) ## | 2022-03-01 | 2022-07-13 | 69 | 0 | 92 | 134 | 100% | 0.51493 | 1 | Completed
ER6666LT | W209 | W209.5560 | HYB Essential Defueling Safety Case | Prepare Spec for Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 2022-03-01 | 2022-03-15 | 5 | 0 | 10 | 14 | 100% | 0.35714 | 1 | Completed
ER6666LT | W209 | W209.5590 | HYB Essential Defueling Safety Case | Prepare Spec for Review of flux detector suitability EAN | 2022-03-01 | 2022-03-15 | 5 | 0 | 10 | 14 | 100% | 0.35714 | 1 | Completed
ER6666LT | W209 | W209.5620 | HYB Essential Defueling Safety Case | Prepare Spec for Boron Bead Injection Feasibility & Control Rod Isolation EAN | 2022-03-01 | 2022-03-15 | 5 | 0 | 10 | 14 | 100% | 0.35714 | 1 | Completed
ER6666LT | W209 | W209.8290 | HYB Essential Defueling Safety Case | Prepare Spec for FPU Maintenance Analysis EAN | 2022-03-01 | 2022-03-04 | 5 | 0 | 3 | 3 | 100% | 1.6667 | 1 | Completed
ER6666LT | W209 | W209.8480 | HYB Essential Defueling Safety Case | Prepare Spec for Define Nuclear Data (PANTHER Validation Calcs) EAN | 2022-03-01 | 2022-03-15 | 5 | 0 | 10 | 14 | 100% | 0.35714 | 1 | Completed
ER6666LT | W209 | W209.8520 | HYB Essential Defueling Safety Case | Prepare Spec for PANTHER SCM Assessments - Agree Defuelling Order | 2022-03-01 | 2022-03-15 | 5 | 0 | 10 | 14 | 100% | 0.35714 | 1 | Completed
ER6668LT | W213 | W213.4180 | TOR Essential Defueling Safety Case | Supplier Generates Task Sheet | 2022-03-01 | 2022-04-22 | 10 | 0 | 36 | 52 | 100% | 0.19231 | 1 | Completed
ER6668LT | W213 | W213.5170 | TOR Essential Defueling Safety Case | Defuelling Order / Fuel Management - De-risking scope - (Cost Summary) ## | 2022-03-01 | 2022-07-13 | 69 | 0 | 92 | 134 | 100% | 0.51493 | 1 | Completed
ER6668LT | W213 | W213.5560 | TOR Essential Defueling Safety Case | Prepare Spec for Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 2022-03-01 | 2022-03-15 | 5 | 0 | 10 | 14 | 100% | 0.35714 | 1 | Completed
ER6668LT | W213 | W213.5590 | TOR Essential Defueling Safety Case | Prepare Spec for Review of flux detector suitability EAN | 2022-03-01 | 2022-03-15 | 5 | 0 | 10 | 14 | 100% | 0.35714 | 1 | Completed
ER6668LT | W213 | W213.5620 | TOR Essential Defueling Safety Case | Prepare Spec for Boron Bead Injection Feasibility & Control Rod Isolation EAN | 2022-03-01 | 2022-03-15 | 5 | 0 | 10 | 14 | 100% | 0.35714 | 1 | Completed
ER6668LT | W213 | W213.8290 | TOR Essential Defueling Safety Case | Prepare Spec for FPU Maintenance Analysis EAN | 2022-03-01 | 2022-03-04 | 5 | 0 | 3 | 3 | 100% | 1.6667 | 1 | Completed
ER6668LT | W213 | W213.8480 | TOR Essential Defueling Safety Case | Prepare Spec for Define Nuclear Data (PANTHER Validation Calcs) EAN | 2022-03-01 | 2022-03-15 | 5 | 0 | 10 | 14 | 100% | 0.35714 | 1 | Completed
ER6668LT | W213 | W213.8520 | TOR Essential Defueling Safety Case | Prepare Spec for PANTHER SCM Assessments - Agree Defuelling Order | 2022-03-01 | 2022-03-15 | 5 | 0 | 10 | 14 | 100% | 0.35714 | 1 | Completed
ER6666LT | W209 | W209.4370 | HYB Essential Defueling Safety Case | Generate Review of Protection Systems EANTask Sheet | 2022-03-01 | 2022-03-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.5340 | HYB Essential Defueling Safety Case | Pre-Job Brief of Previous Lessons Learned (HNB HPB) | 2022-03-01 | 2022-04-27 | 21 | 0 | 39 | 57 | 100% | 0.36842 | 1 | Completed
ER6666LT | W209 | W209.5350 | HYB Essential Defueling Safety Case | Pre-Job Brief of Previous Lessons Learned (HRA HYA) | 2022-03-01 | 2022-04-27 | 21 | 0 | 39 | 57 | 100% | 0.36842 | 1 | Completed
ER6668LT | W213 | W213.4370 | TOR Essential Defueling Safety Case | Generate Review of Protection Systems EANTask Sheet | 2022-03-01 | 2022-03-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.5340 | TOR Essential Defueling Safety Case | Pre-Job Brief of Previous Lessons Learned (HNB HPB) | 2022-03-01 | 2022-04-27 | 21 | 0 | 39 | 57 | 100% | 0.36842 | 1 | Completed
ER6668LT | W213 | W213.5350 | TOR Essential Defueling Safety Case | Pre-Job Brief of Previous Lessons Learned (HRA HYA) | 2022-03-01 | 2022-04-27 | 21 | 0 | 39 | 57 | 100% | 0.36842 | 1 | Completed
ER6666LT | W209 | W209.4740 | HYB Essential Defueling Safety Case | Draft Summary Findings EAN | 2022-03-02 | 2022-03-02 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | W201.1680 | HNB Reactors Shutdown Essential Safety Cases | March NSC MA deadline on 2 March | 2022-03-02 | 2022-03-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.4740 | TOR Essential Defueling Safety Case | Draft Summary Findings EAN | 2022-03-02 | 2022-03-02 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.3690 | HYB Essential Defueling Safety Case | TSA/EDF Best Athlete Review for Flow Induced Vibration EAN | 2022-03-02 | 2022-03-15 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6666LT | W209 | W209.3940 | HYB Essential Defueling Safety Case | Optioneering Workshop | 2022-03-02 | 2022-03-03 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6666LT | W209 | W209.4350 | HYB Essential Defueling Safety Case | Technical Review | 2022-03-02 | 2022-03-15 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6666LT | W209 | W209.4480 | HYB Essential Defueling Safety Case | Incorporate Defueling Assumptions List into PDD | 2022-03-02 | 2022-03-04 | 5 | 0 | 2 | 2 | 100% | 2.5 | 1 | Completed
ER6668LT | W213 | W213.3690 | TOR Essential Defueling Safety Case | TSA/EDF Best Athlete Review for Flow Induced Vibration EAN | 2022-03-02 | 2022-03-15 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6668LT | W213 | W213.3940 | TOR Essential Defueling Safety Case | Optioneering Workshop | 2022-03-02 | 2022-03-03 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6668LT | W213 | W213.4350 | TOR Essential Defueling Safety Case | Technical Review | 2022-03-02 | 2022-03-15 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6668LT | W213 | W213.4480 | TOR Essential Defueling Safety Case | Incorporate Defueling Assumptions List into PDD | 2022-03-02 | 2022-03-04 | 5 | 0 | 2 | 2 | 100% | 2.5 | 1 | Completed
ER6666LT | W209 | W209.4750 | HYB Essential Defueling Safety Case | Verify EAN | 2022-03-03 | 2022-04-26 | 10 | 0 | 36 | 54 | 100% | 0.18519 | 1 | Completed
ER6668LT | W213 | W213.4750 | TOR Essential Defueling Safety Case | Verify EAN | 2022-03-03 | 2022-04-26 | 10 | 0 | 36 | 54 | 100% | 0.18519 | 1 | Completed
ER6666LT | W209 | W209.5090 | HYB Essential Defueling Safety Case | Recieve EDF Comments on Skeleton Document | 2022-03-03 | 2022-03-07 | 10 | 0 | 3 | 4 | 100% | 2.5 | 1 | Completed
ER6668LT | W213 | W213.5090 | TOR Essential Defueling Safety Case | Recieve EDF Comments on Skeleton Document | 2022-03-03 | 2022-03-07 | 10 | 0 | 3 | 4 | 100% | 2.5 | 1 | Completed
ER6666LT | W209 | W209.3250 | HYB Essential Defueling Safety Case | >>>OUTGOING ENABLER (W150) Assumption List Complete (within PDD) | 2022-03-04 | 2022-03-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.5880 | HYB Essential Defueling Safety Case | Approve Task Sheet for Pressure Boundary Integrity of Seals Report EAN | 2022-03-04 | 2022-03-17 | 7 | 0 | 9 | 13 | 100% | 0.53846 | 1 | Completed
ER6666LT | W209 | W209.6870 | HYB Essential Defueling Safety Case | Approve Task Sheet for Reactor Pressure Boundary Seals Integrity (Tech Report) | 2022-03-04 | 2022-03-17 | 7 | 0 | 9 | 13 | 100% | 0.53846 | 1 | Completed
ER6668LT | W213 | W213.3250 | TOR Essential Defueling Safety Case | >>>OUTGOING ENABLER (W150) Assumption List Complete (within PDD) | 2022-03-04 | 2022-03-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.5880 | TOR Essential Defueling Safety Case | Approve Task Sheet for Pressure Boundary Integrity of Seals Report EAN | 2022-03-04 | 2022-03-17 | 7 | 0 | 9 | 13 | 100% | 0.53846 | 1 | Completed
ER6668LT | W213 | W213.6870 | TOR Essential Defueling Safety Case | Approve Task Sheet for Reactor Pressure Boundary Seals Integrity (Tech Report) | 2022-03-04 | 2022-03-17 | 7 | 0 | 9 | 13 | 100% | 0.53846 | 1 | Completed
ER6666LT | W209 | W209.3950 | HYB Essential Defueling Safety Case | Update Report Post Workshop | 2022-03-04 | 2022-03-22 | 5 | 0 | 12 | 18 | 100% | 0.27778 | 1 | Completed
ER6666LT | W209 | W209.5230 | HYB Essential Defueling Safety Case | PJB & Generate Schedule of Seals | 2022-03-04 | 2022-04-28 | 10 | 0 | 37 | 55 | 100% | 0.18182 | 1 | Completed
ER6668LT | W213 | W213.3950 | TOR Essential Defueling Safety Case | Update Report Post Workshop | 2022-03-04 | 2022-03-22 | 5 | 0 | 12 | 18 | 100% | 0.27778 | 1 | Completed
ER6668LT | W213 | W213.5230 | TOR Essential Defueling Safety Case | PJB & Generate Schedule of Seals | 2022-03-04 | 2022-04-28 | 10 | 0 | 37 | 55 | 100% | 0.18182 | 1 | Completed
ER6666LT | W209 | W209.7580 | HYB Essential Defueling Safety Case | PJB for Review of Protection Systems EAN | 2022-03-07 | 2022-03-07 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.8300 | HYB Essential Defueling Safety Case | Prepare Task Sheet for FPU Maintenance Analysis EAN | 2022-03-07 | 2022-03-11 | 10 | 0 | 4 | 4 | 100% | 2.5 | 1 | Completed
ER6668LT | W213 | W213.7580 | TOR Essential Defueling Safety Case | PJB for Review of Protection Systems EAN | 2022-03-07 | 2022-03-07 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.8300 | TOR Essential Defueling Safety Case | Prepare Task Sheet for FPU Maintenance Analysis EAN | 2022-03-07 | 2022-03-11 | 10 | 0 | 4 | 4 | 100% | 2.5 | 1 | Completed
ER6666LT | W209 | W209.7590 | HYB Essential Defueling Safety Case | Issue FM Load Protection EAN | 2022-03-08 | 2022-05-17 | 1 | 0 | 48 | 70 | 100% | 0.014286 | 1 | Completed
ER6668LT | W213 | W213.7590 | TOR Essential Defueling Safety Case | Issue FM Load Protection EAN | 2022-03-08 | 2022-05-17 | 1 | 0 | 48 | 70 | 100% | 0.014286 | 1 | Completed
ER6666LT | W209 | W209.5100 | HYB Essential Defueling Safety Case | Meeting to Discuss Skeleton Document & Recommendations | 2022-03-08 | 2022-03-11 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6668LT | W213 | W213.5100 | TOR Essential Defueling Safety Case | Meeting to Discuss Skeleton Document & Recommendations | 2022-03-08 | 2022-03-11 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6666LT | W209 | W209.4170 | HYB Essential Defueling Safety Case | RFS Issued | 2022-03-08 | 2022-03-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.4170 | TOR Essential Defueling Safety Case | RFS Issued | 2022-03-08 | 2022-03-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | W201.1600 | HNB Reactors Shutdown Essential Safety Cases | Nuclear Safety Specialist Assessment HNB | 2022-03-12 | 2022-03-14 | 1 | 0 | 0 | 2 | 100% | 0.5 | 1 | Completed
ER6370LT | W201 | W201.1610 | HNB Reactors Shutdown Essential Safety Cases | Nuclear Safety Specialist Assessment HPB | 2022-03-12 | 2022-03-14 | 1 | 0 | 0 | 2 | 100% | 0.5 | 1 | Completed
ER6666LT | W209 | W209.7520 | HYB Essential Defueling Safety Case | Prepare Spec for Cooling Plant Availability Review EAN | 2022-03-14 | 2022-04-01 | 5 | 0 | 15 | 18 | 100% | 0.27778 | 1 | Completed
ER6666LT | W209 | W209.7550 | HYB Essential Defueling Safety Case | Prepare Spec for Cooling Plant OPEX Study EAN | 2022-03-14 | 2022-04-01 | 5 | 0 | 15 | 18 | 100% | 0.27778 | 1 | Completed
ER6370LT | W201 | W201.1620 | HNB Reactors Shutdown Essential Safety Cases | CO Endorsed | 2022-03-14 | 2022-03-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | W201.1630 | HNB Reactors Shutdown Essential Safety Cases | Stn RE Endorsed | 2022-03-14 | 2022-03-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | W201.1640 | HNB Reactors Shutdown Essential Safety Cases | Lead INA assessor | 2022-03-14 | 2022-04-27 | 20 | 0 | 30 | 44 | 100% | 0.45455 | 1 | Completed
ER6666LT | W209 | W209.8310 | HYB Essential Defueling Safety Case | Approve Task Sheet for FPU Maintenance Analysis EAN | 2022-03-14 | 2022-03-28 | 7 | 0 | 10 | 14 | 100% | 0.5 | 1 | Completed
ER6668LT | W213 | W213.7520 | TOR Essential Defueling Safety Case | Prepare Spec for Cooling Plant Availability Review EAN | 2022-03-14 | 2022-04-01 | 5 | 0 | 15 | 18 | 100% | 0.27778 | 1 | Completed
ER6668LT | W213 | W213.7550 | TOR Essential Defueling Safety Case | Prepare Spec for Cooling Plant OPEX Study EAN | 2022-03-14 | 2022-04-01 | 5 | 0 | 15 | 18 | 100% | 0.27778 | 1 | Completed
ER6668LT | W213 | W213.8310 | TOR Essential Defueling Safety Case | Approve Task Sheet for FPU Maintenance Analysis EAN | 2022-03-14 | 2022-03-28 | 7 | 0 | 10 | 14 | 100% | 0.5 | 1 | Completed
ER6666LT | W209 | W209.5110 | HYB Essential Defueling Safety Case | Generate Integrity Analysis Task Sheet (Atkins) | 2022-03-14 | 2022-03-23 | 5 | 0 | 7 | 9 | 100% | 0.55556 | 1 | Completed
ER6668LT | W213 | W213.5110 | TOR Essential Defueling Safety Case | Generate Integrity Analysis Task Sheet (Atkins) | 2022-03-14 | 2022-03-23 | 5 | 0 | 7 | 9 | 100% | 0.55556 | 1 | Completed
ER6666LT | W209 | W209.4400 | HYB Essential Defueling Safety Case | Draft Scope for Case Production | 2022-03-16 | 2022-04-01 | 10 | 0 | 12 | 16 | 100% | 0.625 | 1 | Completed
ER6666LT | W209 | W209.5570 | HYB Essential Defueling Safety Case | Prepare Task Sheet for Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 2022-03-16 | 2022-03-28 | 10 | 0 | 8 | 12 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.5600 | HYB Essential Defueling Safety Case | Prepare Task Sheet for Review of flux detector suitability EAN | 2022-03-16 | 2022-03-28 | 10 | 0 | 8 | 12 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.5630 | HYB Essential Defueling Safety Case | Prepare Task Sheet for Boron Bead Injection Feasibility & Control Rod Isolation EAN | 2022-03-16 | 2022-03-28 | 10 | 0 | 8 | 12 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.7670 | HYB Essential Defueling Safety Case | Prepare Spec for Flow Induced Vibration EAN | 2022-03-16 | 2022-03-16 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.8490 | HYB Essential Defueling Safety Case | Prepare Task Sheet for Define Nuclear Data (PANTHER Validation Calcs) EAN | 2022-03-16 | 2022-03-28 | 10 | 0 | 8 | 12 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.8530 | HYB Essential Defueling Safety Case | Prepare Task Sheet for PANTHER SCM Assessments - Agree Defuelling Order | 2022-03-16 | 2022-03-28 | 10 | 0 | 8 | 12 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.4400 | TOR Essential Defueling Safety Case | Draft Scope for Case Production | 2022-03-16 | 2022-04-01 | 10 | 0 | 12 | 16 | 100% | 0.625 | 1 | Completed
ER6668LT | W213 | W213.5570 | TOR Essential Defueling Safety Case | Prepare Task Sheet for Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 2022-03-16 | 2022-03-28 | 10 | 0 | 8 | 12 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.5600 | TOR Essential Defueling Safety Case | Prepare Task Sheet for Review of flux detector suitability EAN | 2022-03-16 | 2022-03-28 | 10 | 0 | 8 | 12 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.5630 | TOR Essential Defueling Safety Case | Prepare Task Sheet for Boron Bead Injection Feasibility & Control Rod Isolation EAN | 2022-03-16 | 2022-03-28 | 10 | 0 | 8 | 12 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.7670 | TOR Essential Defueling Safety Case | Prepare Spec for Flow Induced Vibration EAN | 2022-03-16 | 2022-03-16 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.8490 | TOR Essential Defueling Safety Case | Prepare Task Sheet for Define Nuclear Data (PANTHER Validation Calcs) EAN | 2022-03-16 | 2022-03-28 | 10 | 0 | 8 | 12 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.8530 | TOR Essential Defueling Safety Case | Prepare Task Sheet for PANTHER SCM Assessments - Agree Defuelling Order | 2022-03-16 | 2022-03-28 | 10 | 0 | 8 | 12 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.3790 | HYB Essential Defueling Safety Case | TSA/EDF Best Athlete Review for PCPV Integrity Justification (Civils Internal Resource) | 2022-03-17 | 2022-03-17 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.3840 | HYB Essential Defueling Safety Case | Iteration of Scope for Seismic Assessment | 2022-03-17 | 2022-03-17 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.3850 | HYB Essential Defueling Safety Case | TSA/EDF Best Athlete Review for Seismic Assessment (Civils Internal Resource) | 2022-03-17 | 2022-03-17 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.4230 | HYB Essential Defueling Safety Case | Iteration of Scope for PCPV Integrity Justification | 2022-03-17 | 2022-03-17 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.7680 | HYB Essential Defueling Safety Case | Prepare Task Sheet for Flow Induced Vibration EAN | 2022-03-17 | 2022-03-21 | 10 | 0 | 2 | 4 | 100% | 2.5 | 1 | Completed
ER6668LT | W213 | W213.3790 | TOR Essential Defueling Safety Case | TSA/EDF Best Athlete Review for PCPV Integrity Justification (Civils Internal Resource) | 2022-03-17 | 2022-03-17 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.3840 | TOR Essential Defueling Safety Case | Iteration of Scope for Seismic Assessment | 2022-03-17 | 2022-03-17 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.3850 | TOR Essential Defueling Safety Case | TSA/EDF Best Athlete Review for Seismic Assessment (Civils Internal Resource) | 2022-03-17 | 2022-03-17 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.4230 | TOR Essential Defueling Safety Case | Iteration of Scope for PCPV Integrity Justification | 2022-03-17 | 2022-03-17 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.7680 | TOR Essential Defueling Safety Case | Prepare Task Sheet for Flow Induced Vibration EAN | 2022-03-17 | 2022-03-21 | 10 | 0 | 2 | 4 | 100% | 2.5 | 1 | Completed
ER6666LT | W209 | W209.A26180 | HYB Essential Defueling Safety Case | Pre Job Brief for Pressure Boundary Integrity of Seals Report EAN | 2022-03-18 | 2022-06-01 | 0 | 0 | 51 | 75 | 100% | 0 | 1 | Completed
ER6666LT | W209 | W209.A29300 | HYB Essential Defueling Safety Case | Mid Job Brief for Reactor Pressure Boundary Seals Integrity (Tech Report) | 2022-03-18 | 2022-05-20 | 0 | 0 | 43 | 63 | 100% | 0 | 1 | Completed
ER6666LT | W209 | W209.28770 | HYB Essential Defueling Safety Case | Production of Civils Assessment Report for PCPV Integrity Justification (A-B De-risk) | 2022-03-18 | 2022-07-13 | 1 | 0 | 78 | 117 | 100% | 0.008547 | 1 | Completed
ER6666LT | W209 | W209.28780 | HYB Essential Defueling Safety Case | Production of Civils Assessment Report for Seismic Assessment (A-B De-risk) | 2022-03-18 | 2022-07-13 | 40 | 0 | 78 | 117 | 100% | 0.34188 | 1 | Completed
ER6668LT | W213 | W213.A26180 | TOR Essential Defueling Safety Case | Pre Job Brief for Pressure Boundary Integrity of Seals Report EAN | 2022-03-18 | 2022-06-01 | 0 | 0 | 51 | 75 | 100% | 0 | 1 | Completed
ER6668LT | W213 | W213.A29300 | TOR Essential Defueling Safety Case | Mid Job Brief for Reactor Pressure Boundary Seals Integrity (Tech Report) | 2022-03-18 | 2022-05-20 | 0 | 0 | 43 | 63 | 100% | 0 | 1 | Completed
ER6668LT | W213 | W213.28770 | TOR Essential Defueling Safety Case | Production of Civils Assessment Report for PCPV Integrity Justification (A-B De-risk) | 2022-03-18 | 2022-07-13 | 1 | 0 | 78 | 117 | 100% | 0.008547 | 1 | Completed
ER6668LT | W213 | W213.28780 | TOR Essential Defueling Safety Case | Production of Civils Assessment Report for Seismic Assessment (A-B De-risk) | 2022-03-18 | 2022-07-13 | 40 | 0 | 78 | 117 | 100% | 0.34188 | 1 | Completed
ER6370LT | W201 | ER6370.A16230 | HNB Reactors Shutdown Essential Safety Cases | ONR Agree/Acknowledge Safety Case EC 364023 <NSRS SC Approach & Outline> (Cat 1 MS) (HNB)(Reactor Shutdown Essential SC) | 2022-03-21 | 2022-03-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A17570 | HNB Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W104, W153 HNB Security Plan) ONR Approved | 2022-03-21 | 2022-03-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A18430 | HNB Reactors Shutdown Essential Safety Cases | >>>INCOMING ENABLER (W221) HNB Fuel Handling Essential Safety Case ONR Approved | 2022-03-21 | 2022-03-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A18440 | HNB Reactors Shutdown Essential Safety Cases | >>>MIRROR OF INCOMING ENABLER (W221) HNB Fuel Handling Essential Safety Case ONR Approved | 2022-03-21 | 2022-03-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A16240 | HNB Reactors Shutdown Essential Safety Cases | Station Approval Period | 2022-03-21 | 2022-03-24 | 10 | 0 | 3 | 3 | 100% | 3.3333 | 1 | Completed
ER6370LT | W201 | ER6370.A18450 | HNB Reactors Shutdown Essential Safety Cases | >>> INTERFACE MILESTONE (W221) HNB Fuel Handling Essential Safety Case ONR Approved | 2022-03-21 | 2022-03-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.7690 | HYB Essential Defueling Safety Case | Approve Task Sheet for Flow Induced Vibration EAN | 2022-03-22 | 2022-03-23 | 7 | 0 | 1 | 1 | 100% | 7 | 1 | Completed
ER6668LT | W213 | W213.7690 | TOR Essential Defueling Safety Case | Approve Task Sheet for Flow Induced Vibration EAN | 2022-03-22 | 2022-03-23 | 7 | 0 | 1 | 1 | 100% | 7 | 1 | Completed
ER6666LT | W209 | W209.3960 | HYB Essential Defueling Safety Case | Verify Report Post Workshop | 2022-03-23 | 2022-05-24 | 15 | 0 | 42 | 62 | 100% | 0.24194 | 1 | Completed
ER6666LT | W209 | W209.3970 | HYB Essential Defueling Safety Case | Define Case Production Scope (RFS) | 2022-03-23 | 2022-04-01 | 15 | 0 | 7 | 9 | 100% | 1.6667 | 1 | Completed
ER6370LT | W201 | W201.1690 | HNB Reactors Shutdown Essential Safety Cases | March NSC Meeting on 23 March (pm) | 2022-03-23 | 2022-03-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.3960 | TOR Essential Defueling Safety Case | Verify Report Post Workshop | 2022-03-23 | 2022-05-24 | 15 | 0 | 42 | 62 | 100% | 0.24194 | 1 | Completed
ER6668LT | W213 | W213.3970 | TOR Essential Defueling Safety Case | Define Case Production Scope (RFS) | 2022-03-23 | 2022-04-01 | 15 | 0 | 7 | 9 | 100% | 1.6667 | 1 | Completed
ER6370LT | W201 | ER6370.A16220 | HNB Reactors Shutdown Essential Safety Cases | HNB Shutdown Reactor Essential Safety Case Approved | 2022-03-24 | 2022-03-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A18400 | HNB Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W283) CAT 1 Reactors Shutdown SC Station Approved | 2022-03-24 | 2022-03-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A29530 | HYB Essential Defueling Safety Case | Pre Job Brief for Flow Induced Vibration EAN | 2022-03-24 | 2022-04-04 | 0 | 0 | 8 | 11 | 100% | 0 | 1 | Completed
ER6666LT | W209 | W209.7850 | HYB Essential Defueling Safety Case | Prepare Spec for FPU Integrity Work EAN EAN | 2022-03-24 | 2022-03-24 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.7860 | HYB Essential Defueling Safety Case | Prepare Task Sheet for FPU Integrity Work EAN | 2022-03-24 | 2022-03-24 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.7870 | HYB Essential Defueling Safety Case | Approve Task Sheet for FPU Integrity Work EAN | 2022-03-24 | 2022-03-24 | 7 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A29530 | TOR Essential Defueling Safety Case | Pre Job Brief for Flow Induced Vibration EAN | 2022-03-24 | 2022-04-04 | 0 | 0 | 8 | 11 | 100% | 0 | 1 | Completed
ER6668LT | W213 | W213.7850 | TOR Essential Defueling Safety Case | Prepare Spec for FPU Integrity Work EAN EAN | 2022-03-24 | 2022-03-24 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.7860 | TOR Essential Defueling Safety Case | Prepare Task Sheet for FPU Integrity Work EAN | 2022-03-24 | 2022-03-24 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.7870 | TOR Essential Defueling Safety Case | Approve Task Sheet for FPU Integrity Work EAN | 2022-03-24 | 2022-03-24 | 7 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.5440 | HYB Essential Defueling Safety Case | Workshop Pre-reading pack sent out | 2022-03-25 | 2022-03-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A29650 | HYB Essential Defueling Safety Case | Pre Job Brief for FPU Integrity Work EAN | 2022-03-25 | 2022-03-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.5440 | TOR Essential Defueling Safety Case | Workshop Pre-reading pack sent out | 2022-03-25 | 2022-03-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A29650 | TOR Essential Defueling Safety Case | Pre Job Brief for FPU Integrity Work EAN | 2022-03-25 | 2022-03-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A30520 | HYB Essential Defueling Safety Case | Draft FPU Integrity Work EAN | 2022-03-28 | 2022-07-11 | 30 | 0 | 70 | 105 | 100% | 0.28571 | 1 | Completed
ER6668LT | W213 | W213.A30520 | TOR Essential Defueling Safety Case | Draft FPU Integrity Work EAN | 2022-03-28 | 2022-07-11 | 30 | 0 | 70 | 105 | 100% | 0.28571 | 1 | Completed
ER6370LT | W201 | ER6370.A1580 | HNB Reactors Shutdown Essential Safety Cases | Revise all Affected Drawings and Documents for EC Approval (HNB) | 2022-03-28 | 2022-06-10 | 10 | 0 | 50 | 74 | 100% | 0.13514 | 1 | Completed
ER6370LT | W201 | ER6370.A1500 | HNB Reactors Shutdown Essential Safety Cases | Progress Lessons Learned Review- Station Approve EC 364023 | 2022-03-28 | 2022-08-10 | 20 | 0 | 92 | 135 | 100% | 0.14815 | 1 | Completed
ER6666LT | W209 | W209.5580 | HYB Essential Defueling Safety Case | Approve Task Sheet for Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 2022-03-29 | 2022-05-03 | 7 | 0 | 23 | 35 | 100% | 0.2 | 1 | Completed
ER6666LT | W209 | W209.5610 | HYB Essential Defueling Safety Case | Approve Task Sheet for Review of flux detector suitability EAN | 2022-03-29 | 2022-05-03 | 7 | 0 | 22 | 35 | 100% | 0.2 | 1 | Completed
ER6666LT | W209 | W209.5640 | HYB Essential Defueling Safety Case | Approve Task Sheet for Boron Bead Injection Feasibility & Control Rod Isolation EAN | 2022-03-29 | 2022-04-29 | 7 | 0 | 21 | 31 | 100% | 0.22581 | 1 | Completed
ER6666LT | W209 | W209.8500 | HYB Essential Defueling Safety Case | Approve Task Sheet for Define Nuclear Data (PANTHER Validation Calcs) EAN | 2022-03-29 | 2022-05-03 | 7 | 0 | 23 | 35 | 100% | 0.2 | 1 | Completed
ER6666LT | W209 | W209.8540 | HYB Essential Defueling Safety Case | Approve Task Sheet for PANTHER SCM Assessments - Agree Defuelling Order | 2022-03-29 | 2022-05-03 | 7 | 0 | 23 | 35 | 100% | 0.2 | 1 | Completed
ER6668LT | W213 | W213.5580 | TOR Essential Defueling Safety Case | Approve Task Sheet for Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 2022-03-29 | 2022-05-03 | 7 | 0 | 23 | 35 | 100% | 0.2 | 1 | Completed
ER6668LT | W213 | W213.5610 | TOR Essential Defueling Safety Case | Approve Task Sheet for Review of flux detector suitability EAN | 2022-03-29 | 2022-05-03 | 7 | 0 | 22 | 35 | 100% | 0.2 | 1 | Completed
ER6668LT | W213 | W213.5640 | TOR Essential Defueling Safety Case | Approve Task Sheet for Boron Bead Injection Feasibility & Control Rod Isolation EAN | 2022-03-29 | 2022-04-29 | 7 | 0 | 21 | 31 | 100% | 0.22581 | 1 | Completed
ER6668LT | W213 | W213.8500 | TOR Essential Defueling Safety Case | Approve Task Sheet for Define Nuclear Data (PANTHER Validation Calcs) EAN | 2022-03-29 | 2022-05-03 | 7 | 0 | 23 | 35 | 100% | 0.2 | 1 | Completed
ER6668LT | W213 | W213.8540 | TOR Essential Defueling Safety Case | Approve Task Sheet for PANTHER SCM Assessments - Agree Defuelling Order | 2022-03-29 | 2022-05-03 | 7 | 0 | 23 | 35 | 100% | 0.2 | 1 | Completed
ER6666LT | W209 | W209.6880 | HYB Essential Defueling Safety Case | PJB - HFIP | 2022-03-31 | 2022-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.6880 | TOR Essential Defueling Safety Case | PJB - HFIP | 2022-03-31 | 2022-03-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.7920 | HYB Essential Defueling Safety Case | Draft Human Factors Integration Plan EAN (REV 000) | 2022-04-01 | 2022-05-13 | 48 | 0 | 28 | 42 | 100% | 1.1429 | 1 | Completed
ER6668LT | W213 | W213.7920 | TOR Essential Defueling Safety Case | Draft Human Factors Integration Plan EAN (REV 000) | 2022-04-01 | 2022-05-13 | 48 | 0 | 28 | 42 | 100% | 1.1429 | 1 | Completed
ER6666LT | W209 | W209.1105 | HYB Essential Defueling Safety Case | Station comments on NSRS | 2022-04-01 | 2022-05-27 | 15 | 0 | 38 | 56 | 100% | 0.26786 | 1 | Completed
ER6666LT | W209 | W209.5740 | HYB Essential Defueling Safety Case | Prepare Spec for Safety Case Requirements EAN - TASK E EAN | 2022-04-01 | 2022-04-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.5890 | HYB Essential Defueling Safety Case | Prepare Spec for Reactor Internals & Structural Integrity During Defueling Report EAN | 2022-04-01 | 2022-04-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.1105 | TOR Essential Defueling Safety Case | Station comments on NSRS | 2022-04-01 | 2022-05-27 | 15 | 0 | 38 | 56 | 100% | 0.26786 | 1 | Completed
ER6668LT | W213 | W213.5740 | TOR Essential Defueling Safety Case | Prepare Spec for Safety Case Requirements EAN - TASK E EAN | 2022-04-01 | 2022-04-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.5890 | TOR Essential Defueling Safety Case | Prepare Spec for Reactor Internals & Structural Integrity During Defueling Report EAN | 2022-04-01 | 2022-04-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.4240 | HYB Essential Defueling Safety Case | Approve & Issue RFS | 2022-04-04 | 2022-04-04 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.4250 | HYB Essential Defueling Safety Case | RFS Issued | 2022-04-04 | 2022-04-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.4240 | TOR Essential Defueling Safety Case | Approve & Issue RFS | 2022-04-04 | 2022-04-04 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.4250 | TOR Essential Defueling Safety Case | RFS Issued | 2022-04-04 | 2022-04-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1095 | HYB Essential Defueling Safety Case | INA comments on NSRS | 2022-04-04 | 2022-06-01 | 15 | 0 | 40 | 58 | 100% | 0.25862 | 1 | Completed
ER6666LT | W209 | W209.4770 | HYB Essential Defueling Safety Case | Register EC and identify Milestones in AMS EC 371387 | 2022-04-04 | 2022-04-28 | 7 | 0 | 17 | 24 | 100% | 0.29167 | 1 | Completed
ER6666LT | W209 | W209.7530 | HYB Essential Defueling Safety Case | Prepare Task Sheet for Cooling Plant Availability Review EAN | 2022-04-04 | 2022-05-03 | 10 | 0 | 18 | 29 | 100% | 0.34483 | 1 | Completed
ER6666LT | W209 | W209.7560 | HYB Essential Defueling Safety Case | Prepare Task Sheet for Cooling Plant OPEX Study EAN | 2022-04-04 | 2022-05-03 | 10 | 0 | 18 | 29 | 100% | 0.34483 | 1 | Completed
ER6668LT | W213 | W213.1095 | TOR Essential Defueling Safety Case | INA comments on NSRS | 2022-04-04 | 2022-06-01 | 15 | 0 | 40 | 58 | 100% | 0.25862 | 1 | Completed
ER6668LT | W213 | W213.4770 | TOR Essential Defueling Safety Case | Register EC and identify Milestones in AMS EC 371387 | 2022-04-04 | 2022-04-28 | 7 | 0 | 17 | 24 | 100% | 0.29167 | 1 | Completed
ER6668LT | W213 | W213.7530 | TOR Essential Defueling Safety Case | Prepare Task Sheet for Cooling Plant Availability Review EAN | 2022-04-04 | 2022-05-03 | 10 | 0 | 18 | 29 | 100% | 0.34483 | 1 | Completed
ER6668LT | W213 | W213.7560 | TOR Essential Defueling Safety Case | Prepare Task Sheet for Cooling Plant OPEX Study EAN | 2022-04-04 | 2022-05-03 | 10 | 0 | 18 | 29 | 100% | 0.34483 | 1 | Completed
ER6666LT | W209 | W209.4260 | HYB Essential Defueling Safety Case | Supplier Respond to RFS | 2022-04-05 | 2022-04-22 | 10 | 0 | 11 | 17 | 100% | 0.58824 | 1 | Completed
ER6668LT | W213 | W213.4260 | TOR Essential Defueling Safety Case | Supplier Respond to RFS | 2022-04-05 | 2022-04-22 | 10 | 0 | 11 | 17 | 100% | 0.58824 | 1 | Completed
ER6666LT | W209 | W209.A29540 | HYB Essential Defueling Safety Case | Draft Review of Flow Induced Vibration EAN | 2022-04-05 | 2022-05-31 | 38 | 0 | 38 | 56 | 100% | 0.67857 | 1 | Completed
ER6668LT | W213 | W213.A29540 | TOR Essential Defueling Safety Case | Draft Review of Flow Induced Vibration EAN | 2022-04-05 | 2022-05-31 | 38 | 0 | 38 | 56 | 100% | 0.67857 | 1 | Completed
ER6666LT | W209 | W209.1390 | HYB Essential Defueling Safety Case | Confirm Objectives to be Delivered at Gate B | 2022-04-06 | 2022-04-06 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.5450 | HYB Essential Defueling Safety Case | Optioneering Workshop | 2022-04-06 | 2022-04-06 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1390 | TOR Essential Defueling Safety Case | Confirm Objectives to be Delivered at Gate B | 2022-04-06 | 2022-04-06 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.5450 | TOR Essential Defueling Safety Case | Optioneering Workshop | 2022-04-06 | 2022-04-06 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1400 | HYB Essential Defueling Safety Case | Initial high level scope of programme | 2022-04-07 | 2022-04-07 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.4580 | HYB Essential Defueling Safety Case | Hold Station Workshop to Share OPEX | 2022-04-07 | 2022-04-07 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.5460 | HYB Essential Defueling Safety Case | Workshop Minutes Issued | 2022-04-07 | 2022-04-19 | 3 | 0 | 7 | 12 | 100% | 0.25 | 1 | Completed
ER6668LT | W213 | W213.1400 | TOR Essential Defueling Safety Case | Initial high level scope of programme | 2022-04-07 | 2022-04-07 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.4580 | TOR Essential Defueling Safety Case | Hold Station Workshop to Share OPEX | 2022-04-07 | 2022-04-07 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.5460 | TOR Essential Defueling Safety Case | Workshop Minutes Issued | 2022-04-07 | 2022-04-19 | 3 | 0 | 7 | 12 | 100% | 0.25 | 1 | Completed
ER6666LT | W209 | W209.8620 | HYB Essential Defueling Safety Case | Prepare Spec for FPU Maintenance Work EAN | 2022-04-08 | 2022-04-08 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.8630 | HYB Essential Defueling Safety Case | Prepare Task Sheet for FPU Maintenance Work EAN | 2022-04-08 | 2022-04-08 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.8640 | HYB Essential Defueling Safety Case | Approve Task Sheet for FPU Maintenance Work EAN | 2022-04-08 | 2022-04-08 | 7 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.8620 | TOR Essential Defueling Safety Case | Prepare Spec for FPU Maintenance Work EAN | 2022-04-08 | 2022-04-08 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.8630 | TOR Essential Defueling Safety Case | Prepare Task Sheet for FPU Maintenance Work EAN | 2022-04-08 | 2022-04-08 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.8640 | TOR Essential Defueling Safety Case | Approve Task Sheet for FPU Maintenance Work EAN | 2022-04-08 | 2022-04-08 | 7 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1410 | HYB Essential Defueling Safety Case | Define Project Control Structures (WBS/CBS/OBS/PBS) | 2022-04-08 | 2022-05-31 | 1 | 0 | 35 | 53 | 100% | 0.018868 | 1 | Completed
ER6666LT | W209 | W209.5750 | HYB Essential Defueling Safety Case | Prepare Task Sheet for Safety Case Requirements EAN - TASK E EAN | 2022-04-08 | 2022-05-04 | 10 | 0 | 16 | 26 | 100% | 0.38462 | 1 | Completed
ER6666LT | W209 | W209.5900 | HYB Essential Defueling Safety Case | Prepare Task Sheet for Reactor Internals & Structural Integrity During Defueling Report EAN | 2022-04-08 | 2022-04-11 | 10 | 0 | 1 | 3 | 100% | 3.3333 | 1 | Completed
ER6668LT | W213 | W213.1410 | TOR Essential Defueling Safety Case | Define Project Control Structures (WBS/CBS/OBS/PBS) | 2022-04-08 | 2022-05-31 | 1 | 0 | 35 | 53 | 100% | 0.018868 | 1 | Completed
ER6668LT | W213 | W213.5750 | TOR Essential Defueling Safety Case | Prepare Task Sheet for Safety Case Requirements EAN - TASK E EAN | 2022-04-08 | 2022-05-04 | 10 | 0 | 16 | 26 | 100% | 0.38462 | 1 | Completed
ER6668LT | W213 | W213.5900 | TOR Essential Defueling Safety Case | Prepare Task Sheet for Reactor Internals & Structural Integrity During Defueling Report EAN | 2022-04-08 | 2022-04-11 | 10 | 0 | 1 | 3 | 100% | 3.3333 | 1 | Completed
ER6650LT | W226 | 2160 | HYA Fuel Handling Essential Safety Case | INA of EC without ER updates | 2022-04-08 | 2022-11-10 | 149 | 0 | 149 | 216 | 100% | 0.68981 | 1 | Completed
ER6666LT | W209 | W209.5910 | HYB Essential Defueling Safety Case | Approve Task Sheet for Reactor Internals & Structural Integrity During Defueling Report EAN | 2022-04-11 | 2022-04-12 | 7 | 0 | 1 | 1 | 100% | 7 | 1 | Completed
ER6666LT | W209 | W209.A30450 | HYB Essential Defueling Safety Case | Pre Job Brief for FPU Maintenance Work EAN | 2022-04-11 | 2022-04-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.5910 | TOR Essential Defueling Safety Case | Approve Task Sheet for Reactor Internals & Structural Integrity During Defueling Report EAN | 2022-04-11 | 2022-04-12 | 7 | 0 | 1 | 1 | 100% | 7 | 1 | Completed
ER6668LT | W213 | W213.A30450 | TOR Essential Defueling Safety Case | Pre Job Brief for FPU Maintenance Work EAN | 2022-04-11 | 2022-04-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A30570 | HYB Essential Defueling Safety Case | Draft FPU Maintenance Work EAN | 2022-04-12 | 2022-06-24 | 30 | 0 | 48 | 73 | 100% | 0.41096 | 1 | Completed
ER6668LT | W213 | W213.A30570 | TOR Essential Defueling Safety Case | Draft FPU Maintenance Work EAN | 2022-04-12 | 2022-06-24 | 30 | 0 | 48 | 73 | 100% | 0.41096 | 1 | Completed
ER6666LT | W209 | W209.A26260 | HYB Essential Defueling Safety Case | Pre Job Brief for Reactor Internals & Structural Integrity During Defueling Report EAN | 2022-04-13 | 2022-04-13 | 0 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A26260 | TOR Essential Defueling Safety Case | Pre Job Brief for Reactor Internals & Structural Integrity During Defueling Report EAN | 2022-04-13 | 2022-04-13 | 0 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.5020 | HYB Essential Defueling Safety Case | HOLD POINT 2 - Share Preliminary Analysis Findings Pre-Tech Review | 2022-04-13 | 2022-04-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.5020 | TOR Essential Defueling Safety Case | HOLD POINT 2 - Share Preliminary Analysis Findings Pre-Tech Review | 2022-04-13 | 2022-04-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.5030 | HYB Essential Defueling Safety Case | Issue of Dropped FPU BoA for Tech Review | 2022-04-14 | 2022-05-27 | 27 | 0 | 29 | 43 | 100% | 0.62791 | 1 | Completed
ER6666LT | W209 | W209.A26270 | HYB Essential Defueling Safety Case | Draft Reactor Internals & Structural Integrity During Defueling Report EAN | 2022-04-14 | 2022-05-18 | 30 | 0 | 21 | 34 | 100% | 0.88235 | 1 | Completed
ER6668LT | W213 | W213.5030 | TOR Essential Defueling Safety Case | Issue of Dropped FPU BoA for Tech Review | 2022-04-14 | 2022-05-27 | 27 | 0 | 29 | 43 | 100% | 0.62791 | 1 | Completed
ER6668LT | W213 | W213.A26270 | TOR Essential Defueling Safety Case | Draft Reactor Internals & Structural Integrity During Defueling Report EAN | 2022-04-14 | 2022-05-18 | 30 | 0 | 21 | 34 | 100% | 0.88235 | 1 | Completed
ER6666LT | W209 | W209.5470 | HYB Essential Defueling Safety Case | (Draft) Optioneering Report Issued for Verification | 2022-04-19 | 2022-04-19 | 3 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.5470 | TOR Essential Defueling Safety Case | (Draft) Optioneering Report Issued for Verification | 2022-04-19 | 2022-04-19 | 3 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.4190 | HYB Essential Defueling Safety Case | Approve & Issue RFS | 2022-04-20 | 2022-04-20 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.4200 | HYB Essential Defueling Safety Case | RFS Issued | 2022-04-20 | 2022-04-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.5490 | HYB Essential Defueling Safety Case | Verification | 2022-04-20 | 2022-05-18 | 10 | 0 | 20 | 28 | 100% | 0.35714 | 1 | Completed
ER6668LT | W213 | W213.4190 | TOR Essential Defueling Safety Case | Approve & Issue RFS | 2022-04-20 | 2022-04-20 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.4200 | TOR Essential Defueling Safety Case | RFS Issued | 2022-04-20 | 2022-04-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.5490 | TOR Essential Defueling Safety Case | Verification | 2022-04-20 | 2022-05-18 | 10 | 0 | 20 | 28 | 100% | 0.35714 | 1 | Completed
ER6371LT | W202 | 2900 | HRA Reactors Shutdown Essential Safety Cases | Produce draft NSRS (using BARRIER MODEL) | 2022-04-20 | 2022-05-06 | 12 | 0 | 12 | 16 | 100% | 0.75 | 1 | Completed
ER6661LT | W206 | 2900 | HYA Reactors Shutdown Essential Safety Cases | Produce draft NSRS (using BARRIER MODEL) | 2022-04-20 | 2022-05-06 | 12 | 0 | 12 | 16 | 100% | 0.75 | 1 | Completed
ER6666LT | W209 | W209.4210 | HYB Essential Defueling Safety Case | Supplier Respond to RFS | 2022-04-21 | 2022-05-06 | 10 | 0 | 10 | 15 | 100% | 0.66667 | 1 | Completed
ER6668LT | W213 | W213.4210 | TOR Essential Defueling Safety Case | Supplier Respond to RFS | 2022-04-21 | 2022-05-06 | 10 | 0 | 10 | 15 | 100% | 0.66667 | 1 | Completed
ER6666LT | W209 | W209.4270 | HYB Essential Defueling Safety Case | RFS Responses Recieved | 2022-04-22 | 2022-04-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.4270 | TOR Essential Defueling Safety Case | RFS Responses Recieved | 2022-04-22 | 2022-04-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 2700 | HYA Fuel Handling Essential Safety Case | Produce draft NSRS (using BARRIER MODEL) | 2022-04-26 | 2022-05-18 | 8 | 0 | 15 | 22 | 100% | 0.36364 | 1 | Completed
ER6370LT | W201 | ER6370.A18160 | HNB Reactors Shutdown Essential Safety Cases | Review of Reactor Essential Safety Cases 1 - Lessons Learned Review Complete | 2022-04-27 | 2022-04-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.4760 | HYB Essential Defueling Safety Case | Approve EAN | 2022-04-27 | 2022-05-17 | 10 | 0 | 14 | 20 | 100% | 0.5 | 1 | Completed
ER6666LT | W209 | W209.5330 | HYB Essential Defueling Safety Case | PJBs of Previous Lessons Learned | 2022-04-27 | 2022-04-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | W201.1650 | HNB Reactors Shutdown Essential Safety Cases | INSA complete/INA Approved | 2022-04-27 | 2022-04-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.4760 | TOR Essential Defueling Safety Case | Approve EAN | 2022-04-27 | 2022-05-17 | 10 | 0 | 14 | 20 | 100% | 0.5 | 1 | Completed
ER6668LT | W213 | W213.5330 | TOR Essential Defueling Safety Case | PJBs of Previous Lessons Learned | 2022-04-27 | 2022-04-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A26740 | HYB Essential Defueling Safety Case | Pre Job Brief for Boron Bead Injection Feasibility & Control Rod Isolation EAN | 2022-04-29 | 2022-04-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.5430 | HYB Essential Defueling Safety Case | Verification | 2022-04-29 | 2022-06-01 | 4 | 0 | 23 | 33 | 100% | 0.12121 | 1 | Completed
ER6666LT | W209 | W209.5980 | HYB Essential Defueling Safety Case | Prepare Spec for Review of FM Cyclic Duty EAN | 2022-04-29 | 2022-04-29 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A29730 | HYB Essential Defueling Safety Case | Pre Job Brief for ALARP Review of Not Draining the PVCS (Report) | 2022-04-29 | 2022-04-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A26740 | TOR Essential Defueling Safety Case | Pre Job Brief for Boron Bead Injection Feasibility & Control Rod Isolation EAN | 2022-04-29 | 2022-04-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.5430 | TOR Essential Defueling Safety Case | Verification | 2022-04-29 | 2022-06-01 | 4 | 0 | 23 | 33 | 100% | 0.12121 | 1 | Completed
ER6668LT | W213 | W213.5980 | TOR Essential Defueling Safety Case | Prepare Spec for Review of FM Cyclic Duty EAN | 2022-04-29 | 2022-04-29 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A29730 | TOR Essential Defueling Safety Case | Pre Job Brief for ALARP Review of Not Draining the PVCS (Report) | 2022-04-29 | 2022-04-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.7700 | HYB Essential Defueling Safety Case | Update NSRS to address comments | 2022-04-29 | 2022-06-01 | 13 | 0 | 23 | 33 | 100% | 0.39394 | 1 | Completed
ER6668LT | W213 | W213.7700 | TOR Essential Defueling Safety Case | Update NSRS to address comments | 2022-04-29 | 2022-06-01 | 13 | 0 | 23 | 33 | 100% | 0.39394 | 1 | Completed
ER6666LT | W209 | W209.5990 | HYB Essential Defueling Safety Case | Prepare Task Sheet for Review of FM Cyclic Duty EAN | 2022-05-02 | 2022-05-20 | 10 | 0 | 14 | 18 | 100% | 0.55556 | 1 | Completed
ER6666LT | W209 | W209.A30310 | HYB Essential Defueling Safety Case | Draft Boron Bead Injection Feasibility & Control Rod Isolation EAN (CLAIM 1 - A - B De-risking) | 2022-05-02 | 2022-07-13 | 48 | 0 | 50 | 72 | 100% | 0.66667 | 1 | Completed
ER6666LT | W209 | W209.A30360 | HYB Essential Defueling Safety Case | Draft ALARP Review of Not Draining the PVCS (Report) (A - B De-risking) | 2022-05-02 | 2022-07-13 | 29 | 0 | 50 | 72 | 100% | 0.40278 | 1 | Completed
ER6668LT | W213 | W213.5990 | TOR Essential Defueling Safety Case | Prepare Task Sheet for Review of FM Cyclic Duty EAN | 2022-05-02 | 2022-05-20 | 10 | 0 | 14 | 18 | 100% | 0.55556 | 1 | Completed
ER6668LT | W213 | W213.A30310 | TOR Essential Defueling Safety Case | Draft Boron Bead Injection Feasibility & Control Rod Isolation EAN (CLAIM 1 - A - B De-risking) | 2022-05-02 | 2022-07-13 | 48 | 0 | 50 | 72 | 100% | 0.66667 | 1 | Completed
ER6668LT | W213 | W213.A30360 | TOR Essential Defueling Safety Case | Draft ALARP Review of Not Draining the PVCS (Report) (A - B De-risking) | 2022-05-02 | 2022-07-13 | 29 | 0 | 50 | 72 | 100% | 0.40278 | 1 | Completed
ER6666LT | W209 | W209.A25940 | HYB Essential Defueling Safety Case | Pre Job Brief for Civil Assesment of the Ponds at Low Temperature EAN | 2022-05-03 | 2022-05-10 | 0 | 0 | 5 | 7 | 100% | 0 | 1 | Completed
ER6666LT | W209 | W209.A26020 | HYB Essential Defueling Safety Case | Pre Job Brief for Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN | 2022-05-03 | 2022-05-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A26660 | HYB Essential Defueling Safety Case | Pre Job Brief for Review of flux detector suitability EAN | 2022-05-03 | 2022-05-20 | 1 | 0 | 14 | 17 | 100% | 0.058824 | 1 | Completed
ER6666LT | W209 | W209.6370 | HYB Essential Defueling Safety Case | Prepare Spec for Update Basis of Analysis document EAN | 2022-05-03 | 2022-05-13 | 5 | 0 | 9 | 10 | 100% | 0.5 | 1 | Completed
ER6666LT | W209 | W209.7540 | HYB Essential Defueling Safety Case | Approve Task Sheet for Cooling Plant Availability Review EAN | 2022-05-03 | 2022-05-06 | 7 | 0 | 3 | 3 | 100% | 2.3333 | 1 | Completed
ER6370LT | W201 | W201.1660 | HNB Reactors Shutdown Essential Safety Cases | Station Approve EC | 2022-05-03 | 2022-05-05 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6666LT | W209 | W209.8260 | HYB Essential Defueling Safety Case | Prepare Spec for Feasibility of Draining PVCS (Report) | 2022-05-03 | 2022-05-04 | 10 | 0 | 1 | 1 | 100% | 10 | 1 | Completed
ER6666LT | W209 | W209.A29870 | HYB Essential Defueling Safety Case | Pre Job Brief for FPU Maintenance Analysis EAN | 2022-05-03 | 2022-05-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A30380 | HYB Essential Defueling Safety Case | Draft Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN (A-B De-risking) | 2022-05-03 | 2022-07-13 | 50 | 0 | 50 | 71 | 100% | 0.70423 | 1 | Completed
ER6668LT | W213 | W213.A25940 | TOR Essential Defueling Safety Case | Pre Job Brief for Civil Assesment of the Ponds at Low Temperature EAN | 2022-05-03 | 2022-05-10 | 0 | 0 | 5 | 7 | 100% | 0 | 1 | Completed
ER6668LT | W213 | W213.A26020 | TOR Essential Defueling Safety Case | Pre Job Brief for Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN | 2022-05-03 | 2022-05-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A26660 | TOR Essential Defueling Safety Case | Pre Job Brief for Review of flux detector suitability EAN | 2022-05-03 | 2022-05-20 | 1 | 0 | 14 | 17 | 100% | 0.058824 | 1 | Completed
ER6668LT | W213 | W213.6370 | TOR Essential Defueling Safety Case | Prepare Spec for Update Basis of Analysis document EAN | 2022-05-03 | 2022-05-13 | 5 | 0 | 9 | 10 | 100% | 0.5 | 1 | Completed
ER6668LT | W213 | W213.7540 | TOR Essential Defueling Safety Case | Approve Task Sheet for Cooling Plant Availability Review EAN | 2022-05-03 | 2022-05-06 | 7 | 0 | 3 | 3 | 100% | 2.3333 | 1 | Completed
ER6668LT | W213 | W213.8260 | TOR Essential Defueling Safety Case | Prepare Spec for Feasibility of Draining PVCS (Report) | 2022-05-03 | 2022-05-04 | 10 | 0 | 1 | 1 | 100% | 10 | 1 | Completed
ER6668LT | W213 | W213.A29870 | TOR Essential Defueling Safety Case | Pre Job Brief for FPU Maintenance Analysis EAN | 2022-05-03 | 2022-05-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A30380 | TOR Essential Defueling Safety Case | Draft Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN (A-B De-risking) | 2022-05-03 | 2022-07-13 | 50 | 0 | 50 | 71 | 100% | 0.70423 | 1 | Completed
ER6666LT | W209 | W209.3390 | HYB Essential Defueling Safety Case | EDF Approve Task Sheet | 2022-05-03 | 2022-05-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.3390 | TOR Essential Defueling Safety Case | EDF Approve Task Sheet | 2022-05-03 | 2022-05-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.7570 | HYB Essential Defueling Safety Case | Approve Task Sheet for Cooling Plant OPEX Study EAN | 2022-05-04 | 2022-05-06 | 7 | 0 | 2 | 2 | 100% | 3.5 | 1 | Completed
ER6668LT | W213 | W213.7570 | TOR Essential Defueling Safety Case | Approve Task Sheet for Cooling Plant OPEX Study EAN | 2022-05-04 | 2022-05-06 | 7 | 0 | 2 | 2 | 100% | 3.5 | 1 | Completed
ER6666LT | W209 | W209.3360 | HYB Essential Defueling Safety Case | Optioneering Report Completed | 2022-05-04 | 2022-05-13 | 1 | 0 | 8 | 9 | 100% | 0.11111 | 1 | Completed
ER6666LT | W209 | W209.A30550 | HYB Essential Defueling Safety Case | Draft Review of FPU Maintenance Analysis EAN (A-B De-risking) | 2022-05-04 | 2022-07-13 | 49 | 0 | 49 | 70 | 100% | 0.7 | 1 | Completed
ER6668LT | W213 | W213.3360 | TOR Essential Defueling Safety Case | Optioneering Report Completed | 2022-05-04 | 2022-05-13 | 1 | 0 | 8 | 9 | 100% | 0.11111 | 1 | Completed
ER6668LT | W213 | W213.A30550 | TOR Essential Defueling Safety Case | Draft Review of FPU Maintenance Analysis EAN (A-B De-risking) | 2022-05-04 | 2022-07-13 | 49 | 0 | 49 | 70 | 100% | 0.7 | 1 | Completed
ER6666LT | W209 | W209.8270 | HYB Essential Defueling Safety Case | Prepare Task Sheet for Feasibility of Draining PVCS (Report) | 2022-05-05 | 2022-05-13 | 10 | 0 | 7 | 8 | 100% | 1.25 | 1 | Completed
ER6668LT | W213 | W213.8270 | TOR Essential Defueling Safety Case | Prepare Task Sheet for Feasibility of Draining PVCS (Report) | 2022-05-05 | 2022-05-13 | 10 | 0 | 7 | 8 | 100% | 1.25 | 1 | Completed
ER6666LT | W209 | W209.5760 | HYB Essential Defueling Safety Case | Approve Task Sheet for Safety Case Requirements EAN - TASK E EAN | 2022-05-05 | 2022-05-06 | 7 | 0 | 1 | 1 | 100% | 7 | 1 | Completed
ER6668LT | W213 | W213.5760 | TOR Essential Defueling Safety Case | Approve Task Sheet for Safety Case Requirements EAN - TASK E EAN | 2022-05-05 | 2022-05-06 | 7 | 0 | 1 | 1 | 100% | 7 | 1 | Completed
ER6370LT | W201 | W201.1670 | HNB Reactors Shutdown Essential Safety Cases | EC Approved | 2022-05-05 | 2022-05-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.4220 | HYB Essential Defueling Safety Case | RFS Responses Recieved | 2022-05-06 | 2022-05-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.28660 | HYB Essential Defueling Safety Case | Pre Job Brief for PCPV Liner Impact Assessment | 2022-05-06 | 2022-05-06 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.6420 | HYB Essential Defueling Safety Case | Receive Responses from TSA for Develop FEA Model | 2022-05-06 | 2022-05-06 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | W201.1700 | HNB Reactors Shutdown Essential Safety Cases | Start of Defuelling HNB R3 - Target date | 2022-05-06 | 2022-05-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.4220 | TOR Essential Defueling Safety Case | RFS Responses Recieved | 2022-05-06 | 2022-05-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.28660 | TOR Essential Defueling Safety Case | Pre Job Brief for PCPV Liner Impact Assessment | 2022-05-06 | 2022-05-06 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.6420 | TOR Essential Defueling Safety Case | Receive Responses from TSA for Develop FEA Model | 2022-05-06 | 2022-05-06 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A25860 | HYB Essential Defueling Safety Case | Pre Job Brief for Safety Case Requirements EAN - TASK E EAN | 2022-05-09 | 2022-05-23 | 0 | 0 | 11 | 14 | 100% | 0 | 1 | Completed
ER6666LT | W209 | W209.28670 | HYB Essential Defueling Safety Case | Draft PCPV Liner Impact Assessment | 2022-05-09 | 2022-05-18 | 30 | 0 | 7 | 9 | 100% | 3.3333 | 1 | Completed
ER6666LT | W209 | W209.A29380 | HYB Essential Defueling Safety Case | Pre Job Brief for Cooling Plant Availability Review EAN | 2022-05-09 | 2022-05-16 | 0 | 0 | 6 | 7 | 100% | 0 | 1 | Completed
ER6666LT | W209 | W209.A29460 | HYB Essential Defueling Safety Case | Pre Job Brief for Cooling Plant OPEX Study EAN | 2022-05-09 | 2022-05-17 | 0 | 0 | 7 | 8 | 100% | 0 | 1 | Completed
ER6666LT | W209 | W209.7810 | HYB Essential Defueling Safety Case | Select Supplier for Develop FEA Model | 2022-05-09 | 2022-05-10 | 10 | 0 | 2 | 1 | 100% | 10 | 1 | Completed
ER6668LT | W213 | W213.A25860 | TOR Essential Defueling Safety Case | Pre Job Brief for Safety Case Requirements EAN - TASK E EAN | 2022-05-09 | 2022-05-23 | 0 | 0 | 11 | 14 | 100% | 0 | 1 | Completed
ER6668LT | W213 | W213.28670 | TOR Essential Defueling Safety Case | Draft PCPV Liner Impact Assessment | 2022-05-09 | 2022-05-18 | 30 | 0 | 7 | 9 | 100% | 3.3333 | 1 | Completed
ER6668LT | W213 | W213.A29380 | TOR Essential Defueling Safety Case | Pre Job Brief for Cooling Plant Availability Review EAN | 2022-05-09 | 2022-05-16 | 0 | 0 | 6 | 7 | 100% | 0 | 1 | Completed
ER6668LT | W213 | W213.A29460 | TOR Essential Defueling Safety Case | Pre Job Brief for Cooling Plant OPEX Study EAN | 2022-05-09 | 2022-05-17 | 0 | 0 | 7 | 8 | 100% | 0 | 1 | Completed
ER6668LT | W213 | W213.7810 | TOR Essential Defueling Safety Case | Select Supplier for Develop FEA Model | 2022-05-09 | 2022-05-10 | 10 | 0 | 2 | 1 | 100% | 10 | 1 | Completed
ER6371LT | W202 | 2910 | HRA Reactors Shutdown Essential Safety Cases | Station comments on NSRS | 2022-05-09 | 2022-05-20 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6371LT | W202 | 2920 | HRA Reactors Shutdown Essential Safety Cases | ED (Peer) comments on NSRS | 2022-05-09 | 2022-05-20 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6371LT | W202 | 2930 | HRA Reactors Shutdown Essential Safety Cases | SRD comments on NSRS | 2022-05-09 | 2022-05-20 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6661LT | W206 | 2910 | HYA Reactors Shutdown Essential Safety Cases | Station comments on NSRS | 2022-05-09 | 2022-05-20 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6661LT | W206 | 2920 | HYA Reactors Shutdown Essential Safety Cases | ED (Peer) comments on NSRS | 2022-05-09 | 2022-05-20 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6661LT | W206 | 2930 | HYA Reactors Shutdown Essential Safety Cases | SRD comments on NSRS | 2022-05-09 | 2022-05-20 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6650LT | W226 | 2730 | HYA Fuel Handling Essential Safety Case | SRD comments on NSRS | 2022-05-09 | 2022-05-20 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6650LT | W226 | 2720 | HYA Fuel Handling Essential Safety Case | ED (Peer) comments on NSRS | 2022-05-09 | 2022-05-20 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6650LT | W226 | 2710 | HYA Fuel Handling Essential Safety Case | Station comments on NSRS | 2022-05-09 | 2022-05-20 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6666LT | W209 | W209.A30240 | HYB Essential Defueling Safety Case | Pre Job Brief for Define Nuclear Data (PANTHER Validation Calcs) EAN | 2022-05-10 | 2022-05-10 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A30280 | HYB Essential Defueling Safety Case | Pre Job Brief for PANTHER SCM Assessments - Agree Defuelling Order EAN | 2022-05-10 | 2022-05-10 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A30330 | HYB Essential Defueling Safety Case | Draft Civil Assesment of the Ponds at Low Temperature EAN (A - B De-risking) | 2022-05-10 | 2022-07-13 | 41 | 0 | 45 | 64 | 100% | 0.64062 | 1 | Completed
ER6668LT | W213 | W213.A30240 | TOR Essential Defueling Safety Case | Pre Job Brief for Define Nuclear Data (PANTHER Validation Calcs) EAN | 2022-05-10 | 2022-05-10 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A30280 | TOR Essential Defueling Safety Case | Pre Job Brief for PANTHER SCM Assessments - Agree Defuelling Order EAN | 2022-05-10 | 2022-05-10 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A30330 | TOR Essential Defueling Safety Case | Draft Civil Assesment of the Ponds at Low Temperature EAN (A - B De-risking) | 2022-05-10 | 2022-07-13 | 41 | 0 | 45 | 64 | 100% | 0.64062 | 1 | Completed
ER6666LT | W209 | W209.A26490 | HYB Essential Defueling Safety Case | PANTHER SCM Assessments - Agree Defuelling Order EAN ## (Cost Summary) (Claim 1) | 2022-05-11 | 2023-01-17 | 175 | 0 | 173 | 251 | 100% | 0.69721 | 1 | Completed
ER6666LT | W209 | W209.A28100 | HYB Essential Defueling Safety Case | Pre Job Brief for Develop FEA Model | 2022-05-11 | 2022-05-17 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.A30250 | HYB Essential Defueling Safety Case | Draft Define Nuclear Data (PANTHER Validation Calcs) EAN | 2022-05-11 | 2022-07-01 | 30 | 0 | 36 | 51 | 100% | 0.58824 | 1 | Completed
ER6666LT | W209 | W209.A30290 | HYB Essential Defueling Safety Case | Draft PANTHER SCM Assessments - Agree Defuelling Order EAN | 2022-05-11 | 2022-09-12 | 4 | 0 | 86 | 124 | 100% | 0.032258 | 1 | Completed
ER6668LT | W213 | W213.A26490 | TOR Essential Defueling Safety Case | PANTHER SCM Assessments - Agree Defuelling Order EAN ## (Cost Summary) (Claim 1) | 2022-05-11 | 2023-01-17 | 175 | 0 | 173 | 251 | 100% | 0.69721 | 1 | Completed
ER6668LT | W213 | W213.A28100 | TOR Essential Defueling Safety Case | Pre Job Brief for Develop FEA Model | 2022-05-11 | 2022-05-17 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.A30250 | TOR Essential Defueling Safety Case | Draft Define Nuclear Data (PANTHER Validation Calcs) EAN | 2022-05-11 | 2022-07-01 | 30 | 0 | 36 | 51 | 100% | 0.58824 | 1 | Completed
ER6668LT | W213 | W213.A30290 | TOR Essential Defueling Safety Case | Draft PANTHER SCM Assessments - Agree Defuelling Order EAN | 2022-05-11 | 2022-09-12 | 4 | 0 | 86 | 124 | 100% | 0.032258 | 1 | Completed
ER6666LT | W209 | W209.4900 | HYB Essential Defueling Safety Case | Case Production Plan Peer Review & Update | 2022-05-11 | 2022-05-31 | 15 | 0 | 15 | 20 | 100% | 0.75 | 1 | Completed
ER6668LT | W213 | W213.4900 | TOR Essential Defueling Safety Case | Case Production Plan Peer Review & Update | 2022-05-11 | 2022-05-31 | 15 | 0 | 15 | 20 | 100% | 0.75 | 1 | Completed
ER6666LT | W209 | W209.6380 | HYB Essential Defueling Safety Case | Prepare Task Sheet for Update Basis of Analysis document EAN | 2022-05-16 | 2022-06-01 | 10 | 0 | 13 | 16 | 100% | 0.625 | 1 | Completed
ER6666LT | W209 | W209.8280 | HYB Essential Defueling Safety Case | Approve Task Sheet for Feasibility of Draining PVCS (Report) | 2022-05-16 | 2022-05-16 | 7 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.6380 | TOR Essential Defueling Safety Case | Prepare Task Sheet for Update Basis of Analysis document EAN | 2022-05-16 | 2022-06-01 | 10 | 0 | 13 | 16 | 100% | 0.625 | 1 | Completed
ER6668LT | W213 | W213.8280 | TOR Essential Defueling Safety Case | Approve Task Sheet for Feasibility of Draining PVCS (Report) | 2022-05-16 | 2022-05-16 | 7 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A30340 | HYB Essential Defueling Safety Case | Draft Cooling Plant Availability Review EAN (A - B De-risking) | 2022-05-17 | 2022-07-13 | 40 | 0 | 40 | 57 | 100% | 0.70175 | 1 | Completed
ER6668LT | W213 | W213.A30340 | TOR Essential Defueling Safety Case | Draft Cooling Plant Availability Review EAN (A - B De-risking) | 2022-05-17 | 2022-07-13 | 40 | 0 | 40 | 57 | 100% | 0.70175 | 1 | Completed
ER6666LT | W209 | W209.7600 | HYB Essential Defueling Safety Case | Review Process Flows for Defueling | 2022-05-18 | 2022-07-01 | 13 | 0 | 31 | 44 | 100% | 0.29545 | 1 | Completed
ER6666LT | W209 | W209.A30350 | HYB Essential Defueling Safety Case | Draft Cooling Plant OPEX Study EAN (A - B De-risking) | 2022-05-18 | 2022-07-13 | 28 | 0 | 39 | 56 | 100% | 0.5 | 1 | Completed
ER6666LT | W209 | W209.A30410 | HYB Essential Defueling Safety Case | Develop FEA Model (A - B De Risking) | 2022-05-18 | 2022-07-13 | 39 | 0 | 39 | 56 | 100% | 0.69643 | 1 | Completed
ER6668LT | W213 | W213.7600 | TOR Essential Defueling Safety Case | Review Process Flows for Defueling | 2022-05-18 | 2022-07-01 | 13 | 0 | 31 | 44 | 100% | 0.29545 | 1 | Completed
ER6668LT | W213 | W213.A30350 | TOR Essential Defueling Safety Case | Draft Cooling Plant OPEX Study EAN (A - B De-risking) | 2022-05-18 | 2022-07-13 | 28 | 0 | 39 | 56 | 100% | 0.5 | 1 | Completed
ER6668LT | W213 | W213.A30410 | TOR Essential Defueling Safety Case | Develop FEA Model (A - B De Risking) | 2022-05-18 | 2022-07-13 | 39 | 0 | 39 | 56 | 100% | 0.69643 | 1 | Completed
ER6666LT | W209 | W209.A26280 | HYB Essential Defueling Safety Case | Verify Reactor Internals & Structural Integrity During Defueling Report EAN Issue for Technical Review | 2022-05-19 | 2022-05-25 | 20 | 0 | 4 | 6 | 100% | 3.3333 | 1 | Completed
ER6666LT | W209 | W209.28680 | HYB Essential Defueling Safety Case | Verify PCPV Liner Impact Assessment & Issue for Technical Review | 2022-05-19 | 2022-05-26 | 10 | 0 | 5 | 7 | 100% | 1.4286 | 1 | Completed
ER6668LT | W213 | W213.A26280 | TOR Essential Defueling Safety Case | Verify Reactor Internals & Structural Integrity During Defueling Report EAN Issue for Technical Review | 2022-05-19 | 2022-05-25 | 20 | 0 | 4 | 6 | 100% | 3.3333 | 1 | Completed
ER6668LT | W213 | W213.28680 | TOR Essential Defueling Safety Case | Verify PCPV Liner Impact Assessment & Issue for Technical Review | 2022-05-19 | 2022-05-26 | 10 | 0 | 5 | 7 | 100% | 1.4286 | 1 | Completed
ER6666LT | W209 | W209.5480 | HYB Essential Defueling Safety Case | Issue Optioneering Report | 2022-05-19 | 2022-05-20 | 9 | 0 | 2 | 1 | 100% | 9 | 1 | Completed
ER6668LT | W213 | W213.5480 | TOR Essential Defueling Safety Case | Issue Optioneering Report | 2022-05-19 | 2022-05-20 | 9 | 0 | 2 | 1 | 100% | 9 | 1 | Completed
ER6666LT | W209 | W209.1480 | HYB Essential Defueling Safety Case | Update Schedule/Estimate from Risk Log & Add Provisions | 2022-05-23 | 2022-05-31 | 1 | 0 | 6 | 8 | 100% | 0.125 | 1 | Completed
ER6668LT | W213 | W213.1480 | TOR Essential Defueling Safety Case | Update Schedule/Estimate from Risk Log & Add Provisions | 2022-05-23 | 2022-05-31 | 1 | 0 | 6 | 8 | 100% | 0.125 | 1 | Completed
ER6666LT | W209 | W209.A26650 | HYB Essential Defueling Safety Case | Review of flux detector suitability EAN ## (Cost Summary) (Claim 1) | 2022-05-23 | 2022-11-21 | 128 | 0 | 128 | 182 | 100% | 0.7033 | 1 | Completed
ER6666LT | W209 | W209.6000 | HYB Essential Defueling Safety Case | Approve Task Sheet for Review of FM Cyclic Duty EAN | 2022-05-23 | 2022-05-31 | 7 | 0 | 7 | 8 | 100% | 0.875 | 1 | Completed
ER6666LT | W209 | W209.A30300 | HYB Essential Defueling Safety Case | Draft Review of flux detector suitability EAN | 2022-05-23 | 2022-08-31 | 38 | 0 | 69 | 100 | 100% | 0.38 | 1 | Completed
ER6371LT | W202 | 2950 | HRA Reactors Shutdown Essential Safety Cases | Incorporate SRD, Station, ED (peer) comments | 2022-05-23 | 2022-05-27 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6661LT | W206 | 2950 | HYA Reactors Shutdown Essential Safety Cases | Incorporate SRD, Station, ED (peer) comments | 2022-05-23 | 2022-05-27 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6668LT | W213 | W213.A26650 | TOR Essential Defueling Safety Case | Review of flux detector suitability EAN ## (Cost Summary) (Claim 1) | 2022-05-23 | 2022-11-21 | 128 | 0 | 128 | 182 | 100% | 0.7033 | 1 | Completed
ER6668LT | W213 | W213.6000 | TOR Essential Defueling Safety Case | Approve Task Sheet for Review of FM Cyclic Duty EAN | 2022-05-23 | 2022-05-31 | 7 | 0 | 7 | 8 | 100% | 0.875 | 1 | Completed
ER6668LT | W213 | W213.A30300 | TOR Essential Defueling Safety Case | Draft Review of flux detector suitability EAN | 2022-05-23 | 2022-08-31 | 38 | 0 | 69 | 100 | 100% | 0.38 | 1 | Completed
ER6650LT | W226 | 2750 | HYA Fuel Handling Essential Safety Case | Incorporate SRD, Station, ED (peer) comments | 2022-05-23 | 2022-05-27 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6666LT | W209 | W209.1460 | HYB Essential Defueling Safety Case | Hold Risk Workshop | 2022-05-24 | 2022-05-24 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.3240 | HYB Essential Defueling Safety Case | >>>OUTGOING ENABLER (W150) Optioneering Complete | 2022-05-24 | 2022-05-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.3240 | TOR Essential Defueling Safety Case | >>>OUTGOING ENABLER (W150) Optioneering Complete | 2022-05-24 | 2022-05-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1460 | TOR Essential Defueling Safety Case | Hold Risk Workshop | 2022-05-24 | 2022-05-24 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A30320 | HYB Essential Defueling Safety Case | Draft Safety Case Requirements EAN - TASK E EAN (A - B De-risking) | 2022-05-24 | 2022-07-13 | 33 | 0 | 35 | 50 | 100% | 0.66 | 1 | Completed
ER6668LT | W213 | W213.A30320 | TOR Essential Defueling Safety Case | Draft Safety Case Requirements EAN - TASK E EAN (A - B De-risking) | 2022-05-24 | 2022-07-13 | 33 | 0 | 35 | 50 | 100% | 0.66 | 1 | Completed
ER6666LT | W209 | W209.5310 | HYB Essential Defueling Safety Case | Optioneering Complete - HYB Essential Defueling Safety Case | 2022-05-24 | 2022-05-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.5310 | TOR Essential Defueling Safety Case | Optioneering Complete - TOR Essential Defueling Safety Case | 2022-05-24 | 2022-05-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1420 | HYB Essential Defueling Safety Case | Prepare Draft Project Definition Document (PDD) | 2022-05-25 | 2022-05-31 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.1490 | HYB Essential Defueling Safety Case | Add Data to IAB Paper | 2022-05-25 | 2022-05-31 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.1440 | HYB Essential Defueling Safety Case | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 2022-05-25 | 2022-05-31 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.1430 | HYB Essential Defueling Safety Case | Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 2022-05-25 | 2022-05-31 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.1420 | TOR Essential Defueling Safety Case | Prepare Draft Project Definition Document (PDD) | 2022-05-25 | 2022-05-31 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.1490 | TOR Essential Defueling Safety Case | Add Data to IAB Paper | 2022-05-25 | 2022-05-31 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.1440 | TOR Essential Defueling Safety Case | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 2022-05-25 | 2022-05-31 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.1430 | TOR Essential Defueling Safety Case | Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 2022-05-25 | 2022-05-31 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.7930 | HYB Essential Defueling Safety Case | Verify Human Factors Integration Plan EAN and Issue for Technical Review (REV 000) | 2022-05-26 | 2022-06-17 | 4 | 0 | 14 | 22 | 100% | 0.18182 | 1 | Completed
ER6666LT | W209 | W209.A30430 | HYB Essential Defueling Safety Case | Technical Review of Reactor Internals & Structural Integrity During Defueling Report EAN (A-B-De-Risking) | 2022-05-26 | 2022-07-13 | 4 | 0 | 33 | 48 | 100% | 0.083333 | 1 | Completed
ER6668LT | W213 | W213.7930 | TOR Essential Defueling Safety Case | Verify Human Factors Integration Plan EAN and Issue for Technical Review (REV 000) | 2022-05-26 | 2022-06-17 | 4 | 0 | 14 | 22 | 100% | 0.18182 | 1 | Completed
ER6668LT | W213 | W213.A30430 | TOR Essential Defueling Safety Case | Technical Review of Reactor Internals & Structural Integrity During Defueling Report EAN (A-B-De-Risking) | 2022-05-26 | 2022-07-13 | 4 | 0 | 33 | 48 | 100% | 0.083333 | 1 | Completed
ER6666LT | W209 | W209.28690 | HYB Essential Defueling Safety Case | Technical Review of PCPV Liner Impact Assessment | 2022-05-27 | 2022-07-01 | 15 | 0 | 24 | 35 | 100% | 0.42857 | 1 | Completed
ER6668LT | W213 | W213.28690 | TOR Essential Defueling Safety Case | Technical Review of PCPV Liner Impact Assessment | 2022-05-27 | 2022-07-01 | 15 | 0 | 24 | 35 | 100% | 0.42857 | 1 | Completed
ER6371LT | W202 | 2940 | HRA Reactors Shutdown Essential Safety Cases | Issue final NSRS | 2022-05-27 | 2022-05-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | 2940 | HYA Reactors Shutdown Essential Safety Cases | Issue final NSRS | 2022-05-27 | 2022-05-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 2740 | HYA Fuel Handling Essential Safety Case | Issue final NSRS | 2022-05-27 | 2022-05-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1450 | HYB Essential Defueling Safety Case | Ensure Alignment of Schedule & Estimate | 2022-05-30 | 2022-05-31 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6666LT | W209 | W209.5040 | HYB Essential Defueling Safety Case | Response to Tech Review Comments | 2022-05-30 | 2022-07-01 | 11 | 0 | 23 | 32 | 100% | 0.34375 | 1 | Completed
ER6668LT | W213 | W213.1450 | TOR Essential Defueling Safety Case | Ensure Alignment of Schedule & Estimate | 2022-05-30 | 2022-05-31 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6668LT | W213 | W213.5040 | TOR Essential Defueling Safety Case | Response to Tech Review Comments | 2022-05-30 | 2022-07-01 | 11 | 0 | 23 | 32 | 100% | 0.34375 | 1 | Completed
ER6371LT | W202 | 2960 | HRA Reactors Shutdown Essential Safety Cases | Station agree NSRS | 2022-05-30 | 2022-05-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | 2980 | HRA Reactors Shutdown Essential Safety Cases | ED (DA) agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2022-05-30 | 2022-05-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | 2960 | HYA Reactors Shutdown Essential Safety Cases | Station agree NSRS | 2022-05-30 | 2022-05-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | 2980 | HYA Reactors Shutdown Essential Safety Cases | ED (DA) agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2022-05-30 | 2022-05-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 2760 | HYA Fuel Handling Essential Safety Case | Station agree NSRS | 2022-05-30 | 2022-05-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1470 | HYB Essential Defueling Safety Case | Complete Risk Log with Estimates | 2022-05-31 | 2022-05-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1470 | TOR Essential Defueling Safety Case | Complete Risk Log with Estimates | 2022-05-31 | 2022-05-31 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 2780 | HYA Fuel Handling Essential Safety Case | ED (DA) agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2022-05-31 | 2022-05-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1500 | HYB Essential Defueling Safety Case | PCL Validate & Approve Baseline Package for PRC Submission | 2022-06-01 | 2022-06-06 | 2 | 0 | 2 | 5 | 100% | 0.4 | 1 | Completed
ER6666LT | W209 | W209.5240 | HYB Essential Defueling Safety Case | Produce Summary Document Outlining Status of Quality of Build Records (Jacobs) - (Cost Summary) ## | 2022-06-01 | 2022-07-13 | 29 | 0 | 29 | 42 | 100% | 0.69048 | 1 | Completed
ER6666LT | W209 | W209.A26980 | HYB Essential Defueling Safety Case | Pre Job Brief for Review of FM Cyclic Duty EAN | 2022-06-01 | 2022-06-10 | 1 | 0 | 5 | 9 | 100% | 0.11111 | 1 | Completed
ER6666LT | W209 | W209.6130 | HYB Essential Defueling Safety Case | Prepare Spec for Fuel Route PSA Update EAN | 2022-06-01 | 2022-06-02 | 6 | 0 | 1 | 1 | 100% | 6 | 1 | Completed
ER6666LT | W209 | W209.6520 | HYB Essential Defueling Safety Case | Prepare Spec for Quality of Build Records Retrieval EAN | 2022-06-01 | 2022-07-01 | 21 | 0 | 21 | 30 | 100% | 0.7 | 1 | Completed
ER6666LT | W209 | W209.6670 | HYB Essential Defueling Safety Case | Prepare Spec for Define Failed Fuel Free Controls EAN | 2022-06-01 | 2022-07-01 | 5 | 0 | 21 | 30 | 100% | 0.16667 | 1 | Completed
ER6666LT | W209 | W209.A29310 | HYB Essential Defueling Safety Case | Draft Civil Integrity of Reactor Pressure Boundary Seals Integrity (Tech Report) - A - B De-risk Point | 2022-06-01 | 2022-07-13 | 5 | 0 | 28 | 42 | 100% | 0.11905 | 1 | Completed
ER6666LT | W209 | W209.A29550 | HYB Essential Defueling Safety Case | Verify Flow Induced Vibration EAN & Issue for Technical Review | 2022-06-01 | 2022-07-01 | 20 | 0 | 21 | 30 | 100% | 0.66667 | 1 | Completed
ER6668LT | W213 | W213.1500 | TOR Essential Defueling Safety Case | PCL Validate & Approve Baseline Package for PRC Submission | 2022-06-01 | 2022-06-06 | 2 | 0 | 2 | 5 | 100% | 0.4 | 1 | Completed
ER6668LT | W213 | W213.5240 | TOR Essential Defueling Safety Case | Produce Summary Document Outlining Status of Quality of Build Records (Jacobs) - (Cost Summary) ## | 2022-06-01 | 2022-07-13 | 29 | 0 | 29 | 42 | 100% | 0.69048 | 1 | Completed
ER6668LT | W213 | W213.A26980 | TOR Essential Defueling Safety Case | Pre Job Brief for Review of FM Cyclic Duty EAN | 2022-06-01 | 2022-06-10 | 1 | 0 | 5 | 9 | 100% | 0.11111 | 1 | Completed
ER6668LT | W213 | W213.6130 | TOR Essential Defueling Safety Case | Prepare Spec for Fuel Route PSA Update EAN | 2022-06-01 | 2022-06-02 | 6 | 0 | 1 | 1 | 100% | 6 | 1 | Completed
ER6668LT | W213 | W213.6520 | TOR Essential Defueling Safety Case | Prepare Spec for Quality of Build Records Retrieval EAN | 2022-06-01 | 2022-07-01 | 21 | 0 | 21 | 30 | 100% | 0.7 | 1 | Completed
ER6668LT | W213 | W213.6670 | TOR Essential Defueling Safety Case | Prepare Spec for Define Failed Fuel Free Controls EAN | 2022-06-01 | 2022-07-01 | 5 | 0 | 21 | 30 | 100% | 0.16667 | 1 | Completed
ER6668LT | W213 | W213.A29310 | TOR Essential Defueling Safety Case | Draft Civil Integrity of Reactor Pressure Boundary Seals Integrity (Tech Report) - A - B De-risk Point | 2022-06-01 | 2022-07-13 | 5 | 0 | 28 | 42 | 100% | 0.11905 | 1 | Completed
ER6668LT | W213 | W213.A29550 | TOR Essential Defueling Safety Case | Verify Flow Induced Vibration EAN & Issue for Technical Review | 2022-06-01 | 2022-07-01 | 20 | 0 | 21 | 30 | 100% | 0.66667 | 1 | Completed
ER6666LT | W209 | W209.6140 | HYB Essential Defueling Safety Case | Prepare Task Sheet for Fuel Route PSA Update EAN | 2022-06-02 | 2022-06-02 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.6150 | HYB Essential Defueling Safety Case | Approve Task Sheet for Fuel Route PSA Update EAN | 2022-06-02 | 2022-06-02 | 7 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.6140 | TOR Essential Defueling Safety Case | Prepare Task Sheet for Fuel Route PSA Update EAN | 2022-06-02 | 2022-06-02 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.6150 | TOR Essential Defueling Safety Case | Approve Task Sheet for Fuel Route PSA Update EAN | 2022-06-02 | 2022-06-02 | 7 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.7830 | HYB Essential Defueling Safety Case | Scope Assumptions Review PJB | 2022-06-03 | 2022-06-03 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.7830 | TOR Essential Defueling Safety Case | Scope Assumptions Review PJB | 2022-06-03 | 2022-06-03 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.8680 | HYB Essential Defueling Safety Case | Scope Assumptions Review (A-B De-risking) | 2022-06-06 | 2022-07-13 | 5 | 0 | 28 | 37 | 100% | 0.13514 | 1 | Completed
ER6668LT | W213 | W213.8680 | TOR Essential Defueling Safety Case | Scope Assumptions Review (A-B De-risking) | 2022-06-06 | 2022-07-13 | 5 | 0 | 28 | 37 | 100% | 0.13514 | 1 | Completed
ER6666LT | W209 | W209.3530 | HYB Essential Defueling Safety Case | Review Comments Addressed | 2022-06-06 | 2022-06-09 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6666LT | W209 | W209.1115 | HYB Essential Defueling Safety Case | Issue final NSRS | 2022-06-06 | 2022-06-06 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A26190 | HYB Essential Defueling Safety Case | Draft Civil Integrity of Pressure Boundary Integrity of Seals Report EAN (A-B-De-Risking) | 2022-06-06 | 2022-07-13 | 28 | 0 | 28 | 37 | 100% | 0.75676 | 1 | Completed
ER6666LT | W209 | W209.6390 | HYB Essential Defueling Safety Case | Approve Task Sheet for Update Basis of Analysis document EAN | 2022-06-06 | 2022-06-14 | 7 | 0 | 7 | 8 | 100% | 0.875 | 1 | Completed
ER6666LT | W209 | W209.A30540 | HYB Essential Defueling Safety Case | Draft Review of FM Cyclic Duty EAN (A - B De-risking) | 2022-06-06 | 2022-07-13 | 28 | 0 | 28 | 37 | 100% | 0.75676 | 1 | Completed
ER6668LT | W213 | W213.3530 | TOR Essential Defueling Safety Case | Review Comments Addressed | 2022-06-06 | 2022-06-09 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6668LT | W213 | W213.1115 | TOR Essential Defueling Safety Case | Issue final NSRS | 2022-06-06 | 2022-06-06 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A26190 | TOR Essential Defueling Safety Case | Draft Civil Integrity of Pressure Boundary Integrity of Seals Report EAN (A-B-De-Risking) | 2022-06-06 | 2022-07-13 | 28 | 0 | 28 | 37 | 100% | 0.75676 | 1 | Completed
ER6668LT | W213 | W213.6390 | TOR Essential Defueling Safety Case | Approve Task Sheet for Update Basis of Analysis document EAN | 2022-06-06 | 2022-06-14 | 7 | 0 | 7 | 8 | 100% | 0.875 | 1 | Completed
ER6668LT | W213 | W213.A30540 | TOR Essential Defueling Safety Case | Draft Review of FM Cyclic Duty EAN (A - B De-risking) | 2022-06-06 | 2022-07-13 | 28 | 0 | 28 | 37 | 100% | 0.75676 | 1 | Completed
ER6666LT | W209 | W209.A29790 | HYB Essential Defueling Safety Case | Pre Job Brief for Feasibility of Draining PVCS (Report) | 2022-06-07 | 2022-07-01 | 1 | 0 | 19 | 24 | 100% | 0.041667 | 1 | Completed
ER6668LT | W213 | W213.A29790 | TOR Essential Defueling Safety Case | Pre Job Brief for Feasibility of Draining PVCS (Report) | 2022-06-07 | 2022-07-01 | 1 | 0 | 19 | 24 | 100% | 0.041667 | 1 | Completed
ER6666LT | W209 | W209.1510 | HYB Essential Defueling Safety Case | Gate B PRC Paper Submission | 2022-06-08 | 2022-06-08 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1125 | HYB Essential Defueling Safety Case | DA & INA agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2022-06-08 | 2022-06-10 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6666LT | W209 | W209.1135 | HYB Essential Defueling Safety Case | Station agree NSRS | 2022-06-08 | 2022-06-10 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6668LT | W213 | W213.1510 | TOR Essential Defueling Safety Case | Gate B PRC Paper Submission | 2022-06-08 | 2022-06-08 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1125 | TOR Essential Defueling Safety Case | DA & INA agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2022-06-08 | 2022-06-10 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6668LT | W213 | W213.1135 | TOR Essential Defueling Safety Case | Station agree NSRS | 2022-06-08 | 2022-06-10 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6371LT | W202 | 2990 | HRA Reactors Shutdown Essential Safety Cases | SRD agree NSRS | 2022-06-08 | 2022-06-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | 2990 | HYA Reactors Shutdown Essential Safety Cases | SRD agree NSRS | 2022-06-08 | 2022-06-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 2790 | HYA Fuel Handling Essential Safety Case | SRD agree NSRS | 2022-06-08 | 2022-06-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1520 | HYB Essential Defueling Safety Case | PRC Members Review IAB Documentation | 2022-06-09 | 2022-06-15 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.1520 | TOR Essential Defueling Safety Case | PRC Members Review IAB Documentation | 2022-06-09 | 2022-06-15 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | 2992 | HRA Reactors Shutdown Essential Safety Cases | Share NSRS with NSC ahead of Meeting Date (T-2 wks) | 2022-06-09 | 2022-06-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | 2992 | HYA Reactors Shutdown Essential Safety Cases | Share NSRS with NSC ahead of Meeting Date (T-2 wks) | 2022-06-09 | 2022-06-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 2794 | HYA Fuel Handling Essential Safety Case | Share NSRS with NSC ahead of Meeting Date (T-2 wks) | 2022-06-09 | 2022-06-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A1620 | HNB Reactors Shutdown Essential Safety Cases | Develop Implementation & closeout Plan (HNB) | 2022-06-13 | 2022-08-10 | 13 | 0 | 42 | 58 | 100% | 0.22414 | 1 | Completed
ER6666LT | W209 | W209.7940 | HYB Essential Defueling Safety Case | Supplier Update and Issue Human Factors Integration Plan EAN (REV 000) | 2022-06-20 | 2022-07-06 | 4 | 0 | 13 | 16 | 100% | 0.25 | 1 | Completed
ER6668LT | W213 | W213.7940 | TOR Essential Defueling Safety Case | Supplier Update and Issue Human Factors Integration Plan EAN (REV 000) | 2022-06-20 | 2022-07-06 | 4 | 0 | 13 | 16 | 100% | 0.25 | 1 | Completed
ER6666LT | W209 | W209.1530 | HYB Essential Defueling Safety Case | Hold PRC Meeting | 2022-06-21 | 2022-06-21 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1530 | TOR Essential Defueling Safety Case | Hold PRC Meeting | 2022-06-21 | 2022-06-21 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1550 | HYB Essential Defueling Safety Case | Modify Estimate, Schedule & Risk Log as Required | 2022-06-22 | 2022-06-22 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1360 | HYB Essential Defueling Safety Case | >>>OUTGOING ENABLER (W150, W273) NSRS Scope Complete | 2022-06-22 | 2022-06-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.3160 | HYB Essential Defueling Safety Case | Discovery Milestone - NSRS Completion - Proceed with Safety Case (HYB) | 2022-06-22 | 2022-06-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1145 | HYB Essential Defueling Safety Case | NSRS Presented to NSC (for complex CAT 1 cases) | 2022-06-22 | 2022-06-22 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | 2995 | HRA Reactors Shutdown Essential Safety Cases | Share NSRS with NSC | 2022-06-22 | 2022-06-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | 2995 | HYA Reactors Shutdown Essential Safety Cases | Share NSRS with NSC | 2022-06-22 | 2022-06-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1550 | TOR Essential Defueling Safety Case | Modify Estimate, Schedule & Risk Log as Required | 2022-06-22 | 2022-06-22 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.3160 | TOR Essential Defueling Safety Case | Discovery Milestone - NSRS Completion - Proceed with Safety Case (TOR) | 2022-06-22 | 2022-06-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1145 | TOR Essential Defueling Safety Case | NSRS Presented to NSC (for complex CAT 1 cases) | 2022-06-22 | 2022-06-22 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 2795 | HYA Fuel Handling Essential Safety Case | Present NSRS to NSC Meeting | 2022-06-22 | 2022-06-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1032 | HYB Essential Defueling Safety Case | NSRS Presented at NSC - EC 371387 - HYB Essential Defueling Safety Case | 2022-06-22 | 2022-06-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1360 | TOR Essential Defueling Safety Case | >>>OUTGOING ENABLER (W152, W274) NSRS Scope Complete | 2022-06-22 | 2022-06-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1032 | TOR Essential Defueling Safety Case | NSRS Presented at NSC - EC 371387 - TOR Essential Defueling Safety Case | 2022-06-22 | 2022-06-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1560 | HYB Essential Defueling Safety Case | Modify IAB Paper as Required | 2022-06-23 | 2022-06-24 | 1 | 0 | 1 | 1 | 100% | 1 | 1 | Completed
ER6666LT | W209 | W209.28790 | HYB Essential Defueling Safety Case | Circulate NSRS for Relevant Stakeholders (A-B Part) | 2022-06-23 | 2022-07-13 | 5 | 0 | 14 | 20 | 100% | 0.25 | 1 | Completed
ER6668LT | W213 | W213.1560 | TOR Essential Defueling Safety Case | Modify IAB Paper as Required | 2022-06-23 | 2022-06-24 | 1 | 0 | 1 | 1 | 100% | 1 | 1 | Completed
ER6668LT | W213 | W213.28790 | TOR Essential Defueling Safety Case | Circulate NSRS for Relevant Stakeholders (A-B Part) | 2022-06-23 | 2022-07-13 | 5 | 0 | 14 | 20 | 100% | 0.25 | 1 | Completed
ER6666LT | W209 | W209.A30870 | HYB Essential Defueling Safety Case | Verify FPU Maintenance Work EAN & Issue for Technic (A-B De-Risking) | 2022-06-27 | 2022-07-13 | 25 | 0 | 12 | 16 | 100% | 1.5625 | 1 | Completed
ER6668LT | W213 | W213.A30870 | TOR Essential Defueling Safety Case | Verify FPU Maintenance Work EAN & Issue for Technic (A-B De-Risking) | 2022-06-27 | 2022-07-13 | 25 | 0 | 12 | 16 | 100% | 1.5625 | 1 | Completed
ER6666LT | W209 | W209.A28020 | HYB Essential Defueling Safety Case | Pre Job Brief for Update Basis of Analysis document EAN | 2022-07-01 | 2022-07-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A28420 | HYB Essential Defueling Safety Case | Pre Job Brief for Quality of Build Records Retrieval EAN | 2022-07-01 | 2022-07-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.6640 | HYB Essential Defueling Safety Case | Prepare Spec for Fuel Free Verification (FFV) Reports EAN | 2022-07-01 | 2022-07-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.A28020 | TOR Essential Defueling Safety Case | Pre Job Brief for Update Basis of Analysis document EAN | 2022-07-01 | 2022-07-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A28420 | TOR Essential Defueling Safety Case | Pre Job Brief for Quality of Build Records Retrieval EAN | 2022-07-01 | 2022-07-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.6640 | TOR Essential Defueling Safety Case | Prepare Spec for Fuel Free Verification (FFV) Reports EAN | 2022-07-01 | 2022-07-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.1630 | HYB Essential Defueling Safety Case | Gate B IAB Paper Submission | 2022-07-04 | 2022-07-04 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A25690 | HYB Essential Defueling Safety Case | Judgement Based Work Diversion EAN ## (Cost Summary) (Claim 2) | 2022-07-04 | 2023-03-31 | 191 | 0 | 191 | 270 | 100% | 0.70741 | 1 | Completed
ER6666LT | W209 | W209.A28430 | HYB Essential Defueling Safety Case | Draft Quality of Build Records Retrieval EAN (A - B Derisk) | 2022-07-04 | 2022-07-13 | 8 | 0 | 8 | 9 | 100% | 0.88889 | 1 | Completed
ER6666LT | W209 | W209.A28600 | HYB Essential Defueling Safety Case | Verify Radiological Consequences Following Failed CSP EAN & Issue for Technical Review | 2022-07-04 | 2022-07-06 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6666LT | W209 | W209.28700 | HYB Essential Defueling Safety Case | Supplier Update and Issue PCPV Liner Impact Assessment | 2022-07-04 | 2022-07-07 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6666LT | W209 | W209.6680 | HYB Essential Defueling Safety Case | Prepare Task Sheet for Define Failed Fuel Free Controls EAN | 2022-07-04 | 2022-07-05 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6666LT | W209 | W209.7610 | HYB Essential Defueling Safety Case | Issue Verified Defueling Engineering Specification | 2022-07-04 | 2022-07-07 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6666LT | W209 | W209.A30260 | HYB Essential Defueling Safety Case | Verify Define Nuclear Data (PANTHER Validation Calcs) EAN & Issue for Technical Review | 2022-07-04 | 2022-07-06 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6666LT | W209 | W209.A30370 | HYB Essential Defueling Safety Case | Draft Feasibility of Draining PVCS (Report) (A - B De-risking) | 2022-07-04 | 2022-07-13 | 8 | 0 | 8 | 9 | 100% | 0.88889 | 1 | Completed
ER6666LT | W209 | W209.A30390 | HYB Essential Defueling Safety Case | Technical Review of Review of Flow Induced Vibration EAN (A-B De-risking) | 2022-07-04 | 2022-07-13 | 8 | 0 | 8 | 9 | 100% | 0.88889 | 1 | Completed
ER6666LT | W209 | W209.A30400 | HYB Essential Defueling Safety Case | Draft Update Basis of Analysis document EAN (A - B De-risking) | 2022-07-04 | 2022-07-13 | 8 | 0 | 8 | 9 | 100% | 0.88889 | 1 | Completed
ER6666LT | W209 | W209.A30850 | HYB Essential Defueling Safety Case | Verify Judgement Based Work Diversion EAN and Issue for Technical Review | 2022-07-04 | 2022-09-23 | 3 | 0 | 58 | 81 | 100% | 0.037037 | 1 | Completed
ER6668LT | W213 | W213.1630 | TOR Essential Defueling Safety Case | Gate B IAB Paper Submission | 2022-07-04 | 2022-07-04 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A25690 | TOR Essential Defueling Safety Case | Judgement Based Work Diversion EAN ## (Cost Summary) (Claim 2) | 2022-07-04 | 2023-03-31 | 191 | 0 | 191 | 270 | 100% | 0.70741 | 1 | Completed
ER6668LT | W213 | W213.A28430 | TOR Essential Defueling Safety Case | Draft Quality of Build Records Retrieval EAN (A - B Derisk) | 2022-07-04 | 2022-07-13 | 8 | 0 | 8 | 9 | 100% | 0.88889 | 1 | Completed
ER6668LT | W213 | W213.A28600 | TOR Essential Defueling Safety Case | Verify Radiological Consequences Following Failed CSP EAN & Issue for Technical Review | 2022-07-04 | 2022-07-06 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6668LT | W213 | W213.28700 | TOR Essential Defueling Safety Case | Supplier Update and Issue PCPV Liner Impact Assessment | 2022-07-04 | 2022-07-07 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6668LT | W213 | W213.6680 | TOR Essential Defueling Safety Case | Prepare Task Sheet for Define Failed Fuel Free Controls EAN | 2022-07-04 | 2022-07-05 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6668LT | W213 | W213.7610 | TOR Essential Defueling Safety Case | Issue Verified Defueling Engineering Specification | 2022-07-04 | 2022-07-07 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6668LT | W213 | W213.A30260 | TOR Essential Defueling Safety Case | Verify Define Nuclear Data (PANTHER Validation Calcs) EAN & Issue for Technical Review | 2022-07-04 | 2022-07-06 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6668LT | W213 | W213.A30370 | TOR Essential Defueling Safety Case | Draft Feasibility of Draining PVCS (Report) (A - B De-risking) | 2022-07-04 | 2022-07-13 | 8 | 0 | 8 | 9 | 100% | 0.88889 | 1 | Completed
ER6668LT | W213 | W213.A30390 | TOR Essential Defueling Safety Case | Technical Review of Review of Flow Induced Vibration EAN (A-B De-risking) | 2022-07-04 | 2022-07-13 | 8 | 0 | 8 | 9 | 100% | 0.88889 | 1 | Completed
ER6668LT | W213 | W213.A30400 | TOR Essential Defueling Safety Case | Draft Update Basis of Analysis document EAN (A - B De-risking) | 2022-07-04 | 2022-07-13 | 8 | 0 | 8 | 9 | 100% | 0.88889 | 1 | Completed
ER6668LT | W213 | W213.A30850 | TOR Essential Defueling Safety Case | Verify Judgement Based Work Diversion EAN and Issue for Technical Review | 2022-07-04 | 2022-09-23 | 3 | 0 | 58 | 81 | 100% | 0.037037 | 1 | Completed
ER6666LT | W209 | W209.1580 | HYB Essential Defueling Safety Case | IAB Members Review IAB Documentation | 2022-07-05 | 2022-07-08 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6668LT | W213 | W213.1580 | TOR Essential Defueling Safety Case | IAB Members Review IAB Documentation | 2022-07-05 | 2022-07-08 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6666LT | W209 | W209.A26340 | HYB Essential Defueling Safety Case | Pre Job Brief for Graphite Summary Report EAN | 2022-07-06 | 2022-07-06 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.6690 | HYB Essential Defueling Safety Case | Approve Task Sheet for Define Failed Fuel Free Controls EAN | 2022-07-06 | 2022-07-07 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6668LT | W213 | W213.A26340 | TOR Essential Defueling Safety Case | Pre Job Brief for Graphite Summary Report EAN | 2022-07-06 | 2022-07-06 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.6690 | TOR Essential Defueling Safety Case | Approve Task Sheet for Define Failed Fuel Free Controls EAN | 2022-07-06 | 2022-07-07 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6666LT | W209 | W209.A28610 | HYB Essential Defueling Safety Case | Technical Review of Radiological Consequences Following Failed CSP EAN (A - B Derisk) | 2022-07-07 | 2022-07-13 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.7950 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Human Factors Integration Plan EAN to CDMS (REV 000) | 2022-07-07 | 2022-07-13 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.A30270 | HYB Essential Defueling Safety Case | Technical Review of Define Nuclear Data (PANTHER Validation Calcs) EAN - (CLAIM 1 - A - B De-risking) | 2022-07-07 | 2022-07-13 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.A30530 | HYB Essential Defueling Safety Case | Draft Graphite Summary Report EAN (A-B De-risking) | 2022-07-07 | 2022-07-13 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.A28610 | TOR Essential Defueling Safety Case | Technical Review of Radiological Consequences Following Failed CSP EAN (A - B Derisk) | 2022-07-07 | 2022-07-13 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.7950 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Human Factors Integration Plan EAN to CDMS (REV 000) | 2022-07-07 | 2022-07-13 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.A30270 | TOR Essential Defueling Safety Case | Technical Review of Define Nuclear Data (PANTHER Validation Calcs) EAN - (CLAIM 1 - A - B De-risking) | 2022-07-07 | 2022-07-13 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.A30530 | TOR Essential Defueling Safety Case | Draft Graphite Summary Report EAN (A-B De-risking) | 2022-07-07 | 2022-07-13 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.28710 | HYB Essential Defueling Safety Case | Complete TR Form and Upload PCPV Liner Impact Assessment to CDMS | 2022-07-08 | 2022-07-13 | 4 | 0 | 4 | 5 | 100% | 0.8 | 1 | Completed
ER6666LT | W209 | W209.A28820 | HYB Essential Defueling Safety Case | Pre Job Brief for Define Failed Fuel Free Controls EAN | 2022-07-08 | 2022-07-08 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.7620 | HYB Essential Defueling Safety Case | EDF Technical Review | 2022-07-08 | 2022-07-13 | 4 | 0 | 4 | 5 | 100% | 0.8 | 1 | Completed
ER6666LT | W209 | W209.8690 | HYB Essential Defueling Safety Case | Prepare Task Sheet for Fuel Free Verification (FFV) Reports EAN | 2022-07-08 | 2022-07-13 | 4 | 0 | 4 | 5 | 100% | 0.8 | 1 | Completed
ER6668LT | W213 | W213.28710 | TOR Essential Defueling Safety Case | Complete TR Form and Upload PCPV Liner Impact Assessment to CDMS | 2022-07-08 | 2022-07-13 | 4 | 0 | 4 | 5 | 100% | 0.8 | 1 | Completed
ER6668LT | W213 | W213.A28820 | TOR Essential Defueling Safety Case | Pre Job Brief for Define Failed Fuel Free Controls EAN | 2022-07-08 | 2022-07-08 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.7620 | TOR Essential Defueling Safety Case | EDF Technical Review | 2022-07-08 | 2022-07-13 | 4 | 0 | 4 | 5 | 100% | 0.8 | 1 | Completed
ER6668LT | W213 | W213.8690 | TOR Essential Defueling Safety Case | Prepare Task Sheet for Fuel Free Verification (FFV) Reports EAN | 2022-07-08 | 2022-07-13 | 4 | 0 | 4 | 5 | 100% | 0.8 | 1 | Completed
ER6666LT | W209 | W209.A30580 | HYB Essential Defueling Safety Case | Draft Define Failed Fuel Free Controls EAN | 2022-07-11 | 2022-07-13 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6666LT | W209 | W209.A30780 | HYB Essential Defueling Safety Case | Verify FPU Integrity Work EAN & Issue for Technic (A - B Derisk to Claim 3 and 5) | 2022-07-11 | 2022-07-13 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6668LT | W213 | W213.A30580 | TOR Essential Defueling Safety Case | Draft Define Failed Fuel Free Controls EAN | 2022-07-11 | 2022-07-13 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6668LT | W213 | W213.A30780 | TOR Essential Defueling Safety Case | Verify FPU Integrity Work EAN & Issue for Technic (A - B Derisk to Claim 3 and 5) | 2022-07-11 | 2022-07-13 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6666LT | W209 | W209.28720 | HYB Essential Defueling Safety Case | PCPV Liner Impact Assessment Available | 2022-07-13 | 2022-07-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.7960 | HYB Essential Defueling Safety Case | Human Factors Integration Plan EAN Available (REV 000) (A-B Derisk for WP1 & WP2) | 2022-07-13 | 2022-07-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.28720 | TOR Essential Defueling Safety Case | PCPV Liner Impact Assessment Available | 2022-07-13 | 2022-07-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.7960 | TOR Essential Defueling Safety Case | Human Factors Integration Plan EAN Available (REV 000) (A-B Derisk for WP1 & WP2) | 2022-07-13 | 2022-07-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1058 | HYB Essential Defueling Safety Case | Gate B - IAB Paper Approval (HYB) | 2022-07-14 | 2022-07-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1155 | HYB Essential Defueling Safety Case | Circulate NSRS for Relevant Stakeholders | 2022-07-14 | 2022-08-01 | 5 | 0 | 13 | 18 | 100% | 0.27778 | 1 | Completed
ER6666LT | W209 | W209.7630 | HYB Essential Defueling Safety Case | Production of Civils Assessment Report for PCPV Integrity Justification | 2022-07-14 | 2022-08-05 | 1 | 0 | 17 | 22 | 100% | 0.045455 | 1 | Completed
ER6666LT | W209 | W209.7650 | HYB Essential Defueling Safety Case | Production of Civils Assessment Report for Seismic Assessment | 2022-07-14 | 2022-08-05 | 40 | 0 | 17 | 22 | 100% | 1.8182 | 1 | Completed
ER6666LT | W209 | W209.A29720 | HYB Essential Defueling Safety Case | ALARP Review of Not Draining the PVCS (Report) ## (Cost Summary) (Claim 2) | 2022-07-14 | 2023-05-19 | 205 | 0 | 213 | 309 | 100% | 0.66343 | 1 | Completed
ER6666LT | W209 | W209.A29740 | HYB Essential Defueling Safety Case | Draft PARTIAL Drain down of the PVCS prior to Defuelling (Report) | 2022-07-14 | 2022-07-29 | 41 | 0 | 11 | 15 | 100% | 2.7333 | 1 | Completed
ER6668LT | W213 | W213.1058 | TOR Essential Defueling Safety Case | Gate B - IAB Paper Approval (TOR) | 2022-07-14 | 2022-07-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1155 | TOR Essential Defueling Safety Case | Circulate NSRS for Relevant Stakeholders | 2022-07-14 | 2022-08-01 | 5 | 0 | 13 | 18 | 100% | 0.27778 | 1 | Completed
ER6668LT | W213 | W213.7630 | TOR Essential Defueling Safety Case | Production of Civils Assessment Report for PCPV Integrity Justification | 2022-07-14 | 2022-08-05 | 1 | 0 | 17 | 22 | 100% | 0.045455 | 1 | Completed
ER6668LT | W213 | W213.7650 | TOR Essential Defueling Safety Case | Production of Civils Assessment Report for Seismic Assessment | 2022-07-14 | 2022-08-05 | 40 | 0 | 17 | 22 | 100% | 1.8182 | 1 | Completed
ER6668LT | W213 | W213.A29720 | TOR Essential Defueling Safety Case | ALARP Review of Not Draining the PVCS (Report) ## (Cost Summary) (Claim 2) | 2022-07-14 | 2023-05-19 | 205 | 0 | 213 | 309 | 100% | 0.66343 | 1 | Completed
ER6668LT | W213 | W213.A29740 | TOR Essential Defueling Safety Case | Draft PARTIAL Drain down of the PVCS prior to Defuelling (Report) | 2022-07-14 | 2022-07-29 | 41 | 0 | 11 | 15 | 100% | 2.7333 | 1 | Completed
ER6666LT | W209 | W209.3110 | HYB Essential Defueling Safety Case | Hold IAB | 2022-07-14 | 2022-07-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A25850 | HYB Essential Defueling Safety Case | Safety Case Requirements EAN - TASK E EAN ## (Cost Summary) (Claim 2) | 2022-07-14 | 2023-04-21 | 196 | 0 | 196 | 281 | 100% | 0.69751 | 1 | Completed
ER6666LT | W209 | W209.A25870 | HYB Essential Defueling Safety Case | Draft Safety Case Requirements EAN - TASK E EAN | 2022-07-14 | 2022-09-29 | 34 | 0 | 55 | 77 | 100% | 0.44156 | 1 | Completed
ER6666LT | W209 | W209.A25930 | HYB Essential Defueling Safety Case | Civil Assesment of the Ponds at Low Temperature EAN ## (Cost Summary) (Claim 2) | 2022-07-14 | 2022-12-07 | 104 | 0 | 104 | 146 | 100% | 0.71233 | 1 | Completed
ER6666LT | W209 | W209.A25950 | HYB Essential Defueling Safety Case | Draft Civil Assesment of the Ponds at Low Temperature EAN | 2022-07-14 | 2022-08-05 | 22 | 0 | 17 | 22 | 100% | 1 | 1 | Completed
ER6666LT | W209 | W209.A26010 | HYB Essential Defueling Safety Case | Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN ## (Cost Summary) (Claim 3) | 2022-07-14 | 2022-12-07 | 104 | 0 | 104 | 146 | 100% | 0.71233 | 1 | Completed
ER6666LT | W209 | W209.A26030 | HYB Essential Defueling Safety Case | Draft Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN | 2022-07-14 | 2022-08-05 | 30 | 0 | 16 | 22 | 100% | 1.3636 | 1 | Completed
ER6666LT | W209 | W209.A26170 | HYB Essential Defueling Safety Case | Pressure Boundary Integrity of Seals Report EAN ## (Cost Summary) (Claim 3) | 2022-07-14 | 2022-11-30 | 99 | 0 | 99 | 139 | 100% | 0.71223 | 1 | Completed
ER6666LT | W209 | W209.A26250 | HYB Essential Defueling Safety Case | Reactor Internals & Structural Integrity During Defueling Report EAN ## (Cost Summary) (Claim 3) | 2022-07-14 | 2022-11-04 | 86 | 0 | 81 | 113 | 100% | 0.76106 | 1 | Completed
ER6666LT | W209 | W209.A26290 | HYB Essential Defueling Safety Case | Technical Review of Reactor Internals & Structural Integrity During Defueling Report EAN | 2022-07-14 | 2022-08-19 | 21 | 0 | 27 | 36 | 100% | 0.58333 | 1 | Completed
ER6666LT | W209 | W209.A26330 | HYB Essential Defueling Safety Case | Graphite Summary Report EAN ## (Cost Summary) (Claim 3) | 2022-07-14 | 2023-03-03 | 163 | 0 | 163 | 232 | 100% | 0.70259 | 1 | Completed
ER6666LT | W209 | W209.A26350 | HYB Essential Defueling Safety Case | Draft Graphite Summary Report EAN | 2022-07-14 | 2023-01-31 | 31 | 0 | 139 | 201 | 100% | 0.15423 | 1 | Completed
ER6666LT | W209 | W209.A26730 | HYB Essential Defueling Safety Case | Boron Bead Inj Feasibility & Boron Bead Injection Feasibility & Control Rod Isolation EAN ## (Cost Summary) (Claim 1) | 2022-07-14 | 2023-04-21 | 196 | 0 | 196 | 281 | 100% | 0.69751 | 1 | Completed
ER6666LT | W209 | W209.A26750 | HYB Essential Defueling Safety Case | Draft Boron Bead Injection Feasibility & Control Rod Isolation EAN | 2022-07-14 | 2022-09-08 | 40 | 0 | 40 | 56 | 100% | 0.71429 | 1 | Completed
ER6666LT | W209 | W209.A26970 | HYB Essential Defueling Safety Case | Review of FM Cyclic Duty EAN ## (Cost Summary) (Claim 3) | 2022-07-14 | 2022-10-31 | 66 | 0 | 76 | 109 | 100% | 0.6055 | 1 | Completed
ER6666LT | W209 | W209.A26990 | HYB Essential Defueling Safety Case | Draft Review of FM Cyclic Duty EAN | 2022-07-14 | 2022-07-22 | 41 | 0 | 6 | 8 | 100% | 5.125 | 1 | Completed
ER6666LT | W209 | W209.A27050 | HYB Essential Defueling Safety Case | FPU Integrity Analysis EAN ## (Cost Summary) (Claim 3) | 2022-07-14 | 2023-05-12 | 203 | 0 | 208 | 302 | 100% | 0.67219 | 1 | Completed
ER6666LT | W209 | W209.A27080 | HYB Essential Defueling Safety Case | Verify Review of FPU Integrity Analysis EAN & Issue for Technical Review | 2022-07-14 | 2023-02-17 | 43 | 0 | 153 | 218 | 100% | 0.19725 | 1 | Completed
ER6666LT | W209 | W209.A27170 | HYB Essential Defueling Safety Case | Technical Review of Review of Flow Induced Vibration EAN | 2022-07-14 | 2022-09-02 | 6 | 0 | 36 | 50 | 100% | 0.12 | 1 | Completed
ER6666LT | W209 | W209.A27370 | HYB Essential Defueling Safety Case | Fuel Route Defueling PSA Update ## (Cost Summary) (Claim 5) | 2022-07-14 | 2024-07-31 | 518 | 0 | 518 | 748 | 100% | 0.69251 | 1 | Completed
ER6666LT | W209 | W209.A28010 | HYB Essential Defueling Safety Case | Update Basis of Analysis document ## (Cost Summary) (Claim 4) | 2022-07-14 | 2023-03-07 | 165 | 0 | 165 | 236 | 100% | 0.69915 | 1 | Completed
ER6666LT | W209 | W209.A28030 | HYB Essential Defueling Safety Case | Draft Update Basis of Analysis document | 2022-07-14 | 2022-07-15 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6666LT | W209 | W209.A28090 | HYB Essential Defueling Safety Case | Develop FEA Model ## (Cost Summary) (Claim 4) | 2022-07-14 | 2022-08-31 | 36 | 0 | 33 | 48 | 100% | 0.75 | 1 | Completed
ER6666LT | W209 | W209.A28110 | HYB Essential Defueling Safety Case | Develop FEA Model | 2022-07-14 | 2022-07-18 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6666LT | W209 | W209.A28410 | HYB Essential Defueling Safety Case | Summary of Credible Start of Life Defects EAN ## (Cost Summary) (Claim 4) | 2022-07-14 | 2022-12-22 | 123 | 0 | 114 | 161 | 100% | 0.76398 | 1 | Completed
ER6666LT | W209 | W209.A28570 | HYB Essential Defueling Safety Case | Radiological Consequences Following Failed CSP EAN ## (Cost Summary) (Claim 4) | 2022-07-14 | 2023-03-07 | 165 | 0 | 165 | 236 | 100% | 0.69915 | 1 | Completed
ER6666LT | W209 | W209.A28730 | HYB Essential Defueling Safety Case | Fuel Free Verification (FFV) Reports EAN ## (Cost Summary) (Claim 6) | 2022-07-14 | 2023-03-31 | 163 | 0 | 182 | 260 | 100% | 0.62692 | 1 | Completed
ER6666LT | W209 | W209.A28810 | HYB Essential Defueling Safety Case | Define Failed Fuel Free Controls File Note ## (Cost Summary) (Claim 6) | 2022-07-14 | 2022-12-23 | 116 | 0 | 116 | 162 | 100% | 0.71605 | 1 | Completed
ER6666LT | W209 | W209.A28830 | HYB Essential Defueling Safety Case | Draft Define Failed Fuel Free Controls File Note (Rhod) | 2022-07-14 | 2022-12-09 | 53 | 0 | 106 | 148 | 100% | 0.35811 | 1 | Completed
ER6666LT | W209 | W209.6650 | HYB Essential Defueling Safety Case | Prepare Task Sheet for Fuel Free Verification methods, an assessment against the ALARP principle EAN | 2022-07-14 | 2022-07-15 | 6 | 0 | 1 | 1 | 100% | 6 | 1 | Completed
ER6666LT | W209 | W209.A29370 | HYB Essential Defueling Safety Case | Cooling Plant Availability Review EAN ## (Cost Summary) (Claim 2) | 2022-07-14 | 2023-02-17 | 147 | 0 | 152 | 218 | 100% | 0.67431 | 1 | Completed
ER6666LT | W209 | W209.A29390 | HYB Essential Defueling Safety Case | Draft Cooling Plant Availability Review EAN | 2022-07-14 | 2022-11-24 | 67 | 0 | 94 | 133 | 100% | 0.50376 | 1 | Completed
ER6666LT | W209 | W209.A29450 | HYB Essential Defueling Safety Case | Cooling Plant OPEX Study EAN ## (Cost Summary) (Claim 2) | 2022-07-14 | 2022-11-11 | 86 | 0 | 86 | 120 | 100% | 0.71667 | 1 | Completed
ER6666LT | W209 | W209.A29470 | HYB Essential Defueling Safety Case | Draft Cooling Plant OPEX Study EAN | 2022-07-14 | 2022-08-19 | 36 | 0 | 26 | 36 | 100% | 1 | 1 | Completed
ER6666LT | W209 | W209.7840 | HYB Essential Defueling Safety Case | Scope Assumptions Review | 2022-07-14 | 2022-08-03 | 15 | 0 | 15 | 20 | 100% | 0.75 | 1 | Completed
ER6666LT | W209 | W209.25760 | HYB Essential Defueling Safety Case | Human Factors ## (Cost Summary) (Claim 5) | 2022-07-14 | 2024-03-28 | 433 | 0 | 433 | 623 | 100% | 0.69502 | 1 | Completed
ER6666LT | W209 | W209.A29780 | HYB Essential Defueling Safety Case | Feasibility of Draining PVCS (Report) ## (Cost Summary) (Claim 2) | 2022-07-14 | 2022-11-23 | 99 | 0 | 93 | 132 | 100% | 0.75 | 1 | Completed
ER6666LT | W209 | W209.A29800 | HYB Essential Defueling Safety Case | Draft Feasibility of Draining PVCS (Report) | 2022-07-14 | 2022-09-05 | 42 | 0 | 36 | 53 | 100% | 0.79245 | 1 | Completed
ER6666LT | W209 | W209.A29860 | HYB Essential Defueling Safety Case | FPU Maintenance Analysis EAN ## (Cost Summary) (Claim 3) | 2022-07-14 | 2022-09-09 | 41 | 0 | 41 | 57 | 100% | 0.7193 | 1 | Completed
ER6666LT | W209 | W209.A29880 | HYB Essential Defueling Safety Case | Draft Review of FPU Maintenance Analysis EAN | 2022-07-14 | 2022-07-14 | 26 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.8650 | HYB Essential Defueling Safety Case | PJB for Human Factors Integration Plan EAN (REV 000) | 2022-07-14 | 2022-07-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A30590 | HYB Essential Defueling Safety Case | FM Direct Process Protection Design ## (Cost Summary) (Claim 5) | 2022-07-14 | 2023-05-24 | 360 | 0 | 216 | 314 | 100% | 1.1465 | 1 | Completed
ER6666LT | W209 | W209.8720 | HYB Essential Defueling Safety Case | PJB for FM Direct Process Protection Design | 2022-07-14 | 2023-05-24 | 1 | 0 | 216 | 314 | 100% | 0.0031847 | 1 | Completed
ER6666LT | W209 | W209.A30660 | HYB Essential Defueling Safety Case | Flow Induced Vibration EAN ## (Cost Summary) (Claim 3) | 2022-07-14 | 2022-10-31 | 62 | 0 | 76 | 109 | 100% | 0.56881 | 1 | Completed
ER6666LT | W209 | W209.8860 | HYB Essential Defueling Safety Case | (B - C SANCTION) - Project Management - (Cost Summary) ## (B to C) | 2022-07-14 | 2024-02-23 | 298 | 0 | 408 | 589 | 100% | 0.50594 | 1 | Completed
ER6666LT | W209 | W209.8870 | HYB Essential Defueling Safety Case | (B - C SANCTION) - Safety Case Development - (Cost Summary) ## (B to C) | 2022-07-14 | 2024-02-23 | 298 | 0 | 408 | 589 | 100% | 0.50594 | 1 | Completed
ER6666LT | W209 | W209.A30770 | HYB Essential Defueling Safety Case | Draft Summary of Credible Start of Life Defects EAN | 2022-07-14 | 2022-11-22 | 11 | 0 | 93 | 131 | 100% | 0.083969 | 1 | Completed
ER6666LT | W209 | W209.A30790 | HYB Essential Defueling Safety Case | Technical Review of Define Nuclear Data (PANTHER Validation Calcs) EAN | 2022-07-14 | 2022-12-16 | 12 | 0 | 111 | 155 | 100% | 0.077419 | 1 | Completed
ER6666LT | W209 | W209.A30810 | HYB Essential Defueling Safety Case | Draft Civil Integrity of Pressure Boundary Integrity of Seals Report EAN | 2022-07-14 | 2022-07-15 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6666LT | W209 | W209.A30830 | HYB Essential Defueling Safety Case | Technical Review of Radiological Consequences Following Failed CSP EAN | 2022-07-14 | 2023-02-20 | 8 | 0 | 153 | 221 | 100% | 0.036199 | 1 | Completed
ER6666LT | W209 | W209.A30840 | HYB Essential Defueling Safety Case | Define Nuclear Data (PANTHER Validation Calcs) EAN ## (Cost Summary) (Claim 1) | 2022-07-14 | 2023-01-13 | 123 | 0 | 127 | 183 | 100% | 0.67213 | 1 | Completed
ER6668LT | W213 | W213.3110 | TOR Essential Defueling Safety Case | Hold IAB | 2022-07-14 | 2022-07-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A25850 | TOR Essential Defueling Safety Case | Safety Case Requirements EAN - TASK E EAN ## (Cost Summary) (Claim 2) | 2022-07-14 | 2023-04-21 | 196 | 0 | 196 | 281 | 100% | 0.69751 | 1 | Completed
ER6668LT | W213 | W213.A25870 | TOR Essential Defueling Safety Case | Draft Safety Case Requirements EAN - TASK E EAN | 2022-07-14 | 2022-09-29 | 34 | 0 | 55 | 77 | 100% | 0.44156 | 1 | Completed
ER6668LT | W213 | W213.A25930 | TOR Essential Defueling Safety Case | Civil Assesment of the Ponds at Low Temperature EAN ## (Cost Summary) (Claim 2) | 2022-07-14 | 2022-12-07 | 104 | 0 | 104 | 146 | 100% | 0.71233 | 1 | Completed
ER6668LT | W213 | W213.A25950 | TOR Essential Defueling Safety Case | Draft Civil Assesment of the Ponds at Low Temperature EAN | 2022-07-14 | 2022-08-05 | 22 | 0 | 17 | 22 | 100% | 1 | 1 | Completed
ER6668LT | W213 | W213.A26010 | TOR Essential Defueling Safety Case | Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN ## (Cost Summary) (Claim 3) | 2022-07-14 | 2022-12-07 | 104 | 0 | 104 | 146 | 100% | 0.71233 | 1 | Completed
ER6668LT | W213 | W213.A26030 | TOR Essential Defueling Safety Case | Draft Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN | 2022-07-14 | 2022-08-05 | 30 | 0 | 16 | 22 | 100% | 1.3636 | 1 | Completed
ER6668LT | W213 | W213.A26170 | TOR Essential Defueling Safety Case | Pressure Boundary Integrity of Seals Report EAN ## (Cost Summary) (Claim 3) | 2022-07-14 | 2022-11-30 | 99 | 0 | 99 | 139 | 100% | 0.71223 | 1 | Completed
ER6668LT | W213 | W213.A26250 | TOR Essential Defueling Safety Case | Reactor Internals & Structural Integrity During Defueling Report EAN ## (Cost Summary) (Claim 3) | 2022-07-14 | 2022-11-04 | 86 | 0 | 81 | 113 | 100% | 0.76106 | 1 | Completed
ER6668LT | W213 | W213.A26290 | TOR Essential Defueling Safety Case | Technical Review of Reactor Internals & Structural Integrity During Defueling Report EAN | 2022-07-14 | 2022-08-19 | 21 | 0 | 27 | 36 | 100% | 0.58333 | 1 | Completed
ER6668LT | W213 | W213.A26330 | TOR Essential Defueling Safety Case | Graphite Summary Report EAN ## (Cost Summary) (Claim 3) | 2022-07-14 | 2023-03-03 | 163 | 0 | 163 | 232 | 100% | 0.70259 | 1 | Completed
ER6668LT | W213 | W213.A26350 | TOR Essential Defueling Safety Case | Draft Graphite Summary Report EAN | 2022-07-14 | 2023-01-31 | 31 | 0 | 139 | 201 | 100% | 0.15423 | 1 | Completed
ER6668LT | W213 | W213.A26730 | TOR Essential Defueling Safety Case | Boron Bead Inj Feasibility & Boron Bead Injection Feasibility & Control Rod Isolation EAN ## (Cost Summary) (Claim 1) | 2022-07-14 | 2023-04-21 | 196 | 0 | 196 | 281 | 100% | 0.69751 | 1 | Completed
ER6668LT | W213 | W213.A26750 | TOR Essential Defueling Safety Case | Draft Boron Bead Injection Feasibility & Control Rod Isolation EAN | 2022-07-14 | 2022-09-08 | 40 | 0 | 40 | 56 | 100% | 0.71429 | 1 | Completed
ER6668LT | W213 | W213.A26970 | TOR Essential Defueling Safety Case | Review of FM Cyclic Duty EAN ## (Cost Summary) (Claim 3) | 2022-07-14 | 2022-10-31 | 66 | 0 | 76 | 109 | 100% | 0.6055 | 1 | Completed
ER6668LT | W213 | W213.A26990 | TOR Essential Defueling Safety Case | Draft Review of FM Cyclic Duty EAN | 2022-07-14 | 2022-07-22 | 41 | 0 | 6 | 8 | 100% | 5.125 | 1 | Completed
ER6668LT | W213 | W213.A27050 | TOR Essential Defueling Safety Case | FPU Integrity Analysis EAN ## (Cost Summary) (Claim 3) | 2022-07-14 | 2023-05-12 | 203 | 0 | 208 | 302 | 100% | 0.67219 | 1 | Completed
ER6668LT | W213 | W213.A27080 | TOR Essential Defueling Safety Case | Verify Review of FPU Integrity Analysis EAN & Issue for Technical Review | 2022-07-14 | 2023-02-17 | 43 | 0 | 153 | 218 | 100% | 0.19725 | 1 | Completed
ER6668LT | W213 | W213.A27170 | TOR Essential Defueling Safety Case | Technical Review of Review of Flow Induced Vibration EAN | 2022-07-14 | 2022-09-02 | 6 | 0 | 36 | 50 | 100% | 0.12 | 1 | Completed
ER6668LT | W213 | W213.A27370 | TOR Essential Defueling Safety Case | Fuel Route Defueling PSA Update ## (Cost Summary) (Claim 5) | 2022-07-14 | 2024-07-31 | 518 | 0 | 518 | 748 | 100% | 0.69251 | 1 | Completed
ER6668LT | W213 | W213.A28010 | TOR Essential Defueling Safety Case | Update Basis of Analysis document ## (Cost Summary) (Claim 4) | 2022-07-14 | 2023-03-07 | 165 | 0 | 165 | 236 | 100% | 0.69915 | 1 | Completed
ER6668LT | W213 | W213.A28030 | TOR Essential Defueling Safety Case | Draft Update Basis of Analysis document | 2022-07-14 | 2022-07-15 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6668LT | W213 | W213.A28090 | TOR Essential Defueling Safety Case | Develop FEA Model ## (Cost Summary) (Claim 4) | 2022-07-14 | 2022-08-31 | 36 | 0 | 33 | 48 | 100% | 0.75 | 1 | Completed
ER6668LT | W213 | W213.A28110 | TOR Essential Defueling Safety Case | Develop FEA Model | 2022-07-14 | 2022-07-18 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6668LT | W213 | W213.A28410 | TOR Essential Defueling Safety Case | Summary of Credible Start of Life Defects EAN ## (Cost Summary) (Claim 4) | 2022-07-14 | 2022-12-22 | 123 | 0 | 114 | 161 | 100% | 0.76398 | 1 | Completed
ER6668LT | W213 | W213.A28570 | TOR Essential Defueling Safety Case | Radiological Consequences Following Failed CSP EAN ## (Cost Summary) (Claim 4) | 2022-07-14 | 2023-03-07 | 165 | 0 | 165 | 236 | 100% | 0.69915 | 1 | Completed
ER6668LT | W213 | W213.A28730 | TOR Essential Defueling Safety Case | Fuel Free Verification (FFV) Reports EAN ## (Cost Summary) (Claim 6) | 2022-07-14 | 2023-03-31 | 163 | 0 | 182 | 260 | 100% | 0.62692 | 1 | Completed
ER6668LT | W213 | W213.A28810 | TOR Essential Defueling Safety Case | Define Failed Fuel Free Controls File Note ## (Cost Summary) (Claim 6) | 2022-07-14 | 2022-12-23 | 116 | 0 | 116 | 162 | 100% | 0.71605 | 1 | Completed
ER6668LT | W213 | W213.A28830 | TOR Essential Defueling Safety Case | Draft Define Failed Fuel Free Controls File Note (Rhod) | 2022-07-14 | 2022-12-09 | 53 | 0 | 106 | 148 | 100% | 0.35811 | 1 | Completed
ER6668LT | W213 | W213.6650 | TOR Essential Defueling Safety Case | Prepare Task Sheet for Fuel Free Verification methods, an assessment against the ALARP principle EAN | 2022-07-14 | 2022-07-15 | 6 | 0 | 1 | 1 | 100% | 6 | 1 | Completed
ER6668LT | W213 | W213.A29370 | TOR Essential Defueling Safety Case | Cooling Plant Availability Review EAN ## (Cost Summary) (Claim 2) | 2022-07-14 | 2023-02-17 | 147 | 0 | 152 | 218 | 100% | 0.67431 | 1 | Completed
ER6668LT | W213 | W213.A29390 | TOR Essential Defueling Safety Case | Draft Cooling Plant Availability Review EAN | 2022-07-14 | 2022-11-24 | 67 | 0 | 94 | 133 | 100% | 0.50376 | 1 | Completed
ER6668LT | W213 | W213.A29450 | TOR Essential Defueling Safety Case | Cooling Plant OPEX Study EAN ## (Cost Summary) (Claim 2) | 2022-07-14 | 2022-11-11 | 86 | 0 | 86 | 120 | 100% | 0.71667 | 1 | Completed
ER6668LT | W213 | W213.A29470 | TOR Essential Defueling Safety Case | Draft Cooling Plant OPEX Study EAN | 2022-07-14 | 2022-08-19 | 36 | 0 | 26 | 36 | 100% | 1 | 1 | Completed
ER6668LT | W213 | W213.7840 | TOR Essential Defueling Safety Case | Scope Assumptions Review | 2022-07-14 | 2022-08-03 | 15 | 0 | 15 | 20 | 100% | 0.75 | 1 | Completed
ER6668LT | W213 | W213.25760 | TOR Essential Defueling Safety Case | Human Factors ## (Cost Summary) (Claim 5) | 2022-07-14 | 2024-03-28 | 466 | 0 | 432 | 623 | 100% | 0.74799 | 1 | Completed
ER6668LT | W213 | W213.A29780 | TOR Essential Defueling Safety Case | Feasibility of Draining PVCS (Report) ## (Cost Summary) (Claim 2) | 2022-07-14 | 2022-11-23 | 99 | 0 | 93 | 132 | 100% | 0.75 | 1 | Completed
ER6668LT | W213 | W213.A29800 | TOR Essential Defueling Safety Case | Draft Feasibility of Draining PVCS (Report) | 2022-07-14 | 2022-09-05 | 42 | 0 | 36 | 53 | 100% | 0.79245 | 1 | Completed
ER6668LT | W213 | W213.A29860 | TOR Essential Defueling Safety Case | FPU Maintenance Analysis EAN ## (Cost Summary) (Claim 3) | 2022-07-14 | 2022-09-09 | 41 | 0 | 41 | 57 | 100% | 0.7193 | 1 | Completed
ER6668LT | W213 | W213.A29880 | TOR Essential Defueling Safety Case | Draft Review of FPU Maintenance Analysis EAN | 2022-07-14 | 2022-07-14 | 26 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.8650 | TOR Essential Defueling Safety Case | PJB for Human Factors Integration Plan EAN (REV 000) | 2022-07-14 | 2022-07-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A30590 | TOR Essential Defueling Safety Case | FM Direct Process Protection Design ## (Cost Summary) (Claim 5) | 2022-07-14 | 2023-05-24 | 360 | 0 | 216 | 314 | 100% | 1.1465 | 1 | Completed
ER6668LT | W213 | W213.8720 | TOR Essential Defueling Safety Case | PJB for FM Direct Process Protection Design | 2022-07-14 | 2023-05-24 | 1 | 0 | 216 | 314 | 100% | 0.0031847 | 1 | Completed
ER6668LT | W213 | W213.A30660 | TOR Essential Defueling Safety Case | Flow Induced Vibration EAN ## (Cost Summary) (Claim 3) | 2022-07-14 | 2022-10-31 | 62 | 0 | 76 | 109 | 100% | 0.56881 | 1 | Completed
ER6668LT | W213 | W213.8860 | TOR Essential Defueling Safety Case | (B - C SANCTION) - Project Management - (Cost Summary) ## (B to C) | 2022-07-14 | 2024-02-23 | 298 | 0 | 408 | 589 | 100% | 0.50594 | 1 | Completed
ER6668LT | W213 | W213.8870 | TOR Essential Defueling Safety Case | (B - C SANCTION) - Safety Case Development - (Cost Summary) ## (B to C) | 2022-07-14 | 2024-02-23 | 298 | 0 | 408 | 589 | 100% | 0.50594 | 1 | Completed
ER6668LT | W213 | W213.A30770 | TOR Essential Defueling Safety Case | Draft Summary of Credible Start of Life Defects EAN | 2022-07-14 | 2022-11-22 | 11 | 0 | 93 | 131 | 100% | 0.083969 | 1 | Completed
ER6668LT | W213 | W213.A30790 | TOR Essential Defueling Safety Case | Technical Review of Define Nuclear Data (PANTHER Validation Calcs) EAN | 2022-07-14 | 2022-12-16 | 12 | 0 | 111 | 155 | 100% | 0.077419 | 1 | Completed
ER6668LT | W213 | W213.A30810 | TOR Essential Defueling Safety Case | Draft Civil Integrity of Pressure Boundary Integrity of Seals Report EAN | 2022-07-14 | 2022-07-15 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6668LT | W213 | W213.A30830 | TOR Essential Defueling Safety Case | Technical Review of Radiological Consequences Following Failed CSP EAN | 2022-07-14 | 2023-02-20 | 8 | 0 | 153 | 221 | 100% | 0.036199 | 1 | Completed
ER6668LT | W213 | W213.A30840 | TOR Essential Defueling Safety Case | Define Nuclear Data (PANTHER Validation Calcs) EAN ## (Cost Summary) (Claim 1) | 2022-07-14 | 2023-01-13 | 123 | 0 | 127 | 183 | 100% | 0.67213 | 1 | Completed
ER6666LT | W209 | W209.1395 | HYB Essential Defueling Safety Case | Commence Supporting References or Supporting EC's | 2022-07-15 | 2022-07-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A24570 | HYB Essential Defueling Safety Case | Pre Job Brief for Human Reliability Baseline Report EAN | 2022-07-15 | 2022-07-15 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1395 | TOR Essential Defueling Safety Case | Commence Supporting References or Supporting EC's | 2022-07-15 | 2022-07-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A24570 | TOR Essential Defueling Safety Case | Pre Job Brief for Human Reliability Baseline Report EAN | 2022-07-15 | 2022-07-15 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A29890 | HYB Essential Defueling Safety Case | Verify Review of FPU Maintenance Analysis EAN & Issue for Technical Review | 2022-07-15 | 2022-07-20 | 4 | 0 | 4 | 5 | 100% | 0.8 | 1 | Completed
ER6666LT | W209 | W209.A29940 | HYB Essential Defueling Safety Case | FM Underload Protection Mods Prelim Design (GLM) ## (Cost Summary) (Claim 5) | 2022-07-15 | 2023-05-19 | 216 | 0 | 212 | 308 | 100% | 0.7013 | 1 | Completed
ER6666LT | W209 | W209.8320 | HYB Essential Defueling Safety Case | Prepare Spec for FM Underload Protection Mods Prelim Design (GLM) | 2022-07-15 | 2022-07-21 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.8830 | HYB Essential Defueling Safety Case | Prepare Spec for Underload Veto Height | 2022-07-15 | 2022-07-21 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.A30670 | HYB Essential Defueling Safety Case | Underload Veto Height ## (Cost Summary) (Claim 5) | 2022-07-15 | 2023-07-14 | 252 | 0 | 252 | 364 | 100% | 0.69231 | 1 | Completed
ER6668LT | W213 | W213.A29890 | TOR Essential Defueling Safety Case | Verify Review of FPU Maintenance Analysis EAN & Issue for Technical Review | 2022-07-15 | 2022-07-20 | 4 | 0 | 4 | 5 | 100% | 0.8 | 1 | Completed
ER6668LT | W213 | W213.A29940 | TOR Essential Defueling Safety Case | FM Underload Protection Mods Prelim Design (GLM) ## (Cost Summary) (Claim 5) | 2022-07-15 | 2023-05-19 | 216 | 0 | 212 | 308 | 100% | 0.7013 | 1 | Completed
ER6668LT | W213 | W213.8320 | TOR Essential Defueling Safety Case | Prepare Spec for FM Underload Protection Mods Prelim Design (GLM) | 2022-07-15 | 2022-07-21 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.8830 | TOR Essential Defueling Safety Case | Prepare Spec for Underload Veto Height | 2022-07-15 | 2022-07-21 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.A30670 | TOR Essential Defueling Safety Case | Underload Veto Height ## (Cost Summary) (Claim 5) | 2022-07-15 | 2023-07-14 | 252 | 0 | 252 | 364 | 100% | 0.69231 | 1 | Completed
ER6666LT | W209 | W209.6660 | HYB Essential Defueling Safety Case | Approve Task Sheet for Fuel Free Verification methods, an assessment against the ALARP principle EAN | 2022-07-18 | 2022-07-18 | 7 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A24580 | HYB Essential Defueling Safety Case | Step 1 - Review of Human Reliability Baseline Report EAN | 2022-07-18 | 2022-09-16 | 20 | 0 | 44 | 60 | 100% | 0.33333 | 1 | Completed
ER6371LT | W202 | 1610 | HRA Reactors Shutdown Essential Safety Cases | Request and address comments from core team | 2022-07-18 | 2022-07-25 | 10 | 0 | 5 | 7 | 100% | 1.4286 | 1 | Completed
ER6661LT | W206 | 1610 | HYA Reactors Shutdown Essential Safety Cases | Request and address comments from core team | 2022-07-18 | 2022-07-25 | 10 | 0 | 5 | 7 | 100% | 1.4286 | 1 | Completed
ER6668LT | W213 | W213.6660 | TOR Essential Defueling Safety Case | Approve Task Sheet for Fuel Free Verification methods, an assessment against the ALARP principle EAN | 2022-07-18 | 2022-07-18 | 7 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A24580 | TOR Essential Defueling Safety Case | Step 1 - Review of Human Reliability Baseline Report EAN | 2022-07-18 | 2022-09-16 | 20 | 0 | 44 | 60 | 100% | 0.33333 | 1 | Completed
ER6666LT | W209 | W209.A26200 | HYB Essential Defueling Safety Case | Verify Pressure Boundary Integrity of Seals Report EAN & Issue for Technical Review | 2022-07-18 | 2022-07-20 | 15 | 0 | 2 | 2 | 100% | 7.5 | 1 | Completed
ER6666LT | W209 | W209.A28040 | HYB Essential Defueling Safety Case | Verify Update Basis of Analysis document & Issue for Technical Review | 2022-07-18 | 2022-08-19 | 15 | 0 | 25 | 32 | 100% | 0.46875 | 1 | Completed
ER6668LT | W213 | W213.A26200 | TOR Essential Defueling Safety Case | Verify Pressure Boundary Integrity of Seals Report EAN & Issue for Technical Review | 2022-07-18 | 2022-07-20 | 15 | 0 | 2 | 2 | 100% | 7.5 | 1 | Completed
ER6668LT | W213 | W213.A28040 | TOR Essential Defueling Safety Case | Verify Update Basis of Analysis document & Issue for Technical Review | 2022-07-18 | 2022-08-19 | 15 | 0 | 25 | 32 | 100% | 0.46875 | 1 | Completed
ER6666LT | W209 | W209.A31080 | HYB Essential Defueling Safety Case | Defueling Process Flow## (Cost Summary) (Claim 5) | 2022-07-19 | 2023-07-31 | 208 | 0 | 261 | 377 | 100% | 0.55172 | 1 | Completed
ER6666LT | W209 | W209.A31090 | HYB Essential Defueling Safety Case | Pre Job Brief for Defueling Process Flow | 2022-07-19 | 2022-07-19 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A31080 | TOR Essential Defueling Safety Case | Defueling Process Flow## (Cost Summary) (Claim 5) | 2022-07-19 | 2023-07-31 | 208 | 0 | 261 | 377 | 100% | 0.55172 | 1 | Completed
ER6668LT | W213 | W213.A31090 | TOR Essential Defueling Safety Case | Pre Job Brief for Defueling Process Flow | 2022-07-19 | 2022-07-19 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A28120 | HYB Essential Defueling Safety Case | Verify FEA Model & Issue for Technical Review | 2022-07-19 | 2022-07-26 | 6 | 0 | 6 | 7 | 100% | 0.85714 | 1 | Completed
ER6666LT | W209 | W209.A28740 | HYB Essential Defueling Safety Case | Pre Job Brief for Fuel Free Verification methods, an assessment against the ALARP principle EAN | 2022-07-19 | 2022-07-19 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A28120 | TOR Essential Defueling Safety Case | Verify FEA Model & Issue for Technical Review | 2022-07-19 | 2022-07-26 | 6 | 0 | 6 | 7 | 100% | 0.85714 | 1 | Completed
ER6668LT | W213 | W213.A28740 | TOR Essential Defueling Safety Case | Pre Job Brief for Fuel Free Verification methods, an assessment against the ALARP principle EAN | 2022-07-19 | 2022-07-19 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A31100 | HYB Essential Defueling Safety Case | Draft Defueling Process Flow | 2022-07-20 | 2022-10-31 | 49 | 0 | 73 | 103 | 100% | 0.47573 | 1 | Completed
ER6668LT | W213 | W213.A31100 | TOR Essential Defueling Safety Case | Draft Defueling Process Flow | 2022-07-20 | 2022-10-31 | 49 | 0 | 73 | 103 | 100% | 0.47573 | 1 | Completed
ER6666LT | W209 | W209.A28750 | HYB Essential Defueling Safety Case | Draft Fuel Free Verification (FFV) Reports EAN | 2022-07-20 | 2022-11-04 | 49 | 0 | 77 | 107 | 100% | 0.45794 | 1 | Completed
ER6668LT | W213 | W213.A28750 | TOR Essential Defueling Safety Case | Draft Fuel Free Verification (FFV) Reports EAN | 2022-07-20 | 2022-11-04 | 49 | 0 | 77 | 107 | 100% | 0.45794 | 1 | Completed
ER6666LT | W209 | W209.A30420 | HYB Essential Defueling Safety Case | Technical Review of Pressure Boundary Integrity of Seals Report EAN | 2022-07-21 | 2022-10-06 | 20 | 0 | 55 | 77 | 100% | 0.25974 | 1 | Completed
ER6668LT | W213 | W213.A30420 | TOR Essential Defueling Safety Case | Technical Review of Pressure Boundary Integrity of Seals Report EAN | 2022-07-21 | 2022-10-06 | 20 | 0 | 55 | 77 | 100% | 0.25974 | 1 | Completed
ER6666LT | W209 | W209.A29900 | HYB Essential Defueling Safety Case | Technical Review of FPU Maintenance Analysis EAN | 2022-07-21 | 2022-08-01 | 25 | 0 | 8 | 11 | 100% | 2.2727 | 1 | Completed
ER6668LT | W213 | W213.A29900 | TOR Essential Defueling Safety Case | Technical Review of FPU Maintenance Analysis EAN | 2022-07-21 | 2022-08-01 | 25 | 0 | 8 | 11 | 100% | 2.2727 | 1 | Completed
ER6666LT | W209 | W209.A24780 | HYB Essential Defueling Safety Case | Pre Job Brief for Human Factors Assessment of Misloading / Mis-Defueling Faults EAN | 2022-07-22 | 2022-07-22 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A24780 | TOR Essential Defueling Safety Case | Pre Job Brief for Human Factors Assessment of Misloading / Mis-Defueling Faults EAN | 2022-07-22 | 2022-07-22 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.8330 | HYB Essential Defueling Safety Case | Prepare Task Sheet for FM Underload Protection Mods Prelim Design (GLM) | 2022-07-22 | 2022-08-04 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6666LT | W209 | W209.8840 | HYB Essential Defueling Safety Case | Prepare Task Sheet for Underload Veto Height | 2022-07-22 | 2022-08-04 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6668LT | W213 | W213.8330 | TOR Essential Defueling Safety Case | Prepare Task Sheet for FM Underload Protection Mods Prelim Design (GLM) | 2022-07-22 | 2022-08-04 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6668LT | W213 | W213.8840 | TOR Essential Defueling Safety Case | Prepare Task Sheet for Underload Veto Height | 2022-07-22 | 2022-08-04 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6666LT | W209 | W209.A27000 | HYB Essential Defueling Safety Case | Verify Review of FM Cyclic Duty EAN & Issue for Technical Review | 2022-07-25 | 2022-08-05 | 25 | 0 | 10 | 11 | 100% | 2.2727 | 1 | Completed
ER6666LT | W209 | W209.A24790 | HYB Essential Defueling Safety Case | Draft Review of Human Factors Assessment of Misloading / Mis-Defueling Faults EAN | 2022-07-25 | 2023-04-11 | 55 | 0 | 181 | 260 | 100% | 0.21154 | 1 | Completed
ER6668LT | W213 | W213.A27000 | TOR Essential Defueling Safety Case | Verify Review of FM Cyclic Duty EAN & Issue for Technical Review | 2022-07-25 | 2022-08-05 | 25 | 0 | 10 | 11 | 100% | 2.2727 | 1 | Completed
ER6668LT | W213 | W213.A24790 | TOR Essential Defueling Safety Case | Draft Review of Human Factors Assessment of Misloading / Mis-Defueling Faults EAN | 2022-07-25 | 2023-04-11 | 55 | 0 | 181 | 260 | 100% | 0.21154 | 1 | Completed
ER6666LT | W209 | W209.A28050 | HYB Essential Defueling Safety Case | Technical Review of Update Basis if Analysis document - (Issue 3) | 2022-07-27 | 2022-11-04 | 20 | 0 | 72 | 100 | 100% | 0.2 | 1 | Completed
ER6666LT | W209 | W209.A30680 | HYB Essential Defueling Safety Case | Pre Job Brief for Channel 1 - HYB | 2022-07-27 | 2022-07-27 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A28050 | TOR Essential Defueling Safety Case | Technical Review of Update Basis if Analysis document - (Issue 3) | 2022-07-27 | 2022-11-04 | 20 | 0 | 72 | 100 | 100% | 0.2 | 1 | Completed
ER6668LT | W213 | W213.A30680 | TOR Essential Defueling Safety Case | Pre Job Brief for Channel 1 - TOR | 2022-07-27 | 2022-07-27 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A28130 | HYB Essential Defueling Safety Case | Technical Review of FEA Model | 2022-07-27 | 2022-08-09 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6371LT | W202 | 1600 | HRA Reactors Shutdown Essential Safety Cases | Update Fault Definition Document | 2022-07-27 | 2022-08-23 | 3 | 0 | 19 | 27 | 100% | 0.11111 | 1 | Completed
ER6661LT | W206 | 1600 | HYA Reactors Shutdown Essential Safety Cases | Update Fault Definition Document | 2022-07-27 | 2022-08-23 | 3 | 0 | 19 | 27 | 100% | 0.11111 | 1 | Completed
ER6668LT | W213 | W213.A28130 | TOR Essential Defueling Safety Case | Technical Review of FEA Model | 2022-07-27 | 2022-08-09 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6666LT | W209 | W209.A30690 | HYB Essential Defueling Safety Case | Functional Requirement Spec for Channel 1 - HYB | 2022-07-28 | 2022-11-01 | 110 | 0 | 68 | 96 | 100% | 1.1458 | 1 | Completed
ER6668LT | W213 | W213.A30690 | TOR Essential Defueling Safety Case | Functional Requirement Spec for Channel 1 - TOR | 2022-07-28 | 2022-11-01 | 110 | 0 | 68 | 96 | 100% | 1.1458 | 1 | Completed
ER6666LT | W209 | W209.A29750 | HYB Essential Defueling Safety Case | Verify PARTIAL Drain down of the PVCS prior to Defuelling (Report) & Issue for Technical Review | 2022-07-29 | 2023-02-28 | 30 | 0 | 149 | 214 | 100% | 0.14019 | 1 | Completed
ER6668LT | W213 | W213.A29750 | TOR Essential Defueling Safety Case | Verify PARTIAL Drain down of the PVCS prior to Defuelling (Report) & Issue for Technical Review | 2022-07-29 | 2023-02-28 | 30 | 0 | 149 | 214 | 100% | 0.14019 | 1 | Completed
ER6371LT | W202 | 1815 | HRA Reactors Shutdown Essential Safety Cases | Review previous ALARP Optioneering and update where appropriate | 2022-08-01 | 2022-08-05 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6371LT | W202 | 1810 | HRA Reactors Shutdown Essential Safety Cases | Review ALARP Position for Safety Case - Summary | 2022-08-01 | 2023-10-19 | 69 | 0 | 308 | 444 | 100% | 0.15541 | 1 | Completed
ER6661LT | W206 | 1815 | HYA Reactors Shutdown Essential Safety Cases | Review previous ALARP Optioneering and update where appropriate | 2022-08-01 | 2022-08-05 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6661LT | W206 | 1810 | HYA Reactors Shutdown Essential Safety Cases | Review ALARP Position for Safety Case - Summary | 2022-08-01 | 2023-10-19 | 69 | 0 | 308 | 444 | 100% | 0.15541 | 1 | Completed
ER6370LT | W201 | ER6370.A1490 | HNB Reactors Shutdown Essential Safety Cases | Safety Case Post Job Debrief (HNB) [FEEDS TO SUMMARY SCHEDULE] | 2022-08-02 | 2022-08-10 | 1 | 0 | 6 | 8 | 100% | 0.125 | 1 | Completed
ER6370LT | W201 | ER6370.A12225 | HNB Reactors Shutdown Essential Safety Cases | Hold Project Closeout and Lessons Learned Meeting | 2022-08-02 | 2022-08-03 | 1 | 0 | 1 | 1 | 100% | 1 | 1 | Completed
ER6666LT | W209 | W209.A29910 | HYB Essential Defueling Safety Case | Supplier Update and Issue FPU Maintenance Analysis EAN | 2022-08-02 | 2022-09-02 | 5 | 0 | 23 | 31 | 100% | 0.16129 | 1 | Completed
ER6668LT | W213 | W213.A29910 | TOR Essential Defueling Safety Case | Supplier Update and Issue FPU Maintenance Analysis EAN | 2022-08-02 | 2022-09-02 | 5 | 0 | 23 | 31 | 100% | 0.16129 | 1 | Completed
ER6370LT | W201 | ER6370.A12235 | HNB Reactors Shutdown Essential Safety Cases | Produce Project Closeout Report | 2022-08-03 | 2022-08-03 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A12240 | HNB Reactors Shutdown Essential Safety Cases | Prepare Gate D PRC Paper | 2022-08-03 | 2022-08-03 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A12230 | HNB Reactors Shutdown Essential Safety Cases | Produce Lessons Learned Report | 2022-08-03 | 2022-08-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.8450 | HYB Essential Defueling Safety Case | Tech Review Assumptions Review | 2022-08-04 | 2022-10-03 | 20 | 0 | 42 | 60 | 100% | 0.33333 | 1 | Completed
ER6668LT | W213 | W213.8450 | TOR Essential Defueling Safety Case | Tech Review Assumptions Review | 2022-08-04 | 2022-10-03 | 20 | 0 | 42 | 60 | 100% | 0.33333 | 1 | Completed
ER6666LT | W209 | W209.8340 | HYB Essential Defueling Safety Case | Approve Task Sheet for FM Underload Protection Mods Prelim Design (GLM) | 2022-08-05 | 2022-08-08 | 7 | 0 | 1 | 3 | 100% | 2.3333 | 1 | Completed
ER6666LT | W209 | W209.8850 | HYB Essential Defueling Safety Case | Approve Task Sheet for Underload Veto Height | 2022-08-05 | 2022-08-08 | 7 | 0 | 1 | 3 | 100% | 2.3333 | 1 | Completed
ER6668LT | W213 | W213.8340 | TOR Essential Defueling Safety Case | Approve Task Sheet for FM Underload Protection Mods Prelim Design (GLM) | 2022-08-05 | 2022-08-08 | 7 | 0 | 1 | 3 | 100% | 2.3333 | 1 | Completed
ER6668LT | W213 | W213.8850 | TOR Essential Defueling Safety Case | Approve Task Sheet for Underload Veto Height | 2022-08-05 | 2022-08-08 | 7 | 0 | 1 | 3 | 100% | 2.3333 | 1 | Completed
ER6666LT | W209 | W209.A26040 | HYB Essential Defueling Safety Case | Verify Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN | 2022-08-08 | 2022-11-30 | 40 | 0 | 81 | 114 | 100% | 0.35088 | 1 | Completed
ER6668LT | W213 | W213.A26040 | TOR Essential Defueling Safety Case | Verify Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN | 2022-08-08 | 2022-11-30 | 40 | 0 | 81 | 114 | 100% | 0.35088 | 1 | Completed
ER6666LT | W209 | W209.A25960 | HYB Essential Defueling Safety Case | Verify Civil Assesment of the Ponds at Low Temperature EAN | 2022-08-08 | 2022-11-30 | 40 | 0 | 81 | 114 | 100% | 0.35088 | 1 | Completed
ER6666LT | W209 | W209.A27010 | HYB Essential Defueling Safety Case | Technical Review of Review of FM Cyclic Duty EAN | 2022-08-08 | 2022-09-12 | 25 | 0 | 25 | 35 | 100% | 0.71429 | 1 | Completed
ER6666LT | W209 | W209.7640 | HYB Essential Defueling Safety Case | Verification of Civils Assessment Report for PCPV Integrity Justification | 2022-08-08 | 2022-12-07 | 40 | 0 | 87 | 121 | 100% | 0.33058 | 1 | Completed
ER6666LT | W209 | W209.7660 | HYB Essential Defueling Safety Case | Verification of Civils Assessment Report for Seismic Assessment | 2022-08-08 | 2022-12-07 | 40 | 0 | 87 | 121 | 100% | 0.33058 | 1 | Completed
ER6668LT | W213 | W213.A25960 | TOR Essential Defueling Safety Case | Verify Civil Assesment of the Ponds at Low Temperature EAN | 2022-08-08 | 2022-11-30 | 40 | 0 | 81 | 114 | 100% | 0.35088 | 1 | Completed
ER6668LT | W213 | W213.A27010 | TOR Essential Defueling Safety Case | Technical Review of Review of FM Cyclic Duty EAN | 2022-08-08 | 2022-09-12 | 25 | 0 | 25 | 35 | 100% | 0.71429 | 1 | Completed
ER6668LT | W213 | W213.7640 | TOR Essential Defueling Safety Case | Verification of Civils Assessment Report for PCPV Integrity Justification | 2022-08-08 | 2022-12-07 | 40 | 0 | 87 | 121 | 100% | 0.33058 | 1 | Completed
ER6668LT | W213 | W213.7660 | TOR Essential Defueling Safety Case | Verification of Civils Assessment Report for Seismic Assessment | 2022-08-08 | 2022-12-07 | 40 | 0 | 87 | 121 | 100% | 0.33058 | 1 | Completed
ER6370LT | W201 | ER6370.A18170 | HNB Reactors Shutdown Essential Safety Cases | Review of Reactor Essential Safety Cases 2 - Lessons Learned Review Complete | 2022-08-10 | 2022-08-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A28140 | HYB Essential Defueling Safety Case | Supplier Update and Issue of FEA Model | 2022-08-10 | 2022-08-12 | 24 | 0 | 3 | 2 | 100% | 12 | 1 | Completed
ER6668LT | W213 | W213.A28140 | TOR Essential Defueling Safety Case | Supplier Update and Issue of FEA Model | 2022-08-10 | 2022-08-12 | 24 | 0 | 3 | 2 | 100% | 12 | 1 | Completed
ER6370LT | W201 | ER6370.A12245 | HNB Reactors Shutdown Essential Safety Cases | Gate D PRC Paper Submission | 2022-08-10 | 2022-08-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.8040 | HYB Essential Defueling Safety Case | Pre Job Brief for HF Assessment of the Extant Fuel Movement in support of Defueling FFV Claim | 2022-08-11 | 2022-08-11 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.8040 | TOR Essential Defueling Safety Case | Pre Job Brief for HF Assessment of the Extant Fuel Movement in support of Defueling FFV Claim | 2022-08-11 | 2022-08-11 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.8050 | HYB Essential Defueling Safety Case | Draft HF Assessment of HF Assessment of the Extant Fuel Movement in support of Defueling FFV Claim | 2022-08-12 | 2022-10-31 | 70 | 0 | 56 | 80 | 100% | 0.875 | 1 | Completed
ER6668LT | W213 | W213.8050 | TOR Essential Defueling Safety Case | Draft HF Assessment of HF Assessment of the Extant Fuel Movement in support of Defueling FFV Claim | 2022-08-12 | 2022-10-31 | 70 | 0 | 56 | 80 | 100% | 0.875 | 1 | Completed
ER6666LT | W209 | W209.A28170 | HYB Essential Defueling Safety Case | CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN ## (Cost Summary) (Claim 4) | 2022-08-15 | 2023-03-31 | 169 | 0 | 160 | 228 | 100% | 0.74123 | 1 | Completed
ER6666LT | W209 | W209.A28180 | HYB Essential Defueling Safety Case | Pre Job Brief for CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN | 2022-08-15 | 2022-08-15 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A28330 | HYB Essential Defueling Safety Case | R6 Assessment of CSP & Diagrid EAN ## (Cost Summary) (Claim 4) | 2022-08-15 | 2023-03-31 | 169 | 0 | 160 | 228 | 100% | 0.74123 | 1 | Completed
ER6668LT | W213 | W213.A28170 | TOR Essential Defueling Safety Case | CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN ## (Cost Summary) (Claim 4) | 2022-08-15 | 2023-03-31 | 169 | 0 | 160 | 228 | 100% | 0.74123 | 1 | Completed
ER6668LT | W213 | W213.A28180 | TOR Essential Defueling Safety Case | Pre Job Brief for CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN | 2022-08-15 | 2022-08-15 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A28330 | TOR Essential Defueling Safety Case | R6 Assessment of CSP & Diagrid EAN ## (Cost Summary) (Claim 4) | 2022-08-15 | 2023-03-31 | 169 | 0 | 160 | 228 | 100% | 0.74123 | 1 | Completed
ER6666LT | W209 | W209.A28150 | HYB Essential Defueling Safety Case | Approve Model | 2022-08-15 | 2022-08-31 | 5 | 0 | 11 | 16 | 100% | 0.3125 | 1 | Completed
ER6668LT | W213 | W213.A28150 | TOR Essential Defueling Safety Case | Approve Model | 2022-08-15 | 2022-08-31 | 5 | 0 | 11 | 16 | 100% | 0.3125 | 1 | Completed
ER6666LT | W209 | W209.A28190 | HYB Essential Defueling Safety Case | Draft CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN | 2022-08-16 | 2022-11-18 | 100 | 0 | 67 | 94 | 100% | 1.0638 | 1 | Completed
ER6668LT | W213 | W213.A28190 | TOR Essential Defueling Safety Case | Draft CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN | 2022-08-16 | 2022-11-18 | 100 | 0 | 67 | 94 | 100% | 1.0638 | 1 | Completed
ER6371LT | W202 | 1820 | HRA Reactors Shutdown Essential Safety Cases | ALARP Meeting to Review Safety Case [Update] | 2022-08-17 | 2022-08-17 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | 1820 | HYA Reactors Shutdown Essential Safety Cases | ALARP Meeting to Review Safety Case [Update] | 2022-08-17 | 2022-08-17 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | 1830 | HRA Reactors Shutdown Essential Safety Cases | Update ALARP Document | 2022-08-18 | 2022-09-26 | 10 | 0 | 26 | 39 | 100% | 0.25641 | 1 | Completed
ER6661LT | W206 | 1830 | HYA Reactors Shutdown Essential Safety Cases | Update ALARP Document | 2022-08-18 | 2022-09-26 | 10 | 0 | 26 | 39 | 100% | 0.25641 | 1 | Completed
ER6666LT | W209 | W209.A26300 | HYB Essential Defueling Safety Case | Supplier Update and Issue Reactor Internals & Structural Integrity During Defueling Report EAN | 2022-08-22 | 2022-11-04 | 5 | 0 | 54 | 74 | 100% | 0.067568 | 1 | Completed
ER6668LT | W213 | W213.A26300 | TOR Essential Defueling Safety Case | Supplier Update and Issue Reactor Internals & Structural Integrity During Defueling Report EAN | 2022-08-22 | 2022-11-04 | 5 | 0 | 54 | 74 | 100% | 0.067568 | 1 | Completed
ER6370LT | W201 | ER6370.A12325 | HNB Reactors Shutdown Essential Safety Cases | Post PRC Actions Closeout | 2022-08-23 | 2022-08-23 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A12315 | HNB Reactors Shutdown Essential Safety Cases | Hold PRC Meeting | 2022-08-23 | 2022-08-23 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13080 | HNB Reactors Shutdown Essential Safety Cases | Gate D For Region 1 Essential Defuelling Safety Case (HNB) | 2022-08-23 | 2022-08-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A29950 | HYB Essential Defueling Safety Case | Pre Job Brief for FM Underload Protection Mods Prelim Design (GLM) | 2022-08-24 | 2022-08-24 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | 2997 | HRA Reactors Shutdown Essential Safety Cases | Share NSRS with ONR | 2022-08-24 | 2022-08-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | 2997 | HYA Reactors Shutdown Essential Safety Cases | Share NSRS with ONR | 2022-08-24 | 2022-08-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A30940 | HYB Essential Defueling Safety Case | Pre Job Brief for Channel X | 2022-08-24 | 2022-08-24 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A29950 | TOR Essential Defueling Safety Case | Pre Job Brief for FM Underload Protection Mods Prelim Design (GLM) | 2022-08-24 | 2022-08-24 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A30940 | TOR Essential Defueling Safety Case | Pre Job Brief for Channel X | 2022-08-24 | 2022-08-24 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A29960 | HYB Essential Defueling Safety Case | Functional Requirement Spec for FM Underload Protection Mods Prelim Design (GLM) | 2022-08-25 | 2022-11-01 | 37 | 0 | 48 | 68 | 100% | 0.54412 | 1 | Completed
ER6666LT | W209 | W209.A30950 | HYB Essential Defueling Safety Case | Functional Requirement Spec for Channel X | 2022-08-25 | 2022-11-01 | 37 | 0 | 48 | 68 | 100% | 0.54412 | 1 | Completed
ER6668LT | W213 | W213.A29960 | TOR Essential Defueling Safety Case | Functional Requirement Spec for FM Underload Protection Mods Prelim Design (GLM) | 2022-08-25 | 2022-11-01 | 37 | 0 | 48 | 68 | 100% | 0.54412 | 1 | Completed
ER6668LT | W213 | W213.A30950 | TOR Essential Defueling Safety Case | Functional Requirement Spec for Channel X | 2022-08-25 | 2022-11-01 | 37 | 0 | 48 | 68 | 100% | 0.54412 | 1 | Completed
ER6650LT | W226 | 2797 | HYA Fuel Handling Essential Safety Case | Share NSRS with ONR | 2022-08-25 | 2022-08-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | 1590 | HRA Reactors Shutdown Essential Safety Cases | Update technical references for FDD | 2022-08-26 | 2022-08-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | 1590 | HYA Reactors Shutdown Essential Safety Cases | Update technical references for FDD | 2022-08-26 | 2022-08-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A17330 | HNB Reactors Shutdown Essential Safety Cases | ETC (DD-PF) | 2022-08-30 | 2022-08-30 | 21 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A28160 | HYB Essential Defueling Safety Case | FEA Model Approved | 2022-08-31 | 2022-08-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A28160 | TOR Essential Defueling Safety Case | FEA Model Approved | 2022-08-31 | 2022-08-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6370LT | W201 | ER6370.A13050 | HNB Reactors Shutdown Essential Safety Cases | Phase 2 Project Completion | 2022-08-31 | 2022-08-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A26680 | HYB Essential Defueling Safety Case | Verify Review of flux detector suitability EAN & Issue for Technical Review | 2022-09-01 | 2022-10-04 | 20 | 0 | 23 | 33 | 100% | 0.60606 | 1 | Completed
ER6668LT | W213 | W213.A26680 | TOR Essential Defueling Safety Case | Verify Review of flux detector suitability EAN & Issue for Technical Review | 2022-09-01 | 2022-10-04 | 20 | 0 | 23 | 33 | 100% | 0.60606 | 1 | Completed
ER6666LT | W209 | W209.A29480 | HYB Essential Defueling Safety Case | Verify Cooling Plant OPEX Study EAN & Issue for Technical Review | 2022-09-01 | 2022-09-05 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6668LT | W213 | W213.A29480 | TOR Essential Defueling Safety Case | Verify Cooling Plant OPEX Study EAN & Issue for Technical Review | 2022-09-01 | 2022-09-05 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6666LT | W209 | W209.A27180 | HYB Essential Defueling Safety Case | Supplier Update and Issue Flow Induced Vibration EAN | 2022-09-05 | 2022-10-03 | 6 | 0 | 21 | 28 | 100% | 0.21429 | 1 | Completed
ER6666LT | W209 | W209.A29920 | HYB Essential Defueling Safety Case | Complete TR Form and Upload FPU Maintenance Analysis EAN to CDMS | 2022-09-05 | 2022-09-09 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6668LT | W213 | W213.A27180 | TOR Essential Defueling Safety Case | Supplier Update and Issue Flow Induced Vibration EAN | 2022-09-05 | 2022-10-03 | 6 | 0 | 21 | 28 | 100% | 0.21429 | 1 | Completed
ER6668LT | W213 | W213.A29920 | TOR Essential Defueling Safety Case | Complete TR Form and Upload FPU Maintenance Analysis EAN to CDMS | 2022-09-05 | 2022-09-09 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6666LT | W209 | W209.A29810 | HYB Essential Defueling Safety Case | Verify Feasibility of Draining PVCS (Report) & Issue for Technical Review | 2022-09-06 | 2022-09-09 | 15 | 0 | 4 | 3 | 100% | 5 | 1 | Completed
ER6668LT | W213 | W213.A29810 | TOR Essential Defueling Safety Case | Verify Feasibility of Draining PVCS (Report) & Issue for Technical Review | 2022-09-06 | 2022-09-09 | 15 | 0 | 4 | 3 | 100% | 5 | 1 | Completed
ER6666LT | W209 | W209.A29490 | HYB Essential Defueling Safety Case | Technical Review of Cooling Plant OPEX Study EAN | 2022-09-06 | 2022-10-21 | 15 | 0 | 34 | 45 | 100% | 0.33333 | 1 | Completed
ER6668LT | W213 | W213.A29490 | TOR Essential Defueling Safety Case | Technical Review of Cooling Plant OPEX Study EAN | 2022-09-06 | 2022-10-21 | 15 | 0 | 34 | 45 | 100% | 0.33333 | 1 | Completed
ER6666LT | W209 | W209.A26760 | HYB Essential Defueling Safety Case | Verify Boron Bead Injection Feasibility & Control Rod Isolation EAN & Issue for Technical Review | 2022-09-09 | 2022-11-15 | 30 | 0 | 48 | 67 | 100% | 0.44776 | 1 | Completed
ER6668LT | W213 | W213.A26760 | TOR Essential Defueling Safety Case | Verify Boron Bead Injection Feasibility & Control Rod Isolation EAN & Issue for Technical Review | 2022-09-09 | 2022-11-15 | 30 | 0 | 48 | 67 | 100% | 0.44776 | 1 | Completed
ER6666LT | W209 | W209.A29930 | HYB Essential Defueling Safety Case | FPU Maintenance Analysis EAN Available | 2022-09-09 | 2022-09-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A29930 | TOR Essential Defueling Safety Case | FPU Maintenance Analysis EAN Available | 2022-09-09 | 2022-09-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A29820 | HYB Essential Defueling Safety Case | Technical Review of Feasibility of Draining PVCS (Report) | 2022-09-12 | 2022-10-28 | 15 | 0 | 35 | 46 | 100% | 0.32609 | 1 | Completed
ER6668LT | W213 | W213.A29820 | TOR Essential Defueling Safety Case | Technical Review of Feasibility of Draining PVCS (Report) | 2022-09-12 | 2022-10-28 | 15 | 0 | 35 | 46 | 100% | 0.32609 | 1 | Completed
ER6666LT | W209 | W209.A27020 | HYB Essential Defueling Safety Case | Supplier Update and Issue Review of FM Cyclic Duty EAN | 2022-09-13 | 2022-10-07 | 5 | 0 | 19 | 24 | 100% | 0.20833 | 1 | Completed
ER6666LT | W209 | W209.A30800 | HYB Essential Defueling Safety Case | Verify PANTHER SCM Assessments - Agree Defuelling Order EAN & Issue for T Review | 2022-09-13 | 2022-10-31 | 20 | 0 | 34 | 48 | 100% | 0.41667 | 1 | Completed
ER6668LT | W213 | W213.A27020 | TOR Essential Defueling Safety Case | Supplier Update and Issue Review of FM Cyclic Duty EAN | 2022-09-13 | 2022-10-07 | 5 | 0 | 19 | 24 | 100% | 0.20833 | 1 | Completed
ER6668LT | W213 | W213.A30800 | TOR Essential Defueling Safety Case | Verify PANTHER SCM Assessments - Agree Defuelling Order EAN & Issue for T Review | 2022-09-13 | 2022-10-31 | 20 | 0 | 34 | 48 | 100% | 0.41667 | 1 | Completed
ER6666LT | W209 | W209.A26890 | HYB Essential Defueling Safety Case | Chemistry Monitoring Strategy EAN ## (Cost Summary) (Claim 3) | 2022-09-14 | 2023-03-03 | 129 | 0 | 120 | 170 | 100% | 0.75882 | 1 | Completed
ER6666LT | W209 | W209.A26900 | HYB Essential Defueling Safety Case | Pre Job Brief for Chemistry Monitoring Strategy EAN | 2022-09-14 | 2022-09-14 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A26890 | TOR Essential Defueling Safety Case | Chemistry Monitoring Strategy EAN ## (Cost Summary) (Claim 3) | 2022-09-14 | 2023-03-03 | 129 | 0 | 120 | 170 | 100% | 0.75882 | 1 | Completed
ER6668LT | W213 | W213.A26900 | TOR Essential Defueling Safety Case | Pre Job Brief for Chemistry Monitoring Strategy EAN | 2022-09-14 | 2022-09-14 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A26910 | HYB Essential Defueling Safety Case | Draft Chemistry Monitoring Strategy EAN | 2022-09-15 | 2022-11-09 | 49 | 0 | 39 | 55 | 100% | 0.89091 | 1 | Completed
ER6668LT | W213 | W213.A26910 | TOR Essential Defueling Safety Case | Draft Chemistry Monitoring Strategy EAN | 2022-09-15 | 2022-11-09 | 49 | 0 | 39 | 55 | 100% | 0.89091 | 1 | Completed
ER6371LT | W202 | 1620 | HRA Reactors Shutdown Essential Safety Cases | Verify updated FDD | 2022-09-27 | 2022-11-30 | 10 | 0 | 46 | 64 | 100% | 0.15625 | 1 | Completed
ER6661LT | W206 | 1620 | HYA Reactors Shutdown Essential Safety Cases | Verify updated FDD | 2022-09-27 | 2022-11-30 | 10 | 0 | 46 | 64 | 100% | 0.15625 | 1 | Completed
ER6371LT | W202 | 1840 | HRA Reactors Shutdown Essential Safety Cases | EDF Verification | 2022-09-28 | 2022-10-12 | 5 | 0 | 10 | 14 | 100% | 0.35714 | 1 | Completed
ER6661LT | W206 | 1840 | HYA Reactors Shutdown Essential Safety Cases | EDF Verification | 2022-09-28 | 2022-10-12 | 5 | 0 | 10 | 14 | 100% | 0.35714 | 1 | Completed
ER6666LT | W209 | W209.A25880 | HYB Essential Defueling Safety Case | Verify Safety Case Requirements EAN - TASK E EAN & Issue for Tech Review | 2022-09-30 | 2023-01-13 | 20 | 0 | 73 | 105 | 100% | 0.19048 | 1 | Completed
ER6668LT | W213 | W213.A25880 | TOR Essential Defueling Safety Case | Verify Safety Case Requirements EAN - TASK E EAN & Issue for Tech Review | 2022-09-30 | 2023-01-13 | 20 | 0 | 73 | 105 | 100% | 0.19048 | 1 | Completed
ER6650LT | W226 | 1950 | HYA Fuel Handling Essential Safety Case | Update Head Document | 2022-10-03 | 2023-01-20 | 20 | 0 | 73 | 109 | 100% | 0.18349 | 1 | Completed
W232LT | W232 | W232.A1050 | DNB Enhanced Safety Cases | Project Management - Early Release Funding | 2022-10-03 | 2023-01-31 | 84 | 0 | 83 | 120 | 100% | 0.7 | 1 | Completed
W232LT | W232 | W232.A1060 | DNB Enhanced Safety Cases | Project Start (FEED TO SUMMARY SCHEDULE) | 2022-10-03 | 2022-10-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1690 | DNB Enhanced Safety Cases | Write PRC Paper | 2022-10-03 | 2022-10-14 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6666LT | W209 | W209.A26570 | HYB Essential Defueling Safety Case | Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN ## (Cost Summary) (Claim 1) | 2022-10-03 | 2023-01-24 | 77 | 0 | 78 | 113 | 100% | 0.68142 | 1 | Completed
ER6666LT | W209 | W209.A26580 | HYB Essential Defueling Safety Case | Pre Job Brief for Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 2022-10-03 | 2022-10-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A28650 | HYB Essential Defueling Safety Case | CSP/Diagrid Structural Integrity Summary Report ## (Cost Summary) (Claim 4) | 2022-10-03 | 2023-03-31 | 127 | 0 | 127 | 179 | 100% | 0.7095 | 1 | Completed
ER6666LT | W209 | W209.A28660 | HYB Essential Defueling Safety Case | Pre Job Brief for CSP/Diagrid Structural Integrity Summary Report | 2022-10-03 | 2022-10-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1030 | DNB Enhanced Safety Cases | Planning Workshop | 2022-10-03 | 2022-10-04 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
W232LT | W232 | W232.A1040 | DNB Enhanced Safety Cases | Technical Oversight - Early Release Funding | 2022-10-03 | 2023-01-31 | 84 | 0 | 83 | 120 | 100% | 0.7 | 1 | Completed
W232LT | W232 | W232.A2660 | DNB Enhanced Safety Cases | Review Risks Related to needing FLSA | 2022-10-03 | 2022-11-17 | 34 | 0 | 34 | 45 | 100% | 0.75556 | 1 | Completed
ER6668LT | W213 | W213.A26570 | TOR Essential Defueling Safety Case | Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN ## (Cost Summary) (Claim 1) | 2022-10-03 | 2023-01-24 | 77 | 0 | 78 | 113 | 100% | 0.68142 | 1 | Completed
ER6668LT | W213 | W213.A26580 | TOR Essential Defueling Safety Case | Pre Job Brief for Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 2022-10-03 | 2022-10-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A28650 | TOR Essential Defueling Safety Case | CSP/Diagrid Structural Integrity Summary Report ## (Cost Summary) (Claim 4) | 2022-10-03 | 2023-03-31 | 127 | 0 | 127 | 179 | 100% | 0.7095 | 1 | Completed
ER6668LT | W213 | W213.A28660 | TOR Essential Defueling Safety Case | Pre Job Brief for CSP/Diagrid Structural Integrity Summary Report | 2022-10-03 | 2022-10-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A25730 | HYB Essential Defueling Safety Case | Technical Review of Judgement Based Work Diversion EAN | 2022-10-04 | 2023-02-10 | 28 | 0 | 91 | 129 | 100% | 0.21705 | 1 | Completed
ER6668LT | W213 | W213.A25730 | TOR Essential Defueling Safety Case | Technical Review of Judgement Based Work Diversion EAN | 2022-10-04 | 2023-02-10 | 28 | 0 | 91 | 129 | 100% | 0.21705 | 1 | Completed
ER6666LT | W209 | W209.A26590 | HYB Essential Defueling Safety Case | Draft Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 2022-10-04 | 2022-10-28 | 13 | 0 | 19 | 24 | 100% | 0.54167 | 1 | Completed
ER6666LT | W209 | W209.A27190 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Flow Induced Vibration EAN to CDMS | 2022-10-04 | 2022-10-31 | 5 | 0 | 19 | 27 | 100% | 0.18519 | 1 | Completed
ER6666LT | W209 | W209.A27380 | HYB Essential Defueling Safety Case | Pre Job Brief for Fuel Route PSA Update EAN | 2022-10-04 | 2022-10-04 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A28670 | HYB Essential Defueling Safety Case | Draft CSP/Diagrid Structural Integrity Summary Report | 2022-10-04 | 2022-11-21 | 35 | 0 | 35 | 48 | 100% | 0.72917 | 1 | Completed
ER6668LT | W213 | W213.A26590 | TOR Essential Defueling Safety Case | Draft Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 2022-10-04 | 2022-10-28 | 13 | 0 | 19 | 24 | 100% | 0.54167 | 1 | Completed
ER6668LT | W213 | W213.A27190 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Flow Induced Vibration EAN to CDMS | 2022-10-04 | 2022-10-31 | 5 | 0 | 19 | 27 | 100% | 0.18519 | 1 | Completed
ER6668LT | W213 | W213.A27380 | TOR Essential Defueling Safety Case | Pre Job Brief for Fuel Route PSA Update EAN | 2022-10-04 | 2022-10-04 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A28670 | TOR Essential Defueling Safety Case | Draft CSP/Diagrid Structural Integrity Summary Report | 2022-10-04 | 2022-11-21 | 35 | 0 | 35 | 48 | 100% | 0.72917 | 1 | Completed
ER6666LT | W209 | W209.A26690 | HYB Essential Defueling Safety Case | Technical Review of Review of flux detector suitability EAN | 2022-10-05 | 2022-11-11 | 23 | 0 | 28 | 37 | 100% | 0.62162 | 1 | Completed
ER6668LT | W213 | W213.A26690 | TOR Essential Defueling Safety Case | Technical Review of Review of flux detector suitability EAN | 2022-10-05 | 2022-11-11 | 23 | 0 | 28 | 37 | 100% | 0.62162 | 1 | Completed
ER6666LT | W209 | W209.A27390 | HYB Essential Defueling Safety Case | Draft Fuel Route PSA Update | 2022-10-05 | 2022-12-14 | 58 | 0 | 51 | 70 | 100% | 0.82857 | 1 | Completed
ER6668LT | W213 | W213.A27390 | TOR Essential Defueling Safety Case | Draft Fuel Route PSA Update | 2022-10-05 | 2022-12-14 | 58 | 0 | 51 | 70 | 100% | 0.82857 | 1 | Completed
ER6666LT | W209 | W209.A26220 | HYB Essential Defueling Safety Case | Supplier Update and Issue Pressure Boundary Integrity of Seals Report EAN | 2022-10-07 | 2022-10-24 | 5 | 0 | 11 | 17 | 100% | 0.29412 | 1 | Completed
ER6668LT | W213 | W213.A26220 | TOR Essential Defueling Safety Case | Supplier Update and Issue Pressure Boundary Integrity of Seals Report EAN | 2022-10-07 | 2022-10-24 | 5 | 0 | 11 | 17 | 100% | 0.29412 | 1 | Completed
ER6666LT | W209 | W209.A27030 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Review of FM Cyclic Duty EAN to CDMS | 2022-10-10 | 2022-10-31 | 5 | 0 | 15 | 21 | 100% | 0.2381 | 1 | Completed
ER6371LT | W202 | 2350 | HRA Reactors Shutdown Essential Safety Cases | Update Verification Plan | 2022-10-10 | 2022-10-11 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6371LT | W202 | 2450 | HRA Reactors Shutdown Essential Safety Cases | LSD Updates | 2022-10-10 | 2022-11-23 | 3 | 0 | 32 | 44 | 100% | 0.068182 | 1 | Completed
ER6371LT | W202 | 2300 | HRA Reactors Shutdown Essential Safety Cases | Update EC | 2022-10-10 | 2022-11-07 | 5 | 0 | 21 | 28 | 100% | 0.17857 | 1 | Completed
ER6371LT | W202 | 2250 | HRA Reactors Shutdown Essential Safety Cases | Paper - Summary | 2022-10-10 | 2023-02-28 | 99 | 0 | 98 | 141 | 100% | 0.70213 | 1 | Completed
ER6371LT | W202 | 2345 | HRA Reactors Shutdown Essential Safety Cases | Verification Phase - Summary | 2022-10-10 | 2023-06-12 | 168 | 0 | 168 | 245 | 100% | 0.68571 | 1 | Completed
ER6371LT | W202 | 2435 | HRA Reactors Shutdown Essential Safety Cases | LSD Updates - Summary | 2022-10-10 | 2023-03-16 | 111 | 0 | 111 | 157 | 100% | 0.70701 | 1 | Completed
ER6661LT | W206 | 2350 | HYA Reactors Shutdown Essential Safety Cases | Update Verification Plan | 2022-10-10 | 2022-10-11 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6661LT | W206 | 2450 | HYA Reactors Shutdown Essential Safety Cases | LSD Updates | 2022-10-10 | 2022-11-23 | 3 | 0 | 32 | 44 | 100% | 0.068182 | 1 | Completed
ER6661LT | W206 | 2300 | HYA Reactors Shutdown Essential Safety Cases | Update EC | 2022-10-10 | 2022-11-07 | 5 | 0 | 21 | 28 | 100% | 0.17857 | 1 | Completed
ER6661LT | W206 | 2250 | HYA Reactors Shutdown Essential Safety Cases | Paper - Summary | 2022-10-10 | 2023-02-28 | 99 | 0 | 99 | 141 | 100% | 0.70213 | 1 | Completed
ER6661LT | W206 | 2345 | HYA Reactors Shutdown Essential Safety Cases | Verification Phase - Summary | 2022-10-10 | 2023-06-12 | 168 | 0 | 168 | 245 | 100% | 0.68571 | 1 | Completed
ER6661LT | W206 | 2435 | HYA Reactors Shutdown Essential Safety Cases | LSD Updates - Summary | 2022-10-10 | 2023-03-16 | 111 | 0 | 111 | 157 | 100% | 0.70701 | 1 | Completed
ER6668LT | W213 | W213.A27030 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Review of FM Cyclic Duty EAN to CDMS | 2022-10-10 | 2022-10-31 | 5 | 0 | 15 | 21 | 100% | 0.2381 | 1 | Completed
ER6666LT | W209 | W209.8380 | HYB Essential Defueling Safety Case | Claim 4 Production ## (Cost Summary) | 2022-10-12 | 2024-02-29 | 312 | 0 | 349 | 505 | 100% | 0.61782 | 1 | Completed
ER6666LT | W209 | W209.8940 | HYB Essential Defueling Safety Case | Discovery Milestone - Dropped FPU Decision Point | 2022-10-12 | 2022-10-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.8950 | HYB Essential Defueling Safety Case | Dropped FPU Decision Point | 2022-10-12 | 2022-10-12 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.8380 | TOR Essential Defueling Safety Case | Claim 4 Production ## (Cost Summary) | 2022-10-12 | 2024-02-29 | 306 | 0 | 349 | 505 | 100% | 0.60594 | 1 | Completed
ER6668LT | W213 | W213.8940 | TOR Essential Defueling Safety Case | Discovery Milestone - Dropped FPU Decision Point | 2022-10-12 | 2022-10-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.8950 | TOR Essential Defueling Safety Case | Dropped FPU Decision Point | 2022-10-12 | 2022-10-12 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | 2360 | HRA Reactors Shutdown Essential Safety Cases | Secure Verification Resource | 2022-10-12 | 2022-10-12 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | 2360 | HYA Reactors Shutdown Essential Safety Cases | Secure Verification Resource | 2022-10-12 | 2022-10-12 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1720 | DNB Enhanced Safety Cases | COST BAR - Obtain Gate A Funding | 2022-10-14 | 2022-12-01 | 43 | 0 | 33 | 48 | 100% | 0.89583 | 1 | Completed
ER6666LT | W209 | W209.A29210 | HYB Essential Defueling Safety Case | Defuelling Hazards Review EAN ## (Cost Summary) (Claim 5) | 2022-10-17 | 2023-07-31 | 191 | 0 | 197 | 287 | 100% | 0.66551 | 1 | Completed
ER6666LT | W209 | W209.6820 | HYB Essential Defueling Safety Case | Prepare Spec for Defuelling Hazards Review EAN | 2022-10-17 | 2022-10-31 | 5 | 0 | 11 | 14 | 100% | 0.35714 | 1 | Completed
ER6668LT | W213 | W213.A29210 | TOR Essential Defueling Safety Case | Defuelling Hazards Review EAN ## (Cost Summary) (Claim 5) | 2022-10-17 | 2023-07-31 | 191 | 0 | 197 | 287 | 100% | 0.66551 | 1 | Completed
ER6668LT | W213 | W213.6820 | TOR Essential Defueling Safety Case | Prepare Spec for Defuelling Hazards Review EAN | 2022-10-17 | 2022-10-31 | 5 | 0 | 11 | 14 | 100% | 0.35714 | 1 | Completed
W232LT | W232 | W232.A1710 | DNB Enhanced Safety Cases | Prepare Schedule | 2022-10-17 | 2022-10-21 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
W232LT | W232 | W232.A1290 | DNB Enhanced Safety Cases | Produce MF | 2022-10-17 | 2022-10-21 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
W232LT | W232 | W232.A1300 | DNB Enhanced Safety Cases | Agree design proposals with Station in the case of hardware mods | 2022-10-17 | 2022-10-21 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
W232LT | W232 | W232.A1270 | DNB Enhanced Safety Cases | Mod requested, Initiate EC, identify RE, register EC & identify milestones in Passport | 2022-10-17 | 2022-10-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1310 | DNB Enhanced Safety Cases | Produce supporting references | 2022-10-17 | 2022-10-21 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
W232LT | W232 | W232.A1280 | DNB Enhanced Safety Cases | Develop deliverable plan with Work Management (using CAT 3 template) | 2022-10-17 | 2022-10-18 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
W232LT | W232 | W232.A1320 | DNB Enhanced Safety Cases | Deliverable plan baselined; all ECs & references identified | 2022-10-18 | 2022-10-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1330 | DNB Enhanced Safety Cases | Issue agreed work programme to stakeholders and suppliers | 2022-10-18 | 2022-10-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.7070 | HYB Essential Defueling Safety Case | PJB for Claim 3 Authoring | 2022-10-19 | 2023-01-10 | 1 | 0 | 57 | 83 | 100% | 0.012048 | 1 | Completed
ER6666LT | W209 | W209.8370 | HYB Essential Defueling Safety Case | Claim 3 Production ## (Cost Summary) | 2022-10-19 | 2024-01-24 | 284 | 0 | 318 | 462 | 100% | 0.61472 | 1 | Completed
ER6668LT | W213 | W213.7070 | TOR Essential Defueling Safety Case | PJB for Claim 3 Authoring | 2022-10-19 | 2023-01-10 | 1 | 0 | 57 | 83 | 100% | 0.012048 | 1 | Completed
ER6668LT | W213 | W213.8370 | TOR Essential Defueling Safety Case | Claim 3 Production ## (Cost Summary) | 2022-10-19 | 2024-01-24 | 290 | 0 | 319 | 462 | 100% | 0.62771 | 1 | Completed
ER6666LT | W209 | W209.7080 | HYB Essential Defueling Safety Case | Author Claim 3 | 2022-10-20 | 2023-03-31 | 80 | 0 | 114 | 162 | 100% | 0.49383 | 1 | Completed
ER6668LT | W213 | W213.7080 | TOR Essential Defueling Safety Case | Author Claim 3 | 2022-10-20 | 2023-03-31 | 80 | 0 | 114 | 162 | 100% | 0.49383 | 1 | Completed
ER6666LT | W209 | W209.6890 | HYB Essential Defueling Safety Case | PJB for Claim 1 Authoring | 2022-10-21 | 2022-10-21 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.8350 | HYB Essential Defueling Safety Case | Claim 1 Production ## (Cost Summary) | 2022-10-21 | 2023-11-29 | 241 | 0 | 279 | 404 | 100% | 0.59653 | 1 | Completed
ER6668LT | W213 | W213.6890 | TOR Essential Defueling Safety Case | PJB for Claim 1 Authoring | 2022-10-21 | 2022-10-21 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.8350 | TOR Essential Defueling Safety Case | Claim 1 Production ## (Cost Summary) | 2022-10-21 | 2023-11-29 | 241 | 0 | 279 | 404 | 100% | 0.59653 | 1 | Completed
W232LT | W232 | W232.A1340 | DNB Enhanced Safety Cases | Issue MF | 2022-10-21 | 2022-10-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1350 | DNB Enhanced Safety Cases | CA appointed | 2022-10-21 | 2022-10-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.6900 | HYB Essential Defueling Safety Case | Author Claim 1 | 2022-10-24 | 2022-12-16 | 42 | 0 | 40 | 53 | 100% | 0.79245 | 1 | Completed
ER6668LT | W213 | W213.6900 | TOR Essential Defueling Safety Case | Author Claim 1 | 2022-10-24 | 2022-12-16 | 42 | 0 | 40 | 53 | 100% | 0.79245 | 1 | Completed
W232LT | W232 | W232.A1730 | DNB Enhanced Safety Cases | Prepare Cost Estimates +/- 10% B-C & +/- 30% Lifecycle | 2022-10-24 | 2022-11-01 | 5 | 0 | 7 | 8 | 100% | 0.625 | 1 | Completed
ER6666LT | W209 | W209.A29500 | HYB Essential Defueling Safety Case | Supplier Update and Issue Cooling Plant OPEX Study EAN | 2022-10-24 | 2022-10-28 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
W232LT | W232 | W232.A1370 | DNB Enhanced Safety Cases | Update MF (if necessary) | 2022-10-24 | 2022-10-26 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
W232LT | W232 | W232.A1380 | DNB Enhanced Safety Cases | Identify verifier (V) for case | 2022-10-24 | 2022-10-25 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
W232LT | W232 | W232.A1360 | DNB Enhanced Safety Cases | Categorisation by station | 2022-10-24 | 2022-10-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A29500 | TOR Essential Defueling Safety Case | Supplier Update and Issue Cooling Plant OPEX Study EAN | 2022-10-24 | 2022-10-28 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6666LT | W209 | W209.A26230 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Pressure Boundary Integrity of Seals Report EAN to CDMS | 2022-10-25 | 2022-11-30 | 5 | 0 | 27 | 36 | 100% | 0.13889 | 1 | Completed
ER6668LT | W213 | W213.A26230 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Pressure Boundary Integrity of Seals Report EAN to CDMS | 2022-10-25 | 2022-11-30 | 5 | 0 | 27 | 36 | 100% | 0.13889 | 1 | Completed
W232LT | W232 | W232.A1400 | DNB Enhanced Safety Cases | Produce verification plan | 2022-10-26 | 2022-10-26 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1410 | DNB Enhanced Safety Cases | MF Complete | 2022-10-26 | 2022-10-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1420 | DNB Enhanced Safety Cases | Prepare the Proposal | 2022-10-27 | 2022-11-02 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.A26530 | HYB Essential Defueling Safety Case | Technical Review of PANTHER SCM Assessments - Agree Defuelling Order EAN | 2022-10-31 | 2022-12-23 | 17 | 0 | 40 | 53 | 100% | 0.32075 | 1 | Completed
ER6666LT | W209 | W209.A27040 | HYB Essential Defueling Safety Case | Review of FM Cyclic Duty EAN Available | 2022-10-31 | 2022-10-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A27200 | HYB Essential Defueling Safety Case | Flow Induced Vibration EAN Available | 2022-10-31 | 2022-10-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A26530 | TOR Essential Defueling Safety Case | Technical Review of PANTHER SCM Assessments - Agree Defuelling Order EAN | 2022-10-31 | 2022-12-23 | 17 | 0 | 40 | 53 | 100% | 0.32075 | 1 | Completed
ER6668LT | W213 | W213.A27040 | TOR Essential Defueling Safety Case | Review of FM Cyclic Duty EAN Available | 2022-10-31 | 2022-10-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A27200 | TOR Essential Defueling Safety Case | Flow Induced Vibration EAN Available | 2022-10-31 | 2022-10-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1740 | DNB Enhanced Safety Cases | PRC Paper stakeholder sign off | 2022-10-31 | 2022-11-04 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6666LT | W209 | W209.A26600 | HYB Essential Defueling Safety Case | Verify Fault Review - Impact on SCM, Misloading Consequences & Issue for Technical Review | 2022-10-31 | 2022-12-13 | 4 | 0 | 32 | 43 | 100% | 0.093023 | 1 | Completed
ER6666LT | W209 | W209.A29510 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Cooling Plant OPEX Study EAN to CDMS | 2022-10-31 | 2022-11-11 | 5 | 0 | 10 | 11 | 100% | 0.45455 | 1 | Completed
ER6666LT | W209 | W209.A29830 | HYB Essential Defueling Safety Case | Supplier Update and Issue Feasibility of Draining PVCS (Report) | 2022-10-31 | 2022-11-18 | 5 | 0 | 15 | 18 | 100% | 0.27778 | 1 | Completed
ER6668LT | W213 | W213.A26600 | TOR Essential Defueling Safety Case | Verify Fault Review - Impact on SCM, Misloading Consequences & Issue for Technical Review | 2022-10-31 | 2022-12-13 | 4 | 0 | 32 | 43 | 100% | 0.093023 | 1 | Completed
ER6668LT | W213 | W213.A29510 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Cooling Plant OPEX Study EAN to CDMS | 2022-10-31 | 2022-11-11 | 5 | 0 | 10 | 11 | 100% | 0.45455 | 1 | Completed
ER6668LT | W213 | W213.A29830 | TOR Essential Defueling Safety Case | Supplier Update and Issue Feasibility of Draining PVCS (Report) | 2022-10-31 | 2022-11-18 | 5 | 0 | 15 | 18 | 100% | 0.27778 | 1 | Completed
ER6666LT | W209 | W209.A28970 | HYB Essential Defueling Safety Case | Summary of Compliance with RADWASTE Assessment Principles EAN ## (Cost Summary) (Claim 7) | 2022-11-01 | 2023-04-14 | 114 | 0 | 114 | 164 | 100% | 0.69512 | 1 | Completed
ER6666LT | W209 | W209.A28980 | HYB Essential Defueling Safety Case | Pre Job Brief for Summary of Compliance with RADWASTE Assessment Principles EAN | 2022-11-01 | 2022-11-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.6830 | HYB Essential Defueling Safety Case | Prepare Task Sheet for Defuelling Hazards Review EAN | 2022-11-01 | 2022-12-23 | 10 | 0 | 39 | 52 | 100% | 0.19231 | 1 | Completed
ER6666LT | W209 | W209.A29560 | HYB Essential Defueling Safety Case | TASK F Review of the Discharge Limits (Permits) EAN ## (Cost Summary) (Claim 7) | 2022-11-01 | 2023-05-12 | 132 | 0 | 132 | 192 | 100% | 0.6875 | 1 | Completed
ER6666LT | W209 | W209.A29570 | HYB Essential Defueling Safety Case | Pre Job Brief for TASK F Review of the Discharge Limits (Permits) EAN | 2022-11-01 | 2022-11-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.8060 | HYB Essential Defueling Safety Case | Verify HF Assessment of HF Assessment of the Extant Fuel Movement in support of Defueling FFV Claim | 2022-11-01 | 2023-02-03 | 20 | 0 | 66 | 94 | 100% | 0.21277 | 1 | Completed
ER6666LT | W209 | W209.8980 | HYB Essential Defueling Safety Case | Discovery Milestone - FM Underload Protection Mods - Drafted | 2022-11-01 | 2022-11-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A28680 | HYB Essential Defueling Safety Case | Verify CSP/Diagrid Structural Integrity Summary Report & Issue for Technical Review | 2022-11-01 | 2022-11-21 | 15 | 0 | 15 | 20 | 100% | 0.75 | 1 | Completed
ER6668LT | W213 | W213.A28970 | TOR Essential Defueling Safety Case | Summary of Compliance with RADWASTE Assessment Principles EAN ## (Cost Summary) (Claim 7) | 2022-11-01 | 2023-04-14 | 114 | 0 | 114 | 164 | 100% | 0.69512 | 1 | Completed
ER6668LT | W213 | W213.A28980 | TOR Essential Defueling Safety Case | Pre Job Brief for Summary of Compliance with RADWASTE Assessment Principles EAN | 2022-11-01 | 2022-11-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.6830 | TOR Essential Defueling Safety Case | Prepare Task Sheet for Defuelling Hazards Review EAN | 2022-11-01 | 2022-12-23 | 10 | 0 | 39 | 52 | 100% | 0.19231 | 1 | Completed
ER6668LT | W213 | W213.A29560 | TOR Essential Defueling Safety Case | TASK F Review of the Discharge Limits (Permits) EAN ## (Cost Summary) (Claim 7) | 2022-11-01 | 2023-05-12 | 132 | 0 | 132 | 192 | 100% | 0.6875 | 1 | Completed
ER6668LT | W213 | W213.A29570 | TOR Essential Defueling Safety Case | Pre Job Brief for TASK F Review of the Discharge Limits (Permits) EAN | 2022-11-01 | 2022-11-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.8060 | TOR Essential Defueling Safety Case | Verify HF Assessment of HF Assessment of the Extant Fuel Movement in support of Defueling FFV Claim | 2022-11-01 | 2023-02-03 | 20 | 0 | 66 | 94 | 100% | 0.21277 | 1 | Completed
ER6668LT | W213 | W213.8980 | TOR Essential Defueling Safety Case | Discovery Milestone - FM Underload Protection Mods - Drafted | 2022-11-01 | 2022-11-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A28680 | TOR Essential Defueling Safety Case | Verify CSP/Diagrid Structural Integrity Summary Report & Issue for Technical Review | 2022-11-01 | 2022-11-21 | 15 | 0 | 15 | 20 | 100% | 0.75 | 1 | Completed
ER6666LT | W209 | W209.A28990 | HYB Essential Defueling Safety Case | Draft Summary of Compliance with RADWASTE Assessment Principles EAN | 2022-11-02 | 2023-02-28 | 60 | 0 | 82 | 118 | 100% | 0.50847 | 1 | Completed
ER6668LT | W213 | W213.A28990 | TOR Essential Defueling Safety Case | Draft Summary of Compliance with RADWASTE Assessment Principles EAN | 2022-11-02 | 2023-02-28 | 60 | 0 | 82 | 118 | 100% | 0.50847 | 1 | Completed
ER6666LT | W209 | W209.A29580 | HYB Essential Defueling Safety Case | Draft TASK F Review of the Discharge Limits (Permits) EAN | 2022-11-02 | 2023-01-09 | 50 | 0 | 45 | 68 | 100% | 0.73529 | 1 | Completed
ER6666LT | W209 | W209.A29970 | HYB Essential Defueling Safety Case | Detailed Design Spec for FM Underload Protection Mods Prelim Design (GLM) | 2022-11-02 | 2023-04-14 | 32 | 0 | 113 | 163 | 100% | 0.19632 | 1 | Completed
ER6666LT | W209 | W209.A30700 | HYB Essential Defueling Safety Case | Detailed Design Spec for Channel 1 - HYB | 2022-11-02 | 2023-02-15 | 54 | 0 | 73 | 105 | 100% | 0.51429 | 1 | Completed
ER6371LT | W202 | 2370 | HRA Reactors Shutdown Essential Safety Cases | Verification PJB | 2022-11-02 | 2022-11-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | 1850 | HRA Reactors Shutdown Essential Safety Cases | Upload ALARP Review use of SA and SSP's to AMS | 2022-11-02 | 2023-10-19 | 3 | 0 | 242 | 351 | 100% | 0.008547 | 1 | Completed
ER6661LT | W206 | 2370 | HYA Reactors Shutdown Essential Safety Cases | Verification PJB | 2022-11-02 | 2022-11-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | 1850 | HYA Reactors Shutdown Essential Safety Cases | Upload ALARP Review use of SA and SSP's to AMS | 2022-11-02 | 2023-10-19 | 3 | 0 | 242 | 351 | 100% | 0.008547 | 1 | Completed
ER6666LT | W209 | W209.A30960 | HYB Essential Defueling Safety Case | Detailed Design Spec for Channel X | 2022-11-02 | 2023-04-21 | 63 | 0 | 117 | 170 | 100% | 0.37059 | 1 | Completed
ER6668LT | W213 | W213.A29580 | TOR Essential Defueling Safety Case | Draft TASK F Review of the Discharge Limits (Permits) EAN | 2022-11-02 | 2023-01-09 | 50 | 0 | 45 | 68 | 100% | 0.73529 | 1 | Completed
ER6668LT | W213 | W213.A29970 | TOR Essential Defueling Safety Case | Detailed Design Spec for FM Underload Protection Mods Prelim Design (GLM) | 2022-11-02 | 2023-04-14 | 32 | 0 | 113 | 163 | 100% | 0.19632 | 1 | Completed
ER6668LT | W213 | W213.A30700 | TOR Essential Defueling Safety Case | Detailed Design Spec for Channel 1 - TOR | 2022-11-02 | 2023-02-15 | 54 | 0 | 73 | 105 | 100% | 0.51429 | 1 | Completed
ER6668LT | W213 | W213.A30960 | TOR Essential Defueling Safety Case | Detailed Design Spec for Channel X | 2022-11-02 | 2023-04-21 | 63 | 0 | 117 | 170 | 100% | 0.37059 | 1 | Completed
W232LT | W232 | W232.A1440 | DNB Enhanced Safety Cases | Issue to SRE for comments | 2022-11-02 | 2022-11-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1450 | DNB Enhanced Safety Cases | Incorporate SRE comments | 2022-11-03 | 2022-11-09 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.A26310 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Reactor Internals & Structural Integrity During Defueling Report EAN to CDMS | 2022-11-04 | 2022-11-04 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A26320 | HYB Essential Defueling Safety Case | Reactor Internals & Structural Integrity During Defueling Report EAN Available | 2022-11-04 | 2022-11-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A26310 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Reactor Internals & Structural Integrity During Defueling Report EAN to CDMS | 2022-11-04 | 2022-11-04 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A26320 | TOR Essential Defueling Safety Case | Reactor Internals & Structural Integrity During Defueling Report EAN Available | 2022-11-04 | 2022-11-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A28060 | HYB Essential Defueling Safety Case | Supplier Update and Issue Update Basis of Analysis document - (Issue 3) | 2022-11-07 | 2022-11-21 | 5 | 0 | 11 | 14 | 100% | 0.35714 | 1 | Completed
ER6666LT | W209 | W209.A28760 | HYB Essential Defueling Safety Case | Verify Fuel Free Verification methods, an assessment against the ALARP principle EAN & Issue for Technical Review | 2022-11-07 | 2022-11-18 | 15 | 0 | 9 | 11 | 100% | 1.3636 | 1 | Completed
ER6666LT | W209 | W209.6980 | HYB Essential Defueling Safety Case | PJB for Claim 2 Authoring | 2022-11-07 | 2022-11-07 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.8360 | HYB Essential Defueling Safety Case | Claim 2 Production ## (Cost Summary) | 2022-11-07 | 2023-12-21 | 266 | 0 | 284 | 409 | 100% | 0.65037 | 1 | Completed
ER6666LT | W209 | W209.A31210 | HYB Essential Defueling Safety Case | Draft Update Basis of Analysis document | 2022-11-07 | 2022-12-01 | 15 | 0 | 19 | 24 | 100% | 0.625 | 1 | Completed
ER6668LT | W213 | W213.A28060 | TOR Essential Defueling Safety Case | Supplier Update and Issue Update Basis of Analysis document - (Issue 3) | 2022-11-07 | 2022-11-21 | 5 | 0 | 11 | 14 | 100% | 0.35714 | 1 | Completed
ER6668LT | W213 | W213.A28760 | TOR Essential Defueling Safety Case | Verify Fuel Free Verification methods, an assessment against the ALARP principle EAN & Issue for Technical Review | 2022-11-07 | 2022-11-18 | 15 | 0 | 9 | 11 | 100% | 1.3636 | 1 | Completed
ER6668LT | W213 | W213.6980 | TOR Essential Defueling Safety Case | PJB for Claim 2 Authoring | 2022-11-07 | 2022-11-07 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.8360 | TOR Essential Defueling Safety Case | Claim 2 Production ## (Cost Summary) | 2022-11-07 | 2023-12-21 | 251 | 0 | 284 | 409 | 100% | 0.61369 | 1 | Completed
ER6668LT | W213 | W213.A31210 | TOR Essential Defueling Safety Case | Draft Update Basis of Analysis document | 2022-11-07 | 2022-12-01 | 15 | 0 | 19 | 24 | 100% | 0.625 | 1 | Completed
ER6666LT | W209 | W209.6990 | HYB Essential Defueling Safety Case | Author Claim 2 | 2022-11-08 | 2023-02-24 | 53 | 0 | 76 | 108 | 100% | 0.49074 | 1 | Completed
ER6371LT | W202 | 2330 | HRA Reactors Shutdown Essential Safety Cases | CO Review | 2022-11-08 | 2022-11-14 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | 2310 | HRA Reactors Shutdown Essential Safety Cases | Review with Station RE's | 2022-11-08 | 2022-11-14 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | 2330 | HYA Reactors Shutdown Essential Safety Cases | CO Review | 2022-11-08 | 2022-11-14 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | 2310 | HYA Reactors Shutdown Essential Safety Cases | Review with Station RE's | 2022-11-08 | 2022-11-14 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.6990 | TOR Essential Defueling Safety Case | Author Claim 2 | 2022-11-08 | 2023-02-24 | 53 | 0 | 76 | 108 | 100% | 0.49074 | 1 | Completed
W232LT | W232 | W232.A1830 | DNB Enhanced Safety Cases | Gate A PRC Paper Submission | 2022-11-09 | 2022-11-09 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1460 | DNB Enhanced Safety Cases | Issue the case for review & verification | 2022-11-09 | 2022-11-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A26920 | HYB Essential Defueling Safety Case | Verify Chemistry Monitoring Strategy EAN & Issue for Technical Review | 2022-11-10 | 2022-11-30 | 16 | 0 | 14 | 20 | 100% | 0.8 | 1 | Completed
ER6668LT | W213 | W213.A26920 | TOR Essential Defueling Safety Case | Verify Chemistry Monitoring Strategy EAN & Issue for Technical Review | 2022-11-10 | 2022-11-30 | 16 | 0 | 14 | 20 | 100% | 0.8 | 1 | Completed
W232LT | W232 | W232.A1020 | DNB Enhanced Safety Cases | Agree resource & timescales with suppliers for delivering key refs, incl contingency, risk & allowance for rework | 2022-11-10 | 2022-11-16 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
W232LT | W232 | W232.A1010 | DNB Enhanced Safety Cases | Mod requested, Initiate EC, identify RE, register EC & identify milestones in AMS | 2022-11-10 | 2022-11-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1000 | DNB Enhanced Safety Cases | Raise Engineering Request (as required) | 2022-11-10 | 2022-11-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1470 | DNB Enhanced Safety Cases | Cat 3 EC - FPU Maintenance Reduction Verification of the case | 2022-11-10 | 2022-11-16 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
W232LT | W232 | W232.A1950 | DNB Enhanced Safety Cases | Cat 2 EC Rate Increase Scoping Exercise | 2022-11-10 | 2022-12-07 | 20 | 0 | 20 | 27 | 100% | 0.74074 | 1 | Completed
W232LT | W232 | W232.A1080 | DNB Enhanced Safety Cases | CO & CA appointed | 2022-11-10 | 2022-11-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1090 | DNB Enhanced Safety Cases | Key Stakeholders Identified | 2022-11-10 | 2022-11-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1100 | DNB Enhanced Safety Cases | Develop initial programme plan using mandatory template | 2022-11-11 | 2022-11-17 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.A29520 | HYB Essential Defueling Safety Case | Cooling Plant OPEX Study EAN Available | 2022-11-11 | 2022-11-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A29520 | TOR Essential Defueling Safety Case | Cooling Plant OPEX Study EAN Available | 2022-11-11 | 2022-11-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A26700 | HYB Essential Defueling Safety Case | Supplier Update and Issue Review of flux detector suitability EAN | 2022-11-14 | 2022-11-14 | 5 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A26700 | TOR Essential Defueling Safety Case | Supplier Update and Issue Review of flux detector suitability EAN | 2022-11-14 | 2022-11-14 | 5 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | 2340 | HRA Reactors Shutdown Essential Safety Cases | AMS Milestone - Ready for Review | 2022-11-14 | 2022-11-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | 2340 | HYA Reactors Shutdown Essential Safety Cases | AMS Milestone - Ready for Review | 2022-11-14 | 2022-11-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A26770 | HYB Essential Defueling Safety Case | Technical Review of Boron Bead Injection Feasibility & Control Rod Isolation EAN | 2022-11-15 | 2023-01-06 | 40 | 0 | 36 | 52 | 100% | 0.76923 | 1 | Completed
ER6668LT | W213 | W213.A26770 | TOR Essential Defueling Safety Case | Technical Review of Boron Bead Injection Feasibility & Control Rod Isolation EAN | 2022-11-15 | 2023-01-06 | 40 | 0 | 36 | 52 | 100% | 0.76923 | 1 | Completed
ER6666LT | W209 | W209.A26710 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Review of flux detector suitability EAN to CDMS | 2022-11-15 | 2022-11-21 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | 2390 | HRA Reactors Shutdown Essential Safety Cases | Sub-verifier(s) including GAP review (HHB Opexs) | 2022-11-15 | 2023-01-03 | 7 | 0 | 33 | 49 | 100% | 0.14286 | 1 | Completed
ER6371LT | W202 | 2380 | HRA Reactors Shutdown Essential Safety Cases | Verification including GAP review (Lead Verifier)( (HHB Opexs) | 2022-11-15 | 2023-01-03 | 7 | 0 | 33 | 49 | 100% | 0.14286 | 1 | Completed
ER6371LT | W202 | 2320 | HRA Reactors Shutdown Essential Safety Cases | Review changes with INA | 2022-11-15 | 2022-11-23 | 7 | 0 | 7 | 8 | 100% | 0.875 | 1 | Completed
ER6661LT | W206 | 2390 | HYA Reactors Shutdown Essential Safety Cases | Sub-verifier(s) including GAP review (HHB Opexs) | 2022-11-15 | 2023-01-03 | 7 | 0 | 33 | 49 | 100% | 0.14286 | 1 | Completed
ER6661LT | W206 | 2380 | HYA Reactors Shutdown Essential Safety Cases | Verification including GAP review (Lead Verifier)( (HHB Opexs) | 2022-11-15 | 2023-01-03 | 7 | 0 | 33 | 49 | 100% | 0.14286 | 1 | Completed
ER6661LT | W206 | 2320 | HYA Reactors Shutdown Essential Safety Cases | Review changes with INA | 2022-11-15 | 2022-11-23 | 7 | 0 | 7 | 8 | 100% | 0.875 | 1 | Completed
ER6668LT | W213 | W213.A26710 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Review of flux detector suitability EAN to CDMS | 2022-11-15 | 2022-11-21 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.A28200 | HYB Essential Defueling Safety Case | Verify CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN & Issue for Technical Review | 2022-11-16 | 2022-11-18 | 10 | 0 | 2 | 2 | 100% | 5 | 1 | Completed
ER6668LT | W213 | W213.A28200 | TOR Essential Defueling Safety Case | Verify CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN & Issue for Technical Review | 2022-11-16 | 2022-11-18 | 10 | 0 | 2 | 2 | 100% | 5 | 1 | Completed
ER6666LT | W209 | W209.A28250 | HYB Essential Defueling Safety Case | Fault Definition Document (FDD) EAN ## (Cost Summary) (Claim 4) | 2022-11-17 | 2023-10-10 | 219 | 0 | 224 | 327 | 100% | 0.66972 | 1 | Completed
ER6666LT | W209 | W209.A28260 | HYB Essential Defueling Safety Case | Pre Job Brief for Fault Definition Document (FDD) EAN | 2022-11-17 | 2022-11-17 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A28250 | TOR Essential Defueling Safety Case | Fault Definition Document (FDD) EAN ## (Cost Summary) (Claim 4) | 2022-11-17 | 2023-10-12 | 218 | 0 | 227 | 329 | 100% | 0.66261 | 1 | Completed
ER6668LT | W213 | W213.A28260 | TOR Essential Defueling Safety Case | Pre Job Brief for Fault Definition Document (FDD) EAN | 2022-11-17 | 2022-11-17 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | 2400 | HRA Reactors Shutdown Essential Safety Cases | Nuclear Safety Specialist Assessment(s) | 2022-11-17 | 2022-11-25 | 5 | 0 | 6 | 8 | 100% | 0.625 | 1 | Completed
ER6661LT | W206 | 2400 | HYA Reactors Shutdown Essential Safety Cases | Nuclear Safety Specialist Assessment(s) | 2022-11-17 | 2022-11-25 | 5 | 0 | 6 | 8 | 100% | 0.625 | 1 | Completed
W232LT | W232 | W232.A1110 | DNB Enhanced Safety Cases | Hold project kick start meeting with Station & key suppliers | 2022-11-17 | 2022-11-23 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
W232LT | W232 | W232.A1500 | DNB Enhanced Safety Cases | Produce verification file | 2022-11-17 | 2022-11-18 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
W232LT | W232 | W232.A1120 | DNB Enhanced Safety Cases | CA PJB Held | 2022-11-17 | 2022-11-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A28270 | HYB Essential Defueling Safety Case | Draft Fault Definition Document (FDD) EAN | 2022-11-18 | 2023-03-22 | 14 | 0 | 86 | 124 | 100% | 0.1129 | 1 | Completed
ER6668LT | W213 | W213.A28270 | TOR Essential Defueling Safety Case | Draft Fault Definition Document (FDD) EAN | 2022-11-18 | 2023-03-22 | 14 | 0 | 86 | 124 | 100% | 0.1129 | 1 | Completed
W232LT | W232 | W232.A1130 | DNB Enhanced Safety Cases | Produce MF (as required) | 2022-11-18 | 2022-11-18 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2670 | DNB Enhanced Safety Cases | Prepare Decision Paper | 2022-11-18 | 2022-12-05 | 9 | 0 | 12 | 17 | 100% | 0.52941 | 1 | Completed
W232LT | W232 | W232.A1160 | DNB Enhanced Safety Cases | Issue MF (as required) | 2022-11-18 | 2022-11-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1530 | DNB Enhanced Safety Cases | Verification complete | 2022-11-18 | 2022-11-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1540 | DNB Enhanced Safety Cases | Submit to Station Approvers | 2022-11-18 | 2022-11-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A28210 | HYB Essential Defueling Safety Case | Technical Review of CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN | 2022-11-21 | 2023-01-13 | 20 | 0 | 37 | 53 | 100% | 0.37736 | 1 | Completed
ER6666LT | W209 | W209.A28780 | HYB Essential Defueling Safety Case | Supplier Update and Issue Fuel Free Verification methods, an assessment against the ALARP principle EAN | 2022-11-21 | 2023-01-05 | 5 | 0 | 31 | 45 | 100% | 0.11111 | 1 | Completed
ER6666LT | W209 | W209.7160 | HYB Essential Defueling Safety Case | PJB for Claim 5 Authoring | 2022-11-21 | 2022-11-21 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.8390 | HYB Essential Defueling Safety Case | Claim 5 Production ## (Cost Summary) | 2022-11-21 | 2023-12-15 | 267 | 0 | 270 | 389 | 100% | 0.68638 | 1 | Completed
ER6668LT | W213 | W213.A28210 | TOR Essential Defueling Safety Case | Technical Review of CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN | 2022-11-21 | 2023-01-13 | 20 | 0 | 37 | 53 | 100% | 0.37736 | 1 | Completed
ER6668LT | W213 | W213.A28780 | TOR Essential Defueling Safety Case | Supplier Update and Issue Fuel Free Verification methods, an assessment against the ALARP principle EAN | 2022-11-21 | 2023-01-05 | 5 | 0 | 31 | 45 | 100% | 0.11111 | 1 | Completed
ER6668LT | W213 | W213.7160 | TOR Essential Defueling Safety Case | PJB for Claim 5 Authoring | 2022-11-21 | 2022-11-21 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.8390 | TOR Essential Defueling Safety Case | Claim 5 Production ## (Cost Summary) | 2022-11-21 | 2023-12-15 | 257 | 0 | 270 | 389 | 100% | 0.66067 | 1 | Completed
ER6666LT | W209 | W209.A29840 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Feasibility of Draining PVCS (Report) to CDMS | 2022-11-21 | 2022-11-23 | 5 | 0 | 2 | 2 | 100% | 2.5 | 1 | Completed
W232LT | W232 | W232.A1180 | DNB Enhanced Safety Cases | Produce draft NSRS (using BARRIER MODEL) | 2022-11-21 | 2022-12-09 | 15 | 0 | 15 | 18 | 100% | 0.83333 | 1 | Completed
W232LT | W232 | W232.A1170 | DNB Enhanced Safety Cases | Categorisation by RE / Station | 2022-11-21 | 2022-11-21 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1190 | DNB Enhanced Safety Cases | Identify verifier for the case & establish all other resources | 2022-11-21 | 2022-12-05 | 5 | 0 | 10 | 14 | 100% | 0.35714 | 1 | Completed
ER6668LT | W213 | W213.A29840 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Feasibility of Draining PVCS (Report) to CDMS | 2022-11-21 | 2022-11-23 | 5 | 0 | 2 | 2 | 100% | 2.5 | 1 | Completed
ER6666LT | W209 | W209.A26720 | HYB Essential Defueling Safety Case | Review of flux detector suitability EAN Available - (CLAIM 1 - A - B De-risking) | 2022-11-21 | 2022-11-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A26720 | TOR Essential Defueling Safety Case | Review of flux detector suitability EAN Available - (CLAIM 1 - A - B De-risking) | 2022-11-21 | 2022-11-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1940 | DNB Enhanced Safety Cases | Gate A IAB Paper Approval (DNB) (Not Required 22.11.2022 DP) | 2022-11-22 | 2022-11-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1920 | DNB Enhanced Safety Cases | Hold IAB Meeting (Not Required 22.11.2022 DP) | 2022-11-22 | 2022-11-22 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1890 | DNB Enhanced Safety Cases | Gate A IAB Paper Submission (Not Required 22.11.2022 DP) | 2022-11-22 | 2022-11-22 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1860 | DNB Enhanced Safety Cases | Gate A PRC Paper Approval | 2022-11-22 | 2022-11-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1850 | DNB Enhanced Safety Cases | Hold PRC | 2022-11-22 | 2022-11-22 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A28070 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Update Basis of Analysis document to CDMS - (Issue 3) | 2022-11-22 | 2022-11-29 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6666LT | W209 | W209.A28690 | HYB Essential Defueling Safety Case | Technical Review of CSP/Diagrid Structural Integrity Summary Report | 2022-11-22 | 2023-01-13 | 15 | 0 | 36 | 52 | 100% | 0.28846 | 1 | Completed
W232LT | W232 | W232.A1210 | DNB Enhanced Safety Cases | INSA agree MF (as required) *(KDM)* | 2022-11-22 | 2022-11-23 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6668LT | W213 | W213.A28070 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Update Basis of Analysis document to CDMS - (Issue 3) | 2022-11-22 | 2022-11-29 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6668LT | W213 | W213.A28690 | TOR Essential Defueling Safety Case | Technical Review of CSP/Diagrid Structural Integrity Summary Report | 2022-11-22 | 2023-01-13 | 15 | 0 | 36 | 52 | 100% | 0.28846 | 1 | Completed
ER6666LT | W209 | W209.A29850 | HYB Essential Defueling Safety Case | Feasibility of Draining PVCS (Report) Available | 2022-11-23 | 2022-11-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A29850 | TOR Essential Defueling Safety Case | Feasibility of Draining PVCS (Report) Available | 2022-11-23 | 2022-11-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A30560 | HYB Essential Defueling Safety Case | Verify Summary of Credible Start of Life Defects EAN & Issue for Technical Review (A - B De-Risking) | 2022-11-23 | 2022-12-01 | 7 | 0 | 6 | 8 | 100% | 0.875 | 1 | Completed
ER6668LT | W213 | W213.A30560 | TOR Essential Defueling Safety Case | Verify Summary of Credible Start of Life Defects EAN & Issue for Technical Review (A - B De-Risking) | 2022-11-23 | 2022-12-01 | 7 | 0 | 6 | 8 | 100% | 0.875 | 1 | Completed
W232LT | W232 | W232.A1240 | DNB Enhanced Safety Cases | INSA Approval Date Identified | 2022-11-23 | 2022-11-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1250 | DNB Enhanced Safety Cases | Provide Provisional NSC Date (Not required DP 23.11.2022) | 2022-11-23 | 2022-11-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A26950 | HYB Essential Defueling Safety Case | Upload Chemistry Monitoring Strategy EAN to CDMS | 2022-11-24 | 2023-03-03 | 12 | 0 | 69 | 99 | 100% | 0.12121 | 1 | Completed
ER6668LT | W213 | W213.A26950 | TOR Essential Defueling Safety Case | Upload Chemistry Monitoring Strategy EAN to CDMS | 2022-11-24 | 2023-03-03 | 12 | 0 | 69 | 99 | 100% | 0.12121 | 1 | Completed
ER6666LT | W209 | W209.A29400 | HYB Essential Defueling Safety Case | Verify Cooling Plant Availability Review EAN & Issue for Technical Review | 2022-11-25 | 2022-12-16 | 6 | 0 | 16 | 21 | 100% | 0.28571 | 1 | Completed
ER6668LT | W213 | W213.A29400 | TOR Essential Defueling Safety Case | Verify Cooling Plant Availability Review EAN & Issue for Technical Review | 2022-11-25 | 2022-12-16 | 6 | 0 | 16 | 21 | 100% | 0.28571 | 1 | Completed
W232LT | W232 | W232.A1960 | DNB Enhanced Safety Cases | Cat 2 EC Scoping Workshop | 2022-11-25 | 2022-11-28 | 2 | 0 | 2 | 3 | 100% | 0.66667 | 1 | Completed
ER6666LT | W209 | W209.A26460 | HYB Essential Defueling Safety Case | Supplier Update and Issue Define Nuclear Data (PANTHER Validation Calcs) EAN | 2022-11-28 | 2022-12-20 | 5 | 0 | 17 | 22 | 100% | 0.22727 | 1 | Completed
ER6666LT | W209 | W209.A26540 | HYB Essential Defueling Safety Case | Supplier Update and Issue PANTHER SCM Assessments - Agree Defuelling Order EAN | 2022-11-28 | 2023-01-04 | 5 | 0 | 25 | 37 | 100% | 0.13514 | 1 | Completed
ER6668LT | W213 | W213.A26460 | TOR Essential Defueling Safety Case | Supplier Update and Issue Define Nuclear Data (PANTHER Validation Calcs) EAN | 2022-11-28 | 2022-12-20 | 5 | 0 | 17 | 22 | 100% | 0.22727 | 1 | Completed
ER6668LT | W213 | W213.A26540 | TOR Essential Defueling Safety Case | Supplier Update and Issue PANTHER SCM Assessments - Agree Defuelling Order EAN | 2022-11-28 | 2023-01-04 | 5 | 0 | 25 | 37 | 100% | 0.13514 | 1 | Completed
ER6666LT | W209 | W209.A28080 | HYB Essential Defueling Safety Case | Update Basis of Analysis document Available - (Issue 3) | 2022-11-29 | 2022-11-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | 3000 | HRA Reactors Shutdown Essential Safety Cases | Address Recommendations and Observations | 2022-11-29 | 2023-02-24 | 51 | 0 | 60 | 87 | 100% | 0.58621 | 1 | Completed
ER6661LT | W206 | 3000 | HYA Reactors Shutdown Essential Safety Cases | Address Recommendations and Observations | 2022-11-29 | 2023-02-24 | 51 | 0 | 60 | 87 | 100% | 0.58621 | 1 | Completed
ER6668LT | W213 | W213.A28080 | TOR Essential Defueling Safety Case | Update Basis of Analysis document Available - (Issue 3) | 2022-11-29 | 2022-11-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.28760 | HYB Essential Defueling Safety Case | Discovery Milestone - Confirm Additional Protections Needed for Preventing ML/MD Faults | 2022-11-30 | 2022-11-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.28760 | TOR Essential Defueling Safety Case | Discovery Milestone - Confirm Additional Protections Needed for Preventing ML/MD Faults | 2022-11-30 | 2022-11-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A26240 | HYB Essential Defueling Safety Case | Pressure Boundary Integrity of Seals Report EAN Available | 2022-11-30 | 2022-11-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A26240 | TOR Essential Defueling Safety Case | Pressure Boundary Integrity of Seals Report EAN Available | 2022-11-30 | 2022-11-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1930 | DNB Enhanced Safety Cases | Release of Funds | 2022-12-01 | 2022-12-14 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6666LT | W209 | W209.A25990 | HYB Essential Defueling Safety Case | Upload Civil Assesment of the Ponds at Low Temperature EAN to CDMS | 2022-12-01 | 2022-12-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.A26070 | HYB Essential Defueling Safety Case | Upload Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN to CDMS | 2022-12-01 | 2022-12-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.A31110 | HYB Essential Defueling Safety Case | Verify Defueling Process Flow & Issue | 2022-12-01 | 2023-07-17 | 10 | 0 | 155 | 228 | 100% | 0.04386 | 1 | Completed
ER6668LT | W213 | W213.A25990 | TOR Essential Defueling Safety Case | Upload Civil Assesment of the Ponds at Low Temperature EAN to CDMS | 2022-12-01 | 2022-12-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.A26070 | TOR Essential Defueling Safety Case | Upload Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN to CDMS | 2022-12-01 | 2022-12-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.A31110 | TOR Essential Defueling Safety Case | Verify Defueling Process Flow & Issue | 2022-12-01 | 2023-07-17 | 10 | 0 | 155 | 228 | 100% | 0.04386 | 1 | Completed
ER6666LT | W209 | W209.A28460 | HYB Essential Defueling Safety Case | Supplier Update and Issue Summary of Credible Start of Life Defects EAN | 2022-12-02 | 2022-12-05 | 5 | 0 | 2 | 3 | 100% | 1.6667 | 1 | Completed
ER6668LT | W213 | W213.A28460 | TOR Essential Defueling Safety Case | Supplier Update and Issue Summary of Credible Start of Life Defects EAN | 2022-12-02 | 2022-12-05 | 5 | 0 | 2 | 3 | 100% | 1.6667 | 1 | Completed
ER6666LT | W209 | W209.A31220 | HYB Essential Defueling Safety Case | Verify Update Basis of Analysis document & Issue for Technical Review | 2022-12-02 | 2023-01-20 | 2 | 0 | 33 | 49 | 100% | 0.040816 | 1 | Completed
ER6668LT | W213 | W213.A31220 | TOR Essential Defueling Safety Case | Verify Update Basis of Analysis document & Issue for Technical Review | 2022-12-02 | 2023-01-20 | 2 | 0 | 33 | 49 | 100% | 0.040816 | 1 | Completed
ER6666LT | W209 | W209.28990 | HYB Essential Defueling Safety Case | OPEX Review (Stations) against existing Misloading / Mis-Defueling Faults | 2022-12-05 | 2023-01-06 | 1 | 0 | 22 | 32 | 100% | 0.03125 | 1 | Completed
ER6666LT | W209 | W209.29000 | HYB Essential Defueling Safety Case | OPEX Review Internal Review and Gap analysis against existing Misloading / Mis-Defueling Faults | 2022-12-05 | 2023-01-06 | 1 | 0 | 22 | 32 | 100% | 0.03125 | 1 | Completed
ER6668LT | W213 | W213.28990 | TOR Essential Defueling Safety Case | OPEX Review (Stations) against existing Misloading / Mis-Defueling Faults | 2022-12-05 | 2023-01-06 | 1 | 0 | 22 | 32 | 100% | 0.03125 | 1 | Completed
ER6668LT | W213 | W213.29000 | TOR Essential Defueling Safety Case | OPEX Review Internal Review and Gap analysis against existing Misloading / Mis-Defueling Faults | 2022-12-05 | 2023-01-06 | 1 | 0 | 22 | 32 | 100% | 0.03125 | 1 | Completed
ER6666LT | W209 | W209.28920 | HYB Essential Defueling Safety Case | Mid Job Brief for WP5 | 2022-12-05 | 2022-12-05 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.28920 | TOR Essential Defueling Safety Case | Mid Job Brief for WP5 | 2022-12-05 | 2022-12-05 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A28470 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Summary of Credible Start of Life Defects EAN to CDMS | 2022-12-06 | 2022-12-22 | 5 | 0 | 12 | 16 | 100% | 0.3125 | 1 | Completed
ER6668LT | W213 | W213.A28470 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Summary of Credible Start of Life Defects EAN to CDMS | 2022-12-06 | 2022-12-22 | 5 | 0 | 12 | 16 | 100% | 0.3125 | 1 | Completed
ER6666LT | W209 | W209.3820 | HYB Essential Defueling Safety Case | Civils Assessment Report Received for PCPV Integrity Justification - Report Available | 2022-12-07 | 2022-12-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.3880 | HYB Essential Defueling Safety Case | Civils Assessment Report Received for Seismic Assessment - Report Available | 2022-12-07 | 2022-12-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A26000 | HYB Essential Defueling Safety Case | Civil Assesment of the Ponds at Low Temperature EAN Available | 2022-12-07 | 2022-12-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A26080 | HYB Essential Defueling Safety Case | Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN Available | 2022-12-07 | 2022-12-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.3820 | TOR Essential Defueling Safety Case | Civils Assessment Report Received for PCPV Integrity Justification - Report Available | 2022-12-07 | 2022-12-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.3880 | TOR Essential Defueling Safety Case | Civils Assessment Report Received for Seismic Assessment - Report Available | 2022-12-07 | 2022-12-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A26000 | TOR Essential Defueling Safety Case | Civil Assesment of the Ponds at Low Temperature EAN Available | 2022-12-07 | 2022-12-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A26080 | TOR Essential Defueling Safety Case | Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN Available | 2022-12-07 | 2022-12-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A27300 | HYB Essential Defueling Safety Case | Pre Job Brief for Reactor Fault Schedule Amendments EAN | 2022-12-08 | 2022-12-08 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A27290 | HYB Essential Defueling Safety Case | Costs Reactor Fault Schedule Amendments EAN ## (Cost Summary) (Claim 5) | 2022-12-08 | 2024-01-31 | 314 | 0 | 287 | 419 | 100% | 0.7494 | 1 | Completed
ER6668LT | W213 | W213.A27300 | TOR Essential Defueling Safety Case | Pre Job Brief for Reactor Fault Schedule Amendments EAN | 2022-12-08 | 2022-12-08 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A27290 | TOR Essential Defueling Safety Case | Costs Reactor Fault Schedule Amendments EAN ## (Cost Summary) (Claim 5) | 2022-12-08 | 2024-01-31 | 314 | 0 | 287 | 419 | 100% | 0.7494 | 1 | Completed
W232LT | W232 | W232.A2680 | DNB Enhanced Safety Cases | Obtain Agreement from Programme Board | 2022-12-12 | 2023-02-17 | 11 | 0 | 47 | 67 | 100% | 0.16418 | 1 | Completed
ER6666LT | W209 | W209.A28850 | HYB Essential Defueling Safety Case | Technical Review by Case Officer for Define Failed Fuel Free Controls File Note | 2022-12-12 | 2022-12-16 | 10 | 0 | 5 | 4 | 100% | 2.5 | 1 | Completed
W232LT | W232 | W232.A1510 | DNB Enhanced Safety Cases | Station comments on NSRS | 2022-12-12 | 2022-12-21 | 8 | 0 | 8 | 9 | 100% | 0.88889 | 1 | Completed
W232LT | W232 | W232.A1520 | DNB Enhanced Safety Cases | Key Stakeholders (Peer) comments on NSRS (as required) | 2022-12-12 | 2022-12-21 | 8 | 0 | 8 | 9 | 100% | 0.88889 | 1 | Completed
ER6668LT | W213 | W213.A28850 | TOR Essential Defueling Safety Case | Technical Review by Case Officer for Define Failed Fuel Free Controls File Note | 2022-12-12 | 2022-12-16 | 10 | 0 | 5 | 4 | 100% | 2.5 | 1 | Completed
ER6666LT | W209 | W209.A26610 | HYB Essential Defueling Safety Case | Technical Review of Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 2022-12-14 | 2023-01-06 | 8 | 0 | 15 | 23 | 100% | 0.34783 | 1 | Completed
ER6668LT | W213 | W213.A26610 | TOR Essential Defueling Safety Case | Technical Review of Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 2022-12-14 | 2023-01-06 | 8 | 0 | 15 | 23 | 100% | 0.34783 | 1 | Completed
ER6666LT | W209 | W209.A27400 | HYB Essential Defueling Safety Case | Verify Fuel Route PSA Update EAN & Issue for Technical Review | 2022-12-15 | 2023-03-20 | 20 | 0 | 65 | 95 | 100% | 0.21053 | 1 | Completed
ER6668LT | W213 | W213.A27400 | TOR Essential Defueling Safety Case | Verify Fuel Route PSA Update EAN & Issue for Technical Review | 2022-12-15 | 2023-03-20 | 20 | 0 | 65 | 95 | 100% | 0.21053 | 1 | Completed
ER6666LT | W209 | W209.29070 | HYB Essential Defueling Safety Case | Review EAT and Phase Imbalance cases and understand defuelling impact | 2022-12-19 | 2023-02-03 | 1 | 0 | 32 | 46 | 100% | 0.021739 | 1 | Completed
ER6666LT | W209 | W209.29080 | HYB Essential Defueling Safety Case | Identify shortfalls against the SCC | 2022-12-19 | 2023-02-28 | 1 | 0 | 49 | 71 | 100% | 0.014085 | 1 | Completed
ER6666LT | W209 | W209.29130 | HYB Essential Defueling Safety Case | Ongoing update of Fault schedule as safety case references and claim text becomes available | 2022-12-19 | 2023-02-03 | 1 | 0 | 32 | 46 | 100% | 0.021739 | 1 | Completed
ER6668LT | W213 | W213.29070 | TOR Essential Defueling Safety Case | Review EAT and Phase Imbalance cases and understand defuelling impact | 2022-12-19 | 2023-02-03 | 1 | 0 | 32 | 46 | 100% | 0.021739 | 1 | Completed
ER6668LT | W213 | W213.29080 | TOR Essential Defueling Safety Case | Identify shortfalls against the SCC | 2022-12-19 | 2023-02-28 | 1 | 0 | 49 | 71 | 100% | 0.014085 | 1 | Completed
ER6668LT | W213 | W213.29130 | TOR Essential Defueling Safety Case | Ongoing update of Fault schedule as safety case references and claim text becomes available | 2022-12-19 | 2023-02-03 | 1 | 0 | 32 | 46 | 100% | 0.021739 | 1 | Completed
ER6666LT | W209 | W209.A28870 | HYB Essential Defueling Safety Case | Complete TR Form and Approve Define Failed Fuel Free Controls File Note | 2022-12-19 | 2022-12-23 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6666LT | W209 | W209.6910 | HYB Essential Defueling Safety Case | Case Officer Tech Lead Review Claim 1 | 2022-12-19 | 2023-01-27 | 30 | 0 | 26 | 39 | 100% | 0.76923 | 1 | Completed
ER6666LT | W209 | W209.A29410 | HYB Essential Defueling Safety Case | Technical Review of Cooling Plant Availability Review EAN | 2022-12-19 | 2023-02-02 | 17 | 0 | 31 | 45 | 100% | 0.37778 | 1 | Completed
ER6668LT | W213 | W213.A28870 | TOR Essential Defueling Safety Case | Complete TR Form and Approve Define Failed Fuel Free Controls File Note | 2022-12-19 | 2022-12-23 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6668LT | W213 | W213.6910 | TOR Essential Defueling Safety Case | Case Officer Tech Lead Review Claim 1 | 2022-12-19 | 2023-01-27 | 30 | 0 | 26 | 39 | 100% | 0.76923 | 1 | Completed
ER6668LT | W213 | W213.A29410 | TOR Essential Defueling Safety Case | Technical Review of Cooling Plant Availability Review EAN | 2022-12-19 | 2023-02-02 | 17 | 0 | 31 | 45 | 100% | 0.37778 | 1 | Completed
ER6666LT | W209 | W209.A26470 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Define Nuclear Data (PANTHER Validation Calcs) EAN to CDMS | 2022-12-21 | 2023-01-13 | 5 | 0 | 14 | 23 | 100% | 0.21739 | 1 | Completed
ER6668LT | W213 | W213.A26470 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Define Nuclear Data (PANTHER Validation Calcs) EAN to CDMS | 2022-12-21 | 2023-01-13 | 5 | 0 | 14 | 23 | 100% | 0.21739 | 1 | Completed
W232LT | W232 | W232.A1560 | DNB Enhanced Safety Cases | INSA Resource Identified | 2022-12-21 | 2022-12-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A28480 | HYB Essential Defueling Safety Case | Summary of Credible Start of Life Defects EAN Available | 2022-12-22 | 2022-12-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A28480 | TOR Essential Defueling Safety Case | Summary of Credible Start of Life Defects EAN Available | 2022-12-22 | 2022-12-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1570 | DNB Enhanced Safety Cases | INA comments on NSRS | 2022-12-22 | 2023-01-27 | 10 | 0 | 23 | 36 | 100% | 0.27778 | 1 | Completed
ER6666LT | W209 | W209.A28880 | HYB Essential Defueling Safety Case | Define Failed Fuel Free Controls File Note Available | 2022-12-23 | 2022-12-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A28880 | TOR Essential Defueling Safety Case | Define Failed Fuel Free Controls File Note Available | 2022-12-23 | 2022-12-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W520LT | W520 | W520.A1020 | FLEETWIDE CTO Defueling Safety Case Delivery | 2023 Costs | 2023-01-03 | 2023-12-29 | 252 | 0 | 251 | 360 | 100% | 0.7 | 1 | Completed
ER6666LT | W209 | W209.28870 | HYB Essential Defueling Safety Case | Update PSA to REV 001 Following all Works | 2023-01-03 | 2023-11-17 | 10 | 0 | 223 | 318 | 100% | 0.031447 | 1 | Completed
ER6668LT | W213 | W213.28870 | TOR Essential Defueling Safety Case | Update PSA to REV 001 Following all Works | 2023-01-03 | 2023-11-17 | 10 | 0 | 222 | 318 | 100% | 0.031447 | 1 | Completed
ER6666LT | W209 | W209.A29050 | HYB Essential Defueling Safety Case | Defuelling Handling Deterministic Assessment EAN ## (Cost Summary) (Claim 7) | 2023-01-03 | 2024-01-31 | 276 | 0 | 272 | 393 | 100% | 0.70229 | 1 | Completed
ER6666LT | W209 | W209.A29130 | HYB Essential Defueling Safety Case | Defuelling Worker Risk Assessment EAN ## (Cost Summary) (Claim 7) | 2023-01-03 | 2024-08-09 | 406 | 0 | 406 | 584 | 100% | 0.69521 | 1 | Completed
ER6666LT | W209 | W209.6760 | HYB Essential Defueling Safety Case | Prepare Spec for Defuelling Handling Deterministic Assessment EAN | 2023-01-03 | 2023-01-09 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.6790 | HYB Essential Defueling Safety Case | Prepare Spec for Defuelling Worker Risk Assessment EAN | 2023-01-03 | 2023-01-09 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.6840 | HYB Essential Defueling Safety Case | Approve Task Sheet for Defuelling Hazards Review EAN | 2023-01-03 | 2023-01-27 | 5 | 0 | 19 | 24 | 100% | 0.20833 | 1 | Completed
ER6666LT | W209 | W209.28800 | HYB Essential Defueling Safety Case | Step 2 - Create Draft Operator Claims Matrix | 2023-01-03 | 2023-03-24 | 19 | 0 | 59 | 80 | 100% | 0.2375 | 1 | Completed
ER6371LT | W202 | 2325 | HRA Reactors Shutdown Essential Safety Cases | Update EC (Version 5) | 2023-01-03 | 2023-02-10 | 29 | 0 | 29 | 38 | 100% | 0.76316 | 1 | Completed
ER6661LT | W206 | 2325 | HYA Reactors Shutdown Essential Safety Cases | Update EC (Version 5) | 2023-01-03 | 2023-02-10 | 29 | 0 | 29 | 38 | 100% | 0.76316 | 1 | Completed
ER6668LT | W213 | W213.A29050 | TOR Essential Defueling Safety Case | Defuelling Handling Deterministic Assessment EAN ## (Cost Summary) (Claim 7) | 2023-01-03 | 2024-01-31 | 278 | 0 | 272 | 393 | 100% | 0.70738 | 1 | Completed
ER6668LT | W213 | W213.A29130 | TOR Essential Defueling Safety Case | Defuelling Worker Risk Assessment EAN ## (Cost Summary) (Claim 7) | 2023-01-03 | 2024-08-09 | 406 | 0 | 406 | 584 | 100% | 0.69521 | 1 | Completed
ER6668LT | W213 | W213.6760 | TOR Essential Defueling Safety Case | Prepare Spec for Defuelling Handling Deterministic Assessment EAN | 2023-01-03 | 2023-01-09 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.6790 | TOR Essential Defueling Safety Case | Prepare Spec for Defuelling Worker Risk Assessment EAN | 2023-01-03 | 2023-01-09 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.6840 | TOR Essential Defueling Safety Case | Approve Task Sheet for Defuelling Hazards Review EAN | 2023-01-03 | 2023-01-27 | 5 | 0 | 19 | 24 | 100% | 0.20833 | 1 | Completed
ER6668LT | W213 | W213.28800 | TOR Essential Defueling Safety Case | Step 2 - Create Draft Operator Claims Matrix | 2023-01-03 | 2023-03-24 | 19 | 0 | 59 | 80 | 100% | 0.2375 | 1 | Completed
ER6666LT | W209 | W209.A26550 | HYB Essential Defueling Safety Case | Complete TR Form and Upload PANTHER SCM Assessments - Agree Defuelling Order EAN to CDMS | 2023-01-05 | 2023-01-17 | 5 | 0 | 8 | 12 | 100% | 0.41667 | 1 | Completed
ER6668LT | W213 | W213.A26550 | TOR Essential Defueling Safety Case | Complete TR Form and Upload PANTHER SCM Assessments - Agree Defuelling Order EAN to CDMS | 2023-01-05 | 2023-01-17 | 5 | 0 | 8 | 12 | 100% | 0.41667 | 1 | Completed
ER6666LT | W209 | W209.A28790 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Fuel Free Verification methods, an assessment against the ALARP principle EAN | 2023-01-06 | 2023-03-31 | 5 | 0 | 60 | 84 | 100% | 0.059524 | 1 | Completed
ER6668LT | W213 | W213.A28790 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Fuel Free Verification methods, an assessment against the ALARP principle EAN | 2023-01-06 | 2023-03-31 | 5 | 0 | 60 | 84 | 100% | 0.059524 | 1 | Completed
ER6666LT | W209 | W209.A26620 | HYB Essential Defueling Safety Case | Supplier Update and Issue Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 2023-01-09 | 2023-01-13 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6666LT | W209 | W209.A26780 | HYB Essential Defueling Safety Case | Supplier Update and Issue Boron Bead Injection Feasibility & Control Rod Isolation EAN | 2023-01-09 | 2023-02-28 | 5 | 0 | 37 | 50 | 100% | 0.1 | 1 | Completed
ER6666LT | W209 | W209.A29590 | HYB Essential Defueling Safety Case | Verify TASK F Review of the Discharge Limits (Permits) EAN & Issue for Technical Review | 2023-01-09 | 2023-02-28 | 5 | 0 | 37 | 50 | 100% | 0.1 | 1 | Completed
ER6668LT | W213 | W213.A26620 | TOR Essential Defueling Safety Case | Supplier Update and Issue Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 2023-01-09 | 2023-01-13 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6668LT | W213 | W213.A26780 | TOR Essential Defueling Safety Case | Supplier Update and Issue Boron Bead Injection Feasibility & Control Rod Isolation EAN | 2023-01-09 | 2023-02-28 | 5 | 0 | 37 | 50 | 100% | 0.1 | 1 | Completed
ER6668LT | W213 | W213.A29590 | TOR Essential Defueling Safety Case | Verify TASK F Review of the Discharge Limits (Permits) EAN & Issue for Technical Review | 2023-01-09 | 2023-02-28 | 5 | 0 | 37 | 50 | 100% | 0.1 | 1 | Completed
W232LT | W232 | W232.A1580 | DNB Enhanced Safety Cases | Develop plan with further iterations | 2023-01-11 | 2023-01-24 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6666LT | W209 | W209.A26480 | HYB Essential Defueling Safety Case | Define Nuclear Data (PANTHER Validation Calcs) EAN Available | 2023-01-13 | 2023-01-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A26480 | TOR Essential Defueling Safety Case | Define Nuclear Data (PANTHER Validation Calcs) EAN Available | 2023-01-13 | 2023-01-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A25890 | HYB Essential Defueling Safety Case | Technical Review of Safety Case Requirements EAN - TASK E EAN | 2023-01-16 | 2023-02-17 | 5 | 0 | 24 | 32 | 100% | 0.15625 | 1 | Completed
ER6666LT | W209 | W209.A26630 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN to CDMS | 2023-01-16 | 2023-01-24 | 5 | 0 | 6 | 8 | 100% | 0.625 | 1 | Completed
ER6666LT | W209 | W209.A28220 | HYB Essential Defueling Safety Case | Supplier Update and Issue CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN | 2023-01-16 | 2023-03-17 | 5 | 0 | 45 | 60 | 100% | 0.083333 | 1 | Completed
ER6666LT | W209 | W209.A28700 | HYB Essential Defueling Safety Case | Supplier Update and Issue CSP/Diagrid Structural Integrity Summary Report | 2023-01-16 | 2023-03-17 | 5 | 0 | 45 | 60 | 100% | 0.083333 | 1 | Completed
ER6668LT | W213 | W213.A25890 | TOR Essential Defueling Safety Case | Technical Review of Safety Case Requirements EAN - TASK E EAN | 2023-01-16 | 2023-02-17 | 5 | 0 | 24 | 32 | 100% | 0.15625 | 1 | Completed
ER6668LT | W213 | W213.A26630 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN to CDMS | 2023-01-16 | 2023-01-24 | 5 | 0 | 6 | 8 | 100% | 0.625 | 1 | Completed
ER6668LT | W213 | W213.A28220 | TOR Essential Defueling Safety Case | Supplier Update and Issue CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN | 2023-01-16 | 2023-03-17 | 5 | 0 | 45 | 60 | 100% | 0.083333 | 1 | Completed
ER6668LT | W213 | W213.A28700 | TOR Essential Defueling Safety Case | Supplier Update and Issue CSP/Diagrid Structural Integrity Summary Report | 2023-01-16 | 2023-03-17 | 5 | 0 | 45 | 60 | 100% | 0.083333 | 1 | Completed
ER6666LT | W209 | W209.A26560 | HYB Essential Defueling Safety Case | PANTHER SCM Assessments - Agree Defuelling Order EAN Available | 2023-01-17 | 2023-01-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A26560 | TOR Essential Defueling Safety Case | PANTHER SCM Assessments - Agree Defuelling Order EAN Available | 2023-01-17 | 2023-01-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1550 | DNB Enhanced Safety Cases | Station approval for mod implementation (inlcuding station review meeting) | 2023-01-20 | 2023-01-20 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A31230 | HYB Essential Defueling Safety Case | Technical Review of Update Basis if Analysis document - (Issue 5) | 2023-01-23 | 2023-02-21 | 10 | 0 | 21 | 29 | 100% | 0.34483 | 1 | Completed
ER6371LT | W202 | 3010 | HRA Reactors Shutdown Essential Safety Cases | Update Summary Report | 2023-01-23 | 2023-02-24 | 20 | 0 | 24 | 32 | 100% | 0.625 | 1 | Completed
ER6661LT | W206 | 3010 | HYA Reactors Shutdown Essential Safety Cases | Update Summary Report | 2023-01-23 | 2023-02-24 | 20 | 0 | 24 | 32 | 100% | 0.625 | 1 | Completed
ER6668LT | W213 | W213.A31230 | TOR Essential Defueling Safety Case | Technical Review of Update Basis if Analysis document - (Issue 5) | 2023-01-23 | 2023-02-21 | 10 | 0 | 21 | 29 | 100% | 0.34483 | 1 | Completed
ER6666LT | W209 | W209.A26640 | HYB Essential Defueling Safety Case | Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN Available | 2023-01-24 | 2023-01-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.25950 | HYB Essential Defueling Safety Case | Discovery Milestone - Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN Available | 2023-01-24 | 2023-01-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A26640 | TOR Essential Defueling Safety Case | Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN Available | 2023-01-24 | 2023-01-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.25950 | TOR Essential Defueling Safety Case | Discovery Milestone - Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN Available | 2023-01-24 | 2023-01-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1640 | DNB Enhanced Safety Cases | Verifier PJB Held | 2023-01-24 | 2023-01-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.8900 | HYB Essential Defueling Safety Case | Human Factors Decision Making (Pre Workshop) Activities on Quantifying ML/MD Faults | 2023-01-25 | 2023-01-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.8910 | HYB Essential Defueling Safety Case | Human Factors Decision Making Workshop on Quantifying ML/MD Faults | 2023-01-25 | 2023-01-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.8920 | HYB Essential Defueling Safety Case | Discovery Milestone - Human Factors Decisions on Scope for WP4 | 2023-01-25 | 2023-01-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.29090 | HYB Essential Defueling Safety Case | Fault schedule sentencing workshop | 2023-01-25 | 2023-01-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.8900 | TOR Essential Defueling Safety Case | Human Factors Decision Making (Pre Workshop) Activities on Quantifying ML/MD Faults | 2023-01-25 | 2023-01-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.8910 | TOR Essential Defueling Safety Case | Human Factors Decision Making Workshop on Quantifying ML/MD Faults | 2023-01-25 | 2023-01-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.8920 | TOR Essential Defueling Safety Case | Discovery Milestone - Human Factors Decisions on Scope for WP4 | 2023-01-25 | 2023-01-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.29090 | TOR Essential Defueling Safety Case | Fault schedule sentencing workshop | 2023-01-25 | 2023-01-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.6770 | HYB Essential Defueling Safety Case | Prepare Task Sheet for Defuelling Handling Deterministic Assessment EAN | 2023-01-26 | 2023-01-30 | 10 | 0 | 3 | 4 | 100% | 2.5 | 1 | Completed
ER6666LT | W209 | W209.6800 | HYB Essential Defueling Safety Case | Prepare Task Sheet for Defuelling Worker Risk Assessment EAN | 2023-01-26 | 2023-02-06 | 10 | 0 | 8 | 11 | 100% | 0.90909 | 1 | Completed
ER6668LT | W213 | W213.6770 | TOR Essential Defueling Safety Case | Prepare Task Sheet for Defuelling Handling Deterministic Assessment EAN | 2023-01-26 | 2023-01-30 | 10 | 0 | 3 | 4 | 100% | 2.5 | 1 | Completed
ER6668LT | W213 | W213.6800 | TOR Essential Defueling Safety Case | Prepare Task Sheet for Defuelling Worker Risk Assessment EAN | 2023-01-26 | 2023-02-06 | 10 | 0 | 8 | 11 | 100% | 0.90909 | 1 | Completed
ER6666LT | W209 | W209.6920 | HYB Essential Defueling Safety Case | Verification of Claim 1 | 2023-01-30 | 2023-09-18 | 20 | 0 | 159 | 231 | 100% | 0.08658 | 1 | Completed
W232LT | W232 | W232.A1590 | DNB Enhanced Safety Cases | Incorporate INA, Station, ED (peer) comments | 2023-01-30 | 2023-02-03 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6668LT | W213 | W213.6920 | TOR Essential Defueling Safety Case | Verification of Claim 1 | 2023-01-30 | 2023-09-18 | 20 | 0 | 159 | 231 | 100% | 0.08658 | 1 | Completed
ER6666LT | W209 | W209.A26360 | HYB Essential Defueling Safety Case | Verify Graphite Summary Report EAN | 2023-01-31 | 2023-02-24 | 21 | 0 | 19 | 24 | 100% | 0.875 | 1 | Completed
ER6666LT | W209 | W209.A29230 | HYB Essential Defueling Safety Case | Draft Defuelling Hazards Review EAN | 2023-01-31 | 2023-03-10 | 28 | 0 | 29 | 38 | 100% | 0.73684 | 1 | Completed
ER6666LT | W209 | W209.9040 | HYB Essential Defueling Safety Case | Discovery Milestone - Fuel Free Verification (FFV) - EAN available | 2023-01-31 | 2023-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1390 | DNB Enhanced Safety Cases | End of Release Funding | 2023-01-31 | 2023-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2700 | DNB Enhanced Safety Cases | Project Management - A-B | 2023-01-31 | 2024-04-23 | 278 | 0 | 310 | 448 | 100% | 0.62054 | 1 | Completed
W232LT | W232 | W232.A2710 | DNB Enhanced Safety Cases | Technical Oversight - A-B | 2023-01-31 | 2024-04-23 | 278 | 0 | 310 | 448 | 100% | 0.62054 | 1 | Completed
ER6668LT | W213 | W213.A26360 | TOR Essential Defueling Safety Case | Verify Graphite Summary Report EAN | 2023-01-31 | 2023-02-24 | 21 | 0 | 19 | 24 | 100% | 0.875 | 1 | Completed
ER6668LT | W213 | W213.A29230 | TOR Essential Defueling Safety Case | Draft Defuelling Hazards Review EAN | 2023-01-31 | 2023-03-10 | 28 | 0 | 29 | 38 | 100% | 0.73684 | 1 | Completed
ER6668LT | W213 | W213.9040 | TOR Essential Defueling Safety Case | Discovery Milestone - Fuel Free Verification (FFV) - EAN available | 2023-01-31 | 2023-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A29220 | HYB Essential Defueling Safety Case | Pre Job Brief for Defuelling Hazards Review EAN | 2023-01-31 | 2023-01-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.6780 | HYB Essential Defueling Safety Case | Approve Task Sheet for Defuelling Handling Deterministic Assessment EAN | 2023-01-31 | 2023-02-03 | 6 | 0 | 4 | 3 | 100% | 2 | 1 | Completed
ER6668LT | W213 | W213.A29220 | TOR Essential Defueling Safety Case | Pre Job Brief for Defuelling Hazards Review EAN | 2023-01-31 | 2023-01-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.6780 | TOR Essential Defueling Safety Case | Approve Task Sheet for Defuelling Handling Deterministic Assessment EAN | 2023-01-31 | 2023-02-03 | 6 | 0 | 4 | 3 | 100% | 2 | 1 | Completed
W232LT | W232 | W232.A1670 | DNB Enhanced Safety Cases | Issue agreed work programme to stakeholders & suppliers | 2023-01-31 | 2023-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A29000 | HYB Essential Defueling Safety Case | Verify Summary of Compliance with RADWASTE Assessment Principles EAN | 2023-02-01 | 2023-03-31 | 15 | 0 | 43 | 58 | 100% | 0.25862 | 1 | Completed
ER6666LT | W209 | W209.6940 | HYB Essential Defueling Safety Case | RAWG Endorse Claim 1 | 2023-02-01 | 2023-11-07 | 20 | 0 | 193 | 279 | 100% | 0.071685 | 1 | Completed
ER6666LT | W209 | W209.28950 | HYB Essential Defueling Safety Case | Review & Integrate TASK F Data Prior to Draft Completion | 2023-02-01 | 2023-02-28 | 25 | 0 | 20 | 27 | 100% | 0.92593 | 1 | Completed
ER6666LT | W209 | W209.29460 | HYB Essential Defueling Safety Case | Thermal Modelling - (Civils Follow-On Work) | 2023-02-01 | 2023-04-21 | 1 | 0 | 55 | 79 | 100% | 0.012658 | 1 | Completed
ER6668LT | W213 | W213.A29000 | TOR Essential Defueling Safety Case | Verify Summary of Compliance with RADWASTE Assessment Principles EAN | 2023-02-01 | 2023-03-31 | 15 | 0 | 43 | 58 | 100% | 0.25862 | 1 | Completed
ER6668LT | W213 | W213.6940 | TOR Essential Defueling Safety Case | RAWG Endorse Claim 1 | 2023-02-01 | 2023-11-07 | 20 | 0 | 193 | 279 | 100% | 0.071685 | 1 | Completed
ER6668LT | W213 | W213.28950 | TOR Essential Defueling Safety Case | Review & Integrate TASK F Data Prior to Draft Completion | 2023-02-01 | 2023-02-28 | 25 | 0 | 20 | 27 | 100% | 0.92593 | 1 | Completed
ER6668LT | W213 | W213.29460 | TOR Essential Defueling Safety Case | Thermal Modelling - (Civils Follow-On Work) | 2023-02-01 | 2023-04-21 | 1 | 0 | 55 | 79 | 100% | 0.012658 | 1 | Completed
ER6666LT | W209 | W209.A29420 | HYB Essential Defueling Safety Case | Supplier Update and Issue Cooling Plant Availability Review EAN | 2023-02-03 | 2023-02-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A29420 | TOR Essential Defueling Safety Case | Supplier Update and Issue Cooling Plant Availability Review EAN | 2023-02-03 | 2023-02-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1600 | DNB Enhanced Safety Cases | Issue final NSRS | 2023-02-06 | 2023-02-13 | 6 | 0 | 5 | 7 | 100% | 0.85714 | 1 | Completed
ER6666LT | W209 | W209.A29430 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Cooling Plant Availability Review EAN to CDMS | 2023-02-06 | 2023-02-17 | 4 | 0 | 9 | 11 | 100% | 0.36364 | 1 | Completed
ER6666LT | W209 | W209.8080 | HYB Essential Defueling Safety Case | Supplier Update and Issue HF Assessment of the Extant Fuel Movement in support of Defueling FFV Claim | 2023-02-06 | 2023-02-24 | 3 | 0 | 14 | 18 | 100% | 0.16667 | 1 | Completed
W232LT | W232 | W232.A2510 | DNB Enhanced Safety Cases | Produce Discussion Paper on Approach to Cold Defuelling Feasibility | 2023-02-06 | 2023-02-20 | 11 | 0 | 11 | 14 | 100% | 0.78571 | 1 | Completed
W232LT | W232 | W232.B2560 | DNB Enhanced Safety Cases | Review Initial Optioneering Report | 2023-02-06 | 2023-02-20 | 11 | 0 | 11 | 14 | 100% | 0.78571 | 1 | Completed
ER6666LT | W209 | W209.29140 | HYB Essential Defueling Safety Case | Draft revision 002 including revised fault schedule | 2023-02-06 | 2023-10-06 | 61 | 0 | 168 | 242 | 100% | 0.25207 | 1 | Completed
ER6668LT | W213 | W213.A29430 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Cooling Plant Availability Review EAN to CDMS | 2023-02-06 | 2023-02-17 | 4 | 0 | 9 | 11 | 100% | 0.36364 | 1 | Completed
ER6668LT | W213 | W213.8080 | TOR Essential Defueling Safety Case | Supplier Update and Issue HF Assessment of the Extant Fuel Movement in support of Defueling FFV Claim | 2023-02-06 | 2023-02-24 | 3 | 0 | 14 | 18 | 100% | 0.16667 | 1 | Completed
ER6668LT | W213 | W213.29140 | TOR Essential Defueling Safety Case | Draft revision 002 including revised fault schedule | 2023-02-06 | 2023-10-06 | 61 | 0 | 168 | 242 | 100% | 0.25207 | 1 | Completed
ER6666LT | W209 | W209.6810 | HYB Essential Defueling Safety Case | Approve Task Sheet for Defuelling Worker Risk Assessment EAN | 2023-02-07 | 2023-02-24 | 6 | 0 | 14 | 17 | 100% | 0.35294 | 1 | Completed
ER6666LT | W209 | W209.7250 | HYB Essential Defueling Safety Case | PJB for Claim 4 Authoring | 2023-02-07 | 2023-02-07 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2720 | DNB Enhanced Safety Cases | Agree design proposals with Station in the case of hardware mods | 2023-02-07 | 2023-02-13 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
W232LT | W232 | W232.A2715 | DNB Enhanced Safety Cases | Maintenance Review of FR Plant - Summary | 2023-02-07 | 2023-06-30 | 82 | 0 | 98 | 143 | 100% | 0.57343 | 1 | Completed
ER6668LT | W213 | W213.6810 | TOR Essential Defueling Safety Case | Approve Task Sheet for Defuelling Worker Risk Assessment EAN | 2023-02-07 | 2023-02-24 | 6 | 0 | 14 | 17 | 100% | 0.35294 | 1 | Completed
ER6668LT | W213 | W213.7250 | TOR Essential Defueling Safety Case | PJB for Claim 4 Authoring | 2023-02-07 | 2023-02-07 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1165 | HYB Essential Defueling Safety Case | Send NSRS to ONR to determine level of review required (Acknowledgement or Agreement) | 2023-02-08 | 2023-02-08 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.7260 | HYB Essential Defueling Safety Case | Author Claim 4 | 2023-02-08 | 2023-10-13 | 20 | 0 | 172 | 247 | 100% | 0.080972 | 1 | Completed
ER6668LT | W213 | W213.1165 | TOR Essential Defueling Safety Case | Send NSRS to ONR to determine level of review required (Acknowledgement or Agreement) | 2023-02-08 | 2023-02-08 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.7260 | TOR Essential Defueling Safety Case | Author Claim 4 | 2023-02-08 | 2023-10-13 | 20 | 0 | 171 | 247 | 100% | 0.080972 | 1 | Completed
W232LT | W232 | W232.A1220 | DNB Enhanced Safety Cases | Produce verification plan | 2023-02-13 | 2023-02-17 | 2 | 0 | 4 | 4 | 100% | 0.5 | 1 | Completed
ER6666LT | W209 | W209.A25740 | HYB Essential Defueling Safety Case | Supplier Update and Issue Judgement Based Work Diversion EAN | 2023-02-13 | 2023-02-28 | 5 | 0 | 12 | 15 | 100% | 0.33333 | 1 | Completed
ER6371LT | W202 | 2385 | HRA Reactors Shutdown Essential Safety Cases | Verification - Focused (Lead Verifier)(HHB Opexs) | 2023-02-13 | 2023-03-16 | 20 | 0 | 24 | 31 | 100% | 0.64516 | 1 | Completed
ER6371LT | W202 | 2395 | HRA Reactors Shutdown Essential Safety Cases | Sub-verifier(s) including GAP review (HHB Opexs) | 2023-02-13 | 2023-03-16 | 20 | 0 | 23 | 31 | 100% | 0.64516 | 1 | Completed
ER6661LT | W206 | 2385 | HYA Reactors Shutdown Essential Safety Cases | Verification - Focused (Lead Verifier)(HHB Opexs) | 2023-02-13 | 2023-03-16 | 20 | 0 | 24 | 31 | 100% | 0.64516 | 1 | Completed
ER6661LT | W206 | 2395 | HYA Reactors Shutdown Essential Safety Cases | Sub-verifier(s) including GAP review (HHB Opexs) | 2023-02-13 | 2023-03-16 | 20 | 0 | 23 | 31 | 100% | 0.64516 | 1 | Completed
ER6668LT | W213 | W213.A25740 | TOR Essential Defueling Safety Case | Supplier Update and Issue Judgement Based Work Diversion EAN | 2023-02-13 | 2023-02-28 | 5 | 0 | 12 | 15 | 100% | 0.33333 | 1 | Completed
W232LT | W232 | W232.A1610 | DNB Enhanced Safety Cases | Station agree NSRS *(KDM)* | 2023-02-13 | 2023-02-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1620 | DNB Enhanced Safety Cases | Key Stakeholders agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2023-02-13 | 2023-02-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1630 | DNB Enhanced Safety Cases | INA agree NSRS | 2023-02-13 | 2023-02-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A29060 | HYB Essential Defueling Safety Case | Pre Job Brief for Defuelling Handling Deterministic Assessment EAN | 2023-02-14 | 2023-02-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1140 | DNB Enhanced Safety Cases | Agree design proposals with Station in the case of hardware mods | 2023-02-14 | 2023-02-20 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
W232LT | W232 | W232.A1650 | DNB Enhanced Safety Cases | Consolidate & issue to stakeholders & suppliers agreed NSRS (as required) | 2023-02-14 | 2023-02-15 | 5 | 0 | 1 | 1 | 100% | 5 | 1 | Completed
W232LT | W232 | W232.A2730 | DNB Enhanced Safety Cases | Produce supporting reference <Maintenance Review of FR Plant> | 2023-02-14 | 2023-04-14 | 30 | 0 | 41 | 59 | 100% | 0.50847 | 1 | Completed
W232LT | W232 | W232.A1135 | DNB Enhanced Safety Cases | PSA Sensitivity Study - Summary | 2023-02-14 | 2023-04-14 | 55 | 0 | 41 | 59 | 100% | 0.9322 | 1 | Completed
ER6668LT | W213 | W213.A29060 | TOR Essential Defueling Safety Case | Pre Job Brief for Defuelling Handling Deterministic Assessment EAN | 2023-02-14 | 2023-02-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A29070 | HYB Essential Defueling Safety Case | Draft Defuelling Handling Deterministic Assessment EAN | 2023-02-15 | 2023-11-16 | 30 | 0 | 190 | 274 | 100% | 0.10949 | 1 | Completed
ER6668LT | W213 | W213.A29070 | TOR Essential Defueling Safety Case | Draft Defuelling Handling Deterministic Assessment EAN | 2023-02-15 | 2023-11-16 | 30 | 0 | 190 | 274 | 100% | 0.10949 | 1 | Completed
ER6666LT | W209 | W209.A30710 | HYB Essential Defueling Safety Case | Technical Review of Underload Veto Height for Channel 1 - HYB | 2023-02-16 | 2023-03-22 | 32 | 0 | 24 | 34 | 100% | 0.94118 | 1 | Completed
ER6668LT | W213 | W213.A30710 | TOR Essential Defueling Safety Case | Technical Review of Underload Veto Height for Channel 1 - TOR | 2023-02-16 | 2023-03-22 | 32 | 0 | 24 | 34 | 100% | 0.94118 | 1 | Completed
ER6666LT | W209 | W209.A29440 | HYB Essential Defueling Safety Case | Cooling Plant Availability Review EAN Available | 2023-02-17 | 2023-02-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A29440 | TOR Essential Defueling Safety Case | Cooling Plant Availability Review EAN Available | 2023-02-17 | 2023-02-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1200 | DNB Enhanced Safety Cases | CA to agree with CO format of the safety case & produce agreed contents page | 2023-02-17 | 2023-02-20 | 2 | 0 | 2 | 3 | 100% | 0.66667 | 1 | Completed
W232LT | W232 | W232.A2960 | DNB Enhanced Safety Cases | Decision Milestone - Progress FLSA's | 2023-02-17 | 2023-02-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A25900 | HYB Essential Defueling Safety Case | Supplier Update and Issue Safety Case Requirements EAN - TASK E EAN | 2023-02-20 | 2023-02-28 | 5 | 0 | 6 | 8 | 100% | 0.625 | 1 | Completed
ER6668LT | W213 | W213.A25900 | TOR Essential Defueling Safety Case | Supplier Update and Issue Safety Case Requirements EAN - TASK E EAN | 2023-02-20 | 2023-02-28 | 5 | 0 | 6 | 8 | 100% | 0.625 | 1 | Completed
ER6666LT | W209 | W209.A27090 | HYB Essential Defueling Safety Case | Technical Review of FPU Integrity Analysis EAN | 2023-02-20 | 2023-03-16 | 19 | 0 | 19 | 24 | 100% | 0.79167 | 1 | Completed
ER6668LT | W213 | W213.A27090 | TOR Essential Defueling Safety Case | Technical Review of FPU Integrity Analysis EAN | 2023-02-20 | 2023-03-16 | 19 | 0 | 19 | 24 | 100% | 0.79167 | 1 | Completed
ER6666LT | W209 | W209.A28620 | HYB Essential Defueling Safety Case | Supplier Update and Issue Radiological Consequences Following Failed CSP EAN | 2023-02-21 | 2023-02-28 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6666LT | W209 | W209.7170 | HYB Essential Defueling Safety Case | Author Claim 5 | 2023-02-21 | 2023-12-01 | 62 | 0 | 197 | 283 | 100% | 0.21908 | 1 | Completed
ER6668LT | W213 | W213.A28620 | TOR Essential Defueling Safety Case | Supplier Update and Issue Radiological Consequences Following Failed CSP EAN | 2023-02-21 | 2023-02-28 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6668LT | W213 | W213.7170 | TOR Essential Defueling Safety Case | Author Claim 5 | 2023-02-21 | 2023-12-01 | 62 | 0 | 198 | 283 | 100% | 0.21908 | 1 | Completed
ER6666LT | W209 | W209.25880 | HYB Essential Defueling Safety Case | Pre Job Brief for Human Reliability Assessment of Unsubstantiated Claims EAN | 2023-02-21 | 2023-02-21 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1150 | DNB Enhanced Safety Cases | Produce supporting reference <PSA Sensitivity Study> | 2023-02-21 | 2023-04-03 | 30 | 0 | 30 | 41 | 100% | 0.73171 | 1 | Completed
W232LT | W232 | W232.A2520 | DNB Enhanced Safety Cases | Develop Worklist and Schedule | 2023-02-21 | 2023-03-06 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
W232LT | W232 | W232.A2530 | DNB Enhanced Safety Cases | Specify Discovery Milestones | 2023-02-21 | 2023-03-06 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
W232LT | W232 | W232.B2550 | DNB Enhanced Safety Cases | Assess Options for Providing Moisture Detection Capability | 2023-02-21 | 2023-04-20 | 41 | 0 | 41 | 58 | 100% | 0.7069 | 1 | Completed
ER6668LT | W213 | W213.25880 | TOR Essential Defueling Safety Case | Pre Job Brief for Human Reliability Assessment of Unsubstantiated Claims EAN | 2023-02-21 | 2023-02-21 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A31240 | HYB Essential Defueling Safety Case | Supplier Update and Issue Update Basis of Analysis document - (Issue 5) | 2023-02-22 | 2023-02-28 | 15 | 0 | 5 | 6 | 100% | 2.5 | 1 | Completed
ER6668LT | W213 | W213.A31240 | TOR Essential Defueling Safety Case | Supplier Update and Issue Update Basis of Analysis document - (Issue 5) | 2023-02-22 | 2023-02-28 | 15 | 0 | 5 | 6 | 100% | 2.5 | 1 | Completed
ER6666LT | W209 | W209.29370 | HYB Essential Defueling Safety Case | Screening Activity | 2023-02-22 | 2023-03-16 | 15 | 0 | 17 | 22 | 100% | 0.68182 | 1 | Completed
ER6668LT | W213 | W213.29370 | TOR Essential Defueling Safety Case | Screening Activity | 2023-02-22 | 2023-03-16 | 15 | 0 | 17 | 22 | 100% | 0.68182 | 1 | Completed
ER6666LT | W209 | W209.7090 | HYB Essential Defueling Safety Case | Case Officer Tech Lead Review Claim 3 | 2023-02-24 | 2023-05-26 | 20 | 0 | 61 | 91 | 100% | 0.21978 | 1 | Completed
ER6668LT | W213 | W213.7090 | TOR Essential Defueling Safety Case | Case Officer Tech Lead Review Claim 3 | 2023-02-24 | 2023-05-26 | 20 | 0 | 61 | 91 | 100% | 0.21978 | 1 | Completed
ER6666LT | W209 | W209.8090 | HYB Essential Defueling Safety Case | Complete TR Form and Upload HF Assessment of the Extant Fuel Movement in support of Defueling FFV Claim | 2023-02-27 | 2023-03-03 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6668LT | W213 | W213.8090 | TOR Essential Defueling Safety Case | Complete TR Form and Upload HF Assessment of the Extant Fuel Movement in support of Defueling FFV Claim | 2023-02-27 | 2023-03-03 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6666LT | W209 | W209.A26390 | HYB Essential Defueling Safety Case | Approve & Upload Graphite Summary Report EAN to CDMS | 2023-02-27 | 2023-03-03 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6666LT | W209 | W209.A29140 | HYB Essential Defueling Safety Case | Pre Job Brief for Defuelling Worker Risk Assessment EAN | 2023-02-27 | 2023-05-23 | 1 | 0 | 58 | 85 | 100% | 0.011765 | 1 | Completed
ER6666LT | W209 | W209.7000 | HYB Essential Defueling Safety Case | Case Officer Tech Lead Review Claim 2 | 2023-02-27 | 2023-03-16 | 10 | 0 | 13 | 17 | 100% | 0.58824 | 1 | Completed
ER6668LT | W213 | W213.A26390 | TOR Essential Defueling Safety Case | Approve & Upload Graphite Summary Report EAN to CDMS | 2023-02-27 | 2023-03-03 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6668LT | W213 | W213.A29140 | TOR Essential Defueling Safety Case | Pre Job Brief for Defuelling Worker Risk Assessment EAN | 2023-02-27 | 2023-05-23 | 1 | 0 | 58 | 85 | 100% | 0.011765 | 1 | Completed
ER6668LT | W213 | W213.7000 | TOR Essential Defueling Safety Case | Case Officer Tech Lead Review Claim 2 | 2023-02-27 | 2023-03-16 | 10 | 0 | 13 | 17 | 100% | 0.58824 | 1 | Completed
ER6372LT | W203 | W203.A2320 | HNB Enhanced Defuelling Safety Cases | <SCOPE REMOVED CN571> Consideration of Deliberate Admission of Air to a Defuelling Reactor - SC Approved | 2023-02-28 | 2023-02-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1280 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Cooling faults (decay heats) EAN updated - Prepare Draft Report | 2023-02-28 | 2023-02-28 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1380 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Cooling faults (decay heats) EAN updated - Issued Draft Report to EDF for Review. | 2023-02-28 | 2023-02-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1430 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Cooling faults (decay heats) EAN updated - Reviewed by EDF SQEP | 2023-02-28 | 2023-02-28 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1530 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Cooling faults (decay heats) EAN updated - Address Comments from EDF Review | 2023-02-28 | 2023-02-28 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1590 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Cooling faults (decay heats) EAN updated - Issue Final Report | 2023-02-28 | 2023-02-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1620 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Cooling faults (decay heats) EAN updated - Completed and Uploaded to CDMS | 2023-02-28 | 2023-02-28 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1660 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Cooling faults (decay heats) EAN updated - Report Completed | 2023-02-28 | 2023-02-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1270 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Cooling faults (decay heats) EAN updated - Summary | 2023-02-28 | 2023-02-28 | 40 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A2440 | HNB Enhanced Defuelling Safety Cases | <SCOPE REMOVED CN571> Admission to Air technical work progressed | 2023-02-28 | 2023-02-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A25750 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Judgement Based Work Diversion EAN Requirements to CDMS | 2023-02-28 | 2023-03-31 | 1 | 0 | 24 | 31 | 100% | 0.032258 | 1 | Completed
ER6666LT | W209 | W209.A25910 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Safety Case Requirements EAN - TASK E EAN to CDMS | 2023-02-28 | 2023-04-21 | 5 | 0 | 37 | 52 | 100% | 0.096154 | 1 | Completed
ER6666LT | W209 | W209.A26790 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Boron Bead Injection Feasibility & Control Rod Isolation EAN to CDMS | 2023-02-28 | 2023-04-21 | 5 | 0 | 37 | 52 | 100% | 0.096154 | 1 | Completed
ER6666LT | W209 | W209.A28630 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Radiological Consequences Following Failed CSP EAN to CDMS | 2023-02-28 | 2023-03-07 | 5 | 0 | 6 | 7 | 100% | 0.71429 | 1 | Completed
ER6666LT | W209 | W209.A29620 | HYB Essential Defueling Safety Case | Complete TR Form and Upload TASK F Review of the Discharge Limits (Permits) EAN to CDMS | 2023-02-28 | 2023-05-12 | 5 | 0 | 50 | 73 | 100% | 0.068493 | 1 | Completed
ER6666LT | W209 | W209.A31250 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Update Basis of Analysis document to CDMS - (Issue 5) | 2023-02-28 | 2023-03-07 | 5 | 0 | 6 | 7 | 100% | 0.71429 | 1 | Completed
ER6371LT | W202 | 2335 | HRA Reactors Shutdown Essential Safety Cases | Lesson Learn - Authoring Phase | 2023-02-28 | 2023-02-28 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A25750 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Judgement Based Work Diversion EAN Requirements to CDMS | 2023-02-28 | 2023-03-31 | 1 | 0 | 24 | 31 | 100% | 0.032258 | 1 | Completed
ER6668LT | W213 | W213.A25910 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Safety Case Requirements EAN - TASK E EAN to CDMS | 2023-02-28 | 2023-04-21 | 5 | 0 | 37 | 52 | 100% | 0.096154 | 1 | Completed
ER6668LT | W213 | W213.A26790 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Boron Bead Injection Feasibility & Control Rod Isolation EAN to CDMS | 2023-02-28 | 2023-04-21 | 5 | 0 | 37 | 52 | 100% | 0.096154 | 1 | Completed
ER6668LT | W213 | W213.A28630 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Radiological Consequences Following Failed CSP EAN to CDMS | 2023-02-28 | 2023-03-07 | 5 | 0 | 6 | 7 | 100% | 0.71429 | 1 | Completed
ER6668LT | W213 | W213.A29620 | TOR Essential Defueling Safety Case | Complete TR Form and Upload TASK F Review of the Discharge Limits (Permits) EAN to CDMS | 2023-02-28 | 2023-05-12 | 5 | 0 | 50 | 73 | 100% | 0.068493 | 1 | Completed
ER6668LT | W213 | W213.A31250 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Update Basis of Analysis document to CDMS - (Issue 5) | 2023-02-28 | 2023-03-07 | 5 | 0 | 6 | 7 | 100% | 0.71429 | 1 | Completed
ER6661LT | W206 | 2335 | HYA Reactors Shutdown Essential Safety Cases | Lesson Learn - Authoring Phase | 2023-02-28 | 2023-02-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A2120 | HNB Enhanced Defuelling Safety Cases | Technical Oversight Gate B - C | 2023-03-01 | 2024-11-19 | 149 | 0 | 436 | 629 | 100% | 0.23688 | 1 | Completed
ER6372LT | W203 | W203.A2130 | HNB Enhanced Defuelling Safety Cases | Station Oversight Gate B - C | 2023-03-01 | 2024-11-19 | 149 | 0 | 436 | 629 | 100% | 0.23688 | 1 | Completed
ER6666LT | W209 | W209.A29760 | HYB Essential Defueling Safety Case | Complete TR Form and Upload PARTIAL Drain down of the PVCS prior to Defuelling (Report) to CDMS | 2023-03-01 | 2023-05-19 | 5 | 0 | 53 | 79 | 100% | 0.063291 | 1 | Completed
ER6666LT | W209 | W209.29100 | HYB Essential Defueling Safety Case | Draft Revision 001 | 2023-03-01 | 2023-03-10 | 8 | 0 | 8 | 9 | 100% | 0.88889 | 1 | Completed
ER6371LT | W202 | 1625 | HRA Reactors Shutdown Essential Safety Cases | Update Fault Definition Document | 2023-03-01 | 2023-03-21 | 15 | 0 | 15 | 20 | 100% | 0.75 | 1 | Completed
ER6661LT | W206 | 1625 | HYA Reactors Shutdown Essential Safety Cases | Update Fault Definition Document | 2023-03-01 | 2023-03-21 | 15 | 0 | 15 | 20 | 100% | 0.75 | 1 | Completed
ER6371LT | W202 | W202.A2206690 | HRA Reactors Shutdown Essential Safety Cases | Confirm Objectives to be Delivered at Gate C+ | 2023-03-01 | 2023-03-14 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6371LT | W202 | W202.A2206720 | HRA Reactors Shutdown Essential Safety Cases | Gate C+ Planning | 2023-03-01 | 2023-04-25 | 38 | 0 | 38 | 55 | 100% | 0.69091 | 1 | Completed
ER6661LT | W206 | W206.A2206690 | HYA Reactors Shutdown Essential Safety Cases | Confirm Objectives to be Delivered at Gate C+ | 2023-03-01 | 2023-03-14 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6661LT | W206 | W206.A2206720 | HYA Reactors Shutdown Essential Safety Cases | Gate C+ Planning | 2023-03-01 | 2023-04-25 | 38 | 0 | 38 | 55 | 100% | 0.69091 | 1 | Completed
ER6372LT | W203 | W203.A3400 | HNB Enhanced Defuelling Safety Cases | Raise Engineering Request | 2023-03-01 | 2023-03-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6372LT | W203 | W203.A3910 | HNB Enhanced Defuelling Safety Cases | Raise Engineering Request | 2023-03-01 | 2023-03-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.A29760 | TOR Essential Defueling Safety Case | Complete TR Form and Upload PARTIAL Drain down of the PVCS prior to Defuelling (Report) to CDMS | 2023-03-01 | 2023-05-19 | 5 | 0 | 53 | 79 | 100% | 0.063291 | 1 | Completed
ER6668LT | W213 | W213.29100 | TOR Essential Defueling Safety Case | Draft Revision 001 | 2023-03-01 | 2023-03-10 | 8 | 0 | 8 | 9 | 100% | 0.88889 | 1 | Completed
ER6666LT | W209 | W209.A26400 | HYB Essential Defueling Safety Case | Graphite Summary Report EAN Available | 2023-03-03 | 2023-03-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A26960 | HYB Essential Defueling Safety Case | Chemistry Monitoring Strategy EAN EAN Available | 2023-03-03 | 2023-03-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.8100 | HYB Essential Defueling Safety Case | HF Assessment of the Extant Fuel Movement in support of Defueling FFV Claim EAN Available (System) | 2023-03-03 | 2023-03-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A26400 | TOR Essential Defueling Safety Case | Graphite Summary Report EAN Available | 2023-03-03 | 2023-03-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A26960 | TOR Essential Defueling Safety Case | Chemistry Monitoring Strategy EAN EAN Available | 2023-03-03 | 2023-03-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.8100 | TOR Essential Defueling Safety Case | HF Assessment of the Extant Fuel Movement in support of Defueling FFV Claim EAN Available (System) | 2023-03-03 | 2023-03-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.9000 | HYB Essential Defueling Safety Case | Discovery Milestone - PSA Reviewed Following Dropped FPU Case Conference | 2023-03-07 | 2023-03-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2570 | DNB Enhanced Safety Cases | Define Required Lift Lower Trials | 2023-03-07 | 2023-03-17 | 10 | 0 | 8 | 10 | 100% | 1 | 1 | Completed
ER6668LT | W213 | W213.9000 | TOR Essential Defueling Safety Case | Discovery Milestone - PSA Reviewed Following Dropped FPU Case Conference | 2023-03-07 | 2023-03-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2540 | DNB Enhanced Safety Cases | Document Basis of Safety Case Claims | 2023-03-07 | 2023-04-03 | 24 | 0 | 20 | 27 | 100% | 0.88889 | 1 | Completed
W232LT | W232 | W232.A2580 | DNB Enhanced Safety Cases | Confirm Approach to Re-entrant Seal Stiction Issue | 2023-03-07 | 2023-03-21 | 11 | 0 | 11 | 14 | 100% | 0.78571 | 1 | Completed
ER6666LT | W209 | W209.A28640 | HYB Essential Defueling Safety Case | Radiological Consequences Following Failed CSP EAN Available | 2023-03-07 | 2023-03-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.8460 | HYB Essential Defueling Safety Case | Reviewed PSA following CSP/Diagrid Structural Integrity Summary Report | 2023-03-07 | 2023-03-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A31260 | HYB Essential Defueling Safety Case | Update Basis of Analysis document Available - (Issue 5) | 2023-03-07 | 2023-03-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A28640 | TOR Essential Defueling Safety Case | Radiological Consequences Following Failed CSP EAN Available | 2023-03-07 | 2023-03-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.8460 | TOR Essential Defueling Safety Case | Reviewed PSA following CSP/Diagrid Structural Integrity Summary Report | 2023-03-07 | 2023-03-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A31260 | TOR Essential Defueling Safety Case | Update Basis of Analysis document Available - (Issue 5) | 2023-03-07 | 2023-03-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3320 | HNB Enhanced Defuelling Safety Cases | Mod req'd, Initiate EC, identify RE, register EC & identify MS in Passport | 2023-03-08 | 2023-03-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3390 | HNB Enhanced Defuelling Safety Cases | Develop initial programme plan using mandatory template | 2023-03-08 | 2023-03-14 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6372LT | W203 | W203.A3830 | HNB Enhanced Defuelling Safety Cases | Mod req'd, Initiate EC, identify RE, register EC & identify MS in Passport | 2023-03-08 | 2023-03-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3900 | HNB Enhanced Defuelling Safety Cases | Develop initial programme plan using mandatory template | 2023-03-08 | 2023-03-14 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | 3020 | HRA Reactors Shutdown Essential Safety Cases | Lesson Learn - Event Recovery Phase | 2023-03-10 | 2023-03-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | 3020 | HYA Reactors Shutdown Essential Safety Cases | Lesson Learn - Event Recovery Phase | 2023-03-10 | 2023-03-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A29240 | HYB Essential Defueling Safety Case | Verify Defuelling Hazards Review EAN & Issue for Technical Review | 2023-03-13 | 2023-04-06 | 15 | 0 | 19 | 24 | 100% | 0.625 | 1 | Completed
ER6668LT | W213 | W213.A29240 | TOR Essential Defueling Safety Case | Verify Defuelling Hazards Review EAN & Issue for Technical Review | 2023-03-13 | 2023-04-06 | 15 | 0 | 19 | 24 | 100% | 0.625 | 1 | Completed
ER6666LT | W209 | W209.7340 | HYB Essential Defueling Safety Case | PJB for Claim 6 Authoring | 2023-03-14 | 2023-03-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.8400 | HYB Essential Defueling Safety Case | Claim 6 Production ## (Cost Summary) | 2023-03-14 | 2023-11-10 | 183 | 0 | 167 | 241 | 100% | 0.75934 | 1 | Completed
ER6371LT | W202 | 2460 | HRA Reactors Shutdown Essential Safety Cases | Re-attach to ADL | 2023-03-14 | 2023-03-16 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6661LT | W206 | 2460 | HYA Reactors Shutdown Essential Safety Cases | Re-attach to ADL | 2023-03-14 | 2023-03-16 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6668LT | W213 | W213.7340 | TOR Essential Defueling Safety Case | PJB for Claim 6 Authoring | 2023-03-14 | 2023-03-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.8400 | TOR Essential Defueling Safety Case | Claim 6 Production ## (Cost Summary) | 2023-03-14 | 2023-11-10 | 188 | 0 | 168 | 241 | 100% | 0.78008 | 1 | Completed
ER6666LT | W209 | W209.A29150 | HYB Essential Defueling Safety Case | Draft Defuelling Worker Risk Assessment EAN | 2023-03-15 | 2024-06-28 | 30 | 0 | 325 | 471 | 100% | 0.063694 | 1 | Completed
ER6668LT | W213 | W213.A29150 | TOR Essential Defueling Safety Case | Draft Defuelling Worker Risk Assessment EAN | 2023-03-15 | 2024-06-28 | 30 | 0 | 325 | 471 | 100% | 0.063694 | 1 | Completed
ER6666LT | W209 | W209.7350 | HYB Essential Defueling Safety Case | Author Claim 6 | 2023-03-15 | 2023-04-17 | 24 | 0 | 22 | 33 | 100% | 0.72727 | 1 | Completed
ER6371LT | W202 | W202.A2206560 | HRA Reactors Shutdown Essential Safety Cases | Define Project Control Structures (WBS/CBS/OBS/PBS) | 2023-03-15 | 2023-03-21 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6371LT | W202 | W202.A2206650 | HRA Reactors Shutdown Essential Safety Cases | Prepare Draft Project Definition Document (PDD) | 2023-03-15 | 2023-03-15 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206700 | HRA Reactors Shutdown Essential Safety Cases | Initial high level scope of programme | 2023-03-15 | 2023-03-21 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | W206.A2206560 | HYA Reactors Shutdown Essential Safety Cases | Define Project Control Structures (WBS/CBS/OBS/PBS) | 2023-03-15 | 2023-03-21 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | W206.A2206650 | HYA Reactors Shutdown Essential Safety Cases | Prepare Draft Project Definition Document (PDD) | 2023-03-15 | 2023-03-15 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206700 | HYA Reactors Shutdown Essential Safety Cases | Initial high level scope of programme | 2023-03-15 | 2023-03-21 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.7350 | TOR Essential Defueling Safety Case | Author Claim 6 | 2023-03-15 | 2023-04-17 | 24 | 0 | 22 | 33 | 100% | 0.72727 | 1 | Completed
ER6666LT | W209 | W209.29010 | HYB Essential Defueling Safety Case | Discovery Milestone - Define scope for WP6 - Claims to be Substantiated | 2023-03-16 | 2023-03-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.29010 | TOR Essential Defueling Safety Case | Discovery Milestone - Define scope for WP6 - Claims to be Substantiated | 2023-03-16 | 2023-03-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.6930 | HYB Essential Defueling Safety Case | Update Claim 1 | 2023-03-17 | 2023-09-18 | 20 | 0 | 125 | 185 | 100% | 0.10811 | 1 | Completed
ER6666LT | W209 | W209.7010 | HYB Essential Defueling Safety Case | Verification of Claim 2 | 2023-03-17 | 2023-10-27 | 20 | 0 | 154 | 224 | 100% | 0.089286 | 1 | Completed
ER6666LT | W209 | W209.25890 | HYB Essential Defueling Safety Case | Draft of Human Reliability Assessment of Unsubstantiated Claims EAN | 2023-03-17 | 2023-04-28 | 5 | 0 | 28 | 42 | 100% | 0.11905 | 1 | Completed
ER6666LT | W209 | W209.29430 | HYB Essential Defueling Safety Case | Qualitative Analysis & Write Up (Supporting Drafting of the Refeence) | 2023-03-17 | 2023-04-28 | 1 | 0 | 29 | 42 | 100% | 0.02381 | 1 | Completed
ER6668LT | W213 | W213.6930 | TOR Essential Defueling Safety Case | Update Claim 1 | 2023-03-17 | 2023-09-18 | 20 | 0 | 125 | 185 | 100% | 0.10811 | 1 | Completed
ER6668LT | W213 | W213.7010 | TOR Essential Defueling Safety Case | Verification of Claim 2 | 2023-03-17 | 2023-10-27 | 20 | 0 | 154 | 224 | 100% | 0.089286 | 1 | Completed
ER6668LT | W213 | W213.25890 | TOR Essential Defueling Safety Case | Draft of Human Reliability Assessment of Unsubstantiated Claims EAN | 2023-03-17 | 2023-04-28 | 5 | 0 | 28 | 42 | 100% | 0.11905 | 1 | Completed
ER6668LT | W213 | W213.29430 | TOR Essential Defueling Safety Case | Qualitative Analysis & Write Up (Supporting Drafting of the Refeence) | 2023-03-17 | 2023-04-28 | 1 | 0 | 29 | 42 | 100% | 0.02381 | 1 | Completed
ER6666LT | W209 | W209.A27100 | HYB Essential Defueling Safety Case | Supplier Update and Issue FPU Integrity Analysis EAN | 2023-03-17 | 2023-04-25 | 5 | 0 | 26 | 39 | 100% | 0.12821 | 1 | Completed
ER6371LT | W202 | 2410 | HRA Reactors Shutdown Essential Safety Cases | Respond to Verification Comments and Updates | 2023-03-17 | 2023-03-30 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6661LT | W206 | 2410 | HYA Reactors Shutdown Essential Safety Cases | Respond to Verification Comments and Updates | 2023-03-17 | 2023-03-30 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6668LT | W213 | W213.A27100 | TOR Essential Defueling Safety Case | Supplier Update and Issue FPU Integrity Analysis EAN | 2023-03-17 | 2023-04-25 | 5 | 0 | 26 | 39 | 100% | 0.12821 | 1 | Completed
ER6666LT | W209 | W209.29110 | HYB Essential Defueling Safety Case | Verification | 2023-03-20 | 2023-06-12 | 21 | 0 | 56 | 84 | 100% | 0.25 | 1 | Completed
ER6668LT | W213 | W213.29110 | TOR Essential Defueling Safety Case | Verification | 2023-03-20 | 2023-06-12 | 21 | 0 | 56 | 84 | 100% | 0.25 | 1 | Completed
ER6666LT | W209 | W209.A28230 | HYB Essential Defueling Safety Case | Complete TR Form and Upload CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN to CDMS | 2023-03-20 | 2023-03-31 | 5 | 0 | 9 | 11 | 100% | 0.45455 | 1 | Completed
ER6666LT | W209 | W209.A28710 | HYB Essential Defueling Safety Case | Complete TR Form and CSP/Diagrid Structural Integrity Summary Report to CDMS | 2023-03-20 | 2023-03-31 | 5 | 0 | 10 | 11 | 100% | 0.45455 | 1 | Completed
ER6668LT | W213 | W213.A28230 | TOR Essential Defueling Safety Case | Complete TR Form and Upload CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN to CDMS | 2023-03-20 | 2023-03-31 | 5 | 0 | 9 | 11 | 100% | 0.45455 | 1 | Completed
ER6668LT | W213 | W213.A28710 | TOR Essential Defueling Safety Case | Complete TR Form and CSP/Diagrid Structural Integrity Summary Report to CDMS | 2023-03-20 | 2023-03-31 | 5 | 0 | 10 | 11 | 100% | 0.45455 | 1 | Completed
W232LT | W232 | W232.A1660 | DNB Enhanced Safety Cases | Prepare the Safety Case Proposal (including OPEX Review) | 2023-03-21 | 2023-06-22 | 30 | 0 | 62 | 93 | 100% | 0.32258 | 1 | Completed
ER6666LT | W209 | W209.A30720 | HYB Essential Defueling Safety Case | Supplier Update and Issue Channel 1 - HYB | 2023-03-22 | 2023-06-15 | 5 | 0 | 57 | 85 | 100% | 0.058824 | 1 | Completed
ER6668LT | W213 | W213.A30720 | TOR Essential Defueling Safety Case | Supplier Update and Issue Channel 1 - TOR | 2023-03-22 | 2023-06-15 | 5 | 0 | 57 | 85 | 100% | 0.058824 | 1 | Completed
ER6371LT | W202 | 1626 | HRA Reactors Shutdown Essential Safety Cases | 6 Verify updated FDD v2 | 2023-03-22 | 2023-06-12 | 10 | 0 | 53 | 82 | 100% | 0.12195 | 1 | Completed
ER6661LT | W206 | 1626 | HYA Reactors Shutdown Essential Safety Cases | 6 Verify updated FDD | 2023-03-22 | 2023-06-12 | 5 | 0 | 53 | 82 | 100% | 0.060976 | 1 | Completed
ER6371LT | W202 | W202.A2206570 | HRA Reactors Shutdown Essential Safety Cases | Plan Scope in Primavera (Level 2 C+-D & Level 1 Lifecycle) | 2023-03-22 | 2023-03-28 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6661LT | W206 | W206.A2206570 | HYA Reactors Shutdown Essential Safety Cases | Plan Scope in Primavera (Level 2 C+-D & Level 1 Lifecycle) | 2023-03-22 | 2023-03-28 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.A28280 | HYB Essential Defueling Safety Case | Verify Fault Definition Document (FDD) EAN | 2023-03-23 | 2023-10-05 | 33 | 0 | 135 | 196 | 100% | 0.16837 | 1 | Completed
ER6668LT | W213 | W213.A28280 | TOR Essential Defueling Safety Case | Verify Fault Definition Document (FDD) EAN | 2023-03-23 | 2023-10-05 | 33 | 0 | 135 | 196 | 100% | 0.16837 | 1 | Completed
ER6371LT | W202 | 2396 | HRA Reactors Shutdown Essential Safety Cases | First Round Verifier Comments Addressed | 2023-03-24 | 2023-03-30 | 1 | 0 | 4 | 6 | 100% | 0.16667 | 1 | Completed
ER6661LT | W206 | 2396 | HYA Reactors Shutdown Essential Safety Cases | First Round Verifier Comments Addressed | 2023-03-24 | 2023-03-30 | 1 | 0 | 4 | 6 | 100% | 0.16667 | 1 | Completed
W232LT | W232 | W232.A2590 | DNB Enhanced Safety Cases | Agree Implementation of Lift Lower Trials with Station | 2023-03-27 | 2023-06-15 | 75 | 0 | 53 | 80 | 100% | 0.9375 | 1 | Completed
ER6666LT | W209 | W209.29360 | HYB Essential Defueling Safety Case | Step 3 - Draft Human Reliability Baseline Report EAN | 2023-03-27 | 2023-04-21 | 20 | 0 | 17 | 25 | 100% | 0.8 | 1 | Completed
ER6668LT | W213 | W213.29360 | TOR Essential Defueling Safety Case | Step 3 - Draft Human Reliability Baseline Report EAN | 2023-03-27 | 2023-04-21 | 20 | 0 | 17 | 25 | 100% | 0.8 | 1 | Completed
ER6666LT | W209 | W209.29220 | HYB Essential Defueling Safety Case | Verify Operator Claims Matrix | 2023-03-27 | 2023-04-21 | 9 | 0 | 18 | 25 | 100% | 0.36 | 1 | Completed
ER6668LT | W213 | W213.29220 | TOR Essential Defueling Safety Case | Verify Operator Claims Matrix | 2023-03-27 | 2023-04-21 | 9 | 0 | 18 | 25 | 100% | 0.36 | 1 | Completed
ER6371LT | W202 | W202.A2206600 | HRA Reactors Shutdown Essential Safety Cases | Hold Risk Workshop | 2023-03-30 | 2023-03-30 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206600 | HYA Reactors Shutdown Essential Safety Cases | Hold Risk Workshop | 2023-03-30 | 2023-03-30 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A28240 | HYB Essential Defueling Safety Case | CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN Available | 2023-03-31 | 2023-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A28800 | HYB Essential Defueling Safety Case | Fuel Free Verification methods, an assessment against the ALARP principle EAN Available | 2023-03-31 | 2023-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A28240 | TOR Essential Defueling Safety Case | CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN Available | 2023-03-31 | 2023-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A28800 | TOR Essential Defueling Safety Case | Fuel Free Verification methods, an assessment against the ALARP principle EAN Available | 2023-03-31 | 2023-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | 2430 | HRA Reactors Shutdown Essential Safety Cases | Stn RE Endorsed | 2023-03-31 | 2023-05-26 | 5 | 0 | 36 | 56 | 100% | 0.089286 | 1 | Completed
ER6371LT | W202 | 2420 | HRA Reactors Shutdown Essential Safety Cases | CO Endorsed | 2023-03-31 | 2023-05-26 | 5 | 0 | 36 | 56 | 100% | 0.089286 | 1 | Completed
ER6661LT | W206 | 2430 | HYA Reactors Shutdown Essential Safety Cases | Stn RE Endorsed | 2023-03-31 | 2023-05-26 | 5 | 0 | 36 | 56 | 100% | 0.089286 | 1 | Completed
ER6661LT | W206 | 2420 | HYA Reactors Shutdown Essential Safety Cases | CO Endorsed | 2023-03-31 | 2023-05-26 | 5 | 0 | 36 | 56 | 100% | 0.089286 | 1 | Completed
ER6371LT | W202 | W202.A2206610 | HRA Reactors Shutdown Essential Safety Cases | Complete Risk Log with Estimates | 2023-03-31 | 2023-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206610 | HYA Reactors Shutdown Essential Safety Cases | Complete Risk Log with Estimates | 2023-03-31 | 2023-03-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A25760 | HYB Essential Defueling Safety Case | Judgement Based Work Diversion EAN Available | 2023-03-31 | 2023-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.8990 | HYB Essential Defueling Safety Case | Discovery Milestone - FM Underload Veto - Drafted | 2023-03-31 | 2023-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A28720 | HYB Essential Defueling Safety Case | CSP/Diagrid Structural Integrity Summary Report Available | 2023-03-31 | 2023-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A25760 | TOR Essential Defueling Safety Case | Judgement Based Work Diversion EAN Available | 2023-03-31 | 2023-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.8990 | TOR Essential Defueling Safety Case | Discovery Milestone - FM Underload Veto - Drafted | 2023-03-31 | 2023-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A28720 | TOR Essential Defueling Safety Case | CSP/Diagrid Structural Integrity Summary Report Available | 2023-03-31 | 2023-03-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3150 | HNB Enhanced Defuelling Safety Cases | Produce MF | 2023-04-03 | 2023-04-11 | 5 | 0 | 4 | 8 | 100% | 0.625 | 1 | Completed
ER6378LT | W222 | W222.3060 | HRA Fuel Handling Essential Safety Case | ETC (DD-PF) April 23 only | 2023-04-03 | 2023-04-28 | 18 | 0 | 17 | 25 | 100% | 0.72 | 1 | Completed
ER6650LT | W226 | W226.3060 | HYA Fuel Handling Essential Safety Case | ETC (April 23 Only) | 2023-04-03 | 2023-04-28 | 14 | 0 | 17 | 25 | 100% | 0.56 | 1 | Completed
ER6666LT | W209 | W209.29480 | HYB Essential Defueling Safety Case | Structural Integrity (SI) Justification - Liner & Penetrations - (Civils Follow-On Work) | 2023-04-03 | 2023-05-19 | 1 | 0 | 30 | 46 | 100% | 0.021739 | 1 | Completed
ER6666LT | W209 | W209.A31270 | HYB Essential Defueling Safety Case | Draft PSA Documentation | 2023-04-03 | 2023-12-15 | 0 | 0 | 179 | 256 | 100% | 0 | 1 | Completed
ER6666LT | W209 | W209.A31330 | HYB Essential Defueling Safety Case | Fuelling Machine Purging Requirements During Defueling (Cost Summary) (Claim 5) | 2023-04-03 | 2023-07-28 | 187 | 0 | 79 | 116 | 100% | 1.6121 | 1 | Completed
ER6666LT | W209 | W209.A31350 | HYB Essential Defueling Safety Case | Draft Fuelling Machine Purging Requirements During Defueling | 2023-04-03 | 2023-04-14 | 0 | 0 | 8 | 11 | 100% | 0 | 1 | Completed
ER6668LT | W213 | W213.29480 | TOR Essential Defueling Safety Case | Structural Integrity (SI) Justification - Liner & Penetrations - (Civils Follow-On Work) | 2023-04-03 | 2023-05-19 | 1 | 0 | 30 | 46 | 100% | 0.021739 | 1 | Completed
ER6668LT | W213 | W213.A31270 | TOR Essential Defueling Safety Case | Draft PSA Documentation | 2023-04-03 | 2023-12-15 | 0 | 0 | 178 | 256 | 100% | 0 | 1 | Completed
ER6668LT | W213 | W213.A31330 | TOR Essential Defueling Safety Case | Fuelling Machine Purging Requirements During Defueling (Cost Summary) (Claim 5) | 2023-04-03 | 2023-07-28 | 187 | 0 | 79 | 116 | 100% | 1.6121 | 1 | Completed
ER6668LT | W213 | W213.A31350 | TOR Essential Defueling Safety Case | Draft Fuelling Machine Purging Requirements During Defueling | 2023-04-03 | 2023-04-14 | 0 | 0 | 8 | 11 | 100% | 0 | 1 | Completed
ER6666LT | W209 | W209.A29030 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Summary of Compliance with RADWASTE Assessment Principles EAN to CDMS | 2023-04-03 | 2023-04-14 | 8 | 0 | 8 | 11 | 100% | 0.72727 | 1 | Completed
ER6371LT | W202 | W202.A2206580 | HRA Reactors Shutdown Essential Safety Cases | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 2023-04-03 | 2023-04-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206590 | HRA Reactors Shutdown Essential Safety Cases | Ensure Alignment of Schedule & Estimate | 2023-04-03 | 2023-04-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206710 | HRA Reactors Shutdown Essential Safety Cases | Workshop to agree scope, effort and links | 2023-04-03 | 2023-04-04 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6661LT | W206 | W206.A2206580 | HYA Reactors Shutdown Essential Safety Cases | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 2023-04-03 | 2023-04-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206590 | HYA Reactors Shutdown Essential Safety Cases | Ensure Alignment of Schedule & Estimate | 2023-04-03 | 2023-04-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206710 | HYA Reactors Shutdown Essential Safety Cases | Workshop to agree scope, effort and links | 2023-04-03 | 2023-04-04 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6372LT | W203 | W203.A3660 | HNB Enhanced Defuelling Safety Cases | Produce MF | 2023-04-03 | 2023-04-11 | 5 | 0 | 5 | 8 | 100% | 0.625 | 1 | Completed
ER6668LT | W213 | W213.A29030 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Summary of Compliance with RADWASTE Assessment Principles EAN to CDMS | 2023-04-03 | 2023-04-14 | 8 | 0 | 8 | 11 | 100% | 0.72727 | 1 | Completed
W232LT | W232 | W232.A1260 | DNB Enhanced Safety Cases | Verify supporting reference <PSA Sensitivity Study> | 2023-04-04 | 2023-04-07 | 10 | 0 | 3 | 3 | 100% | 3.3333 | 1 | Completed
W232LT | W232 | W232.A1230 | DNB Enhanced Safety Cases | FEGO / TOG Stakeholder Mgmt | 2023-04-04 | 2023-04-11 | 9 | 0 | 4 | 7 | 100% | 1.2857 | 1 | Completed
ER6371LT | W202 | W202.A2206620 | HRA Reactors Shutdown Essential Safety Cases | Update Schedule/Estimate from Risk Log & Add Provisions | 2023-04-04 | 2023-04-04 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206620 | HYA Reactors Shutdown Essential Safety Cases | Update Schedule/Estimate from Risk Log & Add Provisions | 2023-04-04 | 2023-04-04 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206630 | HRA Reactors Shutdown Essential Safety Cases | Add Data to IAB Paper | 2023-04-05 | 2023-04-05 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206630 | HYA Reactors Shutdown Essential Safety Cases | Add Data to IAB Paper | 2023-04-05 | 2023-04-05 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206640 | HRA Reactors Shutdown Essential Safety Cases | PCL Validate & Approve Baseline Package for PRC Submission | 2023-04-06 | 2023-04-06 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206640 | HYA Reactors Shutdown Essential Safety Cases | PCL Validate & Approve Baseline Package for PRC Submission | 2023-04-06 | 2023-04-06 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1430 | DNB Enhanced Safety Cases | EDF Technical review of supporting reference <PSA Sensitivity Study> | 2023-04-10 | 2023-04-12 | 10 | 0 | 1 | 2 | 100% | 5 | 1 | Completed
ER6372LT | W203 | W203.A3330 | HNB Enhanced Defuelling Safety Cases | Issue MF | 2023-04-11 | 2023-04-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3380 | HNB Enhanced Defuelling Safety Cases | CO & CA appointed | 2023-04-11 | 2023-04-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A29250 | HYB Essential Defueling Safety Case | Technical Review of Defuelling Hazards Review EAN | 2023-04-11 | 2023-04-14 | 20 | 0 | 4 | 3 | 100% | 6.6667 | 1 | Completed
ER6668LT | W213 | W213.A29250 | TOR Essential Defueling Safety Case | Technical Review of Defuelling Hazards Review EAN | 2023-04-11 | 2023-04-14 | 20 | 0 | 4 | 3 | 100% | 6.6667 | 1 | Completed
ER6372LT | W203 | W203.A3840 | HNB Enhanced Defuelling Safety Cases | Issue MF | 2023-04-11 | 2023-04-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3890 | HNB Enhanced Defuelling Safety Cases | CO & CA appointed | 2023-04-11 | 2023-04-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3210 | HNB Enhanced Defuelling Safety Cases | Hold project kick start meeting with Station & key suppliers | 2023-04-12 | 2023-04-18 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6372LT | W203 | W203.A3480 | HNB Enhanced Defuelling Safety Cases | Identify verifier for the case & establish all other resources | 2023-04-12 | 2023-04-18 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.A24800 | HYB Essential Defueling Safety Case | Verify Human Factors Assessment of Misloading / Mis-Defueling Faults EAN & Issue | 2023-04-12 | 2023-06-16 | 14 | 0 | 45 | 65 | 100% | 0.21538 | 1 | Completed
ER6371LT | W202 | W202.A2206550 | HRA Reactors Shutdown Essential Safety Cases | Gate C+ PRC Paper Submission | 2023-04-12 | 2023-04-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206670 | HRA Reactors Shutdown Essential Safety Cases | PRC Members Review PRC Documentation | 2023-04-12 | 2023-04-17 | 4 | 0 | 4 | 5 | 100% | 0.8 | 1 | Completed
ER6661LT | W206 | W206.A2206550 | HYA Reactors Shutdown Essential Safety Cases | Gate C+ PRC Paper Submission | 2023-04-12 | 2023-04-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206670 | HYA Reactors Shutdown Essential Safety Cases | PRC Members Review PRC Documentation | 2023-04-12 | 2023-04-17 | 4 | 0 | 4 | 5 | 100% | 0.8 | 1 | Completed
ER6372LT | W203 | W203.A3720 | HNB Enhanced Defuelling Safety Cases | Hold project kick start meeting with Station & key suppliers | 2023-04-12 | 2023-04-18 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6372LT | W203 | W203.A3990 | HNB Enhanced Defuelling Safety Cases | Identify verifier for the case & establish all other resources | 2023-04-12 | 2023-04-18 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.A24800 | TOR Essential Defueling Safety Case | Verify Human Factors Assessment of Misloading / Mis-Defueling Faults EAN & Issue | 2023-04-12 | 2023-06-16 | 14 | 0 | 45 | 65 | 100% | 0.21538 | 1 | Completed
W232LT | W232 | W232.A1480 | DNB Enhanced Safety Cases | Supporting reference <PSA Sensitivity Study> approved | 2023-04-14 | 2023-04-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.28900 | HYB Essential Defueling Safety Case | Discover Milestone - Review need for Further HF Assessment | 2023-04-14 | 2023-04-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.2020 | DNB Enhanced Safety Cases | >>>OUTGOING ENABLER PSA Sensitivity Study Complete | 2023-04-14 | 2023-04-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.28900 | TOR Essential Defueling Safety Case | Discover Milestone - Review need for Further HF Assessment | 2023-04-14 | 2023-04-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A29040 | HYB Essential Defueling Safety Case | Summary of Compliance with RADWASTE Assessment Principles EAN Available | 2023-04-14 | 2023-04-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A29040 | TOR Essential Defueling Safety Case | Summary of Compliance with RADWASTE Assessment Principles EAN Available | 2023-04-14 | 2023-04-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2740 | DNB Enhanced Safety Cases | Verify supporting reference <Maintenance Review of FR Plant> | 2023-04-17 | 2023-05-23 | 10 | 0 | 25 | 36 | 100% | 0.27778 | 1 | Completed
ER6666LT | W209 | W209.A29260 | HYB Essential Defueling Safety Case | Supplier Update and Issue Defuelling Hazards Review EAN | 2023-04-17 | 2023-07-20 | 5 | 0 | 66 | 94 | 100% | 0.053191 | 1 | Completed
ER6666LT | W209 | W209.A29980 | HYB Essential Defueling Safety Case | Technical Review of FM Underload Protection Mods Prelim Design (GLM) | 2023-04-17 | 2023-05-10 | 16 | 0 | 16 | 23 | 100% | 0.69565 | 1 | Completed
ER6666LT | W209 | W209.A31360 | HYB Essential Defueling Safety Case | Verify Fuelling Machine Purging Requirements During Defueling | 2023-04-17 | 2023-07-21 | 32 | 0 | 67 | 95 | 100% | 0.33684 | 1 | Completed
ER6668LT | W213 | W213.A29260 | TOR Essential Defueling Safety Case | Supplier Update and Issue Defuelling Hazards Review EAN | 2023-04-17 | 2023-07-20 | 5 | 0 | 66 | 94 | 100% | 0.053191 | 1 | Completed
ER6668LT | W213 | W213.A29980 | TOR Essential Defueling Safety Case | Technical Review of FM Underload Protection Mods Prelim Design (GLM) | 2023-04-17 | 2023-05-10 | 16 | 0 | 16 | 23 | 100% | 0.69565 | 1 | Completed
ER6668LT | W213 | W213.A31360 | TOR Essential Defueling Safety Case | Verify Fuelling Machine Purging Requirements During Defueling | 2023-04-17 | 2023-07-21 | 32 | 0 | 67 | 95 | 100% | 0.33684 | 1 | Completed
ER6666LT | W209 | W209.7360 | HYB Essential Defueling Safety Case | Case Officer Tech Lead Review Claim 6 and Address Comments | 2023-04-18 | 2023-06-13 | 20 | 0 | 38 | 56 | 100% | 0.35714 | 1 | Completed
ER6668LT | W213 | W213.7360 | TOR Essential Defueling Safety Case | Case Officer Tech Lead Review Claim 6 and Address Comments | 2023-04-18 | 2023-06-13 | 20 | 0 | 38 | 56 | 100% | 0.35714 | 1 | Completed
ER6372LT | W203 | W203.A3450 | HNB Enhanced Defuelling Safety Cases | Categorisation by station | 2023-04-19 | 2023-04-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3960 | HNB Enhanced Defuelling Safety Cases | Categorisation by station | 2023-04-19 | 2023-04-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3220 | HNB Enhanced Defuelling Safety Cases | Agree resource & timescales with suppliers for delivering key refs, incl contingency, risk & allowance for rework | 2023-04-20 | 2023-04-20 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3730 | HNB Enhanced Defuelling Safety Cases | Agree resource & timescales with suppliers for delivering key refs, incl contingency, risk & allowance for rework | 2023-04-20 | 2023-04-20 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 1955 | HYA Fuel Handling Essential Safety Case | Final Update of Head Document (Needs PSA Numbers and Verified Draft FDD **ACTION** Review Predecsessors ie 5 key Docs) | 2023-04-20 | 2023-11-22 | 20 | 0 | 151 | 216 | 100% | 0.092593 | 1 | Completed
ER6666LT | W209 | W209.A30970 | HYB Essential Defueling Safety Case | Technical Review of Channel X | 2023-04-21 | 2023-05-22 | 30 | 0 | 19 | 31 | 100% | 0.96774 | 1 | Completed
W232LT | W232 | W232.A2930 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Discovery Milestone: Moisture Detection Capability | 2023-04-21 | 2023-04-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A30970 | TOR Essential Defueling Safety Case | Technical Review of Channel X | 2023-04-21 | 2023-05-22 | 30 | 0 | 19 | 31 | 100% | 0.96774 | 1 | Completed
W232LT | W232 | W232.B6620 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Summary | 2023-04-21 | 2023-04-21 | 69 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6630 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Summary | 2023-04-21 | 2023-04-21 | 10 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6640 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Approve Task Sheet | 2023-04-21 | 2023-04-21 | 2 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6650 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Pre Job Brief | 2023-04-21 | 2023-04-21 | 2 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6660 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Draft and issue Task Sheet | 2023-04-21 | 2023-04-21 | 10 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6670 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Prepare Draft EAN | 2023-04-21 | 2023-04-21 | 20 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6690 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Draft EAN Reviewed by EDF SQEP | 2023-04-21 | 2023-04-21 | 10 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6700 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Address Comments from EDF Review on Draft EAN | 2023-04-21 | 2023-04-21 | 10 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6720 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Moisture Detection Capability - EAN Completed and Uploaded to CDMS | 2023-04-21 | 2023-04-21 | 10 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6740 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Moisture Detection Capability - TSA Internal Review of Draft EAN | 2023-04-21 | 2023-04-21 | 5 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A25920 | HYB Essential Defueling Safety Case | Safety Case Requirements EAN - TASK E EAN Available | 2023-04-21 | 2023-04-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A26800 | HYB Essential Defueling Safety Case | Boron Bead Injection Feasibility & Control Rod Isolation EAN Available | 2023-04-21 | 2023-04-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6680 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Issue Draft EAN to EDF for Review. | 2023-04-21 | 2023-04-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6710 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Issue Final EAN | 2023-04-21 | 2023-04-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6730 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Moisture Detection Capability - EAN Completed | 2023-04-21 | 2023-04-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A25920 | TOR Essential Defueling Safety Case | Safety Case Requirements EAN - TASK E EAN Available | 2023-04-21 | 2023-04-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A26800 | TOR Essential Defueling Safety Case | Boron Bead Injection Feasibility & Control Rod Isolation EAN Available | 2023-04-21 | 2023-04-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A24590 | HYB Essential Defueling Safety Case | Verify Human Reliability Baseline Report EAN & Issue for Technical Review | 2023-04-24 | 2023-07-03 | 15 | 0 | 48 | 70 | 100% | 0.21429 | 1 | Completed
ER6372LT | W203 | W203.A3620 | HNB Enhanced Defuelling Safety Cases | Produce supporting reference <Purge and Pressurisation> | 2023-04-24 | 2023-05-19 | 20 | 0 | 18 | 25 | 100% | 0.8 | 1 | Completed
ER6372LT | W203 | W203.A4130 | HNB Enhanced Defuelling Safety Cases | Produce supporting reference <IFD Deluge> | 2023-04-24 | 2023-06-09 | 10 | 0 | 31 | 46 | 100% | 0.21739 | 1 | Completed
ER6372LT | W203 | W203.B1030 | HNB Enhanced Defuelling Safety Cases | Produce supporting reference <Dropped Fuel Consequences EAN> | 2023-04-24 | 2023-05-26 | 20 | 0 | 22 | 32 | 100% | 0.625 | 1 | Completed
ER6668LT | W213 | W213.A24590 | TOR Essential Defueling Safety Case | Verify Human Reliability Baseline Report EAN & Issue for Technical Review | 2023-04-24 | 2023-07-03 | 15 | 0 | 48 | 70 | 100% | 0.21429 | 1 | Completed
ER6666LT | W209 | W209.28980 | HYB Essential Defueling Safety Case | Decision Milestone on Boron Bead Injection | 2023-04-25 | 2023-04-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A27290 | HRA Fuel Handling Essential Safety Case | Revise Project Definition Document (PDD) | 2023-04-25 | 2023-04-25 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A27380 | HRA Fuel Handling Essential Safety Case | Hold Risk Workshop | 2023-04-25 | 2023-04-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A27400 | HRA Fuel Handling Essential Safety Case | Estimate Scope +/- 10% Lifecycle | 2023-04-25 | 2023-05-02 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6378LT | W222 | W222.A27410 | HRA Fuel Handling Essential Safety Case | Plan Scope in Primavera Level 2 Lifecycle) | 2023-04-25 | 2023-05-02 | 1 | 0 | 5 | 7 | 100% | 0.14286 | 1 | Completed
ER6650LT | W226 | W226.A27290 | HYA Fuel Handling Essential Safety Case | Revise Project Definition Document (PDD) | 2023-04-25 | 2023-04-25 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27380 | HYA Fuel Handling Essential Safety Case | Hold Risk Workshop | 2023-04-25 | 2023-04-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27400 | HYA Fuel Handling Essential Safety Case | Estimate Scope +/- 10% Lifecycle | 2023-04-25 | 2023-05-02 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6650LT | W226 | W226.A27410 | HYA Fuel Handling Essential Safety Case | Plan Scope in Primavera Level 2 Lifecycle) | 2023-04-25 | 2023-05-02 | 1 | 0 | 5 | 7 | 100% | 0.14286 | 1 | Completed
ER6372LT | W203 | W203.A3340 | HNB Enhanced Defuelling Safety Cases | INSA agree MF and Identify INSA Resource (KDM) | 2023-04-25 | 2023-04-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3540 | HNB Enhanced Defuelling Safety Cases | INSA Approval Date Identified | 2023-04-25 | 2023-04-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3550 | HNB Enhanced Defuelling Safety Cases | Provide Provisional NSC Date | 2023-04-25 | 2023-04-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.28980 | TOR Essential Defueling Safety Case | Decision Milestone on Boron Bead Injection | 2023-04-25 | 2023-04-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206660 | HRA Reactors Shutdown Essential Safety Cases | Hold PRC Meeting | 2023-04-25 | 2023-04-25 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206660 | HYA Reactors Shutdown Essential Safety Cases | Hold PRC Meeting | 2023-04-25 | 2023-04-25 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206680 | HRA Reactors Shutdown Essential Safety Cases | Gate C+ PRC Paper Approval | 2023-04-25 | 2023-04-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206680 | HYA Reactors Shutdown Essential Safety Cases | Gate C+ PRC Paper Approval | 2023-04-25 | 2023-04-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206730 | HRA Reactors Shutdown Essential Safety Cases | Gate C+ PRC Paper Approval | 2023-04-25 | 2023-04-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206730 | HYA Reactors Shutdown Essential Safety Cases | Gate C+ PRC Paper Approval | 2023-04-25 | 2023-04-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3850 | HNB Enhanced Defuelling Safety Cases | INSA agree MF and Identify INSA Resource (KDM) - <IFD Deluge> | 2023-04-25 | 2023-04-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A4050 | HNB Enhanced Defuelling Safety Cases | INSA Approval Date Identified | 2023-04-25 | 2023-04-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A4060 | HNB Enhanced Defuelling Safety Cases | Provide Provisional NSC Date | 2023-04-25 | 2023-04-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A5205 | HRA Reactors Shutdown Essential Safety Cases | SC - Safety Case development - INSA - HRA - C-D - INSA | 2023-04-26 | 2024-10-02 | 124 | 0 | 364 | 525 | 100% | 0.23619 | 1 | Completed
ER6661LT | W206 | W206.A5205 | HYA Reactors Shutdown Essential Safety Cases | SC - Safety Case development - INSA - HYA - C-D - INSA | 2023-04-26 | 2024-10-10 | 124 | 0 | 369 | 533 | 100% | 0.23265 | 1 | Completed
ER6371LT | W202 | W202.A5255 | HRA Reactors Shutdown Essential Safety Cases | INSA review & iteration of comments (using BARRIER MODEL) (HRA) (Resumed after Event Recovery) | 2023-04-26 | 2023-07-31 | 25 | 0 | 65 | 96 | 100% | 0.26042 | 1 | Completed
ER6661LT | W206 | W206.A5255 | HYA Reactors Shutdown Essential Safety Cases | INSA review & iteration of comments (using BARRIER MODEL) (HYA) (Resumed after Event Recovery) | 2023-04-26 | 2023-07-31 | 25 | 0 | 65 | 96 | 100% | 0.26042 | 1 | Completed
ER6372LT | W203 | W203.A3160 | HNB Enhanced Defuelling Safety Cases | Produce draft NSRS (using BARRIER MODEL) | 2023-04-26 | 2023-05-31 | 10 | 0 | 22 | 35 | 100% | 0.28571 | 1 | Completed
ER6666LT | W209 | W209.A27110 | HYB Essential Defueling Safety Case | Complete TR Form and Upload FPU Integrity Analysis EAN to CDMS | 2023-04-26 | 2023-05-12 | 5 | 0 | 10 | 16 | 100% | 0.3125 | 1 | Completed
ER6372LT | W203 | W203.A3670 | HNB Enhanced Defuelling Safety Cases | Produce draft NSRS (using BARRIER MODEL) | 2023-04-26 | 2023-07-31 | 15 | 0 | 65 | 96 | 100% | 0.15625 | 1 | Completed
ER6668LT | W213 | W213.A27110 | TOR Essential Defueling Safety Case | Complete TR Form and Upload FPU Integrity Analysis EAN to CDMS | 2023-04-26 | 2023-05-12 | 5 | 0 | 10 | 16 | 100% | 0.3125 | 1 | Completed
ER6666LT | W209 | W209.25900 | HYB Essential Defueling Safety Case | Verify Human Reliability Assessment of Unsubstantiated Claims EAN & Issue for Technical Review | 2023-04-28 | 2023-07-28 | 15 | 0 | 63 | 91 | 100% | 0.16484 | 1 | Completed
ER6668LT | W213 | W213.25900 | TOR Essential Defueling Safety Case | Verify Human Reliability Assessment of Unsubstantiated Claims EAN & Issue for Technical Review | 2023-04-28 | 2023-07-28 | 15 | 0 | 63 | 91 | 100% | 0.16484 | 1 | Completed
ER6666LT | W209 | W209.7020 | HYB Essential Defueling Safety Case | Update Claim 2 | 2023-05-01 | 2023-10-27 | 9 | 0 | 126 | 179 | 100% | 0.050279 | 1 | Completed
ER6668LT | W213 | W213.7020 | TOR Essential Defueling Safety Case | Update Claim 2 | 2023-05-01 | 2023-10-27 | 9 | 0 | 125 | 179 | 100% | 0.050279 | 1 | Completed
ER6666LT | W209 | W209.29510 | HYB Essential Defueling Safety Case | PVCS Draindown Volume Calc Note - EAN Available | 2023-05-02 | 2024-01-10 | 1 | 0 | 175 | 253 | 100% | 0.0039526 | 1 | Completed
ER6668LT | W213 | W213.29510 | TOR Essential Defueling Safety Case | PVCS Draindown Volume Calc Note - EAN Available | 2023-05-02 | 2024-01-10 | 1 | 0 | 175 | 253 | 100% | 0.0039526 | 1 | Completed
ER6666LT | W209 | W209.A24640 | HYB Essential Defueling Safety Case | Pre Job Brief for Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN | 2023-05-02 | 2023-05-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6500 | DNB Enhanced Safety Cases | Core Support Plate Structural Integrity Criticality - Summary | 2023-05-02 | 2023-06-23 | 30 | 0 | 36 | 52 | 100% | 0.57692 | 1 | Completed
W232LT | W232 | W232.B6530 | DNB Enhanced Safety Cases | Core Support Plate Structural Integrity Criticality - Draft and issue Task Sheet | 2023-05-02 | 2023-05-31 | 10 | 0 | 19 | 29 | 100% | 0.34483 | 1 | Completed
ER6668LT | W213 | W213.A24640 | TOR Essential Defueling Safety Case | Pre Job Brief for Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN | 2023-05-02 | 2023-05-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A24650 | HYB Essential Defueling Safety Case | Draft Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN | 2023-05-03 | 2023-05-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A30600 | HYB Essential Defueling Safety Case | Draft FM Direct Process Protection Design | 2023-05-03 | 2023-05-24 | 68 | 0 | 14 | 21 | 100% | 3.2381 | 1 | Completed
ER6378LT | W222 | W222.A27390 | HRA Fuel Handling Essential Safety Case | Ensure Alignment of Schedule & Estimate | 2023-05-03 | 2023-05-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27390 | HYA Fuel Handling Essential Safety Case | Ensure Alignment of Schedule & Estimate | 2023-05-03 | 2023-05-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A24650 | TOR Essential Defueling Safety Case | Draft Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN | 2023-05-03 | 2023-05-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A30600 | TOR Essential Defueling Safety Case | Draft FM Direct Process Protection Design | 2023-05-03 | 2023-05-24 | 68 | 0 | 14 | 21 | 100% | 3.2381 | 1 | Completed
ER6666LT | W209 | W209.A31390 | HYB Essential Defueling Safety Case | Pre Job Brief for Stress Modelling | 2023-05-04 | 2023-05-04 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A31390 | TOR Essential Defueling Safety Case | Pre Job Brief for Stress Modelling | 2023-05-04 | 2023-05-04 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A24660 | HYB Essential Defueling Safety Case | Verify Human Reliability Assessment of New and/or Modified Human Based Safety Claims & Issue for Technical Review | 2023-05-04 | 2023-05-04 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A27370 | HRA Fuel Handling Essential Safety Case | Complete Risk Log with Estimates | 2023-05-04 | 2023-05-04 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27370 | HYA Fuel Handling Essential Safety Case | Complete Risk Log with Estimates | 2023-05-04 | 2023-05-04 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2490 | DNB Enhanced Safety Cases | Structural Integrity TOG Engagement | 2023-05-04 | 2023-05-04 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A24660 | TOR Essential Defueling Safety Case | Verify Human Reliability Assessment of New and/or Modified Human Based Safety Claims & Issue for Technical Review | 2023-05-04 | 2023-05-04 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A31400 | HYB Essential Defueling Safety Case | Draft Review of Stress Modelling EAN | 2023-05-05 | 2023-05-24 | 0 | 0 | 12 | 19 | 100% | 0 | 1 | Completed
ER6668LT | W213 | W213.A31400 | TOR Essential Defueling Safety Case | Draft Review of Stress Modelling EAN | 2023-05-05 | 2023-05-24 | 0 | 0 | 12 | 19 | 100% | 0 | 1 | Completed
ER6666LT | W209 | W209.A24670 | HYB Essential Defueling Safety Case | Technical Review of Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN | 2023-05-05 | 2023-05-05 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A27360 | HRA Fuel Handling Essential Safety Case | Update Schedule/Estimate from Risk Log & Add Provisions | 2023-05-05 | 2023-05-05 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27360 | HYA Fuel Handling Essential Safety Case | Update Schedule/Estimate from Risk Log & Add Provisions | 2023-05-05 | 2023-05-05 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A24670 | TOR Essential Defueling Safety Case | Technical Review of Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN | 2023-05-05 | 2023-05-05 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A24680 | HYB Essential Defueling Safety Case | Supplier Update and Issue Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN | 2023-05-09 | 2023-05-09 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A27350 | HRA Fuel Handling Essential Safety Case | Add Data to PRC Paper | 2023-05-09 | 2023-05-09 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27350 | HYA Fuel Handling Essential Safety Case | Add Data to PRC Paper | 2023-05-09 | 2023-05-09 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A24680 | TOR Essential Defueling Safety Case | Supplier Update and Issue Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN | 2023-05-09 | 2023-05-09 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A24690 | HYB Essential Defueling Safety Case | Complete Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN to CDMS | 2023-05-10 | 2023-05-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A27340 | HRA Fuel Handling Essential Safety Case | PCL Validate & Approve Baseline Package for PRC Submission | 2023-05-10 | 2023-05-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27340 | HYA Fuel Handling Essential Safety Case | PCL Validate & Approve Baseline Package for PRC Submission | 2023-05-10 | 2023-05-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A24690 | TOR Essential Defueling Safety Case | Complete Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN to CDMS | 2023-05-10 | 2023-05-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A24700 | HYB Essential Defueling Safety Case | Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN Available | 2023-05-10 | 2023-05-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A27420 | HRA Fuel Handling Essential Safety Case | Issue PRC Paper to R4 PRC Members | 2023-05-10 | 2023-05-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27420 | HYA Fuel Handling Essential Safety Case | Issue PRC Paper to R4 PRC Members | 2023-05-10 | 2023-05-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A24700 | TOR Essential Defueling Safety Case | Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN Available | 2023-05-10 | 2023-05-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A29990 | HYB Essential Defueling Safety Case | Supplier Update and Issue FM Underload Protection Mods Prelim Design (GLM) | 2023-05-11 | 2023-05-17 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6378LT | W222 | W222.A27330 | HRA Fuel Handling Essential Safety Case | PRC Members Review PRC Documentation | 2023-05-11 | 2023-05-17 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6650LT | W226 | W226.A27335 | HYA Fuel Handling Essential Safety Case | PRC Members Review PRC Documentation | 2023-05-11 | 2023-05-17 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.A29990 | TOR Essential Defueling Safety Case | Supplier Update and Issue FM Underload Protection Mods Prelim Design (GLM) | 2023-05-11 | 2023-05-17 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.A27120 | HYB Essential Defueling Safety Case | FPU Integrity Analysis EAN Available | 2023-05-12 | 2023-05-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A27120 | TOR Essential Defueling Safety Case | FPU Integrity Analysis EAN Available | 2023-05-12 | 2023-05-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A29630 | HYB Essential Defueling Safety Case | TASK F Review of the Discharge Limits (Permits) EAN Available | 2023-05-12 | 2023-05-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A29630 | TOR Essential Defueling Safety Case | TASK F Review of the Discharge Limits (Permits) EAN Available | 2023-05-12 | 2023-05-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A4960 | DNB Enhanced Safety Cases | Discovery Milestone: What Further Supporting Work Do We Require? | 2023-05-15 | 2023-05-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.29500 | HYB Essential Defueling Safety Case | Fuel Plug Unit Thermal Shield Performance During Defuelling - EAN Available | 2023-05-17 | 2023-06-15 | 1 | 0 | 21 | 29 | 100% | 0.034483 | 1 | Completed
ER6668LT | W213 | W213.29500 | TOR Essential Defueling Safety Case | Fuel Plug Unit Thermal Shield Performance During Defuelling - EAN Available | 2023-05-17 | 2023-06-15 | 1 | 0 | 21 | 29 | 100% | 0.034483 | 1 | Completed
ER6666LT | W209 | W209.A30000 | HYB Essential Defueling Safety Case | Complete TR Form and Upload FM Underload Protection Mods Prelim Design (GLM) to CDMS | 2023-05-18 | 2023-05-19 | 5 | 0 | 1 | 1 | 100% | 5 | 1 | Completed
ER6668LT | W213 | W213.A30000 | TOR Essential Defueling Safety Case | Complete TR Form and Upload FM Underload Protection Mods Prelim Design (GLM) to CDMS | 2023-05-18 | 2023-05-19 | 5 | 0 | 1 | 1 | 100% | 5 | 1 | Completed
ER6666LT | W209 | W209.A29770 | HYB Essential Defueling Safety Case | ALARP Review of Not Draining the PVCS (Report) Available | 2023-05-19 | 2023-05-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A30010 | HYB Essential Defueling Safety Case | FM Underload Protection Mods Prelim Design (GLM) Available | 2023-05-19 | 2023-05-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A29770 | TOR Essential Defueling Safety Case | ALARP Review of Not Draining the PVCS (Report) Available | 2023-05-19 | 2023-05-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A30010 | TOR Essential Defueling Safety Case | FM Underload Protection Mods Prelim Design (GLM) Available | 2023-05-19 | 2023-05-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A30980 | HYB Essential Defueling Safety Case | Supplier Update and Issue Channel X | 2023-05-22 | 2023-05-22 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A30990 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Channel X to CDMS | 2023-05-22 | 2023-05-31 | 5 | 0 | 6 | 9 | 100% | 0.55556 | 1 | Completed
ER6668LT | W213 | W213.A30980 | TOR Essential Defueling Safety Case | Supplier Update and Issue Channel X | 2023-05-22 | 2023-05-22 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A30990 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Channel X to CDMS | 2023-05-22 | 2023-05-31 | 5 | 0 | 6 | 9 | 100% | 0.55556 | 1 | Completed
ER6372LT | W203 | W203.A3610 | HNB Enhanced Defuelling Safety Cases | Verify supporting reference <Purge and Pressurisation> | 2023-05-22 | 2023-05-24 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6378LT | W222 | W222.A27430 | HRA Fuel Handling Essential Safety Case | Gate C+ for Region 1 - HRA Defuelling Fuel Handling Essential Safety Case | 2023-05-23 | 2023-05-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W222.A27430 | HYA Fuel Handling Essential Safety Case | Gate C+ for Region 1 - HYA Defuelling Fuel Handling Essential Safety Case | 2023-05-23 | 2023-05-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A27320 | HRA Fuel Handling Essential Safety Case | Hold R4 PRC Meeting | 2023-05-23 | 2023-05-23 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27325 | HYA Fuel Handling Essential Safety Case | Hold R4 PRC Meeting | 2023-05-23 | 2023-05-23 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A30610 | HYB Essential Defueling Safety Case | Verify FM Direct Process Protection Design & Issue for Technic | 2023-05-24 | 2023-05-24 | 40 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A30620 | HYB Essential Defueling Safety Case | Technical Review of FM Direct Process Protection Design | 2023-05-24 | 2023-05-24 | 30 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A30630 | HYB Essential Defueling Safety Case | Supplier Update and Issue FM Direct Process Protection Design | 2023-05-24 | 2023-05-24 | 15 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A30640 | HYB Essential Defueling Safety Case | Complete TR Form and Upload FM Direct Process Protection Design | 2023-05-24 | 2023-05-24 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A30650 | HYB Essential Defueling Safety Case | FM Direct Process Protection Design Available | 2023-05-24 | 2023-05-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.9010 | HYB Essential Defueling Safety Case | Discovery Milestone - FM Direct Process Protection Design - Drafted | 2023-05-24 | 2023-05-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A30610 | TOR Essential Defueling Safety Case | Verify FM Direct Process Protection Design & Issue for Technic | 2023-05-24 | 2023-05-24 | 40 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A30620 | TOR Essential Defueling Safety Case | Technical Review of FM Direct Process Protection Design | 2023-05-24 | 2023-05-24 | 30 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A30630 | TOR Essential Defueling Safety Case | Supplier Update and Issue FM Direct Process Protection Design | 2023-05-24 | 2023-05-24 | 15 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A30640 | TOR Essential Defueling Safety Case | Complete TR Form and Upload FM Direct Process Protection Design | 2023-05-24 | 2023-05-24 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A30650 | TOR Essential Defueling Safety Case | FM Direct Process Protection Design Available | 2023-05-24 | 2023-05-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.9010 | TOR Essential Defueling Safety Case | Discovery Milestone - FM Direct Process Protection Design - Drafted | 2023-05-24 | 2023-05-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2750 | DNB Enhanced Safety Cases | EDF Technical review of supporting reference <Maintenance Review of FR Plant> | 2023-05-24 | 2023-06-30 | 10 | 0 | 26 | 37 | 100% | 0.27027 | 1 | Completed
ER6378LT | W222 | W222.A27310 | HRA Fuel Handling Essential Safety Case | Modify Estimate, Schedule & Risk Log as Required | 2023-05-24 | 2023-05-25 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6650LT | W226 | W226.A27315 | HYA Fuel Handling Essential Safety Case | Modify Estimate, Schedule & Risk Log as Required | 2023-05-24 | 2023-05-25 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6666LT | W209 | W209.A31410 | HYB Essential Defueling Safety Case | Verify Review of Stress Modelling EAN & Issue for Technical Review | 2023-05-25 | 2023-06-30 | 0 | 0 | 25 | 36 | 100% | 0 | 1 | Completed
ER6668LT | W213 | W213.A31410 | TOR Essential Defueling Safety Case | Verify Review of Stress Modelling EAN & Issue for Technical Review | 2023-05-25 | 2023-06-30 | 0 | 0 | 25 | 36 | 100% | 0 | 1 | Completed
ER6372LT | W203 | W203.A3600 | HNB Enhanced Defuelling Safety Cases | BE Technical review of supporting reference <Purge and Pressurisation> | 2023-05-25 | 2023-05-30 | 3 | 0 | 3 | 5 | 100% | 0.6 | 1 | Completed
ER6378LT | W222 | W222.A27300 | HRA Fuel Handling Essential Safety Case | Update Cost Management Tool | 2023-05-26 | 2023-05-26 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27305 | HYA Fuel Handling Essential Safety Case | Update Cost Management Tool | 2023-05-26 | 2023-05-26 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.B1020 | HNB Enhanced Defuelling Safety Cases | Verify supporting reference <Dropped Fuel Consequences EAN> | 2023-05-29 | 2023-05-31 | 3 | 0 | 1 | 2 | 100% | 1.5 | 1 | Completed
ER6371LT | W202 | W202.A5545 | HRA Reactors Shutdown Essential Safety Cases | Verification Complete - (Event Recovery) - EC 363682 | 2023-05-30 | 2023-05-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5545 | HYA Reactors Shutdown Essential Safety Cases | Verification Complete - (Event Recovery) - EC 363676 | 2023-05-30 | 2023-05-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A2670 | HNB Enhanced Defuelling Safety Cases | All key supporting technical references complete <RESUMED 01.03.2023> - Purge and Pressurisation | 2023-05-30 | 2023-05-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3590 | HNB Enhanced Defuelling Safety Cases | Supporting reference <Purge and Pressurisation> approved | 2023-05-30 | 2023-05-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3640 | HNB Enhanced Defuelling Safety Cases | All supporting references completed | 2023-05-30 | 2023-05-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A2590 | HNB Enhanced Defuelling Safety Cases | XXXX DISCOVERY MILESTONE: Decision to Proceed with EC Production XXXX | 2023-05-31 | 2023-05-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A31000 | HYB Essential Defueling Safety Case | Channel X Available | 2023-05-31 | 2023-05-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3650 | HNB Enhanced Defuelling Safety Cases | Draft NSRS complete - Purge and Pressurisation | 2023-05-31 | 2023-05-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A31000 | TOR Essential Defueling Safety Case | Channel X Available | 2023-05-31 | 2023-05-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.B1010 | HNB Enhanced Defuelling Safety Cases | BE Technical review of supporting reference <Dropped Fuel Consequences EAN> | 2023-06-01 | 2023-06-05 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6666LT | W209 | W209.29520 | HYB Essential Defueling Safety Case | Draft - HYB R:77 (Deformed Standpipe Liner) EAN | 2023-06-01 | 2023-06-16 | 1 | 0 | 12 | 15 | 100% | 0.066667 | 1 | Completed
ER6668LT | W213 | W213.29520 | TOR Essential Defueling Safety Case | Draft - TOR R:77 (Deformed Standpipe Liner) EAN | 2023-06-01 | 2023-06-16 | 1 | 0 | 12 | 15 | 100% | 0.066667 | 1 | Completed
ER6372LT | W203 | W203.A1870 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Define Project Control Structures (WBS/CBS/OBS/PBS) | 2023-06-01 | 2023-06-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1890 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 2023-06-01 | 2023-06-01 | 5 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1900 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 2023-06-01 | 2023-06-01 | 5 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1920 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Ensure Alignment of Schedule & Estimate | 2023-06-01 | 2023-06-01 | 3 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1930 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Hold Risk Workshop | 2023-06-01 | 2023-06-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1940 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Complete Risk Log with Estimates | 2023-06-01 | 2023-06-01 | 2 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1950 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Update Schedule/Estimate from Risk Log & Add Provisions | 2023-06-01 | 2023-06-01 | 2 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1960 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Add Data to PRC Paper | 2023-06-01 | 2023-06-01 | 2 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1970 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> PCL Validate & Approve Baseline Package for PRC Submission | 2023-06-01 | 2023-06-01 | 3 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1880 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Prepare Draft Project Definition Document (PDD) | 2023-06-01 | 2023-06-01 | 5 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A2000 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Hold PRC Meeting | 2023-06-01 | 2023-06-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1990 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> PRC Members Review PRC Documentation | 2023-06-01 | 2023-06-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1850 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Confirm Objectives to be Delivered at Gate B | 2023-06-01 | 2023-06-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1860 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Initial high level scope of programme | 2023-06-01 | 2023-06-01 | 2 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1910 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Workshop to agree scope, effort and links | 2023-06-01 | 2023-06-01 | 5 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A2110 | HNB Enhanced Defuelling Safety Cases | Project Management Gate B - C | 2023-06-01 | 2024-11-19 | 107 | 0 | 375 | 537 | 100% | 0.19926 | 1 | Completed
W232LT | W232 | W232.B6510 | DNB Enhanced Safety Cases | Core Support Plate Structural Integrity Criticality - Approve Task Sheet | 2023-06-01 | 2023-06-20 | 5 | 0 | 13 | 19 | 100% | 0.26316 | 1 | Completed
ER6372LT | W203 | W203.A3170 | HNB Enhanced Defuelling Safety Cases | Station comments on NSRS | 2023-06-01 | 2023-06-23 | 10 | 0 | 17 | 22 | 100% | 0.45455 | 1 | Completed
ER6372LT | W203 | W203.A3180 | HNB Enhanced Defuelling Safety Cases | Key Stakeholders (Peer) comments on NSRS | 2023-06-01 | 2023-06-23 | 10 | 0 | 17 | 22 | 100% | 0.45455 | 1 | Completed
ER6372LT | W203 | W203.A4040 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Develop plan with further iterations | 2023-06-01 | 2023-06-01 | 10 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A1980 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Gate B PRC Paper Submission | 2023-06-01 | 2023-06-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A2020 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Gate B PRC Paper Approval | 2023-06-01 | 2023-06-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A4000 | HNB Enhanced Defuelling Safety Cases | < SCOPE REMOVED CN571> Issue agreed work programme to stakeholders & suppliers | 2023-06-01 | 2023-06-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.B1000 | HNB Enhanced Defuelling Safety Cases | Supporting reference <Dropped Fuel Consequences EAN> approved | 2023-06-05 | 2023-06-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.7100 | HYB Essential Defueling Safety Case | Verification of Claim 3 | 2023-06-07 | 2023-11-13 | 28 | 0 | 112 | 159 | 100% | 0.1761 | 1 | Completed
ER6668LT | W213 | W213.7100 | TOR Essential Defueling Safety Case | Verification of Claim 3 | 2023-06-07 | 2023-11-13 | 28 | 0 | 113 | 159 | 100% | 0.1761 | 1 | Completed
W232LT | W232 | W232.A1700 | DNB Enhanced Safety Cases | Verification of the case (using BARRIER MODEL) | 2023-06-08 | 2023-07-12 | 20 | 0 | 24 | 34 | 100% | 0.58824 | 1 | Completed
ER6666LT | W209 | W209.7440 | HYB Essential Defueling Safety Case | Author Claim 7 | 2023-06-12 | 2024-01-12 | 40 | 0 | 151 | 214 | 100% | 0.18692 | 1 | Completed
ER6666LT | W209 | W209.8410 | HYB Essential Defueling Safety Case | Claim 7 Production ## (Cost Summary) | 2023-06-12 | 2024-01-26 | 156 | 0 | 161 | 228 | 100% | 0.68421 | 1 | Completed
ER6372LT | W203 | W203.A4120 | HNB Enhanced Defuelling Safety Cases | Verify supporting reference <IFD Deluge> | 2023-06-12 | 2023-06-15 | 3 | 0 | 3 | 3 | 100% | 1 | 1 | Completed
ER6372LT | W203 | W203.B1070 | HNB Enhanced Defuelling Safety Cases | Produce supporting reference <PSA Updates> | 2023-06-12 | 2023-11-03 | 20 | 0 | 104 | 144 | 100% | 0.13889 | 1 | Completed
ER6668LT | W213 | W213.7440 | TOR Essential Defueling Safety Case | Author Claim 7 | 2023-06-12 | 2024-01-12 | 40 | 0 | 151 | 214 | 100% | 0.18692 | 1 | Completed
ER6668LT | W213 | W213.8410 | TOR Essential Defueling Safety Case | Claim 7 Production ## (Cost Summary) | 2023-06-12 | 2024-01-26 | 152 | 0 | 161 | 228 | 100% | 0.66667 | 1 | Completed
ER6371LT | W202 | 3010 | HRA Reactors Shutdown Essential Safety Cases | Lesson Learn - Verification Phase | 2023-06-12 | 2023-06-12 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | 3010 | HYA Reactors Shutdown Essential Safety Cases | Lesson Learn - Verification Phase | 2023-06-12 | 2023-06-12 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.29120 | HYB Essential Defueling Safety Case | Upload to CDMS | 2023-06-13 | 2023-06-19 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.29120 | TOR Essential Defueling Safety Case | Upload to CDMS | 2023-06-13 | 2023-06-19 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.7370 | HYB Essential Defueling Safety Case | Verification of Claim 6 | 2023-06-14 | 2023-11-10 | 20 | 0 | 106 | 149 | 100% | 0.13423 | 1 | Completed
ER6668LT | W213 | W213.7370 | TOR Essential Defueling Safety Case | Verification of Claim 6 | 2023-06-14 | 2023-11-10 | 20 | 0 | 107 | 149 | 100% | 0.13423 | 1 | Completed
ER6372LT | W203 | W203.A4110 | HNB Enhanced Defuelling Safety Cases | BE Technical review of supporting reference <IFD Deluge> | 2023-06-15 | 2023-06-30 | 3 | 0 | 11 | 15 | 100% | 0.2 | 1 | Completed
ER6666LT | W209 | W209.A30730 | HYB Essential Defueling Safety Case | Complete TR Form and Issue Channel 1 - HYB to CDMS | 2023-06-16 | 2023-07-14 | 15 | 0 | 21 | 28 | 100% | 0.53571 | 1 | Completed
ER6668LT | W213 | W213.A30730 | TOR Essential Defueling Safety Case | Complete TR Form and Issue Channel 1 - TOR to CDMS | 2023-06-16 | 2023-07-14 | 15 | 0 | 21 | 28 | 100% | 0.53571 | 1 | Completed
ER6371LT | W202 | 1636 | HRA Reactors Shutdown Essential Safety Cases | Re-Write of FDD v3 | 2023-06-19 | 2023-07-18 | 1 | 0 | 21 | 29 | 100% | 0.034483 | 1 | Completed
ER6661LT | W206 | 1636 | HYA Reactors Shutdown Essential Safety Cases | Re-Write of FDD v3 | 2023-06-19 | 2023-07-18 | 1 | 0 | 21 | 29 | 100% | 0.034483 | 1 | Completed
ER6666LT | W209 | W209.29440 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Human Factors Assessment of Misloading / Mis-Defueling Faults EAN to CDMS | 2023-06-19 | 2023-06-30 | 5 | 0 | 10 | 11 | 100% | 0.45455 | 1 | Completed
ER6666LT | W209 | W209.29530 | HYB Essential Defueling Safety Case | Verify - HYB R:77 (Deformed Standpipe Liner) EAN | 2023-06-19 | 2023-07-20 | 1 | 0 | 24 | 31 | 100% | 0.032258 | 1 | Completed
ER6668LT | W213 | W213.29440 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Human Factors Assessment of Misloading / Mis-Defueling Faults EAN to CDMS | 2023-06-19 | 2023-06-30 | 5 | 0 | 10 | 11 | 100% | 0.45455 | 1 | Completed
ER6668LT | W213 | W213.29530 | TOR Essential Defueling Safety Case | Verify - TOR R:77 (Deformed Standpipe Liner) EAN | 2023-06-19 | 2023-07-20 | 1 | 0 | 24 | 31 | 100% | 0.032258 | 1 | Completed
ER6666LT | W209 | W209.7430 | HYB Essential Defueling Safety Case | PJB for Claim 7 Authoring | 2023-06-20 | 2023-06-20 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6520 | DNB Enhanced Safety Cases | Core Support Plate Structural Integrity Criticality - Pre Job Brief | 2023-06-20 | 2023-06-23 | 5 | 0 | 3 | 3 | 100% | 1.6667 | 1 | Completed
ER6668LT | W213 | W213.7430 | TOR Essential Defueling Safety Case | PJB for Claim 7 Authoring | 2023-06-20 | 2023-06-20 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.7180 | HYB Essential Defueling Safety Case | Case Officer Tech Lead Review Claim 5 | 2023-06-21 | 2023-12-15 | 10 | 0 | 126 | 177 | 100% | 0.056497 | 1 | Completed
ER6668LT | W213 | W213.7180 | TOR Essential Defueling Safety Case | Case Officer Tech Lead Review Claim 5 | 2023-06-21 | 2023-12-15 | 10 | 0 | 126 | 177 | 100% | 0.056497 | 1 | Completed
ER6372LT | W203 | W203.A3510 | HNB Enhanced Defuelling Safety Cases | INA comments on NSRS | 2023-06-23 | 2023-07-24 | 10 | 0 | 21 | 31 | 100% | 0.32258 | 1 | Completed
W232LT | W232 | W232.B6490 | DNB Enhanced Safety Cases | Core Support Plate Structural Integrity Criticality - Summary | 2023-06-26 | 2023-09-25 | 87 | 0 | 64 | 91 | 100% | 0.95604 | 1 | Completed
W232LT | W232 | W232.B6540 | DNB Enhanced Safety Cases | Core Support Plate Structural Integrity Criticality - Prepare Draft EAN | 2023-06-26 | 2023-08-21 | 20 | 0 | 40 | 56 | 100% | 0.35714 | 1 | Completed
ER6666LT | W209 | W209.9020 | HYB Essential Defueling Safety Case | Discovery Milestone - HF assessment of Misloading/Misdefueling - EAN Available | 2023-06-30 | 2023-06-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1490 | DNB Enhanced Safety Cases | All supporting references completed | 2023-06-30 | 2023-06-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2760 | DNB Enhanced Safety Cases | Supporting reference <Maintenance Review of FR Plant> approved | 2023-06-30 | 2023-06-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A4100 | HNB Enhanced Defuelling Safety Cases | Supporting reference <IFD Deluge> approved | 2023-06-30 | 2023-06-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.9020 | TOR Essential Defueling Safety Case | Discovery Milestone - HF assessment of Misloading/Misdefueling - EAN Available | 2023-06-30 | 2023-06-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.29450 | HYB Essential Defueling Safety Case | Human Factors Assessment of Misloading / Mis-Defueling Faults EAN Available (REV 001) | 2023-06-30 | 2023-06-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.29450 | TOR Essential Defueling Safety Case | Human Factors Assessment of Misloading / Mis-Defueling Faults EAN Available (REV 001) | 2023-06-30 | 2023-06-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3240 | HNB Enhanced Defuelling Safety Cases | CA to agree with CO format of the safety case & produce agreed contents page | 2023-07-03 | 2023-07-06 | 2 | 0 | 3 | 3 | 100% | 0.66667 | 1 | Completed
ER6372LT | W203 | W203.A3530 | HNB Enhanced Defuelling Safety Cases | Develop plan with further iterations | 2023-07-03 | 2023-07-14 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6666LT | W209 | W209.A24600 | HYB Essential Defueling Safety Case | Technical Review of Human Reliability Baseline Report EAN | 2023-07-04 | 2023-07-31 | 16 | 0 | 20 | 27 | 100% | 0.59259 | 1 | Completed
ER6668LT | W213 | W213.A24600 | TOR Essential Defueling Safety Case | Technical Review of Human Reliability Baseline Report EAN | 2023-07-04 | 2023-07-31 | 16 | 0 | 20 | 27 | 100% | 0.59259 | 1 | Completed
ER6372LT | W203 | W203.A3250 | HNB Enhanced Defuelling Safety Cases | Prepare the Safety Case Proposal - <Purge and Pressurisation> | 2023-07-10 | 2023-08-19 | 12 | 0 | 30 | 40 | 100% | 0.3 | 1 | Completed
W232LT | W232 | W232.A1750 | DNB Enhanced Safety Cases | Issue to CO & Station for comments | 2023-07-12 | 2023-07-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A30740 | HYB Essential Defueling Safety Case | Channel 1 Detailed Design Spec - HYB Available | 2023-07-14 | 2023-07-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A30740 | TOR Essential Defueling Safety Case | Channel 1 Detailed Design Spec - TOR Available | 2023-07-14 | 2023-07-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3760 | HNB Enhanced Defuelling Safety Cases | Prepare the Safety Case Proposal | 2023-07-17 | 2023-11-20 | 28 | 0 | 90 | 126 | 100% | 0.22222 | 1 | Completed
W232LT | W232 | W232.A1760 | DNB Enhanced Safety Cases | Incorporate CO & Station comments | 2023-07-17 | 2023-07-21 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6666LT | W209 | W209.A31120 | HYB Essential Defueling Safety Case | Upload Defueling Process Flow to CDMS | 2023-07-18 | 2023-07-31 | 5 | 0 | 10 | 13 | 100% | 0.38462 | 1 | Completed
ER6668LT | W213 | W213.A31120 | TOR Essential Defueling Safety Case | Upload Defueling Process Flow to CDMS | 2023-07-18 | 2023-07-31 | 5 | 0 | 10 | 13 | 100% | 0.38462 | 1 | Completed
ER6371LT | W202 | 1646 | HRA Reactors Shutdown Essential Safety Cases | Verifed updated FDD v3 | 2023-07-19 | 2023-10-09 | 10 | 0 | 57 | 82 | 100% | 0.12195 | 1 | Completed
ER6661LT | W206 | 1646 | HYA Reactors Shutdown Essential Safety Cases | Verifed updated FDD v3 | 2023-07-19 | 2023-10-09 | 10 | 0 | 57 | 82 | 100% | 0.12195 | 1 | Completed
ER6666LT | W209 | W209.A29270 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Defuelling Hazards Review EAN to CDMS | 2023-07-21 | 2023-07-31 | 5 | 0 | 6 | 10 | 100% | 0.5 | 1 | Completed
ER6666LT | W209 | W209.29540 | HYB Essential Defueling Safety Case | Complete HYB R:77 (Deformed Standpipe Liner) EAN and Upload to CDMS | 2023-07-21 | 2023-07-31 | 5 | 0 | 6 | 10 | 100% | 0.5 | 1 | Completed
ER6668LT | W213 | W213.A29270 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Defuelling Hazards Review EAN to CDMS | 2023-07-21 | 2023-07-31 | 5 | 0 | 6 | 10 | 100% | 0.5 | 1 | Completed
ER6668LT | W213 | W213.29540 | TOR Essential Defueling Safety Case | Complete TOR R:77 (Deformed Standpipe Liner) EAN and Upload to CDMS | 2023-07-21 | 2023-07-31 | 5 | 0 | 6 | 10 | 100% | 0.5 | 1 | Completed
W232LT | W232 | W232.A1810 | DNB Enhanced Safety Cases | Key Stakeholders Approval, if requested | 2023-07-24 | 2023-07-25 | 5 | 0 | 1 | 1 | 100% | 5 | 1 | Completed
ER6666LT | W209 | W209.29150 | HYB Essential Defueling Safety Case | Verification | 2023-07-24 | 2023-10-20 | 12 | 0 | 64 | 88 | 100% | 0.13636 | 1 | Completed
ER6372LT | W203 | W203.A3350 | HNB Enhanced Defuelling Safety Cases | Incorporate INA, Station, ED (peer) comments | 2023-07-24 | 2023-07-25 | 3 | 0 | 2 | 1 | 100% | 3 | 1 | Completed
ER6666LT | W209 | W209.A31420 | HYB Essential Defueling Safety Case | Technical Review of Stress Modelling EAN | 2023-07-24 | 2023-08-11 | 10 | 0 | 14 | 18 | 100% | 0.55556 | 1 | Completed
ER6668LT | W213 | W213.29150 | TOR Essential Defueling Safety Case | Verification | 2023-07-24 | 2023-10-20 | 12 | 0 | 63 | 88 | 100% | 0.13636 | 1 | Completed
ER6668LT | W213 | W213.A31420 | TOR Essential Defueling Safety Case | Technical Review of Stress Modelling EAN | 2023-07-24 | 2023-08-11 | 10 | 0 | 14 | 18 | 100% | 0.55556 | 1 | Completed
ER6666LT | W209 | W209.A31370 | HYB Essential Defueling Safety Case | Upload Fuelling Machine Purging Requirements During Defueling to CDMS | 2023-07-24 | 2023-07-28 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6668LT | W213 | W213.A31370 | TOR Essential Defueling Safety Case | Upload Fuelling Machine Purging Requirements During Defueling to CDMS | 2023-07-24 | 2023-07-28 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6372LT | W203 | W203.A3490 | HNB Enhanced Defuelling Safety Cases | Issue agreed work programme to stakeholders & suppliers | 2023-07-24 | 2023-07-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A2450 | HNB Enhanced Defuelling Safety Cases | NSRS approved - Purge and Pressurisation | 2023-07-25 | 2023-07-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3190 | HNB Enhanced Defuelling Safety Cases | Issue final NSRS - <Purge and Pressurisation> | 2023-07-25 | 2023-07-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3200 | HNB Enhanced Defuelling Safety Cases | Station agree NSRS (KDM) - <Purge and Pressurisation> | 2023-07-25 | 2023-07-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3230 | HNB Enhanced Defuelling Safety Cases | Consolidate & issue to stakeholders & suppliers agreed NSRS | 2023-07-25 | 2023-07-26 | 1 | 0 | 1 | 1 | 100% | 1 | 1 | Completed
ER6372LT | W203 | W203.A3370 | HNB Enhanced Defuelling Safety Cases | Key Stakeholders (DA) agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2023-07-25 | 2023-07-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3520 | HNB Enhanced Defuelling Safety Cases | INA agree NSRS - <Purge and Pressurisation> | 2023-07-25 | 2023-07-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1770 | DNB Enhanced Safety Cases | Produce verification file | 2023-07-26 | 2023-07-28 | 2 | 0 | 2 | 2 | 100% | 1 | 1 | Completed
ER6371LT | W202 | W202.A5290 | HRA Reactors Shutdown Essential Safety Cases | Incorporate INSA comments (HRA) | 2023-07-28 | 2023-09-19 | 9 | 0 | 36 | 53 | 100% | 0.16981 | 1 | Completed
ER6661LT | W206 | W206.A5290 | HYA Reactors Shutdown Essential Safety Cases | Incorporate INSA comments (HYA) | 2023-07-28 | 2023-09-19 | 9 | 0 | 36 | 53 | 100% | 0.16981 | 1 | Completed
W232LT | W232 | W232.A4930 | DNB Enhanced Safety Cases | Lessons Learned Workshop 2 - FPU Safety Case Authored | 2023-07-28 | 2023-07-28 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A31380 | HYB Essential Defueling Safety Case | Fuelling Machine Purging Requirements During Defueling Available | 2023-07-28 | 2023-07-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A31380 | TOR Essential Defueling Safety Case | Fuelling Machine Purging Requirements During Defueling Available | 2023-07-28 | 2023-07-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A29280 | HYB Essential Defueling Safety Case | Defuelling Hazards Review EAN Available | 2023-07-31 | 2023-07-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A24610 | HYB Essential Defueling Safety Case | Supplier Update and Issue Human Reliability Baseline Report EAN | 2023-07-31 | 2023-08-23 | 5 | 0 | 18 | 23 | 100% | 0.21739 | 1 | Completed
ER6668LT | W213 | W213.A29280 | TOR Essential Defueling Safety Case | Defuelling Hazards Review EAN Available | 2023-07-31 | 2023-07-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A24610 | TOR Essential Defueling Safety Case | Supplier Update and Issue Human Reliability Baseline Report EAN | 2023-07-31 | 2023-08-23 | 5 | 0 | 18 | 23 | 100% | 0.21739 | 1 | Completed
ER6666LT | W209 | W209.25910 | HYB Essential Defueling Safety Case | Technical Review of Human Reliability Assessment of Unsubstantiated Claims EAN | 2023-07-31 | 2023-09-29 | 6 | 0 | 44 | 60 | 100% | 0.1 | 1 | Completed
ER6668LT | W213 | W213.25910 | TOR Essential Defueling Safety Case | Technical Review of Human Reliability Assessment of Unsubstantiated Claims EAN | 2023-07-31 | 2023-09-29 | 6 | 0 | 44 | 60 | 100% | 0.1 | 1 | Completed
ER6666LT | W209 | W209.A31130 | HYB Essential Defueling Safety Case | Defueling Process Flow Available | 2023-07-31 | 2023-07-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A4160 | HNB Enhanced Defuelling Safety Cases | Draft NSRS complete - IFD Deluge | 2023-07-31 | 2023-07-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A31130 | TOR Essential Defueling Safety Case | Defueling Process Flow Available | 2023-07-31 | 2023-07-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1800 | DNB Enhanced Safety Cases | Issue high quality verified draft issue A with verification file to INSA & station (T - 3 weeks before NSC date) *(KDM)* | 2023-08-02 | 2023-08-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1780 | DNB Enhanced Safety Cases | Verification complete | 2023-08-02 | 2023-08-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1790 | DNB Enhanced Safety Cases | Submit for approval - Categoriser ratifies; RE/CO endorsement | 2023-08-02 | 2023-08-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.7380 | HYB Essential Defueling Safety Case | Update Claim 6 | 2023-08-03 | 2023-11-10 | 19 | 0 | 70 | 99 | 100% | 0.19192 | 1 | Completed
ER6668LT | W213 | W213.7380 | TOR Essential Defueling Safety Case | Update Claim 6 | 2023-08-03 | 2023-11-10 | 19 | 0 | 71 | 99 | 100% | 0.19192 | 1 | Completed
ER6666LT | W209 | W209.28860 | HYB Essential Defueling Safety Case | Verification of PSA following Updates | 2023-08-04 | 2023-12-08 | 5 | 0 | 90 | 126 | 100% | 0.039683 | 1 | Completed
ER6668LT | W213 | W213.28860 | TOR Essential Defueling Safety Case | Verification of PSA following Updates | 2023-08-04 | 2023-12-08 | 5 | 0 | 89 | 126 | 100% | 0.039683 | 1 | Completed
W232LT | W232 | W232.A1820 | DNB Enhanced Safety Cases | INSA review & iteration of comments (using BARRIER MODEL) | 2023-08-04 | 2023-08-08 | 10 | 0 | 2 | 4 | 100% | 2.5 | 1 | Completed
W232LT | W232 | W232.A2870 | DNB Enhanced Safety Cases | Carry out ALARP Review of OEM NSP Removal | 2023-08-07 | 2023-09-25 | 34 | 0 | 34 | 49 | 100% | 0.69388 | 1 | Completed
ER6372LT | W203 | W203.B1060 | HNB Enhanced Defuelling Safety Cases | Verify supporting reference <PSA Updates> | 2023-08-08 | 2023-11-08 | 3 | 0 | 66 | 92 | 100% | 0.032609 | 1 | Completed
W232LT | W232 | W232.A1840 | DNB Enhanced Safety Cases | Incorporate INSA comments | 2023-08-09 | 2023-08-15 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6372LT | W203 | W203.A3280 | HNB Enhanced Defuelling Safety Cases | Verification of the case (using BARRIER MODEL) - <Purge and Pressurisation> | 2023-08-11 | 2023-08-25 | 13 | 0 | 10 | 14 | 100% | 0.92857 | 1 | Completed
ER6372LT | W203 | W203.A3570 | HNB Enhanced Defuelling Safety Cases | Specialist Assessment | 2023-08-11 | 2023-08-25 | 13 | 0 | 10 | 14 | 100% | 0.92857 | 1 | Completed
ER6666LT | W209 | W209.1435 | HYB Essential Defueling Safety Case | Prepare the Safety Case Proposal - Part 1 | 2023-08-14 | 2023-12-22 | 1 | 0 | 93 | 130 | 100% | 0.0076923 | 1 | Completed
ER6666LT | W209 | W209.A31430 | HYB Essential Defueling Safety Case | Supplier Update and Issue Stress Modelling EAN | 2023-08-14 | 2023-08-18 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
ER6668LT | W213 | W213.1435 | TOR Essential Defueling Safety Case | Prepare the Safety Case Proposal - Part 1 | 2023-08-14 | 2023-12-22 | 1 | 0 | 93 | 130 | 100% | 0.0076923 | 1 | Completed
ER6668LT | W213 | W213.A31430 | TOR Essential Defueling Safety Case | Supplier Update and Issue Stress Modelling EAN | 2023-08-14 | 2023-08-18 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
W232LT | W232 | W232.A1870 | DNB Enhanced Safety Cases | INSA Final Approval *(KDM)* | 2023-08-16 | 2023-08-17 | 5 | 0 | 2 | 1 | 100% | 5 | 1 | Completed
ER6372LT | W203 | W203.A3680 | HNB Enhanced Defuelling Safety Cases | Station comments on NSRS | 2023-08-18 | 2023-08-24 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6372LT | W203 | W203.A3690 | HNB Enhanced Defuelling Safety Cases | Key Stakeholders (Peer) comments on NSRS | 2023-08-18 | 2023-08-24 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
W232LT | W232 | W232.A4940 | DNB Enhanced Safety Cases | Lessons Learned Workshop 3 - FPU Safety Case Verified | 2023-08-18 | 2023-08-18 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3270 | HNB Enhanced Defuelling Safety Cases | Produce verification plan | 2023-08-19 | 2023-08-20 | 2 | 0 | 0 | 1 | 100% | 2 | 1 | Completed
ER6666LT | W209 | W209.A31440 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Stress Modelling EAN to CDMS | 2023-08-21 | 2023-08-25 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6668LT | W213 | W213.A31440 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Stress Modelling EAN to CDMS | 2023-08-21 | 2023-08-25 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
W232LT | W232 | W232.A2600 | DNB Enhanced Safety Cases | Assess Results of Lift Lower Trials | 2023-08-21 | 2023-08-25 | 9 | 0 | 4 | 4 | 100% | 2.25 | 1 | Completed
W232LT | W232 | W232.B6610 | DNB Enhanced Safety Cases | Core Support Plate Structural Integrity Criticality - TSA Internal Review of Draft EAN | 2023-08-22 | 2023-09-04 | 5 | 0 | 8 | 13 | 100% | 0.38462 | 1 | Completed
ER6372LT | W203 | W203.A4020 | HNB Enhanced Defuelling Safety Cases | INA comments on NSRS | 2023-08-24 | 2023-11-03 | 5 | 0 | 51 | 71 | 100% | 0.070423 | 1 | Completed
ER6666LT | W209 | W209.A24620 | HYB Essential Defueling Safety Case | Complete Review of Human Reliability Baseline Report EAN to CDMS | 2023-08-24 | 2023-08-31 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6668LT | W213 | W213.A24620 | TOR Essential Defueling Safety Case | Complete Review of Human Reliability Baseline Report EAN to CDMS | 2023-08-24 | 2023-08-31 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6372LT | W203 | W203.A3460 | HNB Enhanced Defuelling Safety Cases | Issue to CO & Station for comments - <Purge and Pressurisation> | 2023-08-25 | 2023-08-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A31450 | HYB Essential Defueling Safety Case | Stress Modelling EAN Available | 2023-08-25 | 2023-08-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A31450 | TOR Essential Defueling Safety Case | Stress Modelling EAN Available | 2023-08-25 | 2023-08-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3260 | HNB Enhanced Defuelling Safety Cases | Incorporate CO & Station comments | 2023-08-28 | 2023-08-29 | 1 | 0 | 1 | 1 | 100% | 1 | 1 | Completed
ER6372LT | W203 | W203.A3290 | HNB Enhanced Defuelling Safety Cases | Produce verification file | 2023-08-29 | 2023-08-29 | 2 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3300 | HNB Enhanced Defuelling Safety Cases | Issue high quality verified draft issue A with verification file to INSA & station (KDM) - <Purge and Pressurisation> | 2023-08-29 | 2023-08-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3310 | HNB Enhanced Defuelling Safety Cases | INSA review & iteration of comments (using BARRIER MODEL) | 2023-08-29 | 2023-09-12 | 10 | 0 | 11 | 14 | 100% | 0.71429 | 1 | Completed
ER6372LT | W203 | W203.A3410 | HNB Enhanced Defuelling Safety Cases | Verification complete | 2023-08-29 | 2023-08-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3420 | HNB Enhanced Defuelling Safety Cases | Submit for approval - Categoriser ratifies; RE/CO endorsement | 2023-08-29 | 2023-08-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3430 | HNB Enhanced Defuelling Safety Cases | Key Stakeholders Approval, if requested | 2023-08-29 | 2023-09-05 | 5 | 0 | 6 | 7 | 100% | 0.71429 | 1 | Completed
ER6666LT | W209 | W209.A31280 | HYB Essential Defueling Safety Case | Verify PSA Documentation & Issue for Technical Review | 2023-08-29 | 2024-06-03 | 31 | 0 | 193 | 279 | 100% | 0.11111 | 1 | Completed
ER6668LT | W213 | W213.A31280 | TOR Essential Defueling Safety Case | Verify PSA Documentation & Issue for Technical Review | 2023-08-29 | 2024-06-03 | 31 | 0 | 193 | 279 | 100% | 0.11111 | 1 | Completed
ER6666LT | W209 | W209.9030 | HYB Essential Defueling Safety Case | Discovery Milestone - Human Reliability Baseline Report - EAN Available | 2023-08-31 | 2023-08-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.9030 | TOR Essential Defueling Safety Case | Discovery Milestone - Human Reliability Baseline Report - EAN Available | 2023-08-31 | 2023-08-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A24630 | HYB Essential Defueling Safety Case | Human Reliability Baseline Report EAN Available | 2023-08-31 | 2023-08-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A24630 | TOR Essential Defueling Safety Case | Human Reliability Baseline Report EAN Available | 2023-08-31 | 2023-08-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1880 | DNB Enhanced Safety Cases | Station Approval for mod implementation (including station review meeting) | 2023-09-01 | 2023-09-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.7970 | HYB Essential Defueling Safety Case | Draft Human Factors Integration Plan EAN (REV 001) | 2023-09-04 | 2023-10-13 | 10 | 0 | 30 | 39 | 100% | 0.25641 | 1 | Completed
ER6668LT | W213 | W213.7970 | TOR Essential Defueling Safety Case | Draft Human Factors Integration Plan EAN (REV 001) | 2023-09-04 | 2023-10-13 | 10 | 0 | 29 | 39 | 100% | 0.25641 | 1 | Completed
W232LT | W232 | W232.B6550 | DNB Enhanced Safety Cases | Core Support Plate Structural Integrity Criticality - Issue Draft EAN to EDF for Review. | 2023-09-04 | 2023-09-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6560 | DNB Enhanced Safety Cases | Core Support Plate Structural Integrity Criticality - Draft EAN Reviewed by EDF SQEP | 2023-09-05 | 2023-09-18 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6650LT | W226 | 001955a | HYA Fuel Handling Essential Safety Case | Claim 5 Updates - Needs FDD | 2023-09-05 | 2023-09-21 | 15 | 0 | 12 | 16 | 100% | 0.9375 | 1 | Completed
W232LT | W232 | W232.A1900 | DNB Enhanced Safety Cases | Station Approval Obtained and CAT 2 Safety Case Complete *(KDM)* | 2023-09-07 | 2023-09-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2610 | DNB Enhanced Safety Cases | Define Benefits and Objectives of Cold Defuelling | 2023-09-11 | 2023-09-25 | 15 | 0 | 10 | 14 | 100% | 1.0714 | 1 | Completed
ER6372LT | W203 | W203.A3470 | HNB Enhanced Defuelling Safety Cases | Incorporate INSA comments | 2023-09-13 | 2023-09-29 | 1 | 0 | 12 | 16 | 100% | 0.0625 | 1 | Completed
ER6666LT | W209 | W209.A27410 | HYB Essential Defueling Safety Case | Technical Review of Fuel Route PSA Update EAN | 2023-09-18 | 2023-12-22 | 15 | 0 | 70 | 95 | 100% | 0.15789 | 1 | Completed
ER6668LT | W213 | W213.A27410 | TOR Essential Defueling Safety Case | Technical Review of Fuel Route PSA Update EAN | 2023-09-18 | 2023-12-22 | 15 | 0 | 69 | 95 | 100% | 0.15789 | 1 | Completed
ER6666LT | W209 | W209.28940 | HYB Essential Defueling Safety Case | Update Claim 3 | 2023-09-18 | 2023-11-13 | 5 | 0 | 40 | 56 | 100% | 0.089286 | 1 | Completed
ER6668LT | W213 | W213.28940 | TOR Essential Defueling Safety Case | Update Claim 3 | 2023-09-18 | 2023-11-13 | 5 | 0 | 41 | 56 | 100% | 0.089286 | 1 | Completed
ER6666LT | W209 | W209.7710 | HYB Essential Defueling Safety Case | Early INA Review Claim 1 | 2023-09-19 | 2023-11-29 | 20 | 0 | 51 | 71 | 100% | 0.28169 | 1 | Completed
ER6668LT | W213 | W213.7710 | TOR Essential Defueling Safety Case | INSA Pre Review Claim 1 | 2023-09-19 | 2023-11-29 | 20 | 0 | 51 | 71 | 100% | 0.28169 | 1 | Completed
W232LT | W232 | W232.B6570 | DNB Enhanced Safety Cases | Core Support Plate Structural Integrity Criticality - Address Comments from EDF Review on Draft EAN | 2023-09-19 | 2023-09-22 | 10 | 0 | 3 | 3 | 100% | 3.3333 | 1 | Completed
W232LT | W232 | W232.B6580 | DNB Enhanced Safety Cases | Core Support Plate Structural Integrity Criticality - Issue Final EAN | 2023-09-22 | 2023-09-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6590 | DNB Enhanced Safety Cases | Core Support Plate Structural Integrity Criticality - EAN Completed and Uploaded to CDMS | 2023-09-22 | 2023-09-25 | 10 | 0 | 1 | 3 | 100% | 3.3333 | 1 | Completed
ER6650LT | W226 | 001955b | HYA Fuel Handling Essential Safety Case | Claim 6 Updates - ALARP | 2023-09-22 | 2023-11-07 | 4 | 0 | 33 | 46 | 100% | 0.086957 | 1 | Completed
W232LT | W232 | W232.B6600 | DNB Enhanced Safety Cases | Core Support Plate Structural Integrity Criticality - EAN Completed | 2023-09-25 | 2023-09-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.29180 | HYB Essential Defueling Safety Case | Produce new Defuelling SSR text | 2023-09-25 | 2023-12-08 | 20 | 0 | 55 | 74 | 100% | 0.27027 | 1 | Completed
ER6668LT | W213 | W213.29180 | TOR Essential Defueling Safety Case | Produce new Defuelling SSR text | 2023-09-25 | 2023-12-08 | 20 | 0 | 55 | 74 | 100% | 0.27027 | 1 | Completed
W232LT | W232 | W232.A2880 | DNB Enhanced Safety Cases | Discovery Milestone - Warm Extraction Acceptable Y/N | 2023-09-25 | 2023-11-01 | 15 | 0 | 28 | 37 | 100% | 0.40541 | 1 | Completed
ER6666LT | W209 | W209.5360 | HYB Essential Defueling Safety Case | CLAIM 1 - Sub Critical Margin (SCM) | 2023-09-28 | 2023-09-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.6960 | HYB Essential Defueling Safety Case | Claim 1 Ready | 2023-09-28 | 2023-09-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.5360 | TOR Essential Defueling Safety Case | CLAIM 1 - Sub Critical Margin (SCM) | 2023-09-28 | 2023-09-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.6960 | TOR Essential Defueling Safety Case | Claim 1 Ready | 2023-09-28 | 2023-09-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A2650 | HNB Enhanced Defuelling Safety Cases | >>>OUTGOING ENABLER (W104, W153) Reactor S/D Enhanced INSA Finally Approved | 2023-09-29 | 2023-09-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.25920 | HYB Essential Defueling Safety Case | Supplier Update and Issue Human Reliability Assessment of Unsubstantiated Claims EAN | 2023-09-29 | 2023-10-06 | 5 | 0 | 6 | 7 | 100% | 0.71429 | 1 | Completed
ER6372LT | W203 | W203.A3500 | HNB Enhanced Defuelling Safety Cases | INSA Final Approval (KDM) - <Purge and Pressurisation> | 2023-09-29 | 2023-09-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.25920 | TOR Essential Defueling Safety Case | Supplier Update and Issue Human Reliability Assessment of Unsubstantiated Claims EAN | 2023-09-29 | 2023-10-06 | 5 | 0 | 6 | 7 | 100% | 0.71429 | 1 | Completed
W232LT | W232 | W232.A2620 | DNB Enhanced Safety Cases | Review Output from the Discovery Milestones | 2023-10-02 | 2023-10-13 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
W232LT | W232 | W232.A2920 | DNB Enhanced Safety Cases | Discovery Milestone: Core Support Plate Structural Integrity Criticality | 2023-10-02 | 2023-10-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2560 | DNB Enhanced Safety Cases | TOG sentences CSP strategy | 2023-10-02 | 2023-10-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1910 | DNB Enhanced Safety Cases | Post Job Debrief | 2023-10-04 | 2023-10-04 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.28910 | HYB Essential Defueling Safety Case | Discovery Milestone - Review need for any Post Fault Actions | 2023-10-05 | 2023-10-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.28910 | TOR Essential Defueling Safety Case | Discovery Milestone - Review need for any Post Fault Actions | 2023-10-05 | 2023-10-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2150 | DNB Enhanced Safety Cases | Mod requested, Initiate EC, identify RE, register EC & identify milestones in AMS | 2023-10-05 | 2023-10-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2220 | DNB Enhanced Safety Cases | Raise Engineering Request (as required) | 2023-10-05 | 2023-10-11 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.A28310 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Fault Definition Document (FDD) EAN to CDMS | 2023-10-06 | 2023-10-10 | 5 | 0 | 2 | 4 | 100% | 1.25 | 1 | Completed
ER6666LT | W209 | W209.25930 | HYB Essential Defueling Safety Case | Complete Review of Human Reliability Assessment of Unsubstantiated Claims EAN to CDMS | 2023-10-06 | 2023-10-06 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.25940 | HYB Essential Defueling Safety Case | Human Reliability Assessment of Unsubstantiated Claims EAN Available | 2023-10-06 | 2023-10-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.25930 | TOR Essential Defueling Safety Case | Complete Review of Human Reliability Assessment of Unsubstantiated Claims EAN to CDMS | 2023-10-06 | 2023-10-06 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.25940 | TOR Essential Defueling Safety Case | Human Reliability Assessment of Unsubstantiated Claims EAN Available | 2023-10-06 | 2023-10-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A28310 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Fault Definition Document (FDD) EAN to CDMS | 2023-10-06 | 2023-10-10 | 5 | 0 | 2 | 4 | 100% | 1.25 | 1 | Completed
ER6371LT | W202 | 1630 | HRA Reactors Shutdown Essential Safety Cases | Upload Fault Definition Document to AMS | 2023-10-09 | 2023-10-11 | 1 | 0 | 2 | 2 | 100% | 0.5 | 1 | Completed
ER6661LT | W206 | 1630 | HYA Reactors Shutdown Essential Safety Cases | Upload Fault Definition Document to AMS | 2023-10-09 | 2023-10-11 | 1 | 0 | 2 | 2 | 100% | 0.5 | 1 | Completed
ER6378LT | W222 | W222.A25270 | HRA Fuel Handling Essential Safety Case | Reauthor FDD in Report REP (REV 000) & approve on AMS (EVENT RECOVERY 1630) | 2023-10-09 | 2023-10-11 | 1 | 0 | 2 | 2 | 100% | 0.5 | 1 | Completed
ER6650LT | W226 | W226.A25270 | HYA Fuel Handling Essential Safety Case | Reauthor FDD in Report REP (REV 000) & approve on AMS (EVENT RECOVERY 1630) | 2023-10-09 | 2023-10-11 | 1 | 0 | 2 | 2 | 100% | 0.5 | 1 | Completed
ER6666LT | W209 | W209.A28320 | HYB Essential Defueling Safety Case | Fault Definition Document (FDD) EAN Available | 2023-10-10 | 2023-10-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | 1940 | HRA Reactors Shutdown Essential Safety Cases | Updated All technical references for SC's | 2023-10-10 | 2023-12-22 | 1 | 0 | 53 | 73 | 100% | 0.013699 | 1 | Completed
ER6661LT | W206 | 1940 | HYA Reactors Shutdown Essential Safety Cases | Updated All technical references for SC's | 2023-10-10 | 2023-12-22 | 1 | 0 | 53 | 73 | 100% | 0.013699 | 1 | Completed
W232LT | W232 | W232.A2430 | DNB Enhanced Safety Cases | CO & CA appointed | 2023-10-11 | 2023-10-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2440 | DNB Enhanced Safety Cases | Key Stakeholders Identified | 2023-10-11 | 2023-10-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.3070 | HRA Fuel Handling Essential Safety Case | FDD Post Job Debrief & Lessons Learnt | 2023-10-12 | 2023-10-12 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A27465 | HRA Fuel Handling Essential Safety Case | FDD Lessons Learnt Complete | 2023-10-12 | 2023-10-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27465 | HYA Fuel Handling Essential Safety Case | FDD Lessons Learnt Complete | 2023-10-12 | 2023-10-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.3070 | HYA Fuel Handling Essential Safety Case | FDD Post Job Debrief & Lessons Learnt | 2023-10-12 | 2023-10-12 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2210 | DNB Enhanced Safety Cases | Develop initial programme plan using mandatory template | 2023-10-12 | 2023-10-18 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.A28320 | TOR Essential Defueling Safety Case | Fault Definition Document (FDD) EAN Available | 2023-10-12 | 2023-10-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3440 | HNB Enhanced Defuelling Safety Cases | Station approval for mod implementation (including station review meeting) | 2023-10-13 | 2023-10-13 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3580 | HNB Enhanced Defuelling Safety Cases | Station Approval Obtained and CAT 2 Safety Case Complete *(KDM)* (FEEDS TO SUMMARY SCHEDULE) | 2023-10-13 | 2023-10-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1980 | DNB Enhanced Safety Cases | Produce Draft NSRS (using BARRIER MODEL) | 2023-10-16 | 2023-12-07 | 39 | 0 | 38 | 52 | 100% | 0.75 | 1 | Completed
ER6668LT | W213 | W213.7270 | TOR Essential Defueling Safety Case | Case Officer Tech Lead Review Claim 4 | 2023-10-16 | 2023-10-19 | 5 | 0 | 3 | 3 | 100% | 1.6667 | 1 | Completed
ER6666LT | W209 | W209.7270 | HYB Essential Defueling Safety Case | Case Officer Tech Lead Review Claim 4 | 2023-10-16 | 2023-10-19 | 5 | 0 | 3 | 3 | 100% | 1.6667 | 1 | Completed
ER6666LT | W209 | W209.7980 | HYB Essential Defueling Safety Case | Verify Human Factors Integration Plan EAN and Issue for Technical Review (REV 001) | 2023-10-16 | 2023-11-06 | 12 | 0 | 16 | 21 | 100% | 0.57143 | 1 | Completed
W232LT | W232 | W232.A2630 | DNB Enhanced Safety Cases | Prepare Decision Paper | 2023-10-16 | 2023-10-27 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6668LT | W213 | W213.7980 | TOR Essential Defueling Safety Case | Verify Human Factors Integration Plan EAN and Issue for Technical Review (REV 001) | 2023-10-16 | 2023-11-06 | 12 | 0 | 16 | 21 | 100% | 0.57143 | 1 | Completed
W232LT | W232 | W232.A2450 | DNB Enhanced Safety Cases | CA PJB Held | 2023-10-18 | 2023-10-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A4980 | DNB Enhanced Safety Cases | Discovery Milestone: Cat 2 Case Feasible- go/no go | 2023-10-18 | 2023-10-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6760 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Re-entrant Seal Stiction - Summary | 2023-10-19 | 2023-10-19 | 14 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6770 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Re-entrant Seal Stiction - Approve Task Sheet | 2023-10-19 | 2023-10-19 | 2 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6790 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Re-entrant Seal Stiction - Draft and issue Task Sheet | 2023-10-19 | 2023-10-19 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1970 | DNB Enhanced Safety Cases | Produce MF (as required) | 2023-10-19 | 2023-10-25 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
W232LT | W232 | W232.B6750 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Re-entrant Seal Stiction - Summary | 2023-10-19 | 2023-10-19 | 22 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6780 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Re-entrant Seal Stiction - Pre Job Brief | 2023-10-19 | 2023-10-19 | 2 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6800 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727> Re-entrant Seal Stiction - Prepare Draft EAN | 2023-10-19 | 2023-10-19 | 20 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6820 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727>Re-entrant Seal Stiction - Draft EAN Reviewed by EDF SQEP | 2023-10-19 | 2023-10-19 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6830 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727>Re-entrant Seal Stiction - Address Comments from EDF Review on Draft EAN | 2023-10-19 | 2023-10-19 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6850 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727>Re-entrant Seal Stiction - EAN Completed and Uploaded to CDMS | 2023-10-19 | 2023-10-19 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6870 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727>Re-entrant Seal Stiction - TSA Internal Review of Draft EAN | 2023-10-19 | 2023-10-19 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6810 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727>Re-entrant Seal Stiction - Issue Draft EAN to EDF for Review. | 2023-10-19 | 2023-10-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6840 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727>Re-entrant Seal Stiction - Issue Final EAN | 2023-10-19 | 2023-10-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B6860 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727>Re-entrant Seal Stiction - EAN Completed (FEED TOS UMMARY SCHEDULE) | 2023-10-19 | 2023-10-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2940 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 1727>Discovery Milestone: Re-entrant Seal Stiction | 2023-10-19 | 2023-10-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.7280 | HYB Essential Defueling Safety Case | Verification of Claim 4 | 2023-10-20 | 2023-12-01 | 5 | 0 | 31 | 42 | 100% | 0.11905 | 1 | Completed
ER6666LT | W209 | W209.7290 | HYB Essential Defueling Safety Case | Update Claim 4 | 2023-10-20 | 2023-12-20 | 8 | 0 | 43 | 61 | 100% | 0.13115 | 1 | Completed
ER6668LT | W213 | W213.7280 | TOR Essential Defueling Safety Case | Verification of Claim 4 | 2023-10-20 | 2023-12-01 | 10 | 0 | 31 | 42 | 100% | 0.2381 | 1 | Completed
ER6668LT | W213 | W213.7290 | TOR Essential Defueling Safety Case | Update Claim 4 | 2023-10-20 | 2023-12-20 | 4 | 0 | 43 | 61 | 100% | 0.065574 | 1 | Completed
ER6650LT | W226 | 001955d | HYA Fuel Handling Essential Safety Case | Claim 2 Updates - H&I PSA Worker Risk | 2023-10-20 | 2023-11-16 | 4 | 0 | 20 | 27 | 100% | 0.14815 | 1 | Completed
ER6668LT | W213 | W213.29160 | TOR Essential Defueling Safety Case | Technical Review | 2023-10-23 | 2023-11-27 | 10 | 0 | 25 | 35 | 100% | 0.28571 | 1 | Completed
ER6666LT | W209 | W209.29160 | HYB Essential Defueling Safety Case | Technical Review | 2023-10-23 | 2023-11-27 | 7 | 0 | 26 | 35 | 100% | 0.2 | 1 | Completed
W232LT | W232 | W232.A4950 | DNB Enhanced Safety Cases | Lessons Learned Workshop 1 - TOG Learning | 2023-10-25 | 2023-10-25 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2160 | DNB Enhanced Safety Cases | Issue MF (as required) | 2023-10-25 | 2023-10-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2270 | DNB Enhanced Safety Cases | Categorisation by RE / Station | 2023-10-26 | 2023-11-01 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
W232LT | W232 | W232.A2300 | DNB Enhanced Safety Cases | Identify verifier for the case & establish all other resources | 2023-10-26 | 2023-11-01 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6650LT | W226 | 001955e | HYA Fuel Handling Essential Safety Case | Claim 4 Updates - Refuelling Cooling | 2023-10-26 | 2023-11-16 | 4 | 0 | 15 | 21 | 100% | 0.19048 | 1 | Completed
ER6666LT | W209 | W209.5370 | HYB Essential Defueling Safety Case | CLAIM 2 - Shutdown and Fuel Handling Cooling | 2023-10-27 | 2023-10-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.5370 | TOR Essential Defueling Safety Case | CLAIM 2 - Shutdown and Fuel Handling Cooling | 2023-10-27 | 2023-10-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.7050 | TOR Essential Defueling Safety Case | Claim 2 Ready | 2023-10-27 | 2023-10-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3560 | HNB Enhanced Defuelling Safety Cases | Post Job Debrief | 2023-10-27 | 2023-10-27 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 001955f | HYA Fuel Handling Essential Safety Case | Claim 3 - No updates Required | 2023-10-27 | 2023-10-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.7050 | HYB Essential Defueling Safety Case | Claim 2 Ready | 2023-10-27 | 2023-10-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.7720 | TOR Essential Defueling Safety Case | INSA Pre Review Claim 2 | 2023-10-30 | 2023-12-21 | 20 | 0 | 38 | 52 | 100% | 0.38462 | 1 | Completed
ER6666LT | W209 | W209.7720 | HYB Essential Defueling Safety Case | Early INA Review Claim 2 | 2023-10-30 | 2023-12-21 | 20 | 0 | 38 | 52 | 100% | 0.38462 | 1 | Completed
W232LT | W232 | W232.A2640 | DNB Enhanced Safety Cases | Obtain Agreement from Programme Board | 2023-10-30 | 2023-12-14 | 10 | 0 | 34 | 45 | 100% | 0.22222 | 1 | Completed
ER6371LT | W202 | W202.B5540 | HRA Reactors Shutdown Essential Safety Cases | Reactor Case INSA held for FH Case INSA | 2023-10-31 | 2023-10-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.B5540 | HYA Reactors Shutdown Essential Safety Cases | Reactor Case INSA held for FH Case INSA | 2023-10-31 | 2023-10-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A25660 | HRA Fuel Handling Essential Safety Case | Worker Risk Assessment Updates (REV 001) (EVENT RECOVERY 2000f) | 2023-11-01 | 2023-11-02 | 22 | 0 | 1 | 1 | 100% | 22 | 1 | Completed
ER6650LT | W226 | W226.A25660 | HYA Fuel Handling Essential Safety Case | Worker Risk Assessment Updates (REV 001) (EVENT RECOVERY 2000f) | 2023-11-01 | 2023-11-02 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
W232LT | W232 | W232.A2170 | DNB Enhanced Safety Cases | INSA agree MF (as required) *(KDM)* | 2023-11-02 | 2023-11-03 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
W232LT | W232 | W232.A2400 | DNB Enhanced Safety Cases | INSA Approval Date Identified | 2023-11-03 | 2023-11-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2410 | DNB Enhanced Safety Cases | Provide Provisional NSC Date (as required) | 2023-11-03 | 2023-11-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3860 | HNB Enhanced Defuelling Safety Cases | Incorporate INA, Station, ED (peer) comments | 2023-11-06 | 2023-11-10 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6666LT | W209 | W209.28840 | HYB Essential Defueling Safety Case | Technical Review of Human Factors Integration Plan EAN (REV 001) | 2023-11-07 | 2024-01-17 | 10 | 0 | 49 | 71 | 100% | 0.14085 | 1 | Completed
ER6668LT | W213 | W213.28840 | TOR Essential Defueling Safety Case | Technical Review of Human Factors Integration Plan EAN (REV 001) | 2023-11-07 | 2024-01-17 | 10 | 0 | 49 | 71 | 100% | 0.14085 | 1 | Completed
ER6650LT | W226 | 001955c | HYA Fuel Handling Essential Safety Case | Claim 1 Updates - Defuelling Process Specification | 2023-11-08 | 2023-11-16 | 3 | 0 | 6 | 8 | 100% | 0.375 | 1 | Completed
ER6372LT | W203 | W203.B1050 | HNB Enhanced Defuelling Safety Cases | BE Technical review of supporting reference <PSA Updates> | 2023-11-09 | 2023-11-14 | 4 | 0 | 4 | 5 | 100% | 0.8 | 1 | Completed
ER6666LT | W209 | W209.5410 | HYB Essential Defueling Safety Case | CLAIM 6 - Configuration Control | 2023-11-10 | 2023-11-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.7410 | HYB Essential Defueling Safety Case | Claim 6 Ready | 2023-11-10 | 2023-11-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.7760 | HYB Essential Defueling Safety Case | Early INA Review Claim 6 | 2023-11-10 | 2023-11-10 | 20 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.5410 | TOR Essential Defueling Safety Case | CLAIM 6 - Configuration Control | 2023-11-10 | 2023-11-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.7760 | TOR Essential Defueling Safety Case | INSA Pre Review Claim 6 | 2023-11-10 | 2023-11-10 | 20 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3700 | HNB Enhanced Defuelling Safety Cases | Issue final NSRS | 2023-11-10 | 2023-11-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.7410 | TOR Essential Defueling Safety Case | Claim 6 Ready | 2023-11-10 | 2023-11-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.5380 | HYB Essential Defueling Safety Case | CLAIM 3 - Containment and Structural Integrity | 2023-11-13 | 2023-11-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.7140 | HYB Essential Defueling Safety Case | Claim 3 Ready | 2023-11-13 | 2023-11-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A4170 | HNB Enhanced Defuelling Safety Cases | NSRS approved - IFD Deluge | 2023-11-13 | 2023-11-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.5380 | TOR Essential Defueling Safety Case | CLAIM 3 - Containment and Structural Integrity | 2023-11-13 | 2023-11-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 001955g | HYA Fuel Handling Essential Safety Case | Head Document Formatting Checks | 2023-11-13 | 2023-11-21 | 2 | 0 | 7 | 8 | 100% | 0.25 | 1 | Completed
ER6372LT | W203 | W203.A3710 | HNB Enhanced Defuelling Safety Cases | Station agree NSRS (KDM) - <IFD Deluge> | 2023-11-13 | 2023-11-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3880 | HNB Enhanced Defuelling Safety Cases | Key Stakeholders (DA) agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2023-11-13 | 2023-11-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A4030 | HNB Enhanced Defuelling Safety Cases | INA agree NSRS | 2023-11-13 | 2023-11-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.7140 | TOR Essential Defueling Safety Case | Claim 3 Ready | 2023-11-13 | 2023-11-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.7730 | HYB Essential Defueling Safety Case | Early INA Review Claim 3 | 2023-11-14 | 2024-01-24 | 20 | 0 | 48 | 71 | 100% | 0.28169 | 1 | Completed
ER6372LT | W203 | W203.A4180 | HNB Enhanced Defuelling Safety Cases | All key supporting technical references complete <RESUMED 01.03.2023> - IFD Deluge | 2023-11-14 | 2023-11-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3740 | HNB Enhanced Defuelling Safety Cases | Consolidate & issue to stakeholders & suppliers agreed NSRS | 2023-11-14 | 2023-11-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.7730 | TOR Essential Defueling Safety Case | Early INA Review Claim 3 | 2023-11-14 | 2024-01-24 | 20 | 0 | 49 | 71 | 100% | 0.28169 | 1 | Completed
ER6372LT | W203 | W203.A4150 | HNB Enhanced Defuelling Safety Cases | All supporting references completed | 2023-11-14 | 2023-11-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.B1040 | HNB Enhanced Defuelling Safety Cases | Supporting reference <PSA Updates> approved | 2023-11-14 | 2023-11-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3750 | HNB Enhanced Defuelling Safety Cases | CA to agree with CO format of the safety case & produce agreed contents page | 2023-11-15 | 2023-11-16 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6666LT | W209 | W209.A29080 | HYB Essential Defueling Safety Case | Verify Defuelling Handling Deterministic Assessment EAN & Issue for Technical Review | 2023-11-17 | 2024-01-19 | 5 | 0 | 43 | 63 | 100% | 0.079365 | 1 | Completed
ER6668LT | W213 | W213.A29080 | TOR Essential Defueling Safety Case | Verify Defuelling Handling Deterministic Assessment EAN & Issue for Technical Review | 2023-11-17 | 2024-01-19 | 5 | 0 | 43 | 63 | 100% | 0.079365 | 1 | Completed
ER6372LT | W203 | W203.A3780 | HNB Enhanced Defuelling Safety Cases | Produce verification plan | 2023-11-17 | 2023-11-20 | 2 | 0 | 2 | 3 | 100% | 0.66667 | 1 | Completed
ER6650LT | W226 | 1956 | HYA Fuel Handling Essential Safety Case | Verification Pre Job Brief (Head Document) | 2023-11-20 | 2023-11-20 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3790 | HNB Enhanced Defuelling Safety Cases | Verification of the case (using BARRIER MODEL) | 2023-11-21 | 2023-12-04 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6372LT | W203 | W203.A4080 | HNB Enhanced Defuelling Safety Cases | Specialist Assessment | 2023-11-21 | 2023-12-04 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6378LT | W222 | 001962a | HRA Fuel Handling Essential Safety Case | Station RE Verification | 2023-11-22 | 2023-12-28 | 13 | 0 | 24 | 36 | 100% | 0.36111 | 1 | Completed
ER6378LT | W222 | 1963 | HRA Fuel Handling Essential Safety Case | Sub Verifiers First Round Comments | 2023-11-22 | 2023-12-20 | 13 | 0 | 21 | 28 | 100% | 0.46429 | 1 | Completed
ER6378LT | W222 | 1962 | HRA Fuel Handling Essential Safety Case | Station RE Verification | 2023-11-22 | 2023-11-27 | 13 | 0 | 4 | 5 | 100% | 2.6 | 1 | Completed
ER6378LT | W222 | 1961 | HRA Fuel Handling Essential Safety Case | Lead Verifier and Detail checkers first Round comments | 2023-11-22 | 2023-12-17 | 13 | 0 | 25 | 25 | 100% | 0.52 | 1 | Completed
ER6378LT | W222 | 1960 | HRA Fuel Handling Essential Safety Case | Verification of Head Document | 2023-11-22 | 2024-03-21 | 25 | 0 | 80 | 120 | 100% | 0.20833 | 1 | Completed
ER6650LT | W226 | 001962a | HYA Fuel Handling Essential Safety Case | Station RE Verification Grant | 2023-11-22 | 2023-12-28 | 13 | 0 | 24 | 36 | 100% | 0.36111 | 1 | Completed
ER6650LT | W226 | 1963 | HYA Fuel Handling Essential Safety Case | Sub Verifiers First Round Comments Grant | 2023-11-22 | 2023-12-20 | 13 | 0 | 21 | 28 | 100% | 0.46429 | 1 | Completed
ER6650LT | W226 | 1962 | HYA Fuel Handling Essential Safety Case | Station RE Verification Grant | 2023-11-22 | 2023-11-27 | 13 | 0 | 4 | 5 | 100% | 2.6 | 1 | Completed
ER6650LT | W226 | 1961 | HYA Fuel Handling Essential Safety Case | Lead Verifier and Detail checkers first Round comments Grant | 2023-11-22 | 2023-12-17 | 13 | 0 | 25 | 25 | 100% | 0.52 | 1 | Completed
ER6650LT | W226 | 001955h | HYA Fuel Handling Essential Safety Case | Cross Referencing Checks | 2023-11-22 | 2023-11-22 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 1960 | HYA Fuel Handling Essential Safety Case | Verification of Head Document Grant | 2023-11-22 | 2024-02-22 | 25 | 0 | 60 | 92 | 100% | 0.27174 | 1 | Completed
ER6668LT | W213 | W213.29170 | TOR Essential Defueling Safety Case | Upload to CDMS | 2023-11-28 | 2023-12-22 | 12 | 0 | 18 | 24 | 100% | 0.5 | 1 | Completed
ER6666LT | W209 | W209.29170 | HYB Essential Defueling Safety Case | Upload to CDMS | 2023-11-28 | 2023-12-22 | 5 | 0 | 19 | 24 | 100% | 0.20833 | 1 | Completed
W520LT | W520 | W520.A1260 | FLEETWIDE CTO Defueling Safety Case Delivery | ETC (DD-PF) 2023 | 2023-12-01 | 2023-12-22 | 16 | 0 | 15 | 21 | 100% | 0.7619 | 1 | Completed
ER6666LT | W209 | W209.7450 | HYB Essential Defueling Safety Case | Case Officer Tech Lead Review Claim 7 | 2023-12-01 | 2024-01-17 | 5 | 0 | 31 | 47 | 100% | 0.10638 | 1 | Completed
ER6668LT | W213 | W213.7450 | TOR Essential Defueling Safety Case | Case Officer Tech Lead Review Claim 7 | 2023-12-01 | 2024-01-17 | 5 | 0 | 31 | 47 | 100% | 0.10638 | 1 | Completed
ER6372LT | W203 | W203.A3800 | HNB Enhanced Defuelling Safety Cases | Produce verification file | 2023-12-05 | 2023-12-06 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6372LT | W203 | W203.A3970 | HNB Enhanced Defuelling Safety Cases | Issue to CO & Station for comments | 2023-12-06 | 2023-12-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3770 | HNB Enhanced Defuelling Safety Cases | Incorporate CO & Station comments | 2023-12-07 | 2023-12-11 | 4 | 0 | 2 | 4 | 100% | 1 | 1 | Completed
ER6372LT | W203 | W203.A3940 | HNB Enhanced Defuelling Safety Cases | Key Stakeholders Approval, if requested | 2023-12-07 | 2023-12-11 | 5 | 0 | 2 | 4 | 100% | 1.25 | 1 | Completed
W232LT | W232 | W232.A2980 | DNB Enhanced Safety Cases | Produce Draft NSRS Complete | 2023-12-07 | 2023-12-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3810 | HNB Enhanced Defuelling Safety Cases | Issue high quality verified draft issue A with verification file to INSA & station (KDM) - <IFD Deluge> | 2023-12-11 | 2023-12-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3920 | HNB Enhanced Defuelling Safety Cases | Verification complete | 2023-12-11 | 2023-12-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A3930 | HNB Enhanced Defuelling Safety Cases | Submit for approval - Categoriser ratifies; RE/CO endorsement | 2023-12-11 | 2023-12-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.29190 | HYB Essential Defueling Safety Case | Include verified defuelling fault schedule from Task 2 to complete defuelling SSR | 2023-12-11 | 2023-12-11 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.29190 | TOR Essential Defueling Safety Case | Include verified defuelling fault schedule from Task 2 to complete defuelling SSR | 2023-12-11 | 2023-12-11 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1425 | HYB Essential Defueling Safety Case | Produce verification plan | 2023-12-12 | 2023-12-12 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.29210 | HYB Essential Defueling Safety Case | Verification/TR/specialist assessment (station review) of SSR text only as fault schedule already QA2 | 2023-12-12 | 2024-01-31 | 6 | 0 | 33 | 50 | 100% | 0.12 | 1 | Completed
ER6372LT | W203 | W203.A3820 | HNB Enhanced Defuelling Safety Cases | INSA review & iteration of comments (using BARRIER MODEL) | 2023-12-12 | 2023-12-15 | 10 | 0 | 3 | 3 | 100% | 3.3333 | 1 | Completed
ER6668LT | W213 | W213.1425 | TOR Essential Defueling Safety Case | Produce verification plan | 2023-12-12 | 2023-12-12 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.29210 | TOR Essential Defueling Safety Case | Verification/TR/specialist assessment (station review) of SSR text only as fault schedule already QA2 | 2023-12-12 | 2024-01-31 | 6 | 0 | 33 | 50 | 100% | 0.12 | 1 | Completed
ER6666LT | W209 | W209.29200 | HYB Essential Defueling Safety Case | Draft SSR Ready for review and uploaded to ADL alongside Cat 1 Ready to Review | 2023-12-12 | 2024-01-31 | 1 | 0 | 33 | 50 | 100% | 0.02 | 1 | Completed
ER6668LT | W213 | W213.29200 | TOR Essential Defueling Safety Case | Draft SSR Ready for review and uploaded to ADL alongside Cat 1 Ready to Review | 2023-12-12 | 2024-01-31 | 1 | 0 | 33 | 50 | 100% | 0.02 | 1 | Completed
ER6372LT | W203 | W203.1010 | HNB Enhanced Defuelling Safety Cases | Purge and Pressurisation - Lessons Learnt Review Complete | 2023-12-14 | 2023-12-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.7230 | HYB Essential Defueling Safety Case | Claim 5 Ready | 2023-12-15 | 2023-12-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.7230 | TOR Essential Defueling Safety Case | Claim 5 Ready | 2023-12-15 | 2023-12-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2650 | DNB Enhanced Safety Cases | Obtain Agreement from Executive (FEED TO SUMMARY SCHEDULE) | 2023-12-15 | 2023-12-21 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6372LT | W203 | W203.A3980 | HNB Enhanced Defuelling Safety Cases | Incorporate INSA comments | 2023-12-16 | 2023-12-19 | 10 | 0 | 1 | 3 | 100% | 3.3333 | 1 | Completed
ER6666LT | W209 | W209.A29090 | HYB Essential Defueling Safety Case | Technical Review of Defuelling Handling Deterministic Assessment EAN | 2023-12-18 | 2024-01-24 | 5 | 0 | 24 | 37 | 100% | 0.13514 | 1 | Completed
ER6668LT | W213 | W213.A29090 | TOR Essential Defueling Safety Case | Technical Review of Defuelling Handling Deterministic Assessment EAN | 2023-12-18 | 2024-01-24 | 5 | 0 | 25 | 37 | 100% | 0.13514 | 1 | Completed
ER6378LT | W222 | 001964a | HRA Fuel Handling Essential Safety Case | Repsond to First Round Comments | 2023-12-18 | 2024-02-08 | 14 | 0 | 35 | 52 | 100% | 0.26923 | 1 | Completed
ER6378LT | W222 | 1964 | HRA Fuel Handling Essential Safety Case | Respond to First Round comments (Claim 5 Re-write & Peer Review) | 2023-12-18 | 2024-02-08 | 14 | 0 | 32 | 52 | 100% | 0.26923 | 1 | Completed
ER6650LT | W226 | 001964a | HYA Fuel Handling Essential Safety Case | Repsond to First Round Comments | 2023-12-18 | 2024-02-08 | 14 | 0 | 35 | 52 | 100% | 0.26923 | 1 | Completed
ER6650LT | W226 | 1964 | HYA Fuel Handling Essential Safety Case | Respond to First Round comments (Claim 5 Re-write & Peer Review) Grant | 2023-12-18 | 2024-01-31 | 14 | 0 | 26 | 44 | 100% | 0.31818 | 1 | Completed
ER6666LT | W209 | W209.5400 | HYB Essential Defueling Safety Case | CLAIM 4 - Dropped Fuel Plug Assemblies | 2023-12-20 | 2023-12-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.7320 | HYB Essential Defueling Safety Case | Claim 4 Ready | 2023-12-20 | 2023-12-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.5400 | TOR Essential Defueling Safety Case | CLAIM 4 - Dropped Fuel Plug Assemblies | 2023-12-20 | 2023-12-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.7320 | TOR Essential Defueling Safety Case | Claim 4 Ready | 2023-12-20 | 2023-12-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1990 | DNB Enhanced Safety Cases | Station comments on NSRS | 2023-12-20 | 2024-01-19 | 8 | 0 | 19 | 30 | 100% | 0.26667 | 1 | Completed
W232LT | W232 | W232.A2000 | DNB Enhanced Safety Cases | Key Stakeholders (Peer) comments on NSRS (as required) | 2023-12-20 | 2024-01-19 | 8 | 0 | 19 | 30 | 100% | 0.26667 | 1 | Completed
ER6372LT | W203 | W203.A3950 | HNB Enhanced Defuelling Safety Cases | Station approval for mod implementation (including station review meeting) | 2023-12-21 | 2023-12-21 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A4010 | HNB Enhanced Defuelling Safety Cases | INSA Final Approval (KDM) - <IFD Deluge> | 2023-12-21 | 2023-12-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A4090 | HNB Enhanced Defuelling Safety Cases | Station Approval Obtained and CAT 2 Safety Case Complete *(KDM)* (FEEDS TO SUMMARY SCHEDULE) - <IFD Deluge> | 2023-12-21 | 2023-12-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1465 | HYB Essential Defueling Safety Case | Cost Summary for Veriification - (Cost Summary) ## | 2023-12-22 | 2024-05-31 | 95 | 0 | 108 | 161 | 100% | 0.59006 | 1 | Completed
ER6666LT | W209 | W209.5390 | HYB Essential Defueling Safety Case | CLAIM 5 - Faults | 2023-12-22 | 2023-12-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.8700 | HYB Essential Defueling Safety Case | Claims Integration | 2023-12-22 | 2024-01-31 | 5 | 0 | 26 | 40 | 100% | 0.125 | 1 | Completed
ER6668LT | W213 | W213.1465 | TOR Essential Defueling Safety Case | Cost Summary for Veriification - (Cost Summary) ## | 2023-12-22 | 2024-05-31 | 93 | 0 | 108 | 161 | 100% | 0.57764 | 1 | Completed
ER6668LT | W213 | W213.5390 | TOR Essential Defueling Safety Case | CLAIM 5 - Faults | 2023-12-22 | 2023-12-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.8700 | TOR Essential Defueling Safety Case | Claims Integration | 2023-12-22 | 2024-01-31 | 5 | 0 | 25 | 40 | 100% | 0.125 | 1 | Completed
ER6378LT | W222 | W222.A27445 | HRA Fuel Handling Essential Safety Case | All Technical References (EVENT RECOVERY) Complete | 2023-12-22 | 2023-12-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27445 | HYA Fuel Handling Essential Safety Case | All Technical References (EVENT RECOVERY) Complete | 2023-12-22 | 2023-12-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2950 | DNB Enhanced Safety Cases | Decision Milestone - Cold Defuelling Feasibility and Benefits | 2023-12-22 | 2023-12-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A4970 | DNB Enhanced Safety Cases | >>>OUTGOING ENABLER Decision Milestone - Cold Defuelling Feasibility and Benefits | 2023-12-22 | 2023-12-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A27420 | TOR Essential Defueling Safety Case | Supplier Update and Issue Fuel Route PSA Update EAN | 2023-12-27 | 2024-01-12 | 5 | 0 | 12 | 16 | 100% | 0.3125 | 1 | Completed
ER6666LT | W209 | W209.A27420 | HYB Essential Defueling Safety Case | Supplier Update and Issue Fuel Route PSA Update EAN | 2023-12-27 | 2024-01-12 | 10 | 0 | 12 | 16 | 100% | 0.625 | 1 | Completed
ER6666LT | W209 | W209.A30020 | HYB Essential Defueling Safety Case | Compliance Arrangement Review EAN - Scope No Longer Required ## (Cost Summary) (Claim 6) | 2024-01-02 | 2024-01-31 | 71 | 0 | 21 | 29 | 100% | 2.4483 | 1 | Completed
ER6666LT | W209 | W209.A30030 | HYB Essential Defueling Safety Case | HOLDING LINE - Compliance Arrangement Review EAN - Scope No Longer Required | 2024-01-02 | 2024-01-31 | 71 | 0 | 21 | 29 | 100% | 2.4483 | 1 | Completed
ER6666LT | W209 | W209.A30110 | HYB Essential Defueling Safety Case | HOLDING LINE - Substantiate Station Comply with New Controls - Scope No Longer Required | 2024-01-02 | 2024-01-31 | 71 | 0 | 21 | 29 | 100% | 2.4483 | 1 | Completed
ER6666LT | W209 | W209.A30100 | HYB Essential Defueling Safety Case | Substantiate Station Comply with New Controls - Scope No Longer Required ## (Cost Summary) (Claim 6) | 2024-01-02 | 2024-01-31 | 71 | 0 | 21 | 29 | 100% | 2.4483 | 1 | Completed
ER6666LT | W209 | W209.A30880 | HYB Essential Defueling Safety Case | Plant Area Review in Support of Argument 6.1 EAN - Scope No Longer Required ## (Cost Summary) (Claim 6) | 2024-01-02 | 2024-01-31 | 24 | 0 | 21 | 29 | 100% | 0.82759 | 1 | Completed
ER6666LT | W209 | W209.A30890 | HYB Essential Defueling Safety Case | HOLDING LINE - Plant Area Review in Support of Argument 6.1 EAN - Scope No Longer Required | 2024-01-02 | 2024-01-31 | 24 | 0 | 21 | 29 | 100% | 0.82759 | 1 | Completed
W232LT | W232 | W232.A2890 | DNB Enhanced Safety Cases | <TRANSFER SCOPE TO W699 CN 1727> Cat 2 EC for Cold Extraction (if required) | 2024-01-02 | 2024-02-01 | 62 | 0 | 22 | 30 | 100% | 2.0667 | 1 | Completed
ER6668LT | W213 | W213.A30020 | TOR Essential Defueling Safety Case | Compliance Arrangement Review EAN - Scope No Longer Required ## (Cost Summary) (Claim 6) | 2024-01-02 | 2024-01-31 | 71 | 0 | 21 | 29 | 100% | 2.4483 | 1 | Completed
ER6668LT | W213 | W213.A30030 | TOR Essential Defueling Safety Case | HOLDING LINE - Compliance Arrangement Review EAN - Scope No Longer Required | 2024-01-02 | 2024-01-31 | 71 | 0 | 21 | 29 | 100% | 2.4483 | 1 | Completed
ER6668LT | W213 | W213.A30110 | TOR Essential Defueling Safety Case | HOLDING LINE - Substantiate Station Comply with New Controls - Scope No Longer Required | 2024-01-02 | 2024-01-31 | 71 | 0 | 21 | 29 | 100% | 2.4483 | 1 | Completed
ER6668LT | W213 | W213.A30100 | TOR Essential Defueling Safety Case | Substantiate Station Comply with New Controls - Scope No Longer Required ## (Cost Summary) (Claim 6) | 2024-01-02 | 2024-01-31 | 71 | 0 | 21 | 29 | 100% | 2.4483 | 1 | Completed
ER6668LT | W213 | W213.A30880 | TOR Essential Defueling Safety Case | Plant Area Review in Support of Argument 6.1 EAN - Scope No Longer Required ## (Cost Summary) (Claim 6) | 2024-01-02 | 2024-01-31 | 24 | 0 | 21 | 29 | 100% | 0.82759 | 1 | Completed
ER6668LT | W213 | W213.A30890 | TOR Essential Defueling Safety Case | HOLDING LINE - Plant Area Review in Support of Argument 6.1 EAN - Scope No Longer Required | 2024-01-02 | 2024-01-31 | 24 | 0 | 21 | 29 | 100% | 0.82759 | 1 | Completed
ER6666LT | W209 | W209.1445 | HYB Essential Defueling Safety Case | Obtain CO Review & Detail Checker | 2024-01-08 | 2024-02-01 | 5 | 0 | 18 | 24 | 100% | 0.20833 | 1 | Completed
ER6666LT | W209 | W209.29490 | HYB Essential Defueling Safety Case | Final Authoring Consolidation Check | 2024-01-08 | 2024-02-01 | 5 | 0 | 18 | 24 | 100% | 0.20833 | 1 | Completed
ER6668LT | W213 | W213.1445 | TOR Essential Defueling Safety Case | Obtain CO Review & Detail Checker | 2024-01-08 | 2024-02-01 | 5 | 0 | 18 | 24 | 100% | 0.20833 | 1 | Completed
ER6668LT | W213 | W213.29490 | TOR Essential Defueling Safety Case | Final Authoring Consolidation Check | 2024-01-08 | 2024-02-01 | 5 | 0 | 18 | 24 | 100% | 0.20833 | 1 | Completed
ER6668LT | W213 | W213.A27430 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Fuel Route PSA Update EAN to CDMS | 2024-01-15 | 2024-01-31 | 13 | 0 | 13 | 16 | 100% | 0.8125 | 1 | Completed
ER6666LT | W209 | W209.A27430 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Fuel Route PSA Update EAN to CDMS | 2024-01-15 | 2024-01-31 | 5 | 0 | 13 | 16 | 100% | 0.3125 | 1 | Completed
ER6666LT | W209 | W209.7460 | HYB Essential Defueling Safety Case | Verification of Claim 7 | 2024-01-17 | 2024-01-17 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.7470 | HYB Essential Defueling Safety Case | Update Claim 7 | 2024-01-17 | 2024-01-26 | 1 | 0 | 8 | 9 | 100% | 0.11111 | 1 | Completed
ER6668LT | W213 | W213.7460 | TOR Essential Defueling Safety Case | Verification of Claim 7 | 2024-01-17 | 2024-01-17 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.7470 | TOR Essential Defueling Safety Case | Update Claim 7 | 2024-01-17 | 2024-01-26 | 1 | 0 | 8 | 9 | 100% | 0.11111 | 1 | Completed
ER6666LT | W209 | W209.28850 | HYB Essential Defueling Safety Case | Supplier Update and Issue Human Factors Integration Plan EAN (REV 001) | 2024-01-18 | 2024-03-15 | 3 | 0 | 42 | 57 | 100% | 0.052632 | 1 | Completed
ER6668LT | W213 | W213.28850 | TOR Essential Defueling Safety Case | Supplier Update and Issue Human Factors Integration Plan EAN (REV 001) | 2024-01-18 | 2024-03-15 | 9 | 0 | 41 | 57 | 100% | 0.15789 | 1 | Completed
W232LT | W232 | W232.A2040 | DNB Enhanced Safety Cases | Agree resource & timescales with suppliers for delivering key refs, incl contingency, risk & allowance for rework | 2024-01-19 | 2024-03-11 | 5 | 0 | 36 | 52 | 100% | 0.096154 | 1 | Completed
W232LT | W232 | W232.A2970 | DNB Enhanced Safety Cases | Incorporate Station, ED (peer) comments | 2024-01-22 | 2024-01-26 | 1 | 0 | 4 | 4 | 100% | 0.25 | 1 | Completed
ER6372LT | W203 | W203.C1020 | HNB Enhanced Defuelling Safety Cases | Agree resource & timescales with suppliers for delivering key refs, incl contingency, risk & allowance for rework | 2024-01-23 | 2024-01-29 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6372LT | W203 | W203.C1010 | HNB Enhanced Defuelling Safety Cases | Mod requested, Initiate EC, identify RE, register EC & identify milestones in AMS | 2024-01-23 | 2024-01-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1000 | HNB Enhanced Defuelling Safety Cases | Raise Engineering Request (as required) | 2024-01-23 | 2024-01-29 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.A29100 | HYB Essential Defueling Safety Case | Supplier Update and Issue Defuelling Handling Deterministic Assessment EAN | 2024-01-25 | 2024-01-29 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6668LT | W213 | W213.A29100 | TOR Essential Defueling Safety Case | Supplier Update and Issue Defuelling Handling Deterministic Assessment EAN | 2024-01-25 | 2024-01-29 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6666LT | W209 | W209.5420 | HYB Essential Defueling Safety Case | CLAIM 7 - NSP / ALARP | 2024-01-26 | 2024-01-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.5420 | TOR Essential Defueling Safety Case | CLAIM 7 - NSP / ALARP | 2024-01-26 | 2024-01-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2030 | DNB Enhanced Safety Cases | Hold project kick start meeting with Station & key suppliers | 2024-01-26 | 2024-03-26 | 5 | 0 | 42 | 60 | 100% | 0.083333 | 1 | Completed
ER6666LT | W209 | W209.7500 | HYB Essential Defueling Safety Case | Claim 7 Ready | 2024-01-26 | 2024-01-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.7500 | TOR Essential Defueling Safety Case | Claim 7 Ready | 2024-01-26 | 2024-01-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.7750 | HYB Essential Defueling Safety Case | Early INA Review Claim 4 | 2024-01-29 | 2024-02-29 | 3 | 0 | 23 | 31 | 100% | 0.096774 | 1 | Completed
ER6668LT | W213 | W213.7750 | TOR Essential Defueling Safety Case | Early INA Review Claim 4 | 2024-01-29 | 2024-02-29 | 3 | 0 | 23 | 31 | 100% | 0.096774 | 1 | Completed
ER6372LT | W203 | W203.C1030 | HNB Enhanced Defuelling Safety Cases | CO & CA appointed | 2024-01-29 | 2024-01-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1040 | HNB Enhanced Defuelling Safety Cases | Key Stakeholders Identified | 2024-01-29 | 2024-01-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A29110 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Defuelling Handling Deterministic Assessment EAN to CDMS | 2024-01-30 | 2024-01-31 | 5 | 0 | 1 | 1 | 100% | 5 | 1 | Completed
ER6666LT | W209 | W209.A29110 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Defuelling Handling Deterministic Assessment EAN to CDMS | 2024-01-30 | 2024-01-31 | 5 | 0 | 1 | 1 | 100% | 5 | 1 | Completed
ER6372LT | W203 | W203.C1060 | HNB Enhanced Defuelling Safety Cases | Hold project kick start meeting with Station & key suppliers | 2024-01-30 | 2024-01-31 | 5 | 0 | 1 | 1 | 100% | 5 | 1 | Completed
ER6372LT | W203 | W203.C1050 | HNB Enhanced Defuelling Safety Cases | Develop initial programme plan using mandatory template | 2024-01-30 | 2024-02-05 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
W730LT_UN | W730 | W730.1180 | HYB Enhanced Defueling Safety Cases | >>>INCOMING ENABLER (W209) Supporting References Complete | 2024-01-31 | 2024-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W730LT_UN | W730 | W730.1190 | HYB Enhanced Defueling Safety Cases | >>>MIRROR OF INCOMING ENABLER (W209) Supporting References Complete | 2024-01-31 | 2024-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1034 | HYB Essential Defueling Safety Case | All Key Supporting Technical References Completed for HYB Essential Defueling Safety Case | 2024-01-31 | 2024-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1350 | HYB Essential Defueling Safety Case | >>>OUTGOING ENABLER (W730, W305) Supporting References Complete | 2024-01-31 | 2024-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1405 | HYB Essential Defueling Safety Case | All Supporting References Approved and Issued | 2024-01-31 | 2024-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A29120 | HYB Essential Defueling Safety Case | Defuelling Handling Deterministic Assessment EAN Available | 2024-01-31 | 2024-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1350 | TOR Essential Defueling Safety Case | >>>OUTGOING ENABLER (W731, W214) Supporting References Complete | 2024-01-31 | 2024-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1034 | TOR Essential Defueling Safety Case | All Key Supporting Technical References Completed for TOR Essential Defueling Safety Case | 2024-01-31 | 2024-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1405 | TOR Essential Defueling Safety Case | All Supporting References Approved and Issued | 2024-01-31 | 2024-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A29120 | TOR Essential Defueling Safety Case | Defuelling Handling Deterministic Assessment EAN Available | 2024-01-31 | 2024-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W731LT_UN | W731 | W731.1000 | TOR Enhanced Defueling Safety Cases | >>>MIRROR OF INCOMING ENABLER (W209) Supporting References Complete | 2024-01-31 | 2024-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W731LT_UN | W731 | W731.1010 | TOR Enhanced Defueling Safety Cases | >>>INCOMING ENABLER (W209) Supporting References Complete | 2024-01-31 | 2024-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A27440 | HYB Essential Defueling Safety Case | Fuel Route PSA Update EAN Available | 2024-01-31 | 2024-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A27440 | TOR Essential Defueling Safety Case | Fuel Route PSA Update EAN Available | 2024-01-31 | 2024-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2900 | DNB Enhanced Safety Cases | Clearance to Remove High Risk OEM NSPs | 2024-02-01 | 2024-02-01 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W230LT | W230 | W230.1010 | HYB Enhanced Defueling Safety Case Strategy | Project Start | 2024-02-01 | 2024-02-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W234LT | W234 | W234.1010 | TOR Enhanced Defueling Safety Case Strategy | Project Start | 2024-02-01 | 2024-02-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2050 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Agree design proposals with Station in the case of hardware mods | 2024-02-01 | 2024-02-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2200 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Produce supporting reference <Structural Integrity Report 1 EAN> | 2024-02-01 | 2024-02-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B3020 | DNB Enhanced Safety Cases | Confirm Objectives to be Delivered at Gate B | 2024-02-01 | 2024-02-16 | 1 | 0 | 11 | 15 | 100% | 0.066667 | 1 | Completed
W232LT | W232 | W232.A2820 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Agree design proposals with Station in the case of hardware mods | 2024-02-01 | 2024-02-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2830 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Produce supporting reference <OEM Lifting Integrity> | 2024-02-01 | 2024-02-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2045 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Structural Integrity Report 1 - Summary | 2024-02-01 | 2024-02-05 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
W232LT | W232 | W232.A2815 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> OEM Lifting Integrity - Summary | 2024-02-01 | 2024-02-05 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6372LT | W203 | W203.C1090 | HNB Enhanced Defuelling Safety Cases | Agree design proposals with Station in the case of hardware mods | 2024-02-01 | 2024-02-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6372LT | W203 | W203.C1100 | HNB Enhanced Defuelling Safety Cases | Produce supporting reference <Enhanced Defueling rate EC> | 2024-02-01 | 2024-04-08 | 20 | 0 | 45 | 67 | 100% | 0.29851 | 1 | Completed
ER6378LT | W222 | 001965i | HRA Fuel Handling Essential Safety Case | Second Round Verification | 2024-02-01 | 2024-02-14 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6378LT | W222 | 001965g | HRA Fuel Handling Essential Safety Case | Second Round Verification | 2024-02-01 | 2024-02-21 | 10 | 0 | 14 | 20 | 100% | 0.5 | 1 | Completed
ER6378LT | W222 | 001965f | HRA Fuel Handling Essential Safety Case | Second Round Verification | 2024-02-01 | 2024-02-20 | 10 | 0 | 13 | 19 | 100% | 0.52632 | 1 | Completed
ER6378LT | W222 | 001965h | HRA Fuel Handling Essential Safety Case | Second Round Verification | 2024-02-01 | 2024-02-22 | 10 | 0 | 15 | 21 | 100% | 0.47619 | 1 | Completed
ER6378LT | W222 | 001965e | HRA Fuel Handling Essential Safety Case | Second Round Verification | 2024-02-01 | 2024-02-22 | 10 | 0 | 15 | 21 | 100% | 0.47619 | 1 | Completed
ER6378LT | W222 | 001965d | HRA Fuel Handling Essential Safety Case | Second Round Verification | 2024-02-01 | 2024-02-23 | 10 | 0 | 16 | 22 | 100% | 0.45455 | 1 | Completed
ER6378LT | W222 | 001965c | HRA Fuel Handling Essential Safety Case | Second Round Verification | 2024-02-01 | 2024-03-19 | 10 | 0 | 33 | 47 | 100% | 0.21277 | 1 | Completed
ER6378LT | W222 | 001965b | HRA Fuel Handling Essential Safety Case | Second Round Verification (Claim 5) | 2024-02-01 | 2024-02-21 | 15 | 0 | 15 | 20 | 100% | 0.75 | 1 | Completed
ER6378LT | W222 | 001965a | HRA Fuel Handling Essential Safety Case | Second Round Verification | 2024-02-01 | 2024-02-08 | 15 | 0 | 5 | 7 | 100% | 2.1429 | 1 | Completed
ER6378LT | W222 | 1965 | HRA Fuel Handling Essential Safety Case | Second Round Verification | 2024-02-01 | 2024-02-29 | 10 | 0 | 20 | 28 | 100% | 0.35714 | 1 | Completed
W232LT | W232 | W232.C1390 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Lifting Integrity Faults> - Summary Bar | 2024-02-01 | 2024-04-03 | 43 | 0 | 43 | 62 | 100% | 0.69355 | 1 | Completed
W232LT | W232 | W232.C1400 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Lifting Integrity Faults> - Draft and issue RFS | 2024-02-01 | 2024-02-14 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
W232LT | W232 | W232.C1630 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Further Review of Shock Loaded Unit Events> - Summary Bar | 2024-02-01 | 2024-04-03 | 43 | 0 | 43 | 62 | 100% | 0.69355 | 1 | Completed
W232LT | W232 | W232.C1640 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Further Review of Shock Loaded Unit Events> - Draft and issue RFS | 2024-02-01 | 2024-02-14 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6666LT | W209 | W209.1475 | HYB Essential Defueling Safety Case | Issue to Peer CO & Station for comments | 2024-02-02 | 2024-02-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.8730 | HYB Essential Defueling Safety Case | Chemistry - Specialist Assessments | 2024-02-02 | 2024-04-30 | 20 | 0 | 60 | 88 | 100% | 0.22727 | 1 | Completed
ER6666LT | W209 | W209.8740 | HYB Essential Defueling Safety Case | Civils - Specialist Assessments | 2024-02-02 | 2024-04-30 | 20 | 0 | 60 | 88 | 100% | 0.22727 | 1 | Completed
ER6666LT | W209 | W209.8750 | HYB Essential Defueling Safety Case | Emergency Arrangements - Specialist Assessments | 2024-02-02 | 2024-04-30 | 20 | 0 | 60 | 88 | 100% | 0.22727 | 1 | Completed
ER6666LT | W209 | W209.8770 | HYB Essential Defueling Safety Case | Env Protection & Radwaste - Specialist Assessments | 2024-02-02 | 2024-04-30 | 20 | 0 | 60 | 88 | 100% | 0.22727 | 1 | Completed
ER6666LT | W209 | W209.8780 | HYB Essential Defueling Safety Case | Health Physics - Specialist Assessments | 2024-02-02 | 2024-04-30 | 20 | 0 | 60 | 88 | 100% | 0.22727 | 1 | Completed
ER6666LT | W209 | W209.8790 | HYB Essential Defueling Safety Case | Liabilities - Specialist Assessments | 2024-02-02 | 2024-04-30 | 20 | 0 | 60 | 88 | 100% | 0.22727 | 1 | Completed
ER6666LT | W209 | W209.8800 | HYB Essential Defueling Safety Case | Nuclear Safety - Specialist Assessments | 2024-02-02 | 2024-04-30 | 20 | 0 | 60 | 88 | 100% | 0.22727 | 1 | Completed
ER6666LT | W209 | W209.8810 | HYB Essential Defueling Safety Case | Ops - Specialist Assessments | 2024-02-02 | 2024-04-30 | 20 | 0 | 60 | 88 | 100% | 0.22727 | 1 | Completed
ER6666LT | W209 | W209.8820 | HYB Essential Defueling Safety Case | PSSR - Liner & Pens - Specialist Assessments | 2024-02-02 | 2024-04-30 | 20 | 0 | 60 | 88 | 100% | 0.22727 | 1 | Completed
ER6666LT | W209 | W209.28930 | HYB Essential Defueling Safety Case | Verification of the case - First Round Comments (using BARRIER MODEL) | 2024-02-02 | 2024-04-30 | 20 | 0 | 61 | 88 | 100% | 0.22727 | 1 | Completed
ER6668LT | W213 | W213.1475 | TOR Essential Defueling Safety Case | Issue to Peer CO & Station for comments | 2024-02-02 | 2024-02-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.8730 | TOR Essential Defueling Safety Case | Chemistry - Specialist Assessments (if Necessary) | 2024-02-02 | 2024-04-30 | 20 | 0 | 60 | 88 | 100% | 0.22727 | 1 | Completed
ER6668LT | W213 | W213.8740 | TOR Essential Defueling Safety Case | Civils - Specialist Assessments (if Necessary) | 2024-02-02 | 2024-04-30 | 20 | 0 | 60 | 88 | 100% | 0.22727 | 1 | Completed
ER6668LT | W213 | W213.8750 | TOR Essential Defueling Safety Case | Emergency Arrangements - Specialist Assessments (if Necessary) | 2024-02-02 | 2024-04-30 | 20 | 0 | 60 | 88 | 100% | 0.22727 | 1 | Completed
ER6668LT | W213 | W213.8770 | TOR Essential Defueling Safety Case | Env Protection & Radwaste - Specialist Assessments (if Necessary) | 2024-02-02 | 2024-04-30 | 20 | 0 | 60 | 88 | 100% | 0.22727 | 1 | Completed
ER6668LT | W213 | W213.8780 | TOR Essential Defueling Safety Case | H&V - Specialist Assessments (if Necessary) | 2024-02-02 | 2024-04-30 | 20 | 0 | 60 | 88 | 100% | 0.22727 | 1 | Completed
ER6668LT | W213 | W213.8790 | TOR Essential Defueling Safety Case | Liabilities - Specialist Assessments (if Necessary) | 2024-02-02 | 2024-04-30 | 20 | 0 | 60 | 88 | 100% | 0.22727 | 1 | Completed
ER6668LT | W213 | W213.8800 | TOR Essential Defueling Safety Case | Nuclear Safety - Specialist Assessments (if Necessary) | 2024-02-02 | 2024-04-30 | 20 | 0 | 60 | 88 | 100% | 0.22727 | 1 | Completed
ER6668LT | W213 | W213.8810 | TOR Essential Defueling Safety Case | Ops - Specialist Assessments (if Necessary) | 2024-02-02 | 2024-04-30 | 20 | 0 | 60 | 88 | 100% | 0.22727 | 1 | Completed
ER6668LT | W213 | W213.8820 | TOR Essential Defueling Safety Case | PSSR - Specialist Assessments (if Necessary) | 2024-02-02 | 2024-04-30 | 20 | 0 | 60 | 88 | 100% | 0.22727 | 1 | Completed
ER6668LT | W213 | W213.28930 | TOR Essential Defueling Safety Case | Verification of the case (using BARRIER MODEL) | 2024-02-02 | 2024-04-30 | 20 | 0 | 60 | 88 | 100% | 0.22727 | 1 | Completed
ER6666LT | W209 | W209.29620 | HYB Essential Defueling Safety Case | PSSR - PCPV - Specialist Assessments | 2024-02-02 | 2024-04-30 | 20 | 0 | 60 | 88 | 100% | 0.22727 | 1 | Completed
ER6666LT | W209 | W209.29630 | HYB Essential Defueling Safety Case | APEX - PCPV Specialist Assessments | 2024-02-02 | 2024-04-30 | 20 | 0 | 60 | 88 | 100% | 0.22727 | 1 | Completed
W232LT | W232 | W232.A2350 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Verify supporting reference <Structural Integrity Report 1 EAN> | 2024-02-02 | 2024-02-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B3030 | DNB Enhanced Safety Cases | Initial high level scope of programme | 2024-02-02 | 2024-02-16 | 1 | 0 | 10 | 14 | 100% | 0.071429 | 1 | Completed
W232LT | W232 | W232.A2770 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Agree design proposals with Station in the case of hardware mods | 2024-02-02 | 2024-02-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2780 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Produce supporting reference <Structural Integrity Report 2 EAN> | 2024-02-02 | 2024-02-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2840 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Verify supporting reference <OEM Lifting Integrity> | 2024-02-02 | 2024-02-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2765 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Structural Integrity Report 2 - Summary | 2024-02-02 | 2024-02-06 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6666LT | W209 | W209.1455 | HYB Essential Defueling Safety Case | Verification Commenced (T-11) | 2024-02-02 | 2024-02-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1036 | HYB Essential Defueling Safety Case | Safety Case Paper Authoring Complete EC 371387 -HYB Essential Defueling Safety Case | 2024-02-02 | 2024-02-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1455 | TOR Essential Defueling Safety Case | Verification Commenced (T-11) | 2024-02-02 | 2024-02-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1036 | TOR Essential Defueling Safety Case | Safety Case Paper Authoring Complete EC 371386 -TOR Essential Defueling Safety Case | 2024-02-02 | 2024-02-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2360 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> BE Technical review of supporting reference <Structural Integrity Report 1 EAN> | 2024-02-05 | 2024-02-05 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2790 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Verify supporting reference <Structural Integrity Report 2 EAN> | 2024-02-05 | 2024-02-05 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2850 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> BE Technical review of supporting reference <OEM Lifting Integrity> | 2024-02-05 | 2024-02-05 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2370 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Supporting reference <Structural Integrity Report 1 EAN> approved | 2024-02-05 | 2024-02-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2860 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Supporting reference <OEM Lifting Integrity> approved | 2024-02-05 | 2024-02-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 001965f | HYA Fuel Handling Essential Safety Case | Second Round Verification Grant | 2024-02-06 | 2024-02-20 | 10 | 0 | 10 | 14 | 100% | 0.71429 | 1 | Completed
W232LT | W232 | W232.A2800 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> BE Technical review of supporting reference <Structural Integrity Report 2 EAN> | 2024-02-06 | 2024-02-06 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C1240 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Weld Inspection Data> - Summary Bar | 2024-02-06 | 2024-04-03 | 40 | 0 | 40 | 57 | 100% | 0.70175 | 1 | Completed
W232LT | W232 | W232.C1250 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Weld Inspection Data> - Draft and issue RFS | 2024-02-06 | 2024-02-19 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
W232LT | W232 | W232.A2810 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 1727> Supporting reference <Structural Integrity Report 2 EAN> approved | 2024-02-06 | 2024-02-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 001965g | HYA Fuel Handling Essential Safety Case | Second Round Verification Grant | 2024-02-07 | 2024-02-21 | 10 | 0 | 10 | 14 | 100% | 0.71429 | 1 | Completed
W232LT | W232 | W232.C1460 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Shock Loaded Unit Events> - Prepare Draft EAN | 2024-02-07 | 2024-04-04 | 40 | 0 | 40 | 57 | 100% | 0.70175 | 1 | Completed
ER6372LT | W203 | W203.A4070 | HNB Enhanced Defuelling Safety Cases | Post Job Debrief | 2024-02-08 | 2024-02-08 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 001965h | HYA Fuel Handling Essential Safety Case | Second Round Verification Grant | 2024-02-08 | 2024-02-22 | 10 | 0 | 10 | 14 | 100% | 0.71429 | 1 | Completed
ER6650LT | W226 | 001965e | HYA Fuel Handling Essential Safety Case | Second Round Verification Grant | 2024-02-08 | 2024-02-22 | 10 | 0 | 10 | 14 | 100% | 0.71429 | 1 | Completed
ER6372LT | W203 | W203.1020 | HNB Enhanced Defuelling Safety Cases | IFD Deluge - Lessons Learnt Review Complete | 2024-02-08 | 2024-02-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 001965a | HYA Fuel Handling Essential Safety Case | Second Round Verification Grant | 2024-02-09 | 2024-03-01 | 15 | 0 | 15 | 21 | 100% | 0.71429 | 1 | Completed
ER6372LT | W203 | W203.C1140 | HNB Enhanced Defuelling Safety Cases | CA to agree with CO format of the safety case & produce agreed contents page | 2024-02-13 | 2024-02-14 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6372LT | W203 | W203.C1130 | HNB Enhanced Defuelling Safety Cases | Identify verifier for the case & establish all other resources | 2024-02-13 | 2024-02-19 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6650LT | W226 | 1965 | HYA Fuel Handling Essential Safety Case | Second Round Verification Grant | 2024-02-15 | 2024-02-29 | 10 | 0 | 10 | 14 | 100% | 0.71429 | 1 | Completed
W232LT | W232 | W232.C1410 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Lifting Integrity Faults> - Supplier prepare and issue Offer | 2024-02-15 | 2024-03-15 | 8 | 0 | 21 | 29 | 100% | 0.27586 | 1 | Completed
W232LT | W232 | W232.C1650 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Further Review of Shock Loaded Unit Events> - Supplier prepare and issue Offer | 2024-02-15 | 2024-03-15 | 8 | 0 | 21 | 29 | 100% | 0.27586 | 1 | Completed
W232LT | W232 | W232.A2470 | DNB Enhanced Safety Cases | INSA Resource Identified | 2024-02-19 | 2024-02-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.2020 | HYB Essential Defueling Safety Case | Hold Gate C Equivalent Mid Job Brief | 2024-02-20 | 2024-02-23 | 25 | 0 | 3 | 3 | 100% | 8.3333 | 1 | Completed
ER6666LT | W209 | W209.29260 | HYB Essential Defueling Safety Case | Lessons Learnt Activity – Following Technical References | 2024-02-20 | 2024-02-23 | 25 | 0 | 3 | 3 | 100% | 8.3333 | 1 | Completed
ER6666LT | W209 | W209.29280 | HYB Essential Defueling Safety Case | Lessons Learnt Activitiy - Following Authoring of SC | 2024-02-20 | 2024-02-23 | 20 | 0 | 3 | 3 | 100% | 6.6667 | 1 | Completed
ER6668LT | W213 | W213.2020 | TOR Essential Defueling Safety Case | Hold Gate C Equivalent Mid Job Brief | 2024-02-20 | 2024-02-23 | 25 | 0 | 3 | 3 | 100% | 8.3333 | 1 | Completed
ER6668LT | W213 | W213.29260 | TOR Essential Defueling Safety Case | Lessons Learnt Activity – Following Technical References | 2024-02-20 | 2024-02-23 | 25 | 0 | 3 | 3 | 100% | 8.3333 | 1 | Completed
ER6668LT | W213 | W213.29280 | TOR Essential Defueling Safety Case | Lessons Learnt Activitiy - Following Authoring of SC | 2024-02-20 | 2024-02-23 | 20 | 0 | 3 | 3 | 100% | 6.6667 | 1 | Completed
ER6372LT | W203 | W203.C1170 | HNB Enhanced Defuelling Safety Cases | Produce verification plan | 2024-02-20 | 2024-02-21 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
W232LT | W232 | W232.C1260 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Weld Inspection Data> - Supplier prepare and issue Offer | 2024-02-20 | 2024-03-15 | 8 | 0 | 18 | 24 | 100% | 0.33333 | 1 | Completed
W232LT | W232 | W232.A2330 | DNB Enhanced Safety Cases | INA comments on NSRS | 2024-02-21 | 2024-02-28 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
W230LT | W230 | W230.1850 | HYB Enhanced Defueling Safety Case Strategy | ## Technical Development / Project Management - Pre Gate A - (Cost Summary) ## | 2024-02-22 | 2024-06-28 | 626 | 0 | 88 | 127 | 100% | 4.9291 | 1 | Completed
W230LT | W230 | W230.1910 | HYB Enhanced Defueling Safety Case Strategy | HYB Enhanced SC's & Cat C MoTA Workshop | 2024-02-22 | 2024-02-22 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W230LT | W230 | W230.3730 | HYB Enhanced Defueling Safety Case Strategy | ## Technical Development / Project Management - Pre Gate A - (Cost Summary) ## SUNK COSTS | 2024-02-22 | 2024-06-28 | 626 | 0 | 88 | 127 | 100% | 4.9291 | 1 | Completed
W234LT | W234 | W234.1850 | TOR Enhanced Defueling Safety Case Strategy | ## Technical Development / Project Management - Pre Gate A - (Cost Summary) ## | 2024-02-22 | 2024-06-28 | 626 | 0 | 88 | 127 | 100% | 4.9291 | 1 | Completed
W234LT | W234 | W234.1910 | TOR Enhanced Defueling Safety Case Strategy | TOR Enhanced SC's & Cat C MoTA Workshop | 2024-02-22 | 2024-02-22 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W234LT | W234 | W234.3730 | TOR Enhanced Defueling Safety Case Strategy | ## Technical Development / Project Management - Pre Gate A - (Cost Summary) ## SUNK COSTS | 2024-02-22 | 2024-06-28 | 626 | 0 | 88 | 127 | 100% | 4.9291 | 1 | Completed
ER6666LT | W209 | W209.1062 | HYB Essential Defueling Safety Case | Gate C Equivalent Mid Job Brief Held | 2024-02-23 | 2024-02-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.29270 | HYB Essential Defueling Safety Case | Lessons Learnt Milestone - Technical References | 2024-02-23 | 2024-02-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.29290 | HYB Essential Defueling Safety Case | Lessons Learnt Milestone - Authoring of the Safety Case | 2024-02-23 | 2024-02-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1062 | TOR Essential Defueling Safety Case | Gate C Equivalent Mid Job Brief Held | 2024-02-23 | 2024-02-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.29270 | TOR Essential Defueling Safety Case | Lessons Learnt Milestone - Technical References | 2024-02-23 | 2024-02-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.29290 | TOR Essential Defueling Safety Case | Lessons Learnt Milestone - Authoring of the Safety Case | 2024-02-23 | 2024-02-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1485 | HYB Essential Defueling Safety Case | Incorporate all stakeholder comments | 2024-02-29 | 2024-05-31 | 10 | 0 | 63 | 92 | 100% | 0.1087 | 1 | Completed
ER6668LT | W213 | W213.1485 | TOR Essential Defueling Safety Case | Incorporate all stakeholder comments | 2024-02-29 | 2024-05-31 | 10 | 0 | 63 | 92 | 100% | 0.1087 | 1 | Completed
W230LT | W230 | W230.1920 | HYB Enhanced Defueling Safety Case Strategy | TOR Enhanced SC's & Cat C MoTA Workshop | 2024-02-29 | 2024-02-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W234LT | W234 | W234.1920 | TOR Enhanced Defueling Safety Case Strategy | TOR Enhanced SC's & Cat C MoTA Workshop | 2024-02-29 | 2024-02-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6698LT | W224 | W224.1020 | HRA Enhanced Defueling Safety Case | Review of station OPEX | 2024-03-01 | 2024-03-29 | 1 | 0 | 20 | 28 | 100% | 0.035714 | 1 | Completed
ER6698LT | W224 | W224.1030 | HRA Enhanced Defueling Safety Case | Mass | 2024-03-01 | 2024-03-29 | 1 | 0 | 20 | 28 | 100% | 0.035714 | 1 | Completed
ER6698LT | W224 | W224.1040 | HRA Enhanced Defueling Safety Case | MSM Handling and attachment to Tie Bar | 2024-03-01 | 2024-03-29 | 1 | 0 | 20 | 28 | 100% | 0.035714 | 1 | Completed
ER6698LT | W224 | W224.1050 | HRA Enhanced Defueling Safety Case | Storing and loading into the IFDF | 2024-03-01 | 2024-03-29 | 1 | 0 | 20 | 28 | 100% | 0.035714 | 1 | Completed
ER6698LT | W224 | W224.1060 | HRA Enhanced Defueling Safety Case | Operations Tooling | 2024-03-01 | 2024-03-29 | 1 | 0 | 20 | 28 | 100% | 0.035714 | 1 | Completed
ER6698LT | W224 | W224.1070 | HRA Enhanced Defueling Safety Case | Removal/Release mechanism | 2024-03-01 | 2024-03-29 | 1 | 0 | 20 | 28 | 100% | 0.035714 | 1 | Completed
ER6698LT | W224 | W224.1080 | HRA Enhanced Defueling Safety Case | Chamfers and curves | 2024-03-01 | 2024-04-30 | 1 | 0 | 40 | 60 | 100% | 0.016667 | 1 | Completed
ER6698LT | W224 | W224.A1110 | HRA Enhanced Defueling Safety Case | Project Start | 2024-03-01 | 2024-03-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6698LT | W224 | W224.3530 | HRA Enhanced Defueling Safety Case | Pre Gate A Actual Cost | 2024-03-01 | 2024-05-24 | 62 | 0 | 58 | 84 | 100% | 0.7381 | 1 | Completed
ER6701LT | W228 | W228.3530 | HYA Enhanced Defueling Safety Case | Pre Gate A Actual Cost | 2024-03-01 | 2024-05-24 | 62 | 0 | 58 | 84 | 100% | 0.7381 | 1 | Completed
ER6701LT | W228 | W228.A1110 | HYA Enhanced Defueling Safety Case | Project Start | 2024-03-01 | 2024-03-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6701LT | W228 | W228.1080 | HYA Enhanced Defueling Safety Case | Chamfers and curves | 2024-03-01 | 2024-04-30 | 1 | 0 | 40 | 60 | 100% | 0.016667 | 1 | Completed
ER6701LT | W228 | W228.1070 | HYA Enhanced Defueling Safety Case | Removal/Release mechanism | 2024-03-01 | 2024-03-29 | 1 | 0 | 20 | 28 | 100% | 0.035714 | 1 | Completed
ER6701LT | W228 | W228.1060 | HYA Enhanced Defueling Safety Case | Operations Tooling | 2024-03-01 | 2024-03-29 | 1 | 0 | 20 | 28 | 100% | 0.035714 | 1 | Completed
ER6701LT | W228 | W228.1050 | HYA Enhanced Defueling Safety Case | Storing and loading into the IFDF | 2024-03-01 | 2024-03-29 | 1 | 0 | 20 | 28 | 100% | 0.035714 | 1 | Completed
ER6701LT | W228 | W228.1040 | HYA Enhanced Defueling Safety Case | MSM Handling and attachment to Tie Bar | 2024-03-01 | 2024-03-29 | 1 | 0 | 20 | 28 | 100% | 0.035714 | 1 | Completed
ER6701LT | W228 | W228.1030 | HYA Enhanced Defueling Safety Case | Mass | 2024-03-01 | 2024-03-29 | 1 | 0 | 20 | 28 | 100% | 0.035714 | 1 | Completed
ER6701LT | W228 | W228.1020 | HYA Enhanced Defueling Safety Case | Review of station OPEX | 2024-03-01 | 2024-03-29 | 1 | 0 | 20 | 28 | 100% | 0.035714 | 1 | Completed
ER6701LT | W228 | W228.1010 | HYA Enhanced Defueling Safety Case | Sunk Cost (Mar - Dec 24) | 2024-03-01 | 2024-12-31 | 1 | 0 | 210 | 305 | 100% | 0.0032787 | 1 | Completed
ER6666LT | W209 | W209.8760 | HYB Essential Defueling Safety Case | Computing - Specialist Assessments (Not Required) | 2024-03-01 | 2024-03-04 | 20 | 0 | 1 | 3 | 100% | 6.6667 | 1 | Completed
W232LT | W232 | W232.A2180 | DNB Enhanced Safety Cases | Incorporate INA, Station, ED (peer) comments | 2024-03-01 | 2024-03-04 | 4 | 0 | 1 | 3 | 100% | 1.3333 | 1 | Completed
W232LT | W232 | W232.A2500 | DNB Enhanced Safety Cases | Cat 2 EC Scoping Workshop | 2024-03-01 | 2024-03-04 | 2 | 0 | 2 | 3 | 100% | 0.66667 | 1 | Completed
W232LT | W232 | W232.B3120 | DNB Enhanced Safety Cases | Define Project Control Structures (WBS/CBS/OBS/PBS) | 2024-03-01 | 2024-03-01 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.8760 | TOR Essential Defueling Safety Case | Computing - Specialist Assessments (if Necessary) | 2024-03-01 | 2024-03-04 | 20 | 0 | 1 | 3 | 100% | 6.6667 | 1 | Completed
ER6650LT | W226 | 2130 | HYA Fuel Handling Essential Safety Case | LSD Updates | 2024-03-01 | 2024-03-07 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6698LT | W224 | W224.1090 | HRA Enhanced Defueling Safety Case | Latching / nonsliding | 2024-03-01 | 2024-04-30 | 1 | 0 | 40 | 60 | 100% | 0.016667 | 1 | Completed
ER6701LT | W228 | W228.1090 | HYA Enhanced Defueling Safety Case | Latching / nonsliding | 2024-03-01 | 2024-04-30 | 1 | 0 | 40 | 60 | 100% | 0.016667 | 1 | Completed
W232LT | W232 | W232.A2010 | DNB Enhanced Safety Cases | Issue final NSRS | 2024-03-04 | 2024-03-04 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2020 | DNB Enhanced Safety Cases | Station agree NSRS *(KDM)* | 2024-03-04 | 2024-03-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2190 | DNB Enhanced Safety Cases | Key Stakeholders agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2024-03-04 | 2024-03-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2340 | DNB Enhanced Safety Cases | INA agree NSRS | 2024-03-04 | 2024-03-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A3000 | DNB Enhanced Safety Cases | NSRS Station Approval | 2024-03-04 | 2024-03-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B3140 | DNB Enhanced Safety Cases | Prepare Draft Project Definition Document (PDD) | 2024-03-04 | 2024-03-28 | 1 | 0 | 18 | 24 | 100% | 0.041667 | 1 | Completed
W232LT | W232 | W232.B3150 | DNB Enhanced Safety Cases | Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 2024-03-04 | 2024-03-04 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2990 | DNB Enhanced Safety Cases | NSRS INA Review/Approval | 2024-03-04 | 2024-03-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2390 | DNB Enhanced Safety Cases | Develop plan with further iterations | 2024-03-05 | 2024-03-26 | 10 | 0 | 15 | 21 | 100% | 0.47619 | 1 | Completed
W232LT | W232 | W232.B3350 | DNB Enhanced Safety Cases | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 2024-03-05 | 2024-03-28 | 1 | 0 | 17 | 23 | 100% | 0.043478 | 1 | Completed
ER6650LT | W226 | 001965i | HYA Fuel Handling Essential Safety Case | Second Round Verification Grant | 2024-03-05 | 2024-03-15 | 10 | 0 | 8 | 10 | 100% | 1 | 1 | Completed
ER6650LT | W226 | 001965d | HYA Fuel Handling Essential Safety Case | Second Round Verification | 2024-03-05 | 2024-04-19 | 10 | 0 | 31 | 45 | 100% | 0.22222 | 1 | Completed
ER6650LT | W226 | 001965c | HYA Fuel Handling Essential Safety Case | Second Round Verification Grant | 2024-03-05 | 2024-03-19 | 10 | 0 | 10 | 14 | 100% | 0.71429 | 1 | Completed
ER6650LT | W226 | 001965b | HYA Fuel Handling Essential Safety Case | Second Round Verification (Claim 5) | 2024-03-05 | 2024-03-22 | 15 | 0 | 13 | 17 | 100% | 0.88235 | 1 | Completed
W232LT | W232 | W232.B3370 | DNB Enhanced Safety Cases | Ensure Alignment of Schedule & Estimate | 2024-03-06 | 2024-03-28 | 1 | 0 | 16 | 22 | 100% | 0.045455 | 1 | Completed
W232LT | W232 | W232.B3440 | DNB Enhanced Safety Cases | Hold Risk Workshop | 2024-03-07 | 2024-03-07 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B3490 | DNB Enhanced Safety Cases | Complete Risk Log with Estimates | 2024-03-08 | 2024-03-28 | 1 | 0 | 14 | 20 | 100% | 0.05 | 1 | Completed
W232LT | W232 | W232.B3500 | DNB Enhanced Safety Cases | Update Schedule/Estimate from Risk Log & Add Provisions | 2024-03-11 | 2024-03-28 | 1 | 0 | 13 | 17 | 100% | 0.058824 | 1 | Completed
W232LT | W232 | W232.B3580 | DNB Enhanced Safety Cases | Add Data to PRC Paper | 2024-03-12 | 2024-03-28 | 1 | 0 | 12 | 16 | 100% | 0.0625 | 1 | Completed
W230LT | W230 | W230.1930 | HYB Enhanced Defueling Safety Case Strategy | Kick-Off/Setting to Work Meeting | 2024-03-13 | 2024-03-13 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W234LT | W234 | W234.1930 | TOR Enhanced Defueling Safety Case Strategy | Kick-Off/Setting to Work Meeting | 2024-03-13 | 2024-03-13 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B3670 | DNB Enhanced Safety Cases | PCL Validate & Approve Baseline Package for PRC Submission | 2024-03-13 | 2024-03-28 | 1 | 0 | 11 | 15 | 100% | 0.066667 | 1 | Completed
ER6668LT | W213 | W213.7990 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Human Factors Integration Plan EAN to CDMS (REV 001) | 2024-03-18 | 2024-03-28 | 5 | 0 | 8 | 10 | 100% | 0.5 | 1 | Completed
ER6650LT | W226 | 1990 | HYA Fuel Handling Essential Safety Case | Update Proposal (First Draft) Including Appendices & Implementation | 2024-03-18 | 2024-05-09 | 25 | 0 | 36 | 52 | 100% | 0.48077 | 1 | Completed
ER6666LT | W209 | W209.7990 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Human Factors Integration Plan EAN to CDMS (REV 001) | 2024-03-18 | 2024-03-28 | 5 | 0 | 9 | 10 | 100% | 0.5 | 1 | Completed
W232LT | W232 | W232.C1270 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Weld Inspection Data> - Review Offer, prepare and issue CI | 2024-03-18 | 2024-03-22 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
W232LT | W232 | W232.C1420 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Lifting Integrity Faults> - Review Offer, prepare and issue CI | 2024-03-18 | 2024-03-22 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
W232LT | W232 | W232.C1660 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Further Review of Shock Loaded Unit Events> - Review Offer, prepare and issue CI | 2024-03-18 | 2024-03-22 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6378LT | W222 | 1990 | HRA Fuel Handling Essential Safety Case | Update Proposal (First Draft) Including Appendices & Implementation | 2024-03-19 | 2024-05-13 | 25 | 0 | 37 | 55 | 100% | 0.45455 | 1 | Completed
W232LT | W232 | W232.A2025 | DNB Enhanced Safety Cases | <NEW SCOPE CN1743> NSRS Presented to NSC (for complex CAT 2 cases) | 2024-03-20 | 2024-03-20 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2060 | DNB Enhanced Safety Cases | Consolidate & issue to stakeholders & suppliers agreed NSRS (as required) | 2024-03-21 | 2024-03-27 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6378LT | W222 | 1968 | HRA Fuel Handling Essential Safety Case | Repsond to Second Round and Tidy Up | 2024-03-22 | 2024-04-05 | 10 | 0 | 8 | 14 | 100% | 0.71429 | 1 | Completed
ER6378LT | W222 | W222.A24330 | HRA Fuel Handling Essential Safety Case | Supplier Update and Issue Living Safety Document EAN | 2024-03-25 | 2024-03-26 | 5 | 0 | 1 | 1 | 100% | 5 | 1 | Completed
ER6650LT | W226 | W226.A24330 | HYA Fuel Handling Essential Safety Case | Supplier Update and Issue Living Safety Document EAN | 2024-03-25 | 2024-03-26 | 5 | 0 | 1 | 1 | 100% | 5 | 1 | Completed
W232LT | W232 | W232.C1280 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Weld Inspection Data> - Supplier mobilisation time | 2024-03-25 | 2024-04-02 | 5 | 0 | 5 | 8 | 100% | 0.625 | 1 | Completed
W232LT | W232 | W232.C1430 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Lifting Integrity Faults> - Supplier mobilisation time | 2024-03-25 | 2024-04-02 | 5 | 0 | 5 | 8 | 100% | 0.625 | 1 | Completed
W232LT | W232 | W232.C1670 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Further Review of Shock Loaded Unit Events> - Supplier mobilisation time | 2024-03-25 | 2024-04-02 | 5 | 0 | 5 | 8 | 100% | 0.625 | 1 | Completed
W232LT | W232 | W232.A2310 | DNB Enhanced Safety Cases | Issue agreed work programme to stakeholders & suppliers | 2024-03-26 | 2024-03-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2460 | DNB Enhanced Safety Cases | Verifier PJB Held | 2024-03-26 | 2024-03-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W230LT | W230 | W230.1870 | HYB Enhanced Defueling Safety Case Strategy | Initial Categorisation by Station | 2024-03-26 | 2024-03-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W230LT | W230 | W230.1940 | HYB Enhanced Defueling Safety Case Strategy | H2T Enhanced SC's EC Strategy Opex/L&L | 2024-03-26 | 2024-03-26 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W234LT | W234 | W234.1870 | TOR Enhanced Defueling Safety Case Strategy | Initial Categorisation by Station | 2024-03-26 | 2024-03-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W234LT | W234 | W234.1940 | TOR Enhanced Defueling Safety Case Strategy | H2T Enhanced SC's EC Strategy Opex/L&L | 2024-03-26 | 2024-03-26 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 1968 | HYA Fuel Handling Essential Safety Case | Repsond to Second Round and Tidy Up | 2024-03-26 | 2024-04-05 | 10 | 0 | 6 | 10 | 100% | 1 | 1 | Completed
ER6378LT | W222 | W222.A24340 | HRA Fuel Handling Essential Safety Case | Complete TR Form and Upload Living Safety Document EAN to CDMS | 2024-03-27 | 2024-07-22 | 5 | 0 | 80 | 117 | 100% | 0.042735 | 1 | Completed
ER6650LT | W226 | W226.A24340 | HYA Fuel Handling Essential Safety Case | Complete TR Form and Upload Living Safety Document EAN to CDMS | 2024-03-27 | 2024-09-02 | 5 | 0 | 108 | 159 | 100% | 0.031447 | 1 | Completed
W230LT | W230 | W230.1950 | HYB Enhanced Defueling Safety Case Strategy | Pre Job Brief | 2024-03-27 | 2024-03-27 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W234LT | W234 | W234.1950 | TOR Enhanced Defueling Safety Case Strategy | Pre Job Brief | 2024-03-27 | 2024-03-27 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.8000 | TOR Essential Defueling Safety Case | Human Factors Integration Plan EAN Available (REV 001) | 2024-03-28 | 2024-03-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W230LT | W230 | W230.1310 | HYB Enhanced Defueling Safety Case Strategy | Confirm Objectives to be Delivered at Gate A (FEEDS TO SUMMARY SCHEDULE) | 2024-03-28 | 2024-04-03 | 10 | 0 | 3 | 6 | 100% | 1.6667 | 1 | Completed
W230LT | W230 | W230.1960 | HYB Enhanced Defueling Safety Case Strategy | Draft Report | 2024-03-28 | 2024-06-03 | 1 | 0 | 44 | 67 | 100% | 0.014925 | 1 | Completed
W234LT | W234 | W234.1310 | TOR Enhanced Defueling Safety Case Strategy | Confirm Objectives to be Delivered at Gate A (FEEDS TO SUMMARY SCHEDULE) | 2024-03-28 | 2024-04-03 | 10 | 0 | 3 | 6 | 100% | 1.6667 | 1 | Completed
W234LT | W234 | W234.1960 | TOR Enhanced Defueling Safety Case Strategy | Draft Report | 2024-03-28 | 2024-06-03 | 1 | 0 | 44 | 67 | 100% | 0.014925 | 1 | Completed
ER6666LT | W209 | W209.8000 | HYB Essential Defueling Safety Case | Human Factors Integration Plan - EAN Available (REV 001) | 2024-03-28 | 2024-03-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6698LT | W224 | W224.1110 | HRA Enhanced Defueling Safety Case | Feasibility Workshop Tech Reports CNL) - early technical reference | 2024-04-02 | 2024-05-10 | 21 | 0 | 28 | 38 | 100% | 0.55263 | 1 | Completed
ER6698LT | W224 | W224.1120 | HRA Enhanced Defueling Safety Case | Requirements Elicitation Workshop | 2024-04-02 | 2024-04-30 | 21 | 0 | 20 | 28 | 100% | 0.75 | 1 | Completed
ER6698LT | W224 | W224.1130 | HRA Enhanced Defueling Safety Case | Meeting Output/Notes | 2024-04-02 | 2024-05-24 | 21 | 0 | 38 | 52 | 100% | 0.40385 | 1 | Completed
ER6698LT | W224 | W224.1170 | HRA Enhanced Defueling Safety Case | Scheme Design | 2024-04-02 | 2024-08-07 | 42 | 0 | 89 | 127 | 100% | 0.33071 | 1 | Completed
ER6698LT | W224 | W224.1180 | HRA Enhanced Defueling Safety Case | Main/Key Features , for estimating purposes | 2024-04-02 | 2024-10-31 | 42 | 0 | 149 | 212 | 100% | 0.19811 | 1 | Completed
ER6701LT | W228 | W228.1180 | HYA Enhanced Defueling Safety Case | Main/Key Features , for estimating purposes | 2024-04-02 | 2024-10-31 | 42 | 0 | 149 | 212 | 100% | 0.19811 | 1 | Completed
ER6701LT | W228 | W228.1170 | HYA Enhanced Defueling Safety Case | Scheme Design | 2024-04-02 | 2024-08-07 | 42 | 0 | 89 | 127 | 100% | 0.33071 | 1 | Completed
ER6701LT | W228 | W228.1130 | HYA Enhanced Defueling Safety Case | Meeting Output/Notes | 2024-04-02 | 2024-05-24 | 21 | 0 | 38 | 52 | 100% | 0.40385 | 1 | Completed
ER6701LT | W228 | W228.1120 | HYA Enhanced Defueling Safety Case | Requirements Elicitation Workshop | 2024-04-02 | 2024-04-30 | 21 | 0 | 20 | 28 | 100% | 0.75 | 1 | Completed
ER6701LT | W228 | W228.1110 | HYA Enhanced Defueling Safety Case | Feasibility Workshop Tech Reports CNL) - early technical reference | 2024-04-02 | 2024-05-10 | 21 | 0 | 28 | 38 | 100% | 0.55263 | 1 | Completed
ER6666LT | W209 | W209.1415 | HYB Essential Defueling Safety Case | Populate Affected Documents List | 2024-04-02 | 2024-06-28 | 10 | 0 | 62 | 87 | 100% | 0.11494 | 1 | Completed
ER6668LT | W213 | W213.1415 | TOR Essential Defueling Safety Case | Populate Affected Documents List | 2024-04-02 | 2024-06-28 | 10 | 0 | 62 | 87 | 100% | 0.11494 | 1 | Completed
W232LT | W232 | W232.C1290 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Weld Inspection Data> - Pre Job Brief | 2024-04-03 | 2024-04-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C1440 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Lifting Integrity Faults> - Pre Job Brief | 2024-04-03 | 2024-04-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C1680 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Further Review of Shock Loaded Unit Events> - Pre Job Brief | 2024-04-03 | 2024-04-03 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C3040 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Weld Inspection Data> - Prepare Draft EAN - Part 1 | 2024-04-04 | 2024-04-23 | 14 | 0 | 14 | 19 | 100% | 0.73684 | 1 | Completed
W232LT | W232 | W232.C3050 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Lifting Integrity Faults> - Prepare Draft EAN - Part 1 | 2024-04-04 | 2024-04-23 | 14 | 0 | 14 | 19 | 100% | 0.73684 | 1 | Completed
W232LT | W232 | W232.A5680 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Further Review of Shock Loaded Unit Events> - Prepare Draft EAN - Part 1 | 2024-04-04 | 2024-04-23 | 14 | 0 | 14 | 19 | 100% | 0.73684 | 1 | Completed
W230LT | W230 | W230.1300 | HYB Enhanced Defueling Safety Case Strategy | Initial high level scope of programme | 2024-04-04 | 2024-05-07 | 5 | 0 | 23 | 33 | 100% | 0.15152 | 1 | Completed
W234LT | W234 | W234.1300 | TOR Enhanced Defueling Safety Case Strategy | Initial high level scope of programme | 2024-04-04 | 2024-05-07 | 5 | 0 | 23 | 33 | 100% | 0.15152 | 1 | Completed
W232LT | W232 | W232.C1470 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Shock Loaded Unit Events> - Issue Draft EAN to EDF for Review. | 2024-04-04 | 2024-04-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | 1970 | HRA Fuel Handling Essential Safety Case | Upload into AMS | 2024-04-05 | 2024-07-19 | 1 | 0 | 74 | 105 | 100% | 0.0095238 | 1 | Completed
ER6650LT | W226 | 1970 | HYA Fuel Handling Essential Safety Case | Upload into AMS | 2024-04-05 | 2024-07-19 | 1 | 0 | 74 | 105 | 100% | 0.0095238 | 1 | Completed
ER6378LT | W222 | 1969 | HRA Fuel Handling Essential Safety Case | Head Document Verification Complete | 2024-04-05 | 2024-04-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 1969 | HYA Fuel Handling Essential Safety Case | Head Document Verification Complete | 2024-04-05 | 2024-04-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C3060 | DNB Enhanced Safety Cases | <NEW SCOPE CN 1727><Review of Shock Loaded Unit Events> - Draft EAN Reviewed by EDF SQEP - Part 1 | 2024-04-05 | 2024-04-23 | 13 | 0 | 13 | 18 | 100% | 0.72222 | 1 | Completed
ER6666LT | W209 | W209.29570 | HYB Essential Defueling Safety Case | Verification Schedule Risk - (Risk Ref 28381) | 2024-04-08 | 2024-04-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.29580 | HYB Essential Defueling Safety Case | Risk Milestone - Verification (Risk Ref 28381) - Verification Substantially Complete | 2024-04-08 | 2024-04-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.29570 | TOR Essential Defueling Safety Case | Verification Schedule Risk - (Risk Ref 28381) | 2024-04-08 | 2024-04-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.29580 | TOR Essential Defueling Safety Case | Risk Milestone - Verification (Risk Ref 28381) - Verification Substantially Complete | 2024-04-08 | 2024-04-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1220 | HNB Enhanced Defuelling Safety Cases | Verify supporting reference <Enhanced Defueling rate EC> | 2024-04-08 | 2024-04-19 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
W232LT | W232 | W232.B4020 | DNB Enhanced Safety Cases | Gate B PRC Paper Submission | 2024-04-10 | 2024-04-10 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W230LT | W230 | W230.1860 | HYB Enhanced Defueling Safety Case Strategy | PM / CO and PCE Create Initial Plan of Work | 2024-04-11 | 2024-05-15 | 0 | 0 | 24 | 34 | 100% | 0 | 1 | Completed
W234LT | W234 | W234.1860 | TOR Enhanced Defueling Safety Case Strategy | PM / CO and PCE Create Initial Plan of Work | 2024-04-11 | 2024-05-15 | 0 | 0 | 24 | 34 | 100% | 0 | 1 | Completed
W232LT | W232 | W232.B4030 | DNB Enhanced Safety Cases | PRC Members Review PRC Documentation | 2024-04-11 | 2024-04-17 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6666LT | W209 | W209.29640 | HYB Essential Defueling Safety Case | Complete TR Statement - IFD EAN | 2024-04-12 | 2024-04-23 | 1 | 0 | 7 | 11 | 100% | 0.090909 | 1 | Completed
ER6666LT | W209 | W209.29660 | HYB Essential Defueling Safety Case | Close Out TR Comments - (Dose Band Review & Post Fault Action EAN) | 2024-04-12 | 2024-05-20 | 1 | 0 | 26 | 38 | 100% | 0.026316 | 1 | Completed
ER6666LT | W209 | W209.29690 | HYB Essential Defueling Safety Case | Complete Verification - (Failed Fuel Handling in ODR condition) | 2024-04-12 | 2024-06-12 | 1 | 0 | 41 | 61 | 100% | 0.016393 | 1 | Completed
ER6668LT | W213 | W209.29640 | TOR Essential Defueling Safety Case | Complete TR Statement - IFD EAN | 2024-04-12 | 2024-04-23 | 1 | 0 | 7 | 11 | 100% | 0.090909 | 1 | Completed
ER6668LT | W213 | W209.29660 | TOR Essential Defueling Safety Case | Close Out TR Comments - (Dose Band Review & Post Fault Action EAN) | 2024-04-12 | 2024-05-20 | 1 | 0 | 26 | 38 | 100% | 0.026316 | 1 | Completed
ER6668LT | W213 | W209.29690 | TOR Essential Defueling Safety Case | Complete Verification - (Failed Fuel Handling in ODR condition) | 2024-04-12 | 2024-06-12 | 1 | 0 | 41 | 61 | 100% | 0.016393 | 1 | Completed
ER6372LT | W203 | W203.C1270 | HNB Enhanced Defuelling Safety Cases | BE Technical review of supporting reference <Enhanced Defueling rate EC> | 2024-04-22 | 2024-06-28 | 10 | 0 | 48 | 67 | 100% | 0.14925 | 1 | Completed
W232LT | W232 | W232.A2690 | DNB Enhanced Safety Cases | Gate B PRC Paper Approval (DNB) | 2024-04-23 | 2024-04-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B4300 | DNB Enhanced Safety Cases | Hold PRC Meeting | 2024-04-23 | 2024-04-23 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.B4310 | DNB Enhanced Safety Cases | Gate B PRC Paper Approval | 2024-04-23 | 2024-04-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.29650 | HYB Essential Defueling Safety Case | Issue on CDMS - IFD EAN | 2024-04-24 | 2024-04-30 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W209.29650 | TOR Essential Defueling Safety Case | Issue on CDMS - IFD EAN | 2024-04-24 | 2024-04-30 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
W232LT | W232 | W232.C1150 | DNB Enhanced Safety Cases | <Review of Weld Inspection Data> - Summary | 2024-04-24 | 2024-09-30 | 106 | 0 | 110 | 159 | 100% | 0.66667 | 1 | Completed
W232LT | W232 | W232.C1160 | DNB Enhanced Safety Cases | <Review of Weld Inspection Data> - Prepare Draft EAN - Part 2 | 2024-04-24 | 2024-05-23 | 21 | 0 | 21 | 29 | 100% | 0.72414 | 1 | Completed
W232LT | W232 | W232.C1300 | DNB Enhanced Safety Cases | <Review of Lifting Integrity Faults> - Summary | 2024-04-24 | 2024-09-30 | 105 | 0 | 110 | 159 | 100% | 0.66038 | 1 | Completed
W232LT | W232 | W232.C1310 | DNB Enhanced Safety Cases | <Review of Lifting Integrity Faults> - Prepare Draft EAN - Part 2 | 2024-04-24 | 2024-05-13 | 21 | 0 | 12 | 19 | 100% | 1.1053 | 1 | Completed
W232LT | W232 | W232.C1450 | DNB Enhanced Safety Cases | <Review of Shock Loaded Unit Events> - Summary | 2024-04-24 | 2024-05-24 | 28 | 0 | 21 | 30 | 100% | 0.93333 | 1 | Completed
W232LT | W232 | W232.C1480 | DNB Enhanced Safety Cases | <Review of Shock Loaded Unit Events> - Draft EAN Reviewed by EDF SQEP - Part 2 | 2024-04-24 | 2024-05-03 | 8 | 0 | 8 | 9 | 100% | 0.88889 | 1 | Completed
W232LT | W232 | W232.C1540 | DNB Enhanced Safety Cases | <SCOPE NAME CHANGE CN 2615><Further Review of Shock Loaded Unit Events (Group 1)> - Summary | 2024-04-24 | 2024-10-08 | 115 | 0 | 116 | 167 | 100% | 0.68862 | 1 | Completed
W232LT | W232 | W232.C1550 | DNB Enhanced Safety Cases | <SCOPE NAME CHANGE CN 2615><Further Review of Shock Loaded Unit Events (Group 1)> - Prepare Draft EAN - Part 2 | 2024-04-24 | 2024-08-08 | 21 | 0 | 75 | 106 | 100% | 0.19811 | 1 | Completed
ER6372LT | W203 | W203.C1070 | HNB Enhanced Defuelling Safety Cases | CA PJB Held | 2024-04-25 | 2024-04-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1080 | HNB Enhanced Defuelling Safety Cases | Produce MF (as required) | 2024-04-29 | 2024-06-10 | 5 | 0 | 29 | 42 | 100% | 0.11905 | 1 | Completed
ER6372LT | W203 | W203.C1380 | HNB Enhanced Defuelling Safety Cases | Prepare the Safety Case Proposal (including OPEX Review) | 2024-04-29 | 2024-06-28 | 10 | 0 | 42 | 60 | 100% | 0.16667 | 1 | Completed
W232LT | W232 | W232.A2080 | DNB Enhanced Safety Cases | Rev 000 - Prepare the Safety Case Proposal (including OPEX Review) | 2024-05-01 | 2024-10-08 | 35 | 0 | 111 | 160 | 100% | 0.21875 | 1 | Completed
ER6698LT | W224 | W224. A1010 | HRA Enhanced Defueling Safety Case | Prepare Schedule [FEEDS TO SUMMARY SCHEDULE] | 2024-05-01 | 2024-05-28 | 5 | 0 | 17 | 27 | 100% | 0.18519 | 1 | Completed
ER6698LT | W224 | W224. A1020 | HRA Enhanced Defueling Safety Case | Prepare Cost Estimates | 2024-05-01 | 2024-05-28 | 5 | 0 | 17 | 27 | 100% | 0.18519 | 1 | Completed
ER6698LT | W224 | W224. A1030 | HRA Enhanced Defueling Safety Case | Write IRM Paper | 2024-05-01 | 2024-05-22 | 15 | 0 | 15 | 21 | 100% | 0.71429 | 1 | Completed
ER6701LT | W228 | W228. A1030 | HYA Enhanced Defueling Safety Case | Write IRM Paper | 2024-05-01 | 2024-05-22 | 15 | 0 | 15 | 21 | 100% | 0.71429 | 1 | Completed
ER6701LT | W228 | W228. A1020 | HYA Enhanced Defueling Safety Case | Prepare Cost Estimates | 2024-05-01 | 2024-05-28 | 5 | 0 | 17 | 27 | 100% | 0.18519 | 1 | Completed
ER6701LT | W228 | W228. A1010 | HYA Enhanced Defueling Safety Case | Prepare Schedule [FEEDS TO SUMMARY SCHEDULE] | 2024-05-01 | 2024-05-28 | 5 | 0 | 17 | 27 | 100% | 0.18519 | 1 | Completed
W232LT | W232 | W232.C1490 | DNB Enhanced Safety Cases | <Review of Shock Loaded Unit Events> - Address Comments from EDF Review on Draft EAN | 2024-05-07 | 2024-05-20 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
W230LT | W230 | W230.1290 | HYB Enhanced Defueling Safety Case Strategy | Update Schedule/Estimate from Risk Log & Add Provisions | 2024-05-08 | 2024-05-14 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
W234LT | W234 | W234.1290 | TOR Enhanced Defueling Safety Case Strategy | Update Schedule/Estimate from Risk Log & Add Provisions | 2024-05-08 | 2024-05-14 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6378LT | W222 | 2030 | HRA Fuel Handling Essential Safety Case | Update Verification Plan | 2024-05-09 | 2024-05-10 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6650LT | W226 | 2030 | HYA Fuel Handling Essential Safety Case | Update Verification Plan | 2024-05-09 | 2024-05-10 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6650LT | W226 | 1991 | HYA Fuel Handling Essential Safety Case | Update Proposal Peer Review | 2024-05-10 | 2024-05-14 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6378LT | W222 | 1991 | HRA Fuel Handling Essential Safety Case | Update Proposal Peer Review | 2024-05-13 | 2024-05-14 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6378LT | W222 | 2040 | HRA Fuel Handling Essential Safety Case | Secure Verification Resource | 2024-05-13 | 2024-05-13 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 2040 | HYA Fuel Handling Essential Safety Case | Secure Verification Resource | 2024-05-13 | 2024-05-13 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C1380 | DNB Enhanced Safety Cases | <Review of Lifting Integrity Faults> - TSA Internal Review of Draft EAN | 2024-05-14 | 2024-07-23 | 10 | 0 | 49 | 70 | 100% | 0.14286 | 1 | Completed
ER6378LT | W222 | 2050 | HRA Fuel Handling Essential Safety Case | Verification PJB | 2024-05-14 | 2024-05-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 2050 | HYA Fuel Handling Essential Safety Case | Verification PJB | 2024-05-14 | 2024-05-14 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | 2071 | HRA Fuel Handling Essential Safety Case | Sub-verifier(s) including GAP review (HHB OPEX) First Round | 2024-05-15 | 2024-06-05 | 15 | 0 | 15 | 21 | 100% | 0.71429 | 1 | Completed
ER6378LT | W222 | 1992 | HRA Fuel Handling Essential Safety Case | Update Proposal (Second Draft) | 2024-05-15 | 2024-05-21 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6378LT | W222 | 2068 | HRA Fuel Handling Essential Safety Case | First Round Verification - Stn Verifier Comments | 2024-05-15 | 2024-06-05 | 15 | 0 | 15 | 21 | 100% | 0.71429 | 1 | Completed
ER6378LT | W222 | 2060 | HRA Fuel Handling Essential Safety Case | Verification including GAP review (Lead Verifier)(HHB OPEX) First Round | 2024-05-15 | 2024-06-05 | 15 | 0 | 15 | 21 | 100% | 0.71429 | 1 | Completed
ER6378LT | W222 | 2070 | HRA Fuel Handling Essential Safety Case | Sub-verifier(s) including GAP review (HHB OPEX) First Round | 2024-05-15 | 2024-06-05 | 15 | 0 | 15 | 21 | 100% | 0.71429 | 1 | Completed
ER6650LT | W226 | 2071 | HYA Fuel Handling Essential Safety Case | Sub-verifier(s) including GAP review (HHB OPEX) First Round | 2024-05-15 | 2024-07-08 | 15 | 0 | 38 | 54 | 100% | 0.27778 | 1 | Completed
ER6650LT | W226 | 1992 | HYA Fuel Handling Essential Safety Case | Update Proposal (Second Draft) | 2024-05-15 | 2024-05-21 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6650LT | W226 | 2068 | HYA Fuel Handling Essential Safety Case | First Round Verification - Stn Verifier Comments | 2024-05-15 | 2024-07-08 | 15 | 0 | 38 | 54 | 100% | 0.27778 | 1 | Completed
ER6650LT | W226 | 2060 | HYA Fuel Handling Essential Safety Case | Verification including GAP review (Lead Verifier)(HHB OPEX) First Round | 2024-05-15 | 2024-07-01 | 15 | 0 | 32 | 47 | 100% | 0.31915 | 1 | Completed
ER6650LT | W226 | 2070 | HYA Fuel Handling Essential Safety Case | Sub-verifier(s) including GAP review (HHB OPEX) First Round | 2024-05-15 | 2024-07-08 | 15 | 0 | 38 | 54 | 100% | 0.27778 | 1 | Completed
W230LT | W230 | W230.1280 | HYB Enhanced Defueling Safety Case Strategy | Draft / Add Data to PRC/IMS2 Paper | 2024-05-15 | 2024-06-03 | 5 | 0 | 13 | 19 | 100% | 0.26316 | 1 | Completed
W234LT | W234 | W234.1280 | TOR Enhanced Defueling Safety Case Strategy | Draft / Add Data to PRC/IMS2 Paper | 2024-05-15 | 2024-06-03 | 5 | 0 | 13 | 19 | 100% | 0.26316 | 1 | Completed
W230LT | W230 | W230.1880 | HYB Enhanced Defueling Safety Case Strategy | Appoint CO / AE / RE | 2024-05-16 | 2024-05-16 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W234LT | W234 | W234.1880 | TOR Enhanced Defueling Safety Case Strategy | Appoint CO / AE / RE | 2024-05-16 | 2024-05-16 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W230LT | W230 | W230.1890 | HYB Enhanced Defueling Safety Case Strategy | Key Stakeholders Identified | 2024-05-17 | 2024-05-17 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W234LT | W234 | W234.1890 | TOR Enhanced Defueling Safety Case Strategy | Key Stakeholders Identified | 2024-05-17 | 2024-05-17 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C1500 | DNB Enhanced Safety Cases | <Review of Shock Loaded Unit Events> - Issue Final EAN | 2024-05-20 | 2024-05-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A4990 | DNB Enhanced Safety Cases | Lessons Learned Workshop - FPU Safety Case Ph 3 NSRS Approved | 2024-05-21 | 2024-05-21 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.1200 | HRA Fuel Handling Essential Safety Case | Verification and SAs of the case (using BARRIER MODEL) (PART 2 - IMPACT from EVENT RECOVERY) | 2024-05-21 | 2024-07-16 | 40 | 0 | 40 | 56 | 100% | 0.71429 | 1 | Completed
ER6650LT | W226 | W226.1200 | HYA Fuel Handling Essential Safety Case | Verification of the case (using BARRIER MODEL) (PART 2 - IMPACT from EVENT RECOVERY) | 2024-05-21 | 2024-07-16 | 40 | 0 | 40 | 56 | 100% | 0.71429 | 1 | Completed
ER6650LT | W226 | W226.3020 | HYA Fuel Handling Essential Safety Case | Lesson Learn - Event Recovery Phase | 2024-05-21 | 2024-05-21 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C1510 | DNB Enhanced Safety Cases | <Review of Shock Loaded Unit Events> - EAN Completed and Uploaded to CDMS | 2024-05-21 | 2024-05-24 | 10 | 0 | 3 | 3 | 100% | 3.3333 | 1 | Completed
ER6666LT | W209 | W209.29670 | HYB Essential Defueling Safety Case | Complete TR Statement - (Dose Band Review & Post Fault Action EAN) | 2024-05-21 | 2024-05-23 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6668LT | W213 | W209.29670 | TOR Essential Defueling Safety Case | Complete TR Statement - (Dose Band Review & Post Fault Action EAN) | 2024-05-21 | 2024-05-23 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
ER6378LT | W222 | W222.1210 | HRA Fuel Handling Essential Safety Case | EVENT RECOVERY MILESTONE - AMS Milestone - EC Ready for Review - Activity No 2020 | 2024-05-21 | 2024-05-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.1210 | HYA Fuel Handling Essential Safety Case | EVENT RECOVERY MILESTONE - AMS Milestone - EC Ready for Review - Activity No 2020 | 2024-05-21 | 2024-05-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 2020 | HYA Fuel Handling Essential Safety Case | AMS Milestone - Ready for Review | 2024-05-21 | 2024-05-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A27485 | HRA Fuel Handling Essential Safety Case | AMS Ready for Review | 2024-05-21 | 2024-05-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27485 | HYA Fuel Handling Essential Safety Case | AMS Ready for Review | 2024-05-21 | 2024-05-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6698LT | W224 | W224. A1040 | HRA Enhanced Defueling Safety Case | IRM Paper stakeholder sign off | 2024-05-23 | 2024-06-07 | 5 | 0 | 11 | 15 | 100% | 0.33333 | 1 | Completed
ER6701LT | W228 | W228. A1040 | HYA Enhanced Defueling Safety Case | IRM Paper stakeholder sign off | 2024-05-23 | 2024-06-07 | 5 | 0 | 11 | 15 | 100% | 0.33333 | 1 | Completed
W232LT | W232 | W232.C1520 | DNB Enhanced Safety Cases | <Review of Shock Loaded Unit Events> - EAN Completed | 2024-05-24 | 2024-05-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C1230 | DNB Enhanced Safety Cases | <Review of Weld Inspection Data> - TSA Internal Review of Draft EAN | 2024-05-24 | 2024-06-21 | 10 | 0 | 19 | 28 | 100% | 0.35714 | 1 | Completed
ER6666LT | W209 | W209.29680 | HYB Essential Defueling Safety Case | Issue on CDMS - (Dose Band Review & Post Fault Action EAN) | 2024-05-24 | 2024-06-03 | 5 | 0 | 6 | 10 | 100% | 0.5 | 1 | Completed
ER6668LT | W213 | W209.29680 | TOR Essential Defueling Safety Case | Issue on CDMS - (Dose Band Review & Post Fault Action EAN) | 2024-05-24 | 2024-06-03 | 5 | 0 | 6 | 10 | 100% | 0.5 | 1 | Completed
ER6698LT | W224 | W224.1340 | HRA Enhanced Defueling Safety Case | RFS | 2024-05-28 | 2024-06-07 | 10 | 0 | 9 | 10 | 100% | 1 | 1 | Completed
ER6701LT | W228 | W228.1340 | HYA Enhanced Defueling Safety Case | RFS | 2024-05-28 | 2024-06-07 | 10 | 0 | 9 | 10 | 100% | 1 | 1 | Completed
ER6378LT | W222 | W222.3020 | HRA Fuel Handling Essential Safety Case | Lesson Learn - Event Recovery Phase | 2024-05-28 | 2024-05-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1495 | HYB Essential Defueling Safety Case | Final Verification - (Including = CLAIM 7 Update and Detailed Check) | 2024-05-31 | 2024-09-18 | 20 | 0 | 78 | 110 | 100% | 0.18182 | 1 | Completed
ER6668LT | W213 | W213.1495 | TOR Essential Defueling Safety Case | Final Verification - (Including = CLAIM 7 Update and Detailed Check) | 2024-05-31 | 2024-09-18 | 20 | 0 | 78 | 110 | 100% | 0.18182 | 1 | Completed
ER6698LT | W224 | W224.1250 | HRA Enhanced Defueling Safety Case | RFS | 2024-06-03 | 2024-06-14 | 1 | 0 | 10 | 11 | 100% | 0.090909 | 1 | Completed
ER6701LT | W228 | W228.3810 | HYA Enhanced Defueling Safety Case | WBS Cost Summary Analysis in support of Tie Bar Buckling | 2024-06-03 | 2025-02-03 | 162 | 0 | 171 | 245 | 100% | 0.66122 | 1 | Completed
ER6701LT | W228 | W228.1250 | HYA Enhanced Defueling Safety Case | RFS | 2024-06-03 | 2024-06-14 | 1 | 0 | 10 | 11 | 100% | 0.090909 | 1 | Completed
ER6666LT | W209 | W209.A31290 | HYB Essential Defueling Safety Case | Technical Review of PSA Documentation | 2024-06-04 | 2024-06-17 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6668LT | W213 | W213.A31290 | TOR Essential Defueling Safety Case | Technical Review of PSA Documentation | 2024-06-04 | 2024-06-17 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
W230LT | W230 | W230.1320 | HYB Enhanced Defueling Safety Case Strategy | Prepare Draft Project Definition Document (PDD) | 2024-06-04 | 2024-06-07 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
W230LT | W230 | W230.1970 | HYB Enhanced Defueling Safety Case Strategy | Verified by TSA | 2024-06-04 | 2024-06-17 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
W234LT | W234 | W234.1320 | TOR Enhanced Defueling Safety Case Strategy | Prepare Draft Project Definition Document (PDD) | 2024-06-04 | 2024-06-07 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
W234LT | W234 | W234.1970 | TOR Enhanced Defueling Safety Case Strategy | Verified by TSA | 2024-06-04 | 2024-06-17 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6378LT | W222 | 2072 | HRA Fuel Handling Essential Safety Case | Respond to First Round Comments | 2024-06-06 | 2024-07-08 | 23 | 0 | 23 | 32 | 100% | 0.71875 | 1 | Completed
W230LT | W230 | W230.1330 | HYB Enhanced Defueling Safety Case Strategy | PCL Validate & Approve Baseline Package for PRC Submission | 2024-06-10 | 2024-06-11 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
W234LT | W234 | W234.1330 | TOR Enhanced Defueling Safety Case Strategy | PCL Validate & Approve Baseline Package for PRC Submission | 2024-06-10 | 2024-06-11 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6372LT | W203 | W203.C1110 | HNB Enhanced Defuelling Safety Cases | Issue MF (as required) | 2024-06-10 | 2024-06-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1160 | HNB Enhanced Defuelling Safety Cases | Produce draft NSRS (using BARRIER MODEL) | 2024-06-11 | 2024-06-14 | 4 | 0 | 4 | 3 | 100% | 1.3333 | 1 | Completed
ER6372LT | W203 | W203.C1120 | HNB Enhanced Defuelling Safety Cases | Categorisation by RE / Station | 2024-06-11 | 2024-06-12 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6666LT | W209 | W209.29700 | HYB Essential Defueling Safety Case | Issue on CDMS - (Failed Fuel Handling in ODR condition) | 2024-06-12 | 2024-06-12 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W209.29700 | TOR Essential Defueling Safety Case | Issue on CDMS - (Failed Fuel Handling in ODR condition) | 2024-06-12 | 2024-06-12 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6698LT | W224 | W224. A1050 | HRA Enhanced Defueling Safety Case | Gate A PRC Paper Submission | 2024-06-12 | 2024-06-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6701LT | W228 | W228. A1050 | HYA Enhanced Defueling Safety Case | Gate A PRC Paper Submission | 2024-06-12 | 2024-06-12 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W230LT | W230 | W230.1340 | HYB Enhanced Defueling Safety Case Strategy | Gate A PRC Paper Submission | 2024-06-12 | 2024-06-12 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W234LT | W234 | W234.1340 | TOR Enhanced Defueling Safety Case Strategy | Gate A PRC Paper Submission | 2024-06-12 | 2024-06-12 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W230LT | W230 | W230.1360 | HYB Enhanced Defueling Safety Case Strategy | PRC Members Review PRC/IMS2 Documentation | 2024-06-13 | 2024-06-24 | 8 | 0 | 8 | 11 | 100% | 0.72727 | 1 | Completed
W234LT | W234 | W234.1360 | TOR Enhanced Defueling Safety Case Strategy | PRC Members Review PRC/IMS2 Documentation | 2024-06-13 | 2024-06-24 | 8 | 0 | 8 | 11 | 100% | 0.72727 | 1 | Completed
ER6372LT | W203 | W203.C1200 | HNB Enhanced Defuelling Safety Cases | Station comments on NSRS | 2024-06-17 | 2024-06-18 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6372LT | W203 | W203.C1210 | HNB Enhanced Defuelling Safety Cases | Key Stakeholders (Peer) comments on NSRS (as required) | 2024-06-17 | 2024-06-18 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6372LT | W203 | W203.C1250 | HNB Enhanced Defuelling Safety Cases | Develop plan with further iterations | 2024-06-17 | 2024-06-26 | 10 | 0 | 7 | 9 | 100% | 1.1111 | 1 | Completed
W230LT | W230 | W230.1980 | HYB Enhanced Defueling Safety Case Strategy | Issued to EDF for Technical Reviews | 2024-06-17 | 2024-06-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W234LT | W234 | W234.1980 | TOR Enhanced Defueling Safety Case Strategy | Issued to EDF for Technical Reviews | 2024-06-17 | 2024-06-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A31300 | HYB Essential Defueling Safety Case | Supplier Update and Issue PSA Documentation | 2024-06-18 | 2024-06-24 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6668LT | W213 | W213.A31300 | TOR Essential Defueling Safety Case | Supplier Update and Issue PSA Documentation | 2024-06-18 | 2024-06-24 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
W230LT | W230 | W230.1990 | HYB Enhanced Defueling Safety Case Strategy | Tech Review by EDF SQEP | 2024-06-18 | 2024-06-28 | 9 | 0 | 9 | 10 | 100% | 0.9 | 1 | Completed
W234LT | W234 | W234.1990 | TOR Enhanced Defueling Safety Case Strategy | Tech Review by EDF SQEP | 2024-06-18 | 2024-06-28 | 9 | 0 | 9 | 10 | 100% | 0.9 | 1 | Completed
ER6372LT | W203 | W203.C1230 | HNB Enhanced Defuelling Safety Cases | INSA Resource Identified | 2024-06-18 | 2024-06-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1150 | HNB Enhanced Defuelling Safety Cases | INSA agree MF (as required) *(EC375412)* | 2024-06-20 | 2024-06-20 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1180 | HNB Enhanced Defuelling Safety Cases | INSA Approval Date Identified | 2024-06-20 | 2024-06-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1190 | HNB Enhanced Defuelling Safety Cases | Provide Provisional NSC Date (as required) | 2024-06-20 | 2024-06-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C1170 | DNB Enhanced Safety Cases | <Review of Weld Inspection Data> - Issue Draft EAN to EDF for Review. | 2024-06-21 | 2024-06-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1240 | HNB Enhanced Defuelling Safety Cases | INA comments on NSRS | 2024-06-24 | 2024-06-28 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6698LT | W224 | W224.1010 | HRA Enhanced Defueling Safety Case | Sunk Cost (Mar - Dec 24) | 2024-06-24 | 2024-12-31 | 1 | 0 | 133 | 190 | 100% | 0.0052632 | 1 | Completed
ER6698LT | W224 | W224.A1010 | HRA Enhanced Defueling Safety Case | Gate A for Defuelling Programme Enhancement ECs (HH1) | 2024-06-25 | 2024-06-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6701LT | W228 | W228.A1010 | HYA Enhanced Defueling Safety Case | Gate A for Defuelling Programme Enhancement ECs (HH1) | 2024-06-25 | 2024-06-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6698LT | W224 | W224.A1061 | HRA Enhanced Defueling Safety Case | Hold PRC | 2024-06-25 | 2024-06-25 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A31310 | HYB Essential Defueling Safety Case | Complete TR Form and PSA Documentation to CDMS | 2024-06-25 | 2024-07-31 | 10 | 0 | 27 | 36 | 100% | 0.27778 | 1 | Completed
ER6668LT | W213 | W213.A31310 | TOR Essential Defueling Safety Case | Complete TR Form and PSA Documentation to CDMS | 2024-06-25 | 2024-07-31 | 10 | 0 | 27 | 36 | 100% | 0.27778 | 1 | Completed
ER6701LT | W228 | W228.A1061 | HYA Enhanced Defueling Safety Case | Hold PRC | 2024-06-25 | 2024-06-25 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W230LT | W230 | W230.1390 | HYB Enhanced Defueling Safety Case Strategy | Hold PRC Meeting | 2024-06-25 | 2024-06-25 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W234LT | W234 | W234.1390 | TOR Enhanced Defueling Safety Case Strategy | Hold PRC Meeting | 2024-06-25 | 2024-06-25 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6698LT | W224 | W224. A1070 | HRA Enhanced Defueling Safety Case | Gate A PRC Paper Approval | 2024-06-25 | 2024-06-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6701LT | W228 | W228. A1070 | HYA Enhanced Defueling Safety Case | Gate A PRC Paper Approval | 2024-06-25 | 2024-06-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W230LT | W230 | W230.1120 | HYB Enhanced Defueling Safety Case Strategy | Gate A Approved | 2024-06-25 | 2024-06-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W230LT | W230 | W230.1350 | HYB Enhanced Defueling Safety Case Strategy | Gate A PRC Paper Approval | 2024-06-25 | 2024-06-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W234LT | W234 | W234.1120 | TOR Enhanced Defueling Safety Case Strategy | Gate A Approved | 2024-06-25 | 2024-06-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W234LT | W234 | W234.1350 | TOR Enhanced Defueling Safety Case Strategy | Gate A PRC Paper Approval | 2024-06-25 | 2024-06-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1330 | HNB Enhanced Defuelling Safety Cases | Verifier PJB Held | 2024-06-26 | 2024-06-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6698LT | W224 | W224.A1160 | HRA Enhanced Defueling Safety Case | Gate A-B Programme Management External - Cost Summary | 2024-06-26 | 2025-02-12 | 127 | 0 | 162 | 231 | 100% | 0.54978 | 1 | Completed
ER6698LT | W224 | W224.A1170 | HRA Enhanced Defueling Safety Case | Gate A-B Programme Management Internal - Cost Summary | 2024-06-26 | 2025-02-12 | 0 | 0 | 162 | 231 | 100% | 0 | 1 | Completed
ER6698LT | W224 | W224. A1080 | HRA Enhanced Defueling Safety Case | Funds Released | 2024-06-26 | 2024-07-10 | 12 | 0 | 11 | 14 | 100% | 0.85714 | 1 | Completed
ER6701LT | W228 | W228. A1080 | HYA Enhanced Defueling Safety Case | Funds Released | 2024-06-26 | 2024-07-09 | 12 | 0 | 10 | 13 | 100% | 0.92308 | 1 | Completed
ER6701LT | W228 | W228.A1170 | HYA Enhanced Defueling Safety Case | Gate A-B Programme Management Internal - Cost Summary | 2024-06-26 | 2025-02-12 | 0 | 0 | 162 | 231 | 100% | 0 | 1 | Completed
ER6701LT | W228 | W228.A1160 | HYA Enhanced Defueling Safety Case | Gate A-B Programme Management External - Cost Summary | 2024-06-26 | 2025-02-12 | 127 | 0 | 162 | 231 | 100% | 0.54978 | 1 | Completed
W230LT | W230 | W230.1380 | HYB Enhanced Defueling Safety Case Strategy | Modify Estimate, Schedule & Risk Log as Required | 2024-06-26 | 2024-06-28 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
W234LT | W234 | W234.1380 | TOR Enhanced Defueling Safety Case Strategy | Modify Estimate, Schedule & Risk Log as Required | 2024-06-26 | 2024-06-28 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
W230LT | W230 | W230.1370 | HYB Enhanced Defueling Safety Case Strategy | Modify PRC Paper as Required | 2024-06-27 | 2024-06-28 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
W234LT | W234 | W234.1370 | TOR Enhanced Defueling Safety Case Strategy | Modify PRC Paper as Required | 2024-06-27 | 2024-06-28 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6666LT | W209 | W209.A29160 | HYB Essential Defueling Safety Case | Verify Defuelling Worker Risk Assessment EAN & Issue for Technical Review | 2024-06-28 | 2024-07-26 | 5 | 0 | 21 | 28 | 100% | 0.17857 | 1 | Completed
ER6668LT | W213 | W213.A29160 | TOR Essential Defueling Safety Case | Verify Defuelling Worker Risk Assessment EAN & Issue for Technical Review | 2024-06-28 | 2024-07-26 | 5 | 0 | 21 | 28 | 100% | 0.17857 | 1 | Completed
ER6372LT | W203 | W203.C1280 | HNB Enhanced Defuelling Safety Cases | Issue final NSRS | 2024-06-28 | 2024-06-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1290 | HNB Enhanced Defuelling Safety Cases | Station agree NSRS *(EC375412)* | 2024-06-28 | 2024-06-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1340 | HNB Enhanced Defuelling Safety Cases | Consolidate & issue to stakeholders & suppliers agreed NSRS (as required) | 2024-06-28 | 2024-06-28 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1260 | HNB Enhanced Defuelling Safety Cases | Incorporate INA, Station, ED (peer) comments | 2024-06-28 | 2024-06-28 | 2 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1300 | HNB Enhanced Defuelling Safety Cases | Key Stakeholders agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2024-06-28 | 2024-06-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1350 | HNB Enhanced Defuelling Safety Cases | Issue agreed work programme to stakeholders & suppliers | 2024-06-28 | 2024-06-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1320 | HNB Enhanced Defuelling Safety Cases | INA agree NSRS | 2024-06-28 | 2024-06-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A4190 | HNB Enhanced Defuelling Safety Cases | All key supporting technical references complete - Enhanced Defueling rate EC | 2024-06-28 | 2024-06-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1360 | HNB Enhanced Defuelling Safety Cases | Supporting reference <Enhanced Defueling rate EC> approved | 2024-06-28 | 2024-06-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1370 | HNB Enhanced Defuelling Safety Cases | All supporting references completed | 2024-06-28 | 2024-06-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C1330 | DNB Enhanced Safety Cases | <Review of Lifting Integrity Faults> - Draft EAN Reviewed by EDF SQEP | 2024-07-01 | 2024-08-09 | 10 | 0 | 30 | 39 | 100% | 0.25641 | 1 | Completed
ER6650LT | W226 | 2072 | HYA Fuel Handling Essential Safety Case | Respond to First Round Comments | 2024-07-01 | 2024-07-08 | 6 | 0 | 6 | 7 | 100% | 0.85714 | 1 | Completed
W232LT | W232 | W232.A3050 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 2164> Rev 000 - ONR Approval of Safety Case (Letter sent to initiate) EC 374183 KDM | 2024-07-01 | 2024-07-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A3060 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 2164> Rev 000 - KDM - ONR Agree/Acknowledge Safety Case EC 374183 KDM | 2024-07-01 | 2024-07-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A5550 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 2164> Rev 001 - ONR Approval of Safety Case (Letter sent to initiate) EC 374183 KDM | 2024-07-01 | 2024-07-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A5560 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 2164> Rev 001 - KDM - ONR Agree/Acknowledge Safety Case EC 374183 KDM | 2024-07-01 | 2024-07-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6698LT | W224 | W224.1410 | HRA Enhanced Defueling Safety Case | Contract Award | 2024-07-01 | 2024-07-12 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6701LT | W228 | W228.1410 | HYA Enhanced Defueling Safety Case | Contract Award | 2024-07-01 | 2024-07-12 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
W772LT | W772 | W772LT.A1260 | DNB Pull Harder Safety Case | Mod Requested, Identify RE and EC Request Raised and Screened | 2024-07-01 | 2024-07-25 | 19 | 0 | 19 | 24 | 100% | 0.79167 | 1 | Completed
W772LT | W772 | W772LT.A2200 | DNB Pull Harder Safety Case | Project Start | 2024-07-01 | 2024-07-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.D2080 | DNB Pull Harder Safety Case | Project Management - Pre Gate A | 2024-07-01 | 2024-10-04 | 104 | 0 | 68 | 95 | 100% | 1.0947 | 1 | Completed
W772LT | W772 | W772LT.D2110 | DNB Pull Harder Safety Case | Technical Support - Pre Gate A | 2024-07-01 | 2024-10-04 | 104 | 0 | 68 | 95 | 100% | 1.0947 | 1 | Completed
ER6698LT | W224 | W224.1280 | HRA Enhanced Defueling Safety Case | EDF Review and contract awards | 2024-07-03 | 2024-07-26 | 15 | 0 | 18 | 23 | 100% | 0.65217 | 1 | Completed
ER6701LT | W228 | W228.1280 | HYA Enhanced Defueling Safety Case | EDF Review and contract awards | 2024-07-03 | 2024-07-26 | 1 | 0 | 18 | 23 | 100% | 0.043478 | 1 | Completed
ER6701LT | W228 | W228.3740 | HYA Enhanced Defueling Safety Case | EC Register | 2024-07-05 | 2024-07-19 | 10 | 0 | 11 | 14 | 100% | 0.71429 | 1 | Completed
ER6698LT | W224 | W224.3740 | HRA Enhanced Defueling Safety Case | EC Register | 2024-07-05 | 2024-07-15 | 10 | 0 | 5 | 10 | 100% | 1 | 1 | Completed
ER6372LT | W203 | W203.C1400 | HNB Enhanced Defuelling Safety Cases | Issue to CO & Station for comments | 2024-07-05 | 2024-07-05 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6698LT | W224 | W224.1190 | HRA Enhanced Defueling Safety Case | RFS - Trip Function | 2024-07-08 | 2024-08-09 | 10 | 0 | 25 | 32 | 100% | 0.3125 | 1 | Completed
ER6701LT | W228 | W228.1190 | HYA Enhanced Defueling Safety Case | RFS - Trip Function | 2024-07-08 | 2024-08-09 | 10 | 0 | 25 | 32 | 100% | 0.3125 | 1 | Completed
ER6372LT | W203 | W203.D1390 | HNB Enhanced Defuelling Safety Cases | Mod requested, Initiate EC, identify RE, register EC & identify milestones in AMS | 2024-07-08 | 2024-07-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1470 | HNB Enhanced Defuelling Safety Cases | Raise Engineering Request (as required) | 2024-07-08 | 2024-07-15 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6650LT | W226 | 2075 | HYA Fuel Handling Essential Safety Case | Station Verifiers (HHB OPEX) Second Round | 2024-07-08 | 2024-07-16 | 7 | 0 | 7 | 8 | 100% | 0.875 | 1 | Completed
ER6650LT | W226 | 2076 | HYA Fuel Handling Essential Safety Case | Lead Verifier Second Round | 2024-07-08 | 2024-07-16 | 7 | 0 | 7 | 8 | 100% | 0.875 | 1 | Completed
ER6650LT | W226 | 2074 | HYA Fuel Handling Essential Safety Case | Sub-verifier(s) including GAP review (HHB OPEX) Second Round | 2024-07-08 | 2024-07-16 | 7 | 0 | 7 | 8 | 100% | 0.875 | 1 | Completed
ER6650LT | W226 | 2073 | HYA Fuel Handling Essential Safety Case | Sub-verifier(s) including GAP review (HHB OPEX) Second Round | 2024-07-08 | 2024-07-16 | 10 | 0 | 7 | 8 | 100% | 1.25 | 1 | Completed
ER6650LT | W226 | 2082 | HYA Fuel Handling Essential Safety Case | CTO Civils, Nuclear Liabilities, Environmental (GEM), Specialist Assessment(s) | 2024-07-08 | 2024-07-16 | 7 | 0 | 7 | 8 | 100% | 0.875 | 1 | Completed
ER6650LT | W226 | 2081 | HYA Fuel Handling Essential Safety Case | HYA Nuclear Safety, Env, Rad Protection, Radwaste, Ops, Emergency Arrangements, Specialist Assessment(s) | 2024-07-08 | 2024-07-16 | 7 | 0 | 7 | 8 | 100% | 0.875 | 1 | Completed
ER6650LT | W226 | 2080 | HYA Fuel Handling Essential Safety Case | HRA Nuclear Safety, Env, Rad Protection, Radwaste, Ops, Emergency Arrangements,Chemistry,Specialist Assessment(s) | 2024-07-08 | 2024-07-16 | 7 | 0 | 7 | 8 | 100% | 0.875 | 1 | Completed
ER6378LT | W222 | 2075 | HRA Fuel Handling Essential Safety Case | Station Verifiers (HHB OPEX) Second Round | 2024-07-09 | 2024-07-16 | 10 | 0 | 5 | 7 | 100% | 1.4286 | 1 | Completed
ER6378LT | W222 | 2076 | HRA Fuel Handling Essential Safety Case | Lead Verifier Second Round | 2024-07-09 | 2024-07-16 | 10 | 0 | 5 | 7 | 100% | 1.4286 | 1 | Completed
ER6378LT | W222 | 2074 | HRA Fuel Handling Essential Safety Case | Sub-verifier(s) including GAP review (HHB OPEX) Second Round | 2024-07-09 | 2024-07-16 | 10 | 0 | 5 | 7 | 100% | 1.4286 | 1 | Completed
ER6378LT | W222 | 2073 | HRA Fuel Handling Essential Safety Case | Sub-verifier(s) including GAP review (HHB OPEX) Second Round | 2024-07-09 | 2024-07-16 | 10 | 0 | 6 | 7 | 100% | 1.4286 | 1 | Completed
ER6378LT | W222 | 2082 | HRA Fuel Handling Essential Safety Case | CTO Civils, Nuclear Liabilities, Environmental (GEM), Specialist Assessment(s) | 2024-07-09 | 2024-07-16 | 10 | 0 | 5 | 7 | 100% | 1.4286 | 1 | Completed
ER6378LT | W222 | 2081 | HRA Fuel Handling Essential Safety Case | HYA Nuclear Safety, Env, Rad Protection, Radwaste, Ops, Emergency Arrangements, Specialist Assessment(s) | 2024-07-09 | 2024-07-16 | 10 | 0 | 5 | 7 | 100% | 1.4286 | 1 | Completed
ER6378LT | W222 | 2080 | HRA Fuel Handling Essential Safety Case | HRA Nuclear Safety, Env, Rad Protection, Radwaste, Ops, Emergency Arrangements,Chemistry,Specialist Assessment(s) | 2024-07-09 | 2024-07-16 | 10 | 0 | 5 | 7 | 100% | 1.4286 | 1 | Completed
W230LT | W230 | W230.3710 | HYB Enhanced Defueling Safety Case Strategy | Tech Review by EDF SQEP (Continued) | 2024-07-12 | 2024-07-18 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
W230LT | W230 | W230.3720 | HYB Enhanced Defueling Safety Case Strategy | ## Technical Development / Project Management - Gate A - D - (Cost Summary) ## | 2024-07-12 | 2024-12-20 | 115 | 0 | 115 | 161 | 100% | 0.71429 | 1 | Completed
W234LT | W234 | W234.3710 | TOR Enhanced Defueling Safety Case Strategy | Tech Review by EDF SQEP (Continued) | 2024-07-12 | 2024-07-18 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
W234LT | W234 | W234.3720 | TOR Enhanced Defueling Safety Case Strategy | ## Technical Development / Project Management - Gate A - D - (Cost Summary) ## | 2024-07-12 | 2024-12-20 | 115 | 0 | 115 | 161 | 100% | 0.71429 | 1 | Completed
ER6372LT | W203 | W203.D1680 | HNB Enhanced Defuelling Safety Cases | CO & CA appointed | 2024-07-15 | 2024-07-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1690 | HNB Enhanced Defuelling Safety Cases | Key Stakeholders Identified | 2024-07-15 | 2024-07-15 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 2150 | HYA Fuel Handling Essential Safety Case | PJB with INA | 2024-07-15 | 2024-07-15 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 2140 | HYA Fuel Handling Essential Safety Case | Re-attach to ADL | 2024-07-15 | 2024-07-16 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6698LT | W224 | W224.1260 | HRA Enhanced Defueling Safety Case | PJB | 2024-07-15 | 2024-07-19 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6701LT | W228 | W228.1260 | HYA Enhanced Defueling Safety Case | PJB | 2024-07-15 | 2024-07-19 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6378LT | W222 | W222.A4720 | HRA Fuel Handling Essential Safety Case | Issue to CO & Station for comments | 2024-07-16 | 2024-07-16 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.A29170 | HYB Essential Defueling Safety Case | Technical Review of Defuelling Worker Risk Assessment EAN | 2024-07-16 | 2024-07-31 | 0 | 0 | 12 | 15 | 100% | 0 | 1 | Completed
ER6668LT | W213 | W213.A29170 | TOR Essential Defueling Safety Case | Technical Review of Defuelling Worker Risk Assessment EAN | 2024-07-16 | 2024-07-31 | 10 | 0 | 12 | 15 | 100% | 0.66667 | 1 | Completed
ER6372LT | W203 | W203.D1460 | HNB Enhanced Defuelling Safety Cases | Develop initial programme plan using mandatory template | 2024-07-16 | 2024-07-22 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6698LT | W224 | W224.3720 | HRA Enhanced Defueling Safety Case | NSRS | 2024-07-16 | 2024-07-29 | 49 | 0 | 10 | 13 | 100% | 3.7692 | 1 | Completed
ER6650LT | W226 | 2170 | HYA Fuel Handling Essential Safety Case | *****INSA****** | 2024-07-17 | 2024-08-29 | 30 | 0 | 31 | 43 | 100% | 0.69767 | 1 | Completed
ER6378LT | W222 | W222.A4680 | HRA Fuel Handling Essential Safety Case | Incorporate all stakeholder comments and Final Sign Off | 2024-07-17 | 2024-07-17 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A4740 | HRA Fuel Handling Essential Safety Case | Final Verification - Statement Issued | 2024-07-17 | 2024-07-17 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A4970 | HRA Fuel Handling Essential Safety Case | INSA review & iteration of comments (using BARRIER MODEL) | 2024-07-17 | 2024-08-27 | 25 | 0 | 28 | 41 | 100% | 0.60976 | 1 | Completed
ER6378LT | W222 | W222.A4990 | HRA Fuel Handling Essential Safety Case | DA (Authorised Designer) Approval of CAT1 Safety Case | 2024-07-17 | 2024-07-23 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6650LT | W226 | W226.A4740 | HYA Fuel Handling Essential Safety Case | Final Verification | 2024-07-17 | 2024-07-17 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A4680 | HYA Fuel Handling Essential Safety Case | Incorporate all stakeholder comments and Final Sign Off | 2024-07-17 | 2024-07-17 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.1130 | HRA Fuel Handling Essential Safety Case | Safety Case Development Costs - INSA Phase (C to D ) ##Cost Summary## | 2024-07-17 | 2024-09-18 | 65 | 0 | 45 | 63 | 100% | 1.0317 | 1 | Completed
ER6378LT | W222 | W222.1140 | HRA Fuel Handling Essential Safety Case | Project Management Costs - INSA Phase (C to D ) ##Cost Summary## | 2024-07-17 | 2024-09-18 | 65 | 0 | 45 | 63 | 100% | 1.0317 | 1 | Completed
ER6650LT | W226 | 2100 | HYA Fuel Handling Essential Safety Case | CO Endorsed | 2024-07-17 | 2024-07-17 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 2110 | HYA Fuel Handling Essential Safety Case | Stn RE Endorsed | 2024-07-17 | 2024-07-17 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A4710 | HRA Fuel Handling Essential Safety Case | Submit for approval - Categoriser ratifies; RE/CO endorsement | 2024-07-17 | 2024-07-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A4960 | HRA Fuel Handling Essential Safety Case | Verified Draft Available for INSA (T-7) ECs(HRA-363840) - HRA Defuelling Fuel Handling Essential SC | 2024-07-17 | 2024-07-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A4960 | HYA Fuel Handling Essential Safety Case | Verified Draft Available for INSA (T-7) ECs(HYA-363839) - HYA Defuelling Fuel Handling Essential SC | 2024-07-17 | 2024-07-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A4720 | HYA Fuel Handling Essential Safety Case | Issue to CO & Station for comments | 2024-07-17 | 2024-07-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A4710 | HYA Fuel Handling Essential Safety Case | Submit for approval - Categoriser ratifies; RE/CO endorsement | 2024-07-17 | 2024-07-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A4990 | HYA Fuel Handling Essential Safety Case | DA (Authorised Designer) Approval of CAT1 Safety Case | 2024-07-18 | 2024-07-24 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6650LT | W226 | W226.A4970 | HYA Fuel Handling Essential Safety Case | INSA review & iteration of comments (using BARRIER MODEL) | 2024-07-18 | 2024-08-29 | 25 | 0 | 30 | 42 | 100% | 0.59524 | 1 | Completed
ER6650LT | W226 | W226.1130 | HYA Fuel Handling Essential Safety Case | Safety Case Development Costs - INSA Phase (C to D ) ##Cost Summary## | 2024-07-18 | 2024-09-18 | 64 | 0 | 44 | 62 | 100% | 1.0323 | 1 | Completed
ER6650LT | W226 | W226.1140 | HYA Fuel Handling Essential Safety Case | Project Management Costs - INSA Phase (C to D ) ##Cost Summary## | 2024-07-18 | 2024-09-18 | 64 | 0 | 44 | 62 | 100% | 1.0323 | 1 | Completed
ER6378LT | W222 | 1971 | HRA Fuel Handling Essential Safety Case | Issue Head Document onto CDMS | 2024-07-18 | 2024-07-19 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6650LT | W226 | 1971 | HYA Fuel Handling Essential Safety Case | Issue Head Document onto CDMS | 2024-07-18 | 2024-07-19 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
W230LT | W230 | W230.2000 | HYB Enhanced Defueling Safety Case Strategy | TSA Addressess Comments | 2024-07-19 | 2024-11-26 | 10 | 0 | 92 | 130 | 100% | 0.076923 | 1 | Completed
W772LT | W772 | W772LT.A1200 | DNB Pull Harder Safety Case | Initiate and Register EC and identify Milestones in AMS EC 375698<DNB Pull Harder SC> | 2024-07-19 | 2024-07-26 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
W234LT | W234 | W234.2000 | TOR Enhanced Defueling Safety Case Strategy | TSA Addressess Comments | 2024-07-19 | 2024-11-26 | 10 | 0 | 92 | 130 | 100% | 0.076923 | 1 | Completed
ER6701LT | W228 | W228.3720 | HYA Enhanced Defueling Safety Case | NSRS | 2024-07-19 | 2024-08-02 | 21 | 0 | 10 | 14 | 100% | 1.5 | 1 | Completed
ER6372LT | W203 | W203.D1710 | HNB Enhanced Defuelling Safety Cases | CA PJB Held | 2024-07-22 | 2024-07-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6698LT | W224 | W224.1270 | HRA Enhanced Defueling Safety Case | Information Gathering | 2024-07-22 | 2024-09-06 | 29 | 0 | 34 | 46 | 100% | 0.63043 | 1 | Completed
ER6701LT | W228 | W228.1270 | HYA Enhanced Defueling Safety Case | Information Gathering | 2024-07-22 | 2024-09-06 | 29 | 0 | 34 | 46 | 100% | 0.63043 | 1 | Completed
ER6372LT | W203 | W203.D1280 | HNB Enhanced Defuelling Safety Cases | Agree resource & timescales with suppliers for delivering key refs, incl contingency, risk & allowance for rework | 2024-07-22 | 2024-07-26 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6378LT | W222 | W222.A24350 | HRA Fuel Handling Essential Safety Case | Living Safety Document EAN Available | 2024-07-22 | 2024-07-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C1180 | DNB Enhanced Safety Cases | <Review of Weld Inspection Data> - Draft EAN Reviewed by EDF SQEP | 2024-07-23 | 2024-08-05 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6701LT | W228 | W228.1520 | HYA Enhanced Defueling Safety Case | Hold PJB | 2024-07-23 | 2024-07-30 | 1 | 0 | 6 | 7 | 100% | 0.14286 | 1 | Completed
ER6698LT | W224 | W224.1520 | HRA Enhanced Defueling Safety Case | Hold PJB | 2024-07-24 | 2024-07-29 | 5 | 0 | 4 | 5 | 100% | 1 | 1 | Completed
W232LT | W232 | W232.A2110 | DNB Enhanced Safety Cases | Rev 000 - Verification of the case (using BARRIER MODEL) | 2024-07-25 | 2024-10-08 | 30 | 0 | 52 | 75 | 100% | 0.4 | 1 | Completed
W772LT | W772 | W772LT.A1680 | DNB Pull Harder Safety Case | CO and PCE Create Initial Plan of Work ==> KDM | 2024-07-26 | 2024-08-05 | 7 | 0 | 7 | 10 | 100% | 0.7 | 1 | Completed
ER6372LT | W203 | W203.D1270 | HNB Enhanced Defuelling Safety Cases | Hold project kick start meeting with Station & key suppliers | 2024-07-29 | 2024-11-19 | 5 | 0 | 80 | 113 | 100% | 0.044248 | 1 | Completed
ER6701LT | W228 | W228.1590 | HYA Enhanced Defueling Safety Case | Analysis | 2024-07-30 | 2024-08-30 | 1 | 0 | 23 | 31 | 100% | 0.032258 | 1 | Completed
ER6698LT | W224 | W224.1590 | HRA Enhanced Defueling Safety Case | Analysis | 2024-07-30 | 2024-08-30 | 15 | 0 | 23 | 31 | 100% | 0.48387 | 1 | Completed
ER6666LT | W209 | W209.A29180 | HYB Essential Defueling Safety Case | Supplier Update and Issue Defuelling Worker Risk Assessment EAN | 2024-07-31 | 2024-08-07 | 5 | 0 | 6 | 7 | 100% | 0.71429 | 1 | Completed
ER6666LT | W209 | W209.A29190 | HYB Essential Defueling Safety Case | Complete TR Form and Upload Defuelling Worker Risk Assessment EAN to CDMS | 2024-07-31 | 2024-08-09 | 4 | 0 | 8 | 9 | 100% | 0.44444 | 1 | Completed
ER6668LT | W213 | W213.A29180 | TOR Essential Defueling Safety Case | Supplier Update and Issue Defuelling Worker Risk Assessment EAN | 2024-07-31 | 2024-08-07 | 5 | 0 | 6 | 7 | 100% | 0.71429 | 1 | Completed
ER6668LT | W213 | W213.A29190 | TOR Essential Defueling Safety Case | Complete TR Form and Upload Defuelling Worker Risk Assessment EAN to CDMS | 2024-07-31 | 2024-08-09 | 5 | 0 | 8 | 9 | 100% | 0.55556 | 1 | Completed
ER6666LT | W209 | W209.A31320 | HYB Essential Defueling Safety Case | PSA Documentation Available | 2024-07-31 | 2024-07-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A31320 | TOR Essential Defueling Safety Case | PSA Documentation Available | 2024-07-31 | 2024-07-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C1320 | DNB Enhanced Safety Cases | <Review of Lifting Integrity Faults> - Issue Draft EAN to EDF for Review. | 2024-08-01 | 2024-08-01 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6698LT | W224 | W224.2510 | HRA Enhanced Defueling Safety Case | RFS Load Trace TSA Support | 2024-08-01 | 2024-08-14 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6701LT | W228 | W228.2510 | HYA Enhanced Defueling Safety Case | RFS Load Trace TSA Support | 2024-08-01 | 2024-08-14 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
W232LT | W232 | W232.C1190 | DNB Enhanced Safety Cases | <Review of Weld Inspection Data> - Address Comments from EDF Review on Draft EAN | 2024-08-06 | 2024-08-19 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
W772LT | W772 | W772LT.A1000 | DNB Pull Harder Safety Case | Produce MF EC 375698 <DNB Pull Harder SC> & obtain approval | 2024-08-06 | 2024-08-16 | 9 | 0 | 9 | 10 | 100% | 0.9 | 1 | Completed
ER6378LT | W222 | W222.1010 | HRA Fuel Handling Essential Safety Case | Discovery Milestone - Confirm INSA Review Period | 2024-08-06 | 2024-08-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6701LT | W228 | W228.3650 | HYA Enhanced Defueling Safety Case | Production/Author CETS | 2024-08-07 | 2024-08-20 | 35 | 0 | 9 | 13 | 100% | 2.6923 | 1 | Completed
ER6701LT | W228 | W228.1300 | HYA Enhanced Defueling Safety Case | EDF Review | 2024-08-07 | 2024-09-09 | 23 | 0 | 23 | 33 | 100% | 0.69697 | 1 | Completed
ER6698LT | W224 | W224.1300 | HRA Enhanced Defueling Safety Case | EDF Review | 2024-08-07 | 2024-09-09 | 23 | 0 | 23 | 33 | 100% | 0.69697 | 1 | Completed
ER6698LT | W224 | W224.3650 | HRA Enhanced Defueling Safety Case | Production/Author CETS | 2024-08-07 | 2024-08-20 | 25 | 0 | 10 | 13 | 100% | 1.9231 | 1 | Completed
ER6650LT | W226 | W226.1010 | HYA Fuel Handling Essential Safety Case | Discovery Milestone - Confirm INSA Review Period | 2024-08-07 | 2024-08-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1020 | HNB Enhanced Defuelling Safety Cases | Plan Scope in Primavera Level 2 Lifecycle) | 2024-08-08 | 2024-08-14 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
W232LT | W232 | W232.C1620 | DNB Enhanced Safety Cases | <SCOPE NAME CHANGE CN 2615><Further Review of Shock Loaded Unit Events (Group 1)> - TSA Internal Review of Draft | 2024-08-09 | 2024-08-22 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6666LT | W209 | W209.A29200 | HYB Essential Defueling Safety Case | Defuelling Worker Risk Assessment EAN Available | 2024-08-09 | 2024-08-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.A29200 | TOR Essential Defueling Safety Case | Defuelling Worker Risk Assessment EAN Available | 2024-08-09 | 2024-08-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6701LT | W228 | W228.2150 | HYA Enhanced Defueling Safety Case | Outline Safety Case Strategy - Trip function change | 2024-08-12 | 2024-08-29 | 10 | 0 | 12 | 17 | 100% | 0.58824 | 1 | Completed
ER6701LT | W228 | W228.2140 | HYA Enhanced Defueling Safety Case | Outline Safety Case Strategy - Software based load trace change | 2024-08-12 | 2024-08-29 | 10 | 0 | 12 | 17 | 100% | 0.58824 | 1 | Completed
ER6701LT | W228 | W228.2130 | HYA Enhanced Defueling Safety Case | Outline Safety Case Strategy - Gripping Sleeve/BoB Weight | 2024-08-12 | 2024-08-29 | 10 | 0 | 12 | 17 | 100% | 0.58824 | 1 | Completed
W232LT | W232 | W232.C1340 | DNB Enhanced Safety Cases | <Review of Lifting Integrity Faults> - Address Comments from EDF Review on Draft EAN | 2024-08-12 | 2024-08-23 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6698LT | W224 | W224.1200 | HRA Enhanced Defueling Safety Case | EDF Review and contract awards | 2024-08-12 | 2024-09-02 | 15 | 0 | 15 | 21 | 100% | 0.71429 | 1 | Completed
ER6698LT | W224 | W224.2130 | HRA Enhanced Defueling Safety Case | Outline Safety Case Strategy - Gripping Sleeve/BoB Weight | 2024-08-12 | 2024-08-29 | 10 | 0 | 12 | 17 | 100% | 0.58824 | 1 | Completed
ER6698LT | W224 | W224.2140 | HRA Enhanced Defueling Safety Case | Outline Safety Case Strategy - Software based load trace change | 2024-08-12 | 2024-08-29 | 10 | 0 | 12 | 17 | 100% | 0.58824 | 1 | Completed
ER6698LT | W224 | W224.2150 | HRA Enhanced Defueling Safety Case | Outline Safety Case Strategy - Trip function change | 2024-08-12 | 2024-08-29 | 10 | 0 | 12 | 17 | 100% | 0.58824 | 1 | Completed
ER6701LT | W228 | W228.1200 | HYA Enhanced Defueling Safety Case | EDF Review and contract awards | 2024-08-12 | 2024-09-02 | 15 | 0 | 15 | 21 | 100% | 0.71429 | 1 | Completed
ER6701LT | W228 | W228.3660 | HYA Enhanced Defueling Safety Case | Author | 2024-08-13 | 2024-10-31 | 1 | 0 | 56 | 79 | 100% | 0.012658 | 1 | Completed
ER6698LT | W224 | W224.3660 | HRA Enhanced Defueling Safety Case | Author | 2024-08-13 | 2024-11-01 | 16 | 0 | 57 | 80 | 100% | 0.2 | 1 | Completed
ER6698LT | W224 | W224.2460 | HRA Enhanced Defueling Safety Case | Supplier Return Period | 2024-08-15 | 2024-08-30 | 10 | 0 | 11 | 15 | 100% | 0.66667 | 1 | Completed
ER6701LT | W228 | W228.2460 | HYA Enhanced Defueling Safety Case | Supplier Return Period | 2024-08-15 | 2024-08-30 | 10 | 0 | 11 | 15 | 100% | 0.66667 | 1 | Completed
ER6372LT | W203 | W203.D1030 | HNB Enhanced Defuelling Safety Cases | Estimate Scope +/- 10% Lifecycle | 2024-08-15 | 2024-08-21 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6650LT | W226 | 2205 | HYA Fuel Handling Essential Safety Case | *******INA Support paper going to NSC (T-3) Target******* | 2024-08-19 | 2024-08-19 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A1310 | DNB Pull Harder Safety Case | Initial Categorisation by Station ==> KDM | 2024-08-19 | 2024-08-19 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C1200 | DNB Enhanced Safety Cases | <Review of Weld Inspection Data> - Issue Final EAN | 2024-08-19 | 2024-08-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.KDM.SP01 | DNB Pull Harder Safety Case | KDM - Gate EC1 completed EC 375698 <DNB Pull Harder SC> | 2024-08-19 | 2024-08-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C1210 | DNB Enhanced Safety Cases | <Review of Weld Inspection Data> - EAN Completed and Uploaded to CDMS | 2024-08-20 | 2024-09-30 | 5 | 0 | 28 | 41 | 100% | 0.12195 | 1 | Completed
W772LT | W772 | W772LT.A1010 | DNB Pull Harder Safety Case | Produce draft NSRS (using BARRIER MODEL) | 2024-08-20 | 2024-10-10 | 28 | 0 | 36 | 51 | 100% | 0.54902 | 1 | Completed
W772LT | W772 | W772LT.A1250 | DNB Pull Harder Safety Case | Appoint CO & CA | 2024-08-20 | 2024-08-20 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6701LT | W228 | W228.3700 | HYA Enhanced Defueling Safety Case | Verify | 2024-08-21 | 2024-09-04 | 1 | 0 | 10 | 14 | 100% | 0.071429 | 1 | Completed
ER6698LT | W224 | W224.3700 | HRA Enhanced Defueling Safety Case | Verify | 2024-08-21 | 2024-09-04 | 11 | 0 | 10 | 14 | 100% | 0.78571 | 1 | Completed
W772LT | W772 | W772LT.A1110 | DNB Pull Harder Safety Case | CA to agree with CO format of the safety case | 2024-08-21 | 2024-08-22 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
W772LT | W772 | W772LT.A1340 | DNB Pull Harder Safety Case | Identify verifier for the case & establish all other resources | 2024-08-21 | 2024-08-30 | 7 | 0 | 7 | 9 | 100% | 0.77778 | 1 | Completed
ER6698LT | W224 | W224.1290 | HRA Enhanced Defueling Safety Case | Author SWIFT Briefing Pack | 2024-08-22 | 2024-09-13 | 16 | 0 | 16 | 22 | 100% | 0.72727 | 1 | Completed
ER6701LT | W228 | W228.1290 | HYA Enhanced Defueling Safety Case | Author Draft SWIFT Report - Confirm Nodes | 2024-08-22 | 2024-09-13 | 16 | 0 | 16 | 22 | 100% | 0.72727 | 1 | Completed
ER6372LT | W203 | W203.D1040 | HNB Enhanced Defuelling Safety Cases | Ensure Alignment of Schedule & Estimate | 2024-08-22 | 2024-08-27 | 3 | 0 | 3 | 5 | 100% | 0.6 | 1 | Completed
W232LT | W232 | W232.C1560 | DNB Enhanced Safety Cases | <SCOPE NAME CHANGE CN 2615><Further Review of Shock Loaded Unit Events (Group 1)> - Issue Draft EAN to EDF for R | 2024-08-22 | 2024-08-22 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C1570 | DNB Enhanced Safety Cases | <SCOPE NAME CHANGE CN 2615><Further Review of Shock Loaded Unit Events (Group 1)> - Draft EAN Reviewed by EDF SQ | 2024-08-23 | 2024-09-06 | 10 | 0 | 10 | 14 | 100% | 0.71429 | 1 | Completed
W232LT | W232 | W232.C1350 | DNB Enhanced Safety Cases | <Review of Lifting Integrity Faults> - Issue Final EAN | 2024-08-23 | 2024-08-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1200 | HNB Enhanced Defuelling Safety Cases | Revise Project Definition Document (PDD) | 2024-08-26 | 2024-10-02 | 5 | 0 | 26 | 37 | 100% | 0.13514 | 1 | Completed
W232LT | W232 | W232.C1360 | DNB Enhanced Safety Cases | <Review of Lifting Integrity Faults> - EAN Completed and Uploaded to CDMS | 2024-08-27 | 2024-09-30 | 5 | 0 | 24 | 34 | 100% | 0.14706 | 1 | Completed
ER6698LT | W224 | W224.2430 | HRA Enhanced Defueling Safety Case | EDF Review and contract awards | 2024-08-28 | 2024-08-30 | 10 | 0 | 3 | 2 | 100% | 5 | 1 | Completed
ER6701LT | W228 | W228.2430 | HYA Enhanced Defueling Safety Case | EDF Review and contract awards | 2024-08-28 | 2024-08-30 | 10 | 0 | 3 | 2 | 100% | 5 | 1 | Completed
ER6372LT | W203 | W203.D1050 | HNB Enhanced Defuelling Safety Cases | Hold Risk Workshop | 2024-08-28 | 2024-08-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 2200 | HYA Fuel Handling Essential Safety Case | INA Support paper going to NSC (T-3) | 2024-08-29 | 2024-08-29 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1060 | HNB Enhanced Defuelling Safety Cases | Complete Risk Log with Estimates | 2024-08-29 | 2024-08-30 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
ER6371LT | W202 | W202.A5300 | HRA Reactors Shutdown Essential Safety Cases | INSA Assessment substantially comp (T-3 weeks before NSC date) EC 363682 <Reactor Shutdown Essential SC> (Cat 1 MS) HRA | 2024-08-29 | 2024-08-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A5310 | HRA Reactors Shutdown Essential Safety Cases | INSA Assessment substantially comp (T-3 weeks before NSC date) EC 363682 Reactor Shutdown Essential SC (Cat 1 MS) (HRA) | 2024-08-29 | 2024-08-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5300 | HYA Reactors Shutdown Essential Safety Cases | INSA Assessment substantially comp (T-3 weeks before NSC date) EC 363676 <Reactor Shutdown Essential SC> (Cat 1 MS) HYA | 2024-08-29 | 2024-08-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5310 | HYA Reactors Shutdown Essential Safety Cases | INSA Assessment substantially comp (T-3 weeks before NSC date) EC 363676 Reactor Shutdown Essential SC (Cat 1 MS) (HYA) | 2024-08-29 | 2024-08-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A5010 | HRA Fuel Handling Essential Safety Case | INSA Assess substantially comp (T-3 wks<NSC date) ECs (HRA-363840) Essential Fuel Handling Safety Case | 2024-08-29 | 2024-08-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A5010 | HYA Fuel Handling Essential Safety Case | INSA Assess substntlly comp (T-3 wks<NSC date) ECs (HYA-363839) Essential Fuel Handling Safety Case | 2024-08-29 | 2024-08-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206180 | HRA Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W222, HRA Security Plan) INSA Assessment substantially comp (T - 3 weeks before NSC date) | 2024-08-29 | 2024-08-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206240 | HYA Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W226, HYA Security Plan) INSA Assessment substantially comp (T - 3 weeks before NSC date) | 2024-08-29 | 2024-08-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.1020 | HRA Fuel Handling Essential Safety Case | >>>OUTGOING ENABLER (HRA Security Plan (W155)) INSA Assessment substantially comp (T - 3 weeks before NSC date) | 2024-08-29 | 2024-08-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.1020 | HYA Fuel Handling Essential Safety Case | >>>OUTGOING ENABLER (HYA Security Plan (W156)) INSA Assessment substantially comp (T - 3 weeks before NSC date) | 2024-08-29 | 2024-08-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.1360 | HRA Reactors Shutdown Essential Safety Cases | >>>INCOMING ENABLER (W222) INA Support paper going to NSC (T-3) | 2024-08-29 | 2024-08-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.1370 | HRA Reactors Shutdown Essential Safety Cases | >>>MIRROR of INCOMING ENABLER (W222) INA Support paper going to NSC (T-3) | 2024-08-29 | 2024-08-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.B1360 | HYA Reactors Shutdown Essential Safety Cases | >>>INCOMING ENABLER (W226) INA Support paper going to NSC (T-3) | 2024-08-29 | 2024-08-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.B1370 | HYA Reactors Shutdown Essential Safety Cases | >>>MIRROR of INCOMING ENABLER (W226) INA Support paper going to NSC (T-3) | 2024-08-29 | 2024-08-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5540 | HYA Reactors Shutdown Essential Safety Cases | >>>INTERFACE MILESTONE (W226) INA Support paper going to NSC (T-3) | 2024-08-29 | 2024-08-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206540 | HRA Reactors Shutdown Essential Safety Cases | >>>INTERFACE MILESTONE (W222) INA Support paper going to NSC (T-3) | 2024-08-29 | 2024-08-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A5270 | HRA Reactors Shutdown Essential Safety Cases | Prepare Station Director's Brief (HRA) | 2024-08-30 | 2024-09-11 | 5 | 0 | 8 | 12 | 100% | 0.41667 | 1 | Completed
ER6661LT | W206 | W206.A5270 | HYA Reactors Shutdown Essential Safety Cases | Prepare Station Director's Brief (HYA) | 2024-08-30 | 2024-09-11 | 5 | 0 | 8 | 12 | 100% | 0.41667 | 1 | Completed
ER6378LT | W222 | W222.A1520 | HRA Fuel Handling Essential Safety Case | Prepare Station Director's Brief | 2024-08-30 | 2024-09-11 | 5 | 0 | 9 | 12 | 100% | 0.41667 | 1 | Completed
ER6378LT | W222 | W222.A5000 | HRA Fuel Handling Essential Safety Case | Incorporate INSA comments | 2024-08-30 | 2024-09-05 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6650LT | W226 | W226.A5000 | HYA Fuel Handling Essential Safety Case | Incorporate INSA comments | 2024-08-30 | 2024-09-05 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6650LT | W226 | W226.A1520 | HYA Fuel Handling Essential Safety Case | Prepare Station Director's Brief | 2024-08-30 | 2024-09-11 | 5 | 0 | 8 | 12 | 100% | 0.41667 | 1 | Completed
ER6650LT | W226 | 2180 | HYA Fuel Handling Essential Safety Case | Respond to Minor INSA Comments | 2024-08-30 | 2024-09-05 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6650LT | W226 | 2210 | HYA Fuel Handling Essential Safety Case | pre-NSC notification period to be determined/agreed (T-3)(Jun=29 May)(Jul=26 Jun) | 2024-08-30 | 2024-08-30 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 2190 | HYA Fuel Handling Essential Safety Case | Close Out Minor INSA Comments | 2024-08-30 | 2024-09-05 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6701LT | W228 | W228.1400 | HYA Enhanced Defueling Safety Case | HYA Reduce IFDF Cooling Requirements Reduce cooling to one blower | 2024-09-02 | 2025-01-02 | 64 | 0 | 86 | 122 | 100% | 0.52459 | 1 | Completed
ER6650LT | W226 | W226.A24350 | HYA Fuel Handling Essential Safety Case | Living Safety Document EAN Available | 2024-09-02 | 2024-09-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6698LT | W224 | W224.1400 | HRA Enhanced Defueling Safety Case | HRA Reduce IFDF Cooling Requirements Reduce Cooling to one Blower | 2024-09-02 | 2025-01-02 | 64 | 0 | 85 | 122 | 100% | 0.52459 | 1 | Completed
ER6698LT | W224 | W224.2530 | HRA Enhanced Defueling Safety Case | Hold PJB for TSA Support | 2024-09-02 | 2024-09-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6698LT | W224 | W224.2570 | HRA Enhanced Defueling Safety Case | Technical Discussion | 2024-09-02 | 2024-09-17 | 12 | 0 | 12 | 15 | 100% | 0.8 | 1 | Completed
ER6701LT | W228 | W228.2570 | HYA Enhanced Defueling Safety Case | Technical Discussion for PC1/PC2 software | 2024-09-02 | 2024-09-17 | 1 | 0 | 12 | 15 | 100% | 0.066667 | 1 | Completed
ER6701LT | W228 | W228.2530 | HYA Enhanced Defueling Safety Case | Hold PJB for TSA Support | 2024-09-02 | 2024-09-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.D3000 | DNB Pull Harder Safety Case | Define Project Control Structures (WBS/CBS/OBS/PBS) | 2024-09-02 | 2024-09-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6698LT | W224 | W224.1210 | HRA Enhanced Defueling Safety Case | Hold PJB | 2024-09-03 | 2024-09-16 | 5 | 0 | 9 | 13 | 100% | 0.38462 | 1 | Completed
ER6701LT | W228 | W228.1210 | HYA Enhanced Defueling Safety Case | Hold PJB | 2024-09-03 | 2024-09-16 | 5 | 0 | 9 | 13 | 100% | 0.38462 | 1 | Completed
W772LT | W772 | W772LT.D3010 | DNB Pull Harder Safety Case | Plan Scope in Primavera (level 2 for Phase A to B & Level 1 for Lifecycle | 2024-09-03 | 2024-10-18 | 34 | 0 | 34 | 45 | 100% | 0.75556 | 1 | Completed
W772LT | W772 | W772LT.D3020 | DNB Pull Harder Safety Case | Estimate scope (+/- 10% A-B & +/- 50% Lifecycle | 2024-09-03 | 2024-10-18 | 34 | 0 | 34 | 45 | 100% | 0.75556 | 1 | Completed
ER6698LT | W224 | W224.3710 | HRA Enhanced Defueling Safety Case | TR of CETS (may Not be Needed) | 2024-09-05 | 2024-09-05 | 11 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6701LT | W228 | W228.3710 | HYA Enhanced Defueling Safety Case | TR of CETS | 2024-09-05 | 2024-09-05 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6698LT | W224 | W224.1325 | HRA Enhanced Defueling Safety Case | KDM - CETS ISSUE PoC and Detailed Design for BoB Weight and Gripping Sleeve | 2024-09-09 | 2024-09-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C1580 | DNB Enhanced Safety Cases | <SCOPE NAME CHANGE CN 2615><Further Review of Shock Loaded Unit Events (Group 1)> - Address Comments from EDF Re | 2024-09-09 | 2024-10-08 | 10 | 0 | 21 | 29 | 100% | 0.34483 | 1 | Completed
ER6698LT | W224 | W224.1330 | HRA Enhanced Defueling Safety Case | KDM - CETS ISSUE Approval | 2024-09-09 | 2024-09-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6701LT | W228 | W228.1330 | HYA Enhanced Defueling Safety Case | KDM - CETS ISSUE Approval | 2024-09-09 | 2024-09-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6701LT | W228 | W228.1325 | HYA Enhanced Defueling Safety Case | KDM - CETS ISSUE PoC and Detailed Design for BoB Weight and Gripping Sleeve | 2024-09-09 | 2024-09-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6698LT | W224 | W224.2200 | HRA Enhanced Defueling Safety Case | Issue CETS for Tender | 2024-09-10 | 2024-09-26 | 5 | 0 | 12 | 16 | 100% | 0.3125 | 1 | Completed
ER6701LT | W228 | W228.2200 | HYA Enhanced Defueling Safety Case | Issue CETS for Tender | 2024-09-10 | 2024-09-26 | 5 | 0 | 12 | 16 | 100% | 0.3125 | 1 | Completed
ER6701LT | W228 | W228.1220 | HYA Enhanced Defueling Safety Case | Optioneering Workshop | 2024-09-16 | 2025-01-02 | 5 | 0 | 75 | 108 | 100% | 0.046296 | 1 | Completed
ER6698LT | W224 | W224.1220 | HRA Enhanced Defueling Safety Case | Optioneering Studying Report | 2024-09-16 | 2025-01-02 | 5 | 0 | 75 | 108 | 100% | 0.046296 | 1 | Completed
ER6371LT | W202 | W202.A5330 | HRA Reactors Shutdown Essential Safety Cases | NSC Presentation Date EC 363682 <Reactor Shutdown Essential SC> (Cat 1 B KDM) (T) (HRA) | 2024-09-18 | 2024-09-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A5350 | HRA Reactors Shutdown Essential Safety Cases | NSC Consideration & advice to Station Director (HRA) | 2024-09-18 | 2024-10-02 | 11 | 0 | 11 | 14 | 100% | 0.78571 | 1 | Completed
ER6371LT | W202 | W202.A5340 | HRA Reactors Shutdown Essential Safety Cases | NSC Presentation Date (T) EC (HRA-363682) Reactor Shutdown Essential Safety Case | 2024-09-18 | 2024-09-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5330 | HYA Reactors Shutdown Essential Safety Cases | NSC Presentation Date EC 363676 <Reactor Shutdown Essential SC> (Cat 1 B KDM) (T) (HYA) | 2024-09-18 | 2024-09-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5350 | HYA Reactors Shutdown Essential Safety Cases | NSC Consideration & advice to Station Director (HYA) | 2024-09-18 | 2024-10-02 | 11 | 0 | 11 | 14 | 100% | 0.78571 | 1 | Completed
ER6661LT | W206 | W206.A5340 | HYA Reactors Shutdown Essential Safety Cases | NSC Presentation Date (T) EC (HYA-363676) Reactor Shutdown Essential Safety Case | 2024-09-18 | 2024-09-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A4980 | HRA Fuel Handling Essential Safety Case | NSC Presentation Date (T) ECs (HRA-363840) Essential Fuel Handling Safety Case | 2024-09-18 | 2024-09-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1038 | TOR Essential Defueling Safety Case | Verification Complete/ Verified Draft A Issued for INSA (T-7) EC 371386 - TOR Essential Defueling Safety Case | 2024-09-18 | 2024-09-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A27280 | HRA Fuel Handling Essential Safety Case | NSC Presentation Date (T) ECs (HRA-363840) Essential Fuel Handling Safety Case | 2024-09-18 | 2024-09-18 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27330 | HYA Fuel Handling Essential Safety Case | NSC Presentation Date (T) ECs (HYA-363839) Essential Fuel Handling Safety Case | 2024-09-18 | 2024-09-18 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 2220 | HYA Fuel Handling Essential Safety Case | NSC Meeting | 2024-09-18 | 2024-09-18 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A4980 | HYA Fuel Handling Essential Safety Case | NSC Presentation Date (T) ECs (HYA-363839) Essential Fuel Handling Safety Case | 2024-09-18 | 2024-09-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1505 | HYB Essential Defueling Safety Case | Submit for approval - Categoriser ratifies; RE/CO endorsement | 2024-09-18 | 2024-09-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1038 | HYB Essential Defueling Safety Case | Verification Complete/ Verified Draft A Issued for INSA (T-7) EC 371387 - HYB Essential Defueling Safety Case | 2024-09-18 | 2024-09-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1505 | TOR Essential Defueling Safety Case | Submit for approval - Categoriser ratifies; RE/CO endorsement | 2024-09-18 | 2024-09-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1525 | TOR Essential Defueling Safety Case | DA (Authorised Designer) Approval of CAT1 Safety Case | 2024-09-19 | 2024-09-20 | 5 | 0 | 2 | 1 | 100% | 5 | 1 | Completed
ER6668LT | W213 | W213.1535 | TOR Essential Defueling Safety Case | INSA review & iteration of comments (using BARRIER MODEL) | 2024-09-19 | 2025-01-31 | 20 | 0 | 93 | 134 | 100% | 0.14925 | 1 | Completed
ER6378LT | W222 | W222.A1660 | HRA Fuel Handling Essential Safety Case | NSC Consideration & advice to Station Director | 2024-09-19 | 2024-10-02 | 10 | 0 | 9 | 13 | 100% | 0.76923 | 1 | Completed
ER6650LT | W226 | W226.A1660 | HYA Fuel Handling Essential Safety Case | NSC Consideration & advice to Station Director | 2024-09-19 | 2024-10-02 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6666LT | W209 | W209.1525 | HYB Essential Defueling Safety Case | DA (Authorised Designer) Approval of CAT1 Safety Case | 2024-09-19 | 2024-09-20 | 5 | 0 | 1 | 1 | 100% | 5 | 1 | Completed
ER6666LT | W209 | W209.1535 | HYB Essential Defueling Safety Case | INSA review & iteration of comments (using BARRIER MODEL) | 2024-09-19 | 2025-01-31 | 20 | 0 | 94 | 134 | 100% | 0.14925 | 1 | Completed
ER6666LT | W209 | W209.29300 | HYB Essential Defueling Safety Case | Lessons Learnt Activity - Following Verification of the SC | 2024-09-19 | 2024-10-23 | 10 | 0 | 24 | 34 | 100% | 0.29412 | 1 | Completed
ER6668LT | W213 | W213.29300 | TOR Essential Defueling Safety Case | Lessons Learnt Activity - Following Verification of the SC | 2024-09-19 | 2024-10-23 | 10 | 0 | 25 | 34 | 100% | 0.29412 | 1 | Completed
ER6650LT | W226 | 2240 | HYA Fuel Handling Essential Safety Case | Respond to NSC as appropriate | 2024-09-19 | 2024-10-02 | 10 | 0 | 9 | 13 | 100% | 0.76923 | 1 | Completed
ER6650LT | W226 | 2230 | HYA Fuel Handling Essential Safety Case | NSC Minutes Issued | 2024-09-19 | 2024-10-10 | 10 | 0 | 15 | 21 | 100% | 0.47619 | 1 | Completed
W232LT | W232 | W232.A2100 | DNB Enhanced Safety Cases | Rev 000 - Produce verification plan | 2024-09-23 | 2024-09-30 | 2 | 0 | 5 | 7 | 100% | 0.28571 | 1 | Completed
ER6372LT | W203 | W203.C1390 | HNB Enhanced Defuelling Safety Cases | Verification of the case (using BARRIER MODEL) | 2024-09-26 | 2024-11-15 | 0 | 0 | 37 | 50 | 100% | 0 | 1 | Completed
ER6378LT | W222 | W222.3090 | HRA Fuel Handling Essential Safety Case | Verification of Proposal Lessons Learnt Review Complete | 2024-09-26 | 2024-09-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.3080 | HYA Fuel Handling Essential Safety Case | Verification of Proposal - Lesson Learnt Review Complete | 2024-09-26 | 2024-09-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6698LT | W224 | W224.2210 | HRA Enhanced Defueling Safety Case | Supplier Return Period | 2024-09-27 | 2025-01-02 | 14 | 0 | 66 | 97 | 100% | 0.14433 | 1 | Completed
ER6701LT | W228 | W228.2210 | HYA Enhanced Defueling Safety Case | Supplier Return Period | 2024-09-27 | 2025-01-02 | 14 | 0 | 66 | 97 | 100% | 0.14433 | 1 | Completed
ER6378LT | W222 | W222.3050 | HRA Fuel Handling Essential Safety Case | Lesson Learn - Verification Phase | 2024-09-27 | 2024-09-27 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.3050 | HYA Fuel Handling Essential Safety Case | Lesson Learn - Verification Phase | 2024-09-27 | 2024-09-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C1220 | DNB Enhanced Safety Cases | <Review of Weld Inspection Data> - EAN Completed | 2024-09-30 | 2024-09-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C1370 | DNB Enhanced Safety Cases | <Review of Lifting Integrity Faults> - EAN Completed | 2024-09-30 | 2024-09-30 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A1070 | DNB Pull Harder Safety Case | Create EC Definition Document if not part of Project Definition Document (Insert Template Ref) | 2024-09-30 | 2024-09-30 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2090 | DNB Enhanced Safety Cases | Rev 000 - Incorporate CO & Station comments | 2024-10-01 | 2024-10-08 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
W772LT | W772 | W772LT.A1460 | DNB Pull Harder Safety Case | Continue to Develop & resource mandatory template ==> KDM | 2024-10-01 | 2024-10-01 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A1060 | DNB Pull Harder Safety Case | Hold project kick start meeting with Station & key suppliers | 2024-10-01 | 2024-10-02 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
W772LT | W772 | W772LT.A1350 | DNB Pull Harder Safety Case | Circulate work programme to stakeholders for agreement | 2024-10-02 | 2024-10-09 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
W772LT | W772 | W772LT.KDM.SP03 | DNB Pull Harder Safety Case | KDM - Gate EC2 completed and Cat 1 Baselined EC 375698 <DNB Pull Harder SC> | 2024-10-02 | 2024-10-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C1600 | DNB Enhanced Safety Cases | <SCOPE NAME CHANGE CN 2615><Further Review of Shock Loaded Unit Events (Group 1)> - EAN Completed and Uploaded t | 2024-10-02 | 2024-10-08 | 3 | 0 | 4 | 6 | 100% | 0.5 | 1 | Completed
ER6372LT | W203 | W203.D1070 | HNB Enhanced Defuelling Safety Cases | Update Schedule/Estimate from Risk Log & Add Provisions | 2024-10-03 | 2024-10-11 | 2 | 0 | 6 | 8 | 100% | 0.25 | 1 | Completed
W772LT | W772 | W772LT.A1090 | DNB Pull Harder Safety Case | Agree INSA resource with INA | 2024-10-03 | 2024-10-04 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
W772LT | W772 | W772LT.A1520 | DNB Pull Harder Safety Case | Commence Supporting References or Supporting EC's | 2024-10-04 | 2024-10-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.T1250 | DNB Pull Harder Safety Case | <Operating Strategy for Pull Harder Facility> - Prepare Draft EAN / Report | 2024-10-04 | 2024-10-25 | 15 | 0 | 15 | 21 | 100% | 0.71429 | 1 | Completed
W232LT | W232 | W232.A2120 | DNB Enhanced Safety Cases | Rev 000 - Produce verification file | 2024-10-07 | 2024-10-08 | 2 | 0 | 1 | 1 | 100% | 2 | 1 | Completed
W232LT | W232 | W232.A2250 | DNB Enhanced Safety Cases | Rev 000 - Key Stakeholders Approval, if requested | 2024-10-07 | 2024-10-08 | 5 | 0 | 1 | 1 | 100% | 5 | 1 | Completed
W232LT | W232 | W232.A2070 | DNB Enhanced Safety Cases | Rev 000 - CA to agree with CO format of the safety case & produce agreed contents page | 2024-10-07 | 2024-10-08 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
W232LT | W232 | W232.A2130 | DNB Enhanced Safety Cases | Rev 000 - Verified Draft Issue A with verification file to INSA & station *(KDM)* | 2024-10-08 | 2024-10-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2140 | DNB Enhanced Safety Cases | Rev 000 - INSA review & iteration of comments (using BARRIER MODEL) | 2024-10-08 | 2024-10-18 | 20 | 0 | 8 | 10 | 100% | 2 | 1 | Completed
W232LT | W232 | W232.A2230 | DNB Enhanced Safety Cases | Rev 000 - Verification complete | 2024-10-08 | 2024-10-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2240 | DNB Enhanced Safety Cases | Rev 000 - Submit for approval - Categoriser ratifies; RE/CO endorsement | 2024-10-08 | 2024-10-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2280 | DNB Enhanced Safety Cases | Rev 000 - Issue to CO & Station for comments | 2024-10-08 | 2024-10-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A3010 | DNB Enhanced Safety Cases | All Technical References Complete - Rev 000 | 2024-10-08 | 2024-10-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A3020 | DNB Enhanced Safety Cases | Safety Case Authoring Complete - Rev 000 | 2024-10-08 | 2024-10-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A3030 | DNB Enhanced Safety Cases | Safety Case Verification Complete - Rev 000 | 2024-10-08 | 2024-10-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C1590 | DNB Enhanced Safety Cases | <SCOPE NAME CHANGE CN 2615><Further Review of Shock Loaded Unit Events (Group 1)> - Issue Final EAN | 2024-10-08 | 2024-10-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C1610 | DNB Enhanced Safety Cases | <SCOPE NAME CHANGE CN 2615><Further Review of Shock Loaded Unit Events (Group 1)> - EAN Completed | 2024-10-08 | 2024-10-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2380 | DNB Enhanced Safety Cases | Rev 000 - All supporting references completed | 2024-10-08 | 2024-10-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A1630 | DNB Pull Harder Safety Case | Baseline Plan to Verification Commenced (T-11) ==> KDM | 2024-10-09 | 2024-10-09 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A5360 | HRA Reactors Shutdown Essential Safety Cases | INSA Final Approval EC 363682 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HRA) | 2024-10-10 | 2024-10-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A5380 | HRA Reactors Shutdown Essential Safety Cases | INSA Final Approval EC 363682 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HRA) | 2024-10-10 | 2024-10-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5360 | HYA Reactors Shutdown Essential Safety Cases | INSA Final Approval EC 363676 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HYA) | 2024-10-10 | 2024-10-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5380 | HYA Reactors Shutdown Essential Safety Cases | INSA Final Approval EC 363676 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HYA) | 2024-10-10 | 2024-10-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206510 | HRA Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W285)(W148) INSA Finally Approved | 2024-10-10 | 2024-10-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206310 | HYA Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W286) (W148) INSA Finally Approved | 2024-10-10 | 2024-10-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A1015 | DNB Pull Harder Safety Case | Draft NSRS Verify - Atkins | 2024-10-10 | 2024-10-31 | 10 | 0 | 15 | 21 | 100% | 0.47619 | 1 | Completed
ER6378LT | W222 | W222.A17490 | HRA Fuel Handling Essential Safety Case | INSA Final Approval EC 363840 HRA Defuelling Fuel Handling Essential Safety Case (Cat 1 Milestone) | 2024-10-10 | 2024-10-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A17490 | HYA Fuel Handling Essential Safety Case | INSA Final Approval EC 363839 HYA Defuelling Fuel Handling Essential Safety Case (Cat 1 Milestone) | 2024-10-10 | 2024-10-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.1040 | HRA Fuel Handling Essential Safety Case | >>>OUTGOING ENABLER (W285) INSA Final Approval | 2024-10-10 | 2024-10-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27320 | HYA Fuel Handling Essential Safety Case | >>>OUTGOING ENABLER (W286) CAT 1 Fuel Handling SC INSA Finally Approved | 2024-10-10 | 2024-10-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A5370 | HRA Reactors Shutdown Essential Safety Cases | CAT 1 Satety Case Submitted to ONR - Reactor Shutdown Essential SC HRA | 2024-10-10 | 2024-10-11 | 0 | 0 | 0 | 1 | 100% | 0 | 1 | Completed
ER6661LT | W206 | W206.A5370 | HYA Reactors Shutdown Essential Safety Cases | CAT 1 Satety Case Submitted to ONR - Reactor Shutdown Essential SC HYA | 2024-10-10 | 2024-10-11 | 0 | 0 | 0 | 1 | 100% | 0 | 1 | Completed
ER6378LT | W222 | W222.1220 | HRA Fuel Handling Essential Safety Case | Letter Sent to ONR to Initiate Acknowlegement / Agreement | 2024-10-11 | 2024-10-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.1190 | HYA Fuel Handling Essential Safety Case | Letter Sent to ONR to Initiate Acknowledgement / Agreement | 2024-10-11 | 2024-10-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 2250 | HYA Fuel Handling Essential Safety Case | Draft HRA Formal ONR Letter/Review | 2024-10-11 | 2024-10-11 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 2260 | HYA Fuel Handling Essential Safety Case | Draft HYA Formal ONR Letter/Review | 2024-10-11 | 2024-10-11 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 2270 | HYA Fuel Handling Essential Safety Case | Station Directors sign letters | 2024-10-11 | 2024-10-11 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 2280 | HYA Fuel Handling Essential Safety Case | Safety Case Submitted to the ONR | 2024-10-11 | 2024-10-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A5390 | HRA Reactors Shutdown Essential Safety Cases | ONR Approval of Safety Case EC 363682 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HRA) | 2024-10-14 | 2025-01-24 | 63 | 0 | 71 | 102 | 100% | 0.61765 | 1 | Completed
ER6661LT | W206 | W206.A5390 | HYA Reactors Shutdown Essential Safety Cases | ONR Approval of Safety Case EC 363676 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HYA) | 2024-10-14 | 2025-01-24 | 63 | 0 | 71 | 102 | 100% | 0.61765 | 1 | Completed
ER6378LT | W222 | W222.A17500 | HRA Fuel Handling Essential Safety Case | ONR Approval of SC (Letter sent to initiate) HYA HRA Defuelling Fuel Handling Essential Safety Case | 2024-10-14 | 2025-01-24 | 63 | 0 | 71 | 102 | 100% | 0.61765 | 1 | Completed
ER6378LT | W222 | W222.1150 | HRA Fuel Handling Essential Safety Case | Safety Case Development Costs - ONR Phase (C to D ) ##Cost Summary## | 2024-10-14 | 2025-01-24 | 63 | 0 | 72 | 102 | 100% | 0.61765 | 1 | Completed
ER6378LT | W222 | W222.1160 | HRA Fuel Handling Essential Safety Case | Project Management Costs - ONR Phase (C to D ) ##Cost Summary## | 2024-10-14 | 2025-01-24 | 63 | 0 | 72 | 102 | 100% | 0.61765 | 1 | Completed
ER6371LT | W202 | W202.A2206530 | HRA Reactors Shutdown Essential Safety Cases | SC - Safety Case development - tech oversight Cat 1 - HRA - C-D - STN | 2024-10-14 | 2025-02-21 | 94 | 0 | 91 | 130 | 100% | 0.72308 | 1 | Completed
ER6661LT | W206 | W206.A2206330 | HYA Reactors Shutdown Essential Safety Cases | SC - Safety Case development - tech oversight Cat 1 - HYA - C-D - STN | 2024-10-14 | 2025-02-21 | 94 | 0 | 91 | 130 | 100% | 0.72308 | 1 | Completed
ER6372LT | W203 | W203.D1080 | HNB Enhanced Defuelling Safety Cases | Add Data to PRC Paper | 2024-10-14 | 2024-10-18 | 2 | 0 | 4 | 4 | 100% | 0.5 | 1 | Completed
ER6650LT | W226 | W226.A17500 | HYA Fuel Handling Essential Safety Case | ONR Approval of SC (Letter sent to initiate) HYA HRA Defuelling Fuel Handling Essential Safety Case | 2024-10-14 | 2025-01-24 | 64 | 0 | 71 | 102 | 100% | 0.62745 | 1 | Completed
ER6650LT | W226 | W226.1150 | HYA Fuel Handling Essential Safety Case | Safety Case Development Costs - ONR Phase (C to D ) ##Cost Summary## | 2024-10-14 | 2025-01-13 | 63 | 0 | 63 | 91 | 100% | 0.69231 | 1 | Completed
ER6650LT | W226 | W226.1160 | HYA Fuel Handling Essential Safety Case | Project Management Costs - ONR Phase (C to D ) ##Cost Summary## | 2024-10-14 | 2025-01-24 | 63 | 0 | 72 | 102 | 100% | 0.61765 | 1 | Completed
W772LT | W772 | W772LT.A1020 | DNB Pull Harder Safety Case | Station comments on NSRS | 2024-10-14 | 2024-10-31 | 8 | 0 | 13 | 17 | 100% | 0.47059 | 1 | Completed
W772LT | W772 | W772LT.A1030 | DNB Pull Harder Safety Case | DA (Peer) comments on NSRS | 2024-10-14 | 2024-10-31 | 8 | 0 | 13 | 17 | 100% | 0.47059 | 1 | Completed
W772LT | W772 | W772LT.A2000 | DNB Pull Harder Safety Case | Load Path Assessment - Preliminary Work - DNB Defuelling | 2024-10-14 | 2024-11-22 | 30 | 0 | 30 | 39 | 100% | 0.76923 | 1 | Completed
W772LT | W772 | W772LT.A2250 | DNB Pull Harder Safety Case | Load Path Assessment - Preliminary Work - Atkins | 2024-10-14 | 2024-11-22 | 30 | 0 | 30 | 39 | 100% | 0.76923 | 1 | Completed
W772LT | W772 | W772LT.T1170 | DNB Pull Harder Safety Case | <Specification for Pull Harder Facility> - Prepare Draft EAN / Report | 2024-10-14 | 2024-10-18 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6698LT | W224 | W224.2190 | HRA Enhanced Defueling Safety Case | SWIFT Workshop | 2024-10-15 | 2024-10-15 | 5 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6701LT | W228 | W228.2190 | HYA Enhanced Defueling Safety Case | SWIFT Workshop | 2024-10-15 | 2024-10-21 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6701LT | W228 | W228.2180 | HYA Enhanced Defueling Safety Case | SWIFT Report (Update & Verify) | 2024-10-16 | 2025-01-02 | 20 | 0 | 53 | 78 | 100% | 0.25641 | 1 | Completed
ER6698LT | W224 | W224.2180 | HRA Enhanced Defueling Safety Case | SWIFT Report (Update & Verify) | 2024-10-16 | 2025-01-02 | 20 | 0 | 53 | 78 | 100% | 0.25641 | 1 | Completed
W232LT | W232 | W232.A2290 | DNB Enhanced Safety Cases | Rev 000 - Incorporate INSA comments | 2024-10-18 | 2024-10-25 | 10 | 0 | 5 | 7 | 100% | 1.4286 | 1 | Completed
W772LT | W772 | W772LT.T1180 | DNB Pull Harder Safety Case | <Specification for Pull Harder Facility> - Issue Draft EAN / Report for Tech Review. | 2024-10-18 | 2024-10-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1090 | HNB Enhanced Defuelling Safety Cases | PCL Validate & Approve Baseline Package for PRC Submission | 2024-10-21 | 2024-10-25 | 3 | 0 | 4 | 4 | 100% | 0.75 | 1 | Completed
W772LT | W772 | W772LT.D3030 | DNB Pull Harder Safety Case | Ensure Alignment of Schedule & Estimate | 2024-10-21 | 2024-10-22 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
W772LT | W772 | W772LT.T1190 | DNB Pull Harder Safety Case | <Specification for Pull Harder Facility> - Draft EAN / Report Tech Reviewed by EDF SQEP | 2024-10-21 | 2024-10-28 | 5 | 0 | 5 | 7 | 100% | 0.71429 | 1 | Completed
ER6666LT | W209 | W209.29310 | HYB Essential Defueling Safety Case | Lessons Learnt Milestone - Verification of the Safety Case | 2024-10-23 | 2024-10-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.D3040 | DNB Pull Harder Safety Case | Hold Risk Workshop | 2024-10-23 | 2024-10-23 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.29310 | TOR Essential Defueling Safety Case | Lessons Learnt Milestone - Verification of the Safety Case | 2024-10-23 | 2024-10-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.D3050 | DNB Pull Harder Safety Case | Finalise Risk Log | 2024-10-24 | 2024-10-25 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
W772LT | W772 | W772LT.T1260 | DNB Pull Harder Safety Case | <Operating Strategy for Pull Harder Facility> - Issue Draft EAN / Report for Tech Review. | 2024-10-25 | 2024-10-25 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.D3060 | DNB Pull Harder Safety Case | Update Schedule from Risk Log/Estimate, Adding Provisions | 2024-10-28 | 2024-10-30 | 3 | 0 | 3 | 2 | 100% | 1.5 | 1 | Completed
W772LT | W772 | W772LT.T1200 | DNB Pull Harder Safety Case | <Specification for Pull Harder Facility> - Address Comments from EDF Review on Draft EAN / Report | 2024-10-28 | 2024-10-28 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.T1210 | DNB Pull Harder Safety Case | <Specification for Pull Harder Facility> - Issue Final EAN / Report to FMAPS | 2024-10-28 | 2024-10-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2320 | DNB Enhanced Safety Cases | Rev 000 - INSA Final Approval *(KDM)* | 2024-10-28 | 2024-10-29 | 0 | 0 | 0 | 1 | 100% | 0 | 1 | Completed
W232LT | W232 | W232.A5000 | DNB Enhanced Safety Cases | Lessons Learned Workshop - FPU Safety Case Ph 3 Rev 000 Technical References complete | 2024-10-29 | 2024-10-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A5010 | DNB Enhanced Safety Cases | Lessons Learned Workshop - FPU Safety Case Ph 3 Rev 000 Authored | 2024-10-29 | 2024-10-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A5020 | DNB Enhanced Safety Cases | Lessons Learned Workshop - FPU Safety Case Ph 3 Rev 000 Verified | 2024-10-29 | 2024-10-29 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A3040 | DNB Enhanced Safety Cases | Safety Case INA Final Approval - Rev 000 | 2024-10-29 | 2024-10-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A5330 | DNB Enhanced Safety Cases | Hold project kick start meeting with Station & key suppliers | 2024-10-29 | 2024-11-07 | 5 | 0 | 7 | 9 | 100% | 0.55556 | 1 | Completed
W232LT | W232 | W232.A5340 | DNB Enhanced Safety Cases | Agree resource & timescales with suppliers for delivering key refs, incl contingency, risk & allowance for rework | 2024-10-29 | 2024-11-07 | 5 | 0 | 7 | 9 | 100% | 0.55556 | 1 | Completed
W772LT | W772 | W772LT.T1220 | DNB Pull Harder Safety Case | <Specification for Pull Harder Facility> - FMAPS Review EAN / Report | 2024-10-29 | 2024-11-04 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
W772LT | W772 | W772LT.A1035 | DNB Pull Harder Safety Case | INSA comments on NSRS | 2024-10-31 | 2024-11-08 | 10 | 0 | 6 | 8 | 100% | 1.25 | 1 | Completed
W772LT | W772 | W772LT.D3070 | DNB Pull Harder Safety Case | Add Data to PRC Paper | 2024-10-31 | 2024-10-31 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.D3080 | DNB Pull Harder Safety Case | PCL Validate & Approve Baseline Package for PRC Submission | 2024-11-01 | 2024-11-05 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
W232LT | W232 | W232.A2260 | DNB Enhanced Safety Cases | Rev 000 - Station Approval for mod implementation (including station review meeting) | 2024-11-04 | 2024-11-07 | 5 | 0 | 3 | 3 | 100% | 1.6667 | 1 | Completed
W772LT | W772 | W772LT.T1230 | DNB Pull Harder Safety Case | <Specification for Pull Harder Facility> - EAN / Report Completed | 2024-11-04 | 2024-11-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6698LT | W224 | W224.3670 | HRA Enhanced Defueling Safety Case | Verify | 2024-11-05 | 2025-01-02 | 10 | 0 | 39 | 58 | 100% | 0.17241 | 1 | Completed
ER6701LT | W228 | W228.3670 | HYA Enhanced Defueling Safety Case | Verify | 2024-11-05 | 2025-01-02 | 10 | 0 | 39 | 58 | 100% | 0.17241 | 1 | Completed
ER6372LT | W203 | W203.D1000 | HNB Enhanced Defuelling Safety Cases | Issue PRC Paper to PRC Members | 2024-11-06 | 2024-11-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1100 | HNB Enhanced Defuelling Safety Cases | PRC Members Review IRM Documentation | 2024-11-06 | 2024-11-12 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
W772LT | W772 | W772LT.D3090 | DNB Pull Harder Safety Case | Gate A PRC Paper Submission | 2024-11-06 | 2024-11-06 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.D3100 | DNB Pull Harder Safety Case | PRC Members Review PRC Documentation | 2024-11-06 | 2024-11-12 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
W232LT | W232 | W232.2010 | DNB Enhanced Safety Cases | >>>OUTGOING ENABLER DNB Enhanced Safety Case Station Approved - Rev 000 | 2024-11-07 | 2024-11-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A1070 | DNB Enhanced Safety Cases | All Safety Cases Approved - Rev 000 (FEED TO SUMMARY SCHEDULE) | 2024-11-07 | 2024-11-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A2480 | DNB Enhanced Safety Cases | Rev 000 - Station Approval Obtained and CAT 2 Safety Case Complete *(KDM)* | 2024-11-07 | 2024-11-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A5390 | DNB Enhanced Safety Cases | Issue agreed work programme to stakeholders & suppliers | 2024-11-07 | 2024-11-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A5400 | DNB Enhanced Safety Cases | Develop plan with further iterations and confirm approval from key stakeholders | 2024-11-07 | 2024-12-18 | 10 | 0 | 29 | 41 | 100% | 0.2439 | 1 | Completed
W232LT | W232 | W232.A5420 | DNB Enhanced Safety Cases | Key Stakeholders Identified | 2024-11-07 | 2024-11-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A5430 | DNB Enhanced Safety Cases | CA PJB Held | 2024-11-07 | 2024-11-07 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A1037 | DNB Pull Harder Safety Case | Incorporate INSA, Station, DA (peer) comments | 2024-11-08 | 2024-11-21 | 10 | 0 | 9 | 13 | 100% | 0.76923 | 1 | Completed
W772LT | W772 | W772.A1000 | DNB Pull Harder Safety Case | Discovery Milestone: Human Factors Confirm Requirements | 2024-11-08 | 2024-11-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.1380 | HRA Reactors Shutdown Essential Safety Cases | Review of Reactor Ess Safety Case 1 - (INSA) Lessons Learnt Review Complete | 2024-11-11 | 2024-11-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.1380 | HYA Reactors Shutdown Essential Safety Cases | Review of Reactor Ess Safety Case 1 - (INSA) Lessons Learnt Review Complete | 2024-11-11 | 2024-11-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A2130 | DNB Pull Harder Safety Case | <Human Factors> - Advice and Review | 2024-11-11 | 2024-12-17 | 20 | 0 | 26 | 36 | 100% | 0.55556 | 1 | Completed
ER6650LT | W226 | W226.1380 | HYA Fuel Handling Essential Safety Case | Review of Reactor Ess Safety Case 1 - Lessons Learnt Review Complete | 2024-11-11 | 2024-11-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.1385 | HRA Fuel Handling Essential Safety Case | INSA Final Approval - Lessons Learnt Review Complete | 2024-11-11 | 2024-11-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.1385 | HYA Fuel Handling Essential Safety Case | INSA Final Approval - Lessons Learnt Review Complete | 2024-11-11 | 2024-11-11 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C1930 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><FPU Handling with Uninspected Welds item 6> - Summary Bar | 2024-11-12 | 2024-11-12 | 29 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C1940 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><FPU Handling with Uninspected Welds item 6> - Draft and issue RFS | 2024-11-12 | 2024-11-12 | 10 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C1950 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><FPU Handling with Uninspected Welds item 6> - Supplier prepare and issue Offer | 2024-11-12 | 2024-11-12 | 8 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C1960 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><FPU Handling with Uninspected Welds item 6> - Review Offer, prepare and issue CI | 2024-11-12 | 2024-11-12 | 5 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C1970 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><FPU Handling with Uninspected Welds item 6> - Supplier mobilisation time | 2024-11-12 | 2024-11-12 | 5 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C1980 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><FPU Handling with Uninspected Welds item 6> - Pre Job Brief | 2024-11-12 | 2024-11-12 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2170 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><ESA Handling with OEM NSPs item 8> - Summary Bar | 2024-11-12 | 2024-11-12 | 29 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2180 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><ESA Handling with OEM NSPs item 8> - Draft and issue RFS | 2024-11-12 | 2024-11-12 | 10 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2190 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><ESA Handling with OEM NSPs item 8> - Supplier prepare and issue Offer | 2024-11-12 | 2024-11-12 | 8 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2200 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><ESA Handling with OEM NSPs item 8> - Review Offer, prepare and issue CI | 2024-11-12 | 2024-11-12 | 5 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2210 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><ESA Handling with OEM NSPs item 8> - Supplier mobilisation time | 2024-11-12 | 2024-11-12 | 5 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2220 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><ESA Handling with OEM NSPs item 8> - Pre Job Brief | 2024-11-12 | 2024-11-12 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2410 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 10> - Summary Bar | 2024-11-12 | 2024-11-12 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2420 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 10> - Draft and issue RFS | 2024-11-12 | 2024-11-12 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2430 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 10> - Supplier prepare and issue Offer | 2024-11-12 | 2024-11-12 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2440 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 10> - Review Offer, prepare and issue CI | 2024-11-12 | 2024-11-12 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2450 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 10> - Supplier mobilisation time | 2024-11-12 | 2024-11-12 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2460 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 10> - Pre Job Brief | 2024-11-12 | 2024-11-12 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2740 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 13> - Summary Bar | 2024-11-12 | 2024-11-12 | 29 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2750 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 13> - Draft and issue RFS | 2024-11-12 | 2024-11-12 | 10 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2760 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 13> - Supplier prepare and issue Offer | 2024-11-12 | 2024-11-12 | 8 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2770 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 13> - Review Offer, prepare and issue CI | 2024-11-12 | 2024-11-12 | 5 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2780 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 13> - Supplier mobilisation time | 2024-11-12 | 2024-11-12 | 5 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2790 | DNB Enhanced Safety Cases | < SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 13> - Pre Job Brief | 2024-11-12 | 2024-11-12 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772.A1010 | DNB Pull Harder Safety Case | <S'standt'n of Funct'l Cap of PWTS and DWTS at the Enh'ed Overload Trip Settings> - Prepare Draft EAN / Report | 2024-11-13 | 2025-02-14 | 20 | 0 | 65 | 93 | 100% | 0.21505 | 1 | Completed
W232LT | W232 | W232.C2890 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Summary | 2024-11-14 | 2024-11-14 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2900 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Prepare Draft EAN | 2024-11-14 | 2024-11-14 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2910 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Issue Draft EAN to EDF for Review. | 2024-11-14 | 2024-11-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2920 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Draft EAN Reviewed by EDF SQEP | 2024-11-14 | 2024-11-14 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2930 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Address Comments from EDF Review on Draft EAN | 2024-11-14 | 2024-11-14 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2940 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Issue Final EAN | 2024-11-14 | 2024-11-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2950 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - EAN Completed and Uploaded to CDMS | 2024-11-14 | 2024-11-14 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2960 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - EAN Completed | 2024-11-14 | 2024-11-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2970 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Summary Bar | 2024-11-14 | 2024-11-14 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2980 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Draft and issue RFS | 2024-11-14 | 2024-11-14 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C2990 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Supplier prepare and issue Offer | 2024-11-14 | 2024-11-14 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C3000 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Review Offer, prepare and issue CI | 2024-11-14 | 2024-11-14 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C3010 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Supplier mobilisation time | 2024-11-14 | 2024-11-14 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C3020 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Pre Job Brief | 2024-11-14 | 2024-11-14 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C3030 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - TSA Internal Review of Draft EAN | 2024-11-14 | 2024-11-14 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A5690 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events (Group 2)> - Draft Task Sheet | 2024-11-14 | 2024-11-14 | 15 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A5700 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events (Group 2)> - Issue Task sheet | 2024-11-14 | 2024-11-14 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A5710 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events (Group 2)> - Review Task sheet | 2024-11-14 | 2024-11-14 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A5720 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events (Group 2)> - Approve Task sheet | 2024-11-14 | 2024-11-14 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A5730 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events (Group 2)> - Search for station Lifetime Record | 2024-11-14 | 2024-11-14 | 20 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A5740 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events (Group 2)> - Review station Lifetime Record | 2024-11-14 | 2024-11-14 | 20 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A5750 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit (Group 2)>-Issue finding from Review of Lifetime Record | 2024-11-14 | 2024-11-14 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A5760 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit (Grp 2)> Hold scoping session with DA, SAG and Station | 2024-11-14 | 2024-11-14 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A5770 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events (Group 2)> - Issue scope for review | 2024-11-14 | 2024-11-14 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A5780 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events (Group 2)> - Approve Scope | 2024-11-14 | 2024-11-14 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 2290 | HYA Fuel Handling Essential Safety Case | ONR issue letter of No Objection | 2024-11-14 | 2025-01-24 | 37 | 0 | 45 | 71 | 100% | 0.52113 | 1 | Completed
ER6698LT | W224 | W224. A1550 | HRA Enhanced Defueling Safety Case | Write & Prepare IRM Paper [Schedule, Cost, Estimates, Risks] | 2024-11-18 | 2025-01-02 | 15 | 0 | 30 | 45 | 100% | 0.33333 | 1 | Completed
ER6701LT | W228 | W228. A1550 | HYA Enhanced Defueling Safety Case | Write & Prepare IRM Paper [Schedule, Cost, Estimates, Risks] | 2024-11-18 | 2025-01-02 | 15 | 0 | 30 | 45 | 100% | 0.33333 | 1 | Completed
ER6372LT | W203 | W203.C1410 | HNB Enhanced Defuelling Safety Cases | Incorporate CO & Station comments | 2024-11-18 | 2024-11-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1420 | HNB Enhanced Defuelling Safety Cases | Produce verification file | 2024-11-18 | 2024-11-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1120 | HNB Enhanced Defuelling Safety Cases | Modify Estimate, Schedule & Risk Log as Required | 2024-11-19 | 2024-11-19 | 3 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A4220 | HNB Enhanced Defuelling Safety Cases | SC - Cost of Contract - Atkins realis Contract | 2024-11-19 | 2025-01-17 | 99 | 0 | 40 | 59 | 100% | 1.678 | 1 | Completed
ER6372LT | W203 | W203.D1110 | HNB Enhanced Defuelling Safety Cases | Hold PRC Meeting | 2024-11-19 | 2024-11-19 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.E4200 | HNB Enhanced Defuelling Safety Cases | Project Management C - D | 2024-11-19 | 2025-01-17 | 101 | 0 | 40 | 59 | 100% | 1.7119 | 1 | Completed
ER6372LT | W203 | W203.E1550 | HNB Enhanced Defuelling Safety Cases | Station Oversight C - D | 2024-11-19 | 2025-01-17 | 101 | 0 | 40 | 59 | 100% | 1.7119 | 1 | Completed
W772LT | W772 | W772LT.D3110 | DNB Pull Harder Safety Case | Hold PRC Meeting | 2024-11-19 | 2024-11-19 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.D3120 | DNB Pull Harder Safety Case | Modify Estimate, Schedule & Risk Log as Required | 2024-11-19 | 2024-11-19 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.A4210 | HNB Enhanced Defuelling Safety Cases | Gate C PRC Paper Approval | 2024-11-19 | 2024-11-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.D3130 | DNB Pull Harder Safety Case | Gate A PRC Paper Approval | 2024-11-19 | 2024-11-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.D2065 | DNB Pull Harder Safety Case | Gate A PRC Paper Approval | 2024-11-19 | 2024-11-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1290 | HNB Enhanced Defuelling Safety Cases | Agree design proposals with Station in the case of hardware mods | 2024-11-20 | 2024-11-26 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6372LT | W203 | W203.D1450 | HNB Enhanced Defuelling Safety Cases | Produce supporting reference <Generic Hoist Trip Setting Increase SC> | 2024-11-20 | 2024-12-17 | 20 | 0 | 19 | 27 | 100% | 0.74074 | 1 | Completed
ER6372LT | W203 | W203.D1550 | HNB Enhanced Defuelling Safety Cases | Identify verifier for the case & establish all other resources | 2024-11-20 | 2024-11-26 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6372LT | W203 | W203.D1310 | HNB Enhanced Defuelling Safety Cases | CA to agree with CO format of the safety case & produce agreed contents page | 2024-11-25 | 2024-11-26 | 2 | 0 | 1 | 1 | 100% | 2 | 1 | Completed
W232LT | W232 | W232.C3070 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events> - Summary | 2024-11-26 | 2024-11-26 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C3080 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events> - Prepare Draft EAN - Group 2 | 2024-11-26 | 2024-11-26 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C3090 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events> - Issue Draft EAN to EDF for Review. | 2024-11-26 | 2024-11-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C3100 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events> - Draft EAN Reviewed by EDF SQEP | 2024-11-26 | 2024-11-26 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C3110 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events> - Address Comments from EDF Review on | 2024-11-26 | 2024-11-26 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C3120 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events> - Issue Final EAN | 2024-11-26 | 2024-11-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C3130 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events> - EAN Completed and Uploaded to CDMS | 2024-11-26 | 2024-11-26 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C3140 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events> - EAN Completed | 2024-11-26 | 2024-11-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C3085 | DNB Enhanced Safety Cases | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events> - TSA Internal Review of Draft EAN | 2024-11-26 | 2024-11-26 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1220 | HNB Enhanced Defuelling Safety Cases | Produce draft NSRS (using BARRIER MODEL) | 2024-11-27 | 2024-12-03 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6372LT | W203 | W203.D1340 | HNB Enhanced Defuelling Safety Cases | Produce verification plan | 2024-11-27 | 2024-11-28 | 2 | 0 | 1 | 1 | 100% | 2 | 1 | Completed
W230LT | W230 | W230.2010 | HYB Enhanced Defueling Safety Case Strategy | TSA Issue Final Report | 2024-11-27 | 2024-12-18 | 1 | 0 | 16 | 21 | 100% | 0.047619 | 1 | Completed
W234LT | W234 | W234.2010 | TOR Enhanced Defueling Safety Case Strategy | TSA Issue Final Report | 2024-11-27 | 2024-12-18 | 1 | 0 | 16 | 21 | 100% | 0.047619 | 1 | Completed
W232LT | W232 | W232.A2420 | DNB Enhanced Safety Cases | Rev 000 - Post Job Debrief | 2024-11-28 | 2024-11-28 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A5030 | DNB Enhanced Safety Cases | Lessons Learned Workshop - FPU Safety Case Ph 3 Rev 000 Station approved | 2024-11-28 | 2024-11-28 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.A5220 | DNB Enhanced Safety Cases | Lessons Learned Workshop - FPU Safety Case Ph 3 Rev 000 INSA | 2024-11-28 | 2024-11-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A27130 | HRA Fuel Handling Essential Safety Case | ETC (DD-PF) 2024 | 2024-12-02 | 2024-12-31 | 20 | 0 | 20 | 29 | 100% | 0.68966 | 1 | Completed
ER6650LT | W226 | W226.A27130 | HYA Fuel Handling Essential Safety Case | ETC (DD-PF) 2024 | 2024-12-02 | 2024-12-31 | 20 | 0 | 20 | 29 | 100% | 0.68966 | 1 | Completed
W520LT | W520 | W520.A1030 | FLEETWIDE CTO Defueling Safety Case Delivery | 2024 Costs | 2024-12-02 | 2024-12-27 | 18 | 0 | 18 | 25 | 100% | 0.72 | 1 | Completed
W520LT | W520 | W520.A1290 | FLEETWIDE CTO Defueling Safety Case Delivery | ETC (DD-PF) 2024 | 2024-12-02 | 2024-12-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.T1270 | DNB Pull Harder Safety Case | <Operating Strategy for Pull Harder Facility> - Draft EAN / Report Tech Reviewed by EDF SQEP | 2024-12-02 | 2024-12-13 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
W232LT | W232 | W232.C3410 | DNB Enhanced Safety Cases | <NEW SCOPE CN3472> Scoping of Requirement | 2024-12-02 | 2024-12-31 | 18 | 0 | 19 | 29 | 100% | 0.62069 | 1 | Completed
ER6372LT | W203 | W203.D1230 | HNB Enhanced Defuelling Safety Cases | Station comments on NSRS | 2024-12-04 | 2024-12-13 | 8 | 0 | 7 | 9 | 100% | 0.88889 | 1 | Completed
ER6372LT | W203 | W203.D1240 | HNB Enhanced Defuelling Safety Cases | Key Stakeholders (Peer) comments on NSRS (as required) | 2024-12-04 | 2024-12-13 | 8 | 0 | 7 | 9 | 100% | 0.88889 | 1 | Completed
W772LT | W772 | W772LT.KDM.A1047-1 | DNB Pull Harder Safety Case | KDM - <NEW SCOPE CN 3373> - NSRS presented at NSC | 2024-12-04 | 2024-12-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A1047 | DNB Pull Harder Safety Case | <NEW SCOPE CN 3373> - NSRS presented at NSC | 2024-12-04 | 2024-12-04 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772.A1110 | DNB Pull Harder Safety Case | <New SCOPE PENDING CN3634> - <Cavendish PWTS Funct Capability Report> - Produce Report | 2024-12-05 | 2025-01-06 | 1 | 0 | 20 | 32 | 100% | 0.03125 | 1 | Completed
W772LT | W772 | W772LT.A1057 | DNB Pull Harder Safety Case | <NEW SCOPE CN 3373> - Address NSC Comments | 2024-12-05 | 2024-12-18 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
W232LT | W232 | W232.C3150 | DNB Enhanced Safety Cases | <NEW SCOPE CN3472> - Review faults | 2024-12-06 | 2025-01-10 | 14 | 0 | 22 | 35 | 100% | 0.4 | 1 | Completed
W232LT | W232 | W232.C3330 | DNB Enhanced Safety Cases | <NEW SCOPE CN3472> Review Technical note to be issued to SAG | 2024-12-06 | 2025-01-10 | 11 | 0 | 23 | 35 | 100% | 0.31429 | 1 | Completed
W232LT | W232 | W232.A5470 | DNB Enhanced Safety Cases | Draft task sheet | 2024-12-06 | 2025-01-24 | 33 | 0 | 33 | 49 | 100% | 0.67347 | 1 | Completed
ER6666LT | W209 | W209.1545 | HYB Essential Defueling Safety Case | Incorporate INSA comments | 2024-12-09 | 2025-02-19 | 22 | 0 | 50 | 72 | 100% | 0.30556 | 1 | Completed
ER6668LT | W213 | W213.1545 | TOR Essential Defueling Safety Case | Incorporate INSA comments | 2024-12-09 | 2025-02-19 | 27 | 0 | 49 | 72 | 100% | 0.375 | 1 | Completed
ER6372LT | W203 | W203.D1730 | HNB Enhanced Defuelling Safety Cases | INSA Resource Identified | 2024-12-13 | 2024-12-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1580 | HNB Enhanced Defuelling Safety Cases | INA comments on NSRS | 2024-12-16 | 2024-12-20 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
W772LT | W772 | W772LT.T1280 | DNB Pull Harder Safety Case | <Operating Strategy for Pull Harder Facility> - Address Comments from EDF Review on Draft EAN / Report | 2024-12-16 | 2025-02-28 | 5 | 0 | 51 | 74 | 100% | 0.067568 | 1 | Completed
ER6372LT | W203 | W203.D1640 | HNB Enhanced Defuelling Safety Cases | Develop plan with further iterations | 2024-12-17 | 2025-01-02 | 10 | 0 | 9 | 16 | 100% | 0.625 | 1 | Completed
W772LT | W772 | W772LT.A2140 | DNB Pull Harder Safety Case | <Human Factors> - Populate HF Template | 2024-12-17 | 2024-12-17 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1600 | HNB Enhanced Defuelling Safety Cases | Verify supporting reference <Generic Hoist Trip Setting Increase SC> | 2024-12-18 | 2025-01-03 | 10 | 0 | 9 | 16 | 100% | 0.625 | 1 | Completed
W772LT | W772 | W772LT.A1125 | DNB Pull Harder Safety Case | Proposal - Preliminary Work | 2024-12-18 | 2025-01-06 | 26 | 0 | 11 | 19 | 100% | 1.3684 | 1 | Completed
W232LT | W232 | W232.C1850 | DNB Enhanced Safety Cases | <SCOPE CHANGE CN3472><FPU Uninspected Welds lifting integrity (including sub-veto faults)> - Prepare Draft EAN Part 1 | 2024-12-19 | 2025-01-23 | 20 | 0 | 22 | 35 | 100% | 0.57143 | 1 | Completed
W772LT | W772 | W772LT.KDM.A1067-1 | DNB Pull Harder Safety Case | KDM - <NEW SCOPE CN 3373> - Final INSA Approval and Re-sign Milestones | 2024-12-19 | 2024-12-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W230LT | W230 | W230.2020 | HYB Enhanced Defueling Safety Case Strategy | TR Completed and Uploaded to CDMS | 2024-12-19 | 2024-12-20 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
W772LT | W772 | W772LT.A1040 | DNB Pull Harder Safety Case | Issue final NSRS | 2024-12-19 | 2024-12-19 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A1050 | DNB Pull Harder Safety Case | Station agree NSRS ==> KDM | 2024-12-19 | 2024-12-19 | 10 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A1235 | DNB Pull Harder Safety Case | Circulate NSRS for Relevant Stakeholders | 2024-12-19 | 2024-12-19 | 5 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A1230 | DNB Pull Harder Safety Case | DA & INSA agree NSRS (for authorised designers-NSRS must be reviewed by DA) ==> KDM | 2024-12-19 | 2024-12-19 | 10 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A1500 | DNB Pull Harder Safety Case | Send NSRS to ONR to determine level of review required (Acknowledgement or Agreement) | 2024-12-19 | 2024-12-19 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A1510 | DNB Pull Harder Safety Case | ONR L4 Meeting | 2024-12-19 | 2024-12-19 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A1067 | DNB Pull Harder Safety Case | <NEW SCOPE CN 3373> - Final INSA Approval and Re-sign Milestones | 2024-12-19 | 2024-12-19 | 12 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W234LT | W234 | W234.2020 | TOR Enhanced Defueling Safety Case Strategy | TR Completed and Uploaded to CDMS | 2024-12-19 | 2024-12-20 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
W772LT | W772 | W772LT.KDM.SP02 | DNB Pull Harder Safety Case | KDM - NSRS agreed by stakeholders EC 375698 <DNB Pull Harder SC> | 2024-12-19 | 2024-12-19 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W230LT | W230 | W230.1900 | HYB Enhanced Defueling Safety Case Strategy | EC Kick Off Meeting & Early Strategy Development | 2024-12-20 | 2024-12-20 | 2 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W230LT | W230 | W230.3760 | HYB Enhanced Defueling Safety Case Strategy | HYB Enhanced Defueling Rate: Strategy EAN Complete | 2024-12-20 | 2024-12-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W234LT | W234 | W234.1900 | TOR Enhanced Defueling Safety Case Strategy | EC Kick Off Meeting & Early Strategy Development | 2024-12-20 | 2024-12-20 | 2 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W234LT | W234 | W234.3760 | TOR Enhanced Defueling Safety Case Strategy | TOR Enhanced Defueling Rate: Strategy EAN Complete | 2024-12-20 | 2024-12-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W230LT | W230 | W230.2030 | HYB Enhanced Defueling Safety Case Strategy | Strategy EAN Complete | 2024-12-20 | 2024-12-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W230LT | W230 | W230.3740 | HYB Enhanced Defueling Safety Case Strategy | HYB - EC Kick Off Meeting & Early Strategy Development | 2024-12-20 | 2024-12-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W234LT | W234 | W234.2030 | TOR Enhanced Defueling Safety Case Strategy | Strategy EAN Complete | 2024-12-20 | 2024-12-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W234LT | W234 | W234.3740 | TOR Enhanced Defueling Safety Case Strategy | TOR - EC Kick Off Meeting & Early Strategy Development | 2024-12-20 | 2024-12-20 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1420 | HNB Enhanced Defuelling Safety Cases | Incorporate INA, Station, ED (peer) comments | 2024-12-23 | 2024-12-31 | 5 | 0 | 4 | 8 | 100% | 0.625 | 1 | Completed
ER6701LT | W228 | W228.2220 | HYA Enhanced Defueling Safety Case | Contract Negotiations | 2025-01-02 | 2025-02-03 | 1 | 0 | 23 | 32 | 100% | 0.03125 | 1 | Completed
ER6372LT | W203 | W203.D1250 | HNB Enhanced Defuelling Safety Cases | Issue final NSRS | 2025-01-02 | 2025-01-02 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1260 | HNB Enhanced Defuelling Safety Cases | Station agree NSRS *(KDM)* <Generic Hoist Trip Setting Increase EC375945> | 2025-01-02 | 2025-01-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1720 | HNB Enhanced Defuelling Safety Cases | Verifier PJB Held | 2025-01-02 | 2025-01-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1460 | HNB Enhanced Defuelling Safety Cases | Issue high quality verified draft iss A with verification file to INSA & station (T - 3 wks before NSC date) *(E375412)* | 2025-01-02 | 2025-01-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1480 | HNB Enhanced Defuelling Safety Cases | INSA review & iteration of comments (using BARRIER MODEL) | 2025-01-02 | 2025-02-04 | 6 | 0 | 23 | 33 | 100% | 0.18182 | 1 | Completed
ER6372LT | W203 | W203.C1430 | HNB Enhanced Defuelling Safety Cases | Verification complete | 2025-01-02 | 2025-01-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1440 | HNB Enhanced Defuelling Safety Cases | Submit for approval - Categoriser ratifies; RE/CO endorsement | 2025-01-02 | 2025-01-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1470 | HNB Enhanced Defuelling Safety Cases | Key Stakeholders Approval, if requested | 2025-01-02 | 2025-01-10 | 7 | 0 | 7 | 8 | 100% | 0.875 | 1 | Completed
ER6698LT | W224 | W224.1230 | HRA Enhanced Defueling Safety Case | Design Feedback into Scheme | 2025-01-02 | 2025-01-08 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6698LT | W224 | W224.1310 | HRA Enhanced Defueling Safety Case | HAZOP - Feed into CETS (trip Function) | 2025-01-02 | 2025-01-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6698LT | W224 | W224.1530 | HRA Enhanced Defueling Safety Case | Review & Approval | 2025-01-02 | 2025-01-15 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6698LT | W224 | W224.2220 | HRA Enhanced Defueling Safety Case | Contract Negotiations | 2025-01-02 | 2025-02-03 | 9 | 0 | 22 | 32 | 100% | 0.28125 | 1 | Completed
ER6698LT | W224 | W224. A1560 | HRA Enhanced Defueling Safety Case | IRM Paper Stakeholder Sign Off | 2025-01-02 | 2025-01-06 | 8 | 0 | 2 | 4 | 100% | 2 | 1 | Completed
ER6698LT | W224 | W224.3680 | HRA Enhanced Defueling Safety Case | EdF Technical Review | 2025-01-02 | 2025-01-31 | 11 | 0 | 21 | 29 | 100% | 0.37931 | 1 | Completed
ER6701LT | W228 | W228.3680 | HYA Enhanced Defueling Safety Case | EdF Technical Review | 2025-01-02 | 2025-01-28 | 11 | 0 | 18 | 26 | 100% | 0.42308 | 1 | Completed
ER6701LT | W228 | W228. A1560 | HYA Enhanced Defueling Safety Case | IRM Paper stakeholder sign off | 2025-01-02 | 2025-01-06 | 8 | 0 | 2 | 4 | 100% | 2 | 1 | Completed
ER6701LT | W228 | W228.1530 | HYA Enhanced Defueling Safety Case | Review & Approval | 2025-01-02 | 2025-01-15 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6701LT | W228 | W228.1310 | HYA Enhanced Defueling Safety Case | HAZOP - Feed into CETS (trip Function) | 2025-01-02 | 2025-01-02 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6701LT | W228 | W228.1230 | HYA Enhanced Defueling Safety Case | Design Feedback into Scheme | 2025-01-02 | 2025-01-08 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
ER6372LT | W203 | W203.D1210 | HNB Enhanced Defuelling Safety Cases | Produce MF (as required) | 2025-01-02 | 2025-01-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1400 | HNB Enhanced Defuelling Safety Cases | Issue MF (as required) | 2025-01-02 | 2025-01-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1520 | HNB Enhanced Defuelling Safety Cases | Categorisation by RE / Station | 2025-01-02 | 2025-01-08 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
W232LT | W232 | W232.C3420 | DNB Enhanced Safety Cases | <NEW SCOPE CN3472> Draft SCDP | 2025-01-02 | 2025-01-07 | 14 | 0 | 3 | 5 | 100% | 2.8 | 1 | Completed
ER6372LT | W203 | W203.D1430 | HNB Enhanced Defuelling Safety Cases | NSORC agree NSRS (SZB Only) | 2025-01-02 | 2025-01-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1440 | HNB Enhanced Defuelling Safety Cases | Key Stakeholders agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2025-01-02 | 2025-01-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1590 | HNB Enhanced Defuelling Safety Cases | INA agree NSRS | 2025-01-02 | 2025-01-02 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1300 | HNB Enhanced Defuelling Safety Cases | Consolidate & issue to stakeholders & suppliers agreed NSRS (as required) | 2025-01-03 | 2025-01-09 | 5 | 0 | 4 | 6 | 100% | 0.83333 | 1 | Completed
ER6372LT | W203 | W203.D1610 | HNB Enhanced Defuelling Safety Cases | BE Technical review of supporting reference <Generic Hoist Trip Setting Increase SC> | 2025-01-06 | 2025-01-17 | 10 | 0 | 9 | 11 | 100% | 0.90909 | 1 | Completed
W772LT | W772 | W772.A1120 | DNB Pull Harder Safety Case | <New SCOPE PENDING CN3634> - <Cavendish PWTS Report> - EDF TR Round 1 | 2025-01-06 | 2025-01-10 | 1 | 0 | 5 | 4 | 100% | 0.25 | 1 | Completed
W772LT | W772 | W772LT.A1145 | DNB Pull Harder Safety Case | Pre Job Brief | 2025-01-06 | 2025-01-06 | 10 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6698LT | W224 | W224. A1570 | HRA Enhanced Defueling Safety Case | Gate B-D PRC Paper Submission | 2025-01-08 | 2025-01-08 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C3430 | DNB Enhanced Safety Cases | <NEW SCOPE CN3472> Review SCDP | 2025-01-08 | 2025-01-16 | 10 | 0 | 6 | 8 | 100% | 1.25 | 1 | Completed
ER6372LT | W203 | W203.D1560 | HNB Enhanced Defuelling Safety Cases | Issue agreed work programme to stakeholders & suppliers | 2025-01-09 | 2025-01-09 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1410 | HNB Enhanced Defuelling Safety Cases | INSA agree MF (as required) *(KDM)* <Generic Hoist Trip Setting Increase EC375945> | 2025-01-09 | 2025-01-10 | 2 | 0 | 2 | 1 | 100% | 2 | 1 | Completed
W772LT | W772 | W772.A1130 | DNB Pull Harder Safety Case | <New SCOPE PENDING CN3634> - <Cavendish PWTS Report> - Address Comments | 2025-01-10 | 2025-01-28 | 1 | 0 | 13 | 18 | 100% | 0.055556 | 1 | Completed
W232LT | W232 | W232.C3160 | DNB Enhanced Safety Cases | <NEW SCOPE CN3472> - Draft specification of R6 assessment to be issue to SAG will include OEM NSPs | 2025-01-10 | 2025-01-13 | 14 | 0 | 2 | 3 | 100% | 4.6667 | 1 | Completed
ER6372LT | W203 | W203.D1650 | HNB Enhanced Defuelling Safety Cases | INSA Approval Date Identified | 2025-01-10 | 2025-01-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1660 | HNB Enhanced Defuelling Safety Cases | Provide Provisional NSC Date (as required) | 2025-01-10 | 2025-01-10 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6698LT | W224 | W224. A1580 | HRA Enhanced Defueling Safety Case | Hold PRC | 2025-01-13 | 2025-01-22 | 1 | 0 | 1 | 9 | 100% | 0.11111 | 1 | Completed
ER6701LT | W228 | W228. A1580 | HYA Enhanced Defueling Safety Case | Hold PRC | 2025-01-13 | 2025-01-22 | 1 | 0 | 1 | 9 | 100% | 0.11111 | 1 | Completed
W232LT | W232 | W232.C3340 | DNB Enhanced Safety Cases | <NEW SCOPE CN3472> Atkins to issue Technical note to SAG | 2025-01-13 | 2025-01-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C3360 | DNB Enhanced Safety Cases | Decision Point Milestone - (NSP Pin Failure) | 2025-01-13 | 2025-01-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C3170 | DNB Enhanced Safety Cases | <NEW SCOPE CN3472> - Issue specification to SAG | 2025-01-13 | 2025-01-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.1190 | HRA Fuel Handling Essential Safety Case | Station Approval of HRA Defuelling Fuel Handling Essential Safety Case | 2025-01-14 | 2025-01-27 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6650LT | W226 | W226.1195 | HYA Fuel Handling Essential Safety Case | Station Approval of HYA Defuelling Fuel Handling Essential Safety Case | 2025-01-14 | 2025-01-29 | 10 | 0 | 11 | 15 | 100% | 0.66667 | 1 | Completed
ER6698LT | W224 | W224.2160 | HRA Enhanced Defueling Safety Case | Best Option/ALARP Strategy >>> Discovery Milestone | 2025-01-16 | 2025-01-29 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6701LT | W228 | W228.2160 | HYA Enhanced Defueling Safety Case | Best Option/ALARP Strategy | 2025-01-16 | 2025-01-29 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
W772LT | W772 | W772LT.A2630 | DNB Pull Harder Safety Case | <<NEW SCOPE PENDING CN3634><Load Path Assessment Appendix - Fixed DWTS> > - Pre Job Brief | 2025-01-16 | 2025-01-16 | 133 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1320 | HNB Enhanced Defuelling Safety Cases | Prepare the Safety Case Proposal (including OPEX Review) | 2025-01-17 | 2025-01-17 | 30 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1330 | HNB Enhanced Defuelling Safety Cases | Incorporate CO & Station comments | 2025-01-17 | 2025-01-17 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1350 | HNB Enhanced Defuelling Safety Cases | Verification of the case (using BARRIER MODEL) | 2025-01-17 | 2025-01-17 | 20 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1360 | HNB Enhanced Defuelling Safety Cases | Produce verification file | 2025-01-17 | 2025-01-17 | 2 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1380 | HNB Enhanced Defuelling Safety Cases | INSA review & iteration of comments (using BARRIER MODEL) | 2025-01-17 | 2025-01-17 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1480 | HNB Enhanced Defuelling Safety Cases | Verification complete | 2025-01-17 | 2025-01-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1510 | HNB Enhanced Defuelling Safety Cases | Station Approval for mod implementation (including station review meeting) | 2025-01-17 | 2025-01-17 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1530 | HNB Enhanced Defuelling Safety Cases | Issue to CO & Station for comments | 2025-01-17 | 2025-01-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1570 | HNB Enhanced Defuelling Safety Cases | INSA Final Approval *(KDM)* <Generic Hoist Trip Setting Increase EC375945> | 2025-01-17 | 2025-01-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1620 | HNB Enhanced Defuelling Safety Cases | Supporting reference <Generic Hoist Trip Setting Increase SC> approved | 2025-01-17 | 2025-01-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1630 | HNB Enhanced Defuelling Safety Cases | All supporting references completed | 2025-01-17 | 2025-01-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1670 | HNB Enhanced Defuelling Safety Cases | Post Job Debrief | 2025-01-17 | 2025-01-17 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1740 | HNB Enhanced Defuelling Safety Cases | Station Approval Obtained and CAT 2 Safety Case Complete *(KDM)* <Generic Hoist Trip Setting Increase EC375945> | 2025-01-17 | 2025-01-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D1900 | HNB Enhanced Defuelling Safety Cases | All key supporting technical references complete - Generic Hoist Trip Setting Increase SC | 2025-01-17 | 2025-01-17 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A2640 | DNB Pull Harder Safety Case | <<NEW SCOPE PENDING CN3634><Load Path Assessment Appendix - Fixed DWTS> > - Prepare Draft Report | 2025-01-17 | 2025-02-28 | 21 | 0 | 30 | 42 | 100% | 0.5 | 1 | Completed
ER6698LT | W224 | W224.3920 | HRA Enhanced Defueling Safety Case | Issue RFS | 2025-01-21 | 2025-02-05 | 10 | 0 | 12 | 15 | 100% | 0.66667 | 1 | Completed
ER6701LT | W228 | W228.3920 | HYA Enhanced Defueling Safety Case | Issue RFS | 2025-01-21 | 2025-02-07 | 10 | 0 | 13 | 17 | 100% | 0.58824 | 1 | Completed
W232LT | W232 | W232.C3440 | DNB Enhanced Safety Cases | Decision Point Milestone - Hold Safety Case Decision Panel | 2025-01-23 | 2025-01-23 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C3580 | DNB Enhanced Safety Cases | <SCOPE CHANGE CN3472><FPU Uninspected Welds lifting integrity incl'g sub-veto faults> - Mid Job Brief | 2025-01-23 | 2025-01-23 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A5400 | HRA Reactors Shutdown Essential Safety Cases | ONR Agree/Acknowledge Safety Case EC 363682 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HRA) | 2025-01-24 | 2025-01-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A5410 | HRA Reactors Shutdown Essential Safety Cases | ONR Agree/Acknowledge Safety Case EC 363682 <Reactor Shutdown Essential SC> (Cat 1 MS) (HRA) (FEEDS SUMMARY SCHEDULE) | 2025-01-24 | 2025-01-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5400 | HYA Reactors Shutdown Essential Safety Cases | ONR Agree/Acknowledge Safety Case EC 363676 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HYA) | 2025-01-24 | 2025-01-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5410 | HYA Reactors Shutdown Essential Safety Cases | ONR Agree/Acknowledge Safety Case EC 363676 <Reactor Shutdown Essential SC> (Cat 1 MS) (HYA) (FEEDS SUMMARY SCHEDULE) | 2025-01-24 | 2025-01-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206250 | HYA Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W104, HNB Security Plan) ONR Approved | 2025-01-24 | 2025-01-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.1030 | HYA Fuel Handling Essential Safety Case | >>>OUTGOING ENABLER (W283, HYA Security Plan, W206) HYA Fuel Handling Essential Safety Case ONR Approved | 2025-01-24 | 2025-01-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.1330 | HRA Reactors Shutdown Essential Safety Cases | >>>INCOMING ENABLER (W222) HRA Fuel Handling Essential Safety Case ONR Approved | 2025-01-24 | 2025-01-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.1340 | HRA Reactors Shutdown Essential Safety Cases | >>>MIRROR of INCOMING ENABLER(W222) HRA Fuel Handling Essential Safety Case ONR Approved | 2025-01-24 | 2025-01-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.13125 | HYA Reactors Shutdown Essential Safety Cases | >>>INCOMING ENABLER (W226) HYA Fuel Handling Essential Safety Case ONR Approved | 2025-01-24 | 2025-01-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.13135 | HYA Reactors Shutdown Essential Safety Cases | >>>MIRROR of INCOMING ENABLER (W226) HYA Fuel Handling Essential Safety Case ONR Approved | 2025-01-24 | 2025-01-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.13145 | HYA Reactors Shutdown Essential Safety Cases | >>>INTERFACE MILESTONE (W226) HYA Fuel Handling Essential Safety Case ONR Approved | 2025-01-24 | 2025-01-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A1150 | DNB Pull Harder Safety Case | Produce verification plan | 2025-01-24 | 2025-01-31 | 2 | 0 | 6 | 7 | 100% | 0.28571 | 1 | Completed
ER6378LT | W222 | W222.A13370 | HRA Fuel Handling Essential Safety Case | Cat 1 Safety Case Complete (ONR LI Issued) HRA Defuelling Fuel Handling Essential Safety Case | 2025-01-24 | 2025-01-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A17480 | HRA Fuel Handling Essential Safety Case | ONR Agree/Acknowledge SC ECs(HRA-363840) HRA Defuelling Fuel Handling Essential SC (Cat 1 KDM) (FEEDS SUMMARY SCHEDULE) | 2025-01-24 | 2025-01-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A17480 | HYA Fuel Handling Essential Safety Case | ONR Agree/Acknowledge SC ECs(HYA-363839) HYA Defuelling Fuel Handling Essential SC (Cat 1 KDM) (FEEDS SUMMARY SCHEDULE) | 2025-01-24 | 2025-01-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A13370 | HYA Fuel Handling Essential Safety Case | Cat 1 Safety Case Complete (ONR LI Issued) HYA Defuelling Fuel Handling Essential Safety Case | 2025-01-24 | 2025-01-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.1030 | HRA Fuel Handling Essential Safety Case | >>>OUTGOING ENABLER (HRA Security Plan (W155), W202) - HRA Fuel Handling Essential Safety Case ONR Approved | 2025-01-24 | 2025-01-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.1350 | HRA Reactors Shutdown Essential Safety Cases | >>>INTERFACE MILESTONE (W222) HRA Fuel Handling Essential Safety Case ONR Approved | 2025-01-24 | 2025-01-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A5530 | HRA Reactors Shutdown Essential Safety Cases | Station Approval Period | 2025-01-27 | 2025-01-27 | 10 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
W232LT | W232 | W232.C1700 | DNB Enhanced Safety Cases | <SCOPE CHANGE CN3472><FPU Sub-veto fault frequency> - Prepare Draft EAN Part 1 | 2025-01-27 | 2025-02-21 | 20 | 0 | 20 | 25 | 100% | 0.8 | 1 | Completed
ER6701LT | W228 | W228. A1591 | HYA Enhanced Defueling Safety Case | Gate B PRC Paper Approval | 2025-01-27 | 2025-01-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A2420 | DNB Pull Harder Safety Case | <Load Path Assessment> - R6 Monte Carlo Assessment | 2025-01-27 | 2025-02-28 | 10 | 0 | 24 | 32 | 100% | 0.3125 | 1 | Completed
W232LT | W232 | W232.A5480 | DNB Enhanced Safety Cases | Review task sheet | 2025-01-27 | 2025-01-31 | 5 | 0 | 5 | 4 | 100% | 1.25 | 1 | Completed
ER6371LT | W202 | W202.A5420 | HRA Reactors Shutdown Essential Safety Cases | Station Approve EC 363682 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HRA) (FEEDS TO SUMMARY SCHEDULE) | 2025-01-27 | 2025-01-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A18480 | HRA Fuel Handling Essential Safety Case | Station Approve ECs (HRA-363840) HRA Defuelling Fuel Handling Essential Safety Case (Cat 1 KDM) Delivered (FEEDS TO SUMM | 2025-01-27 | 2025-01-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6371LT | W202 | W202.A2206200 | HRA Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W104 HPB Security Plan)(W285)(W148) CAT 1 Reactors Shutdown SC Station Approved | 2025-01-27 | 2025-01-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.A27270 | HRA Fuel Handling Essential Safety Case | >>>OUTGOING ENABLER (W285)(W148) CAT 1 Fuel Handling SC Station Approved | 2025-01-27 | 2025-01-27 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772.A1140 | DNB Pull Harder Safety Case | <New SCOPE PENDING CN3634> - <Cavendish PWTS Report> - EDF TR Round 2 | 2025-01-28 | 2025-01-31 | 1 | 0 | 4 | 3 | 100% | 0.33333 | 1 | Completed
ER6371LT | W202 | W202.A5430 | HRA Reactors Shutdown Essential Safety Cases | Revise all Affected Drawings and Documents for EC Approval (HRA) | 2025-01-28 | 2025-02-14 | 10 | 0 | 13 | 17 | 100% | 0.58824 | 1 | Completed
ER6378LT | W222 | W222.A17470 | HRA Fuel Handling Essential Safety Case | Revise all Affected Drawings and Documents Following EC Approval | 2025-01-28 | 2025-02-10 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6650LT | W226 | W226.A17470 | HYA Fuel Handling Essential Safety Case | Revise all Affected Drawings and Documents following EC Approval | 2025-01-28 | 2025-02-10 | 10 | 0 | 10 | 13 | 100% | 0.76923 | 1 | Completed
ER6650LT | W226 | W226.A18480 | HYA Fuel Handling Essential Safety Case | Station Approve ECs (HYA-363839) HYA Defuelling Fuel Handling Essential Safety Case (Cat 1 KDM) Delivered (FEEDS TO SUMM | 2025-01-29 | 2025-01-29 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A2150 | DNB Pull Harder Safety Case | <Human Factors> - Review and Finalise HF Template | 2025-01-29 | 2025-01-29 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A2180 | DNB Pull Harder Safety Case | <Human Factors> - HF Template Complete | 2025-01-29 | 2025-01-29 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5430 | HYA Reactors Shutdown Essential Safety Cases | Revise all Affected Drawings and Documents for EC Approval (HYA) | 2025-01-31 | 2025-02-14 | 10 | 0 | 10 | 14 | 100% | 0.71429 | 1 | Completed
ER6661LT | W206 | W206.A5420 | HYA Reactors Shutdown Essential Safety Cases | Station Approve EC 363676 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HYA) (FEEDS TO SUMMARY SCHEDULE) | 2025-01-31 | 2025-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A2206220 | HYA Reactors Shutdown Essential Safety Cases | >>>OUTGOING ENABLER (W286)(W149) CAT 1 Reactors Shutdown SC Station Approved | 2025-01-31 | 2025-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.A27310 | HYA Fuel Handling Essential Safety Case | >>>OUTGOING ENABLER (W286)(W149) CAT 1 Fuel Handling SC Station Approved | 2025-01-31 | 2025-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5530 | HYA Reactors Shutdown Essential Safety Cases | Station Approval Period | 2025-01-31 | 2025-01-31 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | 2295 | HYA Fuel Handling Essential Safety Case | Station Approval of Safety Case | 2025-01-31 | 2025-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6698LT | W224 | W224. A1591 | HRA Enhanced Defueling Safety Case | Gate B PRC Paper Approval | 2025-01-31 | 2025-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6701LT | W228 | W228. A1570 | HYA Enhanced Defueling Safety Case | Gate B-D PRC Paper Submission | 2025-01-31 | 2025-01-31 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W730LT_UN | W730 | W730.1010 | HYB Enhanced Defueling Safety Cases | Project Start | 2025-02-03 | 2025-02-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W730LT_UN | W730 | W730.1410 | HYB Enhanced Defueling Safety Cases | Confirm Objectives to be Delivered at Gate B | 2025-02-03 | 2025-02-13 | 9 | 0 | 9 | 10 | 100% | 0.9 | 1 | Completed
ER6698LT | W224 | W224. A1600 | HRA Enhanced Defueling Safety Case | Funds Released | 2025-02-03 | 2025-02-12 | 8 | 0 | 8 | 9 | 100% | 0.88889 | 1 | Completed
ER6701LT | W228 | W228. A1600 | HYA Enhanced Defueling Safety Case | Funds Released | 2025-02-03 | 2025-02-12 | 8 | 0 | 8 | 9 | 100% | 0.88889 | 1 | Completed
W230LT | W230 | W230.2060 | HYB Enhanced Defueling Safety Case Strategy | HYB Enhanced Defueling Rate: Strategy Development & Produce MF EC NNNNN & Obtain Approval | 2025-02-03 | 2025-02-10 | 6 | 0 | 6 | 7 | 100% | 0.85714 | 1 | Completed
ER6698LT | W224 | W224.A1590 | HRA Enhanced Defueling Safety Case | Gate B for Defuelling Programme Enhancement ECs (HH1) | 2025-02-03 | 2025-02-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A2105 | DNB Pull Harder Safety Case | EC Appendix 4 - Test Schedule - Preliminary Work & Authour - EDF | 2025-02-03 | 2025-02-14 | 10 | 0 | 10 | 11 | 100% | 0.90909 | 1 | Completed
ER6701LT | W228 | W228.A1590 | HYA Enhanced Defueling Safety Case | Gate B for Defuelling Programme Enhancement ECs (HH1) | 2025-02-03 | 2025-02-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772.A1150 | DNB Pull Harder Safety Case | <New SCOPE PENDING CN3634> - <Cavendish PWTS Report> - Complete ( Incorporated into Appendix 1 ) | 2025-02-03 | 2025-02-21 | 5 | 0 | 14 | 18 | 100% | 0.27778 | 1 | Completed
W234LT | W234 | W234.2130 | TOR Enhanced Defueling Safety Case Strategy | TOR Enhanced Defueling Rate: Produce draft NSRS (using BARRIER MODEL) | 2025-02-03 | 2025-02-28 | 20 | 0 | 20 | 25 | 100% | 0.8 | 1 | Completed
W234LT | W234 | W234.2060 | TOR Enhanced Defueling Safety Case Strategy | TOR Enhanced Defueling Rate: Strategy Development & Produce MF EC NNNNN & Obtain Approval | 2025-02-03 | 2025-02-10 | 6 | 0 | 6 | 7 | 100% | 0.85714 | 1 | Completed
W772LT | W772 | W772LT.A2720 | DNB Pull Harder Safety Case | <Load Path Assessment> -Cyclic Loading of Seized OEM NSP Welds Assessment | 2025-02-03 | 2025-02-28 | 10 | 0 | 19 | 25 | 100% | 0.4 | 1 | Completed
W731LT_UN | W731 | W731.1020 | TOR Enhanced Defueling Safety Cases | Confirm Objectives to be Delivered at Gate B | 2025-02-03 | 2025-02-13 | 9 | 0 | 9 | 10 | 100% | 0.9 | 1 | Completed
W731LT_UN | W731 | W731.1030 | TOR Enhanced Defueling Safety Cases | Project Start | 2025-02-03 | 2025-02-03 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1510 | HNB Enhanced Defuelling Safety Cases | Station Approval for mod implementation (including station review meeting) | 2025-02-04 | 2025-02-04 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1490 | HNB Enhanced Defuelling Safety Cases | Incorporate INSA comments | 2025-02-04 | 2025-02-04 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1500 | HNB Enhanced Defuelling Safety Cases | INSA Final Approval *(EC375412)* | 2025-02-04 | 2025-02-04 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1530 | HNB Enhanced Defuelling Safety Cases | Post Job Debrief | 2025-02-04 | 2025-02-04 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.C1520 | HNB Enhanced Defuelling Safety Cases | Station Approval Obtained and CAT 2 Safety Case Complete *(EC375412)* | 2025-02-04 | 2025-02-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6372LT | W203 | W203.D4230 | HNB Enhanced Defuelling Safety Cases | EC Station Approved - EC375412 | 2025-02-04 | 2025-02-04 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W230LT | W230 | W230.2130 | HYB Enhanced Defueling Safety Case Strategy | HYB Enhanced Defueling Rate: Produce draft NSRS (using BARRIER MODEL) | 2025-02-11 | 2025-02-28 | 14 | 0 | 14 | 17 | 100% | 0.82353 | 1 | Completed
ER6698LT | W224 | W224.1580 | HRA Enhanced Defueling Safety Case | PJB | 2025-02-13 | 2025-02-21 | 7 | 0 | 7 | 8 | 100% | 0.875 | 1 | Completed
ER6698LT | W224 | W224.3200 | HRA Enhanced Defueling Safety Case | Start Gate B Activities | 2025-02-13 | 2025-02-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6701LT | W228 | W228.3200 | HYA Enhanced Defueling Safety Case | Start Gate B Activities | 2025-02-13 | 2025-02-13 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6701LT | W228 | W228.1580 | HYA Enhanced Defueling Safety Case | PJB | 2025-02-13 | 2025-02-21 | 7 | 0 | 7 | 8 | 100% | 0.875 | 1 | Completed
ER6371LT | W202 | W202.A5440 | HRA Reactors Shutdown Essential Safety Cases | Develop Implementation & closeout Plan (HRA) | 2025-02-14 | 2025-02-21 | 10 | 0 | 6 | 7 | 100% | 1.4286 | 1 | Completed
W730LT_UN | W730 | W730.1400 | HYB Enhanced Defueling Safety Cases | Initial high level scope of programme | 2025-02-14 | 2025-02-20 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
W731LT_UN | W731 | W731.1070 | TOR Enhanced Defueling Safety Cases | Initial high level scope of programme | 2025-02-14 | 2025-02-20 | 5 | 0 | 5 | 6 | 100% | 0.83333 | 1 | Completed
W772LT | W772 | W772.A1020 | DNB Pull Harder Safety Case | <S'standt'n of Funct'l Cap of PWTS & DWTS at the Enh'ed O'load Trip Sett's> - Issue Draft EAN / Report for Tech Review. | 2025-02-14 | 2025-02-14 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5440 | HYA Reactors Shutdown Essential Safety Cases | Develop Implementation & closeout Plan (HYA) | 2025-02-17 | 2025-02-21 | 10 | 0 | 5 | 4 | 100% | 2.5 | 1 | Completed
W772LT | W772 | W772LT.A2160 | DNB Pull Harder Safety Case | <Test Schedulet> - Prepare Draft Report | 2025-02-17 | 2025-02-21 | 10 | 0 | 4 | 4 | 100% | 2.5 | 1 | Completed
ER6371LT | W202 | W202.1390 | HRA Reactors Shutdown Essential Safety Cases | Review of Reactor Ess Safety Case 2 - (ONR & Station Approved) Lessons Learnt Review Complete | 2025-02-18 | 2025-02-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.1391 | HYA Reactors Shutdown Essential Safety Cases | Review of Reactor Ess Safety Case 2 - (ONR & Station Approved) Lessons Learnt Review Complete | 2025-02-18 | 2025-02-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.1390 | HYA Fuel Handling Essential Safety Case | Review of Reactor Ess Safety Case 2 - Lessons Learnt Review Complete | 2025-02-18 | 2025-02-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6378LT | W222 | W222.1395 | HRA Fuel Handling Essential Safety Case | Station Approval of Safety Case - Lessons Learnt Review Complete | 2025-02-18 | 2025-02-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6650LT | W226 | W226.1395 | HYA Fuel Handling Essential Safety Case | Station Approval of Safety Case - Lessons Learnt Review Complete | 2025-02-18 | 2025-02-18 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1555 | TOR Essential Defueling Safety Case | Prepare Station Director's Brief | 2025-02-20 | 2025-02-20 | 5 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.29590 | TOR Essential Defueling Safety Case | INSA Schedule Risk - (Risk Ref 28382) - Generic (Potential) | 2025-02-20 | 2025-02-24 | 0 | 0 | 2 | 4 | 100% | 0 | 1 | Completed
W772LT | W772 | W772LT.A2470 | DNB Pull Harder Safety Case | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Nuclear Fuel Group - Review and Comment | 2025-02-20 | 2025-02-20 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A2480 | DNB Pull Harder Safety Case | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Human Factors (Human Reliability Assessment) - Review and Comment | 2025-02-20 | 2025-02-20 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A2490 | DNB Pull Harder Safety Case | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Human Factors - (Work Procedures) - Review and Comment | 2025-02-20 | 2025-02-20 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A2500 | DNB Pull Harder Safety Case | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Engineering (Instrumentation & Control) - Review and Comment | 2025-02-20 | 2025-02-20 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A2510 | DNB Pull Harder Safety Case | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Engineering (Mechanical Systems) - Review and Comment | 2025-02-20 | 2025-02-20 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A2520 | DNB Pull Harder Safety Case | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Structural Integrity (Structural Analysis) - Review and Comment | 2025-02-20 | 2025-02-20 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A2550 | DNB Pull Harder Safety Case | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Nuclear Fuel Group - Close Comments | 2025-02-20 | 2025-02-20 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A2560 | DNB Pull Harder Safety Case | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Human Factors (Human Reliability Assessment) - Close Comments | 2025-02-20 | 2025-02-20 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A2570 | DNB Pull Harder Safety Case | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Human Factors - (Work Procedures) - Close Comments | 2025-02-20 | 2025-02-20 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A2580 | DNB Pull Harder Safety Case | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Engineering (Instrumentation & Control) - Close Comments | 2025-02-20 | 2025-02-20 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A2590 | DNB Pull Harder Safety Case | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Engineering (Mechanical Systems) - Close Comments | 2025-02-20 | 2025-02-20 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A2600 | DNB Pull Harder Safety Case | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Structural Integrity (Structural Analysis) - Close Comments | 2025-02-20 | 2025-02-20 | 10 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1555 | HYB Essential Defueling Safety Case | Prepare Station Director's Brief | 2025-02-20 | 2025-02-20 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.29590 | HYB Essential Defueling Safety Case | INSA Schedule Risk - (Risk Ref 28382) - Generic (Unknown) | 2025-02-20 | 2025-02-24 | 3 | 0 | 3 | 4 | 100% | 0.75 | 1 | Completed
ER6371LT | W202 | W202.A5450 | HRA Reactors Shutdown Essential Safety Cases | Safety Case Post Job Debrief (HRA) | 2025-02-21 | 2025-02-21 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6661LT | W206 | W206.A5450 | HYA Reactors Shutdown Essential Safety Cases | Safety Case Post Job Debrief (HYA) | 2025-02-21 | 2025-02-21 | 1 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A2350 | DNB Pull Harder Safety Case | <Test Schedule> - Issue Draft EAN / Report for Tech Review. | 2025-02-21 | 2025-02-21 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.29600 | HYB Essential Defueling Safety Case | Risk Milestone - INSA Schedule Risk - (Risk Ref 28382) - INSA Substantially Complete | 2025-02-24 | 2025-02-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.29600 | TOR Essential Defueling Safety Case | Risk Milestone - INSA Schedule Risk - (Risk Ref 28382) - INSA Substantially Complete | 2025-02-24 | 2025-02-24 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.A2170 | DNB Pull Harder Safety Case | <Test Schedule> - Draft EAN / Report Tech Reviewed by EDF SQEP | 2025-02-24 | 2025-02-28 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
W772LT | W772 | W772.A1030 | DNB Pull Harder Safety Case | <S'standt'n of Funct'l Cap of PWTS & DWTS at the Enh'ed O'load Trip Sett's> - Draft EAN / Report TR by EDF SQEP | 2025-02-24 | 2025-02-28 | 5 | 0 | 4 | 4 | 100% | 1.25 | 1 | Completed
W232LT | W232 | W232.C3560 | DNB Enhanced Safety Cases | <SCOPE CHANGE CN3472><FPU Sub-veto fault frequency> - Mid Job Brief | 2025-02-24 | 2025-02-24 | 1 | 0 | 1 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.1042 | HYB Essential Defueling Safety Case | INSA Assessment Substantially Comp (T-3) weeks before NSC date)) | 2025-02-26 | 2025-02-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6666LT | W209 | W209.4970 | HYB Essential Defueling Safety Case | >>>OUTGOING ENABLER (W273) INSA Approved | 2025-02-26 | 2025-02-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.4970 | TOR Essential Defueling Safety Case | >>>OUTGOING ENABLER (W274) INSA Approved | 2025-02-26 | 2025-02-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
ER6668LT | W213 | W213.1042 | TOR Essential Defueling Safety Case | INSA Assessment Substantially Comp (T-3) weeks before NSC date)) | 2025-02-26 | 2025-02-26 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W230LT | W230 | W230.3770 | HYB Enhanced Defueling Safety Case Strategy | HYB Enhanced Defueling Rate: Produce draft NSRS (using BARRIER MODEL) | 2025-02-28 | 2025-02-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W772LT | W772 | W772LT.T1290 | DNB Pull Harder Safety Case | <Operating Strategy for Pull Harder Facility> - Issue Final EAN / Report | 2025-02-28 | 2025-02-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed
W234LT | W234 | W234.3770 | TOR Enhanced Defueling Safety Case Strategy | TOR Enhanced Defueling Rate: Produce draft NSRS (using BARRIER MODEL) | 2025-02-28 | 2025-02-28 | 0 | 0 | 0 | 0 | 100% | #DIV/0! | 1 | Completed

## template
activity_id | activity_name | start_date | finish_date | original_duration | total_float
A1700 | ONR Approval of Safety Case (Letter sent to initiate) EC NNNNN <Enter Paper Title Here> ==> KDM | 2023-06-22 | 2023-12-07 | 120 | 0
A1430 | Prepare the Safety Case Proposal | 2022-10-24 | 2023-02-15 | 80 | 0
A1340 | Produce supporting reference <Insert Title> | 2022-07-28 | 2022-09-22 | 40 | 0
A1400 | Scope Work or Produce RFS | 2022-06-30 | 2022-07-27 | 20 | 0
A1570 | Specialist Assessments if Necessary (Expand as Required) | 2023-02-23 | 2023-03-22 | 20 | 6
A1350 | Verify supporting reference or EDF Technical review of supporting reference <Insert Title> | 2022-09-23 | 2022-10-13 | 15 | 0
A1620 | INSA review & iteration of comments (using BARRIER MODEL) | 2023-03-31 | 2023-04-24 | 15 | 0
A1060 | CO and PCE Create Initial Plan of Work ==> KDM | 2022-02-09 | 2022-02-22 | 10 | 17
A1730 | Develop Implementation & closeout Plan | 2023-12-27 | 2024-01-10 | 10 | 20
A1590 | Prepare and Populate Affected Documents List | 2022-10-21 | 2022-11-03 | 10 | 298
A1720 | Revise all Affected Drawings and Documents for EC Approval | 2023-12-11 | 2023-12-22 | 10 | 20
A1530 | Final Verification ==> KDM | 2023-03-17 | 2023-03-30 | 10 | 0
A1110 | SRD comments on NSRS | 2022-04-06 | 2022-04-21 | 10 | 17
A1150 | DA & SRD agree NSRS (for authorised designers-NSRS must be reviewed by DA) ==> KDM | 2022-05-11 | 2022-05-24 | 10 | 17
A1120 | Incorporate SRD, Station, DA (peer) comments | 2022-04-22 | 2022-05-06 | 10 | 17
A10100 | Initiate and Register EC and identify Milestones in AMS EC NNNNN<Enter Paper Title Here> | 2022-01-11 | 2022-01-24 | 10 | 17
A1460 | Verification of the case (using BARRIER MODEL) | 2023-02-23 | 2023-03-08 | 10 | 0
A1240 | Create EC Definition Document if not part of Project Definition Document (Insert Template Ref) | 2022-03-09 | 2022-03-22 | 10 | 17
A1140 | Station agree NSRS ==> KDM | 2022-05-11 | 2022-05-24 | 10 | 17
A1100 | DA (Peer) comments on NSRS | 2022-03-09 | 2022-03-22 | 10 | 37
A1090 | Station comments on NSRS | 2022-03-09 | 2022-03-22 | 10 | 37
A1080 | Produce draft NSRS (using BARRIER MODEL) | 2022-02-23 | 2022-03-08 | 10 | 17
A1010 | Produce MF EC NNNNN <Enter Paper Title Here> & obtain approval | 2022-01-25 | 2022-02-07 | 10 | 17
A1230 | Hold Case Conference as Appropriate | 2022-02-23 | 2022-03-01 | 5 | 490
A1380 | Address TR or Verifiers Comments <Insert Title> | 2022-10-14 | 2022-10-20 | 5 | 0
A1520 | Prepare Station Director's Brief | 2023-03-31 | 2023-04-06 | 5 | 45
A1280 | Circulate work programme to stakeholders for agreement | 2022-07-04 | 2022-07-08 | 5 | 401
A1260 | Identify verifier for the case & establish all other resources | 2022-02-10 | 2022-02-16 | 5 | 41
A1630 | Incorporate INSA comments | 2023-04-25 | 2023-05-02 | 5 | 0
A1660 | NSC Consideration & advice to Station Director ==> KDM | 2023-06-01 | 2023-06-07 | 5 | 10
A1610 | DA (Authorised Designer) Approval of CAT1 Safety Case | 2023-03-31 | 2023-04-06 | 5 | 15
A1000 | Mod Requested, Identify RE and EC Request Raised and Screened | 2022-01-04 | 2022-01-10 | 5 | 17
A1440 | Obtain peer review (if required) ==> KDM | 2023-02-16 | 2023-02-22 | 5 | 0
A1180 | Circulate NSRS for Relevant Stakeholders | 2022-06-23 | 2022-06-29 | 5 | 0
A1270 | Agree INSA resource with INA | 2022-03-30 | 2022-04-05 | 5 | 17
A1330 | Agree design proposals with Station in the case of hardware mods | 2022-03-30 | 2022-04-05 | 5 | 465
A1250 | Hold project kick start meeting with Station & key suppliers | 2022-03-23 | 2022-03-29 | 5 | 17
A1490 | Incorporate all stakeholder comments | 2023-03-09 | 2023-03-13 | 3 | 3
A1420 | Produce verification plan | 2022-10-24 | 2022-10-25 | 2 | 326
A1070 | CA to agree with CO format of the safety case | 2022-02-10 | 2022-02-11 | 2 | 173
A1320 | Baseline Plan to Verification Commenced (T-11) ==> KDM | 2022-07-11 | 2022-07-11 | 1 | 401
A1220 | NSRS Presented to NSC (for complex CAT 1 cases) | 2022-06-22 | 2022-06-22 | 1 | 0
A1190 | Send NSRS to ONR to determine level of review required (Acknowledgement or Agreement) | 2022-06-30 | 2022-06-30 | 1 | 79
A1290 | Continue to Develop & resource mandatory template ==> KDM | 2022-07-01 | 2022-07-01 | 1 | 401
A1470 | NSORC review and agree NSC CAT 1 Paper - < insert title > (SZB Only) | 2023-03-16 | 2023-03-16 | 1 | 0
A1690 | Post Job Debrief | 2024-02-08 | 2024-02-08 | 1 | 0
A1020 | Initial Categorisation by Station ==> KDM | 2022-02-08 | 2022-02-08 | 1 | 17
KDM.BU.02 | KDM - Station Approve EC NNNNN <Enter Paper Title Here> | 2023-12-08 | 2023-12-08 | 1 | 0
A1030 | Appoint CO & CA | 2022-02-09 | 2022-02-09 | 1 | 41
A1160 | NSORC agree NSRS (SZB) ==> KDM | 2022-05-25 | 2022-05-25 | 1 | 17
A1130 | Issue final NSRS | 2022-05-09 | 2022-05-09 | 1 | 17
A1550 | Verification Commenced (T-11) | 2023-02-23 | 2023-02-23 | 0 | 243
KDM.PR02 | KDM - Safety Case Paper Authoring Complete EC NNNNN <Enter Paper Title Here> (Cat 1 KDM) ==> KDM | 2023-02-22 | 2023-02-22 | 0 | 0
A1560 | Issue to NSORC (SZB) | 2023-03-08 | 2023-03-08 | 0 | 0
A1200 | Issue to NSORC (SZB Only) | 2022-05-06 | 2022-05-06 | 0 | 24
KDM.SP06 | KDM - ONR Agree/Acknowledge Safety Case EC NNNNN <Enter Paper Title Here> ==> KDM | 2023-12-07 | 2023-12-07 | 0 | 0
KDM.SP05 | KDM - INSA Final Approval EC NNNNN <Enter Paper Title Here> | 2023-06-21 | 2023-06-21 | 0 | 0
KDM.PR01 | KDM - Gate EC3 Completed and NSC/ONR dates Committed | 2023-02-22 | 2023-02-22 | 0 | 243
A1390 | Commence Supporting References or Supporting EC's | 2022-06-29 | 2022-06-29 | 0 | 0
KDM.SP03 | KDM - Gate EC2 completed and Cat 1 Baselined EC NNNNN <Enter Paper Title Here> | 2022-07-04 | 2022-07-04 | 0 | 406
KDM.SP01 | KDM - Gate EC1 completed EC NNNNN <Enter Paper Title Here> | 2022-02-22 | 2022-02-22 | 0 | 17
A1410 | All supporting references Approved and Issued | 2022-10-20 | 2022-10-20 | 0 | 0
A1370 | Supporting reference Complete <Insert Title> Approved and issued | 2022-10-20 | 2022-10-20 | 0 | 0
KDM.SP02 | KDM - NSRS agreed by stakeholders EC NNNNN <Enter Paper Title Here> | 2022-05-25 | 2022-05-25 | 0 | 17
A1640 | INSA Assessment Substantially Comp (T - 3 weeks before NSC date) ==> KDM | 2023-05-02 | 2023-05-02 | 0 | 0
A1480 | Issue to CO & Station for comments | 2023-03-08 | 2023-03-08 | 0 | 3
A1510 | Submit for approval - Categoriser ratifies; RE/CO endorsement ==> KDM | 2023-03-30 | 2023-03-30 | 0 | 0
KDM.BU01 | KDM - Safetc Case Presented at NSC EC NNNNN <Enter Paper Title Here> (Cat 1 KDM) (T) ==> KDM | 2023-05-23 | 2023-05-23 | 0 | 0
KDM.PR03 | KDM - Verification Complete/ Verified Draft A Issued for INSA (T-7) EC NNNNN <Enter Paper Title Here> ==> KDM | 2023-03-30 | 2023-03-30 | 0 | 0

## cost
workpack_id | project_name | year | final_cost
W200 | Prog 6.1-Reg.1 Reactors Shutdown SC | 2020 | -4000
W200 | Prog 6.1-Reg.1 Reactors Shutdown SC | 2019 | 161000
W200 | Prog 6.1-Reg.1 Reactors Shutdown SC | 2018 | 1371000
W200 | Prog 6.1-Reg.1 Reactors Shutdown SC | 2017 | 488000
W201 | HNB Reactors Shutdown Essential SC | 2022 | 27000
W201 | HNB Reactors Shutdown Essential SC | 2021 | 269000
W201 | HNB Reactors Shutdown Essential SC | 2020 | 1309000
W201 | HNB Reactors Shutdown Essential SC | 2019 | 2732000
W201 | HNB Reactors Shutdown Essential SC | 2018 | 42000
W202 | HRA Reactors Shutdown Essential Safety Cases | 2025 | 38000
W202 | HRA Reactors Shutdown Essential Safety Cases | 2024 | 103000
W202 | HRA Reactors Shutdown Essential Safety Cases | 2023 | 186000
W202 | HRA Reactors Shutdown Essential Safety Cases | 2022 | 354000
W202 | HRA Reactors Shutdown Essential Safety Cases | 2021 | 587000
W202 | HRA Reactors Shutdown Essential Safety Cases | 2020 | 808000
W202 | HRA Reactors Shutdown Essential Safety Cases | 2019 | 29000
W203 | HNB Enhanced Defuelling Safety Cases | 2025 | 30000
W203 | HNB Enhanced Defuelling Safety Cases | 2024 | 115000
W203 | HNB Enhanced Defuelling Safety Cases | 2023 | 142000
W203 | HNB Enhanced Defuelling Safety Cases | 2022 | 0
W203 | HNB Enhanced Defuelling Safety Cases | 2021 | 22000
W203 | HNB Enhanced Defuelling Safety Cases | 2020 | 30000
W204 | HRA Reactors Shutdown Enhanced SC | 2020 | 0
W205 | HPB Reactor Shutdown Essential SC | 2022 | 33000
W205 | HPB Reactor Shutdown Essential SC | 2021 | 275000
W205 | HPB Reactor Shutdown Essential SC | 2020 | 427000
W206 | HYA Reactors Shutdown Essential Safety Cases | 2025 | 38000
W206 | HYA Reactors Shutdown Essential Safety Cases | 2024 | 107000
W206 | HYA Reactors Shutdown Essential Safety Cases | 2023 | 173000
W206 | HYA Reactors Shutdown Essential Safety Cases | 2022 | 361000
W206 | HYA Reactors Shutdown Essential Safety Cases | 2021 | 586000
W206 | HYA Reactors Shutdown Essential Safety Cases | 2020 | 422000
W207 | HPB Enhanced Defuelling Safety Cases | 2025 | 30000
W207 | HPB Enhanced Defuelling Safety Cases | 2024 | 121000
W207 | HPB Enhanced Defuelling Safety Cases | 2023 | 176000
W207 | HPB Enhanced Defuelling Safety Cases | 2022 | 0
W207 | HPB Enhanced Defuelling Safety Cases | 2021 | 35000
W207 | HPB Enhanced Defuelling Safety Cases | 2020 | 15000
W209 | HYB Essential Defueling Safety Case | 2025 | 94000
W209 | HYB Essential Defueling Safety Case | 2024 | 505000
W209 | HYB Essential Defueling Safety Case | 2023 | 1087000
W209 | HYB Essential Defueling Safety Case | 2022 | 1349000
W209 | HYB Essential Defueling Safety Case | 2021 | 100000
W211 | DNB Follow-on Defuelling Safety Case | 2025 | 15000
W211 | DNB Follow-on Defuelling Safety Case | 2024 | 416000
W211 | DNB Follow-on Defuelling Safety Case | 2023 | 805000
W211 | DNB Follow-on Defuelling Safety Case | 2022 | 1016000
W211 | DNB Follow-on Defuelling Safety Case | 2021 | 78000
W211 | DNB Follow-on Defuelling Safety Case | 2020 | 136000
W213 | TOR Essential Defueling Safety Case | 2025 | 86000
W213 | TOR Essential Defueling Safety Case | 2024 | 457000
W213 | TOR Essential Defueling Safety Case | 2023 | 1068000
W213 | TOR Essential Defueling Safety Case | 2022 | 1332000
W213 | TOR Essential Defueling Safety Case | 2021 | 117000
W220 | Prog 6.2-Reg.1 Stn Fuel Route Handl.SC | 2020 | -6000
W220 | Prog 6.2-Reg.1 Stn Fuel Route Handl.SC | 2019 | 109000
W220 | Prog 6.2-Reg.1 Stn Fuel Route Handl.SC | 2018 | 1343000
W220 | Prog 6.2-Reg.1 Stn Fuel Route Handl.SC | 2017 | 531000
W221 | HNB Fuel Handling Essential Safety Case | 2022 | 66000
W221 | HNB Fuel Handling Essential Safety Case | 2021 | 304000
W221 | HNB Fuel Handling Essential Safety Case | 2020 | 1204000
W221 | HNB Fuel Handling Essential Safety Case | 2019 | 2479000
W221 | HNB Fuel Handling Essential Safety Case | 2018 | 226000
W222 | HRA Fuel Handling Essential Safety Case | 2025 | 45000
W222 | HRA Fuel Handling Essential Safety Case | 2024 | 299000
W222 | HRA Fuel Handling Essential Safety Case | 2023 | 338000
W222 | HRA Fuel Handling Essential Safety Case | 2022 | 435000
W222 | HRA Fuel Handling Essential Safety Case | 2021 | 963000
W222 | HRA Fuel Handling Essential Safety Case | 2020 | 1291000
W222 | HRA Fuel Handling Essential Safety Case | 2019 | 43000
W224 | HRA Enhanced Defueling Safety Case | 2026 | 15000
W224 | HRA Enhanced Defueling Safety Case | 2025 | 831000
W224 | HRA Enhanced Defueling Safety Case | 2024 | 249000
W224 | HRA Enhanced Defueling Safety Case | 2023 | 17000
W225 | HPB Fuel Handling Essential SC | 2022 | 74000
W225 | HPB Fuel Handling Essential SC | 2021 | 284000
W225 | HPB Fuel Handling Essential SC | 2020 | 410000
W226 | HYA Fuel Handling Essential Safety Case | 2025 | 45000
W226 | HYA Fuel Handling Essential Safety Case | 2024 | 303000
W226 | HYA Fuel Handling Essential Safety Case | 2023 | 337000
W226 | HYA Fuel Handling Essential Safety Case | 2022 | 492000
W226 | HYA Fuel Handling Essential Safety Case | 2021 | 960000
W226 | HYA Fuel Handling Essential Safety Case | 2020 | 730000
W228 | HYA Enhanced Defueling Safety Case | 2026 | 15000
W228 | HYA Enhanced Defueling Safety Case | 2025 | 831000
W228 | HYA Enhanced Defueling Safety Case | 2024 | 250000
W228 | HYA Enhanced Defueling Safety Case | 2023 | 17000
W229 | HYB SC Superseded by W209 | 2022 | 0
W229 | HYB SC Superseded by W209 | 2021 | 0
W230 | HYB Enhanced Defueling Safety Case Strategy | 2025 | 154000
W230 | HYB Enhanced Defueling Safety Case Strategy | 2024 | 108000
W231 | DNB Fuel Handling Essential SC | 2023 | -6000
W231 | DNB Fuel Handling Essential SC | 2022 | 9000
W231 | DNB Fuel Handling Essential SC | 2021 | 165000
W231 | DNB Fuel Handling Essential SC | 2020 | 29000
W232 | DNB Enhanced Safety Cases | 2025 | 403000
W232 | DNB Enhanced Safety Cases | 2024 | 473000
W232 | DNB Enhanced Safety Cases | 2023 | 613000
W232 | DNB Enhanced Safety Cases | 2022 | 57000
W233 | TOR Fuel Handling Essential SC | 2022 | -13000
W233 | TOR Fuel Handling Essential SC | 2021 | 0
W234 | TOR Enhanced Defueling Safety Case Strategy | 2025 | 154000
W234 | TOR Enhanced Defueling Safety Case Strategy | 2024 | 108000
W520 | FLEETWIDE CTO Defueling Safety Case Delivery | 2026 | 1239000
W520 | FLEETWIDE CTO Defueling Safety Case Delivery | 2025 | 1239000
W520 | FLEETWIDE CTO Defueling Safety Case Delivery | 2024 | 885000
W520 | FLEETWIDE CTO Defueling Safety Case Delivery | 2023 | 976000
W520 | FLEETWIDE CTO Defueling Safety Case Delivery | 2022 | 1128000
W520 | FLEETWIDE CTO Defueling Safety Case Delivery | 2021 | 685000
W521 | DNB Initial Defuelling Safety Case | 2023 | 33000
W521 | DNB Initial Defuelling Safety Case | 2022 | 1223000
W521 | DNB Initial Defuelling Safety Case | 2021 | 1965000
W699 | DNB Cold Defuelling Safety Case | 2025 | 206000
W699 | DNB Cold Defuelling Safety Case | 2024 | 423000
W730 | HYB Enhanced Defueling Safety Cases | 2027 | 323000
W730 | HYB Enhanced Defueling Safety Cases | 2026 | 423000
W730 | HYB Enhanced Defueling Safety Cases | 2025 | 398000
W731 | TOR Enhanced Defueling Safety Cases | 2027 | 323000
W731 | TOR Enhanced Defueling Safety Cases | 2026 | 423000
W731 | TOR Enhanced Defueling Safety Cases | 2025 | 398000
W772 | DNB Pull Harder Safety Case | 2026 | 206000
W772 | DNB Pull Harder Safety Case | 2025 | 423000
W783 | DNB Tie Bar Cutting Removal Safety Case | 2025 | 315000
W784 | DNB Cold Depressurised Safety Case | 2026 | 206000
W784 | DNB Cold Depressurised Safety Case | 2025 | 423000