## Notes
Comment
1 | Out of sequence activity on critical path
2 | New project completion date following correction
Notes
Current and previous project schedules has been reviewed to assess their quality and to look for any major changes month to month that would warrant further investigation. The spreadsheet’s attached, but the simple summary is:
1 | The March updates are consistent with the previous month
2 | The March update deviated from the agreed February date
3 | How many number of activities statred in March
4 | How any number of activities finsihed in March
6 | There are still sequencing mismatches (items out of sequence on critical path) to be resolved.
7 | There are mismatches between the dates and schedule dates indicating that the two are updated independently, rather than having a common information source
Progress Updates and Misalignments
|  | No | Workpack Number | Project Name | Weghting | Total Number of activities | Total number of activities started | Total number of activities finished
|  | 1 | W085 | REGION 1 Further Flasks in Readiness
|  | 2 | W155 | HRA Security
|  | 3 | W156 | HYA Security
|  | 4 | W157 | HYB Security
|  | 5 | W158 | DNB Security
|  | 6 | W159 | TOR Security
|  | 7 | W160 | HNB PSR4
|  | 8 | W161 | HPB PSR4
|  | 9 | W193 | HNB DPCS Defueling Support
|  | 10 | W194 | HPB DPCS Defueling Support
|  | 11 | W195 | HRA DPCS Defueling Support
|  | 12 | W196 | HYA DPCS Defueling Support
|  | 13 | W526 | HYB DPCS Defueling Support
|  | 14 | W527 | DNB DPCS Defueling Support
|  | 15 | W529 | TOR DPCS Defueling Support

## Feb 25
Workpack Number | Activity ID | Project Name | Activity Name | Start | Finish | Original Duration | Remaining Duration | At Completion Duration | Physical % Complete | Total Float | Activity Status | Column1
W085 | W085.A7200 | REGION 1 Further Flasks in Readiness | ETC (DD-PF) | 2024-07-01 | 2025-08-29 | 204 | 145 | 296 | 62% | 0 | In Progress | #N/A
W155 | W155.24600 | HRA Security | Reactor Equivalence Confirmed by NSG Group Head | 2023-02-01 | 2026-12-31 | 484 | 485 | 991 | 50% | 0 | In Progress | #N/A
W155 | W155.000010 | HRA Security | EAC (DD-PF) | 2025-02-03 | 2026-12-31 | 485 | 485 | 485 | 0% | 0 | Not Started | #N/A
W156 | W156.24600 | HYA Security | Reactor Equivalence Confirmed by NSG Group Head | 2023-02-01 | 2026-12-31 | 484 | 485 | 991 | 51% | 0 | In Progress | #N/A
W156 | W156.000010 | HYA Security | EAC (DD-PF) | 2025-02-03 | 2026-12-31 | 485 | 485 | 485 | 0% | 0 | Not Started | #N/A
W157 | W157.000010 | HYB Security | EAC (DD-PF) | 2025-02-03 | 2026-12-31 | 485 | 485 | 485 | 0% | 0 | Not Started | #N/A
W158 | W158.34851 | DNB Security | 2025 | 2025-02-03 | 2025-12-31 | 231 | 231 | 231 | 0% | 0 | Not Started | #N/A
W159 | W159.1000 | TOR Security | Summary for TOR Security W159 | 2023-05-02 | 2027-01-29 | 800 | 505 | 950 | 21% | 0 | In Progress | #N/A
W159 | W159.24600 | TOR Security | Reactor Equivalence Confirmed by NSG Group Head | 2026-07-01 | 2026-11-04 | 90 | 90 | 90 | 0% | 0 | Not Started | #N/A
W159 | W159.2600 | TOR Security | Implement permanent infrastructure and organisational mitigations | 2026-11-05 | 2027-01-29 | 60 | 60 | 60 | 0% | 0 | Not Started | #N/A
W159 | W159.2590 | TOR Security | Implement temp. infrastructure and org mitigations required to enable commencement of defuelling (FEEDS TO SUMMARY SCHE) | 2026-11-05 | 2027-01-29 | 60 | 60 | 60 | 0% | 0 | Not Started | #N/A
W159 | W159.2580 | TOR Security | Implement administratively based mitigations | 2026-11-05 | 2026-12-02 | 20 | 20 | 20 | 0% | 0 | Not Started | #N/A
W160 | W160.8110 | HNB PSR4 | Summary of HNB PSR4 - W160 | 2023-04-03 | 2026-08-25 | 1 | 395 | 857 | 0% | 0 | In Progress | #N/A
W160 | W160.5970 | HNB PSR4 | HNB PSR4 Head Doc: HNB PSR4 Head Doc: INSA review & iteration of comments (using BARRIER MODEL) | 2024-12-04 | 2025-02-18 | 40 | 12 | 52 | 30% | 0 | In Progress | #N/A
W160 | W160.5980 | HNB PSR4 | HNB PSR4 Head Doc: Incorporate INSA comments | 2025-02-19 | 2025-02-25 | 5 | 5 | 5 | 0% | 0 | Not Started | #N/A
W160 | W160.9540 | HNB PSR4 | HNB PSR4 Head Doc: Verification Schedule Risk - (Risk Ref 38853) | 2025-02-26 | 2025-02-26 | 0 | 0 | 0 | 0% | 0 | Not Started | #N/A
W160 | W160.9630 | HNB PSR4 | HNB PSR3 Extension EC: Review NSRS for Completeness | 2025-08-04 | 2025-08-04 | 1 | 1 | 1 | 0% | -248 | Not Started | #N/A
W160 | W160.9640 | HNB PSR4 | HNB PSR3 Extension EC: Author Up-Rev of PSR3 Extension EC | 2025-08-05 | 2025-08-18 | 10 | 10 | 10 | 0% | -248 | Not Started | #N/A
W160 | W160.8970 | HNB PSR4 | HNB PSR3 Extension EC: Issue Document to NRS for comment | 2025-08-19 | 2025-08-26 | 5 | 5 | 5 | 0% | -248 | Not Started | #N/A
W160 | W160.8700 | HNB PSR4 | HNB PSR3 Extension EC: Verification of the Submission (using BARRIER MODEL) | 2025-08-19 | 2025-08-26 | 5 | 5 | 5 | 0% | -248 | Not Started | #N/A
W160 | W160.8980 | HNB PSR4 | HNB PSR3 Extension EC: NRS Comments | 2025-08-27 | 2025-09-02 | 5 | 5 | 5 | 0% | -248 | Not Started | #N/A
W160 | W160.8720 | HNB PSR4 | HNB PSR3 Extension EC: Address Verifier Comments | 2025-08-27 | 2025-08-28 | 2 | 2 | 2 | 0% | -244 | Not Started | #N/A
W160 | W160.8990 | HNB PSR4 | HNB PSR3 Extension EC: NRS Comments Addressed | 2025-09-03 | 2025-09-09 | 5 | 5 | 5 | 0% | -248 | Not Started | #N/A
W160 | W160.9000 | HNB PSR4 | HNB PSR3 Extension EC: TR Complete | 2025-09-10 | 2025-09-16 | 5 | 5 | 5 | 0% | -248 | Not Started | #N/A
W160 | W160.9010 | HNB PSR4 | HNB PSR3 Extension EC: Issue for PRWG (Allow 5d) | 2025-09-17 | 2025-09-23 | 5 | 5 | 5 | 0% | -248 | Not Started | #N/A
W160 | W160.9020 | HNB PSR4 | HNB PSR3 Extension EC: PRWG Meeting for Head Doc | 2025-09-24 | 2025-09-24 | 1 | 1 | 1 | 0% | -248 | Not Started | #N/A
W160 | W160.9030 | HNB PSR4 | HNB PSR3 Extension EC: PRWG Comments Addressed | 2025-09-25 | 2025-10-01 | 5 | 5 | 5 | 0% | -248 | Not Started | #N/A
W160 | W160.8690 | HNB PSR4 | HNB PSR3 Extension EC: INSA review & iteration of comments (using BARRIER MODEL) | 2025-10-02 | 2025-10-29 | 20 | 20 | 20 | 0% | -248 | Not Started | #N/A
W160 | W160.8630 | HNB PSR4 | HNB PSR3 Extension EC: Incorporate INSA comments | 2025-10-30 | 2025-11-05 | 5 | 5 | 5 | 0% | -248 | Not Started | #N/A
W160 | W160.2140 | HNB PSR4 | Gate D PRC Paper Submission | 2026-08-12 | 2026-08-12 | 1 | 1 | 1 | 0% | 0 | Not Started | #N/A
W160 | W160.2150 | HNB PSR4 | Gate D - Hold PRC Meeting | 2026-08-25 | 2026-08-25 | 1 | 1 | 1 | 0% | 0 | Not Started | #N/A
W161 | W161.8110 | HPB PSR4 | Summary of HPB PSR4 - W160 | 2023-04-03 | 2027-03-03 | 1 | 528 | 990 | 0% | 0 | In Progress | #N/A
W161 | W161.5820 | HPB PSR4 | HPB PSR4 Head Doc: Authoring of the Submission Proposal | 2024-04-05 | 2025-07-09 | 100 | 98 | 318 | 30% | -45 | In Progress | #N/A
W161 | W161.8180 | HPB PSR4 | HPB PSR Head Doc: Upload Submission Proposal to AMS | 2025-07-09 | 2025-07-15 | 5 | 5 | 5 | 0% | -45 | Not Started | #N/A
W161 | W161.5810 | HPB PSR4 | HPB PSR4 Head Doc: Produce and Approve Verification Plan | 2025-07-16 | 2025-07-22 | 5 | 5 | 5 | 0% | -45 | Not Started | #N/A
W161 | W161.8190 | HPB PSR4 | HPB PSR4 Head Doc: PJB Verifier | 2025-07-23 | 2025-07-25 | 3 | 3 | 3 | 0% | -45 | Not Started | #N/A
W161 | W161.5870 | HPB PSR4 | HPB PSR4 Head Doc:Verification of the Submission (using BARRIER MODEL) | 2025-07-28 | 2025-09-01 | 25 | 25 | 25 | 0% | -45 | Not Started | #N/A
W161 | W161.9620 | HPB PSR4 | HPB PSR3 Extension EC: Review NSRS for Completeness | 2025-08-04 | 2025-08-04 | 1 | 1 | 1 | 0% | -252 | Not Started | #N/A
W161 | W161.9630 | HPB PSR4 | HPB PSR3 Extension EC: Author Up-Rev of PSR3 Extension EC | 2025-08-05 | 2025-08-18 | 10 | 10 | 10 | 0% | -252 | Not Started | #N/A
W161 | W161.8700 | HPB PSR4 | HPB PSR3 Extension EC: Verification of the Submission (using BARRIER MODEL) | 2025-08-19 | 2025-09-02 | 10 | 10 | 10 | 0% | -252 | Not Started | #N/A
W161 | W161.8970 | HPB PSR4 | HPB PSR3 Extension EC: Issue Document to NRS for comment | 2025-08-19 | 2025-08-26 | 5 | 5 | 5 | 0% | -243 | Not Started | #N/A
W161 | W161.8980 | HPB PSR4 | HPB PSR3 Extension EC: NRS Comments | 2025-08-27 | 2025-09-02 | 5 | 5 | 5 | 0% | -243 | Not Started | #N/A
W161 | W161.5900 | HPB PSR4 | HPB PSR4 Head Doc: Address Verifier Comments | 2025-09-02 | 2025-09-15 | 10 | 10 | 10 | 0% | -45 | Not Started | #N/A
W161 | W161.8200 | HPB PSR4 | HPB PSR4 Head Doc: Issue Document to NRS for comment | 2025-09-02 | 2025-09-08 | 5 | 5 | 5 | 0% | -40 | Not Started | #N/A
W161 | W161.8720 | HPB PSR4 | HPB PSR3 Extension EC: Address Verifier Comments | 2025-09-03 | 2025-09-09 | 5 | 5 | 5 | 0% | -252 | Not Started | #N/A
W161 | W161.8990 | HPB PSR4 | HPB PSR3 Extension EC: NRS Comments Addressed | 2025-09-03 | 2025-09-09 | 5 | 5 | 5 | 0% | -243 | Not Started | #N/A
W161 | W161.8210 | HPB PSR4 | HPB PSR4 Head Doc: NRS Comments | 2025-09-09 | 2025-09-15 | 5 | 5 | 5 | 0% | -40 | Not Started | #N/A
W161 | W161.9010 | HPB PSR4 | HPB PSR3 Extension EC: Issue for PRWG (Allow 5d) | 2025-09-10 | 2025-09-16 | 5 | 5 | 5 | 0% | -243 | Not Started | #N/A
W161 | W161.8220 | HPB PSR4 | HPB PSR4 Head Doc: NRS Comments Addressed | 2025-09-16 | 2025-09-22 | 5 | 5 | 5 | 0% | -40 | Not Started | #N/A
W161 | W161.9540 | HPB PSR4 | HPB PSR4 Head Doc: Verification Schedule Risk - (Risk Ref 38853) | 2025-09-16 | 2025-10-07 | 16 | 16 | 16 | 0% | -45 | Not Started | #N/A
W161 | W161.9020 | HPB PSR4 | HPB PSR3 Extension EC: PRWG Meeting for Head Doc | 2025-09-17 | 2025-09-17 | 1 | 1 | 1 | 0% | -243 | Not Started | #N/A
W161 | W161.9030 | HPB PSR4 | HPB PSR3 Extension EC: PRWG Comments Addressed | 2025-09-18 | 2025-09-24 | 5 | 5 | 5 | 0% | -243 | Not Started | #N/A
W161 | W161.8230 | HPB PSR4 | HPB PSR4 Head Doc: TR Complete (No Longer Required) | 2025-09-23 | 2025-09-29 | 5 | 5 | 5 | 0% | -40 | Not Started | #N/A
W161 | W161.8240 | HPB PSR4 | HPB PSR4 Head Doc: Issue for PRWG (Allow 5d) | 2025-09-30 | 2025-10-06 | 5 | 5 | 5 | 0% | -40 | Not Started | #N/A
W161 | W161.8250 | HPB PSR4 | HPB PSR4 Head Doc: PRWG Meeting for Head Doc | 2025-10-07 | 2025-10-07 | 1 | 1 | 1 | 0% | -40 | Not Started | #N/A
W161 | W161.5920 | HPB PSR4 | HPB PSR4 Head Doc: Final Verification | 2025-10-08 | 2025-10-21 | 10 | 10 | 10 | 0% | -45 | Not Started | #N/A
W161 | W161.8260 | HPB PSR4 | HPB PSR4 Head Doc: PRWG Comments Addressed | 2025-10-08 | 2025-10-14 | 5 | 5 | 5 | 0% | -40 | Not Started | #N/A
W161 | W161.8690 | HPB PSR4 | HPB PSR3 Extension EC: INSA review & iteration of comments (using BARRIER MODEL) | 2025-10-08 | 2025-11-04 | 20 | 20 | 20 | 0% | -252 | Not Started | #N/A
W161 | W161.5970 | HPB PSR4 | HPB PSR4 Head Doc: HPB PSR4 Head Doc: INSA review & iteration of comments (using BARRIER MODEL) | 2025-10-22 | 2025-11-18 | 20 | 20 | 20 | 0% | -45 | Not Started | #N/A
W161 | W161.8630 | HPB PSR4 | HPB PSR3 Extension EC: Incorporate INSA comments | 2025-11-05 | 2025-11-11 | 5 | 5 | 5 | 0% | -252 | Not Started | #N/A
W161 | W161.5980 | HPB PSR4 | HPB PSR4 Head Doc: Incorporate INSA comments | 2025-11-19 | 2025-11-25 | 5 | 5 | 5 | 0% | -45 | Not Started | #N/A
W161 | W161.6020 | HPB PSR4 | HPB PSR4 Head Doc: NSC Consideration & advice to Station Director ==> KDM | 2026-01-02 | 2026-01-15 | 10 | 10 | 10 | 0% | 0 | Not Started | #N/A
W161 | W161.6040 | HPB PSR4 | HPB PSR4 Head Doc: ONR Approval of Safety Case (Letter sent to initiate) EC 374795 | 2026-01-16 | 2027-01-15 | 254 | 254 | 254 | 0% | 0 | Not Started | #N/A
W161 | W161.7060 | HPB PSR4 | HPB PSR4 Head Doc: Prepare Paper for Submission to ONR | 2026-01-16 | 2026-01-29 | 10 | 10 | 10 | 0% | 0 | Not Started | #N/A
W161 | W161.6070 | HPB PSR4 | HPB PSR4 Head Doc: Revise all Affected Drawings and Documents for EC Approval | 2027-01-18 | 2027-01-29 | 10 | 10 | 10 | 0% | 0 | Not Started | #N/A
W161 | W161.6080 | HPB PSR4 | HPB PSR4 Head Doc: Develop Implementation & closeout Plan | 2027-02-01 | 2027-02-12 | 10 | 10 | 10 | 0% | 0 | Not Started | #N/A
W161 | W161.6090 | HPB PSR4 | HPB PSR4 Head Doc: Post Job Debrief (CAT 2) | 2027-02-15 | 2027-02-15 | 1 | 1 | 1 | 0% | 0 | Not Started | #N/A
W161 | W161.2100 | HPB PSR4 | Hold Project Closeout and Lessons Learned Meeting | 2027-02-16 | 2027-02-16 | 1 | 1 | 1 | 0% | 0 | Not Started | #N/A
W161 | W161.2110 | HPB PSR4 | Produce Lessons Learned Report | 2027-02-17 | 2027-02-17 | 1 | 1 | 1 | 0% | 0 | Not Started | #N/A
W161 | W161.2120 | HPB PSR4 | Produce Project Closeout Report | 2027-02-18 | 2027-02-19 | 2 | 2 | 2 | 0% | 0 | Not Started | #N/A
W161 | W161.2130 | HPB PSR4 | Prepare Gate D PRC Paper | 2027-02-22 | 2027-03-01 | 6 | 6 | 6 | 0% | 0 | Not Started | #N/A
W161 | W161.2140 | HPB PSR4 | Gate D PRC Paper Submission | 2027-03-02 | 2027-03-02 | 1 | 1 | 1 | 0% | 0 | Not Started | #N/A
W161 | W161.2150 | HPB PSR4 | Gate D - Hold PRC Meeting | 2027-03-03 | 2027-03-03 | 1 | 1 | 1 | 0% | 0 | Not Started | #N/A
W193 | W193.25300 | HNB DPCS Defueling Support | Summary HNB DPCS Defueling Support | 2024-01-02 | 2025-12-31 | 507 | 231 | 507 | 53% | 0 | In Progress | #N/A
W193 | W193.2040 | HNB DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group | 2025-01-02 | 2025-12-31 | 253 | 231 | 253 | 8% | 0 | In Progress | #N/A
W193 | W193.2030 | HNB DPCS Defueling Support | HNB PES Group Support - 2025 | 2025-01-02 | 2025-12-31 | 253 | 231 | 253 | 8% | 0 | In Progress | #N/A
W193 | W193.25200 | HNB DPCS Defueling Support | 2025 Externals | 2025-01-02 | 2025-12-31 | 253 | 231 | 253 | 8% | 0 | In Progress | #N/A
W193 | W193.2000 | HNB DPCS Defueling Support | ETC (DD-PF) | 2025-02-03 | 2025-12-31 | 231 | 231 | 231 | 0% | 0 | Not Started | #N/A
W194 | W194.25790 | HPB DPCS Defueling Support | Project Support - 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 0 | Not Started | #N/A
W194 | W194.25800 | HPB DPCS Defueling Support | HPB PES Group Support - 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 0 | Not Started | #N/A
W194 | W194.25810 | HPB DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 0 | Not Started | #N/A
W195 | W195.26060 | HRA DPCS Defueling Support | ETC 2025 | 2025-02-03 | 2025-12-31 | 231 | 231 | 231 | 0% | 0 | Not Started | #N/A
W195 | W195.26070 | HRA DPCS Defueling Support | ETC 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 0 | Not Started | #N/A
W195 | W195.26080 | HRA DPCS Defueling Support | ETC 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 0 | Not Started | #N/A
W195 | W195.26090 | HRA DPCS Defueling Support | ETC 2028 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W195 | W195.26100 | HRA DPCS Defueling Support | ETC 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W195 | W194.1030 | HRA DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W195 | W195.26110 | HRA DPCS Defueling Support | ETC 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W195 | W194.1040 | HRA DPCS Defueling Support | HRA PES Group Support - 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W195 | W194.1050 | HRA DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W196 | W196.2060 | HYA DPCS Defueling Support | ETC 2025 | 2025-02-03 | 2025-12-31 | 231 | 231 | 231 | 0% | 0 | Not Started | #N/A
W196 | W196.2070 | HYA DPCS Defueling Support | ETC 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 0 | Not Started | #N/A
W196 | W196.1030 | HYA DPCS Defueling Support | 2027 Externals | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 0 | Not Started | #N/A
W196 | W196.2100 | HYA DPCS Defueling Support | ETC 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 0 | Not Started | #N/A
W196 | W196.2110 | HYA DPCS Defueling Support | ETC 2028 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W196 | W194.1000 | HYA DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2028 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W196 | W194.1010 | HYA DPCS Defueling Support | HYA PES Group Support - 2028 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W196 | W196.2120 | HYA DPCS Defueling Support | ETC 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W196 | W194.1020 | HYA DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W196 | W194.1030 | HYA DPCS Defueling Support | HYA PES Group Support - 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W196 | W196.2350 | HYA DPCS Defueling Support | ETC 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W196 | W194.1040 | HYA DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W196 | W194.1050 | HYA DPCS Defueling Support | HYA PES Group Support - 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W526 | W526.1050 | HYB DPCS Defueling Support | HYB Plant Control Systems & Simulators (PCS&S) Group - 2025 | 2025-01-02 | 2025-12-31 | 253 | 231 | 253 | 8% | 0 | In Progress | #N/A
W526 | W526.10000 | HYB DPCS Defueling Support | HYB 2025 External Costs | 2025-01-02 | 2025-12-31 | 253 | 231 | 253 | 8% | 0 | In Progress | #N/A
W526 | W526.10160 | HYB DPCS Defueling Support | TPM and JCRB Meeting Held 2025 | 2025-01-02 | 2025-12-31 | 253 | 231 | 253 | 8% | 0 | In Progress | #N/A
W526 | W526.1030 | HYB DPCS Defueling Support | ETC 2025 | 2025-02-03 | 2025-12-31 | 231 | 231 | 231 | 0% | 0 | Not Started | #N/A
W526 | W526.1285 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q1 2026 | 2026-01-02 | 2026-03-31 | 63 | 63 | 63 | 0% | 0 | Not Started | #N/A
W526 | W526.1070 | HYB DPCS Defueling Support | HYB Plant Control Systems & Simulators (PCS&S) Group - 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 0 | Not Started | #N/A
W526 | W526.1060 | HYB DPCS Defueling Support | HYB PES Group Support - 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 0 | Not Started | #N/A
W526 | W526.10010 | HYB DPCS Defueling Support | HYB 2026 External Costs | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 0 | Not Started | #N/A
W526 | W526.10170 | HYB DPCS Defueling Support | TPM and JCRB Meeting Held 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 0 | Not Started | #N/A
W526 | W526.1200 | HYB DPCS Defueling Support | ETC 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 0 | Not Started | #N/A
W526 | W526.1295 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q2 2026 | 2026-04-01 | 2026-06-30 | 61 | 61 | 61 | 0% | 0 | Not Started | #N/A
W526 | W526.1305 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q3 2026 | 2026-07-01 | 2026-09-30 | 65 | 65 | 65 | 0% | 0 | Not Started | #N/A
W526 | W526.1315 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q4 2026 | 2026-10-01 | 2026-12-31 | 65 | 65 | 65 | 0% | 0 | Not Started | #N/A
W526 | W526.1090 | HYB DPCS Defueling Support | HYB Plant Control Systems & Simulators (PCS&S) Group - 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 0 | Not Started | #N/A
W526 | W526.1080 | HYB DPCS Defueling Support | HYB PES Group Support - 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 0 | Not Started | #N/A
W526 | W526.10020 | HYB DPCS Defueling Support | HYB 2027 External Costs | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 0 | Not Started | #N/A
W526 | W526.10180 | HYB DPCS Defueling Support | TPM and JCRB Meeting Held 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 0 | Not Started | #N/A
W526 | W526.1210 | HYB DPCS Defueling Support | ETC 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 0 | Not Started | #N/A
W526 | W526.1100 | HYB DPCS Defueling Support | HYB PES Group Support - 2028 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W526 | W526.1425 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q1 2028 | 2028-01-03 | 2028-03-31 | 65 | 65 | 65 | 0% | 0 | Not Started | #N/A
W526 | W526.10030 | HYB DPCS Defueling Support | HYB 2028 External Costs | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W526 | W526.10190 | HYB DPCS Defueling Support | TPM and JCRB Meeting Held 2028 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W526 | W526.1220 | HYB DPCS Defueling Support | ETC 2028 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W526 | W526.1435 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q2 2028 | 2028-04-03 | 2028-06-30 | 61 | 61 | 61 | 0% | 0 | Not Started | #N/A
W526 | W526.1445 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q3 2028 | 2028-07-03 | 2028-09-29 | 64 | 64 | 64 | 0% | 0 | Not Started | #N/A
W526 | W526.1455 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q4 | 2028-10-02 | 2028-12-29 | 63 | 63 | 63 | 0% | 0 | Not Started | #N/A
W526 | W526.1505 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q1 2029 | 2029-01-02 | 2029-03-29 | 63 | 63 | 63 | 0% | 0 | Not Started | #N/A
W526 | W526.1465 | HYB DPCS Defueling Support | HYB Argus Support Contract - Q1 2029 | 2029-01-02 | 2029-03-29 | 63 | 63 | 63 | 0% | 0 | Not Started | #N/A
W526 | W526.1120 | HYB DPCS Defueling Support | HYB PES Group Support - 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W526 | W526.10040 | HYB DPCS Defueling Support | HYB 2029 External Costs | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W526 | W526.10200 | HYB DPCS Defueling Support | TPM and JCRB Meeting Held 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W526 | W526.1230 | HYB DPCS Defueling Support | ETC 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W526 | W526.1515 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q2 2029 | 2029-04-03 | 2029-06-29 | 62 | 62 | 62 | 0% | 0 | Not Started | #N/A
W526 | W526.1475 | HYB DPCS Defueling Support | HYB Argus Support Contract - Q2 2029 | 2029-04-03 | 2029-06-29 | 62 | 62 | 62 | 0% | 0 | Not Started | #N/A
W526 | W526.1525 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q3 2029 | 2029-07-02 | 2029-09-28 | 64 | 64 | 64 | 0% | 0 | Not Started | #N/A
W526 | W526.1485 | HYB DPCS Defueling Support | HYB Argus Support Contract - Q3 2029 | 2029-07-02 | 2029-09-28 | 64 | 64 | 64 | 0% | 0 | Not Started | #N/A
W526 | W526.1535 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q4 2029 | 2029-10-01 | 2029-12-31 | 64 | 64 | 64 | 0% | 0 | Not Started | #N/A
W526 | W526.1495 | HYB DPCS Defueling Support | HYB Argus Support Contract - Q4 2029 | 2029-10-01 | 2029-12-31 | 64 | 64 | 64 | 0% | 0 | Not Started | #N/A
W526 | W526.1545 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q1 2030 | 2030-01-02 | 2030-03-29 | 63 | 63 | 63 | 0% | 0 | Not Started | #N/A
W526 | W526.1140 | HYB DPCS Defueling Support | HYB PES Group Support - 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W526 | W526.10050 | HYB DPCS Defueling Support | HYB 2030 External Costs | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W526 | W526.10210 | HYB DPCS Defueling Support | TPM and JCRB Meeting Held 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W526 | W526.1240 | HYB DPCS Defueling Support | ETC 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W526 | W526.1555 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q2 2030 | 2030-04-01 | 2030-06-28 | 61 | 61 | 61 | 0% | 0 | Not Started | #N/A
W526 | W526.1565 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q3 2030 | 2030-07-01 | 2030-09-30 | 65 | 65 | 65 | 0% | 0 | Not Started | #N/A
W526 | W526.1575 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q4 2030 | 2030-10-01 | 2030-12-31 | 64 | 64 | 64 | 0% | 0 | Not Started | #N/A
W526 | W526.1170 | HYB DPCS Defueling Support | HYB Plant Control Systems & Simulators (PCS&S) Group - 2031 | 2031-01-02 | 2031-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W526 | W526.1160 | HYB DPCS Defueling Support | HYB PES Group Support - 2031 | 2031-01-02 | 2031-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W526 | W526.1585 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q1 2031 | 2031-01-02 | 2031-03-31 | 63 | 63 | 63 | 0% | 0 | Not Started | #N/A
W526 | W526.10060 | HYB DPCS Defueling Support | HYB 2031 External Costs | 2031-01-02 | 2031-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W526 | W526.10220 | HYB DPCS Defueling Support | TPM and JCRB Meeting Held 2031 | 2031-01-02 | 2031-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W526 | W526.1250 | HYB DPCS Defueling Support | ETC 2031 | 2031-01-02 | 2031-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W526 | W526.1595 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q2 2031 | 2031-04-01 | 2031-06-30 | 61 | 61 | 61 | 0% | 0 | Not Started | #N/A
W526 | W526.1605 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q3 2031 | 2031-07-01 | 2031-09-30 | 65 | 65 | 65 | 0% | 0 | Not Started | #N/A
W526 | W526.1615 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q4 2031 | 2031-10-01 | 2031-12-31 | 64 | 64 | 64 | 0% | 0 | Not Started | #N/A
W526 | W526.1190 | HYB DPCS Defueling Support | HYB Plant Control Systems & Simulators (PCS&S) Group - 2032 | 2032-01-02 | 2032-12-31 | 256 | 256 | 256 | 0% | 0 | Not Started | #N/A
W526 | W526.1180 | HYB DPCS Defueling Support | HYB PES Group Support - 2032 | 2032-01-02 | 2032-12-31 | 256 | 256 | 256 | 0% | 0 | Not Started | #N/A
W526 | W526.3150 | HYB DPCS Defueling Support | HYB DPCS Long Term Support Contract 2032 | 2032-01-02 | 2032-12-31 | 256 | 256 | 256 | 0% | 0 | Not Started | #N/A
W526 | W526.1625 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q1 2032 Delivery | 2032-01-02 | 2032-03-31 | 62 | 62 | 62 | 0% | 0 | Not Started | #N/A
W526 | W526.10070 | HYB DPCS Defueling Support | HYB 2032 External Costs | 2032-01-02 | 2032-12-31 | 256 | 256 | 256 | 0% | 0 | Not Started | #N/A
W526 | W526.10230 | HYB DPCS Defueling Support | TPM and JCRB Meeting Held 2032 | 2032-01-02 | 2032-12-31 | 256 | 256 | 256 | 0% | 0 | Not Started | #N/A
W526 | W526.1260 | HYB DPCS Defueling Support | ETC 2032 | 2032-01-02 | 2032-12-31 | 256 | 256 | 256 | 0% | 0 | Not Started | #N/A
W526 | W526.1635 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q2 2032 Delivery | 2032-04-01 | 2032-06-30 | 63 | 63 | 63 | 0% | 0 | Not Started | #N/A
W526 | W526.1645 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q3 2032 Delivery | 2032-07-01 | 2032-09-30 | 65 | 65 | 65 | 0% | 0 | Not Started | #N/A
W526 | W526.1655 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q4 2032 Delivery | 2032-10-01 | 2032-12-31 | 66 | 66 | 66 | 0% | 0 | Not Started | #N/A
W527 | W527.25230 | DNB DPCS Defueling Support | ETC 2025 | 2025-02-03 | 2025-12-31 | 231 | 231 | 231 | 0% | 0 | Not Started | #N/A
W527 | W527.25240 | DNB DPCS Defueling Support | ETC 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 0 | Not Started | #N/A
W527 | W527.25250 | DNB DPCS Defueling Support | ETC 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 0 | Not Started | #N/A
W527 | W527.1150 | DNB DPCS Defueling Support | ETC 2028 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W527 | W527.1160 | DNB DPCS Defueling Support | ETC 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W527 | W527.26630 | DNB DPCS Defueling Support | DNB PES Group Support - 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W527 | W527.26640 | DNB DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W527 | W527.26660 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q1 2030 | 2030-01-02 | 2030-03-27 | 61 | 61 | 61 | 0% | 0 | Not Started | #N/A
W527 | W527.26680 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q1 2030 | 2030-01-02 | 2030-03-27 | 61 | 61 | 61 | 0% | 0 | Not Started | #N/A
W527 | W527.26700 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q1 2030 | 2030-01-02 | 2030-03-27 | 61 | 61 | 61 | 0% | 0 | Not Started | #N/A
W527 | W527.26750 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q1 2030 | 2030-01-02 | 2030-03-27 | 61 | 61 | 61 | 0% | 0 | Not Started | #N/A
W527 | W527.26810 | DNB DPCS Defueling Support | Cost Engineer Support 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W527 | W527.1250 | DNB DPCS Defueling Support | ETC 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W527 | W527.26910 | DNB DPCS Defueling Support | DNB PES Group Support - 2031 | 2031-01-02 | 2031-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W527 | W527.26920 | DNB DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2031 | 2031-01-02 | 2031-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W527 | W527.26940 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q1 2031 | 2031-01-02 | 2031-03-27 | 61 | 61 | 61 | 0% | 0 | Not Started | #N/A
W527 | W527.26960 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q1 2031 | 2031-01-02 | 2031-03-27 | 61 | 61 | 61 | 0% | 0 | Not Started | #N/A
W527 | W527.26980 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q1 2031 | 2031-01-02 | 2031-03-27 | 61 | 61 | 61 | 0% | 0 | Not Started | #N/A
W527 | W527.27030 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q1 2031 | 2031-01-02 | 2031-03-27 | 61 | 61 | 61 | 0% | 0 | Not Started | #N/A
W527 | W527.27090 | DNB DPCS Defueling Support | Cost Engineer Support 2031 | 2031-01-02 | 2031-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W527 | W527.1290 | DNB DPCS Defueling Support | ETC 2031 | 2031-01-02 | 2031-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W527 | W527.26950 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q2 2031 | 2031-03-28 | 2031-06-30 | 63 | 63 | 63 | 0% | 0 | Not Started | #N/A
W527 | W527.27000 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q2 2031 | 2031-03-28 | 2031-06-30 | 63 | 63 | 63 | 0% | 0 | Not Started | #N/A
W527 | W527.27020 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q2 2031 | 2031-03-28 | 2031-06-30 | 63 | 63 | 63 | 0% | 0 | Not Started | #N/A
W527 | W527.27060 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q2 2031 | 2031-03-28 | 2031-06-30 | 63 | 63 | 63 | 0% | 0 | Not Started | #N/A
W527 | W527.26970 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q3 2031 | 2031-07-01 | 2031-09-30 | 65 | 65 | 65 | 0% | 0 | Not Started | #N/A
W527 | W527.26990 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q3 2031 | 2031-07-01 | 2031-09-30 | 65 | 65 | 65 | 0% | 0 | Not Started | #N/A
W527 | W527.27050 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q3 2031 | 2031-07-01 | 2031-09-30 | 65 | 65 | 65 | 0% | 0 | Not Started | #N/A
W527 | W527.26930 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q4 2031 | 2031-10-01 | 2031-12-31 | 64 | 64 | 64 | 0% | 0 | Not Started | #N/A
W527 | W527.27010 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q4 2031 | 2031-10-01 | 2031-12-31 | 64 | 64 | 64 | 0% | 0 | Not Started | #N/A
W527 | W527.27040 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q4 2031 | 2031-10-01 | 2031-12-31 | 64 | 64 | 64 | 0% | 0 | Not Started | #N/A
W527 | W527.27080 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q4 2031 | 2031-10-01 | 2031-12-31 | 64 | 64 | 64 | 0% | 0 | Not Started | #N/A
W529 | W195.1000 | TOR DPCS Defueling Support | TPM and JCRB Meetings Held - 2025 | 2025-01-02 | 2025-12-31 | 253 | 231 | 253 | 8% | 0 | In Progress | #N/A
W529 | W195.1010 | TOR DPCS Defueling Support | TPM and JCRB Meetings Held - 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 0 | Not Started | #N/A
W529 | W195.1020 | TOR DPCS Defueling Support | TPM and JCRB Meetings Held - 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 0 | Not Started | #N/A
W529 | W195.1030 | TOR DPCS Defueling Support | TPM and JCRB Meetings Held - 2028 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W529 | W529.1120 | TOR DPCS Defueling Support | TOR PES Group Support - 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W529 | W529.1130 | TOR DPCS Defueling Support | TOR Plant Control Systems & Simulators (PCS&S) Group - 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W529 | W529.1465 | TOR DPCS Defueling Support | TOR Argus Support Contract - Q1 2029 | 2029-01-02 | 2029-03-29 | 63 | 63 | 63 | 0% | 0 | Not Started | #N/A
W529 | W529.1505 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q1 2029 | 2029-01-02 | 2029-03-29 | 63 | 63 | 63 | 0% | 0 | Not Started | #N/A
W529 | W529.10040 | TOR DPCS Defueling Support | TOR 2029 External Costs | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W529 | W195.1040 | TOR DPCS Defueling Support | TPM and JCRB Meetings Held - 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W529 | W529.1475 | TOR DPCS Defueling Support | TOR Argus Support Contract - Q2 2029 | 2029-04-03 | 2029-06-29 | 62 | 62 | 62 | 0% | 0 | Not Started | #N/A
W529 | W529.1515 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q2 2029 | 2029-04-03 | 2029-06-29 | 62 | 62 | 62 | 0% | 0 | Not Started | #N/A
W529 | W529.1485 | TOR DPCS Defueling Support | TOR Argus Support Contract - Q3 2029 | 2029-07-02 | 2029-09-28 | 64 | 64 | 64 | 0% | 0 | Not Started | #N/A
W529 | W529.1525 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q3 2029 | 2029-07-02 | 2029-09-28 | 64 | 64 | 64 | 0% | 0 | Not Started | #N/A
W529 | W529.1495 | TOR DPCS Defueling Support | TOR Argus Support Contract - Q4 2029 | 2029-10-01 | 2029-12-31 | 64 | 64 | 64 | 0% | 0 | Not Started | #N/A
W529 | W529.1535 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q4 2029 | 2029-10-01 | 2029-12-31 | 64 | 64 | 64 | 0% | 0 | Not Started | #N/A
W529 | W529.1140 | TOR DPCS Defueling Support | TOR PES Group Support - 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W529 | W529.1150 | TOR DPCS Defueling Support | TOR Plant Control Systems & Simulators (PCS&S) Group - 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W529 | W529.1545 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q1 2030 | 2030-01-02 | 2030-03-29 | 63 | 63 | 63 | 0% | 0 | Not Started | #N/A
W529 | W529.10050 | TOR DPCS Defueling Support | TOR 2030 External Costs | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W529 | W195.1050 | TOR DPCS Defueling Support | TPM and JCRB Meetings Held - 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W529 | W529.1555 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q2 2030 | 2030-04-01 | 2030-06-28 | 61 | 61 | 61 | 0% | 0 | Not Started | #N/A
W529 | W529.1565 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q3 2030 | 2030-07-01 | 2030-09-30 | 65 | 65 | 65 | 0% | 0 | Not Started | #N/A
W529 | W529.1575 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q4 2030 | 2030-10-01 | 2030-12-31 | 64 | 64 | 64 | 0% | 0 | Not Started | #N/A
W529 | W529.1585 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q1 2031 | 2031-01-02 | 2031-03-31 | 63 | 63 | 63 | 0% | 0 | Not Started | #N/A
W529 | W529.1160 | TOR DPCS Defueling Support | TOR PES Group Support - 2031 | 2031-01-02 | 2031-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W529 | W529.1170 | TOR DPCS Defueling Support | TOR Plant Control Systems & Simulators (PCS&S) Group - 2031 | 2031-01-02 | 2031-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W529 | W529.10060 | TOR DPCS Defueling Support | TOR 2031 External Costs | 2031-01-02 | 2031-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W529 | W195.1060 | TOR DPCS Defueling Support | TPM and JCRB Meetings Held - 2031 | 2031-01-02 | 2031-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started | #N/A
W529 | W529.1595 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q2 2031 | 2031-04-01 | 2031-06-30 | 61 | 61 | 61 | 0% | 0 | Not Started | #N/A
W529 | W529.1605 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q3 2031 | 2031-07-01 | 2031-09-30 | 65 | 65 | 65 | 0% | 0 | Not Started | #N/A
W529 | W529.1615 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q4 2031 | 2031-10-01 | 2031-12-31 | 64 | 64 | 64 | 0% | 0 | Not Started | #N/A
W529 | W529.1625 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q1 2032 | 2032-01-02 | 2032-03-31 | 62 | 62 | 62 | 0% | 0 | Not Started | #N/A
W529 | W529.3150 | TOR DPCS Defueling Support | TOR DPCS Long Term Support Contract 2032 | 2032-01-02 | 2032-12-31 | 256 | 256 | 256 | 0% | 0 | Not Started | #N/A
W529 | W529.1180 | TOR DPCS Defueling Support | TOR PES Group Support - 2032 | 2032-01-02 | 2032-12-31 | 256 | 256 | 256 | 0% | 0 | Not Started | #N/A
W529 | W529.1190 | TOR DPCS Defueling Support | TOR Plant Control Systems & Simulators (PCS&S) Group - 2032 | 2032-01-02 | 2032-12-31 | 256 | 256 | 256 | 0% | 0 | Not Started | #N/A
W529 | W529.10070 | TOR DPCS Defueling Support | TOR 2032 External Costs | 2032-01-02 | 2032-12-31 | 256 | 256 | 256 | 0% | 0 | Not Started | #N/A
W529 | W195.1070 | TOR DPCS Defueling Support | TPM and JCRB Meetings Held - 2032 | 2032-01-02 | 2032-12-31 | 256 | 256 | 256 | 0% | 0 | Not Started | #N/A
W529 | W529.1635 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q2 2032 | 2032-04-01 | 2032-06-30 | 63 | 63 | 63 | 0% | 0 | Not Started | #N/A
W529 | W529.1645 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q3 2032 | 2032-07-01 | 2032-09-30 | 65 | 65 | 65 | 0% | 0 | Not Started | #N/A
W529 | W529.1655 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q4 2032 | 2032-10-01 | 2032-12-31 | 66 | 66 | 66 | 0% | 0 | Not Started | #N/A

## Mar 25
Workpack Number | Activity ID | Project Name | Activity Name | Start | Finish | Original Duration | Remaining Duration | At Completion Duration | PhysicaL % Complete | Total Flaot | Activity Status
W085 | W085.A1210 | REGION 1 Further Flasks in Readiness | Summary for REGION 1 Further Flasks in Readiness W085 | 2018-01-02 | 2025-08-11 | 1 | 112 | 1923 | 83% | 6 | In Progress
W155 | W155.A1830 | HRA Security | Summary for HRA Security W155 | 2020-09-01 | 2026-11-11 | 1339 | 430 | 1567 | 52% | 35 | In Progress
W158 | W158.1000 | DNB Security | Summary for DNB Security W158 | 2021-08-02 | 2025-07-09 | 278 | 89 | 994 | 65% | 142 | In Progress
W085 | W085.A2600 | REGION 1 Further Flasks in Readiness | Gate C-D Flask 1 Cost Summary | 2022-05-24 | 2025-03-21 | 97 | 15 | 716 | 85% | 88 | In Progress
W085 | W085.DS14560 | REGION 1 Further Flasks in Readiness | Gate C-D Flask 4 Cost Summary | 2022-07-01 | 2025-05-07 | 135 | 45 | 720 | 70% | 10 | In Progress
W085 | W085.DS15580 | REGION 1 Further Flasks in Readiness | Gate C-D Flask 5 Cost Summary | 2022-07-11 | 2025-05-13 | 117 | 49 | 718 | 70% | 6 | In Progress
W085 | W085.DS16600 | REGION 1 Further Flasks in Readiness | Gate C-D Flask 6 Cost Summary | 2022-10-02 | 2025-05-21 | 246 | 55 | 665 | 50% | 11 | In Progress
W085 | W085.DS17620 | REGION 1 Further Flasks in Readiness | Gate C-D Flask 7 Cost Summary | 2023-01-23 | 2025-04-25 | 241 | 38 | 571 | 20% | 96 | In Progress
W085 | W085.DS1020 | REGION 1 Further Flasks in Readiness | Cost Summary Final 5 Flasks | 2023-01-23 | 2025-07-11 | 321 | 91 | 624 | 80% | 7 | In Progress
W157 | W157.1000 | HYB Security | Summary for HYB Security W157 | 2023-02-01 | 2026-12-02 | 855 | 445 | 971 | 53% | 20 | In Progress
W155 | W155.24600 | HRA Security | Reactor Equivalence Confirmed by NSG Group Head | 2023-02-01 | 2026-12-31 | 484 | 465 | 991 | 50% | 0 | In Progress
W156 | W156.24600 | HYA Security | Reactor Equivalence Confirmed by NSG Group Head | 2023-02-01 | 2026-12-31 | 484 | 465 | 991 | 51% | 221 | In Progress
W085 | W085.DS18640 | REGION 1 Further Flasks in Readiness | Gate C-D Flask 8 Cost Summary | 2023-02-27 | 2025-05-19 | 260 | 53 | 561 | 12% | 81 | In Progress
W161 | W161.8110 | HPB PSR4 | Summary of HPB PSR4 - W160 | 2023-04-03 | 2026-08-25 | 1 | 375 | 857 | 0% | 90 | In Progress
W160 | W160.8110 | HNB PSR4 | Summary of HNB PSR4 - W160 | 2023-04-03 | 2025-12-16 | 1 | 202 | 684 | 0% | 9 | In Progress
W159 | W159.1000 | TOR Security | Summary for TOR Security W159 | 2023-05-02 | 2027-01-29 | 800 | 485 | 950 | 21% | 0 | In Progress
W085 | W085.DS19660 | REGION 1 Further Flasks in Readiness | Gate C-D Flask 9 Cost Summary | 2023-06-05 | 2025-09-11 | 270 | 134 | 577 | 5% | 0 | In Progress
W527 | W527.25660 | DNB DPCS Defueling Support | Summary for DNB DPCS Defueling Support | 2024-01-02 | 2029-03-01 | 1016 | 1016 | 1312 | 13% | 716 | In Progress
W193 | W193.25300 | HNB DPCS Defueling Support | Summary HNB DPCS Defueling Support | 2024-01-02 | 2025-12-31 | 507 | 211 | 507 | 55% | 0 | In Progress
W196 | W196.25460 | HYA DPCS Defueling Support | Summary of HYA DPCS Defueling Support Plan | 2024-01-02 | 2027-12-31 | 1016 | 720 | 1016 | 10% | 759 | In Progress
W195 | W195.25720 | HRA DPCS Defueling Support | Summary of HRA DPCS Defueling Support Plan | 2024-01-02 | 2027-12-31 | 1 | 720 | 1016 | 20% | 759 | In Progress
W160 | W160.9360 | HNB PSR4 | ## HNB PSR4 Head Doc: Safety Case Development - (B - D) - Cost Summary ## | 2024-01-08 | 2025-11-18 | 435 | 182 | 474 | 40% | 1 | In Progress
W160 | W160.9350 | HNB PSR4 | ## HNB PSR4 Head Doc: Project Management - (B - D) - Cost Summary ## | 2024-01-08 | 2025-11-18 | 435 | 182 | 474 | 40% | 1 | In Progress
W161 | W161.9350 | HPB PSR4 | ## HPB PSR4 Head Doc: Project Management - (B - D) - Cost Summary ## | 2024-02-26 | 2026-06-29 | 587 | 334 | 591 | 32% | 131 | In Progress
W161 | W161.9360 | HPB PSR4 | ## HPB PSR4 Head Doc: Safety Case Development - (B - D) - Cost Summary ## | 2024-02-26 | 2026-06-29 | 587 | 334 | 591 | 32% | 131 | In Progress
W161 | W161.5820 | HPB PSR4 | HPB PSR4 Head Doc: Authoring of the Submission Proposal | 2024-04-05 | 2025-08-29 | 100 | 98 | 354 | 30% | -66 | In Progress
W161 | W161.9390 | HPB PSR4 | ## HPB PSR4 Head Doc: Authoring of Paper - ## Cost Summary ## | 2024-04-05 | 2025-09-11 | 237 | 108 | 364 | 50% | -66 | In Progress
W085 | W085.A2660 | REGION 1 Further Flasks in Readiness | Gate C - D Project Management and Engineering Support - Cost Summary | 2024-06-03 | 2025-09-02 | 334 | 127 | 318 | 75% | 6 | In Progress
W085 | W085.A7200 | REGION 1 Further Flasks in Readiness | ETC (DD-PF) | 2024-07-01 | 2025-08-29 | 204 | 125 | 296 | 68% | 9 | In Progress
W161 | W161.9460 | HPB PSR4 | ## HPB PSR3 Extension EC: Verification - Cost Summary ## | 2024-07-15 | 2025-09-09 | 303 | 15 | 293 | 75% | -232 | In Progress
W160 | W160.9460 | HNB PSR4 | ## HNB PSR3 Extension EC: Verification - Cost Summary ## | 2024-07-15 | 2025-08-28 | 285 | 7 | 285 | 99% | -224 | In Progress
W161 | W161.9470 | HPB PSR4 | ## HPB PSR3 Extension EC: Key Stakeholders Engagement - Cost Summary ## | 2024-08-01 | 2025-09-24 | 291 | 26 | 291 | 0% | -243 | In Progress
W085 | W085.DS20290 | REGION 1 Further Flasks in Readiness | Paint Flask Body | 2024-08-23 | 2025-05-08 | 12 | 46 | 178 | 80% | 0 | In Progress
W085 | W085.DS20140 | REGION 1 Further Flasks in Readiness | Cavity Testing | 2024-08-27 | 2025-03-24 | 5 | 16 | 147 | 90% | 26 | In Progress
W085 | W085.DS21440 | REGION 1 Further Flasks in Readiness | Paint Lid Topside | 2024-09-23 | 2025-05-08 | 1 | 46 | 158 | 50% | 7 | In Progress
W196 | W196.6210 | HYA DPCS Defueling Support | HYA 2024 - Design, Consolidation and Testing | 2024-10-09 | 2025-03-28 | 120 | 20 | 120 | 80% | 1459 | In Progress
W085 | W085.DS24800 | REGION 1 Further Flasks in Readiness | Flask 4 - Flask Licensing Prepare Cat C Mod | 2024-10-28 | 2025-03-28 | 5 | 20 | 107 | 15% | 10 | In Progress
W194 | W194.25660 | HPB DPCS Defueling Support | Raise RFS for Decommissioning Rig | 2024-11-27 | 2025-10-31 | 30 | 170 | 235 | 75% | 299 | In Progress
W085 | W085.DS18610 | REGION 1 Further Flasks in Readiness | Approve Flask LTQRs | 2024-11-29 | 2025-03-07 | 10 | 5 | 68 | 75% | 96 | In Progress
W160 | W160.9420 | HNB PSR4 | ## HNB PSR4 Head Doc: Clearances and Closeout - Cost Summary ## | 2024-11-29 | 2025-11-18 | 245 | 182 | 245 | 1.25% | 1 | In Progress
W160 | W160.6010 | HNB PSR4 | HNB PSR4 Head Doc: Prepare Station Director's Brief | 2024-11-29 | 2025-04-04 | 5 | 25 | 88 | 90% | 8 | In Progress
W160 | W160.9410 | HNB PSR4 | ## HNB PSR4 Head Doc: INSA & NSC Meeting Readiness - Cost Summary ## | 2024-12-04 | 2025-04-16 | 92 | 32 | 92 | 37% | 1 | In Progress
W160 | W160.5970 | HNB PSR4 | HNB PSR4 Head Doc: HNB PSR4 Head Doc: INSA review & iteration of comments (using BARRIER MODEL) | 2024-12-04 | 2025-03-18 | 40 | 12 | 72 | 40% | -8 | In Progress
W194 | W194.2100 | HPB DPCS Defueling Support | HPB PES Group Support - 2025 | 2025-01-02 | 2025-12-31 | 253 | 211 | 253 | 16% | 509 | In Progress
W194 | W194.2110 | HPB DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2025 | 2025-01-02 | 2025-12-31 | 253 | 211 | 253 | 16% | 509 | In Progress
W194 | W194.2250 | HPB DPCS Defueling Support | Thales Long Term Support Contract Q1 2025 | 2025-01-02 | 2025-03-31 | 63 | 21 | 63 | 66% | 509 | In Progress
W195 | W195.2030 | HRA DPCS Defueling Support | HRA PES Group Support - 2025 | 2025-01-02 | 2025-12-31 | 253 | 211 | 253 | 16% | 1268 | In Progress
W195 | W195.2040 | HRA DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2025 | 2025-01-02 | 2025-12-31 | 253 | 211 | 253 | 16% | 1268 | In Progress
W195 | W195.2260 | HRA DPCS Defueling Support | Thales Long Term Support Contract Q1 2025 | 2025-01-02 | 2025-03-31 | 63 | 21 | 63 | 66% | 1268 | In Progress
W195 | W195.2630 | HRA DPCS Defueling Support | Argus Support Contract 2025 - Jan Q1 | 2025-01-02 | 2025-03-31 | 63 | 21 | 63 | 66% | 1268 | In Progress
W196 | W196.2030 | HYA DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2025 | 2025-01-02 | 2025-12-31 | 253 | 211 | 253 | 16% | 1268 | In Progress
W196 | W196.2040 | HYA DPCS Defueling Support | HYA PES Group Support - 2025 | 2025-01-02 | 2025-12-31 | 253 | 211 | 253 | 16% | 1268 | In Progress
W196 | W196.2270 | HYA DPCS Defueling Support | Thales Long Term Support Contract Q1 2025 | 2025-01-02 | 2025-03-31 | 63 | 21 | 63 | 66% | 1458 | In Progress
W196 | W196.2590 | HYA DPCS Defueling Support | Argus Support Contract - 2025 - Q1 | 2025-01-02 | 2025-03-31 | 63 | 21 | 63 | 66% | 1458 | In Progress
W527 | W527.1493 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q1 2025 | 2025-01-02 | 2025-03-31 | 63 | 21 | 63 | 66% | 1711 | In Progress
W527 | W527.1490 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q1 2025 | 2025-01-02 | 2025-03-31 | 63 | 21 | 63 | 66% | 1711 | In Progress
W527 | W527.1540 | DNB DPCS Defueling Support | DNB PES Group Support - 2025 | 2025-01-02 | 2025-12-31 | 253 | 211 | 253 | 16% | 1521 | In Progress
W527 | W527.1550 | DNB DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2025 | 2025-01-02 | 2025-12-31 | 253 | 211 | 253 | 16% | 1521 | In Progress
W527 | W527.1491 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q1 2025 | 2025-01-02 | 2025-03-31 | 63 | 21 | 63 | 66% | 1711 | In Progress
W527 | W527.1492 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q1 2025 | 2025-01-02 | 2025-03-31 | 63 | 21 | 63 | 66% | 1711 | In Progress
W193 | W193.2040 | HNB DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group | 2025-01-02 | 2025-12-31 | 253 | 211 | 253 | 16% | 0 | In Progress
W193 | W193.2030 | HNB DPCS Defueling Support | HNB PES Group Support - 2025 | 2025-01-02 | 2025-12-31 | 253 | 211 | 253 | 16% | 0 | In Progress
W527 | W527.1503 | DNB DPCS Defueling Support | Cost Engineer support 2025 | 2025-01-02 | 2025-12-31 | 253 | 211 | 253 | 66% | 1521 | In Progress
W529 | W529.1040 | TOR DPCS Defueling Support | TOR PES Group Support - 2025 | 2025-01-02 | 2025-12-30 | 252 | 210 | 252 | 16% | 1778 | In Progress
W529 | W529.1050 | TOR DPCS Defueling Support | TOR Plant Control Systems & Simulators (PCS&S) Group - 2025 | 2025-01-02 | 2025-12-31 | 253 | 211 | 253 | 16% | 1777 | In Progress
W529 | W529.1200 | TOR DPCS Defueling Support | TOR Argus Support Contract Q1 2025 | 2025-01-02 | 2025-03-31 | 63 | 21 | 63 | 66% | 1777 | In Progress
W529 | W529.1220 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract Q1 2025 | 2025-01-02 | 2025-03-31 | 1 | 21 | 63 | 66% | 1777 | In Progress
W526 | W526.1225 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract Q1 2025 | 2025-01-02 | 2025-03-31 | 63 | 21 | 63 | 66% | 1778 | In Progress
W526 | W526.1050 | HYB DPCS Defueling Support | HYB Plant Control Systems & Simulators (PCS&S) Group - 2025 | 2025-01-02 | 2025-12-31 | 253 | 211 | 253 | 16% | 1777 | In Progress
W526 | W526.1040 | HYB DPCS Defueling Support | HYB PES Group Support - 2025 | 2025-01-02 | 2025-12-30 | 252 | 210 | 252 | 16% | 1778 | In Progress
W529 | W529.6310 | TOR DPCS Defueling Support | TOR 2025 S13R2 - Software Build Requirement | 2025-01-02 | 2025-06-30 | 124 | 82 | 124 | 30% | 1736 | In Progress
W527 | W527.25180 | DNB DPCS Defueling Support | 2025 Costs | 2025-01-02 | 2025-03-03 | 253 | 0 | 42 | 16% | 1732 | In Progress
W526 | W526.10000 | HYB DPCS Defueling Support | HYB 2025 External Costs | 2025-01-02 | 2025-12-31 | 253 | 211 | 253 | 16% | 1777 | In Progress
W529 | W529.10000 | TOR DPCS Defueling Support | TOR 2025 External Costs | 2025-01-02 | 2025-12-31 | 253 | 211 | 253 | 8% | 1777 | In Progress
W194 | W194.25200 | HPB DPCS Defueling Support | 2025 External | 2025-01-02 | 2025-12-31 | 253 | 211 | 253 | 16% | 509 | In Progress
W193 | W193.25200 | HNB DPCS Defueling Support | 2025 Externals | 2025-01-02 | 2025-12-31 | 253 | 211 | 253 | 16% | 0 | In Progress
W195 | W195.1020 | HRA DPCS Defueling Support | 2025 Externals | 2025-01-02 | 2025-12-31 | 253 | 211 | 253 | 16% | 1268 | In Progress
W196 | W196.1020 | HYA DPCS Defueling Support | 2025 External | 2025-01-02 | 2025-12-31 | 253 | 211 | 253 | 16% | 1268 | In Progress
W194 | W194.25360 | HPB DPCS Defueling Support | TPM and JCRB Meetings Held 2025 | 2025-01-02 | 2025-12-31 | 253 | 211 | 253 | 16% | 509 | In Progress
W526 | W526.10160 | HYB DPCS Defueling Support | TPM and JCRB Meeting Held 2025 | 2025-01-02 | 2025-12-31 | 253 | 211 | 253 | 16% | 0 | In Progress
W195 | W195.25680 | HRA DPCS Defueling Support | TPM and JCRB Meetings Held - 2025 | 2025-01-02 | 2025-12-31 | 253 | 211 | 253 | 16% | 759 | In Progress
W196 | W196.1225 | HYA DPCS Defueling Support | TPM and JCRB Meetings Held 2025 | 2025-01-02 | 2025-12-31 | 253 | 211 | 253 | 16% | 759 | In Progress
W527 | W527.4820 | DNB DPCS Defueling Support | TPM and JCRB Meetings Held 2025 | 2025-01-02 | 2025-12-31 | 253 | 211 | 253 | 16% | 1012 | In Progress
W529 | W195.1000 | TOR DPCS Defueling Support | TPM and JCRB Meetings Held - 2025 | 2025-01-02 | 2025-12-31 | 253 | 211 | 253 | 16% | 0 | In Progress
W529 | W529.3010 | TOR DPCS Defueling Support | TOR DPCS Long Term Support Contract 2025 | 2025-01-03 | 2025-12-31 | 252 | 211 | 252 | 8% | 1777 | In Progress
W196 | W196.6350 | HYA DPCS Defueling Support | HYA 2025 - Data Modifications and Amendments | 2025-01-03 | 2025-12-31 | 252 | 211 | 252 | 16% | 1268 | In Progress
W195 | W195.25610 | HRA DPCS Defueling Support | HRA 2025 - Data Modifications and Amendments | 2025-01-03 | 2025-12-31 | 252 | 211 | 252 | 16% | 1268 | In Progress
W527 | W527.25610 | DNB DPCS Defueling Support | DNB 2025 2.9 - Site Acceptance Testing | 2025-01-06 | 2025-06-30 | 122 | 82 | 122 | 30% | 1594 | In Progress
W085 | W085.2950 | REGION 1 Further Flasks in Readiness | Manufacture Dummy LSM'S | 2025-01-14 | 2025-03-28 | 1 | 20 | 54 | 75% | 114 | In Progress
W085 | W085.DS2260 | REGION 1 Further Flasks in Readiness | Approve Flask LTQRs | 2025-01-20 | 2025-03-21 | 10 | 15 | 45 | 50% | 88 | In Progress
W527 | W527.25690 | DNB DPCS Defueling Support | DNB 2026 2.10 - Specification | 2025-01-20 | 2025-10-03 | 180 | 150 | 180 | 20% | 1404 | In Progress
W193 | W193.25320 | HNB DPCS Defueling Support | HNB SQEP declaration | 2025-01-20 | 2025-04-11 | 60 | 30 | 60 | 30% | 31 | In Progress
W155 | W155.2590 | HRA Security | Implement temporary infrastructure and organisational mitigations required to enable commencement of defuelling | 2025-02-03 | 2026-11-11 | 450 | 430 | 450 | 5% | 35 | In Progress
W155 | W155.2600 | HRA Security | Implement permanent infrastructure and organisational mitigations | 2025-02-03 | 2026-11-11 | 450 | 430 | 450 | 5% | 35 | In Progress
W195 | W195.1065 | HRA DPCS Defueling Support | HRA 2024 - Design, Consolidation and Testing | 2025-02-03 | 2025-03-28 | 40 | 20 | 40 | 50% | 1404 | In Progress
W527 | W527.25020 | DNB DPCS Defueling Support | DNB TGN097 POLARIS - Plan Produced | 2025-02-07 | 2025-04-03 | 40 | 24 | 40 | 40% | 1708 | In Progress
W527 | W527.25100 | DNB DPCS Defueling Support | DNB TGN097 AIC - Plan Produced | 2025-02-07 | 2025-04-03 | 40 | 24 | 40 | 40% | 1708 | In Progress
W196 | W196.25310 | HYA DPCS Defueling Support | LSR Data Export, Analysis, Draft Report | 2025-02-17 | 2025-03-07 | 15 | 5 | 15 | 80% | 1446 | In Progress
W156 | W156.2710 | HYA Security | Review and Agree Security Changes and MSI Category (INA, SPB, NSC) | 2025-02-24 | 2025-04-04 | 30 | 25 | 30 | 80% | 616 | In Progress
W526 | W526.2080 | HYB DPCS Defueling Support | HYB 2025 LSR - Data Export Produced and Issued | 2025-02-25 | 2025-03-24 | 20 | 16 | 20 | 30% | 1921 | In Progress
W155 | W155.000010 | HRA Security | EAC (DD-PF) | 2025-03-03 | 2026-12-31 | 465 | 465 | 465 | 0% | 0 | Not Started
W156 | W156.000010 | HYA Security | EAC (DD-PF) | 2025-03-03 | 2026-12-31 | 465 | 465 | 465 | 0% | 221 | Not Started
W193 | W193.2000 | HNB DPCS Defueling Support | ETC (DD-PF) | 2025-03-03 | 2025-12-31 | 211 | 211 | 211 | 0% | 0 | Not Started
W085 | W085.DS17570 | REGION 1 Further Flasks in Readiness | Verify Testing and Approve Report (EDF) | 2025-03-03 | 2025-03-07 | 5 | 5 | 5 | 0% | 11 | Not Started
W085 | W085.DS19620 | REGION 1 Further Flasks in Readiness | Produce Flask LTQRs | 2025-03-03 | 2025-03-14 | 10 | 10 | 10 | 0% | 81 | Not Started
W085 | W085.DS20340 | REGION 1 Further Flasks in Readiness | Paint Flask Base | 2025-03-03 | 2025-03-21 | 12 | 15 | 15 | 0% | 0 | Not Started
W529 | 00 | TOR DPCS Defueling Support | ETC (DD-PF) | 2025-03-03 | 2032-12-30 | 1987 | 1987 | 1987 | 0% | 1 | Not Started
W529 | W529.2070 | TOR DPCS Defueling Support | TOR 2025 LSR - Pre-export Data Validation Produced and Completed | 2025-03-03 | 2025-03-31 | 21 | 21 | 21 | 0% | 1929 | Not Started
W529 | W529.3020 | TOR DPCS Defueling Support | TOR 2026 Defueling Software Build | 2025-03-03 | 2026-01-30 | 232 | 232 | 232 | 0% | 1756 | Not Started
W529 | W529.3030 | TOR DPCS Defueling Support | TOR DPCS Long Term Support Contract 2026 | 2025-03-03 | 2026-03-03 | 254 | 254 | 254 | 0% | 1734 | Not Started
W526 | W526.1020 | HYB DPCS Defueling Support | ETC (DD-PF) | 2025-03-03 | 2032-12-30 | 1987 | 1987 | 1987 | 0% | 1 | Not Started
W155 | W155.37761 | HRA Security | 2025 | 2025-03-03 | 2026-01-29 | 231 | 231 | 231 | 0% | 234 | Not Started
W156 | W156.34991 | HYA Security | 2025 | 2025-03-03 | 2026-01-29 | 231 | 231 | 231 | 0% | 455 | Not Started
W158 | W158.34851 | DNB Security | 2025 | 2025-03-03 | 2026-01-29 | 231 | 231 | 231 | 0% | 0 | Not Started
W527 | W527.25190 | DNB DPCS Defueling Support | 2026 Costs | 2025-03-03 | 2025-03-03 | 0 | 0 | 0 | 0% | 1732 | Not Started
W527 | W527.25200 | DNB DPCS Defueling Support | 2027 Costs | 2025-03-03 | 2025-03-03 | 0 | 0 | 0 | 0% | 1732 | Not Started
W527 | W527.25230 | DNB DPCS Defueling Support | ETC 2025 | 2025-03-03 | 2025-12-31 | 211 | 211 | 211 | 0% | 0 | Not Started
W195 | W195.25250 | HRA DPCS Defueling Support | HRA DPCS Defuleing Support Project End | 2025-03-03 | 2025-03-03 | 1 | 1 | 1 | 0% | 1478 | Not Started
W196 | W196.25180 | HYA DPCS Defueling Support | HYA DPCS Defueling Support Project End | 2025-03-03 | 2025-03-03 | 1 | 1 | 1 | 0% | 1478 | Not Started
W157 | W157.000010 | HYB Security | EAC (DD-PF) | 2025-03-03 | 2026-12-31 | 465 | 465 | 465 | 0% | 0 | Not Started
W157 | W157.34821 | HYB Security | 2025 | 2025-03-03 | 2026-01-29 | 231 | 231 | 231 | 0% | 234 | Not Started
W159 | W159.000010 | TOR Security | EAC (DD-PF) | 2025-03-03 | 2026-12-31 | 465 | 465 | 465 | 0% | 20 | Not Started
W159 | W159.34991 | TOR Security | 2025 | 2025-03-03 | 2026-01-29 | 231 | 231 | 231 | 0% | 254 | Not Started
W194 | W194.25640 | HPB DPCS Defueling Support | Update LSR | 2025-03-03 | 2025-03-07 | 5 | 5 | 5 | 0% | 714 | Not Started
W156 | W156.3220 | HYA Security | Review Flasks SPPI File Against Issued Enhanced Safety Cases | 2025-03-03 | 2025-07-24 | 100 | 100 | 100 | 0% | 583 | Not Started
W161 | W161.8020 | HPB PSR4 | ETC (DD-PF) | 2025-03-03 | 2026-12-31 | 465 | 465 | 465 | 0% | 0 | Not Started
W193 | W193.25350 | HNB DPCS Defueling Support | Fuel Free Verification (FFV) declared | 2025-03-03 | 2025-03-05 | 3 | 3 | 3 | 0% | 208 | Not Started
W194 | W194.25750 | HPB DPCS Defueling Support | ETC 2025 | 2025-03-03 | 2025-12-31 | 211 | 211 | 211 | 0% | 255 | Not Started
W195 | W195.26060 | HRA DPCS Defueling Support | ETC 2025 | 2025-03-03 | 2025-12-31 | 211 | 211 | 211 | 0% | 0 | Not Started
W196 | W196.2060 | HYA DPCS Defueling Support | ETC 2025 | 2025-03-03 | 2025-12-31 | 211 | 211 | 211 | 0% | 0 | Not Started
W160 | W160.8002 | HNB PSR4 | ETC (DD-PF) | 2025-03-03 | 2025-12-31 | 211 | 211 | 211 | 0% | 0 | Not Started
W529 | 10 | TOR DPCS Defueling Support | ETC 2025 | 2025-03-03 | 2025-12-31 | 211 | 211 | 211 | 0% | 1777 | Not Started
W526 | W526.1030 | HYB DPCS Defueling Support | ETC 2025 | 2025-03-03 | 2025-12-31 | 211 | 211 | 211 | 0% | 0 | Not Started
W527 | W527.25030 | DNB DPCS Defueling Support | DNB TGN097 POLARIS - Inspection | 2025-03-06 | 2025-03-12 | 5 | 5 | 5 | 0% | 1694 | Not Started
W527 | W527.25110 | DNB DPCS Defueling Support | DNB TGN097 AIC - Inspection | 2025-03-06 | 2025-03-12 | 5 | 5 | 5 | 0% | 1694 | Not Started
W085 | W085.DS17580 | REGION 1 Further Flasks in Readiness | Produce Flask LTQRs | 2025-03-10 | 2025-03-21 | 10 | 10 | 10 | 0% | 11 | Not Started
W085 | W085.DS24920 | REGION 1 Further Flasks in Readiness | Flask 7 - Flask Licensing Prepare Cat C Mod | 2025-03-10 | 2025-03-14 | 5 | 5 | 5 | 0% | 96 | Not Started
W194 | W194.25650 | HPB DPCS Defueling Support | Issue Complete LSR | 2025-03-10 | 2025-03-10 | 1 | 1 | 1 | 0% | 714 | Not Started
W196 | W196.25320 | HYA DPCS Defueling Support | Issue Recommendations | 2025-03-10 | 2025-03-10 | 1 | 1 | 1 | 0% | 1446 | Not Started
W527 | W527.25070 | DNB DPCS Defueling Support | DNB TGN097 POLARIS - Draft Report Produced, Internal Review and Issue to EDF | 2025-03-13 | 2025-03-26 | 10 | 10 | 10 | 0% | 1694 | Not Started
W527 | W527.25140 | DNB DPCS Defueling Support | DNB TGN097 AIC - Draft Report Produced, Internal Review and Issue to EDF | 2025-03-13 | 2025-03-26 | 10 | 10 | 10 | 0% | 1694 | Not Started
W196 | W196.25330 | HYA DPCS Defueling Support | Recommendations Workshop | 2025-03-14 | 2025-03-14 | 1 | 1 | 1 | 0% | 1446 | Not Started
W085 | W085.DS19630 | REGION 1 Further Flasks in Readiness | Approve Flask LTQRs | 2025-03-17 | 2025-03-28 | 10 | 10 | 10 | 0% | 81 | Not Started
W085 | W085.DS25220 | REGION 1 Further Flasks in Readiness | Flask 7 - Flask Licensing Verification Cat C Mod | 2025-03-17 | 2025-03-25 | 5 | 7 | 7 | 0% | 96 | Not Started
W196 | W196.25340 | HYA DPCS Defueling Support | LSR Update, Internal Review & Issue to EDF | 2025-03-17 | 2025-03-28 | 10 | 10 | 10 | 0% | 1446 | Not Started
W160 | W160.5980 | HNB PSR4 | HNB PSR4 Head Doc: Incorporate INSA comments | 2025-03-19 | 2025-03-25 | 5 | 5 | 5 | 0% | -8 | Not Started
W085 | W085.2880 | REGION 1 Further Flasks in Readiness | Blast Tent Removal | 2025-03-20 | 2025-03-24 | 1 | 3 | 3 | 0% | 90 | Not Started
W085 | W085.DS17590 | REGION 1 Further Flasks in Readiness | Approve Flask LTQRs | 2025-03-24 | 2025-04-04 | 10 | 10 | 10 | 0% | 11 | Not Started
W085 | W085.DS20410 | REGION 1 Further Flasks in Readiness | Verify Painting Complete (EDF) | 2025-03-24 | 2025-03-28 | 1 | 5 | 5 | 0% | 31 | Not Started
W085 | W085.DS24710 | REGION 1 Further Flasks in Readiness | Flask 2 - Flask Licensing Prepare Cat C Mod | 2025-03-24 | 2025-03-24 | 5 | 0 | 0 | 0% | 88 | Not Started
W085 | W085.DS25120 | REGION 1 Further Flasks in Readiness | Flask 2 - Flask Licensing Verification Cat C Mod | 2025-03-24 | 2025-04-01 | 5 | 7 | 7 | 0% | 88 | Not Started
W085 | W085.DS20160 | REGION 1 Further Flasks in Readiness | Verify Repairs and NDT Complete (EDF) | 2025-03-25 | 2025-03-31 | 5 | 5 | 5 | 0% | 26 | Not Started
W526 | W526.2090 | HYB DPCS Defueling Support | HYB 2025 LSR - Recommendations Produced and Issued | 2025-03-25 | 2025-04-07 | 10 | 10 | 10 | 0% | 1921 | Not Started
W085 | W085.DS25230 | REGION 1 Further Flasks in Readiness | Flask 7 - Flask Licensing CO Review Cat C Mod | 2025-03-26 | 2025-04-04 | 5 | 8 | 8 | 0% | 96 | Not Started
W160 | W160.9540 | HNB PSR4 | HNB PSR4 Head Doc: Verification Schedule Risk - (Risk Ref 38853) | 2025-03-26 | 2025-03-26 | 0 | 0 | 0 | 0% | -8 | Not Started
W527 | W527.25080 | DNB DPCS Defueling Support | DNB TGN097 POLARIS - EDF Review | 2025-03-27 | 2025-04-09 | 10 | 10 | 10 | 0% | 1694 | Not Started
W527 | W527.25130 | DNB DPCS Defueling Support | DNB TGN097 AIC - EDF Review | 2025-03-27 | 2025-04-09 | 10 | 10 | 10 | 0% | 1694 | Not Started
W085 | W085.2890 | REGION 1 Further Flasks in Readiness | Paint Tent Removal | 2025-03-27 | 2025-03-28 | 1 | 2 | 2 | 0% | 90 | Not Started
W196 | W196.25030 | HYA DPCS Defueling Support | TGN097 R2 - Inspection | 2025-03-28 | 2025-04-03 | 5 | 5 | 5 | 0% | 1437 | Not Started
W085 | W085.DS24840 | REGION 1 Further Flasks in Readiness | Flask 5 - Flask Licensing Prepare Cat C Mod | 2025-03-28 | 2025-04-03 | 5 | 5 | 5 | 0% | 6 | Not Started
W085 | W085.DS24960 | REGION 1 Further Flasks in Readiness | Flask 8 - Flask Licensing Prepare Cat C Mod | 2025-03-31 | 2025-04-04 | 5 | 5 | 5 | 0% | 81 | Not Started
W085 | W085.DS25160 | REGION 1 Further Flasks in Readiness | Flask 4 - Flask Licensing Verification Cat C Mod | 2025-03-31 | 2025-04-08 | 5 | 7 | 7 | 0% | 10 | Not Started
W196 | W196.25350 | HYA DPCS Defueling Support | EDF Review | 2025-03-31 | 2025-04-08 | 7 | 7 | 7 | 0% | 1446 | Not Started
W085 | W085.2900 | REGION 1 Further Flasks in Readiness | Extractor Removal | 2025-03-31 | 2025-04-01 | 1 | 2 | 2 | 0% | 90 | Not Started
W085 | W085.2980 | REGION 1 Further Flasks in Readiness | E117 | 2025-03-31 | 2025-04-01 | 1 | 2 | 2 | 0% | 97 | Not Started
W194 | W194.2280 | HPB DPCS Defueling Support | Thales Long Term Support Contract Q2 2025 | 2025-04-01 | 2025-06-30 | 61 | 61 | 61 | 0% | 509 | Not Started
W195 | W195.2270 | HRA DPCS Defueling Support | Thales Long Term Support Contract Q2 2025 | 2025-04-01 | 2025-06-30 | 61 | 61 | 61 | 0% | 1268 | Not Started
W195 | W195.2640 | HRA DPCS Defueling Support | Argus Support Contract 2025 - Apr Q2 | 2025-04-01 | 2025-06-30 | 61 | 61 | 61 | 0% | 1268 | Not Started
W196 | W196.2280 | HYA DPCS Defueling Support | Thales Long Term Support Contract Q2 2025 | 2025-04-01 | 2025-06-30 | 61 | 61 | 61 | 0% | 1397 | Not Started
W196 | W196.2600 | HYA DPCS Defueling Support | Argus Support Contract - 2025 - Q2 | 2025-04-01 | 2025-06-30 | 61 | 61 | 61 | 0% | 1397 | Not Started
W527 | W527.1575 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q2 2025 | 2025-04-01 | 2025-06-30 | 61 | 61 | 61 | 0% | 1650 | Not Started
W527 | W527.1570 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q2 2025 | 2025-04-01 | 2025-06-30 | 61 | 61 | 61 | 0% | 1650 | Not Started
W527 | W527.1572 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q2 2025 | 2025-04-01 | 2025-06-30 | 61 | 61 | 61 | 0% | 1650 | Not Started
W527 | W527.1574 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q2 2025 | 2025-04-01 | 2025-06-30 | 61 | 61 | 61 | 0% | 1650 | Not Started
W085 | W085.DS20270 | REGION 1 Further Flasks in Readiness | Produce Refurbishment Report | 2025-04-01 | 2025-04-23 | 14 | 15 | 15 | 0% | 26 | Not Started
W529 | W529.1230 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract Q2 2025 | 2025-04-01 | 2025-06-30 | 61 | 61 | 61 | 0% | 1777 | Not Started
W529 | W529.1205 | TOR DPCS Defueling Support | TOR Argus Support Contract Q2 2025 | 2025-04-01 | 2025-06-30 | 61 | 61 | 61 | 0% | 1777 | Not Started
W529 | W529.2080 | TOR DPCS Defueling Support | TOR 2025 LSR - Data Export Produced and Issued | 2025-04-01 | 2025-04-17 | 13 | 13 | 13 | 0% | 1929 | Not Started
W526 | W526.1235 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract Q2 2025 | 2025-04-01 | 2025-06-30 | 61 | 61 | 61 | 0% | 1778 | Not Started
W085 | W085.DS25130 | REGION 1 Further Flasks in Readiness | Flask 2 - Flask Licensing CO Review Cat C Mod | 2025-04-02 | 2025-04-11 | 5 | 8 | 8 | 0% | 88 | Not Started
W085 | W085.2990 | REGION 1 Further Flasks in Readiness | E112 | 2025-04-02 | 2025-04-03 | 1 | 2 | 2 | 0% | 97 | Not Started
W196 | W196.25070 | HYA DPCS Defueling Support | TGN097 R2 - Draft Report Produced, Internal Review and Issue to EDF | 2025-04-04 | 2025-04-10 | 5 | 5 | 5 | 0% | 1437 | Not Started
W085 | W085.DS25180 | REGION 1 Further Flasks in Readiness | Flask 5 - Flask Licensing Verification Cat C Mod | 2025-04-04 | 2025-04-14 | 5 | 7 | 7 | 0% | 6 | Not Started
W085 | W085.3000 | REGION 1 Further Flasks in Readiness | E120 | 2025-04-04 | 2025-04-07 | 1 | 2 | 2 | 0% | 97 | Not Started
W156 | W156.2570 | HYA Security | Complete MSI process | 2025-04-07 | 2025-05-21 | 30 | 30 | 30 | 0% | 616 | Not Started
W085 | W085.DS24880 | REGION 1 Further Flasks in Readiness | Flask 6 - Flask Licensing Prepare Cat C Mod | 2025-04-07 | 2025-04-11 | 5 | 5 | 5 | 0% | 11 | Not Started
W085 | W085.DS24930 | REGION 1 Further Flasks in Readiness | Flask 7 - Flask Licensing INA Approval of Cat C | 2025-04-07 | 2025-04-22 | 10 | 10 | 10 | 0% | 96 | Not Started
W085 | W085.DS25240 | REGION 1 Further Flasks in Readiness | Flask 8 - Flask Licensing Verification Cat C Mod | 2025-04-07 | 2025-04-15 | 5 | 7 | 7 | 0% | 81 | Not Started
W526 | W526.2100 | HYB DPCS Defueling Support | HYB 2025 LSR - Recommendation Sentencing Workshop Preparation and Event | 2025-04-08 | 2025-04-23 | 10 | 10 | 10 | 0% | 1921 | Not Started
W085 | W085.3010 | REGION 1 Further Flasks in Readiness | E113 | 2025-04-08 | 2025-04-09 | 1 | 2 | 2 | 0% | 97 | Not Started
W085 | W085.DS25170 | REGION 1 Further Flasks in Readiness | Flask 4 - Flask Licensing CO Review Cat C Mod | 2025-04-09 | 2025-04-22 | 5 | 8 | 8 | 0% | 10 | Not Started
W196 | W196.25360 | HYA DPCS Defueling Support | Update LSR | 2025-04-09 | 2025-04-15 | 5 | 5 | 5 | 0% | 1446 | Not Started
W527 | W527.25090 | DNB DPCS Defueling Support | DNB TGN097 POLARIS - Report Issued | 2025-04-10 | 2025-04-25 | 10 | 10 | 10 | 0% | 1694 | Not Started
W527 | W527.25120 | DNB DPCS Defueling Support | DNB TGN097 AIC - Report Issued | 2025-04-10 | 2025-04-25 | 10 | 10 | 10 | 0% | 1694 | Not Started
W085 | W085.3020 | REGION 1 Further Flasks in Readiness | E122 | 2025-04-10 | 2025-04-10 | 1 | 1 | 1 | 0% | 97 | Not Started
W196 | W196.25080 | HYA DPCS Defueling Support | TGN097 R2 - EDF Review | 2025-04-11 | 2025-04-24 | 8 | 8 | 8 | 0% | 1437 | Not Started
W085 | W085.3030 | REGION 1 Further Flasks in Readiness | E114 | 2025-04-11 | 2025-04-14 | 1 | 2 | 2 | 0% | 97 | Not Started
W085 | W085.DS12550 | REGION 1 Further Flasks in Readiness | Flask 2 - Flask Licensing INA Approval of Cat C | 2025-04-14 | 2025-04-29 | 10 | 10 | 10 | 0% | 88 | Not Started
W085 | W085.DS25200 | REGION 1 Further Flasks in Readiness | Flask 6 - Flask Licensing Verification Cat C Mod | 2025-04-14 | 2025-04-24 | 5 | 7 | 7 | 0% | 11 | Not Started
W526 | W526.3160 | HYB DPCS Defueling Support | HYB 2025 LSR Pre Data Extract | 2025-04-14 | 2025-05-12 | 18 | 18 | 18 | 0% | 1901 | Not Started
W193 | W193.25330 | HNB DPCS Defueling Support | Asset Assessment | 2025-04-14 | 2025-05-29 | 30 | 30 | 30 | 0% | 31 | Not Started
W085 | W085.DS25190 | REGION 1 Further Flasks in Readiness | Flask 5 - Flask Licensing CO Review Cat C Mod | 2025-04-15 | 2025-04-28 | 5 | 8 | 8 | 0% | 6 | Not Started
W085 | W085.3040 | REGION 1 Further Flasks in Readiness | E137 | 2025-04-15 | 2025-04-16 | 1 | 2 | 2 | 0% | 97 | Not Started
W085 | W085.DS24940 | REGION 1 Further Flasks in Readiness | Flask 7 - Prepare Transport Paperwork | 2025-04-16 | 2025-04-24 | 5 | 5 | 5 | 0% | 96 | Not Started
W085 | W085.DS25250 | REGION 1 Further Flasks in Readiness | Flask 8 - Flask Licensing CO Review Cat C Mod | 2025-04-16 | 2025-04-29 | 5 | 8 | 8 | 0% | 81 | Not Started
W196 | W196.25370 | HYA DPCS Defueling Support | Issue LSR | 2025-04-16 | 2025-04-16 | 1 | 1 | 1 | 0% | 1446 | Not Started
W160 | W160.6020 | HNB PSR4 | HNB PSR4 Head Doc: NSC Consideration & advice to Station Director ==> KDM | 2025-04-16 | 2025-05-01 | 10 | 10 | 10 | 0% | 1 | Not Started
W085 | W085.3050 | REGION 1 Further Flasks in Readiness | E116 | 2025-04-17 | 2025-04-22 | 1 | 2 | 2 | 0% | 97 | Not Started
W529 | W529.2090 | TOR DPCS Defueling Support | TOR 2025 LSR - Recommendations Produced and Issued | 2025-04-22 | 2025-04-22 | 1 | 1 | 1 | 0% | 1929 | Not Started
W085 | W085.2920 | REGION 1 Further Flasks in Readiness | Dismantle Lid Turning Table and Store | 2025-04-22 | 2025-04-28 | 1 | 5 | 5 | 0% | 91 | Not Started
W085 | W085.DS14590 | REGION 1 Further Flasks in Readiness | Flask 4 - Flask Licensing INA Approval of Cat C | 2025-04-23 | 2025-05-07 | 10 | 10 | 10 | 0% | 10 | Not Started
W529 | W529.2100 | TOR DPCS Defueling Support | TOR 2025 LSR - Recommendation Sentencing Workshop Preparation and Event | 2025-04-23 | 2025-04-23 | 1 | 1 | 1 | 0% | 1929 | Not Started
W085 | W085.3060 | REGION 1 Further Flasks in Readiness | E99 | 2025-04-23 | 2025-04-24 | 1 | 2 | 2 | 0% | 97 | Not Started
W085 | W085.DS20280 | REGION 1 Further Flasks in Readiness | Approve Refurbishment Report | 2025-04-24 | 2025-05-08 | 9 | 10 | 10 | 0% | 26 | Not Started
W529 | W529.2110 | TOR DPCS Defueling Support | TOR 2025 LSR - Draft Report Produced and Issued for EDF Review | 2025-04-24 | 2025-05-08 | 10 | 10 | 10 | 0% | 1929 | Not Started
W526 | W526.2110 | HYB DPCS Defueling Support | HYB 2025 LSR - Draft Report Produced and Issued for EDF Review | 2025-04-24 | 2025-05-09 | 11 | 11 | 11 | 0% | 1921 | Not Started
W196 | W196.25090 | HYA DPCS Defueling Support | TGN097 R2 - Report Issue | 2025-04-25 | 2025-05-01 | 5 | 5 | 5 | 0% | 1437 | Not Started
W085 | W085.DS24950 | REGION 1 Further Flasks in Readiness | Flask 7 - Transport Flask to HNB | 2025-04-25 | 2025-04-25 | 1 | 1 | 1 | 0% | 96 | Not Started
W085 | W085.DS25210 | REGION 1 Further Flasks in Readiness | Flask 6 - Flask Licensing CO Review Cat C Mod | 2025-04-25 | 2025-05-07 | 5 | 8 | 8 | 0% | 11 | Not Started
W526 | W526.10520 | HYB DPCS Defueling Support | HYB 2026 S13R8 - Specification | 2025-04-28 | 2026-05-29 | 275 | 275 | 275 | 0% | 1505 | Not Started
W085 | W085.DS15610 | REGION 1 Further Flasks in Readiness | Flask 5 - Flask Licensing INA Approve Cat C Mod | 2025-04-29 | 2025-05-13 | 10 | 10 | 10 | 0% | 6 | Not Started
W085 | W085.2910 | REGION 1 Further Flasks in Readiness | Fence Erecting Stage 2 | 2025-04-29 | 2025-05-06 | 1 | 5 | 5 | 0% | 90 | Not Started
W085 | W085.2930 | REGION 1 Further Flasks in Readiness | Dimantle LSM Turning Table and Store | 2025-04-29 | 2025-05-02 | 1 | 4 | 4 | 0% | 91 | Not Started
W085 | W085.DS24740 | REGION 1 Further Flasks in Readiness | Flask 2 - Prepare Transport Paperwork | 2025-04-30 | 2025-05-07 | 5 | 5 | 5 | 0% | 88 | Not Started
W085 | W085.DS24970 | REGION 1 Further Flasks in Readiness | Flask 8 - Flask Licensing INA Approval of Cat C | 2025-04-30 | 2025-05-14 | 10 | 10 | 10 | 0% | 81 | Not Started
W085 | W085.DS24820 | REGION 1 Further Flasks in Readiness | Flask 4 - Prepare Transport Paperwork | 2025-05-02 | 2025-05-09 | 5 | 5 | 5 | 0% | 86 | Not Started
W157 | W157.1930 | HYB Security | Undertake Site assessment of defuelling impacts on existing and new SPP and resources | 2025-05-02 | 2025-05-09 | 5 | 5 | 5 | 0% | 267 | Not Started
W160 | W160.7060 | HNB PSR4 | HNB PSR4 Head Doc: Prepare Paper for Submission to ONR | 2025-05-02 | 2025-07-01 | 41 | 41 | 41 | 0% | 1 | Not Started
W158 | W158.3220 | DNB Security | Review Flask Security Arrangments Against Issued Enhanced Safety Cases | 2025-05-06 | 2025-05-12 | 5 | 5 | 5 | 0% | 142 | Not Started
W158 | W158.2380 | DNB Security | Revise SPPI File Against Issued Enhanced Safety Cases | 2025-05-06 | 2025-05-12 | 5 | 5 | 5 | 0% | 172 | Not Started
W085 | W085.DS16630 | REGION 1 Further Flasks in Readiness | Flask 6 - Flask Licensing INA Approval of Cat C | 2025-05-08 | 2025-05-21 | 10 | 10 | 10 | 0% | 11 | Not Started
W085 | W085.DS24750 | REGION 1 Further Flasks in Readiness | Flask 2 - Transport Flask to HNB | 2025-05-08 | 2025-05-08 | 1 | 1 | 1 | 0% | 88 | Not Started
W085 | W085.DS20330 | REGION 1 Further Flasks in Readiness | Verify Painting Complete (EDF) | 2025-05-09 | 2025-05-15 | 1 | 5 | 5 | 0% | 0 | Not Started
W085 | W085.DS21500 | REGION 1 Further Flasks in Readiness | Verify Painting Complete (EDF) | 2025-05-09 | 2025-05-15 | 2 | 5 | 5 | 0% | 7 | Not Started
W529 | W529.2120 | TOR DPCS Defueling Support | TOR 2025 LSR - EDF Review Comments Produced and Provided | 2025-05-09 | 2025-05-20 | 8 | 8 | 8 | 0% | 1929 | Not Started
W085 | W085.DS24860 | REGION 1 Further Flasks in Readiness | Flask 5 - Prepare Transport Paperwork | 2025-05-09 | 2025-05-15 | 5 | 5 | 5 | 0% | 82 | Not Started
W526 | W526.2120 | HYB DPCS Defueling Support | HYB 2025 LSR - EDF Review Comments Produced and Provided | 2025-05-12 | 2025-05-27 | 11 | 11 | 11 | 0% | 1921 | Not Started
W085 | W085.DS24830 | REGION 1 Further Flasks in Readiness | Flask 4 - Transport Flask to HNB | 2025-05-12 | 2025-05-12 | 1 | 1 | 1 | 0% | 86 | Not Started
W085 | W085.DS24980 | REGION 1 Further Flasks in Readiness | Flask 8 - Prepare Transport Paperwork | 2025-05-12 | 2025-05-16 | 5 | 5 | 5 | 0% | 81 | Not Started
W157 | W157.1940 | HYB Security | Write up Defuelling SPPI file V1 | 2025-05-12 | 2025-06-02 | 15 | 15 | 15 | 0% | 267 | Not Started
W158 | W158.3230 | DNB Security | Review and Update SPORS | 2025-05-13 | 2025-05-19 | 5 | 5 | 5 | 0% | 142 | Not Started
W158 | W158.2390 | DNB Security | Review and Update SPORS (Enhanced Safety Cases) | 2025-05-13 | 2025-05-19 | 5 | 5 | 5 | 0% | 172 | Not Started
W526 | W526.3170 | HYB DPCS Defueling Support | HYB 2025 LSR Data Export, Analysis, Draft Report | 2025-05-13 | 2025-05-29 | 12 | 12 | 12 | 0% | 1901 | Not Started
W085 | W085.DS1035 | REGION 1 Further Flasks in Readiness | Transport of Final 5 Refurbished Flasks | 2025-05-14 | 2025-08-11 | 63 | 63 | 63 | 0% | 6 | Not Started
W085 | W085.DS20560 | REGION 1 Further Flasks in Readiness | Verify All Parts Ready for Assembly | 2025-05-16 | 2025-05-20 | 1 | 3 | 3 | 0% | 0 | Not Started
W085 | W085.DS21660 | REGION 1 Further Flasks in Readiness | Produce Flask LTQRs (Reduced Duration) | 2025-05-16 | 2025-05-30 | 10 | 10 | 10 | 0% | 7 | Not Started
W085 | W085.DS24870 | REGION 1 Further Flasks in Readiness | Flask 5 - Transport Flask to HNB | 2025-05-16 | 2025-05-16 | 1 | 1 | 1 | 0% | 82 | Not Started
W085 | W085.DS24900 | REGION 1 Further Flasks in Readiness | Flask 6 - Prepare Transport Paperwork | 2025-05-19 | 2025-05-23 | 5 | 5 | 5 | 0% | 76 | Not Started
W085 | W085.DS24990 | REGION 1 Further Flasks in Readiness | Flask 8 - Transport Flask to HNB | 2025-05-19 | 2025-05-19 | 1 | 1 | 1 | 0% | 81 | Not Started
W158 | W158.3240 | DNB Security | Issue Revised SPORS (FEED TO SUMMARY SCHEDULE) | 2025-05-20 | 2025-05-20 | 1 | 1 | 1 | 0% | 142 | Not Started
W158 | W158.2400 | DNB Security | Issue Revised SPORS (Enhanced Safety Cases) | 2025-05-20 | 2025-05-20 | 1 | 1 | 1 | 0% | 172 | Not Started
W158 | W158.3250 | DNB Security | Incorporate New Mitigations | 2025-05-21 | 2025-07-09 | 35 | 35 | 35 | 0% | 142 | Not Started
W158 | W158.34801 | DNB Security | Update Site SRCL & Submit to ONR (Enhanced Safety Cases) | 2025-05-21 | 2025-05-28 | 5 | 5 | 5 | 0% | 172 | Not Started
W085 | W085.DS20570 | REGION 1 Further Flasks in Readiness | Assemble Flask, Deflection and Leak Tests | 2025-05-21 | 2025-06-16 | 2 | 18 | 18 | 0% | 0 | Not Started
W529 | W529.2130 | TOR DPCS Defueling Support | TOR 2025 LSR - Final Report Produced and Issued | 2025-05-21 | 2025-05-28 | 5 | 5 | 5 | 0% | 1929 | Not Started
W085 | W085.DS24910 | REGION 1 Further Flasks in Readiness | Flask 6 - Transport Flask to HNB | 2025-05-27 | 2025-05-27 | 1 | 1 | 1 | 0% | 76 | Not Started
W195 | W195.25430 | HRA DPCS Defueling Support | LSR Pre Data Extract | 2025-05-27 | 2025-06-16 | 15 | 15 | 15 | 0% | 1360 | Not Started
W526 | W526.2130 | HYB DPCS Defueling Support | HYB 2025 LSR - Final Report Produced and Issued | 2025-05-28 | 2025-06-09 | 9 | 9 | 9 | 0% | 1921 | Not Started
W527 | W527.25280 | DNB DPCS Defueling Support | Asset Guardian Licences and Support 2025 - 2026 | 2025-05-28 | 2025-05-28 | 1 | 1 | 1 | 0% | 1673 | Not Started
W195 | W195.25120 | HRA DPCS Defueling Support | TGN097 R2 - Inspection | 2025-05-30 | 2025-06-05 | 5 | 5 | 5 | 0% | 1349 | Not Started
W526 | W526.3180 | HYB DPCS Defueling Support | HYB 2025 Issue Recommendations | 2025-05-30 | 2025-05-30 | 1 | 1 | 1 | 0% | 1901 | Not Started
W193 | W193.25340 | HNB DPCS Defueling Support | Revised Costs Provided | 2025-05-30 | 2025-07-10 | 30 | 30 | 30 | 0% | 31 | Not Started
W085 | W085.DS21670 | REGION 1 Further Flasks in Readiness | Approve Flask LTQRs (Reduce Duration) | 2025-06-02 | 2025-06-13 | 10 | 10 | 10 | 0% | 7 | Not Started
W526 | W526.3190 | HYB DPCS Defueling Support | HYB 2025 Recommendations Workshop | 2025-06-02 | 2025-06-02 | 1 | 1 | 1 | 0% | 1901 | Not Started
W157 | W157.2700 | HYB Security | Draft List of Security changes and proposed MSI Categories | 2025-06-03 | 2025-06-16 | 10 | 10 | 10 | 0% | 393 | Not Started
W157 | W157.2520 | HYB Security | Site SQEP verification and INA review of SPPI File | 2025-06-03 | 2025-06-16 | 10 | 10 | 10 | 0% | 383 | Not Started
W157 | W157.1950 | HYB Security | Undertake Security Vulnerability Assessments on changes to existing and new SPP V1 | 2025-06-03 | 2025-06-23 | 15 | 15 | 15 | 0% | 293 | Not Started
W526 | W526.3200 | HYB DPCS Defueling Support | HYB 2025 LSR Update, Internal Review & Issue to EDF | 2025-06-03 | 2025-06-16 | 10 | 10 | 10 | 0% | 1901 | Not Started
W085 | W085.DS1030 | REGION 1 Further Flasks in Readiness | Transport of First 6 Refurbished Flasks | 2025-06-04 | 2025-08-27 | 60 | 60 | 60 | 0% | 11 | Not Started
W195 | W195.25150 | HRA DPCS Defueling Support | TGN097 R2 - Draft Report Produced, Internal Review and Issue to EDF | 2025-06-06 | 2025-07-03 | 20 | 20 | 20 | 0% | 1349 | Not Started
W195 | W195.1075 | HRA DPCS Defueling Support | HRA 2024 - Installation R1 | 2025-06-10 | 2025-06-30 | 15 | 15 | 15 | 0% | 1397 | Not Started
W196 | W196.6220 | HYA DPCS Defueling Support | HYA 2024 - Installation R1 | 2025-06-10 | 2025-06-30 | 15 | 15 | 15 | 0% | 1397 | Not Started
W085 | W085.1790 | REGION 1 Further Flasks in Readiness | Lid Bolting Exercise (PROVISIONAL) | 2025-06-10 | 2025-06-26 | 1 | 13 | 13 | 0% | 28 | Not Started
W085 | W085.DS22680 | REGION 1 Further Flasks in Readiness | Produce Flask LTQRs (Reduced Duration) | 2025-06-16 | 2025-06-27 | 10 | 10 | 10 | 0% | 7 | Not Started
W085 | W085.DS20580 | REGION 1 Further Flasks in Readiness | Generate Rebuild Report | 2025-06-17 | 2025-06-20 | 5 | 4 | 4 | 0% | 0 | Not Started
W157 | W157.2530 | HYB Security | Revision of SPPI File Folliowing INA Review V1 | 2025-06-17 | 2025-06-23 | 5 | 5 | 5 | 0% | 383 | Not Started
W195 | W195.25440 | HRA DPCS Defueling Support | LSR Data Export, Analysis, Draft Report | 2025-06-17 | 2025-07-07 | 15 | 15 | 15 | 0% | 1360 | Not Started
W526 | W526.3210 | HYB DPCS Defueling Support | HYB 2025 EDF Review | 2025-06-17 | 2025-06-30 | 10 | 10 | 10 | 0% | 1901 | Not Started
W085 | W085.DS20630 | REGION 1 Further Flasks in Readiness | Verify Testing and Approve Report (EDF) | 2025-06-23 | 2025-06-27 | 5 | 5 | 5 | 0% | 0 | Not Started
W157 | W157.2540 | HYB Security | Issue of SPPI File and submit to ONR V1 | 2025-06-24 | 2025-06-30 | 5 | 5 | 5 | 0% | 383 | Not Started
W157 | W157.1960 | HYB Security | Draft SPORs for all changes to existing and new SPP requiring revised or new mitigation measures V1 | 2025-06-24 | 2025-07-21 | 20 | 20 | 20 | 0% | 293 | Not Started
W159 | W159.2020 | TOR Security | Undertake Site assessment of revised Flask Transfer/Storage arrangements | 2025-06-25 | 2025-07-22 | 20 | 20 | 20 | 0% | 346 | Not Started
W085 | W085.DS20640 | REGION 1 Further Flasks in Readiness | Produce Flask LTQRs | 2025-06-30 | 2025-07-11 | 10 | 10 | 10 | 0% | 0 | Not Started
W085 | W085.DS22690 | REGION 1 Further Flasks in Readiness | Approve Flask LTQRs (Reduced Duration) | 2025-06-30 | 2025-07-11 | 10 | 10 | 10 | 0% | 7 | Not Started
W194 | W194.2270 | HPB DPCS Defueling Support | Thales Long Term Support Contract Q3 2025 | 2025-07-01 | 2025-09-30 | 65 | 65 | 65 | 0% | 509 | Not Started
W195 | W195.2280 | HRA DPCS Defueling Support | Thales Long Term Support Contract Q3 2025 | 2025-07-01 | 2025-09-30 | 65 | 65 | 65 | 0% | 1268 | Not Started
W195 | W195.2650 | HRA DPCS Defueling Support | Argus Support Contract 2025 - Jul Q3 | 2025-07-01 | 2025-09-30 | 65 | 65 | 65 | 0% | 1268 | Not Started
W196 | W196.2290 | HYA DPCS Defueling Support | Thales Long Term Support Contract Q3 2025 | 2025-07-01 | 2025-09-30 | 65 | 65 | 65 | 0% | 1332 | Not Started
W196 | W196.2610 | HYA DPCS Defueling Support | Argus Support Contract - 2025 - Q3 | 2025-07-01 | 2025-09-30 | 65 | 65 | 65 | 0% | 1332 | Not Started
W527 | W527.1595 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q3 2025 | 2025-07-01 | 2025-09-30 | 65 | 65 | 65 | 0% | 1585 | Not Started
W527 | W527.1590 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q3 2025 | 2025-07-01 | 2025-09-30 | 65 | 65 | 65 | 0% | 1585 | Not Started
W527 | W527.1592 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q3 2025 | 2025-07-01 | 2025-09-30 | 65 | 65 | 65 | 0% | 1585 | Not Started
W527 | W527.1594 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q3 2025 | 2025-07-01 | 2025-09-30 | 65 | 65 | 65 | 0% | 1585 | Not Started
W529 | W529.1210 | TOR DPCS Defueling Support | TOR Argus Support Contract Q3 | 2025-07-01 | 2025-09-30 | 65 | 65 | 65 | 0% | 1777 | Not Started
W529 | W529.1245 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract Q3 2025 Delivery | 2025-07-01 | 2025-09-30 | 65 | 65 | 65 | 0% | 1777 | Not Started
W526 | W526.1245 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract Q3 2025 | 2025-07-01 | 2025-09-30 | 65 | 65 | 65 | 0% | 1778 | Not Started
W529 | W529.6330 | TOR DPCS Defueling Support | TOR 2025 S13R2 - Specification | 2025-07-01 | 2025-09-19 | 58 | 58 | 58 | 0% | 1736 | Not Started
W526 | W526.3220 | HYB DPCS Defueling Support | HYB 2025 Update LSR | 2025-07-01 | 2025-07-07 | 5 | 5 | 5 | 0% | 1901 | Not Started
W160 | W160.6040 | HNB PSR4 | HNB PSR4 Head Doc: ONR Approval of Safety Case (Letter sent to initiate) EC 374897 <Enter Paper Title Here> ==> KDM | 2025-07-02 | 2025-10-22 | 80 | 80 | 80 | 0% | 1 | Not Started
W195 | W195.25140 | HRA DPCS Defueling Support | TGN097 R2 - EDF Review | 2025-07-04 | 2025-07-17 | 10 | 10 | 10 | 0% | 1349 | Not Started
W195 | W195.25450 | HRA DPCS Defueling Support | Issue Recommendations | 2025-07-08 | 2025-07-08 | 1 | 1 | 1 | 0% | 1360 | Not Started
W193 | W193.25360 | HNB DPCS Defueling Support | Decommission Reference Rig | 2025-07-11 | 2025-08-21 | 30 | 30 | 30 | 0% | 31 | Not Started
W085 | W085.A2410 | REGION 1 Further Flasks in Readiness | Handover of Life Time Records for all Flasks & Spares | 2025-07-14 | 2025-07-25 | 10 | 10 | 10 | 0% | 7 | Not Started
W085 | W085.DS20650 | REGION 1 Further Flasks in Readiness | Approve Flask LTQRs | 2025-07-14 | 2025-07-25 | 10 | 10 | 10 | 0% | 0 | Not Started
W085 | W085.A7280 | REGION 1 Further Flasks in Readiness | Operational Handover with NDA and SL | 2025-07-15 | 2025-08-11 | 20 | 20 | 20 | 0% | 22 | Not Started
W195 | W195.25460 | HRA DPCS Defueling Support | Recommendations Workshop | 2025-07-15 | 2025-07-15 | 1 | 1 | 1 | 0% | 1360 | Not Started
W195 | W195.25470 | HRA DPCS Defueling Support | LSR Update, Internal Review & Issue to EDF | 2025-07-16 | 2025-07-29 | 10 | 10 | 10 | 0% | 1360 | Not Started
W157 | W157.2350 | HYB Security | Issue SPORS V1 | 2025-07-22 | 2025-07-22 | 1 | 1 | 1 | 0% | 362 | Not Started
W157 | W157.2560 | HYB Security | Optioneer potential revised or new mitigations | 2025-07-22 | 2025-08-11 | 15 | 15 | 15 | 0% | 293 | Not Started
W157 | W157.2550 | HYB Security | Review SPPI File V1 Aganist Approved Defuelling Safety case And submit To ONR | 2025-07-23 | 2025-07-29 | 5 | 5 | 5 | 0% | 232 | Not Started
W157 | W157.2370 | HYB Security | Review SPPI File Against Approved Essential Safety Cases | 2025-07-23 | 2025-07-29 | 5 | 5 | 5 | 0% | 231 | Not Started
W157 | W157.2650 | HYB Security | Update Site SRCL V1 | 2025-07-23 | 2025-07-29 | 5 | 5 | 5 | 0% | 362 | Not Started
W159 | W159.2040 | TOR Security | Undertake Security Vulnerability Assessments of Off-site and On-site rail heads and potential storage areas | 2025-07-23 | 2025-08-05 | 10 | 10 | 10 | 0% | 346 | Not Started
W527 | W527.25620 | DNB DPCS Defueling Support | DNB 2025 2.9 - Installation R1 | 2025-07-24 | 2025-08-06 | 10 | 10 | 10 | 0% | 1594 | Not Started
W156 | W156.3230 | HYA Security | Review and Update SPORS | 2025-07-25 | 2025-07-25 | 1 | 1 | 1 | 0% | 583 | Not Started
W085 | W085.A6440 | REGION 1 Further Flasks in Readiness | Final Acceptance of flasks by EDF (HOLD POINT - ONR MOD) | 2025-07-28 | 2025-08-01 | 5 | 5 | 5 | 0% | 9 | Not Started
W085 | W085.DS25000 | REGION 1 Further Flasks in Readiness | Flask 9 - Flask Licensing Prepare Cat C Mod | 2025-07-28 | 2025-08-01 | 5 | 5 | 5 | 0% | 0 | Not Started
W156 | W156.3240 | HYA Security | Issue revised SPORS | 2025-07-28 | 2025-07-28 | 1 | 1 | 1 | 0% | 583 | Not Started
W085 | W085.A1440 | REGION 1 Further Flasks in Readiness | Gate D PRC Paper Preparation [FEEDS TO SUMMARY SCHEDULE] | 2025-07-29 | 2025-08-11 | 10 | 10 | 10 | 0% | 6 | Not Started
W156 | W156.3250 | HYA Security | Incoporate New Mitigations | 2025-07-29 | 2025-07-29 | 1 | 1 | 1 | 0% | 583 | Not Started
W157 | W157.2410 | HYB Security | Review SVAs (Final) | 2025-07-30 | 2025-08-05 | 5 | 5 | 5 | 0% | 351 | Not Started
W157 | W157.2440 | HYB Security | Submit Final Defuelling SPPI File to ONR | 2025-07-30 | 2025-07-30 | 1 | 1 | 1 | 0% | 231 | Not Started
W157 | W157.2490 | HYB Security | Draft DNSSP And Sumit To ONR | 2025-07-30 | 2025-08-05 | 5 | 5 | 5 | 0% | 347 | Not Started
W195 | W195.25480 | HRA DPCS Defueling Support | EDF Review | 2025-07-30 | 2025-08-12 | 10 | 10 | 10 | 0% | 1360 | Not Started
W157 | W157.3630 | HYB Security | ONR acknowledgement of SPPI File Final | 2025-07-31 | 2025-08-28 | 20 | 20 | 20 | 0% | 231 | Not Started
W529 | W529.7570 | TOR DPCS Defueling Support | TGN097 R2 - Inspection | 2025-08-01 | 2025-08-07 | 5 | 5 | 5 | 0% | 1857 | Not Started
W085 | W085.DS25260 | REGION 1 Further Flasks in Readiness | Flask 9 - Flask Licensing Verification Cat C Mod | 2025-08-04 | 2025-08-12 | 5 | 7 | 7 | 0% | 0 | Not Started
W160 | W160.9630 | HNB PSR4 | HNB PSR3 Extension EC: Review NSRS for Completeness | 2025-08-04 | 2025-08-04 | 1 | 1 | 1 | 0% | -248 | Not Started
W161 | W161.9620 | HPB PSR4 | HPB PSR3 Extension EC: Review NSRS for Completeness | 2025-08-04 | 2025-08-04 | 1 | 1 | 1 | 0% | -252 | Not Started
W160 | W160.9640 | HNB PSR4 | HNB PSR3 Extension EC: Author Up-Rev of PSR3 Extension EC | 2025-08-05 | 2025-08-18 | 10 | 10 | 10 | 0% | -248 | Not Started
W161 | W161.9630 | HPB PSR4 | HPB PSR3 Extension EC: Author Up-Rev of PSR3 Extension EC | 2025-08-05 | 2025-08-18 | 10 | 10 | 10 | 0% | -252 | Not Started
W157 | W157.2420 | HYB Security | Review SPORs (Final) | 2025-08-06 | 2025-08-12 | 5 | 5 | 5 | 0% | 351 | Not Started
W159 | W159.1990 | TOR Security | Undertake assessment of potential impacts on existing TSS/TSP in respect of increased Flask movements | 2025-08-06 | 2025-08-19 | 10 | 10 | 10 | 0% | 346 | Not Started
W085 | W085.A6210 | REGION 1 Further Flasks in Readiness | Flask Collection from contractor / Delivery to Storage Location / Final Handover to EDF | 2025-08-07 | 2025-08-11 | 3 | 3 | 3 | 0% | 6 | Not Started
W085 | W085.A4430 | REGION 1 Further Flasks in Readiness | Gate C-D Flask Storage - Cost Summary | 2025-08-07 | 2025-09-04 | 24 | 20 | 20 | 0% | 6 | Not Started
W529 | W529.7580 | TOR DPCS Defueling Support | TGN097 R2 - Draft Report Produced, Internal Review and Issue to EDF | 2025-08-08 | 2025-08-21 | 10 | 10 | 10 | 0% | 1857 | Not Started
W085 | W085.A1450 | REGION 1 Further Flasks in Readiness | Internal L&T Review | 2025-08-12 | 2025-09-02 | 1 | 15 | 15 | 0% | 6 | Not Started
W157 | W157.2710 | HYB Security | Review and Agree Security Changes and MSI Category (INA, SPB, NSC) | 2025-08-12 | 2025-09-23 | 30 | 30 | 30 | 0% | 323 | Not Started
W157 | W157.2570 | HYB Security | Complete MSI process | 2025-08-12 | 2025-09-23 | 30 | 30 | 30 | 0% | 293 | Not Started
W085 | W085.DS25270 | REGION 1 Further Flasks in Readiness | Flask 9 - Flask Licensing CO Review Cat C Mod | 2025-08-13 | 2025-08-22 | 5 | 8 | 8 | 0% | 0 | Not Started
W157 | W157.2430 | HYB Security | Update SRCL (Final) | 2025-08-13 | 2025-08-13 | 1 | 1 | 1 | 0% | 351 | Not Started
W195 | W195.25490 | HRA DPCS Defueling Support | Update LSR | 2025-08-13 | 2025-08-19 | 5 | 5 | 5 | 0% | 1360 | Not Started
W161 | W161.8700 | HPB PSR4 | HPB PSR3 Extension EC: Verification of the Submission (using BARRIER MODEL) | 2025-08-19 | 2025-09-02 | 10 | 10 | 10 | 0% | -252 | Not Started
W161 | W161.8970 | HPB PSR4 | HPB PSR3 Extension EC: Issue Document to NRS for comment | 2025-08-19 | 2025-08-26 | 5 | 5 | 5 | 0% | -243 | Not Started
W160 | W160.9470 | HNB PSR4 | ## HNB PSR3 Extension EC: Key Stakeholders Engagement - Cost Summary ## | 2025-08-19 | 2025-10-01 | 31 | 31 | 31 | 0% | -248 | Not Started
W160 | W160.8970 | HNB PSR4 | HNB PSR3 Extension EC: Issue Document to NRS for comment | 2025-08-19 | 2025-08-26 | 5 | 5 | 5 | 0% | -248 | Not Started
W160 | W160.8700 | HNB PSR4 | HNB PSR3 Extension EC: Verification of the Submission (using BARRIER MODEL) | 2025-08-19 | 2025-08-26 | 5 | 5 | 5 | 0% | -248 | Not Started
W159 | W159.2000 | TOR Security | Submit Revised TSS/TSP To ONR | 2025-08-20 | 2025-08-20 | 1 | 1 | 1 | 0% | 346 | Not Started
W195 | W195.25500 | HRA DPCS Defueling Support | Issue Complete LSR | 2025-08-20 | 2025-08-20 | 1 | 1 | 1 | 0% | 1360 | Not Started
W159 | W159.2010 | TOR Security | ONR Approval Of Revised TSS/TSP | 2025-08-21 | 2025-09-18 | 20 | 20 | 20 | 0% | 346 | Not Started
W195 | W195.25130 | HRA DPCS Defueling Support | TGN097 R2 - Report Issue | 2025-08-22 | 2025-09-05 | 10 | 10 | 10 | 0% | 1349 | Not Started
W529 | W529.7590 | TOR DPCS Defueling Support | TGN097 R2 - EDF Review | 2025-08-22 | 2025-09-05 | 10 | 10 | 10 | 0% | 1857 | Not Started
W193 | W193.25370 | HNB DPCS Defueling Support | Redistribute Assets | 2025-08-22 | 2025-10-03 | 30 | 30 | 30 | 0% | 31 | Not Started
W085 | W085.DS25010 | REGION 1 Further Flasks in Readiness | Flask 9 - Flask Licensing INA Approval of Cat C | 2025-08-26 | 2025-09-08 | 10 | 10 | 10 | 0% | 0 | Not Started
W161 | W161.8980 | HPB PSR4 | HPB PSR3 Extension EC: NRS Comments | 2025-08-27 | 2025-09-02 | 5 | 5 | 5 | 0% | -243 | Not Started
W160 | W160.8980 | HNB PSR4 | HNB PSR3 Extension EC: NRS Comments | 2025-08-27 | 2025-09-02 | 5 | 5 | 5 | 0% | -248 | Not Started
W160 | W160.8720 | HNB PSR4 | HNB PSR3 Extension EC: Address Verifier Comments | 2025-08-27 | 2025-08-28 | 2 | 2 | 2 | 0% | -244 | Not Started
W157 | W157.24500 | HYB Security | Sign Station Defuelling QP- Ready to Implement Defuelling Security Regime | 2025-08-29 | 2025-09-25 | 20 | 20 | 20 | 0% | 231 | Not Started
W157 | W157.2500 | HYB Security | ONR Approval of Draft DNSSP | 2025-08-29 | 2025-09-11 | 10 | 10 | 10 | 0% | 331 | Not Started
W161 | W161.8180 | HPB PSR4 | HPB PSR Head Doc: Upload Submission Proposal to AMS | 2025-08-29 | 2025-09-04 | 5 | 5 | 5 | 0% | -66 | Not Started
W160 | W160.9490 | HNB PSR4 | ## HNB PSR3 Extension EC: Clearances and Closeout - Cost Summary ## | 2025-08-29 | 2025-12-23 | 83 | 83 | 83 | 0% | 4 | Not Started
W160 | W160.8620 | HNB PSR4 | HNB PSR3 Extension EC: Prepare Station Director's Brief | 2025-08-29 | 2025-09-04 | 5 | 5 | 5 | 0% | 67 | Not Started
W155 | W155.3220 | HRA Security | Final ONR review of D/SPPI | 2025-09-01 | 2025-11-21 | 60 | 60 | 60 | 0% | 280 | Not Started
W155 | W155.3330 | HRA Security | Draft DNSSP And Sumbit To ONR | 2025-09-01 | 2025-12-19 | 80 | 80 | 80 | 0% | 225 | Not Started
W156 | W156.3120 | HYA Security | Draft DNSSP | 2025-09-01 | 2025-12-19 | 80 | 80 | 80 | 0% | 466 | Not Started
W157 | W157.1980 | HYB Security | Draft Site specific Flask Transport Impact initial assessment template | 2025-09-02 | 2025-09-02 | 1 | 1 | 1 | 0% | 297 | Not Started
W085 | W085.A1460 | REGION 1 Further Flasks in Readiness | Gate D PRC Paper Submission | 2025-09-03 | 2025-09-03 | 1 | 1 | 1 | 0% | 6 | Not Started
W157 | W157.2020 | HYB Security | Undertake Site assessment of revised Flask Transfer/Storage arrangements | 2025-09-03 | 2025-09-30 | 20 | 20 | 20 | 0% | 297 | Not Started
W157 | W157.1990 | HYB Security | Undertake assessment of potential impacts on existing TSS/TSP in respect of increased Flask movements | 2025-09-03 | 2025-10-28 | 40 | 40 | 40 | 0% | 298 | Not Started
W161 | W161.8720 | HPB PSR4 | HPB PSR3 Extension EC: Address Verifier Comments | 2025-09-03 | 2025-09-09 | 5 | 5 | 5 | 0% | -252 | Not Started
W161 | W161.8990 | HPB PSR4 | HPB PSR3 Extension EC: NRS Comments Addressed | 2025-09-03 | 2025-09-09 | 5 | 5 | 5 | 0% | -243 | Not Started
W160 | W160.8990 | HNB PSR4 | HNB PSR3 Extension EC: NRS Comments Addressed | 2025-09-03 | 2025-09-09 | 5 | 5 | 5 | 0% | -248 | Not Started
W085 | W085.A1470 | REGION 1 Further Flasks in Readiness | Gate D PRC Review | 2025-09-03 | 2025-09-04 | 1 | 1 | 1 | 0% | 6 | Not Started
W085 | W085.DS25020 | REGION 1 Further Flasks in Readiness | Flask 9 - Prepare Transport Paperwork | 2025-09-04 | 2025-09-10 | 5 | 5 | 5 | 0% | 0 | Not Started
W527 | W527.25630 | DNB DPCS Defueling Support | DNB 2025 2.9 - Installation R2 | 2025-09-04 | 2025-09-17 | 10 | 10 | 10 | 0% | 1594 | Not Started
W161 | W161.5810 | HPB PSR4 | HPB PSR4 Head Doc: Produce and Approve Verification Plan | 2025-09-05 | 2025-09-11 | 5 | 5 | 5 | 0% | -66 | Not Started
W529 | W529.7600 | TOR DPCS Defueling Support | TGN097 R2 - Update and Issue Report | 2025-09-08 | 2025-09-08 | 1 | 1 | 1 | 0% | 1857 | Not Started
W195 | W195.25590 | HRA DPCS Defueling Support | HRA 2024 - Installation R2 | 2025-09-10 | 2025-09-30 | 15 | 15 | 15 | 0% | 1332 | Not Started
W196 | W196.25410 | HYA DPCS Defueling Support | HYA 2024 - Installation R2 | 2025-09-10 | 2025-09-30 | 15 | 15 | 15 | 0% | 1332 | Not Started
W161 | W161.8620 | HPB PSR4 | HPB PSR3 Extension EC: Prepare Station Director's Brief | 2025-09-10 | 2025-09-16 | 5 | 5 | 5 | 0% | 212 | Not Started
W161 | W161.9010 | HPB PSR4 | HPB PSR3 Extension EC: Issue for PRWG (Allow 5d) | 2025-09-10 | 2025-09-16 | 5 | 5 | 5 | 0% | -243 | Not Started
W161 | W161.9490 | HPB PSR4 | ## HPB PSR3 Extension EC: Clearances and Closeout - Cost Summary ## | 2025-09-10 | 2026-05-21 | 176 | 176 | 176 | 0% | 157 | Not Started
W160 | W160.9000 | HNB PSR4 | HNB PSR3 Extension EC: TR Complete | 2025-09-10 | 2025-09-16 | 5 | 5 | 5 | 0% | -248 | Not Started
W085 | W085.DS25030 | REGION 1 Further Flasks in Readiness | Flask 9 - Transport Flask to HNB | 2025-09-11 | 2025-09-11 | 1 | 1 | 1 | 0% | 0 | Not Started
W161 | W161.8190 | HPB PSR4 | HPB PSR4 Head Doc: PJB Verifier | 2025-09-12 | 2025-09-16 | 3 | 3 | 3 | 0% | -66 | Not Started
W161 | W161.9370 | HPB PSR4 | ## HPB PSR4 Head Doc: Verification - Cost Summary ## | 2025-09-12 | 2025-11-07 | 41 | 41 | 41 | 0% | -58 | Not Started
W161 | W161.5870 | HPB PSR4 | HPB PSR4 Head Doc:Verification of the Submission (using BARRIER MODEL) | 2025-09-17 | 2025-10-14 | 20 | 20 | 20 | 0% | -66 | Not Started
W161 | W161.9020 | HPB PSR4 | HPB PSR3 Extension EC: PRWG Meeting for Head Doc | 2025-09-17 | 2025-09-17 | 1 | 1 | 1 | 0% | -243 | Not Started
W160 | W160.9010 | HNB PSR4 | HNB PSR3 Extension EC: Issue for PRWG (Allow 5d) | 2025-09-17 | 2025-09-23 | 5 | 5 | 5 | 0% | -248 | Not Started
W161 | W161.9030 | HPB PSR4 | HPB PSR3 Extension EC: PRWG Comments Addressed | 2025-09-18 | 2025-09-24 | 5 | 5 | 5 | 0% | -243 | Not Started
W529 | W529.6340 | TOR DPCS Defueling Support | TOR 2025 S13R2 - Testing | 2025-09-22 | 2025-12-12 | 60 | 60 | 60 | 0% | 1736 | Not Started
W157 | W157.2590 | HYB Security | Implement temp. infrastructure and org mitigations required to enable commencement of defuelling (FEEDS TO SUMMARY SCHE) | 2025-09-24 | 2025-11-04 | 30 | 30 | 30 | 0% | 293 | Not Started
W160 | W160.9020 | HNB PSR4 | HNB PSR3 Extension EC: PRWG Meeting for Head Doc | 2025-09-24 | 2025-09-24 | 1 | 1 | 1 | 0% | -248 | Not Started
W160 | W160.9030 | HNB PSR4 | HNB PSR3 Extension EC: PRWG Comments Addressed | 2025-09-25 | 2025-10-01 | 5 | 5 | 5 | 0% | -248 | Not Started
W194 | W194.2260 | HPB DPCS Defueling Support | Thales Long Term Support Contract Q4 2025 | 2025-10-01 | 2025-12-31 | 64 | 64 | 64 | 0% | 509 | Not Started
W195 | W195.2290 | HRA DPCS Defueling Support | Thales Long Term Support Contract Q4 2025 | 2025-10-01 | 2025-12-31 | 64 | 64 | 64 | 0% | 1268 | Not Started
W195 | W195.2660 | HRA DPCS Defueling Support | Argus Support Contract 2025 - Oct Q4 | 2025-10-01 | 2025-12-31 | 64 | 64 | 64 | 0% | 1268 | Not Started
W196 | W196.2300 | HYA DPCS Defueling Support | Thales Long Term Support Contract Q4 2025 | 2025-10-01 | 2025-12-31 | 64 | 64 | 64 | 0% | 1268 | Not Started
W196 | W196.2620 | HYA DPCS Defueling Support | Argus Support Contract - 2025 - Q4 | 2025-10-01 | 2025-12-31 | 64 | 64 | 64 | 0% | 1268 | Not Started
W527 | W527.1625 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q4 2025 | 2025-10-01 | 2025-12-31 | 64 | 64 | 64 | 0% | 1521 | Not Started
W527 | W527.1620 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q4 2025 | 2025-10-01 | 2025-12-31 | 64 | 64 | 64 | 0% | 1521 | Not Started
W527 | W527.1623 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q4 2025 | 2025-10-01 | 2025-12-31 | 64 | 64 | 64 | 0% | 1521 | Not Started
W527 | W527.1624 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q4 2025 | 2025-10-01 | 2025-12-31 | 64 | 64 | 64 | 0% | 1521 | Not Started
W529 | W529.1215 | TOR DPCS Defueling Support | TOR Argus Support Contract Q4 | 2025-10-01 | 2025-12-31 | 64 | 64 | 64 | 0% | 1777 | Not Started
W529 | W529.1255 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract Q4 2025 Delivery | 2025-10-01 | 2025-12-31 | 64 | 64 | 64 | 0% | 1777 | Not Started
W526 | W526.1255 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract Q4 2025 | 2025-10-01 | 2025-12-30 | 63 | 63 | 63 | 0% | 1778 | Not Started
W157 | W157.2040 | HYB Security | Submit Proprosed Changes To TSS/TSP To ONR | 2025-10-01 | 2025-10-01 | 1 | 1 | 1 | 0% | 297 | Not Started
W159 | W159.2550 | TOR Security | Review SPPI File V1 Aganist Approved Defuelling Safety case And submit To ONR (Not Required if SC is Delivered on Time) | 2025-10-01 | 2025-10-07 | 5 | 5 | 5 | 0% | 333 | Not Started
W159 | W159.1930 | TOR Security | Undertake Site assessment of defuelling impacts on existing and new SPP and resources | 2025-10-01 | 2025-10-07 | 5 | 5 | 5 | 0% | 127 | Not Started
W157 | W157.2050 | HYB Security | ONR Approval Of Any changes To TSS/TSP | 2025-10-02 | 2025-10-29 | 20 | 20 | 20 | 0% | 297 | Not Started
W160 | W160.9480 | HNB PSR4 | ## HNB PSR3 Extension EC: INSA & NSC Meeting Readiness - Cost Summary ## | 2025-10-02 | 2025-12-03 | 44 | 44 | 44 | 0% | 1 | Not Started
W160 | W160.8690 | HNB PSR4 | HNB PSR3 Extension EC: INSA review & iteration of comments (using BARRIER MODEL) | 2025-10-02 | 2025-10-29 | 20 | 20 | 20 | 0% | -248 | Not Started
W194 | W194.25120 | HPB DPCS Defueling Support | TGN097 R3 - Inspection | 2025-10-03 | 2025-10-09 | 5 | 5 | 5 | 0% | 546 | Not Started
W527 | W527.25700 | DNB DPCS Defueling Support | DNB 2026 2.10 - Testing | 2025-10-06 | 2025-11-14 | 30 | 30 | 30 | 0% | 1404 | Not Started
W193 | W193.25380 | HNB DPCS Defueling Support | Disposal of Assets | 2025-10-06 | 2025-11-14 | 30 | 30 | 30 | 0% | 31 | Not Started
W159 | W159.1940 | TOR Security | Write up Defuelling SPPI file V1 | 2025-10-08 | 2025-10-28 | 15 | 15 | 15 | 0% | 127 | Not Started
W161 | W161.8690 | HPB PSR4 | HPB PSR3 Extension EC: INSA review & iteration of comments (using BARRIER MODEL) | 2025-10-08 | 2025-11-04 | 20 | 20 | 20 | 0% | -252 | Not Started
W161 | W161.9480 | HPB PSR4 | ## HPB PSR3 Extension EC: INSA & NSC Meeting Readiness - Cost Summary ## | 2025-10-08 | 2025-12-03 | 40 | 40 | 40 | 0% | 157 | Not Started
W196 | W196.6330 | HYA DPCS Defueling Support | HYA 2025 - Consolidation and Testing | 2025-10-09 | 2026-03-30 | 120 | 120 | 120 | 0% | 1206 | Not Started
W194 | W194.25150 | HPB DPCS Defueling Support | TGN097 R3 - Draft Report Produced, Internal Review and Issue to EDF | 2025-10-10 | 2025-10-16 | 5 | 5 | 5 | 0% | 546 | Not Started
W161 | W161.5900 | HPB PSR4 | HPB PSR4 Head Doc: Address Verifier Comments | 2025-10-15 | 2025-10-24 | 8 | 8 | 8 | 0% | -58 | Not Started
W161 | W161.8200 | HPB PSR4 | HPB PSR4 Head Doc: Issue Document to NRS for comment | 2025-10-15 | 2025-10-21 | 5 | 5 | 5 | 0% | -66 | Not Started
W161 | W161.9400 | HPB PSR4 | ## HPB PSR4 Head Doc: Key Stakeholders Engagement - Cost Summary ## | 2025-10-15 | 2025-11-19 | 26 | 26 | 26 | 0% | -66 | Not Started
W194 | W194.25140 | HPB DPCS Defueling Support | TGN097 R3 - EDF Review | 2025-10-17 | 2025-10-30 | 10 | 10 | 10 | 0% | 546 | Not Started
W161 | W161.8210 | HPB PSR4 | HPB PSR4 Head Doc: NRS Comments | 2025-10-22 | 2025-10-28 | 5 | 5 | 5 | 0% | -66 | Not Started
W160 | W160.6070 | HNB PSR4 | HNB PSR4 Head Doc: Revise all Affected Drawings and Documents for EC Approval | 2025-10-23 | 2025-11-05 | 10 | 10 | 10 | 0% | 1 | Not Started
W161 | W161.9540 | HPB PSR4 | HPB PSR4 Head Doc: Verification Schedule Risk - (Risk Ref 38853) | 2025-10-27 | 2025-10-31 | 5 | 5 | 5 | 0% | -58 | Not Started
W159 | W159.1950 | TOR Security | Undertake Security Vulnerability Assessments on changes to existing and new SPP V1 | 2025-10-29 | 2025-11-18 | 15 | 15 | 15 | 0% | 127 | Not Started
W159 | W159.2440 | TOR Security | Submit Defuelling SPPI File to ONR | 2025-10-29 | 2025-10-29 | 1 | 1 | 1 | 0% | 302 | Not Started
W161 | W161.8220 | HPB PSR4 | HPB PSR4 Head Doc: NRS Comments Addressed | 2025-10-29 | 2025-11-04 | 5 | 5 | 5 | 0% | -66 | Not Started
W159 | W159.2490 | TOR Security | Draft DNSSP And Sumit To ONR | 2025-10-30 | 2025-11-05 | 5 | 5 | 5 | 0% | 302 | Not Started
W160 | W160.8630 | HNB PSR4 | HNB PSR3 Extension EC: Incorporate INSA comments | 2025-10-30 | 2025-11-05 | 5 | 5 | 5 | 0% | -248 | Not Started
W194 | W194.25130 | HPB DPCS Defueling Support | TGN097 R3 - Update and Issue Report | 2025-10-31 | 2025-11-06 | 5 | 5 | 5 | 0% | 546 | Not Started
W196 | W196.6360 | HYA DPCS Defueling Support | HYA 2025 - Specification | 2025-11-03 | 2025-12-12 | 30 | 30 | 30 | 0% | 1278 | Not Started
W195 | W195.25620 | HRA DPCS Defueling Support | HRA 2025 - Specification | 2025-11-03 | 2025-12-12 | 30 | 30 | 30 | 0% | 1175 | Not Started
W161 | W161.5920 | HPB PSR4 | HPB PSR4 Head Doc: Final Verification | 2025-11-03 | 2025-11-07 | 5 | 5 | 5 | 0% | -58 | Not Started
W157 | W157.2600 | HYB Security | Implement permanent infrastructure and organisational mitigations | 2025-11-05 | 2025-12-16 | 30 | 30 | 30 | 0% | 243 | Not Started
W161 | W161.8230 | HPB PSR4 | HPB PSR4 Head Doc: TR Complete (No Longer Required) | 2025-11-05 | 2025-11-05 | 0 | 0 | 0 | 0% | -66 | Not Started
W161 | W161.8240 | HPB PSR4 | HPB PSR4 Head Doc: Issue for PRWG (Allow 5d) | 2025-11-05 | 2025-11-11 | 5 | 5 | 5 | 0% | -66 | Not Started
W161 | W161.8630 | HPB PSR4 | HPB PSR3 Extension EC: Incorporate INSA comments | 2025-11-05 | 2025-11-11 | 5 | 5 | 5 | 0% | -252 | Not Started
W159 | W159.2500 | TOR Security | ONR Approval of Draft DNSSP | 2025-11-06 | 2025-11-19 | 10 | 10 | 10 | 0% | 302 | Not Started
W160 | W160.6080 | HNB PSR4 | HNB PSR4 Head Doc: Develop Implementation & closeout Plan | 2025-11-06 | 2025-11-17 | 8 | 8 | 8 | 0% | 1 | Not Started
W161 | W161.6010 | HPB PSR4 | HPB PSR4 Head Doc: Prepare Station Director's Brief | 2025-11-10 | 2025-11-14 | 5 | 5 | 5 | 0% | 142 | Not Started
W161 | W161.9420 | HPB PSR4 | ## HPB PSR4 Head Doc: Clearances and Closeout - Cost Summary ## | 2025-11-10 | 2026-06-29 | 159 | 159 | 159 | 0% | 131 | Not Started
W161 | W161.8250 | HPB PSR4 | HPB PSR4 Head Doc: PRWG Meeting for Head Doc | 2025-11-12 | 2025-11-12 | 1 | 1 | 1 | 0% | -66 | Not Started
W161 | W161.8260 | HPB PSR4 | HPB PSR4 Head Doc: PRWG Comments Addressed | 2025-11-13 | 2025-11-19 | 5 | 5 | 5 | 0% | -66 | Not Started
W160 | W160.6090 | HNB PSR4 | HNB PSR4 Head Doc: Post Job Debrief (CAT 2) | 2025-11-18 | 2025-11-18 | 1 | 1 | 1 | 0% | 1 | Not Started
W159 | W159.1960 | TOR Security | Draft SPORs for all changes to existing and new SPP requiring revised or new mitigation measures V1 | 2025-11-19 | 2025-12-16 | 20 | 20 | 20 | 0% | 127 | Not Started
W160 | W160.2100 | HNB PSR4 | Hold Project Closeout and Lessons Learned Meeting | 2025-11-19 | 2025-11-19 | 1 | 1 | 1 | 0% | 1 | Not Started
W161 | W161.5970 | HPB PSR4 | HPB PSR4 Head Doc: HPB PSR4 Head Doc: INSA review & iteration of comments (using BARRIER MODEL) | 2025-11-20 | 2025-12-17 | 20 | 20 | 20 | 0% | -66 | Not Started
W161 | W161.9410 | HPB PSR4 | ## HPB PSR4 Head Doc: INSA & NSC Meeting Readiness - Cost Summary ## | 2025-11-20 | 2026-01-19 | 40 | 40 | 40 | 0% | 99 | Not Started
W160 | W160.2110 | HNB PSR4 | Produce Lessons Learned Report | 2025-11-20 | 2025-11-20 | 1 | 1 | 1 | 0% | 1 | Not Started
W160 | W160.2120 | HNB PSR4 | Produce Project Closeout Report | 2025-11-21 | 2025-11-24 | 2 | 2 | 2 | 0% | 1 | Not Started
W527 | W527.25710 | DNB DPCS Defueling Support | DNB 2026 2.10 - Delivery | 2025-11-24 | 2025-12-19 | 20 | 20 | 20 | 0% | 1404 | Not Started
W160 | W160.2130 | HNB PSR4 | Prepare Gate D PRC Paper | 2025-11-25 | 2025-12-01 | 5 | 5 | 5 | 0% | 1 | Not Started
W161 | W161.8650 | HPB PSR4 | HPB PSR3 Extension EC: NSC Consideration & advice to Station Director ==> KDM | 2025-12-03 | 2025-12-16 | 10 | 10 | 10 | 0% | 157 | Not Started
W160 | W160.8650 | HNB PSR4 | HNB PSR3 Extension EC: NSC Consideration & advice to Station Director ==> KDM | 2025-12-03 | 2025-12-16 | 10 | 10 | 10 | 0% | 4 | Not Started
W160 | W160.2140 | HNB PSR4 | Gate D PRC Paper Submission | 2025-12-03 | 2025-12-03 | 1 | 1 | 1 | 0% | 0 | Not Started
W529 | W529.6350 | TOR DPCS Defueling Support | TOR 2025 S13R2 - Delivery | 2025-12-15 | 2026-01-09 | 17 | 17 | 17 | 0% | 1736 | Not Started
W160 | W160.2150 | HNB PSR4 | Gate D - Hold PRC Meeting | 2025-12-16 | 2025-12-16 | 1 | 1 | 1 | 0% | 0 | Not Started
W159 | W159.2350 | TOR Security | Issue SPORS V1 | 2025-12-17 | 2025-12-17 | 1 | 1 | 1 | 0% | 127 | Not Started
W159 | W159.2710 | TOR Security | Review and Agree Security Changes and MSI Category (INA, SPB, NSC) | 2025-12-17 | 2026-01-30 | 30 | 30 | 30 | 0% | 193 | Not Started
W159 | W159.2570 | TOR Security | Complete MSI process | 2025-12-17 | 2026-01-30 | 30 | 30 | 30 | 0% | 193 | Not Started
W161 | W161.8920 | HPB PSR4 | HPB PSR3 Extension EC: Prepare Paper for Submission to ONR | 2025-12-17 | 2026-01-16 | 20 | 20 | 20 | 0% | 157 | Not Started
W160 | W160.8920 | HNB PSR4 | HNB PSR3 Extension EC: Prepare Paper for Submission to ONR | 2025-12-17 | 2025-12-17 | 1 | 1 | 1 | 0% | 4 | Not Started
W159 | W159.2650 | TOR Security | Update Site SRCL And Sumbit To ONR V1 | 2025-12-18 | 2025-12-24 | 5 | 5 | 5 | 0% | 127 | Not Started
W161 | W161.5980 | HPB PSR4 | HPB PSR4 Head Doc: Incorporate INSA comments | 2025-12-18 | 2025-12-24 | 5 | 5 | 5 | 0% | -66 | Not Started
W160 | W160.8570 | HNB PSR4 | HNB PSR3 Extension EC: ONR Approval of Safety Case (Letter sent to initiate) EC 375144 <Enter Paper Title Here> ==> KDM | 2025-12-18 | 2025-12-18 | 1 | 1 | 1 | 0% | 4 | Not Started
W160 | W160.8540 | HNB PSR4 | HNB PSR3 Extension EC: Revise all Affected Drawings and Documents for EC Approval | 2025-12-19 | 2025-12-19 | 1 | 1 | 1 | 0% | 4 | Not Started
W155 | W155.3310 | HRA Security | ONR Approval of Defuelling NSSP | 2025-12-22 | 2026-01-21 | 20 | 20 | 20 | 0% | 225 | Not Started
W156 | W156.3310 | HYA Security | ONR approval of DNSSP | 2025-12-22 | 2026-01-14 | 15 | 15 | 15 | 0% | 466 | Not Started
W160 | W160.8510 | HNB PSR4 | HNB PSR3 Extension EC: Develop Implementation & closeout Plan | 2025-12-22 | 2025-12-22 | 1 | 1 | 1 | 0% | 4 | Not Started
W160 | W160.8590 | HNB PSR4 | HNB PSR3 Extension EC: Post Job Debrief (CAT 2) | 2025-12-23 | 2025-12-23 | 1 | 1 | 1 | 0% | 4 | Not Started
W159 | W159.24500 | TOR Security | Sign Station Defuelling QP- Ready to Implement Defuelling Security Regime | 2025-12-29 | 2025-12-29 | 0 | 0 | 0 | 0% | 127 | Not Started
W195 | W195.2300 | HRA DPCS Defueling Support | HRA PES Group Support - 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 1014 | Not Started
W195 | W195.2310 | HRA DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 1014 | Not Started
W195 | W195.2380 | HRA DPCS Defueling Support | Thales Long Term Support Contract Q1 2026 | 2026-01-02 | 2026-03-31 | 63 | 63 | 63 | 0% | 1014 | Not Started
W196 | W196.2310 | HYA DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 1014 | Not Started
W196 | W196.2320 | HYA DPCS Defueling Support | HYA PES Group Support - 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 1014 | Not Started
W196 | W196.2390 | HYA DPCS Defueling Support | Thales Long Term Support Contract Q1 2026 | 2026-01-02 | 2026-03-31 | 63 | 63 | 63 | 0% | 1014 | Not Started
W529 | W529.1060 | TOR DPCS Defueling Support | TOR PES Group Support - 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 1523 | Not Started
W529 | W529.1070 | TOR DPCS Defueling Support | TOR Plant Control Systems & Simulators (PCS&S) Group - 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 1523 | Not Started
W529 | W529.1265 | TOR DPCS Defueling Support | TOR Argus Support Contract - Q1 2026 | 2026-01-02 | 2026-03-31 | 63 | 63 | 63 | 0% | 1523 | Not Started
W529 | W529.1275 | TOR DPCS Defueling Support | TOR Argus Support Contract - Q2 2026 | 2026-01-02 | 2026-03-31 | 63 | 63 | 63 | 0% | 1584 | Not Started
W529 | W529.1285 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q1 2026 | 2026-01-02 | 2026-03-31 | 63 | 63 | 63 | 0% | 1523 | Not Started
W529 | W529.4550 | TOR DPCS Defueling Support | TOR 2026 LSR - Pre-export Data Validation Produced and Completed | 2026-01-02 | 2026-02-24 | 38 | 38 | 38 | 0% | 1668 | Not Started
W526 | W526.4550 | HYB DPCS Defueling Support | HYB 2026 LSR - Pre-export Data Validation Produced and Completed | 2026-01-02 | 2026-02-24 | 38 | 38 | 38 | 0% | 1668 | Not Started
W526 | W526.3030 | HYB DPCS Defueling Support | HYB DPCS Long Term Support Contract 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 1523 | Not Started
W526 | W526.3020 | HYB DPCS Defueling Support | HYB 2026 Defueling Software Build | 2026-01-02 | 2026-11-30 | 232 | 232 | 232 | 0% | 1545 | Not Started
W526 | W526.1285 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q1 2026 | 2026-01-02 | 2026-03-31 | 63 | 63 | 63 | 0% | 1523 | Not Started
W526 | W526.1265 | HYB DPCS Defueling Support | HYB Argus Support Contract - Q1 2026 | 2026-01-02 | 2026-03-31 | 63 | 63 | 63 | 0% | 1523 | Not Started
W526 | W526.1070 | HYB DPCS Defueling Support | HYB Plant Control Systems & Simulators (PCS&S) Group - 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 1523 | Not Started
W526 | W526.1060 | HYB DPCS Defueling Support | HYB PES Group Support - 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 1523 | Not Started
W529 | W529.6370 | TOR DPCS Defueling Support | TOR 2025 S14R1 - Software Build Requirement | 2026-01-02 | 2026-06-30 | 124 | 124 | 124 | 0% | 1387 | Not Started
W527 | W527.25240 | DNB DPCS Defueling Support | ETC 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 0 | Not Started
W526 | W526.10010 | HYB DPCS Defueling Support | HYB 2026 External Costs | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 1523 | Not Started
W529 | W529.10010 | TOR DPCS Defueling Support | TOR 2026 External Costs | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 1523 | Not Started
W195 | W195.25210 | HRA DPCS Defueling Support | 2026 External | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 1014 | Not Started
W196 | W196.1025 | HYA DPCS Defueling Support | 2026 External | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 1014 | Not Started
W194 | W194.25280 | HPB DPCS Defueling Support | Project Support - 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 255 | Not Started
W526 | W526.10170 | HYB DPCS Defueling Support | TPM and JCRB Meeting Held 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 0 | Not Started
W195 | W195.25690 | HRA DPCS Defueling Support | TPM and JCRB Meetings Held - 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 759 | Not Started
W196 | W196.1235 | HYA DPCS Defueling Support | TPM and JCRB Meetings Held 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 759 | Not Started
W527 | W527.4830 | DNB DPCS Defueling Support | TPM and JCRB Meetings Held 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 1012 | Not Started
W196 | W195.1080 | HYA DPCS Defueling Support | TGN097 R1 - Plan Produced | 2026-01-02 | 2026-02-06 | 26 | 26 | 26 | 0% | 1242 | Not Started
W196 | W196.25470 | HYA DPCS Defueling Support | LSR Pre Data Extract | 2026-01-02 | 2026-01-08 | 5 | 5 | 5 | 0% | 1202 | Not Started
W194 | W194.25760 | HPB DPCS Defueling Support | ETC 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 255 | Not Started
W194 | W194.25770 | HPB DPCS Defueling Support | HPB PES Group Support - 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 255 | Not Started
W194 | W194.25780 | HPB DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 255 | Not Started
W195 | W195.26070 | HRA DPCS Defueling Support | ETC 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 0 | Not Started
W196 | W196.2070 | HYA DPCS Defueling Support | ETC 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 0 | Not Started
W529 | 20 | TOR DPCS Defueling Support | ETC 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 1523 | Not Started
W529 | W195.1010 | TOR DPCS Defueling Support | TPM and JCRB Meetings Held - 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 0 | Not Started
W526 | W526.1200 | HYB DPCS Defueling Support | ETC 2026 | 2026-01-02 | 2026-12-31 | 254 | 254 | 254 | 0% | 0 | Not Started
W527 | W527.1657 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q1 2026 | 2026-01-05 | 2026-03-31 | 62 | 62 | 62 | 0% | 1267 | Not Started
W527 | W527.1700 | DNB DPCS Defueling Support | DNB PES Group Support - 2026 | 2026-01-05 | 2026-12-31 | 253 | 253 | 253 | 0% | 1267 | Not Started
W527 | W527.1710 | DNB DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2026 | 2026-01-05 | 2026-12-31 | 253 | 253 | 253 | 0% | 1267 | Not Started
W527 | W527.1655 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q1 2026 | 2026-01-05 | 2026-03-31 | 62 | 62 | 62 | 0% | 1267 | Not Started
W527 | W527.1651 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q1 2026 | 2026-01-05 | 2026-03-31 | 62 | 62 | 62 | 0% | 1458 | Not Started
W527 | W527.1653 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q1 2026 | 2026-01-05 | 2026-03-31 | 62 | 62 | 62 | 0% | 1458 | Not Started
W527 | W527.1667 | DNB DPCS Defueling Support | Cost Engineer support 2026 | 2026-01-05 | 2026-12-31 | 253 | 253 | 253 | 0% | 1267 | Not Started
W527 | W527.25670 | DNB DPCS Defueling Support | DNB 2026 2.10 - Site Acceptance Testing | 2026-01-05 | 2026-03-27 | 60 | 60 | 60 | 0% | 1404 | Not Started
W195 | W195.25730 | HRA DPCS Defueling Support | HRA 2026 - Data Modifications and Amendments | 2026-01-05 | 2026-12-30 | 252 | 252 | 252 | 0% | 1015 | Not Started
W196 | W195.1000 | HYA DPCS Defueling Support | HYA 2026 - Data Modifications and Amendments | 2026-01-05 | 2026-12-30 | 252 | 252 | 252 | 0% | 1015 | Not Started
W526 | W526.10570 | HYB DPCS Defueling Support | HYB 2027 S14R7 - Specification | 2026-01-05 | 2027-02-02 | 275 | 275 | 275 | 0% | 1377 | Not Started
W529 | W529.6360 | TOR DPCS Defueling Support | TOR 2025 S13R2 - Installation R2 | 2026-01-12 | 2026-02-27 | 35 | 35 | 35 | 0% | 1736 | Not Started
W161 | W161.8570 | HPB PSR4 | HPB PSR3 Extension EC: ONR Approval of Safety Case (Letter sent to initiate) EC 374794 | 2026-01-19 | 2026-04-21 | 65 | 65 | 65 | 0% | 157 | Not Started
W527 | W527.25750 | DNB DPCS Defueling Support | DNB 2027 2.11 - Specification | 2026-01-19 | 2026-10-02 | 180 | 180 | 180 | 0% | 1152 | Not Started
W161 | W161.6020 | HPB PSR4 | HPB PSR4 Head Doc: NSC Consideration & advice to Station Director ==> KDM | 2026-01-20 | 2026-02-02 | 10 | 10 | 10 | 0% | 99 | Not Started
W196 | W196.6320 | HYA DPCS Defueling Support | HYA 2025 - Go / No Go Decision | 2026-01-30 | 2026-01-30 | 1 | 1 | 1 | 0% | 1247 | Not Started
W195 | W195.25630 | HRA DPCS Defueling Support | HRA 2025 - Go / No Go Decision | 2026-01-30 | 2026-01-30 | 1 | 1 | 1 | 0% | 1144 | Not Started
W196 | W196.25480 | HYA DPCS Defueling Support | LSR Data Export, Analysis, Draft Report | 2026-01-30 | 2026-02-19 | 15 | 15 | 15 | 0% | 1202 | Not Started
W156 | W156.2580 | HYA Security | Implement administratively based mitigations | 2026-02-02 | 2027-11-15 | 454 | 454 | 454 | 0% | 0 | Not Started
W156 | W156.2590 | HYA Security | Implement temp. infrastructure and org. mitigations required to enable commencement of defuelling (FEEDS TO SUMMARY SCHE | 2026-02-02 | 2027-11-15 | 454 | 454 | 454 | 0% | 0 | Not Started
W156 | W156.2600 | HYA Security | Implement permanent infrastructure and organisational mitigations | 2026-02-02 | 2027-11-15 | 454 | 454 | 454 | 0% | 0 | Not Started
W195 | W195.25640 | HRA DPCS Defueling Support | HRA 2025 - Design, Consolidation and Testing | 2026-02-03 | 2026-03-30 | 40 | 40 | 40 | 0% | 1144 | Not Started
W161 | W161.6040 | HPB PSR4 | HPB PSR4 Head Doc: ONR Approval of Safety Case (Letter sent to initiate) EC 374795 | 2026-02-03 | 2026-05-29 | 80 | 80 | 80 | 0% | 99 | Not Started
W161 | W161.7060 | HPB PSR4 | HPB PSR4 Head Doc: Prepare Paper for Submission to ONR | 2026-02-03 | 2026-02-16 | 10 | 10 | 10 | 0% | 99 | Not Started
W526 | W526.10340 | HYB DPCS Defueling Support | HYB 2026 TGN097 R8 - Plan Produced | 2026-02-06 | 2026-04-02 | 40 | 40 | 40 | 0% | 1681 | Not Started
W196 | W196.25490 | HYA DPCS Defueling Support | Issue Recommendations | 2026-02-20 | 2026-02-20 | 1 | 1 | 1 | 0% | 1202 | Not Started
W194 | W194.25700 | HPB DPCS Defueling Support | Fuel Free Verification (FFV) declared | 2026-02-24 | 2026-02-26 | 3 | 3 | 3 | 0% | 299 | Not Started
W529 | W529.4540 | TOR DPCS Defueling Support | TOR 2026 LSR - Data Export Produced and Issued | 2026-02-25 | 2026-03-24 | 20 | 20 | 20 | 0% | 1668 | Not Started
W526 | W526.4540 | HYB DPCS Defueling Support | HYB 2026 LSR - Data Export Produced and Issued | 2026-02-25 | 2026-03-24 | 20 | 20 | 20 | 0% | 1668 | Not Started
W196 | W196.25500 | HYA DPCS Defueling Support | Recommendations Workshop | 2026-02-26 | 2026-02-26 | 1 | 1 | 1 | 0% | 1202 | Not Started
W194 | W194.25670 | HPB DPCS Defueling Support | HPB SQEP declaration | 2026-02-27 | 2026-03-26 | 20 | 20 | 20 | 0% | 299 | Not Started
W196 | W196.25510 | HYA DPCS Defueling Support | LSR Update, Internal Review & Issue to EDF | 2026-02-27 | 2026-03-12 | 10 | 10 | 10 | 0% | 1202 | Not Started
W527 | W527.25500 | DNB DPCS Defueling Support | LSR Pre Data Extract | 2026-03-06 | 2026-03-12 | 5 | 5 | 5 | 0% | 1412 | Not Started
W196 | W196.25520 | HYA DPCS Defueling Support | EDF Review | 2026-03-13 | 2026-03-26 | 10 | 10 | 10 | 0% | 1202 | Not Started
W529 | W529.4530 | TOR DPCS Defueling Support | TOR 2026 LSR - Recommendations Produced and Issued | 2026-03-25 | 2026-04-09 | 10 | 10 | 10 | 0% | 1668 | Not Started
W526 | W526.4530 | HYB DPCS Defueling Support | HYB 2026 LSR - Recommendations Produced and Issued | 2026-03-25 | 2026-04-09 | 10 | 10 | 10 | 0% | 1668 | Not Started
W161 | W161.9600 | HPB PSR4 | HPB PSR4 Head Doc: EC PDSC Safety Case Submitted to ONR (Incoming milestone to be linked) | 2026-03-26 | 2026-03-26 | 1 | 1 | 1 | 0% | 194 | Not Started
W194 | W194.25680 | HPB DPCS Defueling Support | Asset Assessment | 2026-03-27 | 2026-05-12 | 30 | 30 | 30 | 0% | 299 | Not Started
W196 | W196.25530 | HYA DPCS Defueling Support | Update LSR | 2026-03-27 | 2026-04-02 | 5 | 5 | 5 | 0% | 1202 | Not Started
W155 | W155..2580 | HRA Security | Implement administratively based mitigations | 2026-04-01 | 2026-04-23 | 15 | 15 | 15 | 0% | 176 | Not Started
W195 | W195.2390 | HRA DPCS Defueling Support | Thales Long Term Support Contract Q2 2026 | 2026-04-01 | 2026-06-30 | 61 | 61 | 61 | 0% | 1014 | Not Started
W196 | W196.2400 | HYA DPCS Defueling Support | Thales Long Term Support Contract Q2 2026 | 2026-04-01 | 2026-06-30 | 61 | 61 | 61 | 0% | 1144 | Not Started
W527 | W527.1720 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q2 2026 | 2026-04-01 | 2026-06-30 | 61 | 61 | 61 | 0% | 1397 | Not Started
W527 | W527.1705 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q2 2026 | 2026-04-01 | 2026-06-30 | 61 | 61 | 61 | 0% | 1397 | Not Started
W527 | W527.1701 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q2 2026 | 2026-04-01 | 2026-06-30 | 61 | 61 | 61 | 0% | 1397 | Not Started
W527 | W527.1703 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q2 2026 | 2026-04-01 | 2026-06-30 | 61 | 61 | 61 | 0% | 1397 | Not Started
W529 | W529.1295 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q2 2026 | 2026-04-01 | 2026-06-30 | 61 | 61 | 61 | 0% | 1523 | Not Started
W526 | W526.1295 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q2 2026 | 2026-04-01 | 2026-06-30 | 61 | 61 | 61 | 0% | 1523 | Not Started
W526 | W526.1270 | HYB DPCS Defueling Support | HYB Argus Support Contract - Q3 2026 | 2026-04-01 | 2026-04-01 | 1 | 1 | 1 | 0% | 1652 | Not Started
W529 | W529.1665 | TOR DPCS Defueling Support | TOR Argus Support Contract - Q3 2026 | 2026-04-01 | 2026-07-06 | 65 | 65 | 65 | 0% | 1584 | Not Started
W526 | W526.1275 | HYB DPCS Defueling Support | HYB Argus Support Contract - Q2 2026 | 2026-04-02 | 2026-07-01 | 61 | 61 | 61 | 0% | 1652 | Not Started
W527 | W527.25510 | DNB DPCS Defueling Support | LSR Data Export, Analysis, Draft Report | 2026-04-02 | 2026-04-24 | 15 | 15 | 15 | 0% | 1412 | Not Started
W196 | W196.25540 | HYA DPCS Defueling Support | Issue LSR | 2026-04-07 | 2026-04-07 | 1 | 1 | 1 | 0% | 1202 | Not Started
W526 | W526.10350 | HYB DPCS Defueling Support | HYB 2026 TGN097 R8 - Inspection | 2026-04-07 | 2026-04-13 | 5 | 5 | 5 | 0% | 1681 | Not Started
W529 | W529.4520 | TOR DPCS Defueling Support | TOR 2026 LSR - Recommendation Sentencing Workshop Preparation and Event | 2026-04-10 | 2026-04-23 | 10 | 10 | 10 | 0% | 1668 | Not Started
W526 | W526.4520 | HYB DPCS Defueling Support | HYB 2026 LSR - Recommendation Sentencing Workshop Preparation and Event | 2026-04-10 | 2026-04-23 | 10 | 10 | 10 | 0% | 1668 | Not Started
W526 | W526.10360 | HYB DPCS Defueling Support | HYB 2026 TGN097 R8 - Draft Report Produced, Internal Review and Issue to EDF | 2026-04-14 | 2026-04-27 | 10 | 10 | 10 | 0% | 1681 | Not Started
W161 | W161.8540 | HPB PSR4 | HPB PSR3 Extension EC: Revise all Affected Drawings and Documents for EC Approval | 2026-04-22 | 2026-05-06 | 10 | 10 | 10 | 0% | 157 | Not Started
W529 | W529.4510 | TOR DPCS Defueling Support | TOR 2026 LSR - Draft Report Produced and Issued for EDF Review | 2026-04-24 | 2026-05-11 | 11 | 11 | 11 | 0% | 1668 | Not Started
W526 | W526.4510 | HYB DPCS Defueling Support | HYB 2026 LSR - Draft Report Produced and Issued for EDF Review | 2026-04-24 | 2026-05-11 | 11 | 11 | 11 | 0% | 1668 | Not Started
W527 | W527.25720 | DNB DPCS Defueling Support | DNB 2026 2.10 - Installation R1 | 2026-04-24 | 2026-05-08 | 10 | 10 | 10 | 0% | 1404 | Not Started
W527 | W527.25520 | DNB DPCS Defueling Support | Issue Recommendations | 2026-04-27 | 2026-04-27 | 1 | 1 | 1 | 0% | 1412 | Not Started
W526 | W526.10370 | HYB DPCS Defueling Support | HYB 2026 TGN097 R8 - EDF Review | 2026-04-28 | 2026-05-12 | 10 | 10 | 10 | 0% | 1681 | Not Started
W527 | W527.25530 | DNB DPCS Defueling Support | Recommendations Workshop | 2026-04-30 | 2026-04-30 | 1 | 1 | 1 | 0% | 1412 | Not Started
W527 | W527.25540 | DNB DPCS Defueling Support | LSR Update, Internal Review & Issue to EDF | 2026-05-01 | 2026-05-15 | 10 | 10 | 10 | 0% | 1412 | Not Started
W161 | W161.8510 | HPB PSR4 | HPB PSR3 Extension EC: Develop Implementation & closeout Plan | 2026-05-07 | 2026-05-20 | 10 | 10 | 10 | 0% | 157 | Not Started
W529 | W529.4500 | TOR DPCS Defueling Support | TOR 2026 LSR - EDF Review Comments Produced and Provided | 2026-05-12 | 2026-05-27 | 11 | 11 | 11 | 0% | 1668 | Not Started
W526 | W526.4500 | HYB DPCS Defueling Support | HYB 2026 LSR - EDF Review Comments Produced and Provided | 2026-05-12 | 2026-05-27 | 11 | 11 | 11 | 0% | 1668 | Not Started
W194 | W194.25690 | HPB DPCS Defueling Support | Revised Costs Provided | 2026-05-13 | 2026-06-24 | 30 | 30 | 30 | 0% | 299 | Not Started
W526 | W526.10380 | HYB DPCS Defueling Support | HYB 2026 TGN097 R8 - Update and Issue Report | 2026-05-13 | 2026-05-19 | 5 | 5 | 5 | 0% | 1681 | Not Started
W527 | W527.25550 | DNB DPCS Defueling Support | EDF Review | 2026-05-18 | 2026-06-01 | 10 | 10 | 10 | 0% | 1412 | Not Started
W526 | W526.10390 | HYB DPCS Defueling Support | HYB 2026 TGN097 R8 - Report | 2026-05-20 | 2026-05-20 | 1 | 1 | 1 | 0% | 1681 | Not Started
W161 | W161.8590 | HPB PSR4 | HPB PSR3 Extension EC: Post Job Debrief (CAT 2) | 2026-05-21 | 2026-05-21 | 1 | 1 | 1 | 0% | 157 | Not Started
W529 | W529.4490 | TOR DPCS Defueling Support | TOR 2026 LSR - Final Report Produced and Issued | 2026-05-28 | 2026-06-09 | 9 | 9 | 9 | 0% | 1668 | Not Started
W526 | W526.4490 | HYB DPCS Defueling Support | HYB 2026 LSR - Final Report Produced and Issued | 2026-05-28 | 2026-06-09 | 9 | 9 | 9 | 0% | 1668 | Not Started
W527 | W527.25290 | DNB DPCS Defueling Support | Asset Guardian Licences and Support 2026 - 2027 | 2026-05-28 | 2026-05-28 | 1 | 1 | 1 | 0% | 1420 | Not Started
W161 | W161.6070 | HPB PSR4 | HPB PSR4 Head Doc: Revise all Affected Drawings and Documents for EC Approval | 2026-06-01 | 2026-06-12 | 10 | 10 | 10 | 0% | 99 | Not Started
W526 | W526.10530 | HYB DPCS Defueling Support | HYB 2026 S13R8 - Testing | 2026-06-01 | 2026-10-28 | 107 | 107 | 107 | 0% | 1505 | Not Started
W527 | W527.25560 | DNB DPCS Defueling Support | Update LSR | 2026-06-02 | 2026-06-08 | 5 | 5 | 5 | 0% | 1412 | Not Started
W527 | W527.25680 | DNB DPCS Defueling Support | DNB 2026 2.10 - Installation R2 | 2026-06-08 | 2026-06-19 | 10 | 10 | 10 | 0% | 1404 | Not Started
W527 | W527.25570 | DNB DPCS Defueling Support | Issue Complete LSR | 2026-06-09 | 2026-06-09 | 1 | 1 | 1 | 0% | 1412 | Not Started
W196 | W196.6340 | HYA DPCS Defueling Support | HYA 2025 - Installation R1 | 2026-06-10 | 2026-06-30 | 15 | 15 | 15 | 0% | 1144 | Not Started
W195 | W195.25650 | HRA DPCS Defueling Support | HRA 2025 - Installation R1 | 2026-06-10 | 2026-06-30 | 15 | 15 | 15 | 0% | 1144 | Not Started
W161 | W161.6080 | HPB PSR4 | HPB PSR4 Head Doc: Develop Implementation & closeout Plan | 2026-06-15 | 2026-06-26 | 10 | 10 | 10 | 0% | 99 | Not Started
W155 | W155.2380 | HRA Security | Revise SPPI File Against Issued Enhanced Safety Cases (W224) | 2026-06-22 | 2026-06-26 | 5 | 5 | 5 | 0% | 126 | Not Started
W155 | W155..3220 | HRA Security | Revise Flasks SPPI File Against Issued Enhanced Safety Cases | 2026-06-22 | 2026-06-26 | 5 | 5 | 5 | 0% | 91 | Not Started
W194 | W194.25710 | HPB DPCS Defueling Support | Decommission Reference Rig | 2026-06-25 | 2026-08-05 | 30 | 30 | 30 | 0% | 299 | Not Started
W155 | W155..2390 | HRA Security | Review and Update SPORS | 2026-06-29 | 2026-07-03 | 5 | 5 | 5 | 0% | 126 | Not Started
W155 | W155.3230 | HRA Security | Review and Update SPORS | 2026-06-29 | 2026-07-03 | 5 | 5 | 5 | 0% | 91 | Not Started
W161 | W161.6090 | HPB PSR4 | HPB PSR4 Head Doc: Post Job Debrief (CAT 2) | 2026-06-29 | 2026-06-29 | 1 | 1 | 1 | 0% | 99 | Not Started
W161 | W161.2100 | HPB PSR4 | Hold Project Closeout and Lessons Learned Meeting | 2026-06-30 | 2026-06-30 | 1 | 1 | 1 | 0% | 99 | Not Started
W195 | W195.2400 | HRA DPCS Defueling Support | Thales Long Term Support Contract Q3 2026 | 2026-07-01 | 2026-09-30 | 65 | 65 | 65 | 0% | 1014 | Not Started
W196 | W196.2410 | HYA DPCS Defueling Support | Thales Long Term Support Contract Q3 2026 | 2026-07-01 | 2026-09-30 | 65 | 65 | 65 | 0% | 1079 | Not Started
W527 | W527.1730 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q3 2026 | 2026-07-01 | 2026-09-30 | 65 | 65 | 65 | 0% | 1332 | Not Started
W527 | W527.1731 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q3 2026 | 2026-07-01 | 2026-09-30 | 65 | 65 | 65 | 0% | 1332 | Not Started
W527 | W527.1732 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q3 2026 | 2026-07-01 | 2026-09-30 | 65 | 65 | 65 | 0% | 1332 | Not Started
W527 | W527.1735 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q3 2026 | 2026-07-01 | 2026-09-30 | 65 | 65 | 65 | 0% | 1332 | Not Started
W529 | W529.1305 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q3 2026 | 2026-07-01 | 2026-09-30 | 65 | 65 | 65 | 0% | 1523 | Not Started
W526 | W526.1305 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q3 2026 | 2026-07-01 | 2026-09-30 | 65 | 65 | 65 | 0% | 1523 | Not Started
W529 | W529.6390 | TOR DPCS Defueling Support | TOR 2025 S14R1 - Specification | 2026-07-01 | 2027-01-22 | 145 | 145 | 145 | 0% | 1387 | Not Started
W157 | W157.24600 | HYB Security | Reactor Equivalence Confirmed by NSG Group Head | 2026-07-01 | 2026-11-04 | 90 | 90 | 90 | 0% | 40 | Not Started
W159 | W159.2030 | TOR Security | Implement Revised TSS/TSP Arrangements | 2026-07-01 | 2026-09-23 | 60 | 60 | 60 | 0% | 90 | Not Started
W159 | W159.24600 | TOR Security | Reactor Equivalence Confirmed by NSG Group Head | 2026-07-01 | 2026-11-04 | 90 | 90 | 90 | 0% | 0 | Not Started
W161 | W161.2110 | HPB PSR4 | Produce Lessons Learned Report | 2026-07-01 | 2026-07-01 | 1 | 1 | 1 | 0% | 99 | Not Started
W526 | W526.10080 | HYB DPCS Defueling Support | HYB 2026 LSR Pre Data Extract | 2026-07-02 | 2026-07-08 | 5 | 5 | 5 | 0% | 1585 | Not Started
W161 | W161.2120 | HPB PSR4 | Produce Project Closeout Report | 2026-07-02 | 2026-07-03 | 2 | 2 | 2 | 0% | 99 | Not Started
W155 | W155.2400 | HRA Security | Issue Revised SPORS | 2026-07-06 | 2026-07-06 | 1 | 1 | 1 | 0% | 126 | Not Started
W155 | W155.3240 | HRA Security | Issue Revised SPORS | 2026-07-06 | 2026-07-06 | 1 | 1 | 1 | 0% | 91 | Not Started
W161 | W161.2130 | HPB PSR4 | Prepare Gate D PRC Paper | 2026-07-06 | 2026-07-13 | 6 | 6 | 6 | 0% | 99 | Not Started
W155 | W155.3250 | HRA Security | Incorporate New Mitigations | 2026-07-07 | 2026-08-24 | 35 | 35 | 35 | 0% | 91 | Not Started
W529 | W529.1675 | TOR DPCS Defueling Support | TOR Argus Support Contract - Q4 2026 | 2026-07-07 | 2026-10-06 | 65 | 65 | 65 | 0% | 1584 | Not Started
W526 | W526.10090 | HYB DPCS Defueling Support | HYB 2026 LSR Data Export, Analysis, Draft Report | 2026-07-30 | 2026-08-19 | 15 | 15 | 15 | 0% | 1585 | Not Started
W194 | W194.25720 | HPB DPCS Defueling Support | Redistribute Assets | 2026-08-06 | 2026-09-17 | 30 | 30 | 30 | 0% | 299 | Not Started
W161 | W161.2140 | HPB PSR4 | Gate D PRC Paper Submission | 2026-08-12 | 2026-08-12 | 1 | 1 | 1 | 0% | 4 | Not Started
W526 | W526.10100 | HYB DPCS Defueling Support | HYB 2026 Issue Recommendations | 2026-08-20 | 2026-08-20 | 1 | 1 | 1 | 0% | 1585 | Not Started
W161 | W161.2150 | HPB PSR4 | Gate D - Hold PRC Meeting | 2026-08-25 | 2026-08-25 | 1 | 1 | 1 | 0% | 4 | Not Started
W526 | W526.10110 | HYB DPCS Defueling Support | HYB 2026 Recommendations Workshop | 2026-08-27 | 2026-08-27 | 1 | 1 | 1 | 0% | 1585 | Not Started
W526 | W526.10120 | HYB DPCS Defueling Support | HYB 2026 LSR Update, Internal Review & Issue to EDF | 2026-08-28 | 2026-09-11 | 10 | 10 | 10 | 0% | 1585 | Not Started
W195 | W195.25880 | HRA DPCS Defueling Support | LSR Pre Data Extract | 2026-08-28 | 2026-09-04 | 5 | 5 | 5 | 0% | 1034 | Not Started
W196 | W195.1090 | HYA DPCS Defueling Support | TGN097 R1 - Inspection | 2026-09-03 | 2026-09-09 | 5 | 5 | 5 | 0% | 1062 | Not Started
W196 | W196.6380 | HYA DPCS Defueling Support | HYA 2025 - Installation R2 | 2026-09-10 | 2026-09-30 | 15 | 15 | 15 | 0% | 1079 | Not Started
W195 | W195.25660 | HRA DPCS Defueling Support | HRA 2025 - Installation R2 | 2026-09-10 | 2026-09-30 | 15 | 15 | 15 | 0% | 1079 | Not Started
W196 | W195.1120 | HYA DPCS Defueling Support | TGN097 R1 - Draft Report Produced, Internal Review and Issue to EDF | 2026-09-10 | 2026-09-23 | 10 | 10 | 10 | 0% | 1062 | Not Started
W526 | W526.10130 | HYB DPCS Defueling Support | HYB 2026 EDF Review | 2026-09-14 | 2026-09-25 | 10 | 10 | 10 | 0% | 1585 | Not Started
W194 | W194.25730 | HPB DPCS Defueling Support | Disposal of Assets | 2026-09-18 | 2026-10-29 | 30 | 30 | 30 | 0% | 299 | Not Started
W196 | W195.1110 | HYA DPCS Defueling Support | TGN097 R1 - EDF Review | 2026-09-24 | 2026-10-07 | 10 | 10 | 10 | 0% | 1062 | Not Started
W526 | W526.10140 | HYB DPCS Defueling Support | HYB 2026 Update LSR | 2026-09-28 | 2026-10-02 | 5 | 5 | 5 | 0% | 1585 | Not Started
W195 | W195.25890 | HRA DPCS Defueling Support | LSR Data Export, Analysis, Draft Report | 2026-09-28 | 2026-10-16 | 15 | 15 | 15 | 0% | 1034 | Not Started
W195 | W195.2410 | HRA DPCS Defueling Support | Thales Long Term Support Contract Q4 2026 | 2026-10-01 | 2026-12-31 | 65 | 65 | 65 | 0% | 1014 | Not Started
W196 | W196.2420 | HYA DPCS Defueling Support | Thales Long Term Support Contract Q4 2026 | 2026-10-01 | 2026-12-31 | 65 | 65 | 65 | 0% | 1014 | Not Started
W527 | W527.1750 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q4 2026 | 2026-10-01 | 2026-12-31 | 65 | 65 | 65 | 0% | 1267 | Not Started
W527 | W527.1752 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q4 2026 | 2026-10-01 | 2026-12-31 | 65 | 65 | 65 | 0% | 1267 | Not Started
W527 | W527.1754 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q4 2026 | 2026-10-01 | 2026-12-31 | 65 | 65 | 65 | 0% | 1267 | Not Started
W527 | W527.1756 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q4 2026 | 2026-10-01 | 2026-12-31 | 65 | 65 | 65 | 0% | 1267 | Not Started
W529 | W529.1315 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q4 2026 | 2026-10-01 | 2026-12-31 | 65 | 65 | 65 | 0% | 1523 | Not Started
W526 | W526.1315 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q4 2026 | 2026-10-01 | 2026-12-31 | 65 | 65 | 65 | 0% | 1523 | Not Started
W526 | W526.10150 | HYB DPCS Defueling Support | HYB 2026 Issue Complete LSR | 2026-10-05 | 2026-10-05 | 1 | 1 | 1 | 0% | 1585 | Not Started
W527 | W527.25760 | DNB DPCS Defueling Support | DNB 2027 2.11 - Testing | 2026-10-05 | 2026-11-13 | 30 | 30 | 30 | 0% | 1152 | Not Started
W196 | W195.1020 | HYA DPCS Defueling Support | HYA 2026 - Consolidation and Testing | 2026-10-08 | 2027-03-30 | 120 | 120 | 120 | 0% | 954 | Not Started
W195 | W195.25900 | HRA DPCS Defueling Support | Issue Recommendations | 2026-10-19 | 2026-10-19 | 1 | 1 | 1 | 0% | 1034 | Not Started
W196 | W195.1100 | HYA DPCS Defueling Support | TGN097 R1 - Report Issue | 2026-10-19 | 2026-10-23 | 5 | 5 | 5 | 0% | 1062 | Not Started
W195 | W195.25910 | HRA DPCS Defueling Support | Recommendations Workshop | 2026-10-27 | 2026-10-27 | 1 | 1 | 1 | 0% | 1034 | Not Started
W195 | W195.25920 | HRA DPCS Defueling Support | LSR Update, Internal Review & Issue to EDF | 2026-10-28 | 2026-11-10 | 10 | 10 | 10 | 0% | 1034 | Not Started
W526 | W526.10540 | HYB DPCS Defueling Support | HYB 2026 S13R8 - Delivery | 2026-10-29 | 2026-11-30 | 23 | 23 | 23 | 0% | 1505 | Not Started
W195 | W195.25780 | HRA DPCS Defueling Support | HRA 2026 - Specification | 2026-11-02 | 2026-12-15 | 32 | 32 | 32 | 0% | 890 | Not Started
W196 | W195.1040 | HYA DPCS Defueling Support | HYA 2026 - Specification | 2026-11-04 | 2026-12-15 | 30 | 30 | 30 | 0% | 1024 | Not Started
W157 | W157.2580 | HYB Security | Implement administratively based mitigations | 2026-11-05 | 2026-12-02 | 20 | 20 | 20 | 0% | 20 | Not Started
W159 | W159.2600 | TOR Security | Implement permanent infrastructure and organisational mitigations | 2026-11-05 | 2027-01-29 | 60 | 60 | 60 | 0% | 0 | Not Started
W159 | W159.2590 | TOR Security | Implement temp. infrastructure and org mitigations required to enable commencement of defuelling (FEEDS TO SUMMARY SCHE) | 2026-11-05 | 2027-01-29 | 60 | 60 | 60 | 0% | 0 | Not Started
W159 | W159.2580 | TOR Security | Implement administratively based mitigations | 2026-11-05 | 2026-12-02 | 20 | 20 | 20 | 0% | 0 | Not Started
W195 | W195.25930 | HRA DPCS Defueling Support | EDF Review | 2026-11-11 | 2026-11-24 | 10 | 10 | 10 | 0% | 1034 | Not Started
W527 | W527.25770 | DNB DPCS Defueling Support | DNB 2027 2.11 - Delivery | 2026-11-23 | 2026-12-18 | 20 | 20 | 20 | 0% | 1152 | Not Started
W195 | W195.25940 | HRA DPCS Defueling Support | Update LSR | 2026-11-25 | 2026-12-01 | 5 | 5 | 5 | 0% | 1034 | Not Started
W195 | W195.25950 | HRA DPCS Defueling Support | Issue Complete LSR | 2026-12-02 | 2026-12-02 | 1 | 1 | 1 | 0% | 1034 | Not Started
W195 | W195.25790 | HRA DPCS Defueling Support | TGN097 R1 - Plan Produced | 2026-12-10 | 2027-02-05 | 40 | 40 | 40 | 0% | 989 | Not Started
W195 | W195.25740 | HRA DPCS Defueling Support | HRA 2026 - Go / No Go Decision | 2026-12-16 | 2027-01-29 | 31 | 31 | 31 | 0% | 890 | Not Started
W527 | W527.25730 | DNB DPCS Defueling Support | DNB 2027 2.11 - Site Acceptance Testing | 2026-12-31 | 2027-03-25 | 60 | 60 | 60 | 0% | 1152 | Not Started
W195 | W195.2320 | HRA DPCS Defueling Support | HRA PES Group Support - 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 759 | Not Started
W195 | W195.2330 | HRA DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 759 | Not Started
W195 | W195.2460 | HRA DPCS Defueling Support | Thales Long Term Support Contract Q1 2027 | 2027-01-04 | 2027-03-31 | 61 | 61 | 61 | 0% | 759 | Not Started
W196 | W196.2330 | HYA DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 759 | Not Started
W196 | W196.2340 | HYA DPCS Defueling Support | HYA PES Group Support - 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 759 | Not Started
W196 | W196.2470 | HYA DPCS Defueling Support | Thales Long Term Support Contract Q1 2027 | 2027-01-04 | 2027-03-31 | 61 | 61 | 61 | 0% | 759 | Not Started
W527 | W527.1782 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q1 2027 | 2027-01-04 | 2027-03-31 | 61 | 61 | 61 | 0% | 1012 | Not Started
W527 | W527.1787 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q1 2027 | 2027-01-04 | 2027-03-31 | 61 | 61 | 61 | 0% | 1012 | Not Started
W527 | W527.1830 | DNB DPCS Defueling Support | DNB PES Group Support - 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 1012 | Not Started
W527 | W527.1840 | DNB DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 1012 | Not Started
W527 | W527.1783 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q1 2027 | 2027-01-04 | 2027-03-31 | 61 | 61 | 61 | 0% | 1012 | Not Started
W527 | W527.1785 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q1 2027 | 2027-01-04 | 2027-03-31 | 61 | 61 | 61 | 0% | 1012 | Not Started
W527 | W527.1797 | DNB DPCS Defueling Support | Cost Engineer Support 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 1012 | Not Started
W529 | W529.3040 | TOR DPCS Defueling Support | TOR 2027 Defueling Software Build | 2027-01-04 | 2027-11-30 | 232 | 232 | 232 | 0% | 1268 | Not Started
W529 | W529.1320 | TOR DPCS Defueling Support | TOR Argus Support Contract - Q1 2027 | 2027-01-04 | 2027-03-31 | 61 | 61 | 61 | 0% | 1268 | Not Started
W529 | W529.1345 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q1 2027 | 2027-01-04 | 2027-03-31 | 61 | 61 | 61 | 0% | 1268 | Not Started
W529 | W529.1080 | TOR DPCS Defueling Support | TOR PES Group Support - 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 1268 | Not Started
W529 | W529.1090 | TOR DPCS Defueling Support | TOR Plant Control Systems & Simulators (PCS&S) Group - 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 1268 | Not Started
W529 | W529.3050 | TOR DPCS Defueling Support | TOR DPCS Long Term Support Contract 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 1268 | Not Started
W526 | W526.4620 | HYB DPCS Defueling Support | HYB 2027 LSR - Pre-export Data Validation Produced and Completed | 2027-01-04 | 2027-02-24 | 38 | 38 | 38 | 0% | 1414 | Not Started
W526 | W526.1325 | HYB DPCS Defueling Support | HYB Argus Support Contract - Q1 2027 | 2027-01-04 | 2027-04-02 | 63 | 63 | 63 | 0% | 1268 | Not Started
W526 | W526.3050 | HYB DPCS Defueling Support | HYB DPCS Long Term Support Contract 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 1036 | Not Started
W526 | W526.1090 | HYB DPCS Defueling Support | HYB Plant Control Systems & Simulators (PCS&S) Group - 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 1268 | Not Started
W526 | W526.1080 | HYB DPCS Defueling Support | HYB PES Group Support - 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 1268 | Not Started
W526 | W526.1345 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q1 2027 | 2027-01-04 | 2027-04-02 | 63 | 63 | 63 | 0% | 1268 | Not Started
W527 | W527.25250 | DNB DPCS Defueling Support | ETC 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 0 | Not Started
W526 | W526.10020 | HYB DPCS Defueling Support | HYB 2027 External Costs | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 1268 | Not Started
W529 | W529.10020 | TOR DPCS Defueling Support | TOR 2027 External Costs | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 1268 | Not Started
W195 | W195.25220 | HRA DPCS Defueling Support | 2027 External | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 759 | Not Started
W196 | W196.1030 | HYA DPCS Defueling Support | 2027 Externals | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 759 | Not Started
W195 | W195.25700 | HRA DPCS Defueling Support | TPM and JCRB Meetings Held - 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 759 | Not Started
W196 | W196.1245 | HYA DPCS Defueling Support | TPM and JCRB Meetings Held 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 759 | Not Started
W527 | W527.4840 | DNB DPCS Defueling Support | TPM and JCRB Meetings Held 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 1012 | Not Started
W526 | W526.10180 | HYB DPCS Defueling Support | TPM and JCRB Meeting Held 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 0 | Not Started
W196 | W196.25550 | HYA DPCS Defueling Support | LSR Pre Data Extract | 2027-01-04 | 2027-01-08 | 5 | 5 | 5 | 0% | 946 | Not Started
W529 | W529.10090 | TOR DPCS Defueling Support | TGN097 R1 - Plan Produced | 2027-01-04 | 2027-02-05 | 25 | 25 | 25 | 0% | 1323 | Not Started
W529 | W529.10160 | TOR DPCS Defueling Support | TOR 2027 S14R2 - Software Build Requirement | 2027-01-04 | 2027-06-30 | 124 | 124 | 124 | 0% | 1176 | Not Started
W194 | W194.25790 | HPB DPCS Defueling Support | Project Support - 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 0 | Not Started
W194 | W194.25800 | HPB DPCS Defueling Support | HPB PES Group Support - 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 0 | Not Started
W194 | W194.25810 | HPB DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 0 | Not Started
W195 | W195.26080 | HRA DPCS Defueling Support | ETC 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 0 | Not Started
W196 | W196.2100 | HYA DPCS Defueling Support | ETC 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 0 | Not Started
W529 | 30 | TOR DPCS Defueling Support | ETC 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 1268 | Not Started
W529 | W195.1020 | TOR DPCS Defueling Support | TPM and JCRB Meetings Held - 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 0 | Not Started
W526 | W526.1210 | HYB DPCS Defueling Support | ETC 2027 | 2027-01-04 | 2027-12-31 | 255 | 255 | 255 | 0% | 0 | Not Started
W529 | W529.6400 | TOR DPCS Defueling Support | TOR 2025 S14R1 - Testing | 2027-01-25 | 2027-04-16 | 58 | 58 | 58 | 0% | 1387 | Not Started
W526 | W526.10560 | HYB DPCS Defueling Support | HYB 2026 S13R8 - Installation R8 | 2027-01-27 | 2027-01-27 | 1 | 1 | 1 | 0% | 1505 | Not Started
W196 | W195.1010 | HYA DPCS Defueling Support | HYA 2026 - Go / No Go Decision | 2027-01-29 | 2027-01-29 | 1 | 1 | 1 | 0% | 994 | Not Started
W196 | W196.25560 | HYA DPCS Defueling Support | LSR Data Export, Analysis, Draft Report | 2027-02-01 | 2027-02-19 | 15 | 15 | 15 | 0% | 946 | Not Started
W195 | W195.25750 | HRA DPCS Defueling Support | HRA 2026 - Design, Consolidation and Testing | 2027-02-02 | 2027-03-30 | 39 | 39 | 39 | 0% | 890 | Not Started
W526 | W526.10580 | HYB DPCS Defueling Support | HYB 2027 S14R7 - Testing | 2027-02-03 | 2027-04-23 | 56 | 56 | 56 | 0% | 1377 | Not Started
W526 | W526.10400 | HYB DPCS Defueling Support | HYB 2027 TGN097 R7 - Plan Produced | 2027-02-05 | 2027-04-05 | 40 | 40 | 40 | 0% | 1459 | Not Started
W196 | W196.25570 | HYA DPCS Defueling Support | Issue Recommendations | 2027-02-22 | 2027-02-22 | 1 | 1 | 1 | 0% | 946 | Not Started
W526 | W526.4610 | HYB DPCS Defueling Support | HYB 2027 LSR - Data Export Produced and Issued | 2027-02-25 | 2027-03-24 | 20 | 20 | 20 | 0% | 1414 | Not Started
W529 | W529.4620 | TOR DPCS Defueling Support | TOR 2027 LSR - Pre-export Data Validation Produced and Completed | 2027-03-01 | 2027-04-23 | 38 | 38 | 38 | 0% | 1374 | Not Started
W196 | W196.25580 | HYA DPCS Defueling Support | Recommendations Workshop | 2027-03-02 | 2027-03-02 | 1 | 1 | 1 | 0% | 946 | Not Started
W196 | W196.25590 | HYA DPCS Defueling Support | LSR Update, Internal Review & Issue to EDF | 2027-03-03 | 2027-03-16 | 10 | 10 | 10 | 0% | 946 | Not Started
W527 | W527.25850 | DNB DPCS Defueling Support | LSR Pre Data Extract | 2027-03-05 | 2027-03-11 | 5 | 5 | 5 | 0% | 1159 | Not Started
W526 | W526.10410 | HYB DPCS Defueling Support | HYB 2027 TGN097 R7 - Inspection | 2027-03-08 | 2027-03-12 | 5 | 5 | 5 | 0% | 1447 | Not Started
W526 | W526.10420 | HYB DPCS Defueling Support | HYB 2027 TGN097 R7 - Draft Report Produced, Internal Review and Issue to EDF | 2027-03-15 | 2027-03-30 | 10 | 10 | 10 | 0% | 1447 | Not Started
W196 | W196.25600 | HYA DPCS Defueling Support | EDF Review | 2027-03-17 | 2027-04-01 | 10 | 10 | 10 | 0% | 946 | Not Started
W526 | W526.4600 | HYB DPCS Defueling Support | HYB 2027 LSR - Recommendations Produced and Issued | 2027-03-25 | 2027-04-09 | 10 | 10 | 10 | 0% | 1414 | Not Started
W526 | W526.10430 | HYB DPCS Defueling Support | HYB 2027 TGN097 R7 - EDF Review | 2027-03-31 | 2027-04-13 | 10 | 10 | 10 | 0% | 1447 | Not Started
W195 | W195.2470 | HRA DPCS Defueling Support | Thales Long Term Support Contract Q2 2027 | 2027-04-01 | 2027-06-30 | 63 | 63 | 63 | 0% | 759 | Not Started
W196 | W196.2480 | HYA DPCS Defueling Support | Thales Long Term Support Contract Q2 2027 | 2027-04-01 | 2027-06-30 | 63 | 63 | 63 | 0% | 890 | Not Started
W527 | W527.1807 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q2 2027 | 2027-04-01 | 2027-06-30 | 63 | 63 | 63 | 0% | 1143 | Not Started
W527 | W527.1802 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q2 2027 | 2027-04-01 | 2027-06-30 | 63 | 63 | 63 | 0% | 1143 | Not Started
W527 | W527.1805 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q2 2027 | 2027-04-01 | 2027-06-30 | 63 | 63 | 63 | 0% | 1143 | Not Started
W527 | W527.1806 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q2 2022 | 2027-04-01 | 2027-06-30 | 63 | 63 | 63 | 0% | 1143 | Not Started
W529 | W529.1355 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q2 2027 | 2027-04-01 | 2027-06-30 | 63 | 63 | 63 | 0% | 1268 | Not Started
W529 | W529.1325 | TOR DPCS Defueling Support | TOR Argus Support Contract - Q2 2027 | 2027-04-01 | 2027-06-30 | 63 | 63 | 63 | 0% | 1268 | Not Started
W196 | W196.25610 | HYA DPCS Defueling Support | Update LSR | 2027-04-02 | 2027-04-08 | 5 | 5 | 5 | 0% | 946 | Not Started
W527 | W527.25860 | DNB DPCS Defueling Support | LSR Data Export, Analysis, Draft Report | 2027-04-02 | 2027-04-22 | 15 | 15 | 15 | 0% | 1159 | Not Started
W526 | W526.1355 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q2 2027 | 2027-04-05 | 2027-06-30 | 61 | 61 | 61 | 0% | 1270 | Not Started
W526 | W526.1320 | HYB DPCS Defueling Support | HYB Argus Support Contract - Q2 2027 | 2027-04-05 | 2027-06-30 | 61 | 61 | 61 | 0% | 1270 | Not Started
W196 | W196.25620 | HYA DPCS Defueling Support | Issue LSR | 2027-04-09 | 2027-04-09 | 1 | 1 | 1 | 0% | 946 | Not Started
W526 | W526.4590 | HYB DPCS Defueling Support | HYB 2027 LSR - Recommendation Sentencing Workshop Preparation and Event | 2027-04-12 | 2027-04-23 | 10 | 10 | 10 | 0% | 1414 | Not Started
W526 | W526.10440 | HYB DPCS Defueling Support | HYB 2027 TGN097 R7 - Update and Issue Report | 2027-04-14 | 2027-04-20 | 5 | 5 | 5 | 0% | 1447 | Not Started
W529 | W529.6410 | TOR DPCS Defueling Support | TOR 2025 S14R1 - Delivery | 2027-04-19 | 2027-05-14 | 19 | 19 | 19 | 0% | 1387 | Not Started
W526 | W526.10450 | HYB DPCS Defueling Support | HYB 2027 TGN097 R7 - Report | 2027-04-21 | 2027-04-21 | 1 | 1 | 1 | 0% | 1447 | Not Started
W527 | W527.25780 | DNB DPCS Defueling Support | DNB 2027 2.11 - Installation R1 | 2027-04-22 | 2027-05-06 | 10 | 10 | 10 | 0% | 1152 | Not Started
W527 | W527.25870 | DNB DPCS Defueling Support | Issue Recommendations | 2027-04-23 | 2027-04-23 | 1 | 1 | 1 | 0% | 1159 | Not Started
W529 | W529.4610 | TOR DPCS Defueling Support | TOR 2027 LSR - Data Export Produced and Issued | 2027-04-26 | 2027-05-24 | 20 | 20 | 20 | 0% | 1374 | Not Started
W526 | W526.4580 | HYB DPCS Defueling Support | HYB 2027 LSR - Draft Report Produced and Issued for EDF Review | 2027-04-26 | 2027-05-11 | 11 | 11 | 11 | 0% | 1414 | Not Started
W526 | W526.10590 | HYB DPCS Defueling Support | HYB 2027 S14R7 - Delivery | 2027-04-26 | 2027-05-27 | 23 | 23 | 23 | 0% | 1377 | Not Started
W527 | W527.25880 | DNB DPCS Defueling Support | Recommendations Workshop | 2027-04-29 | 2027-04-29 | 1 | 1 | 1 | 0% | 1159 | Not Started
W527 | W527.25890 | DNB DPCS Defueling Support | LSR Update, Internal Review & Issue to EDF | 2027-04-30 | 2027-05-14 | 10 | 10 | 10 | 0% | 1159 | Not Started
W526 | W526.4570 | HYB DPCS Defueling Support | HYB 2027 LSR - EDF Review Comments Produced and Provided | 2027-05-12 | 2027-05-26 | 11 | 11 | 11 | 0% | 1414 | Not Started
W529 | W529.6420 | TOR DPCS Defueling Support | TOR 2025 S14R1 - Installation R1 | 2027-05-17 | 2027-07-16 | 44 | 44 | 44 | 0% | 1387 | Not Started
W527 | W527.25900 | DNB DPCS Defueling Support | EDF Review | 2027-05-17 | 2027-05-28 | 10 | 10 | 10 | 0% | 1159 | Not Started
W529 | W529.4600 | TOR DPCS Defueling Support | TOR 2027 LSR - Recommendations Produced and Issued | 2027-05-25 | 2027-06-08 | 10 | 10 | 10 | 0% | 1374 | Not Started
W526 | W526.4560 | HYB DPCS Defueling Support | HYB 2027 LSR - Final Report Produced and Issued | 2027-05-27 | 2027-06-09 | 9 | 9 | 9 | 0% | 1414 | Not Started
W527 | W527.25300 | DNB DPCS Defueling Support | Asset Guardian Licences and Support 2027 | 2027-05-28 | 2027-05-28 | 1 | 1 | 1 | 0% | 1165 | Not Started
W195 | W195.25800 | HRA DPCS Defueling Support | TGN097 R1 - Inspection | 2027-06-01 | 2027-06-07 | 5 | 5 | 5 | 0% | 857 | Not Started
W527 | W527.25910 | DNB DPCS Defueling Support | Update LSR | 2027-06-01 | 2027-06-07 | 5 | 5 | 5 | 0% | 1159 | Not Started
W527 | W527.25740 | DNB DPCS Defueling Support | DNB 2027 2.11 - Installation R2 | 2027-06-04 | 2027-06-17 | 10 | 10 | 10 | 0% | 1152 | Not Started
W195 | W195.25760 | HRA DPCS Defueling Support | HRA 2026 - Installation R1 | 2027-06-08 | 2027-06-30 | 17 | 17 | 17 | 0% | 890 | Not Started
W195 | W195.25830 | HRA DPCS Defueling Support | TGN097 R1 - Draft Report Produced, Internal Review and Issue to EDF | 2027-06-08 | 2027-06-21 | 10 | 10 | 10 | 0% | 857 | Not Started
W527 | W527.25920 | DNB DPCS Defueling Support | Issue Complete LSR | 2027-06-08 | 2027-06-08 | 1 | 1 | 1 | 0% | 1159 | Not Started
W529 | W529.4590 | TOR DPCS Defueling Support | TOR 2027 LSR - Recommendation Sentencing Workshop Preparation and Event | 2027-06-09 | 2027-06-22 | 10 | 10 | 10 | 0% | 1374 | Not Started
W196 | W195.1030 | HYA DPCS Defueling Support | HYA 2026 - Installation R1 | 2027-06-10 | 2027-06-30 | 15 | 15 | 15 | 0% | 890 | Not Started
W195 | W195.25820 | HRA DPCS Defueling Support | TGN097 R1 - EDF Review | 2027-06-22 | 2027-07-05 | 10 | 10 | 10 | 0% | 857 | Not Started
W529 | W529.4580 | TOR DPCS Defueling Support | TOR 2027 LSR - Draft Report Produced and Issued for EDF Review | 2027-06-23 | 2027-07-07 | 11 | 11 | 11 | 0% | 1374 | Not Started
W195 | W195.2480 | HRA DPCS Defueling Support | Thales Long Term Support Contract Q3 2027 | 2027-07-01 | 2027-09-30 | 65 | 65 | 65 | 0% | 759 | Not Started
W196 | W196.2490 | HYA DPCS Defueling Support | Thales Long Term Support Contract Q3 2027 | 2027-07-01 | 2027-09-30 | 65 | 65 | 65 | 0% | 825 | Not Started
W527 | W527.1812 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q3 2027 | 2027-07-01 | 2027-09-30 | 65 | 65 | 65 | 0% | 1078 | Not Started
W527 | W527.1809 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q3 2027 | 2027-07-01 | 2027-09-30 | 65 | 65 | 65 | 0% | 1078 | Not Started
W527 | W527.1815 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q3 2027 | 2027-07-01 | 2027-09-30 | 65 | 65 | 65 | 0% | 1078 | Not Started
W527 | W527.1817 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q3 2027 | 2027-07-01 | 2027-09-30 | 65 | 65 | 65 | 0% | 1078 | Not Started
W529 | W529.1330 | TOR DPCS Defueling Support | TOR Argus Support Contract - Q3 2027 | 2027-07-01 | 2027-09-30 | 65 | 65 | 65 | 0% | 1268 | Not Started
W529 | W529.1365 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q3 2027 | 2027-07-01 | 2027-09-30 | 65 | 65 | 65 | 0% | 1268 | Not Started
W526 | W526.1335 | HYB DPCS Defueling Support | HYB Argus Support Contract - Q3 2027 | 2027-07-01 | 2027-09-30 | 65 | 65 | 65 | 0% | 1270 | Not Started
W526 | W526.1365 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q3 2027 | 2027-07-01 | 2027-09-30 | 65 | 65 | 65 | 0% | 1270 | Not Started
W526 | W526.10240 | HYB DPCS Defueling Support | HYB 2026 LSR Pre Data Extract | 2027-07-01 | 2027-07-07 | 5 | 5 | 5 | 0% | 1332 | Not Started
W529 | W529.10180 | TOR DPCS Defueling Support | TOR 2027 S14R2 - Specification | 2027-07-01 | 2027-12-10 | 116 | 116 | 116 | 0% | 1176 | Not Started
W529 | W529.4570 | TOR DPCS Defueling Support | TOR 2027 LSR - EDF Review Comments Produced and Provided | 2027-07-08 | 2027-07-22 | 11 | 11 | 11 | 0% | 1374 | Not Started
W529 | W529.4560 | TOR DPCS Defueling Support | TOR 2027 LSR - Final Report Produced and Issued | 2027-07-23 | 2027-08-04 | 9 | 9 | 9 | 0% | 1374 | Not Started
W526 | W526.10250 | HYB DPCS Defueling Support | HYB 2026 LSR Data Export, Analysis, Draft Report | 2027-07-29 | 2027-08-18 | 15 | 15 | 15 | 0% | 1332 | Not Started
W526 | W526.10610 | HYB DPCS Defueling Support | HYB 2027 S14R7 - Installation R7 | 2027-07-30 | 2027-07-30 | 1 | 1 | 1 | 0% | 1377 | Not Started
W195 | W195.25810 | HRA DPCS Defueling Support | TGN097 R1 - Report Issue | 2027-08-10 | 2027-08-16 | 5 | 5 | 5 | 0% | 857 | Not Started
W526 | W526.10260 | HYB DPCS Defueling Support | HYB 2026 Issue Recommendations | 2027-08-19 | 2027-08-19 | 1 | 1 | 1 | 0% | 1332 | Not Started
W526 | W526.10270 | HYB DPCS Defueling Support | HYB 2026 Recommendations Workshop | 2027-08-26 | 2027-08-26 | 1 | 1 | 1 | 0% | 1332 | Not Started
W526 | W526.10280 | HYB DPCS Defueling Support | HYB 2026 LSR Update, Internal Review & Issue to EDF | 2027-08-27 | 2027-09-10 | 10 | 10 | 10 | 0% | 1332 | Not Started
W195 | W195.25980 | HRA DPCS Defueling Support | LSR Pre Data Extract | 2027-08-31 | 2027-09-06 | 5 | 5 | 5 | 0% | 781 | Not Started
W529 | W529.10100 | TOR DPCS Defueling Support | TGN097 R1 - Inspection | 2027-08-31 | 2027-09-06 | 5 | 5 | 5 | 0% | 1323 | Not Started
W529 | W529.10130 | TOR DPCS Defueling Support | TGN097 R1 - Draft Report Produced, Internal Review and Issue to EDF | 2027-09-07 | 2027-09-20 | 10 | 10 | 10 | 0% | 1323 | Not Started
W196 | W195.1050 | HYA DPCS Defueling Support | HYA 2026 - Installation R2 | 2027-09-10 | 2027-09-30 | 15 | 15 | 15 | 0% | 825 | Not Started
W195 | W195.25770 | HRA DPCS Defueling Support | HRA 2026 - Installation R2 | 2027-09-13 | 2027-09-30 | 14 | 14 | 14 | 0% | 825 | Not Started
W526 | W526.10290 | HYB DPCS Defueling Support | HYB 2026 EDF Review | 2027-09-13 | 2027-09-24 | 10 | 10 | 10 | 0% | 1332 | Not Started
W529 | W529.10120 | TOR DPCS Defueling Support | TGN097 R1 - EDF Review | 2027-09-21 | 2027-10-04 | 10 | 10 | 10 | 0% | 1323 | Not Started
W195 | W195.25990 | HRA DPCS Defueling Support | LSR Data Export, Analysis, Draft Report | 2027-09-27 | 2027-10-15 | 15 | 15 | 15 | 0% | 781 | Not Started
W526 | W526.10300 | HYB DPCS Defueling Support | HYB 2026 Update LSR | 2027-09-27 | 2027-10-01 | 5 | 5 | 5 | 0% | 1332 | Not Started
W195 | W195.2490 | HRA DPCS Defueling Support | Thales Long Term Support Contract Q4 2027 | 2027-10-01 | 2027-12-31 | 66 | 66 | 66 | 0% | 759 | Not Started
W196 | W196.2500 | HYA DPCS Defueling Support | Thales Long Term Support Contract Q4 2027 | 2027-10-01 | 2027-12-31 | 66 | 66 | 66 | 0% | 759 | Not Started
W527 | W527.1880 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q4 2027 | 2027-10-01 | 2027-12-31 | 66 | 66 | 66 | 0% | 1012 | Not Started
W527 | W527.1883 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q4 2027 | 2027-10-01 | 2027-12-31 | 66 | 66 | 66 | 0% | 1012 | Not Started
W527 | W527.1885 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q4 2027 | 2027-10-01 | 2027-12-31 | 66 | 66 | 66 | 0% | 1012 | Not Started
W527 | W527.1888 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q4 2027 | 2027-10-01 | 2027-12-31 | 66 | 66 | 66 | 0% | 1012 | Not Started
W529 | W529.1375 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q4 2027 | 2027-10-01 | 2027-12-31 | 66 | 66 | 66 | 0% | 1268 | Not Started
W529 | W529.1335 | TOR DPCS Defueling Support | TOR Argus Support Contract - Q4 2027 | 2027-10-01 | 2027-12-31 | 66 | 66 | 66 | 0% | 1268 | Not Started
W526 | W526.1375 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q4 2027 | 2027-10-01 | 2027-12-29 | 64 | 64 | 64 | 0% | 1270 | Not Started
W526 | W526.1330 | HYB DPCS Defueling Support | HYB Argus Support Contract - Q4 2027 | 2027-10-01 | 2027-12-29 | 64 | 64 | 64 | 0% | 1270 | Not Started
W526 | W526.10310 | HYB DPCS Defueling Support | HYB 2026 Issue Complete LSR | 2027-10-04 | 2027-10-04 | 1 | 1 | 1 | 0% | 1332 | Not Started
W529 | W529.10110 | TOR DPCS Defueling Support | TGN097 R1 - Update and Issue Report | 2027-10-11 | 2027-10-15 | 5 | 5 | 5 | 0% | 1323 | Not Started
W195 | W195.26000 | HRA DPCS Defueling Support | Issue Recommendations | 2027-10-18 | 2027-10-18 | 1 | 1 | 1 | 0% | 781 | Not Started
W195 | W195.26010 | HRA DPCS Defueling Support | Recommendations Workshop | 2027-10-26 | 2027-10-26 | 1 | 1 | 1 | 0% | 781 | Not Started
W195 | W195.26020 | HRA DPCS Defueling Support | LSR Update, Internal Review & Issue to EDF | 2027-10-27 | 2027-10-27 | 1 | 1 | 1 | 0% | 781 | Not Started
W195 | W195.26030 | HRA DPCS Defueling Support | EDF Review | 2027-11-10 | 2027-11-23 | 10 | 10 | 10 | 0% | 781 | Not Started
W195 | W195.26040 | HRA DPCS Defueling Support | Update LSR | 2027-11-24 | 2027-11-30 | 5 | 5 | 5 | 0% | 781 | Not Started
W195 | W195.26050 | HRA DPCS Defueling Support | Issue Complete LSR | 2027-12-01 | 2027-12-01 | 1 | 1 | 1 | 0% | 781 | Not Started
W529 | W529.10190 | TOR DPCS Defueling Support | TOR 2027 S14R2 - Testing | 2027-12-13 | 2028-03-17 | 70 | 70 | 70 | 0% | 1176 | Not Started
W529 | W529.3080 | TOR DPCS Defueling Support | TOR 2029 Defueling Software Build | 2028-01-03 | 2028-11-27 | 231 | 231 | 231 | 0% | 1015 | Not Started
W529 | W529.3060 | TOR DPCS Defueling Support | TOR 2028 Defueling Software Build | 2028-01-03 | 2028-11-29 | 233 | 233 | 233 | 0% | 782 | Not Started
W529 | W529.1385 | TOR DPCS Defueling Support | TOR Argus Support Contract - Q1 2028 Delivery | 2028-01-03 | 2028-03-31 | 65 | 65 | 65 | 0% | 1015 | Not Started
W529 | W529.1425 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q1 2028 Delivery | 2028-01-03 | 2028-03-31 | 65 | 65 | 65 | 0% | 1015 | Not Started
W529 | W529.3090 | TOR DPCS Defueling Support | TOR DPCS Long Term Support Contract 2029 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 1015 | Not Started
W529 | W529.1100 | TOR DPCS Defueling Support | TOR PES Group Support - 2028 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 1015 | Not Started
W529 | W529.1110 | TOR DPCS Defueling Support | TOR Plant Control Systems & Simulators (PCS&S) Group - 2028 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 1015 | Not Started
W529 | W529.4690 | TOR DPCS Defueling Support | TOR 2028 LSR - Pre-export Data Validation Produced and Completed | 2028-01-03 | 2028-02-23 | 38 | 38 | 38 | 0% | 1015 | Not Started
W526 | W526.4690 | HYB DPCS Defueling Support | HYB 2028 LSR - Pre-export Data Validation Produced and Completed | 2028-01-03 | 2028-02-23 | 38 | 38 | 38 | 0% | 1159 | Not Started
W526 | W526.1380 | HYB DPCS Defueling Support | HYB Argus Support Contract - Q1 2028 | 2028-01-03 | 2028-03-31 | 65 | 65 | 65 | 0% | 1015 | Not Started
W526 | W526.1110 | HYB DPCS Defueling Support | HYB Plant Control Systems & Simulators (PCS&S) Group - 2028 | 2028-01-03 | 2028-12-08 | 240 | 240 | 240 | 0% | 1015 | Not Started
W526 | W526.1100 | HYB DPCS Defueling Support | HYB PES Group Support - 2028 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 1015 | Not Started
W526 | W526.3070 | HYB DPCS Defueling Support | HYB DPCS Long Term Support Contract 2028 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 1015 | Not Started
W526 | W526.1425 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q1 2028 | 2028-01-03 | 2028-03-31 | 65 | 65 | 65 | 0% | 1015 | Not Started
W526 | W526.3040 | HYB DPCS Defueling Support | HYB 2027 Defueling Software Build | 2028-01-03 | 2028-11-28 | 232 | 232 | 232 | 0% | 1036 | Not Started
W526 | W526.3060 | HYB DPCS Defueling Support | HYB 2028 Defueling Software Build | 2028-01-03 | 2028-11-29 | 233 | 233 | 233 | 0% | 1015 | Not Started
W526 | W526.10030 | HYB DPCS Defueling Support | HYB 2028 External Costs | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 1015 | Not Started
W529 | W529.10030 | TOR DPCS Defueling Support | TOR 2028 External Costs | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 1015 | Not Started
W526 | W526.10190 | HYB DPCS Defueling Support | TPM and JCRB Meeting Held 2028 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 0 | Not Started
W527 | W527.26020 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q1 2028 | 2028-01-03 | 2028-03-31 | 65 | 65 | 65 | 0% | 756 | Not Started
W527 | W527.26040 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q1 2028 | 2028-01-03 | 2028-03-27 | 61 | 61 | 61 | 0% | 951 | Not Started
W527 | W527.26080 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q1 2028 | 2028-01-03 | 2028-03-27 | 61 | 61 | 61 | 0% | 951 | Not Started
W527 | W527.26130 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q1 2028 | 2028-01-03 | 2028-03-27 | 61 | 61 | 61 | 0% | 951 | Not Started
W527 | W527.26190 | DNB DPCS Defueling Support | Cost Engineer Support 2028 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 759 | Not Started
W527 | W527.26390 | DNB DPCS Defueling Support | DNB PES Group Support - 2028 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 759 | Not Started
W527 | W527.26400 | DNB DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2028 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 759 | Not Started
W195 | W195.26090 | HRA DPCS Defueling Support | ETC 2028 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 0 | Not Started
W195 | W194.1000 | HRA DPCS Defueling Support | HRA PES Group Support - 2028 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 506 | Not Started
W195 | W194.1010 | HRA DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2028 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 506 | Not Started
W196 | W196.2110 | HYA DPCS Defueling Support | ETC 2028 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 0 | Not Started
W196 | W194.1000 | HYA DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2028 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 0 | Not Started
W196 | W194.1010 | HYA DPCS Defueling Support | HYA PES Group Support - 2028 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 0 | Not Started
W527 | W527.1150 | DNB DPCS Defueling Support | ETC 2028 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 0 | Not Started
W529 | 40 | TOR DPCS Defueling Support | ETC 2028 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 1015 | Not Started
W529 | W195.1030 | TOR DPCS Defueling Support | TPM and JCRB Meetings Held - 2028 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 0 | Not Started
W526 | W526.1220 | HYB DPCS Defueling Support | ETC 2028 | 2028-01-03 | 2028-12-29 | 253 | 253 | 253 | 0% | 0 | Not Started
W529 | W529.4680 | TOR DPCS Defueling Support | TOR 2028 LSR - Data Export Produced and Issued | 2028-02-24 | 2028-03-22 | 20 | 20 | 20 | 0% | 1159 | Not Started
W526 | W526.4680 | HYB DPCS Defueling Support | HYB 2028 LSR - Data Export Produced and Issued | 2028-02-24 | 2028-03-22 | 20 | 20 | 20 | 0% | 1159 | Not Started
W529 | W529.10200 | TOR DPCS Defueling Support | TOR 2027 S14R2 - Delivery | 2028-03-20 | 2028-04-13 | 19 | 19 | 19 | 0% | 1176 | Not Started
W529 | W529.4670 | TOR DPCS Defueling Support | TOR 2028 LSR - Recommendations Produced and Issued | 2028-03-23 | 2028-04-05 | 10 | 10 | 10 | 0% | 1159 | Not Started
W526 | W526.4670 | HYB DPCS Defueling Support | HYB 2028 LSR - Recommendations Produced and Issued | 2028-03-23 | 2028-04-05 | 10 | 10 | 10 | 0% | 1159 | Not Started
W529 | W529.1395 | TOR DPCS Defueling Support | TOR Argus Support Contract - Q2 2028 | 2028-04-03 | 2028-06-30 | 61 | 61 | 61 | 0% | 1015 | Not Started
W529 | W529.1435 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q2 2028 | 2028-04-03 | 2028-06-30 | 61 | 61 | 61 | 0% | 1015 | Not Started
W526 | W526.1390 | HYB DPCS Defueling Support | HYB Argus Support Contract - Q2 2028 | 2028-04-03 | 2028-06-30 | 61 | 61 | 61 | 0% | 1015 | Not Started
W526 | W526.1435 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q2 2028 | 2028-04-03 | 2028-06-30 | 61 | 61 | 61 | 0% | 1015 | Not Started
W527 | W527.26030 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q2 2028 | 2028-04-03 | 2028-07-04 | 63 | 63 | 63 | 0% | 884 | Not Started
W527 | W527.26100 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q2 2028 | 2028-04-03 | 2028-06-30 | 61 | 61 | 61 | 0% | 756 | Not Started
W527 | W527.26120 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q2 2028 | 2028-04-03 | 2028-07-04 | 63 | 63 | 63 | 0% | 884 | Not Started
W527 | W527.26160 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q2 2028 | 2028-04-03 | 2028-07-04 | 63 | 63 | 63 | 0% | 884 | Not Started
W529 | W529.4660 | TOR DPCS Defueling Support | TOR 2028 LSR - Recommendation Sentencing Workshop Preparation and Event | 2028-04-06 | 2028-04-21 | 10 | 10 | 10 | 0% | 1159 | Not Started
W526 | W526.4660 | HYB DPCS Defueling Support | HYB 2028 LSR - Recommendation Sentencing Workshop Preparation and Event | 2028-04-06 | 2028-04-21 | 10 | 10 | 10 | 0% | 1159 | Not Started
W529 | W529.10210 | TOR DPCS Defueling Support | TOR 2027 S14R2 - Installation R2 | 2028-04-18 | 2028-05-12 | 18 | 18 | 18 | 0% | 1176 | Not Started
W529 | W529.4650 | TOR DPCS Defueling Support | TOR 2028 LSR - Draft Report Produced and Issued for EDF Review | 2028-04-24 | 2028-05-09 | 11 | 11 | 11 | 0% | 1159 | Not Started
W526 | W526.4650 | HYB DPCS Defueling Support | HYB 2028 LSR - Draft Report Produced and Issued for EDF Review | 2028-04-24 | 2028-05-09 | 11 | 11 | 11 | 0% | 1159 | Not Started
W527 | W527.26200 | DNB DPCS Defueling Support | Asset Guardian Licences and Support 2028 | 2028-05-02 | 2028-05-02 | 1 | 1 | 1 | 0% | 928 | Not Started
W529 | W529.4640 | TOR DPCS Defueling Support | TOR 2028 LSR - EDF Review Comments Produced and Provided | 2028-05-10 | 2028-05-24 | 11 | 11 | 11 | 0% | 1159 | Not Started
W526 | W526.4640 | HYB DPCS Defueling Support | HYB 2028 LSR - EDF Review Comments Produced and Provided | 2028-05-10 | 2028-05-24 | 11 | 11 | 11 | 0% | 1159 | Not Started
W529 | W529.4630 | TOR DPCS Defueling Support | TOR 2028 LSR - Final Report Produced and Issued | 2028-05-25 | 2028-06-07 | 9 | 9 | 9 | 0% | 1159 | Not Started
W526 | W526.4630 | HYB DPCS Defueling Support | HYB 2028 LSR - Final Report Produced and Issued | 2028-05-25 | 2028-06-07 | 9 | 9 | 9 | 0% | 1159 | Not Started
W529 | W529.1405 | TOR DPCS Defueling Support | TOR Argus Support Contract - Q3 2028 | 2028-07-03 | 2028-09-29 | 64 | 64 | 64 | 0% | 1015 | Not Started
W529 | W529.1445 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q3 2028 | 2028-07-03 | 2028-09-29 | 64 | 64 | 64 | 0% | 1015 | Not Started
W526 | W526.1400 | HYB DPCS Defueling Support | HYB Argus Support Contract - Q3 2028 | 2028-07-03 | 2028-09-29 | 64 | 64 | 64 | 0% | 1015 | Not Started
W526 | W526.1445 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q3 2028 | 2028-07-03 | 2028-09-29 | 64 | 64 | 64 | 0% | 1015 | Not Started
W527 | W527.26070 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q3 2028 | 2028-07-03 | 2028-10-02 | 65 | 65 | 65 | 0% | 821 | Not Started
W527 | W527.26090 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q3 2028 | 2028-07-03 | 2028-09-29 | 64 | 64 | 64 | 0% | 756 | Not Started
W527 | W527.26150 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q3 2028 | 2028-07-03 | 2028-10-02 | 65 | 65 | 65 | 0% | 821 | Not Started
W527 | W527.26170 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q3 2028 | 2028-07-03 | 2028-10-02 | 65 | 65 | 65 | 0% | 821 | Not Started
W529 | W529.1415 | TOR DPCS Defueling Support | TOR Argus Support Contract - Q4 2028 | 2028-10-02 | 2028-12-29 | 63 | 63 | 63 | 0% | 1015 | Not Started
W529 | W529.1455 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q4 2028 | 2028-10-02 | 2028-12-29 | 63 | 63 | 63 | 0% | 1015 | Not Started
W526 | W526.1410 | HYB DPCS Defueling Support | HYB Argus Support Contract - Q4 2028 | 2028-10-02 | 2028-12-29 | 63 | 63 | 63 | 0% | 1015 | Not Started
W526 | W526.1455 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q4 | 2028-10-02 | 2028-12-29 | 63 | 63 | 63 | 0% | 1015 | Not Started
W527 | W527.26010 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q4 2028 | 2028-10-02 | 2028-12-29 | 63 | 63 | 63 | 0% | 756 | Not Started
W527 | W527.26110 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q4 2028 | 2028-10-02 | 2029-01-04 | 66 | 66 | 66 | 0% | 756 | Not Started
W527 | W527.26140 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q4 2028 | 2028-10-02 | 2029-01-04 | 66 | 66 | 66 | 0% | 756 | Not Started
W527 | W527.26180 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q4 2028 | 2028-10-02 | 2029-01-04 | 66 | 66 | 66 | 0% | 756 | Not Started
W529 | W529.3070 | TOR DPCS Defueling Support | TOR DPCS Long Term Support Contract 2028 | 2028-11-30 | 2029-11-29 | 253 | 253 | 253 | 0% | 782 | Not Started
W529 | W529.1120 | TOR DPCS Defueling Support | TOR PES Group Support - 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 762 | Not Started
W529 | W529.1130 | TOR DPCS Defueling Support | TOR Plant Control Systems & Simulators (PCS&S) Group - 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 762 | Not Started
W529 | W529.1465 | TOR DPCS Defueling Support | TOR Argus Support Contract - Q1 2029 | 2029-01-02 | 2029-03-29 | 63 | 63 | 63 | 0% | 762 | Not Started
W529 | W529.1505 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q1 2029 | 2029-01-02 | 2029-03-29 | 63 | 63 | 63 | 0% | 762 | Not Started
W529 | W529.4760 | TOR DPCS Defueling Support | TOR 2029 LSR - Pre-export Data Validation Produced and Completed | 2029-01-02 | 2029-02-22 | 38 | 38 | 38 | 0% | 906 | Not Started
W526 | W526.4760 | HYB DPCS Defueling Support | HYB 2029 LSR - Pre-export Data Validation Produced and Completed | 2029-01-02 | 2029-02-22 | 38 | 38 | 38 | 0% | 906 | Not Started
W526 | W526.1505 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q1 2029 | 2029-01-02 | 2029-03-29 | 63 | 63 | 63 | 0% | 762 | Not Started
W526 | W526.1465 | HYB DPCS Defueling Support | HYB Argus Support Contract - Q1 2029 | 2029-01-02 | 2029-03-29 | 63 | 63 | 63 | 0% | 762 | Not Started
W526 | W526.1130 | HYB DPCS Defueling Support | HYB Plant Control Systems & Simulators (PCS&S) Group - 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 762 | Not Started
W526 | W526.1120 | HYB DPCS Defueling Support | HYB PES Group Support - 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 762 | Not Started
W526 | W526.3090 | HYB DPCS Defueling Support | HYB DPCS Long Term Support Contract 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 762 | Not Started
W526 | W526.3080 | HYB DPCS Defueling Support | HYB 2029 Defueling Software Build | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 762 | Not Started
W526 | W526.10040 | HYB DPCS Defueling Support | HYB 2029 External Costs | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 762 | Not Started
W529 | W529.10040 | TOR DPCS Defueling Support | TOR 2029 External Costs | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 762 | Not Started
W526 | W526.10200 | HYB DPCS Defueling Support | TPM and JCRB Meeting Held 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W527 | W527.26050 | DNB DPCS Defueling Support | DNB PES Group Support - 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 506 | Not Started
W527 | W527.26060 | DNB DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 506 | Not Started
W527 | W527.26360 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q1 2029 | 2029-01-02 | 2029-03-27 | 61 | 61 | 61 | 0% | 506 | Not Started
W527 | W527.26380 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q1 2029 | 2029-01-02 | 2029-03-27 | 61 | 61 | 61 | 0% | 506 | Not Started
W527 | W527.26420 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q1 2029 | 2029-01-02 | 2029-03-27 | 61 | 61 | 61 | 0% | 506 | Not Started
W527 | W527.26470 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q1 2029 | 2029-01-02 | 2029-03-27 | 61 | 61 | 61 | 0% | 506 | Not Started
W527 | W527.26530 | DNB DPCS Defueling Support | Cost Engineer Support 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 506 | Not Started
W195 | W195.26100 | HRA DPCS Defueling Support | ETC 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W195 | W194.1020 | HRA DPCS Defueling Support | HRA PES Group Support - 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 253 | Not Started
W195 | W194.1030 | HRA DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W196 | W196.2120 | HYA DPCS Defueling Support | ETC 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W196 | W194.1020 | HYA DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W196 | W194.1030 | HYA DPCS Defueling Support | HYA PES Group Support - 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W527 | W527.1160 | DNB DPCS Defueling Support | ETC 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W529 | 50 | TOR DPCS Defueling Support | ETC 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 762 | Not Started
W529 | W195.1040 | TOR DPCS Defueling Support | TPM and JCRB Meetings Held - 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W526 | W526.1230 | HYB DPCS Defueling Support | ETC 2029 | 2029-01-02 | 2029-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W529 | W529.4750 | TOR DPCS Defueling Support | TOR 2029 LSR - Data Export Produced and Issued | 2029-02-23 | 2029-03-22 | 20 | 20 | 20 | 0% | 906 | Not Started
W526 | W526.4750 | HYB DPCS Defueling Support | HYB 2029 LSR - Data Export Produced and Issued | 2029-02-23 | 2029-03-22 | 20 | 20 | 20 | 0% | 906 | Not Started
W529 | W529.4740 | TOR DPCS Defueling Support | TOR 2029 LSR - Recommendations Produced and Issued | 2029-03-23 | 2029-04-09 | 10 | 10 | 10 | 0% | 906 | Not Started
W526 | W526.4740 | HYB DPCS Defueling Support | HYB 2029 LSR - Recommendations Produced and Issued | 2029-03-23 | 2029-04-09 | 10 | 10 | 10 | 0% | 906 | Not Started
W527 | W527.26370 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q2 2029 | 2029-03-28 | 2029-06-28 | 63 | 63 | 63 | 0% | 506 | Not Started
W527 | W527.26440 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q2 2029 | 2029-03-28 | 2029-06-28 | 63 | 63 | 63 | 0% | 506 | Not Started
W527 | W527.26460 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q2 2029 | 2029-03-28 | 2029-06-28 | 63 | 63 | 63 | 0% | 506 | Not Started
W527 | W527.26500 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q2 2029 | 2029-03-28 | 2029-06-28 | 63 | 63 | 63 | 0% | 506 | Not Started
W529 | W529.1475 | TOR DPCS Defueling Support | TOR Argus Support Contract - Q2 2029 | 2029-04-03 | 2029-06-29 | 62 | 62 | 62 | 0% | 762 | Not Started
W529 | W529.1515 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q2 2029 | 2029-04-03 | 2029-06-29 | 62 | 62 | 62 | 0% | 762 | Not Started
W526 | W526.1515 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q2 2029 | 2029-04-03 | 2029-06-29 | 62 | 62 | 62 | 0% | 762 | Not Started
W526 | W526.1475 | HYB DPCS Defueling Support | HYB Argus Support Contract - Q2 2029 | 2029-04-03 | 2029-06-29 | 62 | 62 | 62 | 0% | 762 | Not Started
W529 | W529.4730 | TOR DPCS Defueling Support | TOR 2029 LSR - Recommendation Sentencing Workshop Preparation and Event | 2029-04-10 | 2029-04-23 | 10 | 10 | 10 | 0% | 906 | Not Started
W526 | W526.4730 | HYB DPCS Defueling Support | HYB 2029 LSR - Recommendation Sentencing Workshop Preparation and Event | 2029-04-10 | 2029-04-23 | 10 | 10 | 10 | 0% | 906 | Not Started
W529 | W529.4720 | TOR DPCS Defueling Support | TOR 2029 LSR - Draft Report Produced and Issued for EDF Review | 2029-04-24 | 2029-05-09 | 11 | 11 | 11 | 0% | 906 | Not Started
W526 | W526.4720 | HYB DPCS Defueling Support | HYB 2029 LSR - Draft Report Produced and Issued for EDF Review | 2029-04-24 | 2029-05-09 | 11 | 11 | 11 | 0% | 906 | Not Started
W527 | W527.26540 | DNB DPCS Defueling Support | Asset Guardian Licences and Support 2029 | 2029-05-01 | 2029-05-01 | 1 | 1 | 1 | 0% | 675 | Not Started
W529 | W529.4710 | TOR DPCS Defueling Support | TOR 2029 LSR - EDF Review Comments Produced and Provided | 2029-05-10 | 2029-05-24 | 11 | 11 | 11 | 0% | 906 | Not Started
W526 | W526.4710 | HYB DPCS Defueling Support | HYB 2029 LSR - EDF Review Comments Produced and Provided | 2029-05-10 | 2029-05-24 | 11 | 11 | 11 | 0% | 906 | Not Started
W529 | W529.4700 | TOR DPCS Defueling Support | TOR 2029 LSR - Final Report Produced and Issued | 2029-05-25 | 2029-06-07 | 9 | 9 | 9 | 0% | 906 | Not Started
W526 | W526.4700 | HYB DPCS Defueling Support | HYB 2029 LSR - Final Report Produced and Issued | 2029-05-25 | 2029-06-07 | 9 | 9 | 9 | 0% | 906 | Not Started
W527 | W527.26410 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q3 2027 | 2029-06-29 | 2029-09-28 | 65 | 65 | 65 | 0% | 506 | Not Started
W527 | W527.26430 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q3 2028 | 2029-06-29 | 2029-09-28 | 65 | 65 | 65 | 0% | 506 | Not Started
W527 | W527.26490 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q3 2029 | 2029-06-29 | 2029-09-28 | 65 | 65 | 65 | 0% | 506 | Not Started
W527 | W527.26510 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q3 2029 | 2029-06-29 | 2029-09-28 | 65 | 65 | 65 | 0% | 506 | Not Started
W529 | W529.1485 | TOR DPCS Defueling Support | TOR Argus Support Contract - Q3 2029 | 2029-07-02 | 2029-09-28 | 64 | 64 | 64 | 0% | 762 | Not Started
W529 | W529.1525 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q3 2029 | 2029-07-02 | 2029-09-28 | 64 | 64 | 64 | 0% | 762 | Not Started
W526 | W526.1525 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q3 2029 | 2029-07-02 | 2029-09-28 | 64 | 64 | 64 | 0% | 762 | Not Started
W526 | W526.1485 | HYB DPCS Defueling Support | HYB Argus Support Contract - Q3 2029 | 2029-07-02 | 2029-09-28 | 64 | 64 | 64 | 0% | 762 | Not Started
W529 | W529.1495 | TOR DPCS Defueling Support | TOR Argus Support Contract - Q4 2029 | 2029-10-01 | 2029-12-31 | 64 | 64 | 64 | 0% | 762 | Not Started
W529 | W529.1535 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q4 2029 | 2029-10-01 | 2029-12-31 | 64 | 64 | 64 | 0% | 762 | Not Started
W526 | W526.1535 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q4 2029 | 2029-10-01 | 2029-12-31 | 64 | 64 | 64 | 0% | 762 | Not Started
W526 | W526.1495 | HYB DPCS Defueling Support | HYB Argus Support Contract - Q4 2029 | 2029-10-01 | 2029-12-31 | 64 | 64 | 64 | 0% | 762 | Not Started
W527 | W527.26350 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q4 2029 | 2029-10-01 | 2029-12-31 | 64 | 64 | 64 | 0% | 506 | Not Started
W527 | W527.26450 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q4 2029 | 2029-10-01 | 2029-12-31 | 64 | 64 | 64 | 0% | 506 | Not Started
W527 | W527.26480 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q4 2029 | 2029-10-01 | 2029-12-31 | 64 | 64 | 64 | 0% | 506 | Not Started
W527 | W527.26520 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q4 2029 | 2029-10-01 | 2029-12-31 | 64 | 64 | 64 | 0% | 506 | Not Started
W529 | W529.3100 | TOR DPCS Defueling Support | TOR 2030 Defueling Software Build | 2030-01-02 | 2030-11-27 | 231 | 231 | 231 | 0% | 509 | Not Started
W529 | W529.3110 | TOR DPCS Defueling Support | TOR DPCS Long Term Support Contract 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 509 | Not Started
W529 | W529.1140 | TOR DPCS Defueling Support | TOR PES Group Support - 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 509 | Not Started
W529 | W529.1150 | TOR DPCS Defueling Support | TOR Plant Control Systems & Simulators (PCS&S) Group - 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 509 | Not Started
W529 | W529.1545 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q1 2030 | 2030-01-02 | 2030-03-29 | 63 | 63 | 63 | 0% | 509 | Not Started
W529 | W529.4830 | TOR DPCS Defueling Support | TOR 2030 LSR - Pre-export Data Validation Produced and Completed | 2030-01-02 | 2030-02-22 | 38 | 38 | 38 | 0% | 653 | Not Started
W526 | W526.4830 | HYB DPCS Defueling Support | HYB 2030 LSR - Pre-export Data Validation Produced and Completed | 2030-01-02 | 2030-02-22 | 38 | 38 | 38 | 0% | 653 | Not Started
W526 | W526.1545 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q1 2030 | 2030-01-02 | 2030-03-29 | 63 | 63 | 63 | 0% | 509 | Not Started
W526 | W526.1150 | HYB DPCS Defueling Support | HYB Plant Control Systems & Simulators (PCS&S) Group - 2030 | 2030-01-02 | 2030-12-10 | 240 | 240 | 240 | 0% | 509 | Not Started
W526 | W526.1140 | HYB DPCS Defueling Support | HYB PES Group Support - 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 509 | Not Started
W526 | W526.3110 | HYB DPCS Defueling Support | HYB DPCS Long Term Support Contract 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 509 | Not Started
W526 | W526.3100 | HYB DPCS Defueling Support | HYB 2030 Defueling Software Build | 2030-01-02 | 2030-11-27 | 231 | 231 | 231 | 0% | 509 | Not Started
W526 | W526.10050 | HYB DPCS Defueling Support | HYB 2030 External Costs | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 509 | Not Started
W529 | W529.10050 | TOR DPCS Defueling Support | TOR 2030 External Costs | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 509 | Not Started
W526 | W526.10210 | HYB DPCS Defueling Support | TPM and JCRB Meeting Held 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W527 | W527.26630 | DNB DPCS Defueling Support | DNB PES Group Support - 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W527 | W527.26640 | DNB DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W527 | W527.26660 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q1 2030 | 2030-01-02 | 2030-03-27 | 61 | 61 | 61 | 0% | 0 | Not Started
W527 | W527.26680 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q1 2030 | 2030-01-02 | 2030-03-27 | 61 | 61 | 61 | 0% | 0 | Not Started
W527 | W527.26700 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q1 2030 | 2030-01-02 | 2030-03-27 | 61 | 61 | 61 | 0% | 0 | Not Started
W527 | W527.26750 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q1 2030 | 2030-01-02 | 2030-03-27 | 61 | 61 | 61 | 0% | 0 | Not Started
W527 | W527.26810 | DNB DPCS Defueling Support | Cost Engineer Support 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W195 | W195.26110 | HRA DPCS Defueling Support | ETC 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W195 | W194.1040 | HRA DPCS Defueling Support | HRA PES Group Support - 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W195 | W194.1050 | HRA DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W196 | W196.2350 | HYA DPCS Defueling Support | ETC 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W196 | W194.1040 | HYA DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W196 | W194.1050 | HYA DPCS Defueling Support | HYA PES Group Support - 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W527 | W527.1250 | DNB DPCS Defueling Support | ETC 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W529 | 60 | TOR DPCS Defueling Support | ETC 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 509 | Not Started
W529 | W195.1050 | TOR DPCS Defueling Support | TPM and JCRB Meetings Held - 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W526 | W526.1240 | HYB DPCS Defueling Support | ETC 2030 | 2030-01-02 | 2030-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W529 | W529.4820 | TOR DPCS Defueling Support | TOR 2030 LSR - Data Export Produced and Issued | 2030-02-25 | 2030-03-22 | 20 | 20 | 20 | 0% | 653 | Not Started
W526 | W526.4820 | HYB DPCS Defueling Support | HYB 2030 LSR - Data Export Produced and Issued | 2030-02-25 | 2030-03-22 | 20 | 20 | 20 | 0% | 653 | Not Started
W529 | W529.4810 | TOR DPCS Defueling Support | TOR 2030 LSR - Recommendations Produced and Issued | 2030-03-25 | 2030-04-05 | 10 | 10 | 10 | 0% | 653 | Not Started
W526 | W526.4810 | HYB DPCS Defueling Support | HYB 2030 LSR - Recommendations Produced and Issued | 2030-03-25 | 2030-04-05 | 10 | 10 | 10 | 0% | 653 | Not Started
W527 | W527.26670 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q2 2030 | 2030-03-28 | 2030-06-28 | 63 | 63 | 63 | 0% | 253 | Not Started
W527 | W527.26720 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q2 2030 | 2030-03-28 | 2030-06-28 | 63 | 63 | 63 | 0% | 253 | Not Started
W527 | W527.26740 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q2 2030 | 2030-03-28 | 2030-06-28 | 63 | 63 | 63 | 0% | 253 | Not Started
W527 | W527.26780 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q2 2030 | 2030-03-28 | 2030-06-28 | 63 | 63 | 63 | 0% | 253 | Not Started
W529 | W529.1555 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q2 2030 | 2030-04-01 | 2030-06-28 | 61 | 61 | 61 | 0% | 509 | Not Started
W526 | W526.1555 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q2 2030 | 2030-04-01 | 2030-06-28 | 61 | 61 | 61 | 0% | 509 | Not Started
W529 | W529.4800 | TOR DPCS Defueling Support | TOR 2030 LSR - Recommendation Sentencing Workshop Preparation and Event | 2030-04-08 | 2030-04-23 | 10 | 10 | 10 | 0% | 653 | Not Started
W526 | W526.4800 | HYB DPCS Defueling Support | HYB 2030 LSR - Recommendation Sentencing Workshop Preparation and Event | 2030-04-08 | 2030-04-23 | 10 | 10 | 10 | 0% | 653 | Not Started
W529 | W529.4790 | TOR DPCS Defueling Support | TOR 2030 LSR - Draft Report Produced and Issued for EDF Review | 2030-04-24 | 2030-05-09 | 11 | 11 | 11 | 0% | 653 | Not Started
W526 | W526.4790 | HYB DPCS Defueling Support | HYB 2030 LSR - Draft Report Produced and Issued for EDF Review | 2030-04-24 | 2030-05-09 | 11 | 11 | 11 | 0% | 653 | Not Started
W529 | W529.4780 | TOR DPCS Defueling Support | TOR 2030 LSR - EDF Review Comments Produced and Provided | 2030-05-10 | 2030-05-24 | 11 | 11 | 11 | 0% | 653 | Not Started
W526 | W526.4780 | HYB DPCS Defueling Support | HYB 2030 LSR - EDF Review Comments Produced and Provided | 2030-05-10 | 2030-05-24 | 11 | 11 | 11 | 0% | 653 | Not Started
W529 | W529.4770 | TOR DPCS Defueling Support | TOR 2030 LSR - Final Report Produced and Issued | 2030-05-28 | 2030-06-07 | 9 | 9 | 9 | 0% | 653 | Not Started
W526 | W526.4770 | HYB DPCS Defueling Support | HYB 2030 LSR - Final Report Produced and Issued | 2030-05-28 | 2030-06-07 | 9 | 9 | 9 | 0% | 653 | Not Started
W527 | W527.26820 | DNB DPCS Defueling Support | Asset Guardian Licences and Support 2030 | 2030-05-28 | 2030-05-28 | 1 | 1 | 1 | 0% | 405 | Not Started
W529 | W529.1565 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q3 2030 | 2030-07-01 | 2030-09-30 | 65 | 65 | 65 | 0% | 509 | Not Started
W526 | W526.1565 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q3 2030 | 2030-07-01 | 2030-09-30 | 65 | 65 | 65 | 0% | 509 | Not Started
W527 | W527.26690 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q3 2030 | 2030-07-01 | 2030-09-30 | 65 | 65 | 65 | 0% | 253 | Not Started
W527 | W527.26710 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q3 2030 | 2030-07-01 | 2030-09-30 | 65 | 65 | 65 | 0% | 253 | Not Started
W527 | W527.26770 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q3 2030 | 2030-07-01 | 2030-09-30 | 65 | 65 | 65 | 0% | 253 | Not Started
W527 | W527.26790 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q3 2030 | 2030-07-01 | 2030-09-30 | 65 | 65 | 65 | 0% | 253 | Not Started
W529 | W529.1575 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q4 2030 | 2030-10-01 | 2030-12-31 | 64 | 64 | 64 | 0% | 509 | Not Started
W526 | W526.1575 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q4 2030 | 2030-10-01 | 2030-12-31 | 64 | 64 | 64 | 0% | 509 | Not Started
W527 | W527.26650 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q4 2030 | 2030-10-01 | 2030-12-31 | 64 | 64 | 64 | 0% | 253 | Not Started
W527 | W527.26730 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q4 2030 | 2030-10-01 | 2030-12-31 | 64 | 64 | 64 | 0% | 253 | Not Started
W527 | W527.26760 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q4 2030 | 2030-10-01 | 2030-12-31 | 64 | 64 | 64 | 0% | 253 | Not Started
W527 | W527.26800 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q4 2030 | 2030-10-01 | 2030-12-31 | 64 | 64 | 64 | 0% | 253 | Not Started
W529 | W529.1585 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q1 2031 | 2031-01-02 | 2031-03-31 | 63 | 63 | 63 | 0% | 256 | Not Started
W529 | W529.4900 | TOR DPCS Defueling Support | TOR 2031 LSR - Pre-export Data Validation Produced and Completed | 2031-01-02 | 2031-02-24 | 38 | 38 | 38 | 0% | 400 | Not Started
W526 | W526.4900 | HYB DPCS Defueling Support | HYB 2031 LSR - Pre-export Data Validation Produced and Completed | 2031-01-02 | 2031-02-24 | 38 | 38 | 38 | 0% | 400 | Not Started
W526 | W526.1170 | HYB DPCS Defueling Support | HYB Plant Control Systems & Simulators (PCS&S) Group - 2031 | 2031-01-02 | 2031-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W526 | W526.1160 | HYB DPCS Defueling Support | HYB PES Group Support - 2031 | 2031-01-02 | 2031-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W526 | W526.3130 | HYB DPCS Defueling Support | HYB DPCS Long Term Support Contract 2031 | 2031-01-02 | 2031-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W526 | W526.1585 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q1 2031 | 2031-01-02 | 2031-03-31 | 63 | 63 | 63 | 0% | 0 | Not Started
W526 | W526.1595 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q2 2031 | 2031-01-02 | 2031-03-27 | 61 | 61 | 61 | 0% | 319 | Not Started
W526 | W526.3120 | HYB DPCS Defueling Support | HYB 2031 Defueling Software Build | 2031-01-02 | 2031-11-27 | 231 | 231 | 231 | 0% | 0 | Not Started
W526 | W526.10060 | HYB DPCS Defueling Support | HYB 2031 External Costs | 2031-01-02 | 2031-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W526 | W526.10220 | HYB DPCS Defueling Support | TPM and JCRB Meeting Held 2031 | 2031-01-02 | 2031-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W527 | W527.26910 | DNB DPCS Defueling Support | DNB PES Group Support - 2031 | 2031-01-02 | 2031-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W527 | W527.26920 | DNB DPCS Defueling Support | Plant Control Systems & Simulators (PCS&S) Group - 2031 | 2031-01-02 | 2031-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W527 | W527.26940 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q1 2031 | 2031-01-02 | 2031-03-27 | 61 | 61 | 61 | 0% | 0 | Not Started
W527 | W527.26960 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q1 2031 | 2031-01-02 | 2031-03-27 | 61 | 61 | 61 | 0% | 0 | Not Started
W527 | W527.26980 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q1 2031 | 2031-01-02 | 2031-03-27 | 61 | 61 | 61 | 0% | 0 | Not Started
W527 | W527.27030 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q1 2031 | 2031-01-02 | 2031-03-27 | 61 | 61 | 61 | 0% | 0 | Not Started
W527 | W527.27090 | DNB DPCS Defueling Support | Cost Engineer Support 2031 | 2031-01-02 | 2031-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W527 | W527.1290 | DNB DPCS Defueling Support | ETC 2031 | 2031-01-02 | 2031-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W529 | 70 | TOR DPCS Defueling Support | ETC 2031 | 2031-01-02 | 2031-12-31 | 253 | 253 | 253 | 0% | 256 | Not Started
W529 | W195.1060 | TOR DPCS Defueling Support | TPM and JCRB Meetings Held - 2031 | 2031-01-02 | 2031-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W526 | W526.1250 | HYB DPCS Defueling Support | ETC 2031 | 2031-01-02 | 2031-12-31 | 253 | 253 | 253 | 0% | 0 | Not Started
W529 | W529.3120 | TOR DPCS Defueling Support | TOR 2031 Defueling Software Build | 2031-01-03 | 2031-11-28 | 231 | 231 | 231 | 0% | 255 | Not Started
W529 | W529.3130 | TOR DPCS Defueling Support | TOR DPCS Long Term Support Contract 2031 | 2031-01-03 | 2032-01-02 | 253 | 253 | 253 | 0% | 255 | Not Started
W529 | W529.1160 | TOR DPCS Defueling Support | TOR PES Group Support - 2031 | 2031-01-03 | 2032-01-02 | 253 | 253 | 253 | 0% | 255 | Not Started
W529 | W529.1170 | TOR DPCS Defueling Support | TOR Plant Control Systems & Simulators (PCS&S) Group - 2031 | 2031-01-03 | 2032-01-02 | 253 | 253 | 253 | 0% | 255 | Not Started
W529 | W529.10060 | TOR DPCS Defueling Support | TOR 2031 External Costs | 2031-01-03 | 2032-01-02 | 253 | 253 | 253 | 0% | 255 | Not Started
W529 | W529.4890 | TOR DPCS Defueling Support | TOR 2031 LSR - Data Export Produced and Issued | 2031-02-25 | 2031-03-24 | 20 | 20 | 20 | 0% | 400 | Not Started
W526 | W526.4890 | HYB DPCS Defueling Support | HYB 2031 LSR - Data Export Produced and Issued | 2031-02-25 | 2031-03-24 | 20 | 20 | 20 | 0% | 400 | Not Started
W529 | W529.4880 | TOR DPCS Defueling Support | TOR 2031 LSR - Recommendations Produced and Issued | 2031-03-25 | 2031-04-07 | 10 | 10 | 10 | 0% | 400 | Not Started
W526 | W526.4880 | HYB DPCS Defueling Support | HYB 2031 LSR - Recommendations Produced and Issued | 2031-03-25 | 2031-04-07 | 10 | 10 | 10 | 0% | 400 | Not Started
W526 | W526.1605 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q3 2031 | 2031-03-28 | 2031-07-02 | 65 | 65 | 65 | 0% | 319 | Not Started
W527 | W527.26950 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q2 2031 | 2031-03-28 | 2031-06-30 | 63 | 63 | 63 | 0% | 0 | Not Started
W527 | W527.27000 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q2 2031 | 2031-03-28 | 2031-06-30 | 63 | 63 | 63 | 0% | 0 | Not Started
W527 | W527.27020 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q2 2031 | 2031-03-28 | 2031-06-30 | 63 | 63 | 63 | 0% | 0 | Not Started
W527 | W527.27060 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q2 2031 | 2031-03-28 | 2031-06-30 | 63 | 63 | 63 | 0% | 0 | Not Started
W529 | W529.1595 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q2 2031 | 2031-04-01 | 2031-06-30 | 61 | 61 | 61 | 0% | 256 | Not Started
W529 | W529.4870 | TOR DPCS Defueling Support | TOR 2031 LSR - Recommendation Sentencing Workshop Preparation and Event | 2031-04-08 | 2031-04-23 | 10 | 10 | 10 | 0% | 400 | Not Started
W526 | W526.4870 | HYB DPCS Defueling Support | HYB 2031 LSR - Recommendation Sentencing Workshop Preparation and Event | 2031-04-08 | 2031-04-23 | 10 | 10 | 10 | 0% | 400 | Not Started
W529 | W529.4860 | TOR DPCS Defueling Support | TOR 2031 LSR - Draft Report Produced and Issued for EDF Review | 2031-04-24 | 2031-05-09 | 11 | 11 | 11 | 0% | 400 | Not Started
W526 | W526.4860 | HYB DPCS Defueling Support | HYB 2031 LSR - Draft Report Produced and Issued for EDF Review | 2031-04-24 | 2031-05-09 | 11 | 11 | 11 | 0% | 400 | Not Started
W529 | W529.4850 | TOR DPCS Defueling Support | TOR 2031 LSR - EDF Review Comments Produced and Provided | 2031-05-12 | 2031-05-27 | 11 | 11 | 11 | 0% | 400 | Not Started
W526 | W526.4850 | HYB DPCS Defueling Support | HYB 2031 LSR - EDF Review Comments Produced and Provided | 2031-05-12 | 2031-05-27 | 11 | 11 | 11 | 0% | 400 | Not Started
W529 | W529.4840 | TOR DPCS Defueling Support | TOR 2031 LSR - Final Report Produced and Issued | 2031-05-28 | 2031-06-09 | 9 | 9 | 9 | 0% | 400 | Not Started
W526 | W526.4840 | HYB DPCS Defueling Support | HYB 2031 LSR - Final Report Produced and Issued | 2031-05-28 | 2031-06-09 | 9 | 9 | 9 | 0% | 400 | Not Started
W527 | W527.27100 | DNB DPCS Defueling Support | Asset Guardian Licences and Support 2031 | 2031-05-30 | 2031-05-30 | 1 | 1 | 1 | 0% | 150 | Not Started
W529 | W529.1605 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q3 2031 | 2031-07-01 | 2031-09-30 | 65 | 65 | 65 | 0% | 256 | Not Started
W527 | W527.26970 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q3 2031 | 2031-07-01 | 2031-09-30 | 65 | 65 | 65 | 0% | 0 | Not Started
W527 | W527.26990 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q3 2031 | 2031-07-01 | 2031-09-30 | 65 | 65 | 65 | 0% | 0 | Not Started
W527 | W527.27050 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q3 2031 | 2031-07-01 | 2031-09-30 | 65 | 65 | 65 | 0% | 0 | Not Started
W527 | W527.27070 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q3 2031 | 2031-07-01 | 2031-09-30 | 65 | 65 | 65 | 0% | 64 | Not Started
W526 | W526.1615 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q4 2031 | 2031-07-03 | 2031-10-01 | 64 | 64 | 64 | 0% | 319 | Not Started
W529 | W529.1615 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q4 2031 | 2031-10-01 | 2031-12-31 | 64 | 64 | 64 | 0% | 256 | Not Started
W527 | W527.26930 | DNB DPCS Defueling Support | Worldgrid System Engineering Support (SQEP) Q4 2031 | 2031-10-01 | 2031-12-31 | 64 | 64 | 64 | 0% | 0 | Not Started
W527 | W527.27010 | DNB DPCS Defueling Support | Worldgrid Long Term Support Contract Q4 2031 | 2031-10-01 | 2031-12-31 | 64 | 64 | 64 | 0% | 0 | Not Started
W527 | W527.27040 | DNB DPCS Defueling Support | Thales POLARIS & AIC Support Contract Q4 2031 | 2031-10-01 | 2031-12-31 | 64 | 64 | 64 | 0% | 0 | Not Started
W527 | W527.27080 | DNB DPCS Defueling Support | Worldgrid Software Modification Support (LAMPS) - Q4 2031 | 2031-10-01 | 2031-12-31 | 64 | 64 | 64 | 0% | 0 | Not Started
W529 | W529.3140 | TOR DPCS Defueling Support | TOR 2032 Defueling Software Build | 2032-01-02 | 2032-11-26 | 231 | 231 | 231 | 0% | 0 | Not Started
W529 | W529.1625 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q1 2032 | 2032-01-02 | 2032-03-31 | 62 | 62 | 62 | 0% | 0 | Not Started
W529 | W529.3150 | TOR DPCS Defueling Support | TOR DPCS Long Term Support Contract 2032 | 2032-01-02 | 2032-12-31 | 256 | 256 | 256 | 0% | 0 | Not Started
W529 | W529.1180 | TOR DPCS Defueling Support | TOR PES Group Support - 2032 | 2032-01-02 | 2032-12-31 | 256 | 256 | 256 | 0% | 0 | Not Started
W529 | W529.1190 | TOR DPCS Defueling Support | TOR Plant Control Systems & Simulators (PCS&S) Group - 2032 | 2032-01-02 | 2032-12-31 | 256 | 256 | 256 | 0% | 0 | Not Started
W529 | W529.4970 | TOR DPCS Defueling Support | TOR 2032 LSR - Pre-export Data Validation Produced and Completed | 2032-01-02 | 2032-02-24 | 38 | 38 | 38 | 0% | 147 | Not Started
W526 | W526.4970 | HYB DPCS Defueling Support | HYB 2032 LSR - Pre-export Data Validation Produced and Completed | 2032-01-02 | 2032-02-24 | 38 | 38 | 38 | 0% | 147 | Not Started
W526 | W526.1190 | HYB DPCS Defueling Support | HYB Plant Control Systems & Simulators (PCS&S) Group - 2032 | 2032-01-02 | 2032-12-31 | 256 | 256 | 256 | 0% | 0 | Not Started
W526 | W526.1180 | HYB DPCS Defueling Support | HYB PES Group Support - 2032 | 2032-01-02 | 2032-12-31 | 256 | 256 | 256 | 0% | 0 | Not Started
W526 | W526.3150 | HYB DPCS Defueling Support | HYB DPCS Long Term Support Contract 2032 | 2032-01-02 | 2032-12-31 | 256 | 256 | 256 | 0% | 0 | Not Started
W526 | W526.1625 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q1 2032 Delivery | 2032-01-02 | 2032-03-31 | 62 | 62 | 62 | 0% | 62 | Not Started
W526 | W526.1635 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q2 2032 Delivery | 2032-01-02 | 2032-04-01 | 63 | 63 | 63 | 0% | 62 | Not Started
W526 | W526.3140 | HYB DPCS Defueling Support | HYB 2032 Defueling Software Build | 2032-01-02 | 2032-11-26 | 231 | 231 | 231 | 0% | 0 | Not Started
W526 | W526.10070 | HYB DPCS Defueling Support | HYB 2032 External Costs | 2032-01-02 | 2032-12-31 | 256 | 256 | 256 | 0% | 0 | Not Started
W529 | W529.10070 | TOR DPCS Defueling Support | TOR 2032 External Costs | 2032-01-02 | 2032-12-31 | 256 | 256 | 256 | 0% | 0 | Not Started
W526 | W526.10230 | HYB DPCS Defueling Support | TPM and JCRB Meeting Held 2032 | 2032-01-02 | 2032-12-31 | 256 | 256 | 256 | 0% | 0 | Not Started
W529 | 80 | TOR DPCS Defueling Support | ETC 2032 | 2032-01-02 | 2032-12-31 | 256 | 256 | 256 | 0% | 0 | Not Started
W529 | W195.1070 | TOR DPCS Defueling Support | TPM and JCRB Meetings Held - 2032 | 2032-01-02 | 2032-12-31 | 256 | 256 | 256 | 0% | 0 | Not Started
W526 | W526.1260 | HYB DPCS Defueling Support | ETC 2032 | 2032-01-02 | 2032-12-31 | 256 | 256 | 256 | 0% | 0 | Not Started
W529 | W529.4960 | TOR DPCS Defueling Support | TOR 2032 LSR - Asset Guardian Data Export Produced and Issued | 2032-02-25 | 2032-03-23 | 20 | 20 | 20 | 0% | 147 | Not Started
W526 | W526.4960 | HYB DPCS Defueling Support | HYB 2032 LSR - Data Export Produced and Issued | 2032-02-25 | 2032-03-23 | 20 | 20 | 20 | 0% | 147 | Not Started
W529 | W529.4950 | TOR DPCS Defueling Support | TOR 2032 LSR - Recommendations Produced and Issued | 2032-03-24 | 2032-04-08 | 10 | 10 | 10 | 0% | 147 | Not Started
W526 | W526.4950 | HYB DPCS Defueling Support | HYB 2032 LSR - Recommendations Produced and Issued | 2032-03-24 | 2032-04-08 | 10 | 10 | 10 | 0% | 147 | Not Started
W529 | W529.1635 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q2 2032 | 2032-04-01 | 2032-06-30 | 63 | 63 | 63 | 0% | 0 | Not Started
W526 | W526.1645 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q3 2032 Delivery | 2032-04-02 | 2032-07-05 | 65 | 65 | 65 | 0% | 62 | Not Started
W529 | W529.4940 | TOR DPCS Defueling Support | TOR 2032 LSR - Recommendation Sentencing Workshop Preparation and Event | 2032-04-09 | 2032-04-22 | 10 | 10 | 10 | 0% | 147 | Not Started
W526 | W526.4940 | HYB DPCS Defueling Support | HYB 2032 LSR - Recommendation Sentencing Workshop Preparation and Event | 2032-04-09 | 2032-04-22 | 10 | 10 | 10 | 0% | 147 | Not Started
W529 | W529.4930 | TOR DPCS Defueling Support | TOR 2032 LSR - Draft Report Produced and Issued for EDF Review | 2032-04-23 | 2032-05-10 | 11 | 11 | 11 | 0% | 147 | Not Started
W526 | W526.4930 | HYB DPCS Defueling Support | HYB 2032 LSR - Draft Report Produced and Issued for EDF Review | 2032-04-23 | 2032-05-10 | 11 | 11 | 11 | 0% | 147 | Not Started
W529 | W529.4920 | TOR DPCS Defueling Support | TOR 2032 LSR - EDF Review Comments Produced and Provided | 2032-05-11 | 2032-05-25 | 11 | 11 | 11 | 0% | 147 | Not Started
W526 | W526.4920 | HYB DPCS Defueling Support | HYB 2032 LSR - EDF Review Comments Produced and Provided | 2032-05-11 | 2032-05-25 | 11 | 11 | 11 | 0% | 147 | Not Started
W529 | W529.4910 | TOR DPCS Defueling Support | TOR 2032 LSR - Final Report Produced and Issued | 2032-05-26 | 2032-06-08 | 9 | 9 | 9 | 0% | 147 | Not Started
W526 | W526.4910 | HYB DPCS Defueling Support | HYB 2032 LSR - Final Report Produced and Issued | 2032-05-26 | 2032-06-08 | 9 | 9 | 9 | 0% | 147 | Not Started
W529 | W529.1645 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q3 2032 | 2032-07-01 | 2032-09-30 | 65 | 65 | 65 | 0% | 0 | Not Started
W526 | W526.1655 | HYB DPCS Defueling Support | HYB Thales Long Term Support Contract - Q4 2032 Delivery | 2032-07-06 | 2032-10-06 | 66 | 66 | 66 | 0% | 62 | Not Started
W529 | W529.1655 | TOR DPCS Defueling Support | TOR Thales Long Term Support Contract - Q4 2032 | 2032-10-01 | 2032-12-31 | 66 | 66 | 66 | 0% | 0 | Not Started