## Project 1

Analysing variances in project planning: A data analysis on planning complexity and execution effectiveness.

This project will aim to investigate the misalignment between planned and actual project activities.

By analysing complexity of effort required in terms of activities starting and finishing each month, this project will evaluate the variance between scheduled plans and actual outcomes.

We aim to develop independent metrics to assess planning effectiveness and provide insights into potential improvements in project planning and management processes.

Benefits

By analysis the misalignment between planned and actual project activities, the business will gain a clearer understanding of the gaps in its project’s execution.

This insight will allow for more accurate planning, better resource allocation, and improved efficiency in future projects. Overall, it could lead to cost savings, timely project completions and enhanced strategic planning capabilities.

STEP 1. Project planning and set up.

Analyse the misalignment between planned and actual project activities to identify gaps and inefficiencies.

- Assess the variance between scheduled plans and actual outcomes.

- Develop independent metrics for planning effectiveness.

- Provide insights to improve future project planning and management.

Investigate the misalignment between planned and actual project activities.

- Analyse the complexity of effort required for activities each month.

- Evaluate the variance between scheduled plans and actual outcomes.

- Develop metrics to assess planning effectiveness and provide actionable insights.

Step 2. Data collection and preparation

Data extraction and preparation

- Project ID

- Project name

- Planned start date

- Planned finish date

- Actual start date

- Actual finish date

- Activity ID

- Activity name

- Planned Start date

- Planned Finish date

- Actual start date

- Actual finish date

- Duration

- Percentage complete

May consider

- Predecessors/successors

- Assigned resources

- Cost

- Baseline date

Filter data: export the selected data from p6 in a compatible format (excel, CSV)

Data cleaning and transformation in excel : address any missing data by imputing missing values or remove rows with missing critical information.

Ensure data consistency across different fields

STPE 3. Data Analysis &develop metrics

Data transformation

- Calculate key metrics (SV): schedule variance, planned start date – actual start date

- Schedule performance index (SPI), earned value/planned value

- Cost variance (CV), earned value – actual cost

- Cost Performance index (CPI), earned value – actual cost

Create calculated fields

- Monthly activity start and finish: categorise activities base on their planned and actual start/finish months.

- Activity complexity: develop a metric to quantify activity complexity (eg number of predecessors/successors, resource allocation, duration).

- Planned completion rate

STEP 4. Data visualisation

- Visualise variance: create a chart to visualise schedule and cost variance (eg gantt charts, scatter plots, bar charts).

- Analyse complexity: complexity vs performance, analyse the relationship between activity complexity and schedule/cost performance.

- Complexity vs variance: visualise the impact of activity complexity on schedule and cost variances.

- Trend analysis: analyse trends in project performance over time.

- Identify patterns: identify recuring patterns in project execution that contribute to misalignments.

Step 5. General Insights

Develop a dashboards and reports: create interactive dashboards and reports to present the analysis findings clearly and concisely.

STEP 6. Report Findings

- Summarise key findings and insights from the analysis

- Identify areas for improvement in project planning and execution.

- Quantify the potential impact of these improvements (eg cost savings, time savings)

STEP 7. recommendations Improvements

Provide specific recommendations for improving project planning processes, like

- More accurate resource estimation

- Enhanced risk management

- Improved communication and collaboration

- Better use of project management tools

| Project Timeline | Duration |
| --- | --- |
| Project planning and set up. |  |
| Project scope defined | 4 weeks |
| Data collection and preparation |  |
| P6 data extraction and initial data import into excel. | 1 week |
| Data cleaning and transformation in Power BI | 2 weeks |
| Data Analysis & develop metrics |  |
| Data import into power BI and initial data modelling. | 2 weeks |
| Data visualisation |  |
| Development of key visualisations and dashboards. | 2 weeks |
| General Insights & report findings |  |
| Initial analysis and draft report | 1 week |
| Final data analysis and refinement | 1 week |
| Final report and presentation | 1 week |

As for Feedback:

- We might consider specifying how the data analysis will be conducted to further refine the projects scope.

- Include a High level timeline or key milestones could help, clarify the project delivery stages.

- Perhaps we could tie the benefits to measurable outcomes (e.g. percentage reduction in planning variances or improvements in resource optimisation.)

Let me know your thoughts and I have included Neil Cooper also into this email as I want him to lead on some items and ensure we have a holistic plan.