## SC Plans
Project ID | CTO.PG.Workpack Number | Activity ID | Project Name | BL Project Start | BL Project Finish | Activity Name | Start | Finish | Original Duration | Remaining Duration | At Completion Duration | Physical % Complete | Total Float | Activity Status
ER6243LT | W200 | A10430 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-06-01 | 2017-12-29 | P.10.01.01 - Defuelling Shutdown Safety Cases - Project Management | 02-May-17 A | 29-Dec-17 A | 149 | 0 | 169 | 100% |  | Completed
ER6243LT | W200 | A10440 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-06-01 | 2017-12-29 | P.10.01.02 - Defuelling Shutdown Safety Cases - Safety Case | 02-May-17 A | 29-Dec-17 A | 149 | 0 | 169 | 100% |  | Completed
ER6243LT | W200 | A10450 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-06-01 | 2017-12-29 | P.10.01.03 - Defuelling Shutdown Safety Cases - Operation Compliance | 02-May-17 A | 29-Dec-17 A | 149 | 0 | 169 | 100% |  | Completed
ER6243LT | W200 | A10490 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-06-01 | 2017-12-14 | P.10.01.11 - Defuelling Shutdown Safety Cases - Vessel Integrity | 02-May-17 A | 29-Dec-17 A | 140 | 0 | 169 | 100% |  | Completed
ER6243LT | W200 | A10840 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-05-02 | 2017-07-31 | PCPV Integrity - RFS Summary - PCPV Hanging Plug Unit | 02-May-17 A | 22-Sep-17 A | 96 | 0 | 101 | 100% |  | Completed
ER6243LT | W200 | A10850 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-05-02 | 2017-06-05 | PCPV Integrity - Prepare Request for Service (RFS) | 02-May-17 A | 09-Jun-17 A | 24 | 0 | 27 | 100% |  | Completed
ER6243LT | W200 | A13070 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-05-02 | 2017-06-16 | PCPV Integrity - Verification Engineering Specification | 02-May-17 A | 16-Jun-17 A | 33 | 0 | 32 | 100% |  | Completed
ER6243LT | W200 | A13180 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-02 | 2018-02-28 | PCPV Integrity Summary - Outline Investment | 02-May-17 A | 19-Mar-19 A | 488 | 0 | 477 | 100% |  | Completed
ER6244LT | W220 | A1000 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-05-02 | 2019-04-01 | Cost Profile and Reporting Activity | 02-May-17 A | 02-Dec-19 A | 1920 | 0 | 656 | 100% |  | Completed
ER6244LT | W220 | A1130 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-05-02 | 2019-01-16 | Project Management Costs Gate A to Gate B | 02-May-17 A | 16-Jan-19 A | 359 | 0 | 434 | 100% |  | Completed
ER6243LT | W200 | RSSC.PM.A100 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-05-02 | 2018-09-28 | Project Management for the phase of work to Gate B | 02-May-17 A | 11-Oct-19 A | 359 | 0 | 620 | 100% |  | Completed
ER6243LT | W200 | A3000 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-04-24 |  | Project Start Date [FEEDS TO SUMMARY SCHEDULE] | 02-May-17 A | 02-May-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A1740 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-05-02 |  | Project Start Date [FEEDS TO SUMMARY SCHEDULE] | 02-May-17 A | 02-May-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A3040.C0 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2017-05-02 | Alignment of Internal Resource to the Plan and Contractor Resource to Execute Gate A to B | 02-May-17 A | 02-May-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A4060 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-05-02 | 2017-12-29 | P20.01.01.01 - Project Management | 02-May-17 A | 29-Dec-17 A | 170 | 0 | 169 | 100% |  | Completed
ER6244LT | W220 | A4070 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-05-02 | 2017-12-29 | P20.01.01.02 - Safety Case (Del 3005569) | 02-May-17 A | 29-Dec-17 A | 170 | 0 | 169 | 100% |  | Completed
ER6244LT | W220 | A4100 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-05-02 | 2018-04-30 | P20.01.01.05 - Defuelling Process (Del 3005570) | 02-May-17 A | 30-Apr-18 A | 170 | 0 | 252 | 100% |  | Completed
ER6244LT | W220 | A4170 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-05-02 | 2018-01-31 | P20.01.01.12 - Structural Integrity (Del 3005574) | 02-May-17 A | 31-Jan-18 A | 170 | 0 | 191 | 100% |  | Completed
ER6244LT | W220 | A5620 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-05-02 | 2017-05-08 | Prepare RFS/Spec for Dropped FPU impact on Reactor Internals and Standpipe Breach EAN (HPB and HNB) | 02-May-17 A | 08-May-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | A11930 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-05-02 | 2017-07-13 | Ops Compliance - RFS Summary | 02-May-17 A | 07-Jul-17 A | 55 | 0 | 48 | 100% |  | Completed
ER6243LT | W200 | A11940 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-05-02 | 2017-05-04 | Ops Compliance - Prepare Request for Service (RFS) Specification | 02-May-17 A | 05-May-17 A | 5 | 0 | 4 | 100% |  | Completed
ER6243LT | W200 | A11950 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-05-02 | 2017-05-02 | Ops Compliance - Review, Approve and Issue RFS to Supplier | 02-May-17 A | 02-May-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A11929 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-02 | 2018-04-26 | Operation Compliance Summary - Outline Investment | 02-May-17 A | 20-Dec-18 A | 446 | 0 | 417 | 100% |  | Completed
ER6243LT | W200 | A1000 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Summary for HNB Reactors Shutdown Safety Cases Programme W200 | 02-May-17 A | 15-Apr-20 A | 1 | 0 | 748 | 100% |  | Completed
ER6244LT | W220 | W220.A1030 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  |  | Summary for Defuelling Programme Fuel Handling Safety Case W220 | 02-May-17 A | 15-Apr-20 A | 1 | 0 | 749 | 100% |  | Completed
ER6244LT | W220 | A4080 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-05-03 | 2018-01-31 | P20.01.01.09 - Radiological Consequences | 03-May-17 A | 31-Jan-18 A | 170 | 0 | 190 | 100% |  | Completed
ER6243LT | W200 | A11960 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-05-03 | 2017-06-19 | Ops Compliance - Prepare and Issue Offer | 03-May-17 A | 31-May-17 A | 33 | 0 | 20 | 100% |  | Completed
ER6244LT | W220 | A5100 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-05-09 | 2017-06-26 | Prepare RFS/Spec for CO2 purity and decay heat report | 09-May-17 A | 26-Jun-17 A | 5 | 0 | 33 | 100% |  | Completed
ER6244LT | W220 | A5630 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-05-09 | 2017-05-10 | Review, approve and issue RFS for Dropped FPU impact on Reactor Internals and Standpipe Breach EAN (HPB and HNB) | 09-May-17 A | 10-May-17 A | 2 | 0 | 2 | 100% |  | Completed
ER6243LT | W200 | A3030.C0 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-05-31 | Approval of programme optioneering phase 2 for Region 1 stations gate A to B | 11-May-17 A | 11-May-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A3040 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-04-28 | Alignment of Internal Resource to the Plan and Contractor Resource to Excute Gate A to B | 11-May-17 A | 11-May-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A5640 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-05-11 | 2017-06-12 | Offer prepared and issued by FNC for Dropped FPU impact on Reactor Internals and Standpipe Breach EAN (HPB and HNB) | 11-May-17 A | 12-Jun-17 A | 22 | 0 | 22 | 100% |  | Completed
ER6244LT | W220 | A5650 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-05-15 | 2017-05-16 | Review and negotiate offer for Dropped FPU impact on Reactor Internals and Standpipe Breach EAN (HPB and HNB) | 15-May-17 A | 16-May-17 A | 2 | 0 | 2 | 100% |  | Completed
ER6244LT | W220 | A5750 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-05-16 | 2017-05-16 | Prepare RFS/Spec for Dropped FPU impact on Reactor Internals EAN (HYA and HRA) | 16-May-17 A | 16-May-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A5660 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-05-17 | 2017-05-18 | Complete req. approval and issue CI for Dropped FPU impact on Reactor Internals and Standpipe Breach EAN (HPB and HNB) | 17-May-17 A | 18-May-17 A | 2 | 0 | 2 | 100% |  | Completed
ER6244LT | W220 | A5760 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-05-17 | 2017-05-17 | Review, approve and issue RFS for Dropped FPU impact on Reactor Internals EAN (HYA and HRA) | 17-May-17 A | 17-May-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A5770 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-05-18 | 2017-05-24 | Offer prepared and issued by FNC for Dropped FPU impact on Reactor Internals EAN (HYA and HRA) | 18-May-17 A | 24-May-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A6400 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2017-05-18 | Dropped FPU Impact on Reactor Internals Assessments (HPB/HNB): Req Approved | 18-May-17 A | 18-May-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A10510 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-06-01 | 2017-06-01 | P.10.01.19 - Defuelling Shutdown Safety Cases - Supporting Systems | 19-May-17 A | 19-May-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A5670 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-05-19 | 2017-05-19 | Supplier mobilisation | 19-May-17 A | 19-May-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A5680 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-05-22 | 2017-05-22 | Pre Job Brief for Dropped FPU impact on Reactor Internals and Standpipe Breach EAN (HPB and HNB) | 22-May-17 A | 22-May-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A5690 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-05-22 | 2017-05-26 | Draft Dropped FPU impact on Reactor Internals and Standpipe Breach EAN (HPB and HNB) | 22-May-17 A | 26-May-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A5780 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-05-25 | 2017-05-31 | Review and negotiate offer for Dropped FPU impact on Reactor Internals EAN (HYA and HRA) | 25-May-17 A | 31-May-17 A | 10 | 0 | 3 | 100% |  | Completed
ER6244LT | W220 | A5700 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2017-05-26 | Draft Dropped FPU impact on Reactor Internals and Standpipe Breach EAN (HPB and HNB) verified & issued for tech. review | 26-May-17 A | 26-May-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11970 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-06-20 | 2017-06-26 | Ops Compliance - Review and Negotiate Offer | 31-May-17 A | 16-Jun-17 A | 5 | 0 | 13 | 100% |  | Completed
ER6244LT | W220 | A2180.C0 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2017-05-31 | Approval of Programme Detailed Optioneering (Phase 2) for Region 1 Stations Gate A to B | 31-May-17 A | 31-May-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A4110 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-06-01 | 2017-10-31 | P20.01.01.06 - Lifting Integrity (Del 3005571) | 01-Jun-17 A | 31-Oct-17 A | 106 | 0 | 107 | 100% |  | Completed
ER6243LT | W200 | A10520 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-06-01 | 2017-06-01 | P.10.01.22 - Defuelling Shutdown Safety Cases - Decommissioning Phase | 01-Jun-17 A | 01-Jun-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A1270 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-06-01 | 2018-01-02 | Establish fuelling machine trip settings/overrun speeds for new PIFA/IFA/Loading FPUs for defuelling. HPB and HNB | 01-Jun-17 A | 02-Jan-18 A | 150 | 0 | 150 | 100% |  | Completed
ER6243LT | W200 | A10420 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-06-01 | 2017-06-01 | P.10 - Reactors Shutdown Safety Cases | 01-Jun-17 A | 01-Jun-17 A | 0 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A10540 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-06-01 | 2017-06-01 | P.10.01.25 - Defuelling Shutdown Safety Cases - Station Support | 01-Jun-17 A | 01-Jun-17 A | 0 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A5710 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-06-01 | 2017-06-14 | Technical review of Dropped FPU impact on Reactor Internals and Standpipe Breach EAN (HPB and HNB) | 01-Jun-17 A | 14-Jun-17 A | 10 | 0 | 10 | 100% |  | Completed
ER6244LT | W220 | A5790 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-06-01 | 2017-06-07 | Complete requisition approval and issue CI for Dropped FPU impact on Reactor Internals EAN (HYA and HRA) | 01-Jun-17 A | 07-Jun-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A8510 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-06-01 | 2017-06-09 | Prepare RFS/Spec for Initial Fault Studies and Risk Estimation Report (HYA/HRA) | 01-Jun-17 A | 09-Jun-17 A | 7 | 0 | 7 | 100% |  | Completed
ER6244LT | W220 | A1240 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-06-02 | 2017-10-30 | Large batch refuelling - feasibility/impact on reactor operations (including radial shuffling and fuel route logistics) | 02-Jun-17 A | 30-Oct-17 A | 106 | 0 | 106 | 100% |  | Completed
ER6244LT | W220 | A8220 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2017-06-07 | Dropped FPU Impact on Reactor Internals Assessments (HPB/HNB): Req Approved | 07-Jun-17 A | 07-Jun-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A5800 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-06-08 | 2017-06-12 | Supplier mobilisation | 08-Jun-17 A | 12-Jun-17 A | 3 | 0 | 3 | 100% |  | Completed
ER6244LT | W220 | A5810.EJ | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-06-12 | 2017-06-12 | Pre Job Brief for Dropped FPU impact on Reactor Internals EAN (HYA and HRA) | 12-Jun-17 A | 12-Jun-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A5820 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-06-12 | 2017-08-01 | Draft Dropped FPU impact on Reactor Internals Report (HYA and HRA) | 12-Jun-17 A | 01-Aug-17 A | 60 | 0 | 37 | 100% |  | Completed
ER6244LT | W220 | A8520 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-06-12 | 2017-06-16 | Review, approve and issue RFS for Initial Fault Studies and Risk Estimation Report (HYA/HRA) | 12-Jun-17 A | 16-Jun-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A5230 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-06-15 | 2017-07-21 | Prepare RFS/Spec for Refuelling Cooling Assessment EAN | 15-Jun-17 A | 21-Jul-17 A | 13 | 0 | 26 | 100% |  | Completed
ER6244LT | W220 | A5720 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-06-15 | 2017-06-16 | FNC update and issue Dropped FPU impact on Reactor Internals and Standpipe Breach EAN (HPB and HNB) | 15-Jun-17 A | 16-Jun-17 A | 10 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A7180 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-06-15 | 2017-07-21 | Prepare RFS/Spec for Impact of Empty Channels on Reactor Cooling EAN | 15-Jun-17 A | 21-Jul-17 A | 13 | 0 | 26 | 100% |  | Completed
ER6244LT | W220 | A7310 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-06-15 | 2017-08-01 | Prepare RFS/Spec for Minimum Forced Gas Circulation Requirements EAN | 15-Jun-17 A | 01-Aug-17 A | 13 | 0 | 34 | 100% |  | Completed
ER6243LT | W200 | A13080 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-06-19 | 2017-06-30 | PCPV Integrity - Address Verification Comments | 19-Jun-17 A | 19-Jul-17 A | 10 | 0 | 22 | 100% |  | Completed
ER6244LT | W220 | A5730 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-06-19 | 2017-08-16 | Complete TR form and upload Dropped FPU impact on Reactor Internals and Standpipe Breach EAN (HPB and HNB) to CDMS | 19-Jun-17 A | 16-Aug-17 A | 10 | 0 | 43 | 100% |  | Completed
ER6243LT | W200 | A11980 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-06-27 | 2017-06-27 | Ops Compliance - Complete Requisition Approval and Issue CI | 19-Jun-17 A | 19-Jun-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A8530 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-06-19 | 2017-06-20 | Offer prepared and issued by supplier for Initial Fault Studies and Risk Estimation Report (HYA/HRA) | 19-Jun-17 A | 20-Jun-17 A | 2 | 0 | 2 | 100% |  | Completed
ER6244LT | W220 | A8540 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-06-21 | 2017-06-21 | Review and negotiate offer for Initial Fault Studies and Risk Estimation Report (HYA/HRA) | 21-Jun-17 A | 21-Jun-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A8550 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-06-22 | 2017-06-22 | Complete requisition approval and issue CI for Initial Fault Studies and Risk Estimation Report (HYA/HRA) | 22-Jun-17 A | 22-Jun-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A8560 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-06-23 | 2017-06-30 | Supplier mobilisation | 23-Jun-17 A | 30-Jun-17 A | 6 | 0 | 6 | 100% |  | Completed
ER6243LT | W200 | A11990 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-06-28 | 2017-07-13 | Ops Compliance - Supplier Mobilisation Time | 26-Jun-17 A | 07-Jul-17 A | 12 | 0 | 10 | 100% |  | Completed
ER6244LT | W220 | A5110 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-06-27 | 2017-06-30 | Review, approve and issue RFS to Amec for CO2 purity and decay heat report | 27-Jun-17 A | 30-Jun-17 A | 4 | 0 | 4 | 100% |  | Completed
ER6244LT | W220 | A4150 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-03 | 2018-01-31 | P20.01.01.10 - Fault Studies (Del 3005573) | 03-Jul-17 A | 31-Jan-18 A | 106 | 0 | 148 | 100% |  | Completed
ER6244LT | W220 | A4270 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-03 | 2018-01-31 | P20.01.01.23 - Maintenance (Del 3005582) | 03-Jul-17 A | 31-Jan-18 A | 106 | 0 | 148 | 100% |  | Completed
ER6243LT | W200 | A11730 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-06-21 | 2017-07-19 | Thermal Hydraulics (MACE) - RFS Summary Thermal Hydraulics (MACE) | 03-Jul-17 A | 16-Nov-17 A | 109 | 0 | 97 | 100% |  | Completed
ER6243LT | W200 | A11740 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-06-21 | 2017-06-22 | Thermal Hydraulics (MACE) - Prepare Request for Service (RFS) Specification | 03-Jul-17 A | 06-Sep-17 A | 9 | 0 | 46 | 100% |  | Completed
ER6243LT | W200 | A13220 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-02 | 2018-05-24 | Reactor Physics Summary - Outline Investment | 03-Jul-17 A | 28-Feb-19 A | 434 | 0 | 421 | 100% |  | Completed
ER6244LT | W220 | A4120 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-03 | 2018-06-29 | P20.01.01.07 - Fuel Storage Conditions (Del 3005572) | 03-Jul-17 A | 29-Jun-18 A | 127 | 0 | 251 | 100% |  | Completed
ER6244LT | W220 | A4130 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-03 | 2018-01-31 | P20.01.01.20 - Fuel Route Facilities (Del 3005580) | 03-Jul-17 A | 31-Jan-18 A | 127 | 0 | 148 | 100% |  | Completed
ER6244LT | W220 | A4220 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-03 | 2018-01-31 | P20.01.01.17 - Stringer Integrity (Del 3005579) | 03-Jul-17 A | 31-Jan-18 A | 127 | 0 | 148 | 100% |  | Completed
ER6244LT | W220 | A4250 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-03 | 2018-01-31 | P20.01.01.21 - Human Factors (Del 3005581) | 03-Jul-17 A | 31-Jan-18 A | 127 | 0 | 148 | 100% |  | Completed
ER6243LT | W200 | A10460 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-06-01 | 2017-12-29 | P.10.01.04 - Defuelling Shutdown Safety Cases - Reactor Physics | 03-Jul-17 A | 31-Jan-18 A | 116 | 0 | 148 | 100% |  | Completed
ER6244LT | W220 | A5120 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-03 | 2017-07-04 | Offer prepared and issued by Amec for CO2 purity and decay heat report | 03-Jul-17 A | 04-Jul-17 A | 2 | 0 | 2 | 100% |  | Completed
ER6244LT | W220 | A6140 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-03 | 2017-09-07 | Prepare RFS/Spec for Buffer Store Defueling EAN (HPB and HNB) | 03-Jul-17 A | 07-Sep-17 A | 21 | 0 | 48 | 100% |  | Completed
ER6244LT | W220 | A6270 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-03 | 2017-09-07 | Prepare RFS/Spec for IFDF Defueling EAN (HPB and HNB) | 03-Jul-17 A | 07-Sep-17 A | 21 | 0 | 48 | 100% |  | Completed
ER6244LT | W220 | A6530 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-03 | 2017-08-01 | Prepare RFS/Spec for IFDF Defueling EAN (HYA and HRA) | 03-Jul-17 A | 01-Aug-17 A | 16 | 0 | 22 | 100% |  | Completed
ER6244LT | W220 | A8240 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-03 | 2017-07-06 | Prepare RFS/Spec for Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 03-Jul-17 A | 06-Jul-17 A | 4 | 0 | 4 | 100% |  | Completed
ER6244LT | W220 | A8370 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-03 | 2017-07-06 | Prepare RFS/Spec for Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 03-Jul-17 A | 06-Jul-17 A | 4 | 0 | 4 | 100% |  | Completed
ER6244LT | W220 | A8570 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-03 | 2017-07-03 | Pre Job Brief for Initial Fault Studies and Risk Estimation Report (HYA/HRA) | 03-Jul-17 A | 03-Jul-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A5130 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-05 | 2017-07-11 | Review and negotiate offer for CO2 purity and decay heat report | 05-Jul-17 A | 11-Jul-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A8250 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-07 | 2017-07-12 | Review, approve and issue RFS for Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 07-Jul-17 A | 12-Jul-17 A | 4 | 0 | 4 | 100% |  | Completed
ER6244LT | W220 | A8380 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-07 | 2017-07-12 | Review, approve and issue RFS for Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 07-Jul-17 A | 12-Jul-17 A | 4 | 0 | 4 | 100% |  | Completed
ER6244LT | W220 | A8640 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-11 | 2017-07-17 | Prepare RFS/Spec for Initial Fault Studies and Risk Estimation Report (HPB/HNB) | 11-Jul-17 A | 17-Jul-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A5140 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-12 | 2017-07-14 | Complete requisition approval and issue CI for CO2 purity and decay heat report | 12-Jul-17 A | 14-Jul-17 A | 3 | 0 | 3 | 100% |  | Completed
ER6244LT | W220 | A6660 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-13 | 2017-09-07 | Prepare RFS/Spec for Ponds and Flasks EAN (HPB and HNB) | 13-Jul-17 A | 07-Sep-17 A | 13 | 0 | 40 | 100% |  | Completed
ER6244LT | W220 | A7440 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-13 | 2017-08-01 | Prepare RFS/Spec for Assessment of Temperatures vs Decay Heat for Natural Circulation EAN | 13-Jul-17 A | 01-Aug-17 A | 14 | 0 | 14 | 100% |  | Completed
ER6244LT | W220 | A8260 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-13 | 2017-07-18 | Offer prepared and issued for Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 13-Jul-17 A | 18-Jul-17 A | 4 | 0 | 4 | 100% |  | Completed
ER6244LT | W220 | A8390 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-13 | 2017-07-18 | Offer prepared and issued for Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 13-Jul-17 A | 18-Jul-17 A | 4 | 0 | 4 | 100% |  | Completed
ER6243LT | W200 | A10470 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-06-01 | 2017-10-03 | P.10.01.08 - Defuelling Shutdown Safety Cases - Cooling - Normal Operations | 17-Jul-17 A | 31-Jan-18 A | 66 | 0 | 138 | 100% |  | Completed
ER6244LT | W220 | A5150 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-17 | 2017-07-19 | Amec mobilisation | 17-Jul-17 A | 19-Jul-17 A | 3 | 0 | 3 | 100% |  | Completed
ER6244LT | W220 | A8650 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-18 | 2017-07-24 | Review, approve and issue RFS for Initial Fault Studies and Risk Estimation Report (HPB/HNB) | 18-Jul-17 A | 24-Jul-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A8270 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-19 | 2017-07-24 | Review and negotiate offer for Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 19-Jul-17 A | 24-Jul-17 A | 4 | 0 | 4 | 100% |  | Completed
ER6244LT | W220 | A8400 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-19 | 2017-07-24 | Review and negotiate offer for Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 19-Jul-17 A | 24-Jul-17 A | 4 | 0 | 4 | 100% |  | Completed
ER6243LT | W200 | A10860 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-07-03 | 2017-07-03 | PCPV Integrity - Review, Approve and Issue RFS to Supplier | 20-Jul-17 A | 20-Jul-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A5160 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-20 | 2017-07-20 | Pre Job Brief for CO2 purity and decay heat report | 20-Jul-17 A | 20-Jul-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A5170 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-20 | 2018-01-02 | Draft CO2 purity and decay heat report | 20-Jul-17 A | 02-Jan-18 A | 30 | 0 | 114 | 100% |  | Completed
ER6243LT | W200 | A13200 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-07-20 | Risk Workshop Held | 20-Jul-17 A | 20-Jul-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A10870 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-07-04 | 2017-07-07 | PCPV Integrity - Prepare and Issue Offer | 21-Jul-17 A | 24-Aug-17 A | 15 | 0 | 24 | 100% |  | Completed
ER6244LT | W220 | A5240 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-24 | 2017-07-28 | Review, approve and issue RFS for Refuelling Cooling Assessment EAN | 24-Jul-17 A | 28-Jul-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A7190 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-24 | 2017-07-28 | Review, approve and issue RFS for Impact of Empty Channels on Reactor Cooling EAN | 24-Jul-17 A | 28-Jul-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A7830 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-24 | 2017-08-01 | Prepare RFS/Spec for Review Radial Shuffling Safety Case EAN (HYA and HRA) | 24-Jul-17 A | 01-Aug-17 A | 5 | 0 | 7 | 100% |  | Completed
ER6244LT | W220 | A8770 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-24 | 2017-08-03 | Prepare RFS/Spec for Fuel Free Verification EAN | 24-Jul-17 A | 03-Aug-17 A | 8 | 0 | 9 | 100% |  | Completed
ER6244LT | W220 | A9540 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-24 | 2017-08-03 | Prepare RFS/Spec for Fuel Free Verification EAN | 24-Jul-17 A | 03-Aug-17 A | 8 | 0 | 9 | 100% |  | Completed
ER6244LT | W220 | A9670 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-24 | 2017-08-03 | Prepare RFS/Spec for Fuel Free Verification EAN | 24-Jul-17 A | 03-Aug-17 A | 8 | 0 | 9 | 100% |  | Completed
ER6244LT | W220 | A9800 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-24 | 2017-08-03 | Prepare RFS/Spec for Fuel Free Verification EAN | 24-Jul-17 A | 03-Aug-17 A | 8 | 0 | 9 | 100% |  | Completed
ER6244LT | W220 | A8280 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-25 | 2017-09-06 | Complete requisition approval and issue CI for Justify Zero Maintenance for FPU Prior to Load in Shutdown Reactor EAN | 25-Jul-17 A | 06-Sep-17 A | 4 | 0 | 31 | 100% |  | Completed
ER6244LT | W220 | A8410 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-25 | 2017-09-06 | Complete requisition approval and issue CI for Justify Zero Maintenance for FPU Prior to Load in Shutdown Reactor EAN | 25-Jul-17 A | 06-Sep-17 A | 4 | 0 | 31 | 100% |  | Completed
ER6244LT | W220 | A8660 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-25 | 2017-07-26 | Offer prepared and issued by supplier for Initial Fault Studies and Risk Estimation Report (HPB/HNB) | 25-Jul-17 A | 26-Jul-17 A | 2 | 0 | 2 | 100% |  | Completed
ER6243LT | W200 | RSSC.OC.A100 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-07-14 | 2018-01-16 | Ops Compliance - QA3 rpt from defuelling SDM compliance optioneering & control rod/flux detector/monitoring arrangements | 27-Jul-17 A | 29-Jun-18 A | 235 | 0 | 233 | 100% |  | Completed
ER6243LT | W200 | RSSC.OC.A102 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-07-14 | 2017-07-14 | Ops Compliance - Pre Job Brief | 27-Jul-17 A | 27-Jul-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A8670 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-27 | 2017-07-27 | Review and negotiate offer for Initial Fault Studies and Risk Estimation Report (HPB/HNB) | 27-Jul-17 A | 27-Jul-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.OC.A105 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-07-14 | 2017-11-16 | Ops Compliance - Prepare QA3 SDM Defuelling Strategy Optioneering Report (1st Phase) | 28-Jul-17 A | 31-Oct-17 A | 34 | 0 | 66 | 100% |  | Completed
ER6244LT | W220 | A8680 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-28 | 2017-07-31 | Complete requisition approval and issue CI for Initial Fault Studies and Risk Estimation Report (HPB/HNB) | 28-Jul-17 A | 31-Jul-17 A | 2 | 0 | 2 | 100% |  | Completed
ER6244LT | W220 | A8690 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-31 | 2017-07-31 | Supplier mobilisation | 31-Jul-17 A | 31-Jul-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A8700 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-31 | 2017-07-31 | Pre Job Brief for Initial Fault Studies and Risk Estimation Report (HPB/HNB) | 31-Jul-17 A | 31-Jul-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A8710 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-07-31 | 2017-10-30 | Draft Initial Fault Studies and Risk Estimation Report (HPB/HNB) | 31-Jul-17 A | 30-Oct-17 A | 60 | 0 | 65 | 100% |  | Completed
ER6244LT | W220 | A3460 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-01 | 2017-08-11 | Update defueling options EAN to Rev 001 for defueling mode | 01-Aug-17 A | 11-Aug-17 A | 9 | 0 | 9 | 100% |  | Completed
ER6244LT | W220 | A4280 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-01 | 2018-01-31 | P20.01.01.18 - Interlock Changes | 01-Aug-17 A | 31-Jan-18 A | 19 | 0 | 127 | 100% |  | Completed
ER6244LT | W220 | A5880 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-01 | 2017-08-07 | Prepare RFS/Spec for Dropped FPU Impact on Buffer Store EAN (HPB and HNB) | 01-Aug-17 A | 07-Aug-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A6010 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-01 | 2017-08-07 | Prepare RFS/Spec for Dropped FPU Impact on Buffer Store EAN (HYA and HRA) | 01-Aug-17 A | 07-Aug-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A6790 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-01 | 2017-09-07 | Prepare RFS/Spec for Waste Vault Storage Capacity EAN (HPB and HNB) | 01-Aug-17 A | 07-Sep-17 A | 19 | 0 | 27 | 100% |  | Completed
ER6244LT | W220 | A6920 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-01 | 2017-08-01 | Prepare RFS/Spec for Ponds and Flasks EAN (HYA and HRA) | 01-Aug-17 A | 01-Aug-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A7050 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-01 | 2017-08-01 | Prepare RFS/Spec for Waste Vault Storage Capacity EAN (HYA and HRA) | 01-Aug-17 A | 01-Aug-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A7200 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-01 | 2017-08-04 | Offer prepared and issued for Impact of Empty Channels on Reactor Cooling EAN | 01-Aug-17 A | 04-Aug-17 A | 4 | 0 | 4 | 100% |  | Completed
ER6244LT | W220 | A7960 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-01 | 2017-09-02 | Prepare RFS/Spec for CRA Isolation Requirements EAN | 01-Aug-17 A | 02-Sep-17 A | 19 | 0 | 23 | 100% |  | Completed
ER6244LT | W220 | A8910 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-01 | 2017-08-04 | Prepare RFS/Spec for Fuelling Machine Light Load Protection & Interlocks EAN (HPB/HNB) | 01-Aug-17 A | 04-Aug-17 A | 4 | 0 | 4 | 100% |  | Completed
ER6244LT | W220 | A9930 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-01 | 2017-08-04 | Prepare RFS/Spec for Fuelling Machine Light Load Protection & Interlocks EAN(HYA and HRA) | 01-Aug-17 A | 04-Aug-17 A | 4 | 0 | 4 | 100% |  | Completed
ER6244LT | W220 | A5830.EJ | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2017-08-01 | Draft Dropped FPU impact on Reactor Internals Report (HYA and HRA) verified and issued for technical review | 01-Aug-17 A | 01-Aug-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A5840 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-02 | 2017-09-08 | Technical review of Dropped FPU impact on Reactor Internals Report (HYA and HRA) | 02-Aug-17 A | 08-Sep-17 A | 42 | 0 | 27 | 100% |  | Completed
ER6244LT | W220 | A6540 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-02 | 2017-08-03 | Review, approve and issue RFS for IFDF Defueling EAN (HYA and HRA) | 02-Aug-17 A | 03-Aug-17 A | 2 | 0 | 2 | 100% |  | Completed
ER6244LT | W220 | A6930 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-02 | 2017-08-03 | Review, approve and issue RFS for Ponds and Flasks EAN (HYA and HRA) | 02-Aug-17 A | 03-Aug-17 A | 2 | 0 | 2 | 100% |  | Completed
ER6244LT | W220 | A7060 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-02 | 2017-08-03 | Review, approve and issue RFS for Waste Vault Storage Capacity EAN (HYA and HRA) | 02-Aug-17 A | 03-Aug-17 A | 2 | 0 | 2 | 100% |  | Completed
ER6244LT | W220 | A7320 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-02 | 2017-08-03 | Review, approve and issue RFS for Minimum Forced Gas Circulation Requirements EAN | 02-Aug-17 A | 03-Aug-17 A | 2 | 0 | 2 | 100% |  | Completed
ER6244LT | W220 | A7450 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-02 | 2017-08-03 | Review, approve and issue RFS for Assessment of Temperatures vs Decay Heat for Natural Circulation EAN | 02-Aug-17 A | 03-Aug-17 A | 2 | 0 | 2 | 100% |  | Completed
ER6244LT | W220 | A7840 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-02 | 2017-08-02 | Review, approve and issue RFS for Review Radial Shuffling Safety Case EAN (HYA and HRA) | 02-Aug-17 A | 02-Aug-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A7850 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-03 | 2017-08-03 | Offer prepared and issued for Review Radial Shuffling Safety Case EAN (HYA and HRA) | 03-Aug-17 A | 03-Aug-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A6550 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-04 | 2017-08-04 | Offer prepared and issued by supplier for IFDF Defueling EAN (HYA and HRA) | 04-Aug-17 A | 04-Aug-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A6940 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-04 | 2017-08-04 | Offer prepared and issued by supplier for Ponds and Flasks EAN (HYA and HRA) | 04-Aug-17 A | 04-Aug-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A7070 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-04 | 2017-08-04 | Offer prepared and issued by supplier for Waste Vault Storage Capacity EAN (HYA and HRA) | 04-Aug-17 A | 04-Aug-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A7330 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-04 | 2017-08-04 | Offer prepared and issued for Minimum Forced Gas Circulation Requirements EAN | 04-Aug-17 A | 04-Aug-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A7460 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-04 | 2017-08-04 | Offer prepared and issued for Assessment of Temperatures vs Decay Heat for Natural Circulation EAN | 04-Aug-17 A | 04-Aug-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A7860 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-04 | 2017-08-04 | Review and negotiate offer for Review Radial Shuffling Safety Case EAN (HYA and HRA) | 04-Aug-17 A | 04-Aug-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A8780 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-04 | 2017-08-07 | Review, approve and issue RFS for Fuel Free Verification EAN | 04-Aug-17 A | 07-Aug-17 A | 2 | 0 | 2 | 100% |  | Completed
ER6244LT | W220 | A9550 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-04 | 2017-08-07 | Review, approve and issue RFS for Fuel Free Verification EAN | 04-Aug-17 A | 07-Aug-17 A | 2 | 0 | 2 | 100% |  | Completed
ER6244LT | W220 | A9680 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-04 | 2017-08-07 | Review, approve and issue RFS for Fuel Free Verification EAN | 04-Aug-17 A | 07-Aug-17 A | 2 | 0 | 2 | 100% |  | Completed
ER6244LT | W220 | A9810 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-04 | 2017-08-07 | Review, approve and issue RFS for Fuel Free Verification EAN | 04-Aug-17 A | 07-Aug-17 A | 2 | 0 | 2 | 100% |  | Completed
ER6243LT | W200 | RSSC.OC.A170 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-04-30 | Principles of Fuel Free Verification - RFS Review Before it is Issued to Supplier (HPB, HNB) | 07-Aug-17 A | 07-Aug-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.OC.A500 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-04-30 | Principles of Fuel Free Verification - RFS Review Before it is Issued to Supplier (HYA, HAR) | 07-Aug-17 A | 07-Aug-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A6560 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-07 | 2017-08-11 | Review and negotiate offer for IFDF Defueling EAN (HYA and HRA) | 07-Aug-17 A | 11-Aug-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A6950 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-07 | 2017-08-11 | Review and negotiate offer for Ponds and Flasks EAN (HYA and HRA) | 07-Aug-17 A | 11-Aug-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A7080 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-07 | 2017-08-11 | Review and negotiate offer for Waste Vault Storage Capacity EAN (HYA and HRA) | 07-Aug-17 A | 11-Aug-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A7210 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-07 | 2017-08-11 | Review and negotiate offer for Impact of Empty Channels on Reactor Cooling EAN | 07-Aug-17 A | 11-Aug-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A7340 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-07 | 2017-08-11 | Review and negotiate offer for Minimum Forced Gas Circulation Requirements EAN | 07-Aug-17 A | 11-Aug-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A7470 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-07 | 2017-08-11 | Review and negotiate offer for Assessment of Temperatures vs Decay Heat for Natural Circulation EAN | 07-Aug-17 A | 11-Aug-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A7870 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-07 | 2017-08-07 | Complete requisition approval and issue CI for Review Radial Shuffling Safety Case EAN (HYA and HRA) | 07-Aug-17 A | 07-Aug-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A8920 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-07 | 2017-08-11 | Review, approve and issue RFS for Fuelling Machine Light Load Protection & Interlocks EAN (HPB/HNB) | 07-Aug-17 A | 11-Aug-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A9940 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-07 | 2017-08-11 | Review, approve and issue RFS for Fuelling Machine Light Load Protection & Interlocks EAN (HYA and HRA) | 07-Aug-17 A | 11-Aug-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A5890 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-08 | 2017-08-14 | Review, approve and issue RFS for Dropped FPU Impact on Buffer Store EAN (HPB and HNB) | 08-Aug-17 A | 14-Aug-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A6020 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-08 | 2017-08-14 | Review, approve and issue RFS for Dropped FPU Impact on Buffer Store EAN (HYA and HRA) | 08-Aug-17 A | 14-Aug-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A7880 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-08 | 2017-08-08 | Supplier mobilisation (HYA and HRA) | 08-Aug-17 A | 08-Aug-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A8790 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-08 | 2017-08-25 | Offer prepared and issued for Fuel Free Verification EAN | 08-Aug-17 A | 25-Aug-17 A | 14 | 0 | 14 | 100% |  | Completed
ER6244LT | W220 | A9560 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-08 | 2017-08-25 | Offer prepared and issued for Fuel Free Verification EAN | 08-Aug-17 A | 25-Aug-17 A | 14 | 0 | 14 | 100% |  | Completed
ER6244LT | W220 | A9690 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-08 | 2017-08-25 | Offer prepared and issued for Fuel Free Verification EAN | 08-Aug-17 A | 25-Aug-17 A | 14 | 0 | 14 | 100% |  | Completed
ER6244LT | W220 | A9820 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-08 | 2017-08-25 | Offer prepared and issued for Fuel Free Verification EAN | 08-Aug-17 A | 25-Aug-17 A | 14 | 0 | 14 | 100% |  | Completed
ER6244LT | W220 | A7890 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-09 | 2017-08-09 | Pre Job Brief for Review Radial Shuffling Safety Case EAN (HYA and HRA) | 09-Aug-17 A | 09-Aug-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A3580 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2017-08-11 | Defueling Options EAN Available for Verification | 11-Aug-17 A | 11-Aug-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A6570 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-14 | 2017-08-15 | Complete requisition approval and issue CI for IFDF Defueling EAN (HYA and HRA) | 14-Aug-17 A | 15-Aug-17 A | 2 | 0 | 2 | 100% |  | Completed
ER6244LT | W220 | A6960 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-14 | 2017-08-15 | Complete requisition approval and issue CI for Ponds and Flasks EAN (HYA and HRA) | 14-Aug-17 A | 15-Aug-17 A | 2 | 0 | 2 | 100% |  | Completed
ER6244LT | W220 | A7090 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-14 | 2017-08-15 | Complete requisition approval and issue CI for Waste Vault Storage Capacity EAN (HYA and HRA) | 14-Aug-17 A | 15-Aug-17 A | 2 | 0 | 2 | 100% |  | Completed
ER6244LT | W220 | A7220 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-14 | 2017-08-15 | Complete requisition approval and issue CI for Impact of Empty Channels on Reactor Cooling EAN | 14-Aug-17 A | 15-Aug-17 A | 2 | 0 | 2 | 100% |  | Completed
ER6244LT | W220 | A3590 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-14 | 2018-02-01 | Verification Review of Defueling Options EAN | 14-Aug-17 A | 01-Feb-18 A | 10 | 0 | 119 | 100% |  | Completed
ER6244LT | W220 | A8930 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-14 | 2017-08-18 | Offer prepared and issued by supplier for Fuelling Machine Light Load Protection & Interlocks EAN (HPB/HNB) | 14-Aug-17 A | 18-Aug-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A9950 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-14 | 2017-08-18 | Offer prepared and issued by supplier for Fuelling Machine Light Load Protection & Interlocks EAN (HYA and HRA) | 14-Aug-17 A | 18-Aug-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A5900 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-15 | 2017-08-21 | Offer prepared and issued by supplier for Dropped FPU Impact on Buffer Store EAN (HPB and HNB) | 15-Aug-17 A | 21-Aug-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A6030 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-15 | 2017-08-21 | Offer prepared and issued by supplier for Dropped FPU Impact on Buffer Store EAN (HYA and HRA) | 15-Aug-17 A | 21-Aug-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A6580 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-16 | 2017-08-16 | Supplier mobilisation | 16-Aug-17 A | 16-Aug-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A6970 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-16 | 2017-08-16 | Supplier mobilisation | 16-Aug-17 A | 16-Aug-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A7100 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-16 | 2017-08-16 | Supplier mobilisation | 16-Aug-17 A | 16-Aug-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A7230 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-16 | 2017-08-16 | Supplier mobilisation | 16-Aug-17 A | 16-Aug-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A5740.EJ | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2017-08-16 | Dropped FPU impact on Reactor Internals and Standpipe Breach EAN (HPB and HNB) available | 16-Aug-17 A | 16-Aug-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A6590 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-17 | 2017-08-17 | Pre Job Brief for IFDF Defueling EAN (HYA and HRA) | 17-Aug-17 A | 17-Aug-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A6600 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-17 | 2018-05-14 | Draft IFDF Defueling EAN (HYA and HRA) | 17-Aug-17 A | 14-May-18 A | 16 | 0 | 186 | 100% |  | Completed
ER6244LT | W220 | A6980 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-17 | 2017-08-17 | Pre Job Brief for Ponds and Flasks EAN (HYA and HRA) | 17-Aug-17 A | 17-Aug-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A6990 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-17 | 2018-05-14 | Draft Ponds and Flasks EAN (HYA and HRA) | 17-Aug-17 A | 14-May-18 A | 16 | 0 | 186 | 100% |  | Completed
ER6244LT | W220 | A7110 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-17 | 2017-08-17 | Pre Job Brief for Waste Vault Storage Capacity EAN (HYA and HRA) | 17-Aug-17 A | 17-Aug-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A7120 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-17 | 2018-05-14 | Draft Waste Vault Storage Capacity EAN (HYA and HRA) | 17-Aug-17 A | 14-May-18 A | 16 | 0 | 186 | 100% |  | Completed
ER6244LT | W220 | A7240 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-17 | 2017-08-17 | Pre Job Brief for Impact of Empty Channels on Reactor Cooling EAN | 17-Aug-17 A | 17-Aug-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A10480 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-06-01 | 2017-11-30 | P.10.01.10 - Defuelling Shutdown Safety Cases - Fault Studies | 21-Aug-17 A | 31-Jan-18 A | 61 | 0 | 113 | 100% |  | Completed
ER6243LT | W200 | A10530 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-06-01 | 2017-06-01 | P.10.01.23 - Defuelling Shutdown Safety Cases - Maintenance | 21-Aug-17 A | 29-Dec-17 A | 0 | 0 | 91 | 100% |  | Completed
ER6243LT | W200 | A13580 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Cooling Faults - RFS Summary Credible Hazards and Faults | 21-Aug-17 A | 29-Sep-17 A | 28 | 0 | 28 | 100% |  | Completed
ER6243LT | W200 | A13590 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Cooling Faults - Prepare Request for Service (RFS) Specification | 21-Aug-17 A | 25-Aug-17 A | 2 | 0 | 4 | 100% |  | Completed
ER6243LT | W200 | A14870 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-02 | 2017-10-13 | Maintenance - RFS Summary - Summary of TS Charges Required | 21-Aug-17 A | 12-Oct-17 A | 50 | 0 | 37 | 100% |  | Completed
ER6243LT | W200 | A14880 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Maintenance - Prepare Request for Service (RFS) Specification | 21-Aug-17 A | 22-Aug-17 A | 2 | 0 | 2 | 100% |  | Completed
ER6243LT | W200 | A16710 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Fault Studies Summary | 21-Aug-17 A | 13-Jul-18 A | 236 | 0 | 226 | 100% |  | Completed
ER6244LT | W220 | A8940 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-21 | 2017-08-22 | Review and negotiate offer for Fuelling Machine Light Load Protection & Interlocks EAN (HPB/HNB) | 21-Aug-17 A | 22-Aug-17 A | 24 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A9960 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-21 | 2017-08-22 | Review and negotiate offer for Fuelling Machine Light Load Protection & Interlocks EAN (HYA and HRA) | 21-Aug-17 A | 22-Aug-17 A | 24 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A5910 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-22 | 2017-08-29 | Review and negotiate offer for Dropped FPU Impact on Buffer Store EAN (HPB and HNB) | 22-Aug-17 A | 29-Aug-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A6040 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-22 | 2017-08-29 | Review and negotiate offer for Dropped FPU Impact on Buffer Store EAN (HYA and HRA) | 22-Aug-17 A | 29-Aug-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | A14890 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Maintenance - Review, Approve and Issue RFS to Supplier | 23-Aug-17 A | 23-Aug-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A15000 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Maintenance - Request for Service (RFS) Specification Issued | 23-Aug-17 A | 23-Aug-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A8950 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-23 | 2017-09-04 | Complete requisition approval and issue CI for Fuelling Machine Light Load Protection & Interlocks EAN (HPB/HNB) | 23-Aug-17 A | 04-Sep-17 A | 12 | 0 | 8 | 100% |  | Completed
ER6244LT | W220 | A9970 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-23 | 2017-09-04 | Complete requisition approval and issue CI for Fuelling Machine Light Load Protection & Interlocks EAN (HYA and HRA) | 23-Aug-17 A | 04-Sep-17 A | 12 | 0 | 8 | 100% |  | Completed
ER6243LT | W200 | A13170.EI | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | PCPV Integrity - Initial Offer Issued for Review | 24-Aug-17 A | 24-Aug-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14900 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Maintenance - Prepare and Issue Offer | 24-Aug-17 A | 25-Aug-17 A | 5 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A15010 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Maintenance - Initial Offer Issued for Review | 25-Aug-17 A | 25-Aug-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A10880 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-07-10 | 2017-07-21 | PCPV Integrity - Review and Negotiate Offer | 25-Aug-17 A | 31-Aug-17 A | 4 | 0 | 4 | 100% |  | Completed
ER6243LT | W200 | A13600 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Cooling Faults - Review, Approve and Issue RFS to Supplier | 28-Aug-17 A | 29-Aug-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A14910 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Maintenance - Review and Negotiate Offer | 28-Aug-17 A | 08-Sep-17 A | 5 | 0 | 8 | 100% |  | Completed
ER6243LT | W200 | A13610 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Cooling Faults - Prepare and Issue Offer | 29-Aug-17 A | 08-Sep-17 A | 5 | 0 | 8 | 100% |  | Completed
ER6243LT | W200 | A13650 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Cooling Faults - Request for Service (RFS) Specification Issued | 29-Aug-17 A | 29-Aug-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A8800 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-29 | 2017-09-04 | Review and negotiate offer for Fuel Free Verification EAN | 29-Aug-17 A | 04-Sep-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A9570 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-29 | 2017-09-04 | Review and negotiate offer for Fuel Free Verification EAN | 29-Aug-17 A | 04-Sep-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A9700 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-29 | 2017-09-04 | Review and negotiate offer for Fuel Free Verification EAN | 29-Aug-17 A | 04-Sep-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A9830 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-29 | 2017-09-04 | Review and negotiate offer for Fuel Free Verification EAN | 29-Aug-17 A | 04-Sep-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A1080 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-08-31 | 2018-10-19 | Produce draft NSRS for HPB and HNB (using BARRIER MODEL) | 31-Aug-17 A | 19-Oct-18 A | 135 | 0 | 289 | 100% |  | Completed
ER6243LT | W200 | A11170 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-09-29 | 2017-10-27 | Cooling Faults - RFS Summary - Rad Con's Requirements for Post NSRS | 01-Sep-17 A | 19-Sep-17 A | 7 | 0 | 12 | 100% |  | Completed
ER6243LT | W200 | A11180 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-09-29 | 2017-10-02 | Cooling Faults - Prepare Request for Service (RFS) Specification | 01-Sep-17 A | 04-Sep-17 A | 2 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A11400 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-17 | 2017-12-22 | Assessm't of Other Faults - RFS Summary | 01-Sep-17 A | 21-Sep-17 A | 12 | 0 | 14 | 100% |  | Completed
ER6243LT | W200 | A11410 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-17 | 2017-11-20 | Assessm't of Other Faults - Prepare Request for Service (RFS) Specification | 01-Sep-17 A | 05-Sep-17 A | 2 | 0 | 2 | 100% |  | Completed
ER6243LT | W200 | A11405 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-23 |  | Assessm't of Other Faults - Start Specifying the Work | 01-Sep-17 A | 01-Sep-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15720 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Prepare Review NSP's for Shutdown Cooling Safety Cases (HPB, HNB) | 01-Sep-17 A | 18-Sep-17 A | 20 | 0 | 11 | 100% |  | Completed
ER6243LT | W200 | A15780 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Prepare Review NSP's for Shutdown Cooling Safety Cases (HYA, HAR) | 01-Sep-17 A | 18-Sep-17 A | 20 | 0 | 11 | 100% |  | Completed
ER6244LT | W220 | A9280 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-01 | 2017-09-29 | Prepare RFS/Spec for Fuel Storage Conditions EAN | 01-Sep-17 A | 29-Sep-17 A | 1 | 0 | 20 | 100% |  | Completed
ER6243LT | W200 | A10890 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-07-24 | 2017-07-25 | PCPV Integrity - Complete Requisition Approval and Issue CI | 01-Sep-17 A | 22-Sep-17 A | 2 | 0 | 15 | 100% |  | Completed
ER6244LT | W220 | A5250 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-01 | 2017-09-04 | Offer prepared and issued for Refuelling Cooling Assessment EAN | 01-Sep-17 A | 04-Sep-17 A | 2 | 0 | 2 | 100% |  | Completed
ER6244LT | W220 | A5920 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-01 | 2017-09-05 | Complete requisition approval and issue CI for Dropped FPU Impact on Buffer Store EAN (HPB and HNB) | 01-Sep-17 A | 05-Sep-17 A | 3 | 0 | 3 | 100% |  | Completed
ER6244LT | W220 | A6050 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-01 | 2017-09-05 | Complete requisition approval and issue CI for Dropped FPU Impact on Buffer Store EAN (HYA and HRA) | 01-Sep-17 A | 05-Sep-17 A | 3 | 0 | 3 | 100% |  | Completed
ER6243LT | W200 | A10885 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | PCPV Integrity - Offer Accepted/Approved | 01-Sep-17 A | 01-Sep-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A9030 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-01 | 2017-09-29 | Prepare RFS/Spec for Fuel Storage Conditions EAN | 01-Sep-17 A | 29-Sep-17 A | 21 | 0 | 21 | 100% |  | Completed
ER6243LT | W200 | A15180 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Prepare Linking BAT/BPM into optioneering Specification (HPB, HNB) | 01-Sep-17 A | 15-Sep-17 A | 11 | 0 | 10 | 100% |  | Completed
ER6243LT | W200 | A15420 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Prepare Linking BAT/BPM into optioneering Specification (HYA, HAR) | 01-Sep-17 A | 15-Sep-17 A | 11 | 0 | 10 | 100% |  | Completed
ER6243LT | W200 | A14540 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Principles of Fuel Free Verification - Review of Offer before Req is approved & CI Issued (HPB, HNB) | 04-Sep-17 A | 04-Sep-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14560 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Principles of Fuel Free Verification - Review of Offer before Req is approved & CI Issued (HYA, HAR) | 04-Sep-17 A | 04-Sep-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A7970 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-04 | 2017-09-08 | Review, approve and issue RFS for CRA Isolation Requirements EAN | 04-Sep-17 A | 08-Sep-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | A11190 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-03 | 2017-10-03 | Cooling Faults - Review, Approve and Issue RFS to Supplier | 05-Sep-17 A | 05-Sep-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A11195 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Cooling Faults - Request for Service (RFS) Specification Issued | 05-Sep-17 A | 05-Sep-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A5260 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-05 | 2017-09-06 | Review and negotiate offer for Refuelling Cooling Assessment EAN | 05-Sep-17 A | 06-Sep-17 A | 2 | 0 | 2 | 100% |  | Completed
ER6244LT | W220 | A8810 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-05 | 2017-09-11 | Complete requisition approval and issue CI for Fuel Free Verification EAN | 05-Sep-17 A | 11-Sep-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A8960 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-05 | 2017-09-11 | Supplier mobilisation | 05-Sep-17 A | 11-Sep-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A9580 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-05 | 2017-09-11 | Complete requisition approval and issue CI for Fuel Free Verification EAN | 05-Sep-17 A | 11-Sep-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A9710 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-05 | 2017-09-11 | Complete requisition approval and issue CI for Fuel Free Verification EAN | 05-Sep-17 A | 11-Sep-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A9840 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-05 | 2017-09-11 | Complete requisition approval and issue CI for Fuel Free Verification EAN | 05-Sep-17 A | 11-Sep-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A9980 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-05 | 2017-09-11 | Supplier mobilisation | 05-Sep-17 A | 11-Sep-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | A11200 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-04 | 2017-10-10 | Cooling Faults - Prepare and Issue Offer | 06-Sep-17 A | 12-Sep-17 A | 5 | 0 | 4 | 100% |  | Completed
ER6243LT | W200 | A11420 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-21 | 2017-11-21 | Assessm't of Other Faults - Review, Approve and Issue RFS to Supplier | 06-Sep-17 A | 07-Sep-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A5930 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-06 | 2017-09-06 | Supplier mobilisation | 06-Sep-17 A | 06-Sep-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A6060 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-06 | 2017-09-06 | Supplier mobilisation | 06-Sep-17 A | 06-Sep-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | RSSC.VI.A100 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-07-26 | 2018-02-02 | PCPV Integrity - Structural Integrity Calcs for the Impact of Hanging the Plug Unit from the Pilecap (HPB, HNB) | 07-Sep-17 A | 19-Mar-19 A | 398 | 0 | 387 | 100% |  | Completed
ER6243LT | W200 | RSSC.VI.A105 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-07-26 | 2017-07-26 | PCPV Integrity - Pre Job Brief (HPB, HNB) | 07-Sep-17 A | 07-Sep-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A11425 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-10-25 | Assessm't of Other Faults - Request for Service (RFS) Specification Issued | 07-Sep-17 A | 07-Sep-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A5270 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-07 | 2017-09-07 | Complete requisition approval and issue CI for Refuelling Cooling Assessment EAN | 07-Sep-17 A | 07-Sep-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A5940 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-07 | 2017-09-07 | Pre Job Brief for Dropped FPU Impact on Buffer Store EAN (HPB and HNB) | 07-Sep-17 A | 07-Sep-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A5950 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-07 | 2018-01-05 | Draft Dropped FPU Impact on Buffer Store EAN (HPB and HNB) | 07-Sep-17 A | 05-Jan-18 A | 45 | 0 | 84 | 100% |  | Completed
ER6244LT | W220 | A6070 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-07 | 2017-09-07 | Pre Job Brief for Dropped FPU Impact on Buffer Store EAN (HYA and HRA) | 07-Sep-17 A | 07-Sep-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A6080 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-07 | 2018-01-05 | Draft Dropped FPU Impact on Buffer Store EAN (HYA and HRA) | 07-Sep-17 A | 05-Jan-18 A | 45 | 0 | 84 | 100% |  | Completed
ER6244LT | W220 | A8290 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-07 | 2017-09-11 | Supplier mobilisation | 07-Sep-17 A | 11-Sep-17 A | 3 | 0 | 3 | 100% |  | Completed
ER6244LT | W220 | A8420 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-07 | 2017-09-11 | Supplier mobilisation | 07-Sep-17 A | 11-Sep-17 A | 3 | 0 | 3 | 100% |  | Completed
ER6243LT | W200 | RSSC.VI.A160 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-07-31 | 2018-02-02 | PCPV Integrity - Structural Integrity Calcs for the Impact of Hanging the Plug Unit from the Pilecap (HYA, HAR) | 08-Sep-17 A | 19-Mar-19 A | 397 | 0 | 386 | 100% |  | Completed
ER6243LT | W200 | A10900 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-07-17 | 2017-07-31 | PCPV Integrity - Supplier Mobilisation Time | 08-Sep-17 A | 11-Sep-17 A | 10 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | RSSC.VI.A106 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-07-31 | 2018-01-05 | PCPV Integrity - Prepare Basis of Design Report (Phase 1) for Structural Integrity of PCPV (HPB, HNB) | 08-Sep-17 A | 31-Oct-17 A | 111 | 0 | 37 | 100% |  | Completed
ER6243LT | W200 | RSSC.VI.A165 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-07-31 | 2018-01-05 | PCPV Integrity - Prepare Basis of Design Report (Phase 1) for Structural Integrity of PCPV (HYA, HAR) | 08-Sep-17 A | 31-Oct-17 A | 111 | 0 | 37 | 100% |  | Completed
ER6243LT | W200 | A11100 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-08-23 | Closure and Seal Integrity - RFS review before it is issued to Supplier (HPB, HNB) | 08-Sep-17 A | 08-Sep-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11140 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-11-02 | Closure and Seal Integrity - RFS review before it is issued to Supplier (HYA, HAR) | 08-Sep-17 A | 08-Sep-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11430 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-22 | 2017-11-28 | Assessm't of Other Faults - Prepare and Issue Offer | 12-Sep-17 A | 12-Sep-17 A | 5 | 0 | 2 | 100% |  | Completed
ER6243LT | W200 | A13660 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Cooling Faults - Initial Offer Issued for Review | 08-Sep-17 A | 08-Sep-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15020 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-09-29 | Maintenance - Offer Accepted/Approved | 08-Sep-17 A | 08-Sep-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A5280 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-08 | 2017-09-08 | Supplier mobilisation | 08-Sep-17 A | 08-Sep-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A6150 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-08 | 2017-09-14 | Review, approve and issue RFS for Buffer Store Defueling EAN (HPB and HNB) | 08-Sep-17 A | 14-Sep-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A6280 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-08 | 2017-09-14 | Review, approve and issue RFS for IFDF Defueling EAN (HPB and HNB) | 08-Sep-17 A | 14-Sep-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A6670 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-08 | 2017-09-14 | Review, approve and issue RFS for Ponds and Flasks EAN (HPB and HNB) | 08-Sep-17 A | 14-Sep-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A6800 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-08 | 2017-09-13 | Review, approve and issue RFS for Waste Vault Storage Capacity EAN (HPB and HNB) | 08-Sep-17 A | 13-Sep-17 A | 4 | 0 | 4 | 100% |  | Completed
ER6243LT | W200 | A13620 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Cooling Faults - Review and Negotiate Offer | 11-Sep-17 A | 11-Sep-17 A | 5 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A13670 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Cooling Faults - Offer Accepted/Approved | 11-Sep-17 A | 11-Sep-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14920 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-02 | 2017-10-02 | Maintenance - Complete Requisition Approval and Issue CI | 11-Sep-17 A | 29-Sep-17 A | 1 | 0 | 14 | 100% |  | Completed
ER6244LT | W220 | A5290 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-11 | 2017-09-11 | Pre Job Brief for Refuelling Cooling Assessment EAN | 11-Sep-17 A | 11-Sep-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A5300 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-11 | 2018-02-23 | Draft Refuelling Cooling Assessment EAN | 11-Sep-17 A | 23-Feb-18 A | 15 | 0 | 116 | 100% |  | Completed
ER6244LT | W220 | A5850 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-11 | 2017-09-15 | FNC update and issue Dropped FPU impact on Reactor Internals Report (HYA and HRA) | 11-Sep-17 A | 15-Sep-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A7980 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-11 | 2017-09-15 | Offer prepared and issued for CRA Isolation Requirements EAN | 11-Sep-17 A | 15-Sep-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | A11205 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Cooling Faults - Initial Offer Issued for Review | 12-Sep-17 A | 12-Sep-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11435 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-11-01 | Assessm't of Other Faults - Initial Offer Issued for Review | 12-Sep-17 A | 12-Sep-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A13630 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Cooling Faults - Complete Requisition Approval and Issue CI | 12-Sep-17 A | 25-Sep-17 A | 1 | 0 | 9 | 100% |  | Completed
ER6244LT | W220 | A8300 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-12 | 2017-09-12 | Pre Job Brief for Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 12-Sep-17 A | 12-Sep-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A8820 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-12 | 2017-09-21 | Supplier mobilisation | 12-Sep-17 A | 21-Sep-17 A | 8 | 0 | 8 | 100% |  | Completed
ER6244LT | W220 | A8970 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-12 | 2017-09-12 | Pre Job Brief for Fuelling Machine Light Load Protection & Interlocks EAN (HPB/HNB) | 12-Sep-17 A | 12-Sep-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A8980 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-12 | 2018-02-22 | Draft Fuelling Machine Light Load Protection & Interlocks EAN (HYA and HRA) | 12-Sep-17 A | 22-Feb-18 A | 49 | 0 | 115 | 100% |  | Completed
ER6244LT | W220 | A9590 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-12 | 2017-09-21 | Supplier mobilisation | 12-Sep-17 A | 21-Sep-17 A | 8 | 0 | 8 | 100% |  | Completed
ER6244LT | W220 | A9720 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-12 | 2017-09-21 | Supplier mobilisation | 12-Sep-17 A | 21-Sep-17 A | 8 | 0 | 8 | 100% |  | Completed
ER6244LT | W220 | A9850 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-12 | 2017-09-21 | Supplier mobilisation | 12-Sep-17 A | 21-Sep-17 A | 8 | 0 | 8 | 100% |  | Completed
ER6244LT | W220 | A9990 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-12 | 2017-09-12 | Pre Job Brief for Fuelling Machine Light Load Protection & Interlocks EAN (HYA and HRA) | 12-Sep-17 A | 12-Sep-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A10000 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-12 | 2018-08-01 | Draft Fuelling Machine Light Load Protection & Interlocks EAN (HYA/HRA) | 12-Sep-17 A | 01-Aug-18 A | 49 | 0 | 225 | 100% |  | Completed
ER6243LT | W200 | A11210 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-11 | 2017-10-17 | Cooling Faults - Review and Negotiate Offer | 13-Sep-17 A | 15-Sep-17 A | 5 | 0 | 2 | 100% |  | Completed
ER6243LT | W200 | A11440 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-29 | 2017-12-05 | Assessm't of Other Faults - Review and Negotiate Offer | 13-Sep-17 A | 15-Sep-17 A | 5 | 0 | 2 | 100% |  | Completed
ER6244LT | W220 | A8310 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-13 | 2018-01-12 | Draft Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 13-Sep-17 A | 12-Jan-18 A | 85 | 0 | 84 | 100% |  | Completed
ER6244LT | W220 | A8430 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-13 | 2017-09-13 | Pre Job Brief for Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 13-Sep-17 A | 13-Sep-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A8440 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-13 | 2018-01-12 | Draft Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 13-Sep-17 A | 12-Jan-18 A | 85 | 0 | 84 | 100% |  | Completed
ER6244LT | W220 | A6810 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-14 | 2017-09-25 | Offer prepared and issued by supplier for Waste Vault Storage Capacity EAN (HPB and HNB) | 14-Sep-17 A | 25-Sep-17 A | 8 | 0 | 8 | 100% |  | Completed
ER6243LT | W200 | A11215 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Cooling Faults - Offer Accepted/Approved | 15-Sep-17 A | 15-Sep-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11445 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-11-08 | Assessm't of Other Faults - Offer Accepted/Approved | 15-Sep-17 A | 15-Sep-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15190 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Linking BAT/BPM into optioneering Specification Agreed (HPB, HNB) | 15-Sep-17 A | 15-Sep-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15430 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Linking BAT/BPM into optioneering Specification Agreed (HYA, HAR) | 15-Sep-17 A | 15-Sep-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A6160 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-15 | 2017-09-25 | Offer prepared and issued by supplier for Buffer Store Defueling EAN (HPB and HNB) | 15-Sep-17 A | 25-Sep-17 A | 7 | 0 | 7 | 100% |  | Completed
ER6244LT | W220 | A6290 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-15 | 2017-09-25 | Offer prepared and issued by supplier for IFDF Defueling EAN (HPB and HNB) | 15-Sep-17 A | 25-Sep-17 A | 7 | 0 | 7 | 100% |  | Completed
ER6244LT | W220 | A6680 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-15 | 2017-09-25 | Offer prepared and issued by supplier for Ponds and Flasks EAN (HPB and HNB) | 15-Sep-17 A | 25-Sep-17 A | 7 | 0 | 7 | 100% |  | Completed
ER6243LT | W200 | A11220 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-18 | 2017-10-18 | Cooling Faults - Complete Requisition Approval and Issue CI | 18-Sep-17 A | 19-Sep-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A11450 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-06 | 2017-12-06 | Assessm't of Other Faults - Complete Requisition Approval and Issue CI | 18-Sep-17 A | 19-Sep-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A15200 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Prepare Linking BAT/BPM into optioneering Report (HPB, HNB) | 18-Sep-17 A | 22-Sep-17 A | 5 | 0 | 4 | 100% |  | Completed
ER6243LT | W200 | A15440 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Prepare Linking BAT/BPM into optioneering Report (HYA, HAR) | 18-Sep-17 A | 22-Sep-17 A | 5 | 0 | 4 | 100% |  | Completed
ER6243LT | W200 | A15730 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Review NSP's for Shutdown Cooling Safety Cases Agreed (HPB, HNB) | 18-Sep-17 A | 18-Sep-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15790 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Review NSP's for Shutdown Cooling Safety Cases Agreed (HYA, HAR) | 18-Sep-17 A | 18-Sep-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A5860 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-18 | 2017-09-22 | Complete TR form and upload Dropped FPU impact on Reactor Internals Report (HYA and HRA) to CDMS | 18-Sep-17 A | 22-Sep-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A7990 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-18 | 2017-09-22 | Review and negotiate offer for CRA Isolation Requirements EAN | 18-Sep-17 A | 22-Sep-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | A11230 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-19 | 2017-10-27 | Cooling Faults - Supplier Mobilisation Time | 19-Sep-17 A | 19-Sep-17 A | 7 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15740 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-09-19 | 2017-10-31 | Prepare Review NSP's for Shutdown Cooling Safety Cases Report (HPB, HNB) | 19-Sep-17 A | 31-Oct-17 A | 40 | 0 | 30 | 100% |  | Completed
ER6243LT | W200 | A15800 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-09-19 | 2017-10-31 | Prepare Review NSP's for Shutdown Cooling Safety Cases Report (HYA, HAR) | 19-Sep-17 A | 31-Oct-17 A | 40 | 0 | 30 | 100% |  | Completed
ER6243LT | W200 | A11460 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-07 | 2017-12-22 | Assessm't of Other Faults - Supplier Mobilisation Time | 20-Sep-17 A | 21-Sep-17 A | 12 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | RSSC.FS.A120 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-02-22 | 2018-05-04 | Review of assumptions and revision of fault schedules for reactor defuelling (HPB, HNB) | 22-Sep-17 A | 13-Jul-18 A | 221 | 0 | 203 | 100% |  | Completed
ER6243LT | W200 | A15120 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-28 | 2017-11-28 | Assessm't of Other Faults - Pre Job Brief (HPB, HNB) | 22-Sep-17 A | 22-Sep-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A15210 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Draft Linking BAT/BPM into optioneering Report Available for Review (HPB, HNB) | 22-Sep-17 A | 22-Sep-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15450 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Draft Linking BAT/BPM into optioneering Report Available for Review (HYA, HAR) | 22-Sep-17 A | 22-Sep-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A8830 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-22 | 2017-09-22 | Pre Job Brief for Fuel Free Verification EAN | 22-Sep-17 A | 22-Sep-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A9600 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-22 | 2017-09-22 | Pre Job Brief for Fuel Free Verification EAN | 22-Sep-17 A | 22-Sep-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A9730 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-22 | 2017-09-22 | Pre Job Brief for Fuel Free Verification EAN | 22-Sep-17 A | 22-Sep-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A9860 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-22 | 2017-09-22 | Pre Job Brief for Fuel Free Verification EAN | 22-Sep-17 A | 22-Sep-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A5870.EJ | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2017-09-22 | Dropped FPU impact on Reactor Internals Rerport (HYA and HRA) available | 22-Sep-17 A | 22-Sep-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.FS.A190 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-02-22 | 2018-05-04 | Review of assumptions and revision of fault schedules for reactor defuelling (HYA, HAR) | 25-Sep-17 A | 13-Jul-18 A | 220 | 0 | 202 | 100% |  | Completed
ER6243LT | W200 | RSSC.FS.A340 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-02-22 | 2018-04-06 | Assessm't of Other Faults - Prepare Fault Studies Report (HPB, HNB) | 25-Sep-17 A | 22-Dec-17 A | 30 | 0 | 65 | 100% |  | Completed
ER6243LT | W200 | RSSC.FS.A380 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-02-22 | 2018-04-06 | Assessm't of Other Faults - Prepare Fault Studies Report (HYA, HAR) | 25-Sep-17 A | 08-Dec-17 A | 30 | 0 | 55 | 100% |  | Completed
ER6243LT | W200 | A13640 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Cooling Faults - Supplier Mobilisation Time | 25-Sep-17 A | 29-Sep-17 A | 7 | 0 | 4 | 100% |  | Completed
ER6243LT | W200 | A15220 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-09-25 | 2018-01-19 | Review & Acceptance of Linking BAT/BPM into optioneering Report (HPB, HNB) | 25-Sep-17 A | 13-Dec-17 A | 36 | 0 | 57 | 100% |  | Completed
ER6243LT | W200 | A15460 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-09-25 | 2018-01-19 | Review & Acceptance of Linking BAT/BPM into optioneering Report (HYA, HAR) | 25-Sep-17 A | 13-Dec-17 A | 58 | 0 | 57 | 100% |  | Completed
ER6244LT | W220 | A8000 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-25 | 2017-09-29 | Complete requisition approval and issue CI for CRA Isolation Requirements EAN | 25-Sep-17 A | 29-Sep-17 A | 4 | 0 | 4 | 100% |  | Completed
ER6244LT | W220 | A8840 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-25 | 2018-02-23 | Draft Fuel Free Verification EAN | 25-Sep-17 A | 23-Feb-18 A | 68 | 0 | 106 | 100% |  | Completed
ER6244LT | W220 | A5870.EJ10 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-25 | 2017-12-22 | Dropped FPU Impact on Reactor Internals Report upreved (HYA and HRA) | 25-Sep-17 A | 22-Dec-17 A | 21 | 0 | 64 | 100% |  | Completed
ER6244LT | W220 | A9610 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-25 | 2018-07-09 | Draft Fuel Free Verification EAN | 25-Sep-17 A | 09-Jul-18 A | 68 | 0 | 199 | 100% |  | Completed
ER6244LT | W220 | A9740 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-25 | 2018-09-27 | Draft Fuel Free Verification EAN | 25-Sep-17 A | 27-Sep-18 A | 68 | 0 | 256 | 100% |  | Completed
ER6244LT | W220 | A9870 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-25 | 2018-05-04 | Draft Fuel Free Verification EAN | 25-Sep-17 A | 04-May-18 A | 68 | 0 | 155 | 100% |  | Completed
ER6243LT | W200 | A11750 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-06-23 | 2017-06-23 | Thermal Hydraulics (MACE) - Review, Approve and Issue RFS to Supplier | 26-Sep-17 A | 26-Sep-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A11760 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-06-26 | 2017-06-30 | Thermal Hydraulics (MACE) - Prepare and Issue Offer | 26-Sep-17 A | 11-Oct-17 A | 5 | 0 | 11 | 100% |  | Completed
ER6243LT | W200 | A11755 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Thermal Hydraulics (MACE) - Request for Service (RFS) Specification Issued | 26-Sep-17 A | 26-Sep-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A6170 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-26 | 2017-10-03 | Review and negotiate offer for Buffer Store Defueling EAN (HPB and HNB) | 26-Sep-17 A | 03-Oct-17 A | 6 | 0 | 6 | 100% |  | Completed
ER6244LT | W220 | A6300 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-26 | 2017-10-03 | Review and negotiate offer for IFDF Defueling EAN (HPB and HNB) | 26-Sep-17 A | 03-Oct-17 A | 6 | 0 | 6 | 100% |  | Completed
ER6244LT | W220 | A6690 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-26 | 2017-10-03 | Review and negotiate offer for Ponds and Flasks EAN (HPB and HNB) | 26-Sep-17 A | 03-Oct-17 A | 6 | 0 | 6 | 100% |  | Completed
ER6244LT | W220 | A6820 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-09-26 | 2017-10-03 | Review and negotiate offer for Waste Vault Storage Capacity EAN (HPB and HNB) | 26-Sep-17 A | 03-Oct-17 A | 6 | 0 | 6 | 100% |  | Completed
ER6243LT | W200 | A11110 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-09-14 | Closure and Seal Integrity - Review of Offer before the Req is approved and CI issued (HPB, HNB) | 29-Sep-17 A | 29-Sep-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11150 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-11-23 | Closure and Seal Integrity - Review of Offer before the Req is approved and CI issued (HYA, HAR) | 29-Sep-17 A | 29-Sep-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.FS.A170 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-30 | 2017-12-22 | Cooling Faults - Credible Hazards and Faults Summary (HPB, HNB) | 02-Oct-17 A | 29-Jun-18 A | 193 | 0 | 187 | 100% |  | Completed
ER6243LT | W200 | A14930 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-03 | 2017-10-11 | Maintenance - Supplier Mobilisation Time | 02-Oct-17 A | 12-Oct-17 A | 7 | 0 | 8 | 100% |  | Completed
ER6243LT | W200 | A15110 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-02 | 2017-10-02 | Cooling Faults - Pre Job Brief (HPB, HNB) | 02-Oct-17 A | 02-Oct-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A9290 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-02 | 2017-10-05 | Review, approve and issue RFS for Fuel Storage Conditions EAN | 02-Oct-17 A | 05-Oct-17 A | 2 | 0 | 3 | 100% |  | Completed
ER6244LT | W220 | A6310 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-02 | 2017-10-27 | Complete requisition approval and issue CI for IFDF Defueling EAN (HPB and HNB) | 02-Oct-17 A | 27-Oct-17 A | 20 | 0 | 20 | 100% |  | Completed
ER6244LT | W220 | A8010 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-02 | 2017-10-02 | Supplier mobilisation | 02-Oct-17 A | 02-Oct-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A9040 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-02 | 2017-10-05 | Review, approve and issue RFS for Fuel Storage Conditions EAN | 02-Oct-17 A | 05-Oct-17 A | 4 | 0 | 4 | 100% |  | Completed
ER6243LT | W200 | RSSC.FS.A300 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-30 | 2017-11-24 | Cooling Faults - Credible Hazards and Faults (HPB, HNB) | 03-Oct-17 A | 21-Nov-17 A | 20 | 0 | 35 | 100% |  | Completed
ER6243LT | W200 | A13510 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-03 | 2017-12-08 | Cooling Faults - Credible Hazards and Faults Summary (HYA, HAR) | 03-Oct-17 A | 29-Jun-18 A | 192 | 0 | 186 | 100% |  | Completed
ER6243LT | W200 | A13570 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-03 | 2017-10-30 | Cooling Faults - Credible Hazards and Faults (HYA, HAR) | 03-Oct-17 A | 03-Jan-18 A | 20 | 0 | 63 | 100% |  | Completed
ER6244LT | W220 | A8020 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-03 | 2017-10-03 | Pre Job Brief for CRA Isolation Requirements EAN | 03-Oct-17 A | 03-Oct-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A8030 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-03 | 2018-02-28 | Draft CRA Isolation Requirements EAN | 03-Oct-17 A | 28-Feb-18 A | 47 | 0 | 103 | 100% |  | Completed
ER6244LT | W220 | A6180 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-04 | 2017-10-27 | Complete requisition approval and issue CI for Buffer Store Defueling EAN (HPB and HNB) | 04-Oct-17 A | 27-Oct-17 A | 20 | 0 | 18 | 100% |  | Completed
ER6244LT | W220 | A6700 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-04 | 2017-10-27 | Complete requisition approval and issue CI for Ponds and Flasks EAN (HPB and HNB) | 04-Oct-17 A | 27-Oct-17 A | 20 | 0 | 18 | 100% |  | Completed
ER6244LT | W220 | A6830 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-04 | 2017-10-27 | Complete requisition approval and issue CI for Waste Vault Storage Capacity EAN (HPB and HNB) | 04-Oct-17 A | 27-Oct-17 A | 20 | 0 | 18 | 100% |  | Completed
ER6244LT | W220 | A9300 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-06 | 2017-10-12 | Offer prepared and issued by supplier for Fuel Storage Conditions EAN | 06-Oct-17 A | 12-Oct-17 A | 1 | 0 | 4 | 100% |  | Completed
ER6244LT | W220 | A9050 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-06 | 2017-10-12 | Offer prepared and issued by supplier for Fuel Storage Conditions EAN | 06-Oct-17 A | 12-Oct-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | A11765 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-10-20 | Thermal Hydraulics (MACE) - Initial Offer issued for Review | 11-Oct-17 A | 11-Oct-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11770 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-07-03 | 2017-07-07 | Thermal Hydraulics (MACE) - Review and Negotiate Offer | 12-Oct-17 A | 23-Oct-17 A | 5 | 0 | 7 | 100% |  | Completed
ER6243LT | W200 | A14850 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-16 | 2018-01-11 | Maintenance - Summary of TS Charges Required (HPB, HNB) | 13-Oct-17 A | 06-Jul-18 A | 224 | 0 | 183 | 100% |  | Completed
ER6243LT | W200 | A14940 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-16 | 2017-10-16 | Maintenance - Pre Job Brief (HPB, HNB) | 13-Oct-17 A | 13-Oct-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A15030 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-16 | 2018-01-11 | Maintenance - Summary of TS Charges Required (HYA, HAR) | 13-Oct-17 A | 06-Jul-18 A | 224 | 0 | 183 | 100% |  | Completed
ER6243LT | W200 | A15050 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-16 | 2017-10-16 | Maintenance - Pre Job Brief (HYA, HAR) | 13-Oct-17 A | 13-Oct-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A9310 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-13 | 2017-10-18 | Review and negotiate offer for Fuel Storage Conditions EAN | 13-Oct-17 A | 18-Oct-17 A | 5 | 0 | 3 | 100% |  | Completed
ER6244LT | W220 | A9060 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-13 | 2017-10-18 | Review and negotiate offer for Fuel Storage Conditions EAN | 13-Oct-17 A | 18-Oct-17 A | 4 | 0 | 4 | 100% |  | Completed
ER6243LT | W200 | A14990 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-17 | 2017-12-04 | Maintenance - Summary of TS Charges Required (HPB, HNB) | 16-Oct-17 A | 16-Feb-18 A | 35 | 0 | 86 | 100% |  | Completed
ER6243LT | W200 | A15100 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-17 | 2017-12-04 | Maintenance - Summary of TS Charges Required (HYA, HAR) | 16-Oct-17 A | 16-Feb-18 A | 35 | 0 | 86 | 100% |  | Completed
ER6243LT | W200 | RSSC.FS.A100 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-30 | 2017-12-22 | Cooling Faults - Rad Con's Requirements for Post NSRS (HPB, HNB) | 19-Oct-17 A | 29-Jun-18 A | 180 | 0 | 174 | 100% |  | Completed
ER6243LT | W200 | RSSC.FS.A280 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-30 | 2017-10-30 | Cooling Faults - Pre Job Brief (HPB, HNB) | 19-Oct-17 A | 19-Oct-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A13430 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-02 | 2018-01-17 | Cooling Faults - Rad Con's Requirements for Post NSRS (HYA, HAR) Summary | 19-Oct-17 A | 29-Jun-18 A | 185 | 0 | 174 | 100% |  | Completed
ER6243LT | W200 | A13450 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-02 | 2017-10-02 | Cooling Faults - Pre Job Brief (HYA, HAR) | 19-Oct-17 A | 19-Oct-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A9320 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-19 | 2017-11-27 | Complete requisition approval and issue CI for Fuel Storage Conditions EAN | 19-Oct-17 A | 27-Nov-17 A | 2 | 0 | 27 | 100% |  | Completed
ER6243LT | W200 | RSSC.FS.A290 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-30 | 2017-11-24 | Cooling Faults - Rad Con's Requirements for Post NSRS (HPB, HNB) | 20-Oct-17 A | 25-Jan-18 A | 20 | 0 | 66 | 100% |  | Completed
ER6243LT | W200 | A13500 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-02 | 2017-10-27 | Cooling Faults - Rad Con's Requirements for Post NSRS (HYA, HAR) | 20-Oct-17 A | 25-Jan-18 A | 20 | 0 | 66 | 100% |  | Completed
ER6243LT | W200 | A11775 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-10-27 | Thermal Hydraulics (MACE) - Offer Accepted/Approved | 23-Oct-17 A | 23-Oct-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A1440 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-23 | 2018-02-14 | Assess interlock changes required for staggered operation of reactors, defueling mode & FPUs back in reactor (HPB & HNB) | 23-Oct-17 A | 14-Feb-18 A | 80 | 0 | 80 | 100% |  | Completed
ER6243LT | W200 | A11780 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-07-10 | 2017-07-10 | Thermal Hydraulics (MACE) - Complete Requisition Approval and Issue CI | 24-Oct-17 A | 10-Nov-17 A | 1 | 0 | 13 | 100% |  | Completed
ER6244LT | W220 | A6190 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-30 | 2017-10-30 | Supplier mobilisation | 30-Oct-17 A | 30-Oct-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A6320 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-30 | 2017-10-30 | Supplier mobilisation | 30-Oct-17 A | 30-Oct-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A6710 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-30 | 2017-10-30 | Supplier mobilisation | 30-Oct-17 A | 30-Oct-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A6840 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-30 | 2017-10-30 | Supplier mobilisation | 30-Oct-17 A | 30-Oct-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A8720 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2017-10-30 | Draft Initial Fault Studies and Risk Estimation Report verified and issued for Verification (HPB/HNB) | 30-Oct-17 A | 30-Oct-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15750 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-10-31 | Draft Review NSP's for Shutdown Cooling Safety CasesReport Available for Review (HPB, HNB) | 31-Oct-17 A | 31-Oct-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15810 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-10-31 | Draft Review NSP's for Shutdown Cooling Safety CasesReport Available for Review (HYA, HAR) | 31-Oct-17 A | 31-Oct-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A6200 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-31 | 2017-10-31 | Pre Job Brief for Buffer Store Defueling EAN (HPB and HNB) | 31-Oct-17 A | 31-Oct-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A6210 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-31 | 2018-03-26 | Draft Buffer Store Defueling EAN (HPB and HNB) | 31-Oct-17 A | 26-Mar-18 A | 86 | 0 | 102 | 100% |  | Completed
ER6244LT | W220 | A6330 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-31 | 2017-10-31 | Pre Job Brief for IFDF Defueling EAN (HPB and HNB) | 31-Oct-17 A | 31-Oct-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A6340 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-31 | 2018-03-26 | Draft IFDF Defueling EAN (HPB and HNB) | 31-Oct-17 A | 26-Mar-18 A | 86 | 0 | 102 | 100% |  | Completed
ER6244LT | W220 | A6720 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-31 | 2017-10-31 | Pre Job Brief for Ponds and Flasks EAN (HPB and HNB) | 31-Oct-17 A | 31-Oct-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A6730 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-31 | 2018-03-26 | Draft Ponds and Flasks EAN (HPB and HNB) | 31-Oct-17 A | 26-Mar-18 A | 86 | 0 | 102 | 100% |  | Completed
ER6244LT | W220 | A6850 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-31 | 2017-10-31 | Pre Job Brief for Waste Vault Storage Capacity EAN (HPB and HNB) | 31-Oct-17 A | 31-Oct-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A6860 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-31 | 2018-03-26 | Draft Waste Vault Storage Capacity EAN (HPB and HNB) | 31-Oct-17 A | 26-Mar-18 A | 86 | 0 | 102 | 100% |  | Completed
ER6244LT | W220 | A8730 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-10-31 | 2018-01-02 | Verification of Initial Fault Studies and Risk Estimation Report (HPB/HNB) | 31-Oct-17 A | 02-Jan-18 A | 16 | 0 | 42 | 100% |  | Completed
ER6244LT | W220 | A4200 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-11-01 | 2018-06-29 | P20.01.01.15 - Pile Cap Equipment | 01-Nov-17 A | 29-Jun-18 A | 41 | 0 | 165 | 100% |  | Completed
ER6244LT | W220 | A3640 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2017-11-03 | Guidance for batch size for defuelling during staggered operation | 03-Nov-17 A | 03-Nov-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A10500 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-06-01 | 2017-06-01 | P.10.01.13 - Defuelling Shutdown Safety Cases - Reactor Control System | 03-Nov-17 A | 29-Dec-17 A | 0 | 0 | 38 | 100% |  | Completed
ER6243LT | W200 | A11790 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-07-11 | 2017-07-19 | Thermal Hydraulics (MACE) - Supplier Mobilisation Time | 13-Nov-17 A | 16-Nov-17 A | 1 | 0 | 3 | 100% |  | Completed
ER6243LT | W200 | A13130.EA | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-10-31 | Contract Variation approved for next phase | 17-Nov-17 A | 17-Nov-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A13140 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-01 | 2018-03-02 | Ops Compliance - Prepare QA3 SDM Defuelling Strategy Optioneering Report (2nd Phase) | 17-Nov-17 A | 26-Jan-18 A | 61 | 0 | 47 | 100% |  | Completed
ER6243LT | W200 | A11280 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-11-24 | Cooling Faults - Credible Hazards and Faults verified and issued for Technical Review (HPB, HNB) | 21-Nov-17 A | 21-Nov-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11290 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-27 | 2017-12-08 | Cooling Faults - Credible Hazards and Faults Technical Review by SQEP (HPB, HNB) | 21-Nov-17 A | 14-Mar-18 A | 10 | 0 | 78 | 100% |  | Completed
ER6243LT | W200 | A12140 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-03 | 2018-01-02 | RCS Basis of Design - RFS Summary - High Level Impact Assessment | 21-Nov-17 A | 12-Feb-18 A | 67 | 0 | 56 | 100% |  | Completed
ER6243LT | W200 | A12150 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-03 | 2017-11-09 | RCS Basis of Design - Prepare Request for Service (RFS) Specification | 21-Nov-17 A | 12-Dec-17 A | 5 | 0 | 15 | 100% |  | Completed
ER6243LT | W200 | A12145 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-03 |  | RCS Basis of Design - Start Specifying the Work | 21-Nov-17 A | 21-Nov-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15880 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-02-28 | 2018-04-26 | RCS Basis of Design - RFS Summary - Overall Delivery Plan | 21-Nov-17 A | 12-Feb-18 A | 50 | 0 | 56 | 100% |  | Completed
ER6243LT | W200 | A15890 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-02-28 | 2018-03-06 | RCS Basis of Design - Prepare Request for Service (RFS) Specification | 21-Nov-17 A | 15-Dec-17 A | 5 | 0 | 18 | 100% |  | Completed
ER6243LT | W200 | A16090 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-02-28 |  | RCS Basis of Design - Start Specifying the Work | 21-Nov-17 A | 21-Nov-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A9330 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-11-27 | 2017-11-27 | Supplier mobilisation | 27-Nov-17 A | 27-Nov-17 A | 1 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A9340 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-11-27 | 2017-11-27 | Pre Job Brief for Fuel Storage Conditions EAN | 27-Nov-17 A | 27-Nov-17 A | 1 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A9350 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-11-27 | 2018-03-29 | Draft Fuel Storage Conditions EAN | 27-Nov-17 A | 29-Mar-18 A | 16 | 0 | 86 | 100% |  | Completed
ER6243LT | W200 | A14620 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-01 | 2017-12-08 | Thermal Hydraulics - RFS Summary - PCPV Integrity for Changing Temperatures | 01-Dec-17 A | 20-Feb-18 A | 55 | 0 | 55 | 100% |  | Completed
ER6243LT | W200 | A14630 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-01 | 2017-11-13 | Thermal Hydraulics - Prepare Request for Service (RFS) Specification | 01-Dec-17 A | 13-Dec-17 A | 9 | 0 | 9 | 100% |  | Completed
ER6243LT | W200 | A16370 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | PCPV Integrity - Contract Variation for next phase | 01-Dec-17 A | 24-Jan-18 A | 1 | 0 | 35 | 100% |  | Completed
ER6243LT | W200 | WP365807.A1000 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | PCPV Integrity - Contract Variation for next phase | 01-Dec-17 A | 24-Jan-18 A | 1 | 0 | 35 | 100% |  | Completed
ER6244LT | W220 | A7350 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-12-01 | 2017-12-07 | Complete requisition approval and issue CI for Minimum Forced Gas Circulation Requirements EAN | 01-Dec-17 A | 07-Dec-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A7480 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-12-01 | 2017-12-07 | Complete requisition approval and issue CI for Assessment of Temperatures vs Decay Heat for Natural Circulation EAN | 01-Dec-17 A | 07-Dec-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | A15760 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-01 | 2017-11-28 | Review & Acceptance of Review NSP's for Shutdown Cooling Safety Cases Report (HPB, HNB) (Not Req'd move to Post Gate B) | 04-Dec-17 A | 23-Aug-18 A | 20 | 0 | 181 | 100% |  | Completed
ER6243LT | W200 | A15820 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-01 | 2017-11-28 | Review & Acceptance of Review NSP's for Shutdown Cooling Safety Cases Report (HYA, HAR)(Not Req'd move to Post Gate B) | 04-Dec-17 A | 23-Aug-18 A | 20 | 0 | 181 | 100% |  | Completed
ER6243LT | W200 | RSSC.RP.A110 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-07-20 | 2017-08-16 | Prepare Thermal Hydraulics (MACE) Report (PH1) | 06-Dec-17 A | 07-Nov-18 A | 239 | 0 | 233 | 100% |  | Completed
ER6243LT | W200 | RSSC.RP.A112 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-07-20 | 2017-07-20 | Thermal Hydraulics (MACE) - Pre Job Brief (PH1) | 06-Dec-17 A | 06-Dec-17 A | 1 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11510 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-04-06 | Assessm't of Other Faults - Fault Studies Report verified and issued for Technical Review (HYA, HAR) | 08-Dec-17 A | 08-Dec-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A7360 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-12-08 | 2017-12-14 | Supplier mobilisation | 08-Dec-17 A | 14-Dec-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A7490 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-12-08 | 2017-12-14 | Supplier mobilisation | 08-Dec-17 A | 14-Dec-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | RSSC.RP.A240 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-08-17 | 2017-09-14 | Develop approach to cooling flows with empty channels (HPB, HNB) | 11-Dec-17 A | 29-Dec-17 A | 20 | 0 | 12 | 100% |  | Completed
ER6243LT | W200 | RSSC.RP.A250 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-09-15 | 2017-10-12 | Develop approach to cooling flows with empty channels (HYA, HAR) | 11-Dec-17 A | 29-Dec-17 A | 20 | 0 | 12 | 100% |  | Completed
ER6243LT | W200 | A12160 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-10 | 2017-11-14 | RCS Basis of Design - Review, Approve and Issue RFS to Supplier | 13-Dec-17 A | 15-Dec-17 A | 3 | 0 | 2 | 100% |  | Completed
ER6243LT | W200 | A13310 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-01-19 | Linking BAT/BPM into optioneering Report Issued to CDMS (HPB, HNB) | 13-Dec-17 A | 13-Dec-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A13320 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-01-19 | Linking BAT/BPM into optioneering Report Issued to CDMS (HYA, HAR) | 13-Dec-17 A | 13-Dec-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15900 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-03-07 | 2018-03-09 | RCS Basis of Design - Review, Approve and Issue RFS to Supplier | 13-Dec-17 A | 15-Dec-17 A | 3 | 0 | 2 | 100% |  | Completed
ER6243LT | W200 | A14640 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-14 | 2017-11-14 | Thermal Hydraulics - Review, Approve and Issue RFS to Supplier | 14-Dec-17 A | 14-Dec-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A14820 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-11-14 | Thermal Hydraulics - Request for Service (RFS) Specification Issued | 14-Dec-17 A | 14-Dec-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A12165 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-11-14 | RCS Basis of Design - Request for Service (RFS) Specification Issued | 15-Dec-17 A | 15-Dec-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14650 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-15 | 2017-11-21 | Thermal Hydraulics - Prepare and Issue Offer | 15-Dec-17 A | 21-Dec-17 A | 5 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | A16060 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-03-09 | RCS Basis of Design - Request for Service (RFS) Specification Issued | 15-Dec-17 A | 15-Dec-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A7370 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-12-15 | 2017-12-15 | Pre Job Brief for Minimum Forced Gas Circulation Requirements EAN | 15-Dec-17 A | 15-Dec-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A7500 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2017-12-15 | 2017-12-15 | Pre Job Brief for Assessment of Temperatures vs Decay Heat for Natural Circulation EAN | 15-Dec-17 A | 15-Dec-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A14830 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-11-21 | Thermal Hydraulics - Initial Offer issued for Review | 21-Dec-17 A | 21-Dec-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11360 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-04-06 | Assessm't of Other Faults - Fault Studies Report verified and issued for Technical Review (HPB, HNB) | 22-Dec-17 A | 22-Dec-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A5870.EJ20 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2017-12-22 | Dropped FPU Impact on Reactor Internals Report Rev001 available (HYA and HRA) | 22-Dec-17 A | 22-Dec-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.RP.A380.EB | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-03-29 | Heat transfer/thermal hydraulics initial assessments (HPB, HNB) | 29-Dec-17 A | 29-Dec-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.RP.A390.EB | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-03-29 | Heat transfer/thermal hydraulics initial assessments (HYA, HAR) | 29-Dec-17 A | 29-Dec-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A13230 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-10 | 2018-01-10 | Determine reactor/core temperature over time - Element decay heat over time - Review CHT for Depress'd ops C02. | 29-Dec-17 A | 29-Dec-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A13240 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-02-07 | 2018-02-07 | Determine reactor/core temperature over time - Element decay heat over time - Review CHT for Depress'd ops C02. | 29-Dec-17 A | 29-Dec-17 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A3610 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2017-12-29 | Failed fuel strategy agreed (HPB and HNB) | 29-Dec-17 A | 29-Dec-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A3620 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2017-12-29 | Failed fuel strategy agreed (HYA and HRA) | 29-Dec-17 A | 29-Dec-17 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A4290 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-01 | 2018-12-31 | P20.01.01.01 - Project Management | 01-Jan-18 A | 03-Apr-20 A | 148 | 0 | 572 | 100% |  | Completed
ER6243LT | W200 | A10560 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-02 | 2018-09-28 | P.10.01.01 - Defuelling Shutdown Safety Cases - Project Management | 02-Jan-18 A | 15-Apr-20 A | 346 | 0 | 578 | 100% |  | Completed
ER6243LT | W200 | A10570 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-02 | 2018-09-28 | P.10.01.02 - Defuelling Shutdown Safety Cases - Safety Case | 02-Jan-18 A | 11-Oct-19 A | 197 | 0 | 450 | 100% |  | Completed
ER6243LT | W200 | A10580 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-02 | 2018-07-18 | P.10.01.03 - Defuelling Shutdown Safety Cases - Operation Compliance | 02-Jan-18 A | 20-Dec-18 A | 122 | 0 | 247 | 100% |  | Completed
ER6243LT | W200 | A10620 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-02 | 2018-03-29 | P.10.01.11 - Defuelling Shutdown Safety Cases - Vessel Integrity | 02-Jan-18 A | 19-Mar-19 A | 83 | 0 | 307 | 100% |  | Completed
ER6243LT | W200 | A10630 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-03 | 2018-04-12 | P.10.01.13 - Defuelling Shutdown Safety Cases - Reactor Control System | 02-Jan-18 A | 21-Sep-18 A | 118 | 0 | 183 | 100% |  | Completed
ER6243LT | W200 | A10640 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-17 | 2018-08-02 | P.10.01.19 - Defuelling Shutdown Safety Cases - Supporting Systems | 02-Jan-18 A | 23-Jul-19 A | 80 | 0 | 393 | 100% |  | Completed
ER6243LT | W200 | RSSC.RP.A115 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-07-20 | 2017-07-26 | Thermal Hydraulics (MACE) - Develop Thermal Hydraulics (MACE) Scoping Report (PH1) | 02-Jan-18 A | 27-Apr-18 A | 20 | 0 | 81 | 100% |  | Completed
ER6243LT | W200 | A13190 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-03-27 | 2018-07-23 | Support Systems Summary - Outline Investment | 02-Jan-18 A | 23-Jul-19 A | 337 | 0 | 393 | 100% |  | Completed
ER6243LT | W200 | A15910 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-03-12 | 2018-03-16 | RCS Basis of Design - Prepare and Issue Offer | 02-Jan-18 A | 03-Jan-18 A | 10 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A16100 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-03-27 | 2018-04-25 | Prepare Support System Specification (HPB, HNB) | 02-Jan-18 A | 10-Jan-18 A | 20 | 0 | 6 | 100% |  | Completed
ER6243LT | W200 | A16160 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-03-28 | 2018-04-26 | Prepare Support System Specification (HYA, HAR) | 02-Jan-18 A | 10-Jan-18 A | 20 | 0 | 6 | 100% |  | Completed
ER6244LT | W220 | A1370 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-02 | 2018-06-22 | Assess dropped fuel assembly impact on reactor internals (at different temps.) & determine reactor damage HPB and HNB | 02-Jan-18 A | 22-Jun-18 A | 120 | 0 | 120 | 100% |  | Completed
ER6244LT | W220 | A4040 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-02 | 2018-03-26 | Identify issues related to HYA/HRA tie bars left on the FPUs and returned to the reactor for safe store | 02-Jan-18 A | 26-Mar-18 A | 60 | 0 | 60 | 100% |  | Completed
ER6244LT | W220 | A4300 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-02 | 2018-10-31 | P20.01.01.02 - Safety Case | 02-Jan-18 A | 31-Oct-18 A | 103 | 0 | 211 | 100% |  | Completed
ER6244LT | W220 | A4330 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-02 | 2019-03-15 | P20.01.01.05 - Defuelling Process | 02-Jan-18 A | 15-Mar-19 A | 63 | 0 | 306 | 100% |  | Completed
ER6244LT | W220 | A4340 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-02 | 2018-06-29 | P20.01.01.06 - Lifting Integrity | 02-Jan-18 A | 29-Jun-18 A | 167 | 0 | 124 | 100% |  | Completed
ER6244LT | W220 | A4360 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-02 | 2018-08-31 | P20.01.01.20 - Fuel Route Facilities | 02-Jan-18 A | 31-Aug-18 A | 128 | 0 | 169 | 100% |  | Completed
ER6244LT | W220 | A4370 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-02 | 2018-12-31 | P20.01.01.09 - Radiological Consequences | 02-Jan-18 A | 31-Dec-18 A | 167 | 0 | 253 | 100% |  | Completed
ER6244LT | W220 | A4380 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-02 | 2018-12-31 | P20.01.01.10 - Fault Studies | 02-Jan-18 A | 31-Dec-18 A | 148 | 0 | 253 | 100% |  | Completed
ER6244LT | W220 | A4400 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-02 | 2018-12-31 | P20.01.01.12 - Structural Integrity | 02-Jan-18 A | 31-Dec-18 A | 148 | 0 | 253 | 100% |  | Completed
ER6244LT | W220 | A4430 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-02 | 2018-12-31 | P20.01.01.15 - Pile Cap Equipment | 02-Jan-18 A | 31-Dec-18 A | 22 | 0 | 253 | 100% |  | Completed
ER6244LT | W220 | A4450 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-02 | 2018-12-31 | P20.01.01.17 - Stringer Integrity | 02-Jan-18 A | 31-Dec-18 A | 148 | 0 | 253 | 100% |  | Completed
ER6244LT | W220 | A4460 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-02 | 2018-12-31 | P20.01.01.18 - Interlock Changes | 02-Jan-18 A | 31-Dec-18 A | 147 | 0 | 253 | 100% |  | Completed
ER6244LT | W220 | A4480 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-02 | 2018-12-31 | P20.01.01.21 - Human Factors | 02-Jan-18 A | 31-Dec-18 A | 84 | 0 | 253 | 100% |  | Completed
ER6244LT | W220 | A4500 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-02 | 2018-06-29 | P20.01.01.23 - Maintenance | 02-Jan-18 A | 29-Jun-18 A | 148 | 0 | 124 | 100% |  | Completed
ER6243LT | W200 | A10660 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-04-13 | 2018-06-27 | P.10.01.23 - Defuelling Shutdown Safety Cases - Maintenance | 02-Jan-18 A | 06-Jul-18 A | 52 | 0 | 129 | 100% |  | Completed
ER6244LT | W220 | A5180 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-01-02 | Draft CO2 purity and decay heat report verified and issued for technical review | 02-Jan-18 A | 02-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A5190 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-02 | 2018-09-03 | Technical review of CO2 purity and decay heat report | 02-Jan-18 A | 03-Sep-18 A | 19 | 0 | 170 | 100% |  | Completed
ER6243LT | W200 | A12170 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-15 | 2017-11-21 | RCS Basis of Design - Prepare and Issue Offer | 02-Jan-18 A | 03-Jan-18 A | 5 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A13210 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-10-31 | Project Quality Plan Audit | 02-Jan-18 A | 02-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A8200 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-01-02 | Risk Workshop Held | 02-Jan-18 A | 02-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A8210 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-01-02 | Project Quality Plan Audit | 02-Jan-18 A | 02-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A8740 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-02 | 2018-01-22 | Supplier update and issue Initial Fault Studies and Risk Estimation Report (HPB/HNB) | 02-Jan-18 A | 22-Jan-18 A | 15 | 0 | 15 | 100% |  | Completed
ER6244LT | W220 | A9530 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-02 | 2018-08-31 | P20.01.01.07 - Fuel Storage Conditions | 02-Jan-18 A | 31-Aug-18 A | 0 | 0 | 168 | 100% |  | Completed
ER6244LT | W220 | A10420 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-02 | 2018-03-20 | Draft Optioneering Report for HPB/HNB | 02-Jan-18 A | 20-Mar-18 A | 18 | 0 | 56 | 100% |  | Completed
ER6244LT | W220 | A10490 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-02 | 2018-06-15 | Draft Optioneering Report for HRA/HYA | 02-Jan-18 A | 15-Jun-18 A | 18 | 0 | 115 | 100% |  | Completed
ER6243LT | W200 | A12175 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-11-21 | RCS Basis of Design - Initial Offer Issued for Review | 03-Jan-18 A | 03-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A13530 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-11-10 | Cooling Faults - Credible Hazards and Faults verified and issued for Technical Review (HYA, HAR) | 03-Jan-18 A | 03-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16070 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-03-16 | RCS Basis of Design - Initial Offer Issued for Review | 03-Jan-18 A | 03-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A3710 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-01-03 | Decision on any changes to FM trip settings (HPB) and HNB) | 03-Jan-18 A | 03-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A1860 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-03 | 2018-07-31 | Establish fuelling machine trip settings/overrun speeds for new PIFA/IFA/Loading FPUs for defuelling. HYA and HRA | 03-Jan-18 A | 31-Jul-18 A | 145 | 0 | 145 | 100% |  | Completed
ER6243LT | W200 | A12180 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-22 | 2017-12-05 | RCS Basis of Design - Review and Negotiate Offer | 04-Jan-18 A | 08-Jan-18 A | 3 | 0 | 3 | 100% |  | Completed
ER6243LT | W200 | A13540 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-13 | 2017-11-24 | Cooling Faults - Credible Hazards and Faults Technical Review by SQEP (HYA, HAR) | 04-Jan-18 A | 14-Mar-18 A | 10 | 0 | 49 | 100% |  | Completed
ER6243LT | W200 | A15920 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-03-19 | 2018-04-03 | RCS Basis of Design - Review and Negotiate Offer | 04-Jan-18 A | 08-Jan-18 A | 3 | 0 | 3 | 100% |  | Completed
ER6244LT | W220 | A5960 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-01-05 | Draft Dropped FPU Impact on Buffer Store EAN (HPB and HNB) verified and issued for technical review | 05-Jan-18 A | 05-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A6090 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-01-05 | Draft Dropped FPU Impact on Buffer Store EAN (HYA and HRA) verified and issued for technical review | 05-Jan-18 A | 05-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A12185 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-12-05 | RCS Basis of Design - Offer Accepted/Approved | 05-Jan-18 A | 08-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16080 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-04-03 | RCS Basis of Design - Offer Accepted/Approved | 05-Jan-18 A | 08-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A5970 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-08 | 2018-01-12 | Technical review of Dropped FPU Impact on Buffer Store EAN (HPB and HNB) | 08-Jan-18 A | 12-Jan-18 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A6100 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-08 | 2018-01-15 | Technical review of Dropped FPU Impact on Buffer Store EAN (HYA and HRA) | 08-Jan-18 A | 15-Jan-18 A | 5 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | A12190 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-06 | 2017-12-07 | RCS Basis of Design - Complete Requisition Approval and Issue CI | 09-Jan-18 A | 02-Feb-18 A | 5 | 0 | 18 | 100% |  | Completed
ER6243LT | W200 | A15930 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-04-04 | 2018-04-05 | RCS Basis of Design - Complete Requisition Approval and Issue CI | 09-Jan-18 A | 02-Feb-18 A | 5 | 0 | 18 | 100% |  | Completed
ER6243LT | W200 | A16110 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-04-25 | Support System Specification Agreed (HPB, HNB) | 10-Jan-18 A | 10-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16170 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-04-26 | Support System Specification Agreed (HYA, HAR) | 10-Jan-18 A | 10-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A8320 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-01-12 | Draft Justify Zero Maintenance for FPU Prio to Load in Shutdown Reactor EAN verified and issued for technical review | 12-Jan-18 A | 12-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A8450 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-01-12 | Draft Justify Zero Maintenance for FPU Prio to Load in Shutdown Reactor EAN verified and issued for technical review | 12-Jan-18 A | 12-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A5980 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-15 | 2018-01-19 | Supplier update and issue Dropped FPU Impact on Buffer Store EAN (HPB and HNB) | 15-Jan-18 A | 19-Jan-18 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A6110 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-15 | 2018-01-19 | Supplier update and issue Dropped FPU Impact on Buffer Store EAN (HYA and HRA) | 15-Jan-18 A | 19-Jan-18 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A8330 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-15 | 2018-01-19 | Technical review of Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 15-Jan-18 A | 19-Jan-18 A | 13 | 0 | 4 | 100% |  | Completed
ER6244LT | W220 | A8460 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-15 | 2018-01-19 | Technical review of Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 15-Jan-18 A | 19-Jan-18 A | 13 | 0 | 4 | 100% |  | Completed
ER6244LT | W220 | A8340 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-22 | 2018-01-24 | Supplier update and issue Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 22-Jan-18 A | 24-Jan-18 A | 10 | 0 | 2 | 100% |  | Completed
ER6244LT | W220 | A8470 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-22 | 2018-01-24 | Supplier update and issue Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN | 22-Jan-18 A | 24-Jan-18 A | 20 | 0 | 2 | 100% |  | Completed
ER6244LT | W220 | A5990 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-22 | 2018-01-31 | Complete TR form and upload Dropped FPU Impact on Buffer Store EAN (HPB and HNB) to CDMS | 22-Jan-18 A | 31-Jan-18 A | 8 | 0 | 8 | 100% |  | Completed
ER6244LT | W220 | A6120 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-22 | 2018-01-31 | Complete TR form and upload Dropped FPU Impact on Buffer Store EAN (HYA and HRA) to CDMS | 22-Jan-18 A | 31-Jan-18 A | 8 | 0 | 8 | 100% |  | Completed
ER6244LT | W220 | A8750 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-23 | 2018-02-09 | Complete TR form and upload Initial Fault Studies and Risk Estimation Report to CDMS (HPB/HNB) | 23-Jan-18 A | 09-Feb-18 A | 10 | 0 | 14 | 100% |  | Completed
ER6243LT | W200 | RSSC.RP.A200 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-08-17 | 2017-09-14 | Prepare Thermal Hydraulics (MACE) Calculations Report (PH2) | 24-Jan-18 A | 07-Nov-18 A | 223 | 0 | 200 | 100% |  | Completed
ER6243LT | W200 | RSSC.RP.A205 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-08-17 | 2017-08-23 | Thermal Hydraulics (MACE) - Develop Thermal Hydraulics (MACE) Calculations Report (PH2) | 24-Jan-18 A | 27-Apr-18 A | 20 | 0 | 65 | 100% |  | Completed
ER6243LT | W200 | A16240 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-10-31 | PCPV Integrity - Contract Variation approved for next phase (HPB, HNB) | 24-Jan-18 A | 24-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16260 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-10-31 | PCPV Integrity - Contract Variation approved for next phase (HYA, HAR) | 24-Jan-18 A | 24-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11240 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-11-24 | Cooling Faults - Draft Rad Con's Requirements for Post NSRS verified and issued for Technical Review (HPB, HNB) | 24-Jan-18 A | 25-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A8350 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-25 | 2018-01-29 | Complete TR form and upload Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN to CDMS | 25-Jan-18 A | 29-Jan-18 A | 10 | 0 | 2 | 100% |  | Completed
ER6244LT | W220 | A8480 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-01-25 | 2018-01-29 | Complete TR form and upload Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN to CDMS | 25-Jan-18 A | 29-Jan-18 A | 15 | 0 | 2 | 100% |  | Completed
ER6243LT | W200 | A13460 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-12-15 | Cooling Faults - Draft Rad Con's Requirements for Post NSRS verified and issued for Technical Review (HYA, HAR) | 25-Jan-18 A | 25-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14040 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-01 | 2018-01-15 | Ops Compliance - RFS Summary - Optionnering for CR and N2 systems (Deleted No Longer Req'd) | 25-Jan-18 A | 25-Jan-18 A | 93 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14050 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-01 | 2017-12-14 | Ops Compliance - Prepare Request for Service (RFS) Specification (Deleted No Longer Req'd) | 25-Jan-18 A | 25-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14060 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-15 | 2017-12-15 | Ops Compliance - Review, Approve and Issue RFS to Supplier (Deleted No Longer Req'd) | 25-Jan-18 A | 25-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14100 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-27 | 2018-01-03 | Ops Compliance - Review and Negotiate Offer (Deleted No Longer Req'd) | 25-Jan-18 A | 25-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14120 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-04 | 2018-01-04 | Ops Compliance - Complete Requisition Approval and Issue CI (Deleted No Longer Req'd) | 25-Jan-18 A | 25-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14130 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-05 | 2018-01-15 | Ops Compliance - Supplier Mobilisation Time (Deleted No Longer Req'd) | 25-Jan-18 A | 25-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14070 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-12-15 | Ops Compliance - Request for Service (RFS) Specification Issued (Deleted No Longer Req'd) | 25-Jan-18 A | 25-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14090 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-12-22 | Ops Compliance - Initial Offer Issued for Review (Deleted No Longer Req'd) | 25-Jan-18 A | 25-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14110 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-01-03 | Ops Compliance - Offer Accepted/Approved (Deleted No Longer Req'd) | 25-Jan-18 A | 25-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16250 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-15 | 2018-03-29 | PCPV Integrity - Prepare Engineering Substantiation Report (Phase 2) for Structural Integrity of PCPV (HPB, HNB) | 25-Jan-18 A | 25-May-18 A | 54 | 0 | 83 | 100% |  | Completed
ER6243LT | W200 | A16270 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-15 | 2018-03-29 | PCPV Integrity - Prepare Engineering Substantiation Report (Phase 2) for Structural Integrity of PCPV (HYA, HAR) | 25-Jan-18 A | 25-May-18 A | 54 | 0 | 83 | 100% |  | Completed
ER6243LT | W200 | A14080 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-18 | 2018-01-03 | Ops Compliance - Prepare and Issue Offer (Deleted No Longer Req'd) | 25-Jan-18 A | 25-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A12020.EA | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-03-02 | Ops Compliance - Draft QA3 SDM Defuelling Strategy Optioneering Report verified and issued for Tech Review | 26-Jan-18 A | 26-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A12030 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-17 | 2017-12-14 | Ops Compliance - QA3 SDM Defuelling Strategy Optioneering Report Technical Review by SQEP | 29-Jan-18 A | 14-Mar-18 A | 12 | 0 | 32 | 100% |  | Completed
ER6244LT | W220 | A8360 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-01-29 | Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN available | 29-Jan-18 A | 29-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A8490 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-01-29 | Justify Zero Maintenance for FPU Prior to Load Back into Shutdown Reactor EAN available | 29-Jan-18 A | 29-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15600 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-01 | 2018-01-02 | Prepare Human Factor Principles for Reactors in Different Conditions (HPB, HNB) | 29-Jan-18 A | 23-Feb-18 A | 20 | 0 | 20 | 100% |  | Completed
ER6243LT | W200 | A15660 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-01 | 2018-01-02 | Prepare Human Factor Principles for Reactors in Different Conditions (HYA, HAR) | 29-Jan-18 A | 23-Feb-18 A | 20 | 0 | 19 | 100% |  | Completed
ER6244LT | W220 | A6000.EJ | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-01-31 | Dropped FPU Impact on Buffer Store EAN (HPB and HNB) available | 31-Jan-18 A | 31-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A6130.EJ | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-01-31 | Dropped FPU Impact on Buffer Store EAN (HYA and HRA) available | 31-Jan-18 A | 31-Jan-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A10590 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-02 | 2018-03-13 | P.10.01.04 - Defuelling Shutdown Safety Cases - Reactor Physics | 01-Feb-18 A | 28-Feb-19 A | 45 | 0 | 272 | 100% |  | Completed
ER6243LT | W200 | A10600 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-04 | 2017-10-04 | P.10.01.08 - Defuelling Shutdown Safety Cases - Cooling - Normal Operations | 01-Feb-18 A | 23-Aug-18 A | 0 | 0 | 141 | 100% |  | Completed
ER6243LT | W200 | A10610 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-01 | 2017-12-01 | P.10.01.10 - Defuelling Shutdown Safety Cases - Fault Studies | 01-Feb-18 A | 13-Jul-18 A | 7 | 0 | 112 | 100% |  | Completed
ER6244LT | W220 | A3600 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-02-01 | 2018-02-14 | Update and Issue Defueling Options EAN | 01-Feb-18 A | 14-Feb-18 A | 10 | 0 | 10 | 100% |  | Completed
ER6244LT | W220 | A10220 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-02-01 | 2018-02-23 | Draft Permit Depressurised Fuelling Machine to Access IFD | 01-Feb-18 A | 23-Feb-18 A | 17 | 0 | 17 | 100% |  | Completed
ER6244LT | W220 | A4730 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-02-01 | 2018-12-31 | P20.01.01.19 - EP - Supporting Systems | 01-Feb-18 A | 31-Dec-18 A | 0 | 0 | 231 | 100% |  | Completed
ER6243LT | W200 | A12200 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-08 | 2018-01-02 | RCS Basis of Design - Supplier Mobilisation Time | 05-Feb-18 A | 12-Feb-18 A | 6 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | A15940 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-04-06 | 2018-04-26 | RCS Basis of Design - Supplier Mobilisation Time | 05-Feb-18 A | 12-Feb-18 A | 26 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A8900 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-02-12 | 2018-04-10 | Final Update of Initial Fault Studies and Risk Estimation Report to CDMS (HPB/HNB) | 12-Feb-18 A | 10-Apr-18 A | 10 | 0 | 40 | 100% |  | Completed
ER6243LT | W200 | RSSC.RCS.A100 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-03 | 2018-04-12 | RCS Basis of Design - Undertake a High Level Impact Assessment & C&I BoD (HPB, HNB) | 14-Feb-18 A | 21-Sep-18 A | 162 | 0 | 152 | 100% |  | Completed
ER6243LT | W200 | RSSC.RCS.A102 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-03 | 2018-01-03 | RCS Basis of Design - Pre Job Brief (HPB, HNB) | 14-Feb-18 A | 14-Feb-18 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | RSSC.RCS.A110 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-03 | 2018-04-12 | RCS Basis of Design - Undertake a High Level Impact Assessment & C&I BoD (HYA, HAR) | 15-Feb-18 A | 21-Sep-18 A | 151 | 0 | 151 | 100% |  | Completed
ER6243LT | W200 | RSSC.RCS.A105 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-03 | 2018-02-27 | RCS Basis of Design - Prepare Impact Assessment Report & C&I BoD (HPB, HNB) (Deliverable 1 Hold Point) | 15-Feb-18 A | 09-May-18 A | 56 | 0 | 56 | 100% |  | Completed
ER6243LT | W200 | RSSC.RCS.A320 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-03 | 2018-02-27 | RCS Basis of Design - Prepare Impact Assessment Report & C&I BoD (HYA, HAR) (Deliverable 1 Hold Point) | 15-Feb-18 A | 09-May-18 A | 58 | 0 | 56 | 100% |  | Completed
ER6244LT | W220 | A3720 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-02-15 | 2018-02-28 | Complete TR form and upload Defueling Options EAN to CDMS | 15-Feb-18 A | 28-Feb-18 A | 10 | 0 | 10 | 100% |  | Completed
ER6243LT | W200 | A14950 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-12-04 | Maintenance - Draft Summary of TS Charges Required verified and issued for Technical Review (HPB, HNB) | 16-Feb-18 A | 16-Feb-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15060 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-12-04 | Maintenance - Draft Summary of TS Charges Required verified and issued for Technical Review (HYA, HAR) | 16-Feb-18 A | 16-Feb-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A7900 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-02-19 | 2018-03-30 | Draft Review Radial Shuffling Safety Case EAN - Rev 001 | 19-Feb-18 A | 30-Mar-18 A | 8 | 0 | 29 | 100% |  | Completed
ER6243LT | W200 | RSSC.RP.A120 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-09-14 | Thermal Hydraulics - PCPV Integrity for Changing Temperatures Report Completed (HPB, HNB) (Not Req'd 20.02.18 as per DA) | 20-Feb-18 A | 20-Feb-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.RP.A210 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-10-12 | Thermal Hydraulics - PCPV Integrity for Changing Temperatures Report Completed (HYA, HAR) (Not Req'd 20.02.18 as per DA) | 20-Feb-18 A | 20-Feb-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14580 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-11 | 2018-01-10 | Thermal Hydraulics - PCPV Integrity for Changing Temperatures Summary (HPB, HNB) (Not Req'd 20.02.18 as per DA) | 20-Feb-18 A | 20-Feb-18 A | 20 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14600 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-11 | 2018-02-07 | Thermal Hydraulics - PCPV Integrity for Changing Temperatures Summary (HYA, HAR) (Not Req'd 20.02.18 as per DA) | 20-Feb-18 A | 20-Feb-18 A | 20 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14660 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-22 | 2017-11-28 | Thermal Hydraulics - Review and Negotiate Offer (Not Req'd 20.02.18 as per DA) | 20-Feb-18 A | 20-Feb-18 A | 5 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A14670 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-29 | 2017-11-29 | Thermal Hydraulics - Complete Requisition Approval and Issue CI (Not Req'd 20.02.18 as per DA) | 20-Feb-18 A | 20-Feb-18 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A14680 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-30 | 2017-12-08 | Thermal Hydraulics - Supplier Mobilisation Time (Not Req'd 20.02.18 as per DA) | 20-Feb-18 A | 20-Feb-18 A | 7 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A14700 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-11 | 2017-12-11 | Thermal Hydraulics - Pre Job Brief (HPB, HNB) (Not Req'd 20.02.18 as per DA) | 20-Feb-18 A | 20-Feb-18 A | 1 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14710 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-12-15 | Thermal Hydraulics-Draft PCPV Integrity for Changing Temp Report verified & issued for TR (Not Req'd 20.02.18 as per DA) | 20-Feb-18 A | 20-Feb-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14720 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-18 | 2017-12-22 | Thermal Hydraulics - PCPV Integrity for Changing Temp Report Technical Review by SQEP (Not Req'd 20.02.18 as per DA) | 20-Feb-18 A | 20-Feb-18 A | 5 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14730 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-27 | 2018-01-03 | Thermal Hydraulics - Update and issue PCPV Integrity for Changing Temp Report (HPB, HNB) (Not Req'd 20.02.18 as per DA) | 20-Feb-18 A | 20-Feb-18 A | 5 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14740 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-04 | 2018-01-10 | Thermal Hydraulics - Complete TR form and upload to CDMS (HPB, HNB) (Not Req'd 20.02.18 as per DA) | 20-Feb-18 A | 20-Feb-18 A | 5 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14750 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-11 | 2017-12-15 | Thermal Hydraulics - PCPV Integrity for Changing Temperatures Report (HPB, HNB) (Not Req'd 20.02.18 as per DA) | 20-Feb-18 A | 20-Feb-18 A | 5 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14770 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-01-17 | Thermal Hydraulics-Draft PCPV Integrity for Changing Temp Report verified & issued for TR (Not Req'd 20.02.18 as per DA) | 20-Feb-18 A | 20-Feb-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14780 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-18 | 2018-01-24 | Thermal Hydraulics - PCPV Integrity for Changing Temperatures Report TR by SQEP (Not Req'd 20.02.18 as per DA) | 20-Feb-18 A | 20-Feb-18 A | 5 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14790 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-25 | 2018-01-31 | Thermal Hydraulics - Update and issue PCPV Integrity for Changing Temp Report (HYA, HAR) (Not Req'd 20.02.18 as per DA) | 20-Feb-18 A | 20-Feb-18 A | 5 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14800 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-02-01 | 2018-02-07 | Thermal Hydraulics - Complete TR form and upload to CDMS (HYA, HAR) (Not Req'd 20.02.18 as per DA) | 20-Feb-18 A | 20-Feb-18 A | 5 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14810 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-11 | 2018-01-17 | Thermal Hydraulics - PCPV Integrity for Changing Temperatures Report (HYA, HAR) (Not Req'd 20.02.18 as per DA) | 20-Feb-18 A | 20-Feb-18 A | 5 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14840 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-11-28 | Thermal Hydraulics - Offer Accepted/Approved (Not Req'd 20.02.18 as per DA) | 20-Feb-18 A | 20-Feb-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A8990 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-02-22 | Draft Fuelling Machine Light Load Protection & Interlocks EAN (HYA and HRA) verified and issued for technical review | 20-Feb-18 A | 22-Feb-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A5310 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-02-23 | Draft Refuelling Cooling Assessment EAN verified and issued for technical review | 23-Feb-18 A | 23-Feb-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A8850 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-02-23 | Draft Fuel Free Verification EAN issued for Verification | 23-Feb-18 A | 23-Feb-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14550 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-12-29 | Principles of Fuel Free Verification - Receipt of the Draft Report for TR (HPB, HNB) | 23-Feb-18 A | 23-Feb-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14570 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-12-29 | Principles of Fuel Free Verification - Receipt of the Draft Report for TR (HYA, HAR) | 23-Feb-18 A | 23-Feb-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15610 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-01-02 | Human Factor Principles for Reactors in Different Conditions Specification Agreed (HPB, HNB) | 23-Feb-18 A | 23-Feb-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15670 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-01-02 | Human Factor Principles for Reactors in Different Conditions Specification Agreed (HYA, HAR) | 23-Feb-18 A | 23-Feb-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A10230 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-02-23 | Draft Permit Depressurised Fuelling Machine to Access IFD verified and issued for technical review | 23-Feb-18 A | 23-Feb-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15620 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-03 | 2018-02-27 | Prepare Human Factor Principles for Reactors in Different Conditions Report (HPB, HNB) | 26-Feb-18 A | 31-May-18 A | 40 | 0 | 64 | 100% |  | Completed
ER6243LT | W200 | A15680 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-03 | 2018-02-27 | Prepare Human Factor Principles for Reactors in Different Conditions Report (HYA, HAR) | 26-Feb-18 A | 31-May-18 A | 40 | 0 | 64 | 100% |  | Completed
ER6244LT | W220 | A5320 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-02-26 | 2018-06-01 | Technical review of Refuelling Cooling Assessment EAN | 26-Feb-18 A | 01-Jun-18 A | 26 | 0 | 66 | 100% |  | Completed
ER6244LT | W220 | A8860 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-02-26 | 2018-03-12 | Technical Review of Fuel Free Verification EAN | 26-Feb-18 A | 12-Mar-18 A | 8 | 0 | 11 | 100% |  | Completed
ER6243LT | W200 | A14140 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-30 | 2018-04-03 | Ops Compliance - Optionnering for CR and N2 systems Summary (HPB, HNB) | 27-Feb-18 A | 31-Aug-18 A | 132 | 0 | 128 | 100% |  | Completed
ER6243LT | W200 | A14150 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-30 | 2018-01-30 | Ops Compliance - Workshop (HPB, HNB) | 27-Feb-18 A | 27-Feb-18 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A10080 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-02-27 | 2018-07-09 | Draft Dropped FPU RadCons Analysis of Core Support Plate Failure | 27-Feb-18 A | 09-Jul-18 A | 25 | 0 | 90 | 100% |  | Completed
ER6243LT | W200 | A11120 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-10-05 | Closure and Seal Integrity - Receipt of the draft report for TR (HPB, HNB) | 28-Feb-18 A | 28-Feb-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11160 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-12-14 | Closure and Seal Integrity - Receipt of the draft report for TR (HYA, HAR) | 28-Feb-18 A | 28-Feb-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14160 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-30 | 2018-03-02 | Ops Compliance - Draft Optioneering for CR and N2 systems Report (HPB, HNB) | 28-Feb-18 A | 29-Jun-18 A | 24 | 0 | 83 | 100% |  | Completed
ER6244LT | W220 | A3730.EC | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-02-28 | Defueling Options EAN Rev 001 Available | 28-Feb-18 A | 28-Feb-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14960 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-05 | 2017-12-18 | Maintenance - Summary of TS Charges Required Technical Review by SQEP (HPB, HNB) | 01-Mar-18 A | 14-Mar-18 A | 11 | 0 | 9 | 100% |  | Completed
ER6243LT | W200 | A15070 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-05 | 2017-12-18 | Maintenance - Summary of TS Charges Required Technical Review by SQEP (HYA, HAR) | 01-Mar-18 A | 14-Mar-18 A | 11 | 0 | 9 | 100% |  | Completed
ER6243LT | W200 | A16120 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-04-26 | 2018-06-22 | Prepare Support System Report (HPB, HNB) | 01-Mar-18 A | 12-Apr-18 A | 40 | 0 | 28 | 100% |  | Completed
ER6243LT | W200 | A16180 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-04-27 | 2018-06-25 | Prepare Support System Report (HYA, HAR) | 01-Mar-18 A | 12-Apr-18 A | 40 | 0 | 28 | 100% |  | Completed
ER6244LT | W220 | A8580 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-03-01 | 2018-03-29 | Draft Initial Fault Studies and Risk Estimation Report (HYA/HRA) | 01-Mar-18 A | 29-Mar-18 A | 21 | 0 | 21 | 100% |  | Completed
ER6244LT | W220 | A10150 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-03-01 | 2018-07-02 | Draft Review of Rad Cons for Lower Decay Heat for Input into PSA | 01-Mar-18 A | 02-Jul-18 A | 60 | 0 | 84 | 100% |  | Completed
ER6243LT | W200 | A1050 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-07-20 | 2018-07-20 | Confirm Objectives to be Delivered at Gate C | 06-Mar-18 A | 19-Mar-18 A | 10 | 0 | 9 | 100% |  | Completed
ER6244LT | W220 | A8040 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-03-07 | Draft CRA Isolation Requirements EAN verified and issued for technical review | 07-Mar-18 A | 07-Mar-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A8050 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-03-08 | 2018-05-11 | Technical review of CRA Isolation Requirements EAN | 08-Mar-18 A | 11-May-18 A | 20 | 0 | 44 | 100% |  | Completed
ER6243LT | W200 | A11250 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-27 | 2017-12-08 | Cooling Faults - Rad Con's Requirements for Post NSRS Technical Review by SQEP (HPB, HNB) | 12-Mar-18 A | 06-Apr-18 A | 11 | 0 | 17 | 100% |  | Completed
ER6243LT | W200 | A11370 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-04-09 | 2018-04-20 | Assessm't of Other Faults - Fault Studies Report Technical Review by SQEP (HPB, HNB) | 12-Mar-18 A | 15-May-18 A | 10 | 0 | 44 | 100% |  | Completed
ER6243LT | W200 | A11520 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-04-09 | 2018-04-20 | Assessm't of Other Faults - Fault Studies Report Technical Review by SQEP (HYA, HAR) | 12-Mar-18 A | 15-May-18 A | 10 | 0 | 44 | 100% |  | Completed
ER6243LT | W200 | A13470 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-18 | 2018-01-03 | Cooling Faults - Rad Con's Requirements for Post NSRS Technical Review by SQEP (HYA, HAR) | 12-Mar-18 A | 06-Apr-18 A | 11 | 0 | 17 | 100% |  | Completed
ER6243LT | W200 | A15520 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-05-01 | 2018-05-30 | Prepare Summary of supporting references Specification (HYA, HAR) | 12-Mar-18 A | 13-Mar-18 A | 20 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A15515 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Summary of Supporting References required for Safety Case (HYA, HAR) | 12-Mar-18 A | 21-Aug-18 A | 112 | 0 | 112 | 100% |  | Completed
ER6243LT | W200 | A15280 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-05-01 | 2018-05-30 | Prepare Summary of supporting references Specification (HPB, HNB) | 12-Mar-18 A | 13-Mar-18 A | 20 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A15275 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Summary of Supporting References required for Safety Case (HPB, HNB) | 12-Mar-18 A | 21-Aug-18 A | 146 | 0 | 112 | 100% |  | Completed
ER6243LT | W200 | A15290 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-05-30 | Summary of supporting references Specification Agreed (HPB, HNB) | 13-Mar-18 A | 13-Mar-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15530 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-05-30 | Summary of supporting references Specification Agreed (HYA, HAR) | 13-Mar-18 A | 13-Mar-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A8870 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-03-13 | 2018-05-08 | Update and issue Fuel Free Verification EAN | 13-Mar-18 A | 08-May-18 A | 5 | 0 | 38 | 100% |  | Completed
ER6243LT | W200 | A15300 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-05-31 | 2018-07-25 | Prepare Summary of supporting references Report (HPB, HNB) | 14-Mar-18 A | 04-May-18 A | 40 | 0 | 36 | 100% |  | Completed
ER6243LT | W200 | A15540 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-05-31 | 2018-07-25 | Prepare Summary of supporting references Report (HYA, HAR) | 14-Mar-18 A | 04-May-18 A | 40 | 0 | 36 | 100% |  | Completed
ER6244LT | W220 | A2080 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-03-14 | 2018-07-10 | Assess interlock changes required for staggered operation of reactors, defueling mode & FPUs back in reactor (HYA & HRA) | 14-Mar-18 A | 10-Jul-18 A | 80 | 0 | 80 | 100% |  | Completed
ER6243LT | W200 | A11300 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-11 | 2017-12-15 | Cooling Faults - Update and issue Credible Hazards and Faults (HPB, HNB) | 15-Mar-18 A | 04-May-18 A | 5 | 0 | 34 | 100% |  | Completed
ER6243LT | W200 | A13550 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-27 | 2017-12-01 | Cooling Faults - Update and issue Credible Hazards and Faults (HYA, HAR) | 15-Mar-18 A | 04-May-18 A | 5 | 0 | 34 | 100% |  | Completed
ER6243LT | W200 | A12040 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-15 | 2018-01-02 | Ops Compliance - Update and issue QA3 SDM Defuelling Strategy Optioneering Report | 15-Mar-18 A | 12-Apr-18 A | 10 | 0 | 18 | 100% |  | Completed
ER6243LT | W200 | RSSC.CNO.A100 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-17 | 2017-12-15 | Cooling Systems - Cooling Plant Availability (Optioneering) (HPB, HNB) | 20-Mar-18 A | 23-Aug-18 A | 119 | 0 | 108 | 100% |  | Completed
ER6243LT | W200 | A11550 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-09-18 | 2017-10-16 | Cooling Systems - RFS Summary - Cooling Plant Availability (Optioneering) | 20-Mar-18 A | 20-Mar-18 A | 29 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A11560 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-09-18 | 2017-09-19 | Cooling Systems - Prepare (RFS) Cooling Plant Availability (Optioneering) Specification (N/A Using Existing Contract) | 20-Mar-18 A | 20-Mar-18 A | 10 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A11570 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-09-20 | 2017-09-20 | Cooling Systems - Review, Approve and Issue RFS to Supplier (N/A Using Existing Contract) | 20-Mar-18 A | 20-Mar-18 A | 1 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11580 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-09-21 | 2017-09-27 | Cooling Systems - Prepare and Issue Offer (N/A Using Existing Contract) | 20-Mar-18 A | 20-Mar-18 A | 5 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11590 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-09-28 | 2017-10-04 | Cooling Systems - Review and Negotiate Offer (N/A Using Existing Contract) | 20-Mar-18 A | 20-Mar-18 A | 5 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11600 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-05 | 2017-10-05 | Cooling Systems - Complete Requisition Approval and Issue CI (N/A Using Existing Contract) | 20-Mar-18 A | 20-Mar-18 A | 1 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11610 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-06 | 2017-10-16 | Cooling Systems - Supplier Mobilisation Time (N/A Using Existing Contract) | 20-Mar-18 A | 20-Mar-18 A | 7 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.CNO.A101 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-17 | 2017-10-17 | Cooling Systems - Pre Job Brief (HPB, HNB) (N/A Using Existing Contract) | 20-Mar-18 A | 20-Mar-18 A | 1 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11575 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-12-27 | Cooling Systems - Request for Service (RFS) Specification Issued (N/A Using Existing Contract) | 20-Mar-18 A | 20-Mar-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11585 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-01-04 | Cooling Systems - Initial Offer Issued for Review (N/A Using Existing Contract) | 20-Mar-18 A | 20-Mar-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11595 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-01-11 | Cooling Systems - Offer Accepted/Approved (N/A Using Existing Contract) | 20-Mar-18 A | 20-Mar-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.CNO.A105 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-17 | 2017-11-17 | Cooling Systems - Cooling Plant Availability (Optioneering) (HPB, HNB) | 21-Mar-18 A | 29-Jun-18 A | 48 | 0 | 68 | 100% |  | Completed
ER6244LT | W220 | A10440 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-03-21 | 2018-07-13 | Technical Review of Optioneering Report for HPB/HNB | 21-Mar-18 A | 13-Jul-18 A | 16 | 0 | 79 | 100% |  | Completed
ER6244LT | W220 | A4050 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-03-26 | Confirm that HYA/HRA tie bars can be left on the FPUs and returned to the reactor for safe store | 26-Mar-18 A | 26-Mar-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A6220 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-03-26 | Draft Buffer Store Defueling EAN verified and issued for technical review (HPB and HNB) | 26-Mar-18 A | 26-Mar-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A6350 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-03-26 | Draft IFDF Defueling EAN verified and issued for technical review (HPB and HNB) | 26-Mar-18 A | 26-Mar-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A6740 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-03-26 | Draft Ponds and Flasks EAN verified and issued for technical review (HPB and HNB) | 26-Mar-18 A | 26-Mar-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A6870 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-03-26 | Draft Waste Vault Storage Capacity EAN verified and issued for technical review (HPB and HNB) | 26-Mar-18 A | 26-Mar-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A6230 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-03-27 | 2018-05-04 | Technical review of Buffer Store Defueling EAN (HPB and HNB) | 27-Mar-18 A | 04-May-18 A | 23 | 0 | 27 | 100% |  | Completed
ER6244LT | W220 | A6360 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-03-27 | 2018-05-04 | Technical review of IFDF Defueling EAN (HPB and HNB) | 27-Mar-18 A | 04-May-18 A | 23 | 0 | 27 | 100% |  | Completed
ER6244LT | W220 | A6750 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-03-27 | 2018-05-04 | Technical review of Ponds and Flasks EAN (HPB and HNB) | 27-Mar-18 A | 04-May-18 A | 23 | 0 | 27 | 100% |  | Completed
ER6244LT | W220 | A6880 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-03-27 | 2018-05-04 | Technical review of Waste Vault Storage Capacity EAN (HPB and HNB) | 27-Mar-18 A | 04-May-18 A | 23 | 0 | 27 | 100% |  | Completed
ER6244LT | W220 | A8590 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-03-29 | Draft Initial Fault Studies and Risk Estimation Report verified and issued for technical review (HYA/HRA) | 29-Mar-18 A | 29-Mar-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A9360 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-03-29 | Draft Fuel Storage Conditions EAN verified and issued for technical review (HYA and HRA) | 29-Mar-18 A | 29-Mar-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A7910 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-03-30 | Draft Review Radial Shuffling Safety Case EAN issued for verification - Rev 001 | 29-Mar-18 A | 30-Mar-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14970 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-19 | 2018-01-04 | Maintenance - Update and issue Summary of TS Charges Required (HPB, HNB) | 03-Apr-18 A | 04-May-18 A | 10 | 0 | 24 | 100% |  | Completed
ER6243LT | W200 | A15080 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-19 | 2018-01-04 | Maintenance - Update and issue Summary of TS Charges Required (HYA, HAR) | 03-Apr-18 A | 04-May-18 A | 10 | 0 | 24 | 100% |  | Completed
ER6244LT | W220 | A7920 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-04-03 | 2018-05-31 | Verification of Review Radial Shuffling Safety Case EAN - Rev 001 | 03-Apr-18 A | 31-May-18 A | 41 | 0 | 41 | 100% |  | Completed
ER6244LT | W220 | A9370 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-04-03 | 2018-07-09 | Technical review of Fuel Storage Conditions EAN | 03-Apr-18 A | 09-Jul-18 A | 23 | 0 | 68 | 100% |  | Completed
ER6243LT | W200 | A11260 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-11 | 2017-12-15 | Cooling Faults - Update and issue Rad Con's Requirements for Post NSRS (HPB, HNB) | 09-Apr-18 A | 07-Jun-18 A | 5 | 0 | 42 | 100% |  | Completed
ER6243LT | W200 | A13480 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-04 | 2018-01-10 | Cooling Faults - Update and issue Rad Con's Requirements for Post NSRS (HYA, HAR) | 09-Apr-18 A | 07-Jun-18 A | 5 | 0 | 42 | 100% |  | Completed
ER6244LT | W220 | A10070 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-04-10 | 2018-04-10 | Define H&I Work to Support Detailed PSA | 10-Apr-18 A | 10-Apr-18 A | 20 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A8760 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-04-10 | Initial Fault Studies and Risk Estimation Report available (HPB/HNB) | 10-Apr-18 A | 10-Apr-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16130 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-06-22 | Draft Support System Report Available for Review (HPB, HNB) | 10-Apr-18 A | 12-Apr-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16190 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-06-25 | Draft Support System Report Available for Review (HYA, HAR) | 10-Apr-18 A | 12-Apr-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A1040 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Initial high level scope of programme | 12-Apr-18 A | 20-Jul-18 A | 10 | 0 | 69 | 100% |  | Completed
ER6243LT | W200 | A16140 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-06-25 | 2018-07-20 | Review & Acceptance of Support System Report (HPB, HNB) | 13-Apr-18 A | 14-Jun-18 A | 16 | 0 | 42 | 100% |  | Completed
ER6243LT | W200 | A16200 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-06-26 | 2018-07-23 | Review & Acceptance of Support System Report (HYA, HAR) | 13-Apr-18 A | 14-Jun-18 A | 20 | 0 | 42 | 100% |  | Completed
ER6243LT | W200 | A14210 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-30 | 2018-04-03 | Ops Compliance - Optionnering for CR and N2 systems Summary (HYA, HAR) | 25-Apr-18 A | 31-Aug-18 A | 91 | 0 | 89 | 100% |  | Completed
ER6243LT | W200 | A14220 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-30 | 2018-01-30 | Ops Compliance - Workshop (HYA, HAR) | 25-Apr-18 A | 25-Apr-18 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A14230 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-30 | 2018-03-02 | Ops Compliance - Draft Optionnering for CR and N2 systems Report (HYA, HAR) | 26-Apr-18 A | 29-Jun-18 A | 24 | 0 | 44 | 100% |  | Completed
ER6243LT | W200 | A11820 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-07-26 | Thermal Hydraulics (MACE) - Draft Thermal Hydraulics (MACE) Scoping Report verified and issued for Technical Review(PH1) | 27-Apr-18 A | 27-Apr-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11880 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-08-23 | Thermal Hydraulics (MACE) - Draft (MACE) Calculations Report verified and issued for Technical Review(PH2) | 27-Apr-18 A | 27-Apr-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.CNO.A140 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-18 | 2017-12-18 | Cooling Systems - Cooling Plant Availability (Optioneering) (HYA, HAR) | 30-Apr-18 A | 23-Aug-18 A | 112 | 0 | 81 | 100% |  | Completed
ER6243LT | W200 | RSSC.CNO.A145 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-10-18 | 2017-11-20 | Cooling Systems - Cooling Plant Availability (Optioneering) (HYA, HAR) | 30-Apr-18 A | 29-Jun-18 A | 32 | 0 | 42 | 100% |  | Completed
ER6243LT | W200 | A12050 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-03 | 2018-01-16 | Ops Compliance - Complete TR form and upload to CDMS | 01-May-18 A | 29-Jun-18 A | 21 | 0 | 41 | 100% |  | Completed
ER6243LT | W200 | A16550 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Thermal Hydraulics (MACE) - Initial Review & Recommendation by WOOD | 01-May-18 A | 15-May-18 A | 10 | 0 | 9 | 100% |  | Completed
ER6243LT | W200 | A16590 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Thermal Hydraulics (MACE) - Initial Review & Recommendation | 01-May-18 A | 15-May-18 A | 10 | 0 | 9 | 100% |  | Completed
ER6244LT | W220 | A1300 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-05-01 | 2018-07-31 | Determine fuel storage conditions - general guidance that will inform reactor storageand for ex-reactor facilities | 01-May-18 A | 31-Jul-18 A | 64 | 0 | 64 | 100% |  | Completed
ER6244LT | W220 | A1310 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-05-01 | 2018-07-31 | Review Inter-Granular Attack (IGA) assessments - determine whether these would need to be updated to support defuelling. | 01-May-18 A | 31-Jul-18 A | 64 | 0 | 64 | 100% |  | Completed
ER6244LT | W220 | A8600 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-05-01 | 2018-07-16 | Technical review of Initial Fault Studies and Risk Estimation Report (HYA/HRA) | 01-May-18 A | 16-Jul-18 A | 21 | 0 | 53 | 100% |  | Completed
ER6244LT | W220 | A9000 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-05-01 | 2018-06-01 | Technical review of Fuelling Machine Light Load Protection & Interlocks EAN (HPB and HNB) | 01-May-18 A | 01-Jun-18 A | 22 | 0 | 22 | 100% |  | Completed
ER6244LT | W220 | A9880 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-05-04 | Draft Fuel Free Verification EAN verified and issued for technical review | 04-May-18 A | 04-May-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11310 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-18 | 2017-12-22 | Cooling Faults - Complete TR form and upload to CDMS (HPB, HNB) | 07-May-18 A | 29-Jun-18 A | 5 | 0 | 37 | 100% |  | Completed
ER6243LT | W200 | A13560 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-04 | 2017-12-08 | Cooling Faults - Complete TR form and upload to CDMS (HYA, HAR) | 07-May-18 A | 29-Jun-18 A | 5 | 0 | 37 | 100% |  | Completed
ER6244LT | W220 | A6240 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-05-08 | 2018-05-18 | Supplier update and issue Buffer Store Defueling EAN (HPB and HNB) | 08-May-18 A | 18-May-18 A | 9 | 0 | 9 | 100% |  | Completed
ER6244LT | W220 | A6370 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-05-08 | 2018-05-18 | Supplier update and issue IFDF Defueling EAN (HPB and HNB) | 08-May-18 A | 18-May-18 A | 9 | 0 | 9 | 100% |  | Completed
ER6244LT | W220 | A6760 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-05-08 | 2018-05-18 | Supplier update and issue Ponds and Flasks EAN (HPB and HNB) | 08-May-18 A | 18-May-18 A | 9 | 0 | 9 | 100% |  | Completed
ER6244LT | W220 | A6890 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-05-08 | 2018-05-18 | Supplier update and issue Waste Vault Storage Capacity EAN (HPB and HNB) | 08-May-18 A | 18-May-18 A | 9 | 0 | 9 | 100% |  | Completed
ER6244LT | W220 | A8060 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-05-08 | 2018-05-25 | Supplier update and issue CRA Isolation Requirements EAN | 08-May-18 A | 25-May-18 A | 20 | 0 | 13 | 100% |  | Completed
ER6244LT | W220 | A9890 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-05-08 | 2018-07-11 | Technical review of Fuel Free Verification EAN | 08-May-18 A | 11-Jul-18 A | 9 | 0 | 46 | 100% |  | Completed
ER6244LT | W220 | A8890 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-05-08 | Fuel Free Verification EAN available | 08-May-18 A | 08-May-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A12230 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-02-27 | RCS Basis of Design - Draft Impact Assessment Report & C&I BoD verified and issued for Technical Review (HPB, HNB) | 09-May-18 A | 09-May-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A12270 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-02-27 | RCS Basis of Design - Draft Impact Assessment Report & C&I BoD verified and issued for Technical Review (HYA, HAR) | 09-May-18 A | 09-May-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A12240 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-02-28 | 2018-03-20 | RCS Basis of Design - Impact Assessment Report & C&I BoD Technical Review by SQEP (HPB, HNB) | 10-May-18 A | 29-Jun-18 A | 10 | 0 | 35 | 100% |  | Completed
ER6243LT | W200 | A12280 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-02-28 | 2018-03-20 | RCS Basis of Design - Impact Assessment Report & C&I BoD Technical Review by SQEP (HYA, HAR) | 10-May-18 A | 29-Jun-18 A | 10 | 0 | 35 | 100% |  | Completed
ER6244LT | W220 | A6610 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-05-14 | Draft IFDF Defueling EAN verified and issued for technical review (HYA and HRA) | 14-May-18 A | 14-May-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A7000 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-05-14 | Draft Ponds and Flasks EAN verified and issued for technical review (HYA and HRA) | 14-May-18 A | 14-May-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A7130 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-05-14 | Draft Waste Vault Storage Capacity EAN verified and issued for technical review (HYA and HRA) | 14-May-18 A | 14-May-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A6620 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-05-15 | 2018-05-21 | Technical review of IFDF Defueling EAN (HYA and HRA) | 15-May-18 A | 21-May-18 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A7010 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-05-15 | 2018-05-21 | Technical review of Ponds and Flasks EAN (HYA and HRA) | 15-May-18 A | 21-May-18 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A7140 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-05-15 | 2018-05-21 | Technical review of Waste Vault Storage Capacity EAN (HYA and HRA) | 15-May-18 A | 21-May-18 A | 5 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | A11380 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-04-23 | 2018-04-27 | Assessm't of Other Faults - Update and issue Fault Studies Report (HPB, HNB) | 16-May-18 A | 31-May-18 A | 5 | 0 | 10 | 100% |  | Completed
ER6243LT | W200 | A11530 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-04-23 | 2018-04-27 | Assessm't of Other Faults - Update and issue Fault Studies Report (HYA, HAR) | 16-May-18 A | 31-May-18 A | 5 | 0 | 10 | 100% |  | Completed
ER6243LT | W200 | A16560 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Thermal Hydraulics (MACE) - Prepare Updated Draft Summary Document | 16-May-18 A | 29-Jun-18 A | 15 | 0 | 31 | 100% |  | Completed
ER6243LT | W200 | A16600 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Thermal Hydraulics (MACE) - Prepare Updated HPB Defuelling Dataset | 16-May-18 A | 29-Jun-18 A | 15 | 0 | 31 | 100% |  | Completed
ER6244LT | W220 | A6250 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-05-21 | 2018-08-17 | Complete TR form and upload Buffer Store Defueling EAN to CDMS (HPB and HNB) | 21-May-18 A | 17-Aug-18 A | 4 | 0 | 64 | 100% |  | Completed
ER6244LT | W220 | A6380 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-05-21 | 2018-08-17 | Complete TR form and upload IFDF Defueling EAN to CDMS (HPB and HNB) | 21-May-18 A | 17-Aug-18 A | 4 | 0 | 64 | 100% |  | Completed
ER6244LT | W220 | A6770 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-05-21 | 2018-08-17 | Complete TR form and upload Ponds and Flasks EAN to CDMS (HPB and HNB) | 21-May-18 A | 17-Aug-18 A | 4 | 0 | 64 | 100% |  | Completed
ER6244LT | W220 | A6900 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-05-21 | 2018-08-17 | Complete TR form and upload Waste Vault Storage Capacity EAN to CDMS (HPB and HNB) | 21-May-18 A | 17-Aug-18 A | 4 | 0 | 64 | 100% |  | Completed
ER6244LT | W220 | A6630 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-05-22 | 2018-05-25 | Supplier update and issue IFDF Defueling EAN (HYA and HRA) | 22-May-18 A | 25-May-18 A | 4 | 0 | 4 | 100% |  | Completed
ER6244LT | W220 | A7020 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-05-22 | 2018-05-25 | Supplier update and issue Ponds and Flasks EAN (HYA and HRA) | 22-May-18 A | 25-May-18 A | 4 | 0 | 4 | 100% |  | Completed
ER6244LT | W220 | A7150 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-05-22 | 2018-05-25 | Supplier update and issue Waste Vault Storage Capacity EAN (HYA and HRA) | 22-May-18 A | 25-May-18 A | 4 | 0 | 4 | 100% |  | Completed
ER6243LT | W200 | A10920 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-03-29 | PCPV Integrity - Engineering Substantiation Report verified and issued for Technical Review (HPB, HNB) | 25-May-18 A | 25-May-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A10980 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-03-29 | PCPV Integrity - Engineering Substantiation Report verified and issued for Technical Review (HYA, HAR) | 25-May-18 A | 25-May-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A6640 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-05-29 | 2018-07-27 | Complete TR form and upload IFDF Defueling EAN to CDMS (HYA and HRA) | 29-May-18 A | 27-Jul-18 A | 3 | 0 | 44 | 100% |  | Completed
ER6244LT | W220 | A7030 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-05-29 | 2018-07-27 | Complete TR form and upload Ponds and Flasks EAN to CDMS (HYA and HRA) | 29-May-18 A | 27-Jul-18 A | 3 | 0 | 44 | 100% |  | Completed
ER6244LT | W220 | A7160 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-05-29 | 2018-07-27 | Complete TR form and upload Waste Vault Storage Capacity EAN to CDMS (HYA and HRA) | 29-May-18 A | 27-Jul-18 A | 3 | 0 | 44 | 100% |  | Completed
ER6244LT | W220 | A8070 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-05-29 | 2018-06-04 | Complete TR form and upload CRA Isolation Requirements EAN to CDMS | 29-May-18 A | 04-Jun-18 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A10360 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-06-01 | 2018-12-17 | Draft Review of Safety Case Limits & LOLER Inspection Requirements | 01-Jun-18 A | 17-Dec-18 A | 85 | 0 | 141 | 100% |  | Completed
ER6244LT | W220 | A10540 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-06-01 | 2018-08-01 | Technical Review of OPR Cycle Times EAN | 01-Jun-18 A | 01-Aug-18 A | 43 | 0 | 44 | 100% |  | Completed
ER6244LT | W220 | A10580 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-06-01 | 2018-06-08 | Draft Review of Off-Load Pressurised Refuelling Safety Case for Defuelling Verified and Issued for TR | 01-Jun-18 A | 08-Jun-18 A | 21 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A10830 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-06-01 | 2018-07-02 | Draft HHB Scoping Review Assessing Radcons 90days after EoG | 01-Jun-18 A | 02-Jul-18 A | 5 | 0 | 21 | 100% |  | Completed
ER6243LT | W200 | A1010 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-07-13 | 2018-07-19 | Produce MF EC 363701 & 364023 <NSRS SC Approach & Outline> & obtain approval (HPB, HNB) | 04-Jun-18 A | 28-Aug-18 A | 5 | 0 | 60 | 100% |  | Completed
ER6243LT | W200 | A10190 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-07-20 | 2018-07-26 | Produce MF EC 363682 & 363676 <NSRS SC Approach & Outline> & obtain approval (HYA, HAR) | 04-Jun-18 A | 21-Aug-18 A | 5 | 0 | 56 | 100% |  | Completed
ER6243LT | W200 | RSSC.VI.A230.EI | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-08-10 | Closure and Seal Integrity - Issue of the report on to CDMS. (HPB, HNB) | 04-Jun-18 A | 04-Jun-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.VI.A240.EI | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-08-15 | Closure and Seal Integrity - Issue of the report on to CDMS (HYA, HAR) | 04-Jun-18 A | 04-Jun-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A5330 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-06-04 | 2018-08-01 | Supplier update and issue Refuelling Cooling Assessment EAN | 04-Jun-18 A | 01-Aug-18 A | 10 | 0 | 43 | 100% |  | Completed
ER6244LT | W220 | A7930 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-06-04 | 2018-06-08 | Update and issue Review Radial Shuffling Safety Case EAN - Rev 001 | 04-Jun-18 A | 08-Jun-18 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A9010 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-06-04 | 2018-06-07 | Supplier update and issue Fuelling Machine Light Load Protection & Interlocks EAN (HPB and HNB) | 04-Jun-18 A | 07-Jun-18 A | 4 | 0 | 4 | 100% |  | Completed
ER6244LT | W220 | A8080.EC | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-06-04 | CRA Isolation Requirements EAN available | 04-Jun-18 A | 04-Jun-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16530 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Prepare Draft Human Factors Integration Plan EAN (HPB, HNB) | 06-Jun-18 A | 31-Jul-18 A | 20 | 0 | 39 | 100% |  | Completed
ER6243LT | W200 | A16540 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Prepare Draft Human Factors Integration Plan EAN (HYA, HAR) | 06-Jun-18 A | 31-Jul-18 A | 20 | 0 | 40 | 100% |  | Completed
ER6244LT | W220 | A7950.EC | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-06-06 | Review Radial Shuffling Safety Case EAN available - Rev 001 | 06-Jun-18 A | 06-Jun-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11270 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-18 | 2017-12-22 | Cooling Faults - Complete TR form and upload to CDMS (HPB, HNB) | 08-Jun-18 A | 29-Jun-18 A | 5 | 0 | 15 | 100% |  | Completed
ER6244LT | W220 | A9020 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-06-08 | 2018-06-15 | Complete TR form and upload Fuelling Machine Light Load Protection & Interlocks EAN (HPB and HNB) to CDMS | 08-Jun-18 A | 15-Jun-18 A | 6 | 0 | 6 | 100% |  | Completed
ER6243LT | W200 | A13490 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-11 | 2018-01-17 | Cooling Faults - Complete TR form and upload to CDMS (HYA, HAR) | 08-Jun-18 A | 29-Jun-18 A | 5 | 0 | 15 | 100% |  | Completed
ER6243LT | W200 | A3120 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-07-05 | 2018-07-11 | Mod Requested, Identify RE and EC Request Raised and Screened (HPB, HNB) | 11-Jun-18 A | 13-Jul-18 A | 5 | 0 | 24 | 100% |  | Completed
ER6243LT | W200 | A10310 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-07-12 | 2018-07-18 | Mod Requested, Identify RE and EC Request Raised and Screened (HYA, HAR) | 11-Jun-18 A | 07-Aug-18 A | 5 | 0 | 42 | 100% |  | Completed
ER6244LT | W220 | A10590 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-06-11 | 2018-08-21 | Technical Review of Review of Off-Load Pressurised Refuelling Safety Case for Defuelling | 11-Jun-18 A | 21-Aug-18 A | 22 | 0 | 52 | 100% |  | Completed
ER6244LT | W220 | A9900 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-06-13 | 2018-07-18 | Supplier update and issue Fuel Free Verification EAN | 13-Jun-18 A | 18-Jul-18 A | 5 | 0 | 26 | 100% |  | Completed
ER6243LT | W200 | A15840 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-04-27 | 2018-08-06 | Overall Delivery Plan - Produce Overall Delivery Plan (HPB, HNB) (No Longer Req,d) | 14-Jun-18 A | 14-Jun-18 A | 13 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A15850 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-04-27 | 2018-08-06 | Overall Delivery Plan - Produce Overall Delivery Plan (HYA, HAR) (No Longer Req,d) | 14-Jun-18 A | 14-Jun-18 A | 65 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A15950 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-04-27 | 2018-04-27 | Overall Delivery Plan - Pre Job Brief (HPB, HNB)(No Longer Req,d) | 14-Jun-18 A | 14-Jun-18 A | 1 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16030 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-07-17 | 2018-07-30 | Overall Delivery Plan - Update and issue Overall Delivery Plan (HYA, HAR) (No Longer Req,d) | 14-Jun-18 A | 14-Jun-18 A | 10 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15970 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-06-26 | 2018-07-16 | Overall Delivery Plan - Overall Delivery Plan Technical Review by SQEP (HPB, HNB) (No Longer Req,d) | 14-Jun-18 A | 14-Jun-18 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A15980 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-07-17 | 2018-07-30 | Overall Delivery Plan - Update and issue Overall Delivery Plan (HPB, HNB) (No Longer Req,d) | 14-Jun-18 A | 14-Jun-18 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A15990 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-07-31 | 2018-08-06 | Overall Delivery Plan - Complete TR form and upload to CDMS (HPB, HNB) (No Longer Req,d) | 14-Jun-18 A | 14-Jun-18 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A16000 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-04-27 | 2018-06-25 | Overall Delivery Plan - Prepare Overall Delivery Plan (HPB, HNB) (Deliverable 1 Post Hold Point) (No Longer Req,d) | 14-Jun-18 A | 14-Jun-18 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A16020 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-06-26 | 2018-07-16 | Overall Delivery Plan - Overall Delivery Plan Technical Review by SQEP (HYA, HAR) (No Longer Req,d) | 14-Jun-18 A | 14-Jun-18 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A16040 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-07-31 | 2018-08-06 | Overall Delivery Plan - Complete TR form and upload to CDMS (HYA, HAR) (No Longer Req,d) | 14-Jun-18 A | 14-Jun-18 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A16050 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-04-27 | 2018-06-25 | Overall Delivery Plan - Prepare Overall Delivery Plan (HYA, HAR) (Deliverable 1 Post Hold Point) (No Longer Req,d) | 14-Jun-18 A | 14-Jun-18 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A15860 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-09-10 | Overall Delivery Plan - Overall Delivery Plan for required plant modifications Completed. (HPB, HNB) (No Longer Req,d) | 14-Jun-18 A | 14-Jun-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15870 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-09-14 | Overall Delivery Plan - Overall Delivery Plan for required plant modifications Completed. (HYA, HAR) (No Longer Req,d) | 14-Jun-18 A | 14-Jun-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15960 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-06-25 | Overall Delivery Plan - Draft Overall Delivery Plan verified and issued for Tech Review (HPB, HNB) (No Longer Req,d) | 14-Jun-18 A | 14-Jun-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16010 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-06-25 | Overall Delivery Plan - Draft Overall Delivery Plan verified and issued for Tech Review (HYA, HAR) (No Longer Req,d) | 14-Jun-18 A | 14-Jun-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16720 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Complete and Issue Contract Variation (HPB, HNB) | 15-Jun-18 A | 29-Jun-18 A | 5 | 0 | 10 | 100% |  | Completed
ER6243LT | W200 | A16750 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Complete and Issue Contract Variation (HYA, HAR) | 15-Jun-18 A | 29-Jun-18 A | 5 | 0 | 10 | 100% |  | Completed
ER6244LT | W220 | A6130 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-06-15 | Fuelling Machine Light Load Protection & Interlocks EAN (HPB and HNB) available | 15-Jun-18 A | 15-Jun-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A10500 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-06-18 | 2018-07-27 | Technical Review of Optioneering Report for HRA/HYA | 18-Jun-18 A | 27-Jul-18 A | 10 | 0 | 30 | 100% |  | Completed
ER6244LT | W220 | A1650 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-06-22 | Confirm reactor internals damage (at diff. temps) & buffer store plant damage caused by dropped FPU impact (HPB & HNB) | 22-Jun-18 A | 22-Jun-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.FS.A200 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-08-24 | Cooling Faults - Rad Con's Requirements for Post NSRS Identified and Scoped Completed (HPB, HNB) | 29-Jun-18 A | 29-Jun-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.FS.A210 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-02-07 | Cooling Faults - Credible Hazards and Faults Identified and Scoped Completed (HPB, HNB) | 29-Jun-18 A | 29-Jun-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11640 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-11-17 | Cooling Systems - Draft Cooling Plant Availability (Optioneering) verified and issued for Technical Review (HPB, HNB) | 29-Jun-18 A | 29-Jun-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11690 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-11-20 | Cooling Systems - Draft Cooling Plant Availability (Optioneering) verified and issued for Technical Review (HYA, HAR) | 29-Jun-18 A | 29-Jun-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A12060.EA | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-06-29 | Ops Compliance - QA3 SDM Defuelling Strategy Optioneering Report Completed | 29-Jun-18 A | 29-Jun-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A13440 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-08-31 | Cooling Faults - Rad Con's Requirements for Post NSRS Identified and Scoped Completed (HYA, HAR) | 29-Jun-18 A | 29-Jun-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A13520 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-02-07 | Cooling Faults - Credible Hazards and Faults Identified and Scoped Completed (HYA, HAR) | 29-Jun-18 A | 29-Jun-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14170 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-03-02 | Ops Compliance - Draft Optioneering for CR and N2 systems verified and issued for Technical Review (HPB, HNB) | 29-Jun-18 A | 29-Jun-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14240 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-03-02 | Ops Compliance - Draft Optionnering for CR and N2 systems verified and issued for Technical Review (HYA, HAR) | 29-Jun-18 A | 29-Jun-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A10930 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-04-03 | 2018-04-19 | PCPV Integrity - Engineering Substantiation Report Technical Review by SQEP (HPB, HNB) | 02-Jul-18 A | 13-Jul-18 A | 10 | 0 | 10 | 100% |  | Completed
ER6243LT | W200 | A11390 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-04-30 | 2018-05-04 | Assessm't of Other Faults - Complete TR form and upload to CDMS (HPB, HNB) | 02-Jul-18 A | 13-Jul-18 A | 5 | 0 | 9 | 100% |  | Completed
ER6243LT | W200 | A11540 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-04-30 | 2018-05-04 | Assessm't of Other Faults - Complete TR form and upload to CDMS (HYA, HAR) | 02-Jul-18 A | 13-Jul-18 A | 5 | 0 | 9 | 100% |  | Completed
ER6243LT | W200 | A11650 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-20 | 2017-12-01 | Cooling Systems - Cooling Plant Availability (Optioneering) Technical Review by SQEP (HPB, HNB) | 02-Jul-18 A | 16-Jul-18 A | 10 | 0 | 10 | 100% |  | Completed
ER6243LT | W200 | A11700 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-11-21 | 2017-12-04 | Cooling Systems - Cooling Plant Availability (Optioneering) Technical Review by SQEP (HYA, HAR) | 02-Jul-18 A | 16-Jul-18 A | 10 | 0 | 10 | 100% |  | Completed
ER6243LT | W200 | A12250 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-03-21 | 2018-04-05 | RCS Basis of Design - Update and issue Impact Assessment Report & C&I BoD (HPB, HNB) | 02-Jul-18 A | 30-Jul-18 A | 10 | 0 | 20 | 100% |  | Completed
ER6243LT | W200 | A12290 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-03-21 | 2018-04-05 | RCS Basis of Design - Update and issue Impact Assessment Report & C&I BoD (HYA, HAR) | 02-Jul-18 A | 30-Jul-18 A | 10 | 0 | 20 | 100% |  | Completed
ER6243LT | W200 | A14180 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-03-05 | 2018-03-16 | Ops Compliance - Optioneering for CR and N2 systems Technical Review by SQEP (HPB, HNB) | 02-Jul-18 A | 16-Jul-18 A | 19 | 0 | 10 | 100% |  | Completed
ER6243LT | W200 | A14250 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-03-05 | 2018-03-16 | Ops Compliance - Optionnering for CR and N2 systems Technical Review by SQEP (HYA, HAR) | 02-Jul-18 A | 16-Jul-18 A | 19 | 0 | 10 | 100% |  | Completed
ER6243LT | W200 | A14980 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-05 | 2018-01-11 | Maintenance - Complete TR form and upload to CDMS (HPB, HNB) | 02-Jul-18 A | 06-Jul-18 A | 5 | 0 | 4 | 100% |  | Completed
ER6243LT | W200 | A15090 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-01-05 | 2018-01-11 | Maintenance - Complete TR form and upload to CDMS (HYA, HAR) | 02-Jul-18 A | 06-Jul-18 A | 5 | 0 | 4 | 100% |  | Completed
ER6243LT | W200 | A16630 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | PCPV Ageing & Degradation - Engineering Substantiation Report Technical Review by SQEP (HPB, HNB) | 02-Jul-18 A | 13-Jul-18 A | 10 | 0 | 10 | 100% |  | Completed
ER6243LT | W200 | A16670 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | PCPV Ageing & Degradation - Engineering Substantiation Report Technical Review by SQEP (HYA, HAR) | 02-Jul-18 A | 13-Jul-18 A | 10 | 0 | 10 | 100% |  | Completed
ER6244LT | W220 | A3330 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-07-02 | 2018-10-19 | Produce draft NSRS for HYA and HRA (using BARRIER MODEL) | 02-Jul-18 A | 19-Oct-18 A | 75 | 0 | 79 | 100% |  | Completed
ER6244LT | W220 | A10290 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-07-02 | 2018-12-17 | Draft Review of Plant Requirements for Defuelling | 02-Jul-18 A | 17-Dec-18 A | 60 | 0 | 120 | 100% |  | Completed
ER6244LT | W220 | A10730 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-07-02 | Draft HHB Scoping Review Assessing Radcons 90days after EoG Verified and Issued for Technical Review | 02-Jul-18 A | 02-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A10900 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-07-02 | 2018-07-04 | Supplier mobilisation | 02-Jul-18 A | 04-Jul-18 A | 3 | 0 | 3 | 100% |  | Completed
ER6244LT | W220 | A10160 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-07-02 | Draft Review of Rad Cons for Lower Decay Heat for Input into PSA verified and issued for technical review | 02-Jul-18 A | 02-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16570 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Thermal Hydraulics (MACE) - Updated Draft Summary Document Internally Verified | 03-Jul-18 A | 31-Jul-18 A | 22 | 0 | 20 | 100% |  | Completed
ER6243LT | W200 | A16780 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Develop Draft Station resourced Plans for HPB and HNB | 03-Jul-18 A | 10-Oct-18 A | 20 | 0 | 70 | 100% |  | Completed
ER6243LT | W200 | A16800 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Develop Draft Station resourced Plans for HNB (Reactor 3 early closure) | 03-Jul-18 A | 10-Oct-18 A | 20 | 0 | 70 | 100% |  | Completed
ER6244LT | W220 | A10170 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-07-03 | 2018-10-19 | Technical review of Review of Rad Cons for Lower Decay Heat for Input into PSA | 03-Jul-18 A | 19-Oct-18 A | 25 | 0 | 78 | 100% |  | Completed
ER6244LT | W220 | A10905.EJ | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-07-05 |  | Pre Job Brief for Dropped FPU impact on Core Support Structure (HYA and HRA) | 05-Jul-18 A | 05-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A10910 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-07-05 | 2018-10-01 | Draft Dropped FPU impact on Core Support Structure Report (HYA and HRA) | 05-Jul-18 A | 01-Oct-18 A | 60 | 0 | 62 | 100% |  | Completed
ER6243LT | W200 | RSSC.M.A180.ET | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-08-24 | Maintenance - Report identifying key safety related plant for post operational phase (HPB, HNB) | 06-Jul-18 A | 06-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.M.A190.ET | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-08-31 | Maintenance - Report identifying key safety related plant for post operational phase (HYA, HAR) | 06-Jul-18 A | 06-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14860 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-01-11 | Maintenance - Summary of TS Charges Required Identified and Scoped Completed (HPB, HNB) | 06-Jul-18 A | 06-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15040 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-01-11 | Maintenance - Summary of TS Charges Required Identified and Scoped Completed (HYA, HAR) | 06-Jul-18 A | 06-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A10090 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-07-09 | Draft Dropped FPU RadCons Analysis of Core Support Plate Failure verified and issued for technical review | 09-Jul-18 A | 09-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A9620 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-07-09 | Draft Fuel Free Verification EAN verified and issued for technical review | 09-Jul-18 A | 09-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A10100 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-07-10 | 2018-12-17 | Technical review of Dropped FPU RadCons Analysis of Core Support Plate Failure | 10-Jul-18 A | 17-Dec-18 A | 29 | 0 | 114 | 100% |  | Completed
ER6244LT | W220 | A9380 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-07-10 | 2018-07-16 | Supplier update and issue Fuel Storage Conditions EAN | 10-Jul-18 A | 16-Jul-18 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A9630 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-07-10 | 2018-09-24 | Technical review of Fuel Free Verification EAN | 10-Jul-18 A | 24-Sep-18 A | 15 | 0 | 53 | 100% |  | Completed
ER6244LT | W220 | A3850 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-07-10 | Produce report on interlock changes req. for staggered operation of reactors, defuelling mode and FPUs back in reactor | 10-Jul-18 A | 10-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.FS.A220.EH | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-09-17 | Assessm't of Other Faults - Preliminary fault schedule for a shutdown reactor, depressurised in CO2 (HPB, HNB) | 13-Jul-18 A | 13-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.FS.A230.EH | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-08-31 | Assessm't of Other Faults - Preliminary fault schedule for a shutdown reactor, depressurised in CO2 (HYA, HAR) | 13-Jul-18 A | 13-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.FS.A240.EH | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-09-17 | Assessm't of Other Faults - Consider faults with air atmosphere (HPB, HNB) | 13-Jul-18 A | 13-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.FS.A250.EH | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-09-21 | Assessm't of Other Faults - Consider faults with air atmosphere (HYA, HAR) | 13-Jul-18 A | 13-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A10940 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-04-20 | 2018-04-26 | PCPV Integrity - Update and issue Engineering Substantiation Report (HPB, HNB) | 16-Jul-18 A | 17-Dec-18 A | 10 | 0 | 109 | 100% |  | Completed
ER6243LT | W200 | A15310 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-08-06 | Draft Summary of supporting references Report Available for Review (HPB, HNB) | 16-Jul-18 A | 16-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15550 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-08-06 | Draft Summary of supporting references Report Available for Review (HYA, HAR) | 16-Jul-18 A | 16-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16610 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Thermal Hydraulics (MACE) - Updated Defuelling Dataset Internally Verified by TSA | 16-Jul-18 A | 03-Sep-18 A | 5 | 0 | 35 | 100% |  | Completed
ER6243LT | W200 | A16640 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-10-17 | 2018-10-23 | PCPV Ageing & Degradation - Update and issue Engineering Substantiation Report (HPB, HNB) | 16-Jul-18 A | 30-Aug-18 A | 10 | 0 | 32 | 100% |  | Completed
ER6244LT | W220 | A10450 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-07-16 | 2018-08-10 | Update and Issue Optioneering Report for HPB/HNB | 16-Jul-18 A | 10-Aug-18 A | 5 | 0 | 20 | 100% |  | Completed
ER6244LT | W220 | A3050.C0 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-07-16 | Identify any Major Hardware Changes required for Gate B Submission | 16-Jul-18 A | 16-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A10990 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-04-03 | 2018-04-19 | PCPV Integrity - Engineering Substantiation Report Technical Review by SQEP (HYA, HAR) | 17-Jul-18 A | 30-Jul-18 A | 10 | 0 | 10 | 100% |  | Completed
ER6243LT | W200 | A11660 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-04 | 2017-12-08 | Cooling Systems - Update and issue Cooling Plant Availability (Optioneering) (HPB, HNB) | 17-Jul-18 A | 24-Jul-18 A | 5 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | A11710 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-05 | 2017-12-11 | Cooling Systems - Update and issue Cooling Plant Availability (Optioneering) (HYA, HAR) | 17-Jul-18 A | 24-Jul-18 A | 5 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | A14190 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-03-19 | 2018-03-23 | Ops Compliance - Update and issue Optioneering for CR and N2 systems (HPB, HNB) | 17-Jul-18 A | 24-Jul-18 A | 5 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | A14260 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-03-19 | 2018-03-23 | Ops Compliance - Update and issue Optionnering for CR and N2 systems (HYA, HAR) | 17-Jul-18 A | 24-Jul-18 A | 5 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | A15320 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-08-07 | 2018-09-24 | Review & Acceptance of Summary of supporting references Report (HPB, HNB) | 17-Jul-18 A | 21-Aug-18 A | 10 | 0 | 25 | 100% |  | Completed
ER6243LT | W200 | A15560 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-08-07 | 2018-09-28 | Review & Acceptance of Summary of supporting references Report (HYA, HAR) | 17-Jul-18 A | 21-Aug-18 A | 10 | 0 | 25 | 100% |  | Completed
ER6244LT | W220 | A8610 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-07-17 | 2018-08-01 | Supplier update and issue Initial Fault Studies and Risk Estimation Report (HYA/HRA) | 17-Jul-18 A | 01-Aug-18 A | 12 | 0 | 12 | 100% |  | Completed
ER6244LT | W220 | A9390 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-07-17 | 2018-07-25 | Complete TR form and upload Fuel Storage Conditions EAN to CDMS (HYA and HRA) | 17-Jul-18 A | 25-Jul-18 A | 7 | 0 | 7 | 100% |  | Completed
ER6244LT | W220 | A9910 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-07-19 | 2018-07-25 | Complete TR form and upload Fuel Free Verification EAN to CDMS | 19-Jul-18 A | 25-Jul-18 A | 5 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1000 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Define Project Control Structures (WBS/CBS/OBS/PBS) | 23-Jul-18 A | 23-Jul-18 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A1145 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Workshop to agree scope, effort and links | 23-Jul-18 A | 03-Dec-18 A | 17 | 0 | 94 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1010 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Prepare Draft Project Definition Document (PDD) | 24-Jul-18 A | 04-Dec-18 A | 22 | 0 | 94 | 100% |  | Completed
ER6243LT | W200 | RSSC.OC.A540.EA | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-09-14 | Principles of Fuel Free Verification - Issue of the Report onto CDMS (HPB, HNB) | 25-Jul-18 A | 25-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.CNO.A160.EF | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-08-28 | Report identifying issues/ provide assurance that Carbon deposition with not be a problem during defuelling (HPB, HNB) | 25-Jul-18 A | 25-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.CNO.A170.EF | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-08-28 | Cooling Systems - Report on clad sensitisation aspects (HPB, HNB) | 25-Jul-18 A | 25-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.CNO.A190.EF | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-08-31 | Report identifying issues/ provide assurance that Carbon deposition with not be a problem during defuelling (HYA, HAR) | 25-Jul-18 A | 25-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.CNO.A200.EF | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-08-31 | Cooling Systems - Report on clad sensitisation aspects (HYA, HAR) | 25-Jul-18 A | 25-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A7170.EQ10 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-07-25 | Fuel Storage Conditions EAN available | 25-Jul-18 A | 25-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A9920 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-07-25 | Fuel Free Verification EAN available | 25-Jul-18 A | 25-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A6650.EQ | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-07-27 | IFDF Defueling EAN available (HYA and HRA) | 27-Jul-18 A | 27-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A7040.EQ | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-07-27 | Ponds and Flasks EAN available (HYA and HRA) | 27-Jul-18 A | 27-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A7170.EQ | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-07-27 | Waste Vault Storage Capacity EAN available (HYA and HRA) | 27-Jul-18 A | 27-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A10510 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-07-30 | 2018-08-10 | Update and Issue Optioneering Report for HRA/HYA | 30-Jul-18 A | 10-Aug-18 A | 5 | 0 | 10 | 100% |  | Completed
ER6244LT | W220 | A3700 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-07-31 | Decision on any changes to FM trip settings (HYA and HRA) | 31-Jul-18 A | 31-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A12260 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-04-06 | 2018-04-12 | RCS Basis of Design - Complete TR form and upload to CDMS (HPB, HNB) | 31-Jul-18 A | 21-Sep-18 A | 5 | 0 | 37 | 100% |  | Completed
ER6243LT | W200 | A12300 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-04-06 | 2018-04-12 | RCS Basis of Design - Complete TR form and upload to CDMS (HYA, HAR) | 31-Jul-18 A | 21-Sep-18 A | 5 | 0 | 37 | 100% |  | Completed
ER6243LT | W200 | A15630 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-02-27 | Draft Human Factor Integration Plan EAN Available for Review (HPB, HNB) | 31-Jul-18 A | 31-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15690 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-02-27 | Draft Human Factors Integration Plan EAN Available for Review (HYA, HAR) | 31-Jul-18 A | 31-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16580 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Thermal Hydraulics (MACE) - Updated Draft Summary Document Issued for Technical Review | 31-Jul-18 A | 31-Jul-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16680 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | PCPV Ageing & Degradation - Update and issue Engineering Substantiation Report (HYA, HAR) | 31-Jul-18 A | 17-Sep-18 A | 0 | 0 | 33 | 100% |  | Completed
ER6243LT | W200 | A11670 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-11 | 2017-12-15 | Cooling Systems - Complete TR form and upload to CDMS (HPB, HNB) | 01-Aug-18 A | 23-Aug-18 A | 5 | 0 | 16 | 100% |  | Completed
ER6243LT | W200 | A11720 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-12-12 | 2017-12-18 | Cooling Systems - Complete TR form and upload to CDMS (HYA, HAR) | 01-Aug-18 A | 23-Aug-18 A | 5 | 0 | 16 | 100% |  | Completed
ER6244LT | W220 | A10010 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-08-01 | Draft Fuelling Machine Light Load Protection & Interlocks EAN (HYA/HRA) issued for verification | 01-Aug-18 A | 01-Aug-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A5340 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-08-02 | 2018-08-31 | Complete TR form and upload Refuelling Cooling Assessment EAN to CDMS | 02-Aug-18 A | 31-Aug-18 A | 21 | 0 | 20 | 100% |  | Completed
ER6244LT | W220 | A8620 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-08-02 | 2018-09-03 | Complete TR form and upload Initial Fault Studies and Risk Estimation Report to CDMS (HYA/HRA) | 02-Aug-18 A | 03-Sep-18 A | 0 | 0 | 22 | 100% |  | Completed
ER6244LT | W220 | A10020 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-08-02 | 2018-08-02 | Verification of Fuelling Machine Light Load Protection & Interlocks EAN (HYA/HRA) | 02-Aug-18 A | 02-Aug-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A10030 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-08-02 | 2018-08-15 | Update and issue Fuelling Machine Light Load Protection & Interlocks EAN (HYA/HRA) | 02-Aug-18 A | 15-Aug-18 A | 10 | 0 | 10 | 100% |  | Completed
ER6244LT | W220 | A10550 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-08-02 | 2018-08-03 | Supplier Update and Issue OPR Cycle Times EAN | 02-Aug-18 A | 03-Aug-18 A | 2 | 0 | 2 | 100% |  | Completed
ER6243LT | W200 | A11830 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-07-27 | 2017-08-02 | Thermal Hydraulics (MACE) - Thermal Hydraulics (MACE) Draft Summary Document Technical Review by SQEP (PH1) | 06-Aug-18 A | 21-Sep-18 A | 10 | 0 | 33 | 100% |  | Completed
ER6244LT | W220 | A10560 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-08-06 | 2018-08-10 | Complete TR Form and Upload OPR Cycle Times EAN to CDMS | 06-Aug-18 A | 10-Aug-18 A | 5 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | A10100 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-07-12 | 2018-07-12 | Initiate and Register EC and identify Milestones in AMS EC 363701 & 364023 (HPB, HNB) | 10-Aug-18 A | 10-Aug-18 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A10270 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-07-19 | 2018-07-19 | Initiate and Register EC and identify Milestones in AMS EC 363682 & 363676 (HYA, HAR) | 10-Aug-18 A | 10-Aug-18 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A10570 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-08-10 | OPR Cycle Times EAN Available | 10-Aug-18 A | 10-Aug-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11000 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-04-20 | 2018-04-26 | PCPV Integrity - Update and issue Engineering Substantiation Report (HYA, HAR) | 13-Aug-18 A | 17-Dec-18 A | 8 | 0 | 89 | 100% |  | Completed
ER6244LT | W220 | A10460 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-08-13 | 2018-08-17 | Complete TR Form and Upload Optioneering Report for HPB/HNB to CDMS | 13-Aug-18 A | 17-Aug-18 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A10520 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-08-13 | 2018-08-17 | Complete TR Form and Upload Optioneering Report for HRA/HYA to CDMS | 13-Aug-18 A | 17-Aug-18 A | 5 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | A1230 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-10-01 | 2018-10-05 | Hold Case Conference as Appropriate (HPB, HNB) | 14-Aug-18 A | 14-Aug-18 A | 5 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A10380 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-10-01 | 2018-10-05 | Hold Case Conference as Appropriate (HYA, HAR) | 14-Aug-18 A | 14-Aug-18 A | 5 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A1260 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-07-24 | 2018-07-30 | Identify verifier for the case & establish all other resources (HPB, HNB) | 14-Aug-18 A | 14-Aug-18 A | 5 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15130 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-04-04 | 2018-05-01 | Prepare Mapping Optioneering Specification (HPB, HNB)(Not Required as per DS 27.09.18) | 14-Aug-18 A | 14-Aug-18 A | 10 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15140 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-05-01 | Mapping Optioneering Specification Agreed (HPB, HNB) (Not Required as per DS 27.09.18) | 14-Aug-18 A | 14-Aug-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15150 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-05-02 | 2018-06-28 | Prepare Mapping Optioneering Report (HPB, HNB) | 14-Aug-18 A | 21-Feb-19 A | 20 | 0 | 134 | 100% |  | Completed
ER6243LT | W200 | A15370 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-04-04 | 2018-05-01 | Prepare Mapping Optioneering Specification (HYA, HAR)(Not Required as per DS 27.09.18) | 14-Aug-18 A | 14-Aug-18 A | 10 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15380 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-05-01 | Mapping Optioneering Specification Agreed (HYA, HAR)(Not Required as per DS 27.09.18) | 14-Aug-18 A | 14-Aug-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15390 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-05-02 | 2018-06-28 | Prepare Mapping Optioneering Report (HYA, HAR) | 14-Aug-18 A | 21-Feb-19 A | 20 | 0 | 133 | 100% |  | Completed
ER6243LT | W200 | A15365 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Mapping Optioneering - Summary (HYA, HAR) | 14-Aug-18 A | 21-Feb-19 A | 121 | 0 | 133 | 100% |  | Completed
ER6243LT | W200 | A15125 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Mapping Optioneering - Summary (HPB, HNB) | 14-Aug-18 A | 21-Feb-19 A | 101 | 0 | 134 | 100% |  | Completed
ER6244LT | W220 | A10050 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-08-15 | Fuelling Machine Light Load Protection & Interlocks EAN (HYA/HRA) available | 15-Aug-18 A | 15-Aug-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A14200 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-03-26 | 2018-04-03 | Ops Compliance - Complete TR form and upload to CDMS (HPB, HNB) | 17-Aug-18 A | 31-Aug-18 A | 5 | 0 | 9 | 100% |  | Completed
ER6243LT | W200 | A14270 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-03-26 | 2018-04-03 | Ops Compliance - Complete TR form and upload to CDMS (HYA, HAR) | 17-Aug-18 A | 31-Aug-18 A | 5 | 0 | 9 | 100% |  | Completed
ER6244LT | W220 | A6260.EQ | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-08-17 | Buffer Store Defueling EAN available (HPB and HNB) | 17-Aug-18 A | 17-Aug-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A6390.EQ | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-08-17 | IFDF Defueling EAN available (HPB and HNB) | 17-Aug-18 A | 17-Aug-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A6780.EQ | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-08-17 | Ponds and Flasks EAN available (HPB and HNB) | 17-Aug-18 A | 17-Aug-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A6910.EQ | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-08-17 | Waste Vault Storage Capacity EAN available (HPB and HNB) | 17-Aug-18 A | 17-Aug-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A10470 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-08-17 | Optioneering Report for HPB/HNB Available | 17-Aug-18 A | 17-Aug-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A10530 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-08-17 | Optioneering Report for HRA/HYA Available | 17-Aug-18 A | 17-Aug-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A1020 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-07-20 | 2018-07-20 | Initial Categorisation by Station (HPB, HNB) | 21-Aug-18 A | 28-Aug-18 A | 1 | 0 | 4 | 100% |  | Completed
ER6243LT | W200 | A13250 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-09-24 | Summary of supporting references required for safety case Issued to CDMS (HPB, HNB) | 21-Aug-18 A | 21-Aug-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A13260 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-09-28 | Summary of supporting references required for safety case issued to CDMS (HYA, HAR) | 21-Aug-18 A | 21-Aug-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A10320 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-07-27 | 2018-07-27 | Initial Categorisation by Station (HYA, HAR) | 22-Aug-18 A | 29-Oct-18 A | 1 | 0 | 47 | 100% |  | Completed
ER6244LT | W220 | A10600 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-08-22 | 2018-08-28 | Supplier Update and Issue Review of Off-Load Pressurised Refuelling Safety Case for Defuelling | 22-Aug-18 A | 28-Aug-18 A | 5 | 0 | 3 | 100% |  | Completed
ER6244LT | W220 | A10990 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-08-22 | 2018-08-22 | Complete requisition approval and issue CI for Updated EoG Initial Fault Studies and Risk Estimation Report | 22-Aug-18 A | 22-Aug-18 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | RSSC.CNO.A150.EF | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-06-29 | Cooling Systems - Options for Cooling Post Shutdown - Report (HPB, HNB) | 23-Aug-18 A | 23-Aug-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.CNO.A180.EF | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-06-29 | Cooling Systems - Options for Cooling Post Shutdown - Report (HYA, HAR) | 23-Aug-18 A | 23-Aug-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15770 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-01-24 | Review NSP's for Shutdown Cooling Safety CasesReport Issued to CDMS (HPB, HNB) (Not Req'd move to Post Gate B) | 23-Aug-18 A | 23-Aug-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15830 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-01-24 | Review NSP's for Shutdown Cooling Safety CasesReport Issued to CDMS (HYA, HAR)(Not Req'd move to Post Gate B) | 23-Aug-18 A | 23-Aug-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A11000 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-08-23 | 2018-08-24 | Supplier Mobilisation | 23-Aug-18 A | 24-Aug-18 A | 2 | 0 | 2 | 100% |  | Completed
ER6244LT | W220 | A11010 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-08-28 | 2018-08-28 | Pre Job Brief for Updated EoG Initial Fault Studies and Risk Estimation Report | 28-Aug-18 A | 28-Aug-18 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A11020 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-08-28 | 2018-10-05 | Draft Updated EoG Initial Fault Studies and Risk Estimation Report | 28-Aug-18 A | 05-Oct-18 A | 35 | 0 | 29 | 100% |  | Completed
ER6244LT | W220 | A10610 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-08-29 | 2018-08-29 | Complete TR Form and Upload Review of Off-Load Pressurised Refuelling Safety Case for Defuelling to CDMS | 29-Aug-18 A | 29-Aug-18 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A10620 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-08-29 | Review of Off-Load Pressurised Refuelling Safety Case for Defuelling Available | 29-Aug-18 A | 29-Aug-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A13390 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-06-29 | Optionnering for CR and N2 systems to meet shutdown and holddown requirements (HPB, HNB) | 31-Aug-18 A | 31-Aug-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A13400 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-06-29 | Optionnering for CR and N2 systems to meet shutdown and holddown requirements (HYA, HAR) | 31-Aug-18 A | 31-Aug-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A5350.EC | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-08-31 | Refuelling Cooling Assessment EAN available | 31-Aug-18 A | 31-Aug-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A1080 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-09-05 | 2018-09-25 | Produce draft NSRS (using BARRIER MODEL) (HPB, HNB) | 03-Sep-18 A | 24-Oct-18 A | 6 | 0 | 37 | 100% |  | Completed
ER6243LT | W200 | A10200 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-09-10 | 2018-09-28 | Produce draft NSRS (using BARRIER MODEL) (HYA, HAR) | 03-Sep-18 A | 24-Oct-18 A | 6 | 0 | 37 | 100% |  | Completed
ER6243LT | W200 | A15640 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-02-28 | 2018-04-26 | Review & Acceptance of Human Factor Integration Plan EAN (HPB, HNB) | 03-Sep-18 A | 20-Dec-18 A | 20 | 0 | 78 | 100% |  | Completed
ER6243LT | W200 | A15700 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-02-28 | 2018-04-26 | Review & Acceptance of Draft Human Factors Integration Plan EAN (HYA, HAR) | 03-Sep-18 A | 20-Dec-18 A | 20 | 0 | 78 | 100% |  | Completed
ER6243LT | W200 | A16620 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Thermal Hydraulics (MACE) - Updated Defuelling Dataset Issued for Technical Review | 03-Sep-18 A | 03-Sep-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16650 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | PCPV Ageing & Degradation - Complete TR form and upload to CDMS (HPB, HNB) | 03-Sep-18 A | 05-Sep-18 A | 3 | 0 | 3 | 100% |  | Completed
ER6244LT | W220 | A8630 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-09-03 | Initial Fault Studies and Risk Estimation Report available (HYA/HRA) | 03-Sep-18 A | 03-Sep-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A5200 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-09-04 | 2018-09-12 | Amec update and issue CO2 purity and decay heat report | 04-Sep-18 A | 12-Sep-18 A | 7 | 0 | 7 | 100% |  | Completed
ER6243LT | W200 | A11890 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-08-24 | 2017-08-31 | Thermal Hydraulics (MACE) - Thermal Hydraulics (MACE) Calculations Report Technical Review by SQEP (PH2) | 04-Sep-18 A | 17-Sep-18 A | 10 | 0 | 10 | 100% |  | Completed
ER6243LT | W200 | A16660 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | PCPV Ageing & Degradation - Engineering Substantiation Report Completed (HPB, HNB) | 05-Sep-18 A | 05-Sep-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16730 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Draft Support System Report (HPB, HNB) | 07-Sep-18 A | 31-Jan-19 A | 50 | 0 | 101 | 100% |  | Completed
ER6243LT | W200 | A16760 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Draft Support System Report (HYA, HAR) | 07-Sep-18 A | 22-Jul-19 A | 50 | 0 | 219 | 100% |  | Completed
ER6244LT | W220 | A5210 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-09-13 | 2018-09-26 | Complete TR form and upload CO2 purity and decay heat report to CDMS | 13-Sep-18 A | 26-Sep-18 A | 10 | 0 | 10 | 100% |  | Completed
ER6243LT | W200 | A16690 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | PCPV Ageing & Degradation - Complete TR form and upload to CDMS (HYA, HAR) | 18-Sep-18 A | 20-Sep-18 A | 3 | 0 | 2 | 100% |  | Completed
ER6243LT | W200 | A11900 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-09-01 | 2017-09-07 | Thermal Hydraulics (MACE) - Update and issue Defuelling Dataset (PH2) | 18-Sep-18 A | 27-Sep-18 A | 10 | 0 | 7 | 100% |  | Completed
ER6243LT | W200 | A16700 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | PCPV Ageing & Degradation - Engineering Substantiation Report Completed (HYA, HAR) | 20-Sep-18 A | 20-Sep-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A3080.E0 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-09-04 | Complete Optioneering Design of Safety Cases (HPB, HNB) | 21-Sep-18 A | 21-Sep-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.RCS.A290.EK | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-06-29 | RCS Basis of Design - Impact Assessment Report & C&I BoD for plant modifications Completed. (HPB, HNB) | 21-Sep-18 A | 21-Sep-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.RCS.A310.EK | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-06-29 | RCS Basis of Design - Impact Assessment Report & C&I BoD for plant modifications Completed. (HYA, HAR) | 21-Sep-18 A | 21-Sep-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A10410.E0 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-09-07 | Complete Optioneering Design of Safety Cases (HYA, HAR) | 21-Sep-18 A | 21-Sep-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A13150.C0 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-07-26 | Preferred Technical Strategy Endorsed by the Programme Board (HPB, HNB) | 21-Sep-18 A | 21-Sep-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A13160.C0 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-07-26 | Preferred Technical Strategy Endorsed by the Programme Board (HYA, HAR) | 21-Sep-18 A | 21-Sep-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16460 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-10-01 | Optioneering of the Defuelling Preparations Programme Completed | 21-Sep-18 A | 21-Sep-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11840 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-08-03 | 2017-08-09 | Thermal Hydraulics (MACE) - Update and issue Thermal Hydraulics (MACE) Draft Summary Document (PH1) | 24-Sep-18 A | 27-Sep-18 A | 10 | 0 | 3 | 100% |  | Completed
ER6243LT | W200 | A16290 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-05-24 | Thermal Hydraulics (MACE) - Calcs Spec & Model Development Report Completed (PH3)(Not Req'd 24.09.18 as per DS) | 24-Sep-18 A | 24-Sep-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16300 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-04-18 | Thermal Hydraulics (MACE) - Draft Calcs Spec & Model Development Report verified and issued for TR(PH3) | 24-Sep-18 A | 24-Sep-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16310 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-04-19 | 2018-05-02 | Thermal Hydraulics (MACE) - Calcs Spec & Model Development Report TR by SQEP (PH3)(Not Req'd 24.09.18 as per DS) | 24-Sep-18 A | 24-Sep-18 A | 10 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16320 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-05-03 | 2018-05-17 | Thermal Hydraulics (MACE) - Update and issue Calcs Spec & Model Development Report (PH3)(Not Req'd 24.09.18 as per DS) | 24-Sep-18 A | 24-Sep-18 A | 10 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16330 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-05-18 | 2018-05-24 | Thermal Hydraulics (MACE) - Complete TR form and upload to CDMS (PH3)(Not Req'd 24.09.18 as per DS) | 24-Sep-18 A | 24-Sep-18 A | 5 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16340 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-03-20 | 2018-04-18 | Thermal Hydraulics (MACE) - Develop (MACE) Calcs Spec & Model Development Report (PH3)(Not Req'd 24.09.18 as per DS) | 24-Sep-18 A | 24-Sep-18 A | 20 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A9640 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-09-25 | 2018-09-27 | Supplier update and issue Fuel Free Verification EAN | 25-Sep-18 A | 27-Sep-18 A | 3 | 0 | 2 | 100% |  | Completed
ER6244LT | W220 | A3080.E0 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-09-26 | Complete Optioneering Design of Safety Cases | 26-Sep-18 A | 26-Sep-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A5220.EC | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-09-26 | CO2 purity and decay heat report available | 26-Sep-18 A | 26-Sep-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15160 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-06-28 | Draft Mapping Optioneering Report Available for Review (HPB, HNB)(Not Required as per DS 27.09.18) | 27-Sep-18 A | 27-Sep-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15170 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-06-29 | 2018-08-31 | Review & Acceptance of Mapping Optioneering Report (HPB, HNB)(Not Required as per DS 27.09.18) | 27-Sep-18 A | 27-Sep-18 A | 10 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15400 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-06-28 | Draft Mapping Optioneering Report Available for Review (HYA, HAR) (Not Required as per DS 27.09.18) | 27-Sep-18 A | 27-Sep-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15410 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-06-29 | 2018-09-05 | Review & Acceptance of Mapping Optioneering Report (HYA, HAR) (Not Required as per DS 27.09.18) | 27-Sep-18 A | 27-Sep-18 A | 10 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A9750 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-09-27 | Draft Fuel Free Verification EAN verified and issued for technical review | 27-Sep-18 A | 27-Sep-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.OC.A550.EA | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-09-19 | Principles of Fuel Free Verification - Issue of the Report onto CDMS (HYA, HAR) | 28-Sep-18 A | 28-Sep-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A9650 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-09-28 | 2018-09-28 | Complete TR form and upload Fuel Free Verification EAN to CDMS | 28-Sep-18 A | 28-Sep-18 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A9760 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-09-28 | 2019-03-08 | Technical review of Fuel Free Verification EAN | 28-Sep-18 A | 08-Mar-19 A | 20 | 0 | 113 | 100% |  | Completed
ER6244LT | W220 | A9660 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-09-28 | Fuel Free Verification EAN available | 28-Sep-18 A | 28-Sep-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A1030 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-07-23 | 2018-07-23 | Appoint CO & CA (HPB, HNB) | 01-Oct-18 A | 01-Oct-18 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A1050.E0 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-04-19 | Gate EC1 completed EC 363701/364023 <NSRS SC Approach & Outline> (Cat 1 Milestone) (HPB, HNB) | 01-Oct-18 A | 01-Oct-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A1250 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-10-10 | 2018-10-16 | Hold project kick start meeting with Station & key suppliers (HPB, HNB) (Not Req'd until after Gate B) | 01-Oct-18 A | 01-Oct-18 A | 5 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A1240 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-09-26 | 2018-10-09 | Create EC Definition Document if not part of Project Definition Document (363701) (HPB, HNB) (See PDD) | 01-Oct-18 A | 01-Oct-18 A | 10 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A12580 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-10-15 | 2018-10-19 | Hold project kick start meeting with Station & key suppliers (HYA, HAR) | 01-Oct-18 A | 01-Oct-18 A | 5 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A12590 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-10-01 | 2018-10-12 | Create EC Definition Document if not part of Project Definition Document (363676) (HYA, HAR) | 01-Oct-18 A | 01-Oct-18 A | 10 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16380 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Draft Environmental Aspect/Impact & Waste Management Assessment Form (HPB, HNB) | 01-Oct-18 A | 02-Oct-18 A | 10 | 0 | 2 | 100% |  | Completed
ER6243LT | W200 | A16420 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Draft Environmental Aspect/Impact & Waste Management Assessment Form (HYA, HAR) | 01-Oct-18 A | 02-Oct-18 A | 10 | 0 | 2 | 100% |  | Completed
ER6244LT | W220 | A3220 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-10-01 | 2018-10-05 | Hold Case Conference as Appropriate | 01-Oct-18 A | 05-Oct-18 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A10915.EJ | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-10-01 | Draft Dropped FPU impact on Core Support Structure Report (HYA and HRA) verified and issued for technical review | 01-Oct-18 A | 01-Oct-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A1070 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | CA to agree with CO format of the safety case (HPB, HNB) | 02-Oct-18 A | 03-Oct-18 A | 2 | 0 | 2 | 100% |  | Completed
ER6244LT | W220 | A10920 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-10-02 | 2018-10-18 | Technical review of Dropped FPU impact on Core Support Structure Report (HYA and HRA) | 02-Oct-18 A | 18-Oct-18 A | 13 | 0 | 13 | 100% |  | Completed
ER6244LT | W220 | A11030 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-10-05 | Draft Updated EoG Initial Fault Studies and Risk Estimation Report Verified and Issued for Technical Review | 05-Oct-18 A | 05-Oct-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A11040 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-10-08 | 2018-10-18 | Technical Review of Updated EoG Initial Fault Studies and Risk Estimation Report | 08-Oct-18 A | 18-Oct-18 A | 9 | 0 | 9 | 100% |  | Completed
ER6243LT | W200 | A16790 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Issue Draft Station resourced Plans for Review | 10-Oct-18 A | 10-Oct-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16860 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Thermal Hydraulics (MACE) - Pre Job Brief | 10-Oct-18 A | 10-Oct-18 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A16390 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | GEM & Case Officer review of Draft Environmental Aspect/Impact & Waste Management Assessment Form (HPB, HNB) | 11-Oct-18 A | 23-Nov-18 A | 10 | 0 | 31 | 100% |  | Completed
ER6243LT | W200 | A16430 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | GEM & Case Officer review of Draft Environmental Aspect/Impact & Waste Management Assessment Form (HYA, HAR) | 11-Oct-18 A | 23-Nov-18 A | 10 | 0 | 31 | 100% |  | Completed
ER6243LT | W200 | A16870 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Thermal Hydraulics (MACE) - Generate Requested Data using the MACE Model | 11-Oct-18 A | 23-Oct-18 A | 10 | 0 | 9 | 100% |  | Completed
ER6244LT | W220 | A11050 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-10-19 | 2018-10-26 | Supplier update and issue Updated EoG Initial Fault Studies and Risk Estimation Report | 19-Oct-18 A | 26-Oct-18 A | 6 | 0 | 6 | 100% |  | Completed
ER6378LT | W222 | W222.A1090 | HRA Fuel Handling Essential Safety Case | 2018-10-19 | 2018-11-05 | Station comments on NSRS | 19-Oct-18 A | 05-Nov-18 A | 12 | 0 | 12 | 100% |  | Completed
ER6378LT | W222 | W222.A1100 | HRA Fuel Handling Essential Safety Case | 2018-10-19 | 2018-11-05 | DA (Peer) comments on NSRS | 19-Oct-18 A | 05-Nov-18 A | 12 | 0 | 12 | 100% |  | Completed
ER6378LT | W222 | W222.A3230 | HRA Fuel Handling Essential Safety Case | 2018-10-19 | 2019-03-29 | INA comments on NSRS | 19-Oct-18 A | 29-Mar-19 A | 113 | 0 | 112 | 100% |  | Completed
ER6378LT | W222 | W222.A8140 | HRA Fuel Handling Essential Safety Case |  | 2018-10-19 | Draft NSRS Produced for HRA and HYA (using BARRIER model) | 19-Oct-18 A | 19-Oct-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A8140 | HYA Fuel Handling Essential Safety Case |  | 2018-10-19 | Draft NSRS Produced for HYA and HYA (using BARRIER model) | 19-Oct-18 A | 19-Oct-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A3230 | HYA Fuel Handling Essential Safety Case | 2018-10-19 | 2019-03-29 | INA comments on NSRS | 19-Oct-18 A | 29-Mar-19 A | 113 | 0 | 112 | 100% |  | Completed
ER6650LT | W226 | W226.A1100 | HYA Fuel Handling Essential Safety Case | 2018-10-19 | 2018-11-05 | DA (Peer) comments on NSRS | 19-Oct-18 A | 05-Nov-18 A | 12 | 0 | 12 | 100% |  | Completed
ER6650LT | W226 | W226.A1090 | HYA Fuel Handling Essential Safety Case | 2018-10-19 | 2018-11-05 | Station comments on NSRS | 19-Oct-18 A | 05-Nov-18 A | 12 | 0 | 12 | 100% |  | Completed
ER6378LT | W222 | W222.A27190 | HRA Fuel Handling Essential Safety Case | 2018-10-19 | 2024-05-21 | Summary for HRA Fuel Handling Essential Safety Case W222 | 19-Oct-18 A | 2025-03-25 | 1 | 17 | 1625 | 0% | 4 | In Progress
ER6650LT | W226 | W226.A1000 | HYA Fuel Handling Essential Safety Case | 2018-10-19 | 2024-05-21 | Summary for HYA Fuel Handling Essential Safety Case | 19-Oct-18 A | 2025-03-25 | 1 | 17 | 1625 | 0% | 4 | In Progress
ER6244LT | W220 | A8140 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-10-19 | Draft NSRS Produced for HPB and HNB (using BARRIER model) | 19-Oct-18 A | 19-Oct-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A8150 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-10-19 | Draft NSRS Produced for HYA and HRA (using BARRIER model) | 19-Oct-18 A | 19-Oct-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A8160.E0 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-10-19 | Draft NSRS Produced for HPB and HNB (using BARRIER model) | 19-Oct-18 A | 19-Oct-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A8170.E0 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-10-19 | Draft NSRS Produced for HYA and HRA (using BARRIER model) | 19-Oct-18 A | 19-Oct-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A1090 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-10-22 | 2018-12-17 | Station comments on NSRS | 22-Oct-18 A | 17-Dec-18 A | 15 | 0 | 41 | 100% |  | Completed
ER6244LT | W220 | A1100 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-10-22 | 2018-12-17 | DA (Peer) comments on NSRS | 22-Oct-18 A | 17-Dec-18 A | 15 | 0 | 41 | 100% |  | Completed
ER6244LT | W220 | A3240 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-10-22 | 2019-05-01 | Incorporate INA, Station, DA (peer) comments | 22-Oct-18 A | 29-May-19 A | 15 | 0 | 150 | 100% |  | Completed
ER6244LT | W220 | A3230 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-10-22 | 2019-03-29 | INA comments on NSRS | 22-Oct-18 A | 29-Mar-19 A | 15 | 0 | 112 | 100% |  | Completed
ER6244LT | W220 | A3340 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-10-22 | 2018-12-17 | Station comments on NSRS | 22-Oct-18 A | 17-Dec-18 A | 50 | 0 | 41 | 100% |  | Completed
ER6244LT | W220 | A3350 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-10-22 | 2018-12-17 | DA (Peer) comments on NSRS | 22-Oct-18 A | 17-Dec-18 A | 50 | 0 | 41 | 100% |  | Completed
ER6244LT | W220 | A3410 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-10-22 | 2019-03-29 | INA comments on NSRS | 22-Oct-18 A | 29-Mar-19 A | 50 | 0 | 112 | 100% |  | Completed
ER6244LT | W220 | A10180 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-10-22 | 2018-10-26 | Supplier update and issue Review of Rad Cons for Lower Decay Heat for Input into PSA | 22-Oct-18 A | 26-Oct-18 A | 5 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | A16880 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Thermal Hydraulics (MACE) - Interim Progress Meeting | 23-Oct-18 A | 23-Oct-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A13030.E0 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-08-20 | Draft NSRS Produced Ready for Review and Approval (using BARRIER MODEL) (HPB, HNB) | 24-Oct-18 A | 24-Oct-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A13040.E0 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-08-20 | Draft NSRS Produced Ready for Review and Approval(using BARRIER MODEL) (HYA, HAR) | 24-Oct-18 A | 24-Oct-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16890 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Thermal Hydraulics (MACE) - Update the Analysis and Produce QA Grade 2 Technical Note | 24-Oct-18 A | 09-Nov-18 A | 10 | 0 | 12 | 100% |  | Completed
ER6243LT | W200 | A1090 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-10-10 | 2018-10-23 | Station comments on NSRS (HPB, HNB) | 25-Oct-18 A | 03-Dec-18 A | 10 | 0 | 27 | 100% |  | Completed
ER6243LT | W200 | A1100 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-10-01 | 2018-10-12 | DA (Peer) comments on NSRS (HPB, HNB) | 25-Oct-18 A | 14-Nov-18 A | 10 | 0 | 14 | 100% |  | Completed
ER6244LT | W220 | A11060 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-10-26 | 2018-10-26 | Complete TR form and upload Updated EoG Initial Fault Studies and Risk Estimation Report to CDMS | 26-Oct-18 A | 26-Oct-18 A | 3 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A3060.C0 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-10-26 | Develop HPB HNB Detailed Costing and Schedules for Future Phases (Post Gate B) | 26-Oct-18 A | 26-Oct-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A11070 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-10-26 | Updated EoG Initial Fault Studies and Risk Estimation Report Available | 26-Oct-18 A | 26-Oct-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A10300 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-07-30 | 2018-07-30 | Appoint CO & CA (HYA, HAR) | 29-Oct-18 A | 29-Oct-18 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A10350.E0 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-04-19 | Gate EC1 completed EC 363676/363682 <NSRS SC Approach & Outline> (Cat 1 Milestone) (HYA, HAR) | 29-Oct-18 A | 29-Oct-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A10190 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-10-29 | 2019-01-18 | Complete TR form and upload Review of Rad Cons for Lower Decay Heat for Input into PSA to CDMS | 29-Oct-18 A | 18-Jan-19 A | 4 | 0 | 57 | 100% |  | Completed
ER6243LT | W200 | A10220 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-10-01 | 2018-10-12 | DA (Peer) comments on NSRS (HYA, HAR) | 01-Nov-18 A | 14-Nov-18 A | 10 | 0 | 10 | 100% |  | Completed
ER6243LT | W200 | A11850 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-08-10 | 2017-08-16 | Thermal Hydraulics (MACE) - Complete TR form and upload to CDMS (PH1) | 01-Nov-18 A | 07-Nov-18 A | 5 | 0 | 4 | 100% |  | Completed
ER6243LT | W200 | A11910 | REGION 1 Reactors Shutdown Safety Cases Programme | 2017-09-08 | 2017-09-14 | Thermal Hydraulics (MACE) - Complete TR form and upload to CDMS (PH2) | 01-Nov-18 A | 07-Nov-18 A | 5 | 0 | 4 | 100% |  | Completed
ER6243LT | W200 | A10210 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-10-10 | 2018-10-23 | Station comments on NSRS (HYA, HAR) | 05-Nov-18 A | 03-Dec-18 A | 10 | 0 | 20 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1020 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 05-Nov-18 A | 07-Dec-18 A | 5 | 0 | 24 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1030 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 05-Nov-18 A | 07-Dec-18 A | 5 | 0 | 24 | 100% |  | Completed
ER6243LT | W200 | A11920 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-09-14 | Thermal Hydraulics (MACE) - Defuelling Dataset to Support Optioneering / Decision Making Completed (PH2) | 07-Nov-18 A | 07-Nov-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11860 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2017-08-16 | Thermal Hydraulics (MACE) - Thermal Hydraulics (MACE) Draft Summary Document Completed for (PH1) | 07-Nov-18 A | 07-Nov-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A17220 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Thermal Hydraulics (MACE) - Update the Analysis and Produce QA Grade 2 TSA Verification | 12-Nov-18 A | 10-Dec-18 A | 1 | 0 | 20 | 100% |  | Completed
ER6243LT | W200 | A16810 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | EDF Review / Verify Station Plans (HPB) (Transfer to W282 Workpack) | 19-Nov-18 A | 05-Mar-19 A | 10 | 0 | 73 | 100% |  | Completed
ER6243LT | W200 | A17190 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | EDF Review / Verify Station Plans (HNB) (Transfer to W282 Workpack) | 19-Nov-18 A | 05-Mar-19 A | 10 | 0 | 73 | 100% |  | Completed
ER6243LT | W200 | A10110 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-10-01 | 2018-10-12 | SRD comments on NSRS (HPB, HNB) | 03-Dec-18 A | 01-Apr-19 A | 10 | 0 | 83 | 100% |  | Completed
ER6243LT | W200 | A10330 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-10-01 | 2018-10-12 | SRD comments on NSRS (HYA, HAR) | 03-Dec-18 A | 01-Apr-19 A | 10 | 0 | 82 | 100% |  | Completed
ER6244LT | W220 | A4490 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-12-03 | 2018-12-31 | P20.01.01.22 - Decommissioning Phase | 03-Dec-18 A | 31-Dec-18 A | 19 | 0 | 19 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1250 | HNB Reactors Shutdown Essential Safety Cases | 2018-12-03 | 2018-12-04 | Confirm Objectives to be Delivered at Gate B | 03-Dec-18 A | 04-Dec-18 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13000 | HNB Reactors Shutdown Essential Safety Cases | 2018-12-03 |  | Phase 2 Accelerated Start [FEEDS TO SUMMARY SCHEDULE] | 03-Dec-18 A | 03-Dec-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17320 | HNB Reactors Shutdown Essential Safety Cases | 2018-12-03 | 2020-02-29 | Actuals (PS-29-Feb-2020) | 03-Dec-18 A | 02-Mar-20 A | 314 | 0 | 314 | 100% |  | Completed
ER6370LT | W201 | A1010 | HNB Reactors Shutdown Essential Safety Cases |  |  | Summary for HNB Reactors Shutdown Essential Safety Cases W201 | 03-Dec-18 A | 23-Aug-22 A | 1 | 0 | 939 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1260 | HNB Reactors Shutdown Essential Safety Cases | 2018-12-05 | 2018-12-05 | Initial high level scope of programme | 05-Dec-18 A | 05-Dec-18 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1020 | HNB Reactors Shutdown Essential Safety Cases | 2018-12-06 | 2018-12-07 | Define Project Control Structures (WBS/CBS/OBS/PBS) | 06-Dec-18 A | 07-Dec-18 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1110 | HNB Reactors Shutdown Essential Safety Cases | 2018-12-06 | 2018-12-10 | Prepare Draft Project Definition Document (PDD) | 06-Dec-18 A | 10-Dec-18 A | 3 | 0 | 3 | 100% |  | Completed
ER6243LT | W200 | A10140 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-11-08 | 2018-11-21 | Station agree NSRS (HPB, HNB) | 10-Dec-18 A | 11-Dec-18 A | 10 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A10240 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-11-09 | 2018-11-22 | Station agree NSRS (HYA, HAR) | 10-Dec-18 A | 11-Dec-18 A | 10 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1040 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Ensure Alignment of Schedule & Estimate | 10-Dec-18 A | 10-Dec-18 A | 2 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1050 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Hold Risk Workshop | 10-Dec-18 A | 10-Dec-18 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A16900 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Thermal Hydraulics (MACE) - Submit QA Grade 2 Technical Note for Technical Review | 10-Dec-18 A | 10-Dec-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A3060.C0 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-09-28 | Develop Detailed Costing and Schedules for Future Phases (Post Gate B) | 11-Dec-18 A | 11-Dec-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1060 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Complete Risk Log with Estimates | 11-Dec-18 A | 11-Dec-18 A | 2 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1070 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Update Schedule/Estimate from Risk Log & Add Provisions | 11-Dec-18 A | 11-Dec-18 A | 2 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1080 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Add Data to IRM Paper | 11-Dec-18 A | 11-Dec-18 A | 2 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1090 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | PCL Validate & Approve Baseline Package for PRC Submission | 11-Dec-18 A | 11-Dec-18 A | 3 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1030 | HNB Reactors Shutdown Essential Safety Cases | 2018-12-13 | 2018-12-14 | Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 13-Dec-18 A | 14-Dec-18 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1040 | HNB Reactors Shutdown Essential Safety Cases | 2018-12-13 | 2018-12-14 | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 13-Dec-18 A | 14-Dec-18 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1270 | HNB Reactors Shutdown Essential Safety Cases | 2018-12-13 | 2018-12-14 | Workshop to agree scope, effort and links | 13-Dec-18 A | 14-Dec-18 A | 2 | 0 | 2 | 100% |  | Completed
ER6243LT | W200 | A3020.C0 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-09-28 | Confirm scope post gate 2 | 14-Dec-18 A | 14-Dec-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1100 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Gate B PRC Paper Submission | 14-Dec-18 A | 14-Dec-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A10110 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-12-17 | 2019-02-15 | Supplier update and issue Dropped FPU RadCons Analysis of Core Support Plate Failure | 17-Dec-18 A | 15-Feb-19 A | 14 | 0 | 42 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1050 | HNB Reactors Shutdown Essential Safety Cases | 2018-12-17 | 2018-12-18 | Ensure Alignment of Schedule & Estimate | 17-Dec-18 A | 18-Dec-18 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1060 | HNB Reactors Shutdown Essential Safety Cases | 2018-12-17 | 2018-12-17 | Hold Risk Workshop | 17-Dec-18 A | 17-Dec-18 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A10300 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-12-17 | Draft Review of Plant Requirements for Defuelling verified and issued for technical review | 17-Dec-18 A | 17-Dec-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A10370 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2018-12-17 | Draft Review of Safety Case Limits & LOLER Inspection Requirements verified and issued for technical review | 17-Dec-18 A | 17-Dec-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A11010 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-04-27 | 2018-04-30 | PCPV Integrity - Complete TR form and upload to CDMS (HYA, HAR) | 18-Dec-18 A | 19-Mar-19 A | 10 | 0 | 62 | 100% |  | Completed
ER6243LT | W200 | A10950 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-04-27 | 2018-04-30 | PCPV Integrity - Complete TR form and upload to CDMS (HPB, HNB) | 18-Dec-18 A | 19-Mar-19 A | 10 | 0 | 62 | 100% |  | Completed
ER6244LT | W220 | A10380 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2018-12-18 | 2019-01-24 | Technical review of Review of Safety Case Limits & LOLER Inspection Requirements | 18-Dec-18 A | 24-Jan-19 A | 30 | 0 | 25 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1070 | HNB Reactors Shutdown Essential Safety Cases | 2018-12-18 | 2018-12-19 | Complete Risk Log with Estimates | 18-Dec-18 A | 19-Dec-18 A | 2 | 0 | 2 | 100% |  | Completed
ER6243LT | W200 | A15650 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-09-21 | Human Factor Integration Plan EAN Issued to CDMS (HPB, HNB) | 20-Dec-18 A | 20-Dec-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A15710 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-09-25 | Draft Human Factors Integration Plan EAN Issued to CDMS (HYA, HAR) | 20-Dec-18 A | 20-Dec-18 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1080 | HNB Reactors Shutdown Essential Safety Cases | 2018-12-20 | 2018-12-21 | Update Schedule/Estimate from Risk Log & Add Provisions | 20-Dec-18 A | 21-Dec-18 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1090 | HNB Reactors Shutdown Essential Safety Cases | 2018-12-24 | 2018-12-27 | Add Data to IRM Paper | 24-Dec-18 A | 27-Dec-18 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1100 | HNB Reactors Shutdown Essential Safety Cases | 2018-12-28 | 2019-01-02 | PCL Validate & Approve Baseline Package for PRC Submission | 28-Dec-18 A | 02-Jan-19 A | 3 | 0 | 3 | 100% |  | Completed
ER6243LT | W200 | A16440 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Issue Environmental Aspect/Impact & Waste Management Assessment Form (HYA, HAR) | 02-Jan-19 A | 16-Jan-19 A | 3 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7690 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-02 | 2019-02-13 | Safety Case Strategy Development Meetings | 02-Jan-19 A | 13-Feb-19 A | 31 | 0 | 31 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10515 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-02 |  | Start of Environmental Permitting and Permissioing Scoping and Stakeholder Engagement | 02-Jan-19 A | 02-Jan-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10710 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-02 | 2019-11-29 | Scoping of Implementation ECs B-C | 02-Jan-19 A | 29-Nov-19 A | 233 | 0 | 232 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10720 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-02 | 2019-01-31 | Prepare Current Code Applicability Range | 02-Jan-19 A | 31-Jan-19 A | 22 | 0 | 22 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10800 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-02 | 2019-01-31 | Prepare Scope Codes and Methods Options and Validation | 02-Jan-19 A | 31-Jan-19 A | 22 | 0 | 22 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10990 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-02 | 2019-01-15 | Prepare SDM Assumptions Document Draft Report | 02-Jan-19 A | 15-Jan-19 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10715 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-02 | 2019-04-30 | Current Code Applicability Range Summary | 02-Jan-19 A | 30-Apr-19 A | 82 | 0 | 82 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10795 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-02 | 2019-03-15 | Scope Codes and Methods Options and Validation Summary | 02-Jan-19 A | 15-Mar-19 A | 53 | 0 | 53 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10985 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-02 | 2019-06-03 | SDM Assumptions Document Summary | 02-Jan-19 A | 03-Jun-19 A | 104 | 0 | 104 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11250 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-02 | 2019-02-07 | Prepare Stress Test Draft EAN | 02-Jan-19 A | 07-Feb-19 A | 27 | 0 | 26 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11245 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-02 | 2019-04-12 | Stress Test EAN Summary | 02-Jan-19 A | 12-Apr-19 A | 72 | 0 | 72 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16010 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-02 | 2019-03-15 | Prepare Stress Test Draft EAN | 02-Jan-19 A | 15-Mar-19 A | 53 | 0 | 52 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16000 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-02 | 2019-04-12 | ALARP Framework Support for ALARP/BAT/BPM Report Summary | 02-Jan-19 A | 12-Apr-19 A | 72 | 0 | 72 | 100% |  | Completed
ER6244LT | W220 | A3070.C0 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2019-01-02 | [PR KDM] Identify and De-risk Major Threats to the Strategy | 02-Jan-19 A | 02-Jan-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16400 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Issue Environmental Aspect/Impact & Waste Management Assessment Form (HPB, HNB) | 02-Jan-19 A | 16-Jan-19 A | 3 | 0 | 10 | 100% |  | Completed
ER6244LT | W220 | A10400 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2019-01-02 | 2019-01-30 | Complete TR form and upload Review of Safety Case Limits & LOLER Inspection Requirements to CDMS | 02-Jan-19 A | 30-Jan-19 A | 21 | 0 | 21 | 100% |  | Completed
ER6244LT | W220 | A3630 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2019-01-02 | [PR KDM] Draft Failed Fuel Gas Sampling EAN available for Technical Review | 02-Jan-19 A | 02-Jan-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13010 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-02 |  | Phase 2 Project Start (FEEDS TO SUMMARY SCHEDULE) | 02-Jan-19 A | 02-Jan-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2270 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-02 | 2020-07-17 | Phase 2 Project Management - Gate B - C | 02-Jan-19 A | 14-Oct-20 A | 399 | 0 | 452 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1530 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-02 |  | Commence Supporting References or Supporting EC's (HNB) | 02-Jan-19 A | 02-Jan-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7240 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-02 | 2019-01-31 | Prepare Code Validation from Operational Reactor Draft Report | 02-Jan-19 A | 31-Jan-19 A | 22 | 0 | 22 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10520 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-02 | 2019-11-15 | Environmental Permitting and Permissioing Scoping and Stakeholder Engagement | 02-Jan-19 A | 15-Nov-19 A | 223 | 0 | 222 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7235 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-02 | 2019-06-28 | SDM- Code Validation from Operational Reactor Summary | 02-Jan-19 A | 28-Jun-19 A | 123 | 0 | 123 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1000 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-01-02 | Gate B PRC Paper Submission | 02-Jan-19 A | 02-Jan-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1110 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | PRC Members Review IRM Documentation | 03-Jan-19 A | 09-Jan-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1150 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-03 | 2019-01-09 | PRC Members Review IRM Documentation | 03-Jan-19 A | 09-Jan-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13150 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-04 | 2019-01-31 | Develop Defuelling Dataset Part 1 - Accelerated Work | 04-Jan-19 A | 31-Jan-19 A | 20 | 0 | 19 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13210 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-04 | 2019-02-14 | Prepare ALARP Strategy Document Draft EAN | 04-Jan-19 A | 14-Feb-19 A | 30 | 0 | 29 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13200 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-04 | 2019-04-23 | ALARP Strategy Document Summary | 04-Jan-19 A | 23-Apr-19 A | 75 | 0 | 75 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1120 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Hold PRC Meeting | 10-Jan-19 A | 10-Jan-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1140 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Modify Estimate, Schedule & Risk Log as Required | 10-Jan-19 A | 10-Jan-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1120 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-10 | 2019-01-10 | Hold PRC Meeting | 10-Jan-19 A | 10-Jan-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1130 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Gate B PRC Paper Approval | 10-Jan-19 A | 10-Jan-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1200 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-01-10 | Gate B PRC Paper Approval | 10-Jan-19 A | 10-Jan-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1150 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Modify IRM Paper as Required | 11-Jan-19 A | 11-Jan-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1130 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-11 | 2019-01-11 | Modify Estimate, Schedule & Risk Log as Required | 11-Jan-19 A | 11-Jan-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1140 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-14 | 2019-01-14 | Modify IRM Paper as Required | 14-Jan-19 A | 14-Jan-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11000 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-01-15 | Issued SDM Assumptions Document Draft Report to EDF for Review. | 15-Jan-19 A | 15-Jan-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1010 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-01-15 | Gate B MS PRC Paper Submission | 15-Jan-19 A | 15-Jan-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1170 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-15 | 2019-01-15 | Modify Estimate, Schedule, Cost Tool & Risk Log as Required | 15-Jan-19 A | 15-Jan-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1180 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-15 | 2019-01-21 | Update Cost Management Tool | 15-Jan-19 A | 21-Jan-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1190 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-15 | 2019-01-23 | IRM Members Review IRM Documentation | 15-Jan-19 A | 23-Jan-19 A | 7 | 0 | 7 | 100% |  | Completed
ER6243LT | W200 | A16410 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Environmental Aspect/Impact & Waste Management Assessment Form Complete (HPB, HNB) | 16-Jan-19 A | 16-Jan-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16450 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Environmental Aspect/Impact & Waste Management Assessment Form Complete (HYA, HAR) | 16-Jan-19 A | 16-Jan-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7450 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-16 | 2019-04-30 | Prepare Flux Detection Scoping Draft Report | 16-Jan-19 A | 30-Apr-19 A | 73 | 0 | 72 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11010 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-16 | 2019-03-04 | SDM Assumptions Document Draft Report Reviewed by EDF SQEP | 16-Jan-19 A | 04-Mar-19 A | 34 | 0 | 33 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7445 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-16 | 2019-07-19 | Flux Detection Scoping Summary | 16-Jan-19 A | 19-Jul-19 A | 128 | 0 | 128 | 100% |  | Completed
ER6244LT | W220 | A1670.C0 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2019-01-16 | [PR KDM] Gate B for HPB HNB Station Fuel Handling Safety Case Programme | 16-Jan-19 A | 16-Jan-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13380 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-18 | 2019-01-24 | Safety Rod Insertion Scoping - Draft and issue RFS | 18-Jan-19 A | 24-Jan-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13375 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-18 | 2019-05-17 | RFS - Safety Rod Insertion Scoping Summary | 18-Jan-19 A | 17-May-19 A | 83 | 0 | 83 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13580 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-18 | 2019-02-28 | Scope Additional SDM Calcs - Draft and issue RFS | 18-Jan-19 A | 28-Feb-19 A | 30 | 0 | 29 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13575 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-18 | 2019-02-28 | RFS - Scope Additional SDM Calcs Summary | 18-Jan-19 A | 28-Feb-19 A | 30 | 0 | 30 | 100% |  | Completed
ER6244LT | W220 | A10200 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2019-01-18 | [KDM] Review of Rad Cons for Lower Decay Heat for Input into PSA available | 18-Jan-19 A | 18-Jan-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A3300 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2019-01-23 | 2019-01-23 | NSRS Presented to NSC (for complex CAT 1 cases) | 23-Jan-19 A | 23-Jan-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A3300 | HRA Fuel Handling Essential Safety Case | 2019-01-23 | 2019-01-23 | NSRS Presented to NSC (for complex CAT 1 cases) | 23-Jan-19 A | 23-Jan-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A3300 | HYA Fuel Handling Essential Safety Case | 2019-01-23 | 2019-01-23 | NSRS Presented to NSC (for complex CAT 1 cases) | 23-Jan-19 A | 23-Jan-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13390 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-25 | 2019-02-07 | Safety Rod Insertion Scoping - Supplier prepare and issue Offer | 25-Jan-19 A | 07-Feb-19 A | 10 | 0 | 10 | 100% |  | Completed
ER6244LT | W220 | A10390 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2019-01-25 | 2019-01-31 | Supplier update and issue Review of Safety Case Limits & LOLER Inspection Requirements | 25-Jan-19 A | 31-Jan-19 A | 4 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4920 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-28 | 2019-03-04 | Prepare C&I Review Specification | 28-Jan-19 A | 04-Mar-19 A | 26 | 0 | 25 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4915 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-28 | 2019-04-12 | C&I Review Summary | 28-Jan-19 A | 12-Apr-19 A | 54 | 0 | 54 | 100% |  | Completed
ER6243LT | W200 | A16150 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-09-07 | Support System Report Issued to CDMS (HPB, HNB) | 31-Jan-19 A | 31-Jan-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16740 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-10-08 | 2018-10-09 | Support System Report Review and Acceptance (HPB, HNB) | 31-Jan-19 A | 31-Jan-19 A | 10 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3640 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-31 | 2019-04-15 | Develop Defuelling Dataset Part 1 | 31-Jan-19 A | 15-Apr-19 A | 53 | 0 | 52 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7950 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-01-31 | MACE Defuelling Dataset Specification Completed (FNC Summary Report) | 31-Jan-19 A | 31-Jan-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3635 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-31 | 2019-04-15 | Develop Defuelling Dataset Part 1 Summary | 31-Jan-19 A | 15-Apr-19 A | 52 | 0 | 52 | 100% |  | Completed
ER6244LT | W220 | A10410 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2019-01-31 | [KDM] Review of Safety Case Limits & LOLER Inspection Requirements available | 31-Jan-19 A | 31-Jan-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7250 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-01-31 | Issued Code Validation from Operational Reactor Draft Report to EDF for Review. | 31-Jan-19 A | 31-Jan-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8360 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-01 | 2019-02-22 | Prepare Pressure Boundary Seals Specification | 01-Feb-19 A | 22-Feb-19 A | 16 | 0 | 15 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10730 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-01 | 2019-02-07 | Current Code Applicability Range Verified by TSA | 01-Feb-19 A | 07-Feb-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10810 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-01 | 2019-02-07 | Scope Codes and Methods Options and Validation Verified by TSA | 01-Feb-19 A | 07-Feb-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8355 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-01 | 2019-05-31 | Pressure Boundary Seals Specification Summary | 01-Feb-19 A | 31-May-19 A | 81 | 0 | 81 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13160 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-01 | 2019-03-15 | Validate Model and Datasets Part 1 - Accelerated Work | 01-Feb-19 A | 15-Mar-19 A | 31 | 0 | 30 | 100% |  | Completed
ER6243LT | W200 | A16910 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Thermal Hydraulics (MACE) - QA Grade 2 Technical Note TR by EDF SQEP (Not Req'd as per DS notes 26.02.18) | 01-Feb-19 A | 28-Feb-19 A | 15 | 0 | 19 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3480 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-04 | 2019-03-15 | Verify MACE Code v3.2.2 Defuelling Prototype Model | 04-Feb-19 A | 15-Mar-19 A | 30 | 0 | 29 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13300 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-04 | 2019-03-01 | Prepare Implementation Strategy Document Draft EAN | 04-Feb-19 A | 01-Mar-19 A | 20 | 0 | 19 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13290 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-04 | 2019-05-31 | Implementation Strategy Document Summary | 04-Feb-19 A | 31-May-19 A | 80 | 0 | 80 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13830 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-05 | 2019-03-06 | Shutdown Margin Head Document - Draft and issue RFS(Call Off Task Sheet) | 05-Feb-19 A | 06-Mar-19 A | 22 | 0 | 21 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13825 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-05 | 2019-07-17 | RFS - Shutdown Margin Head Document Summary | 05-Feb-19 A | 17-Jul-19 A | 113 | 0 | 113 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10740 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-02-07 | Verified Current Code Applicability Range Issued to EDF for Technical Review. | 07-Feb-19 A | 07-Feb-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10820 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-02-07 | Verified Scope Codes and Methods Options and Validation Issued to EDF for Technical Review. | 07-Feb-19 A | 07-Feb-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10750 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-08 | 2019-03-25 | Current Code Applicability Range Technically Reviewed by EDF SQEP | 08-Feb-19 A | 25-Mar-19 A | 32 | 0 | 31 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10830 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-08 | 2019-03-01 | Scope Codes and Methods Options and Validation Technically Reviewed by EDF SQEP | 08-Feb-19 A | 01-Mar-19 A | 16 | 0 | 15 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13400 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-08 | 2019-02-14 | Safety Rod Insertion Scoping - Review Offer, prepare and issue CI | 08-Feb-19 A | 14-Feb-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1160 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Gate B MS PRC Paper Submission | 12-Feb-19 A | 12-Feb-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1170 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Update Cost Management Tool | 12-Feb-19 A | 18-Feb-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1180 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | IRM Members Review IRM Documentation | 12-Feb-19 A | 18-Feb-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13220 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-15 | 2019-04-05 | ALARP Strategy Document Draft EAN Verified by TSA | 15-Feb-19 A | 05-Apr-19 A | 36 | 0 | 35 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13410 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-15 | 2019-02-28 | Safety Rod Insertion Scoping - Supplier mobilisation time | 15-Feb-19 A | 28-Feb-19 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13480 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-15 | 2019-02-21 | SDM Assessments with Uncertainties - Draft and issue RFS | 15-Feb-19 A | 21-Feb-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13475 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-15 | 2019-04-29 | RFS - SDM Assessments with Uncertainties Summary | 15-Feb-19 A | 29-Apr-19 A | 50 | 0 | 50 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7305 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-18 | 2020-02-07 | DNB Commissiong Core Validation Summary | 18-Feb-19 A | 07-Feb-20 A | 246 | 0 | 246 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7340 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-18 | 2019-03-01 | Prepare DNB Commissiong Core Validation Specification | 18-Feb-19 A | 01-Mar-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15940 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-18 | 2019-02-22 | Structures and Equipment Integrity - Draft and issue RFS | 18-Feb-19 A | 22-Feb-19 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15935 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-18 | 2019-04-19 | RFS - Structures and Equipment Integrity Summary | 18-Feb-19 A | 19-Apr-19 A | 45 | 0 | 44 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15990 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-18 | 2019-04-12 | Prepare Timeline for Technical Specification updates for defuelling | 18-Feb-19 A | 12-Apr-19 A | 40 | 0 | 39 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15985 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-18 | 2019-04-12 | Timeline for Technical Specification updates for defuelling Summary | 18-Feb-19 A | 12-Apr-19 A | 39 | 0 | 39 | 100% |  | Completed
ER6244LT | W220 | A10120 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2019-02-18 | 2019-02-28 | Complete TR form and upload Dropped FPU RadCons Analysis of Core Support Plate Failure to CDMS | 18-Feb-19 A | 28-Feb-19 A | 9 | 0 | 9 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1190 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Hold MS PRC | 20-Feb-19 A | 20-Feb-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1160 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-20 | 2019-02-20 | Hold MS PRC | 20-Feb-19 A | 20-Feb-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A16520 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-10-09 | Gate B MS PRC Approval | 20-Feb-19 A | 20-Feb-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1210 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-02-20 | Gate B MS PRC Approval | 20-Feb-19 A | 20-Feb-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A13380 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-09-05 | Mapping Optioneering Report Issued (HYA, HAR) | 21-Feb-19 A | 21-Feb-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1200 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Modify Estimate, Schedule, Cost Tool & Risk Log as Required | 21-Feb-19 A | 26-Feb-19 A | 1 | 0 | 3 | 100% |  | Completed
ER6243LT | W200 | A13270 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-08-31 | Mapping Optioneering Report Issued (HPB, HNB) | 21-Feb-19 A | 21-Feb-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8370 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-02-22 | Issue Pressure Boundary Seals Specification to EDF Review. | 22-Feb-19 A | 22-Feb-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13490 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-22 | 2019-03-07 | SDM Assessments with Uncertainties - Supplier prepare and issue Offer | 22-Feb-19 A | 07-Mar-19 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8380 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-25 | 2019-03-08 | Pressure Boundary Seals Specification Reviewed by EDF SQEP | 25-Feb-19 A | 08-Mar-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15950 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-25 | 2019-04-12 | Structures and Equipment Integrity - Supplier prepare and issue Offer | 25-Feb-19 A | 12-Apr-19 A | 35 | 0 | 34 | 100% |  | Completed
ER6243LT | W200 | A16920 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Thermal Hydraulics (MACE) - TSA Address TR Comments (Not Req'd as per DS notes 26.02.18) | 28-Feb-19 A | 28-Feb-19 A | 10 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16930 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Thermal Hydraulics (MACE) - Issue Final QA Grade 2 Technical Note (Not Req'd as per DS notes 26.02.18) | 28-Feb-19 A | 28-Feb-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16950 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Thermal Hydraulics (MACE) - Development of Suitable Boundary Conditions Completed (Not Req'd as per DS notes 26.02.18) | 28-Feb-19 A | 28-Feb-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16940 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Thermal Hydraulics (MACE) - Complete TR form and upload to CDMS (Not Req'd as per DS notes 26.02.18) | 28-Feb-19 A | 28-Feb-19 A | 5 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13180 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-02-28 | Discovery Milestone: Scope confirmation following NSC advice on NSRS and internal workshops (HNB) | 28-Feb-19 A | 28-Feb-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13590 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-28 | 2019-02-28 | Scope Additional SDM Calcs - Supplier prepare and issue Offer | 28-Feb-19 A | 28-Feb-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13600 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-28 | 2019-02-28 | Scope Additional SDM Calcs - Review Offer, prepare and issue CI | 28-Feb-19 A | 28-Feb-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13610 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-28 | 2019-02-28 | Scope Additional SDM Calcs - Supplier mobilisation time | 28-Feb-19 A | 28-Feb-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13620 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-28 | 2019-02-28 | Scope Additional SDM Calcs - Pre Job Brief | 28-Feb-19 A | 28-Feb-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13880 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-28 | 2019-02-28 | Civil Integrity Overview - Draft and issue RFS | 28-Feb-19 A | 28-Feb-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13890 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-28 | 2019-02-28 | Civil Integrity Overview - Supplier prepare and issue Offer | 28-Feb-19 A | 28-Feb-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13900 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-28 | 2019-02-28 | Civil Integrity Overview - Review Offer, prepare and issue CI | 28-Feb-19 A | 28-Feb-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13910 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-28 | 2019-02-28 | Civil Integrity Overview - Supplier mobilisation time | 28-Feb-19 A | 28-Feb-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13875 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-28 | 2019-03-04 | RFS - Civil Integrity Overview Summary | 28-Feb-19 A | 04-Mar-19 A | 3 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14240 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-28 | 2019-02-28 | Ass'ment of Graphite behaviour for Shutdown Defuelling - Draft and issue RFS | 28-Feb-19 A | 28-Feb-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14250 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-28 | 2019-02-28 | Ass'ment of Graphite behaviour for Shutdown Defuelling - Supplier prepare and issue Offer | 28-Feb-19 A | 28-Feb-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14260 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-28 | 2019-02-28 | Ass'ment of Graphite behaviour for Shutdown Defuelling - Review Offer, prepare and issue CI | 28-Feb-19 A | 28-Feb-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14270 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-28 | 2019-02-28 | Ass'ment of Graphite behaviour for Shutdown Defuelling - Supplier mobilisation time | 28-Feb-19 A | 28-Feb-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14235 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-28 | 2019-04-30 | RFS - Ass'ment of Graphite behaviour for Shutdown Defuelling Summary | 28-Feb-19 A | 30-Apr-19 A | 42 | 0 | 42 | 100% |  | Completed
ER6244LT | W220 | A10130 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2019-02-28 | [KDM] Dropped FPU RadCons Analysis of Core Support Plate Failure available | 28-Feb-19 A | 28-Feb-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1210 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Gate B IRM Paper Submission | 01-Mar-19 A | 01-Mar-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10300 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-01 | 2019-06-03 | Prepare Specification for LSD Strategy Draft Report | 01-Mar-19 A | 03-Jun-19 A | 63 | 0 | 63 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10420 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-01 | 2019-04-10 | Prepare Specification for Boilers and Gas Circulator Performance EAN | 01-Mar-19 A | 10-Apr-19 A | 29 | 0 | 28 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10295 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-01 | 2019-10-04 | Specification for LSD Strategy Draft Report Summary | 01-Mar-19 A | 04-Oct-19 A | 150 | 0 | 150 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10415 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-01 | 2020-04-07 | Boilers and Gas Circulator Performance for Changing Plant Conditions Summary | 01-Mar-19 A | 28-Jul-20 A | 354 | 0 | 355 | 100% |  | Completed
ER6370LT | W201 | ER6370.A12305 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-01 | 2019-04-02 | Prepare EPRI Tool - HNB | 01-Mar-19 A | 02-Apr-19 A | 23 | 0 | 22 | 100% |  | Completed
ER6370LT | W201 | ER6370.A12300 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-01 | 2019-05-15 | EPRI Tool Summary - HNB | 01-Mar-19 A | 15-May-19 A | 51 | 0 | 51 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13310 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-01 | 2019-05-15 | Implementation Strategy Document Draft EAN Verified by TSA | 01-Mar-19 A | 15-May-19 A | 51 | 0 | 50 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11260 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-01 | 2019-04-05 | Response to Stress Test EAN Verification | 01-Mar-19 A | 05-Apr-19 A | 26 | 0 | 25 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1240 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-03-01 | Gate B IRM Paper Submission | 01-Mar-19 A | 01-Mar-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4940 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-03-04 | C&I Review Specification Completed | 04-Mar-19 A | 04-Mar-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7310 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-04 | 2019-05-08 | Prepare DNB Commissiong Core Validation Scoping Draft Report | 04-Mar-19 A | 08-May-19 A | 45 | 0 | 44 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10840 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-04 | 2019-03-08 | TSA Address Comments on TR'd Scope Codes and Methods Options and Validation | 04-Mar-19 A | 08-Mar-19 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13920 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-04 | 2019-03-04 | Civil Integrity Overview - Pre Job Brief | 04-Mar-19 A | 04-Mar-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A16820 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Address EDF Comments on Draft resourced Station Plans (HPB) (Transfer to W282 Workpack) | 05-Mar-19 A | 05-Mar-19 A | 4 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16830 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Re-issue Final resourced Station Plans (HPB) (Transfer to W282 Workpack) | 05-Mar-19 A | 05-Mar-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A17200 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Address EDF Comments on Draft resourced Station Plans (HNB) (Transfer to W282 Workpack) | 05-Mar-19 A | 05-Mar-19 A | 4 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A17210 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Re-issue Final resourced Station Plans (HNB) (Transfer to W282 Workpack) | 05-Mar-19 A | 05-Mar-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2840 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-05 | 2019-07-17 | Prepare Civil Integrity Overview Draft EAN | 05-Mar-19 A | 17-Jul-19 A | 93 | 0 | 92 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4950 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-05 | 2019-04-12 | C&I Review Authoring | 05-Mar-19 A | 12-Apr-19 A | 29 | 0 | 28 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7260 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-05 | 2019-03-18 | Code Validation from Operational Reactor Draft Report Reviewed by TSA SQEP | 05-Mar-19 A | 18-Mar-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11020 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-05 | 2019-04-12 | Address Comments from EDF Review on SDM Assumptions Document Draft Report | 05-Mar-19 A | 12-Apr-19 A | 29 | 0 | 28 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2835 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-05 | 2019-08-19 | Civil Integrity Overview Summary | 05-Mar-19 A | 19-Aug-19 A | 115 | 0 | 115 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10850 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-03-08 | TSA Issue Final Scope Codes and Methods Options and Validation | 08-Mar-19 A | 08-Mar-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13500 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-08 | 2019-03-14 | SDM Assessments with Uncertainties - Review Offer, prepare and issue CI | 08-Mar-19 A | 14-Mar-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3800 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-11 | 2019-04-15 | Validate Model and Datasets Part 1 | 11-Mar-19 A | 15-Apr-19 A | 26 | 0 | 25 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8390 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-11 | 2019-04-30 | Address Comments on Reviewed Pressure Boundary Seals Specification | 11-Mar-19 A | 30-Apr-19 A | 35 | 0 | 34 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10860 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-11 | 2019-03-15 | Scope Codes and Methods Options and Validation TR Completed and uploaded to CDMS | 11-Mar-19 A | 15-Mar-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10950 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-11 | 2019-04-26 | Prepare Scope Additional SDM Calcs Draft Report (Phase 1) | 11-Mar-19 A | 26-Apr-19 A | 33 | 0 | 32 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10945 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-11 | 2019-09-20 | Scope Additional SDM Calcs Summary | 11-Mar-19 A | 20-Sep-19 A | 134 | 0 | 134 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3795 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-11 | 2019-04-15 | Validate Model and Datasets Part 1 Summary | 11-Mar-19 A | 15-Apr-19 A | 25 | 0 | 25 | 100% |  | Completed
ER6244LT | W220 | A9770 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2019-03-11 | 2019-03-22 | Supplier update and issue Fuel Free Verification EAN | 11-Mar-19 A | 22-Mar-19 A | 10 | 0 | 10 | 100% |  | Completed
ER6243LT | W200 | A1670.C0 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-09-28 | Gate B - 6.1 Reactors Shutdown Safety Cases Programme HPB/HNB | 13-Mar-19 A | 13-Mar-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1230 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Gate B IRM Paper Approval | 13-Mar-19 A | 13-Mar-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1220 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Hold IRM | 13-Mar-19 A | 13-Mar-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1230 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-13 | 2019-03-13 | Hold IRM | 13-Mar-19 A | 13-Mar-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1220 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-03-13 | Gate B IRM Paper Approval | 13-Mar-19 A | 13-Mar-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10410 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-14 | 2019-05-13 | Prepare Specification for Boiler Supporting Systems EAN | 14-Mar-19 A | 13-May-19 A | 40 | 0 | 39 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10405 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-14 | 2020-04-07 | Boiler Supporting Systems Summary | 14-Mar-19 A | 24-Apr-20 A | 282 | 0 | 281 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10870 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-03-15 | Scope Codes and Methods Options and Validation Completed | 15-Mar-19 A | 15-Mar-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13510 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-15 | 2019-03-28 | SDM Assessments with Uncertainties - Supplier mobilisation time | 15-Mar-19 A | 28-Mar-19 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14940 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-15 | 2019-05-01 | Boiler Control and Protection Draft Report - Draft and issue RFS | 15-Mar-19 A | 01-May-19 A | 32 | 0 | 31 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14935 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-15 | 2019-05-23 | RFS - Boiler Control and Protection Draft Report Summary | 15-Mar-19 A | 23-May-19 A | 47 | 0 | 47 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14990 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-15 | 2019-05-01 | Reactor Cooling Systems Draft Report - Draft and issue RFS | 15-Mar-19 A | 01-May-19 A | 32 | 0 | 31 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14985 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-15 | 2019-05-23 | RFS - Reactor Cooling Systems Draft Report Summary | 15-Mar-19 A | 23-May-19 A | 47 | 0 | 47 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2000 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-18 | 2019-06-28 | Prepare Establish Codes and Methods for Safety Case Draft Report | 18-Mar-19 A | 28-Jun-19 A | 71 | 0 | 70 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1999 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-18 | 2019-11-08 | Establish Codes and Methods for Safety Case Summary | 18-Mar-19 A | 08-Nov-19 A | 164 | 0 | 164 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16020 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-18 | 2019-04-05 | Response to ALARP Framework Support for ALARP/BAT/BPM Report Verification | 18-Mar-19 A | 05-Apr-19 A | 15 | 0 | 14 | 100% |  | Completed
ER6243LT | W200 | A3070.C0 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-09-28 | Identify and De-risk Major Threats to the Strategy | 19-Mar-19 A | 19-Mar-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.VI.A190.EI | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-04-30 | PCPV Integrity - Engineering Substantiation Report Completed (HPB, HNB) | 19-Mar-19 A | 19-Mar-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | RSSC.VI.A200.EI | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-04-30 | PCPV Integrity - Engineering Substantiation Report Completed (HYA, HAR) | 19-Mar-19 A | 19-Mar-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A1270 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-10-17 | 2018-10-23 | Agree INSA resource with SRD (HPB, HNB) | 19-Mar-19 A | 19-Mar-19 A | 5 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A1280 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-12-27 | 2019-01-03 | Circulate work programme to stakeholders for agreement (HPB, HNB) | 19-Mar-19 A | 19-Mar-19 A | 5 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A12600 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-10-22 | 2018-10-26 | Agree design proposals with Station in the case of hardware mods (HYA, HAR) | 19-Mar-19 A | 19-Mar-19 A | 5 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A13050.C0 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-09-28 | Key Risks Identified and Assumptions underpinned | 19-Mar-19 A | 19-Mar-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7270 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-19 | 2019-04-30 | Address Comments from EDF Review on Code Validation from Operational Reactor Draft Report | 19-Mar-19 A | 30-Apr-19 A | 29 | 0 | 28 | 100% |  | Completed
ER6243LT | W200 | A3050.C0 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-06-29 | Identify any Major Hardware Changes required for Gate B Submission | 19-Mar-19 A | 19-Mar-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14640 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-25 | 2019-04-05 | Fault Schedule Review (Plant Based Faults) - Draft and issue RFS | 25-Mar-19 A | 05-Apr-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14635 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-25 | 2019-05-17 | RFS - Fault Schedule Review (Plant Based Faults) Summary | 25-Mar-19 A | 17-May-19 A | 37 | 0 | 37 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14690 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-25 | 2019-04-05 | Fault Schedule Review (Hazards) - Draft and issue RFS | 25-Mar-19 A | 05-Apr-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14685 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-25 | 2019-05-17 | RFS - Fault Schedule Review (Hazards) Summary | 25-Mar-19 A | 17-May-19 A | 37 | 0 | 37 | 100% |  | Completed
ER6244LT | W220 | A9780 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2019-03-25 | 2019-03-28 | Complete TR form and upload Fuel Free Verification EAN to CDMS | 25-Mar-19 A | 28-Mar-19 A | 4 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10760 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-26 | 2019-03-29 | TSA Address Comments on TR'd Current Code Applicability Range | 26-Mar-19 A | 29-Mar-19 A | 4 | 0 | 3 | 100% |  | Completed
ER6378LT | W222 | W222.A14040 | HRA Fuel Handling Essential Safety Case | 2019-03-26 | 2019-03-26 | Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 26-Mar-19 A | 26-Mar-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A14030 | HRA Fuel Handling Essential Safety Case | 2019-03-26 | 2019-03-26 | Define Project Control Structures (WBS/CBS/OBS/PBS) | 26-Mar-19 A | 26-Mar-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A22150 | HRA Fuel Handling Essential Safety Case | 2019-03-26 | 2020-02-28 | EAC (PS - 28-Feb-2020) ##(Cost Summary)## | 26-Mar-19 A | 28-Feb-20 A | 257 | 0 | 235 | 100% |  | Completed
ER6650LT | W226 | W226.A14030 | HYA Fuel Handling Essential Safety Case | 2019-03-26 | 2019-03-26 | Define Project Control Structures (WBS/CBS/OBS/PBS) [FEEDS TO SUMMARY SCHEDULE] | 26-Mar-19 A | 26-Mar-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A14040 | HYA Fuel Handling Essential Safety Case | 2019-03-26 | 2019-03-26 | Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 26-Mar-19 A | 26-Mar-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A12770 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-07-31 | 2018-08-06 | Identify verifier for the case & establish all other resources (HYA, HAR) (Deferred to W202 Workpack) | 27-Mar-19 A | 27-Mar-19 A | 5 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A12900 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2019-07-02 | Gate EC2 completed EC 363682 & 363676 <NSRS SC Approach & Outline> (Cat 1 Milestone) (HYA, HAR) (Deferred to W202 WP) | 27-Mar-19 A | 27-Mar-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A12610 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-10-22 | 2018-10-26 | Agree INSA resource with SRD (HYA, HAR) (Deferred to W202 Workpack) | 27-Mar-19 A | 27-Mar-19 A | 5 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A12780 | REGION 1 Reactors Shutdown Safety Cases Programme | 2019-07-02 | 2019-07-08 | Circulate work programme to stakeholders for agreement (HYA, HAR) (Deferred to W202 Workpack) | 27-Mar-19 A | 27-Mar-19 A | 5 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A12870 | REGION 1 Reactors Shutdown Safety Cases Programme | 2019-07-01 | 2019-07-01 | Develop & resource mandatory template (HYA, HAR) (Deferred to W202 Workpack) | 27-Mar-19 A | 27-Mar-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A12980 | REGION 1 Reactors Shutdown Safety Cases Programme | 2019-07-09 | 2019-07-09 | Baseline Plan to Verification Commenced (T-11) (HYA, HAR) (Deferred to W202 Workpack) | 27-Mar-19 A | 27-Mar-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13230 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-03-28 | Verified ALARP Strategy Document Draft EAN Issued to EDF for Technical Review. (Deleted) | 28-Mar-19 A | 28-Mar-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13240 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-28 | 2019-03-28 | ALARP Strategy Document Draft EAN Technically Reviewed by EDF SQEP (Deleted) | 28-Mar-19 A | 28-Mar-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13250 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-28 | 2019-03-28 | TSA Address Comments on TR'd ALARP Strategy Document Draft EAN (Deleted) | 28-Mar-19 A | 28-Mar-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14450 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-28 | 2019-03-28 | Gas Chemistry Assessment - Supplier prepare and issue Offer | 28-Mar-19 A | 28-Mar-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14460 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-28 | 2019-03-28 | Gas Chemistry Assessment - Review Offer, prepare and issue CI | 28-Mar-19 A | 28-Mar-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14470 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-28 | 2019-03-28 | Gas Chemistry Assessment - Supplier mobilisation time | 28-Mar-19 A | 28-Mar-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14480 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-28 | 2019-03-28 | Gas Chemistry Assessment - Pre Job Brief | 28-Mar-19 A | 28-Mar-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14435 | HNB Reactors Shutdown Essential Safety Cases | 2019-03-28 | 2019-05-10 | RFS - Gas Chemistry Assessment Specification Summary | 28-Mar-19 A | 10-May-19 A | 28 | 0 | 28 | 100% |  | Completed
ER6244LT | W220 | A9790 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2019-03-28 | [KDM] Fuel Free Verification EAN available | 28-Mar-19 A | 28-Mar-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10770 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-03-29 | TSA Issue Final Current Code Applicability Range | 29-Mar-19 A | 29-Mar-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10430 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-01 | 2020-03-30 | General HF Oversight of Work Carried out on Safety Case (WP1) | 01-Apr-19 A | 30-Apr-20 A | 274 | 0 | 274 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10525 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-01 | 2019-11-15 | ALARP / BAT/ BPM Summary | 01-Apr-19 A | 15-Nov-19 A | 159 | 0 | 159 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13980 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-01 | 2019-04-12 | Component Life Assessment - Draft and issue RFS | 01-Apr-19 A | 12-Apr-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13975 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-01 | 2019-05-22 | RFS - Component Life Assessment Summary | 01-Apr-19 A | 22-May-19 A | 35 | 0 | 35 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14090 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-01 | 2019-04-12 | Specification for Standpipe and Guide Tube Integrity Assessment - Draft and issue RFS | 01-Apr-19 A | 12-Apr-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14085 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-01 | 2019-05-22 | RFS - Specification for Standpipe and Guide Tube Integrity Assessment Summary | 01-Apr-19 A | 22-May-19 A | 35 | 0 | 35 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14190 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-01 | 2019-04-12 | Specification for Degradation of Boilers - Draft and issue RFS | 01-Apr-19 A | 12-Apr-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14185 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-01 | 2019-05-22 | RFS - Specification for Degradation of Boilers Summary | 01-Apr-19 A | 22-May-19 A | 35 | 0 | 35 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14440 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-01 | 2019-05-10 | Prepare Gas Chemistry Specification | 01-Apr-19 A | 10-May-19 A | 27 | 0 | 26 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14490 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-01 | 2019-05-31 | Reactor Coolant Chemistry Conditions - Draft and issue RFS | 01-Apr-19 A | 31-May-19 A | 41 | 0 | 40 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14485 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-01 | 2019-07-12 | RFS - Reactor Coolant Chemistry Conditions Summary | 01-Apr-19 A | 12-Jul-19 A | 71 | 0 | 71 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15090 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-01 | 2019-04-05 | HF Compliance Assessment for Shutdown Margin - Draft and issue RFS | 01-Apr-19 A | 05-Apr-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15085 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-01 | 2019-04-30 | RFS - HF Compliance Assessment for Shutdown Margin Summary | 01-Apr-19 A | 30-Apr-19 A | 20 | 0 | 20 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15140 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-01 | 2019-04-05 | HF Compliance / Tech Spec As'ment for Core Cooling - Draft and issue RFS | 01-Apr-19 A | 05-Apr-19 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15135 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-01 | 2019-04-30 | RFS - HF Compliance / Tech Spec As'ment for Core Cooling Summary | 01-Apr-19 A | 30-Apr-19 A | 20 | 0 | 20 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15340 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-01 | 2019-04-03 | HF Risk Assessment Draft Report - Draft and issue RFS | 01-Apr-19 A | 03-Apr-19 A | 3 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15335 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-01 | 2019-04-12 | RFS - HF Risk Assessment Draft Report Summary | 01-Apr-19 A | 12-Apr-19 A | 9 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15840 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-01 | 2019-04-05 | Summary of Compliance with NSPs - Draft and issue RFS | 01-Apr-19 A | 05-Apr-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15835 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-01 | 2019-04-24 | RFS - Summary of Compliance with NSPs Summary | 01-Apr-19 A | 24-Apr-19 A | 16 | 0 | 16 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16130 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-01 | 2019-07-08 | Phase 1: Scoping and Parameters for Station Documentation Update Strategy | 01-Apr-19 A | 08-Jul-19 A | 67 | 0 | 66 | 100% |  | Completed
ER6243LT | W200 | A10260 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | CA to agree with CO format of the safety case (HYA, HAR) | 01-Apr-19 A | 02-Apr-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | W222.A3240 | HRA Fuel Handling Essential Safety Case | 2019-04-01 | 2019-05-24 | Incorporate INA, Station, DA (peer) comments | 01-Apr-19 A | 24-May-19 A | 16 | 0 | 36 | 100% |  | Completed
ER6650LT | W226 | W226.A3240 | HYA Fuel Handling Essential Safety Case | 2019-04-01 | 2019-05-24 | Incorporate INA, Station, DA (peer) comments | 01-Apr-19 A | 24-May-19 A | 16 | 0 | 36 | 100% |  | Completed
ER6243LT | W200 | A10760 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Estimating Uncertainty - 2019 | 01-Apr-19 A | 01-Apr-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14290 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-02 | 2019-04-12 | Specification for Reactor Internals - Draft and issue RFS | 02-Apr-19 A | 12-Apr-19 A | 9 | 0 | 8 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14285 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-02 | 2019-05-22 | RFS - Specification for Reactor Internals Summary | 02-Apr-19 A | 22-May-19 A | 34 | 0 | 34 | 100% |  | Completed
ER6243LT | W200 | A10120 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-10-24 | 2018-11-06 | Incorporate SRD, Station, DA (peer) comments (HPB, HNB) | 02-Apr-19 A | 30-Apr-19 A | 10 | 0 | 18 | 100% |  | Completed
ER6370LT | W201 | ER6370.A12255 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-03 | 2019-04-16 | EPRI Tool Verified by TSA - HNB | 03-Apr-19 A | 16-Apr-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6243LT | W200 | A10280 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-10-24 | 2018-11-06 | Incorporate SRD, Station, DA (peer) comments (HYA, HAR) | 03-Apr-19 A | 30-Apr-19 A | 10 | 0 | 17 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15350 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-04 | 2019-04-08 | HF Risk Assessment Draft Report - Supplier prepare and issue Offer | 04-Apr-19 A | 08-Apr-19 A | 3 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13260 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-04-05 | TSA Issue Final ALARP Strategy Document EAN | 05-Apr-19 A | 05-Apr-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14540 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-05 | 2019-04-12 | Claim 2 Containment Head Document - Draft and issue RFS | 05-Apr-19 A | 12-Apr-19 A | 6 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14535 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-05 | 2019-05-29 | RFS - Specification for Claim 2 Containment Head Document Summary | 05-Apr-19 A | 29-May-19 A | 35 | 0 | 35 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10290 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-08 | 2019-05-02 | (SCOPE REMOVED) - Prepare Specification for Tech Specs HEAD DOCUMENT Report | 08-Apr-19 A | 02-May-19 A | 17 | 0 | 16 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10285 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-08 | 2019-07-25 | (SCOPE REMOVED) - Specification for Tech Specs HEAD DOCUMENT Report Summary | 08-Apr-19 A | 25-Jul-19 A | 75 | 0 | 74 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13270 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-08 | 2019-04-23 | ALARP Strategy Document EAN TR Completed and uploaded to CDMS | 08-Apr-19 A | 23-Apr-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11320 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-08 | 2019-04-12 | Stress Test EAN Version 0 Upload to CDMS | 08-Apr-19 A | 12-Apr-19 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14650 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-08 | 2019-04-23 | Fault Schedule Review (Plant Based Faults) - Supplier prepare and issue Offer | 08-Apr-19 A | 23-Apr-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14700 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-08 | 2019-04-23 | Fault Schedule Review (Hazards) - Supplier prepare and issue Offer | 08-Apr-19 A | 23-Apr-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15100 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-08 | 2019-04-15 | HF Compliance Assessment for Shutdown Margin - Supplier prepare and issue Offer | 08-Apr-19 A | 15-Apr-19 A | 6 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15150 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-08 | 2019-04-15 | HF Compliance / Tech Spec As'ment for Core Cooling - Supplier prepare and issue Offer | 08-Apr-19 A | 15-Apr-19 A | 6 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15850 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-08 | 2019-04-12 | Summary of Compliance with NSPs - Supplier prepare and issue Offer | 08-Apr-19 A | 12-Apr-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16030 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-08 | 2019-04-12 | ALARP Framework Support for ALARP/BAT/BPM Report Version 0 Upload to CDMS | 08-Apr-19 A | 12-Apr-19 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14390 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-09 | 2019-04-15 | Pressure Boundary Seals - Draft and issue RFS | 09-Apr-19 A | 15-Apr-19 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14385 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-09 | 2019-05-17 | RFS - Specification for Pressure Boundary Seals Summary | 09-Apr-19 A | 17-May-19 A | 26 | 0 | 26 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15360 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-09 | 2019-04-10 | HF Risk Assessment Draft Report - Review Offer, prepare and issue CI | 09-Apr-19 A | 10-Apr-19 A | 2 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15370 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-11 | 2019-04-11 | HF Risk Assessment Draft Report - Supplier mobilisation time | 11-Apr-19 A | 11-Apr-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15790 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-11 | 2019-04-17 | Boilers and Gas Circulator Performance - Draft and issue RFS | 11-Apr-19 A | 17-Apr-19 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4970 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-04-12 | C&I Review Authoring Completed and Issued | 12-Apr-19 A | 12-Apr-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15380 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-12 | 2019-04-12 | HF Risk Assessment Draft Report - Pre Job Brief | 12-Apr-19 A | 12-Apr-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A13100.E0 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-09-25 | Draft NSRS Produced - HPB and HNB | 15-Apr-19 A | 15-Apr-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A13110.E0 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-09-28 | Draft NSRS Produced - HRA and HYA | 15-Apr-19 A | 15-Apr-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3710 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-04-15 | Develop Defuelling Dataset Part 1 Completed | 15-Apr-19 A | 15-Apr-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3870 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-04-15 | Model and Datasets Part 1 Completed | 15-Apr-19 A | 15-Apr-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10530 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-15 | 2019-07-16 | Prepare ALARP / BAT/ BPM Draft Report | 15-Apr-19 A | 16-Jul-19 A | 63 | 0 | 62 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13990 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-15 | 2019-04-25 | Component Life Assessment - Supplier prepare and issue Offer | 15-Apr-19 A | 25-Apr-19 A | 7 | 0 | 7 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14100 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-15 | 2019-04-25 | Specification for Standpipe and Guide Tube Integrity Assessment - Supplier prepare and issue Offer | 15-Apr-19 A | 25-Apr-19 A | 7 | 0 | 6 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14200 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-15 | 2019-04-26 | Specification for Degradation of Boilers - Supplier prepare and issue Offer | 15-Apr-19 A | 26-Apr-19 A | 8 | 0 | 7 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14300 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-15 | 2019-05-06 | Specification for Reactor Internals - Supplier prepare and issue Offer | 15-Apr-19 A | 06-May-19 A | 13 | 0 | 13 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14550 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-15 | 2019-05-03 | Claim 2 Containment Head Document - Supplier prepare and issue Offer | 15-Apr-19 A | 03-May-19 A | 13 | 0 | 12 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15860 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-15 | 2019-04-16 | Summary of Compliance with NSPs - Review Offer, prepare and issue CI | 15-Apr-19 A | 16-Apr-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15960 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-15 | 2019-04-16 | Structures and Equipment Integrity - Review Offer, prepare and issue CI | 15-Apr-19 A | 16-Apr-19 A | 2 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10780 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-16 | 2019-04-30 | Current Code Applicability Range TR Completed and uploaded to CDMS | 16-Apr-19 A | 30-Apr-19 A | 9 | 0 | 8 | 100% |  | Completed
ER6370LT | W201 | ER6370.A12265 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-04-16 | Verified EPRI Tool Issued to Station for Review - HNB | 16-Apr-19 A | 16-Apr-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14400 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-16 | 2019-04-22 | Pressure Boundary Seals - Supplier prepare and issue Offer | 16-Apr-19 A | 22-Apr-19 A | 3 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15110 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-16 | 2019-04-17 | HF Compliance Assessment for Shutdown Margin - Review Offer, prepare and issue CI | 16-Apr-19 A | 17-Apr-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15160 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-16 | 2019-04-17 | HF Compliance / Tech Spec As'ment for Core Cooling - Review Offer, prepare and issue CI | 16-Apr-19 A | 17-Apr-19 A | 2 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A10290 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-11-09 | 2018-11-22 | DA & SRD agree NSRS (for authorised designers-NSRS must be reviewed by DA) (HYA, HAR) | 17-Apr-19 A | 30-Apr-19 A | 10 | 0 | 7 | 100% |  | Completed
ER6370LT | W201 | ER6370.A12275 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-17 | 2019-04-26 | EPRI Tool Reviewed by Station - HNB | 17-Apr-19 A | 26-Apr-19 A | 6 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15870 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-17 | 2019-04-23 | Summary of Compliance with NSPs - Supplier mobilisation time | 17-Apr-19 A | 23-Apr-19 A | 3 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15970 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-17 | 2019-04-18 | Structures and Equipment Integrity - Supplier mobilisation time | 17-Apr-19 A | 18-Apr-19 A | 2 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A10150 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-11-08 | 2018-11-21 | DA & SRD agree NSRS (for authorised designers-NSRS must be reviewed by DA) (HPB, HNB) | 17-Apr-19 A | 30-Apr-19 A | 10 | 0 | 7 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3880 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-18 | 2019-07-12 | Validate Model and Datasets Part 2 (See Steps) | 18-Apr-19 A | 12-Jul-19 A | 58 | 0 | 57 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3875 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-18 | 2019-11-29 | Validate Model and Datasets Part 2 Summary | 18-Apr-19 A | 29-Nov-19 A | 156 | 0 | 156 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15120 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-18 | 2019-04-29 | HF Compliance Assessment for Shutdown Margin - Supplier mobilisation time | 18-Apr-19 A | 29-Apr-19 A | 6 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15800 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-18 | 2019-05-10 | Boilers and Gas Circulator Performance - Supplier prepare and issue Offer | 18-Apr-19 A | 10-May-19 A | 14 | 0 | 13 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15170 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-18 | 2019-04-29 | HF Compliance / Tech Spec As'ment for Core Cooling - Supplier mobilisation time | 18-Apr-19 A | 29-Apr-19 A | 6 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10330 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-19 | 2019-07-05 | Prepare Structures and Equipment Integrity Draft Report | 19-Apr-19 A | 05-Jul-19 A | 52 | 0 | 51 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10325 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-19 | 2019-10-21 | Structures and Equipment Integrity Summary | 19-Apr-19 A | 21-Oct-19 A | 126 | 0 | 126 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15980 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-19 | 2019-04-19 | Structures and Equipment Integrity - Pre Job Brief | 19-Apr-19 A | 19-Apr-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A5560 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-23 | 2019-09-09 | Prepare HF Risk Assessment Draft Report | 23-Apr-19 A | 09-Sep-19 A | 97 | 0 | 96 | 100% |  | Completed
ER6370LT | W201 | ER6370.A5555 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-23 | 2019-11-01 | HF Risk Assessment Summary | 23-Apr-19 A | 01-Nov-19 A | 136 | 0 | 136 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13280 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-04-23 | ALARP Strategy Document EAN Completed | 23-Apr-19 A | 23-Apr-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14410 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-23 | 2019-04-26 | Pressure Boundary Seals - Review Offer, prepare and issue CI | 23-Apr-19 A | 26-Apr-19 A | 4 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14660 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-24 | 2019-05-01 | Fault Schedule Review (Plant Based Faults) - Review Offer, prepare and issue CI | 24-Apr-19 A | 01-May-19 A | 6 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14710 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-24 | 2019-05-01 | Fault Schedule Review (Hazards) - Review Offer, prepare and issue CI | 24-Apr-19 A | 01-May-19 A | 6 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15880 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-24 | 2019-04-24 | Summary of Compliance with NSPs - Pre Job Brief | 24-Apr-19 A | 24-Apr-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10960 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-04-26 | Issued Scope Additional SDM Calcs Draft Report to EDF for Review. | 26-Apr-19 A | 26-Apr-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10970 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-26 | 2019-05-17 | Scope Additional SDM Calcs Draft Report Reviewed by EDF SQEP | 26-Apr-19 A | 17-May-19 A | 15 | 0 | 15 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14110 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-26 | 2019-05-06 | Specification for Standpipe and Guide Tube Integrity Assessment - Review Offer, prepare and issue CI | 26-Apr-19 A | 06-May-19 A | 6 | 0 | 6 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13520 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-29 | 2019-04-29 | SDM Assessments with Uncertainties - Pre Job Brief | 29-Apr-19 A | 29-Apr-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13840 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-29 | 2019-04-29 | Shutdown Margin Head Document - Supplier prepare and issue Offer (Not Req'd) | 29-Apr-19 A | 29-Apr-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13850 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-29 | 2019-04-29 | Shutdown Margin Head Document - Review Offer, prepare and issue CI (Not Req'd) | 29-Apr-19 A | 29-Apr-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13860 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-29 | 2019-04-29 | Shutdown Margin Head Document - Supplier mobilisation time (Not Req'd) | 29-Apr-19 A | 29-Apr-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14000 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-29 | 2019-05-06 | Component Life Assessment - Review Offer, prepare and issue CI | 29-Apr-19 A | 06-May-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14210 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-29 | 2019-05-06 | Specification for Degradation of Boilers - Review Offer, prepare and issue CI | 29-Apr-19 A | 06-May-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14420 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-29 | 2019-05-16 | Pressure Boundary Seals - Supplier mobilisation time | 29-Apr-19 A | 16-May-19 A | 13 | 0 | 12 | 100% |  | Completed
ER6243LT | W200 | A10130 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-11-07 | 2018-11-07 | Issue final NSRS (HPB, HNB) | 30-Apr-19 A | 30-Apr-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A10230 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-11-07 | 2018-11-07 | Issue final NSRS (HYA, HAR) | 30-Apr-19 A | 30-Apr-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7280 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-04-30 | Issue Final Code Validation from Operational Reactor Report | 30-Apr-19 A | 30-Apr-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7460 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-04-30 | Issued Flux Detection Scoping Draft Report to EDF for Review. | 30-Apr-19 A | 30-Apr-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7590 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-30 | 2019-07-02 | Prepare SDM Assessments with uncertainties / sensitivity studies Draft Report | 30-Apr-19 A | 02-Jul-19 A | 44 | 0 | 43 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8400 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-04-30 | Issue Final Pressure Boundary Seals Specification | 30-Apr-19 A | 30-Apr-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10790 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-04-30 | Current Code Applicability Range Completed | 30-Apr-19 A | 30-Apr-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11030 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-04-30 | Issue Final SDM Assumptions Document Report Report | 30-Apr-19 A | 30-Apr-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7585 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-30 | 2019-11-14 | Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 1) Summary | 30-Apr-19 A | 14-Nov-19 A | 139 | 0 | 139 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14280 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-30 | 2019-04-30 | Ass'ment of Graphite behaviour for Shutdown Defuelling - Pre Job Brief | 30-Apr-19 A | 30-Apr-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15130 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-30 | 2019-04-30 | HF Compliance Assessment for Shutdown Margin - Pre Job Brief | 30-Apr-19 A | 30-Apr-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15180 | HNB Reactors Shutdown Essential Safety Cases | 2019-04-30 | 2019-04-30 | HF Compliance / Tech Spec As'ment for Core Cooling - Pre Job Brief | 30-Apr-19 A | 30-Apr-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3320 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-01 | 2019-05-30 | Prepare Ass'ment of Graphite behaviour for Shutdown Defuelling Draft Report | 01-May-19 A | 30-May-19 A | 20 | 0 | 20 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3500 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-05-01 | Issue MACE code v3.2.2 defuelling prototype model Issued to EDF for Review. | 01-May-19 A | 01-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3720 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-01 | 2019-12-20 | Prepare Defuelling Dataset QA Grade 2 Part 2 Report | 01-May-19 A | 20-Dec-19 A | 165 | 0 | 164 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7290 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-01 | 2019-06-28 | Code Validation from Operational Reactor Report Completed and Uploaded to CDMS | 01-May-19 A | 28-Jun-19 A | 41 | 0 | 40 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7470 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-01 | 2019-05-31 | Flux Detection Scoping Draft Report Reviewed by EDF SQEP | 01-May-19 A | 31-May-19 A | 21 | 0 | 20 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8040 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-05-01 | Specifications for RADCONs Completed | 01-May-19 A | 01-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8050 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-05-01 | Specifications for Fault Schedule Review Completed | 01-May-19 A | 01-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8410 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-01 | 2019-05-31 | Pressure Boundary Seals Specification Completed and uploaded to CDMS | 01-May-19 A | 31-May-19 A | 21 | 0 | 20 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10610 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-01 | 2019-07-19 | Prepare In Reactor NSP Compliance and Risk Draft Report | 01-May-19 A | 19-Jul-19 A | 56 | 0 | 55 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3315 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-01 | 2019-09-02 | Assessment of Graphite behaviour for Shutdown Defuelling Summary | 01-May-19 A | 02-Sep-19 A | 85 | 0 | 85 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3715 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-01 | 2020-03-13 | Develop Defuelling Dataset Part 2 Summary | 01-May-19 A | 27-Mar-20 A | 232 | 0 | 231 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10605 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-01 | 2019-11-15 | In Reactor NSP Compliance and Risk Report Summary | 01-May-19 A | 15-Nov-19 A | 139 | 0 | 139 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3475 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-01 | 2019-05-24 | MACE Develop Code Summary | 01-May-19 A | 24-May-19 A | 17 | 0 | 17 | 100% |  | Completed
ER6370LT | W201 | ER6370.A12285 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-01 | 2019-05-15 | Address Station Comments on EPRI Tool - HNB | 01-May-19 A | 15-May-19 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16050 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-01 | 2019-05-21 | Prepare Impacts for the Order of Defuelling Draft EAN | 01-May-19 A | 21-May-19 A | 14 | 0 | 13 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16040 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-01 | 2019-08-27 | Impacts for the Order of Defuelling Summary | 01-May-19 A | 27-Aug-19 A | 81 | 0 | 81 | 100% |  | Completed
ER6378LT | W222 | W222.A14060 | HRA Fuel Handling Essential Safety Case | 2019-05-01 | 2019-09-02 | Project Definition Document (PDD) | 01-May-19 A | 02-Sep-19 A | 86 | 0 | 86 | 100% |  | Completed
ER6378LT | W222 | W222.A14050 | HRA Fuel Handling Essential Safety Case | 2019-05-01 | 2019-09-02 | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 01-May-19 A | 02-Sep-19 A | 86 | 0 | 86 | 100% |  | Completed
ER6650LT | W226 | W226.A14050 | HYA Fuel Handling Essential Safety Case | 2019-05-01 | 2019-09-02 | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 01-May-19 A | 02-Sep-19 A | 86 | 0 | 86 | 100% |  | Completed
ER6650LT | W226 | W226.A14060 | HYA Fuel Handling Essential Safety Case | 2019-05-01 | 2019-09-02 | Project Definition Document (PDD) | 01-May-19 A | 02-Sep-19 A | 86 | 0 | 86 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3510 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-01 | 2019-05-15 | Verify MACE code v3.2.2 defuelling prototype model Reviewed by EDF SQEP | 01-May-19 A | 15-May-19 A | 10 | 0 | 10 | 100% |  | Completed
ER6243LT | W200 | A10340 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-11-22 | NSRS agreed by stakeholders EC 363682 & 363676 <NSRS SC Approach & Outline> (Cat 1 Milestone) (HYA, HAR) | 02-May-19 A | 02-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A10370 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-11-23 | 2018-11-23 | NSRS Presented to NSC (for complex CAT 1 cases) (HYA, HAR) | 02-May-19 A | 03-May-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A17240 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | NSRS agreed by stakeholders EC 363682 & 363676 <NSRS SC Approach & Outline> (Cat 1 Milestone) (HYA, HAR) | 02-May-19 A | 02-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14670 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-02 | 2019-05-16 | Fault Schedule Review (Plant Based Faults) - Supplier mobilisation time | 02-May-19 A | 16-May-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14720 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-02 | 2019-05-16 | Fault Schedule Review (Hazards) - Supplier mobilisation time | 02-May-19 A | 16-May-19 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14950 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-02 | 2019-05-14 | Boiler Control and Protection Draft Report - Supplier prepare and issue Offer | 02-May-19 A | 14-May-19 A | 8 | 0 | 7 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15000 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-02 | 2019-05-14 | Reactor Cooling Systems Draft Report - Supplier prepare and issue Offer | 02-May-19 A | 14-May-19 A | 8 | 0 | 7 | 100% |  | Completed
ER6243LT | W200 | A10250 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-11-26 | 2018-11-30 | Circulate NSRS for Relevant Stakeholders (HYA, HAR) | 03-May-19 A | 13-May-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15590 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-03 | 2019-05-10 | (SCOPE REMOVED) - Tech Specs HEAD DOCUMENT Report - Draft and issue RFS | 03-May-19 A | 10-May-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14010 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-07 | 2019-05-21 | Component Life Assessment - Supplier mobilisation time | 07-May-19 A | 21-May-19 A | 11 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14120 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-07 | 2019-05-21 | Specification for Standpipe and Guide Tube Integrity Assessment - Supplier mobilisation time | 07-May-19 A | 21-May-19 A | 11 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14220 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-07 | 2019-05-21 | Specification for Degradation of Boilers - Supplier mobilisation time | 07-May-19 A | 21-May-19 A | 11 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14310 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-07 | 2019-05-14 | Specification for Reactor Internals - Review Offer, prepare and issue CI | 07-May-19 A | 14-May-19 A | 6 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14560 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-07 | 2019-05-13 | Claim 2 Containment Head Document - Review Offer, prepare and issue CI | 07-May-19 A | 13-May-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | A1130 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-12-21 | NSRS Complete - HPB and HNB | 08-May-19 A | 08-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A1140 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2019-06-28 | NSRS Complete - HRA and HYA | 08-May-19 A | 08-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A1150.E0 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2021-03-31 | Safety Case Submitted (Including Submission to INSA, NSC and ONR if required) HPB and HNB | 08-May-19 A | 08-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A1160.E0 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2022-03-31 | Safety Case Submitted (Including Submission to INSA, NSC and ONR if required) HRA and HYA | 08-May-19 A | 08-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A1170 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2022-10-31 | First Reactor Implementation plan Complete & close-out (One for each of HPB and HNB) | 08-May-19 A | 08-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A10170 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-11-21 | NSRS agreed by stakeholders EC 363701 & 364023 <NSRS SC Approach & Outline> (Cat 1 Milestone) (HPB, HNB) | 08-May-19 A | 08-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A13090 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-11-21 | NSRS Agreed by Stakeholders - HPB and HNB | 08-May-19 A | 08-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A13120 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-11-22 | NSRS Agreed by Stakeholders - HRA and HYA | 08-May-19 A | 08-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A17230 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | NSRS agreed by stakeholders EC 363701 & 364023 <NSRS SC Approach & Outline> (Cat 1 Milestone) (HPB, HNB) | 08-May-19 A | 08-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7320 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-05-08 | Issued DNB Commissiong Core Validation Scoping Draft Report to EDF for Review. | 08-May-19 A | 08-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7330 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-09 | 2020-02-07 | DNB Commissiong Core Validation Scoping Draft Report Reviewed by EDF SQEP | 09-May-19 A | 07-Feb-20 A | 192 | 0 | 191 | 100% |  | Completed
ER6243LT | W200 | A1220 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-11-22 | 2018-11-22 | NSRS Presented to NSC (for complex CAT 1 cases) (HPB, HNB) | 09-May-19 A | 09-May-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A10180 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-11-23 | 2018-11-29 | Circulate NSRS for Relevant Stakeholders (HPB, HNB) | 10-May-19 A | 13-May-19 A | 5 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11350 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-10 | 2019-05-31 | ALARP Strategy Note | 10-May-19 A | 31-May-19 A | 15 | 0 | 14 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3240 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-13 | 2019-08-23 | Prepare Gas Chemistry Assessment Draft Report | 13-May-19 A | 23-Aug-19 A | 74 | 0 | 73 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3235 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-13 | 2019-11-29 | Gas Chemistry Assessment Summary | 13-May-19 A | 29-Nov-19 A | 142 | 0 | 142 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15600 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-13 | 2019-05-17 | (SCOPE REMOVED) - Tech Specs HEAD DOCUMENT Report - Supplier prepare and issue Offer | 13-May-19 A | 17-May-19 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15810 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-13 | 2019-05-17 | Boilers and Gas Circulator Performance - Review Offer, prepare and issue CI | 13-May-19 A | 17-May-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | A1190 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-11-30 | 2018-11-30 | Send NSRS to ONR to determine level of review required (Acknowledgement or Agreement) (HPB, HNB) | 14-May-19 A | 14-May-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | A10360 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-12-03 | 2018-12-03 | Send NSRS to ONR to determine level of review required (Acknowledgement or Agreement) (HYA, HAR) | 14-May-19 A | 14-May-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7000 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-14 | 2019-08-27 | Prepare Boiler Supporting Systems Draft EAN | 14-May-19 A | 27-Aug-19 A | 74 | 0 | 73 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14570 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-14 | 2019-05-28 | Claim 2 Containment Head Document - Supplier mobilisation time | 14-May-19 A | 28-May-19 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A12295 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-05-15 | Issue EPRI Tool for functional use - HNB | 15-May-19 A | 15-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13320 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-05-15 | Verified Implementation Strategy Document Draft EAN Issued to EDF for Technical Review. | 15-May-19 A | 15-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14320 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-15 | 2019-05-21 | Specification for Reactor Internals - Supplier mobilisation time | 15-May-19 A | 21-May-19 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14960 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-15 | 2019-05-20 | Boiler Control and Protection Draft Report - Review Offer, prepare and issue CI | 15-May-19 A | 20-May-19 A | 4 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15010 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-15 | 2019-05-20 | Reactor Cooling Systems Draft Report - Review Offer, prepare and issue CI | 15-May-19 A | 20-May-19 A | 4 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3520 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-16 | 2019-05-22 | Address Comments from EDF Review on MACE code v3.2.2 defuelling prototype model | 16-May-19 A | 22-May-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13330 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-16 | 2019-05-17 | Implementation Strategy Document Draft EAN Technically Reviewed by EDF SQEP | 16-May-19 A | 17-May-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1490 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Confirm Objectives to be Delivered at Gate B | 17-May-19 A | 23-May-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10980 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-05-17 | Issue Findings on Scope Additional SDM Calcs | 17-May-19 A | 17-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13420 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-17 | 2019-05-17 | Safety Rod Insertion Scoping - Pre Job Brief | 17-May-19 A | 17-May-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14430 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-17 | 2019-05-17 | Pressure Boundary Seals - Pre Job Brief | 17-May-19 A | 17-May-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14680 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-17 | 2019-05-17 | Fault Schedule Review (Plant Based Faults) - Pre Job Brief | 17-May-19 A | 17-May-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14730 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-17 | 2019-05-17 | Fault Schedule Review (Hazards) - Pre Job Brief | 17-May-19 A | 17-May-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3160 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-20 | 2019-07-12 | Prepare Pressure Boundary Seals Draft Report | 20-May-19 A | 12-Jul-19 A | 39 | 0 | 38 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4360 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-20 | 2019-06-24 | Prepare Fault Schedule Review (Plant Based Faults) Draft Report | 20-May-19 A | 24-Jun-19 A | 25 | 0 | 24 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4440 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-20 | 2019-06-24 | Prepare Fault Schedule Review (Harzards) Draft Report | 20-May-19 A | 24-Jun-19 A | 25 | 0 | 24 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3155 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-20 | 2019-09-13 | Pressure Boundary Seals Summary | 20-May-19 A | 13-Sep-19 A | 82 | 0 | 82 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4355 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-20 | 2019-12-23 | Fault Schedule Review (Plant Based Faults) Summary | 20-May-19 A | 23-Dec-19 A | 153 | 0 | 153 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4435 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-20 | 2019-12-23 | Fault Schedule Review (Harzards) Summary | 20-May-19 A | 23-Dec-19 A | 153 | 0 | 153 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13340 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-20 | 2019-05-22 | TSA Address Comments on TR'd Implementation Strategy Document Draft EAN | 20-May-19 A | 22-May-19 A | 3 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13430 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-20 | 2019-06-07 | Uncertainty in SDM Calculations - Task Control Sheet | 20-May-19 A | 07-Jun-19 A | 14 | 0 | 14 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13425 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-20 | 2019-06-07 | Task Control Sheet - Uncertainty in SDM Calculations Summary | 20-May-19 A | 07-Jun-19 A | 14 | 0 | 14 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15610 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-20 | 2019-05-21 | (SCOPE REMOVED) - Tech Specs HEAD DOCUMENT Report - Review Offer, prepare and issue CI | 20-May-19 A | 21-May-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15820 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-20 | 2019-05-22 | Boilers and Gas Circulator Performance - Supplier mobilisation time | 20-May-19 A | 22-May-19 A | 3 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14970 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-21 | 2019-05-22 | Boiler Control and Protection Draft Report - Supplier mobilisation time | 21-May-19 A | 22-May-19 A | 2 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15020 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-21 | 2019-05-22 | Reactor Cooling Systems Draft Report - Supplier mobilisation time | 21-May-19 A | 22-May-19 A | 2 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3530 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-05-22 | Issue Final Validated MACE code v3.2.2 defuelling prototype model | 22-May-19 A | 22-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13350 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-05-22 | TSA Issue Final Implementation Strategy Document EAN | 22-May-19 A | 22-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14020 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-22 | 2019-05-22 | Component Life Assessment - Pre Job Brief | 22-May-19 A | 22-May-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14130 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-22 | 2019-05-22 | Specification for Standpipe and Guide Tube Integrity Assessment - Pre Job Brief | 22-May-19 A | 22-May-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14230 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-22 | 2019-05-22 | Specification for Degradation of Boilers - Pre Job Brief | 22-May-19 A | 22-May-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14330 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-22 | 2019-05-22 | Specification for Reactor Internals - Pre Job Brief | 22-May-19 A | 22-May-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15620 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-22 | 2019-05-29 | (SCOPE REMOVED) - Tech Specs HEAD DOCUMENT Report - Supplier mobilisation time | 22-May-19 A | 29-May-19 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16060 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-22 | 2019-06-04 | Impacts for the Order of Defuelling Draft EAN Verified by TSA | 22-May-19 A | 04-Jun-19 A | 9 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3540 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-23 | 2019-05-24 | Validated MACE code v3.2.2 defuelling prototype model Completed and uploaded to CDMS | 23-May-19 A | 24-May-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8140 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-23 | 2019-05-27 | Prepare Component Life Assessment Specification | 23-May-19 A | 27-May-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8220 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-23 | 2019-05-27 | Prepare Standpipe and Guide Tube Integrity Assessment Specification | 23-May-19 A | 27-May-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8290 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-23 | 2019-05-27 | Prepare Degradation of Boilers Specification | 23-May-19 A | 27-May-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11040 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-23 | 2019-05-31 | SDM Assumptions Document Report Completed and Uploaded to CDMS | 23-May-19 A | 31-May-19 A | 6 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11090 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-23 | 2019-05-31 | Standpipe and Guide Tube Integrity Assessment Specification Summary | 23-May-19 A | 31-May-19 A | 6 | 0 | 6 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8285 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-23 | 2019-05-31 | Degradation of Boilers Specification Summary | 23-May-19 A | 31-May-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8135 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-23 | 2019-05-31 | Component Life Assessment Specification Summary | 23-May-19 A | 31-May-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13360 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-23 | 2019-05-31 | Implementation Strategy Document EAN TR Completed and uploaded to CDMS | 23-May-19 A | 31-May-19 A | 6 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14980 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-23 | 2019-05-23 | Boiler Control and Protection Draft Report - Pre Job Brief | 23-May-19 A | 23-May-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15030 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-23 | 2019-05-23 | Reactor Cooling Systems Draft Report - Pre Job Brief | 23-May-19 A | 23-May-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1070 | HRA Reactors Shutdown Essential Safety Cases | 2019-05-23 |  | Phase 2 Project Start [FEEDS TO SUMMARY SCHEDULE] | 23-May-19 A | 23-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1000 | HRA Reactors Shutdown Essential Safety Cases | 2019-05-23 | 2019-05-24 | Confirm Objectives to be Delivered at Gate B (FEEDS TO SUMMARY SCHEDULE) | 23-May-19 A | 24-May-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A1080 | HRA Reactors Shutdown Essential Safety Cases | 2019-05-23 | 2020-02-29 | Actuals (PS - 29-Feb-2020) | 23-May-19 A | 29-Feb-20 A | 197 | 0 | 197 | 100% |  | Completed
ER6661LT | W206 | W206.A1070 | HYA Reactors Shutdown Essential Safety Cases | 2019-05-23 |  | Phase 2 Project Start [FEEDS TO SUMMARY SCHEDULE] | 23-May-19 A | 23-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1000 | HYA Reactors Shutdown Essential Safety Cases | 2019-05-23 | 2019-05-24 | Confirm Objectives to be Delivered at Gate B [FEEDS TO SUMMARY SCHEDULE] | 23-May-19 A | 24-May-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A1080 | HYA Reactors Shutdown Essential Safety Cases | 2019-05-23 | 2020-02-29 | Actuals (PS - 29-Feb-2020) | 23-May-19 A | 29-Feb-20 A | 197 | 0 | 197 | 100% |  | Completed
ER6371LT | W202 | W202.A10101 | HRA Reactors Shutdown Essential Safety Cases |  |  | Summary for HRA Reactors Shutdown Essential Safety Cases W202 | 23-May-19 A | 07-Feb-25 A | 1 | 0 | 1445 | 100% |  | Completed
ER6661LT | W206 | W202.A1010 | HYA Reactors Shutdown Essential Safety Cases | 2019-05-23 | 2022-09-05 | Summary for HYA Reactors Shutdown Essential Safety Cases W206 | 23-May-19 A | 07-Feb-25 A | 1 | 0 | 1445 | 100% |  | Completed
ER6661LT | W206 | W206.A2206740 | HYA Reactors Shutdown Essential Safety Cases | 2019-05-23 | 2023-03-31 | Actuals (PS - 31-Mar-2023) | 23-May-19 A | 31-Mar-23 A | 197 | 0 | 976 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15830 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-23 | 2019-05-23 | Boilers and Gas Circulator Performance - Pre Job Brief | 23-May-19 A | 23-May-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A2206740 | HRA Reactors Shutdown Essential Safety Cases | 2019-05-23 | 2023-03-31 | Actuals (PS - 31-Mar-2023) | 23-May-19 A | 31-Mar-23 A | 977 | 0 | 977 | 100% |  | Completed
ER6244LT | W220 | A8180.E0 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2019-05-24 | [PR KDM] NSRS for HPB and HNB agreed by stakeholders - Defuelling Prog FH SC (Cat 1 ECs HPB 363993 & HNB 363991) | 24-May-19 A | 24-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A8190.E0 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2019-07-12 | [PR KDM] NSRS for HYA and HRA agreed by stakeholders - Defuelling Prog FH SC (Cat 1 ECs HRA 363839 & HYA 363840) | 24-May-19 A | 24-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1500 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Initial high level scope of programme | 24-May-19 A | 31-May-19 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3550 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-05-24 | Validated MACE code v3.2.2 defuelling prototype model Completed | 24-May-19 A | 24-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A3260 | HRA Fuel Handling Essential Safety Case | 2019-05-24 | 2019-05-24 | Issue final NSRS | 24-May-19 A | 24-May-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A1140 | HRA Fuel Handling Essential Safety Case | 2019-05-24 | 2019-05-24 | Station agree NSRS | 24-May-19 A | 24-May-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A3310 | HRA Fuel Handling Essential Safety Case | 2019-05-24 | 2019-05-24 | Circulate NSRS for Relevant Stakeholders | 24-May-19 A | 24-May-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A3270 | HRA Fuel Handling Essential Safety Case | 2019-05-24 | 2019-05-24 | DA & INA agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 24-May-19 A | 24-May-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A3290 | HRA Fuel Handling Essential Safety Case |  | 2019-05-24 | NSRS for HRA/HYA agreed by stakeholders Offload Depressurised Defuelling (Cat 1 Milestone) | 24-May-19 A | 24-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A3290 | HYA Fuel Handling Essential Safety Case |  | 2019-05-24 | NSRS for HYA/HYA agreed by stakeholders Offload Depressurised Defuelling (Cat 1 Milestone) | 24-May-19 A | 24-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A3270 | HYA Fuel Handling Essential Safety Case | 2019-05-24 | 2019-05-24 | DA & INA agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 24-May-19 A | 24-May-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A3310 | HYA Fuel Handling Essential Safety Case | 2019-05-24 | 2019-05-24 | Circulate NSRS for Relevant Stakeholders | 24-May-19 A | 24-May-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A1140 | HYA Fuel Handling Essential Safety Case | 2019-05-24 | 2019-05-24 | Station agree NSRS | 24-May-19 A | 24-May-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A3260 | HYA Fuel Handling Essential Safety Case | 2019-05-24 | 2019-05-24 | Issue final NSRS | 24-May-19 A | 24-May-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6920 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-27 | 2019-08-27 | Prepare Boilers and Gas Circulator Performance Draft EAN | 27-May-19 A | 27-Aug-19 A | 65 | 0 | 64 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8160 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-05-27 | Issue Component Life Assessment Specification to EDF Review. | 27-May-19 A | 27-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8230 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-05-27 | Issue Standpipe and Guide Tube Integrity Assessment Specification to EDF Review. | 27-May-19 A | 27-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8300 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-05-27 | Issue Degradation of Boilers Specification to EDF Review. | 27-May-19 A | 27-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A3320 | HRA Fuel Handling Essential Safety Case | 2019-05-27 | 2019-12-02 | Send NSRS to ONR to determine level of review required (Acknowledgement or Agreement) | 27-May-19 A | 02-Dec-19 A | 134 | 0 | 134 | 100% |  | Completed
ER6650LT | W226 | W226.A3320 | HYA Fuel Handling Essential Safety Case | 2019-05-27 | 2019-12-02 | Send NSRS to ONR to determine level of review required (Acknowledgement or Agreement) | 27-May-19 A | 02-Dec-19 A | 134 | 0 | 134 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8240 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-28 | 2019-05-29 | Standpipe and Guide Tube Integrity Assessment Specification Reviewed by EDF SQEP | 28-May-19 A | 29-May-19 A | 2 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8310 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-28 | 2019-05-29 | Degradation of Boilers Specification Reviewed by EDF SQEP | 28-May-19 A | 29-May-19 A | 2 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2010 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-28 | 2019-08-01 | Validate codes and methods against logged flux detector response | 28-May-19 A | 01-Aug-19 A | 48 | 0 | 48 | 100% |  | Completed
ER6371LT | W202 | W202.A1110 | HRA Reactors Shutdown Essential Safety Cases | 2019-05-28 | 2019-05-28 | Initial high level scope of programme | 28-May-19 A | 28-May-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A1110 | HYA Reactors Shutdown Essential Safety Cases | 2019-05-28 | 2019-05-28 | Initial high level scope of programme | 28-May-19 A | 28-May-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14890 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-28 | 2019-05-28 | Review of/Changes to Emergency Arrangements - Draft and issue RFS (Not Req'd 28.05.19 GW) | 28-May-19 A | 28-May-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14900 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-28 | 2019-05-28 | Review of/Changes to Emergency Arrangements - Supplier prepare and issue Offer (Not Req'd 28.05.19 GW) | 28-May-19 A | 28-May-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14910 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-28 | 2019-05-28 | Review of/Changes to Emergency Arrangements - Review Offer, prepare and issue CI (Not Req'd 28.05.19 GW) | 28-May-19 A | 28-May-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14920 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-28 | 2019-05-28 | Review of/Changes to Emergency Arrangements - Supplier mobilisation time (Not Req'd 28.05.19 GW) | 28-May-19 A | 28-May-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14885 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-28 | 2019-07-29 | RFS - Review of/Changes to Emergency Arrangements Summary (Not Req'd 28.05.19 GW) | 28-May-19 A | 29-Jul-19 A | 45 | 0 | 45 | 100% |  | Completed
ER6244LT | W220 | A3260 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2019-05-02 | 2019-05-02 | Issue final NSRS | 29-May-19 A | 29-May-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A1140 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2019-05-07 | 2019-05-24 | Station agree NSRS | 29-May-19 A | 29-May-19 A | 14 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A3270 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2019-05-07 | 2019-05-24 | DA & INA agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 29-May-19 A | 29-May-19 A | 14 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A3290 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2019-05-24 | NSRS for HPB and HNB agreed by stakeholders EC NNNNN <Enter Paper Title Here> (Cat 1 Milestone) | 29-May-19 A | 29-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1120 | HRA Reactors Shutdown Essential Safety Cases | 2019-05-29 | 2019-05-30 | Define Project Control Structures (WBS/CBS/OBS/PBS) | 29-May-19 A | 30-May-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A1130 | HRA Reactors Shutdown Essential Safety Cases | 2019-05-29 | 2019-05-31 | Prepare Draft Project Definition Document (PDD) | 29-May-19 A | 31-May-19 A | 3 | 0 | 3 | 100% |  | Completed
ER6661LT | W206 | W206.A1120 | HYA Reactors Shutdown Essential Safety Cases | 2019-05-29 | 2019-05-30 | Define Project Control Structures (WBS/CBS/OBS/PBS) | 29-May-19 A | 30-May-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A1130 | HYA Reactors Shutdown Essential Safety Cases | 2019-05-29 | 2019-05-31 | Prepare Draft Project Definition Document (PDD) | 29-May-19 A | 31-May-19 A | 3 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8170 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-29 | 2019-05-29 | Component Life Assessment Specification Reviewed by EDF SQEP | 29-May-19 A | 29-May-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14580 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-29 | 2019-05-29 | Claim 2 Containment Head Document - Pre Job Brief | 29-May-19 A | 29-May-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A3310 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2019-05-28 | 2019-06-17 | Circulate NSRS for Relevant Stakeholders | 30-May-19 A | 27-Jun-19 A | 15 | 0 | 20 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3400 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-30 | 2019-06-28 | Prepare Reactor Internals Draft Report | 30-May-19 A | 28-Jun-19 A | 22 | 0 | 21 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8180 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-30 | 2019-05-30 | Address Comments on Reviewed Component Life Assessment Specification | 30-May-19 A | 30-May-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8190 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-05-30 | Issue Final Component Life Assessment Specification | 30-May-19 A | 30-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8250 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-30 | 2019-05-30 | Address Comments on Reviewed Standpipe and Guide Tube Integrity Assessment Specification | 30-May-19 A | 30-May-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8260 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-05-30 | Issue Final Standpipe and Guide Tube Integrity Assessment Specification | 30-May-19 A | 30-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8320 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-30 | 2019-05-30 | Address Comments on Reviewed Degradation of Boilers Specification | 30-May-19 A | 30-May-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8330 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-05-30 | Issue Final Degradation of Boilers Specification | 30-May-19 A | 30-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3395 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-30 | 2019-10-22 | Reactor Internals Summary | 30-May-19 A | 22-Oct-19 A | 102 | 0 | 102 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15630 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-30 | 2019-05-30 | (SCOPE REMOVED) - Tech Specs HEAD DOCUMENT Report - Pre Job Brief | 30-May-19 A | 30-May-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3330 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-31 | 2019-07-12 | Ass'ment of Graphite behaviour for Shutdown Defuelling Draft Report Verified by TSA | 31-May-19 A | 12-Jul-19 A | 31 | 0 | 30 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8200 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-31 | 2019-05-31 | Component Life Assessment Specification Completed and uploaded to CDMS | 31-May-19 A | 31-May-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8210 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-05-31 | Component Life Assessment Specification Completed | 31-May-19 A | 31-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8270 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-31 | 2019-05-31 | Standpipe and Guide Tube Integrity Assessment Specification Completed and uploaded to CDMS | 31-May-19 A | 31-May-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8280 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-05-31 | Standpipe and Guide Tube Integrity Assessment Specification Completed | 31-May-19 A | 31-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8340 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-31 | 2019-05-31 | Degradation of Boilers Specification Completed and uploaded to CDMS | 31-May-19 A | 31-May-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8350 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-05-31 | Degradation of Boilers Specification Completed | 31-May-19 A | 31-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8420 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-05-31 | Pressure Boundary Seals Specification Completed | 31-May-19 A | 31-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13370 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-05-31 | Implementation Strategy Document EAN Completed | 31-May-19 A | 31-May-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13530 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-31 | 2019-05-31 | Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) - Draft and issue RFS | 31-May-19 A | 31-May-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13525 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-31 | 2019-07-29 | RFS - Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) Summary | 31-May-19 A | 29-Jul-19 A | 42 | 0 | 42 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6120 | HNB Reactors Shutdown Essential Safety Cases | 2019-05-31 | 2019-07-25 | (SCOPE REMOVED) - Prepare Tech Specs HEAD DOCUMENT Draft Report | 31-May-19 A | 25-Jul-19 A | 40 | 0 | 39 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2920 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-03 | 2019-06-28 | Prepare Component Life Assessment Draft Report | 03-Jun-19 A | 28-Jun-19 A | 20 | 0 | 19 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3000 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-03 | 2019-06-28 | Prepare Standpipe and Guide Tube Integrity Assessment Draft Report | 03-Jun-19 A | 28-Jun-19 A | 20 | 0 | 19 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3080 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-03 | 2019-06-28 | Prepare Degradation of Boilers Draft Report | 03-Jun-19 A | 28-Jun-19 A | 20 | 0 | 19 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3560 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-03 | 2019-09-06 | Prepare MACE Dataset Development and Analysis for Minimum Temperature Issue | 03-Jun-19 A | 06-Sep-19 A | 69 | 0 | 68 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7480 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-03 | 2019-07-05 | Address Comments from EDF Review on Flux Detection Scoping Draft Report | 03-Jun-19 A | 05-Jul-19 A | 25 | 0 | 24 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11050 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-06-03 | SDM Assumptions Document Report Completed | 03-Jun-19 A | 03-Jun-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2915 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-03 | 2019-10-22 | Component Life Assessment Summary | 03-Jun-19 A | 22-Oct-19 A | 100 | 0 | 100 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2995 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-03 | 2019-10-22 | Standpipe and Guide Tube Integrity Assessment Summary | 03-Jun-19 A | 22-Oct-19 A | 100 | 0 | 100 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3075 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-03 | 2019-10-22 | Degradation of Boilers Summary | 03-Jun-19 A | 22-Oct-19 A | 100 | 0 | 100 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3555 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-03 | 2019-09-06 | MACE Dataset Development and Analysis Summary | 03-Jun-19 A | 06-Sep-19 A | 68 | 0 | 68 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13540 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-03 | 2019-06-07 | Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) - Supplier prepare and issue Offer | 03-Jun-19 A | 07-Jun-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14500 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-03 | 2019-06-14 | Reactor Coolant Chemistry Conditions - Supplier prepare and issue Offer | 03-Jun-19 A | 14-Jun-19 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15040 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-03 | 2019-06-07 | (SCOPE REMOVED) - Operator Display Requirements Draft Report - Draft and issue RFS | 03-Jun-19 A | 07-Jun-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15035 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-03 | 2019-07-25 | (SCOPE REMOVED) - RFS - Operator Display Requirements Draft Report Summary | 03-Jun-19 A | 25-Jul-19 A | 38 | 0 | 38 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15640 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-04 | 2019-06-07 | LSD Strategy Draft Report - Draft and issue RFS | 04-Jun-19 A | 07-Jun-19 A | 4 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16070 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-06-04 | Verified Impacts for the Order of Defuelling Draft EAN Issued to EDF for Technical Review. | 04-Jun-19 A | 04-Jun-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16080 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-05 | 2019-06-17 | Impacts for the Order of Defuelling Draft EAN Technically Reviewed by EDF SQEP | 05-Jun-19 A | 17-Jun-19 A | 9 | 0 | 9 | 100% |  | Completed
ER6371LT | W202 | W202.A1140 | HRA Reactors Shutdown Essential Safety Cases | 2019-06-05 | 2019-06-06 | Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 05-Jun-19 A | 06-Jun-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A1150 | HRA Reactors Shutdown Essential Safety Cases | 2019-06-05 | 2019-06-06 | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 05-Jun-19 A | 06-Jun-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A1160 | HRA Reactors Shutdown Essential Safety Cases | 2019-06-05 | 2019-06-06 | Workshop to agree scope, effort and links | 05-Jun-19 A | 06-Jun-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A1140 | HYA Reactors Shutdown Essential Safety Cases | 2019-06-05 | 2019-06-06 | Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 05-Jun-19 A | 06-Jun-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A1150 | HYA Reactors Shutdown Essential Safety Cases | 2019-06-05 | 2019-06-06 | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 05-Jun-19 A | 06-Jun-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A1160 | HYA Reactors Shutdown Essential Safety Cases | 2019-06-05 | 2019-06-06 | Workshop to agree scope, effort and links | 05-Jun-19 A | 06-Jun-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14840 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-06 | 2019-06-13 | Worker Dose and Risks from Faults Draft Report - Draft and issue RFS | 06-Jun-19 A | 13-Jun-19 A | 6 | 0 | 6 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14835 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-06 | 2019-07-30 | RFS - Worker Dose and Risks from Faults Draft Report Summary | 06-Jun-19 A | 30-Jul-19 A | 39 | 0 | 39 | 100% |  | Completed
ER6371LT | W202 | W202.A1170 | HRA Reactors Shutdown Essential Safety Cases | 2019-06-07 | 2019-06-10 | Ensure Alignment of Schedule & Estimate | 07-Jun-19 A | 10-Jun-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A1180 | HRA Reactors Shutdown Essential Safety Cases | 2019-06-07 | 2019-06-07 | Hold Risk Workshop | 07-Jun-19 A | 07-Jun-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A1170 | HYA Reactors Shutdown Essential Safety Cases | 2019-06-07 | 2019-06-10 | Ensure Alignment of Schedule & Estimate | 07-Jun-19 A | 10-Jun-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A1180 | HYA Reactors Shutdown Essential Safety Cases | 2019-06-07 | 2019-06-07 | Hold Risk Workshop | 07-Jun-19 A | 07-Jun-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10880 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-10 | 2019-08-30 | Prepare Uncertainty in SDM Calculations Draft Report | 10-Jun-19 A | 30-Aug-19 A | 59 | 0 | 58 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10875 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-10 | 2020-03-11 | Uncertainty in SDM Calculations Summary | 10-Jun-19 A | 08-May-20 A | 252 | 0 | 233 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13550 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-10 | 2019-06-14 | Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) - Review Offer, prepare and issue CI | 10-Jun-19 A | 14-Jun-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15050 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-10 | 2019-06-21 | (SCOPE REMOVED) - Operator Display Requirements Draft Report - Supplier prepare and issue Offer | 10-Jun-19 A | 21-Jun-19 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15650 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-10 | 2019-06-21 | LSD Strategy Draft Report - Supplier prepare and issue Offer | 10-Jun-19 A | 21-Jun-19 A | 10 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | W202.A1190 | HRA Reactors Shutdown Essential Safety Cases | 2019-06-10 | 2019-06-11 | Complete Risk Log with Estimates | 10-Jun-19 A | 11-Jun-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A1190 | HYA Reactors Shutdown Essential Safety Cases | 2019-06-10 | 2019-06-11 | Complete Risk Log with Estimates | 10-Jun-19 A | 11-Jun-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1300 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Hold Risk Workshop | 11-Jun-19 A | 11-Jun-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1200 | HRA Reactors Shutdown Essential Safety Cases | 2019-06-12 | 2019-07-12 | Update Schedule/Estimate from Risk Log & Add Provisions | 12-Jun-19 A | 12-Jul-19 A | 23 | 0 | 23 | 100% |  | Completed
ER6661LT | W206 | W206.A1200 | HYA Reactors Shutdown Essential Safety Cases | 2019-06-12 | 2019-07-12 | Update Schedule/Estimate from Risk Log & Add Provisions | 12-Jun-19 A | 12-Jul-19 A | 23 | 0 | 23 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14790 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-13 | 2019-07-05 | Requirements for Severe Accidents Draft Report - Draft and issue RFS | 13-Jun-19 A | 05-Jul-19 A | 17 | 0 | 16 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14785 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-13 | 2019-07-31 | RFS - Requirements for Severe Accidents Draft Report Summary | 13-Jun-19 A | 31-Jul-19 A | 35 | 0 | 35 | 100% |  | Completed
ER6243LT | W200 | A1290 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-12-24 | 2018-12-24 | Develop & resource mandatory template (HPB, HNB) | 14-Jun-19 A | 14-Jun-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14850 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-14 | 2019-06-27 | Worker Dose and Risks from Faults Draft Report - Supplier prepare and issue Offer | 14-Jun-19 A | 27-Jun-19 A | 10 | 0 | 10 | 100% |  | Completed
ER6243LT | W200 | A1320 | REGION 1 Reactors Shutdown Safety Cases Programme | 2019-01-04 | 2019-01-04 | Baseline Plan to Verification Commenced (T-11) (HPB, HNB) | 17-Jun-19 A | 17-Jun-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13560 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-17 | 2019-06-28 | Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) - Supplier mobilisation time | 17-Jun-19 A | 28-Jun-19 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14510 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-17 | 2019-06-21 | Reactor Coolant Chemistry Conditions - Review Offer, prepare and issue CI | 17-Jun-19 A | 21-Jun-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1350 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Prepare Draft Project Definition Document (PDD) | 18-Jun-19 A | 17-Jul-19 A | 15 | 0 | 21 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16090 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-18 | 2019-07-30 | TSA Address Comments on TR'd Impacts for the Order of Defuelling Draft EAN | 18-Jun-19 A | 30-Jul-19 A | 31 | 0 | 30 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1260 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Define Project Control Structures (WBS/CBS/OBS/PBS) | 18-Jun-19 A | 26-Jun-19 A | 5 | 0 | 6 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13630 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-24 | 2019-06-28 | Compliance Scoping - Draft Task Sheet | 24-Jun-19 A | 28-Jun-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13625 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-24 | 2019-07-01 | RFS - Compliance Scoping Summary | 24-Jun-19 A | 01-Jul-19 A | 6 | 0 | 6 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14520 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-24 | 2019-07-05 | Reactor Coolant Chemistry Conditions - Supplier mobilisation time | 24-Jun-19 A | 05-Jul-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15060 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-24 | 2019-06-28 | (SCOPE REMOVED) - Operator Display Requirements Draft Report - Review Offer, prepare and issue CI | 24-Jun-19 A | 28-Jun-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15660 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-24 | 2019-06-28 | LSD Strategy Draft Report - Review Offer, prepare and issue CI | 24-Jun-19 A | 28-Jun-19 A | 5 | 0 | 4 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1270 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 25-Jun-19 A | 17-Jul-19 A | 10 | 0 | 16 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1280 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 25-Jun-19 A | 17-Jul-19 A | 10 | 0 | 16 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1510 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Workshop to agree scope, effort and links | 25-Jun-19 A | 25-Jun-19 A | 10 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4370 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-07-19 | Fault Schedule Review (Plant Based Faults) Draft Report Verified by TSA | 25-Jun-19 A | 19-Jul-19 A | 19 | 0 | 18 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4450 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-07-19 | Fault Schedule Review (Harzards) Draft Report Verified by TSA | 25-Jun-19 A | 19-Jul-19 A | 19 | 0 | 18 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4520 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-06-25 | (SCOPE REMOVED) - Prepare RADCONs Draft Report | 25-Jun-19 A | 25-Jun-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4530 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-06-25 | (SCOPE REMOVED) - RADCONs Draft Report Verified by TSA | 25-Jun-19 A | 25-Jun-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4540 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-06-25 | (SCOPE REMOVED) - Verified RADCONs Draft Report Issued to EDF for Technical Review. | 25-Jun-19 A | 25-Jun-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4550 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-06-25 | (SCOPE REMOVED) - RADCONs Draft Report Technically Reviewed by EDF SQEP | 25-Jun-19 A | 25-Jun-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4560 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-06-25 | (SCOPE REMOVED) - TSA Address Comments on TR'd RADCONs Draft Report | 25-Jun-19 A | 25-Jun-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4570 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-06-25 | (SCOPE REMOVED) - TSA Issue Final RADCONs Report | 25-Jun-19 A | 25-Jun-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4580 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-06-25 | (SCOPE REMOVED) - RADCONs Report TR Completed and uploaded to CDMS | 25-Jun-19 A | 25-Jun-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4590 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-06-25 | (SCOPE REMOVED) - RADCONs Report Completed | 25-Jun-19 A | 25-Jun-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4620 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-06-25 | (SCOPE REMOVED) - Verified Removal of Claims on 2nd and 3rd Shutdown/Holdown Sys Draft Report Issued to EDF for TR | 25-Jun-19 A | 25-Jun-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4630 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-06-25 | (SCOPE REMOVED) - Removal of Claims on 2nd and 3rd Shutdown/Holdown Sys Draft Report TR'd by EDF SQEP | 25-Jun-19 A | 25-Jun-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4640 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-06-25 | (SCOPE REMOVED) - TSA Address Comments on TR'd Removal of Claims on 2nd and 3rd Shutdown/Holdown Sys Draft Report | 25-Jun-19 A | 25-Jun-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4650 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-06-25 | (SCOPE REMOVED) - TSA Issue Final Removal of Claims on Secondary and Tertiary Shutdown/Holdown Sys Report | 25-Jun-19 A | 25-Jun-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4660 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-06-25 | (SCOPE REMOVED) - Removal of Claims on 2nd and 3rd Shutdown/Holdown Sys Report TR Completed and uploaded to CDMS | 25-Jun-19 A | 25-Jun-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4670 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-06-25 | (SCOPE REMOVED) - Removal of Claims on Secondary and Tertiary Shutdown/Holdown Sys Report Completed | 25-Jun-19 A | 25-Jun-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A9460 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-08-27 | Prepare Boiler Control and Protection Draft Report | 25-Jun-19 A | 27-Aug-19 A | 45 | 0 | 44 | 100% |  | Completed
ER6370LT | W201 | ER6370.A9540 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-08-27 | Prepare Reactor Cooling Systems Draft Report | 25-Jun-19 A | 27-Aug-19 A | 45 | 0 | 44 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10690 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-06-25 | (SCOPE REMOVED) - Impact on Decommissioning Plans - (Scope Removed) | 25-Jun-19 A | 25-Jun-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10700 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-06-25 | (SCOPE REMOVED) - Nuclear Liabilities - (Scope Removed) | 25-Jun-19 A | 25-Jun-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4515 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-06-25 | (SCOPE REMOVED) - RADCONs Summary | 25-Jun-19 A | 25-Jun-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4595 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-06-25 | (SCOPE REMOVED) - Removal of Claims on the Secondary and Tertiary Shutdown / Holdown Systems Summary | 25-Jun-19 A | 25-Jun-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A9455 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-12-06 | Boiler Control and Protection Summary | 25-Jun-19 A | 06-Dec-19 A | 117 | 0 | 117 | 100% |  | Completed
ER6370LT | W201 | ER6370.A9535 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-12-06 | Reactor Cooling Systems Summary | 25-Jun-19 A | 06-Dec-19 A | 118 | 0 | 118 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14590 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-06-25 | (SCOPE REMOVED) - RADCONs - Draft and issue RFS | 25-Jun-19 A | 25-Jun-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14600 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-06-25 | (SCOPE REMOVED) - RADCONs - Supplier prepare and issue Offer | 25-Jun-19 A | 25-Jun-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14610 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-06-25 | (SCOPE REMOVED) - RADCONs - Review Offer, prepare and issue CI | 25-Jun-19 A | 25-Jun-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14620 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-06-25 | (SCOPE REMOVED) - RADCONs - Supplier mobilisation time | 25-Jun-19 A | 25-Jun-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14630 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-06-25 | (SCOPE REMOVED) - RADCONs - Pre Job Brief | 25-Jun-19 A | 25-Jun-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14585 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-06-25 | (SCOPE REMOVED) - RFS - RADCONs Summary | 25-Jun-19 A | 25-Jun-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14740 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-06-25 | (SCOPE REMOVED) - Removal of Claims on the 2nd and 3rd Shutdown / Holdown Systems - Draft and issue RFS | 25-Jun-19 A | 25-Jun-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14750 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-06-25 | (SCOPE REMOVED) - Removal of Claims on the 2nd and 3rd Shutdown / Holdown Systems - Supplier prepare and issue Offer | 25-Jun-19 A | 25-Jun-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14735 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-06-25 | (SCOPE REMOVED) - RFS - Removal of Claims on the 2nd and 3rd Shutdown / Holdown Systems Summary | 25-Jun-19 A | 25-Jun-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4600 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-06-25 | (SCOPE REMOVED) - Prepare Removal of Claims on the Secondary and Tertiary Shutdown / Holdown Systems Draft Report | 25-Jun-19 A | 25-Jun-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4610 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-06-25 | (SCOPE REMOVED) - Removal of Claims on Secondary and Tertiary Shutdown/Holdown Sys Draft Report Verified by TSA | 25-Jun-19 A | 25-Jun-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14760 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-06-25 | (SCOPE REMOVED) - Removal of Claims on the 2nd and 3rd Shutdown / Holdown Systems - Review Offer, prepare and issue CI | 25-Jun-19 A | 25-Jun-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14770 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-06-25 | (SCOPE REMOVED) - Removal of Claims on the 2nd and 3rd Shutdown / Holdown Systems - Supplier mobilisation time | 25-Jun-19 A | 25-Jun-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14780 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-25 | 2019-06-25 | (SCOPE REMOVED) - Removal of Claims on the 2nd and 3rd Shutdown / Holdown Systems - Pre Job Brief | 25-Jun-19 A | 25-Jun-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6244LT | W220 | A3090 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2019-06-18 | NSRS Complete - HPB and HNB | 27-Jun-19 A | 27-Jun-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A3100 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2019-08-09 | NSRS Complete - HRA and HYA | 27-Jun-19 A | 27-Jun-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A3320 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2019-06-18 | 2019-06-18 | Send NSRS to ONR to determine level of review required (Acknowledgement or Agreement) | 27-Jun-19 A | 27-Jun-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A3360 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2019-05-01 | 2019-05-01 | Issue final NSRS | 27-Jun-19 A | 27-Jun-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A3370 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2019-05-02 | 2019-07-12 | Station agree NSRS | 27-Jun-19 A | 27-Jun-19 A | 50 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A3380 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2019-07-19 | 2019-08-08 | Circulate NSRS for Relevant Stakeholders | 27-Jun-19 A | 27-Jun-19 A | 15 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A3390 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2019-04-08 | 2019-04-30 | Incorporate INA, Station, DA (peer) comments | 27-Jun-19 A | 27-Jun-19 A | 15 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A3400 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2019-05-02 | 2019-07-12 | DA & INA agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 27-Jun-19 A | 27-Jun-19 A | 50 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A3420 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2019-07-12 | NSRS for HYA and HRA agreed by stakeholders EC NNNNN <Enter Paper Title Here> (Cat 1 Milestone) | 27-Jun-19 A | 27-Jun-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A3430 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2019-08-09 | 2019-08-09 | Send NSRS to ONR to determine level of review required (Acknowledgement or Agreement) | 27-Jun-19 A | 27-Jun-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A3440 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2019-07-18 | 2019-07-18 | NSRS Presented to NSC (for complex CAT 1 cases) | 27-Jun-19 A | 27-Jun-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A3450 | REGION 1 Defuelling Programme Fuel Handling Safety Case | 2019-04-01 | 2019-04-05 | Hold Case Conference as Appropriate | 27-Jun-19 A | 27-Jun-19 A | 3 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2020 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-06-28 | Issue Establish Codes and Methods for Safety Case Draft Report to EDF for Review. | 28-Jun-19 A | 28-Jun-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2930 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-28 | 2019-07-12 | Component Life Assessment Draft Report Verified by TSA | 28-Jun-19 A | 12-Jul-19 A | 11 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3010 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-28 | 2019-07-12 | Standpipe and Guide Tube Integrity Assessment Draft Report Verified by TSA | 28-Jun-19 A | 12-Jul-19 A | 11 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3090 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-28 | 2019-07-12 | Degradation of Boilers Draft Report Verified by TSA | 28-Jun-19 A | 12-Jul-19 A | 11 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3410 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-28 | 2019-07-12 | Reactor Internals Draft Report Verified by TSA | 28-Jun-19 A | 12-Jul-19 A | 11 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7300 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-06-28 | Code Validation from Operational Reactor Report Completed | 28-Jun-19 A | 28-Jun-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14860 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-28 | 2019-07-05 | Worker Dose and Risks from Faults Draft Report - Review Offer, prepare and issue CI | 28-Jun-19 A | 05-Jul-19 A | 6 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15670 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-28 | 2019-07-22 | LSD Strategy Draft Report - Supplier mobilisation time | 28-Jun-19 A | 22-Jul-19 A | 17 | 0 | 17 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2030 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-01 | 2019-08-02 | Establish Codes and Methods for Safety Case Draft Report Reviewed by EDF SQEP | 01-Jul-19 A | 02-Aug-19 A | 25 | 0 | 24 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7520 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-01 | 2019-07-12 | Prepare Safety Rod Insertion Scoping Draft Report | 01-Jul-19 A | 12-Jul-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7515 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-01 | 2019-07-18 | Safety Rod Insertion Scoping Summary | 01-Jul-19 A | 18-Jul-19 A | 13 | 0 | 13 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13640 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-01 | 2019-07-01 | Compliance Scoping - Supplier prepare and issue Offer (Remove from Scope) | 01-Jul-19 A | 01-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13650 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-01 | 2019-07-01 | Compliance Scoping - Review Offer, prepare and issue CI (Remove from Scope) | 01-Jul-19 A | 01-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13660 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-01 | 2019-07-01 | Compliance Scoping - Supplier mobilisation time (Remove from Scope) | 01-Jul-19 A | 01-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13670 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-01 | 2019-07-01 | Compliance Scoping - Pre Job Brief | 01-Jul-19 A | 01-Jul-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15890 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-01 | 2019-07-05 | Summary of Compliance with RADWASTE - Draft and issue RFS | 01-Jul-19 A | 05-Jul-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15885 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-01 | 2019-07-31 | RFS - Summary of Compliance with RADWASTE Summary | 01-Jul-19 A | 31-Jul-19 A | 23 | 0 | 23 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16140 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-01 | 2020-01-31 | Phase 2: Programme 6.1 Station Documentation and Implementation Strategy | 01-Jul-19 A | 31-Jan-20 A | 151 | 0 | 150 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11360 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-01 | 2019-08-21 | Optioneering Report | 01-Jul-19 A | 21-Aug-19 A | 38 | 0 | 37 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7600 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-07-02 | Issued SDM Assessments with uncertainties / sensitivity studies Draft Report to EDF for Review. | 02-Jul-19 A | 02-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7610 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-03 | 2019-08-01 | SDM Assessments with uncertainties / sensitivity studies Draft Report Reviewed by EDF SQEP | 03-Jul-19 A | 01-Aug-19 A | 22 | 0 | 21 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7490 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-07-05 | Issue Final Flux Detection Scoping Report | 05-Jul-19 A | 05-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7500 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-08 | 2019-07-19 | Flux Detection Scoping Report Completed and Uploaded to CDMS | 08-Jul-19 A | 19-Jul-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10340 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-08 | 2019-07-19 | Structures and Equipment Integrity Draft Report Verified by TSA | 08-Jul-19 A | 19-Jul-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14800 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-08 | 2019-07-19 | Requirements for Severe Accidents Draft Report - Supplier prepare and issue Offer | 08-Jul-19 A | 19-Jul-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14870 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-08 | 2019-07-29 | Worker Dose and Risks from Faults Draft Report - Supplier mobilisation time | 08-Jul-19 A | 29-Jul-19 A | 16 | 0 | 15 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15900 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-08 | 2019-07-19 | Summary of Compliance with RADWASTE - Supplier prepare and issue Offer | 08-Jul-19 A | 19-Jul-19 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8430 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-09 | 2019-09-18 | Prepare Reactor Coolant Chemistry Conditions Draft Report | 09-Jul-19 A | 18-Sep-19 A | 51 | 0 | 50 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11230 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-09 | 2020-01-02 | Reactor Coolant Chemistry Conditions Summary | 09-Jul-19 A | 02-Jan-20 A | 123 | 0 | 123 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10540 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-11 | 2019-08-30 | ALARP / BAT/ BPM Draft Report Verified by TSA | 11-Jul-19 A | 30-Aug-19 A | 36 | 0 | 35 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2940 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-07-12 | Verified Component Life Assessment Draft Report Issued to EDF for Technical Review. | 12-Jul-19 A | 12-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3020 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-07-12 | Verified Standpipe and Guide Tube Integrity Assessment Draft Report Issued to EDF for Technical Review. | 12-Jul-19 A | 12-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3100 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-07-12 | Verified Degradation of Boilers Draft Report Issued to EDF for Technical Review. | 12-Jul-19 A | 12-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3340 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-07-12 | Verified Ass'ment of Graphite behaviour for Shutdown Defuelling Draft Report Issued to EDF for Technical Review. | 12-Jul-19 A | 12-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3420 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-07-12 | Verified Reactor Internals Draft Report Issued to EDF for Technical Review. | 12-Jul-19 A | 12-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7530 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-07-12 | Issued Safety Rod Insertion Scoping Draft Report to EDF for Review. | 12-Jul-19 A | 12-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14530 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-12 | 2019-07-12 | Reactor Coolant Chemistry Conditions - Pre Job Brief | 12-Jul-19 A | 12-Jul-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2950 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-15 | 2019-08-23 | Component Life Assessment Draft Report Technically Reviewed by EDF SQEP | 15-Jul-19 A | 23-Aug-19 A | 30 | 0 | 29 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3030 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-15 | 2019-08-23 | Standpipe and Guide Tube Integrity Assessment Draft Report Technically Reviewed by EDF SQEP | 15-Jul-19 A | 23-Aug-19 A | 30 | 0 | 29 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3110 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-15 | 2019-08-23 | Degradation of Boilers Draft Report Technically Reviewed by EDF SQEP | 15-Jul-19 A | 23-Aug-19 A | 30 | 0 | 29 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3170 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-15 | 2019-08-08 | Pressure Boundary Seals Draft Report Verified by TSA | 15-Jul-19 A | 08-Aug-19 A | 19 | 0 | 18 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3350 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-15 | 2019-08-01 | Ass'ment of Graphite behaviour for Shutdown Defuelling Draft Report Technically Reviewed by EDF SQEP | 15-Jul-19 A | 01-Aug-19 A | 14 | 0 | 13 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3430 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-15 | 2019-08-23 | Reactor Internals Draft Report Technically Reviewed by EDF SQEP | 15-Jul-19 A | 23-Aug-19 A | 30 | 0 | 29 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3890 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-15 | 2019-09-27 | Model and Datasets Part 2 Reports Verified by TSA | 15-Jul-19 A | 27-Sep-19 A | 54 | 0 | 53 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7570 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-15 | 2019-07-18 | Safety Rod Insertion Scoping Report Completed and Uploaded to CDMS | 15-Jul-19 A | 18-Jul-19 A | 4 | 0 | 3 | 100% |  | Completed
ER6371LT | W202 | W202.A1210 | HRA Reactors Shutdown Essential Safety Cases | 2019-07-15 | 2019-07-16 | Add Data to IRM Paper | 15-Jul-19 A | 16-Jul-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A1210 | HYA Reactors Shutdown Essential Safety Cases | 2019-07-15 | 2019-07-16 | Add Data to IRM Paper | 15-Jul-19 A | 16-Jul-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1290 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Ensure Alignment of Schedule & Estimate | 15-Jul-19 A | 16-Jul-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1310 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Complete Risk Log with Estimates | 15-Jul-19 A | 16-Jul-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2860 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-07-17 | Issue Civil Integrity Overview Draft EAN to EDF for Review. | 17-Jul-19 A | 17-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13870 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-17 | 2019-07-17 | Shutdown Margin Head Document - Pre Job Brief | 17-Jul-19 A | 17-Jul-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1220 | HRA Reactors Shutdown Essential Safety Cases | 2019-07-17 | 2019-07-19 | PCL Validate & Approve Baseline Package for PRC Submission | 17-Jul-19 A | 19-Jul-19 A | 3 | 0 | 3 | 100% |  | Completed
ER6661LT | W206 | W206.A1220 | HYA Reactors Shutdown Essential Safety Cases | 2019-07-17 | 2019-07-19 | PCL Validate & Approve Baseline Package for PRC Submission | 17-Jul-19 A | 19-Jul-19 A | 3 | 0 | 3 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1320 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Update Schedule/Estimate from Risk Log & Add Provisions | 17-Jul-19 A | 18-Jul-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2870 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-18 | 2019-08-01 | Civil Integrity Overview Draft EAN Reviewed by EDF SQEP | 18-Jul-19 A | 01-Aug-19 A | 11 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7540 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-18 | 2019-07-18 | Safety Rod Insertion Scoping Draft Report Reviewed by EDF SQEP (Remove from Scope) | 18-Jul-19 A | 18-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7550 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-18 | 2019-07-18 | Address Comments from EDF Review on Safety Rod Insertion Scoping Draft Report (Remove from Scope) | 18-Jul-19 A | 18-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7560 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-07-18 | Issue Final Safety Rod Insertion Scoping Report Report (Remove from Scope) | 18-Jul-19 A | 18-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7580 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-07-18 | Safety Rod Insertion Scoping Report Completed | 18-Jul-19 A | 18-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4380 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-07-19 | Verified Fault Schedule Review (Plant Based Faults) Draft Report Issued to EDF for Technical Review. | 19-Jul-19 A | 19-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4460 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-07-19 | Verified Fault Schedule Review (Harzards) Draft Report Issued to EDF for Technical Review. | 19-Jul-19 A | 19-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7510 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-07-19 | Flux Detection Scoping Report Completed | 19-Jul-19 A | 19-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10350 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-07-19 | Verified Structures and Equipment Integrity Draft Report Issued to EDF for Technical Review. | 19-Jul-19 A | 19-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1330 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Add Data to IRM Paper | 19-Jul-19 A | 22-Jul-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4390 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-22 | 2019-09-27 | Fault Schedule Review (Plant Based Faults) Draft Report Technically Reviewed by EDF SQEP | 22-Jul-19 A | 27-Sep-19 A | 49 | 0 | 48 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4470 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-22 | 2019-09-27 | Fault Schedule Review (Harzards) Draft Report Technically Reviewed by EDF SQEP | 22-Jul-19 A | 27-Sep-19 A | 49 | 0 | 48 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7790 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-22 | 2019-10-31 | Prepare Shutdown Margin Head Document | 22-Jul-19 A | 31-Oct-19 A | 73 | 0 | 72 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10360 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-22 | 2019-08-23 | Structures and Equipment Integrity Draft Report Technically Reviewed by EDF SQEP | 22-Jul-19 A | 23-Aug-19 A | 25 | 0 | 24 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10620 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-22 | 2019-08-30 | In Reactor NSP Compliance and Risk Report - Draft Report Verified by TSA | 22-Jul-19 A | 30-Aug-19 A | 29 | 0 | 28 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7785 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-22 | 2020-03-20 | Shutdown Margin Head Document Summary | 22-Jul-19 A | 26-Jun-20 A | 223 | 0 | 236 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14810 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-22 | 2019-07-24 | Requirements for Severe Accidents Draft Report - Review Offer, prepare and issue CI | 22-Jul-19 A | 24-Jul-19 A | 3 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15910 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-22 | 2019-07-26 | Summary of Compliance with RADWASTE - Review Offer, prepare and issue CI | 22-Jul-19 A | 26-Jul-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | A16210 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-09-12 | Support System Report Issued to CDMS (HYA, HAR) | 23-Jul-19 A | 23-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A16770 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Support System Report Review and Acceptance (HYA, HAR) | 23-Jul-19 A | 23-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7660 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-23 | 2019-07-23 | Hold Meeting for Optioneering of timing of safety group insertion | 23-Jul-19 A | 23-Jul-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7680 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-23 | 2019-07-23 | Hold Meeting for Optioneering pattern of defuelling | 23-Jul-19 A | 23-Jul-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13680 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-23 | 2019-07-29 | Compliance Sensitivities Study - Draft Task Sheet | 23-Jul-19 A | 29-Jul-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13675 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-23 | 2019-07-30 | RFS - Compliance Sensitivities Study Summary | 23-Jul-19 A | 30-Jul-19 A | 6 | 0 | 6 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15680 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-23 | 2019-07-23 | LSD Strategy Draft Report - Pre Job Brief | 23-Jul-19 A | 23-Jul-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16640 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-23 | 2019-07-23 | Thermal Analysis of FPU - FEAT - Draft and issue RFS | 23-Jul-19 A | 23-Jul-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16650 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-23 | 2019-07-23 | Thermal Analysis of FPU - FEAT - Supplier prepare and issue Offer | 23-Jul-19 A | 23-Jul-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16660 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-23 | 2019-07-23 | Thermal Analysis of FPU - FEAT - Review Offer, prepare and issue CI | 23-Jul-19 A | 23-Jul-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16670 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-23 | 2019-07-23 | Thermal Analysis of FPU - FEAT - Supplier mobilisation time | 23-Jul-19 A | 23-Jul-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16680 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-23 | 2019-07-23 | Thermal Analysis of FPU - FEAT - Pre Job Brief | 23-Jul-19 A | 23-Jul-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16690 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-23 | 2019-07-23 | RFS - Thermal Analysis of FPU - FEAT Summary | 23-Jul-19 A | 23-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1340 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | PCL Validate & Approve Baseline Package for PRC Submission | 23-Jul-19 A | 25-Jul-19 A | 3 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6200 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-24 | 2019-07-31 | Prepare LSD Strategy Draft Report | 24-Jul-19 A | 31-Jul-19 A | 6 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8060 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-24 | 2019-10-11 | Prepare Optioneering of Timing Meeting Minutes | 24-Jul-19 A | 11-Oct-19 A | 57 | 0 | 56 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8080 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-24 | 2019-10-11 | Prepare Optioneering Pattern of Defuelling Meeting Minutes | 24-Jul-19 A | 11-Oct-19 A | 57 | 0 | 56 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16510 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-24 | 2019-07-24 | ability of the PCPV to satisfy support in-resident FPUs - Draft and issue RFS | 24-Jul-19 A | 24-Jul-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16520 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-24 | 2019-07-24 | ability of the PCPV to satisfy support in-resident FPUs - Supplier prepare and issue Offer | 24-Jul-19 A | 24-Jul-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16530 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-24 | 2019-07-24 | ability of the PCPV to satisfy support in-resident FPUs - Review Offer, prepare and issue CI | 24-Jul-19 A | 24-Jul-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16540 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-24 | 2019-07-24 | ability of the PCPV to satisfy support in-resident FPUs - Supplier mobilisation time | 24-Jul-19 A | 24-Jul-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16550 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-24 | 2019-07-24 | ability of the PCPV to satisfy support in-resident FPUs - Pre Job Brief | 24-Jul-19 A | 24-Jul-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16465 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-24 | 2019-07-24 | RFS - ability of the PCPV to satisfy support in-resident FPUs Summary | 24-Jul-19 A | 24-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16560 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-24 | 2019-08-05 | Prepare Thermal Analysis of FPU - FEAT - Report - QA Grade 2 | 24-Jul-19 A | 05-Aug-19 A | 9 | 0 | 8 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16385 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-24 | 2019-09-23 | Thermal Analysis of FPU - FEAT - Report - QA Grade 2 Summary | 24-Jul-19 A | 23-Sep-19 A | 42 | 0 | 42 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6130 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-25 | 2019-07-25 | (SCOPE REMOVED) - Tech Specs HEAD DOCUMENT Draft Report Verified by TSA | 25-Jul-19 A | 25-Jul-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6140 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-07-25 | (SCOPE REMOVED) - Verified Tech Specs HEAD DOCUMENT Draft Report Issued to EDF for Technical Review. | 25-Jul-19 A | 25-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6150 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-25 | 2019-07-25 | (SCOPE REMOVED) - Tech Specs HEAD DOCUMENT Draft Report Technically Reviewed by EDF SQEP | 25-Jul-19 A | 25-Jul-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6160 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-25 | 2019-07-25 | (SCOPE REMOVED) - TSA Address Comments on TR'd Tech Specs HEAD DOCUMENT Draft Report | 25-Jul-19 A | 25-Jul-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6170 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-07-25 | (SCOPE REMOVED) - TSA Issue Final Tech Specs HEAD DOCUMENT Report | 25-Jul-19 A | 25-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6180 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-25 | 2019-07-25 | (SCOPE REMOVED) - Tech Specs HEAD DOCUMENT Report TR Completed and uploaded to CDMS (Not Req'd 28.05.19 GW) | 25-Jul-19 A | 25-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6190 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-07-25 | (SCOPE REMOVED) - Tech Specs HEAD DOCUMENT Report Completed | 25-Jul-19 A | 25-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A9620 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-25 | 2019-07-25 | (SCOPE REMOVED) - Prepare Operator Display Requirements Draft Report | 25-Jul-19 A | 25-Jul-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A9630 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-25 | 2019-07-25 | (SCOPE REMOVED) - Operator Display Requirements Draft Report Verified by TSA | 25-Jul-19 A | 25-Jul-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A9640 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-07-25 | (SCOPE REMOVED) - Verified Operator Display Requirements Draft Report Issued to EDF for Technical Review. | 25-Jul-19 A | 25-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A9650 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-25 | 2019-07-25 | (SCOPE REMOVED) - Operator Display Requirements Draft Report Technically Reviewed by EDF SQEP | 25-Jul-19 A | 25-Jul-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A9660 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-25 | 2019-07-25 | (SCOPE REMOVED) - TSA Address Comments on TR'd Operator Display Requirements Draft Report | 25-Jul-19 A | 25-Jul-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A9670 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-07-25 | (SCOPE REMOVED) - TSA Issue Final Operator Display Requirements Report | 25-Jul-19 A | 25-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A9680 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-25 | 2019-07-25 | (SCOPE REMOVED) - Operator Display Requirements Report TR Completed and uploaded to CDMS | 25-Jul-19 A | 25-Jul-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A9690 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-07-25 | (SCOPE REMOVED) - Operator Display Requirements Report Completed | 25-Jul-19 A | 25-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A9615 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-25 | 2019-07-25 | (SCOPE REMOVED) - Operator Display Requirements Summary | 25-Jul-19 A | 25-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14820 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-25 | 2019-07-30 | Requirements for Severe Accidents Draft Report - Supplier mobilisation time | 25-Jul-19 A | 30-Jul-19 A | 4 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15070 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-25 | 2019-07-25 | (SCOPE REMOVED) - Operator Display Requirements Draft Report - Supplier mobilisation time | 25-Jul-19 A | 25-Jul-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15080 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-25 | 2019-07-25 | (SCOPE REMOVED) - Operator Display Requirements Draft Report - Pre Job Brief | 25-Jul-19 A | 25-Jul-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16430 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-25 | 2019-08-30 | Prepare Consideration of the ability of the PCPV to satisfactorily support in- resident FPUs - EAN - QA Grade 2 | 25-Jul-19 A | 30-Aug-19 A | 26 | 0 | 25 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16225 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-25 | 2019-10-16 | Consideration of the ability of the PCPV to satisfactorily support in- resident FPUs - EAN - QA Grade 2 Summary | 25-Jul-19 A | 16-Oct-19 A | 58 | 0 | 58 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7670 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-29 | 2019-07-29 | Hold Meeting for SDM - optioneering of confidence required | 29-Jul-19 A | 29-Jul-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13570 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-29 | 2019-07-29 | Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) - Pre Job Brief | 29-Jul-19 A | 29-Jul-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13690 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-29 | 2019-07-29 | Compliance Sensitivities Study - Supplier prepare and issue Offer (Remove from Scope) | 29-Jul-19 A | 29-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13700 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-29 | 2019-07-29 | Compliance Sensitivities Study - Review Offer, prepare and issue CI (Remove from Scope) | 29-Jul-19 A | 29-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13710 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-29 | 2019-07-29 | Compliance Sensitivities Study - Supplier mobilisation time (Remove from Scope) | 29-Jul-19 A | 29-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14930 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-29 | 2019-07-29 | Review of/Changes to Emergency Arrangements - Pre Job Brief | 29-Jul-19 A | 29-Jul-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15920 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-29 | 2019-07-30 | Summary of Compliance with RADWASTE - Supplier mobilisation time | 29-Jul-19 A | 30-Jul-19 A | 2 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A14090 | HRA Fuel Handling Essential Safety Case | 2019-07-29 | 2019-07-29 | Complete Risk Log with Estimates | 29-Jul-19 A | 29-Jul-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A14080 | HRA Fuel Handling Essential Safety Case | 2019-07-29 | 2019-07-29 | Hold Risk Workshop | 29-Jul-19 A | 29-Jul-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A14080 | HYA Fuel Handling Essential Safety Case | 2019-07-29 | 2019-07-29 | Hold Risk Workshop | 29-Jul-19 A | 29-Jul-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A14090 | HYA Fuel Handling Essential Safety Case | 2019-07-29 | 2019-07-29 | Complete Risk Log with Estimates | 29-Jul-19 A | 29-Jul-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4840 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-30 | 2019-09-10 | Prepare Review of/Changes to Emergency Arrangements Draft Report | 30-Jul-19 A | 10-Sep-19 A | 30 | 0 | 29 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4835 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-30 | 2019-10-11 | Review of/Changes to Emergency Arrangements Summary | 30-Jul-19 A | 11-Oct-19 A | 53 | 0 | 53 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13720 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-30 | 2019-07-30 | Compliance Sensitivities Study - Pre Job Brief | 30-Jul-19 A | 30-Jul-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14880 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-30 | 2019-07-30 | Worker Dose and Risks from Faults Draft Report - Pre Job Brief | 30-Jul-19 A | 30-Jul-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16100 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-07-30 | TSA Issue Final Impacts for the Order of Defuelling EAN | 30-Jul-19 A | 30-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8070 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-30 | 2019-10-11 | Prepare SDM Meeting Minutes | 30-Jul-19 A | 11-Oct-19 A | 53 | 0 | 52 | 100% |  | Completed
ER6243LT | W200 | A10750 | REGION 1 Reactors Shutdown Safety Cases Programme | 2018-06-28 | 2018-06-28 | Estimating Uncertainty - 2018 | 31-Jul-19 A | 31-Jul-19 A | 45 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A14830 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-31 | 2019-07-31 | Requirements for Severe Accidents Draft Report - Pre Job Brief | 31-Jul-19 A | 31-Jul-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1230 | HRA Reactors Shutdown Essential Safety Cases |  | 2019-07-31 | Gate B PRC Paper Submission | 31-Jul-19 A | 31-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1240 | HRA Reactors Shutdown Essential Safety Cases | 2019-07-31 | 2019-08-06 | PRC Members Review IRM Documentation | 31-Jul-19 A | 06-Aug-19 A | 5 | 0 | 4 | 100% |  | Completed
ER6661LT | W206 | W206.A1230 | HYA Reactors Shutdown Essential Safety Cases |  | 2019-07-31 | Gate B PRC Paper Submission | 31-Jul-19 A | 31-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1240 | HYA Reactors Shutdown Essential Safety Cases | 2019-07-31 | 2019-08-06 | PRC Members Review IRM Documentation | 31-Jul-19 A | 06-Aug-19 A | 5 | 0 | 4 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1240 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Gate B PRC Paper Submission | 31-Jul-19 A | 31-Jul-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A15930 | HNB Reactors Shutdown Essential Safety Cases | 2019-07-31 | 2019-07-31 | Summary of Compliance with RADWASTE - Pre Job Brief | 31-Jul-19 A | 31-Jul-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A5400 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-01 | 2020-03-02 | Prepare HF Compliance Assessment for Shutdown Margin Draft EAN | 01-Aug-19 A | 01-Apr-20 A | 171 | 0 | 170 | 100% |  | Completed
ER6370LT | W201 | ER6370.A5480 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-01 | 2020-03-02 | Prepare HF Compliance / Tech Spec As'ment for Core Cooling Draft EAN | 01-Aug-19 A | 01-Apr-20 A | 171 | 0 | 170 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6210 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-01 | 2019-08-23 | LSD Strategy Draft Report Verified by TSA | 01-Aug-19 A | 23-Aug-19 A | 17 | 0 | 16 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6760 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-01 | 2019-08-30 | Prepare Summary of Compliance with RADWASTE Assessment Principles Draft EAN | 01-Aug-19 A | 30-Aug-19 A | 21 | 0 | 20 | 100% |  | Completed
ER6370LT | W201 | ER6370.A5395 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-01 | 2020-03-30 | HF Compliance Assessment for Shutdown Margin Summary | 01-Aug-19 A | 30-Apr-20 A | 190 | 0 | 189 | 100% |  | Completed
ER6370LT | W201 | ER6370.A5475 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-01 | 2020-03-30 | HF Compliance / Tech Spec As'ment for Core Cooling Summary | 01-Aug-19 A | 30-Apr-20 A | 190 | 0 | 189 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6755 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-01 | 2019-10-20 | Summary of Compliance with RADWASTE Assessment Principles Summary | 01-Aug-19 A | 20-Oct-19 A | 56 | 0 | 56 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16110 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-01 | 2019-08-27 | Impacts for the Order of Defuelling EAN TR Completed and uploaded to CDMS | 01-Aug-19 A | 27-Aug-19 A | 18 | 0 | 17 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16350 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-01 | 2019-08-30 | Prepare PVCW Calculations - Dropped FPU Fault - EAN - QA Grade 2 | 01-Aug-19 A | 30-Aug-19 A | 21 | 0 | 20 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16145 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-01 | 2019-10-11 | PVCW Calculations - Dropped FPU Fault - EAN - QA Grade 2 Summary | 01-Aug-19 A | 11-Oct-19 A | 50 | 0 | 50 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16700 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-01 | 2019-10-23 | Prepare Summary Conditions Report - EAN - QA Grade 2 | 01-Aug-19 A | 23-Oct-19 A | 59 | 0 | 58 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16305 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-01 | 2020-01-15 | Summary Conditions Report - EAN - QA Grade 2 Summary | 01-Aug-19 A | 15-Jan-20 A | 115 | 0 | 115 | 100% |  | Completed
ER6378LT | W222 | W222.A14100 | HRA Fuel Handling Essential Safety Case | 2019-08-01 | 2019-09-02 | Update Schedule/Estimate from Risk Log & Add Provisions | 01-Aug-19 A | 02-Sep-19 A | 22 | 0 | 22 | 100% |  | Completed
ER6650LT | W226 | W226.A14100 | HYA Fuel Handling Essential Safety Case | 2019-08-01 | 2019-09-02 | Update Schedule/Estimate from Risk Log & Add Provisions | 01-Aug-19 A | 02-Sep-19 A | 22 | 0 | 22 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1390 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | PRC Members Review IRM Documentation | 01-Aug-19 A | 07-Aug-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1920 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-02 | 2019-10-14 | Prepare Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) | 02-Aug-19 A | 14-Oct-19 A | 51 | 0 | 50 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2880 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-02 | 2019-08-09 | Address Comments from EDF Review on Civil Integrity Overview Draft EAN | 02-Aug-19 A | 09-Aug-19 A | 6 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3360 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-02 | 2019-08-09 | TSA Address Comments on TR'd Ass'ment of Graphite behaviour for Shutdown Defuelling Draft Report | 02-Aug-19 A | 09-Aug-19 A | 6 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7620 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-02 | 2019-08-23 | Address Comments from EDF Review on SDM Assessments with uncertainties / sensitivity studies Draft Report | 02-Aug-19 A | 23-Aug-19 A | 16 | 0 | 15 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1915 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-02 | 2020-03-06 | Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) Summary | 02-Aug-19 A | 27-Mar-20 A | 166 | 0 | 166 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2040 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-05 | 2019-08-30 | Address Comments from EDF Review on Establish Codes and Methods for Safety Case Draft Report | 05-Aug-19 A | 30-Aug-19 A | 19 | 0 | 18 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16570 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-06 | 2019-08-26 | Thermal Analysis of FPU - FEAT - Report - QA Grade 2 Verified by TSA | 06-Aug-19 A | 26-Aug-19 A | 14 | 0 | 14 | 100% |  | Completed
ER6371LT | W202 | W202.A1250 | HRA Reactors Shutdown Essential Safety Cases | 2019-08-08 | 2019-08-08 | Hold PRC Meeting | 08-Aug-19 A | 08-Aug-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1260 | HRA Reactors Shutdown Essential Safety Cases |  | 2019-08-08 | Gate B PRC Paper Approval | 08-Aug-19 A | 08-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1250 | HYA Reactors Shutdown Essential Safety Cases | 2019-08-08 | 2019-08-08 | Hold PRC Meeting | 08-Aug-19 A | 08-Aug-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1260 | HYA Reactors Shutdown Essential Safety Cases |  | 2019-08-08 | Gate B PRC Paper Approval | 08-Aug-19 A | 08-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1360 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Hold PRC Meeting | 08-Aug-19 A | 08-Aug-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1440 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Gate B PRC Paper Approval | 08-Aug-19 A | 08-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2890 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-08-09 | Issue Civil Integrity Overview Final EAN | 09-Aug-19 A | 09-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3370 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-08-09 | TSA Issue Final Ass'ment of Graphite behaviour for Shutdown Defuelling Report | 09-Aug-19 A | 09-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4040 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-09 | 2019-08-23 | Prepare Specification for Analysis Draft Report | 09-Aug-19 A | 23-Aug-19 A | 11 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4035 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-09 | 2019-08-30 | Specification for Analysis Summary | 09-Aug-19 A | 30-Aug-19 A | 15 | 0 | 14 | 100% |  | Completed
ER6371LT | W202 | W202.A1270 | HRA Reactors Shutdown Essential Safety Cases | 2019-08-09 | 2019-08-12 | Modify Estimate, Schedule & Risk Log as Required | 09-Aug-19 A | 12-Aug-19 A | 2 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A1270 | HYA Reactors Shutdown Essential Safety Cases | 2019-08-09 | 2019-08-12 | Modify Estimate, Schedule & Risk Log as Required | 09-Aug-19 A | 12-Aug-19 A | 6 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1370 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Modify Estimate, Schedule & Risk Log as Required | 09-Aug-19 A | 09-Aug-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2900 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-12 | 2019-08-19 | Civil Integrity Overview EAN Completed and uploaded to CDMS | 12-Aug-19 A | 19-Aug-19 A | 6 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3380 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-12 | 2019-08-19 | Ass'ment of Graphite behaviour for Shutdown Defuelling Report TR Completed and uploaded to CDMS | 12-Aug-19 A | 19-Aug-19 A | 6 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1380 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Modify IRM Paper as Required | 12-Aug-19 A | 12-Aug-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1290 | HRA Reactors Shutdown Essential Safety Cases |  | 2019-08-13 | Gate B MS PRC Paper Submission | 13-Aug-19 A | 13-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1280 | HRA Reactors Shutdown Essential Safety Cases | 2019-08-13 | 2019-08-13 | Modify IRM Paper as Required | 13-Aug-19 A | 13-Aug-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A1290 | HYA Reactors Shutdown Essential Safety Cases |  | 2019-08-13 | Gate B MS PRC Paper Submission | 13-Aug-19 A | 13-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1280 | HYA Reactors Shutdown Essential Safety Cases | 2019-08-13 | 2019-08-13 | Modify IRM Paper as Required | 13-Aug-19 A | 13-Aug-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1250 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Gate B MS PRC Paper Submission | 13-Aug-19 A | 13-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1410 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Modify Estimate, Schedule, Cost Tool & Risk Log as Required | 13-Aug-19 A | 13-Aug-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1420 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Update Cost Management Tool | 13-Aug-19 A | 19-Aug-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1430 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | IRM Members Review IRM Documentation | 13-Aug-19 A | 19-Aug-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A1300 | HRA Reactors Shutdown Essential Safety Cases | 2019-08-14 | 2019-08-14 | Modify Estimate, Schedule, Cost Tool & Risk Log as Required | 14-Aug-19 A | 14-Aug-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1310 | HRA Reactors Shutdown Essential Safety Cases | 2019-08-14 | 2019-08-14 | Update Cost Management Tool | 14-Aug-19 A | 14-Aug-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1320 | HRA Reactors Shutdown Essential Safety Cases | 2019-08-14 | 2019-08-16 | IRM Members Review IRM Documentation | 14-Aug-19 A | 16-Aug-19 A | 3 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A1300 | HYA Reactors Shutdown Essential Safety Cases | 2019-08-14 | 2019-08-14 | Modify Estimate, Schedule, Cost Tool & Risk Log as Required | 14-Aug-19 A | 14-Aug-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A1310 | HYA Reactors Shutdown Essential Safety Cases | 2019-08-14 | 2019-08-14 | Update Cost Management Tool | 14-Aug-19 A | 14-Aug-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1320 | HYA Reactors Shutdown Essential Safety Cases | 2019-08-14 | 2019-08-16 | IRM Members Review IRM Documentation | 14-Aug-19 A | 16-Aug-19 A | 3 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2910 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-08-19 | Civil Integrity Overview EAN Completed | 19-Aug-19 A | 19-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1330 | HRA Reactors Shutdown Essential Safety Cases | 2019-08-20 | 2019-08-20 | Hold MS PRC | 20-Aug-19 A | 20-Aug-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1340 | HRA Reactors Shutdown Essential Safety Cases |  | 2019-08-20 | Gate B MS PRC Approval | 20-Aug-19 A | 20-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1330 | HYA Reactors Shutdown Essential Safety Cases | 2019-08-20 | 2019-08-20 | Hold MS PRC | 20-Aug-19 A | 20-Aug-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1340 | HYA Reactors Shutdown Essential Safety Cases |  | 2019-08-20 | Gate B MS PRC Approval | 20-Aug-19 A | 20-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1350 | HYA Reactors Shutdown Essential Safety Cases | 2019-08-21 | 2019-08-30 | Update IRM paper with MS PRC Recommendations | 21-Aug-19 A | 30-Aug-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1400 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Hold MS PRC | 21-Aug-19 A | 21-Aug-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1450 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Gate B MS PRC Approval | 21-Aug-19 A | 21-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3180 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-08-23 | Verified Pressure Boundary Seals Draft Report Issued to EDF for Technical Review. | 23-Aug-19 A | 23-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3190 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-23 | 2019-08-23 | Pressure Boundary Seals Draft Report Technically Reviewed by EDF SQEP | 23-Aug-19 A | 23-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3210 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-08-23 | TSA Issue Final Pressure Boundary Seals Report | 23-Aug-19 A | 23-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4060 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-08-23 | Verified Specification for Analysis Draft Report Issued to EDF for Review. | 23-Aug-19 A | 23-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6220 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-08-23 | Verified LSD Strategy Draft Report Issued to EDF for Technical Review. | 23-Aug-19 A | 23-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7630 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-08-23 | Issue Final SDM Assessments with uncertainties / sensitivity studies Report Report | 23-Aug-19 A | 23-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8500 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-23 | 2019-10-18 | Prepare Containment Head Document Draft Report | 23-Aug-19 A | 18-Oct-19 A | 40 | 0 | 39 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8495 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-23 | 2020-04-16 | Claim 2 Containment Head Document Summary | 23-Aug-19 A | 15-Sep-20 A | 269 | 0 | 269 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3200 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-23 | 2019-08-23 | TSA Address Comments on TR'd Pressure Boundary Seals Draft Report | 23-Aug-19 A | 23-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2960 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-26 | 2019-09-09 | TSA Address Comments on TR'd Component Life Assessment Draft Report | 26-Aug-19 A | 09-Sep-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3040 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-26 | 2019-09-09 | TSA Address Comments on TR'd Standpipe and Guide Tube Integrity Assessment Draft Report | 26-Aug-19 A | 09-Sep-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3120 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-26 | 2019-09-09 | TSA Address Comments on TR'd Degradation of Boilers Draft Report | 26-Aug-19 A | 09-Sep-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3440 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-26 | 2019-09-09 | TSA Address Comments on TR'd Reactor Internals Draft Report | 26-Aug-19 A | 09-Sep-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4070 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-26 | 2019-08-30 | Specification for Analysis Draft Report Reviewed by EDF SQEP | 26-Aug-19 A | 30-Aug-19 A | 4 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16580 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-08-26 | Verified Thermal Analysis of FPU - FEAT - Report - QA Grade 2 Issued to EDF for Technical Review. | 26-Aug-19 A | 26-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16120 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-08-27 | Impacts for the Order of Defuelling EAN Completed | 27-Aug-19 A | 27-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2050 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-08-30 | Issue Final Establish Codes and Methods for Safety Case Report | 30-Aug-19 A | 30-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4110 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-08-30 | Specification for Analysis Report Completed | 30-Aug-19 A | 30-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10550 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-08-30 | Verified ALARP / BAT/ BPM Draft Report Issued to EDF for Technical Review. | 30-Aug-19 A | 30-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10890 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-08-30 | Issued Uncertainty in SDM Calculations Draft Report to EDF for Review. | 30-Aug-19 A | 30-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13190 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-08-30 | Discovery Milestone: Scope confirmation following ONR advice on NSRS (HNB) | 30-Aug-19 A | 30-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1360 | HRA Reactors Shutdown Essential Safety Cases |  | 2019-08-30 | Gate B IRM Paper Submission | 30-Aug-19 A | 30-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1350 | HRA Reactors Shutdown Essential Safety Cases | 2019-08-30 | 2019-08-30 | Update IRM paper with MS PRC Recommendations | 30-Aug-19 A | 30-Aug-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A1360 | HYA Reactors Shutdown Essential Safety Cases |  | 2019-08-30 | Gate B IRM Paper Submission | 30-Aug-19 A | 30-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1480 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Gate B IRM Paper Submission | 30-Aug-19 A | 30-Aug-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3220 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-02 | 2019-09-13 | Pressure Boundary Seals Report TR Completed and uploaded to CDMS | 02-Sep-19 A | 13-Sep-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3250 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-02 | 2019-10-31 | Gas Chemistry Assessment Draft Report Verified by EDF | 02-Sep-19 A | 31-Oct-19 A | 44 | 0 | 43 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3390 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-09-02 | Ass'ment of Graphite behaviour for Shutdown Defuelling Report Completed | 02-Sep-19 A | 02-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6230 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-02 | 2019-09-13 | LSD Strategy Draft Report Technically Reviewed by EDF SQEP | 02-Sep-19 A | 13-Sep-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6770 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-02 | 2019-10-04 | Summary of Compliance with RADWASTE Assessment Principles Draft EAN Verified by TSA | 02-Sep-19 A | 04-Oct-19 A | 25 | 0 | 24 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7960 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-02 | 2019-09-13 | Prepare Requirements for Severe Accidents Draft Report | 02-Sep-19 A | 13-Sep-19 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10370 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-02 | 2019-09-27 | TSA Address Comments on TR'd Structures and Equipment Integrity Draft Report | 02-Sep-19 A | 27-Sep-19 A | 20 | 0 | 19 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10560 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-02 | 2019-09-20 | ALARP / BAT/ BPM Draft Report Technically Reviewed by EDF SQEP | 02-Sep-19 A | 20-Sep-19 A | 15 | 0 | 14 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10630 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-09-02 | Verified SIn Reactor NSP Compliance and Risk Report - Draft Report Issued to EDF for Technical Review. | 02-Sep-19 A | 02-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10640 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-02 | 2019-09-13 | In Reactor NSP Compliance and Risk Report - Draft Report Technically Reviewed by EDF SQEP | 02-Sep-19 A | 13-Sep-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10900 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-02 | 2020-02-07 | Uncertainty in SDM Calculations Draft Report Reviewed by EDF SQEP | 02-Sep-19 A | 07-Feb-20 A | 112 | 0 | 111 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7955 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-02 | 2019-10-24 | Requirements for Severe Accidents Summary | 02-Sep-19 A | 24-Oct-19 A | 39 | 0 | 39 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11340 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-02 | 2019-09-20 | Prepare Scope Additional SDM Calcs Report (Phase 2) | 02-Sep-19 A | 20-Sep-19 A | 15 | 0 | 14 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16360 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-02 | 2019-09-12 | PVCW Calculations - Dropped FPU Fault - EAN - QA Grade 2 Verified by TSA | 02-Sep-19 A | 12-Sep-19 A | 9 | 0 | 8 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16440 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-02 | 2019-09-06 | Consideration of the ability of the PCPV to satisfy support in-resident FPUs - EAN - QA Grade 2 Verified by TSA | 02-Sep-19 A | 06-Sep-19 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16590 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-02 | 2019-09-06 | Thermal Analysis of FPU - FEAT - Report - QA Grade 2 Technically Reviewed by EDF SQEP | 02-Sep-19 A | 06-Sep-19 A | 5 | 0 | 4 | 100% |  | Completed
ER6378LT | W222 | W222.A14010 | HRA Fuel Handling Essential Safety Case | 2019-09-02 | 2019-09-02 | PCL Validate & Approve Baseline Package for PRC Submission | 02-Sep-19 A | 02-Sep-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A14000 | HRA Fuel Handling Essential Safety Case | 2019-09-02 | 2019-09-02 | Add Data to Scheme Paper | 02-Sep-19 A | 02-Sep-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A14070 | HRA Fuel Handling Essential Safety Case | 2019-09-02 | 2019-09-02 | Ensure Alignment of Schedule & Estimate | 02-Sep-19 A | 02-Sep-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A14070 | HYA Fuel Handling Essential Safety Case | 2019-09-02 | 2019-09-02 | Ensure Alignment of Schedule & Estimate | 02-Sep-19 A | 02-Sep-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A14000 | HYA Fuel Handling Essential Safety Case | 2019-09-02 | 2019-09-02 | Add Data to Scheme Paper | 02-Sep-19 A | 02-Sep-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A14010 | HYA Fuel Handling Essential Safety Case | 2019-09-02 | 2019-09-02 | PCL Validate & Approve Baseline Package for PRC Submission | 02-Sep-19 A | 02-Sep-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3620 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-03 | 2019-09-06 | MACE Dataset Development and Analysis for Minimum Temperature Issue TR Completed and uploaded to CDMS | 03-Sep-19 A | 06-Sep-19 A | 4 | 0 | 3 | 100% |  | Completed
ER6378LT | W222 | W222.A14120 | HRA Fuel Handling Essential Safety Case | 2019-09-04 | 2019-09-10 | PRC Members Review Scheme Documentation | 04-Sep-19 A | 10-Sep-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A14020 | HRA Fuel Handling Essential Safety Case |  | 2019-09-04 | Issue Scheme Paper to PRC Members | 04-Sep-19 A | 04-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A14020 | HYA Fuel Handling Essential Safety Case |  | 2019-09-04 | Issue Scheme Paper to PRC Members | 04-Sep-19 A | 04-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A14120 | HYA Fuel Handling Essential Safety Case | 2019-09-04 | 2019-09-10 | PRC Members Review Scheme Documentation | 04-Sep-19 A | 10-Sep-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3630 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-09-06 | MACE Dataset Development and Analysis for Minimum Temperature Issue Completed | 06-Sep-19 A | 06-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16450 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-09-06 | Verified ability of the PCPV to satisfy support in-resident FPUs - EAN - QA Grade 2 Issued to EDF for TR. | 06-Sep-19 A | 06-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1660 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-09 | 2019-09-27 | Define Project Control Structures (WBS/CBS/OBS/PBS) | 09-Sep-19 A | 27-Sep-19 A | 15 | 0 | 14 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2970 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-09-09 | TSA Issue Final Component Life Assessment Report | 09-Sep-19 A | 09-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3050 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-09-09 | TSA Issue Final Standpipe and Guide Tube Integrity Assessment Report | 09-Sep-19 A | 09-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3130 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-09-09 | TSA Issue Final Degradation of Boilers Report | 09-Sep-19 A | 09-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3450 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-09-09 | TSA Issue Final Reactor Internals Report | 09-Sep-19 A | 09-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16460 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-09 | 2019-10-02 | ability of the PCPV to satisfy support in-resident FPUs - EAN - QA Grade 2 Technically Reviewed by EDF SQEP | 09-Sep-19 A | 02-Oct-19 A | 18 | 0 | 17 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16600 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-09 | 2019-09-13 | TSA Address Comments on TR'd Thermal Analysis of FPU - FEAT - Report - QA Grade 2 | 09-Sep-19 A | 13-Sep-19 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1680 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-09 | 2019-10-18 | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 09-Sep-19 A | 18-Oct-19 A | 30 | 0 | 29 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2980 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-10 | 2019-10-22 | Component Life Assessment Report TR Completed and uploaded to CDMS | 10-Sep-19 A | 22-Oct-19 A | 31 | 0 | 30 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3060 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-10 | 2019-10-22 | Standpipe and Guide Tube Integrity Assessment Report TR Completed and uploaded to CDMS | 10-Sep-19 A | 22-Oct-19 A | 31 | 0 | 30 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3140 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-10 | 2019-10-22 | Degradation of Boilers Report TR Completed and uploaded to CDMS | 10-Sep-19 A | 22-Oct-19 A | 31 | 0 | 30 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3460 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-10 | 2019-10-22 | Reactor Internals Report TR Completed and uploaded to CDMS | 10-Sep-19 A | 22-Oct-19 A | 31 | 0 | 30 | 100% |  | Completed
ER6370LT | W201 | ER6370.A5570 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-10 | 2019-09-27 | HF Risk Assessment Draft Report Verified by TSA | 10-Sep-19 A | 27-Sep-19 A | 14 | 0 | 13 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4850 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-11 | 2019-09-24 | Review of/Changes to Emergency Arrangements Draft Report Verified by TSA | 11-Sep-19 A | 24-Sep-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16370 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-09-12 | Verified PVCW Calculations - Dropped FPU Fault - EAN - QA Grade 2 Issued to EDF for Technical Review. | 12-Sep-19 A | 12-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3230 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-09-13 | Pressure Boundary Seals Report Completed | 13-Sep-19 A | 13-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16380 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-13 | 2019-09-19 | PVCW Calculations - Dropped FPU Fault - EAN - QA Grade 2 Technically Reviewed by EDF SQEP | 13-Sep-19 A | 19-Sep-19 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16610 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-09-13 | TSA Issue Final Thermal Analysis of FPU - FEAT - Report - QA Grade 2 | 13-Sep-19 A | 13-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17390 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-09-13 | >>>INCOMING ENABLER (W221.A9570) Criticality Assessment for Dropped FPU at Reactor (DRY Condition) EAN Available | 13-Sep-19 A | 13-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17410 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-09-13 | >>>MIRROR OF INCOMING ENABLER (W221.A9570) Criticality Assessment for Dropped FPU at Reactor (DRY Con) EAN Available | 13-Sep-19 A | 13-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1520 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Gate B - 6.1 Reactors Shutdown Safety Cases Programme HAR/HYA | 16-Sep-19 A | 16-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4200 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-16 | 2020-03-27 | Prepare Core Cooling Head Document Draft Report | 16-Sep-19 A | 11-Jun-20 A | 187 | 0 | 186 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6240 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-16 | 2019-09-23 | TSA Address Comments on TR'd LSD Strategy Draft Report | 16-Sep-19 A | 23-Sep-19 A | 6 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7970 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-16 | 2019-09-20 | Requirements for Severe Accidents Draft Report Verified by TSA | 16-Sep-19 A | 20-Sep-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10650 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-16 | 2019-09-27 | TSA Address Comments on TR'd In Reactor NSP Compliance and Risk Report | 16-Sep-19 A | 27-Sep-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4195 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-16 | 2020-06-04 | Core Cooling Head Document Summary | 16-Sep-19 A | 09-Oct-20 A | 276 | 0 | 271 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16620 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-16 | 2019-09-23 | Thermal Analysis of FPU - FEAT - Report - QA Grade 2 TR Completed and uploaded to CDMS | 16-Sep-19 A | 23-Sep-19 A | 6 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A1370 | HRA Reactors Shutdown Essential Safety Cases |  | 2019-09-16 | Gate B IRM Paper Approval | 16-Sep-19 A | 16-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1370 | HYA Reactors Shutdown Essential Safety Cases |  | 2019-09-16 | Gate B IRM Paper Approval | 16-Sep-19 A | 16-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1470 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Hold IRM | 16-Sep-19 A | 16-Sep-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1380 | HRA Reactors Shutdown Essential Safety Cases | 2019-09-16 | 2019-09-16 | Hold IRM | 16-Sep-19 A | 16-Sep-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A1380 | HYA Reactors Shutdown Essential Safety Cases | 2019-09-16 | 2019-09-16 | Hold IRM | 16-Sep-19 A | 16-Sep-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1460 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Gate B IRM Paper Approval - HYA And HRA | 16-Sep-19 A | 16-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A14160 | HRA Fuel Handling Essential Safety Case |  | 2019-09-17 | Issue Scheme Paper to Major Schemes PRC Members | 17-Sep-19 A | 17-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A14160 | HYA Fuel Handling Essential Safety Case |  | 2019-09-17 | Issue Scheme Paper to Major Schemes PRC Members | 17-Sep-19 A | 17-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8440 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-09-18 | Issue Reactor Coolant Chemistry Conditions Draft Report to EDF for Review. | 18-Sep-19 A | 18-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A14130 | HRA Fuel Handling Essential Safety Case | 2019-09-18 | 2019-09-18 | Hold PRC Meeting | 18-Sep-19 A | 18-Sep-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A14130 | HYA Fuel Handling Essential Safety Case | 2019-09-18 | 2019-09-18 | Hold PRC Meeting | 18-Sep-19 A | 18-Sep-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8450 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-19 | 2019-10-31 | Reactor Coolant Chemistry Conditions Draft Report Reviewed by EDF SQEP | 19-Sep-19 A | 31-Oct-19 A | 31 | 0 | 30 | 100% |  | Completed
ER6378LT | W222 | W222.A14140 | HRA Fuel Handling Essential Safety Case | 2019-09-19 | 2019-09-20 | Modify Estimate, Schedule & Risk Log as Required | 19-Sep-19 A | 20-Sep-19 A | 2 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A14140 | HYA Fuel Handling Essential Safety Case | 2019-09-19 | 2019-09-20 | Modify Estimate, Schedule & Risk Log as Required | 19-Sep-19 A | 20-Sep-19 A | 2 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7980 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-09-20 | Verified Requirements for Severe Accidents Draft Report Issued to EDF for Technical Review. | 20-Sep-19 A | 20-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13730 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-20 | 2019-09-20 | Shutdown Margin Compliance Report - Draft and issue RFS | 20-Sep-19 A | 20-Sep-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13740 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-20 | 2019-09-20 | Shutdown Margin Compliance Report - Supplier prepare and issue Offer | 20-Sep-19 A | 20-Sep-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13750 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-20 | 2019-09-20 | Shutdown Margin Compliance Report - Review Offer, prepare and issue CI | 20-Sep-19 A | 20-Sep-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13760 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-20 | 2019-09-20 | Shutdown Margin Compliance Report - Supplier mobilisation time | 20-Sep-19 A | 20-Sep-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13770 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-20 | 2019-09-20 | Shutdown Margin Compliance Report - Pre Job Brief | 20-Sep-19 A | 20-Sep-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13725 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-20 | 2019-09-20 | RFS - Shutdown Margin Compliance Report Summary | 20-Sep-19 A | 20-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16390 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-20 | 2019-09-26 | TSA Address Comments on TR'd PVCW Calculations - Dropped FPU Fault - EAN - QA Grade 2 | 20-Sep-19 A | 26-Sep-19 A | 5 | 0 | 4 | 100% |  | Completed
ER6378LT | W222 | W222.A14150 | HRA Fuel Handling Essential Safety Case | 2019-09-20 | 2019-09-20 | Modify Scheme Paper as Required | 20-Sep-19 A | 20-Sep-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A14150 | HYA Fuel Handling Essential Safety Case | 2019-09-20 | 2019-09-20 | Modify Scheme Paper as Required | 20-Sep-19 A | 20-Sep-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4760 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-23 | 2019-11-22 | Prepare Worker Dose and Risks from Faults Draft Report | 23-Sep-19 A | 22-Nov-19 A | 45 | 0 | 44 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6250 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-09-23 | TSA Issue Final LSD Strategy Report | 23-Sep-19 A | 23-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7990 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-23 | 2019-09-27 | Requirements for Severe Accidents Draft Report Technically Reviewed by EDF SQEP | 23-Sep-19 A | 27-Sep-19 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10570 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-23 | 2019-09-30 | TSA Address Comments on TR'd ALARP / BAT/ BPM Draft Report | 23-Sep-19 A | 30-Sep-19 A | 6 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4755 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-23 | 2020-02-28 | Worker Dose and Risks from Faults Summary | 23-Sep-19 A | 28-Feb-20 A | 111 | 0 | 111 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16630 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-09-23 | Thermal Analysis of FPU - FEAT - Report - QA Grade 2 Completed | 23-Sep-19 A | 23-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A14460 | HRA Fuel Handling Essential Safety Case | 2019-09-23 | 2019-09-30 | Modify Estimate, Schedule & Risk Log as Required | 23-Sep-19 A | 30-Sep-19 A | 6 | 0 | 6 | 100% |  | Completed
ER6650LT | W226 | W226.A14460 | HYA Fuel Handling Essential Safety Case | 2019-09-23 | 2019-09-30 | Modify Estimate, Schedule & Risk Log as Required | 23-Sep-19 A | 30-Sep-19 A | 6 | 0 | 6 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4860 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-09-24 | Verified Review of/Changes to Emergency Arrangements Draft Report Issued to EDF for Technical Review. | 24-Sep-19 A | 24-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6260 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-24 | 2019-10-04 | LSD Strategy Report TR Completed and uploaded to CDMS | 24-Sep-19 A | 04-Oct-19 A | 9 | 0 | 8 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4870 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-25 | 2019-09-27 | Review of/Changes to Emergency Arrangements Draft Report Technically Reviewed by EDF SQEP | 25-Sep-19 A | 27-Sep-19 A | 3 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16400 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-09-26 | TSA Issue Final PVCW Calculations - Dropped FPU Fault - EAN - QA Grade 2 | 26-Sep-19 A | 26-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1750 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-27 | 2019-10-23 | Prepare Draft Project Definition Document (PDD) | 27-Sep-19 A | 23-Oct-19 A | 19 | 0 | 18 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1890 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-27 | 2019-10-23 | Confirm Objectives to be Delivered at Gate C | 27-Sep-19 A | 23-Oct-19 A | 19 | 0 | 19 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1900 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-27 | 2019-10-23 | Initial high level scope of programme | 27-Sep-19 A | 23-Oct-19 A | 19 | 0 | 19 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3900 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-09-27 | Verified Model and Datasets Part 2 Draft Reports Issued to EDF for Technical Review. | 27-Sep-19 A | 27-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A5580 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-09-27 | Verified HF Risk Assessment Draft Report Issued to EDF for Technical Review. | 27-Sep-19 A | 27-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10380 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-09-27 | TSA Issue Final Structures and Equipment Integrity Report | 27-Sep-19 A | 27-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10660 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-09-27 | TSA Issue Final In Reactor NSP Compliance and Risk Report | 27-Sep-19 A | 27-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16410 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-27 | 2019-10-11 | PVCW Calculations - Dropped FPU Fault - EAN - QA Grade 2 TR Completed and uploaded to CDMS | 27-Sep-19 A | 11-Oct-19 A | 11 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4120 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-30 | 2020-01-31 | Prepare Shutdown Cooling Analysis Draft Report | 30-Sep-19 A | 31-Jan-20 A | 87 | 0 | 86 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4880 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-30 | 2019-10-04 | TSA Address Comments on TR'd Review of/Changes to Emergency Arrangements Draft Report | 30-Sep-19 A | 04-Oct-19 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A5590 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-30 | 2019-10-10 | HF Risk Assessment Draft Report Technically Reviewed by EDF SQEP | 30-Sep-19 A | 10-Oct-19 A | 9 | 0 | 8 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7700 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-30 | 2019-11-29 | ALARP input to/from Claim 5 | 30-Sep-19 A | 29-Nov-19 A | 45 | 0 | 44 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8000 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-30 | 2019-10-17 | TSA Address Comments on TR'd Requirements for Severe Accidents Draft Report | 30-Sep-19 A | 17-Oct-19 A | 14 | 0 | 13 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10580 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-09-30 | TSA Issue Final ALARP / BAT/ BPM Report | 30-Sep-19 A | 30-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10600 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-09-30 | ALARP / BAT/ BPM Report Completed | 30-Sep-19 A | 30-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10670 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-30 | 2019-11-15 | In Reactor NSP Compliance and Risk Report TR Completed and uploaded to CDMS | 30-Sep-19 A | 15-Nov-19 A | 35 | 0 | 34 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4115 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-30 | 2020-04-14 | Shutdown Cooling Analysis Summary | 30-Sep-19 A | 28-Apr-20 A | 147 | 0 | 147 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17340 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-09-30 | >>>OUTGOING ENABLER (W221) ALARP / BAT/ BPM Report Completed | 30-Sep-19 A | 30-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17350 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-09-30 | >>>OUTGOING ENABLER (W221) Pressure Boundary Seals Report Completed | 30-Sep-19 A | 30-Sep-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10590 | HNB Reactors Shutdown Essential Safety Cases | 2019-09-30 | 2019-09-30 | ALARP / BAT/ BPM Report TR Completed and uploaded to CDMS | 30-Sep-19 A | 30-Sep-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3910 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-01 | 2019-10-25 | Model and Datasets Part 2 Draft Reports Technically Reviewed by EDF SQEP | 01-Oct-19 A | 25-Oct-19 A | 19 | 0 | 18 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4400 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-01 | 2019-11-29 | TSA Address Comments on TR'd Fault Schedule Review (Plant Based Faults) Draft Report | 01-Oct-19 A | 29-Nov-19 A | 44 | 0 | 43 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4480 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-01 | 2019-11-29 | TSA Address Comments on TR'd Fault Schedule Review (Harzards) Draft Report | 01-Oct-19 A | 29-Nov-19 A | 44 | 0 | 43 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6930 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-01 | 2019-12-20 | Boilers and Gas Circulator Performance Draft EAN Verified by TSA | 01-Oct-19 A | 20-Dec-19 A | 59 | 0 | 58 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7010 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-01 | 2019-11-20 | Boiler Supporting Systems Draft EAN Verified by TSA | 01-Oct-19 A | 20-Nov-19 A | 37 | 0 | 36 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7640 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-01 | 2019-11-14 | SDM Assessments with uncertainties / sensitivity studies Report Completed and Uploaded to CDMS | 01-Oct-19 A | 14-Nov-19 A | 33 | 0 | 32 | 100% |  | Completed
ER6370LT | W201 | ER6370.A9470 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-01 | 2019-10-18 | Boiler Control and Protection Draft Report Verified by TSA | 01-Oct-19 A | 18-Oct-19 A | 14 | 0 | 14 | 100% |  | Completed
ER6370LT | W201 | ER6370.A9550 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-01 | 2019-10-18 | Reactor Cooling Systems Draft Report Verified by TSA | 01-Oct-19 A | 18-Oct-19 A | 14 | 0 | 14 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10390 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-01 | 2019-10-21 | Structures and Equipment Integrity Report TR Completed and uploaded to CDMS | 01-Oct-19 A | 21-Oct-19 A | 15 | 0 | 14 | 100% |  | Completed
ER6378LT | W222 | W222.A14470 | HRA Fuel Handling Essential Safety Case | 2019-10-01 | 2019-10-04 | Modify Scheme Paper as Required | 01-Oct-19 A | 04-Oct-19 A | 4 | 0 | 4 | 100% |  | Completed
ER6650LT | W226 | W226.A14470 | HYA Fuel Handling Essential Safety Case | 2019-10-01 | 2019-10-04 | Modify Scheme Paper as Required | 01-Oct-19 A | 04-Oct-19 A | 4 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16470 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-03 | 2019-10-09 | TSA Address Comments on TR'd ability of the PCPV to satisfy support in-resident FPUs - EAN - QA Grade 2 | 03-Oct-19 A | 09-Oct-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4890 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-10-04 | TSA Issue Final Review of/Changes to Emergency Arrangements Report | 04-Oct-19 A | 04-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6270 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-10-04 | LSD Strategy Report Completed | 04-Oct-19 A | 04-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6780 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-10-04 | Verified Summary of Compliance with RADWASTE Assessment Principles Draft EAN Issued to EDF for Technical Review. | 04-Oct-19 A | 04-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A14440 | HRA Fuel Handling Essential Safety Case |  | 2019-10-04 | Issue Scheme Paper to IRM Members | 04-Oct-19 A | 04-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A14440 | HYA Fuel Handling Essential Safety Case |  | 2019-10-04 | Issue Scheme Paper to IRM Members | 04-Oct-19 A | 04-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4900 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-07 | 2019-10-11 | Review of/Changes to Emergency Arrangements Report TR Completed and uploaded to CDMS | 07-Oct-19 A | 11-Oct-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6790 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-07 | 2019-10-07 | Summary of Compliance with RADWASTE Assessment Principles Draft EAN Technically Reviewed by EDF SQEP | 07-Oct-19 A | 07-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6800 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-07 | 2019-10-07 | TSA Address Comments on TR'd Summary of Compliance with RADWASTE Assessment Principles Draft EAN | 07-Oct-19 A | 07-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6810 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-10-07 | TSA Issue Final Summary of Compliance with RADWASTE Assessment Principles EAN | 07-Oct-19 A | 07-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6820 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-07 | 2019-10-20 | Summary of Compliance with RADWASTE Assessment Principles EAN TR Completed and uploaded to CDMS | 07-Oct-19 A | 20-Oct-19 A | 10 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | W202.A1420 | HRA Reactors Shutdown Essential Safety Cases | 2019-10-07 | 2021-10-21 | Phase 2 Project Management - Gate B - C | 07-Oct-19 A | 01-Sep-21 A | 518 | 0 | 481 | 100% |  | Completed
ER6371LT | W202 | W202.A1410 | HRA Reactors Shutdown Essential Safety Cases | 2019-10-07 |  | Commence Supporting References or Supporting EC's (HRA) | 07-Oct-19 A | 07-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1420 | HYA Reactors Shutdown Essential Safety Cases | 2019-10-07 | 2021-10-21 | Phase 2 Project Management - Gate B - C | 07-Oct-19 A | 01-Sep-21 A | 772 | 0 | 481 | 100% |  | Completed
ER6661LT | W206 | W206.A1410 | HYA Reactors Shutdown Essential Safety Cases | 2019-10-07 |  | Commence Supporting References or Supporting EC's (HYA) | 07-Oct-19 A | 07-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A14180 | HRA Fuel Handling Essential Safety Case | 2019-10-07 | 2019-10-11 | IRM Members Review Sceme Paper Documentation | 07-Oct-19 A | 11-Oct-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A14180 | HYA Fuel Handling Essential Safety Case | 2019-10-07 | 2019-10-11 | IRM Members Review Sceme Paper Documentation | 07-Oct-19 A | 11-Oct-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16480 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-10-09 | TSA Issue Final PVCW Calculations - Dropped FPU Fault - EAN - QA Grade 2 | 09-Oct-19 A | 09-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16490 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-10 | 2019-10-16 | ability of the PCPV to satisfy support in-resident FPUs - EAN - QA Grade 2 TR Completed and uploaded to CDMS | 10-Oct-19 A | 16-Oct-19 A | 5 | 0 | 4 | 100% |  | Completed
ER6243LT | W200 | A1300 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2018-12-27 | Gate EC2 completed EC 363701 & 364023 <NSRS SC Approach & Outline> (Cat 1 Milestone) (HPB, HNB) | 11-Oct-19 A | 11-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4910 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-10-11 | Review of/Changes to Emergency Arrangements Report Completed | 11-Oct-19 A | 11-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A5600 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-11 | 2019-10-18 | TSA Address Comments on TR'd HF Risk Assessment Draft Report | 11-Oct-19 A | 18-Oct-19 A | 6 | 0 | 6 | 100% |  | Completed
ER6370LT | W201 | ER6243.A1100 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-10-11 | Gate EC2 completed EC 364023 <NSRS SC Approach & Outline> (Cat 1 Milestone) (HNB) | 11-Oct-19 A | 11-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16420 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-10-11 | PVCW Calculations - Dropped FPU Fault - EAN - QA Grade 2 Completed | 11-Oct-19 A | 11-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1930 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-15 | 2019-10-21 | Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) Verified by TSA | 15-Oct-19 A | 21-Oct-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A8190.E10 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2019-09-11 | [PR KDM] Gate B for HRA HYA Station Fuel Handling Safety Case Programme | 16-Oct-19 A | 16-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1700 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-16 | 2019-10-16 | Hold Risk Workshop | 16-Oct-19 A | 16-Oct-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16500 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-10-16 | ability of the PCPV to satisfy support in-resident FPUs - EAN - QA Grade 2 Completed | 16-Oct-19 A | 16-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A25950 | HRA Fuel Handling Essential Safety Case | 2019-10-16 | 2021-04-06 | Basis of Analysis Report ##(Cost Summary)## (NEW) (C5) | 16-Oct-19 A | 06-Apr-21 A | 377 | 0 | 371 | 100% |  | Completed
ER6378LT | W222 | W222.A23170 | HRA Fuel Handling Essential Safety Case | 2019-10-16 | 2019-10-16 | Pre Job Brief for Basis of Analysis Report EAN (REV 000) | 16-Oct-19 A | 16-Oct-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A23170 | HYA Fuel Handling Essential Safety Case | 2019-10-16 | 2019-10-16 | Pre Job Brief for Basis of Analysis Report EAN (REV 000) | 16-Oct-19 A | 16-Oct-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25950 | HYA Fuel Handling Essential Safety Case | 2019-10-16 | 2021-04-06 | Basis of Analysis Report ##(Cost Summary)## (NEW) (C5) | 16-Oct-19 A | 06-Apr-21 A | 377 | 0 | 371 | 100% |  | Completed
ER6378LT | W222 | W222.A14190 | HRA Fuel Handling Essential Safety Case | 2019-10-16 | 2019-10-16 | Hold IRM Meeting | 16-Oct-19 A | 16-Oct-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A14190 | HYA Fuel Handling Essential Safety Case | 2019-10-16 | 2019-10-16 | Hold IRM Meeting | 16-Oct-19 A | 16-Oct-19 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A13290 | HRA Fuel Handling Essential Safety Case |  | 2019-10-16 | Gate B for Region 1 - HYA HRA Defuelling Fuel Handling Essential Safety Case | 16-Oct-19 A | 16-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A16690 | HRA Fuel Handling Essential Safety Case |  | 2019-10-16 | Gate B IRM Approval | 16-Oct-19 A | 16-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A16690 | HYA Fuel Handling Essential Safety Case |  | 2019-10-16 | Gate B IRM Approval | 16-Oct-19 A | 16-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A13290 | HYA Fuel Handling Essential Safety Case |  | 2019-10-16 | Gate B for Region 1 - HYA Defuelling Fuel Handling Essential Safety Case | 16-Oct-19 A | 16-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1710 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-17 | 2019-10-18 | Complete Risk Log with Estimates | 17-Oct-19 A | 18-Oct-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8010 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-10-17 | TSA Issue Final Requirements for Severe Accidents Report | 17-Oct-19 A | 17-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A23180 | HRA Fuel Handling Essential Safety Case | 2019-10-17 | 2020-04-15 | Draft Basis of Analysis Report EAN (REV 000) | 17-Oct-19 A | 15-Apr-20 A | 125 | 0 | 124 | 100% |  | Completed
ER6650LT | W226 | W226.A23180 | HYA Fuel Handling Essential Safety Case | 2019-10-17 | 2020-04-15 | Draft Basis of Analysis Report EAN (REV 000) | 17-Oct-19 A | 15-Apr-20 A | 125 | 0 | 124 | 100% |  | Completed
ER6370LT | W201 | ER6370.A5610 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-10-18 | TSA Issue Final HF Risk Assessment Report | 18-Oct-19 A | 18-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8020 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-18 | 2019-10-24 | Requirements for Severe AccidentsReport TR Completed and uploaded to CDMS | 18-Oct-19 A | 24-Oct-19 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A9480 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-10-18 | Verified Boiler Control and Protection Draft Report Issued to EDF for Technical Review. | 18-Oct-19 A | 18-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A9560 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-10-18 | Verified Reactor Cooling Systems Draft Report Issued to EDF for Technical Review. | 18-Oct-19 A | 18-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6830 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-10-20 | Summary of Compliance with RADWASTE Assessment Principles EAN Completed | 20-Oct-19 A | 20-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1940 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-10-21 | Verified Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) Issued to EDF for Technical Revi | 21-Oct-19 A | 21-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A5620 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-21 | 2019-11-01 | HF Risk Assessment Report TR Completed and uploaded to CDMS | 21-Oct-19 A | 01-Nov-19 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8510 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-21 | 2020-01-31 | Containment Head Document Draft Report Verified by TSA | 21-Oct-19 A | 31-Jan-20 A | 72 | 0 | 71 | 100% |  | Completed
ER6370LT | W201 | ER6370.A9490 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-21 | 2019-11-08 | Boiler Control and Protection Draft Report Technically Reviewed by EDF SQEP | 21-Oct-19 A | 08-Nov-19 A | 15 | 0 | 14 | 100% |  | Completed
ER6370LT | W201 | ER6370.A9570 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-21 | 2019-11-08 | Reactor Cooling Systems Draft Report Technically Reviewed by EDF SQEP | 21-Oct-19 A | 08-Nov-19 A | 15 | 0 | 14 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10400 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-10-21 | Structures and Equipment Integrity Report Completed | 21-Oct-19 A | 21-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1910 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-21 | 2019-10-31 | Workshop to agree scope, effort and links | 21-Oct-19 A | 31-Oct-19 A | 9 | 0 | 8 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1950 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-22 | 2019-11-29 | Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) Technically Reviewed by EDF SQEP | 22-Oct-19 A | 29-Nov-19 A | 29 | 0 | 28 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2990 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-10-22 | Component Life Assessment Report Completed | 22-Oct-19 A | 22-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3070 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-10-22 | Standpipe and Guide Tube Integrity Assessment Report Completed | 22-Oct-19 A | 22-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3150 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-10-22 | Degradation of Boilers Report Completed | 22-Oct-19 A | 22-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3470 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-10-22 | Reactor Internals Report Completed | 22-Oct-19 A | 22-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16710 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-23 | 2019-11-29 | Summary Conditions Report - EAN - QA Grade 2 Verified by TSA | 23-Oct-19 A | 29-Nov-19 A | 28 | 0 | 27 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1670 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-24 | 2019-11-18 | Plan Scope in Primavera (Level 2 C-D & Level 1 Lifecycle) | 24-Oct-19 A | 18-Nov-19 A | 18 | 0 | 17 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8030 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-10-24 | Requirements for Severe Accidents Report Completed | 24-Oct-19 A | 24-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2060 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-25 | 2019-11-08 | Establish Codes and Methods for Safety Case Report Completed and Uploaded to CDMS | 25-Oct-19 A | 08-Nov-19 A | 11 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3920 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-25 | 2019-10-31 | TSA Address Comments on TR'd Model and Datasets Part 2 Draft Report | 25-Oct-19 A | 31-Oct-19 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3260 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-10-31 | Verified Gas Chemistry Assessment Draft Report Issued to EDF for Technical Review. | 31-Oct-19 A | 31-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3270 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-31 | 2019-10-31 | Gas Chemistry Assessment Draft Report Technically Reviewed by EDF SQEP | 31-Oct-19 A | 31-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3280 | HNB Reactors Shutdown Essential Safety Cases | 2019-10-31 | 2019-10-31 | TSA Address Comments on TR'd Gas Chemistry Assessment Draft Report | 31-Oct-19 A | 31-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3290 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-10-31 | TSA Issue Final Gas Chemistry Assessment Report | 31-Oct-19 A | 31-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3930 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-10-31 | TSA Issue Final Model and Datasets Part 2 Reports | 31-Oct-19 A | 31-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A5630 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-10-31 | HF Risk Assessment Report Completed | 31-Oct-19 A | 31-Oct-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3940 | HNB Reactors Shutdown Essential Safety Cases | 2019-11-01 | 2019-11-29 | Model and Datasets Part 2 Reports TR Completed and uploaded to CDMS | 01-Nov-19 A | 29-Nov-19 A | 21 | 0 | 20 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7800 | HNB Reactors Shutdown Essential Safety Cases | 2019-11-01 | 2019-12-06 | Shutdown Margin Head Document Verified by TSA | 01-Nov-19 A | 06-Dec-19 A | 26 | 0 | 25 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8460 | HNB Reactors Shutdown Essential Safety Cases | 2019-11-01 | 2019-11-29 | Address Comments on Reviwed Reactor Coolant Chemistry Conditions Draft Report | 01-Nov-19 A | 29-Nov-19 A | 21 | 0 | 20 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3300 | HNB Reactors Shutdown Essential Safety Cases | 2019-11-04 | 2019-11-29 | Gas Chemistry Assessment Report TR Completed and uploaded to CDMS | 04-Nov-19 A | 29-Nov-19 A | 20 | 0 | 19 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2070 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-11-08 | Establish Codes and Methods for Safety Case Report Completed | 08-Nov-19 A | 08-Nov-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13020 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-11-08 | KDM Shutdown Margins – Codes and Method for Safety Case Report Complete (HNB) | 08-Nov-19 A | 08-Nov-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A9500 | HNB Reactors Shutdown Essential Safety Cases | 2019-11-11 | 2019-11-22 | TSA Address Comments on TR'd Boiler Control and Protection Draft Report | 11-Nov-19 A | 22-Nov-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A9580 | HNB Reactors Shutdown Essential Safety Cases | 2019-11-11 | 2019-11-22 | TSA Address Comments on TR'd Reactor Cooling Systems Draft Report | 11-Nov-19 A | 22-Nov-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1310 | HNB Reactors Shutdown Essential Safety Cases | 2019-11-14 | 2019-11-15 | Produce verification plan (HNB) | 14-Nov-19 A | 15-Nov-19 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7650 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-11-14 | SDM Assessments with uncertainties / sensitivity studies Report Completed | 14-Nov-19 A | 14-Nov-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10680 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-11-15 | In Reactor NSP Compliance and Risk Report Completed | 15-Nov-19 A | 15-Nov-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16340 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-11-15 | All Supporting Technical References Complete - Claim 5 ALARP | 15-Nov-19 A | 15-Nov-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7020 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-11-20 | Verified Boiler Supporting Systems Draft EAN Issued to EDF for Technical Review. | 20-Nov-19 A | 20-Nov-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A9510 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-11-22 | TSA Issue Final Boiler Control and Protection Report | 22-Nov-19 A | 22-Nov-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A9590 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-11-22 | TSA Issue Final Reactor Cooling Systems Report | 22-Nov-19 A | 22-Nov-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4770 | HNB Reactors Shutdown Essential Safety Cases | 2019-11-25 | 2020-02-07 | Worker Dose and Risks from Faults Draft Report Verified by TSA | 25-Nov-19 A | 07-Feb-20 A | 52 | 0 | 51 | 100% |  | Completed
ER6370LT | W201 | ER6370.A9520 | HNB Reactors Shutdown Essential Safety Cases | 2019-11-25 | 2019-12-06 | Boiler Control and Protection Report TR Completed and uploaded to CDMS | 25-Nov-19 A | 06-Dec-19 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A9600 | HNB Reactors Shutdown Essential Safety Cases | 2019-11-25 | 2019-12-06 | Reactor Cooling Systems Report TR Completed and uploaded to CDMS | 25-Nov-19 A | 06-Dec-19 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3310 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-11-29 | Gas Chemistry Assessment Report Completed | 29-Nov-19 A | 29-Nov-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3950 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-11-29 | Model and Datasets Part 2 Reports Completed | 29-Nov-19 A | 29-Nov-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4410 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-11-29 | TSA Issue Final Fault Schedule Review (Plant Based Faults) Report | 29-Nov-19 A | 29-Nov-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4490 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-11-29 | TSA Issue Final Fault Schedule Review (Harzards) Report | 29-Nov-19 A | 29-Nov-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8470 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-11-29 | Issue Reactor Coolant Chemistry Conditions Final Report | 29-Nov-19 A | 29-Nov-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16720 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-11-29 | Verified Summary Conditions Report - EAN - QA Grade 2 Issued to EDF for Technical Review. | 29-Nov-19 A | 29-Nov-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1960 | HNB Reactors Shutdown Essential Safety Cases | 2019-12-02 | 2019-12-20 | TSA Address Comments on TR'd Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) | 02-Dec-19 A | 20-Dec-19 A | 15 | 0 | 14 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4420 | HNB Reactors Shutdown Essential Safety Cases | 2019-12-02 | 2019-12-23 | Fault Schedule Review (Plant Based Faults) Report TR Completed and uploaded to CDMS | 02-Dec-19 A | 23-Dec-19 A | 16 | 0 | 15 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4500 | HNB Reactors Shutdown Essential Safety Cases | 2019-12-02 | 2019-12-23 | Fault Schedule Review (Harzards) Report TR Completed and uploaded to CDMS | 02-Dec-19 A | 23-Dec-19 A | 16 | 0 | 15 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8480 | HNB Reactors Shutdown Essential Safety Cases | 2019-12-02 | 2020-01-02 | Reactor Coolant Chemistry Conditions Final Report Completed and uploaded to CDMS | 02-Dec-19 A | 02-Jan-20 A | 21 | 0 | 20 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11200 | HNB Reactors Shutdown Essential Safety Cases | 2019-12-02 | 2020-12-04 | <SCOPE DELETED 13.10.2020> Scoping of Implementation ECs C-D | 02-Dec-19 A | 12-Oct-20 A | 257 | 0 | 217 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16730 | HNB Reactors Shutdown Essential Safety Cases | 2019-12-02 | 2019-12-20 | Summary Conditions Report - EAN - QA Grade 2 Technically Reviewed by EDF SQEP | 02-Dec-19 A | 20-Dec-19 A | 15 | 0 | 14 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7810 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-12-06 | Verified Shutdown Margin Head Document Issued to EDF for Technical Review. | 06-Dec-19 A | 06-Dec-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A9530 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-12-06 | Boiler Control and Protection Report Completed | 06-Dec-19 A | 06-Dec-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A9610 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-12-06 | Reactor Cooling Systems Report Completed | 06-Dec-19 A | 06-Dec-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7820 | HNB Reactors Shutdown Essential Safety Cases | 2019-12-09 | 2020-02-14 | Shutdown Margin Head Document Technically Reviewed by EDF SQEP | 09-Dec-19 A | 14-Feb-20 A | 47 | 0 | 46 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17500 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-12-12 | >>>MIRROR OF INCOMING ENABLER (W282.A3100) SC Implementation and Rationalisation of Tech Specand SOI Documentation | 12-Dec-19 A | 12-Dec-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17490 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-12-12 | >>>INCOMING ENABLER (W282.A3100) SC Implementation and Rationalisation of Tech Specand SOI Documentation - Strategy Appr | 12-Dec-19 A | 12-Dec-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17510 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-02 | INTERFACE MILESTONE - STN Implementation Tech Spec & POI - (W282 Station Defuelling Deployment (Centre) (HNB) | 12-Dec-19 A | 12-Dec-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1440 | HRA Reactors Shutdown Essential Safety Cases | 2019-12-16 | 2020-08-28 | Review of HRA Defuelling Case against the NSPs Summary | 16-Dec-19 A | 09-Oct-20 A | 209 | 0 | 206 | 100% |  | Completed
ER6371LT | W202 | W202.A1430 | HRA Reactors Shutdown Essential Safety Cases | 2019-12-16 | 2021-10-21 | SC - Safety Case development - tech oversight Cat 1 - Claim 5 - HRA - B-C - STN | 16-Dec-19 A | 01-Sep-21 A | 468 | 0 | 431 | 100% |  | Completed
ER6371LT | W202 | W202.A1450 | HRA Reactors Shutdown Essential Safety Cases | 2019-12-16 | 2019-12-16 | Review of HRA Defuelling Case against the NSPs - Pre Job Brief | 16-Dec-19 A | 16-Dec-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1440 | HYA Reactors Shutdown Essential Safety Cases | 2019-12-16 | 2020-03-02 | Review of HYA Defuelling Case against the NSPs Summary | 16-Dec-19 A | 09-Oct-20 A | 207 | 0 | 206 | 100% |  | Completed
ER6661LT | W206 | W206.A1430 | HYA Reactors Shutdown Essential Safety Cases | 2019-12-16 | 2021-10-21 | SC - Safety Case development - tech oversight Cat 1 - Claim 5 - HYA - B-C - STN | 16-Dec-19 A | 01-Sep-21 A | 468 | 0 | 431 | 100% |  | Completed
ER6661LT | W206 | W206.A1450 | HYA Reactors Shutdown Essential Safety Cases | 2019-12-16 | 2019-12-16 | Review of HYA Defuelling Case against the NSPs - Pre Job Brief | 16-Dec-19 A | 16-Dec-19 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5570 | HRA Reactors Shutdown Essential Safety Cases | 2019-12-16 | 2020-11-10 | Early Claim Lead and Deputy Case Office | 16-Dec-19 A | 26-Feb-21 A | 229 | 0 | 304 | 100% |  | Completed
ER6661LT | W206 | W206.A5580 | HYA Reactors Shutdown Essential Safety Cases | 2019-12-16 | 2020-11-20 | Early Claim Lead and Deputy Case Officer | 16-Dec-19 A | 25-Feb-21 A | 251 | 0 | 303 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1970 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-12-20 | TSA Issue Final Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) | 20-Dec-19 A | 20-Dec-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6940 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-12-20 | Verified Boilers and Gas Circulator Performance Draft EAN Issued to EDF for Technical Review. | 20-Dec-19 A | 20-Dec-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4430 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-12-23 | Fault Schedule Review (Plant Based Faults) Report Completed | 23-Dec-19 A | 23-Dec-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4510 | HNB Reactors Shutdown Essential Safety Cases |  | 2019-12-23 | Fault Schedule Review (Harzards) Report Completed | 23-Dec-19 A | 23-Dec-19 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3730 | HNB Reactors Shutdown Essential Safety Cases | 2020-01-02 | 2020-01-22 | Defuelling Dataset QA Grade 2 Part 2 Report Verified by TSA | 02-Jan-20 A | 22-Jan-20 A | 15 | 0 | 14 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6950 | HNB Reactors Shutdown Essential Safety Cases | 2020-01-02 | 2020-03-10 | Boilers and Gas Circulator Performance Draft EAN Technically Reviewed by EDF SQEP | 02-Jan-20 A | 06-Mar-20 A | 47 | 0 | 46 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7030 | HNB Reactors Shutdown Essential Safety Cases | 2020-01-02 | 2020-03-10 | Boiler Supporting Systems Draft EAN Technically Reviewed by EDF SQEP | 02-Jan-20 A | 03-Apr-20 A | 67 | 0 | 66 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8490 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-01-02 | Reactor Coolant Chemistry Conditions Report Completed | 02-Jan-20 A | 02-Jan-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16310 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-01-02 | All Supporting Technical References Complete - Claim 2 Containment | 02-Jan-20 A | 02-Jan-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16740 | HNB Reactors Shutdown Essential Safety Cases | 2020-01-02 | 2020-01-08 | TSA Address Comments on TR'd Summary Conditions Report - EAN - QA Grade 2 | 02-Jan-20 A | 08-Jan-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6371LT | W202 | W202.A1490 | HRA Reactors Shutdown Essential Safety Cases | 2020-01-02 | 2020-04-03 | Prepare Review of HRA Defuelling Case Against the NSPs Draft Report | 02-Jan-20 A | 13-Apr-20 A | 67 | 0 | 71 | 100% |  | Completed
ER6371LT | W202 | W202.A1470 | HRA Reactors Shutdown Essential Safety Cases | 2020-01-02 | 2020-01-06 | Fault Schedule Review (Plant Base Faults and Hazards) - Draft and issue RFS | 02-Jan-20 A | 06-Jan-20 A | 3 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A1460 | HRA Reactors Shutdown Essential Safety Cases | 2020-01-02 | 2020-02-26 | RFS - Fault Schedule Review (Plant Base Faults and Hazards) Summary | 02-Jan-20 A | 26-Feb-20 A | 40 | 0 | 40 | 100% |  | Completed
ER6661LT | W206 | W206.A1490 | HYA Reactors Shutdown Essential Safety Cases | 2020-01-02 | 2020-04-03 | Prepare Review of HYA Defuelling Case Against the NSPs Draft Report | 02-Jan-20 A | 13-Apr-20 A | 71 | 0 | 71 | 100% |  | Completed
ER6661LT | W206 | W206.A1470 | HYA Reactors Shutdown Essential Safety Cases | 2020-01-02 | 2020-01-06 | Fault Schedule Review (Plant Base Faults and Hazards) - Draft and issue RFS | 02-Jan-20 A | 06-Jan-20 A | 3 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A1460 | HYA Reactors Shutdown Essential Safety Cases | 2020-01-02 | 2020-02-26 | RFS - Fault Schedule Review (Plant Base Faults and Hazards) Summary | 02-Jan-20 A | 26-Feb-20 A | 40 | 0 | 40 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16750 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-01-08 | TSA Issue Final Summary Conditions Report - EAN - QA Grade 2 | 08-Jan-20 A | 08-Jan-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16760 | HNB Reactors Shutdown Essential Safety Cases | 2020-01-09 | 2020-01-15 | Summary Conditions Report - EAN - QA Grade 2 TR Completed and uploaded to CDMS | 09-Jan-20 A | 15-Jan-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8590 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-01-09 | INTERFACE MILESTONE -Criticality Asse'ment for Dropped FPU at Reactor - (W221 Fuel Handling Essential Safety Cases (HNB) | 09-Jan-20 A | 09-Jan-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1500 | HRA Reactors Shutdown Essential Safety Cases | 2020-01-09 | 2020-02-04 | Fault Schedule Review (Plant Base Faults and Hazards) - Supplier prepare and issue Offer | 09-Jan-20 A | 04-Feb-20 A | 19 | 0 | 18 | 100% |  | Completed
ER6661LT | W206 | W206.A1500 | HYA Reactors Shutdown Essential Safety Cases | 2020-01-09 | 2020-02-04 | Fault Schedule Review (Plant Base Faults and Hazards) - Supplier prepare and issue Offer | 09-Jan-20 A | 04-Feb-20 A | 19 | 0 | 18 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17400 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-01-09 | >>>INCOMING ENABLER (W221.A19600) Criticality Assessment for Dropped FPU at Reactor (WET Condition) EAN Available | 09-Jan-20 A | 09-Jan-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17420 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-01-09 | >>>MIRROR OF INCOMING ENABLER (W221.A19600) Criticality Assessment for Dropped FPU at Reactor (WET Con) EAN Available | 09-Jan-20 A | 09-Jan-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A17250 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Project Close Out | 15-Jan-20 A | 15-Apr-20 A | 0 | 0 | 63 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16770 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-01-15 | Summary Conditions Report - EAN - QA Grade 2 Completed | 15-Jan-20 A | 15-Jan-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3740 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-01-22 | Verified Defuelling Dataset QA Grade 2 Part 2 Report Issued to EDF for Technical Review. | 22-Jan-20 A | 22-Jan-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3750 | HNB Reactors Shutdown Essential Safety Cases | 2020-01-23 | 2020-02-07 | Defuelling Dataset QA Grade 2 Part 2 Report Technically Reviewed by EDF SQEP | 23-Jan-20 A | 07-Feb-20 A | 12 | 0 | 11 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17470 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | >>>INCOMING ENABLER (W221.A11520) HF Assessment of Fuel Free Verification EAN Available | 24-Jan-20 A | 24-Jan-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17480 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | >>>MIRROR OF INCOMING ENABLER (W221.A11520) HF Assessment of Fuel Free Verification EAN Available | 24-Jan-20 A | 24-Jan-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11280 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | INTERFACE MILESTONE - HF Assessment of FFV EAN Available - (W221 Fuel Handling Essential Safety Cases (HNB) | 24-Jan-20 A | 24-Jan-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1530 | HRA Reactors Shutdown Essential Safety Cases | 2020-01-27 | 2020-02-14 | Prepare Pressure Boundary Seals Specification | 27-Jan-20 A | 14-Feb-20 A | 15 | 0 | 14 | 100% |  | Completed
ER6371LT | W202 | W202.A1520 | HRA Reactors Shutdown Essential Safety Cases | 2020-01-27 | 2020-03-04 | Pressure Boundary Seals Specification Summary | 27-Jan-20 A | 28-Aug-20 A | 136 | 0 | 150 | 100% |  | Completed
ER6661LT | W206 | W206.A1530 | HYA Reactors Shutdown Essential Safety Cases | 2020-01-27 | 2020-02-14 | Prepare Pressure Boundary Seals Specification | 27-Jan-20 A | 14-Feb-20 A | 15 | 0 | 14 | 100% |  | Completed
ER6661LT | W206 | W206.A1520 | HYA Reactors Shutdown Essential Safety Cases | 2020-01-27 | 2020-03-04 | Pressure Boundary Seals Specification Summary | 27-Jan-20 A | 28-Aug-20 A | 136 | 0 | 150 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2680 | HNB Reactors Shutdown Essential Safety Cases | 2020-01-29 | 2020-01-29 | (SCOPE REMOVED) - Prepare Compliance Scoping Draft Report | 29-Jan-20 A | 29-Jan-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2690 | HNB Reactors Shutdown Essential Safety Cases | 2020-01-29 | 2020-01-29 | (SCOPE REMOVED) - Compliance Scoping Draft Report Verified by TSA | 29-Jan-20 A | 29-Jan-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2700 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-01-29 | (SCOPE REMOVED) - Verified Compliance Scoping Draft Report Issued to EDF for Technical Review. | 29-Jan-20 A | 29-Jan-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2710 | HNB Reactors Shutdown Essential Safety Cases | 2020-01-29 | 2020-01-29 | (SCOPE REMOVED) - Compliance Scoping Draft Report Technically Reviewed by EDF SQEP | 29-Jan-20 A | 29-Jan-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2720 | HNB Reactors Shutdown Essential Safety Cases | 2020-01-29 | 2020-01-29 | (SCOPE REMOVED) - TSA Address Comments on TR'd Compliance Scoping Draft Report | 29-Jan-20 A | 29-Jan-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2730 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-01-29 | (SCOPE REMOVED) - TSA Issue Final Compliance Scoping Report | 29-Jan-20 A | 29-Jan-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2740 | HNB Reactors Shutdown Essential Safety Cases | 2020-01-29 | 2020-01-29 | (SCOPE REMOVED) - Compliance Scoping Report TR Completed and uploaded to CDMS | 29-Jan-20 A | 29-Jan-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2750 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-01-29 | (SCOPE REMOVED) - Compliance Scoping Report Completed | 29-Jan-20 A | 29-Jan-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7870 | HNB Reactors Shutdown Essential Safety Cases | 2020-01-29 | 2020-01-29 | (SCOPE REMOVED) - Prepare Compliance Sensitivities Study Draft Report | 29-Jan-20 A | 29-Jan-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7880 | HNB Reactors Shutdown Essential Safety Cases | 2020-01-29 | 2020-01-29 | (SCOPE REMOVED) - Compliance Sensitivities Study Draft Report Verified by TSA | 29-Jan-20 A | 29-Jan-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7890 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-01-29 | (SCOPE REMOVED) - Verified Compliance Sensitivities Study Draft Report Issued to EDF for Technical Review. | 29-Jan-20 A | 29-Jan-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7900 | HNB Reactors Shutdown Essential Safety Cases | 2020-01-29 | 2020-01-29 | (SCOPE REMOVED) - Compliance Sensitivities Study Draft Report Technically Reviewed by EDF SQEP | 29-Jan-20 A | 29-Jan-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7910 | HNB Reactors Shutdown Essential Safety Cases | 2020-01-29 | 2020-01-29 | (SCOPE REMOVED) - TSA Address Comments on TR'd Compliance Sensitivities Study Draft Report | 29-Jan-20 A | 29-Jan-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7920 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-01-29 | (SCOPE REMOVED) - TSA Issue Final Compliance Sensitivities Study Report | 29-Jan-20 A | 29-Jan-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7930 | HNB Reactors Shutdown Essential Safety Cases | 2020-01-29 | 2020-01-29 | (SCOPE REMOVED) - Compliance Sensitivities Study Report TR Completed and uploaded to CDMS | 29-Jan-20 A | 29-Jan-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7940 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-01-29 | (SCOPE REMOVED) - Compliance Sensitivities Study Report Completed | 29-Jan-20 A | 29-Jan-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2675 | HNB Reactors Shutdown Essential Safety Cases | 2020-01-29 | 2020-01-29 | (SCOPE REMOVED) - Compliance Scoping Summary | 29-Jan-20 A | 29-Jan-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11080 | HNB Reactors Shutdown Essential Safety Cases | 2020-01-29 | 2020-01-29 | (SCOPE REMOVED) - Compliance Sensitivities Study Summary | 29-Jan-20 A | 29-Jan-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8520 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-01-31 | Verified Containment Head Document Draft Report Issued to EDF for Technical Review. | 31-Jan-20 A | 31-Jan-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16790 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-01-31 | Confirm Implementation plans are in line with Cat 1 Safety Case | 31-Jan-20 A | 31-Jan-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16820 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-01-31 | Agree Items going into Local Station Documentation EC - HNB | 31-Jan-20 A | 31-Jan-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1980 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-03 | 2020-03-06 | Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) TR Completed and uploaded to CDMS | 03-Feb-20 A | 27-Mar-20 A | 40 | 0 | 39 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2600 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-03 | 2020-02-20 | Prepare Shutdown margin compliance summary Draft Report | 03-Feb-20 A | 20-Feb-20 A | 14 | 0 | 13 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4130 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-03 | 2020-03-13 | Shutdown Cooling Analysis Draft Report Verified by TSA | 03-Feb-20 A | 27-Mar-20 A | 40 | 0 | 39 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8530 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-03 | 2020-03-10 | Containment Head Document Draft Report Technically Reviewed by EDF SQEP | 03-Feb-20 A | 20-Mar-20 A | 35 | 0 | 34 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2595 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-03 | 2020-04-06 | Shutdown Margin Compliance Report Summary - HNB | 03-Feb-20 A | 26-Jun-20 A | 87 | 0 | 100 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1000 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-03 | 2020-05-14 | <NEW SCOPE> - ALARP Report - Summary | 03-Feb-20 A | 28-May-20 A | 90 | 0 | 79 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1010 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-03 | 2020-03-13 | <NEW SCOPE> - ALARP Report - Prepare Draft Report | 03-Feb-20 A | 13-Mar-20 A | 30 | 0 | 30 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1060 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-03 | 2020-03-27 | <NEW SCOPE> - Definition of Faults for PCPV Integrity - Summary | 03-Feb-20 A | 15-May-20 A | 90 | 0 | 72 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1070 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-02-03 | <NEW SCOPE> - Definition of Faults for PCPV Integrity - Prepare Draft Report | 03-Feb-20 A | 03-Feb-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1080 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-03 | 2020-03-06 | <NEW SCOPE> - Definition of Faults for PCPV Integrity - Prepare Final Report | 03-Feb-20 A | 27-Mar-20 A | 40 | 0 | 39 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1110 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-03 | 2020-02-21 | <NEW SCOPE> - Thermal Analysis - Prepare Report | 03-Feb-20 A | 21-Feb-20 A | 15 | 0 | 14 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1105 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-03 | 2020-03-27 | <NEW SCOPE> - Thermal Analysis Report - Summary | 03-Feb-20 A | 27-Mar-20 A | 40 | 0 | 40 | 100% |  | Completed
ER6370LT | W201 | ER6370.P17100 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-03 | 2020-06-19 | <NEW SCOPE> - Additional SC Authoring Effort | 03-Feb-20 A | 07-Sep-20 A | 144 | 0 | 150 | 100% |  | Completed
ER6371LT | W202 | W202.A1540 | HRA Reactors Shutdown Essential Safety Cases | 2020-02-05 | 2020-02-11 | Fault Schedule Review (Plant Base Faults and Hazards) - Review Offer, prepare and issue CI | 05-Feb-20 A | 11-Feb-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6661LT | W206 | W206.A1540 | HYA Reactors Shutdown Essential Safety Cases | 2020-02-05 | 2020-02-11 | Fault Schedule Review (Plant Base Faults and Hazards) - Review Offer, prepare and issue CI | 05-Feb-20 A | 11-Feb-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6378LT | W222 | W222.A25630 | HRA Fuel Handling Essential Safety Case | 2020-02-05 | 2021-04-09 | FPU Lifting Integrity while Handling at the Reactor ##(Cost Summary)## ### (C3) | 05-Feb-20 A | 09-Apr-21 A | 307 | 0 | 297 | 100% |  | Completed
ER6378LT | W222 | W222.A8860 | HRA Fuel Handling Essential Safety Case | 2020-02-05 | 2020-02-05 | Pre Job Brief for FPU Lifting Integrity while Handling at the Reactor EAN | 05-Feb-20 A | 05-Feb-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A8860 | HYA Fuel Handling Essential Safety Case | 2020-02-05 | 2020-02-05 | Pre Job Brief for FPU Lifting Integrity while Handling at the Reactor EAN | 05-Feb-20 A | 05-Feb-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25630 | HYA Fuel Handling Essential Safety Case | 2020-02-05 | 2021-04-09 | FPU Lifting Integrity while Handling at the Reactor ##(Cost Summary)## ### (C3) | 05-Feb-20 A | 09-Apr-21 A | 307 | 0 | 297 | 100% |  | Completed
ER6378LT | W222 | W222.A8870 | HRA Fuel Handling Essential Safety Case | 2020-02-06 | 2020-11-16 | Draft FPU Lifting Integrity while Handling at the Reactor EAN | 06-Feb-20 A | 16-Nov-20 A | 30 | 0 | 197 | 100% |  | Completed
ER6650LT | W226 | W226.A8870 | HYA Fuel Handling Essential Safety Case | 2020-02-06 | 2020-11-16 | Draft FPU Lifting Integrity while Handling at the Reactor EAN | 06-Feb-20 A | 16-Nov-20 A | 30 | 0 | 197 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4780 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-02-07 | Verified Worker Dose and Risks from Faults Draft Report Issued to EDF for Technical Review. | 07-Feb-20 A | 07-Feb-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7350 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-02-07 | Issue Findings on DNB Commissiong Core Validation Scoping | 07-Feb-20 A | 07-Feb-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3760 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-10 | 2020-03-06 | TSA Address Comments on TR'd Defuelling Dataset QA Grade 2 Part 2 Report | 10-Feb-20 A | 13-Mar-20 A | 25 | 0 | 24 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4790 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-10 | 2020-02-14 | Worker Dose and Risks from Faults Draft Report Technically Reviewed by EDF SQEP | 10-Feb-20 A | 14-Feb-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10910 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-10 | 2020-02-21 | Address Comments from EDF Review on Uncertainty in SDM Calculations Draft Report | 10-Feb-20 A | 21-Feb-20 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1200 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-10 | 2020-06-19 | <NEW SCOPE> - Head Document (PVCW) - Summary | 10-Feb-20 A | 07-Sep-20 A | 139 | 0 | 145 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1290 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-10 | 2020-02-12 | <NEW SCOPE> - Head Document (PVCW) - Draft and issue RFS | 10-Feb-20 A | 12-Feb-20 A | 3 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A1550 | HRA Reactors Shutdown Essential Safety Cases | 2020-02-12 | 2020-02-25 | Fault Schedule Review (Plant Base Faults and Hazards) - Supplier mobilisation time | 12-Feb-20 A | 25-Feb-20 A | 10 | 0 | 9 | 100% |  | Completed
ER6661LT | W206 | W206.A1550 | HYA Reactors Shutdown Essential Safety Cases | 2020-02-12 | 2020-02-25 | Fault Schedule Review (Plant Base Faults and Hazards) - Supplier mobilisation time | 12-Feb-20 A | 25-Feb-20 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1300 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-13 | 2020-02-19 | <NEW SCOPE> - Head Document (PVCW) - Supplier prepare and issue Offer | 13-Feb-20 A | 19-Feb-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6371LT | W202 | W202.A1560 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-02-14 | Issue Pressure Boundary Seals Specification to EDF Review. | 14-Feb-20 A | 14-Feb-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1560 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-02-14 | Issue Pressure Boundary Seals Specification to EDF Review. | 14-Feb-20 A | 14-Feb-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4800 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-17 | 2020-02-21 | TSA Address Comments on TR'd Worker Dose and Risks from Faults Draft Report | 17-Feb-20 A | 21-Feb-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7830 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-17 | 2020-03-06 | TSA Address Comments on TR'd Shutdown Margin Head Document | 17-Feb-20 A | 27-Mar-20 A | 30 | 0 | 29 | 100% |  | Completed
ER6371LT | W202 | W202.A1570 | HRA Reactors Shutdown Essential Safety Cases | 2020-02-17 | 2020-02-21 | Pressure Boundary Seals Specification Reviewed by EDF SQEP | 17-Feb-20 A | 21-Feb-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6661LT | W206 | W206.A1570 | HYA Reactors Shutdown Essential Safety Cases | 2020-02-17 | 2020-02-21 | Pressure Boundary Seals Specification Reviewed by EDF SQEP | 17-Feb-20 A | 21-Feb-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1310 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-20 | 2020-02-21 | <NEW SCOPE> - Head Document (PVCW) - Review Offer, prepare and issue CI | 20-Feb-20 A | 21-Feb-20 A | 2 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2610 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-21 | 2020-02-28 | Shutdown margin compliance summary Draft Report Verified by TSA | 21-Feb-20 A | 28-Feb-20 A | 6 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4810 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-02-21 | TSA Issue Final Worker Dose and Risks from Faults Report | 21-Feb-20 A | 21-Feb-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1580 | HRA Reactors Shutdown Essential Safety Cases | 2020-02-21 | 2020-02-21 | Review of HRA Defuelling Case against the NSPs - Mid-Job Brief | 21-Feb-20 A | 21-Feb-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A1580 | HYA Reactors Shutdown Essential Safety Cases | 2020-02-21 | 2020-02-21 | Review of HYA Defuelling Case against the NSPs - Mid-Job Brief | 21-Feb-20 A | 21-Feb-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4280 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-24 | 2020-03-13 | Prepare Core Cooling Compliance Summary Draft Report | 24-Feb-20 A | 12-Jun-20 A | 57 | 0 | 75 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4820 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-24 | 2020-02-28 | Worker Dose and Risks from Faults Report TR Completed and uploaded to CDMS | 24-Feb-20 A | 28-Feb-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4275 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-24 | 2020-04-28 | Core Cooling Compliance Summary | 24-Feb-20 A | 14-Jul-20 A | 109 | 0 | 97 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1120 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-24 | 2020-03-03 | <NEW SCOPE> - Thermal Analysis - Verification and Address Comments of Report | 24-Feb-20 A | 03-Mar-20 A | 7 | 0 | 6 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1320 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-24 | 2020-02-28 | <NEW SCOPE> - Head Document (PVCW) - Supplier mobilisation time | 24-Feb-20 A | 28-Feb-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6371LT | W202 | W202.A1590 | HRA Reactors Shutdown Essential Safety Cases | 2020-02-24 | 2020-02-28 | Address Comments on Reviewed Pressure Boundary Seals Specification | 24-Feb-20 A | 28-Feb-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6661LT | W206 | W206.A1590 | HYA Reactors Shutdown Essential Safety Cases | 2020-02-24 | 2020-02-28 | Address Comments on Reviewed Pressure Boundary Seals Specification | 24-Feb-20 A | 28-Feb-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6378LT | W222 | W222.A26300 | HRA Fuel Handling Essential Safety Case | 2020-02-25 | 2021-04-26 | Shock Absorbers Feasibility Study ##(Cost Summary)## (C5) (NEW) | 25-Feb-20 A | 26-Apr-21 A | 352 | 0 | 294 | 100% |  | Completed
ER6378LT | W222 | W222.A23730 | HRA Fuel Handling Essential Safety Case | 2020-02-25 | 2020-02-25 | Pre Job Brief for Shock Absorbers Feasibility Study EAN | 25-Feb-20 A | 25-Feb-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A23730 | HYA Fuel Handling Essential Safety Case | 2020-02-25 | 2020-02-25 | Pre Job Brief for Shock Absorbers Feasibility Study EAN | 25-Feb-20 A | 25-Feb-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A26300 | HYA Fuel Handling Essential Safety Case | 2020-02-25 | 2021-04-26 | Shock Absorbers Feasibility Study ##(Cost Summary)## (C5) (NEW) | 25-Feb-20 A | 26-Apr-21 A | 352 | 0 | 294 | 100% |  | Completed
ER6371LT | W202 | W202.A1610 | HRA Reactors Shutdown Essential Safety Cases | 2020-02-26 | 2020-02-26 | Fault Schedule Review (Plant Base Faults and Hazards) - Pre Job Brief | 26-Feb-20 A | 26-Feb-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A1610 | HYA Reactors Shutdown Essential Safety Cases | 2020-02-26 | 2020-02-26 | Fault Schedule Review (Plant Base Faults and Hazards) - Pre Job Brief | 26-Feb-20 A | 26-Feb-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A23740 | HRA Fuel Handling Essential Safety Case | 2020-02-26 | 2020-05-29 | Draft Shock Absorbers Feasibility Study EAN | 26-Feb-20 A | 29-May-20 A | 64 | 0 | 63 | 100% |  | Completed
ER6650LT | W226 | W226.A23740 | HYA Fuel Handling Essential Safety Case | 2020-02-26 | 2020-05-29 | Draft Shock Absorbers Feasibility Study EAN | 26-Feb-20 A | 29-May-20 A | 64 | 0 | 63 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1140 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-27 | 2020-04-09 | <NEW SCOPE> - Civils Integrity Report - Prepare Report | 27-Feb-20 A | 22-May-20 A | 45 | 0 | 58 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1135 | HNB Reactors Shutdown Essential Safety Cases | 2020-02-27 | 2020-04-30 | <NEW SCOPE> - Civils Integrity Report - Summary | 27-Feb-20 A | 12-Jun-20 A | 88 | 0 | 72 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2620 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-02-28 | Verified Shutdown margin compliance summary Draft Report Issued to EDF for Technical Review. | 28-Feb-20 A | 28-Feb-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4830 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-02-28 | Worker Dose and Risks from Faults Report Completed | 28-Feb-20 A | 28-Feb-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1620 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-02-28 | Issue Final Pressure Boundary Seals Specification | 28-Feb-20 A | 28-Feb-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1620 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-02-28 | Issue Final Pressure Boundary Seals Specification | 28-Feb-20 A | 28-Feb-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1290 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-27 | 2020-07-17 | Prepare the Safety Case Proposal (HNB) | 02-Mar-20 A | 09-Oct-20 A | 281 | 0 | 155 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11060 | HNB Reactors Shutdown Essential Safety Cases | 2019-06-03 | 2020-04-30 | RAWG Endorsement of Methods | 02-Mar-20 A | 28-Jul-20 A | 272 | 0 | 103 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11100 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-02 | 2020-07-17 | SC - Safety Case development - tech oversight Cat 1 - Claim 1 - HNB - B-C - STN | 02-Mar-20 A | 28-Jul-20 A | 399 | 0 | 102 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11120 | HNB Reactors Shutdown Essential Safety Cases | 2019-02-01 | 2020-07-17 | SC - Safety Case development - tech oversight Cat 1 - Claim 2 - HNB - B-C - STN | 02-Mar-20 A | 15-Sep-20 A | 377 | 0 | 136 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11140 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-02 | 2020-07-17 | SC - Safety Case development - tech oversight Cat 1 - Claim 3 - HNB - B-C - STN | 02-Mar-20 A | 09-Oct-20 A | 399 | 0 | 154 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11160 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-28 | 2020-07-17 | SC - Safety Case development - tech oversight Cat 1 - Claim 4 - HNB - B-C - STN | 02-Mar-20 A | 30-Jun-20 A | 381 | 0 | 82 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11190 | HNB Reactors Shutdown Essential Safety Cases | 2019-01-02 | 2020-07-17 | SC - Safety Case development - tech oversight Cat 1 - Claim 5 - HNB - B-C - STN | 02-Mar-20 A | 30-Jun-20 A | 399 | 0 | 82 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11210 | HNB Reactors Shutdown Essential Safety Cases | 2019-08-27 | 2020-07-17 | SC - Safety Case development - Stakeholder comms Cat 1 - HNB - B-C - INA | 02-Mar-20 A | 09-Oct-20 A | 235 | 0 | 155 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1340 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-09 | 2020-03-13 | <NEW SCOPE> - Case Conferences - Summary | 02-Mar-20 A | 20-Mar-20 A | 15 | 0 | 14 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1350 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-09 | 2020-03-13 | <NEW SCOPE> - Case Conferences | 02-Mar-20 A | 20-Mar-20 A | 15 | 0 | 14 | 100% |  | Completed
ER6371LT | W202 | W202.A1510 | HRA Reactors Shutdown Essential Safety Cases | 2020-01-27 | 2021-10-21 | SC - Safety Case development - tech oversight Cat 1 - Claim 2 - HRA - B-C - STN | 02-Mar-20 A | 01-Sep-21 A | 455 | 0 | 379 | 100% |  | Completed
ER6371LT | W202 | W202.A1600 | HRA Reactors Shutdown Essential Safety Cases | 2020-02-26 | 2021-10-21 | SC - Safety Case development - tech oversight Cat 1 - Claim 3 - HRA - B-C - STN | 02-Mar-20 A | 01-Sep-21 A | 433 | 0 | 379 | 100% |  | Completed
ER6661LT | W206 | W206.A1510 | HYA Reactors Shutdown Essential Safety Cases | 2020-01-27 | 2021-10-21 | SC - Safety Case development - tech oversight Cat 1 - Claim 2 - HYA - B-C - STN | 02-Mar-20 A | 01-Sep-21 A | 455 | 0 | 379 | 100% |  | Completed
ER6661LT | W206 | W206.A1600 | HYA Reactors Shutdown Essential Safety Cases | 2020-02-26 | 2021-10-21 | SC - Safety Case development - tech oversight Cat 1 - Claim 3 - HYA - B-C - STN | 02-Mar-20 A | 01-Sep-21 A | 433 | 0 | 379 | 100% |  | Completed
ER6378LT | W222 | W222.A25960 | HRA Fuel Handling Essential Safety Case | 2020-03-02 | 2020-05-01 | Update Core Support Plate Properties Tensile ##(Cost Summary)## (C5) (NEW) | 02-Mar-20 A | 01-May-20 A | 43 | 0 | 42 | 100% |  | Completed
ER6378LT | W222 | W222.A23240 | HRA Fuel Handling Essential Safety Case | 2020-03-02 | 2020-03-02 | Pre Job Brief for Update Core Support Plate Properties Tensile EAN | 02-Mar-20 A | 02-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A9900 | HRA Fuel Handling Essential Safety Case | 2020-03-02 | 2020-03-02 | Pre Job Brief for Update to Failed Fuel EAN | 02-Mar-20 A | 02-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A19440 | HRA Fuel Handling Essential Safety Case | 2020-03-02 | 2020-09-09 | Failed Fuel ##(Cost Summary)## ### (C1) | 02-Mar-20 A | 09-Sep-20 A | 152 | 0 | 132 | 100% |  | Completed
ER6378LT | W222 | W222.A22240 | HRA Fuel Handling Essential Safety Case | 2020-03-02 | 2020-08-28 | EAC (02-Mar-2020 - 28-Aug-2020) ##(Cost Summary)## | 02-Mar-20 A | 28-Aug-20 A | 126 | 0 | 125 | 100% |  | Completed
ER6650LT | W226 | W226.A22240 | HYA Fuel Handling Essential Safety Case | 2020-03-02 | 2020-08-28 | EAC (02-Mar-2020 - 28-Aug-2020) ##(Cost Summary)## | 02-Mar-20 A | 28-Aug-20 A | 126 | 0 | 125 | 100% |  | Completed
ER6650LT | W226 | W226.A19440 | HYA Fuel Handling Essential Safety Case | 2020-03-02 | 2020-09-09 | Failed Fuel ##(Cost Summary)## ### (C1) | 02-Mar-20 A | 09-Sep-20 A | 152 | 0 | 132 | 100% |  | Completed
ER6650LT | W226 | W226.A9900 | HYA Fuel Handling Essential Safety Case | 2020-03-02 | 2020-03-02 | Pre Job Brief for Update to Failed Fuel EAN | 02-Mar-20 A | 02-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A23240 | HYA Fuel Handling Essential Safety Case | 2020-03-02 | 2020-03-02 | Pre Job Brief for Update Core Support Plate Properties Tensile EAN | 02-Mar-20 A | 02-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25960 | HYA Fuel Handling Essential Safety Case | 2020-03-02 | 2020-05-01 | Update Core Support Plate Properties Tensile ##(Cost Summary)## (C5) (NEW) | 02-Mar-20 A | 01-May-20 A | 43 | 0 | 42 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2630 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-10 | 2020-03-23 | Shutdown margin compliance summary Draft Report Technically Reviewed by EDF SQEP | 03-Mar-20 A | 13-Mar-20 A | 9 | 0 | 8 | 100% |  | Completed
ER6378LT | W222 | W222.A23250 | HRA Fuel Handling Essential Safety Case | 2020-03-03 | 2020-03-31 | Draft Update Core Support Plate Properties Tensile EAN | 03-Mar-20 A | 31-Mar-20 A | 21 | 0 | 20 | 100% |  | Completed
ER6378LT | W222 | W222.A9910 | HRA Fuel Handling Essential Safety Case | 2020-03-03 | 2020-05-26 | Draft Update to Failed Fuel EAN | 03-Mar-20 A | 26-May-20 A | 18 | 0 | 56 | 100% |  | Completed
ER6650LT | W226 | W226.A9910 | HYA Fuel Handling Essential Safety Case | 2020-03-03 | 2020-05-26 | Draft Update to Failed Fuel EAN | 03-Mar-20 A | 26-May-20 A | 18 | 0 | 56 | 100% |  | Completed
ER6650LT | W226 | W226.A23250 | HYA Fuel Handling Essential Safety Case | 2020-03-03 | 2020-03-31 | Draft Update Core Support Plate Properties Tensile EAN | 03-Mar-20 A | 31-Mar-20 A | 21 | 0 | 20 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6960 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-11 | 2020-03-24 | TSA Address Comments on TR'd Boilers and Gas Circulator Performance Draft EAN | 09-Mar-20 A | 17-Mar-20 A | 7 | 0 | 6 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3770 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-06 | TSA Issue Final Defuelling Dataset QA Grade 2 Part 2 Report | 13-Mar-20 A | 13-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2640 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-24 | 2020-03-30 | TSA Address Comments on TR'd Shutdown margin compliance summary Draft Report | 16-Mar-20 A | 27-Mar-20 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3780 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-09 | 2020-03-13 | Defuelling Dataset QA Grade 2 Part 2 Report TR Completed and uploaded to CDMS | 16-Mar-20 A | 27-Mar-20 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1020 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-16 | 2020-03-20 | <NEW SCOPE> - ALARP Report - Draft Report Reviewed by SQEP | 16-Mar-20 A | 20-Mar-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1030 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-16 | 2020-04-03 | <NEW SCOPE> - ALARP Report - Verification of Draft Report | 16-Mar-20 A | 20-May-20 A | 14 | 0 | 44 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1330 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-02 | 2020-03-02 | <NEW SCOPE> - Head Document (PVCW) - Pre Job Brief | 16-Mar-20 A | 16-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1630 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-02 | 2020-03-04 | Pressure Boundary Seals Specification Completed and uploaded to CDMS | 16-Mar-20 A | 28-Aug-20 A | 101 | 0 | 115 | 100% |  | Completed
ER6371LT | W202 | W202.A44580 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-16 | 2020-07-20 | Opex Capture from HPB / HNB | 16-Mar-20 A | 15-Sep-20 A | 66 | 0 | 127 | 100% |  | Completed
ER6661LT | W206 | W206.A1630 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-02 | 2020-03-04 | Pressure Boundary Seals Specification Completed and uploaded to CDMS | 16-Mar-20 A | 28-Aug-20 A | 101 | 0 | 115 | 100% |  | Completed
ER6378LT | W222 | W222.A26070 | HRA Fuel Handling Essential Safety Case | 2020-03-16 | 2021-02-03 | Fuel Route Operational Sequence/Process for Defuelling ##(Cost Summary)## (C6) (NEW) | 16-Mar-20 A | 03-Feb-21 A | 225 | 0 | 225 | 100% |  | Completed
ER6378LT | W222 | W222.A24360 | HRA Fuel Handling Essential Safety Case | 2020-03-16 | 2020-03-16 | Pre Job Brief for Fuel Route Operational Sequence/Process for Defuelling EAN (REV 000) | 16-Mar-20 A | 16-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A24360 | HYA Fuel Handling Essential Safety Case | 2020-03-16 | 2020-03-16 | Pre Job Brief for Fuel Route Operational Sequence/Process for Defuelling EAN (REV 000) | 16-Mar-20 A | 16-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A26070 | HYA Fuel Handling Essential Safety Case | 2020-03-16 | 2021-02-03 | Fuel Route Operational Sequence/Process for Defuelling ##(Cost Summary)## (C6) (NEW) | 16-Mar-20 A | 03-Feb-21 A | 225 | 0 | 225 | 100% |  | Completed
ER6661LT | W206 | W206.A44580 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-16 | 2020-09-01 | Opex Capture from HPB / HNB | 16-Mar-20 A | 15-Sep-20 A | 117 | 0 | 127 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6970 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-24 | TSA Issue Final Boilers and Gas Circulator Performance EAN | 17-Mar-20 A | 17-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1280 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-03 | 2020-04-03 | <NEW SCOPE> - Head Document (PVCW) - Identify and Address Gaps in Head Document | 17-Mar-20 A | 23-Mar-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6378LT | W222 | W222.A24370 | HRA Fuel Handling Essential Safety Case | 2020-03-17 | 2020-04-14 | Draft Fuel Route Operational Sequence/Process for Defuelling EAN (REV 000) | 17-Mar-20 A | 14-Apr-20 A | 19 | 0 | 18 | 100% |  | Completed
ER6650LT | W226 | W226.A24370 | HYA Fuel Handling Essential Safety Case | 2020-03-17 | 2020-04-14 | Draft Fuel Route Operational Sequence/Process for Defuelling EAN (REV 000) | 17-Mar-20 A | 14-Apr-20 A | 19 | 0 | 18 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6980 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-25 | 2020-04-07 | Boilers and Gas Circulator Performance EAN TR Completed and uploaded to CDMS | 18-Mar-20 A | 27-Mar-20 A | 8 | 0 | 7 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1360 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-13 | <NEW SCOPE> - DIscovery MS - Confirm Impact of PVCW Isolation on existing Technical References and Head Documents | 20-Mar-20 A | 20-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1670 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-09 | 2020-03-13 | Dropped FPU Strategy Development HRA - Draft and issue RFS | 20-Mar-20 A | 26-Mar-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6371LT | W202 | W202.A1660 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-09 | 2020-04-22 | RFS - Dropped FPU Strategy Development HRA - Summary | 20-Mar-20 A | 01-Jun-20 A | 25 | 0 | 48 | 100% |  | Completed
ER6661LT | W206 | W206.A1670 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-09 | 2020-03-13 | Dropped FPU Strategy Development HYA - Draft and issue RFS | 20-Mar-20 A | 26-Mar-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A1660 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-09 | 2020-04-22 | RFS - Dropped FPU Strategy Development HYA - Summary | 20-Mar-20 A | 01-Jun-20 A | 31 | 0 | 48 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8540 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-11 | 2020-03-31 | TSA Address Comments on TR'd Containment Head Document Draft Report | 23-Mar-20 A | 12-Jun-20 A | 56 | 0 | 55 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1130 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-23 | 2020-03-27 | <NEW SCOPE> - Thermal Analysis - Issue Report and upload to CDMS | 23-Mar-20 A | 27-Mar-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A1680 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-16 | 2020-05-15 | Assumptions EAN - Summary | 23-Mar-20 A | 15-Jun-20 A | 59 | 0 | 57 | 100% |  | Completed
ER6371LT | W202 | W202.A1690 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-16 | 2020-03-16 | Assumptions EAN - Pre-Job Brief | 23-Mar-20 A | 23-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1680 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-16 | 2020-05-15 | Assumptions EAN - Summary | 23-Mar-20 A | 15-Jun-20 A | 77 | 0 | 57 | 100% |  | Completed
ER6661LT | W206 | W206.A1690 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-16 | 2020-03-16 | Assumptions EAN - Pre-Job Brief | 23-Mar-20 A | 23-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1710 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-17 | 2020-04-15 | Assumptions EAN - Prepare Draft Report | 24-Mar-20 A | 20-Apr-20 A | 18 | 0 | 17 | 100% |  | Completed
ER6661LT | W206 | W206.A1710 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-17 | 2020-04-15 | Assumptions EAN - Prepare Draft Report | 24-Mar-20 A | 20-Apr-20 A | 18 | 0 | 17 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1990 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-06 | Shutdown Margin Assessments with Uncertainties / Sensitivity Studies (Stage 2) Completed | 27-Mar-20 A | 27-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2650 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-30 | TSA Issue Final Shutdown margin compliance summary Report | 27-Mar-20 A | 27-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A3790 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-13 | Defuelling Dataset QA Grade 2 Part 2 Report Completed | 27-Mar-20 A | 27-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4140 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-13 | Verified Shutdown Cooling Analysis Draft Report Issued to EDF for Technical Review. | 27-Mar-20 A | 27-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A6990 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-04-07 | Boilers and Gas Circulator Performance EAN Completed | 27-Mar-20 A | 27-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13030 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-13 | KDM MACE – Dataset and Validation Complete (HNB) | 27-Mar-20 A | 27-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7840 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-06 | TSA Issue Final Shutdown Margin Head Document | 27-Mar-20 A | 27-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10920 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-06 | Issue Final Uncertainty in SDM Calculations Report Report | 27-Mar-20 A | 27-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17360 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-13 | >>>OUTGOING ENABLER (W221) Defuelling Dataset QA Grade 2 Part 2 Report Completed | 27-Mar-20 A | 27-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17430 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-02 | >>>INCOMING ENABLER (W221.A20230) Dropped FPU Characterisation EAN Available | 27-Mar-20 A | 27-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17440 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-02 | >>>MIRROR OF INCOMING ENABLER (W221.A20230) Dropped FPU Characterisation EAN Available | 27-Mar-20 A | 27-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8090 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-02 | INTERFACE MILESTONE - Dropped FPU Characterisation EAN Available - (W221 Fuel Handling Essential Safety Cases (HNB)) | 27-Mar-20 A | 27-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1700 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-16 | 2020-03-27 | Dropped FPU Strategy Development HRA - Supplier prepare and issue Offer | 27-Mar-20 A | 09-Apr-20 A | 10 | 0 | 9 | 100% |  | Completed
ER6661LT | W206 | W206.A1700 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-16 | 2020-03-27 | Dropped FPU Strategy Development HYA - Supplier prepare and issue Offer | 27-Mar-20 A | 09-Apr-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4150 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-16 | 2020-03-27 | Shutdown Cooling Analysis Draft Report Technically Reviewed by EDF SQEP | 30-Mar-20 A | 14-Apr-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7850 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-09 | 2020-03-20 | Shutdown Margin Head Document TR Completed and uploaded to CDMS | 30-Mar-20 A | 26-Jun-20 A | 30 | 0 | 60 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1090 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-09 | 2020-03-20 | <NEW SCOPE> - Definition of Faults for PCPV Integrity - Verification and Address Comments of Final Report | 30-Mar-20 A | 08-May-20 A | 24 | 0 | 27 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1210 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-30 | 2020-05-15 | <NEW SCOPE> - Head Document (PVCW) - Prepare Draft Head Document | 30-Mar-20 A | 17-Jun-20 A | 33 | 0 | 53 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17450 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-06 | >>>INCOMING ENABLER (W221.A16210) Structural Integrity Analysis for Dropped FPU EAN Available | 30-Mar-20 A | 30-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17460 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-06 | >>>MIRROR OF INCOMING ENABLER (W221.A16210) Structural Integrity Analysis for Dropped FPU EAN Available | 30-Mar-20 A | 30-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8600 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-06 | INTERFACE MILESTONE -Structural Integrity Analysis for Dropped FPU EAN- (W221 Fuel Handling Essential Safety Cases (HNB) | 30-Mar-20 A | 30-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7080 | HNB Reactors Shutdown Essential Safety Cases |  |  | Boilers and Gas Circulator Performance - Reworked Draft EAN | 30-Mar-20 A | 24-Apr-20 A | 18 | 0 | 17 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10930 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-06 | 2020-03-11 | Uncertainty in SDM Calculations Report Completed and Uploaded to CDMS | 30-Mar-20 A | 08-May-20 A | 27 | 0 | 27 | 100% |  | Completed
ER6371LT | W202 | W202.A859010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Prepare Shutdown margin compliance summary Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A886010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Prepare Core Cooling Compliance Summary Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A908010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Issue Core Cooling Compliance Summary Draft Report to EDF for Review. - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A911010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Core Cooling Compliance Summary Draft Report Reviewed by EDF SQEP - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A932010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Address Comments from EDF's Review of Core Cooling Compliance Summary Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A950010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Issue Final Core Cooling Compliance Summary Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A952010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Core Cooling Compliance Summary Report Completed and uploaded to CDMS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A965010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Core Cooling Compliance Summary Report Completed - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A863010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Prepare Shutdown margin compliance summary Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A805010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Prepare Requirements for Severe Accidents Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A858010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Shutdown Margin Compliance Report Summary - HYA - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A862010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Shutdown Margin Compliance Report Summary - HAR - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A804010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Requirements for Severe Accidents Summary - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1190510 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Review of / Changes to Emergency Arrangements Summary - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A885010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Core Cooling Compliance Summary - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A743010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Shutdown Margin Compliance Report - Draft and issue RFS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A742010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | RFS - Shutdown Margin Compliance Report Summary - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A219010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Reactor Coolant Chemistry Conditions - Draft and issue RFS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A218010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | RFS - Reactor Coolant Chemistry Conditions Summary - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A497010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | LSD Strategy Draft Report - Draft and issue RFS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A229010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Structures and Equipment Integrity - Draft and issue RFS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A228010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | RFS - Structures and Equipment Integrity Summary - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A2203010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | SDM Assessments - Data / sensitivity studies Draft Report Reviewed by EDF SQEP - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2204010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Address Comments from EDF Review on SDM Assessments - Data / sensitivity studies Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2205010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Issue Final SDM Assessments - Data / sensitivity studies Report Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | SDM Assessments - Data / sensitivity studies Report Completed and Uploaded to CDMS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1092010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Programme 6.1 Station Documentation and Implementation Strategy - Draft and issue RFS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1191010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Prepare Review of / Changes to Emergency Arrangements Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A859010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Prepare Shutdown margin compliance summary Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A886010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Prepare Core Cooling Compliance Summary Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A908010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Issue Core Cooling Compliance Summary Draft Report to EDF for Review. - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A911010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Core Cooling Compliance Summary Draft Report Reviewed by EDF SQEP - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A932010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Address Comments from EDF's Review of Core Cooling Compliance Summary Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A950010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Issue Final Core Cooling Compliance Summary Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A952010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Core Cooling Compliance Summary Report Completed and uploaded to CDMS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A965010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Core Cooling Compliance Summary Report Completed - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A863010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Prepare Shutdown margin compliance summary Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A805010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Prepare Requirements for Severe Accidents Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A858010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Shutdown Margin Compliance Report Summary - HYA - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A862010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Shutdown Margin Compliance Report Summary - HAR - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A804010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Requirements for Severe Accidents Summary - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A1190510 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Review of / Changes to Emergency Arrangements Summary - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A885010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Core Cooling Compliance Summary - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A743010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Shutdown Margin Compliance Report - Draft and issue RFS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A742010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | RFS - Shutdown Margin Compliance Report Summary - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A219010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Reactor Coolant Chemistry Conditions - Draft and issue RFS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A218010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | RFS - Reactor Coolant Chemistry Conditions Summary - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A497010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | LSD Strategy Draft Report - Draft and issue RFS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A229010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Structures and Equipment Integrity - Draft and issue RFS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A228010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | RFS - Structures and Equipment Integrity Summary - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2203010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | SDM Assessments - Data / sensitivity studies Draft Report Reviewed by EDF SQEP - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2204010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Address Comments from EDF Review on SDM Assessments - Data / sensitivity studies Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2205010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Issue Final SDM Assessments - Data / sensitivity studies Report Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | SDM Assessments - Data / sensitivity studies Report Completed and Uploaded to CDMS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1092010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Programme 6.1 Station Documentation and Implementation Strategy - Draft and issue RFS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1191010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Prepare Review of / Changes to Emergency Arrangements Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A898010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Shutdown margin compliance summary Draft Report Verified by TSA - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A918010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Shutdown margin compliance summary Draft Report Technically Reviewed by EDF SQEP - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A942010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | TSA Address Comments on TR'd Shutdown margin compliance summary Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A956010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Shutdown margin compliance summary Report TR Completed and uploaded to CDMS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A642010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Prepare LSD Strategy Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A729010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | LSD Strategy Draft Report Verified by TSA - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A783010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | LSD Strategy Draft Report Technically Reviewed by EDF SQEP - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A813010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | TSA Address Comments on TR'd LSD Strategy Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A844010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | LSD Strategy Report TR Completed and uploaded to CDMS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A901010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Shutdown margin compliance summary Draft Report Verified by TSA - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A921010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Shutdown margin compliance summary Draft Report Technically Reviewed by EDF SQEP - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A943010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | TSA Address Comments on TR'd Shutdown margin compliance summary Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A957010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Shutdown margin compliance summary Report TR Completed and uploaded to CDMS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A866010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Requirements for Severe AccidentsDraft Report Verified by TSA - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A892010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Requirements for Severe AccidentsDraft Report Technically Reviewed by EDF SQEP - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A903010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | TSA Address Comments on TR'd Requirements for Severe AccidentsDraft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A923010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Requirements for Severe AccidentsReport TR Completed and uploaded to CDMS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A409010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Prepare Reactor Coolant Chemistry Conditions Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A459010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Reactor Coolant Chemistry Conditions Draft Report Reviewed by EDF SQEP - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A484010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Address Comments on Reviwed Reactor Coolant Chemistry Conditions Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A510010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Reactor Coolant Chemistry Conditions Final Report Completed and uploaded to CDMS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A412010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Prepare Structures and Equipment Integrity Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A578010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Structures and Equipment Integrity Draft Report Verified by TSA - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A626010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Structures and Equipment Integrity Draft Report Technically Reviewed by EDF SQEP - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A674010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | TSA Address Comments on TR'd Structures and Equipment Integrity Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A719010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Structures and Equipment Integrity Report TR Completed and uploaded to CDMS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A271010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Specification for LSD Strategy Draft Report Summary - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A411010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Structures and Equipment Integrity Summary - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A395010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Reactor Coolant Chemistry Conditions Summary - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A769010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Shutdown Margin Compliance Report - Supplier prepare and issue Offer - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A808010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Shutdown Margin Compliance Report - Review Offer, prepare and issue CI - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A826010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Shutdown Margin Compliance Report - Supplier mobilisation time - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A851010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Shutdown Margin Compliance Report - Pre Job Brief - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A246010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Reactor Coolant Chemistry Conditions - Supplier prepare and issue Offer - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A305010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Reactor Coolant Chemistry Conditions - Review Offer, prepare and issue CI - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A332010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Reactor Coolant Chemistry Conditions - Supplier mobilisation time - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A382010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Reactor Coolant Chemistry Conditions - Pre Job Brief - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A528010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | LSD Strategy Draft Report - Supplier prepare and issue Offer - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A568010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | LSD Strategy Draft Report - Review Offer, prepare and issue CI - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A581010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | LSD Strategy Draft Report - Supplier mobilisation time - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A629010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | LSD Strategy Draft Report - Pre Job Brief - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A255010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Structures and Equipment Integrity - Supplier prepare and issue Offer - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A316010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Structures and Equipment Integrity - Review Offer, prepare and issue CI - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A348010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Structures and Equipment Integrity - Supplier mobilisation time - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A401010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Structures and Equipment Integrity - Pre Job Brief - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1084010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Prepare Programme 6.1 Station Documentation and Implementation Strategy - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1085010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Programme 6.1 Station Documentation and Implementation Strategy Verified by TSA - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1087010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Programme 6.1 Station Documentation and Implementation Strategy Technically Reviewed by EDF SQEP - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1088010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | TSA Address Comments on TR'd Programme 6.1 Station Documentation and Implementation Strategy - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1090010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Programme 6.1 Station Documentation and Implementation Strategy TR Completed and uploaded to CDMS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1093010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Programme 6.1 Station Documentation and Implementation Strategy - Supplier prepare and issue Offer - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1094010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Programme 6.1 Station Documentation and Implementation Strategy - Review Offer, prepare and issue CI - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1095010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Programme 6.1 Station Documentation and Implementation Strategy - Supplier mobilisation time - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1096010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Programme 6.1 Station Documentation and Implementation Strategy - Pre Job Brief - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1193010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Review of / Changes to Emergency Arrangements Report Reviewed by EDF SQEP - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1194010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Address Comments on Reviewed Review of / Changes to Emergency Arrangements Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1196010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Review of / Changes to Emergency Arrangements Report Completed and uploaded to CDMS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1198010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Develop Boundary Conditions Summary - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1199010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Prepare Boundary ConditionsReport - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1200010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Boundary Conditions Report Verified by TSA - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1202010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Boundary Conditions Report Technically Reviewed by EDF SQEP - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1203010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | TSA Address Comments on TR'd Boundary Conditions Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1205010 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Boundary Conditions Report TR Completed and uploaded to CDMS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1083510 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Programme 6.1 Station Documentation and Implementation Strategy Summary - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A898010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Shutdown margin compliance summary Draft Report Verified by TSA - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A918010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Shutdown margin compliance summary Draft Report Technically Reviewed by EDF SQEP - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A942010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | TSA Address Comments on TR'd Shutdown margin compliance summary Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A956010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Shutdown margin compliance summary Report TR Completed and uploaded to CDMS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A642010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Prepare LSD Strategy Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A729010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | LSD Strategy Draft Report Verified by TSA - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A783010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | LSD Strategy Draft Report Technically Reviewed by EDF SQEP - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A813010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | TSA Address Comments on TR'd LSD Strategy Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A844010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | LSD Strategy Report TR Completed and uploaded to CDMS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A901010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Shutdown margin compliance summary Draft Report Verified by TSA - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A921010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Shutdown margin compliance summary Draft Report Technically Reviewed by EDF SQEP - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A943010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | TSA Address Comments on TR'd Shutdown margin compliance summary Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A957010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Shutdown margin compliance summary Report TR Completed and uploaded to CDMS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A866010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Requirements for Severe AccidentsDraft Report Verified by TSA - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A892010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Requirements for Severe AccidentsDraft Report Technically Reviewed by EDF SQEP - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A903010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | TSA Address Comments on TR'd Requirements for Severe AccidentsDraft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A923010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Requirements for Severe AccidentsReport TR Completed and uploaded to CDMS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A409010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Prepare Reactor Coolant Chemistry Conditions Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A459010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Reactor Coolant Chemistry Conditions Draft Report Reviewed by EDF SQEP - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A484010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Address Comments on Reviwed Reactor Coolant Chemistry Conditions Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A510010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Reactor Coolant Chemistry Conditions Final Report Completed and uploaded to CDMS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A412010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Prepare Structures and Equipment Integrity Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A578010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Structures and Equipment Integrity Draft Report Verified by TSA - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A626010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Structures and Equipment Integrity Draft Report Technically Reviewed by EDF SQEP - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A674010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | TSA Address Comments on TR'd Structures and Equipment Integrity Draft Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A719010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Structures and Equipment Integrity Report TR Completed and uploaded to CDMS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A271010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Specification for LSD Strategy Draft Report Summary - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A411010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Structures and Equipment Integrity Summary - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A395010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Reactor Coolant Chemistry Conditions Summary - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A769010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Shutdown Margin Compliance Report - Supplier prepare and issue Offer - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A808010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Shutdown Margin Compliance Report - Review Offer, prepare and issue CI - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A826010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Shutdown Margin Compliance Report - Supplier mobilisation time - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A851010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Shutdown Margin Compliance Report - Pre Job Brief - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A246010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Reactor Coolant Chemistry Conditions - Supplier prepare and issue Offer - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A305010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Reactor Coolant Chemistry Conditions - Review Offer, prepare and issue CI - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A332010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Reactor Coolant Chemistry Conditions - Supplier mobilisation time - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A382010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Reactor Coolant Chemistry Conditions - Pre Job Brief - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A528010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | LSD Strategy Draft Report - Supplier prepare and issue Offer - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A568010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | LSD Strategy Draft Report - Review Offer, prepare and issue CI - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A581010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | LSD Strategy Draft Report - Supplier mobilisation time - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A629010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | LSD Strategy Draft Report - Pre Job Brief - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A255010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Structures and Equipment Integrity - Supplier prepare and issue Offer - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A316010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Structures and Equipment Integrity - Review Offer, prepare and issue CI - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A348010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Structures and Equipment Integrity - Supplier mobilisation time - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A401010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Structures and Equipment Integrity - Pre Job Brief - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A10840 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Prepare Programme 6.1 Station Documentation and Implementation Strategy - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A10850 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Programme 6.1 Station Documentation and Implementation Strategy Verified by TSA - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A10870 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Programme 6.1 Station Documentation and Implementation Strategy Technically Reviewed by EDF SQEP - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A10880 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | TSA Address Comments on TR'd Programme 6.1 Station Documentation and Implementation Strategy - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A10900 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Programme 6.1 Station Documentation and Implementation Strategy TR Completed and uploaded to CDMS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A10930 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Programme 6.1 Station Documentation and Implementation Strategy - Supplier prepare and issue Offer - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A10940 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Programme 6.1 Station Documentation and Implementation Strategy - Review Offer, prepare and issue CI - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A10950 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Programme 6.1 Station Documentation and Implementation Strategy - Supplier mobilisation time - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A10960 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Programme 6.1 Station Documentation and Implementation Strategy - Pre Job Brief - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A1193010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Review of / Changes to Emergency Arrangements Report Reviewed by EDF SQEP - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A1194010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Address Comments on Reviewed Review of / Changes to Emergency Arrangements Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A1196010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Review of / Changes to Emergency Arrangements Report Completed and uploaded to CDMS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A1198010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Develop Boundary Conditions Summary - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A1199010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Prepare Boundary ConditionsReport - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A1200010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Boundary Conditions Report Verified by TSA - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A1202010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Boundary Conditions Report Technically Reviewed by EDF SQEP - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A1203010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | TSA Address Comments on TR'd Boundary Conditions Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A1205010 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Boundary Conditions Report TR Completed and uploaded to CDMS - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A10835 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-03-31 | Programme 6.1 Station Documentation and Implementation Strategy Summary - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A912010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Verified Shutdown margin compliance summary Draft Report Issued to EDF for Technical Review. - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A953010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | TSA Issue Final Shutdown margin compliance summary Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A967010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Shutdown margin compliance summary Report Completed - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A775010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Verified LSD Strategy Draft Report Issued to EDF for Technical Review. - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A841010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | TSA Issue Final LSD Strategy Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A870010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | LSD Strategy Report Completed - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A915010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Verified Shutdown margin compliance summary Draft Report Issued to EDF for Technical Review. - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A954010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | TSA Issue Final Shutdown margin compliance summary Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A968010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Shutdown margin compliance summary Report Completed - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A889010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Verified Requirements for Severe AccidentsDraft Report Issued to EDF for Technical Review. - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A917010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | TSA Issue Final Requirements for Severe AccidentsReport - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A937010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Requirements for Severe AccidentsReport Completed - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A448010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Issue Reactor Coolant Chemistry Conditions Draft Report to EDF for Review. - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A503010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Issue Reactor Coolant Chemistry Conditions Final Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A530010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Reactor Coolant Chemistry Conditions Report Completed - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A623010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Verified Structures and Equipment Integrity Draft Report Issued to EDF for Technical Review. - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A717010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | TSA Issue Final Structures and Equipment Integrity Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A767010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Structures and Equipment Integrity Report Completed - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1086010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Verified Programme 6.1 Station Documentation and Implementation Strategy Issued to EDF for TR. - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1089010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | TSA Issue Final Programme 6.1 Station Documentation and Implementation Strategy - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1091010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Programme 6.1 Station Documentation and Implementation Strategy Completed - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1192010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Issue Review of / Changes to Emergency Arrangements Report to EDF Review. - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1195010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Issue Final Review of / Changes to Emergency Arrangements Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1197010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Review of / Changes to Emergency Arrangements Report Completed - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1201010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Verified Boundary Conditions Report Issued to EDF for Technical Review. - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1204010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | TSA Issue Final Boundary Conditions Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1206010 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Boundary Conditions Report Completed - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A912010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Verified Shutdown margin compliance summary Draft Report Issued to EDF for Technical Review. - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A953010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | TSA Issue Final Shutdown margin compliance summary Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A967010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Shutdown margin compliance summary Report Completed - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A775010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Verified LSD Strategy Draft Report Issued to EDF for Technical Review. - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A841010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | TSA Issue Final LSD Strategy Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A870010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | LSD Strategy Report Completed - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A915010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Verified Shutdown margin compliance summary Draft Report Issued to EDF for Technical Review. - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A954010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | TSA Issue Final Shutdown margin compliance summary Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A968010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Shutdown margin compliance summary Report Completed - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A889010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Verified Requirements for Severe AccidentsDraft Report Issued to EDF for Technical Review. - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A917010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | TSA Issue Final Requirements for Severe AccidentsReport - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A937010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Requirements for Severe AccidentsReport Completed - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A448010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Issue Reactor Coolant Chemistry Conditions Draft Report to EDF for Review. - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A503010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Issue Reactor Coolant Chemistry Conditions Final Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A530010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Reactor Coolant Chemistry Conditions Report Completed - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A623010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Verified Structures and Equipment Integrity Draft Report Issued to EDF for Technical Review. - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A717010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | TSA Issue Final Structures and Equipment Integrity Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A767010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Structures and Equipment Integrity Report Completed - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A10860 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Verified Programme 6.1 Station Documentation and Implementation Strategy Issued to EDF for TR. - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A10890 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | TSA Issue Final Programme 6.1 Station Documentation and Implementation Strategy - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A10910 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Programme 6.1 Station Documentation and Implementation Strategy Completed - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1192010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Issue Review of / Changes to Emergency Arrangements Report to EDF Review. - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1195010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Issue Final Review of / Changes to Emergency Arrangements Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1197010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Review of / Changes to Emergency Arrangements Report Completed - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1201010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Verified Boundary Conditions Report Issued to EDF for Technical Review. - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1204010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | TSA Issue Final Boundary Conditions Report - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1206010 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | Boundary Conditions Report Completed - (Scope Removed) | 31-Mar-20 A | 31-Mar-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1170 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-16 | 2020-04-03 | <NEW SCOPE> - Pressure Vessel Integrity Report - Prepare Report | 01-Apr-20 A | 08-May-20 A | 25 | 0 | 25 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1165 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-16 | 2020-05-01 | <NEW SCOPE> - Pressure Vessel Integrity Report - Summary | 01-Apr-20 A | 10-Jun-20 A | 69 | 0 | 46 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11240 | HNB Reactors Shutdown Essential Safety Cases | 2020-04-01 | 2021-03-31 | Phase 2 Programme Management | 01-Apr-20 A | 31-Mar-21 A | 233 | 0 | 252 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17380 | HNB Reactors Shutdown Essential Safety Cases | 2020-04-01 |  | Programme Management - Start MS | 01-Apr-20 A | 01-Apr-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A23260 | HRA Fuel Handling Essential Safety Case | 2020-04-01 | 2020-04-08 | Verify Update Core Support Plate Properties Tensile and Issue for Technical Review | 01-Apr-20 A | 08-Apr-20 A | 6 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A23260 | HYA Fuel Handling Essential Safety Case | 2020-04-01 | 2020-04-08 | Verify Update Core Support Plate Properties Tensile and Issue for Technical Review | 01-Apr-20 A | 08-Apr-20 A | 6 | 0 | 5 | 100% |  | Completed
ER6372LT | W203 | W203.A1060 | HNB Enhanced Defuelling Safety Cases | 2020-04-01 |  | Phase 2 Project Start [FEEDS TO SUMMARY SCHEDULE] | 01-Apr-20 A | 01-Apr-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A1020 | HNB Enhanced Defuelling Safety Cases | 2020-04-01 | 2020-11-11 | (HNB) Gate A planning | 01-Apr-20 A | 11-Nov-20 A | 156 | 0 | 156 | 100% |  | Completed
ER6372LT | W203 | W203.A1070 | HNB Enhanced Defuelling Safety Cases | 2020-04-01 | 2021-03-10 | Project Management Gate A - B | 01-Apr-20 A | 22-Sep-21 A | 459 | 0 | 373 | 100% |  | Completed
ER6372LT | W203 | W203.A1010 | HNB Enhanced Defuelling Safety Cases | 2020-04-01 | 2021-07-08 | Summary for HNB Reactors Shutdown Enhanced Safety Cases W203 | 01-Apr-20 A | 2025-04-08 | 320 | 27 | 1268 | 94.24% | 3 | In Progress
ER6372LT | W203 | W203.A1080 | HNB Enhanced Defuelling Safety Cases | 2020-04-01 | 2021-03-10 | Technical Oversight Gate A - B | 01-Apr-20 A | 22-Sep-21 A | 459 | 0 | 373 | 100% |  | Completed
ER6372LT | W203 | W203.A1090 | HNB Enhanced Defuelling Safety Cases | 2020-04-01 | 2021-03-10 | Station Oversight Gate A - B | 01-Apr-20 A | 22-Sep-21 A | 459 | 0 | 373 | 100% |  | Completed
ER6372LT | W203 | W203.A2455 | HNB Enhanced Defuelling Safety Cases | 2020-04-01 | 2020-08-14 | Scoping Report - Prepare Draft Report | 01-Apr-20 A | 14-Aug-20 A | 94 | 0 | 94 | 100% |  | Completed
ER6372LT | W203 | W203.A2540 | HNB Enhanced Defuelling Safety Cases | 2020-04-01 | 2020-04-30 | Confirm Objectives to be Delivered at Gate A | 01-Apr-20 A | 30-Apr-20 A | 20 | 0 | 20 | 100% |  | Completed
ER6370LT | W201 | ER6370.A5410 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-03 | 2020-03-09 | HF Compliance Assessment for Shutdown Margin Draft EAN Verified by TSA | 02-Apr-20 A | 08-Apr-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A5490 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-03 | 2020-03-09 | HF Compliance / Tech Spec As'ment for Core Cooling Draft EAN Verified by TSA | 02-Apr-20 A | 08-Apr-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6244LT | W220 | A11090 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  | 2019-06-28 | Develop HRA HYA Detailed Costing and Schedules for Future Phases (Post Gate B) | 03-Apr-20 A | 03-Apr-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7040 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-11 | 2020-03-24 | TSA Address Comments on TR'd Boiler Supporting Systems Draft EAN | 06-Apr-20 A | 21-Apr-20 A | 10 | 0 | 9 | 100% |  | Completed
ER6371LT | W202 | W202.A1780 | HRA Reactors Shutdown Essential Safety Cases | 2020-04-06 | 2020-04-14 | Seismic Assessment of FPU within Reactor - Draft and issue RFS | 06-Apr-20 A | 13-Apr-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6371LT | W202 | W202.A1770 | HRA Reactors Shutdown Essential Safety Cases | 2020-04-06 | 2020-05-21 | RFS - Seismic Assessment of FPU within Reactor Summary | 06-Apr-20 A | 10-Jun-20 A | 25 | 0 | 44 | 100% |  | Completed
ER6661LT | W206 | W206.A1780 | HYA Reactors Shutdown Essential Safety Cases | 2020-04-06 | 2020-04-14 | Seismic Assessment of FPU within Reactor - Draft and issue RFS | 06-Apr-20 A | 13-Apr-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6661LT | W206 | W206.A1770 | HYA Reactors Shutdown Essential Safety Cases | 2020-04-06 | 2020-05-21 | RFS - Seismic Assessment of FPU within Reactor Summary | 06-Apr-20 A | 10-Jun-20 A | 31 | 0 | 43 | 100% |  | Completed
ER6370LT | W201 | ER6370.A5420 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-09 | Verified HF Compliance Assessment for Shutdown Margin Draft EAN Issued to EDF for Technical Review. | 08-Apr-20 A | 08-Apr-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A5500 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-09 | Verified HF Compliance / Tech Spec As'ment for Core Cooling Draft EAN Issued to EDF for Technical Review. | 08-Apr-20 A | 08-Apr-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2660 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-31 | 2020-04-06 | Shutdown margin compliance summary Report TR Completed and uploaded to CDMS | 09-Apr-20 A | 26-Jun-20 A | 5 | 0 | 52 | 100% |  | Completed
ER6370LT | W201 | ER6370.A5430 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-10 | 2020-03-16 | HF Compliance Assessment for Shutdown Margin Draft EAN Technically Reviewed by EDF SQEP | 09-Apr-20 A | 17-Apr-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A5510 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-10 | 2020-03-16 | HF Compliance / Tech Spec As'ment for Core Cooling Draft EAN Technically Reviewed by EDF SQEP | 09-Apr-20 A | 17-Apr-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A23270 | HRA Fuel Handling Essential Safety Case | 2020-04-09 | 2020-04-16 | Technical Review of Update Core Support Plate Properties Tensile EAN | 09-Apr-20 A | 16-Apr-20 A | 4 | 0 | 3 | 100% |  | Completed
ER6650LT | W226 | W226.A23270 | HYA Fuel Handling Essential Safety Case | 2020-04-09 | 2020-04-16 | Technical Review of Update Core Support Plate Properties Tensile EAN | 09-Apr-20 A | 16-Apr-20 A | 4 | 0 | 3 | 100% |  | Completed
ER6371LT | W202 | W202.A1720 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-30 | 2020-04-03 | Dropped FPU Strategy Development HRA - Review Offer, prepare and issue CI | 10-Apr-20 A | 20-Apr-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6661LT | W206 | W206.A1720 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-30 | 2020-04-03 | Dropped FPU Strategy Development HYA - Review Offer, prepare and issue CI | 10-Apr-20 A | 20-Apr-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A1800 | HRA Reactors Shutdown Essential Safety Cases | 2020-04-06 | 2020-04-21 | Review of HRA Defuelling Case against the NSPs Internally Verified by TSA | 14-Apr-20 A | 27-Apr-20 A | 10 | 0 | 9 | 100% |  | Completed
ER6371LT | W202 | W202.A1820 | HRA Reactors Shutdown Essential Safety Cases | 2020-04-15 | 2020-04-28 | Seismic Assessment of FPU within Reactor - Supplier prepare and issue Offer | 14-Apr-20 A | 28-Apr-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.A1800 | HYA Reactors Shutdown Essential Safety Cases | 2020-04-06 | 2020-04-21 | Review of HYA Defuelling Case against the NSPs Internally Verified by TSA | 14-Apr-20 A | 27-Apr-20 A | 10 | 0 | 9 | 100% |  | Completed
ER6661LT | W206 | W206.A1820 | HYA Reactors Shutdown Essential Safety Cases | 2020-04-15 | 2020-04-28 | Seismic Assessment of FPU within Reactor - Supplier prepare and issue Offer | 14-Apr-20 A | 28-Apr-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6243LT | W200 | ER6243.A1580 | REGION 1 Reactors Shutdown Safety Cases Programme |  |  | Gate D IRM - 6.1 W200 Reactors Shutdown Safety Cases Programme [FEEDS TO SUMMARY SCHEDULE] | 15-Apr-20 A | 15-Apr-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4160 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-30 | 2020-04-03 | TSA Address Comments on TR'd Shutdown Cooling Analysis Draft Report | 15-Apr-20 A | 21-Apr-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A26020 | HRA Fuel Handling Essential Safety Case | 2020-04-15 | 2020-12-01 | Confirm Acceptability of CSP Pillars ##(Cost Summary)## (C5) (NEW) | 15-Apr-20 A | 01-Dec-20 A | 162 | 0 | 162 | 100% |  | Completed
ER6378LT | W222 | W222.A24380 | HRA Fuel Handling Essential Safety Case | 2020-04-15 | 2020-04-29 | Verify Fuel Route Operational Sequence/Process for Defuelling EAN and Issue for Technical Review (REV 000) | 15-Apr-20 A | 29-Apr-20 A | 11 | 0 | 10 | 100% |  | Completed
ER6378LT | W222 | W222.A23660 | HRA Fuel Handling Essential Safety Case | 2020-04-15 | 2020-04-15 | Pre Job Brief for Confirm Acceptability of CSP Pillars EAN | 15-Apr-20 A | 15-Apr-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A23660 | HYA Fuel Handling Essential Safety Case | 2020-04-15 | 2020-04-15 | Pre Job Brief for Confirm Acceptability of CSP Pillars EAN | 15-Apr-20 A | 15-Apr-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A24380 | HYA Fuel Handling Essential Safety Case | 2020-04-15 | 2020-04-29 | Verify Fuel Route Operational Sequence/Process for Defuelling EAN and Issue for Technical Review (REV 000) | 15-Apr-20 A | 29-Apr-20 A | 11 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | W226.A26020 | HYA Fuel Handling Essential Safety Case | 2020-04-15 | 2020-12-01 | Confirm Acceptability of CSP Pillars ##(Cost Summary)## (C5) (NEW) | 15-Apr-20 A | 01-Dec-20 A | 162 | 0 | 162 | 100% |  | Completed
ER6243LT | W200 | RSSC.PM.A170 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2024-10-02 | Project Closeout | 15-Apr-20 A | 15-Apr-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6243LT | W200 | A3010 | REGION 1 Reactors Shutdown Safety Cases Programme |  | 2024-12-31 | Project Finish Date | 15-Apr-20 A | 15-Apr-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6244LT | W220 | A13080 | REGION 1 Defuelling Programme Fuel Handling Safety Case |  |  | Gate D For HPB HNB Station Fuel Handling Safety Case Programme [FEEDS TO SUMMARY SCHEDULE] | 15-Apr-20 A | 15-Apr-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A23670 | HRA Fuel Handling Essential Safety Case | 2020-04-16 | 2020-05-14 | Draft Confirm Acceptability of CSP Pillars EAN | 16-Apr-20 A | 14-May-20 A | 20 | 0 | 19 | 100% |  | Completed
ER6378LT | W222 | W222.A23190 | HRA Fuel Handling Essential Safety Case | 2020-04-16 | 2020-05-07 | Verify Basis of Analysis Report EAN and Issue for Technical Review (REV 000) | 16-Apr-20 A | 07-May-20 A | 16 | 0 | 15 | 100% |  | Completed
ER6650LT | W226 | W226.A23190 | HYA Fuel Handling Essential Safety Case | 2020-04-16 | 2020-05-07 | Verify Basis of Analysis Report EAN and Issue for Technical Review (REV 000) | 16-Apr-20 A | 07-May-20 A | 16 | 0 | 15 | 100% |  | Completed
ER6650LT | W226 | W226.A23670 | HYA Fuel Handling Essential Safety Case | 2020-04-16 | 2020-05-14 | Draft Confirm Acceptability of CSP Pillars EAN | 16-Apr-20 A | 14-May-20 A | 20 | 0 | 19 | 100% |  | Completed
ER6378LT | W222 | W222.A23280 | HRA Fuel Handling Essential Safety Case | 2020-04-17 | 2020-04-24 | Supplier Update and Issue Update Core Support Plate Properties Tensile EAN | 17-Apr-20 A | 24-Apr-20 A | 6 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A23280 | HYA Fuel Handling Essential Safety Case | 2020-04-17 | 2020-04-24 | Supplier Update and Issue Update Core Support Plate Properties Tensile EAN | 17-Apr-20 A | 24-Apr-20 A | 6 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A5440 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-17 | 2020-03-23 | TSA Address Comments on TR'd HF Compliance Assessment for Shutdown Margin Draft EAN | 20-Apr-20 A | 24-Apr-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A5520 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-17 | 2020-03-23 | TSA Address Comments on TR'd HF Compliance / Tech Spec As'ment for Core Cooling Draft EAN | 20-Apr-20 A | 24-Apr-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4170 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-04-03 | TSA Issue Final Shutdown Cooling Analysis Report | 21-Apr-20 A | 21-Apr-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7050 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-24 | TSA Issue Final Boiler Supporting Systems EAN | 21-Apr-20 A | 21-Apr-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2960 | HRA Reactors Shutdown Essential Safety Cases | 2020-08-17 | 2020-09-14 | Prepare Worker Dose Report | 21-Apr-20 A | 29-Jun-20 A | 48 | 0 | 47 | 100% |  | Completed
ER6371LT | W202 | W202.A2950 | HRA Reactors Shutdown Essential Safety Cases | 2020-08-17 | 2020-10-19 | Worker Dose Report Summary | 21-Apr-20 A | 20-Oct-20 A | 130 | 0 | 127 | 100% |  | Completed
ER6371LT | W202 | W202.A1790 | HRA Reactors Shutdown Essential Safety Cases | 2020-04-06 | 2020-04-21 | Dropped FPU Strategy Development HRA - Supplier mobilisation time | 21-Apr-20 A | 15-May-20 A | 10 | 0 | 17 | 100% |  | Completed
ER6661LT | W206 | W206.A2960 | HYA Reactors Shutdown Essential Safety Cases | 2020-08-17 | 2020-09-14 | Prepare Worker Dose Report | 21-Apr-20 A | 29-Jun-20 A | 48 | 0 | 47 | 100% |  | Completed
ER6661LT | W206 | W206.A2950 | HYA Reactors Shutdown Essential Safety Cases | 2020-08-17 | 2021-02-18 | Worker Dose Report Summary | 21-Apr-20 A | 26-Oct-20 A | 130 | 0 | 131 | 100% |  | Completed
ER6661LT | W206 | W206.A1790 | HYA Reactors Shutdown Essential Safety Cases | 2020-04-06 | 2020-04-21 | Dropped FPU Strategy Development HYA - Supplier mobilisation time | 21-Apr-20 A | 15-May-20 A | 10 | 0 | 18 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4180 | HNB Reactors Shutdown Essential Safety Cases | 2020-04-06 | 2020-04-14 | Shutdown Cooling Analysis Report TR Completed and uploaded to CDMS | 22-Apr-20 A | 28-Apr-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7060 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-25 | 2020-04-07 | Boiler Supporting Systems EAN TR Completed and uploaded to CDMS | 22-Apr-20 A | 24-Apr-20 A | 3 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | W222.A25910 | HRA Fuel Handling Essential Safety Case | 2020-04-23 | 2020-11-18 | Interpretation of MACE for Fuel Route ##(Cost Summary)## (NEW) (C4) | 23-Apr-20 A | 18-Nov-20 A | 140 | 0 | 146 | 100% |  | Completed
ER6378LT | W222 | W222.A22960 | HRA Fuel Handling Essential Safety Case | 2020-04-23 | 2020-04-23 | Pre Job Brief for Interpretation of MACE for Fuel Route EAN | 23-Apr-20 A | 23-Apr-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A22960 | HYA Fuel Handling Essential Safety Case | 2020-04-23 | 2020-04-23 | Pre Job Brief for Interpretation of MACE for Fuel Route EAN | 23-Apr-20 A | 23-Apr-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25910 | HYA Fuel Handling Essential Safety Case | 2020-04-23 | 2020-11-18 | Interpretation of MACE for Fuel Route ##(Cost Summary)## (NEW) (C4) | 23-Apr-20 A | 18-Nov-20 A | 139 | 0 | 146 | 100% |  | Completed
ER6370LT | W201 | ER6370.A5450 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-23 | TSA Issue Final HF Compliance Assessment for Shutdown Margin EAN | 24-Apr-20 A | 24-Apr-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A5530 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-23 | TSA Issue Final HF Compliance / Tech Spec As'ment for Core Cooling EAN | 24-Apr-20 A | 24-Apr-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7070 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-04-07 | Boiler Supporting Systems EAN Completed | 24-Apr-20 A | 24-Apr-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7090 | HNB Reactors Shutdown Essential Safety Cases |  |  | Boilers and Gas Circulator Performance - Reworked Draft EAN Complete Available for Verification | 24-Apr-20 A | 24-Apr-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A25930 | HRA Fuel Handling Essential Safety Case | 2020-04-24 | 2020-12-10 | Damage and Thermal Analysis Dropped Fuel ##(Cost Summary)## (C5) (NEW) | 24-Apr-20 A | 10-Dec-20 A | 172 | 0 | 162 | 100% |  | Completed
ER6378LT | W222 | W222.A25820 | HRA Fuel Handling Essential Safety Case | 2020-04-24 | 2020-10-09 | Hazop Study of Defuelling Process (REV 000) ##(Cost Summary)## (C2) (NEW) | 24-Apr-20 A | 09-Oct-20 A | 122 | 0 | 117 | 100% |  | Completed
ER6378LT | W222 | W222.A25720 | HRA Fuel Handling Essential Safety Case | 2020-04-24 | 2021-07-22 | Update to Fault Schedule/PSA ##(Cost Summary)## ### (C6) | 24-Apr-20 A | 22-Jul-21 A | 315 | 0 | 315 | 100% |  | Completed
ER6378LT | W222 | W222.A24150 | HRA Fuel Handling Essential Safety Case | 2020-04-24 | 2020-04-24 | Pre Job Brief for Hazop Study of Defuelling Process EAN (REV 000) | 24-Apr-20 A | 24-Apr-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A22970 | HRA Fuel Handling Essential Safety Case | 2020-04-24 | 2020-06-05 | Draft Interpretation of MACE for Fuel Route EAN | 24-Apr-20 A | 05-Jun-20 A | 29 | 0 | 28 | 100% |  | Completed
ER6378LT | W222 | W222.A22900 | HRA Fuel Handling Essential Safety Case | 2020-04-24 | 2020-04-24 | Pre Job Brief for Damage and Thermal Analysis Dropped Fuel EAN | 24-Apr-20 A | 24-Apr-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A22900 | HYA Fuel Handling Essential Safety Case | 2020-04-24 | 2020-04-24 | Pre Job Brief for Damage and Thermal Analysis Dropped Fuel EAN | 24-Apr-20 A | 24-Apr-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A22970 | HYA Fuel Handling Essential Safety Case | 2020-04-24 | 2020-06-05 | Draft Interpretation of MACE for Fuel Route EAN | 24-Apr-20 A | 05-Jun-20 A | 29 | 0 | 28 | 100% |  | Completed
ER6650LT | W226 | W226.A24150 | HYA Fuel Handling Essential Safety Case | 2020-04-24 | 2020-04-24 | Pre Job Brief for Hazop Study of Defuelling Process EAN (REV 000) | 24-Apr-20 A | 24-Apr-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25720 | HYA Fuel Handling Essential Safety Case | 2020-04-24 | 2021-07-22 | Update to Fault Schedule/PSA ##(Cost Summary)## ### (C6) | 24-Apr-20 A | 22-Jul-21 A | 305 | 0 | 314 | 100% |  | Completed
ER6650LT | W226 | W226.A25820 | HYA Fuel Handling Essential Safety Case | 2020-04-24 | 2020-10-09 | Hazop Study of Defuelling Process (REV 000) ##(Cost Summary)## (C2) (NEW) | 24-Apr-20 A | 09-Oct-20 A | 122 | 0 | 117 | 100% |  | Completed
ER6650LT | W226 | W226.A25930 | HYA Fuel Handling Essential Safety Case | 2020-04-24 | 2020-12-10 | Damage and Thermal Analysis Dropped Fuel ##(Cost Summary)## (C5) (NEW) | 24-Apr-20 A | 10-Dec-20 A | 172 | 0 | 162 | 100% |  | Completed
ER6370LT | W201 | ER6370.A5460 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-24 | 2020-03-30 | HF Compliance Assessment for Shutdown Margin EAN TR Completed and uploaded to CDMS | 27-Apr-20 A | 30-Apr-20 A | 4 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | ER6370.A5540 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-24 | 2020-03-30 | HF Compliance / Tech Spec As'ment for Core Cooling EAN TR Completed and uploaded to CDMS | 27-Apr-20 A | 30-Apr-20 A | 4 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7100 | HNB Reactors Shutdown Essential Safety Cases |  |  | Boilers and Gas Circulator Performance - EDF Internal Verification of Reworked Draft EAN | 27-Apr-20 A | 17-Jul-20 A | 5 | 0 | 58 | 100% |  | Completed
ER6371LT | W202 | W202.A1870 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-04-21 | Review of HRA Defuelling Case against the NSPs Draft Report Issued to EDF for Verification | 27-Apr-20 A | 27-Apr-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1870 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-04-21 | Review of HYA Defuelling Case against the NSPs Draft Report Issued to EDF for Verification | 27-Apr-20 A | 27-Apr-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A24160 | HRA Fuel Handling Essential Safety Case | 2020-04-27 | 2020-06-19 | Draft Review of Hazop Study of Defuelling Process (REV 000) | 27-Apr-20 A | 19-Jun-20 A | 38 | 0 | 37 | 100% |  | Completed
ER6378LT | W222 | W222.A23290 | HRA Fuel Handling Essential Safety Case | 2020-04-27 | 2020-05-01 | Complete TR Form and Upload Update Core Support Plate Properties Tensile EAN to CDMS | 27-Apr-20 A | 01-May-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6378LT | W222 | W222.A22890 | HRA Fuel Handling Essential Safety Case | 2020-04-27 | 2020-05-25 | Draft Damage and Thermal Analysis Dropped Fuel EAN | 27-Apr-20 A | 25-May-20 A | 19 | 0 | 19 | 100% |  | Completed
ER6650LT | W226 | W226.A22890 | HYA Fuel Handling Essential Safety Case | 2020-04-27 | 2020-05-25 | Draft Damage and Thermal Analysis Dropped Fuel EAN | 27-Apr-20 A | 25-May-20 A | 19 | 0 | 19 | 100% |  | Completed
ER6650LT | W226 | W226.A23290 | HYA Fuel Handling Essential Safety Case | 2020-04-27 | 2020-05-01 | Complete TR Form and Upload Update Core Support Plate Properties Tensile EAN to CDMS | 27-Apr-20 A | 01-May-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6650LT | W226 | W226.A24160 | HYA Fuel Handling Essential Safety Case | 2020-04-27 | 2020-06-19 | Draft Review of Hazop Study of Defuelling Process (REV 000) | 27-Apr-20 A | 19-Jun-20 A | 38 | 0 | 37 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4190 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-04-14 | Shutdown Cooling Analysis Report Completed | 28-Apr-20 A | 28-Apr-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16320 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-04-14 | All Supporting Technical References Complete - Claim 3 Cooling | 28-Apr-20 A | 28-Apr-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17370 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-04-14 | >>>OUTGOING ENABLER (W221) Shutdown Cooling Analysis Report Completed | 28-Apr-20 A | 28-Apr-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A5470 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-30 | HF Compliance Assessment for Shutdown Margin EAN Completed | 30-Apr-20 A | 30-Apr-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A5550 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-30 | HF Compliance / Tech Spec As'ment for Core Cooling EAN Completed | 30-Apr-20 A | 30-Apr-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A24390 | HRA Fuel Handling Essential Safety Case | 2020-04-30 | 2020-05-14 | Technical Review of Fuel Route Operational Sequence/Process for Defuelling EAN (REV 000) | 30-Apr-20 A | 14-May-20 A | 10 | 0 | 9 | 100% |  | Completed
ER6650LT | W226 | W226.A24390 | HYA Fuel Handling Essential Safety Case | 2020-04-30 | 2020-05-14 | Technical Review of Fuel Route Operational Sequence/Process for Defuelling EAN (REV 000) | 30-Apr-20 A | 14-May-20 A | 10 | 0 | 9 | 100% |  | Completed
ER6371LT | W202 | W202.A1890 | HRA Reactors Shutdown Essential Safety Cases | 2020-04-22 | 2020-05-28 | Review of HRA Defuelling Case against the NSPs Draft Report Verified by EDF SQEP | 01-May-20 A | 31-Jul-20 A | 25 | 0 | 63 | 100% |  | Completed
ER6371LT | W202 | W202.A1970 | HRA Reactors Shutdown Essential Safety Cases | 2020-04-29 | 2020-05-05 | Seismic Assessment of FPU within Reactor - Review Offer, prepare and issue CI | 01-May-20 A | 07-May-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6371LT | W202 | W202.A1830 | HRA Reactors Shutdown Essential Safety Cases | 2020-04-16 | 2020-04-16 | Assumptions EAN - Issue Draft Report to EDF Energy for Verification | 01-May-20 A | 01-May-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1740 | HRA Reactors Shutdown Essential Safety Cases | 2020-04-01 | 2020-06-19 | Prepare Fault Schedule Review (Plant Base Faults and Hazards) Draft Report - (HRA) | 01-May-20 A | 13-Jul-20 A | 54 | 0 | 49 | 100% |  | Completed
ER6371LT | W202 | W202.A1730 | HRA Reactors Shutdown Essential Safety Cases | 2020-04-01 | 2020-08-14 | Fault Schedule Review (Plant Base Faults and Hazards) Summary - (HRA) | 01-May-20 A | 29-Sep-20 A | 105 | 0 | 105 | 100% |  | Completed
ER6661LT | W206 | W206.A1890 | HYA Reactors Shutdown Essential Safety Cases | 2020-04-22 | 2020-05-28 | Review of HYA Defuelling Case against the NSPs Draft Report Verified by EDF SQEP | 01-May-20 A | 31-Jul-20 A | 64 | 0 | 63 | 100% |  | Completed
ER6661LT | W206 | W206.A1970 | HYA Reactors Shutdown Essential Safety Cases | 2020-04-29 | 2020-05-05 | Seismic Assessment of FPU within Reactor - Review Offer, prepare and issue CI | 01-May-20 A | 07-May-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6661LT | W206 | W206.A1830 | HYA Reactors Shutdown Essential Safety Cases | 2020-04-16 | 2020-04-16 | Assumptions EAN - Issue Draft Report to EDF Energy for Verification | 01-May-20 A | 01-May-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1740 | HYA Reactors Shutdown Essential Safety Cases | 2020-04-01 | 2020-06-19 | Prepare Fault Schedule Review (Plant Base Faults and Hazards) Draft Report - (HYA) | 01-May-20 A | 12-Jun-20 A | 54 | 0 | 28 | 100% |  | Completed
ER6661LT | W206 | W206.A1730 | HYA Reactors Shutdown Essential Safety Cases | 2020-04-01 | 2020-09-14 | Fault Schedule Review (Plant Base Faults and Hazards) Summary - (HYA) | 01-May-20 A | 14-Sep-20 A | 114 | 0 | 94 | 100% |  | Completed
ER6378LT | W222 | W222.A25770 | HRA Fuel Handling Essential Safety Case | 2020-05-01 | 2020-10-07 | HF Assessment of Fuel Free Verification ##(Cost Summary)## ### (C2) | 01-May-20 A | 07-Oct-20 A | 107 | 0 | 110 | 100% |  | Completed
ER6378LT | W222 | W222.A23300 | HRA Fuel Handling Essential Safety Case |  | 2020-05-01 | Update Core Support Plate Properties Tensile EAN Available | 01-May-20 A | 01-May-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A11460 | HRA Fuel Handling Essential Safety Case | 2020-05-01 | 2020-05-01 | Pre Job Brief for HF Assessment of Fuel Free Verification EAN (System) | 01-May-20 A | 01-May-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A11460 | HYA Fuel Handling Essential Safety Case | 2020-05-01 | 2020-05-01 | Pre Job Brief for HF Assessment of Fuel Free Verification EAN (System) | 01-May-20 A | 01-May-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A23300 | HYA Fuel Handling Essential Safety Case |  | 2020-05-01 | Update Core Support Plate Properties Tensile EAN Available | 01-May-20 A | 01-May-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25770 | HYA Fuel Handling Essential Safety Case | 2020-05-01 | 2020-10-07 | HF Assessment of Fuel Free Verification ##(Cost Summary)## ### (C2) | 01-May-20 A | 07-Oct-20 A | 107 | 0 | 110 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1690 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-02 | 2020-03-02 | Ensure Alignment of Schedule & Estimate | 01-May-20 A | 11-May-20 A | 1 | 0 | 5 | 100% |  | Completed
ER6372LT | W203 | W203.A2550 | HNB Enhanced Defuelling Safety Cases | 2020-05-01 | 2020-05-15 | Initial high level scope of programme | 01-May-20 A | 15-May-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | W202.A1840 | HRA Reactors Shutdown Essential Safety Cases | 2020-04-17 | 2020-04-27 | Assumptions EAN - Draft Report Verified by EDF Energy | 04-May-20 A | 13-May-20 A | 7 | 0 | 6 | 100% |  | Completed
ER6661LT | W206 | W206.A1840 | HYA Reactors Shutdown Essential Safety Cases | 2020-04-17 | 2020-04-27 | Assumptions EAN - Draft Report Verified by EDF Energy | 04-May-20 A | 13-May-20 A | 7 | 0 | 6 | 100% |  | Completed
ER6378LT | W222 | W222.A17660 | HRA Fuel Handling Essential Safety Case | 2020-05-04 | 2020-06-01 | Draft HF Assessment of Fuel Free Verification EAN (System) | 04-May-20 A | 01-Jun-20 A | 19 | 0 | 18 | 100% |  | Completed
ER6650LT | W226 | W226.A17660 | HYA Fuel Handling Essential Safety Case | 2020-05-04 | 2020-06-01 | Draft HF Assessment of Fuel Free Verification EAN (System) | 04-May-20 A | 01-Jun-20 A | 19 | 0 | 18 | 100% |  | Completed
ER6378LT | W222 | W222.A25980 | HRA Fuel Handling Essential Safety Case | 2020-05-06 | 2021-02-26 | CSP Model and Static Analysis ##(Cost Summary)## (C5) (NEW) | 06-May-20 A | 26-Feb-21 A | 207 | 0 | 206 | 100% |  | Completed
ER6378LT | W222 | W222.A23380 | HRA Fuel Handling Essential Safety Case | 2020-05-06 | 2020-05-06 | Pre Job Brief for CSP Model and Static Analysis EAN | 06-May-20 A | 06-May-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A23380 | HYA Fuel Handling Essential Safety Case | 2020-05-06 | 2020-05-06 | Pre Job Brief for CSP Model and Static Analysis EAN | 06-May-20 A | 06-May-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25980 | HYA Fuel Handling Essential Safety Case | 2020-05-06 | 2021-02-26 | CSP Model and Static Analysis ##(Cost Summary)## (C5) (NEW) | 06-May-20 A | 26-Feb-21 A | 232 | 0 | 206 | 100% |  | Completed
ER6378LT | W222 | W222.A23390 | HRA Fuel Handling Essential Safety Case | 2020-05-07 | 2020-08-07 | Draft CSP Model and Static Analysis EAN | 07-May-20 A | 07-Aug-20 A | 65 | 0 | 64 | 100% |  | Completed
ER6650LT | W226 | W226.A23390 | HYA Fuel Handling Essential Safety Case | 2020-05-07 | 2020-08-07 | Draft CSP Model and Static Analysis EAN | 07-May-20 A | 07-Aug-20 A | 65 | 0 | 64 | 100% |  | Completed
ER6370LT | W201 | ER6370.A10940 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-11 | Uncertainty in SDM Calculations Report Completed | 08-May-20 A | 08-May-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16300 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-11 | All Supporting Technical References Complete - Claim 1 Shutdown Margins | 08-May-20 A | 08-May-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A23200 | HRA Fuel Handling Essential Safety Case | 2020-05-08 | 2020-05-22 | Technical Review of Basis of Analysis Report EAN (REV 000) | 08-May-20 A | 22-May-20 A | 10 | 0 | 9 | 100% |  | Completed
ER6650LT | W226 | W226.A23200 | HYA Fuel Handling Essential Safety Case | 2020-05-08 | 2020-05-22 | Technical Review of Basis of Analysis Report EAN (REV 000) | 08-May-20 A | 22-May-20 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1720 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-03 | 2020-03-04 | Update Schedule/Estimate from Risk Log & Add Provisions | 11-May-20 A | 13-May-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1100 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-23 | 2020-03-27 | <NEW SCOPE> - Definition of Faults for PCPV Integrity - Issue Report and upload to CDMS | 11-May-20 A | 15-May-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1180 | HNB Reactors Shutdown Essential Safety Cases | 2020-04-06 | 2020-04-28 | <NEW SCOPE> - Pressure Vessel Integrity Report - Verification and Address Comments of Report | 11-May-20 A | 05-Jun-20 A | 10 | 0 | 18 | 100% |  | Completed
ER6371LT | W202 | W202.A2030 | HRA Reactors Shutdown Essential Safety Cases | 2020-05-06 | 2020-05-20 | Seismic Assessment of FPU within Reactor - Supplier mobilisation time | 11-May-20 A | 04-Jun-20 A | 10 | 0 | 18 | 100% |  | Completed
ER6661LT | W206 | W206.A2030 | HYA Reactors Shutdown Essential Safety Cases | 2020-05-06 | 2020-05-20 | Seismic Assessment of FPU within Reactor - Supplier mobilisation time | 11-May-20 A | 04-Jun-20 A | 10 | 0 | 17 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1730 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-05 | 2020-03-06 | Add Data to IRM Paper | 14-May-20 A | 15-May-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A1960 | HRA Reactors Shutdown Essential Safety Cases | 2020-04-28 | 2020-04-29 | Assumptions EAN - TSA Address Verification Comments from EDF Energy | 14-May-20 A | 02-Jun-20 A | 2 | 0 | 13 | 100% |  | Completed
ER6661LT | W206 | W206.A1960 | HYA Reactors Shutdown Essential Safety Cases | 2020-04-28 | 2020-04-29 | Assumptions EAN - TSA Address Verification Comments from EDF Energy | 14-May-20 A | 02-Jun-20 A | 2 | 0 | 13 | 100% |  | Completed
ER6378LT | W222 | W222.A25830 | HRA Fuel Handling Essential Safety Case | 2020-05-15 | 2021-07-29 | Human Reliability Baseline Report ##(Cost Summary)## (C2) (NEW) | 15-May-20 A | 29-Jul-21 A | 306 | 0 | 306 | 100% |  | Completed
ER6378LT | W222 | W222.A24570 | HRA Fuel Handling Essential Safety Case | 2020-05-15 | 2020-05-15 | Pre Job Brief for Human Reliability Baseline Report EAN | 15-May-20 A | 15-May-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A24400 | HRA Fuel Handling Essential Safety Case | 2020-05-15 | 2020-05-22 | Supplier Update and Issue Fuel Route Operational Sequence/Process for Defuelling EAN (REV 000) | 15-May-20 A | 22-May-20 A | 6 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A23680 | HRA Fuel Handling Essential Safety Case | 2020-05-15 | 2020-09-16 | Verify Confirm Acceptability of CSP PillarsEAN and Issue for Technical Review | 15-May-20 A | 16-Sep-20 A | 87 | 0 | 87 | 100% |  | Completed
ER6650LT | W226 | W226.A23680 | HYA Fuel Handling Essential Safety Case | 2020-05-15 | 2020-09-16 | Verify Confirm Acceptability of CSP PillarsEAN and Issue for Technical Review | 15-May-20 A | 16-Sep-20 A | 87 | 0 | 87 | 100% |  | Completed
ER6650LT | W226 | W226.A24400 | HYA Fuel Handling Essential Safety Case | 2020-05-15 | 2020-05-22 | Supplier Update and Issue Fuel Route Operational Sequence/Process for Defuelling EAN (REV 000) | 15-May-20 A | 22-May-20 A | 6 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A24570 | HYA Fuel Handling Essential Safety Case | 2020-05-15 | 2020-05-15 | Pre Job Brief for Human Reliability Baseline Report EAN | 15-May-20 A | 15-May-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25830 | HYA Fuel Handling Essential Safety Case | 2020-05-15 | 2021-07-29 | Human Reliability Baseline Report ##(Cost Summary)## (C2) (NEW) | 15-May-20 A | 29-Jul-21 A | 306 | 0 | 306 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1740 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-09 | 2020-03-11 | PCL Validate & Approve Baseline Package for PRC Submission | 18-May-20 A | 22-May-20 A | 3 | 0 | 4 | 100% |  | Completed
ER6378LT | W222 | W222.A24580 | HRA Fuel Handling Essential Safety Case | 2020-05-18 | 2020-12-09 | Draft Review of Human Reliability Baseline Report EAN | 18-May-20 A | 09-Dec-20 A | 83 | 0 | 145 | 100% |  | Completed
ER6378LT | W222 | W222.A24410 | HRA Fuel Handling Essential Safety Case | 2020-05-18 | 2020-07-20 | Complete TR Form and Fuel Route Operational Sequence/Process for Defuelling EAN to CDMS (PROCESS DOCUMENT) (REV 000) | 18-May-20 A | 20-Jul-20 A | 45 | 0 | 44 | 100% |  | Completed
ER6650LT | W226 | W226.A24410 | HYA Fuel Handling Essential Safety Case | 2020-05-18 | 2020-07-20 | Complete TR Form and Fuel Route Operational Sequence/Process for Defuelling EAN to CDMS (PROCESS DOCUMENT) (REV 000) | 18-May-20 A | 20-Jul-20 A | 45 | 0 | 44 | 100% |  | Completed
ER6650LT | W226 | W226.A24580 | HYA Fuel Handling Essential Safety Case | 2020-05-18 | 2020-12-09 | Draft Review of Human Reliability Baseline Report EAN | 18-May-20 A | 09-Dec-20 A | 83 | 0 | 145 | 100% |  | Completed
ER6372LT | W203 | W203.A2560 | HNB Enhanced Defuelling Safety Cases | 2020-05-18 | 2020-05-22 | Define Project Control Structures (WBS/CBS/OBS/PBS) | 18-May-20 A | 22-May-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6372LT | W203 | W203.A2570 | HNB Enhanced Defuelling Safety Cases | 2020-05-18 | 2020-07-13 | Prepare Draft Project Definition Document (PDD) | 18-May-20 A | 13-Jul-20 A | 40 | 0 | 40 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1050 | HNB Reactors Shutdown Essential Safety Cases | 2020-04-06 | 2020-04-14 | <NEW SCOPE> - ALARP Report - Issue Report | 21-May-20 A | 28-May-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1040 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-05-14 | <NEW SCOPE> - ALARP Report - Presented to DSCOG | 22-May-20 A | 22-May-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1150 | HNB Reactors Shutdown Essential Safety Cases | 2020-04-14 | 2020-04-27 | <NEW SCOPE> - Civils Integrity Report - Verification and Address Comments of Report | 25-May-20 A | 29-May-20 A | 5 | 0 | 3 | 100% |  | Completed
ER6378LT | W222 | W222.A23210 | HRA Fuel Handling Essential Safety Case | 2020-05-25 | 2020-06-01 | Supplier Update and Issue Basis of Analysis Report EAN (REV 000) | 25-May-20 A | 01-Jun-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6650LT | W226 | W226.A23210 | HYA Fuel Handling Essential Safety Case | 2020-05-25 | 2020-06-01 | Supplier Update and Issue Basis of Analysis Report EAN (REV 000) | 25-May-20 A | 01-Jun-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6371LT | W202 | W202.A1760 | HRA Reactors Shutdown Essential Safety Cases | 2020-04-02 | 2020-04-08 | Thermal Analysis (FEAT) of FPU Fully Extended - Draft and issue RFS | 26-May-20 A | 05-Jun-20 A | 9 | 0 | 9 | 100% |  | Completed
ER6371LT | W202 | W202.A1750 | HRA Reactors Shutdown Essential Safety Cases | 2020-04-02 | 2020-05-19 | RFS - Thermal Analysis (FEAT) of FPU Fully Extended Summary | 26-May-20 A | 06-Jul-20 A | 37 | 0 | 29 | 100% |  | Completed
ER6378LT | W222 | W222.A22910 | HRA Fuel Handling Essential Safety Case | 2020-05-26 | 2020-06-23 | Verify Damage and Thermal Analysis Dropped Fuel EAN and Issue for Technical Review | 26-May-20 A | 23-Jun-20 A | 21 | 0 | 20 | 100% |  | Completed
ER6650LT | W226 | W226.A22910 | HYA Fuel Handling Essential Safety Case | 2020-05-26 | 2020-06-23 | Verify Damage and Thermal Analysis Dropped Fuel EAN and Issue for Technical Review | 26-May-20 A | 23-Jun-20 A | 21 | 0 | 20 | 100% |  | Completed
ER6378LT | W222 | W222.A9920 | HRA Fuel Handling Essential Safety Case | 2020-05-27 | 2020-06-17 | Verify Update to Failed Fuel EAN and Issue for Technical Review | 27-May-20 A | 17-Jun-20 A | 16 | 0 | 15 | 100% |  | Completed
ER6650LT | W226 | W226.A9920 | HYA Fuel Handling Essential Safety Case | 2020-05-27 | 2020-06-17 | Verify Update to Failed Fuel EAN and Issue for Technical Review | 27-May-20 A | 17-Jun-20 A | 16 | 0 | 15 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1160 | HNB Reactors Shutdown Essential Safety Cases | 2020-04-28 | 2020-04-30 | <NEW SCOPE> - Civils Integrity Report - Issue Report and upload to CDMS | 01-Jun-20 A | 12-Jun-20 A | 3 | 0 | 9 | 100% |  | Completed
ER6378LT | W222 | W222.A25870 | HRA Fuel Handling Essential Safety Case | 2020-06-01 | 2020-06-01 | Human Factors Risk Assessment for Defuelling ##(Cost Summary)## (C2) (NEW) | 01-Jun-20 A | 01-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A25800 | HRA Fuel Handling Essential Safety Case | 2020-06-01 | 2020-09-01 | Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN ##(Cost Summary)## (C2) (NEW) | 01-Jun-20 A | 01-Sep-20 A | 66 | 0 | 66 | 100% |  | Completed
ER6378LT | W222 | W222.A25760 | HRA Fuel Handling Essential Safety Case | 2020-06-01 | 2021-07-29 | Human Factors Integration Plan ##(Cost Summary)## ### (C2) | 01-Jun-20 A | 29-Jul-21 A | 274 | 0 | 296 | 100% |  | Completed
ER6378LT | W222 | W222.A24850 | HRA Fuel Handling Essential Safety Case | 2020-06-01 | 2020-06-01 | Confirm R1 Document is Appropriate (Human Factors Risk Assessment for Defuelling EAN) | 01-Jun-20 A | 01-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A24900 | HRA Fuel Handling Essential Safety Case | 2020-06-01 | 2020-06-01 | Complete Review of Human Factors Risk Assessment for Defuelling EAN to CDMS | 01-Jun-20 A | 01-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A24910 | HRA Fuel Handling Essential Safety Case |  | 2020-06-01 | Human Factors Risk Assessment for Defuelling EAN Available | 01-Jun-20 A | 01-Jun-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A24430 | HRA Fuel Handling Essential Safety Case | 2020-06-01 | 2020-06-01 | Pre Job Brief for Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN | 01-Jun-20 A | 01-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A23750 | HRA Fuel Handling Essential Safety Case | 2020-06-01 | 2020-06-15 | Verify Shock Absorbers Feasibility Study EAN for Technical Review | 01-Jun-20 A | 15-Jun-20 A | 11 | 0 | 10 | 100% |  | Completed
ER6378LT | W222 | W222.A17550 | HRA Fuel Handling Essential Safety Case | 2020-06-01 | 2020-06-30 | Findings of PSA Quick Look Activities (File Note) | 01-Jun-20 A | 30-Jun-20 A | 22 | 0 | 21 | 100% |  | Completed
ER6378LT | W222 | W222.A11590 | HRA Fuel Handling Essential Safety Case | 2020-06-01 | 2020-06-01 | Pre Job Brief for Human Factors Integration Plan EAN (REV 000) | 01-Jun-20 A | 01-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A11590 | HYA Fuel Handling Essential Safety Case | 2020-06-01 | 2020-06-01 | Pre Job Brief for Human Factors Integration Plan EAN (REV 000) | 01-Jun-20 A | 01-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A17550 | HYA Fuel Handling Essential Safety Case | 2020-06-01 | 2020-06-30 | Findings of PSA Quick Look Activities (File Note) | 01-Jun-20 A | 30-Jun-20 A | 22 | 0 | 21 | 100% |  | Completed
ER6650LT | W226 | W226.A23750 | HYA Fuel Handling Essential Safety Case | 2020-06-01 | 2020-06-15 | Verify Shock Absorbers Feasibility Study EAN for Technical Review | 01-Jun-20 A | 15-Jun-20 A | 11 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | W226.A24430 | HYA Fuel Handling Essential Safety Case | 2020-06-01 | 2020-06-01 | Pre Job Brief for Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN | 01-Jun-20 A | 01-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A24910 | HYA Fuel Handling Essential Safety Case |  | 2020-06-01 | Human Factors Risk Assessment for Defuelling EAN Available | 01-Jun-20 A | 01-Jun-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A24900 | HYA Fuel Handling Essential Safety Case | 2020-06-01 | 2020-06-01 | Complete Review of Human Factors Risk Assessment for Defuelling EAN to CDMS | 01-Jun-20 A | 01-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A24850 | HYA Fuel Handling Essential Safety Case | 2020-06-01 | 2020-06-01 | Confirm R1 Document is Appropriate (Human Factors Risk Assessment for Defuelling EAN) | 01-Jun-20 A | 01-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25760 | HYA Fuel Handling Essential Safety Case | 2020-06-01 | 2021-07-29 | Human Factors Integration Plan ##(Cost Summary)## ### (C2) | 01-Jun-20 A | 29-Jul-21 A | 274 | 0 | 296 | 100% |  | Completed
ER6650LT | W226 | W226.A25800 | HYA Fuel Handling Essential Safety Case | 2020-06-01 | 2020-09-01 | Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN ##(Cost Summary)## (C2) (NEW) | 01-Jun-20 A | 01-Sep-20 A | 66 | 0 | 66 | 100% |  | Completed
ER6650LT | W226 | W226.A25870 | HYA Fuel Handling Essential Safety Case | 2020-06-01 | 2020-06-01 | Human Factors Risk Assessment for Defuelling ##(Cost Summary)## (C2) (NEW) | 01-Jun-20 A | 01-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2010 | HRA Reactors Shutdown Essential Safety Cases | 2020-05-04 | 2020-06-16 | Prepare Gas Chemistry Assessment Draft Report | 01-Jun-20 A | 30-Jun-20 A | 30 | 0 | 21 | 100% |  | Completed
ER6371LT | W202 | W202.A2000 | HRA Reactors Shutdown Essential Safety Cases | 2020-05-04 | 2020-09-02 | Gas Chemistry Assessment Summary | 01-Jun-20 A | 26-Oct-20 A | 100 | 0 | 104 | 100% |  | Completed
ER6371LT | W202 | W202.A1880 | HRA Reactors Shutdown Essential Safety Cases | 2020-04-22 | 2020-04-22 | Dropped FPU Strategy Development HRA - Pre Job Brief | 01-Jun-20 A | 01-Jun-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2010 | HYA Reactors Shutdown Essential Safety Cases | 2020-05-04 | 2020-06-16 | Prepare Gas Chemistry Assessment Draft Report | 01-Jun-20 A | 30-Jun-20 A | 30 | 0 | 21 | 100% |  | Completed
ER6661LT | W206 | W206.A2000 | HYA Reactors Shutdown Essential Safety Cases | 2020-05-04 | 2020-09-23 | Gas Chemistry Assessment Summary | 01-Jun-20 A | 26-Oct-20 A | 100 | 0 | 104 | 100% |  | Completed
ER6661LT | W206 | W206.A1760 | HYA Reactors Shutdown Essential Safety Cases | 2020-04-02 | 2020-04-08 | Thermal Analysis (FEAT) of FPU Fully Extended - Draft and issue RFS | 01-Jun-20 A | 05-Jun-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A1750 | HYA Reactors Shutdown Essential Safety Cases | 2020-04-02 | 2020-05-19 | RFS - Thermal Analysis (FEAT) of FPU Fully Extended Summary | 01-Jun-20 A | 06-Jul-20 A | 33 | 0 | 26 | 100% |  | Completed
ER6661LT | W206 | W206.A1880 | HYA Reactors Shutdown Essential Safety Cases | 2020-04-22 | 2020-04-22 | Dropped FPU Strategy Development HYA - Pre Job Brief | 01-Jun-20 A | 01-Jun-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1860 | HRA Reactors Shutdown Essential Safety Cases | 2020-04-20 | 2020-04-24 | HF - Oversight of Work / HF Risk / HFIP - Draft and issue RFS | 02-Jun-20 A | 09-Jun-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A1850 | HRA Reactors Shutdown Essential Safety Cases | 2020-04-20 | 2020-06-03 | RFS - HF - Oversight of Work / HF Risk / HFIP Summary | 02-Jun-20 A | 28-Aug-20 A | 51 | 0 | 64 | 100% |  | Completed
ER6661LT | W206 | W206.A1860 | HYA Reactors Shutdown Essential Safety Cases | 2020-04-20 | 2020-04-24 | HF - Oversight of Work / HF Risk / HFIP - Draft and issue RFS | 02-Jun-20 A | 09-Jun-20 A | 6 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A1850 | HYA Reactors Shutdown Essential Safety Cases | 2020-04-20 | 2020-06-03 | RFS - HF - Oversight of Work / HF Risk / HFIP Summary | 02-Jun-20 A | 28-Aug-20 A | 64 | 0 | 64 | 100% |  | Completed
ER6378LT | W222 | W222.A24440 | HRA Fuel Handling Essential Safety Case | 2020-06-02 | 2020-06-30 | Draft Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN | 02-Jun-20 A | 30-Jun-20 A | 21 | 0 | 20 | 100% |  | Completed
ER6378LT | W222 | W222.A23220 | HRA Fuel Handling Essential Safety Case | 2020-06-02 | 2020-06-05 | Complete TR Form and Upload Basis of Analysis Report EAN to CDMS (REV 000) | 02-Jun-20 A | 05-Jun-20 A | 4 | 0 | 3 | 100% |  | Completed
ER6378LT | W222 | W222.A11480 | HRA Fuel Handling Essential Safety Case | 2020-06-02 | 2020-06-22 | Verify HF Assessment of Fuel Free Verification EAN and Issue for Technical Review (System) | 02-Jun-20 A | 22-Jun-20 A | 15 | 0 | 14 | 100% |  | Completed
ER6378LT | W222 | W222.A11600 | HRA Fuel Handling Essential Safety Case | 2020-06-02 | 2020-08-07 | Draft Human Factors Integration Plan EAN (REV 000) | 02-Jun-20 A | 07-Aug-20 A | 27 | 0 | 48 | 100% |  | Completed
ER6650LT | W226 | W226.A11600 | HYA Fuel Handling Essential Safety Case | 2020-06-02 | 2020-08-07 | Draft Human Factors Integration Plan EAN (REV 000) | 02-Jun-20 A | 07-Aug-20 A | 27 | 0 | 48 | 100% |  | Completed
ER6650LT | W226 | W226.A11480 | HYA Fuel Handling Essential Safety Case | 2020-06-02 | 2020-06-22 | Verify HF Assessment of Fuel Free Verification EAN and Issue for Technical Review (System) | 02-Jun-20 A | 22-Jun-20 A | 15 | 0 | 14 | 100% |  | Completed
ER6650LT | W226 | W226.A23220 | HYA Fuel Handling Essential Safety Case | 2020-06-02 | 2020-06-05 | Complete TR Form and Upload Basis of Analysis Report EAN to CDMS (REV 000) | 02-Jun-20 A | 05-Jun-20 A | 4 | 0 | 3 | 100% |  | Completed
ER6650LT | W226 | W226.A24440 | HYA Fuel Handling Essential Safety Case | 2020-06-02 | 2020-06-30 | Draft Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN | 02-Jun-20 A | 30-Jun-20 A | 21 | 0 | 20 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1640 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-30 | Gate C PRC Paper Submission | 03-Jun-20 A | 03-Jun-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1790 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-30 | 2020-04-03 | PRC Members Review IRM Documentation | 03-Jun-20 A | 09-Jun-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A1980 | HRA Reactors Shutdown Essential Safety Cases | 2020-04-30 | 2020-05-04 | Assumptions EAN - EDF Energy Approve Final Report | 03-Jun-20 A | 05-Jun-20 A | 3 | 0 | 3 | 100% |  | Completed
ER6661LT | W206 | W206.A1980 | HYA Reactors Shutdown Essential Safety Cases | 2020-04-30 | 2020-05-04 | Assumptions EAN - EDF Energy Approve Final Report | 03-Jun-20 A | 05-Jun-20 A | 3 | 0 | 3 | 100% |  | Completed
ER6378LT | W222 | W222.A23230 | HRA Fuel Handling Essential Safety Case |  | 2020-06-05 | Basis of Analysis Report EAN Available (REV 000) | 05-Jun-20 A | 05-Jun-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A23230 | HYA Fuel Handling Essential Safety Case |  | 2020-06-05 | Basis of Analysis Report EAN Available (REV 000) | 05-Jun-20 A | 05-Jun-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1190 | HNB Reactors Shutdown Essential Safety Cases | 2020-04-29 | 2020-05-01 | <NEW SCOPE> - Pressure Vessel Integrity Report - Issue Report and upload to CDMS | 08-Jun-20 A | 10-Jun-20 A | 3 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | W222.A22980 | HRA Fuel Handling Essential Safety Case | 2020-06-08 | 2020-08-10 | Verify Interpretation of MACE for Fuel Route EAN and Issue for Technical Review | 08-Jun-20 A | 10-Aug-20 A | 46 | 0 | 45 | 100% |  | Completed
ER6650LT | W226 | W226.A22980 | HYA Fuel Handling Essential Safety Case | 2020-06-08 | 2020-08-10 | Verify Interpretation of MACE for Fuel Route EAN and Issue for Technical Review | 08-Jun-20 A | 10-Aug-20 A | 46 | 0 | 45 | 100% |  | Completed
ER6371LT | W202 | W202.A1810 | HRA Reactors Shutdown Essential Safety Cases | 2020-04-09 | 2020-04-24 | Thermal Analysis (FEAT) of FPU Fully Extended - Supplier prepare and issue Offer | 08-Jun-20 A | 19-Jun-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | W202.A2020 | HRA Reactors Shutdown Essential Safety Cases | 2020-05-05 | 2020-05-05 | Assumptions EAN - TSA Issue Final Report | 08-Jun-20 A | 08-Jun-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A1810 | HYA Reactors Shutdown Essential Safety Cases | 2020-04-09 | 2020-04-24 | Thermal Analysis (FEAT) of FPU Fully Extended - Supplier prepare and issue Offer | 08-Jun-20 A | 19-Jun-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.A2020 | HYA Reactors Shutdown Essential Safety Cases | 2020-05-05 | 2020-05-05 | Assumptions EAN - TSA Issue Final Report | 08-Jun-20 A | 08-Jun-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A2070 | HRA Reactors Shutdown Essential Safety Cases | 2020-05-14 | 2020-05-15 | Assumptions EAN - Post Job De-Brief | 09-Jun-20 A | 11-Jun-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A2040 | HRA Reactors Shutdown Essential Safety Cases | 2020-05-06 | 2020-05-13 | Assumptions EAN - TR Completed and Final Report Uploaded to CDMS | 09-Jun-20 A | 15-Jun-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A2040 | HYA Reactors Shutdown Essential Safety Cases | 2020-05-06 | 2020-05-13 | Assumptions EAN - TR Completed and Final Report Uploaded to CDMS | 09-Jun-20 A | 15-Jun-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13075 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-05-01 | PVCW Key Technical References Complete | 10-Jun-20 A | 10-Jun-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1950 | HRA Reactors Shutdown Essential Safety Cases | 2020-04-27 | 2020-05-11 | HF - Oversight of Work / HF Risk / HFIP - Supplier prepare and issue Offer | 10-Jun-20 A | 12-Jun-20 A | 10 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A2140 | HRA Reactors Shutdown Essential Safety Cases | 2020-05-21 | 2020-05-21 | Seismic Assessment of FPU within Reactor - Pre Job Brief | 10-Jun-20 A | 10-Jun-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A1950 | HYA Reactors Shutdown Essential Safety Cases | 2020-04-27 | 2020-05-11 | HF - Oversight of Work / HF Risk / HFIP - Supplier prepare and issue Offer | 10-Jun-20 A | 12-Jun-20 A | 3 | 0 | 3 | 100% |  | Completed
ER6661LT | W206 | W206.A2140 | HYA Reactors Shutdown Essential Safety Cases | 2020-05-21 | 2020-05-21 | Seismic Assessment of FPU within Reactor - Pre Job Brief | 10-Jun-20 A | 10-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2070 | HYA Reactors Shutdown Essential Safety Cases | 2020-05-14 | 2020-05-15 | Assumptions EAN - Post Job De-Brief | 10-Jun-20 A | 11-Jun-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1760 | HNB Reactors Shutdown Essential Safety Cases | 2020-04-07 | 2020-04-07 | Hold PRC Meeting | 11-Jun-20 A | 11-Jun-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1840 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-04-07 | Gate C PRC Paper Approval | 11-Jun-20 A | 11-Jun-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1770 | HNB Reactors Shutdown Essential Safety Cases | 2020-04-08 | 2020-04-08 | Modify Estimate, Schedule & Risk Log as Required | 12-Jun-20 A | 12-Jun-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4300 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-13 | Issue Core Cooling Compliance Summary Draft Report to EDF for Review. | 12-Jun-20 A | 12-Jun-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8550 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-31 | TSA Issue Final Containment Head Document Report | 12-Jun-20 A | 12-Jun-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8580 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-16 | 2020-03-16 | Containment Implementation Workshop | 12-Jun-20 A | 12-Jun-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17310 | HNB Reactors Shutdown Essential Safety Cases | 2020-04-06 | 2020-04-06 | Cooling Workshop | 12-Jun-20 A | 12-Jun-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1650 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-04-14 | Gate C MS PRC Paper Submission | 15-Jun-20 A | 15-Jun-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1780 | HNB Reactors Shutdown Essential Safety Cases | 2020-04-09 | 2020-04-09 | Modify IRM Paper as Required | 15-Jun-20 A | 15-Jun-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4310 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-16 | 2020-03-27 | Core Cooling Compliance Summary Draft Report Reviewed by EDF SQEP | 15-Jun-20 A | 01-Jul-20 A | 10 | 0 | 12 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8560 | HNB Reactors Shutdown Essential Safety Cases | 2020-04-01 | 2020-04-16 | Containment Head Document Report TR Completed and uploaded to CDMS | 15-Jun-20 A | 15-Sep-20 A | 10 | 0 | 65 | 100% |  | Completed
ER6371LT | W202 | W202.A2060 | HRA Reactors Shutdown Essential Safety Cases | 2020-05-12 | 2020-05-18 | HF - Oversight of Work / HF Risk / HFIP - Review Offer, prepare and issue CI | 15-Jun-20 A | 15-Jun-20 A | 5 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2060 | HYA Reactors Shutdown Essential Safety Cases | 2020-05-12 | 2020-05-18 | HF - Oversight of Work / HF Risk / HFIP - Review Offer, prepare and issue CI | 15-Jun-20 A | 15-Jun-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A16400 | HRA Fuel Handling Essential Safety Case | 2020-06-15 | 2020-06-15 | Draft Update to Defuelling Programme Assumptions EAN | 15-Jun-20 A | 15-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A16390 | HRA Fuel Handling Essential Safety Case |  | 2020-06-15 | Draft Update to Defuelling Programme Assumptions EAN Verified and Issued for Verification | 15-Jun-20 A | 15-Jun-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A16410 | HRA Fuel Handling Essential Safety Case | 2020-06-15 | 2020-06-15 | Verification of Update to Defuelling Programme Assumptions EAN | 15-Jun-20 A | 15-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A16420 | HRA Fuel Handling Essential Safety Case | 2020-06-15 | 2020-06-15 | Supplier Update and Issue Update to Defuelling Programme Assumptions EAN | 15-Jun-20 A | 15-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A16440 | HRA Fuel Handling Essential Safety Case | 2020-06-15 | 2020-06-15 | Complete TR Form and Upload Update to Defuelling Programme Assumptions EAN to CDMS | 15-Jun-20 A | 15-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A16430 | HRA Fuel Handling Essential Safety Case |  | 2020-06-15 | Update to Defuelling Programme Assumptions EAN Available | 15-Jun-20 A | 15-Jun-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A16380 | HRA Fuel Handling Essential Safety Case | 2020-06-15 | 2020-06-15 | Update to Defuelling Programme Assumptions ##(Cost Summary)## | 15-Jun-20 A | 15-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A16380 | HYA Fuel Handling Essential Safety Case | 2020-06-15 | 2020-06-15 | Update to Defuelling Programme Assumptions ##(Cost Summary)## | 15-Jun-20 A | 15-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A16430 | HYA Fuel Handling Essential Safety Case |  | 2020-06-15 | Update to Defuelling Programme Assumptions EAN Available | 15-Jun-20 A | 15-Jun-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A16440 | HYA Fuel Handling Essential Safety Case | 2020-06-15 | 2020-06-15 | Complete TR Form and Upload Update to Defuelling Programme Assumptions EAN to CDMS | 15-Jun-20 A | 15-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A16420 | HYA Fuel Handling Essential Safety Case | 2020-06-15 | 2020-06-15 | Supplier Update and Issue Update to Defuelling Programme Assumptions EAN | 15-Jun-20 A | 15-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A16410 | HYA Fuel Handling Essential Safety Case | 2020-06-15 | 2020-06-15 | Verification of Update to Defuelling Programme Assumptions EAN | 15-Jun-20 A | 15-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A16390 | HYA Fuel Handling Essential Safety Case |  | 2020-06-15 | Draft Update to Defuelling Programme Assumptions EAN Verified and Issued for Verification | 15-Jun-20 A | 15-Jun-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A16400 | HYA Fuel Handling Essential Safety Case | 2020-06-15 | 2020-06-15 | Draft Update to Defuelling Programme Assumptions EAN | 15-Jun-20 A | 15-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1810 | HNB Reactors Shutdown Essential Safety Cases | 2020-04-14 | 2020-04-14 | Modify Estimate, Schedule, Cost Tool & Risk Log as Required | 16-Jun-20 A | 16-Jun-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1820 | HNB Reactors Shutdown Essential Safety Cases | 2020-04-14 | 2020-04-20 | Update Cost Management Tool | 16-Jun-20 A | 22-Jun-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6378LT | W222 | W222.A23760 | HRA Fuel Handling Essential Safety Case | 2020-06-16 | 2020-06-23 | Technical Review of Shock Absorbers Feasibility Study EAN | 16-Jun-20 A | 23-Jun-20 A | 6 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A23760 | HYA Fuel Handling Essential Safety Case | 2020-06-16 | 2020-06-23 | Technical Review of Shock Absorbers Feasibility Study EAN | 16-Jun-20 A | 23-Jun-20 A | 6 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4210 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-30 | 2020-04-21 | Core Cooling Head Document Draft Report Verified by all Verifiers | 17-Jun-20 A | 17-Jul-20 A | 10 | 0 | 22 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1220 | HNB Reactors Shutdown Essential Safety Cases | 2020-05-18 | 2020-06-05 | <NEW SCOPE> - Head Document (PVCW) - First Round Verification and Address Comments of Head Document | 18-Jun-20 A | 13-Jul-20 A | 8 | 0 | 18 | 100% |  | Completed
ER6378LT | W222 | W222.A9930 | HRA Fuel Handling Essential Safety Case | 2020-06-18 | 2020-09-01 | Technical Review of Update to Failed Fuel EAN | 18-Jun-20 A | 01-Sep-20 A | 53 | 0 | 52 | 100% |  | Completed
ER6650LT | W226 | W226.A9930 | HYA Fuel Handling Essential Safety Case | 2020-06-18 | 2020-09-01 | Technical Review of Update to Failed Fuel EAN | 18-Jun-20 A | 01-Sep-20 A | 53 | 0 | 52 | 100% |  | Completed
ER6378LT | W222 | W222.A24170 | HRA Fuel Handling Essential Safety Case | 2020-06-22 | 2020-09-10 | Verify Review of Hazop Study of Defuelling Process EAN and Issue for Technical Review (REV 000) | 22-Jun-20 A | 10-Sep-20 A | 15 | 0 | 58 | 100% |  | Completed
ER6650LT | W226 | W226.A24170 | HYA Fuel Handling Essential Safety Case | 2020-06-22 | 2020-09-10 | Verify Review of Hazop Study of Defuelling Process EAN and Issue for Technical Review (REV 000) | 22-Jun-20 A | 10-Sep-20 A | 15 | 0 | 58 | 100% |  | Completed
ER6371LT | W202 | W202.A1940 | HRA Reactors Shutdown Essential Safety Cases | 2020-04-27 | 2020-05-01 | Thermal Analysis (FEAT) of FPU Fully Extended - Review Offer, prepare and issue CI | 22-Jun-20 A | 26-Jun-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A1940 | HYA Reactors Shutdown Essential Safety Cases | 2020-04-27 | 2020-05-01 | Thermal Analysis (FEAT) of FPU Fully Extended - Review Offer, prepare and issue CI | 22-Jun-20 A | 26-Jun-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A11490 | HRA Fuel Handling Essential Safety Case | 2020-06-23 | 2020-09-11 | Technical Review of HF Assessment of Fuel Free Verification EAN (System) | 23-Jun-20 A | 11-Sep-20 A | 58 | 0 | 58 | 100% |  | Completed
ER6650LT | W226 | W226.A11490 | HYA Fuel Handling Essential Safety Case | 2020-06-23 | 2020-09-11 | Technical Review of HF Assessment of Fuel Free Verification EAN (System) | 23-Jun-20 A | 11-Sep-20 A | 58 | 0 | 58 | 100% |  | Completed
ER6378LT | W222 | W222.A23770 | HRA Fuel Handling Essential Safety Case | 2020-06-24 | 2020-06-24 | Supplier Update and Issue Shock Absorbers Feasibility Study EAN | 24-Jun-20 A | 24-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A22920 | HRA Fuel Handling Essential Safety Case | 2020-06-24 | 2020-12-10 | Technical Review of Damage and Thermal Analysis Dropped Fuelr EAN | 24-Jun-20 A | 10-Dec-20 A | 23 | 0 | 120 | 100% |  | Completed
ER6650LT | W226 | W226.A22920 | HYA Fuel Handling Essential Safety Case | 2020-06-24 | 2020-12-10 | Technical Review of Damage and Thermal Analysis Dropped Fuelr EAN | 24-Jun-20 A | 10-Dec-20 A | 23 | 0 | 120 | 100% |  | Completed
ER6650LT | W226 | W226.A23770 | HYA Fuel Handling Essential Safety Case | 2020-06-24 | 2020-06-24 | Supplier Update and Issue Shock Absorbers Feasibility Study EAN | 24-Jun-20 A | 24-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A23780 | HRA Fuel Handling Essential Safety Case | 2020-06-25 | 2020-10-02 | Complete TR Form and Upload Shock Absorbers Feasibility Study EAN to CDMS | 25-Jun-20 A | 02-Oct-20 A | 66 | 0 | 71 | 100% |  | Completed
ER6378LT | W222 | W222.A18150 | HRA Fuel Handling Essential Safety Case | 2020-06-25 | 2020-06-25 | Pre Job Brief for P6.6 Handover Document | 25-Jun-20 A | 25-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A18250 | HRA Fuel Handling Essential Safety Case | 2020-06-25 | 2021-02-26 | HH1 EoG Strategy for Implementation of Doc Changes for Essen Fuel/non Fuel Handling SC Handover Doc ##(Cost Summary)## | 25-Jun-20 A | 26-Feb-21 A | 208 | 0 | 172 | 100% |  | Completed
ER6650LT | W226 | W226.A18250 | HYA Fuel Handling Essential Safety Case | 2020-06-25 | 2021-02-26 | HH1 EoG Strategy for Implementation of Doc Changes for Essen Fuel/non Fuel Handling SC Handover Doc ##(Cost Summary)## | 25-Jun-20 A | 26-Feb-21 A | 208 | 0 | 172 | 100% |  | Completed
ER6650LT | W226 | W226.A18150 | HYA Fuel Handling Essential Safety Case | 2020-06-25 | 2020-06-25 | Pre Job Brief for P6.6 Handover Document | 25-Jun-20 A | 25-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A23780 | HYA Fuel Handling Essential Safety Case | 2020-06-25 | 2020-10-02 | Complete TR Form and Upload Shock Absorbers Feasibility Study EAN to CDMS | 25-Jun-20 A | 02-Oct-20 A | 66 | 0 | 71 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1830 | HNB Reactors Shutdown Essential Safety Cases | 2020-04-14 | 2020-04-20 | IRM Members Review IRM Documentation | 26-Jun-20 A | 01-Jul-20 A | 5 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2670 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-04-06 | Shutdown margin compliance summary Report Completed | 26-Jun-20 A | 26-Jun-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7860 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-20 | Shutdown Margin Head Document Completed | 26-Jun-20 A | 26-Jun-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17520 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-03-20 | >>>OUTGOING ENABLER (D414) Shutdown Margin Head Document Completed | 26-Jun-20 A | 26-Jun-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A18160 | HRA Fuel Handling Essential Safety Case | 2020-06-26 | 2020-10-28 | Draft P6.6 Handover Document | 26-Jun-20 A | 28-Oct-20 A | 88 | 0 | 87 | 100% |  | Completed
ER6650LT | W226 | W226.A18160 | HYA Fuel Handling Essential Safety Case | 2020-06-26 | 2020-10-28 | Draft P6.6 Handover Document | 26-Jun-20 A | 28-Oct-20 A | 88 | 0 | 87 | 100% |  | Completed
ER6371LT | W202 | W202.A3240 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-09-14 | Issue Worker Dose Report to EDF Review. | 29-Jun-20 A | 29-Jun-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3240 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-09-14 | Issue Worker Dose Report to EDF Review. | 29-Jun-20 A | 29-Jun-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A26010 | HRA Fuel Handling Essential Safety Case | 2020-06-29 | 2020-12-02 | Quality of Build Considerations ##(Cost Summary)## (C5) (NEW) | 29-Jun-20 A | 02-Dec-20 A | 112 | 0 | 112 | 100% |  | Completed
ER6378LT | W222 | W222.A25730 | HRA Fuel Handling Essential Safety Case | 2020-06-29 | 2021-05-26 | Worker Dose Assessment ##(Cost Summary)## ### (C6) | 29-Jun-20 A | 02-Nov-23 A | 889 | 0 | 846 | 100% |  | Completed
ER6378LT | W222 | W222.A23590 | HRA Fuel Handling Essential Safety Case | 2020-06-29 | 2020-06-29 | Pre Job Brief for Quality of Build Considerations (Task File Note) | 29-Jun-20 A | 29-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A10550 | HRA Fuel Handling Essential Safety Case | 2020-06-29 | 2020-06-29 | Pre Job Brief for Worker Dose Assessment (SKELETON) EAN | 29-Jun-20 A | 29-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A10550 | HYA Fuel Handling Essential Safety Case | 2020-06-29 | 2020-06-29 | Pre Job Brief for Worker Dose Assessment (SKELETON) EAN | 29-Jun-20 A | 29-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A23590 | HYA Fuel Handling Essential Safety Case | 2020-06-29 | 2020-06-29 | Pre Job Brief for Quality of Build Considerations (Task File Note) | 29-Jun-20 A | 29-Jun-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25730 | HYA Fuel Handling Essential Safety Case | 2020-06-29 | 2021-05-26 | Worker Dose Assessment ##(Cost Summary)## ### (C6) | 29-Jun-20 A | 02-Nov-23 A | 847 | 0 | 847 | 100% |  | Completed
ER6650LT | W226 | W226.A26010 | HYA Fuel Handling Essential Safety Case | 2020-06-29 | 2020-12-02 | Quality of Build Considerations ##(Cost Summary)## (C5) (NEW) | 29-Jun-20 A | 02-Dec-20 A | 112 | 0 | 112 | 100% |  | Completed
ER6378LT | W222 | W222.A23600 | HRA Fuel Handling Essential Safety Case | 2020-06-30 | 2020-10-13 | Draft Quality of Build Considerations (Task File Note) | 30-Jun-20 A | 13-Oct-20 A | 56 | 0 | 75 | 100% |  | Completed
ER6378LT | W222 | W222.A10560 | HRA Fuel Handling Essential Safety Case | 2020-06-30 | 2021-02-01 | Draft Worker Dose Assessment (SKELETON) EAN | 30-Jun-20 A | 01-Feb-21 A | 73 | 0 | 151 | 100% |  | Completed
ER6650LT | W226 | W226.A10560 | HYA Fuel Handling Essential Safety Case | 2020-06-30 | 2021-02-01 | Draft Worker Dose Assessment (SKELETON) EAN | 30-Jun-20 A | 01-Feb-21 A | 73 | 0 | 151 | 100% |  | Completed
ER6650LT | W226 | W226.A23600 | HYA Fuel Handling Essential Safety Case | 2020-06-30 | 2020-10-13 | Draft Quality of Build Considerations (Task File Note) | 30-Jun-20 A | 13-Oct-20 A | 56 | 0 | 75 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1800 | HNB Reactors Shutdown Essential Safety Cases | 2020-04-22 | 2020-04-22 | Hold MS PRC | 01-Jul-20 A | 01-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1850 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-04-22 | Gate C MS PRC Approval | 01-Jul-20 A | 01-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2130 | HRA Reactors Shutdown Essential Safety Cases | 2020-05-20 | 2020-07-01 | Prepare Pressure Boundary Seals Draft Report | 01-Jul-20 A | 17-Jul-20 A | 13 | 0 | 12 | 100% |  | Completed
ER6371LT | W202 | W202.A2120 | HRA Reactors Shutdown Essential Safety Cases | 2020-05-20 | 2020-09-24 | Pressure Boundary Seals Summary | 01-Jul-20 A | 23-Nov-20 A | 125 | 0 | 102 | 100% |  | Completed
ER6661LT | W206 | W206.A2350 | HYA Reactors Shutdown Essential Safety Cases | 2020-07-02 | 2020-07-29 | Pressure Boundary Seals Draft Report Verified by TSA | 01-Jul-20 A | 28-Aug-20 A | 43 | 0 | 42 | 100% |  | Completed
ER6661LT | W206 | W206.A2120 | HYA Reactors Shutdown Essential Safety Cases | 2020-05-20 | 2020-11-02 | Pressure Boundary Seals Summary | 01-Jul-20 A | 23-Nov-20 A | 117 | 0 | 102 | 100% |  | Completed
ER6378LT | W222 | W222.A24450 | HRA Fuel Handling Essential Safety Case | 2020-07-01 | 2020-07-02 | Verify Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN & Issue for Technical Review | 01-Jul-20 A | 02-Jul-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | A1040 | HNB Reactors Shutdown Essential Safety Cases |  |  | 4 – Resolution of SC Shortfalls and Key NS Issues - Summary | 01-Jul-20 A | 30-Jul-20 A | 22 | 0 | 22 | 100% |  | Completed
ER6370LT | W201 | A1050 | HNB Reactors Shutdown Essential Safety Cases |  |  | 5 – Description of Updated SC - Summary | 01-Jul-20 A | 05-Aug-20 A | 24 | 0 | 25 | 100% |  | Completed
ER6370LT | W201 | A1060 | HNB Reactors Shutdown Essential Safety Cases |  |  | 5.0 Claim 0 - Summary | 01-Jul-20 A | 14-Aug-20 A | 18 | 0 | 33 | 100% |  | Completed
ER6370LT | W201 | A1070 | HNB Reactors Shutdown Essential Safety Cases |  |  | 5.1 Claim 1 - Summary | 01-Jul-20 A | 06-Aug-20 A | 16 | 0 | 27 | 100% |  | Completed
ER6370LT | W201 | A1080 | HNB Reactors Shutdown Essential Safety Cases |  |  | 5.2 Claim 2 - Summary | 01-Jul-20 A | 28-Aug-20 A | 30 | 0 | 42 | 100% |  | Completed
ER6370LT | W201 | A1130 | HNB Reactors Shutdown Essential Safety Cases |  |  | 7 – QA - Summary | 01-Jul-20 A | 09-Oct-20 A | 59 | 0 | 72 | 100% |  | Completed
ER6370LT | W201 | A1140 | HNB Reactors Shutdown Essential Safety Cases |  |  | 8 – Implementation Programme - Summary | 01-Jul-20 A | 09-Oct-20 A | 61 | 0 | 72 | 100% |  | Completed
ER6370LT | W201 | A1150 | HNB Reactors Shutdown Essential Safety Cases |  |  | 9 – INSA - Summary | 01-Jul-20 A | 25-Sep-20 A | 49 | 0 | 62 | 100% |  | Completed
ER6370LT | W201 | A1440 | HNB Reactors Shutdown Essential Safety Cases |  |  | Resolution of SC Shortfalls and Key NS Issues - Early Draft | 01-Jul-20 A | 01-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A1490 | HNB Reactors Shutdown Essential Safety Cases |  |  | Description of Updated SC - Early Draft | 01-Jul-20 A | 01-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A1540 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 0 - Early Draft | 01-Jul-20 A | 01-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A1590 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 1 - Early Draft | 01-Jul-20 A | 01-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A1640 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 2 - Early Draft | 01-Jul-20 A | 01-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A1890 | HNB Reactors Shutdown Essential Safety Cases |  |  | QA - Early Draft | 01-Jul-20 A | 01-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A1940 | HNB Reactors Shutdown Essential Safety Cases |  |  | Implementation Programme - Early Draft | 01-Jul-20 A | 01-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A2020 | HNB Reactors Shutdown Essential Safety Cases |  |  | INSA - Peer Review | 01-Jul-20 A | 01-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A2745 | HNB Reactors Shutdown Essential Safety Cases |  |  | Safety Case Authoring Start | 01-Jul-20 A | 01-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A2741 | HNB Reactors Shutdown Essential Safety Cases |  |  | Safety Case Authoring - Summary | 01-Jul-20 A | 09-Oct-20 A | 74 | 0 | 72 | 100% |  | Completed
ER6378LT | W222 | W222.A26940 | HRA Fuel Handling Essential Safety Case | 2020-07-01 | 2020-09-21 | Update Project Definition Document (PDD) | 01-Jul-20 A | 21-Sep-20 A | 1 | 0 | 57 | 100% |  | Completed
ER6378LT | W222 | W222.A27020 | HRA Fuel Handling Essential Safety Case | 2020-07-01 | 2020-09-18 | Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 01-Jul-20 A | 18-Sep-20 A | 57 | 0 | 57 | 100% |  | Completed
ER6378LT | W222 | W222.A27030 | HRA Fuel Handling Essential Safety Case | 2020-07-01 | 2020-09-18 | Define Project Control Structures (WBS/CBS/OBS/PBS) (FEEDS TO SUMMARY SCHEDULE) | 01-Jul-20 A | 18-Sep-20 A | 57 | 0 | 57 | 100% |  | Completed
ER6650LT | W226 | W226.A27030 | HYA Fuel Handling Essential Safety Case | 2020-07-01 | 2020-09-18 | Define Project Control Structures (WBS/CBS/OBS/PBS) | 01-Jul-20 A | 18-Sep-20 A | 57 | 0 | 57 | 100% |  | Completed
ER6650LT | W226 | W226.A27020 | HYA Fuel Handling Essential Safety Case | 2020-07-01 | 2020-09-18 | Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 01-Jul-20 A | 18-Sep-20 A | 57 | 0 | 57 | 100% |  | Completed
ER6650LT | W226 | W226.A26940 | HYA Fuel Handling Essential Safety Case | 2020-07-01 | 2020-09-21 | Update Project Definition Document (PDD) | 01-Jul-20 A | 21-Sep-20 A | 1 | 0 | 57 | 100% |  | Completed
ER6650LT | W226 | W226.A24450 | HYA Fuel Handling Essential Safety Case | 2020-07-01 | 2020-07-02 | Verify Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN & Issue for Technical Review | 01-Jul-20 A | 02-Jul-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A2290 | HRA Reactors Shutdown Essential Safety Cases | 2020-06-17 | 2020-07-07 | Gas Chemistry Assessment Draft Report Verified by TSA | 01-Jul-20 A | 06-Jul-20 A | 15 | 0 | 3 | 100% |  | Completed
ER6371LT | W202 | W202.A2170 | HRA Reactors Shutdown Essential Safety Cases | 2020-05-22 | 2020-07-17 | Prepare Seismic Assessment of FPU within Reactor Report | 01-Jul-20 A | 14-Sep-20 A | 53 | 0 | 53 | 100% |  | Completed
ER6371LT | W202 | W202.A2160 | HRA Reactors Shutdown Essential Safety Cases | 2020-05-22 | 2020-08-21 | Seismic Assessment of FPU within Reactor Report Summary | 01-Jul-20 A | 20-Nov-20 A | 92 | 0 | 101 | 100% |  | Completed
ER6371LT | W202 | W202.A1990 | HRA Reactors Shutdown Essential Safety Cases | 2020-05-04 | 2020-05-18 | Thermal Analysis (FEAT) of FPU Fully Extended - Supplier mobilisation time | 01-Jul-20 A | 02-Jul-20 A | 10 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A2340 | HRA Reactors Shutdown Essential Safety Cases | 2020-07-01 | 2020-07-07 | (SCOPE REMOVED) - Station Documentation Update Strategy Report - Draft and issue RFS | 01-Jul-20 A | 02-Jul-20 A | 0 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A2400 | HRA Reactors Shutdown Essential Safety Cases | 2020-07-08 | 2020-07-21 | (SCOPE REMOVED) - Station Documentation Update Strategy Report - Supplier prepare and issue Offer | 01-Jul-20 A | 02-Jul-20 A | 0 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A2580 | HRA Reactors Shutdown Essential Safety Cases | 2020-07-22 | 2020-07-28 | (SCOPE REMOVED) - Station Documentation Update Strategy Report - Review Offer, prepare and issue CI | 01-Jul-20 A | 02-Jul-20 A | 0 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A2600 | HRA Reactors Shutdown Essential Safety Cases | 2020-07-29 | 2020-08-11 | (SCOPE REMOVED) - Station Documentation Update Strategy Report - Supplier mobilisation time | 01-Jul-20 A | 02-Jul-20 A | 0 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A2800 | HRA Reactors Shutdown Essential Safety Cases | 2020-08-12 | 2020-08-12 | (SCOPE REMOVED) - Station Documentation Update Strategy Report - Pre Job Brief | 01-Jul-20 A | 02-Jul-20 A | 0 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A3250 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-15 | 2020-09-28 | Worker Dose Report Reviewed by EDF SQEP | 01-Jul-20 A | 31-Jul-20 A | 10 | 0 | 22 | 100% |  | Completed
ER6661LT | W206 | W206.A2290 | HYA Reactors Shutdown Essential Safety Cases | 2020-06-17 | 2020-07-07 | Gas Chemistry Assessment Draft Report Verified by TSA | 01-Jul-20 A | 06-Jul-20 A | 15 | 0 | 3 | 100% |  | Completed
ER6661LT | W206 | W206.A2170 | HYA Reactors Shutdown Essential Safety Cases | 2020-05-22 | 2020-07-17 | Prepare Seismic Assessment of FPU within Reactor Report | 01-Jul-20 A | 14-Sep-20 A | 53 | 0 | 53 | 100% |  | Completed
ER6661LT | W206 | W206.A2160 | HYA Reactors Shutdown Essential Safety Cases | 2020-05-22 | 2020-09-30 | Seismic Assessment of FPU within Reactor Report Summary | 01-Jul-20 A | 20-Nov-20 A | 92 | 0 | 101 | 100% |  | Completed
ER6661LT | W206 | W206.A1990 | HYA Reactors Shutdown Essential Safety Cases | 2020-05-04 | 2020-05-18 | Thermal Analysis (FEAT) of FPU Fully Extended - Supplier mobilisation time | 01-Jul-20 A | 02-Jul-20 A | 10 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A2340 | HYA Reactors Shutdown Essential Safety Cases | 2020-07-01 | 2020-07-07 | (SCOPE REMOVED) - Station Documentation Update Strategy Report - Draft and issue RFS | 01-Jul-20 A | 02-Jul-20 A | 5 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2400 | HYA Reactors Shutdown Essential Safety Cases | 2020-07-08 | 2020-07-21 | (SCOPE REMOVED) - Station Documentation Update Strategy Report - Supplier prepare and issue Offer | 01-Jul-20 A | 02-Jul-20 A | 10 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2580 | HYA Reactors Shutdown Essential Safety Cases | 2020-07-22 | 2020-07-28 | (SCOPE REMOVED) - Station Documentation Update Strategy Report - Review Offer, prepare and issue CI | 01-Jul-20 A | 02-Jul-20 A | 5 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2600 | HYA Reactors Shutdown Essential Safety Cases | 2020-07-29 | 2020-08-11 | (SCOPE REMOVED) - Station Documentation Update Strategy Report - Supplier mobilisation time | 01-Jul-20 A | 02-Jul-20 A | 10 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2800 | HYA Reactors Shutdown Essential Safety Cases | 2020-08-12 | 2020-08-12 | (SCOPE REMOVED) - Station Documentation Update Strategy Report - Pre Job Brief | 01-Jul-20 A | 02-Jul-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A3250 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-15 | 2020-09-28 | Worker Dose Report Reviewed by EDF SQEP | 01-Jul-20 A | 31-Jul-20 A | 23 | 0 | 22 | 100% |  | Completed
ER6661LT | W206 | W206.A2310 | HYA Reactors Shutdown Essential Safety Cases | 2020-06-22 | 2020-07-03 | Fault Schedule Review (Plant Base Faults and Hazards) Draft Report Verified by TSA - (HYA) | 01-Jul-20 A | 14-Jul-20 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8610 | HNB Reactors Shutdown Essential Safety Cases |  |  | Containment Head Document - Resolution of verification comments | 01-Jul-20 A | 05-Aug-20 A | 13 | 0 | 26 | 100% |  | Completed
ER6378LT | W222 | W222.A25940 | HRA Fuel Handling Essential Safety Case | 2020-07-01 | 2020-09-18 | Breached PVCW Assessment ##(Cost Summary)## (C5) | 01-Jul-20 A | 18-Sep-20 A | 57 | 0 | 57 | 100% |  | Completed
ER6378LT | W222 | W222.A23030 | HRA Fuel Handling Essential Safety Case | 2020-07-01 | 2020-07-01 | Pre Job Brief for Breached PVCW Assessment EAN | 01-Jul-20 A | 01-Jul-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | A1000 | HNB Reactors Shutdown Essential Safety Cases |  |  | 1 – Introduction - Summary | 01-Jul-20 A | 27-Jul-20 A | 19 | 0 | 19 | 100% |  | Completed
ER6370LT | W201 | A1020 | HNB Reactors Shutdown Essential Safety Cases |  |  | 2 – Existing Safety Case - Summary | 01-Jul-20 A | 28-Jul-20 A | 20 | 0 | 20 | 100% |  | Completed
ER6370LT | W201 | A1030 | HNB Reactors Shutdown Essential Safety Cases |  |  | 3 – Description of Essential Defuelling Process - Summary | 01-Jul-20 A | 29-Jul-20 A | 21 | 0 | 21 | 100% |  | Completed
ER6370LT | W201 | A1290 | HNB Reactors Shutdown Essential Safety Cases |  |  | Introduction - Early Draft | 01-Jul-20 A | 01-Jul-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | A1340 | HNB Reactors Shutdown Essential Safety Cases |  |  | Existing Safety Case - Early Draft | 01-Jul-20 A | 01-Jul-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | A1390 | HNB Reactors Shutdown Essential Safety Cases |  |  | Description of Essential Defuelling Process - Early Draft | 01-Jul-20 A | 01-Jul-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A23030 | HYA Fuel Handling Essential Safety Case | 2020-07-01 | 2020-07-01 | Pre Job Brief for Breached PVCW Assessment EAN | 01-Jul-20 A | 01-Jul-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A25940 | HYA Fuel Handling Essential Safety Case | 2020-07-01 | 2020-09-18 | Breached PVCW Assessment ##(Cost Summary)## (C5) | 01-Jul-20 A | 18-Sep-20 A | 57 | 0 | 57 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4320 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-30 | 2020-04-14 | Address Comments from EDF's Review of Core Cooling Compliance Summary Draft Report | 02-Jul-20 A | 08-Jul-20 A | 8 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | A1100 | HNB Reactors Shutdown Essential Safety Cases |  |  | 5.4 Claim 4 - Summary | 02-Jul-20 A | 25-Sep-20 A | 44 | 0 | 61 | 100% |  | Completed
ER6370LT | W201 | A1450 | HNB Reactors Shutdown Essential Safety Cases |  |  | Resolution of SC Shortfalls and Key NS Issues - CO and co-author review | 02-Jul-20 A | 02-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A1500 | HNB Reactors Shutdown Essential Safety Cases |  |  | Description of Updated SC - CO and co-author review | 02-Jul-20 A | 02-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A1550 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 0 - CO and co-author review | 02-Jul-20 A | 02-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A1600 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 1 - CO and co-author review | 02-Jul-20 A | 02-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A1650 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 2 - CO and co-author review | 02-Jul-20 A | 02-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A1750 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 4 - CO and co-author review | 02-Jul-20 A | 02-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A23040 | HRA Fuel Handling Essential Safety Case | 2020-07-02 | 2020-09-07 | Draft Breached PVCW Assessmen EAN | 02-Jul-20 A | 07-Sep-20 A | 30 | 0 | 47 | 100% |  | Completed
ER6370LT | W201 | A1300 | HNB Reactors Shutdown Essential Safety Cases |  |  | Introduction - CO and co-author review | 02-Jul-20 A | 02-Jul-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | A1350 | HNB Reactors Shutdown Essential Safety Cases |  |  | Existing Safety Case - CO and co-author review | 02-Jul-20 A | 02-Jul-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | A1400 | HNB Reactors Shutdown Essential Safety Cases |  |  | Description of Essential Defuelling Process - CO and co-author review | 02-Jul-20 A | 02-Jul-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A23040 | HYA Fuel Handling Essential Safety Case | 2020-07-02 | 2020-09-07 | Draft Breached PVCW Assessmen EAN | 02-Jul-20 A | 07-Sep-20 A | 30 | 0 | 47 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1880 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-05-01 | Gate C IRM Paper Submission | 03-Jul-20 A | 03-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2080 | HRA Reactors Shutdown Essential Safety Cases | 2020-05-19 | 2020-05-19 | Thermal Analysis (FEAT) of FPU Fully Extended - Pre Job Brief | 03-Jul-20 A | 06-Jul-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | A1460 | HNB Reactors Shutdown Essential Safety Cases |  |  | Resolution of SC Shortfalls and Key NS Issues - Mature Draft | 03-Jul-20 A | 03-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A1510 | HNB Reactors Shutdown Essential Safety Cases |  |  | Description of Updated SC - Mature Draft | 03-Jul-20 A | 03-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A1560 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 0 - Mature Draft | 03-Jul-20 A | 03-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A1610 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 1 - Mature Draft | 03-Jul-20 A | 03-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A1660 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 2 - Mature Draft | 03-Jul-20 A | 03-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A24460 | HRA Fuel Handling Essential Safety Case | 2020-07-03 | 2020-07-06 | Technical Review of Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN | 03-Jul-20 A | 06-Jul-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | A1310 | HNB Reactors Shutdown Essential Safety Cases |  |  | Introduction - Mature Draft | 03-Jul-20 A | 03-Jul-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | A1360 | HNB Reactors Shutdown Essential Safety Cases |  |  | Existing Safety Case - Mature Draft | 03-Jul-20 A | 03-Jul-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | A1410 | HNB Reactors Shutdown Essential Safety Cases |  |  | Description of Essential Defuelling Process - Mature Draft | 03-Jul-20 A | 03-Jul-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A24460 | HYA Fuel Handling Essential Safety Case | 2020-07-03 | 2020-07-06 | Technical Review of Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN | 03-Jul-20 A | 06-Jul-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A2390 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-07-07 | Verified Gas Chemistry Assessment Draft Report Issued to EDF for Technical Review. | 06-Jul-20 A | 06-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2080 | HYA Reactors Shutdown Essential Safety Cases | 2020-05-19 | 2020-05-19 | Thermal Analysis (FEAT) of FPU Fully Extended - Pre Job Brief | 06-Jul-20 A | 06-Jul-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A26330 | HRA Fuel Handling Essential Safety Case | 2020-07-06 | 2021-06-11 | The Grab Extend FPU Ledge/ Fault and Associated Protection Needs ##(Cost Summary)## (C2) (NEW) | 06-Jul-20 A | 11-Jun-21 A | 235 | 0 | 236 | 100% |  | Completed
ER6378LT | W222 | W222.A26320 | HRA Fuel Handling Essential Safety Case | 2020-07-06 | 2020-07-06 | Pre Job Brief for The Grab Extend FPU Ledge/ Fault and Associated Protection Needs EAN | 06-Jul-20 A | 06-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A1470 | HNB Reactors Shutdown Essential Safety Cases |  |  | Resolution of SC Shortfalls and Key NS Issues - Peer Review | 06-Jul-20 A | 24-Jul-20 A | 15 | 0 | 15 | 100% |  | Completed
ER6370LT | W201 | A1520 | HNB Reactors Shutdown Essential Safety Cases |  |  | Description of Updated SC - Peer Review | 06-Jul-20 A | 27-Jul-20 A | 15 | 0 | 16 | 100% |  | Completed
ER6650LT | W226 | W226.A26320 | HYA Fuel Handling Essential Safety Case | 2020-07-06 | 2020-07-06 | Pre Job Brief for The Grab Extend FPU Ledge/ Fault and Associated Protection Needs EAN | 06-Jul-20 A | 06-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A26330 | HYA Fuel Handling Essential Safety Case | 2020-07-06 | 2021-06-11 | The Grab Extend FPU Ledge/ Fault and Associated Protection Needs ##(Cost Summary)## (C2) (NEW) | 06-Jul-20 A | 11-Jun-21 A | 235 | 0 | 236 | 100% |  | Completed
ER6370LT | W201 | A1320 | HNB Reactors Shutdown Essential Safety Cases |  |  | Introduction - Peer Review | 06-Jul-20 A | 24-Jul-20 A | 15 | 0 | 15 | 100% |  | Completed
ER6370LT | W201 | A1370 | HNB Reactors Shutdown Essential Safety Cases |  |  | Existing Safety Case - Peer Review | 06-Jul-20 A | 24-Jul-20 A | 1 | 0 | 15 | 100% |  | Completed
ER6370LT | W201 | A1420 | HNB Reactors Shutdown Essential Safety Cases |  |  | Description of Essential Defuelling Process - Peer Review | 06-Jul-20 A | 24-Jul-20 A | 1 | 0 | 15 | 100% |  | Completed
ER6378LT | W222 | W222.A26340 | HRA Fuel Handling Essential Safety Case | 2020-07-07 | 2021-02-12 | Draft The Grab Extend FPU Ledge/ Fault and Associated Protection Needs EAN | 07-Jul-20 A | 12-Feb-21 A | 75 | 0 | 155 | 100% |  | Completed
ER6378LT | W222 | W222.A25890 | HRA Fuel Handling Essential Safety Case | 2020-07-07 | 2020-11-10 | Grab Engagement for Low Burn-up Fuel##(Cost Summary)## (NEW) (C3) | 07-Jul-20 A | 10-Nov-20 A | 90 | 0 | 90 | 100% |  | Completed
ER6378LT | W222 | W222.A22820 | HRA Fuel Handling Essential Safety Case | 2020-07-07 | 2020-07-07 | Pre Job Brief for Grab Engagement for Low Burn-up Fuel EAN | 07-Jul-20 A | 07-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A22820 | HYA Fuel Handling Essential Safety Case | 2020-07-07 | 2020-07-07 | Pre Job Brief for Grab Engagement for Low Burn-up Fuel EAN | 07-Jul-20 A | 07-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25890 | HYA Fuel Handling Essential Safety Case | 2020-07-07 | 2020-11-10 | Grab Engagement for Low Burn-up Fuel##(Cost Summary)## (NEW) (C3) | 07-Jul-20 A | 10-Nov-20 A | 90 | 0 | 90 | 100% |  | Completed
ER6650LT | W226 | W226.A26340 | HYA Fuel Handling Essential Safety Case | 2020-07-07 | 2021-02-12 | Draft The Grab Extend FPU Ledge/ Fault and Associated Protection Needs EAN | 07-Jul-20 A | 12-Feb-21 A | 75 | 0 | 155 | 100% |  | Completed
ER6378LT | W222 | W222.A24470 | HRA Fuel Handling Essential Safety Case | 2020-07-07 | 2020-07-08 | Supplier Update and Issue Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN | 07-Jul-20 A | 08-Jul-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | W226.A24470 | HYA Fuel Handling Essential Safety Case | 2020-07-07 | 2020-07-08 | Supplier Update and Issue Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN | 07-Jul-20 A | 08-Jul-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4330 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-04-14 | Issue Final Core Cooling Compliance Summary Report | 08-Jul-20 A | 08-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A25970 | HRA Fuel Handling Essential Safety Case | 2020-07-08 | 2021-05-04 | Update Core Support Plate Properties Methodology & Toughness Properties ##(Cost Summary)## (C5) (NEW) | 08-Jul-20 A | 04-May-21 A | 208 | 0 | 208 | 100% |  | Completed
ER6378LT | W222 | W222.A23310 | HRA Fuel Handling Essential Safety Case | 2020-07-08 | 2020-07-08 | Pre Job Brief for Update Core Support Plate Properties Methodology & Toughness Properties EAN | 08-Jul-20 A | 08-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A22830 | HRA Fuel Handling Essential Safety Case | 2020-07-08 | 2020-08-07 | Draft Grab Engagement for Low Burn-up Fuel EAN | 08-Jul-20 A | 07-Aug-20 A | 23 | 0 | 22 | 100% |  | Completed
ER6650LT | W226 | W226.A22830 | HYA Fuel Handling Essential Safety Case | 2020-07-08 | 2020-08-07 | Draft Grab Engagement for Low Burn-up Fuel EAN | 08-Jul-20 A | 07-Aug-20 A | 23 | 0 | 22 | 100% |  | Completed
ER6650LT | W226 | W226.A23310 | HYA Fuel Handling Essential Safety Case | 2020-07-08 | 2020-07-08 | Pre Job Brief for Update Core Support Plate Properties Methodology & Toughness Properties EAN | 08-Jul-20 A | 08-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25970 | HYA Fuel Handling Essential Safety Case | 2020-07-08 | 2021-05-04 | Update Core Support Plate Properties Methodology & Toughness Properties ##(Cost Summary)## (C5) (NEW) | 08-Jul-20 A | 04-May-21 A | 208 | 0 | 208 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4340 | HNB Reactors Shutdown Essential Safety Cases | 2020-04-15 | 2020-04-28 | Core Cooling Compliance Summary Report Completed and uploaded to CDMS | 09-Jul-20 A | 14-Jul-20 A | 3 | 0 | 3 | 100% |  | Completed
ER6661LT | W206 | W206.A2190 | HYA Reactors Shutdown Essential Safety Cases | 2020-05-29 | 2020-06-17 | TSA Address Comments on HYA Defuelling Case against the NSPs Draft Report | 09-Jul-20 A | 14-Aug-20 A | 27 | 0 | 26 | 100% |  | Completed
ER6378LT | W222 | W222.A24480 | HRA Fuel Handling Essential Safety Case | 2020-07-09 | 2020-07-10 | Complete Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN to CDMS | 09-Jul-20 A | 10-Jul-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | W226.A24480 | HYA Fuel Handling Essential Safety Case | 2020-07-09 | 2020-07-10 | Complete Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN to CDMS | 09-Jul-20 A | 10-Jul-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | W222.A24490 | HRA Fuel Handling Essential Safety Case |  | 2020-07-10 | Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN Available | 10-Jul-20 A | 10-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A24490 | HYA Fuel Handling Essential Safety Case |  | 2020-07-10 | Review of HH1 Protectection for Handling FPUs at Reactor during Defuelling Ops EAN Available | 10-Jul-20 A | 10-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1910 | HRA Reactors Shutdown Essential Safety Cases | 2021-02-16 | 2021-02-16 | Dropped FPU Strategy Development HRA - TSA Prepare Draft Report | 13-Jul-20 A | 14-Jul-20 A | 2 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A1900 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-01 | 2021-03-29 | Dropped FPU Strategy Development HRA - Summary | 13-Jul-20 A | 28-May-21 A | 223 | 0 | 223 | 100% |  | Completed
ER6370LT | W201 | A1170 | HNB Reactors Shutdown Essential Safety Cases |  |  | 11 – NSC Request for Consideration and Advice - Summary | 13-Jul-20 A | 02-Oct-20 A | 49 | 0 | 59 | 100% |  | Completed
ER6370LT | W201 | A1180 | HNB Reactors Shutdown Essential Safety Cases |  |  | Appendix – Description of Existing Safety Case - Summary | 13-Jul-20 A | 09-Oct-20 A | 59 | 0 | 64 | 100% |  | Completed
ER6370LT | W201 | A1270 | HNB Reactors Shutdown Essential Safety Cases |  |  | Appendix F – Previous Advice from NSC - Summary | 13-Jul-20 A | 09-Oct-20 A | 54 | 0 | 63 | 100% |  | Completed
ER6370LT | W201 | A1990 | HNB Reactors Shutdown Essential Safety Cases |  |  | INSA - Early Draft | 13-Jul-20 A | 13-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A2000 | HNB Reactors Shutdown Essential Safety Cases |  |  | INSA - CO and co-author review | 13-Jul-20 A | 13-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A2010 | HNB Reactors Shutdown Essential Safety Cases |  |  | INSA - Mature Draft | 13-Jul-20 A | 13-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A2090 | HNB Reactors Shutdown Essential Safety Cases |  |  | NSC Request for Consideration and Advice - Early Draft | 13-Jul-20 A | 13-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A2100 | HNB Reactors Shutdown Essential Safety Cases |  |  | NSC Request for Consideration and Advice - CO and co-author review | 13-Jul-20 A | 13-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A2110 | HNB Reactors Shutdown Essential Safety Cases |  |  | NSC Request for Consideration and Advice - Mature Draft | 13-Jul-20 A | 13-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A2140 | HNB Reactors Shutdown Essential Safety Cases |  |  | Appendix – Description of Existing Safety Case - Early Draft | 13-Jul-20 A | 13-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A2640 | HNB Reactors Shutdown Essential Safety Cases |  |  | Appendix F – Previous Advice from NSC - Early Draft | 13-Jul-20 A | 13-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A2650 | HNB Reactors Shutdown Essential Safety Cases |  |  | Appendix F – Previous Advice from NSC - CO and co-author review | 13-Jul-20 A | 13-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A2660 | HNB Reactors Shutdown Essential Safety Cases |  |  | Appendix F – Previous Advice from NSC - Mature Draft | 13-Jul-20 A | 13-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1930 | HRA Reactors Shutdown Essential Safety Cases | 2021-02-16 | 2021-03-01 | Dropped FPU Strategy Development HRA - Draft Report Reviewed by EDF SQEP | 13-Jul-20 A | 14-Jul-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A2050 | HRA Reactors Shutdown Essential Safety Cases | 2021-03-02 | 2021-03-15 | Dropped FPU Strategy Development HRA - TSA Address Comments on Draft Report | 13-Jul-20 A | 14-Jul-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A2180 | HRA Reactors Shutdown Essential Safety Cases | 2021-03-16 | 2021-03-29 | Dropped FPU Strategy Development HRA - Final Report Completed and uploaded to CDMS | 13-Jul-20 A | 14-Jul-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A1910 | HYA Reactors Shutdown Essential Safety Cases | 2021-02-16 | 2021-02-16 | Dropped FPU Strategy Development HYA - TSA Prepare Draft Report | 13-Jul-20 A | 14-Jul-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A1930 | HYA Reactors Shutdown Essential Safety Cases | 2021-02-16 | 2021-03-01 | Dropped FPU Strategy Development HYA - Draft Report Reviewed by EDF SQEP | 13-Jul-20 A | 14-Jul-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A2050 | HYA Reactors Shutdown Essential Safety Cases | 2021-03-02 | 2021-03-15 | Dropped FPU Strategy Development HYA - TSA Address Comments on Draft Report | 13-Jul-20 A | 14-Jul-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A2180 | HYA Reactors Shutdown Essential Safety Cases | 2021-03-16 | 2021-03-29 | Dropped FPU Strategy Development HYA - Final Report Completed and uploaded to CDMS | 13-Jul-20 A | 14-Jul-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A1900 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-02 | 2021-07-20 | Dropped FPU Strategy Development HYA - Summary | 13-Jul-20 A | 28-May-21 A | 223 | 0 | 222 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4350 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-04-28 | Core Cooling Compliance Summary Report Completed | 14-Jul-20 A | 14-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2310 | HRA Reactors Shutdown Essential Safety Cases | 2020-06-22 | 2020-07-03 | Fault Schedule Review (Plant Base Faults and Hazards) Draft Report Verified by TSA - (HRA) | 14-Jul-20 A | 31-Jul-20 A | 10 | 0 | 13 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1230 | HNB Reactors Shutdown Essential Safety Cases | 2020-06-08 | 2020-06-12 | <NEW SCOPE> - Head Document (PVCW) - Second Round Comments Received | 14-Jul-20 A | 22-Jul-20 A | 5 | 0 | 7 | 100% |  | Completed
ER6372LT | W203 | W203.A1030 | HNB Enhanced Defuelling Safety Cases | 2020-07-14 | 2020-08-21 | Prepare Schedule | 14-Jul-20 A | 21-Aug-20 A | 29 | 0 | 29 | 100% |  | Completed
ER6372LT | W203 | W203.A1040 | HNB Enhanced Defuelling Safety Cases | 2020-07-14 | 2020-08-21 | Prepare Cost Estimates +/- 10% B-C & +/- 30% Lifecycle | 14-Jul-20 A | 21-Aug-20 A | 29 | 0 | 29 | 100% |  | Completed
ER6371LT | W202 | W202.A1920 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-02-16 | Dropped FPU Strategy Development HRA - TSA Issue Draft Report to EDF for Review. | 14-Jul-20 A | 14-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2150 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-03-15 | Dropped FPU Strategy Development HRA - TSA Issue Final Report | 14-Jul-20 A | 14-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2270 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-03-29 | Dropped FPU Strategy Development HRA - Report Completed | 14-Jul-20 A | 14-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2280 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-03-29 | Dropped FPU Strategy Development HRA - Discovery MS Strategy Agreed | 14-Jul-20 A | 14-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1920 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-02-16 | Dropped FPU Strategy Development HYA - TSA Issue Draft Report to EDF for Review. | 14-Jul-20 A | 14-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2150 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-03-15 | Dropped FPU Strategy Development HYA - TSA Issue Final Report | 14-Jul-20 A | 14-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2270 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-03-29 | Dropped FPU Strategy Development HYA - Report Completed | 14-Jul-20 A | 14-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2280 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-03-29 | Dropped FPU Strategy Development HYA - Discovery MS Strategy Agreed | 14-Jul-20 A | 14-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2370 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-07-03 | Verified Fault Schedule Review (Plant Base Faults and Hazards) Draft Report Issued to EDF for Technical Review. - (HYA) | 14-Jul-20 A | 14-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2380 | HYA Reactors Shutdown Essential Safety Cases | 2020-07-06 | 2020-07-17 | Fault Schedule Review (Plant Base Faults and Hazards) Draft Report Technically Reviewed by EDF SQEP - (HYA) | 15-Jul-20 A | 28-Jul-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1860 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-05-13 | Gate C IRM Paper Approval - HNB | 16-Jul-20 A | 16-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1870 | HNB Reactors Shutdown Essential Safety Cases | 2020-05-13 | 2020-05-13 | Hold IRM | 16-Jul-20 A | 16-Jul-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13060 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-05-13 | Gate C IRM Paper Approval (HNB) | 16-Jul-20 A | 16-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2110 | HRA Reactors Shutdown Essential Safety Cases | 2020-05-20 | 2020-07-15 | Prepare Thermal Analysis (FEAT) of FPU Fully Extended Report | 16-Jul-20 A | 07-Aug-20 A | 40 | 0 | 16 | 100% |  | Completed
ER6371LT | W202 | W202.A2100 | HRA Reactors Shutdown Essential Safety Cases | 2020-05-20 | 2020-08-19 | Thermal Analysis (FEAT) of FPU Fully Extended Report Summary | 16-Jul-20 A | 12-Feb-21 A | 148 | 0 | 148 | 100% |  | Completed
ER6661LT | W206 | W206.A2130 | HYA Reactors Shutdown Essential Safety Cases | 2020-05-20 | 2020-07-01 | Prepare Pressure Boundary Seals Draft Report | 16-Jul-20 A | 17-Jul-20 A | 30 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2110 | HYA Reactors Shutdown Essential Safety Cases | 2020-05-20 | 2020-07-15 | Prepare Thermal Analysis (FEAT) of FPU Fully Extended Report | 16-Jul-20 A | 07-Aug-20 A | 40 | 0 | 16 | 100% |  | Completed
ER6661LT | W206 | W206.A2100 | HYA Reactors Shutdown Essential Safety Cases | 2020-05-20 | 2020-12-15 | Thermal Analysis (FEAT) of FPU Fully Extended Report Summary | 16-Jul-20 A | 12-Feb-21 A | 148 | 0 | 148 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4220 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-04-21 | Core Cooling Head Document Draft Report - Comments returned from all verifiers | 17-Jul-20 A | 17-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2510 | HRA Reactors Shutdown Essential Safety Cases | 2020-07-17 | 2021-10-21 | SC - Safety Case development - tech oversight Cat 1 - Claim 1 - HRA - B-C - STN | 17-Jul-20 A | 01-Sep-21 A | 335 | 0 | 284 | 100% |  | Completed
ER6371LT | W202 | W202.A2530 | HRA Reactors Shutdown Essential Safety Cases | 2020-07-17 | 2020-07-20 | Shutdown Margin Workshop - Identify / Address any Shortfalls | 17-Jul-20 A | 20-Jul-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A2520 | HRA Reactors Shutdown Essential Safety Cases | 2020-07-17 | 2020-11-10 | Shutdown Margin Workshop Summary | 17-Jul-20 A | 20-Aug-21 A | 118 | 0 | 277 | 100% |  | Completed
ER6371LT | W202 | W202.A2500 | HRA Reactors Shutdown Essential Safety Cases | 2020-07-17 | 2021-10-21 | Safety Case Dev Cat 1 - Station Oversight of tech work & SC - HRA - B-C - T&S NS | 17-Jul-20 A | 01-Sep-21 A | 335 | 0 | 284 | 100% |  | Completed
ER6661LT | W206 | W206.A2510 | HYA Reactors Shutdown Essential Safety Cases | 2020-07-17 | 2021-11-10 | SC - Safety Case development - tech oversight Cat 1 - Claim 1 - HYA - B-C - STN | 17-Jul-20 A | 01-Sep-21 A | 335 | 0 | 284 | 100% |  | Completed
ER6661LT | W206 | W206.A2530 | HYA Reactors Shutdown Essential Safety Cases | 2020-07-17 | 2020-07-20 | Shutdown Margin Workshop - Identify / Address any Shortfalls | 17-Jul-20 A | 20-Jul-20 A | 2 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2520 | HYA Reactors Shutdown Essential Safety Cases | 2020-07-17 | 2021-01-04 | Shutdown Margin Workshop Summary | 17-Jul-20 A | 20-Aug-21 A | 118 | 0 | 277 | 100% |  | Completed
ER6661LT | W206 | W206.A2500 | HYA Reactors Shutdown Essential Safety Cases | 2020-07-17 | 2021-10-21 | Safety Case Dev Cat 1 - Station Oversight of tech work & SC - HYA - B-C - T&S NS | 17-Jul-20 A | 01-Sep-21 A | 335 | 0 | 284 | 100% |  | Completed
ER6370LT | W201 | ER6370.A7110 | HNB Reactors Shutdown Essential Safety Cases |  |  | Boilers and Gas Circulator Performance - EDF Internal Verification of Reworked Draft EAN Complete | 17-Jul-20 A | 17-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A24420 | HRA Fuel Handling Essential Safety Case |  | 2020-07-20 | Fuel Route Operational Sequence/Process for Defuelling EAN Available (REV 000) | 20-Jul-20 A | 20-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A24420 | HYA Fuel Handling Essential Safety Case |  | 2020-07-20 | Fuel Route Operational Sequence/Process for Defuelling EAN Available (REV 000) | 20-Jul-20 A | 20-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4230 | HNB Reactors Shutdown Essential Safety Cases | 2020-04-22 | 2020-05-05 | Core Cooling Head Document Draft Report - Lead verifier collation of comments | 20-Jul-20 A | 27-Jul-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17540 | HNB Reactors Shutdown Essential Safety Cases |  |  | Boilers and Gas Circulator Performance - Verified Reworked Draft EAN Completed and uploaded to CDMS | 20-Jul-20 A | 28-Jul-20 A | 5 | 0 | 6 | 100% |  | Completed
ER6371LT | W202 | W202.A2570 | HRA Reactors Shutdown Essential Safety Cases | 2020-07-21 | 2020-08-03 | Shutdown Margin Workshop - Production of Meeting Notes | 21-Jul-20 A | 25-Sep-20 A | 14 | 0 | 47 | 100% |  | Completed
ER6661LT | W206 | W206.A2570 | HYA Reactors Shutdown Essential Safety Cases | 2020-07-21 | 2020-08-03 | Shutdown Margin Workshop - Production of Meeting Notes | 21-Jul-20 A | 25-Sep-20 A | 14 | 0 | 47 | 100% |  | Completed
ER6371LT | W202 | W202.A2410 | HRA Reactors Shutdown Essential Safety Cases | 2020-07-08 | 2020-07-28 | Gas Chemistry Assessment Draft Report Technically Reviewed by EDF SQEP | 22-Jul-20 A | 28-Aug-20 A | 15 | 0 | 27 | 100% |  | Completed
ER6661LT | W206 | W206.A2410 | HYA Reactors Shutdown Essential Safety Cases | 2020-07-08 | 2020-07-28 | Gas Chemistry Assessment Draft Report Technically Reviewed by EDF SQEP | 22-Jul-20 A | 28-Aug-20 A | 15 | 0 | 27 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1240 | HNB Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE> - Head Document (PVCW) - Hold Point to Re-confirm Delivery Dates | 23-Jul-20 A | 23-Jul-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1250 | HNB Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE> - Head Document (PVCW) - Author Address Second Round Comments and Re-circulate Draft | 24-Jul-20 A | 29-Jul-20 A | 4 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | A1090 | HNB Reactors Shutdown Essential Safety Cases |  |  | 5.3 Claim 3 - Summary | 27-Jul-20 A | 09-Oct-20 A | 54 | 0 | 54 | 100% |  | Completed
ER6370LT | W201 | A1690 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 3 - Early Draft | 27-Jul-20 A | 25-Sep-20 A | 37 | 0 | 44 | 100% |  | Completed
ER6370LT | W201 | A1110 | HNB Reactors Shutdown Essential Safety Cases |  |  | 5.5 Claim 5 - Summary | 27-Jul-20 A | 07-Oct-20 A | 49 | 0 | 52 | 100% |  | Completed
ER6370LT | W201 | A1330 | HNB Reactors Shutdown Essential Safety Cases |  |  | Introduction - Draft Complete | 27-Jul-20 A | 27-Jul-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | A1570 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 0 - Peer Review | 27-Jul-20 A | 06-Aug-20 A | 2 | 0 | 8 | 100% |  | Completed
ER6370LT | W201 | A1740 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 4 - Early Draft | 27-Jul-20 A | 27-Jul-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | A1790 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 5 - Early Draft | 27-Jul-20 A | 26-Aug-20 A | 15 | 0 | 22 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1480 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-04-30 | All supporting references Approved and Issued (HNB) | 28-Jul-20 A | 28-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13040 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-04-30 | All Key Supporting Technical References Completed for Hunterston Essential Safety Case (HNB) | 28-Jul-20 A | 28-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16330 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-04-07 | All Supporting Technical References Complete - Claim 4 Configuration | 28-Jul-20 A | 28-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17550 | HNB Reactors Shutdown Essential Safety Cases |  |  | Boilers and Gas Circulator Performance - Reworked Draft EAN Completed | 28-Jul-20 A | 28-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1640 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-02 | HPB / HNB All Key References Produced | 28-Jul-20 A | 28-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1640 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-02 | HPB / HNB All Key References Produced | 28-Jul-20 A | 28-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A1380 | HNB Reactors Shutdown Essential Safety Cases |  |  | Existing Safety Case - Draft Complete | 28-Jul-20 A | 28-Jul-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2560 | HYA Reactors Shutdown Essential Safety Cases | 2020-07-20 | 2020-07-31 | TSA Address Comments on TR'd Fault Schedule Review (Plant Base Faults and Hazards) Draft Report - (HYA) | 29-Jul-20 A | 26-Aug-20 A | 10 | 0 | 20 | 100% |  | Completed
ER6370LT | W201 | A1430 | HNB Reactors Shutdown Essential Safety Cases |  |  | Description of Essential Defuelling Process - Draft Complete | 29-Jul-20 A | 29-Jul-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | A1760 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 4 - Mature Draft | 29-Jul-20 A | 06-Aug-20 A | 1 | 0 | 6 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4250 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-05-20 | Core Cooling Head Document Report - HOLD POINT - REVIEW COMMENTS AND RE-FORECAST | 29-Jul-20 A | 29-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2190 | HRA Reactors Shutdown Essential Safety Cases | 2020-05-29 | 2020-06-17 | TSA Address Comments on HRA Defuelling Case against the NSPs Draft Report | 30-Jul-20 A | 14-Aug-20 A | 17 | 0 | 11 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4290 | HNB Reactors Shutdown Essential Safety Cases |  |  | Core Cooling Head Document Draft Report - Author respond to comments and update draft | 30-Jul-20 A | 20-Aug-20 A | 9 | 0 | 15 | 100% |  | Completed
ER6370LT | W201 | ER6370.P17110 | HNB Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE> - Head Document (PVCW) - Third Round Comments Received | 30-Jul-20 A | 30-Jul-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | A1480 | HNB Reactors Shutdown Essential Safety Cases |  |  | Resolution of SC Shortfalls and Key NS Issues - Draft Complete | 30-Jul-20 A | 30-Jul-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2390 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-07-07 | Verified Gas Chemistry Assessment Draft Report Issued to EDF for Technical Review. | 31-Jul-20 A | 31-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1260 | HNB Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE> - Head Document (PVCW) - Verifiers Sign-Off and Produce Verification Statement | 31-Jul-20 A | 26-Aug-20 A | 5 | 0 | 18 | 100% |  | Completed
ER6371LT | W202 | W202.A2370 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-07-03 | Verified Fault Schedule Review (Plant Base Faults and Hazards) Draft Report Issued to EDF for Technical Review. - (HRA) | 31-Jul-20 A | 31-Jul-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A25750 | HRA Fuel Handling Essential Safety Case | 2020-08-03 | 2021-03-05 | Management Strategy for Pond Water Treatment Arisings ##(Cost Summary)## ### (C6) | 03-Aug-20 A | 05-Mar-21 A | 131 | 0 | 151 | 100% |  | Completed
ER6378LT | W222 | W222.A25650 | HRA Fuel Handling Essential Safety Case | 2020-08-03 | 2021-03-16 | Defuelling Cooling and Match Analysis ##(Cost Summary)## ### (C4) | 03-Aug-20 A | 16-Mar-21 A | 122 | 0 | 158 | 100% |  | Completed
ER6378LT | W222 | W222.A8210 | HRA Fuel Handling Essential Safety Case | 2020-08-03 | 2020-08-03 | Pre Job Brief for Defuelling Cooling and Match Analysis (Task FIle Note) | 03-Aug-20 A | 03-Aug-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A12500 | HRA Fuel Handling Essential Safety Case | 2020-08-03 | 2020-08-03 | Pre Job Brief for Management Strategy for Pond Water Treatment Arisings EAN | 03-Aug-20 A | 03-Aug-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A1770 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 4 - Peer Review 1 | 03-Aug-20 A | 31-Aug-20 A | 2 | 0 | 20 | 100% |  | Completed
ER6370LT | W201 | A2740 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 0 - Peer Review | 03-Aug-20 A | 06-Aug-20 A | 1 | 0 | 3 | 100% |  | Completed
ER6650LT | W226 | W226.A12500 | HYA Fuel Handling Essential Safety Case | 2020-08-03 | 2020-08-03 | Pre Job Brief for Management Strategy for Pond Water Treatment Arisings EAN | 03-Aug-20 A | 03-Aug-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A8210 | HYA Fuel Handling Essential Safety Case | 2020-08-03 | 2020-08-03 | Pre Job Brief for Defuelling Cooling and Match Analysis (Task FIle Note) | 03-Aug-20 A | 03-Aug-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25650 | HYA Fuel Handling Essential Safety Case | 2020-08-03 | 2021-03-16 | Defuelling Cooling and Match Analysis ##(Cost Summary)## ### (C4) | 03-Aug-20 A | 16-Mar-21 A | 122 | 0 | 158 | 100% |  | Completed
ER6650LT | W226 | W226.A25750 | HYA Fuel Handling Essential Safety Case | 2020-08-03 | 2021-03-05 | Management Strategy for Pond Water Treatment Arisings ##(Cost Summary)## ### (C6) | 03-Aug-20 A | 05-Mar-21 A | 131 | 0 | 151 | 100% |  | Completed
ER6371LT | W202 | W202.A2350 | HRA Reactors Shutdown Essential Safety Cases | 2020-07-02 | 2020-07-29 | Pressure Boundary Seals Draft Report Verified by TSA | 03-Aug-20 A | 28-Aug-20 A | 20 | 0 | 20 | 100% |  | Completed
ER6371LT | W202 | W202.A2090 | HRA Reactors Shutdown Essential Safety Cases | 2020-05-19 | 2020-06-02 | HF - Oversight of Work / HF Risk / HFIP - Supplier mobilisation time | 03-Aug-20 A | 27-Aug-20 A | 19 | 0 | 19 | 100% |  | Completed
ER6371LT | W202 | W202.A2380 | HRA Reactors Shutdown Essential Safety Cases | 2020-07-06 | 2020-07-17 | Fault Schedule Review (Plant Base Faults and Hazards) Draft Report Technically Reviewed by EDF SQEP - (HRA) | 03-Aug-20 A | 28-Aug-20 A | 10 | 0 | 19 | 100% |  | Completed
ER6661LT | W206 | W206.A2090 | HYA Reactors Shutdown Essential Safety Cases | 2020-05-19 | 2020-06-02 | HF - Oversight of Work / HF Risk / HFIP - Supplier mobilisation time | 03-Aug-20 A | 27-Aug-20 A | 19 | 0 | 19 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8620 | HNB Reactors Shutdown Essential Safety Cases |  |  | Containment Head Document - Provision of verification statement | 03-Aug-20 A | 11-Sep-20 A | 3 | 0 | 29 | 100% |  | Completed
ER6370LT | W201 | A1530 | HNB Reactors Shutdown Essential Safety Cases |  |  | Description of Updated SC - Draft Complete | 03-Aug-20 A | 05-Aug-20 A | 1 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | W222.A25640 | HRA Fuel Handling Essential Safety Case | 2020-08-04 | 2021-05-28 | Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment ##(Cost Summary)## ### (C3) | 04-Aug-20 A | 28-May-21 A | 212 | 0 | 207 | 100% |  | Completed
ER6378LT | W222 | W222.A8220 | HRA Fuel Handling Essential Safety Case | 2020-08-04 | 2020-08-28 | Draft Defuelling Cooling and Match Analysis (Task FIle Note) | 04-Aug-20 A | 28-Aug-20 A | 5 | 0 | 18 | 100% |  | Completed
ER6378LT | W222 | W222.A8990 | HRA Fuel Handling Essential Safety Case | 2020-08-04 | 2020-08-04 | Pre Job Brief for Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN | 04-Aug-20 A | 04-Aug-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A12510 | HRA Fuel Handling Essential Safety Case | 2020-08-04 | 2020-11-30 | Draft Management Strategy for Pond Water Treatment Arisings EAN | 04-Aug-20 A | 30-Nov-20 A | 28 | 0 | 83 | 100% |  | Completed
ER6370LT | W201 | A1580 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 0 - Draft Complete | 04-Aug-20 A | 14-Aug-20 A | 2 | 0 | 9 | 100% |  | Completed
ER6650LT | W226 | W226.A12510 | HYA Fuel Handling Essential Safety Case | 2020-08-04 | 2020-11-30 | Draft Management Strategy for Pond Water Treatment Arisings EAN | 04-Aug-20 A | 30-Nov-20 A | 28 | 0 | 83 | 100% |  | Completed
ER6650LT | W226 | W226.A8990 | HYA Fuel Handling Essential Safety Case | 2020-08-04 | 2020-08-04 | Pre Job Brief for Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN | 04-Aug-20 A | 04-Aug-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A8220 | HYA Fuel Handling Essential Safety Case | 2020-08-04 | 2020-08-28 | Draft Defuelling Cooling and Match Analysis (Task FIle Note) | 04-Aug-20 A | 28-Aug-20 A | 10 | 0 | 18 | 100% |  | Completed
ER6650LT | W226 | W226.A25640 | HYA Fuel Handling Essential Safety Case | 2020-08-04 | 2021-05-28 | Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment ##(Cost Summary)## ### (C3) | 04-Aug-20 A | 28-May-21 A | 217 | 0 | 207 | 100% |  | Completed
ER6370LT | W201 | A1620 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 1 - Peer Review | 04-Aug-20 A | 06-Aug-20 A | 3 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | A1630 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 1 - Draft Complete | 05-Aug-20 A | 06-Aug-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A2450 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-07-15 | Issue Thermal Analysis (FEAT) of FPU Fully Extended Report to EDF Review. | 07-Aug-20 A | 07-Aug-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2450 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-07-15 | Issue Thermal Analysis (FEAT) of FPU Fully Extended Report to EDF Review. | 07-Aug-20 A | 07-Aug-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A9000 | HRA Fuel Handling Essential Safety Case | 2020-08-07 | 2021-04-20 | Draft Impact on Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN | 07-Aug-20 A | 20-Apr-21 A | 65 | 0 | 177 | 100% |  | Completed
ER6650LT | W226 | W226.A9000 | HYA Fuel Handling Essential Safety Case | 2020-08-07 | 2021-04-20 | Draft Impact on Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN | 07-Aug-20 A | 20-Apr-21 A | 65 | 0 | 176 | 100% |  | Completed
ER6370LT | W201 | A1670 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 2 - Peer Review | 07-Aug-20 A | 28-Aug-20 A | 3 | 0 | 15 | 100% |  | Completed
ER6371LT | W202 | W202.A2470 | HRA Reactors Shutdown Essential Safety Cases | 2020-07-16 | 2020-07-29 | Thermal Analysis (FEAT) of FPU Fully Extended Report Reviewed by EDF SQEP | 10-Aug-20 A | 28-Aug-20 A | 10 | 0 | 14 | 100% |  | Completed
ER6378LT | W222 | W222.A23400 | HRA Fuel Handling Essential Safety Case | 2020-08-10 | 2020-09-18 | Verify CSP Model and Static Analysis and Isuue for Technical Review | 10-Aug-20 A | 18-Sep-20 A | 29 | 0 | 29 | 100% |  | Completed
ER6378LT | W222 | W222.A22840 | HRA Fuel Handling Essential Safety Case | 2020-08-10 | 2020-10-14 | Verification of Grab Engagement for Low Burn-up Fuel EAN | 10-Aug-20 A | 14-Oct-20 A | 29 | 0 | 47 | 100% |  | Completed
ER6378LT | W222 | W222.A11610 | HRA Fuel Handling Essential Safety Case | 2020-08-10 | 2020-08-14 | Verify Human Factors Integration Plan EAN and Issue for Technical Review (REV 000) | 10-Aug-20 A | 14-Aug-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6378LT | W222 | W222.A26950 | HRA Fuel Handling Essential Safety Case | 2020-08-10 | 2020-09-22 | PCL Validate & Approve Baseline Package for PRC Submission | 10-Aug-20 A | 22-Sep-20 A | 31 | 0 | 30 | 100% |  | Completed
ER6378LT | W222 | W222.A26960 | HRA Fuel Handling Essential Safety Case | 2020-08-10 | 2020-09-22 | Add Data to Scheme Paper | 10-Aug-20 A | 22-Sep-20 A | 31 | 0 | 30 | 100% |  | Completed
ER6378LT | W222 | W222.A26970 | HRA Fuel Handling Essential Safety Case | 2020-08-10 | 2020-09-22 | Update Schedule/Estimate from Risk Log & Add Provisions | 10-Aug-20 A | 22-Sep-20 A | 31 | 0 | 30 | 100% |  | Completed
ER6378LT | W222 | W222.A26980 | HRA Fuel Handling Essential Safety Case | 2020-08-10 | 2020-09-22 | Complete Risk Log with Estimates | 10-Aug-20 A | 22-Sep-20 A | 31 | 0 | 30 | 100% |  | Completed
ER6378LT | W222 | W222.A27000 | HRA Fuel Handling Essential Safety Case | 2020-08-10 | 2020-09-21 | Ensure Alignment of Schedule & Estimate | 10-Aug-20 A | 21-Sep-20 A | 30 | 0 | 30 | 100% |  | Completed
ER6378LT | W222 | W222.A27010 | HRA Fuel Handling Essential Safety Case | 2020-08-10 | 2020-09-21 | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 10-Aug-20 A | 21-Sep-20 A | 30 | 0 | 30 | 100% |  | Completed
ER6650LT | W226 | W226.A27010 | HYA Fuel Handling Essential Safety Case | 2020-08-10 | 2020-09-21 | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 10-Aug-20 A | 21-Sep-20 A | 30 | 0 | 30 | 100% |  | Completed
ER6650LT | W226 | W226.A27000 | HYA Fuel Handling Essential Safety Case | 2020-08-10 | 2020-09-21 | Ensure Alignment of Schedule & Estimate | 10-Aug-20 A | 21-Sep-20 A | 30 | 0 | 30 | 100% |  | Completed
ER6650LT | W226 | W226.A26980 | HYA Fuel Handling Essential Safety Case | 2020-08-10 | 2020-09-22 | Complete Risk Log with Estimates | 10-Aug-20 A | 22-Sep-20 A | 31 | 0 | 30 | 100% |  | Completed
ER6650LT | W226 | W226.A26970 | HYA Fuel Handling Essential Safety Case | 2020-08-10 | 2020-09-22 | Update Schedule/Estimate from Risk Log & Add Provisions | 10-Aug-20 A | 22-Sep-20 A | 31 | 0 | 30 | 100% |  | Completed
ER6650LT | W226 | W226.A26960 | HYA Fuel Handling Essential Safety Case | 2020-08-10 | 2020-09-22 | Add Data to Scheme Paper | 10-Aug-20 A | 22-Sep-20 A | 31 | 0 | 30 | 100% |  | Completed
ER6650LT | W226 | W226.A26950 | HYA Fuel Handling Essential Safety Case | 2020-08-10 | 2020-09-22 | PCL Validate & Approve Baseline Package for PRC Submission | 10-Aug-20 A | 22-Sep-20 A | 31 | 0 | 30 | 100% |  | Completed
ER6650LT | W226 | W226.A11610 | HYA Fuel Handling Essential Safety Case | 2020-08-10 | 2020-08-14 | Verify Human Factors Integration Plan EAN and Issue for Technical Review (REV 000) | 10-Aug-20 A | 14-Aug-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6650LT | W226 | W226.A22840 | HYA Fuel Handling Essential Safety Case | 2020-08-10 | 2020-10-14 | Verification of Grab Engagement for Low Burn-up Fuel EAN | 10-Aug-20 A | 14-Oct-20 A | 29 | 0 | 47 | 100% |  | Completed
ER6650LT | W226 | W226.A23400 | HYA Fuel Handling Essential Safety Case | 2020-08-10 | 2020-09-18 | Verify CSP Model and Static Analysis and Isuue for Technical Review | 10-Aug-20 A | 18-Sep-20 A | 29 | 0 | 29 | 100% |  | Completed
ER6370LT | W201 | A1120 | HNB Reactors Shutdown Essential Safety Cases |  |  | 6 – SC Margins, Judgements and Challenges - Summary | 10-Aug-20 A | 06-Oct-20 A | 41 | 0 | 41 | 100% |  | Completed
ER6370LT | W201 | A1840 | HNB Reactors Shutdown Essential Safety Cases |  |  | SC Margins, Judgements and Challenges - Early Draft | 10-Aug-20 A | 07-Sep-20 A | 22 | 0 | 19 | 100% |  | Completed
ER6378LT | W222 | W222.A22990 | HRA Fuel Handling Essential Safety Case | 2020-08-11 | 2020-10-30 | Technical Review of Interpretation of MACE for Fuel Route EAN | 11-Aug-20 A | 30-Oct-20 A | 28 | 0 | 57 | 100% |  | Completed
ER6370LT | W201 | A1950 | HNB Reactors Shutdown Essential Safety Cases |  |  | Implementation Programme - CO and co-author review | 11-Aug-20 A | 28-Aug-20 A | 1 | 0 | 13 | 100% |  | Completed
ER6650LT | W226 | W226.A22990 | HYA Fuel Handling Essential Safety Case | 2020-08-11 | 2020-10-30 | Technical Review of Interpretation of MACE for Fuel Route EAN | 11-Aug-20 A | 30-Oct-20 A | 28 | 0 | 57 | 100% |  | Completed
ER6370LT | W201 | A2150 | HNB Reactors Shutdown Essential Safety Cases |  |  | Appendix – Description of Existing Safety Case - CO and co-author review | 11-Aug-20 A | 28-Aug-20 A | 4 | 0 | 13 | 100% |  | Completed
ER6378LT | W222 | W222.A25900 | HRA Fuel Handling Essential Safety Case | 2020-08-13 | 2020-12-18 | Lifting Integrity Life Limits ##(Cost Summary)## (NEW) (C3) | 13-Aug-20 A | 18-Dec-20 A | 93 | 0 | 91 | 100% |  | Completed
ER6378LT | W222 | W222.A22750 | HRA Fuel Handling Essential Safety Case | 2020-08-13 | 2020-08-13 | Pre Job Brief for Lifting Integrity Life Limits EAN | 13-Aug-20 A | 13-Aug-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A22750 | HYA Fuel Handling Essential Safety Case | 2020-08-13 | 2020-08-13 | Pre Job Brief for Lifting Integrity Life Limits EAN | 13-Aug-20 A | 13-Aug-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25900 | HYA Fuel Handling Essential Safety Case | 2020-08-13 | 2020-12-18 | Lifting Integrity Life Limits ##(Cost Summary)## (NEW) (C3) | 13-Aug-20 A | 18-Dec-20 A | 93 | 0 | 90 | 100% |  | Completed
ER6661LT | W206 | W206.A2300 | HYA Reactors Shutdown Essential Safety Cases | 2020-06-18 | 2020-06-24 | EDF Energy Issue HYA Defuelling Case against the NSPs Final Report | 14-Aug-20 A | 21-Aug-20 A | 6 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A22760 | HRA Fuel Handling Essential Safety Case | 2020-08-14 | 2020-10-12 | Draft Lifting Integrity Life Limits EAN | 14-Aug-20 A | 12-Oct-20 A | 40 | 0 | 40 | 100% |  | Completed
ER6650LT | W226 | W226.A22760 | HYA Fuel Handling Essential Safety Case | 2020-08-14 | 2020-10-12 | Draft Lifting Integrity Life Limits EAN | 14-Aug-20 A | 12-Oct-20 A | 40 | 0 | 40 | 100% |  | Completed
ER6372LT | W203 | W203.1000 | HNB Enhanced Defuelling Safety Cases | 2020-08-14 | 2020-10-12 | Scoping Report - Summary | 14-Aug-20 A | 10-Aug-21 A | 272 | 0 | 248 | 100% |  | Completed
ER6372LT | W203 | W203.A2465 | HNB Enhanced Defuelling Safety Cases |  | 2020-08-14 | Scoping Report - Issue Draft Repot for Technical Review | 14-Aug-20 A | 14-Aug-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2300 | HRA Reactors Shutdown Essential Safety Cases | 2020-06-18 | 2020-06-24 | EDF Energy Issue HRA Defuelling Case against the NSPs Final Report | 17-Aug-20 A | 21-Aug-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6661LT | W206 | W206.A3340 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-17 | 2020-09-21 | Reactor Internals and Structural Integrity during Defuelling - Draft and issue RFS | 17-Aug-20 A | 20-Aug-20 A | 3 | 0 | 3 | 100% |  | Completed
ER6661LT | W206 | W206.A3330 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-17 | 2020-10-27 | RFS - Reactor Internals and Structural Integrity during Defuelling Summary | 17-Aug-20 A | 02-Oct-20 A | 25 | 0 | 33 | 100% |  | Completed
ER6661LT | W206 | W206.A2470 | HYA Reactors Shutdown Essential Safety Cases | 2020-07-16 | 2020-07-29 | Thermal Analysis (FEAT) of FPU Fully Extended Report Reviewed by EDF SQEP | 17-Aug-20 A | 28-Aug-20 A | 10 | 0 | 9 | 100% |  | Completed
ER6378LT | W222 | W222.A11630 | HRA Fuel Handling Essential Safety Case | 2020-08-17 | 2020-08-21 | Supplier Update and Issue Human Factors Integration Plan EAN (REV 000) | 17-Aug-20 A | 21-Aug-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6650LT | W226 | W226.A11630 | HYA Fuel Handling Essential Safety Case | 2020-08-17 | 2020-08-21 | Supplier Update and Issue Human Factors Integration Plan EAN (REV 000) | 17-Aug-20 A | 21-Aug-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13170 | HNB Reactors Shutdown Essential Safety Cases | 2020-07-20 | 2020-09-25 | SC - Safety Case development - INSA - HNB - B-C | 17-Aug-20 A | 07-May-21 A | 89 | 0 | 182 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18120 | HNB Reactors Shutdown Essential Safety Cases |  |  | Initial review of available Head Documents (Claims 0, 1 and 2) | 17-Aug-20 A | 21-Sep-20 A | 17 | 0 | 24 | 100% |  | Completed
ER6370LT | W201 | A1190 | HNB Reactors Shutdown Essential Safety Cases |  |  | Appendix – OPEX - Summary | 17-Aug-20 A | 07-Oct-20 A | 37 | 0 | 37 | 100% |  | Completed
ER6370LT | W201 | A1800 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 5 - CO and co-author review | 17-Aug-20 A | 01-Sep-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | A2190 | HNB Reactors Shutdown Essential Safety Cases |  |  | Appendix – OPEX - Early Draft | 17-Aug-20 A | 11-Sep-20 A | 10 | 0 | 19 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4680 | HNB Reactors Shutdown Essential Safety Cases |  |  | Core Cooling Head Document Draft Report - Revised draft issued to verifiers | 20-Aug-20 A | 20-Aug-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2320 | HRA Reactors Shutdown Essential Safety Cases | 2020-06-25 | 2020-07-08 | TSA Issue HRA Defuelling Case against the NSPs Final Report | 21-Aug-20 A | 28-Aug-20 A | 10 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A2320 | HYA Reactors Shutdown Essential Safety Cases | 2020-06-25 | 2020-07-08 | TSA Issue HYA Defuelling Case against the NSPs Final Report | 21-Aug-20 A | 28-Aug-20 A | 6 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4690 | HNB Reactors Shutdown Essential Safety Cases |  |  | Core Cooling Head Document Draft Report - Verifiers provide second round comments | 21-Aug-20 A | 14-Sep-20 A | 16 | 0 | 16 | 100% |  | Completed
ER6378LT | W222 | W222.A11640 | HRA Fuel Handling Essential Safety Case | 2020-08-24 | 2020-09-24 | Complete TR Form and Upload Human Factors Integration Plan EAN to CDMS (REV 000) | 24-Aug-20 A | 24-Sep-20 A | 19 | 0 | 22 | 100% |  | Completed
ER6650LT | W226 | W226.A11640 | HYA Fuel Handling Essential Safety Case | 2020-08-24 | 2020-09-24 | Complete TR Form and Upload Human Factors Integration Plan EAN to CDMS (REV 000) | 24-Aug-20 A | 24-Sep-20 A | 19 | 0 | 22 | 100% |  | Completed
ER6372LT | W203 | W203.A1050 | HNB Enhanced Defuelling Safety Cases | 2020-08-24 | 2020-09-07 | Write IRM Paper | 24-Aug-20 A | 07-Sep-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | W202.A3340 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-17 | 2020-09-21 | Reactor Internals and Structural Integrity during Defuelling - Draft and issue RFS | 25-Aug-20 A | 28-Aug-20 A | 3 | 0 | 3 | 100% |  | Completed
ER6371LT | W202 | W202.A3330 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-17 | 2020-10-27 | RFS - Reactor Internals and Structural Integrity during Defuelling Summary | 25-Aug-20 A | 02-Oct-20 A | 25 | 0 | 27 | 100% |  | Completed
ER6370LT | W201 | A1680 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 2 - Draft Complete | 26-Aug-20 A | 28-Aug-20 A | 5 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.P1270 | HNB Reactors Shutdown Essential Safety Cases | 2020-06-15 | 2020-06-19 | <NEW SCOPE> - Head Document (PVCW) - Issue Head Document and upload to CDMS | 27-Aug-20 A | 07-Sep-20 A | 5 | 0 | 6 | 100% |  | Completed
ER6378LT | W222 | W222.A16310 | HRA Fuel Handling Essential Safety Case | 2020-08-27 | 2021-12-24 | Defuelling Safety Case Head Documents ##(Cost Summary)## | 27-Aug-20 A | 24-Dec-21 A | 336 | 0 | 338 | 100% |  | Completed
ER6378LT | W222 | W222.A11330 | HRA Fuel Handling Essential Safety Case | 2020-08-27 | 2020-08-27 | Pre Job Brief for Justification for Pressure Boundary EAN | 27-Aug-20 A | 27-Aug-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A16910 | HRA Fuel Handling Essential Safety Case | 2020-08-27 | 2020-08-27 | Pre-job Brief | 27-Aug-20 A | 27-Aug-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A19400 | HRA Fuel Handling Essential Safety Case | 2020-08-27 | 2021-03-19 | Pressure Boundary ##(Cost Summary)## (C3) (NEW) | 27-Aug-20 A | 19-Mar-21 A | 119 | 0 | 143 | 100% |  | Completed
ER6650LT | W226 | W226.A19400 | HYA Fuel Handling Essential Safety Case | 2020-08-27 | 2021-03-19 | Pressure Boundary ##(Cost Summary)## (C3) (NEW) | 27-Aug-20 A | 19-Mar-21 A | 119 | 0 | 143 | 100% |  | Completed
ER6650LT | W226 | W226.A11330 | HYA Fuel Handling Essential Safety Case | 2020-08-27 | 2020-08-27 | Pre Job Brief for Justification for Pressure Boundary EAN | 27-Aug-20 A | 27-Aug-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1650 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-04 | Pressure Boundary Seals Specification Completed | 28-Aug-20 A | 28-Aug-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1650 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-04 | Pressure Boundary Seals Specification Completed | 28-Aug-20 A | 28-Aug-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206020 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-04 | >>>OUTGOING ENABLER (W222.A22450) Pressure Boundary Seals Report Completed | 28-Aug-20 A | 28-Aug-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206020 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-04 | >>>OUTGOING ENABLER (W222.A22450) Pressure Boundary Seals Report Completed | 28-Aug-20 A | 28-Aug-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206160 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-04 | >>>OUTGOING ENABLER (W226) Pressure Boundary Seals Report Completed | 28-Aug-20 A | 28-Aug-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A17630 | HRA Fuel Handling Essential Safety Case | 2020-08-28 | 2020-12-11 | Draft and Verify Justification for Pressure Boundary EAN | 28-Aug-20 A | 11-Dec-20 A | 60 | 0 | 75 | 100% |  | Completed
ER6378LT | W222 | W222.A16920 | HRA Fuel Handling Essential Safety Case | 2020-08-28 | 2020-12-01 | Proposed Contents Page Shared with EDF Energy | 28-Aug-20 A | 01-Dec-20 A | 30 | 0 | 67 | 100% |  | Completed
ER6378LT | W222 | W222.A22450 | HRA Fuel Handling Essential Safety Case |  | 2020-08-28 | >>>INCOMING ENABLER (W202.A2206020) Pressure Boundary Seals Report Completed | 28-Aug-20 A | 28-Aug-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A22550 | HRA Fuel Handling Essential Safety Case |  | 2020-08-28 | >>>MIRROR OF INCOMING ENABLER (W202.A2206020) Pressure Boundary Seals Report Completed | 28-Aug-20 A | 28-Aug-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A22650 | HRA Fuel Handling Essential Safety Case |  | 2020-08-28 | INTERFACE MILESTONE - Pressure Boundary Seals Report Completed - (W206 Reactors Shutdown Essential Safety Cases (HRA)) | 28-Aug-20 A | 28-Aug-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A2120 | HNB Reactors Shutdown Essential Safety Cases |  |  | NSC Request for Consideration and Advice - Peer Review | 28-Aug-20 A | 28-Aug-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A22650 | HYA Fuel Handling Essential Safety Case |  | 2020-08-28 | INTERFACE MILESTONE - Pressure Boundary Seals Report Completed - (W206 Reactors Shutdown Essential Safety Cases (HYA)) | 28-Aug-20 A | 28-Aug-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A22550 | HYA Fuel Handling Essential Safety Case |  | 2020-08-28 | >>>MIRROR OF INCOMING ENABLER (W202.A2206020) Pressure Boundary Seals Report Completed | 28-Aug-20 A | 28-Aug-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A16920 | HYA Fuel Handling Essential Safety Case | 2020-08-28 | 2020-12-01 | Proposed Contents Page Shared with EDF Energy | 28-Aug-20 A | 01-Dec-20 A | 30 | 0 | 67 | 100% |  | Completed
ER6650LT | W226 | W226.A17630 | HYA Fuel Handling Essential Safety Case | 2020-08-28 | 2020-12-11 | Draft Justification for Pressure Boundary EAN | 28-Aug-20 A | 11-Dec-20 A | 60 | 0 | 75 | 100% |  | Completed
ER6650LT | W226 | W226.A16310 | HYA Fuel Handling Essential Safety Case | 2020-08-28 | 2021-12-24 | Defuelling Safety Case Head Documents ##(Cost Summary)## | 28-Aug-20 A | 24-Dec-21 A | 321 | 0 | 336 | 100% |  | Completed
ER6650LT | W226 | W226.A27190 | HYA Fuel Handling Essential Safety Case |  | 2020-08-28 | >>>INCOMING ENABLER (W206.A2206020) Pressure Boundary Seals Report Completed | 28-Aug-20 A | 28-Aug-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2220 | HRA Reactors Shutdown Essential Safety Cases | 2020-06-03 | 2020-06-03 | HF - Oversight of Work / HF Risk / HFIP - Pre Job Brief | 28-Aug-20 A | 28-Aug-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2220 | HYA Reactors Shutdown Essential Safety Cases | 2020-06-03 | 2020-06-03 | HF - Oversight of Work / HF Risk / HFIP - Pre Job Brief | 28-Aug-20 A | 28-Aug-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A12370 | HRA Fuel Handling Essential Safety Case | 2020-08-31 | 2020-10-01 | Pre Job Brief for Confirm Adequate Capacity for Solid Waste Arisings from Stringer Dismantling EAN | 31-Aug-20 A | 01-Oct-20 A | 0 | 0 | 23 | 100% |  | Completed
ER6370LT | W201 | A1960 | HNB Reactors Shutdown Essential Safety Cases |  |  | Implementation Programme - Mature Draft | 31-Aug-20 A | 08-Oct-20 A | 1 | 0 | 28 | 100% |  | Completed
ER6370LT | W201 | A2160 | HNB Reactors Shutdown Essential Safety Cases |  |  | Appendix – Description of Existing Safety Case - Mature Draft | 31-Aug-20 A | 31-Aug-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A12370 | HYA Fuel Handling Essential Safety Case | 2020-08-31 | 2020-10-01 | Pre Job Brief for Confirm Adequate Capacity for Solid Waste Arisings from Stringer Dismantling EAN | 31-Aug-20 A | 01-Oct-20 A | 0 | 0 | 22 | 100% |  | Completed
ER6661LT | W206 | W206.A2240 | HYA Reactors Shutdown Essential Safety Cases | 2020-06-04 | 2020-07-15 | Prepare General HF Oversight and HFIP Updates and Revisions Draft EAN | 01-Sep-20 A | 05-Oct-20 A | 25 | 0 | 25 | 100% |  | Completed
ER6661LT | W206 | W206.A2230 | HYA Reactors Shutdown Essential Safety Cases | 2020-06-04 | 2020-09-16 | General HF Oversight and HFIP Updates and Revisions Summary | 01-Sep-20 A | 23-Nov-20 A | 74 | 0 | 59 | 100% |  | Completed
ER6661LT | W206 | W206.A2810 | HYA Reactors Shutdown Essential Safety Cases | 2020-08-12 | 2021-09-23 | SC - Safety Case development - tech oversight Cat 1 - Claim 4 - HYA - B-C - STN | 01-Sep-20 A | 24-Aug-21 A | 283 | 0 | 248 | 100% |  | Completed
ER6378LT | W222 | W222.A8230 | HRA Fuel Handling Essential Safety Case | 2020-09-01 | 2020-12-17 | Verify Defuelling Cooling and Match Analysis (Task FIle Note) and Issue for Technical Review | 01-Sep-20 A | 17-Dec-20 A | 27 | 0 | 77 | 100% |  | Completed
ER6378LT | W222 | W222.A12890 | HRA Fuel Handling Essential Safety Case | 2020-09-01 | 2021-12-13 | Safety Case Development - ##(Cost Summary)## (B to C) | 01-Sep-20 A | 13-Dec-21 A | 187 | 0 | 326 | 100% |  | Completed
ER6378LT | W222 | W222.A13260 | HRA Fuel Handling Essential Safety Case | 2020-09-01 | 2021-12-13 | Project Management Costs (B to C) ##(Cost Summary)## | 01-Sep-20 A | 13-Dec-21 A | 187 | 0 | 326 | 100% |  | Completed
ER6370LT | W201 | A1260 | HNB Reactors Shutdown Essential Safety Cases |  |  | Appendix E – Detailed Description of Changes to Documentation - Summary | 01-Sep-20 A | 15-Sep-20 A | 7 | 0 | 11 | 100% |  | Completed
ER6370LT | W201 | A2590 | HNB Reactors Shutdown Essential Safety Cases |  |  | Appendix E – Detailed Description of Changes to Documentation - Early Draft | 01-Sep-20 A | 03-Sep-20 A | 3 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | W222.A27090 | HRA Fuel Handling Essential Safety Case | 2020-09-01 |  | Gate B+ PM Costs START MILESTONE | 01-Sep-20 A | 01-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A27110 | HRA Fuel Handling Essential Safety Case | 2020-09-01 |  | Gate B+ Safety Case Costs START MILESTONE | 01-Sep-20 A | 01-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27110 | HYA Fuel Handling Essential Safety Case | 2020-09-01 |  | Gate B+ Safety Case Costs START MILESTONE | 01-Sep-20 A | 01-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27090 | HYA Fuel Handling Essential Safety Case | 2020-09-01 |  | Gate B+ PM Costs START MILESTONE | 01-Sep-20 A | 01-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A13260 | HYA Fuel Handling Essential Safety Case | 2020-09-01 | 2021-12-13 | Project Management Costs (B to C) ##(Cost Summary)## | 01-Sep-20 A | 13-Dec-21 A | 187 | 0 | 326 | 100% |  | Completed
ER6650LT | W226 | W226.A12890 | HYA Fuel Handling Essential Safety Case | 2020-09-01 | 2021-12-13 | Safety Case Development - ##(Cost Summary)## (B to C) | 01-Sep-20 A | 13-Dec-21 A | 187 | 0 | 326 | 100% |  | Completed
ER6650LT | W226 | W226.A8230 | HYA Fuel Handling Essential Safety Case | 2020-09-01 | 2020-12-17 | Verify Defuelling Cooling and Match Analysis (Task FIle Note) and Issue for Technical Review | 01-Sep-20 A | 17-Dec-20 A | 20 | 0 | 77 | 100% |  | Completed
ER6650LT | W226 | W226.A27430 | HYA Fuel Handling Essential Safety Case | 2020-09-01 | 2023-04-28 | 2020-2023 Reconciliation Sunk Line | 01-Sep-20 A | 28-Apr-23 A | 798 | 0 | 671 | 100% |  | Completed
ER6378LT | W222 | W222.A27435 | HRA Fuel Handling Essential Safety Case | 2020-09-01 | 2023-04-28 | 2020-2023 Reconciliation Sunk Line | 01-Sep-20 A | 28-Apr-23 A | 798 | 0 | 671 | 100% |  | Completed
ER6371LT | W202 | W202.A2610 | HRA Reactors Shutdown Essential Safety Cases | 2020-07-29 | 2020-08-18 | TSA Address Comments on TR'd Gas Chemistry Assessment Draft Report | 01-Sep-20 A | 19-Oct-20 A | 15 | 0 | 34 | 100% |  | Completed
ER6371LT | W202 | W202.A2240 | HRA Reactors Shutdown Essential Safety Cases | 2020-06-04 | 2020-07-15 | Prepare General HF Oversight and HFIP Updates and Revisions Draft EAN | 01-Sep-20 A | 05-Oct-20 A | 25 | 0 | 25 | 100% |  | Completed
ER6371LT | W202 | W202.A2420 | HRA Reactors Shutdown Essential Safety Cases | 2020-07-09 | 2020-08-20 | Review of HRA Defuelling Case against the NSPs TR Completed and uploaded to CDMS | 01-Sep-20 A | 02-Sep-20 A | 31 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A2230 | HRA Reactors Shutdown Essential Safety Cases | 2020-06-04 | 2020-09-10 | General HF Oversight and HFIP Updates and Revisions Summary | 01-Sep-20 A | 27-Nov-20 A | 95 | 0 | 63 | 100% |  | Completed
ER6371LT | W202 | W202.A2810 | HRA Reactors Shutdown Essential Safety Cases | 2020-08-12 | 2021-10-21 | SC - Safety Case development - tech oversight Cat 1 - Claim 4 - HRA - B-C - STN | 01-Sep-20 A | 24-Aug-21 A | 290 | 0 | 248 | 100% |  | Completed
ER6371LT | W202 | W202.A3390 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-22 | 2020-10-05 | Reactor Internals and Structural Integrity during Defuelling - Supplier prepare and issue Offer | 01-Sep-20 A | 14-Sep-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | W202.A2640 | HRA Reactors Shutdown Essential Safety Cases | 2020-07-30 | 2020-08-12 | Address Comments on Reviewed Thermal Analysis (FEAT) of FPU Fully Extended Report | 01-Sep-20 A | 31-Dec-20 A | 10 | 0 | 85 | 100% |  | Completed
ER6371LT | W202 | W202.A3480 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-29 | 2020-10-12 | Address Comments on Reviewed Worker Dose Report | 01-Sep-20 A | 15-Oct-20 A | 10 | 0 | 33 | 100% |  | Completed
ER6661LT | W206 | W206.A2610 | HYA Reactors Shutdown Essential Safety Cases | 2020-07-29 | 2020-08-18 | TSA Address Comments on TR'd Gas Chemistry Assessment Draft Report | 01-Sep-20 A | 19-Oct-20 A | 15 | 0 | 34 | 100% |  | Completed
ER6661LT | W206 | W206.A2420 | HYA Reactors Shutdown Essential Safety Cases | 2020-07-09 | 2020-08-20 | Review of HYA Defuelling Case against the NSPs TR Completed and uploaded to CDMS | 01-Sep-20 A | 02-Sep-20 A | 2 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A3390 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-22 | 2020-10-05 | Reactor Internals and Structural Integrity during Defuelling - Supplier prepare and issue Offer | 01-Sep-20 A | 14-Sep-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.A2640 | HYA Reactors Shutdown Essential Safety Cases | 2020-07-30 | 2020-08-12 | Address Comments on Reviewed Thermal Analysis (FEAT) of FPU Fully Extended Report | 01-Sep-20 A | 31-Dec-20 A | 10 | 0 | 85 | 100% |  | Completed
ER6661LT | W206 | W206.A2680 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-07-31 | TSA Issue Final Fault Schedule Review (Plant Base Faults and Hazards) Report - (HYA) | 01-Sep-20 A | 01-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2700 | HYA Reactors Shutdown Essential Safety Cases | 2020-08-03 | 2020-08-14 | Fault Schedule Review (Plant Base Faults and Hazards) Report TR Completed and uploaded to CDMS - (HYA) | 01-Sep-20 A | 14-Sep-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6378LT | W222 | W222.A26750 | HRA Fuel Handling Essential Safety Case | 2020-09-01 | 2020-09-01 | Pre Job Brief for Fuel Route Operational Sequence/Process for Defuelling EAN (REV 001) | 01-Sep-20 A | 01-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A26490 | HRA Fuel Handling Essential Safety Case | 2020-09-01 | 2021-04-15 | LVDT Weight Sensing System matters arising from Review of HH1 FM Protection ##(Cost Summary)## (C2) (NEW) | 01-Sep-20 A | 15-Apr-21 A | 158 | 0 | 158 | 100% |  | Completed
ER6378LT | W222 | W222.A26480 | HRA Fuel Handling Essential Safety Case | 2020-09-01 | 2020-09-01 | Pre Job Brief for LVDT Weight Sensing System matters arising from Review of HH1 FM Protection | 01-Sep-20 A | 01-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A26410 | HRA Fuel Handling Essential Safety Case | 2020-09-01 | 2021-05-26 | Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection ##(Cost Summary)## (C2) (NEW) | 01-Sep-20 A | 26-May-21 A | 170 | 0 | 185 | 100% |  | Completed
ER6378LT | W222 | W222.A26400 | HRA Fuel Handling Essential Safety Case | 2020-09-01 | 2020-09-01 | Pre Job Brief for Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection | 01-Sep-20 A | 01-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A26100 | HRA Fuel Handling Essential Safety Case | 2020-09-01 | 2021-02-11 | HAZOP updates resulting from defuelling process changes (REV 001) ##(Cost Summary)## (C2) (NEW) | 01-Sep-20 A | 11-Feb-21 A | 115 | 0 | 115 | 100% |  | Completed
ER6378LT | W222 | W222.A26090 | HRA Fuel Handling Essential Safety Case | 2020-09-01 | 2020-09-01 | Pre Job Brief for HAZOP updates resulting from defuelling process changes (REV 001) | 01-Sep-20 A | 01-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A26030 | HRA Fuel Handling Essential Safety Case | 2020-09-01 | 2020-11-20 | Detailed Option Investigation ##(Cost Summary)## (C5) (NEW) | 01-Sep-20 A | 20-Nov-20 A | 59 | 0 | 59 | 100% |  | Completed
ER6378LT | W222 | W222.A25810 | HRA Fuel Handling Essential Safety Case | 2020-09-01 | 2021-09-14 | Review of Interlock Maintenance Review EAN ##(Cost Summary)## (DRAFT) (C2) (NEW) (Claim 2 & 6 Impact Summary) | 01-Sep-20 A | 14-Sep-21 A | 263 | 0 | 263 | 100% |  | Completed
ER6378LT | W222 | W222.A25780 | HRA Fuel Handling Essential Safety Case | 2020-09-01 | 2021-04-19 | Hazards Review ##(Cost Summary)## (C1) (NEW) | 01-Sep-20 A | 19-Apr-21 A | 161 | 0 | 159 | 100% |  | Completed
ER6378LT | W222 | W222.A25130 | HRA Fuel Handling Essential Safety Case | 2020-09-01 | 2021-02-05 | Update Basis of Analysis for Dropped FPU to (UPDATE) (REV 001) | 01-Sep-20 A | 05-Feb-21 A | 13 | 0 | 111 | 100% |  | Completed
ER6378LT | W222 | W222.A24500 | HRA Fuel Handling Essential Safety Case | 2020-09-01 | 2020-09-01 | Pre Job Brief for Review of Interlock Maintenance Review EAN (DRAFT) | 01-Sep-20 A | 01-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A24220 | HRA Fuel Handling Essential Safety Case | 2020-09-01 | 2020-09-01 | Pre Job Brief for Hazards Review EAN | 01-Sep-20 A | 01-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A23800 | HRA Fuel Handling Essential Safety Case | 2020-09-01 | 2020-09-01 | Pre Job Brief for Detailed Option Investigation EAN | 01-Sep-20 A | 01-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A6010 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-01 | 2020-09-02 | <NEW SCOPE CR220> Panther Sensitivity Studies - Draft and issue RFS | 01-Sep-20 A | 02-Sep-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A6000 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-01 | 2020-09-18 | <NEW SCOPE CR220> RFS - Panther Sensitivity Studies Summary | 01-Sep-20 A | 18-Sep-20 A | 14 | 0 | 14 | 100% |  | Completed
ER6371LT | W202 | W202.A6310 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-01 | 2020-09-02 | <NEW SCOPE CR220> Consequences EAN - Draft and issue RFS | 01-Sep-20 A | 02-Sep-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A6300 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-01 | 2020-09-16 | <NEW SCOPE CR220> RFS - Consequences EAN Summary | 01-Sep-20 A | 16-Sep-20 A | 12 | 0 | 12 | 100% |  | Completed
ER6371LT | W202 | W202.A6800 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-01 | 2020-09-02 | <NEW SCOPE CR220> Specified Flows - Draft and issue RFS | 01-Sep-20 A | 02-Sep-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A6790 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-01 | 2020-09-18 | <NEW SCOPE CR220> RFS - Specified Flows Summary | 01-Sep-20 A | 18-Sep-20 A | 14 | 0 | 14 | 100% |  | Completed
ER6371LT | W202 | W202.A6950 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-01 | 2020-09-02 | <NEW SCOPE CR220> Determination of Cliff Edge - Draft and issue RFS | 01-Sep-20 A | 02-Sep-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A6940 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-01 | 2020-09-18 | <NEW SCOPE CR220> RFS - Determination of Cliff Edge Summary | 01-Sep-20 A | 18-Sep-20 A | 14 | 0 | 14 | 100% |  | Completed
ER6661LT | W206 | W206.A6010 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-01 | 2020-09-02 | <NEW SCOPE CR 221> Panther Sensitivity Studies - Draft and issue RFS | 01-Sep-20 A | 02-Sep-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A6000 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-01 | 2020-09-18 | <NEW SCOPE CR 221> RFS - Panther Sensitivity Studies Summary | 01-Sep-20 A | 18-Sep-20 A | 14 | 0 | 14 | 100% |  | Completed
ER6661LT | W206 | W206.A6310 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-01 | 2020-09-02 | <NEW SCOPE CR 221> Consequences EAN - Draft and issue RFS | 01-Sep-20 A | 02-Sep-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A6300 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-01 | 2020-09-16 | <NEW SCOPE CR 221> RFS - Consequences EAN Summary | 01-Sep-20 A | 16-Sep-20 A | 12 | 0 | 12 | 100% |  | Completed
ER6661LT | W206 | W206.A6800 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-01 | 2020-09-02 | <NEW SCOPE CR 221> Specified Flows - Draft and issue RFS | 01-Sep-20 A | 02-Sep-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A6790 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-01 | 2020-09-18 | <NEW SCOPE CR 221> RFS - Specified Flows Summary | 01-Sep-20 A | 18-Sep-20 A | 14 | 0 | 14 | 100% |  | Completed
ER6661LT | W206 | W206.A6950 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-01 | 2020-09-02 | <NEW SCOPE CR 221> Determination of Cliff Edge - Draft and issue RFS | 01-Sep-20 A | 02-Sep-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A6940 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-01 | 2020-09-18 | <NEW SCOPE CR 221> RFS - Determination of Cliff Edge Summary | 01-Sep-20 A | 18-Sep-20 A | 14 | 0 | 14 | 100% |  | Completed
ER6650LT | W226 | W226.A16910 | HYA Fuel Handling Essential Safety Case | 2020-09-01 | 2020-09-01 | Pre-job Brief | 01-Sep-20 A | 01-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A23800 | HYA Fuel Handling Essential Safety Case | 2020-09-01 | 2020-09-01 | Pre Job Brief for Detailed Option Investigation EAN | 01-Sep-20 A | 01-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A24220 | HYA Fuel Handling Essential Safety Case | 2020-09-01 | 2020-09-01 | Pre Job Brief for Hazards Review EAN | 01-Sep-20 A | 01-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A24500 | HYA Fuel Handling Essential Safety Case | 2020-09-01 | 2020-09-01 | Pre Job Brief for Review of Interlock Maintenance Review EAN (DRAFT) | 01-Sep-20 A | 01-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A25130 | HYA Fuel Handling Essential Safety Case | 2020-09-01 | 2021-02-05 | Update Basis of Analysis fro Dropped FPU to (UPDATE) (REV 001) | 01-Sep-20 A | 05-Feb-21 A | 13 | 0 | 111 | 100% |  | Completed
ER6650LT | W226 | W226.A25780 | HYA Fuel Handling Essential Safety Case | 2020-09-01 | 2021-04-19 | Hazards Review ##(Cost Summary)## (C1) (NEW) | 01-Sep-20 A | 19-Apr-21 A | 161 | 0 | 159 | 100% |  | Completed
ER6650LT | W226 | W226.A25810 | HYA Fuel Handling Essential Safety Case | 2020-09-01 | 2021-09-14 | Review of Interlock Maintenance Review EAN ##(Cost Summary)## (DRAFT) (C2) (NEW) | 01-Sep-20 A | 14-Sep-21 A | 263 | 0 | 263 | 100% |  | Completed
ER6650LT | W226 | W226.A26030 | HYA Fuel Handling Essential Safety Case | 2020-09-01 | 2020-11-20 | Detailed Option Investigation ##(Cost Summary)## (C5) (NEW) | 01-Sep-20 A | 20-Nov-20 A | 59 | 0 | 59 | 100% |  | Completed
ER6650LT | W226 | W226.A26090 | HYA Fuel Handling Essential Safety Case | 2020-09-01 | 2020-09-01 | Pre Job Brief for HAZOP updates resulting from defuelling process changes (REV 001) | 01-Sep-20 A | 01-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A26100 | HYA Fuel Handling Essential Safety Case | 2020-09-01 | 2021-02-11 | HAZOP updates resulting from defuelling process changes (REV 001) ##(Cost Summary)## (C2) (NEW) | 01-Sep-20 A | 11-Feb-21 A | 116 | 0 | 114 | 100% |  | Completed
ER6650LT | W226 | W226.A26400 | HYA Fuel Handling Essential Safety Case | 2020-09-01 | 2020-09-01 | Pre Job Brief for Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection | 01-Sep-20 A | 01-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A26410 | HYA Fuel Handling Essential Safety Case | 2020-09-01 | 2021-05-26 | Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection ##(Cost Summary)## (C2) (NEW) | 01-Sep-20 A | 26-May-21 A | 170 | 0 | 185 | 100% |  | Completed
ER6650LT | W226 | W226.A26480 | HYA Fuel Handling Essential Safety Case | 2020-09-01 | 2020-09-01 | Pre Job Brief for LVDT Weight Sensing System matters arising from Review of HH1 FM Protection | 01-Sep-20 A | 01-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A26490 | HYA Fuel Handling Essential Safety Case | 2020-09-01 | 2021-04-15 | LVDT Weight Sensing System matters arising from Review of HH1 FM Protection ##(Cost Summary)## (C2) (NEW) | 01-Sep-20 A | 15-Apr-21 A | 158 | 0 | 158 | 100% |  | Completed
ER6650LT | W226 | W226.A26750 | HYA Fuel Handling Essential Safety Case | 2020-09-01 | 2020-09-01 | Pre Job Brief for Fuel Route Operational Sequence/Process for Defuelling EAN (REV 001) | 01-Sep-20 A | 01-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A27260 | HRA Fuel Handling Essential Safety Case | 2020-09-01 | 2020-09-01 | Post Reference Query | 01-Sep-20 A | 01-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W222.A27260 | HYA Fuel Handling Essential Safety Case | 2020-09-01 | 2020-09-01 | Post Reference Query | 01-Sep-20 A | 01-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A9940 | HRA Fuel Handling Essential Safety Case | 2020-09-02 | 2020-09-07 | Supplier Update and Issue Update to Failed Fuel EAN | 02-Sep-20 A | 07-Sep-20 A | 4 | 0 | 3 | 100% |  | Completed
ER6650LT | W226 | W226.A9940 | HYA Fuel Handling Essential Safety Case | 2020-09-02 | 2020-09-07 | Supplier Update and Issue Update to Failed Fuel EAN | 02-Sep-20 A | 07-Sep-20 A | 4 | 0 | 3 | 100% |  | Completed
ER6371LT | W202 | W202.A2560 | HRA Reactors Shutdown Essential Safety Cases | 2020-07-20 | 2020-07-31 | TSA Address Comments on TR'd Fault Schedule Review (Plant Base Faults and Hazards) Draft Report - (HRA) | 02-Sep-20 A | 15-Sep-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.A3480 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-29 | 2020-10-12 | Address Comments on Reviewed Worker Dose Report | 02-Sep-20 A | 15-Oct-20 A | 10 | 0 | 32 | 100% |  | Completed
ER6378LT | W222 | W222.A26760 | HRA Fuel Handling Essential Safety Case | 2020-09-02 | 2020-09-11 | Draft Fuel Route Operational Sequence/Process for Defuelling EAN (REV 001) | 02-Sep-20 A | 11-Sep-20 A | 8 | 0 | 8 | 100% |  | Completed
ER6378LT | W222 | W222.A26500 | HRA Fuel Handling Essential Safety Case | 2020-09-02 | 2021-04-01 | Draft LVDT Weight Sensing System matters arising from Review of HH1 FM Protection | 02-Sep-20 A | 01-Apr-21 A | 10 | 0 | 149 | 100% |  | Completed
ER6378LT | W222 | W222.A26420 | HRA Fuel Handling Essential Safety Case | 2020-09-02 | 2020-09-16 | Draft Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection | 02-Sep-20 A | 16-Sep-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6378LT | W222 | W222.A26110 | HRA Fuel Handling Essential Safety Case | 2020-09-02 | 2020-10-09 | Draft HAZOP updates resulting from defuelling process changes (REV 001) | 02-Sep-20 A | 09-Oct-20 A | 15 | 0 | 28 | 100% |  | Completed
ER6378LT | W222 | W222.A24510 | HRA Fuel Handling Essential Safety Case | 2020-09-02 | 2020-10-16 | Draft Review of Interlock Maintenance Review EAN (DRAFT) | 02-Sep-20 A | 16-Oct-20 A | 33 | 0 | 33 | 100% |  | Completed
ER6378LT | W222 | W222.A24230 | HRA Fuel Handling Essential Safety Case | 2020-09-02 | 2020-11-02 | Draft Hazards Review EAN | 02-Sep-20 A | 02-Nov-20 A | 15 | 0 | 44 | 100% |  | Completed
ER6378LT | W222 | W222.A23810 | HRA Fuel Handling Essential Safety Case | 2020-09-02 | 2020-10-02 | Draft Detailed Option Investigation EAN | 02-Sep-20 A | 02-Oct-20 A | 20 | 0 | 23 | 100% |  | Completed
ER6370LT | W201 | A1810 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 5 - Mature Draft | 02-Sep-20 A | 04-Sep-20 A | 3 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | A2760 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 4 - Peer Review 2 | 02-Sep-20 A | 22-Sep-20 A | 7 | 0 | 15 | 100% |  | Completed
ER6650LT | W226 | W226.A23810 | HYA Fuel Handling Essential Safety Case | 2020-09-02 | 2020-10-02 | Draft Detailed Option Investigation EAN | 02-Sep-20 A | 02-Oct-20 A | 20 | 0 | 23 | 100% |  | Completed
ER6650LT | W226 | W226.A24230 | HYA Fuel Handling Essential Safety Case | 2020-09-02 | 2020-11-02 | Draft Hazards Review EAN | 02-Sep-20 A | 02-Nov-20 A | 15 | 0 | 44 | 100% |  | Completed
ER6650LT | W226 | W226.A24510 | HYA Fuel Handling Essential Safety Case | 2020-09-02 | 2020-10-16 | Draft Review of Interlock Maintenance Review EAN (DRAFT) | 02-Sep-20 A | 16-Oct-20 A | 33 | 0 | 33 | 100% |  | Completed
ER6650LT | W226 | W226.A26110 | HYA Fuel Handling Essential Safety Case | 2020-09-02 | 2020-10-09 | Draft HAZOP updates resulting from defuelling process changes (REV 001) | 02-Sep-20 A | 09-Oct-20 A | 15 | 0 | 28 | 100% |  | Completed
ER6650LT | W226 | W226.A26420 | HYA Fuel Handling Essential Safety Case | 2020-09-02 | 2020-09-16 | Draft Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection | 02-Sep-20 A | 16-Sep-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | W226.A26500 | HYA Fuel Handling Essential Safety Case | 2020-09-02 | 2021-04-01 | Draft LVDT Weight Sensing System matters arising from Review of HH1 FM Protection | 02-Sep-20 A | 01-Apr-21 A | 10 | 0 | 149 | 100% |  | Completed
ER6650LT | W226 | W226.A26760 | HYA Fuel Handling Essential Safety Case | 2020-09-02 | 2020-09-11 | Draft Fuel Route Operational Sequence/Process for Defuelling EAN (REV 001) | 02-Sep-20 A | 11-Sep-20 A | 8 | 0 | 8 | 100% |  | Completed
ER6371LT | W202 | W202.A6020 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-03 | 2020-09-09 | <NEW SCOPE CR220> Panther Sensitivity Studies - Supplier prepare and issue Offer | 03-Sep-20 A | 09-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A6320 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-03 | 2020-09-09 | <NEW SCOPE CR220> Consequences EAN - Supplier prepare and issue Offer | 03-Sep-20 A | 09-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A6810 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-03 | 2020-09-09 | <NEW SCOPE CR220> Specified Flows - Supplier prepare and issue Offer | 03-Sep-20 A | 09-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A6960 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-03 | 2020-09-09 | <NEW SCOPE CR220> Determination of Cliff Edge - Supplier prepare and issue Offer | 03-Sep-20 A | 09-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A6020 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-03 | 2020-09-09 | <NEW SCOPE CR 221> Panther Sensitivity Studies - Supplier prepare and issue Offer | 03-Sep-20 A | 09-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A6320 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-03 | 2020-09-09 | <NEW SCOPE CR 221> Consequences EAN - Supplier prepare and issue Offer | 03-Sep-20 A | 09-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A6810 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-03 | 2020-09-09 | <NEW SCOPE CR 221> Specified Flows - Supplier prepare and issue Offer | 03-Sep-20 A | 09-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A6960 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-03 | 2020-09-09 | <NEW SCOPE CR 221> Determination of Cliff Edge - Supplier prepare and issue Offer | 03-Sep-20 A | 09-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17660 | HNB Reactors Shutdown Essential Safety Cases |  |  | >>>OUTGOING ENABLER (W283) PVCW Head Document Complete | 07-Sep-20 A | 07-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A2600 | HNB Reactors Shutdown Essential Safety Cases |  |  | Appendix E – Detailed Description of Changes to Documentation - CO and co-author review | 07-Sep-20 A | 08-Sep-20 A | 2 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | A2690 | HNB Reactors Shutdown Essential Safety Cases |  |  | Summary - Early Draft | 07-Sep-20 A | 18-Sep-20 A | 5 | 0 | 10 | 100% |  | Completed
ER6378LT | W222 | W222.A9950 | HRA Fuel Handling Essential Safety Case | 2020-09-08 | 2020-09-09 | Complete TR Form and Upload Update to Failed Fuel EAN to CDMS | 08-Sep-20 A | 09-Sep-20 A | 2 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A9950 | HYA Fuel Handling Essential Safety Case | 2020-09-08 | 2020-09-09 | Complete TR Form and Upload Update to Failed Fuel EAN to CDMS | 08-Sep-20 A | 09-Sep-20 A | 2 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A23050 | HRA Fuel Handling Essential Safety Case | 2020-09-08 | 2020-09-08 | Verify Breached PVCW Assessmen and Issue EAN for Technical Review | 08-Sep-20 A | 08-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1100 | HNB Enhanced Defuelling Safety Cases | 2020-09-08 | 2020-09-14 | IRM Paper stakeholder sign off | 08-Sep-20 A | 14-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A23050 | HYA Fuel Handling Essential Safety Case | 2020-09-08 | 2020-09-08 | Verify Breached PVCW Assessmen and Issue EAN for Technical Review | 08-Sep-20 A | 08-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A9960 | HRA Fuel Handling Essential Safety Case |  | 2020-09-09 | Update to Failed Fuel EAN Available | 09-Sep-20 A | 09-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A9960 | HYA Fuel Handling Essential Safety Case |  | 2020-09-09 | Update to Failed Fuel EAN Available | 09-Sep-20 A | 09-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A23060 | HRA Fuel Handling Essential Safety Case | 2020-09-09 | 2020-09-10 | Technical Review of Breached PVCW Assessmen EAN | 09-Sep-20 A | 10-Sep-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | A2610 | HNB Reactors Shutdown Essential Safety Cases |  |  | Appendix E – Detailed Description of Changes to Documentation - Mature Draft | 09-Sep-20 A | 10-Sep-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | W226.A23060 | HYA Fuel Handling Essential Safety Case | 2020-09-09 | 2020-09-10 | Technical Review of Breached PVCW Assessmen EAN | 09-Sep-20 A | 10-Sep-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A2750 | HRA Reactors Shutdown Essential Safety Cases | 2020-08-04 | 2020-09-01 | Prepare Shutdown Margin Head Document | 10-Sep-20 A | 09-Oct-20 A | 20 | 0 | 21 | 100% |  | Completed
ER6371LT | W202 | W202.A2740 | HRA Reactors Shutdown Essential Safety Cases | 2020-08-04 | 2020-10-27 | Shutdown Margin Head Document Summary | 10-Sep-20 A | 20-Aug-21 A | 198 | 0 | 240 | 100% |  | Completed
ER6661LT | W206 | W206.A2750 | HYA Reactors Shutdown Essential Safety Cases | 2020-08-04 | 2020-09-01 | Prepare Shutdown Margin Head Document | 10-Sep-20 A | 09-Oct-20 A | 20 | 0 | 21 | 100% |  | Completed
ER6661LT | W206 | W206.A2740 | HYA Reactors Shutdown Essential Safety Cases | 2020-08-04 | 2021-05-17 | Shutdown Margin Head Document Summary | 10-Sep-20 A | 20-Aug-21 A | 198 | 0 | 240 | 100% |  | Completed
ER6371LT | W202 | W202.A2770 | HRA Reactors Shutdown Essential Safety Cases | 2020-08-06 | 2020-08-12 | Summary of Compliance with NSPs - Draft and issue RFS | 10-Sep-20 A | 01-Oct-20 A | 5 | 0 | 15 | 100% |  | Completed
ER6371LT | W202 | W202.A2760 | HRA Reactors Shutdown Essential Safety Cases | 2020-08-06 | 2020-09-18 | RFS - Summary of Compliance with NSPs Summary | 10-Sep-20 A | 08-Oct-20 A | 44 | 0 | 21 | 100% |  | Completed
ER6661LT | W206 | W206.A2770 | HYA Reactors Shutdown Essential Safety Cases | 2020-08-06 | 2020-08-12 | Summary of Compliance with NSPs - Draft and issue RFS | 10-Sep-20 A | 01-Oct-20 A | 5 | 0 | 15 | 100% |  | Completed
ER6661LT | W206 | W206.A2760 | HYA Reactors Shutdown Essential Safety Cases | 2020-08-06 | 2020-09-18 | RFS - Summary of Compliance with NSPs Summary | 10-Sep-20 A | 08-Oct-20 A | 44 | 0 | 21 | 100% |  | Completed
ER6371LT | W202 | W202.A6030 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-10 | 2020-09-10 | <NEW SCOPE CR220> Panther Sensitivity Studies - Review Offer, prepare and issue CI | 10-Sep-20 A | 10-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A6330 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-10 | 2020-09-10 | <NEW SCOPE CR220> Consequences EAN - Review Offer, prepare and issue CI | 10-Sep-20 A | 10-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A6820 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-10 | 2020-09-10 | <NEW SCOPE CR220> Specified Flows - Review Offer, prepare and issue CI | 10-Sep-20 A | 10-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A6970 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-10 | 2020-09-10 | <NEW SCOPE CR220> Determination of Cliff Edge - Review Offer, prepare and issue CI | 10-Sep-20 A | 10-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A6030 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-10 | 2020-09-10 | <NEW SCOPE CR 221> Panther Sensitivity Studies - Review Offer, prepare and issue CI | 10-Sep-20 A | 10-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A6330 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-10 | 2020-09-10 | <NEW SCOPE CR 221> Consequences EAN - Review Offer, prepare and issue CI | 10-Sep-20 A | 10-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A6820 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-10 | 2020-09-10 | <NEW SCOPE CR 221> Specified Flows - Review Offer, prepare and issue CI | 10-Sep-20 A | 10-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A6970 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-10 | 2020-09-10 | <NEW SCOPE CR 221> Determination of Cliff Edge - Review Offer, prepare and issue CI | 10-Sep-20 A | 10-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17650 | HNB Reactors Shutdown Essential Safety Cases |  |  | Core Cooling Head Document Draft Report - Second round comments/customer review | 11-Sep-20 A | 14-Sep-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | W222.A24190 | HRA Fuel Handling Essential Safety Case | 2020-09-11 | 2020-09-17 | Supplier Update and Issue Review of Hazop Study of Defuelling Process EAN (REV 000) | 11-Sep-20 A | 17-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A23070 | HRA Fuel Handling Essential Safety Case | 2020-09-11 | 2020-09-11 | Supplier Update and Issue Breached PVCW Assessmen EAN | 11-Sep-20 A | 11-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | A2620 | HNB Reactors Shutdown Essential Safety Cases |  |  | Appendix E – Detailed Description of Changes to Documentation - Peer Review | 11-Sep-20 A | 14-Sep-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A6040 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-11 | 2020-09-17 | <NEW SCOPE CR220> Panther Sensitivity Studies - Supplier mobilisation time | 11-Sep-20 A | 17-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A6340 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-11 | 2020-09-15 | <NEW SCOPE CR220> Consequences EAN - Supplier mobilisation time | 11-Sep-20 A | 15-Sep-20 A | 3 | 0 | 3 | 100% |  | Completed
ER6371LT | W202 | W202.A6830 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-11 | 2020-09-17 | <NEW SCOPE CR220> Specified Flows - Supplier mobilisation time | 11-Sep-20 A | 17-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A6980 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-11 | 2020-09-17 | <NEW SCOPE CR220> Determination of Cliff Edge - Supplier mobilisation time | 11-Sep-20 A | 17-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A6040 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-11 | 2020-09-17 | <NEW SCOPE CR 221> Panther Sensitivity Studies - Supplier mobilisation time | 11-Sep-20 A | 17-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A6340 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-11 | 2020-09-15 | <NEW SCOPE CR 221> Consequences EAN - Supplier mobilisation time | 11-Sep-20 A | 15-Sep-20 A | 3 | 0 | 3 | 100% |  | Completed
ER6661LT | W206 | W206.A6830 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-11 | 2020-09-17 | <NEW SCOPE CR 221> Specified Flows - Supplier mobilisation time | 11-Sep-20 A | 17-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A6980 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-11 | 2020-09-17 | <NEW SCOPE CR 221> Determination of Cliff Edge - Supplier mobilisation time | 11-Sep-20 A | 17-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A23070 | HYA Fuel Handling Essential Safety Case | 2020-09-11 | 2020-09-11 | Supplier Update and Issue Breached PVCW Assessmen EAN | 11-Sep-20 A | 11-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A24190 | HYA Fuel Handling Essential Safety Case | 2020-09-11 | 2020-09-17 | Supplier Update and Issue Review of Hazop Study of Defuelling Process EAN (REV 000) | 11-Sep-20 A | 17-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8630 | HNB Reactors Shutdown Essential Safety Cases |  |  | Containment Head Document - Final sign-off of verification | 14-Sep-20 A | 14-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A26770 | HRA Fuel Handling Essential Safety Case | 2020-09-14 | 2020-10-15 | Verify Fuel Route Operational Sequence/Process for Defuelling EAN and Issue for Technical Review (REV 001) | 14-Sep-20 A | 15-Oct-20 A | 5 | 0 | 24 | 100% |  | Completed
ER6378LT | W222 | W222.A23080 | HRA Fuel Handling Essential Safety Case | 2020-09-14 | 2020-09-18 | Complete TR Form and Upload Breached PVCW Assessmen EAN to CDMS | 14-Sep-20 A | 18-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A11500 | HRA Fuel Handling Essential Safety Case | 2020-09-14 | 2020-09-18 | Supplier Update and Issue HF Assessment of Fuel Free Verification EAN (System) | 14-Sep-20 A | 18-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | A1160 | HNB Reactors Shutdown Essential Safety Cases |  |  | 10 – Conclusions - Summary | 14-Sep-20 A | 09-Oct-20 A | 20 | 0 | 20 | 100% |  | Completed
ER6370LT | W201 | A1900 | HNB Reactors Shutdown Essential Safety Cases |  |  | QA - CO and co-author review | 14-Sep-20 A | 16-Sep-20 A | 3 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | A1970 | HNB Reactors Shutdown Essential Safety Cases |  |  | Implementation Programme - Peer Review | 14-Sep-20 A | 09-Oct-20 A | 1 | 0 | 19 | 100% |  | Completed
ER6370LT | W201 | A2040 | HNB Reactors Shutdown Essential Safety Cases |  |  | Conclusions - Early Draft | 14-Sep-20 A | 25-Sep-20 A | 5 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | W226.A11500 | HYA Fuel Handling Essential Safety Case | 2020-09-14 | 2020-09-18 | Supplier Update and Issue HF Assessment of Fuel Free Verification EAN (System) | 14-Sep-20 A | 18-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A23080 | HYA Fuel Handling Essential Safety Case | 2020-09-14 | 2020-09-18 | Complete TR Form and Upload Breached PVCW Assessmen EAN to CDMS | 14-Sep-20 A | 18-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A26770 | HYA Fuel Handling Essential Safety Case | 2020-09-14 | 2020-10-15 | Verify Fuel Route Operational Sequence/Process for Defuelling EAN and Issue for Technical Review (REV 001) | 14-Sep-20 A | 15-Oct-20 A | 5 | 0 | 24 | 100% |  | Completed
ER6371LT | W202 | W202.A2540 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-07-17 | Issue Seismic Assessment of FPU within Reactor Report to EDF Review. | 14-Sep-20 A | 14-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2540 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-07-17 | Issue Seismic Assessment of FPU within Reactor Report to EDF Review. | 14-Sep-20 A | 14-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2930 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-08-14 | Fault Schedule Review (Plant Base Faults and Hazards) Report Completed - (HYA) | 14-Sep-20 A | 14-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A27140 | HRA Fuel Handling Essential Safety Case |  | 2020-09-15 | >>>INCOMING ENABLER (W202.A2206170) Confirm Requirements for Core Cooling Analysis | 15-Sep-20 A | 15-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A27150 | HRA Fuel Handling Essential Safety Case |  | 2020-09-15 | >>>MIRROR OF INCOMING ENABLER (W202) Confirm Requirements for Core Cooling Analysis | 15-Sep-20 A | 15-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206170 | HRA Reactors Shutdown Essential Safety Cases |  |  | >>>OUTGOING ENABLER (W222.A27140) Confirm Requirements for Core Cooling Analysis | 15-Sep-20 A | 15-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A27160 | HRA Fuel Handling Essential Safety Case |  | 2020-09-15 | INTERFACE MILESTONE - (W202) Confirm Requirements for Core Cooling Analysis | 15-Sep-20 A | 15-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27160 | HYA Fuel Handling Essential Safety Case |  | 2020-09-15 | INTERFACE MILESTONE - (W202) Confirm Requirements for Core Cooling Analysis | 15-Sep-20 A | 15-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27150 | HYA Fuel Handling Essential Safety Case |  | 2020-09-15 | >>>MIRROR OF INCOMING ENABLER (W206) Confirm Requirements for Core Cooling Analysis | 15-Sep-20 A | 15-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27140 | HYA Fuel Handling Essential Safety Case |  | 2020-09-15 | >>>INCOMING ENABLER (W206) Confirm Requirements for Core Cooling Analysis | 15-Sep-20 A | 15-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W226.A2206165 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-09-01 | >>>OUTGOING ENABLER (W226) Confirm Requirements for Core Cooling Analysis | 15-Sep-20 A | 15-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3510 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-06 | 2020-10-12 | Reactor Internals and Structural Integrity during Defuelling - Review Offer, prepare and issue CI | 15-Sep-20 A | 21-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A2550 | HRA Reactors Shutdown Essential Safety Cases | 2020-07-20 | 2020-07-31 | Seismic Assessment of FPU within Reactor Report Reviewed by EDF SQEP | 15-Sep-20 A | 28-Sep-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.A3510 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-06 | 2020-10-12 | Reactor Internals and Structural Integrity during Defuelling - Review Offer, prepare and issue CI | 15-Sep-20 A | 21-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A2550 | HYA Reactors Shutdown Essential Safety Cases | 2020-07-20 | 2020-07-31 | Seismic Assessment of FPU within Reactor Report Reviewed by EDF SQEP | 15-Sep-20 A | 28-Sep-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4700 | HNB Reactors Shutdown Essential Safety Cases |  |  | Core Cooling Head Document Draft Report - Resolution Meeting | 15-Sep-20 A | 15-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | A2630 | HNB Reactors Shutdown Essential Safety Cases |  |  | Appendix E – Detailed Description of Changes to Documentation - Draft Complete | 15-Sep-20 A | 15-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A8570 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-04-16 | Containment Head Document Report Completed | 15-Sep-20 A | 15-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2680 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-07-31 | TSA Issue Final Fault Schedule Review (Plant Base Faults and Hazards) Report - (HRA) | 15-Sep-20 A | 15-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A44590 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-07-20 | Confirm Requirements for Core Cooling Analysis | 15-Sep-20 A | 15-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A44590 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-07-20 | Confirm Requirements for Core Cooling Analysis | 15-Sep-20 A | 15-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4720 | HNB Reactors Shutdown Essential Safety Cases |  |  | Core Cooling Head Document Report - HOLD POINT - REVIEW COMMENTS AND RE-FORECAST | 15-Sep-20 A | 15-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2700 | HRA Reactors Shutdown Essential Safety Cases | 2020-08-03 | 2020-08-14 | Fault Schedule Review (Plant Base Faults and Hazards) Report TR Completed and uploaded to CDMS - (HRA) | 16-Sep-20 A | 29-Sep-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | W202.A3270 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-16 | 2020-10-13 | Review of HHB LSD Strategy Deliverable | 16-Sep-20 A | 16-Oct-20 A | 20 | 0 | 22 | 100% |  | Completed
ER6661LT | W206 | W206.A3270 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-16 | 2020-10-13 | Review of HHB LSD Strategy Deliverable | 16-Sep-20 A | 16-Oct-20 A | 20 | 0 | 22 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4710 | HNB Reactors Shutdown Essential Safety Cases |  |  | Core Cooling Head Document Draft Report - Author Update Draft | 16-Sep-20 A | 24-Sep-20 A | 5 | 0 | 6 | 100% |  | Completed
ER6378LT | W222 | W222.A26430 | HRA Fuel Handling Essential Safety Case | 2020-09-16 | 2020-10-12 | Verify Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection & Issue for Technical Review | 16-Sep-20 A | 12-Oct-20 A | 5 | 0 | 18 | 100% |  | Completed
ER6371LT | W202 | W202.A6350 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-16 | 2020-09-16 | <NEW SCOPE CR220> Consequences EAN - Pre Job Brief | 16-Sep-20 A | 16-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A6350 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-16 | 2020-09-16 | <NEW SCOPE CR 221> Consequences EAN - Pre Job Brief | 16-Sep-20 A | 16-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A26430 | HYA Fuel Handling Essential Safety Case | 2020-09-16 | 2020-10-12 | Verify Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection & Issue for Technical Review | 16-Sep-20 A | 12-Oct-20 A | 5 | 0 | 18 | 100% |  | Completed
ER6378LT | W222 | W222.A23700 | HRA Fuel Handling Essential Safety Case | 2020-09-17 | 2020-09-23 | Supplier Update and Issue Confirm Acceptability of CSP Pillars EAN | 17-Sep-20 A | 23-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | A1910 | HNB Reactors Shutdown Essential Safety Cases |  |  | QA - Mature Draft | 17-Sep-20 A | 18-Sep-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | W226.A23700 | HYA Fuel Handling Essential Safety Case | 2020-09-17 | 2020-09-23 | Supplier Update and Issue Confirm Acceptability of CSP Pillars EAN | 17-Sep-20 A | 23-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A6050 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-18 | 2020-09-18 | <NEW SCOPE CR220> Panther Sensitivity Studies - Pre Job Brief | 18-Sep-20 A | 18-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A6840 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-18 | 2020-09-18 | <NEW SCOPE CR220> Specified Flows - Pre Job Brief | 18-Sep-20 A | 18-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A6990 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-18 | 2020-09-18 | <NEW SCOPE CR220> Determination of Cliff Edge - Pre Job Brief | 18-Sep-20 A | 18-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A6050 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-18 | 2020-09-18 | <NEW SCOPE CR 221> Panther Sensitivity Studies - Pre Job Brief | 18-Sep-20 A | 18-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A6840 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-18 | 2020-09-18 | <NEW SCOPE CR 221> Specified Flows - Pre Job Brief | 18-Sep-20 A | 18-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A6990 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-18 | 2020-09-18 | <NEW SCOPE CR 221> Determination of Cliff Edge - Pre Job Brief | 18-Sep-20 A | 18-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A23090 | HRA Fuel Handling Essential Safety Case |  | 2020-09-18 | Criticality Assessment for Breached PVCW Assessmen EAN Available | 18-Sep-20 A | 18-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A23090 | HYA Fuel Handling Essential Safety Case |  | 2020-09-18 | Criticality Assessment for Breached PVCW Assessmen EAN Available | 18-Sep-20 A | 18-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A23420 | HRA Fuel Handling Essential Safety Case | 2020-09-21 | 2021-01-05 | Supplier Update and Issue CSP Model and Static Analysis EAN | 21-Sep-20 A | 05-Jan-21 A | 5 | 0 | 73 | 100% |  | Completed
ER6378LT | W222 | W222.A11510 | HRA Fuel Handling Essential Safety Case | 2020-09-21 | 2020-10-07 | Complete TR Form and Upload HF Assessment of Fuel Free Verification EAN to CDMS (System) | 21-Sep-20 A | 07-Oct-20 A | 5 | 0 | 12 | 100% |  | Completed
ER6370LT | W201 | A1820 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 5 - Peer Review | 21-Sep-20 A | 25-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | A1850 | HNB Reactors Shutdown Essential Safety Cases |  |  | SC Margins, Judgements and Challenges - CO and co-author review | 21-Sep-20 A | 23-Sep-20 A | 3 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | A1920 | HNB Reactors Shutdown Essential Safety Cases |  |  | QA - Peer Review | 21-Sep-20 A | 09-Oct-20 A | 5 | 0 | 15 | 100% |  | Completed
ER6370LT | W201 | A2030 | HNB Reactors Shutdown Essential Safety Cases |  |  | INSA - Draft Complete | 21-Sep-20 A | 25-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | A2130 | HNB Reactors Shutdown Essential Safety Cases |  |  | NSC Request for Consideration and Advice - Draft Complete | 21-Sep-20 A | 02-Oct-20 A | 5 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | A2170 | HNB Reactors Shutdown Essential Safety Cases |  |  | Appendix – Description of Existing Safety Case - Peer Review | 21-Sep-20 A | 23-Sep-20 A | 3 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | A2200 | HNB Reactors Shutdown Essential Safety Cases |  |  | Appendix – OPEX - CO and co-author review | 21-Sep-20 A | 25-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | A2700 | HNB Reactors Shutdown Essential Safety Cases |  |  | Summary - CO and co-author review | 21-Sep-20 A | 25-Sep-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A6070 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-21 | 2020-10-16 | <NEW SCOPE CR220> Prepare Panther Sensitivity Studies Draft Report | 21-Sep-20 A | 16-Oct-20 A | 20 | 0 | 20 | 100% |  | Completed
ER6371LT | W202 | W202.A6060 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-21 | 2020-12-04 | <NEW SCOPE CR220> Panther Sensitivity Studies Summary | 21-Sep-20 A | 15-Jan-21 A | 82 | 0 | 82 | 100% |  | Completed
ER6371LT | W202 | W202.A6710 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-21 | 2020-10-16 | <NEW SCOPE CR220> Prepare Specified Flows Draft Report | 21-Sep-20 A | 20-Nov-20 A | 20 | 0 | 45 | 100% |  | Completed
ER6371LT | W202 | W202.A6700 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-21 | 2020-12-11 | <NEW SCOPE CR220> Specified Flows Summary | 21-Sep-20 A | 12-Feb-21 A | 102 | 0 | 102 | 100% |  | Completed
ER6371LT | W202 | W202.A6860 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-21 | 2020-10-16 | <NEW SCOPE CR220> Prepare Determination of Cliff Edge Draft Report | 21-Sep-20 A | 23-Oct-20 A | 20 | 0 | 24 | 100% |  | Completed
ER6371LT | W202 | W202.A6850 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-21 | 2020-12-11 | <NEW SCOPE CR220> Determination of Cliff Edge Summary | 21-Sep-20 A | 20-Jan-21 A | 85 | 0 | 85 | 100% |  | Completed
ER6661LT | W206 | W206.A6070 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-21 | 2020-10-16 | <NEW SCOPE CR 221> Prepare Panther Sensitivity Studies Draft Report | 21-Sep-20 A | 16-Oct-20 A | 20 | 0 | 20 | 100% |  | Completed
ER6661LT | W206 | W206.A6060 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-21 | 2021-01-15 | <NEW SCOPE CR 221> Panther Sensitivity Studies Summary | 21-Sep-20 A | 15-Jan-21 A | 82 | 0 | 82 | 100% |  | Completed
ER6661LT | W206 | W206.A6710 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-21 | 2020-10-16 | <NEW SCOPE CR 221> Prepare Specified Flows Draft Report | 21-Sep-20 A | 20-Nov-20 A | 20 | 0 | 45 | 100% |  | Completed
ER6661LT | W206 | W206.A6700 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-21 | 2021-02-12 | <NEW SCOPE CR 221> Specified Flows Summary | 21-Sep-20 A | 12-Feb-21 A | 102 | 0 | 102 | 100% |  | Completed
ER6661LT | W206 | W206.A6860 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-21 | 2020-10-16 | <NEW SCOPE CR 221> Prepare Determination of Cliff Edge Draft Report | 21-Sep-20 A | 23-Oct-20 A | 20 | 0 | 24 | 100% |  | Completed
ER6661LT | W206 | W206.A6850 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-21 | 2021-01-20 | <NEW SCOPE CR 221> Determination of Cliff Edge Summary | 21-Sep-20 A | 20-Jan-21 A | 85 | 0 | 85 | 100% |  | Completed
ER6650LT | W226 | W226.A11510 | HYA Fuel Handling Essential Safety Case | 2020-09-21 | 2020-10-07 | Complete TR Form and Upload HF Assessment of Fuel Free Verification EAN to CDMS (System) | 21-Sep-20 A | 07-Oct-20 A | 5 | 0 | 12 | 100% |  | Completed
ER6650LT | W226 | W226.A23420 | HYA Fuel Handling Essential Safety Case | 2020-09-21 | 2021-01-05 | Supplier Update and Issue CSP Model and Static Analysis EAN | 21-Sep-20 A | 05-Jan-21 A | 5 | 0 | 73 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18270 | HNB Reactors Shutdown Essential Safety Cases | 2020-09-21 | 2020-09-30 | <NEW SCOPE CR 187> - RFS - OPEX/ Literature Review - Draft and issue RFS | 21-Sep-20 A | 30-Sep-20 A | 8 | 0 | 8 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18195 | HNB Reactors Shutdown Essential Safety Cases | 2020-09-21 | 2020-10-29 | <NEW SCOPE CR 187> - RFS - OPEX/ Literature Review Summary | 21-Sep-20 A | 16-Nov-20 A | 41 | 0 | 41 | 100% |  | Completed
ER6371LT | W202 | W202.A3560 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-13 | 2020-10-26 | Reactor Internals and Structural Integrity during Defuelling - Supplier mobilisation time | 22-Sep-20 A | 30-Sep-20 A | 10 | 0 | 6 | 100% |  | Completed
ER6661LT | W206 | W206.A3560 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-13 | 2020-10-26 | Reactor Internals and Structural Integrity during Defuelling - Supplier mobilisation time | 22-Sep-20 A | 30-Sep-20 A | 10 | 0 | 6 | 100% |  | Completed
ER6370LT | W201 | A2050 | HNB Reactors Shutdown Essential Safety Cases |  |  | Conclusions - CO and co-author review | 22-Sep-20 A | 02-Oct-20 A | 4 | 0 | 9 | 100% |  | Completed
ER6378LT | W222 | W222.A26990 | HRA Fuel Handling Essential Safety Case | 2020-09-22 | 2020-09-22 | Hold Risk Workshop | 22-Sep-20 A | 22-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A26990 | HYA Fuel Handling Essential Safety Case | 2020-09-22 | 2020-09-22 | Hold Risk Workshop | 22-Sep-20 A | 22-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A1780 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 4 - Draft Complete | 23-Sep-20 A | 25-Sep-20 A | 3 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17630 | HNB Reactors Shutdown Essential Safety Cases |  |  | Core Cooling Head Document Report - Verifiers sign-off and provide verification statement | 24-Sep-20 A | 07-Oct-20 A | 3 | 0 | 9 | 100% |  | Completed
ER6378LT | W222 | W222.A11650 | HRA Fuel Handling Essential Safety Case |  | 2020-09-24 | Human Factors Integration Plan EAN Available (REV 000) | 24-Sep-20 A | 24-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A11650 | HYA Fuel Handling Essential Safety Case |  | 2020-09-24 | Human Factors Integration Plan EAN Available (REV 000) | 24-Sep-20 A | 24-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A24200 | HRA Fuel Handling Essential Safety Case | 2020-09-24 | 2020-10-09 | Complete TR Form and Upload Hazop Study of Defuelling Process EAN to CDMS (REV 000) | 24-Sep-20 A | 09-Oct-20 A | 5 | 0 | 11 | 100% |  | Completed
ER6378LT | W222 | W222.A23710 | HRA Fuel Handling Essential Safety Case | 2020-09-24 | 2020-12-01 | Complete and Upload Confirm Acceptability of CSP Pillars EAN to CDMS | 24-Sep-20 A | 01-Dec-20 A | 5 | 0 | 49 | 100% |  | Completed
ER6650LT | W226 | W226.A23710 | HYA Fuel Handling Essential Safety Case | 2020-09-24 | 2020-12-01 | Complete TR Form and Upload Confirm Acceptability of CSP Pillars EAN to CDMS | 24-Sep-20 A | 01-Dec-20 A | 5 | 0 | 49 | 100% |  | Completed
ER6650LT | W226 | W226.A24200 | HYA Fuel Handling Essential Safety Case | 2020-09-24 | 2020-10-09 | Complete TR Form and Upload Hazop Study of Defuelling Process EAN to CDMS (REV 000) | 24-Sep-20 A | 09-Oct-20 A | 5 | 0 | 11 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18150 | HNB Reactors Shutdown Essential Safety Cases |  |  | Prepare for Verification Pre-job Brief | 25-Sep-20 A | 30-Sep-20 A | 4 | 0 | 4 | 100% |  | Completed
ER6378LT | W222 | W222.A25990 | HRA Fuel Handling Essential Safety Case | 2020-09-28 | 2021-05-28 | Complex FEA (Dynamic R3 Analysis) ##(Cost Summary)## (C5) (NEW) | 28-Sep-20 A | 28-May-21 A | 188 | 0 | 169 | 100% |  | Completed
ER6378LT | W222 | W222.A23450 | HRA Fuel Handling Essential Safety Case | 2020-09-28 | 2020-09-28 | Pre Job Brief for Complex FEA (Dynamic R3 Analysis) EAN | 28-Sep-20 A | 28-Sep-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A1860 | HNB Reactors Shutdown Essential Safety Cases |  |  | SC Margins, Judgements and Challenges - Mature Draft | 28-Sep-20 A | 30-Sep-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | W222.A26900 | HRA Fuel Handling Essential Safety Case | 2020-09-28 | 2020-10-05 | PRC Members Review Scheme Documentation | 28-Sep-20 A | 05-Oct-20 A | 5 | 0 | 6 | 100% |  | Completed
ER6650LT | W226 | W226.A23450 | HYA Fuel Handling Essential Safety Case | 2020-09-28 | 2020-09-29 | Pre Job Brief for Complex FEA (Dynamic R3 Analysis) EAN | 28-Sep-20 A | 29-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A25990 | HYA Fuel Handling Essential Safety Case | 2020-09-28 | 2021-05-28 | Complex FEA (Dynamic R3 Analysis) ##(Cost Summary)## (C5) (NEW) | 28-Sep-20 A | 28-May-21 A | 188 | 0 | 169 | 100% |  | Completed
ER6370LT | W201 | A2770 | HNB Reactors Shutdown Essential Safety Cases |  |  | Appendix F – TIDYING AND EDITORIAL STUFF, Responding to Station Comments | 28-Sep-20 A | 09-Oct-20 A | 1 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2160 | HNB Reactors Shutdown Essential Safety Cases |  |  | Lead Verifier Familiarisation | 28-Sep-20 A | 09-Oct-20 A | 10 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | A1700 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 3 - CO and co-author review | 28-Sep-20 A | 29-Sep-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | A1830 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 5 - Draft Complete | 28-Sep-20 A | 07-Oct-20 A | 5 | 0 | 8 | 100% |  | Completed
ER6370LT | W201 | A2210 | HNB Reactors Shutdown Essential Safety Cases |  |  | Appendix – OPEX - Mature Draft | 28-Sep-20 A | 30-Sep-20 A | 3 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | A2670 | HNB Reactors Shutdown Essential Safety Cases |  |  | Appendix F – Previous Advice from NSC - Peer Review | 28-Sep-20 A | 30-Sep-20 A | 3 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | A2710 | HNB Reactors Shutdown Essential Safety Cases |  |  | Summary - Mature Draft | 28-Sep-20 A | 30-Sep-20 A | 3 | 0 | 3 | 100% |  | Completed
ER6372LT | W203 | W203.A1130 | HNB Enhanced Defuelling Safety Cases |  | 2020-09-28 | Gate A PRC Paper Submission | 28-Sep-20 A | 28-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A27050 | HRA Fuel Handling Essential Safety Case |  | 2020-09-28 | Issue Scheme Paper to PRC Members | 28-Sep-20 A | 28-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27050 | HYA Fuel Handling Essential Safety Case |  | 2020-09-28 | Issue Scheme Paper to PRC Members | 28-Sep-20 A | 28-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A26900 | HYA Fuel Handling Essential Safety Case | 2020-09-28 | 2020-10-05 | PRC Members Review Scheme Documentation | 28-Sep-20 A | 05-Oct-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A25710 | HRA Fuel Handling Essential Safety Case | 2020-09-29 | 2021-07-14 | Production of Hazard and Interlock Schedule ##(Cost Summary)## ### (C2) | 29-Sep-20 A | 14-Jul-21 A | 205 | 0 | 199 | 100% |  | Completed
ER6378LT | W222 | W222.A25200 | HRA Fuel Handling Essential Safety Case | 2020-09-29 | 2020-09-29 | Pre Job Brief for Hazard and Interlock Schedule (REV 000) EAN | 29-Sep-20 A | 29-Sep-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A23460 | HRA Fuel Handling Essential Safety Case | 2020-09-29 | 2021-04-01 | Draft Complex FEA (Dynamic R3 Analysis) EAN | 29-Sep-20 A | 01-Apr-21 A | 13 | 0 | 130 | 100% |  | Completed
ER6650LT | W226 | W226.A23460 | HYA Fuel Handling Essential Safety Case | 2020-09-29 | 2021-04-01 | Draft Complex FEA (Dynamic R3 Analysis) EAN | 29-Sep-20 A | 01-Apr-21 A | 13 | 0 | 130 | 100% |  | Completed
ER6650LT | W226 | W226.A25200 | HYA Fuel Handling Essential Safety Case | 2020-09-29 | 2020-09-29 | Pre Job Brief for Hazard and Interlock Schedule (REV 000) EAN | 29-Sep-20 A | 29-Sep-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25710 | HYA Fuel Handling Essential Safety Case | 2020-09-29 | 2021-07-14 | Production of Hazard and Interlock Schedule ##(Cost Summary)## ### (C2) | 29-Sep-20 A | 14-Jul-21 A | 205 | 0 | 200 | 100% |  | Completed
ER6371LT | W202 | W202.A2690 | HRA Reactors Shutdown Essential Safety Cases | 2020-08-03 | 2020-08-14 | Address Comments on Reviewed Seismic Assessment of FPU within Reactor Report | 29-Sep-20 A | 26-Oct-20 A | 10 | 0 | 19 | 100% |  | Completed
ER6661LT | W206 | W206.A2690 | HYA Reactors Shutdown Essential Safety Cases | 2020-08-03 | 2020-08-14 | Address Comments on Reviewed Seismic Assessment of FPU within Reactor Report | 29-Sep-20 A | 26-Oct-20 A | 10 | 0 | 19 | 100% |  | Completed
ER6372LT | W203 | W203.A1240 | HNB Enhanced Defuelling Safety Cases | 2020-09-29 | 2020-10-12 | Effect of air admission on reactor containment (Coolant conditions CO2) EAN up Rev - Prepare Draft Report | 29-Sep-20 A | 18-Dec-20 A | 10 | 0 | 59 | 100% |  | Completed
ER6372LT | W203 | W203.A1230 | HNB Enhanced Defuelling Safety Cases | 2020-09-29 | 2020-11-23 | Effect of air admission on reactor containment (Coolant conditions CO2) EAN up Rev - Summary | 29-Sep-20 A | 28-Jun-21 A | 188 | 0 | 188 | 100% |  | Completed
ER6371LT | W202 | W202.A2930 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-08-14 | Fault Schedule Review (Plant Base Faults and Hazards) Report Completed - (HRA) | 29-Sep-20 A | 29-Sep-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A1870 | HNB Reactors Shutdown Essential Safety Cases |  |  | SC Margins, Judgements and Challenges - Peer Review | 30-Sep-20 A | 02-Oct-20 A | 2 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | A1710 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 3 - Mature Draft | 30-Sep-20 A | 02-Oct-20 A | 3 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2170 | HNB Reactors Shutdown Essential Safety Cases |  |  | Verification Pre-job Brief | 30-Sep-20 A | 30-Sep-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A2360 | HRA Reactors Shutdown Essential Safety Cases | 2020-07-02 | 2020-07-15 | HF Risk Assessment Draft Report Verified by TSA | 01-Oct-20 A | 01-Oct-20 A | 10 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2460 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-07-15 | Verified HF Risk Assessment Draft Report Issued to EDF for Technical Review. | 01-Oct-20 A | 01-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2490 | HRA Reactors Shutdown Essential Safety Cases | 2020-07-16 | 2020-07-29 | HF Risk Assessment Draft Report Technically Reviewed by EDF SQEP | 01-Oct-20 A | 01-Oct-20 A | 10 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2670 | HRA Reactors Shutdown Essential Safety Cases | 2020-07-30 | 2020-08-12 | TSA Address Comments on TR'd HF Risk Assessment Draft Report | 01-Oct-20 A | 01-Oct-20 A | 10 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2830 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-08-12 | TSA Issue Final HF Risk Assessment Report | 01-Oct-20 A | 01-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2910 | HRA Reactors Shutdown Essential Safety Cases | 2020-08-13 | 2020-08-26 | HF Risk Assessment Report TR Completed and uploaded to CDMS | 01-Oct-20 A | 01-Oct-20 A | 10 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3090 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-08-26 | HF Risk Assessment Report Completed | 01-Oct-20 A | 01-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2250 | HRA Reactors Shutdown Essential Safety Cases | 2020-06-04 | 2020-08-26 | HF Risk Assessment Summary | 01-Oct-20 A | 02-Oct-20 A | 60 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A2890 | HRA Reactors Shutdown Essential Safety Cases | 2020-08-13 | 2020-08-26 | Summary of Compliance with NSPs - Supplier prepare and issue Offer | 01-Oct-20 A | 01-Oct-20 A | 10 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3100 | HRA Reactors Shutdown Essential Safety Cases | 2020-08-27 | 2020-09-03 | Summary of Compliance with NSPs - Review Offer, prepare and issue CI | 01-Oct-20 A | 01-Oct-20 A | 5 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3170 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-04 | 2020-09-17 | Summary of Compliance with NSPs - Supplier mobilisation time | 01-Oct-20 A | 01-Oct-20 A | 10 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2360 | HYA Reactors Shutdown Essential Safety Cases | 2020-07-02 | 2020-07-15 | HF Risk Assessment Draft Report Verified by TSA | 01-Oct-20 A | 01-Oct-20 A | 10 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2460 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-07-15 | Verified HF Risk Assessment Draft Report Issued to EDF for Technical Review. | 01-Oct-20 A | 01-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2490 | HYA Reactors Shutdown Essential Safety Cases | 2020-07-16 | 2020-07-29 | HF Risk Assessment Draft Report Technically Reviewed by EDF SQEP | 01-Oct-20 A | 01-Oct-20 A | 10 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2670 | HYA Reactors Shutdown Essential Safety Cases | 2020-07-30 | 2020-08-12 | TSA Address Comments on TR'd HF Risk Assessment Draft Report | 01-Oct-20 A | 01-Oct-20 A | 10 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2830 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-08-12 | TSA Issue Final HF Risk Assessment Report | 01-Oct-20 A | 01-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2910 | HYA Reactors Shutdown Essential Safety Cases | 2020-08-13 | 2020-08-26 | HF Risk Assessment Report TR Completed and uploaded to CDMS | 01-Oct-20 A | 01-Oct-20 A | 10 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2250 | HYA Reactors Shutdown Essential Safety Cases | 2020-06-04 | 2020-08-26 | HF Risk Assessment Summary | 01-Oct-20 A | 02-Oct-20 A | 60 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2890 | HYA Reactors Shutdown Essential Safety Cases | 2020-08-13 | 2020-08-26 | Summary of Compliance with NSPs - Supplier prepare and issue Offer | 01-Oct-20 A | 01-Oct-20 A | 10 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3100 | HYA Reactors Shutdown Essential Safety Cases | 2020-08-27 | 2020-09-03 | Summary of Compliance with NSPs - Review Offer, prepare and issue CI | 01-Oct-20 A | 01-Oct-20 A | 5 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3170 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-04 | 2020-09-17 | Summary of Compliance with NSPs - Supplier mobilisation time | 01-Oct-20 A | 01-Oct-20 A | 10 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2260 | HRA Reactors Shutdown Essential Safety Cases | 2020-06-04 | 2020-07-01 | Prepare HF Risk Assessment Draft Report | 01-Oct-20 A | 02-Oct-20 A | 20 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A3680 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-27 | 2020-10-27 | Reactor Internals and Structural Integrity during Defuelling - Pre Job Brief | 01-Oct-20 A | 02-Oct-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A3130 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-01 | 2020-09-07 | Containment Head Document - Draft and issue RFS | 01-Oct-20 A | 30-Oct-20 A | 5 | 0 | 21 | 100% |  | Completed
ER6371LT | W202 | W202.A3120 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-01 | 2020-10-13 | RFS - Specification for Pressure Boundary Seals Summary | 01-Oct-20 A | 07-Jan-21 A | 66 | 0 | 67 | 100% |  | Completed
ER6371LT | W202 | W202.A2880 | HRA Reactors Shutdown Essential Safety Cases | 2020-08-13 | 2020-08-19 | Supporting Plant - Draft and issue RFS | 01-Oct-20 A | 07-Oct-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A2870 | HRA Reactors Shutdown Essential Safety Cases | 2020-08-13 | 2020-09-25 | RFS - Supporting Plant Summary | 01-Oct-20 A | 19-Nov-20 A | 33 | 0 | 35 | 100% |  | Completed
ER6371LT | W202 | W202.A3300 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-17 | 2020-09-24 | ALARP Report - Draft and issue RFS | 01-Oct-20 A | 15-Oct-20 A | 11 | 0 | 11 | 100% |  | Completed
ER6371LT | W202 | W202.A3290 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-25 | 2020-10-30 | RFS - ALARP Report Summary | 01-Oct-20 A | 30-Oct-20 A | 37 | 0 | 22 | 100% |  | Completed
ER6661LT | W206 | W206.A2260 | HYA Reactors Shutdown Essential Safety Cases | 2020-06-04 | 2020-07-01 | Prepare HF Risk Assessment Draft Report | 01-Oct-20 A | 02-Oct-20 A | 20 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A3680 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-27 | 2020-10-27 | Reactor Internals and Structural Integrity during Defuelling - Pre Job Brief | 01-Oct-20 A | 02-Oct-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A3130 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-01 | 2020-09-07 | Containment Head Document - Draft and issue RFS | 01-Oct-20 A | 30-Oct-20 A | 5 | 0 | 21 | 100% |  | Completed
ER6661LT | W206 | W206.A3120 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-01 | 2020-10-13 | RFS - Specification for Pressure Boundary Seals Summary | 01-Oct-20 A | 07-Jan-21 A | 74 | 0 | 67 | 100% |  | Completed
ER6661LT | W206 | W206.A2880 | HYA Reactors Shutdown Essential Safety Cases | 2020-08-13 | 2020-08-19 | Supporting Plant - Draft and issue RFS | 01-Oct-20 A | 07-Oct-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A2870 | HYA Reactors Shutdown Essential Safety Cases | 2020-08-13 | 2020-09-25 | RFS - Supporting Plant Summary | 01-Oct-20 A | 19-Nov-20 A | 33 | 0 | 35 | 100% |  | Completed
ER6661LT | W206 | W206.A3300 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-17 | 2020-09-24 | ALARP Report - Draft and issue RFS | 01-Oct-20 A | 15-Oct-20 A | 11 | 0 | 11 | 100% |  | Completed
ER6661LT | W206 | W206.A3290 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-17 | 2020-10-30 | RFS - ALARP Report Summary | 01-Oct-20 A | 30-Oct-20 A | 37 | 0 | 21 | 100% |  | Completed
ER6378LT | W222 | W222.A25690 | HRA Fuel Handling Essential Safety Case | 2020-10-01 | 2021-04-26 | Criticality Assessment for Dropped FPU at Reactor ##(Cost Summary)## ### (C5) | 01-Oct-20 A | 26-Apr-21 A | 160 | 0 | 143 | 100% |  | Completed
ER6378LT | W222 | W222.A25680 | HRA Fuel Handling Essential Safety Case | 2020-10-01 | 2021-04-28 | Adjacent Fuel Assembly Drop Assessment & Associated Radcons ##(Cost Summary)## ### (C5) | 01-Oct-20 A | 28-Apr-21 A | 147 | 0 | 144 | 100% |  | Completed
ER6378LT | W222 | W222.A25340 | HRA Fuel Handling Essential Safety Case | 2020-10-01 | 2020-10-01 | Pre Job Brief for Update to Fault Schedule/PSA (REV 000) EAN | 01-Oct-20 A | 01-Oct-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A9510 | HRA Fuel Handling Essential Safety Case | 2020-10-01 | 2020-10-01 | Pre Job Brief for Criticality Assessment for Dropped FPU at Reactor EAN | 01-Oct-20 A | 01-Oct-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A9770 | HRA Fuel Handling Essential Safety Case | 2020-10-01 | 2020-10-01 | Pre Job Brief for Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN | 01-Oct-20 A | 01-Oct-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | A2220 | HNB Reactors Shutdown Essential Safety Cases |  |  | Appendix – OPEX - Peer Review | 01-Oct-20 A | 02-Oct-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | A2680 | HNB Reactors Shutdown Essential Safety Cases |  |  | Appendix F – Previous Advice from NSC - Draft Complete | 01-Oct-20 A | 02-Oct-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | A2720 | HNB Reactors Shutdown Essential Safety Cases |  |  | Summary - Peer Review | 01-Oct-20 A | 02-Oct-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A6210 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-01 | 2021-01-15 | <NEW SCOPE CR220> PVCW Management - Technical Lead | 01-Oct-20 A | 01-Feb-21 A | 65 | 0 | 84 | 100% |  | Completed
ER6371LT | W202 | W202.A6200 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-01 | 2021-01-15 | <NEW SCOPE CR220> PVCW Management Summary | 01-Oct-20 A | 01-Feb-21 A | 84 | 0 | 84 | 100% |  | Completed
ER6371LT | W202 | W202.A6370 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-01 | 2020-11-13 | <NEW SCOPE CR220> Prepare Consequences EAN Draft Report | 01-Oct-20 A | 26-Oct-20 A | 32 | 0 | 17 | 100% |  | Completed
ER6371LT | W202 | W202.A6360 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-01 | 2021-01-06 | <NEW SCOPE CR220> Consequences EAN Summary | 01-Oct-20 A | 13-Jan-21 A | 67 | 0 | 71 | 100% |  | Completed
ER6371LT | W202 | W202.A6510 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-01 | 2020-11-13 | <NEW SCOPE CR220> Prepare Optioneering EAN Draft Report | 01-Oct-20 A | 02-Nov-20 A | 32 | 0 | 23 | 100% |  | Completed
ER6371LT | W202 | W202.A6500 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-01 | 2021-01-06 | <NEW SCOPE CR220> Optioneering EAN Summary | 01-Oct-20 A | 29-Jan-21 A | 89 | 0 | 83 | 100% |  | Completed
ER6661LT | W206 | W206.A6210 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-01 | 2021-01-15 | <NEW SCOPE CR 221> PVCW Management - Technical Lead | 01-Oct-20 A | 01-Feb-21 A | 74 | 0 | 84 | 100% |  | Completed
ER6661LT | W206 | W206.A6200 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-01 | 2021-01-29 | <NEW SCOPE CR 221> PVCW Management Summary | 01-Oct-20 A | 01-Feb-21 A | 84 | 0 | 84 | 100% |  | Completed
ER6661LT | W206 | W206.A6370 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-01 | 2020-11-13 | <NEW SCOPE CR 221> Prepare Consequences EAN Draft Report | 01-Oct-20 A | 26-Oct-20 A | 32 | 0 | 17 | 100% |  | Completed
ER6661LT | W206 | W206.A6360 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-01 | 2021-01-29 | <NEW SCOPE CR 221> Consequences EAN Summary | 01-Oct-20 A | 13-Jan-21 A | 84 | 0 | 71 | 100% |  | Completed
ER6661LT | W206 | W206.A6510 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-01 | 2020-11-13 | <NEW SCOPE CR 221> Prepare Optioneering EAN Draft Report | 01-Oct-20 A | 02-Nov-20 A | 32 | 0 | 23 | 100% |  | Completed
ER6661LT | W206 | W206.A6500 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-01 | 2021-02-05 | <NEW SCOPE CR 221> Optioneering EAN Summary | 01-Oct-20 A | 29-Jan-21 A | 89 | 0 | 83 | 100% |  | Completed
ER6650LT | W226 | W226.A9770 | HYA Fuel Handling Essential Safety Case | 2020-10-01 | 2020-10-01 | Pre Job Brief for Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN | 01-Oct-20 A | 01-Oct-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A9510 | HYA Fuel Handling Essential Safety Case | 2020-10-01 | 2020-10-01 | Pre Job Brief for Criticality Assessment for Dropped FPU at Reactor EAN | 01-Oct-20 A | 01-Oct-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A25340 | HYA Fuel Handling Essential Safety Case | 2020-10-01 | 2020-10-01 | Pre Job Brief for Update to Fault Schedule/PSA (REV 000) EAN | 01-Oct-20 A | 01-Oct-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A25680 | HYA Fuel Handling Essential Safety Case | 2020-10-01 | 2021-04-28 | Adjacent Fuel Assembly Drop Assessment & Associated Radcons ##(Cost Summary)## ### (C5) | 01-Oct-20 A | 28-Apr-21 A | 147 | 0 | 144 | 100% |  | Completed
ER6650LT | W226 | W226.A25690 | HYA Fuel Handling Essential Safety Case | 2020-10-01 | 2021-04-26 | Criticality Assessment for Dropped FPU at Reactor ##(Cost Summary)## ### (C5) | 01-Oct-20 A | 26-Apr-21 A | 160 | 0 | 143 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18280 | HNB Reactors Shutdown Essential Safety Cases | 2020-10-01 | 2020-10-14 | <NEW SCOPE CR 187> - RFS - OPEX/ Literature Review - Supplier prepare and issue Offer | 01-Oct-20 A | 14-Oct-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6378LT | W222 | W222.A27205 | HRA Fuel Handling Essential Safety Case | 2020-10-01 | 2021-03-02 | Produce H&I Schedules for All Facilities (FM/Ponds etc) | 01-Oct-20 A | 02-Mar-21 A | 1 | 0 | 106 | 100% |  | Completed
ER6650LT | W226 | W226.A27205 | HYA Fuel Handling Essential Safety Case | 2020-10-01 | 2021-03-02 | Produce H&I Schedules for All Facilities | 01-Oct-20 A | 02-Mar-21 A | 1 | 0 | 106 | 100% |  | Completed
ER6371LT | W202 | W202.A3020 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-08-20 | Review of HRA Defuelling Case against the NSPs Report Completed | 02-Oct-20 A | 02-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3070 | HRA Reactors Shutdown Essential Safety Cases | 2020-08-24 | 2020-08-28 | Review of HRA Defuelling Case against the NSPs - PJDB | 02-Oct-20 A | 09-Oct-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A3090 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-08-26 | HF Risk Assessment Report Completed | 02-Oct-20 A | 02-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3020 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-08-20 | Review of HYA Defuelling Case against the NSPs Report Completed | 02-Oct-20 A | 02-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3070 | HYA Reactors Shutdown Essential Safety Cases | 2020-08-24 | 2020-08-28 | Review of HYA Defuelling Case against the NSPs - PJDB | 02-Oct-20 A | 09-Oct-20 A | 6 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A12380 | HYA Fuel Handling Essential Safety Case | 2020-10-02 | 2020-10-08 | Draft Confirm Adequate Capacity for Solid Waste Arisings from Stringer Dismantling EAN | 02-Oct-20 A | 08-Oct-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6371LT | W202 | W202.A3710 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-28 | 2021-01-08 | Prepare Reactor Internals and Structural Integrity during Defuelling Report | 02-Oct-20 A | 27-Nov-20 A | 50 | 0 | 41 | 100% |  | Completed
ER6371LT | W202 | W202.A3700 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-28 | 2021-02-12 | Reactor Internals and Structural Integrity during Defuelling Report Summary | 02-Oct-20 A | 27-Jan-21 A | 88 | 0 | 80 | 100% |  | Completed
ER6661LT | W206 | W206.A3710 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-28 | 2021-01-08 | Prepare Reactor Internals and Structural Integrity during Defuelling Report | 02-Oct-20 A | 27-Nov-20 A | 50 | 0 | 41 | 100% |  | Completed
ER6661LT | W206 | W206.A3700 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-28 | 2021-03-03 | Reactor Internals and Structural Integrity during Defuelling Report Summary | 02-Oct-20 A | 27-Jan-21 A | 88 | 0 | 80 | 100% |  | Completed
ER6378LT | W222 | W222.A9520 | HRA Fuel Handling Essential Safety Case | 2020-10-02 | 2021-04-26 | Draft Criticality Assessment for Dropped FPU at Reactor EAN | 02-Oct-20 A | 26-Apr-21 A | 20 | 0 | 142 | 100% |  | Completed
ER6378LT | W222 | W222.A9780 | HRA Fuel Handling Essential Safety Case | 2020-10-02 | 2020-10-30 | Draft Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN | 02-Oct-20 A | 30-Oct-20 A | 21 | 0 | 21 | 100% |  | Completed
ER6378LT | W222 | W222.A12380 | HRA Fuel Handling Essential Safety Case | 2020-10-02 | 2020-10-08 | Draft Confirm Adequate Capacity for Solid Waste Arisings from Stringer Dismantling EAN | 02-Oct-20 A | 08-Oct-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A9780 | HYA Fuel Handling Essential Safety Case | 2020-10-02 | 2020-10-30 | Draft Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN | 02-Oct-20 A | 30-Oct-20 A | 21 | 0 | 21 | 100% |  | Completed
ER6650LT | W226 | W226.A9520 | HYA Fuel Handling Essential Safety Case | 2020-10-02 | 2021-04-26 | Draft Criticality Assessment for Dropped FPU at Reactor EAN | 02-Oct-20 A | 26-Apr-21 A | 20 | 0 | 142 | 100% |  | Completed
ER6378LT | W222 | W222.A27230 | HRA Fuel Handling Essential Safety Case | 2020-10-02 | 2021-03-30 | PSA Modelling | 02-Oct-20 A | 30-Mar-21 A | 56 | 0 | 124 | 100% |  | Completed
ER6650LT | W226 | W226.A27230 | HYA Fuel Handling Essential Safety Case | 2020-10-02 | 2021-03-30 | PSA Modelling | 02-Oct-20 A | 30-Mar-21 A | 56 | 0 | 124 | 100% |  | Completed
ER6378LT | W222 | W222.A23790 | HRA Fuel Handling Essential Safety Case |  | 2020-10-02 | Shock Absorbers Feasibility Study EAN Available | 02-Oct-20 A | 02-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A23790 | HYA Fuel Handling Essential Safety Case |  | 2020-10-02 | Shock Absorbers Feasibility Study EAN Available | 02-Oct-20 A | 02-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1280 | HNB Reactors Shutdown Essential Safety Cases | 2020-07-13 | 2020-07-17 | Obtain peer review (if required) (HNB) | 05-Oct-20 A | 09-Oct-20 A | 4 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1360 | HNB Reactors Shutdown Essential Safety Cases | 2020-07-20 | 2020-09-25 | SC - Safety Case development - Cat 1 Case verification & SA - HNB - B-C | 05-Oct-20 A | 05-May-21 A | 56 | 0 | 147 | 100% |  | Completed
ER6371LT | W202 | W202.A2710 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-08-03 | Shutdown Margin Workshop - Discovery MS - Confirm no Further SDM Analysis Required | 05-Oct-20 A | 05-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3760 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-02 | 2020-12-04 | Prepare ALARP Strategy - Confirm HHB Strategy Applicable to HRA Report | 05-Oct-20 A | 09-Oct-20 A | 25 | 0 | 4 | 100% |  | Completed
ER6371LT | W202 | W202.A3750 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-02 | 2021-02-24 | ALARP Strategy - Confirm HHB Strategy Applicable to HRA Report Summary | 05-Oct-20 A | 20-Oct-20 A | 80 | 0 | 11 | 100% |  | Completed
ER6661LT | W206 | W206.A2710 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-08-03 | Shutdown Margin Workshop - Discovery MS - Confirm no Further SDM Analysis Required | 05-Oct-20 A | 05-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3760 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-02 | 2020-12-04 | Prepare ALARP Strategy - Confirm HHB Strategy Applicable to HYA Report | 05-Oct-20 A | 09-Oct-20 A | 25 | 0 | 4 | 100% |  | Completed
ER6661LT | W206 | W206.A3750 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-02 | 2021-02-24 | ALARP Strategy - Confirm HHB Strategy Applicable to HYA Report Summary | 05-Oct-20 A | 20-Oct-20 A | 80 | 0 | 11 | 100% |  | Completed
ER6378LT | W222 | W222.A23820 | HRA Fuel Handling Essential Safety Case | 2020-10-05 | 2020-10-16 | Verify Detailed Option Investigation EAN for Technical Review | 05-Oct-20 A | 16-Oct-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | A1880 | HNB Reactors Shutdown Essential Safety Cases |  |  | SC Margins, Judgements and Challenges - Draft Complete | 05-Oct-20 A | 06-Oct-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | A2060 | HNB Reactors Shutdown Essential Safety Cases |  |  | Conclusions - Mature Draft | 05-Oct-20 A | 06-Oct-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | A2230 | HNB Reactors Shutdown Essential Safety Cases |  |  | Appendix – OPEX - Draft Complete | 05-Oct-20 A | 07-Oct-20 A | 3 | 0 | 3 | 100% |  | Completed
ER6650LT | W226 | W226.A23820 | HYA Fuel Handling Essential Safety Case | 2020-10-05 | 2020-10-16 | Verify Detailed Option Investigation EAN for Technical Review | 05-Oct-20 A | 16-Oct-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | W226.A26930 | HYA Fuel Handling Essential Safety Case | 2020-10-06 | 2020-10-06 | Hold PRC Meeting | 06-Oct-20 A | 06-Oct-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2480 | HRA Reactors Shutdown Essential Safety Cases | 2020-07-16 | 2020-07-29 | General HF Oversight and HFIP Updates and Revisions Draft EAN Verified by TSA | 06-Oct-20 A | 26-Oct-20 A | 10 | 0 | 14 | 100% |  | Completed
ER6661LT | W206 | W206.A2480 | HYA Reactors Shutdown Essential Safety Cases | 2020-07-16 | 2020-07-29 | General HF Oversight and HFIP Updates and Revisions Draft EAN Verified by TSA | 06-Oct-20 A | 26-Oct-20 A | 10 | 0 | 14 | 100% |  | Completed
ER6370LT | W201 | A2730 | HNB Reactors Shutdown Essential Safety Cases |  |  | Summary - Draft Complete | 06-Oct-20 A | 07-Oct-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6372LT | W203 | W203.A1140 | HNB Enhanced Defuelling Safety Cases | 2020-10-06 | 2020-10-06 | Hold PRC | 06-Oct-20 A | 06-Oct-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A26930 | HRA Fuel Handling Essential Safety Case | 2020-10-06 | 2020-10-06 | Hold PRC Meeting | 06-Oct-20 A | 06-Oct-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1150 | HNB Enhanced Defuelling Safety Cases |  | 2020-10-06 | Gate A PRC Paper Approval | 06-Oct-20 A | 06-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4260 | HNB Reactors Shutdown Essential Safety Cases | 2020-05-21 | 2020-06-04 | Core Cooling Head Document Report Verification Completed and uploaded to CDMS | 07-Oct-20 A | 07-Oct-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A2206110 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-02-01 | >>>INCOMING ENABLER (W202.A22350) HF Assessment of Fuel Free Verification EAN Available(TO BE DELETED) | 07-Oct-20 A | 07-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A11520 | HRA Fuel Handling Essential Safety Case |  | 2020-10-07 | HF Assessment of Fuel Free Verification EAN Available (System) | 07-Oct-20 A | 07-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A22350 | HRA Fuel Handling Essential Safety Case |  | 2020-10-07 | >>>OUTGOING ENABLER (W202.A1320?) HF Assessment of Fuel Free Verification EAN Available | 07-Oct-20 A | 07-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A26920 | HYA Fuel Handling Essential Safety Case | 2020-10-07 | 2020-10-08 | Modify Estimate, Schedule & Risk Log as Required | 07-Oct-20 A | 08-Oct-20 A | 2 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A11520 | HYA Fuel Handling Essential Safety Case |  | 2020-10-07 | HF Assessment of Fuel Free Verification EAN Available (System) | 07-Oct-20 A | 07-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27210 | HYA Fuel Handling Essential Safety Case |  | 2020-10-07 | >>>OUTGOING ENABLER (W206.A1320?) HF Assessment of Fuel Free Verification EAN Available | 07-Oct-20 A | 07-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A1720 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 3 - Peer Review | 07-Oct-20 A | 07-Oct-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | A2070 | HNB Reactors Shutdown Essential Safety Cases |  |  | Conclusions - Peer Review | 07-Oct-20 A | 09-Oct-20 A | 1 | 0 | 3 | 100% |  | Completed
ER6378LT | W222 | W222.A26920 | HRA Fuel Handling Essential Safety Case | 2020-10-07 | 2020-10-08 | Modify Estimate, Schedule & Risk Log as Required | 07-Oct-20 A | 08-Oct-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A3350 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-18 | 2020-09-18 | Summary of Compliance with NSPs - Pre Job Brief | 08-Oct-20 A | 08-Oct-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A3350 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-18 | 2020-09-18 | Summary of Compliance with NSPs - Pre Job Brief | 08-Oct-20 A | 08-Oct-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17640 | HNB Reactors Shutdown Essential Safety Cases |  |  | Core Cooling Head Document Report - CDMS route list approval | 08-Oct-20 A | 09-Oct-20 A | 3 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A3000 | HRA Reactors Shutdown Essential Safety Cases | 2020-08-20 | 2020-09-03 | Supporting Plant - Supplier prepare and issue Offer | 08-Oct-20 A | 21-Oct-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.A3000 | HYA Reactors Shutdown Essential Safety Cases | 2020-08-20 | 2020-09-03 | Supporting Plant - Supplier prepare and issue Offer | 08-Oct-20 A | 21-Oct-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | A1730 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 3 - Draft Complete | 08-Oct-20 A | 09-Oct-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | A1930 | HNB Reactors Shutdown Essential Safety Cases |  |  | QA - Draft Complete | 08-Oct-20 A | 09-Oct-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | A2080 | HNB Reactors Shutdown Essential Safety Cases |  |  | Conclusions - Draft Complete | 08-Oct-20 A | 09-Oct-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | A2180 | HNB Reactors Shutdown Essential Safety Cases |  |  | Appendix – Description of Existing Safety Case - Draft Complete | 08-Oct-20 A | 09-Oct-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1630 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-07-20 | Verification Commenced (T-11) (HNB) | 09-Oct-20 A | 09-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A4270 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-06-04 | Core Cooling Head Document Report Completed | 09-Oct-20 A | 09-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16150 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-07-17 | Safety Case Proposal Authoring Draft Complete EC 364023 <NSRS SC Approach & Outline>(Cat 1 KDM) (HNB) RS Essential SC | 09-Oct-20 A | 09-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16810 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-06-04 | Completion of Head Documents (Reactor Shutdown Essential SC) | 09-Oct-20 A | 09-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17530 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-06-04 | >>>OUTGOING ENABLER (D414) Cooling Head Document Completed | 09-Oct-20 A | 09-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3980 | HRA Reactors Shutdown Essential Safety Cases | 2020-12-07 | 2020-12-29 | ALARP Strategy - Confirm HHB Strategy Applicable to HRA Report Verified by TSA | 09-Oct-20 A | 12-Oct-20 A | 15 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A3980 | HYA Reactors Shutdown Essential Safety Cases | 2020-12-07 | 2020-12-29 | ALARP Strategy - Confirm HHB Strategy Applicable to HYA Report Verified by TSA | 09-Oct-20 A | 12-Oct-20 A | 15 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17670 | HNB Reactors Shutdown Essential Safety Cases |  |  | First Round of Verification - Richard James | 09-Oct-20 A | 10-Oct-20 A | 5 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17720 | HNB Reactors Shutdown Essential Safety Cases |  |  | First Round of Verification - Martin Kearns | 09-Oct-20 A | 11-Oct-20 A | 5 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A24210 | HRA Fuel Handling Essential Safety Case |  | 2020-10-09 | Hazop Study of Defuelling Process EAN Available (REV 000) | 09-Oct-20 A | 09-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | A2750 | HNB Reactors Shutdown Essential Safety Cases |  |  | Safety Case Authoring Complete | 09-Oct-20 A | 09-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A26910 | HYA Fuel Handling Essential Safety Case | 2020-10-09 | 2020-10-12 | Modify Scheme Paper as Required | 09-Oct-20 A | 12-Oct-20 A | 2 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A12390 | HYA Fuel Handling Essential Safety Case | 2020-10-09 | 2020-10-15 | Verify Adequate Capacity for Solida Waste Arisings EAN and Issue for Technical Review | 09-Oct-20 A | 15-Oct-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6650LT | W226 | W226.A24210 | HYA Fuel Handling Essential Safety Case |  | 2020-10-09 | Hazop Study of Defuelling Process EAN Available (REV 000) | 09-Oct-20 A | 09-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A12390 | HRA Fuel Handling Essential Safety Case | 2020-10-09 | 2020-10-15 | Verify Adequate Capacity for Solida Waste Arisings EAN and Issue for Technical Review | 09-Oct-20 A | 15-Oct-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | A1980 | HNB Reactors Shutdown Essential Safety Cases |  |  | Implementation Programme - Draft Complete | 09-Oct-20 A | 09-Oct-20 A | 3 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A26910 | HRA Fuel Handling Essential Safety Case | 2020-10-09 | 2020-10-12 | Modify Scheme Paper as Required | 09-Oct-20 A | 12-Oct-20 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A4110 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-12-29 | Verified ALARP Strategy - Confirm HHB Strategy Applicable to HRA Report Issued to EDF for Technical Review. | 12-Oct-20 A | 12-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4110 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-12-29 | Verified ALARP Strategy - Confirm HHB Strategy Applicable to HYA Report Issued to EDF for Technical Review. | 12-Oct-20 A | 12-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27040 | HYA Fuel Handling Essential Safety Case |  | 2020-10-12 | Issue Scheme Paper to Major Schemes PRC Members | 12-Oct-20 A | 12-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1365 | HNB Reactors Shutdown Essential Safety Cases |  |  | SQEP verification (1st round review) (HNB) (Driver to Start EC's on ER6602) Summary | 12-Oct-20 A | 23-Oct-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1570 | HNB Reactors Shutdown Essential Safety Cases | 2020-07-20 | 2020-08-14 | Specialist Assessments if Necessary (HNB) - Summary | 12-Oct-20 A | 30-Oct-20 A | 15 | 0 | 15 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1600 | HNB Reactors Shutdown Essential Safety Cases | 2020-07-20 | 2020-07-31 | Prepare and Populate Affected Documents List (HNB) | 12-Oct-20 A | 30-Oct-20 A | 10 | 0 | 14 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1610 | HNB Reactors Shutdown Essential Safety Cases |  |  | Nuclear Safety | 12-Oct-20 A | 30-Oct-20 A | 15 | 0 | 15 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2080 | HNB Reactors Shutdown Essential Safety Cases |  |  | Ops & PSSR | 12-Oct-20 A | 30-Oct-20 A | 15 | 0 | 15 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2090 | HNB Reactors Shutdown Essential Safety Cases |  |  | Civils | 12-Oct-20 A | 30-Oct-20 A | 15 | 0 | 15 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2100 | HNB Reactors Shutdown Essential Safety Cases |  |  | Emergency Arrangements | 12-Oct-20 A | 30-Oct-20 A | 15 | 0 | 15 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2110 | HNB Reactors Shutdown Essential Safety Cases |  |  | Nuclear Liabilities | 12-Oct-20 A | 30-Oct-20 A | 15 | 0 | 15 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2120 | HNB Reactors Shutdown Essential Safety Cases |  |  | Decommissioning | 12-Oct-20 A | 30-Oct-20 A | 15 | 0 | 15 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1375 | HNB Reactors Shutdown Essential Safety Cases |  |  | First Round of Verification - David Powada | 12-Oct-20 A | 23-Oct-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17690 | HNB Reactors Shutdown Essential Safety Cases |  |  | First Round of Verification - Sarah Penny | 12-Oct-20 A | 14-Oct-20 A | 5 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17710 | HNB Reactors Shutdown Essential Safety Cases |  |  | First Round of Verification - Rob Cotterill | 12-Oct-20 A | 16-Oct-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17750 | HNB Reactors Shutdown Essential Safety Cases |  |  | First Round of Verification - Phil Hurst / Lorna Stevens | 12-Oct-20 A | 16-Oct-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17770 | HNB Reactors Shutdown Essential Safety Cases |  |  | First Round of Verification - Maria Mak | 12-Oct-20 A | 16-Oct-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17780 | HNB Reactors Shutdown Essential Safety Cases |  |  | First Round of Verification - Beth Gaston | 12-Oct-20 A | 21-Oct-20 A | 5 | 0 | 7 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17790 | HNB Reactors Shutdown Essential Safety Cases |  |  | First Round of Verification - Jason Satchell | 12-Oct-20 A | 14-Oct-20 A | 5 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17800 | HNB Reactors Shutdown Essential Safety Cases |  |  | First Round of Verification - Allison Adamson | 12-Oct-20 A | 21-Oct-20 A | 5 | 0 | 7 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17810 | HNB Reactors Shutdown Essential Safety Cases |  |  | First Round of Verification - Jim Kershaw | 12-Oct-20 A | 13-Oct-20 A | 5 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18110 | HNB Reactors Shutdown Essential Safety Cases |  |  | Environment/Rad Protection | 12-Oct-20 A | 30-Oct-20 A | 15 | 0 | 15 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2150 | HNB Reactors Shutdown Essential Safety Cases |  |  | Confirm Specialist Assessments Required | 12-Oct-20 A | 14-Oct-20 A | 3 | 0 | 3 | 100% |  | Completed
ER6378LT | W222 | W222.A26120 | HRA Fuel Handling Essential Safety Case | 2020-10-12 | 2020-10-16 | Verify HAZOP updates resulting from defuelling process changes & Issue for Technical Review (REV 001) | 12-Oct-20 A | 16-Oct-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17665 | HNB Reactors Shutdown Essential Safety Cases |  |  | First Round of Verification - Georgia Pawson | 12-Oct-20 A | 23-Oct-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | W226.A22770 | HYA Fuel Handling Essential Safety Case | 2020-10-12 | 2020-11-19 | Verification of Lifting Integrity Life Limits EAN | 12-Oct-20 A | 19-Nov-20 A | 15 | 0 | 28 | 100% |  | Completed
ER6650LT | W226 | W226.A26120 | HYA Fuel Handling Essential Safety Case | 2020-10-12 | 2020-10-16 | Verify HAZOP updates resulting from defuelling process changes & Issue for Technical Review (REV 001) | 12-Oct-20 A | 16-Oct-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A27040 | HRA Fuel Handling Essential Safety Case |  | 2020-10-12 | Issue Scheme Paper to Major Schemes PRC Members | 12-Oct-20 A | 12-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A4120 | HRA Reactors Shutdown Essential Safety Cases | 2020-12-30 | 2021-01-20 | ALARP Strategy - Confirm HHB Strategy Applicable to HRA Report Technically Reviewed by EDF SQEP | 13-Oct-20 A | 14-Oct-20 A | 15 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A4120 | HYA Reactors Shutdown Essential Safety Cases | 2020-12-30 | 2021-01-20 | ALARP Strategy - Confirm HHB Strategy Applicable to HYA Report Technically Reviewed by EDF SQEP | 13-Oct-20 A | 14-Oct-20 A | 15 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A26440 | HRA Fuel Handling Essential Safety Case | 2020-10-13 | 2020-10-19 | Technical Review of Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection | 13-Oct-20 A | 19-Oct-20 A | 4 | 0 | 4 | 100% |  | Completed
ER6378LT | W222 | W222.A22770 | HRA Fuel Handling Essential Safety Case | 2020-10-13 | 2020-11-19 | Verification of Lifting Integrity Life Limits EAN | 13-Oct-20 A | 19-Nov-20 A | 15 | 0 | 27 | 100% |  | Completed
ER6650LT | W226 | W226.A27070 | HYA Fuel Handling Essential Safety Case | 2020-10-13 | 2020-10-19 | Major Schemes PRC Members Review IRM Documentation | 13-Oct-20 A | 19-Oct-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6650LT | W226 | W226.A26440 | HYA Fuel Handling Essential Safety Case | 2020-10-13 | 2020-10-19 | Technical Review of Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection | 13-Oct-20 A | 19-Oct-20 A | 4 | 0 | 4 | 100% |  | Completed
ER6378LT | W222 | W222.A27070 | HRA Fuel Handling Essential Safety Case | 2020-10-13 | 2020-10-19 | Major Schemes PRC Members Review IRM Documentation | 13-Oct-20 A | 19-Oct-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11070 | HNB Reactors Shutdown Essential Safety Cases | 2020-07-20 | 2021-09-14 | Phase 2 Project Management - Gate C - D | 14-Oct-20 A | 31-Aug-22 A | 208 | 0 | 474 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11110 | HNB Reactors Shutdown Essential Safety Cases | 2020-07-20 | 2021-08-27 | SC - Safety Case development - tech oversight Cat 1 - Claim 1 - HNB - C-D - STN | 14-Oct-20 A | 10-Aug-22 A | 197 | 0 | 459 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11130 | HNB Reactors Shutdown Essential Safety Cases | 2020-07-20 | 2020-12-30 | SC - Safety Case development - tech oversight Cat 1 - Claim 2 - HNB - C-D - STN | 14-Oct-20 A | 31-Dec-20 A | 56 | 0 | 54 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11150 | HNB Reactors Shutdown Essential Safety Cases | 2020-07-20 | 2021-08-27 | SC - Safety Case development - tech oversight Cat 1 - Claim 3 - HNB - C-D - STN | 14-Oct-20 A | 27-Apr-22 A | 197 | 0 | 387 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11170 | HNB Reactors Shutdown Essential Safety Cases | 2020-07-20 | 2021-08-27 | SC - Safety Case development - tech oversight Cat 1 - Claim 4 - HNB - C-D - STN | 14-Oct-20 A | 27-Apr-22 A | 197 | 0 | 387 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11180 | HNB Reactors Shutdown Essential Safety Cases | 2020-07-20 | 2021-08-27 | SC - Safety Case development - tech oversight Cat 1 - Claim 5- HNB - C-D - STN | 14-Oct-20 A | 27-Apr-22 A | 197 | 0 | 387 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11220 | HNB Reactors Shutdown Essential Safety Cases | 2020-07-20 | 2021-08-27 | SC - Safety Case development - Stakeholder comms Cat 1 - HNB - C-D | 14-Oct-20 A | 28-Apr-22 A | 197 | 0 | 388 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16160 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-07-17 | Gate EC3 Completed 364023 (HNB) | 14-Oct-20 A | 14-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A23610 | HRA Fuel Handling Essential Safety Case | 2020-10-14 | 2020-12-01 | Verify Quality of Build Considerations (Task File Note) for Technical Review | 14-Oct-20 A | 01-Dec-20 A | 8 | 0 | 35 | 100% |  | Completed
ER6650LT | W226 | W226.A23610 | HYA Fuel Handling Essential Safety Case | 2020-10-14 | 2020-12-01 | Verify Quality of Build Considerations (Task File Note) for Technical Review | 14-Oct-20 A | 01-Dec-20 A | 8 | 0 | 35 | 100% |  | Completed
ER6371LT | W202 | W202.A4200 | HRA Reactors Shutdown Essential Safety Cases | 2021-01-21 | 2021-02-10 | TSA Address Comments on TR'd ALARP Strategy - Confirm HHB Strategy Applicable to HRA Report | 15-Oct-20 A | 16-Oct-20 A | 15 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A4200 | HYA Reactors Shutdown Essential Safety Cases | 2021-01-21 | 2021-02-10 | TSA Address Comments on TR'd ALARP Strategy - Confirm HHB Strategy Applicable to HYA Report | 15-Oct-20 A | 16-Oct-20 A | 15 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A22850 | HRA Fuel Handling Essential Safety Case | 2020-10-15 | 2020-10-27 | Technical Review of Grab Engagement for Low Burn-up Fuel EAN | 15-Oct-20 A | 27-Oct-20 A | 9 | 0 | 9 | 100% |  | Completed
ER6650LT | W226 | W226.A22850 | HYA Fuel Handling Essential Safety Case | 2020-10-15 | 2020-10-27 | Technical Review of Grab Engagement for Low Burn-up Fuel EAN | 15-Oct-20 A | 27-Oct-20 A | 9 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18220 | HNB Reactors Shutdown Essential Safety Cases | 2020-10-15 | 2020-10-21 | <NEW SCOPE CR 187> - RFS - OPEX/ Literature Review - Review Offer, prepare and issue CI | 15-Oct-20 A | 06-Nov-20 A | 5 | 0 | 17 | 100% |  | Completed
ER6371LT | W202 | W202.A3540 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-10-12 | Issue Final Worker Dose Report | 15-Oct-20 A | 15-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3540 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-10-12 | Issue Final Worker Dose Report | 15-Oct-20 A | 15-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A4250 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-02-10 | TSA Issue Final ALARP Strategy - Confirm HHB Strategy Applicable to HRA Report | 16-Oct-20 A | 16-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3580 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-10-13 | Confirm Applicability to HRA | 16-Oct-20 A | 16-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4250 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-02-10 | TSA Issue Final ALARP Strategy - Confirm HHB Strategy Applicable to HYA Report | 16-Oct-20 A | 16-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3580 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-10-13 | Confirm Applicability to HYA | 16-Oct-20 A | 16-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A12400 | HYA Fuel Handling Essential Safety Case | 2020-10-16 | 2020-10-22 | Technical Review of Confirm Adequate Capacity for Solid Waste Arisings from Stringer Dismantling EAN | 16-Oct-20 A | 22-Oct-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6371LT | W202 | W202.A3440 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-25 | 2020-10-08 | ALARP Report - Supplier prepare and issue Offer | 16-Oct-20 A | 29-Oct-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | W202.A3550 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-13 | 2020-10-19 | Worker Dose Report Completed and uploaded to CDMS | 16-Oct-20 A | 20-Oct-20 A | 5 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A3440 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-25 | 2020-10-08 | ALARP Report - Supplier prepare and issue Offer | 16-Oct-20 A | 29-Oct-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.A3550 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-13 | 2020-10-19 | Worker Dose Report Completed and uploaded to CDMS | 16-Oct-20 A | 26-Oct-20 A | 5 | 0 | 6 | 100% |  | Completed
ER6378LT | W222 | W222.A26780 | HRA Fuel Handling Essential Safety Case | 2020-10-16 | 2020-10-26 | Technical Review of Fuel Route Operational Sequence/Process for Defuelling EAN (REV 001) | 16-Oct-20 A | 26-Oct-20 A | 7 | 0 | 7 | 100% |  | Completed
ER6378LT | W222 | W222.A12400 | HRA Fuel Handling Essential Safety Case | 2020-10-16 | 2020-10-22 | Technical Review of Confirm Adequate Capacity for Solid Waste Arisings from Stringer Dismantling EAN | 16-Oct-20 A | 22-Oct-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A7000 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-16 | 2020-12-18 | <NEW SCOPE CR220> Corroborated Approach Summary | 16-Oct-20 A | 29-Jan-21 A | 78 | 0 | 72 | 100% |  | Completed
ER6371LT | W202 | W202.A7010 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-16 | 2020-10-16 | <NEW SCOPE CR220> Corroborated Approach Pre-Job Brief | 16-Oct-20 A | 16-Oct-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A7000 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-16 | 2021-02-05 | <NEW SCOPE CR 221> Corroborated Approach Summary | 16-Oct-20 A | 29-Jan-21 A | 78 | 0 | 72 | 100% |  | Completed
ER6661LT | W206 | W206.A7010 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-16 | 2020-10-16 | <NEW SCOPE CR 221> Corroborated Approach Pre-Job Brief | 16-Oct-20 A | 16-Oct-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A26780 | HYA Fuel Handling Essential Safety Case | 2020-10-16 | 2020-10-26 | Technical Review of Fuel Route Operational Sequence/Process for Defuelling EAN (REV 001) | 16-Oct-20 A | 26-Oct-20 A | 7 | 0 | 7 | 100% |  | Completed
ER6371LT | W202 | W202.A2630 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-07-29 | Verified Pressure Boundary Seals Draft Report Issued to EDF for Technical Review. | 19-Oct-20 A | 19-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2660 | HRA Reactors Shutdown Essential Safety Cases | 2020-07-30 | 2020-08-19 | Pressure Boundary Seals Draft Report Technically Reviewed by EDF SQEP | 19-Oct-20 A | 06-Nov-20 A | 15 | 0 | 15 | 100% |  | Completed
ER6371LT | W202 | W202.A2970 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-08-18 | TSA Issue Final Gas Chemistry Assessment Report | 19-Oct-20 A | 19-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2980 | HRA Reactors Shutdown Essential Safety Cases | 2020-08-19 | 2020-09-02 | Gas Chemistry Assessment Report TR Completed and uploaded to CDMS | 19-Oct-20 A | 26-Oct-20 A | 10 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A4260 | HRA Reactors Shutdown Essential Safety Cases | 2021-02-11 | 2021-02-24 | ALARP Strategy - Confirm HHB Strategy Applicable to HRA Report TR Completed and uploaded to CDMS | 19-Oct-20 A | 20-Oct-20 A | 10 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2630 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-07-29 | Verified Pressure Boundary Seals Draft Report Issued to EDF for Technical Review. | 19-Oct-20 A | 19-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2970 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-08-18 | TSA Issue Final Gas Chemistry Assessment Report | 19-Oct-20 A | 19-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2980 | HYA Reactors Shutdown Essential Safety Cases | 2020-08-19 | 2020-09-02 | Gas Chemistry Assessment Report TR Completed and uploaded to CDMS | 19-Oct-20 A | 26-Oct-20 A | 10 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A4260 | HYA Reactors Shutdown Essential Safety Cases | 2021-02-11 | 2021-02-24 | ALARP Strategy - Confirm HHB Strategy Applicable to HYA Report TR Completed and uploaded to CDMS | 19-Oct-20 A | 20-Oct-20 A | 10 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A26130 | HRA Fuel Handling Essential Safety Case | 2020-10-19 | 2021-02-04 | Technical Review of HAZOP updates resulting from defuelling process changes EAN (REV 001) | 19-Oct-20 A | 04-Feb-21 A | 4 | 0 | 76 | 100% |  | Completed
ER6650LT | W226 | W226.A26130 | HYA Fuel Handling Essential Safety Case | 2020-10-19 | 2021-02-04 | Technical Review of HAZOP updates resulting from defuelling process changes EAN (REV 001) | 19-Oct-20 A | 04-Feb-21 A | 4 | 0 | 76 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17680 | HNB Reactors Shutdown Essential Safety Cases |  |  | First Round of Verification - Ruth Aldred | 19-Oct-20 A | 23-Oct-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A24520 | HRA Fuel Handling Essential Safety Case | 2020-10-19 | 2020-12-11 | Verify Review of Interlock Maintenance Review EAN & Issue for Technical Review (DRAFT) | 19-Oct-20 A | 11-Dec-20 A | 15 | 0 | 39 | 100% |  | Completed
ER6378LT | W222 | W222.A23830 | HRA Fuel Handling Essential Safety Case | 2020-10-19 | 2020-11-13 | Technical Review of Detailed Option Investigation EAN | 19-Oct-20 A | 13-Nov-20 A | 10 | 0 | 19 | 100% |  | Completed
ER6371LT | W202 | W202.A6080 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-19 | 2020-10-23 | <NEW SCOPE CR220> Panther Sensitivity Studies Draft Report Verified by TSA | 19-Oct-20 A | 23-Oct-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A7020 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-19 | 2020-11-02 | <NEW SCOPE CR220> Prepare Corroborated Approach Draft Report | 19-Oct-20 A | 23-Oct-20 A | 11 | 0 | 4 | 100% |  | Completed
ER6661LT | W206 | W206.A6080 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-19 | 2020-10-23 | <NEW SCOPE CR 221> Panther Sensitivity Studies Draft Report Verified by TSA | 19-Oct-20 A | 23-Oct-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A7020 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-19 | 2020-11-02 | <NEW SCOPE CR 221> Prepare Corroborated Approach Draft Report | 19-Oct-20 A | 23-Oct-20 A | 11 | 0 | 4 | 100% |  | Completed
ER6650LT | W226 | W226.A23830 | HYA Fuel Handling Essential Safety Case | 2020-10-19 | 2020-11-13 | Technical Review of Detailed Option Investigation EAN | 19-Oct-20 A | 13-Nov-20 A | 10 | 0 | 19 | 100% |  | Completed
ER6650LT | W226 | W226.A24520 | HYA Fuel Handling Essential Safety Case | 2020-10-19 | 2020-12-11 | Verify Review of Interlock Maintenance Review EAN & Issue for Technical Review (DRAFT) | 19-Oct-20 A | 11-Dec-20 A | 15 | 0 | 39 | 100% |  | Completed
ER6371LT | W202 | W202.A4320 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-02-24 | ALARP Strategy - Confirm HHB Strategy Applicable to HRA Report Completed | 20-Oct-20 A | 20-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3620 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-10-19 | Worker Dose Report Completed | 20-Oct-20 A | 20-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2660 | HYA Reactors Shutdown Essential Safety Cases | 2020-07-30 | 2020-08-19 | Pressure Boundary Seals Draft Report Technically Reviewed by EDF SQEP | 20-Oct-20 A | 06-Nov-20 A | 15 | 0 | 14 | 100% |  | Completed
ER6661LT | W206 | W206.A4320 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-02-24 | ALARP Strategy - Confirm HHB Strategy Applicable to HYA Report Completed | 20-Oct-20 A | 20-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206150 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-10-30 | >>>OUTGOING ENABLER (W206) ALARP / BAT/ BPM Report Completed | 20-Oct-20 A | 20-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A26450 | HRA Fuel Handling Essential Safety Case | 2020-10-20 | 2020-10-20 | Supplier Update and Issue Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protections | 20-Oct-20 A | 20-Oct-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A22440 | HRA Fuel Handling Essential Safety Case |  | 2020-10-20 | >>>INCOMING ENABLER (W202.A10600?) ALARP / BAT/ BPM Report Completed | 20-Oct-20 A | 20-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A22540 | HRA Fuel Handling Essential Safety Case |  | 2020-10-20 | >>>MIRROR OF INCOMING ENABLER (W202.A10600?) ALARP / BAT/ BPM Report Completed | 20-Oct-20 A | 20-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A22640 | HRA Fuel Handling Essential Safety Case |  | 2020-10-20 | INTERFACE MILESTONE - ALARP / BAT/ BPM Report Completed - (W202 Reactors Shutdown Essential Safety Cases (HRA)) | 20-Oct-20 A | 20-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A22640 | HYA Fuel Handling Essential Safety Case |  | 2020-10-20 | INTERFACE MILESTONE - ALARP / BAT/ BPM Report Completed - (W202 Reactors Shutdown Essential Safety Cases (HYA)) | 20-Oct-20 A | 20-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A22540 | HYA Fuel Handling Essential Safety Case |  | 2020-10-20 | >>>MIRROR OF INCOMING ENABLER (W206) ALARP / BAT/ BPM Report Completed | 20-Oct-20 A | 20-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A22440 | HYA Fuel Handling Essential Safety Case |  | 2020-10-20 | >>>INCOMING ENABLER (W206) ALARP / BAT/ BPM Report Completed | 20-Oct-20 A | 20-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A26450 | HYA Fuel Handling Essential Safety Case | 2020-10-20 | 2020-10-20 | Supplier Update and Issue Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protections | 20-Oct-20 A | 20-Oct-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206165 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-09-01 | >>>OUTGOING ENABLER (W226) ALARP / BAT/ BPM Report Completed | 20-Oct-20 A | 20-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A26460 | HRA Fuel Handling Essential Safety Case | 2020-10-21 | 2021-05-26 | Complete Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection to CDMS | 21-Oct-20 A | 26-May-21 A | 1 | 0 | 149 | 100% |  | Completed
ER6650LT | W226 | W226.A27080 | HYA Fuel Handling Essential Safety Case | 2020-10-21 | 2020-10-21 | Hold Major Schemes PRC Meeting | 21-Oct-20 A | 21-Oct-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A26460 | HYA Fuel Handling Essential Safety Case | 2020-10-21 | 2021-05-26 | Complete Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection to CDMS | 21-Oct-20 A | 26-May-21 A | 1 | 0 | 149 | 100% |  | Completed
ER6378LT | W222 | W222.A27080 | HRA Fuel Handling Essential Safety Case | 2020-10-21 | 2020-10-21 | Hold Major Schemes PRC Meeting | 21-Oct-20 A | 21-Oct-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A26860 | HYA Fuel Handling Essential Safety Case | 2020-10-22 | 2020-10-26 | Modify Estimate, Schedule & Risk Log as Required | 22-Oct-20 A | 26-Oct-20 A | 3 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A3160 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-04 | 2020-09-10 | Supporting Plant - Review Offer, prepare and issue CI | 22-Oct-20 A | 28-Oct-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A3160 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-04 | 2020-09-10 | Supporting Plant - Review Offer, prepare and issue CI | 22-Oct-20 A | 28-Oct-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A26860 | HRA Fuel Handling Essential Safety Case | 2020-10-22 | 2020-10-26 | Modify Estimate, Schedule & Risk Log as Required | 22-Oct-20 A | 26-Oct-20 A | 3 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16850 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-07-31 | Review Comment Response to INSA and Verification - HNB | 23-Oct-20 A | 23-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A12410 | HYA Fuel Handling Essential Safety Case | 2020-10-23 | 2020-10-27 | Supplier Update and Issue Confirm Adequate Capacity for Solid Waste Arisings from Stringer Dismantling EAN | 23-Oct-20 A | 27-Oct-20 A | 3 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | W222.A12410 | HRA Fuel Handling Essential Safety Case | 2020-10-23 | 2020-10-27 | Supplier Update and Issue Confirm Adequate Capacity for Solid Waste Arisings from Stringer Dismantling EAN | 23-Oct-20 A | 27-Oct-20 A | 3 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1410 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-07-31 | First round verification comments received (HNB) | 23-Oct-20 A | 23-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A6090 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-10-23 | <NEW SCOPE CR220> Verified Panther Sensitivity Studies Draft Report Issued to EDF for Technical Review. | 23-Oct-20 A | 23-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A6090 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-10-23 | <NEW SCOPE CR 221> Verified Panther Sensitivity Studies Draft Report Issued to EDF for Technical Review. | 23-Oct-20 A | 23-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3150 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-09-02 | Gas Chemistry Assessment Report Completed | 26-Oct-20 A | 26-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2620 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-07-29 | Verified General HF Oversight and HFIP Updates and Revisions Draft EAN Issued to EDF for Technical Review. | 26-Oct-20 A | 26-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2920 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-08-14 | Issue Final Seismic Assessment of FPU within Reactor Report | 26-Oct-20 A | 26-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3150 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-09-02 | Gas Chemistry Assessment Report Completed | 26-Oct-20 A | 26-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2620 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-07-29 | Verified General HF Oversight and HFIP Updates and Revisions Draft EAN Issued to EDF for Technical Review. | 26-Oct-20 A | 26-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2920 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-08-14 | Issue Final Seismic Assessment of FPU within Reactor Report | 26-Oct-20 A | 26-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3620 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-10-19 | Worker Dose Report Completed | 26-Oct-20 A | 26-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A7030 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-03 | 2020-11-06 | <NEW SCOPE CR220> Corroborated Approach Draft Report Verified by TSA | 26-Oct-20 A | 30-Nov-20 A | 4 | 0 | 25 | 100% |  | Completed
ER6661LT | W206 | W206.A7030 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-03 | 2020-11-06 | <NEW SCOPE CR 221> Corroborated Approach Draft Report Verified by TSA | 26-Oct-20 A | 30-Nov-20 A | 4 | 0 | 25 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1520 | HNB Reactors Shutdown Essential Safety Cases |  |  | Case Author address first round verification comments | 26-Oct-20 A | 16-Nov-20 A | 15 | 0 | 15 | 100% |  | Completed
ER6371LT | W202 | W202.A6100 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-26 | 2020-11-06 | <NEW SCOPE CR220> Panther Sensitivity Studies Draft Report Technically Reviewed by EDF SQEP | 26-Oct-20 A | 16-Nov-20 A | 10 | 0 | 16 | 100% |  | Completed
ER6378LT | W222 | W222.A22860 | HRA Fuel Handling Essential Safety Case | 2020-10-27 | 2020-10-27 | Supplier Update and Issue Grab Engagement for Low Burn-up Fuel EAN | 27-Oct-20 A | 27-Oct-20 A | 5 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A26850 | HYA Fuel Handling Essential Safety Case | 2020-10-27 | 2020-12-04 | Modify Scheme Paper as Required | 27-Oct-20 A | 04-Dec-20 A | 3 | 0 | 29 | 100% |  | Completed
ER6650LT | W226 | W226.A22860 | HYA Fuel Handling Essential Safety Case | 2020-10-27 | 2020-10-27 | Supplier Update and Issue Grab Engagement for Low Burn-up Fuel EAN | 27-Oct-20 A | 27-Oct-20 A | 5 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A26790 | HRA Fuel Handling Essential Safety Case | 2020-10-27 | 2021-02-01 | Supplier Update and Issue Fuel Route Operational Sequence/Process for Defuelling EAN (REV 001) | 27-Oct-20 A | 01-Feb-21 A | 2 | 0 | 67 | 100% |  | Completed
ER6378LT | W222 | W222.A26850 | HRA Fuel Handling Essential Safety Case | 2020-10-27 | 2020-12-04 | Modify Scheme Paper as Required | 27-Oct-20 A | 04-Dec-20 A | 3 | 0 | 29 | 100% |  | Completed
ER6650LT | W226 | W226.A26790 | HYA Fuel Handling Essential Safety Case | 2020-10-27 | 2021-02-01 | Supplier Update and Issue Fuel Route Operational Sequence/Process for Defuelling EAN (REV 001) | 27-Oct-20 A | 01-Feb-21 A | 2 | 0 | 67 | 100% |  | Completed
ER6378LT | W222 | W222.A22870 | HRA Fuel Handling Essential Safety Case | 2020-10-28 | 2020-11-10 | Complete TR Form & Upload Grab Engagement for Low Burn-up Fuel EAN to CDMS | 28-Oct-20 A | 10-Nov-20 A | 5 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | W226.A12420 | HYA Fuel Handling Essential Safety Case | 2020-10-28 | 2020-10-30 | Complete TR Form and Upload Confirm Adequate Capacity for Solid Waste Arisings from Stringer Dismantling EAN to CDMS | 28-Oct-20 A | 30-Oct-20 A | 3 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | W226.A22870 | HYA Fuel Handling Essential Safety Case | 2020-10-28 | 2020-11-10 | Complete TR Form & Upload Grab Engagement for Low Burn-up Fuel EAN to CDMS | 28-Oct-20 A | 10-Nov-20 A | 5 | 0 | 10 | 100% |  | Completed
ER6378LT | W222 | W222.A12420 | HRA Fuel Handling Essential Safety Case | 2020-10-28 | 2020-10-30 | Complete TR Form and Upload Confirm Adequate Capacity for Solid Waste Arisings from Stringer Dismantling EAN to CDMS | 28-Oct-20 A | 30-Oct-20 A | 3 | 0 | 3 | 100% |  | Completed
ER6371LT | W202 | W202.A3530 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-09 | 2020-10-15 | ALARP Report - Review Offer, prepare and issue CI | 29-Oct-20 A | 30-Oct-20 A | 5 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A3530 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-09 | 2020-10-15 | ALARP Report - Review Offer, prepare and issue CI | 29-Oct-20 A | 30-Oct-20 A | 5 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A18170 | HRA Fuel Handling Essential Safety Case | 2020-10-29 | 2020-11-13 | Verification of P6.6 Handover Document | 29-Oct-20 A | 13-Nov-20 A | 10 | 0 | 12 | 100% |  | Completed
ER6650LT | W226 | W226.A18170 | HYA Fuel Handling Essential Safety Case | 2020-10-29 | 2020-11-13 | Verification of P6.6 Handover Document | 29-Oct-20 A | 13-Nov-20 A | 10 | 0 | 12 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2140 | HNB Reactors Shutdown Essential Safety Cases |  |  | Programme Review | 29-Oct-20 A | 29-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17010 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-09-25 | Specialist Assessments of Safety Case - HNB | 30-Oct-20 A | 30-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3610 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-16 | 2020-10-29 | ALARP Report - Supplier mobilisation time | 30-Oct-20 A | 30-Oct-20 A | 10 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A3740 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-30 | 2020-10-30 | ALARP Report - Pre Job Brief | 30-Oct-20 A | 30-Oct-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A3610 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-16 | 2020-10-29 | ALARP Report - Supplier mobilisation time | 30-Oct-20 A | 30-Oct-20 A | 10 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3740 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-30 | 2020-10-30 | ALARP Report - Pre Job Brief | 30-Oct-20 A | 30-Oct-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A9790 | HRA Fuel Handling Essential Safety Case | 2020-10-30 | 2020-12-02 | Verify Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN and Issue for Technical Review | 30-Oct-20 A | 02-Dec-20 A | 5 | 0 | 23 | 100% |  | Completed
ER6650LT | W226 | W226.A12430 | HYA Fuel Handling Essential Safety Case |  | 2020-10-30 | Confirm Adequate Capacity for Solid Waste Arisings from Stringer Dismantling EAN Available | 30-Oct-20 A | 30-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A9790 | HYA Fuel Handling Essential Safety Case | 2020-10-30 | 2020-12-02 | Verify Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN and Issue for Technical Review | 30-Oct-20 A | 02-Dec-20 A | 10 | 0 | 23 | 100% |  | Completed
ER6372LT | W203 | W203.A1160 | HNB Enhanced Defuelling Safety Cases |  | 2020-10-30 | Gate A IRM Paper Submission | 30-Oct-20 A | 30-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A12430 | HRA Fuel Handling Essential Safety Case |  | 2020-10-30 | Confirm Adequate Capacity for Solid Waste Arisings from Stringer Dismantling EAN Available | 30-Oct-20 A | 30-Oct-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2650 | HRA Reactors Shutdown Essential Safety Cases | 2020-07-30 | 2020-08-12 | General HF Oversight and HFIP Updates and Revisions Draft EAN Technically Reviewed by EDF SQEP | 02-Nov-20 A | 13-Nov-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6378LT | W222 | W222.A23000 | HRA Fuel Handling Essential Safety Case | 2020-11-02 | 2020-11-03 | Supplier Update and Issue Interpretation of MACE for Fuel Route EAN | 02-Nov-20 A | 03-Nov-20 A | 2 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A23000 | HYA Fuel Handling Essential Safety Case | 2020-11-02 | 2020-11-03 | Supplier Update and Issue Interpretation of MACE for Fuel Route EAN | 02-Nov-20 A | 03-Nov-20 A | 1 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A3180 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-08 | 2020-09-21 | Containment Head Document - Supplier prepare and issue Offer | 02-Nov-20 A | 23-Nov-20 A | 10 | 0 | 15 | 100% |  | Completed
ER6371LT | W202 | W202.A3220 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-11 | 2020-09-24 | Supporting Plant - Supplier mobilisation time | 02-Nov-20 A | 13-Nov-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | W202.A2940 | HRA Reactors Shutdown Essential Safety Cases | 2020-08-17 | 2020-08-21 | Seismic Assessment of FPU within Reactor Report Completed and uploaded to CDMS | 02-Nov-20 A | 20-Nov-20 A | 5 | 0 | 14 | 100% |  | Completed
ER6371LT | W202 | W202.A2860 | HRA Reactors Shutdown Essential Safety Cases | 2020-08-13 | 2020-09-10 | Prepare Station Documentation Update Strategy Report | 02-Nov-20 A | 04-Dec-20 A | 20 | 0 | 24 | 100% |  | Completed
ER6371LT | W202 | W202.A2850 | HRA Reactors Shutdown Essential Safety Cases | 2020-08-13 | 2020-11-05 | Station Documentation Update Strategy Report Summary | 02-Nov-20 A | 03-Feb-21 A | 72 | 0 | 64 | 100% |  | Completed
ER6661LT | W206 | W206.A2650 | HYA Reactors Shutdown Essential Safety Cases | 2020-07-30 | 2020-08-12 | General HF Oversight and HFIP Updates and Revisions Draft EAN Technically Reviewed by EDF SQEP | 02-Nov-20 A | 13-Nov-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.A3180 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-08 | 2020-09-21 | Containment Head Document - Supplier prepare and issue Offer | 02-Nov-20 A | 23-Nov-20 A | 10 | 0 | 15 | 100% |  | Completed
ER6661LT | W206 | W206.A3220 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-11 | 2020-09-24 | Supporting Plant - Supplier mobilisation time | 02-Nov-20 A | 13-Nov-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.A2940 | HYA Reactors Shutdown Essential Safety Cases | 2020-08-17 | 2020-08-21 | Seismic Assessment of FPU within Reactor Report Completed and uploaded to CDMS | 02-Nov-20 A | 20-Nov-20 A | 5 | 0 | 14 | 100% |  | Completed
ER6661LT | W206 | W206.A2860 | HYA Reactors Shutdown Essential Safety Cases | 2020-08-13 | 2020-09-10 | Prepare Station Documentation Update Strategy Report | 02-Nov-20 A | 04-Dec-20 A | 20 | 0 | 24 | 100% |  | Completed
ER6661LT | W206 | W206.A2850 | HYA Reactors Shutdown Essential Safety Cases | 2020-08-13 | 2020-11-23 | Station Documentation Update Strategy Report Summary | 02-Nov-20 A | 03-Feb-21 A | 72 | 0 | 64 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18115 | HNB Reactors Shutdown Essential Safety Cases |  |  | Formal Review of Head Documents and Head Document Integration | 02-Nov-20 A | 23-Dec-20 A | 20 | 0 | 37 | 100% |  | Completed
ER6378LT | W222 | W222.A25860 | HRA Fuel Handling Essential Safety Case | 2020-11-02 | 2021-07-28 | Review of Human Factors Assessment of FM Movements during Defuelling Operations ##(Cost Summary)## (C2) (NEW) | 02-Nov-20 A | 28-Jul-21 A | 186 | 0 | 186 | 100% |  | Completed
ER6378LT | W222 | W222.A24780 | HRA Fuel Handling Essential Safety Case | 2020-11-02 | 2020-11-02 | Pre Job Brief for Human Factors Assessment of FM Movements during Defuelling Operations EAN | 02-Nov-20 A | 02-Nov-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A23320 | HRA Fuel Handling Essential Safety Case | 2020-11-02 | 2021-02-01 | Draft Update Core Support Plate Properties Methodology & Toughness Properties EAN | 02-Nov-20 A | 01-Feb-21 A | 42 | 0 | 63 | 100% |  | Completed
ER6371LT | W202 | W202.A6380 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-16 | 2020-11-20 | <NEW SCOPE CR220> Consequences EAN Draft Report Verified by TSA | 02-Nov-20 A | 17-Nov-20 A | 5 | 0 | 11 | 100% |  | Completed
ER6371LT | W202 | W202.A6870 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-19 | 2020-10-30 | <NEW SCOPE CR220> Determination of Cliff Edge Draft Report Verified by TSA | 02-Nov-20 A | 16-Nov-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | W202.A7100 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-16 | 2020-12-03 | <NEW SCOPE CR220> Specification of Multi-Channel MACE Model Summary | 02-Nov-20 A | 15-Feb-21 A | 73 | 0 | 73 | 100% |  | Completed
ER6371LT | W202 | W202.A7110 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-16 | 2020-10-16 | <NEW SCOPE CR220> Specification of Multi-Channel MACE Model Pre-Job Brief | 02-Nov-20 A | 02-Nov-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A6100 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-26 | 2020-11-06 | <NEW SCOPE CR 221> Panther Sensitivity Studies Draft Report Technically Reviewed by EDF SQEP | 02-Nov-20 A | 13-Nov-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.A6380 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-16 | 2020-11-20 | <NEW SCOPE CR 221> Consequences EAN Draft Report Verified by TSA | 02-Nov-20 A | 17-Nov-20 A | 5 | 0 | 11 | 100% |  | Completed
ER6661LT | W206 | W206.A6870 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-19 | 2020-10-30 | <NEW SCOPE CR 221> Determination of Cliff Edge Draft Report Verified by TSA | 02-Nov-20 A | 16-Nov-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.A7100 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-16 | 2021-01-29 | <NEW SCOPE CR 221> Specification of Multi-Channel MACE Model Summary | 02-Nov-20 A | 22-Feb-21 A | 73 | 0 | 77 | 100% |  | Completed
ER6661LT | W206 | W206.A7110 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-16 | 2020-10-16 | <NEW SCOPE CR 221> Specification of Multi-Channel MACE Model Pre-Job Brief | 02-Nov-20 A | 02-Nov-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A23320 | HYA Fuel Handling Essential Safety Case | 2020-11-02 | 2021-02-01 | Draft Update Core Support Plate Properties Methodology & Toughness Properties EAN | 02-Nov-20 A | 01-Feb-21 A | 42 | 0 | 63 | 100% |  | Completed
ER6650LT | W226 | W226.A24780 | HYA Fuel Handling Essential Safety Case | 2020-11-02 | 2020-11-02 | Pre Job Brief for Human Factors Assessment of FM Movements during Defuelling Operations EAN | 02-Nov-20 A | 02-Nov-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A25860 | HYA Fuel Handling Essential Safety Case | 2020-11-02 | 2021-07-28 | Review of Human Factors Assessment of FM Movements during Defuelling Operations ##(Cost Summary)## (C2) (NEW) | 02-Nov-20 A | 28-Jul-21 A | 186 | 0 | 186 | 100% |  | Completed
ER6378LT | W222 | W222.A24790 | HRA Fuel Handling Essential Safety Case | 2020-11-03 | 2020-11-23 | Draft Review of Human Factors Assessment of FM Movements during Defuelling Operations EAN | 03-Nov-20 A | 23-Nov-20 A | 15 | 0 | 14 | 100% |  | Completed
ER6378LT | W222 | W222.A24240 | HRA Fuel Handling Essential Safety Case | 2020-11-03 | 2020-11-20 | Verify Hazards Review EAN and Issue for Technical Review | 03-Nov-20 A | 20-Nov-20 A | 9 | 0 | 13 | 100% |  | Completed
ER6371LT | W202 | W202.A6520 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-16 | 2020-11-20 | <NEW SCOPE CR220> Optioneering EAN Draft Report Verified by TSA | 03-Nov-20 A | 27-Nov-20 A | 5 | 0 | 18 | 100% |  | Completed
ER6371LT | W202 | W202.A7120 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-19 | 2020-10-30 | <NEW SCOPE CR220> Prepare Specification of Multi-Channel MACE Model Draft Report | 03-Nov-20 A | 27-Nov-20 A | 10 | 0 | 18 | 100% |  | Completed
ER6661LT | W206 | W206.A6520 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-16 | 2020-11-20 | <NEW SCOPE CR 221> Optioneering EAN Draft Report Verified by TSA | 03-Nov-20 A | 27-Nov-20 A | 5 | 0 | 18 | 100% |  | Completed
ER6661LT | W206 | W206.A7120 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-19 | 2020-10-30 | <NEW SCOPE CR 221> Prepare Specification of Multi-Channel MACE Model Draft Report | 03-Nov-20 A | 27-Nov-20 A | 10 | 0 | 18 | 100% |  | Completed
ER6650LT | W226 | W226.A24240 | HYA Fuel Handling Essential Safety Case | 2020-11-03 | 2020-11-20 | Verify Hazards Review EAN and Issue for Technical Review | 03-Nov-20 A | 20-Nov-20 A | 9 | 0 | 13 | 100% |  | Completed
ER6650LT | W226 | W226.A24790 | HYA Fuel Handling Essential Safety Case | 2020-11-03 | 2020-11-23 | Draft Review of Human Factors Assessment of FM Movements during Defuelling Operations EAN | 03-Nov-20 A | 23-Nov-20 A | 15 | 0 | 14 | 100% |  | Completed
ER6371LT | W202 | W202.A4470 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-20 | 2021-02-11 | Core Cooling Head Document Summary | 04-Nov-20 A | 10-Aug-21 A | 193 | 0 | 193 | 100% |  | Completed
ER6371LT | W202 | W202.A4480 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-20 | 2020-11-16 | Core Cooling Workshop | 04-Nov-20 A | 06-Jan-21 A | 20 | 0 | 42 | 100% |  | Completed
ER6661LT | W206 | W206.A4470 | HYA Reactors Shutdown Essential Safety Cases | 2021-04-08 | 2022-01-10 | Core Cooling Head Document Summary | 04-Nov-20 A | 09-Aug-21 A | 192 | 0 | 192 | 100% |  | Completed
ER6661LT | W206 | W206.A4480 | HYA Reactors Shutdown Essential Safety Cases | 2021-04-08 | 2021-05-06 | Core Cooling Workshop | 04-Nov-20 A | 06-Jan-21 A | 20 | 0 | 43 | 100% |  | Completed
ER6650LT | W226 | W226.A23010 | HYA Fuel Handling Essential Safety Case | 2020-11-05 | 2020-11-18 | Complete TR Form and Upload Interpretation of MACE for Fuel Route EAN to CDMS | 05-Nov-20 A | 18-Nov-20 A | 3 | 0 | 9 | 100% |  | Completed
ER6378LT | W222 | W222.A23010 | HRA Fuel Handling Essential Safety Case | 2020-11-05 | 2020-11-18 | Complete TR Form and Upload Interpretation of MACE for Fuel Route EAN to CDMS | 05-Nov-20 A | 18-Nov-20 A | 3 | 0 | 9 | 100% |  | Completed
ER6371LT | W202 | W202.A3010 | HRA Reactors Shutdown Essential Safety Cases | 2020-08-20 | 2020-09-10 | TSA Address Comments on TR'd Pressure Boundary Seals Draft Report | 09-Nov-20 A | 18-Nov-20 A | 15 | 0 | 7 | 100% |  | Completed
ER6661LT | W206 | W206.A3010 | HYA Reactors Shutdown Essential Safety Cases | 2020-08-20 | 2020-09-10 | TSA Address Comments on TR'd Pressure Boundary Seals Draft Report | 09-Nov-20 A | 18-Nov-20 A | 15 | 0 | 7 | 100% |  | Completed
ER6378LT | W222 | W222.A23840 | HRA Fuel Handling Essential Safety Case | 2020-11-09 | 2020-11-13 | Supplier Update and Issue Detailed Option Investigation EAN | 09-Nov-20 A | 13-Nov-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A23840 | HYA Fuel Handling Essential Safety Case | 2020-11-09 | 2020-11-13 | Supplier Update and Issue Detailed Option Investigation EAN | 09-Nov-20 A | 13-Nov-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18230 | HNB Reactors Shutdown Essential Safety Cases | 2020-10-22 | 2020-10-28 | <NEW SCOPE CR 187> - RFS - OPEX/ Literature Review - Supplier mobilisation time | 09-Nov-20 A | 13-Nov-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A22880 | HRA Fuel Handling Essential Safety Case |  | 2020-11-10 | Grab Engagement for Low Burn-up Fuel EAN Available | 10-Nov-20 A | 10-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A22880 | HYA Fuel Handling Essential Safety Case |  | 2020-11-10 | Grab Engagement for Low Burn-up Fuel EAN Available | 10-Nov-20 A | 10-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A1180 | HNB Enhanced Defuelling Safety Cases |  | 2020-11-11 | Gate A IRM Paper Approval | 11-Nov-20 A | 11-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A1170 | HNB Enhanced Defuelling Safety Cases | 2020-11-11 | 2020-11-11 | Hold IRM (FEEDS TO SUMMARY SCHEDULE) | 11-Nov-20 A | 11-Nov-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A18180 | HRA Fuel Handling Essential Safety Case | 2020-11-13 | 2020-11-13 | Technical Review of P6.6 Handover Document | 13-Nov-20 A | 13-Nov-20 A | 10 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A18190 | HRA Fuel Handling Essential Safety Case | 2020-11-13 | 2020-11-13 | Supplier Update and Issue P6.6 Handover Document | 13-Nov-20 A | 13-Nov-20 A | 2 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A18200 | HRA Fuel Handling Essential Safety Case | 2020-11-13 | 2021-02-26 | Complete TR Form and Upload P6.6 Handover Document to CDMS | 13-Nov-20 A | 26-Feb-21 A | 2 | 0 | 72 | 100% |  | Completed
ER6650LT | W226 | W226.A18200 | HYA Fuel Handling Essential Safety Case | 2020-11-13 | 2021-02-26 | Complete TR Form and Upload P6.6 Handover Document to CDMS | 13-Nov-20 A | 26-Feb-21 A | 2 | 0 | 72 | 100% |  | Completed
ER6650LT | W226 | W226.A18190 | HYA Fuel Handling Essential Safety Case | 2020-11-13 | 2020-11-13 | Supplier Update and Issue P6.6 Handover Document | 13-Nov-20 A | 13-Nov-20 A | 2 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A18180 | HYA Fuel Handling Essential Safety Case | 2020-11-13 | 2020-11-13 | Technical Review of P6.6 Handover Document | 13-Nov-20 A | 13-Nov-20 A | 10 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2900 | HRA Reactors Shutdown Essential Safety Cases | 2020-08-13 | 2020-08-26 | TSA Address Comments on TR'd General HF Oversight and HFIP Updates and Revisions Draft EAN | 16-Nov-20 A | 20-Nov-20 A | 10 | 0 | 4 | 100% |  | Completed
ER6378LT | W222 | W222.A8880 | HRA Fuel Handling Essential Safety Case | 2020-11-16 | 2021-02-12 | Verification of FPU Lifting Integrity while Handling at the Reactor EAN | 16-Nov-20 A | 12-Feb-21 A | 20 | 0 | 62 | 100% |  | Completed
ER6371LT | W202 | W202.A6880 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-10-30 | <NEW SCOPE CR220> Verified Determination of Cliff Edge Draft Report Issued to EDF for Technical Review. | 16-Nov-20 A | 16-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A6880 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-10-30 | <NEW SCOPE CR 221> Verified Determination of Cliff Edge Draft Report Issued to EDF for Technical Review. | 16-Nov-20 A | 16-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A8880 | HYA Fuel Handling Essential Safety Case | 2020-11-16 | 2021-02-12 | Verification of FPU Lifting Integrity while Handling at the Reactor EAN | 16-Nov-20 A | 12-Feb-21 A | 20 | 0 | 62 | 100% |  | Completed
ER6371LT | W202 | W202.A3450 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-25 | 2020-09-25 | Supporting Plant - Pre Job Brief | 16-Nov-20 A | 19-Nov-20 A | 1 | 0 | 3 | 100% |  | Completed
ER6661LT | W206 | W206.A2900 | HYA Reactors Shutdown Essential Safety Cases | 2020-08-13 | 2020-08-26 | TSA Address Comments on TR'd General HF Oversight and HFIP Updates and Revisions Draft EAN | 16-Nov-20 A | 18-Nov-20 A | 10 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A3450 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-25 | 2020-09-25 | Supporting Plant - Pre Job Brief | 16-Nov-20 A | 19-Nov-20 A | 1 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1540 | HNB Reactors Shutdown Essential Safety Cases |  |  | SQEP verification (2nd/3rd/4th/5th round review) Summary | 16-Nov-20 A | 05-May-21 A | 82 | 0 | 117 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17880 | HNB Reactors Shutdown Essential Safety Cases |  |  | Second Round of Verification - David Powada | 16-Nov-20 A | 27-Nov-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6378LT | W222 | W222.A23850 | HRA Fuel Handling Essential Safety Case | 2020-11-16 | 2020-11-20 | Complete TR Form and Upload Detailed Option Investigation EAN to CDMS | 16-Nov-20 A | 20-Nov-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A6890 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-02 | 2020-11-13 | <NEW SCOPE CR220> Determination of Cliff Edge Draft Report Technically Reviewed by EDF SQEP | 16-Nov-20 A | 18-Dec-20 A | 10 | 0 | 24 | 100% |  | Completed
ER6661LT | W206 | W206.A6110 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-09 | 2020-11-20 | <NEW SCOPE CR 221> TSA Address Comments on TR'd Panther Sensitivity Studies Draft Report | 16-Nov-20 A | 30-Nov-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | W226.A23850 | HYA Fuel Handling Essential Safety Case | 2020-11-16 | 2020-11-20 | Complete TR Form and Upload Detailed Option Investigation EAN to CDMS | 16-Nov-20 A | 20-Nov-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18240 | HNB Reactors Shutdown Essential Safety Cases | 2020-10-29 | 2020-10-29 | <NEW SCOPE CR 187> - RFS - OPEX/ Literature Review - Pre Job Brief | 16-Nov-20 A | 16-Nov-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A6890 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-02 | 2020-11-13 | <NEW SCOPE CR 221> Determination of Cliff Edge Draft Report Technically Reviewed by EDF SQEP | 17-Nov-20 A | 18-Dec-20 A | 10 | 0 | 23 | 100% |  | Completed
ER6661LT | W206 | W206.A3470 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-28 | 2020-10-23 | Prepare Supporting Plant | 17-Nov-20 A | 18-Dec-20 A | 20 | 0 | 23 | 100% |  | Completed
ER6661LT | W206 | W206.A3460 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-28 | 2021-03-03 | Boiler Control and Protection Summary | 17-Nov-20 A | 26-Apr-21 A | 110 | 0 | 110 | 100% |  | Completed
ER6371LT | W202 | W202.A6110 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-09 | 2020-11-20 | <NEW SCOPE CR220> TSA Address Comments on TR'd Panther Sensitivity Studies Draft Report | 17-Nov-20 A | 30-Nov-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18250 | HNB Reactors Shutdown Essential Safety Cases | 2020-10-30 | 2021-01-05 | <NEW SCOPE CR 187> - OPEX/ Literature Review - Summary | 17-Nov-20 A | 26-Feb-21 A | 84 | 0 | 70 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18290 | HNB Reactors Shutdown Essential Safety Cases | 2020-10-30 | 2020-11-26 | <NEW SCOPE CR 187> - OPEX/ Literature Review - Prepare Draft EAN | 17-Nov-20 A | 02-Feb-21 A | 20 | 0 | 52 | 100% |  | Completed
ER6371LT | W202 | W202.A3200 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-09-10 | TSA Issue Final Pressure Boundary Seals Report | 18-Nov-20 A | 18-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3200 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-09-10 | TSA Issue Final Pressure Boundary Seals Report | 18-Nov-20 A | 18-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3080 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-08-26 | TSA Issue Final General HF Oversight and HFIP Updates and Revisions EAN | 18-Nov-20 A | 18-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A2130 | HNB Reactors Shutdown Essential Safety Cases |  |  | First round comments addressed and revised draft re-circulated | 18-Nov-20 A | 18-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A23020 | HRA Fuel Handling Essential Safety Case |  | 2020-11-18 | Interpretation of MACE for Fuel Route EAN Available | 18-Nov-20 A | 18-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A23020 | HYA Fuel Handling Essential Safety Case |  | 2020-11-18 | Interpretation of MACE for Fuel Route EAN Available | 18-Nov-20 A | 18-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A26560 | HRA Fuel Handling Essential Safety Case | 2020-11-18 | 2021-07-08 | Draft Human Factors Integration Plan EAN (REV 001) | 18-Nov-20 A | 08-Jul-21 A | 10 | 0 | 160 | 100% |  | Completed
ER6650LT | W226 | W226.A26560 | HYA Fuel Handling Essential Safety Case | 2020-11-18 | 2021-07-08 | Draft Human Factors Integration Plan EAN (REV 001) | 18-Nov-20 A | 08-Jul-21 A | 10 | 0 | 160 | 100% |  | Completed
ER6371LT | W202 | W202.A3230 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-11 | 2020-09-24 | Pressure Boundary Seals Report TR Completed and uploaded to CDMS | 19-Nov-20 A | 23-Nov-20 A | 10 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A3230 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-11 | 2020-09-24 | Pressure Boundary Seals Report TR Completed and uploaded to CDMS | 19-Nov-20 A | 23-Nov-20 A | 10 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A3110 | HYA Reactors Shutdown Essential Safety Cases | 2020-08-27 | 2020-09-10 | General HF Oversight and HFIP Updates and Revisions EAN TR Completed and uploaded to CDMS | 19-Nov-20 A | 23-Nov-20 A | 10 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A3110 | HRA Reactors Shutdown Essential Safety Cases | 2020-08-27 | 2020-09-10 | General HF Oversight and HFIP Updates and Revisions EAN TR Completed and uploaded to CDMS | 20-Nov-20 A | 23-Nov-20 A | 10 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A3470 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-28 | 2020-10-23 | Prepare Supporting Plant | 20-Nov-20 A | 18-Dec-20 A | 20 | 0 | 20 | 100% |  | Completed
ER6371LT | W202 | W202.A3460 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-28 | 2020-12-18 | Boiler Control and Protection Summary | 20-Nov-20 A | 26-Apr-21 A | 110 | 0 | 107 | 100% |  | Completed
ER6371LT | W202 | W202.A3030 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-08-21 | Seismic Assessment of FPU within Reactor Report Completed | 20-Nov-20 A | 20-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3030 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-08-21 | Seismic Assessment of FPU within Reactor Report Completed | 20-Nov-20 A | 20-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A22780 | HRA Fuel Handling Essential Safety Case | 2020-11-20 | 2020-12-04 | Technical Review of Lifting Integrity Life Limits EAN | 20-Nov-20 A | 04-Dec-20 A | 15 | 0 | 11 | 100% |  | Completed
ER6650LT | W226 | W226.A22780 | HYA Fuel Handling Essential Safety Case | 2020-11-20 | 2020-12-04 | Technical Review of Lifting Integrity Life Limits EAN | 20-Nov-20 A | 04-Dec-20 A | 15 | 0 | 11 | 100% |  | Completed
ER6378LT | W222 | W222.A23860 | HRA Fuel Handling Essential Safety Case |  | 2020-11-20 | Detailed Option Investigation EAN Available | 20-Nov-20 A | 20-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A23860 | HYA Fuel Handling Essential Safety Case |  | 2020-11-20 | Detailed Option Investigation EAN Available | 20-Nov-20 A | 20-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3420 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-09-24 | Pressure Boundary Seals Report Completed | 23-Nov-20 A | 23-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3190 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-09-10 | General HF Oversight and HFIP EAN Completed | 23-Nov-20 A | 23-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3420 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-09-24 | Pressure Boundary Seals Report Completed | 23-Nov-20 A | 23-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3190 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-09-10 | General HF Oversight and HFIP EAN Completed | 23-Nov-20 A | 23-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A24250 | HRA Fuel Handling Essential Safety Case | 2020-11-23 | 2021-04-06 | Technical Review of Hazards Review EAN | 23-Nov-20 A | 06-Apr-21 A | 10 | 0 | 92 | 100% |  | Completed
ER6371LT | W202 | W202.A6390 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-11-20 | <NEW SCOPE CR220> Verified Consequences EAN Draft Report Issued to EDF for Technical Review. | 23-Nov-20 A | 23-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A6390 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-11-20 | <NEW SCOPE CR 221> Verified Consequences EAN Draft Report Issued to EDF for Technical Review. | 23-Nov-20 A | 23-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A24250 | HYA Fuel Handling Essential Safety Case | 2020-11-23 | 2021-04-06 | Technical Review of Hazards Review EAN | 23-Nov-20 A | 06-Apr-21 A | 10 | 0 | 92 | 100% |  | Completed
ER6371LT | W202 | W202.A6720 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-19 | 2020-10-30 | <NEW SCOPE CR220> Specified Flows Draft Report Verified by TSA | 23-Nov-20 A | 14-Dec-20 A | 10 | 0 | 15 | 100% |  | Completed
ER6661LT | W206 | W206.A6720 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-19 | 2020-10-30 | <NEW SCOPE CR 221> Specified Flows Draft Report Verified by TSA | 23-Nov-20 A | 14-Dec-20 A | 10 | 0 | 15 | 100% |  | Completed
ER6371LT | W202 | W202.A3400 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-22 | 2020-09-28 | Containment Head Document - Review Offer, prepare and issue CI | 24-Nov-20 A | 17-Dec-20 A | 5 | 0 | 18 | 100% |  | Completed
ER6661LT | W206 | W206.A3400 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-22 | 2020-09-28 | Containment Head Document - Review Offer, prepare and issue CI | 24-Nov-20 A | 17-Dec-20 A | 5 | 0 | 17 | 100% |  | Completed
ER6378LT | W222 | W222.A24800 | HRA Fuel Handling Essential Safety Case | 2020-11-24 | 2021-05-26 | Verify Human Factors Assessment of FM Movements during Defuelling Operations EAN & Issue for Technical Review | 24-Nov-20 A | 26-May-21 A | 15 | 0 | 125 | 100% |  | Completed
ER6371LT | W202 | W202.A6400 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-23 | 2020-12-04 | <NEW SCOPE CR220> Consequences EAN Draft Report Technically Reviewed by EDF SQEP | 24-Nov-20 A | 04-Dec-20 A | 10 | 0 | 9 | 100% |  | Completed
ER6661LT | W206 | W206.A6400 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-23 | 2020-12-04 | <NEW SCOPE CR 221> Consequences EAN Draft Report Technically Reviewed by EDF SQEP | 24-Nov-20 A | 04-Dec-20 A | 10 | 0 | 8 | 100% |  | Completed
ER6650LT | W226 | W226.A24800 | HYA Fuel Handling Essential Safety Case | 2020-11-24 | 2021-05-26 | Verify Human Factors Assessment of FM Movements during Defuelling Operations EAN & Issue for Technical Review | 24-Nov-20 A | 26-May-21 A | 15 | 0 | 125 | 100% |  | Completed
ER6371LT | W202 | W202.A3080 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-08-26 | TSA Issue Final General HF Oversight and HFIP Updates and Revisions EAN | 27-Nov-20 A | 27-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A6530 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-11-20 | <NEW SCOPE CR220> Verified Optioneering EAN Draft Report Issued to EDF for Technical Review. | 27-Nov-20 A | 27-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A6530 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-11-20 | <NEW SCOPE CR 221> Verified Optioneering EAN Draft Report Issued to EDF for Technical Review. | 27-Nov-20 A | 27-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A4150 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-01-08 | Issue Reactor Internals and Structural Integrity during Defuelling Report to EDF Review. | 27-Nov-20 A | 27-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4150 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-01-08 | Issue Reactor Internals and Structural Integrity during Defuelling Report to EDF Review. | 27-Nov-20 A | 27-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A4340 | HRA Reactors Shutdown Essential Safety Cases | 2021-02-25 | 2021-03-31 | Prepare Optioneering Forming Report | 30-Nov-20 A | 18-Dec-20 A | 14 | 0 | 14 | 100% |  | Completed
ER6371LT | W202 | W202.A4330 | HRA Reactors Shutdown Essential Safety Cases | 2021-02-25 | 2021-06-22 | Optioneering Forming Report Summary | 30-Nov-20 A | 09-Feb-21 A | 52 | 0 | 49 | 100% |  | Completed
ER6661LT | W206 | W206.A4340 | HYA Reactors Shutdown Essential Safety Cases | 2021-02-25 | 2021-03-31 | Prepare Optioneering Forming Report | 30-Nov-20 A | 18-Dec-20 A | 14 | 0 | 14 | 100% |  | Completed
ER6661LT | W206 | W206.A4330 | HYA Reactors Shutdown Essential Safety Cases | 2021-02-25 | 2021-05-12 | Optioneering Forming Report Summary | 30-Nov-20 A | 09-Feb-21 A | 52 | 0 | 49 | 100% |  | Completed
ER6371LT | W202 | W202.A6540 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-23 | 2020-12-04 | <NEW SCOPE CR220> Optioneering EAN Draft Report Technically Reviewed by EDF SQEP | 30-Nov-20 A | 08-Dec-20 A | 10 | 0 | 6 | 100% |  | Completed
ER6371LT | W202 | W202.A7040 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-11-06 | <NEW SCOPE CR220> Verified Corroborated Approach Draft Report Issued to EDF for Technical Review. | 30-Nov-20 A | 30-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A6120 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-11-20 | <NEW SCOPE CR 221> TSA Issue Final Panther Sensitivity Studies Report | 30-Nov-20 A | 30-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A6540 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-23 | 2020-12-04 | <NEW SCOPE CR 221> Optioneering EAN Draft Report Technically Reviewed by EDF SQEP | 30-Nov-20 A | 08-Dec-20 A | 10 | 0 | 6 | 100% |  | Completed
ER6661LT | W206 | W206.A7040 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-11-06 | <NEW SCOPE CR 221> Verified Corroborated Approach Draft Report Issued to EDF for Technical Review. | 30-Nov-20 A | 30-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A4160 | HRA Reactors Shutdown Essential Safety Cases | 2021-01-11 | 2021-01-22 | Reactor Internals and Structural Integrity during Defuelling Report Reviewed by EDF SQEP | 30-Nov-20 A | 18-Dec-20 A | 10 | 0 | 15 | 100% |  | Completed
ER6661LT | W206 | W206.A4160 | HYA Reactors Shutdown Essential Safety Cases | 2021-01-11 | 2021-01-22 | Reactor Internals and Structural Integrity during Defuelling Report Reviewed by EDF SQEP | 30-Nov-20 A | 18-Dec-20 A | 10 | 0 | 14 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1550 | HNB Reactors Shutdown Essential Safety Cases |  |  | Resolution meeting held | 30-Nov-20 A | 30-Nov-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A6120 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-11-20 | <NEW SCOPE CR220> TSA Issue Final Panther Sensitivity Studies Report | 30-Nov-20 A | 30-Nov-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3380 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-21 | 2020-10-23 | Prepare Summary of Compliance with RADWASTE Assessment Principles Draft EAN | 01-Dec-20 A | 07-Jan-21 A | 25 | 0 | 25 | 100% |  | Completed
ER6371LT | W202 | W202.A3360 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-21 | 2021-06-22 | Environmental Permitting and Permissioing Scoping and Stakeholder Engagement | 01-Dec-20 A | 11-Feb-21 A | 65 | 0 | 50 | 100% |  | Completed
ER6371LT | W202 | W202.A3370 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-21 | 2020-12-18 | Summary of Compliance with RADWASTE Assessment Principles Summary | 01-Dec-20 A | 11-Feb-21 A | 50 | 0 | 50 | 100% |  | Completed
ER6371LT | W202 | W202.A3840 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-09 | 2020-11-10 | RAWG Endorsement | 01-Dec-20 A | 20-Aug-21 A | 2 | 0 | 181 | 100% |  | Completed
ER6661LT | W206 | W206.A3380 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-21 | 2020-10-23 | Prepare Summary of Compliance with RADWASTE Assessment Principles Draft EAN | 01-Dec-20 A | 07-Jan-21 A | 25 | 0 | 25 | 100% |  | Completed
ER6661LT | W206 | W206.A3360 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-21 | 2021-06-22 | Environmental Permitting and Permissioing Scoping and Stakeholder Engagement | 01-Dec-20 A | 11-Feb-21 A | 44 | 0 | 50 | 100% |  | Completed
ER6661LT | W206 | W206.A3370 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-21 | 2020-11-27 | Summary of Compliance with RADWASTE Assessment Principles Summary | 01-Dec-20 A | 11-Feb-21 A | 50 | 0 | 50 | 100% |  | Completed
ER6661LT | W206 | W206.A3840 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-09 | 2020-11-10 | RAWG Endorsement | 01-Dec-20 A | 20-Aug-21 A | 2 | 0 | 181 | 100% |  | Completed
ER6378LT | W222 | W222.A12520 | HRA Fuel Handling Essential Safety Case | 2020-12-01 | 2021-01-04 | Verify Management Strategy for Pond Water Treatment Arisings EAN and Issue for Technical Review | 01-Dec-20 A | 04-Jan-21 A | 10 | 0 | 21 | 100% |  | Completed
ER6378LT | W222 | W222.AXXX01 | HRA Fuel Handling Essential Safety Case | 2020-12-01 | 2021-09-30 | Programme Manager ##(Cost Summary)## | 01-Dec-20 A | 30-Sep-21 A | 365 | 0 | 209 | 100% |  | Completed
ER6371LT | W202 | W202.A7050 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-09 | 2020-11-20 | <NEW SCOPE CR220> Corroborated Approach Draft Report Technically Reviewed by EDF SQEP | 01-Dec-20 A | 31-Dec-20 A | 21 | 0 | 20 | 100% |  | Completed
ER6661LT | W206 | W206.A7050 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-09 | 2020-11-20 | <NEW SCOPE CR 221> Corroborated Approach Draft Report Technically Reviewed by EDF SQEP | 01-Dec-20 A | 31-Dec-20 A | 21 | 0 | 20 | 100% |  | Completed
ER6378LT | W222 | W222.A27100 | HRA Fuel Handling Essential Safety Case | 2020-12-01 |  | External Programme Manager START MILESTONE | 01-Dec-20 A | 01-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27100 | HYA Fuel Handling Essential Safety Case | 2020-12-01 |  | External Programme Manager START MILESTONE | 01-Dec-20 A | 01-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.AXXX01 | HYA Fuel Handling Essential Safety Case | 2020-12-01 | 2021-09-30 | Programme Manager ##(Cost Summary)## | 01-Dec-20 A | 30-Sep-21 A | 365 | 0 | 209 | 100% |  | Completed
ER6650LT | W226 | W226.A12520 | HYA Fuel Handling Essential Safety Case | 2020-12-01 | 2021-01-04 | Verify Management Strategy for Pond Water Treatment Arisings EAN and Issue for Technical Review | 01-Dec-20 A | 04-Jan-21 A | 10 | 0 | 21 | 100% |  | Completed
ER6650LT | W226 | W226.A25350 | HYA Fuel Handling Essential Safety Case | 2020-12-01 | 2021-06-02 | Draft Update to Fault Schedule/PSA (REV 000) EAN | 01-Dec-20 A | 02-Jun-21 A | 11 | 0 | 125 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1560 | HNB Reactors Shutdown Essential Safety Cases |  |  | Second/Third round comments addressed (author) | 01-Dec-20 A | 22-Jan-21 A | 10 | 0 | 35 | 100% |  | Completed
ER6378LT | W222 | W222.A25350 | HRA Fuel Handling Essential Safety Case | 2020-12-01 | 2021-06-02 | Draft Update to Fault Schedule/PSA (REV 000) EAN | 01-Dec-20 A | 02-Jun-21 A | 49 | 0 | 125 | 100% |  | Completed
ER6378LT | W222 | W222.A23720 | HRA Fuel Handling Essential Safety Case |  | 2020-12-01 | Confirm Acceptability of CSP Pillars EAN Available | 01-Dec-20 A | 01-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A23720 | HYA Fuel Handling Essential Safety Case |  | 2020-12-01 | Confirm Acceptability of CSP Pillars EAN Available | 01-Dec-20 A | 01-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A25850 | HRA Fuel Handling Essential Safety Case | 2020-12-02 | 2021-06-25 | Human Factors Assessment of Dropped FPU Fault Sequences ##(Cost Summary)## (C2) (NEW) | 02-Dec-20 A | 25-Jun-21 A | 142 | 0 | 141 | 100% |  | Completed
ER6378LT | W222 | W222.A24710 | HRA Fuel Handling Essential Safety Case | 2020-12-02 | 2020-12-02 | Pre Job Brief for Human Factors Assessment of Dropped FPU Fault Sequences EAN | 02-Dec-20 A | 02-Dec-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A24710 | HYA Fuel Handling Essential Safety Case | 2020-12-02 | 2020-12-02 | Pre Job Brief for Human Factors Assessment of Dropped FPU Fault Sequences EAN | 02-Dec-20 A | 02-Dec-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25850 | HYA Fuel Handling Essential Safety Case | 2020-12-02 | 2021-06-25 | Human Factors Assessment of Dropped FPU Fault Sequences ##(Cost Summary)## (C2) (NEW) | 02-Dec-20 A | 25-Jun-21 A | 142 | 0 | 141 | 100% |  | Completed
ER6378LT | W222 | W222.A23640 | HRA Fuel Handling Essential Safety Case | 2020-12-02 | 2020-12-02 | Complete and Upload Quality of Build Considerations (Task File Note) | 02-Dec-20 A | 02-Dec-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A16930 | HRA Fuel Handling Essential Safety Case | 2020-12-02 | 2020-12-02 | Unverified Skeleton Road Map Shared with EDF Energy | 02-Dec-20 A | 02-Dec-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A16930 | HYA Fuel Handling Essential Safety Case | 2020-12-02 | 2020-12-02 | Unverified Skeleton Road Map Shared with EDF Energy | 02-Dec-20 A | 02-Dec-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A23640 | HYA Fuel Handling Essential Safety Case | 2020-12-02 | 2020-12-02 | Complete TR Form and Upload Quality of Build Considerations (Task File Note) | 02-Dec-20 A | 02-Dec-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A23650 | HRA Fuel Handling Essential Safety Case |  | 2020-12-02 | Quality of Build Considerations (Task File Note) Available | 02-Dec-20 A | 02-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A23650 | HYA Fuel Handling Essential Safety Case |  | 2020-12-02 | Quality of Build Considerations (Task File Note) Available | 02-Dec-20 A | 02-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A24720 | HRA Fuel Handling Essential Safety Case | 2020-12-03 | 2021-02-01 | Draft Review of Human Factors Assessment of Dropped FPU Fault Sequences EAN | 03-Dec-20 A | 01-Feb-21 A | 15 | 0 | 40 | 100% |  | Completed
ER6378LT | W222 | W222.A9800 | HRA Fuel Handling Essential Safety Case | 2020-12-03 | 2021-03-25 | Technical Review of Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN | 03-Dec-20 A | 25-Mar-21 A | 11 | 0 | 77 | 100% |  | Completed
ER6650LT | W226 | W226.A9800 | HYA Fuel Handling Essential Safety Case | 2020-12-03 | 2021-03-25 | Technical Review of Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN | 03-Dec-20 A | 25-Mar-21 A | 11 | 0 | 77 | 100% |  | Completed
ER6650LT | W226 | W226.A24720 | HYA Fuel Handling Essential Safety Case | 2020-12-03 | 2021-02-01 | Draft Review of Human Factors Assessment of Dropped FPU Fault Sequences EAN | 03-Dec-20 A | 01-Feb-21 A | 15 | 0 | 40 | 100% |  | Completed
ER6370LT | W201 | W201.1000 | HNB Reactors Shutdown Essential Safety Cases |  |  | CAT 1 SC Proposal Revised Draft | 04-Dec-20 A | 23-Dec-20 A | 14 | 0 | 14 | 100% |  | Completed
ER6370LT | W201 | W201.1010 | HNB Reactors Shutdown Essential Safety Cases |  |  | Prepare Verified Task File Notes | 04-Dec-20 A | 16-Dec-20 A | 9 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | W201.1030 | HNB Reactors Shutdown Essential Safety Cases |  |  | Prepare FPU Slot Modelling Technical Reference | 04-Dec-20 A | 30-Dec-20 A | 17 | 0 | 17 | 100% |  | Completed
ER6370LT | W201 | W201.1070 | HNB Reactors Shutdown Essential Safety Cases |  |  | Prepare changes to PVCW Isolation Paper | 04-Dec-20 A | 23-Dec-20 A | 14 | 0 | 14 | 100% |  | Completed
ER6370LT | W201 | W201.1080 | HNB Reactors Shutdown Essential Safety Cases |  |  | Address minor residual comments | 04-Dec-20 A | 23-Dec-20 A | 14 | 0 | 14 | 100% |  | Completed
ER6378LT | W222 | W222.A26870 | HRA Fuel Handling Essential Safety Case |  | 2020-12-04 | Issue Scheme Paper to IRM Members | 04-Dec-20 A | 04-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A26870 | HYA Fuel Handling Essential Safety Case |  | 2020-12-04 | Issue Scheme Paper to IRM Members | 04-Dec-20 A | 04-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3210 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-11 | 2020-09-24 | Station Documentation Update Strategy Report Verified by TSA | 07-Dec-20 A | 18-Dec-20 A | 10 | 0 | 9 | 100% |  | Completed
ER6661LT | W206 | W206.A3210 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-11 | 2020-09-24 | Station Documentation Update Strategy Report Verified by TSA | 07-Dec-20 A | 18-Dec-20 A | 10 | 0 | 9 | 100% |  | Completed
ER6661LT | W206 | W206.A6410 | HYA Reactors Shutdown Essential Safety Cases | 2020-12-07 | 2020-12-18 | <NEW SCOPE CR 221> TSA Address Comments on TR'd Consequences EAN Draft Report | 07-Dec-20 A | 18-Dec-20 A | 10 | 0 | 9 | 100% |  | Completed
ER6378LT | W222 | W222.A22790 | HRA Fuel Handling Essential Safety Case | 2020-12-07 | 2020-12-11 | Supplier Update and Issue Lifting Integrity Life Limits EAN | 07-Dec-20 A | 11-Dec-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6371LT | W202 | W202.A6410 | HRA Reactors Shutdown Essential Safety Cases | 2020-12-07 | 2020-12-18 | <NEW SCOPE CR220> TSA Address Comments on TR'd Consequences EAN Draft Report | 07-Dec-20 A | 18-Dec-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6378LT | W222 | W222.A26880 | HRA Fuel Handling Essential Safety Case | 2020-12-07 | 2020-12-11 | IRM Members Review Sceme Paper Documentation | 07-Dec-20 A | 11-Dec-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A26880 | HYA Fuel Handling Essential Safety Case | 2020-12-07 | 2020-12-11 | IRM Members Review Sceme Paper Documentation | 07-Dec-20 A | 11-Dec-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A22790 | HYA Fuel Handling Essential Safety Case | 2020-12-07 | 2020-12-11 | Supplier Update and Issue Lifting Integrity Life Limits EAN | 07-Dec-20 A | 11-Dec-20 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18100 | HNB Reactors Shutdown Essential Safety Cases |  |  | Programme Review | 09-Dec-20 A | 09-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A22930 | HRA Fuel Handling Essential Safety Case | 2020-12-10 | 2020-12-10 | Supplier Update and Issue Damage and Thermal Analysis Dropped Fuel EAN | 10-Dec-20 A | 10-Dec-20 A | 5 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A22940 | HRA Fuel Handling Essential Safety Case | 2020-12-10 | 2020-12-10 | Complete TR Form and Upload Damage and Thermal Analysis Dropped Fuel EAN to CDMS | 10-Dec-20 A | 10-Dec-20 A | 5 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A22940 | HYA Fuel Handling Essential Safety Case | 2020-12-10 | 2020-12-10 | Complete TR Form and Upload Damage and Thermal Analysis Dropped Fuel EAN to CDMS | 10-Dec-20 A | 10-Dec-20 A | 5 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A22930 | HYA Fuel Handling Essential Safety Case | 2020-12-10 | 2020-12-10 | Supplier Update and Issue Damage and Thermal Analysis Dropped Fuel EAN | 10-Dec-20 A | 10-Dec-20 A | 5 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A24740 | HRA Fuel Handling Essential Safety Case | 2020-12-10 | 2021-02-02 | EDF review draft & scope Human Reliability Assessment of Unsubstantiated Claims | 10-Dec-20 A | 02-Feb-21 A | 1 | 0 | 36 | 100% |  | Completed
ER6650LT | W226 | W226.A24740 | HYA Fuel Handling Essential Safety Case | 2020-12-10 | 2021-02-02 | EDF review draft & scope Human Reliability Assessment of Unsubstantiated Claims | 10-Dec-20 A | 02-Feb-21 A | 36 | 0 | 36 | 100% |  | Completed
ER6370LT | W201 | W201.1050 | HNB Reactors Shutdown Essential Safety Cases |  |  | Implementation Meeting | 10-Dec-20 A | 10-Dec-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A22950 | HRA Fuel Handling Essential Safety Case |  | 2020-12-10 | Damage and Thermal Analysis Dropped Fuel EAN Available | 10-Dec-20 A | 10-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A22950 | HYA Fuel Handling Essential Safety Case |  | 2020-12-10 | Damage and Thermal Analysis Dropped Fuel EAN Available | 10-Dec-20 A | 10-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A24530 | HRA Fuel Handling Essential Safety Case | 2020-12-11 | 2020-12-11 | Technical Review of Review of Interlock Maintenance Review EAN (DRAFT) | 11-Dec-20 A | 11-Dec-20 A | 15 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A24540 | HRA Fuel Handling Essential Safety Case | 2020-12-11 | 2020-12-11 | Supplier Update and Issue Review of Interlock Maintenance Review EAN (DRAFT) | 11-Dec-20 A | 11-Dec-20 A | 5 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A24550 | HRA Fuel Handling Essential Safety Case | 2020-12-11 | 2020-12-11 | Complete Review of Interlock Maintenance Review EAN to CDMS (DRAFT) | 11-Dec-20 A | 11-Dec-20 A | 5 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A24560 | HRA Fuel Handling Essential Safety Case |  | 2020-12-11 | Review of Interlock Maintenance Review EAN Available (DRAFT) | 11-Dec-20 A | 11-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A24560 | HYA Fuel Handling Essential Safety Case |  | 2020-12-11 | Review of Interlock Maintenance Review EAN Available (DRAFT) | 11-Dec-20 A | 11-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A24550 | HYA Fuel Handling Essential Safety Case | 2020-12-11 | 2020-12-11 | Complete Review of Interlock Maintenance Review EAN to CDMS (DRAFT) | 11-Dec-20 A | 11-Dec-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A24540 | HYA Fuel Handling Essential Safety Case | 2020-12-11 | 2020-12-11 | Supplier Update and Issue Review of Interlock Maintenance Review EAN (DRAFT) | 11-Dec-20 A | 11-Dec-20 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A24530 | HYA Fuel Handling Essential Safety Case | 2020-12-11 | 2020-12-11 | Technical Review of Review of Interlock Maintenance Review EAN (DRAFT) | 11-Dec-20 A | 11-Dec-20 A | 15 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A22800 | HRA Fuel Handling Essential Safety Case | 2020-12-11 | 2020-12-18 | Complete TR Form & Upload Lifting Integrity Life Limits EAN to CDMS | 11-Dec-20 A | 18-Dec-20 A | 1 | 0 | 6 | 100% |  | Completed
ER6650LT | W226 | W226.A22800 | HYA Fuel Handling Essential Safety Case | 2020-12-11 | 2020-12-18 | Complete TR Form & Upload Lifting Integrity Life Limits EAN to CDMS | 11-Dec-20 A | 18-Dec-20 A | 1 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | W201.1060 | HNB Reactors Shutdown Essential Safety Cases |  |  | Revise Implementation Appendix | 11-Dec-20 A | 23-Dec-20 A | 9 | 0 | 9 | 100% |  | Completed
ER6371LT | W202 | W202.A6730 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-10-30 | <NEW SCOPE CR220> Verified Specified Flows Draft Report Issued to EDF for Technical Review. | 14-Dec-20 A | 14-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A6730 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-10-30 | <NEW SCOPE CR 221> Verified Specified Flows Draft Report Issued to EDF for Technical Review. | 14-Dec-20 A | 14-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A11360 | HRA Fuel Handling Essential Safety Case | 2020-12-14 | 2021-01-25 | Technical Review of Justification for Pressure Boundary EAN | 14-Dec-20 A | 25-Jan-21 A | 22 | 0 | 28 | 100% |  | Completed
ER6650LT | W226 | W226.A11360 | HYA Fuel Handling Essential Safety Case | 2020-12-14 | 2021-01-25 | Technical Review of Justification for Pressure Boundary EAN | 14-Dec-20 A | 25-Jan-21 A | 22 | 0 | 27 | 100% |  | Completed
ER6371LT | W202 | W202.A6740 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-02 | 2020-11-13 | <NEW SCOPE CR220> Specified Flows Draft Report Technically Reviewed by EDF SQEP | 15-Dec-20 A | 15-Jan-21 A | 10 | 0 | 21 | 100% |  | Completed
ER6661LT | W206 | W206.A6740 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-02 | 2020-11-13 | <NEW SCOPE CR 221> Specified Flows Draft Report Technically Reviewed by EDF SQEP | 15-Dec-20 A | 15-Jan-21 A | 10 | 0 | 21 | 100% |  | Completed
ER6371LT | W202 | W202.A3140 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-02 | 2020-09-15 | Shutdown Margin Head Document Verified by TSA | 15-Dec-20 A | 30-Dec-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.A3140 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-02 | 2020-09-15 | Shutdown Margin Head Document Verified by TSA | 15-Dec-20 A | 30-Dec-20 A | 10 | 0 | 10 | 100% |  | Completed
ER6378LT | W222 | W222.A26840 | HRA Fuel Handling Essential Safety Case |  | 2020-12-15 | Gate B+ for Region 1 - HYA HRA Defuelling Fuel Handling Essential Safety Case | 15-Dec-20 A | 15-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A26890 | HRA Fuel Handling Essential Safety Case | 2020-12-15 | 2020-12-15 | Hold IRM Meeting | 15-Dec-20 A | 15-Dec-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A26890 | HYA Fuel Handling Essential Safety Case | 2020-12-15 | 2020-12-15 | Hold IRM Meeting | 15-Dec-20 A | 15-Dec-20 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18260 | HNB Reactors Shutdown Essential Safety Cases | 2020-11-27 | 2020-12-17 | <NEW SCOPE CR 187> - Prepare Vibration in the FPU Report | 15-Dec-20 A | 22-Mar-21 A | 15 | 0 | 66 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18255 | HNB Reactors Shutdown Essential Safety Cases | 2020-11-27 | 2021-01-19 | <NEW SCOPE CR 187> - Vibration in the FPU Report - Summary | 15-Dec-20 A | 05-May-21 A | 99 | 0 | 96 | 100% |  | Completed
ER6378LT | W222 | W222.A27060 | HRA Fuel Handling Essential Safety Case |  | 2020-12-15 | Gate B IRM Approval | 15-Dec-20 A | 15-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27060 | HYA Fuel Handling Essential Safety Case |  | 2020-12-15 | Gate B IRM Approval | 15-Dec-20 A | 15-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A26840 | HYA Fuel Handling Essential Safety Case |  | 2020-12-15 | Gate B+ for Region 1 - HYA HRA Defuelling Fuel Handling Essential Safety Case | 15-Dec-20 A | 15-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A8240 | HRA Fuel Handling Essential Safety Case | 2020-12-16 | 2021-01-22 | Technical Review of Defuelling Cooling and Match Analysis (Task FIle Note) | 16-Dec-20 A | 22-Jan-21 A | 10 | 0 | 25 | 100% |  | Completed
ER6650LT | W226 | W226.A8240 | HYA Fuel Handling Essential Safety Case | 2020-12-16 | 2021-01-22 | Technical Review of Defuelling Cooling and Match Analysis (Task FIle Note) | 16-Dec-20 A | 22-Jan-21 A | 10 | 0 | 25 | 100% |  | Completed
ER6370LT | W201 | W201.1020 | HNB Reactors Shutdown Essential Safety Cases |  |  | Summary Text fir CAT 1 Paper | 17-Dec-20 A | 23-Dec-20 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A3490 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-29 | 2020-10-12 | Containment Head Document - Supplier mobilisation time | 18-Dec-20 A | 04-Jan-21 A | 10 | 0 | 8 | 100% |  | Completed
ER6371LT | W202 | W202.A3410 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-09-24 | Verified Station Documentation Update Strategy Report Issued to EDF for Technical Review. | 18-Dec-20 A | 18-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3430 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-25 | 2020-10-08 | Station Documentation Update Strategy Report Technically Reviewed by EDF SQEP | 18-Dec-20 A | 29-Jan-21 A | 18 | 0 | 27 | 100% |  | Completed
ER6661LT | W206 | W206.A4430 | HYA Reactors Shutdown Essential Safety Cases | 2021-04-01 | 2021-04-23 | Optioneering Forming Report Verified by TSA | 18-Dec-20 A | 06-Jan-21 A | 15 | 0 | 11 | 100% |  | Completed
ER6661LT | W206 | W206.A3490 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-29 | 2020-10-12 | Containment Head Document - Supplier mobilisation time | 18-Dec-20 A | 04-Jan-21 A | 10 | 0 | 9 | 100% |  | Completed
ER6661LT | W206 | W206.A3410 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-09-24 | Verified Station Documentation Update Strategy Report Issued to EDF for Technical Review. | 18-Dec-20 A | 18-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3430 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-25 | 2020-10-08 | Station Documentation Update Strategy Report Technically Reviewed by EDF SQEP | 18-Dec-20 A | 29-Jan-21 A | 10 | 0 | 27 | 100% |  | Completed
ER6661LT | W206 | W206.A6420 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-12-18 | <NEW SCOPE CR 221> TSA Issue Final Consequences EAN Report | 18-Dec-20 A | 18-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A22810 | HYA Fuel Handling Essential Safety Case |  | 2020-12-18 | Lifting Integrity Life Limits EAN Available | 18-Dec-20 A | 18-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A22810 | HRA Fuel Handling Essential Safety Case |  | 2020-12-18 | Lifting Integrity Life Limits EAN Available | 18-Dec-20 A | 18-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A1370 | HNB Enhanced Defuelling Safety Cases |  | 2020-10-12 | Effect of air admission on reactor containment (Coolant conditions CO2) EAN up Rev - Issued Draft Report to EDF for Revi | 18-Dec-20 A | 18-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A6420 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-12-18 | <NEW SCOPE CR220> TSA Issue Final Consequences EAN Report | 18-Dec-20 A | 18-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A6900 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-16 | 2020-11-27 | <NEW SCOPE CR220> TSA Address Comments on TR'd Determination of Cliff Edge Draft Report | 19-Dec-20 A | 06-Jan-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | W202.A3650 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-26 | 2020-11-06 | Supporting Plant Verified by TSA | 21-Dec-20 A | 26-Feb-21 A | 10 | 0 | 46 | 100% |  | Completed
ER6371LT | W202 | W202.A4430 | HRA Reactors Shutdown Essential Safety Cases | 2021-04-01 | 2021-04-23 | Optioneering Forming Report Verified by TSA | 21-Dec-20 A | 06-Jan-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.A4210 | HYA Reactors Shutdown Essential Safety Cases | 2021-01-25 | 2021-02-05 | Address Comments on Reviewed Reactor Internals and Structural Integrity during Defuelling Report | 21-Dec-20 A | 25-Jan-21 A | 10 | 0 | 22 | 100% |  | Completed
ER6661LT | W206 | W206.A3650 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-26 | 2020-11-06 | Supporting Plant Verified by TSA | 21-Dec-20 A | 26-Feb-21 A | 10 | 0 | 46 | 100% |  | Completed
ER6661LT | W206 | W206.A6430 | HYA Reactors Shutdown Essential Safety Cases | 2020-12-21 | 2021-01-06 | <NEW SCOPE CR 221> Consequences EAN Report TR Completed and uploaded to CDMS | 21-Dec-20 A | 13-Jan-21 A | 10 | 0 | 14 | 100% |  | Completed
ER6661LT | W206 | W206.A6570 | HYA Reactors Shutdown Essential Safety Cases | 2020-12-21 | 2021-01-06 | <NEW SCOPE CR 221> Optioneering EAN Report TR Completed and uploaded to CDMS | 21-Dec-20 A | 29-Jan-21 A | 10 | 0 | 26 | 100% |  | Completed
ER6661LT | W206 | W206.A6900 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-16 | 2020-11-27 | <NEW SCOPE CR 221> TSA Address Comments on TR'd Determination of Cliff Edge Draft Report | 21-Dec-20 A | 06-Jan-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | W202.A4210 | HRA Reactors Shutdown Essential Safety Cases | 2021-01-25 | 2021-02-05 | Address Comments on Reviewed Reactor Internals and Structural Integrity during Defuelling Report | 21-Dec-20 A | 25-Jan-21 A | 10 | 0 | 22 | 100% |  | Completed
ER6371LT | W202 | W202.A6430 | HRA Reactors Shutdown Essential Safety Cases | 2020-12-21 | 2021-01-06 | <NEW SCOPE CR220> Consequences EAN Report TR Completed and uploaded to CDMS | 21-Dec-20 A | 13-Jan-21 A | 10 | 0 | 14 | 100% |  | Completed
ER6371LT | W202 | W202.A6570 | HRA Reactors Shutdown Essential Safety Cases | 2020-12-21 | 2021-01-06 | <NEW SCOPE CR220> Optioneering EAN Report TR Completed and uploaded to CDMS | 21-Dec-20 A | 29-Jan-21 A | 10 | 0 | 26 | 100% |  | Completed
ER6371LT | W202 | W202.A3260 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-09-15 | Verified Shutdown Margin Head Document Issued to EDF for Technical Review. | 30-Dec-20 A | 30-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3260 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-09-15 | Verified Shutdown Margin Head Document Issued to EDF for Technical Review. | 30-Dec-20 A | 30-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16131 | HNB Reactors Shutdown Essential Safety Cases | 2020-12-31 | 2021-08-27 | SC - Safety Case development - tech oversight Cat 1 - Claim 2 -HNB - C-D - STN | 31-Dec-20 A | 27-Apr-22 A | 143 | 0 | 333 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11330 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-12-31 | Claim 2 MS 12/2020 | 31-Dec-20 A | 31-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2820 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-08-12 | Issue Final Thermal Analysis (FEAT) of FPU Fully Extended Report | 31-Dec-20 A | 31-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2820 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-08-12 | Issue Final Thermal Analysis (FEAT) of FPU Fully Extended Report | 31-Dec-20 A | 31-Dec-20 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | W201.1040 | HNB Reactors Shutdown Essential Safety Cases |  |  | Update Head Document | 31-Dec-20 A | 16-Feb-21 A | 6 | 0 | 32 | 100% |  | Completed
ER6650LT | W226 | W226.A25210 | HYA Fuel Handling Essential Safety Case | 2021-01-04 | 2021-06-18 | Draft Hazard and Interlock Schedule EAN (REV 000) EAN | 04-Jan-21 A | 18-Jun-21 A | 10 | 0 | 116 | 100% |  | Completed
ER6371LT | W202 | W202.A2840 | HRA Reactors Shutdown Essential Safety Cases | 2020-08-13 | 2020-08-19 | Thermal Analysis (FEAT) of FPU Fully Extended Report Completed and uploaded to CDMS | 04-Jan-21 A | 12-Feb-21 A | 10 | 0 | 30 | 100% |  | Completed
ER6661LT | W206 | W206.A2840 | HYA Reactors Shutdown Essential Safety Cases | 2020-08-13 | 2020-08-19 | Thermal Analysis (FEAT) of FPU Fully Extended Report Completed and uploaded to CDMS | 04-Jan-21 A | 12-Feb-21 A | 10 | 0 | 30 | 100% |  | Completed
ER6378LT | W222 | W222.A26000 | HRA Fuel Handling Essential Safety Case | 2021-01-04 | 2021-05-21 | Fast Fracture R6 Analysis ##(Cost Summary)## (C5) (NEW) | 04-Jan-21 A | 21-May-21 A | 102 | 0 | 96 | 100% |  | Completed
ER6378LT | W222 | W222.A25210 | HRA Fuel Handling Essential Safety Case | 2021-01-04 | 2021-06-18 | Draft Hazard and Interlock Schedule EAN (REV 000) | 04-Jan-21 A | 18-Jun-21 A | 10 | 0 | 116 | 100% |  | Completed
ER6378LT | W222 | W222.A23520 | HRA Fuel Handling Essential Safety Case | 2021-01-04 | 2021-01-05 | Pre Job Brief for Fast Fracture R6 Analysis EAN | 04-Jan-21 A | 05-Jan-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1420 | HNB Enhanced Defuelling Safety Cases | 2020-10-13 | 2020-10-26 | Effect of air admission on reactor containment (Coolant conditions CO2) EAN up Rev - Reviewed by EDF SQEP | 04-Jan-21 A | 24-May-21 A | 10 | 0 | 97 | 100% |  | Completed
ER6371LT | W202 | W202.A6130 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-23 | 2020-12-04 | <NEW SCOPE CR220> Panther Sensitivity Studies Report TR Completed and uploaded to CDMS | 04-Jan-21 A | 15-Jan-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | W202.A7060 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-23 | 2020-12-04 | <NEW SCOPE CR220> TSA Address Comments on TR'd Corroborated Approach Draft Report | 04-Jan-21 A | 15-Jan-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | W202.A7130 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-02 | 2020-11-05 | <NEW SCOPE CR220> Specification of Multi-Channel MACE Model Draft Report Verified by TSA | 04-Jan-21 A | 07-Jan-21 A | 4 | 0 | 4 | 100% |  | Completed
ER6661LT | W206 | W206.A6130 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-23 | 2020-12-04 | <NEW SCOPE CR 221> Panther Sensitivity Studies Report TR Completed and uploaded to CDMS | 04-Jan-21 A | 15-Jan-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.A7060 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-23 | 2020-12-04 | <NEW SCOPE CR 221> TSA Address Comments on TR'd Corroborated Approach Draft Report | 04-Jan-21 A | 15-Jan-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.A7130 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-02 | 2020-11-05 | <NEW SCOPE CR 221> Specification of Multi-Channel MACE Model Draft Report Verified by TSA | 04-Jan-21 A | 07-Jan-21 A | 4 | 0 | 4 | 100% |  | Completed
ER6650LT | W226 | W226.A23520 | HYA Fuel Handling Essential Safety Case | 2021-01-04 | 2021-01-05 | Pre Job Brief for Fast Fracture R6 Analysis EAN | 04-Jan-21 A | 05-Jan-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A26000 | HYA Fuel Handling Essential Safety Case | 2021-01-04 | 2021-05-21 | Fast Fracture R6 Analysis ##(Cost Summary)## (C5) (NEW) | 04-Jan-21 A | 21-May-21 A | 97 | 0 | 97 | 100% |  | Completed
ER6378LT | W222 | W222.A23530 | HRA Fuel Handling Essential Safety Case | 2021-01-05 | 2021-04-12 | Draft Fast Fracture R6 Analysis EAN | 05-Jan-21 A | 12-Apr-21 A | 5 | 0 | 67 | 100% |  | Completed
ER6378LT | W222 | W222.A12530 | HRA Fuel Handling Essential Safety Case | 2021-01-05 | 2021-01-22 | Address Verification Comments of Management Strategy for Pond Water Treatment Arisings EAN | 05-Jan-21 A | 22-Jan-21 A | 5 | 0 | 13 | 100% |  | Completed
ER6650LT | W226 | W226.A12530 | HYA Fuel Handling Essential Safety Case | 2021-01-05 | 2021-01-22 | Address Verification Comments of Management Strategy for Pond Water Treatment Arisings EAN | 05-Jan-21 A | 22-Jan-21 A | 5 | 0 | 13 | 100% |  | Completed
ER6650LT | W226 | W226.A23530 | HYA Fuel Handling Essential Safety Case | 2021-01-05 | 2021-04-12 | Draft Fast Fracture R6 Analysis EAN | 05-Jan-21 A | 12-Apr-21 A | 5 | 0 | 67 | 100% |  | Completed
ER6371LT | W202 | W202.A3570 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-13 | 2020-10-13 | Containment Head Document - Pre Job Brief | 05-Jan-21 A | 07-Jan-21 A | 1 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A3570 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-13 | 2020-10-13 | Containment Head Document - Pre Job Brief | 05-Jan-21 A | 07-Jan-21 A | 1 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | W222.A23430 | HRA Fuel Handling Essential Safety Case | 2021-01-05 | 2021-02-26 | Complete TR Form and Upload CSP Model and Static Analysis EAN to CDMS | 05-Jan-21 A | 26-Feb-21 A | 4 | 0 | 38 | 100% |  | Completed
ER6650LT | W226 | W226.A23430 | HYA Fuel Handling Essential Safety Case | 2021-01-05 | 2021-02-26 | Complete TR Form and Upload CSP Model and Static Analysis EAN to CDMS | 05-Jan-21 A | 26-Feb-21 A | 4 | 0 | 38 | 100% |  | Completed
ER6371LT | W202 | W202.A4510 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-04-23 | Verified Optioneering Forming Report Issued to EDF for Technical Review. | 06-Jan-21 A | 06-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4510 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-04-23 | Verified Optioneering Forming Report Issued to EDF for Technical Review. | 06-Jan-21 A | 06-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A6910 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-11-27 | <NEW SCOPE CR220> TSA Issue Final Determination of Cliff Edge Report | 06-Jan-21 A | 06-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A6910 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-11-27 | <NEW SCOPE CR 221> TSA Issue Final Determination of Cliff Edge Report | 06-Jan-21 A | 06-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A4520 | HRA Reactors Shutdown Essential Safety Cases | 2021-04-26 | 2021-05-17 | Optioneering Forming Report Technically Reviewed by EDF SQEP | 07-Jan-21 A | 29-Jan-21 A | 17 | 0 | 17 | 100% |  | Completed
ER6661LT | W206 | W206.A4520 | HYA Reactors Shutdown Essential Safety Cases | 2021-04-26 | 2021-05-17 | Optioneering Forming Report Technically Reviewed by EDF SQEP | 07-Jan-21 A | 29-Jan-21 A | 17 | 0 | 17 | 100% |  | Completed
ER6378LT | W222 | W222.A26060 | HRA Fuel Handling Essential Safety Case | 2021-01-07 | 2021-06-11 | Dropped FPU Optioneering Documents ##(Cost Summary)## (C5) (NEW) | 07-Jan-21 A | 11-Jun-21 A | 108 | 0 | 108 | 100% |  | Completed
ER6378LT | W222 | W222.A24010 | HRA Fuel Handling Essential Safety Case | 2021-01-07 | 2021-01-07 | Pre Job Brief for Dropped FPU Optioneering Documents EAN | 07-Jan-21 A | 07-Jan-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A6920 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-30 | 2020-12-11 | <NEW SCOPE CR220> Determination of Cliff Edge Report TR Completed and uploaded to CDMS | 07-Jan-21 A | 20-Jan-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.A6920 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-30 | 2020-12-11 | <NEW SCOPE CR 221> Determination of Cliff Edge Report TR Completed and uploaded to CDMS | 07-Jan-21 A | 20-Jan-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | W226.A24010 | HYA Fuel Handling Essential Safety Case | 2021-01-07 | 2021-01-07 | Pre Job Brief for Dropped FPU Optioneering Documents EAN | 07-Jan-21 A | 07-Jan-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A26060 | HYA Fuel Handling Essential Safety Case | 2021-01-07 | 2021-06-11 | Dropped FPU Optioneering Documents ##(Cost Summary)## (C5) (NEW) | 07-Jan-21 A | 11-Jun-21 A | 108 | 0 | 108 | 100% |  | Completed
ER6371LT | W202 | W202.A7140 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-11-05 | <NEW SCOPE CR220> Verified Specification of Multi-Channel MACE Model Draft Report Issued to EDF for Technical Revie | 07-Jan-21 A | 07-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A7140 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-11-05 | <NEW SCOPE CR 221> Verified Specification of Multi-Channel MACE Model Draft Report Issued to EDF for Technical Revie | 07-Jan-21 A | 07-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A4050 | HRA Reactors Shutdown Essential Safety Cases | 2020-12-10 | 2021-02-23 | Prepare Containment Head Document Draft Report | 08-Jan-21 A | 24-Mar-21 A | 37 | 0 | 53 | 100% |  | Completed
ER6371LT | W202 | W202.A4040 | HRA Reactors Shutdown Essential Safety Cases | 2020-12-10 | 2021-04-29 | Claim 2 Containment Head Document Summary | 08-Jan-21 A | 24-Aug-21 A | 159 | 0 | 159 | 100% |  | Completed
ER6661LT | W206 | W206.A4050 | HYA Reactors Shutdown Essential Safety Cases | 2020-12-10 | 2021-02-23 | Prepare Containment Head Document Draft Report | 08-Jan-21 A | 24-Mar-21 A | 37 | 0 | 54 | 100% |  | Completed
ER6661LT | W206 | W206.A4040 | HYA Reactors Shutdown Essential Safety Cases | 2020-12-10 | 2021-07-29 | Claim 2 Containment Head Document Summary | 08-Jan-21 A | 24-Aug-21 A | 159 | 0 | 159 | 100% |  | Completed
ER6371LT | W202 | W202.A3660 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-26 | 2020-11-06 | Summary of Compliance with RADWASTE Assessment Principles Draft EAN Verified by TSA | 08-Jan-21 A | 21-Jan-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.A3660 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-26 | 2020-11-06 | Summary of Compliance with RADWASTE Assessment Principles Draft EAN Verified by TSA | 08-Jan-21 A | 21-Jan-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6378LT | W222 | W222.A24020 | HRA Fuel Handling Essential Safety Case | 2021-01-08 | 2021-04-23 | Draft Dropped FPU Optioneering Documents EAN | 08-Jan-21 A | 23-Apr-21 A | 12 | 0 | 74 | 100% |  | Completed
ER6371LT | W202 | W202.A7150 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-06 | 2020-11-19 | <NEW SCOPE CR220> Specification of Multi-Channel MACE Model Draft Report Technically Reviewed by EDF SQEP | 08-Jan-21 A | 21-Jan-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.A7150 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-06 | 2020-11-19 | <NEW SCOPE CR 221> Specification of Multi-Channel MACE Model Draft Report Technically Reviewed by EDF SQEP | 08-Jan-21 A | 21-Jan-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | W226.A24020 | HYA Fuel Handling Essential Safety Case | 2021-01-08 | 2021-04-23 | Draft Dropped FPU Optioneering Documents EAN | 08-Jan-21 A | 23-Apr-21 A | 12 | 0 | 73 | 100% |  | Completed
ER6371LT | W202 | W202.A6440 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-01-06 | <NEW SCOPE CR220> Consequences EAN Report Completed | 13-Jan-21 A | 13-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A6440 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-01-06 | <NEW SCOPE CR 221> Consequences EAN Report Completed | 13-Jan-21 A | 13-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2720 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-08-03 | All Supporting Technical References Complete - Claim 1 Shutdown Margins | 15-Jan-21 A | 15-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2720 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-08-03 | All Supporting Technical References Complete - Claim 1 Shutdown Margins | 15-Jan-21 A | 15-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A26080 | HRA Fuel Handling Essential Safety Case | 2021-01-15 | 2021-07-19 | Assessment of Worker Risk ##(Cost Summary)## (C6) (NEW) | 15-Jan-21 A | 19-Jul-21 A | 140 | 0 | 127 | 100% |  | Completed
ER6378LT | W222 | W222.A25490 | HRA Fuel Handling Essential Safety Case | 2021-01-15 | 2021-01-15 | Pre Job Brief for Assessment of Worker Risk (REV 000) EAN | 15-Jan-21 A | 15-Jan-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25490 | HYA Fuel Handling Essential Safety Case | 2021-01-15 | 2021-01-15 | Pre Job Brief for Assessment of Worker Risk (REV 000) EAN | 15-Jan-21 A | 15-Jan-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A26080 | HYA Fuel Handling Essential Safety Case | 2021-01-15 | 2021-07-19 | Assessment of Worker Risk ##(Cost Summary)## (C6) (NEW) | 15-Jan-21 A | 19-Jul-21 A | 139 | 0 | 127 | 100% |  | Completed
ER6371LT | W202 | W202.A6140 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-12-04 | <NEW SCOPE CR220> Panther Sensitivity Studies Report Completed | 15-Jan-21 A | 15-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A7070 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-12-04 | <NEW SCOPE CR220> TSA Issue Final Corroborated Approach Report | 15-Jan-21 A | 15-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A6140 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-12-04 | <NEW SCOPE CR 221> Panther Sensitivity Studies Report Completed | 15-Jan-21 A | 15-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A7070 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-12-04 | <NEW SCOPE CR 221> TSA Issue Final Corroborated Approach Report | 15-Jan-21 A | 15-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A25500 | HRA Fuel Handling Essential Safety Case | 2021-01-18 | 2021-06-21 | Draft Assessment of Worker Risk (REV 000) EAN | 18-Jan-21 A | 21-Jun-21 A | 20 | 0 | 106 | 100% |  | Completed
ER6650LT | W226 | W226.A25500 | HYA Fuel Handling Essential Safety Case | 2021-01-18 | 2021-06-21 | Draft Assessment of Worker Risk (REV 000) EAN | 18-Jan-21 A | 21-Jun-21 A | 20 | 0 | 107 | 100% |  | Completed
ER6370LT | W201 | W201.1090 | HNB Reactors Shutdown Essential Safety Cases |  |  | CAT 1 SC Proposal Revised Draft 4 | 18-Jan-21 A | 15-Feb-21 A | 1 | 0 | 20 | 100% |  | Completed
ER6371LT | W202 | W202.A3320 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-17 | 2020-10-28 | Prepare Civil Integrity Overview Draft EAN | 18-Jan-21 A | 12-Feb-21 A | 30 | 0 | 20 | 100% |  | Completed
ER6371LT | W202 | W202.A3280 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-16 | 2020-09-29 | Shutdown Margin Head Document Technically Reviewed by EDF SQEP | 18-Jan-21 A | 12-Feb-21 A | 21 | 0 | 20 | 100% |  | Completed
ER6371LT | W202 | W202.A3310 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-17 | 2020-12-09 | Civil Integrity Overview Summary | 18-Jan-21 A | 24-Mar-21 A | 48 | 0 | 48 | 100% |  | Completed
ER6661LT | W206 | W206.A3320 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-17 | 2020-10-28 | Prepare Civil Integrity Overview Draft EAN | 18-Jan-21 A | 12-Feb-21 A | 30 | 0 | 20 | 100% |  | Completed
ER6661LT | W206 | W206.A3280 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-16 | 2020-09-29 | Shutdown Margin Head Document Technically Reviewed by EDF SQEP | 18-Jan-21 A | 12-Feb-21 A | 21 | 0 | 20 | 100% |  | Completed
ER6661LT | W206 | W206.A3310 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-17 | 2020-11-23 | Civil Integrity Overview Summary | 18-Jan-21 A | 24-Mar-21 A | 48 | 0 | 48 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1590 | HNB Reactors Shutdown Essential Safety Cases |  |  | SQEP sign off of verification | 18-Jan-21 A | 05-May-21 A | 5 | 0 | 75 | 100% |  | Completed
ER6371LT | W202 | W202.A6750 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-16 | 2020-11-27 | <NEW SCOPE CR220> TSA Address Comments on TR'd Specified Flows Draft Report | 18-Jan-21 A | 29-Jan-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | W202.A7080 | HRA Reactors Shutdown Essential Safety Cases | 2020-12-07 | 2020-12-18 | <NEW SCOPE CR220> Corroborated Approach Report TR Completed and uploaded to CDMS | 18-Jan-21 A | 29-Jan-21 A | 10 | 0 | 9 | 100% |  | Completed
ER6661LT | W206 | W206.A6750 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-16 | 2020-11-27 | <NEW SCOPE CR 221> TSA Address Comments on TR'd Specified Flows Draft Report | 18-Jan-21 A | 29-Jan-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.A7080 | HYA Reactors Shutdown Essential Safety Cases | 2020-12-07 | 2020-12-18 | <NEW SCOPE CR 221> Corroborated Approach Report TR Completed and uploaded to CDMS | 18-Jan-21 A | 29-Jan-21 A | 10 | 0 | 9 | 100% |  | Completed
ER6371LT | W202 | W202.A6930 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-12-11 | <NEW SCOPE CR220> Determination of Cliff Edge Report Completed | 20-Jan-21 A | 20-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A6930 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-12-11 | <NEW SCOPE CR 221> Determination of Cliff Edge Report Completed | 20-Jan-21 A | 20-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3830 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-11-06 | Verified Summary of Compliance with RADWASTE Assessment Principles Draft EAN Issued to EDF for Technical Review. | 21-Jan-21 A | 21-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3830 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-11-06 | Verified Summary of Compliance with RADWASTE Assessment Principles Draft EAN Issued to EDF for Technical Review. | 21-Jan-21 A | 21-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3860 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-09 | 2020-11-20 | Summary of Compliance with RADWASTE Assessment Principles Draft EAN Technically Reviewed by EDF SQEP | 22-Jan-21 A | 04-Feb-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.A3860 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-09 | 2020-11-20 | Summary of Compliance with RADWASTE Assessment Principles Draft EAN Technically Reviewed by EDF SQEP | 22-Jan-21 A | 04-Feb-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | W202.A7160 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-20 | 2020-12-03 | <NEW SCOPE CR220> TSA Address Comments on TR'd Specification of Multi-Channel MACE Model Draft Report | 22-Jan-21 A | 15-Feb-21 A | 10 | 0 | 17 | 100% |  | Completed
ER6661LT | W206 | W206.A7160 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-20 | 2020-12-03 | <NEW SCOPE CR 221> TSA Address Comments on TR'd Specification of Multi-Channel MACE Model Draft Report | 22-Jan-21 A | 22-Feb-21 A | 10 | 0 | 21 | 100% |  | Completed
ER6371LT | W202 | W202.A4230 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-02-05 | Issue Final Reactor Internals and Structural Integrity during Defuelling Report | 25-Jan-21 A | 25-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4230 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-02-05 | Issue Final Reactor Internals and Structural Integrity during Defuelling Report | 25-Jan-21 A | 25-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A8250 | HRA Fuel Handling Essential Safety Case | 2021-01-25 | 2021-02-25 | Supplier Update and Issue Defuelling Cooling and Match Analysis (Task FIle Note) | 25-Jan-21 A | 25-Feb-21 A | 3 | 0 | 23 | 100% |  | Completed
ER6378LT | W222 | W222.A12540 | HRA Fuel Handling Essential Safety Case | 2021-01-25 | 2021-01-25 | Confirm Verification Comments for Pond Water Treatment Arisings EAN | 25-Jan-21 A | 25-Jan-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A6590 | HRA Reactors Shutdown Essential Safety Cases | 2021-01-07 | 2021-01-15 | <NEW SCOPE CR220> Scope Defined to Support Preferred Option | 25-Jan-21 A | 29-Jan-21 A | 7 | 0 | 4 | 100% |  | Completed
ER6661LT | W206 | W206.A6590 | HYA Reactors Shutdown Essential Safety Cases | 2021-01-07 | 2021-01-15 | <NEW SCOPE CR 221> Scope Defined to Support Preferred Option | 25-Jan-21 A | 29-Jan-21 A | 5 | 0 | 4 | 100% |  | Completed
ER6650LT | W226 | W226.A12540 | HYA Fuel Handling Essential Safety Case | 2021-01-25 | 2021-01-25 | Confirm Verification Comments for Pond Water Treatment Arisings EAN | 25-Jan-21 A | 25-Jan-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A8250 | HYA Fuel Handling Essential Safety Case | 2021-01-25 | 2021-02-25 | Supplier Update and Issue Defuelling Cooling and Match Analysis (Task FIle Note) | 25-Jan-21 A | 25-Feb-21 A | 3 | 0 | 23 | 100% |  | Completed
ER6371LT | W202 | W202.A4240 | HRA Reactors Shutdown Essential Safety Cases | 2021-02-08 | 2021-02-12 | Reactor Internals and Structural Integrity during Defuelling Report Completed and uploaded to CDMS | 26-Jan-21 A | 27-Jan-21 A | 5 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A4240 | HYA Reactors Shutdown Essential Safety Cases | 2021-02-08 | 2021-02-12 | Reactor Internals and Structural Integrity during Defuelling Report Completed and uploaded to CDMS | 26-Jan-21 A | 27-Jan-21 A | 5 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A11370 | HRA Fuel Handling Essential Safety Case | 2021-01-26 | 2021-02-25 | Supplier Update and Issue Justification for Pressure Boundary EAN | 26-Jan-21 A | 25-Feb-21 A | 10 | 0 | 22 | 100% |  | Completed
ER6378LT | W222 | W222.A12550 | HRA Fuel Handling Essential Safety Case | 2021-01-26 | 2021-03-05 | Complete TR Form and Upload Management Strategy for Pond Water Treatment Arisings EAN to CDMS | 26-Jan-21 A | 05-Mar-21 A | 4 | 0 | 29 | 100% |  | Completed
ER6650LT | W226 | W226.A12550 | HYA Fuel Handling Essential Safety Case | 2021-01-26 | 2021-03-05 | Complete TR Form and Upload Management Strategy for Pond Water Treatment Arisings EAN to CDMS | 26-Jan-21 A | 05-Mar-21 A | 4 | 0 | 29 | 100% |  | Completed
ER6650LT | W226 | W226.A11370 | HYA Fuel Handling Essential Safety Case | 2021-01-26 | 2021-02-25 | Supplier Update and Issue Justification for Pressure Boundary EAN | 26-Jan-21 A | 25-Feb-21 A | 10 | 0 | 22 | 100% |  | Completed
ER6650LT | W226 | W226.A24920 | HYA Fuel Handling Essential Safety Case | 2021-01-26 | 2021-01-26 | Pre Job Brief for Human Factors Defuelling Issues Management Report EAN | 26-Jan-21 A | 26-Jan-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25880 | HYA Fuel Handling Essential Safety Case | 2021-01-26 | 2021-06-16 | Human Factors Defuelling Issues Management Report ##(Cost Summary)## (C2) (NEW) | 26-Jan-21 A | 16-Jun-21 A | 109 | 0 | 98 | 100% |  | Completed
ER6378LT | W222 | W222.A25880 | HRA Fuel Handling Essential Safety Case | 2021-01-26 | 2021-06-16 | Human Factors Defuelling Issues Management Report ##(Cost Summary)## (C2) (NEW) | 26-Jan-21 A | 16-Jun-21 A | 103 | 0 | 98 | 100% |  | Completed
ER6378LT | W222 | W222.A24920 | HRA Fuel Handling Essential Safety Case | 2021-01-26 | 2021-01-26 | Pre Job Brief for Human Factors Defuelling Issues Management Report EAN | 26-Jan-21 A | 26-Jan-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A4290 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-02-12 | Reactor Internals and Structural Integrity during Defuelling Report Completed | 27-Jan-21 A | 27-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4290 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-02-12 | Reactor Internals and Structural Integrity during Defuelling Report Completed | 27-Jan-21 A | 27-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A24930 | HYA Fuel Handling Essential Safety Case | 2021-01-27 | 2021-04-30 | Draft Review of Human Factors Defuelling Issues Management Report EAN | 27-Jan-21 A | 30-Apr-21 A | 17 | 0 | 66 | 100% |  | Completed
ER6378LT | W222 | W222.A24930 | HRA Fuel Handling Essential Safety Case | 2021-01-27 | 2021-04-30 | Draft Review of Human Factors Defuelling Issues Management Report EAN | 27-Jan-21 A | 30-Apr-21 A | 22 | 0 | 66 | 100% |  | Completed
ER6371LT | W202 | W202.A4550 | HRA Reactors Shutdown Essential Safety Cases | 2021-05-18 | 2021-06-08 | TSA Address Comments on TR'd Optioneering Forming Report | 29-Jan-21 A | 02-Feb-21 A | 11 | 0 | 3 | 100% |  | Completed
ER6371LT | W202 | W202.A3520 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-09 | 2020-10-22 | TSA Address Comments on TR'd Station Documentation Update Strategy Report | 29-Jan-21 A | 02-Feb-21 A | 0 | 0 | 3 | 100% |  | Completed
ER6661LT | W206 | W206.A4550 | HYA Reactors Shutdown Essential Safety Cases | 2021-05-18 | 2021-06-08 | TSA Address Comments on TR'd Optioneering Forming Report | 29-Jan-21 A | 02-Feb-21 A | 11 | 0 | 3 | 100% |  | Completed
ER6661LT | W206 | W206.A3520 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-09 | 2020-10-22 | TSA Address Comments on TR'd Station Documentation Update Strategy Report | 29-Jan-21 A | 02-Feb-21 A | 10 | 0 | 3 | 100% |  | Completed
ER6378LT | W222 | W222.A25740 | HRA Fuel Handling Essential Safety Case | 2021-01-29 | 2021-06-08 | Development of Fuel Free Verification Methods ##(Cost Summary)## ### (C1) | 29-Jan-21 A | 08-Jun-21 A | 86 | 0 | 88 | 100% |  | Completed
ER6378LT | W222 | W222.A12630 | HRA Fuel Handling Essential Safety Case | 2021-01-29 | 2021-01-29 | Pre Job Brief for Development of Fuel Free Verification Methods (File Note) | 29-Jan-21 A | 29-Jan-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A6580 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-01-06 | <NEW SCOPE CR220> Optioneering EAN Report Completed | 29-Jan-21 A | 29-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A7090 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-12-18 | <NEW SCOPE CR220> Corroborated Approach Report Completed | 29-Jan-21 A | 29-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A6580 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-01-06 | <NEW SCOPE CR 221> Optioneering EAN Report Completed | 29-Jan-21 A | 29-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A7090 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-12-18 | <NEW SCOPE CR 221> Corroborated Approach Report Completed | 29-Jan-21 A | 29-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A12630 | HYA Fuel Handling Essential Safety Case | 2021-01-29 | 2021-01-29 | Pre Job Brief for Development of Fuel Free Verification Methods (File Note) | 29-Jan-21 A | 29-Jan-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25740 | HYA Fuel Handling Essential Safety Case | 2021-01-29 | 2021-06-08 | Development of Fuel Free Verification Methods ##(Cost Summary)## ### (C1) | 29-Jan-21 A | 08-Jun-21 A | 92 | 0 | 88 | 100% |  | Completed
ER6371LT | W202 | W202.A6760 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-11-27 | <NEW SCOPE CR220> TSA Issue Final Specified Flows Report | 29-Jan-21 A | 29-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A6760 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-11-27 | <NEW SCOPE CR 221> TSA Issue Final Specified Flows Report | 29-Jan-21 A | 29-Jan-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206030 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-02 | >>>OUTGOING ENABLER (W222.A22460) Defuelling Dataset QA Grade 2 Part 2 Report Completed <SCOPE DELETED CR220> | 01-Feb-21 A | 01-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206030 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-08-21 | >>>OUTGOING ENABLER (W222.A22460) Defuelling Dataset QA Grade 2 Part 2 Report Completed (SCOPE DELETED CR221) | 01-Feb-21 A | 01-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206170 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-08-21 | >>>OUTGOING ENABLER (W226) Defuelling Dataset QA Grade 2 Part 2 Report Completed (SCOPE DELETED CR221) | 01-Feb-21 A | 01-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A12640 | HRA Fuel Handling Essential Safety Case | 2021-02-01 | 2021-04-23 | Draft Development of Fuel Free Verification Methods (File Note) | 01-Feb-21 A | 23-Apr-21 A | 30 | 0 | 58 | 100% |  | Completed
ER6378LT | W222 | W222.A22460 | HRA Fuel Handling Essential Safety Case |  | 2021-02-01 | >>>INCOMING ENABLER (W202.A2206030) Defuelling Dataset QA Grade 2 Part 2 Report Completed ?? CATCH ALL RADCONS ASSESS | 01-Feb-21 A | 01-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A12640 | HYA Fuel Handling Essential Safety Case | 2021-02-01 | 2021-04-23 | Draft Development of Fuel Free Verification Methods (File Note) | 01-Feb-21 A | 23-Apr-21 A | 30 | 0 | 58 | 100% |  | Completed
ER6650LT | W226 | W226.A26050 | HYA Fuel Handling Essential Safety Case | 2021-02-01 | 2021-06-11 | Dropped FPU Fault Definition Document ##(Cost Summary)## (C5) (NEW) | 01-Feb-21 A | 12-Oct-23 A | 697 | 0 | 680 | 100% |  | Completed
ER6650LT | W226 | W226.A26140 | HYA Fuel Handling Essential Safety Case | 2021-02-01 | 2021-02-08 | Supplier Update and Issue HAZOP updates resulting from defuelling process changes EAN (REV 001) | 01-Feb-21 A | 08-Feb-21 A | 3 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A26260 | HYA Fuel Handling Essential Safety Case | 2021-02-01 | 2021-05-14 | Draft Dropped FPU Fault Definition Document (FDD) (REV 001) EAN | 01-Feb-21 A | 14-May-21 A | 10 | 0 | 72 | 100% |  | Completed
ER6378LT | W222 | W222.A26260 | HRA Fuel Handling Essential Safety Case | 2021-02-01 | 2021-05-14 | Draft Dropped FPU Fault Definition Document (FDD) (REV 001) EAN | 01-Feb-21 A | 14-May-21 A | 10 | 0 | 72 | 100% |  | Completed
ER6378LT | W222 | W222.A26140 | HRA Fuel Handling Essential Safety Case | 2021-02-01 | 2021-02-08 | Supplier Update and Issue HAZOP updates resulting from defuelling process changes EAN (REV 001) | 01-Feb-21 A | 08-Feb-21 A | 2 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A26050 | HRA Fuel Handling Essential Safety Case | 2021-02-01 | 2021-06-11 | Dropped FPU Fault Definition Document ##(Cost Summary)## (C5) (NEW) | 01-Feb-21 A | 12-Oct-23 A | 717 | 0 | 680 | 100% |  | Completed
ER6378LT | W222 | W222.A12650 | HRA Fuel Handling Essential Safety Case | 2021-02-01 | 2021-05-26 | Work with Stations to develop Fuel Free Verification Quality Plan (File Note) | 01-Feb-21 A | 26-May-21 A | 41 | 0 | 79 | 100% |  | Completed
ER6378LT | W222 | W222.A22560 | HRA Fuel Handling Essential Safety Case |  | 2021-02-01 | >>>MIRROR OF INCOMING ENABLER (W202.A2206030) Defuelling Dataset QA Grade 2 Part 2 Report Completed ?? | 01-Feb-21 A | 01-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A16470 | HRA Fuel Handling Essential Safety Case |  | 2021-02-01 | INTERFACE MILESTONE - Defuelling Dataset QA Grade 2Part2 Report - (W202 Reactors Shutdown Essential Safety Cases (HRA)) | 01-Feb-21 A | 01-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A6220 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-01-15 | <NEW SCOPE CR220> PVCW Management - Discovery Milestone | 01-Feb-21 A | 01-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A6770 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-30 | 2020-12-11 | <NEW SCOPE CR220> Specified Flows Report TR Completed and uploaded to CDMS | 01-Feb-21 A | 12-Feb-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.A6220 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-01-15 | <NEW SCOPE CR 221> PVCW Management - Discovery Milestone | 01-Feb-21 A | 01-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A6770 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-30 | 2020-12-11 | <NEW SCOPE CR 221> Specified Flows Report TR Completed and uploaded to CDMS | 01-Feb-21 A | 12-Feb-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | W226.A16470 | HYA Fuel Handling Essential Safety Case |  | 2021-02-01 | INTERFACE MILESTONE - Defuelling Dataset QA Grade 2Part2 Report - (W202 Reactors Shutdown Essential Safety Cases (HYA)) | 01-Feb-21 A | 01-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A22560 | HYA Fuel Handling Essential Safety Case |  | 2021-02-01 | >>>MIRROR OF INCOMING ENABLER (W202.A2206030) Defuelling Dataset QA Grade 2 Part 2 Report Completed | 01-Feb-21 A | 01-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A12650 | HYA Fuel Handling Essential Safety Case | 2021-02-01 | 2021-05-26 | Work with Stations to develop Fuel Free Verification Quality Plan (File Note) | 01-Feb-21 A | 26-May-21 A | 41 | 0 | 79 | 100% |  | Completed
ER6650LT | W226 | W226.A27200 | HYA Fuel Handling Essential Safety Case |  | 2021-02-01 | >>>INCOMING ENABLER (W206.A2206030) Defuelling Dataset QA Grade 2 Part 2 Report Completed CATCH ALL RADCONS ASSESS | 01-Feb-21 A | 01-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A10590 | HRA Fuel Handling Essential Safety Case | 2021-02-02 | 2021-02-26 | Supplier Update and Issue Worker Dose Assessment (SKELETON) EAN | 02-Feb-21 A | 26-Feb-21 A | 10 | 0 | 18 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18300 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-11-26 | <NEW SCOPE CR 187> - OPEX/ Literature Review - Issue Draft EAN to EDF for Review. | 02-Feb-21 A | 02-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A26800 | HRA Fuel Handling Essential Safety Case | 2021-02-02 | 2021-02-03 | Complete TR Form and Fuel Route Operational Sequence/Process for Defuelling EAN to CDMS (PROCESS DOCUMENT) (REV 001) | 02-Feb-21 A | 03-Feb-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | W222.A24730 | HRA Fuel Handling Essential Safety Case | 2021-02-02 | 2021-02-15 | Verify Human Factors Assessment of Dropped FPU Fault Sequences EAN & Issue for Technical Review | 02-Feb-21 A | 15-Feb-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6378LT | W222 | W222.A23330 | HRA Fuel Handling Essential Safety Case | 2021-02-02 | 2021-04-01 | Verify Update Core Support Plate Properties Methodology & Toughness Properties EAN and Issue for Technical Review | 02-Feb-21 A | 01-Apr-21 A | 19 | 0 | 43 | 100% |  | Completed
ER6378LT | W222 | W222.A10570 | HRA Fuel Handling Essential Safety Case | 2021-02-02 | 2021-02-26 | Verify Worker Dose Assessment (SKELETON) EAN and Issue for Technical Review | 02-Feb-21 A | 26-Feb-21 A | 20 | 0 | 18 | 100% |  | Completed
ER6650LT | W226 | W226.A10590 | HYA Fuel Handling Essential Safety Case | 2021-02-02 | 2021-02-26 | Supplier Update and Issue Worker Dose Assessment (SKELETON) EAN | 02-Feb-21 A | 26-Feb-21 A | 10 | 0 | 18 | 100% |  | Completed
ER6650LT | W226 | W226.A10570 | HYA Fuel Handling Essential Safety Case | 2021-02-02 | 2021-02-26 | Verify Worker Dose Assessment (SKELETON) EAN and Issue for Technical Review | 02-Feb-21 A | 26-Feb-21 A | 20 | 0 | 18 | 100% |  | Completed
ER6650LT | W226 | W226.A23330 | HYA Fuel Handling Essential Safety Case | 2021-02-02 | 2021-04-01 | Verify Update Core Support Plate Properties Methodology & Toughness Properties EAN and Issue for Technical Review | 02-Feb-21 A | 01-Apr-21 A | 19 | 0 | 43 | 100% |  | Completed
ER6650LT | W226 | W226.A24730 | HYA Fuel Handling Essential Safety Case | 2021-02-02 | 2021-02-15 | Verify Human Factors Assessment of Dropped FPU Fault Sequences EAN & Issue for Technical Review | 02-Feb-21 A | 15-Feb-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | W226.A26800 | HYA Fuel Handling Essential Safety Case | 2021-02-02 | 2021-02-03 | Complete TR Form and Fuel Route Operational Sequence/Process for Defuelling EAN to CDMS (PROCESS DOCUMENT) (REV 001) | 02-Feb-21 A | 03-Feb-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A4570 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-06-08 | TSA Issue Final Optioneering Forming Report | 02-Feb-21 A | 02-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3630 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-10-22 | TSA Issue Final Station Documentation Update Strategy Report | 02-Feb-21 A | 02-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4570 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-06-08 | TSA Issue Final Optioneering Forming Report | 02-Feb-21 A | 02-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3630 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-10-22 | TSA Issue Final Station Documentation Update Strategy Report | 02-Feb-21 A | 02-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3790 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-11-05 | Confirm Implementation plans are in line with Cat 1 Safety Case - HRA | 03-Feb-21 A | 03-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3800 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-11-05 | Agree in principle to changes to Tech Specs - HRA | 03-Feb-21 A | 03-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3780 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-11-05 | All Supporting Technical References Complete - Claim 4 Configuration | 03-Feb-21 A | 03-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3790 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-11-05 | Confirm Implementation plans are in line with Cat 1 Safety Case - HYA | 03-Feb-21 A | 03-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206040 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-03-02 | >>>OUTGOING ENABLER (W222.A22470) Shutdown Cooling Analysis Report Completed <SCOPE DELETED CR220> | 03-Feb-21 A | 03-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206040 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-04-07 | >>>OUTGOING ENABLER (W222.A22470) Shutdown Cooling Analysis Report Completed (SCOPE DELETED CR221) | 03-Feb-21 A | 03-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206180 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-04-07 | >>>OUTGOING ENABLER (W226) Shutdown Cooling Analysis Report Completed (SCOPE DELETED CR221) | 03-Feb-21 A | 03-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18310 | HNB Reactors Shutdown Essential Safety Cases | 2020-11-27 | 2020-12-10 | <NEW SCOPE CR 187> - OPEX/ Literature Review - Draft EAN Reviewed by EDF SQEP | 03-Feb-21 A | 12-Feb-21 A | 10 | 0 | 7 | 100% |  | Completed
ER6371LT | W202 | W202.A4580 | HRA Reactors Shutdown Essential Safety Cases | 2021-06-09 | 2021-06-22 | Optioneering Forming Report TR Completed and uploaded to CDMS | 03-Feb-21 A | 09-Feb-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A3640 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-23 | 2020-11-05 | Station Documentation Update Strategy Report TR Completed and uploaded to CDMS | 03-Feb-21 A | 03-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3770 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-11-05 | Station Documentation Update Strategy Report Completed | 03-Feb-21 A | 03-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3780 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-11-05 | All Supporting Technical References Complete - Claim 4 Configuration | 03-Feb-21 A | 03-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4580 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-09 | 2021-06-22 | Optioneering Forming Report TR Completed and uploaded to CDMS | 03-Feb-21 A | 09-Feb-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A3640 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-23 | 2020-11-05 | Station Documentation Update Strategy Report TR Completed and uploaded to CDMS | 03-Feb-21 A | 03-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3770 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-11-05 | Station Documentation Update Strategy Report Completed | 03-Feb-21 A | 03-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A24860 | HRA Fuel Handling Essential Safety Case | 2021-02-03 | 2021-02-03 | PJB for Phase 2 | 03-Feb-21 A | 03-Feb-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A24870 | HYA Fuel Handling Essential Safety Case | 2021-02-03 | 2021-02-03 | PJB for Phase 2 | 03-Feb-21 A | 03-Feb-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A26810 | HRA Fuel Handling Essential Safety Case |  | 2021-02-03 | Fuel Route Operational Sequence/Process for Defuelling EAN Available (REV 001) | 03-Feb-21 A | 03-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A26810 | HYA Fuel Handling Essential Safety Case |  | 2021-02-03 | Fuel Route Operational Sequence/Process for Defuelling EAN Available (REV 001) | 03-Feb-21 A | 03-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A25840 | HRA Fuel Handling Essential Safety Case | 2021-02-04 | 2021-07-26 | Human Reliability Assessment of Unsubstantaited Claims ##(Cost Summary)## (C2) (NEW) | 04-Feb-21 A | 26-Jul-21 A | 119 | 0 | 119 | 100% |  | Completed
ER6378LT | W222 | W222.A24640 | HRA Fuel Handling Essential Safety Case | 2021-02-04 | 2021-02-04 | Pre Job Brief for Human Reliability Assessment of Unsubstantaited Claims EAN | 04-Feb-21 A | 04-Feb-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A24640 | HYA Fuel Handling Essential Safety Case | 2021-02-04 | 2021-02-04 | Pre Job Brief for Human Reliability Assessment of Unsubstantaited Claims EAN | 04-Feb-21 A | 04-Feb-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A25840 | HYA Fuel Handling Essential Safety Case | 2021-02-04 | 2021-07-26 | Human Reliability Assessment of Unsubstantaited Claims ##(Cost Summary)## (C2) (NEW) | 04-Feb-21 A | 26-Jul-21 A | 119 | 0 | 119 | 100% |  | Completed
ER6378LT | W222 | W222.A24870 | HRA Fuel Handling Essential Safety Case | 2021-02-04 | 2021-06-15 | Review dataset in-line with updated H&I (Atkins Update Tables 1 to 4) | 04-Feb-21 A | 15-Jun-21 A | 9 | 0 | 90 | 100% |  | Completed
ER6650LT | W226 | W226.A24880 | HYA Fuel Handling Essential Safety Case | 2021-02-04 | 2021-06-15 | Review dataset in-line with updated H&I (Atkins Update Tables 1 to 4) | 04-Feb-21 A | 15-Jun-21 A | 9 | 0 | 90 | 100% |  | Completed
ER6371LT | W202 | W202.A4000 | HRA Reactors Shutdown Essential Safety Cases | 2020-12-07 | 2020-12-18 | Summary of Compliance with RADWASTE Assessment Principles EAN TR Completed and uploaded to CDMS | 05-Feb-21 A | 11-Feb-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A3910 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-23 | 2020-12-04 | TSA Address Comments on TR'd Summary of Compliance with RADWASTE Assessment Principles Draft EAN | 05-Feb-21 A | 05-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3970 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-12-04 | TSA Issue Final Summary of Compliance with RADWASTE Assessment Principles EAN | 05-Feb-21 A | 05-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4000 | HYA Reactors Shutdown Essential Safety Cases | 2020-12-07 | 2020-12-18 | Summary of Compliance with RADWASTE Assessment Principles EAN TR Completed and uploaded to CDMS | 05-Feb-21 A | 11-Feb-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A24650 | HRA Fuel Handling Essential Safety Case | 2021-02-05 | 2021-07-02 | Draft Human Reliability Assessment of Unsubstantaited Claims EAN | 05-Feb-21 A | 02-Jul-21 A | 20 | 0 | 102 | 100% |  | Completed
ER6650LT | W226 | W226.A24650 | HYA Fuel Handling Essential Safety Case | 2021-02-05 | 2021-07-02 | Draft Human Reliability Assessment of Unsubstantaited Claims EAN | 05-Feb-21 A | 02-Jul-21 A | 20 | 0 | 102 | 100% |  | Completed
ER6378LT | W222 | W222.A25140 | HRA Fuel Handling Essential Safety Case | 2021-02-08 | 2021-04-06 | Complete TR Form and Upload Basis of Analysis Report EAN to CDMS (UPDATE) (REV 001) | 08-Feb-21 A | 06-Apr-21 A | 6 | 0 | 39 | 100% |  | Completed
ER6650LT | W226 | W226.A25140 | HYA Fuel Handling Essential Safety Case | 2021-02-08 | 2021-04-06 | Complete TR Form and Upload Basis of Analysis Report EAN to CDMS (UPDATE) (REV 001) | 08-Feb-21 A | 06-Apr-21 A | 6 | 0 | 39 | 100% |  | Completed
ER6371LT | W202 | W202.A4610 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-06-22 | All Supporting Technical References Complete - Claim 5 ALARP | 09-Feb-21 A | 09-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A26150 | HYA Fuel Handling Essential Safety Case | 2021-02-09 | 2021-02-11 | Complete TR Form and Upload HAZOP updates resulting from defuelling process changes EAN to CDMS (REV 001) | 09-Feb-21 A | 11-Feb-21 A | 3 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | W222.A26150 | HRA Fuel Handling Essential Safety Case | 2021-02-09 | 2021-02-11 | Complete TR Form and Upload HAZOP updates resulting from defuelling process changes EAN to CDMS (REV 001) | 09-Feb-21 A | 11-Feb-21 A | 3 | 0 | 3 | 100% |  | Completed
ER6371LT | W202 | W202.A4660 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-06-22 | Optioneering Forming Report Completed | 09-Feb-21 A | 09-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4660 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-06-22 | Optioneering Forming Report Completed | 09-Feb-21 A | 09-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A26160 | HYA Fuel Handling Essential Safety Case |  | 2021-02-11 | HAZOP updates resulting from defuelling process changes EAN Available (REV 001) | 11-Feb-21 A | 11-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A4070 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-12-18 | Summary of Compliance with RADWASTE Assessment Principles EAN Completed | 11-Feb-21 A | 11-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4070 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-12-18 | Summary of Compliance with RADWASTE Assessment Principles EAN Completed | 11-Feb-21 A | 11-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4610 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-06-22 | All Supporting Technical References Complete - Claim 5 ALARP | 11-Feb-21 A | 11-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A26160 | HRA Fuel Handling Essential Safety Case |  | 2021-02-11 | HAZOP updates resulting from defuelling process changes EAN Available (REV 001) | 11-Feb-21 A | 11-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3720 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-10-28 | Issue Civil Integrity Overview Draft EAN to EDF for Review. | 12-Feb-21 A | 12-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2990 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-08-19 | Thermal Analysis (FEAT) of FPU Fully Extended Report Completed | 12-Feb-21 A | 12-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3720 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-10-28 | Issue Civil Integrity Overview Draft EAN to EDF for Review. | 12-Feb-21 A | 12-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2990 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-08-19 | Thermal Analysis (FEAT) of FPU Fully Extended Report Completed | 12-Feb-21 A | 12-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A6780 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-12-11 | <NEW SCOPE CR220> Specified Flows Report Completed | 12-Feb-21 A | 12-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A6780 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-12-11 | <NEW SCOPE CR 221> Specified Flows Report Completed | 12-Feb-21 A | 12-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18320 | HNB Reactors Shutdown Essential Safety Cases | 2020-12-11 | 2020-12-17 | <NEW SCOPE CR 187> - OPEX/ Literature Review - Address Comments from EDF Review on Draft EAN | 15-Feb-21 A | 17-Feb-21 A | 10 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A3730 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-29 | 2020-11-11 | Civil Integrity Overview Draft EAN Reviewed by EDF SQEP | 15-Feb-21 A | 26-Feb-21 A | 2 | 0 | 9 | 100% |  | Completed
ER6371LT | W202 | W202.A4540 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-17 | 2020-12-14 | Prepare Core Cooling Head Document Draft Report | 15-Feb-21 A | 23-Apr-21 A | 38 | 0 | 47 | 100% |  | Completed
ER6371LT | W202 | W202.A3500 | HRA Reactors Shutdown Essential Safety Cases | 2020-09-30 | 2020-10-13 | TSA Address Comments on TR'd Shutdown Margin Head Document | 15-Feb-21 A | 26-Feb-21 A | 5 | 0 | 9 | 100% |  | Completed
ER6661LT | W206 | W206.A3730 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-29 | 2020-11-11 | Civil Integrity Overview Draft EAN Reviewed by EDF SQEP | 15-Feb-21 A | 26-Feb-21 A | 2 | 0 | 9 | 100% |  | Completed
ER6661LT | W206 | W206.A4540 | HYA Reactors Shutdown Essential Safety Cases | 2021-05-07 | 2021-06-04 | Prepare Core Cooling Head Document Draft Report | 15-Feb-21 A | 23-Apr-21 A | 38 | 0 | 47 | 100% |  | Completed
ER6661LT | W206 | W206.A3500 | HYA Reactors Shutdown Essential Safety Cases | 2020-09-30 | 2020-10-13 | TSA Address Comments on TR'd Shutdown Margin Head Document | 15-Feb-21 A | 26-Feb-21 A | 5 | 0 | 9 | 100% |  | Completed
ER6378LT | W222 | W222.A26350 | HRA Fuel Handling Essential Safety Case | 2021-02-15 | 2021-04-27 | Verify The Grab Extend FPU Ledge/ Fault and Associated Protection Needs & Issue for Technical Review | 15-Feb-21 A | 27-Apr-21 A | 7 | 0 | 49 | 100% |  | Completed
ER6378LT | W222 | W222.A8890 | HRA Fuel Handling Essential Safety Case | 2021-02-15 | 2021-03-04 | Technical Review of FPU Lifting Integrity while Handling at the Reactor EAN | 15-Feb-21 A | 04-Mar-21 A | 5 | 0 | 13 | 100% |  | Completed
ER6650LT | W226 | W226.A8890 | HYA Fuel Handling Essential Safety Case | 2021-02-15 | 2021-03-04 | Technical Review of FPU Lifting Integrity while Handling at the Reactor EAN | 15-Feb-21 A | 04-Mar-21 A | 5 | 0 | 13 | 100% |  | Completed
ER6650LT | W226 | W226.A26350 | HYA Fuel Handling Essential Safety Case | 2021-02-15 | 2021-04-27 | Verify The Grab Extend FPU Ledge/ Fault and Associated Protection Needs & Issue for Technical Review | 15-Feb-21 A | 27-Apr-21 A | 7 | 0 | 49 | 100% |  | Completed
ER6371LT | W202 | W202.A7170 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-12-03 | <NEW SCOPE CR220> TSA Issue Final Specification of Multi-Channel MACE Model Report | 15-Feb-21 A | 15-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A7190 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-12-03 | <NEW SCOPE CR220> Specification of Multi-Channel MACE Model Report Completed | 15-Feb-21 A | 15-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A24890 | HRA Fuel Handling Essential Safety Case | 2021-02-16 | 2021-05-05 | Technical Review of Human Factors Assessment of Dropped FPU Fault Sequences EAN | 16-Feb-21 A | 05-May-21 A | 10 | 0 | 53 | 100% |  | Completed
ER6650LT | W226 | W226.A24890 | HYA Fuel Handling Essential Safety Case | 2021-02-16 | 2021-05-05 | Technical Review of Human Factors Assessment of Dropped FPU Fault Sequences EAN | 16-Feb-21 A | 05-May-21 A | 10 | 0 | 53 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18330 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-12-17 | <NEW SCOPE CR 187> - OPEX/ Literature Review - Issue Final EAN | 17-Feb-21 A | 17-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3890 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-12 | 2020-11-25 | Address Comments from EDF Review on Civil Integrity Overview Draft EAN | 17-Feb-21 A | 19-Mar-21 A | 5 | 0 | 23 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18340 | HNB Reactors Shutdown Essential Safety Cases | 2020-12-18 | 2021-01-05 | <NEW SCOPE CR 187> - OPEX/ Literature Review - EAN Completed and Uploaded to CDMS | 18-Feb-21 A | 26-Feb-21 A | 10 | 0 | 6 | 100% |  | Completed
ER6661LT | W206 | W206.A7170 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-12-03 | <NEW SCOPE CR 221> TSA Issue Final Specification of Multi-Channel MACE Model Report | 22-Feb-21 A | 22-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A7190 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-12-03 | <NEW SCOPE CR 221> Specification of Multi-Channel MACE Model Report Completed | 22-Feb-21 A | 22-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3590 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-10-13 | TSA Issue Final Shutdown Margin Head Document | 26-Feb-21 A | 26-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3820 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-11-06 | Verified Supporting Plant Issued to EDF for Technical Review. | 26-Feb-21 A | 26-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3590 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-10-13 | TSA Issue Final Shutdown Margin Head Document | 26-Feb-21 A | 26-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3820 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-11-06 | Verified Supporting Plant Issued to EDF for Technical Review. | 26-Feb-21 A | 26-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A23440 | HRA Fuel Handling Essential Safety Case |  | 2021-02-26 | CSP Model and Static Analysis EAN Available | 26-Feb-21 A | 26-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A10600 | HRA Fuel Handling Essential Safety Case | 2021-02-26 | 2021-02-26 | Complete TR Form and Upload Worker Dose Assessment (SKELETON) | 26-Feb-21 A | 26-Feb-21 A | 5 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A10610 | HRA Fuel Handling Essential Safety Case |  | 2021-02-26 | Worker Dose Assessment (SKELETON COMPLETE) | 26-Feb-21 A | 26-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A11380 | HRA Fuel Handling Essential Safety Case | 2021-02-26 | 2021-03-19 | Complete TR Form and Upload Justification for Pressure Boundary EAN to CDMS | 26-Feb-21 A | 19-Mar-21 A | 10 | 0 | 16 | 100% |  | Completed
ER6378LT | W222 | W222.A18210 | HRA Fuel Handling Essential Safety Case |  | 2021-02-26 | P6.6 Handover Document Available | 26-Feb-21 A | 26-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A18210 | HYA Fuel Handling Essential Safety Case |  | 2021-02-26 | P6.6 Handover Document Available | 26-Feb-21 A | 26-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A11380 | HYA Fuel Handling Essential Safety Case | 2021-02-26 | 2021-03-19 | Complete TR Form and Upload Justification for Pressure Boundary EAN to CDMS | 26-Feb-21 A | 19-Mar-21 A | 10 | 0 | 16 | 100% |  | Completed
ER6650LT | W226 | W226.A10610 | HYA Fuel Handling Essential Safety Case |  | 2021-02-26 | Worker Dose Assessment (SKELETON COMPLETE) | 26-Feb-21 A | 26-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A10600 | HYA Fuel Handling Essential Safety Case | 2021-02-26 | 2021-02-26 | Complete TR Form and Upload Worker Dose Assessment (SKELETON) | 26-Feb-21 A | 26-Feb-21 A | 5 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A23440 | HYA Fuel Handling Essential Safety Case |  | 2021-02-26 | CSP Model and Static Analysis EAN Available | 26-Feb-21 A | 26-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18350 | HNB Reactors Shutdown Essential Safety Cases |  | 2021-01-05 | <NEW SCOPE CR 187> - OPEX/ Literature Review - EAN Completed | 26-Feb-21 A | 26-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18390 | HNB Reactors Shutdown Essential Safety Cases |  |  | >>>OUTGOING ENABLER (W202) OPEX/ Literature Review - EAN Completed | 26-Feb-21 A | 26-Feb-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3850 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-09 | 2020-11-20 | Supporting Plant Technically Reviewed by EDF SQEP | 01-Mar-21 A | 31-Mar-21 A | 1 | 0 | 22 | 100% |  | Completed
ER6378LT | W222 | W222.A25420 | HRA Fuel Handling Essential Safety Case | 2021-03-01 | 2021-03-01 | Pre Job Brief for Defuelling NSPs/SAGs (REV 000) EAN | 01-Mar-21 A | 01-Mar-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A8260 | HRA Fuel Handling Essential Safety Case | 2021-03-01 | 2021-03-16 | Complete TR Form and Upload Defuelling Cooling and Match Analysis (Task FIle Note) | 01-Mar-21 A | 16-Mar-21 A | 2 | 0 | 12 | 100% |  | Completed
ER6378LT | W222 | W222.A18260 | HRA Fuel Handling Essential Safety Case | 2021-03-01 | 2021-07-27 | Defuelling NSPs/SAGs ##(Cost Summary)## | 01-Mar-21 A | 27-Jul-21 A | 59 | 0 | 103 | 100% |  | Completed
ER6650LT | W226 | W226.A18260 | HYA Fuel Handling Essential Safety Case | 2021-03-01 | 2021-07-27 | Defuelling NSPs/SAGs ##(Cost Summary)## | 01-Mar-21 A | 27-Jul-21 A | 59 | 0 | 103 | 100% |  | Completed
ER6650LT | W226 | W226.A25420 | HYA Fuel Handling Essential Safety Case | 2021-03-01 | 2021-03-01 | Pre Job Brief for Defuelling NSPs/SAGs (REV 000) EAN | 01-Mar-21 A | 01-Mar-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3850 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-09 | 2020-11-20 | Supporting Plant Technically Reviewed by EDF SQEP | 01-Mar-21 A | 31-Mar-21 A | 1 | 0 | 22 | 100% |  | Completed
ER6661LT | W206 | W206.A3890 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-12 | 2020-11-25 | Address Comments from EDF Review on Civil Integrity Overview Draft EAN | 01-Mar-21 A | 19-Mar-21 A | 15 | 0 | 15 | 100% |  | Completed
ER6378LT | W222 | W222.A25920 | HRA Fuel Handling Essential Safety Case | 2021-03-01 | 2021-05-26 | Dropped Fuel Head Document ##(Cost Summary)## (C5) (NEW) | 01-Mar-21 A | 26-May-21 A | 82 | 0 | 59 | 100% |  | Completed
ER6378LT | W222 | W222.A24990 | HRA Fuel Handling Essential Safety Case | 2021-03-01 | 2021-03-01 | Pre Job Brief for Dropped Fuel Head Document EAN | 01-Mar-21 A | 01-Mar-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A8260 | HYA Fuel Handling Essential Safety Case | 2021-03-01 | 2021-03-16 | Complete TR Form and Upload Defuelling Cooling and Match Analysis (Task FIle Note) | 01-Mar-21 A | 16-Mar-21 A | 2 | 0 | 12 | 100% |  | Completed
ER6650LT | W226 | W226.A24990 | HYA Fuel Handling Essential Safety Case | 2021-03-01 | 2021-03-01 | Pre Job Brief for Dropped Fuel Head Document EAN | 01-Mar-21 A | 01-Mar-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A25920 | HYA Fuel Handling Essential Safety Case | 2021-03-01 | 2021-05-26 | Dropped Fuel Head Document ##(Cost Summary)## (C5) (NEW) | 01-Mar-21 A | 26-May-21 A | 64 | 0 | 59 | 100% |  | Completed
ER6370LT | W201 | W201.1100 | HNB Reactors Shutdown Essential Safety Cases |  |  | Revise Implementation Appendix - Draft 5 | 01-Mar-21 A | 05-Mar-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | W201.1110 | HNB Reactors Shutdown Essential Safety Cases |  |  | CAT 1 SC Proposal Revised Draft 5 | 01-Mar-21 A | 15-Mar-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6378LT | W222 | W222.A25430 | HRA Fuel Handling Essential Safety Case | 2021-03-02 | 2021-06-04 | Draft Defuelling NSPs/SAGs (REV 000) EAN | 02-Mar-21 A | 04-Jun-21 A | 18 | 0 | 65 | 100% |  | Completed
ER6650LT | W226 | W226.A25430 | HYA Fuel Handling Essential Safety Case | 2021-03-02 | 2021-06-04 | Draft Defuelling NSPs/SAGs (REV 000) EAN | 02-Mar-21 A | 04-Jun-21 A | 18 | 0 | 65 | 100% |  | Completed
ER6378LT | W222 | W222.A25000 | HRA Fuel Handling Essential Safety Case | 2021-03-02 | 2021-05-26 | Draft Damage and Dropped Fuel Head Document EAN | 02-Mar-21 A | 26-May-21 A | 20 | 0 | 58 | 100% |  | Completed
ER6650LT | W226 | W226.A25000 | HYA Fuel Handling Essential Safety Case | 2021-03-02 | 2021-05-26 | Draft Damage and Dropped Fuel Head Document EAN | 02-Mar-21 A | 26-May-21 A | 20 | 0 | 58 | 100% |  | Completed
ER6378LT | W222 | W222.A27215 | HRA Fuel Handling Essential Safety Case |  | 2021-03-02 | Mid Job HOLD POINT | 02-Mar-21 A | 02-Mar-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27215 | HYA Fuel Handling Essential Safety Case |  | 2021-03-02 | Mid Job HOLD POINT | 02-Mar-21 A | 02-Mar-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A27225 | HRA Fuel Handling Essential Safety Case | 2021-03-03 | 2021-04-12 | Verify H&I Scheudules for all Facilities | 03-Mar-21 A | 12-Apr-21 A | 17 | 0 | 26 | 100% |  | Completed
ER6650LT | W226 | W226.A27225 | HYA Fuel Handling Essential Safety Case | 2021-03-03 | 2021-04-12 | Verify H&I Scheudules for all Facilities | 03-Mar-21 A | 12-Apr-21 A | 17 | 0 | 26 | 100% |  | Completed
ER6378LT | W222 | W222.A8900 | HRA Fuel Handling Essential Safety Case | 2021-03-05 | 2021-04-09 | Supplier Update and Issue FPU Lifting Integrity while Handling at the Reactor EAN | 05-Mar-21 A | 09-Apr-21 A | 5 | 0 | 23 | 100% |  | Completed
ER6650LT | W226 | W226.A8900 | HYA Fuel Handling Essential Safety Case | 2021-03-05 | 2021-04-09 | Supplier Update and Issue FPU Lifting Integrity while Handling at the Reactor EAN | 05-Mar-21 A | 09-Apr-21 A | 5 | 0 | 23 | 100% |  | Completed
ER6378LT | W222 | W222.A12560 | HRA Fuel Handling Essential Safety Case |  | 2021-03-05 | Management Strategy for Pond Water Treatment Arisings EAN Available | 05-Mar-21 A | 05-Mar-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A12560 | HYA Fuel Handling Essential Safety Case |  | 2021-03-05 | Management Strategy for Pond Water Treatment Arisings EAN Available | 05-Mar-21 A | 05-Mar-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1340 | HNB Reactors Shutdown Essential Safety Cases | 2020-09-28 | 2020-11-13 | INSA review & iteration of comments (using BARRIER MODEL) (HNB) | 15-Mar-21 A | 07-May-21 A | 20 | 0 | 37 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1450 | HNB Reactors Shutdown Essential Safety Cases | 2020-09-28 | 2021-01-08 | SC - Safety Case development - INSA - HNB - C-D - INSA | 15-Mar-21 A | 01-Jul-21 A | 47 | 0 | 74 | 100% |  | Completed
ER6378LT | W222 | W222.A18490 | HRA Fuel Handling Essential Safety Case |  | 2021-03-16 | Claim 4 - P6.2 HRA/HYA Essential Defuelling SC - Defuelling Cooling Complete | 16-Mar-21 A | 16-Mar-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A18760 | HRA Fuel Handling Essential Safety Case | 2021-03-16 | 2021-03-16 | Claim 4 - P6.2 HRA/HYA Essential Defuelling SC - Defuelling Cooling | 16-Mar-21 A | 16-Mar-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A18760 | HYA Fuel Handling Essential Safety Case | 2021-03-16 | 2021-03-16 | Claim 4 - P6.2 HYA/HYA Essential Defuelling SC - Defuelling Cooling | 16-Mar-21 A | 16-Mar-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A18490 | HYA Fuel Handling Essential Safety Case |  | 2021-03-16 | Claim 4 - P6.2 HYA/HYA Essential Defuelling SC - Defuelling Cooling Complete | 16-Mar-21 A | 16-Mar-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A8270 | HRA Fuel Handling Essential Safety Case |  | 2021-03-16 | Defuelling Cooling and Match Analysis (Task FIle Note) Available | 16-Mar-21 A | 16-Mar-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A8270 | HYA Fuel Handling Essential Safety Case |  | 2021-03-16 | Defuelling Cooling and Match Analysis (Task FIle Note) Available | 16-Mar-21 A | 16-Mar-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.1080 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - RFS - Vibration in the FPU - Summary | 18-Mar-21 A | 15-Apr-21 A | 25 | 0 | 19 | 100% |  | Completed
ER6371LT | W202 | W202.1090 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - RFS - Vibration in the FPU - Draft and issue RFS | 18-Mar-21 A | 18-Mar-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.1080 | HYA Reactors Shutdown Essential Safety Cases | 2021-03-18 | 2021-04-15 | <NEW SCOPE PENDING CC> - RFS - Vibration in the FPU - Summary | 18-Mar-21 A | 15-Apr-21 A | 25 | 0 | 19 | 100% |  | Completed
ER6661LT | W206 | W206.1090 | HYA Reactors Shutdown Essential Safety Cases | 2021-03-18 | 2021-03-18 | <NEW SCOPE PENDING CC> - RFS - Vibration in the FPU - Draft and issue RFS | 18-Mar-21 A | 18-Mar-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4690 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-23 | 2021-10-14 | Prepare the Safety Case Proposal (HYA) | 18-Mar-21 A | 27-Aug-21 A | 81 | 0 | 113 | 100% |  | Completed
ER6661LT | W206 | W206.A4680 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-23 | 2021-10-14 | SC - Safety Case development - Stakeholder comms Cat 1 - HYA - B-C - INA | 18-Mar-21 A | 23-Aug-21 A | 81 | 0 | 108 | 100% |  | Completed
ER6371LT | W202 | W202.1100 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - RFS - Vibration in the FPU - Supplier prepare and issue Offer | 19-Mar-21 A | 22-Mar-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.1100 | HYA Reactors Shutdown Essential Safety Cases | 2021-03-19 | 2021-03-22 | <NEW SCOPE PENDING CC> - RFS - Vibration in the FPU - Supplier prepare and issue Offer | 19-Mar-21 A | 22-Mar-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A4690 | HRA Reactors Shutdown Essential Safety Cases | 2021-06-23 | 2021-10-14 | Prepare the Safety Case Proposal (HRA) | 19-Mar-21 A | 27-Aug-21 A | 81 | 0 | 111 | 100% |  | Completed
ER6371LT | W202 | W202.A4680 | HRA Reactors Shutdown Essential Safety Cases | 2021-06-23 | 2021-10-14 | SC - Safety Case development - Stakeholder comms Cat 1 - HRA - B-C - INA | 19-Mar-21 A | 23-Aug-21 A | 94 | 0 | 107 | 100% |  | Completed
ER6371LT | W202 | W202.A3930 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-11-25 | Issue Civil Integrity Overview Final EAN | 19-Mar-21 A | 19-Mar-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3930 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-11-25 | Issue Civil Integrity Overview Final EAN | 19-Mar-21 A | 19-Mar-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A11390 | HRA Fuel Handling Essential Safety Case |  | 2021-03-19 | Justification for Pressure Boundary EAN Available | 19-Mar-21 A | 19-Mar-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A11390 | HYA Fuel Handling Essential Safety Case |  | 2021-03-19 | Justification for Pressure Boundary EAN Available | 19-Mar-21 A | 19-Mar-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | W201.1120 | HNB Reactors Shutdown Essential Safety Cases |  |  | CAT 1 SC Proposal Revised Draft 6 | 22-Mar-21 A | 05-May-21 A | 10 | 0 | 30 | 100% |  | Completed
ER6370LT | W201 | W201.1130 | HNB Reactors Shutdown Essential Safety Cases |  |  | Revise Implementation Appendix - Draft 6 | 22-Mar-21 A | 05-May-21 A | 5 | 0 | 30 | 100% |  | Completed
ER6371LT | W202 | W202.A3940 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-26 | 2020-12-09 | Civil Integrity Overview EAN Completed and uploaded to CDMS | 22-Mar-21 A | 24-Mar-21 A | 3 | 0 | 3 | 100% |  | Completed
ER6661LT | W206 | W206.A3940 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-26 | 2020-12-09 | Civil Integrity Overview EAN Completed and uploaded to CDMS | 22-Mar-21 A | 24-Mar-21 A | 3 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18360 | HNB Reactors Shutdown Essential Safety Cases | 2020-12-18 | 2021-01-05 | <NEW SCOPE CR 187> - Verify Vibration in the FPU Report | 23-Mar-21 A | 28-Apr-21 A | 10 | 0 | 24 | 100% |  | Completed
ER6371LT | W202 | W202.A4030 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-12-09 | Civil Integrity Overview EAN Completed | 24-Mar-21 A | 24-Mar-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4030 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-12-09 | Civil Integrity Overview EAN Completed | 24-Mar-21 A | 24-Mar-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A4310 | HRA Reactors Shutdown Essential Safety Cases | 2021-02-24 | 2021-03-09 | Containment Head Document Draft Report Verified by TSA | 25-Mar-21 A | 21-Jun-21 A | 19 | 0 | 59 | 100% |  | Completed
ER6661LT | W206 | W206.A4310 | HYA Reactors Shutdown Essential Safety Cases | 2021-02-24 | 2021-03-09 | Containment Head Document Draft Report Verified by TSA | 25-Mar-21 A | 21-Jun-21 A | 19 | 0 | 59 | 100% |  | Completed
ER6378LT | W222 | W222.A9810 | HRA Fuel Handling Essential Safety Case | 2021-03-26 | 2021-04-23 | Supplier Update and Issue Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN | 26-Mar-21 A | 23-Apr-21 A | 2 | 0 | 19 | 100% |  | Completed
ER6650LT | W226 | W226.A9810 | HYA Fuel Handling Essential Safety Case | 2021-03-26 | 2021-04-23 | Supplier Update and Issue Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN | 26-Mar-21 A | 23-Apr-21 A | 2 | 0 | 19 | 100% |  | Completed
ER6378LT | W222 | W222.A26680 | HRA Fuel Handling Essential Safety Case | 2021-03-26 | 2021-03-26 | Pre Job Brief for Review of Interlock Maintenance Review EAN (REV 000) | 26-Mar-21 A | 26-Mar-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A26680 | HYA Fuel Handling Essential Safety Case | 2021-03-26 | 2021-03-26 | Pre Job Brief for Review of Interlock Maintenance Review EAN (REV 000) | 26-Mar-21 A | 26-Mar-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A26690 | HRA Fuel Handling Essential Safety Case | 2021-03-29 | 2021-09-01 | Draft Review of Interlock Maintenance Review EAN (REV 000) | 29-Mar-21 A | 01-Sep-21 A | 20 | 0 | 108 | 100% |  | Completed
ER6650LT | W226 | W226.A26690 | HYA Fuel Handling Essential Safety Case | 2021-03-29 | 2021-09-01 | Draft Review of Interlock Maintenance Review EAN (REV 000) | 29-Mar-21 A | 01-Sep-21 A | 20 | 0 | 108 | 100% |  | Completed
ER6370LT | W201 | ER6370.A11270 | HNB Reactors Shutdown Essential Safety Cases |  | 2021-03-31 | Programme Management - End MS | 31-Mar-21 A | 31-Mar-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A27245 | HRA Fuel Handling Essential Safety Case | 2021-03-31 | 2021-05-19 | PSA Model Verification | 31-Mar-21 A | 19-May-21 A | 22 | 0 | 33 | 100% |  | Completed
ER6650LT | W226 | W226.A27245 | HYA Fuel Handling Essential Safety Case | 2021-03-31 | 2021-05-19 | PSA Model Verification | 31-Mar-21 A | 19-May-21 A | 23 | 0 | 32 | 100% |  | Completed
ER6371LT | W202 | W202.A3900 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-23 | 2020-12-04 | TSA Address Comments on TR'd Supporting Plant | 01-Apr-21 A | 12-Apr-21 A | 6 | 0 | 6 | 100% |  | Completed
ER6661LT | W206 | W206.A3900 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-23 | 2020-12-04 | TSA Address Comments on TR'd Supporting Plant | 01-Apr-21 A | 12-Apr-21 A | 6 | 0 | 6 | 100% |  | Completed
ER6378LT | W222 | W222.A26180 | HRA Fuel Handling Essential Safety Case | 2021-04-01 | 2021-04-26 | Additional Thermal and Rad Assessment of High Risk Areas##(Cost Summary)## ### (C5) | 01-Apr-21 A | 26-Apr-21 A | 28 | 0 | 16 | 100% |  | Completed
ER6378LT | W222 | W222.A26170 | HRA Fuel Handling Essential Safety Case | 2021-04-01 | 2021-04-01 | Pre Job Brief for Additional Thermal and Rad Assessment of High Risk Areas EAN | 01-Apr-21 A | 01-Apr-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A18410 | HRA Fuel Handling Essential Safety Case | 2021-04-01 | 2021-04-01 | Pre Job Brief for Operator Training Handover Strategy Document (to P6.6) | 01-Apr-21 A | 01-Apr-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A18370 | HRA Fuel Handling Essential Safety Case | 2021-04-01 | 2021-04-26 | Operator Training Handover Strategy Document ##(Cost Summary)## | 01-Apr-21 A | 26-Apr-21 A | 76 | 0 | 15 | 100% |  | Completed
ER6650LT | W226 | W226.A18370 | HYA Fuel Handling Essential Safety Case | 2021-04-01 | 2021-04-26 | Operator Training Handover Strategy Document ##(Cost Summary)## | 01-Apr-21 A | 26-Apr-21 A | 76 | 0 | 15 | 100% |  | Completed
ER6650LT | W226 | W226.A18410 | HYA Fuel Handling Essential Safety Case | 2021-04-01 | 2021-04-01 | Pre Job Brief for Operator Training Handover Strategy Document (to P6.6) | 01-Apr-21 A | 01-Apr-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A26170 | HYA Fuel Handling Essential Safety Case | 2021-04-01 | 2021-04-01 | Pre Job Brief for Additional Thermal and Rad Assessment of High Risk Areas EAN | 01-Apr-21 A | 01-Apr-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A26180 | HYA Fuel Handling Essential Safety Case | 2021-04-01 | 2021-04-26 | Additional Thermal and Rad Assessment of High Risk Areas##(Cost Summary)## ### (C5) | 01-Apr-21 A | 26-Apr-21 A | 28 | 0 | 16 | 100% |  | Completed
ER6371LT | W202 | W202.1000 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - Summary | 01-Apr-21 A | 23-Jul-21 A | 78 | 0 | 78 | 100% |  | Completed
ER6371LT | W202 | W202.1010 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - Prepare Draft EAN | 01-Apr-21 A | 28-May-21 A | 39 | 0 | 39 | 100% |  | Completed
ER6371LT | W202 | W202.1110 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - RFS - Vibration in the FPU - Review Offer, prepare and issue CI | 01-Apr-21 A | 06-Apr-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.1000 | HYA Reactors Shutdown Essential Safety Cases | 2021-04-01 | 2021-07-23 | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - Summary | 01-Apr-21 A | 23-Jul-21 A | 78 | 0 | 78 | 100% |  | Completed
ER6661LT | W206 | W206.1010 | HYA Reactors Shutdown Essential Safety Cases | 2021-04-01 | 2021-05-28 | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - Prepare Draft EAN | 01-Apr-21 A | 28-May-21 A | 39 | 0 | 39 | 100% |  | Completed
ER6661LT | W206 | W206.1110 | HYA Reactors Shutdown Essential Safety Cases | 2021-04-01 | 2021-04-06 | <NEW SCOPE PENDING CC> - RFS - Vibration in the FPU - Review Offer, prepare and issue CI | 01-Apr-21 A | 06-Apr-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | W222.A25150 | HRA Fuel Handling Essential Safety Case |  | 2021-04-06 | Basis of Analysis Report EAN Available (UPDATE) (REV 001) | 06-Apr-21 A | 06-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25150 | HYA Fuel Handling Essential Safety Case |  | 2021-04-06 | Basis of Analysis Report EAN Available (UPDATE) (REV 001) | 06-Apr-21 A | 06-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A26510 | HRA Fuel Handling Essential Safety Case | 2021-04-06 | 2021-04-07 | Verify LVDT Weight Sensing System matters arising from Review of HH1 FM Protection & Issue for Technical Review | 06-Apr-21 A | 07-Apr-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | W222.A26190 | HRA Fuel Handling Essential Safety Case | 2021-04-06 | 2021-04-16 | Draft Additional Thermal and Rad Assessment of High Risk Areas EAN | 06-Apr-21 A | 16-Apr-21 A | 9 | 0 | 9 | 100% |  | Completed
ER6378LT | W222 | W222.A23470 | HRA Fuel Handling Essential Safety Case | 2021-04-06 | 2021-04-14 | Verify Complex FEA (Dynamic R3 Analysis) EAN and Issue for Technical Review | 06-Apr-21 A | 14-Apr-21 A | 7 | 0 | 7 | 100% |  | Completed
ER6378LT | W222 | W222.A23350 | HRA Fuel Handling Essential Safety Case | 2021-04-06 | 2021-04-08 | Supplier Update and Issue Update Core Support Plate Properties Methodology & Toughness Properties EAN | 06-Apr-21 A | 08-Apr-21 A | 3 | 0 | 3 | 100% |  | Completed
ER6378LT | W222 | W222.A18420 | HRA Fuel Handling Essential Safety Case | 2021-04-06 | 2021-04-26 | Draft Operator Training Handover Strategy Document (to P6.6) | 06-Apr-21 A | 26-Apr-21 A | 20 | 0 | 14 | 100% |  | Completed
ER6650LT | W226 | W226.A18420 | HYA Fuel Handling Essential Safety Case | 2021-04-06 | 2021-04-26 | Draft Operator Training Handover Strategy Document (to P6.6) | 06-Apr-21 A | 26-Apr-21 A | 20 | 0 | 14 | 100% |  | Completed
ER6650LT | W226 | W226.A23350 | HYA Fuel Handling Essential Safety Case | 2021-04-06 | 2021-04-08 | Supplier Update and Issue Update Core Support Plate Properties Methodology & Toughness Properties EAN | 06-Apr-21 A | 08-Apr-21 A | 3 | 0 | 3 | 100% |  | Completed
ER6650LT | W226 | W226.A23470 | HYA Fuel Handling Essential Safety Case | 2021-04-06 | 2021-04-14 | Verify Complex FEA (Dynamic R3 Analysis) EAN and Issue for Technical Review | 06-Apr-21 A | 14-Apr-21 A | 7 | 0 | 7 | 100% |  | Completed
ER6650LT | W226 | W226.A26190 | HYA Fuel Handling Essential Safety Case | 2021-04-06 | 2021-04-16 | Draft Additional Thermal and Rad Assessment of High Risk Areas EAN | 06-Apr-21 A | 16-Apr-21 A | 9 | 0 | 9 | 100% |  | Completed
ER6650LT | W226 | W226.A26510 | HYA Fuel Handling Essential Safety Case | 2021-04-06 | 2021-04-07 | Verify LVDT Weight Sensing System matters arising from Review of HH1 FM Protection & Issue for Technical Review | 06-Apr-21 A | 07-Apr-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | W222.A24260 | HRA Fuel Handling Essential Safety Case | 2021-04-07 | 2021-04-13 | Supplier Update and Issue Hazards Review EAN | 07-Apr-21 A | 13-Apr-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A24260 | HYA Fuel Handling Essential Safety Case | 2021-04-07 | 2021-04-13 | Supplier Update and Issue Hazards Review EAN | 07-Apr-21 A | 13-Apr-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.1120 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - RFS - Vibration in the FPU - Supplier mobilisation time | 07-Apr-21 A | 14-Apr-21 A | 6 | 0 | 6 | 100% |  | Completed
ER6661LT | W206 | W206.1120 | HYA Reactors Shutdown Essential Safety Cases | 2021-04-07 | 2021-04-14 | <NEW SCOPE PENDING CC> - RFS - Vibration in the FPU - Supplier mobilisation time | 07-Apr-21 A | 14-Apr-21 A | 6 | 0 | 6 | 100% |  | Completed
ER6378LT | W222 | W222.A26520 | HRA Fuel Handling Essential Safety Case | 2021-04-08 | 2021-04-13 | Technical Review of LVDT Weight Sensing System matters arising from Review of HH1 FM Protection | 08-Apr-21 A | 13-Apr-21 A | 4 | 0 | 4 | 100% |  | Completed
ER6650LT | W226 | W226.A26520 | HYA Fuel Handling Essential Safety Case | 2021-04-08 | 2021-04-13 | Technical Review of LVDT Weight Sensing System matters arising from Review of HH1 FM Protection | 08-Apr-21 A | 13-Apr-21 A | 4 | 0 | 4 | 100% |  | Completed
ER6378LT | W222 | W222.A8910 | HRA Fuel Handling Essential Safety Case | 2021-04-09 | 2021-04-09 | Complete TR Form and Upload FPU Lifting Integrity while Handling at the Reactor EAN to CDMS | 09-Apr-21 A | 09-Apr-21 A | 5 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A8920 | HRA Fuel Handling Essential Safety Case |  | 2021-04-09 | FPU Lifting Integrity while Handling at the Reactor EAN Available | 09-Apr-21 A | 09-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A8920 | HYA Fuel Handling Essential Safety Case |  | 2021-04-09 | FPU Lifting Integrity while Handling at the Reactor EAN Available | 09-Apr-21 A | 09-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A8910 | HYA Fuel Handling Essential Safety Case | 2021-04-09 | 2021-04-09 | Complete TR Form and Upload FPU Lifting Integrity while Handling at the Reactor EAN to CDMS | 09-Apr-21 A | 09-Apr-21 A | 5 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A23360 | HRA Fuel Handling Essential Safety Case | 2021-04-09 | 2021-05-04 | Complete TR Form and Upload Update Core Support Plate Properties Methodology & Toughness Properties EAN to CDMS | 09-Apr-21 A | 04-May-21 A | 2 | 0 | 17 | 100% |  | Completed
ER6650LT | W226 | W226.A23360 | HYA Fuel Handling Essential Safety Case | 2021-04-09 | 2021-05-04 | Complete TR Form and Upload Update Core Support Plate Properties Methodology & Toughness Properties EAN to CDMS | 09-Apr-21 A | 04-May-21 A | 2 | 0 | 17 | 100% |  | Completed
ER6378LT | W222 | W222.A23540 | HRA Fuel Handling Essential Safety Case | 2021-04-12 | 2021-04-30 | Verify Fast Fracture R6 Analysis EAN and Issue for Technical Review | 12-Apr-21 A | 30-Apr-21 A | 10 | 0 | 14 | 100% |  | Completed
ER6650LT | W226 | W226.A23540 | HYA Fuel Handling Essential Safety Case | 2021-04-12 | 2021-04-30 | Verify Fast Fracture R6 Analysis EAN and Issue for Technical Review | 12-Apr-21 A | 30-Apr-21 A | 10 | 0 | 14 | 100% |  | Completed
ER6371LT | W202 | W202.A3960 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-12-04 | TSA Issue Final Supporting Plant Report | 12-Apr-21 A | 12-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3960 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-12-04 | TSA Issue Final Supporting Plant Report | 12-Apr-21 A | 12-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3990 | HRA Reactors Shutdown Essential Safety Cases | 2020-12-07 | 2020-12-18 | Supporting Plant Report TR Completed and uploaded to CDMS | 13-Apr-21 A | 26-Apr-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.A3990 | HYA Reactors Shutdown Essential Safety Cases | 2020-12-07 | 2020-12-18 | Supporting Plant Report TR Completed and uploaded to CDMS | 13-Apr-21 A | 26-Apr-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6378LT | W222 | W222.A26530 | HRA Fuel Handling Essential Safety Case | 2021-04-14 | 2021-04-14 | Supplier Update and Issue LVDT Weight Sensing System matters arising from Review of HH1 FM Protection | 14-Apr-21 A | 14-Apr-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A24270 | HRA Fuel Handling Essential Safety Case | 2021-04-14 | 2021-04-19 | Complete TR Form and Upload Hazards Review EAN to CDMS | 14-Apr-21 A | 19-Apr-21 A | 5 | 0 | 3 | 100% |  | Completed
ER6650LT | W226 | W226.A24270 | HYA Fuel Handling Essential Safety Case | 2021-04-14 | 2021-04-19 | Complete TR Form and Upload Hazards Review EAN to CDMS | 14-Apr-21 A | 19-Apr-21 A | 5 | 0 | 3 | 100% |  | Completed
ER6650LT | W226 | W226.A26530 | HYA Fuel Handling Essential Safety Case | 2021-04-14 | 2021-04-14 | Supplier Update and Issue LVDT Weight Sensing System matters arising from Review of HH1 FM Protection | 14-Apr-21 A | 14-Apr-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A26540 | HRA Fuel Handling Essential Safety Case | 2021-04-15 | 2021-04-15 | Complete LVDT Weight Sensing System matters arising from Review of HH1 FM Protection to CDMS | 15-Apr-21 A | 15-Apr-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A26040 | HRA Fuel Handling Essential Safety Case | 2021-04-15 | 2021-04-26 | Concept Detail and Specification ##(Cost Summary)## (C5) (NEW) | 15-Apr-21 A | 26-Apr-21 A | 65 | 0 | 7 | 100% |  | Completed
ER6378LT | W222 | W222.A23870 | HRA Fuel Handling Essential Safety Case | 2021-04-15 | 2021-04-15 | Pre Job Brief for Concept Detail and Specification EAN | 15-Apr-21 A | 15-Apr-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A23490 | HRA Fuel Handling Essential Safety Case | 2021-04-15 | 2021-05-21 | Supplier Update and Issue Complex FEA (Dynamic R3 Analysis) EAN | 15-Apr-21 A | 21-May-21 A | 5 | 0 | 26 | 100% |  | Completed
ER6650LT | W226 | W226.A23490 | HYA Fuel Handling Essential Safety Case | 2021-04-15 | 2021-05-21 | Supplier Update and Issue Complex FEA (Dynamic R3 Analysis) EAN | 15-Apr-21 A | 21-May-21 A | 5 | 0 | 26 | 100% |  | Completed
ER6650LT | W226 | W226.A23870 | HYA Fuel Handling Essential Safety Case | 2021-04-15 | 2021-04-15 | Pre Job Brief for Concept Detail and Specification EAN | 15-Apr-21 A | 15-Apr-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A26040 | HYA Fuel Handling Essential Safety Case | 2021-04-15 | 2021-04-26 | Concept Detail and Specification ##(Cost Summary)## (C5) (NEW) | 15-Apr-21 A | 26-Apr-21 A | 65 | 0 | 7 | 100% |  | Completed
ER6650LT | W226 | W226.A26540 | HYA Fuel Handling Essential Safety Case | 2021-04-15 | 2021-04-15 | Complete LVDT Weight Sensing System matters arising from Review of HH1 FM Protection to CDMS | 15-Apr-21 A | 15-Apr-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.1130 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - RFS - Vibration in the FPU - Pre Job Brief | 15-Apr-21 A | 15-Apr-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.1130 | HYA Reactors Shutdown Essential Safety Cases | 2021-04-15 | 2021-04-15 | <NEW SCOPE PENDING CC> - RFS - Vibration in the FPU - Pre Job Brief | 15-Apr-21 A | 15-Apr-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A26550 | HRA Fuel Handling Essential Safety Case |  | 2021-04-15 | LVDT Weight Sensing System matters arising from Review of HH1 FM Protection Available | 15-Apr-21 A | 15-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A26550 | HYA Fuel Handling Essential Safety Case |  | 2021-04-15 | LVDT Weight Sensing System matters arising from Review of HH1 FM Protection Available | 15-Apr-21 A | 15-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A23880 | HRA Fuel Handling Essential Safety Case | 2021-04-16 | 2021-04-26 | Draft Concept Detail and Specification EAN | 16-Apr-21 A | 26-Apr-21 A | 35 | 0 | 6 | 100% |  | Completed
ER6650LT | W226 | W226.A23880 | HYA Fuel Handling Essential Safety Case | 2021-04-16 | 2021-04-26 | Draft Concept Detail and Specification EAN | 16-Apr-21 A | 26-Apr-21 A | 35 | 0 | 6 | 100% |  | Completed
ER6371LT | W202 | W202.A18260 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - Prepare Vibration in the FPU EAN | 16-Apr-21 A | 10-Jun-21 A | 21 | 0 | 38 | 100% |  | Completed
ER6371LT | W202 | W202.A18255 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - Vibration in the FPU EAN - Summary | 16-Apr-21 A | 30-Jul-21 A | 74 | 0 | 74 | 100% |  | Completed
ER6661LT | W206 | W206.A18260 | HYA Reactors Shutdown Essential Safety Cases | 2021-04-16 | 2021-06-10 | <NEW SCOPE PENDING CC> - Prepare Vibration in the FPU Report | 16-Apr-21 A | 10-Jun-21 A | 21 | 0 | 38 | 100% |  | Completed
ER6661LT | W206 | W206.A18255 | HYA Reactors Shutdown Essential Safety Cases | 2021-04-16 | 2021-07-30 | <NEW SCOPE PENDING CC> - Vibration in the FPU Report - Summary | 16-Apr-21 A | 30-Jul-21 A | 74 | 0 | 74 | 100% |  | Completed
ER6378LT | W222 | W222.A24280 | HRA Fuel Handling Essential Safety Case |  | 2021-04-19 | Hazards Review EAN Available | 19-Apr-21 A | 19-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A24280 | HYA Fuel Handling Essential Safety Case |  | 2021-04-19 | Hazards Review EAN Available | 19-Apr-21 A | 19-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.1240 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - RFS - HF Assessment of Misloading Fault - Summary | 19-Apr-21 A | 14-May-21 A | 15 | 0 | 19 | 100% |  | Completed
ER6371LT | W202 | W202.1250 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - RFS - HF Assessment of Misloading Fault - Draft and issue RFS | 19-Apr-21 A | 23-Apr-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.1420 | HYA Reactors Shutdown Essential Safety Cases | 2021-04-19 | 2021-05-14 | <NEW SCOPE PENDING CC> - RFS - HF Assessment of Misloading Fault - Summary | 19-Apr-21 A | 14-May-21 A | 15 | 0 | 19 | 100% |  | Completed
ER6661LT | W206 | W206.1430 | HYA Reactors Shutdown Essential Safety Cases | 2021-04-19 | 2021-04-23 | <NEW SCOPE PENDING CC> - RFS - HF Assessment of Misloading Fault - Draft and issue RFS | 19-Apr-21 A | 23-Apr-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A26200 | HRA Fuel Handling Essential Safety Case | 2021-04-19 | 2021-04-21 | Verify Additional Thermal and Rad Assessment of High Risk Areas and Issue for Technical Review | 19-Apr-21 A | 21-Apr-21 A | 3 | 0 | 3 | 100% |  | Completed
ER6650LT | W226 | W226.A26200 | HYA Fuel Handling Essential Safety Case | 2021-04-19 | 2021-04-21 | Verify Additional Thermal and Rad Assessment of High Risk Areas and Issue for Technical Review | 19-Apr-21 A | 21-Apr-21 A | 3 | 0 | 3 | 100% |  | Completed
ER6650LT | W226 | W226.A9010 | HYA Fuel Handling Essential Safety Case | 2021-04-21 | 2021-05-14 | Verification of Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN | 21-Apr-21 A | 14-May-21 A | 14 | 0 | 16 | 100% |  | Completed
ER6378LT | W222 | W222.A9010 | HRA Fuel Handling Essential Safety Case | 2021-04-21 | 2021-05-14 | Verification of Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN | 21-Apr-21 A | 14-May-21 A | 14 | 0 | 17 | 100% |  | Completed
ER6378LT | W222 | W222.A26210 | HRA Fuel Handling Essential Safety Case | 2021-04-22 | 2021-04-26 | Technical Review of Additional Thermal and Rad Assessment of High Risk AreasEAN | 22-Apr-21 A | 26-Apr-21 A | 3 | 0 | 3 | 100% |  | Completed
ER6650LT | W226 | W226.A26210 | HYA Fuel Handling Essential Safety Case | 2021-04-22 | 2021-04-26 | Technical Review of Additional Thermal and Rad Assessment of High Risk AreasEAN | 22-Apr-21 A | 26-Apr-21 A | 3 | 0 | 3 | 100% |  | Completed
ER6371LT | W202 | W202.A4560 | HRA Reactors Shutdown Essential Safety Cases | 2020-12-15 | 2020-12-30 | Core Cooling Head Document Draft Report Verified by TSA | 23-Apr-21 A | 30-Jun-21 A | 24 | 0 | 46 | 100% |  | Completed
ER6661LT | W206 | W206.A4560 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-07 | 2021-06-18 | Core Cooling Head Document Draft Report Verified by TSA | 23-Apr-21 A | 30-Jun-21 A | 24 | 0 | 46 | 100% |  | Completed
ER6371LT | W202 | W202.1260 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - RFS - HF Assessment of Misloading Fault - Supplier prepare and issue Offer | 23-Apr-21 A | 26-Apr-21 A | 3 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.1440 | HYA Reactors Shutdown Essential Safety Cases | 2021-04-23 | 2021-04-26 | <NEW SCOPE PENDING CC> - RFS - HF Assessment of Misloading Fault - Supplier prepare and issue Offer | 23-Apr-21 A | 26-Apr-21 A | 3 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A2206050 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-02-24 | >>>INCOMING ENABLER (W222.A22250) Criticality Assessment for Dropped FPU at Reactor (DRY Condition) EAN Available ????? | 26-Apr-21 A | 26-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206070 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-10-20 | >>>MIRROR OF INCOMING ENABLER (W222.A22250)Criticality Assessment for Dropped FPU at Reactor(DRY Condition)EAN Available | 26-Apr-21 A | 26-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206050 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-02 | >>>INCOMING ENABLER (W226) Criticality Assessment for Dropped FPU at Reactor (DRY Condition) EAN Available ????? | 26-Apr-21 A | 26-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206070 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-10-20 | >>>MIRROR OF INCOMING ENABLER (W226)Criticality Assessment for Dropped FPU at Reactor(DRY Condition)EAN Available | 26-Apr-21 A | 26-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3950 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-11-10 | INTERFACE MILESTONE - (W222.A22250, A22260)Criticality Assessment for Dropped FPU at Reactor(DRY Condition)EAN Available | 26-Apr-21 A | 26-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5580 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-04-07 | HRA References not Impacted by Core Support Plate/Shock Absorber Decision Complete | 26-Apr-21 A | 26-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5560 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-04-07 | HYA References not Impacted by Core Support Plate/Shock Absorber Decision Complete | 26-Apr-21 A | 26-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A26220 | HRA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-26 | Supplier Update and Issue Additional Thermal and Rad Assessment of High Risk Areas EAN | 26-Apr-21 A | 26-Apr-21 A | 2 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A26230 | HRA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-26 | Complete TR Form and Upload Additional Thermal and Rad Assessment of High Risk Areas EAN to CDMS | 26-Apr-21 A | 26-Apr-21 A | 2 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A26240 | HRA Fuel Handling Essential Safety Case |  | 2021-04-26 | Additional Thermal and Rad Assessment of High Risk Areas EAN Available | 26-Apr-21 A | 26-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A23890 | HRA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-26 | Verify Concept Detail and Specification EAN for Technical Review | 26-Apr-21 A | 26-Apr-21 A | 19 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A23910 | HRA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-26 | Supplier Update and Issue Concept Detail and Specification EAN | 26-Apr-21 A | 26-Apr-21 A | 5 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A23920 | HRA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-26 | Complete TR Form and Upload Concept Detail and Specification EAN to CDMS | 26-Apr-21 A | 26-Apr-21 A | 5 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A23930 | HRA Fuel Handling Essential Safety Case |  | 2021-04-26 | Concept Detail and Specification EAN Available | 26-Apr-21 A | 26-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A9530 | HRA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-26 | Verify Criticality Assessment for Dropped FPU at Reactor EAN and Issue for Technical Review | 26-Apr-21 A | 26-Apr-21 A | 10 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A9540 | HRA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-26 | Technical Review of Criticality Assessment for Dropped FPU at Reactor EAN | 26-Apr-21 A | 26-Apr-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A9550 | HRA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-26 | Supplier Update and Issue Criticality Assessment for Dropped FPU at Reactor EAN | 26-Apr-21 A | 26-Apr-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A9560 | HRA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-26 | Complete TR Form and Upload Criticality Assessment for Dropped FPU at Reactor EAN to CDMS | 26-Apr-21 A | 26-Apr-21 A | 5 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A18430 | HRA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-26 | Verification of Operator Training Handover Strategy Document (to P6.6) | 26-Apr-21 A | 26-Apr-21 A | 10 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A18440 | HRA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-26 | Technical Review of Operator Training Handover Strategy Document (to P6.6) | 26-Apr-21 A | 26-Apr-21 A | 10 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A18450 | HRA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-26 | Supplier Update and Issue Operator Training Handover Strategy Document (to P6.6) | 26-Apr-21 A | 26-Apr-21 A | 2 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A18460 | HRA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-26 | Complete TR Form and Upload Operator Training Handover Strategy Document (to P6.6) to CDMS | 26-Apr-21 A | 26-Apr-21 A | 2 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A18470 | HRA Fuel Handling Essential Safety Case |  | 2021-04-26 | Operator Training Handover Strategy Document (to P6.6) Available | 26-Apr-21 A | 26-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A22250 | HRA Fuel Handling Essential Safety Case |  | 2021-04-26 | >>>OUTGOING ENABLER (W202.A2206050) Criticality Assessment for Dropped FPU at Reactor - EAN Available | 26-Apr-21 A | 26-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A18470 | HYA Fuel Handling Essential Safety Case |  | 2021-04-26 | Operator Training Handover Strategy Document (to P6.6) Available | 26-Apr-21 A | 26-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A18460 | HYA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-26 | Complete TR Form and Upload Operator Training Handover Strategy Document (to P6.6) to CDMS | 26-Apr-21 A | 26-Apr-21 A | 2 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A18450 | HYA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-26 | Supplier Update and Issue Operator Training Handover Strategy Document (to P6.6) | 26-Apr-21 A | 26-Apr-21 A | 2 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A18440 | HYA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-26 | Technical Review of Operator Training Handover Strategy Document (to P6.6) | 26-Apr-21 A | 26-Apr-21 A | 10 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A18430 | HYA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-26 | Verification of Operator Training Handover Strategy Document (to P6.6) | 26-Apr-21 A | 26-Apr-21 A | 10 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A9560 | HYA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-26 | Complete TR Form and Upload Criticality Assessment for Dropped FPU at Reactor EAN to CDMS | 26-Apr-21 A | 26-Apr-21 A | 5 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A9550 | HYA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-26 | Supplier Update and Issue Criticality Assessment for Dropped FPU at Reactor EAN | 26-Apr-21 A | 26-Apr-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A9540 | HYA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-26 | Technical Review of Criticality Assessment for Dropped FPU at Reactor EAN | 26-Apr-21 A | 26-Apr-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A9530 | HYA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-26 | Verify Criticality Assessment for Dropped FPU at Reactor EAN and Issue for Technical Review | 26-Apr-21 A | 26-Apr-21 A | 10 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A23930 | HYA Fuel Handling Essential Safety Case |  | 2021-04-26 | Concept Detail and Specification EAN Available | 26-Apr-21 A | 26-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A23920 | HYA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-26 | Complete TR Form and Upload Concept Detail and Specification EAN to CDMS | 26-Apr-21 A | 26-Apr-21 A | 5 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A23910 | HYA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-26 | Supplier Update and Issue Concept Detail and Specification EAN | 26-Apr-21 A | 26-Apr-21 A | 5 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A23890 | HYA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-26 | Verify Concept Detail and Specification EAN for Technical Review | 26-Apr-21 A | 26-Apr-21 A | 19 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A24030 | HYA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-06-02 | Verify Dropped FPU Optioneering Documents EAN for Technical Review | 26-Apr-21 A | 02-Jun-21 A | 7 | 0 | 25 | 100% |  | Completed
ER6650LT | W226 | W226.A26230 | HYA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-26 | Complete TR Form and Upload Additional Thermal and Rad Assessment of High Risk Areas EAN to CDMS | 26-Apr-21 A | 26-Apr-21 A | 2 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A26220 | HYA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-26 | Supplier Update and Issue Additional Thermal and Rad Assessment of High Risk Areas EAN | 26-Apr-21 A | 26-Apr-21 A | 2 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A27220 | HYA Fuel Handling Essential Safety Case |  | 2021-04-26 | >>>OUTGOING ENABLER (W206.A8500?) Criticality Assessment for Dropped FPU at Reactor (DRY Condition) | 26-Apr-21 A | 26-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A24030 | HRA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-06-02 | Verify Dropped FPU Optioneering Documents EAN for Technical Review | 26-Apr-21 A | 02-Jun-21 A | 11 | 0 | 25 | 100% |  | Completed
ER6378LT | W222 | W222.A9820 | HRA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-28 | Complete TR Form and Upload Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN to CDMS | 26-Apr-21 A | 28-Apr-21 A | 5 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | W226.A9820 | HYA Fuel Handling Essential Safety Case | 2021-04-26 | 2021-04-28 | Complete TR Form and Upload Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN to CDMS | 26-Apr-21 A | 28-Apr-21 A | 5 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A4060 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-12-18 | Supporting Plant Report Completed | 26-Apr-21 A | 26-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A4440 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-12-18 | All Supporting Technical References Complete - Claim 3 Cooling | 26-Apr-21 A | 26-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4060 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-12-18 | Supporting Plant Report Completed | 26-Apr-21 A | 26-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4440 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-04-07 | All Supporting Technical References Complete - Claim 3 Cooling | 26-Apr-21 A | 26-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3950 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-11-10 | INTERFACE MILESTONE - (W222.A22250, A22260)Criticality Assessment for Dropped FPU at Reactor(DRY Condition)EAN Available | 26-Apr-21 A | 26-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A9570 | HRA Fuel Handling Essential Safety Case |  | 2021-04-26 | Criticality Assessment for Dropped FPU at Reactor EAN Available | 26-Apr-21 A | 26-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A9570 | HYA Fuel Handling Essential Safety Case |  | 2021-04-26 | Criticality Assessment for Dropped FPU at Reactor EAN Available | 26-Apr-21 A | 26-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A26240 | HYA Fuel Handling Essential Safety Case |  | 2021-04-26 | Additional Thermal and Rad Assessment of High Risk Areas EAN Available | 26-Apr-21 A | 26-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.1270 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - RFS - HF Assessment of Misloading Fault - Review Offer, prepare and issue CI | 27-Apr-21 A | 27-Apr-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.1450 | HYA Reactors Shutdown Essential Safety Cases | 2021-04-27 | 2021-04-27 | <NEW SCOPE PENDING CC> - RFS - HF Assessment of Misloading Fault - Review Offer, prepare and issue CI | 27-Apr-21 A | 27-Apr-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1510 | HNB Reactors Shutdown Essential Safety Cases | 2020-08-17 | 2020-09-25 | CO Sign-off (HNB) | 28-Apr-21 A | 05-May-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A26360 | HRA Fuel Handling Essential Safety Case | 2021-04-28 | 2021-06-01 | Technical Review of The Grab Extend FPU Ledge/ Fault and Associated Protection Needs EAN | 28-Apr-21 A | 01-Jun-21 A | 14 | 0 | 23 | 100% |  | Completed
ER6378LT | W222 | W222.A9830 | HRA Fuel Handling Essential Safety Case |  | 2021-04-28 | Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN Available | 28-Apr-21 A | 28-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A9830 | HYA Fuel Handling Essential Safety Case |  | 2021-04-28 | Adjacent Fuel Assembly Drop Assessment & Associated Radcons EAN Available | 28-Apr-21 A | 28-Apr-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A26360 | HYA Fuel Handling Essential Safety Case | 2021-04-28 | 2021-06-01 | Technical Review of The Grab Extend FPU Ledge/ Fault and Associated Protection Needs EAN | 28-Apr-21 A | 01-Jun-21 A | 14 | 0 | 23 | 100% |  | Completed
ER6650LT | W226 | W226.A25110 | HYA Fuel Handling Essential Safety Case | 2021-05-03 | 2021-05-04 | Complete TR Form and Upload Environmental Permit Compliance EAN to CDMS | 03-May-21 A | 04-May-21 A | 44 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A23570 | HRA Fuel Handling Essential Safety Case | 2021-05-04 | 2021-05-21 | Complete TR Form and Upload Fast Fracture R6 Analysis EAN to CDMS | 04-May-21 A | 21-May-21 A | 5 | 0 | 13 | 100% |  | Completed
ER6650LT | W226 | W226.A23570 | HYA Fuel Handling Essential Safety Case | 2021-05-04 | 2021-05-21 | Complete TR Form and Upload Fast Fracture R6 Analysis EAN to CDMS | 04-May-21 A | 21-May-21 A | 5 | 0 | 14 | 100% |  | Completed
ER6650LT | W226 | W226.A25120 | HYA Fuel Handling Essential Safety Case |  | 2021-05-04 | Environmental Permit Compliance EAN Available | 04-May-21 A | 04-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3600 | HRA Reactors Shutdown Essential Safety Cases | 2020-10-14 | 2020-10-27 | Shutdown Margin Head Document TR Completed and uploaded to CDMS | 04-May-21 A | 10-Jun-21 A | 10 | 0 | 27 | 100% |  | Completed
ER6661LT | W206 | W206.A3600 | HYA Reactors Shutdown Essential Safety Cases | 2020-10-14 | 2020-10-27 | Shutdown Margin Head Document TR Completed and uploaded to CDMS | 04-May-21 A | 10-Jun-21 A | 10 | 0 | 27 | 100% |  | Completed
ER6378LT | W222 | W222.A25110 | HRA Fuel Handling Essential Safety Case | 2021-05-04 | 2021-05-04 | Complete TR Form and Upload Environmental Permit Compliance EAN to CDMS | 04-May-21 A | 04-May-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A24940 | HRA Fuel Handling Essential Safety Case | 2021-05-04 | 2021-06-16 | Verify Human Factors Defuelling Issues Management Report EAN & Issue for Technical Review | 04-May-21 A | 16-Jun-21 A | 15 | 0 | 31 | 100% |  | Completed
ER6650LT | W226 | W226.A24940 | HYA Fuel Handling Essential Safety Case | 2021-05-04 | 2021-06-16 | Verify Human Factors Defuelling Issues Management Report EAN & Issue for Technical Review | 04-May-21 A | 16-Jun-21 A | 15 | 0 | 31 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18370 | HNB Reactors Shutdown Essential Safety Cases | 2021-01-06 | 2021-01-19 | <NEW SCOPE CR 187> - Vibration in the FPU Report Completed and Uploaded to CDMS | 04-May-21 A | 05-May-21 A | 5 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | W222.A25120 | HRA Fuel Handling Essential Safety Case |  | 2021-05-04 | Environmental Permit Compliance EAN Available | 04-May-21 A | 04-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A23370 | HRA Fuel Handling Essential Safety Case |  | 2021-05-04 | Update Core Support Plate Properties Methodology & Toughness Properties EAN Available | 04-May-21 A | 04-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A23370 | HYA Fuel Handling Essential Safety Case |  | 2021-05-04 | Update Core Support Plate Properties Methodology & Toughness Properties EAN Available | 04-May-21 A | 04-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1370 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-09-25 | Verification complete (HNB) | 05-May-21 A | 05-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18380 | HNB Reactors Shutdown Essential Safety Cases |  | 2021-01-19 | <NEW SCOPE CR 187> - Vibration in the FPU Report Complete | 05-May-21 A | 05-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A24750 | HRA Fuel Handling Essential Safety Case | 2021-05-06 | 2021-06-18 | Supplier Update and Issue Human Factors Assessment of Dropped FPU Fault Sequences EAN | 06-May-21 A | 18-Jun-21 A | 10 | 0 | 31 | 100% |  | Completed
ER6650LT | W226 | W226.A24750 | HYA Fuel Handling Essential Safety Case | 2021-05-06 | 2021-06-18 | Supplier Update and Issue Human Factors Assessment of Dropped FPU Fault Sequences EAN | 06-May-21 A | 18-Jun-21 A | 10 | 0 | 31 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1380 | HNB Reactors Shutdown Essential Safety Cases | 2020-09-28 | 2020-10-02 | DA (Authorised Designer) Approval of CAT1 Safety Case (HNB) | 06-May-21 A | 12-May-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | W201.1140 | HNB Reactors Shutdown Essential Safety Cases |  |  | INSA of Main Proposal - DA review/respond to comments | 06-May-21 A | 12-May-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | W201.1150 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 0 - DA respond to comments | 06-May-21 A | 12-May-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | W201.1180 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 1 - Formal INSA | 06-May-21 A | 19-May-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | W201.1200 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 2 - DA respond to comments | 06-May-21 A | 12-May-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | W201.1240 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 3 - Formal INSA | 06-May-21 A | 19-May-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | W201.1260 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 4 - Formal INSA | 06-May-21 A | 19-May-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | W201.1310 | HNB Reactors Shutdown Essential Safety Cases |  |  | INSA of Appendices | 06-May-21 A | 12-May-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16170 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-09-25 | Verified Draft Available for INSA (T-7) EC 364023 <NSRS SC Approach & Outline> (Cat 1 KDM) (HNB) RS Essential SC | 07-May-21 A | 07-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.1280 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - RFS - HF Assessment of Misloading Fault - Supplier mobilisation time | 12-May-21 A | 13-May-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.1460 | HYA Reactors Shutdown Essential Safety Cases | 2021-05-12 | 2021-05-13 | <NEW SCOPE PENDING CC> - RFS - HF Assessment of Misloading Fault - Supplier mobilisation time | 12-May-21 A | 13-May-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1420 | HNB Reactors Shutdown Essential Safety Cases | 2020-11-09 | 2020-11-13 | Incorporate INSA comments (HNB) | 13-May-21 A | 01-Jun-21 A | 5 | 0 | 13 | 100% |  | Completed
ER6370LT | W201 | W201.1160 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 0 - Formal INSA | 13-May-21 A | 19-May-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | W201.1210 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 2 - Formal INSA | 13-May-21 A | 26-May-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6370LT | W201 | W201.1320 | HNB Reactors Shutdown Essential Safety Cases |  |  | INSA of Appendices - DA respond to comments | 13-May-21 A | 19-May-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.1290 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - RFS - HF Assessment of Misloading Fault - Pre Job Brief | 14-May-21 A | 14-May-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.1470 | HYA Reactors Shutdown Essential Safety Cases | 2021-05-14 | 2021-05-14 | <NEW SCOPE PENDING CC> - RFS - HF Assessment of Misloading Fault - Pre Job Brief | 14-May-21 A | 14-May-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A2600 | HNB Enhanced Defuelling Safety Cases | 2020-08-17 | 2020-08-18 | Flow Diversion EAN - Draft and issue RFS | 14-May-21 A | 01-Jun-21 A | 2 | 0 | 12 | 100% |  | Completed
ER6372LT | W203 | W203.A2595 | HNB Enhanced Defuelling Safety Cases | 2020-08-17 | 2020-09-24 | RFS - Flow Diversion EAN - Summary | 14-May-21 A | 01-Jun-21 A | 38 | 0 | 12 | 100% |  | Completed
ER6378LT | W222 | W222.A25790 | HRA Fuel Handling Essential Safety Case | 2021-05-17 | 2023-05-26 | Living Safety Document ##(Cost Summary)## (C1) (NEW) ** | 17-May-21 A | 22-Jul-24 A | 802 | 0 | 804 | 100% |  | Completed
ER6378LT | W222 | W222.A24290 | HRA Fuel Handling Essential Safety Case | 2021-05-17 | 2021-05-17 | Pre Job Brief for Living Safety Document EAN | 17-May-21 A | 17-May-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A9020 | HYA Fuel Handling Essential Safety Case | 2021-05-17 | 2021-05-28 | Technical Review of Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN | 17-May-21 A | 28-May-21 A | 5 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | W226.A24290 | HYA Fuel Handling Essential Safety Case | 2021-05-17 | 2021-05-17 | Pre Job Brief for Living Safety Document EAN | 17-May-21 A | 17-May-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25790 | HYA Fuel Handling Essential Safety Case | 2021-05-17 | 2023-05-26 | Living Safety Document ##(Cost Summary)## (C1) (NEW) ** | 17-May-21 A | 02-Sep-24 A | 830 | 0 | 832 | 100% |  | Completed
ER6371LT | W202 | W202.A2206440 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - Prepare HF Assessment of Misloading Fault EAN | 17-May-21 A | 21-Jun-21 A | 10 | 0 | 24 | 100% |  | Completed
ER6371LT | W202 | W202.A2206435 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - HF Assessment of Misloading Fault EAN - Summary | 17-May-21 A | 30-Jul-21 A | 44 | 0 | 54 | 100% |  | Completed
ER6661LT | W206 | W206.1370 | HYA Reactors Shutdown Essential Safety Cases | 2021-05-17 | 2021-06-21 | <NEW SCOPE PENDING CC> - Prepare HF Assessment of Misloading Fault EAN | 17-May-21 A | 21-Jun-21 A | 10 | 0 | 24 | 100% |  | Completed
ER6661LT | W206 | W206.1365 | HYA Reactors Shutdown Essential Safety Cases | 2021-05-17 | 2021-07-21 | <NEW SCOPE PENDING CC> - HF Assessment of Misloading Fault EAN - Summary | 17-May-21 A | 21-Jul-21 A | 37 | 0 | 47 | 100% |  | Completed
ER6378LT | W222 | W222.A26270 | HRA Fuel Handling Essential Safety Case | 2021-05-17 | 2021-06-04 | Verify Dropped FPU Fault Definition Document (FDD) (REV 001) EAN for Technical Review | 17-May-21 A | 04-Jun-21 A | 5 | 0 | 14 | 100% |  | Completed
ER6378LT | W222 | W222.A9020 | HRA Fuel Handling Essential Safety Case | 2021-05-17 | 2021-05-28 | Technical Review of Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN | 17-May-21 A | 28-May-21 A | 5 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | W226.A26270 | HYA Fuel Handling Essential Safety Case | 2021-05-17 | 2021-06-04 | Verify Dropped FPU Fault Definition Document (FDD) (REV 001) EAN for Technical Review | 17-May-21 A | 04-Jun-21 A | 5 | 0 | 14 | 100% |  | Completed
ER6370LT | W201 | W201.1280 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 5 - Formal INSA | 17-May-21 A | 28-May-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6378LT | W222 | W222.A24300 | HRA Fuel Handling Essential Safety Case | 2021-05-18 | 2021-12-03 | Draft Living Safety Document EAN | 18-May-21 A | 03-Dec-21 A | 40 | 0 | 142 | 100% |  | Completed
ER6650LT | W226 | W226.A24300 | HYA Fuel Handling Essential Safety Case | 2021-05-18 | 2021-12-03 | Draft Living Safety Document EAN | 18-May-21 A | 03-Dec-21 A | 40 | 0 | 142 | 100% |  | Completed
ER6371LT | W202 | W202.A4730 | HRA Reactors Shutdown Essential Safety Cases | 2021-06-23 | 2021-06-29 | Confirm Objectives to be Delivered at Gate C | 18-May-21 A | 15-Jun-21 A | 20 | 0 | 20 | 100% |  | Completed
ER6371LT | W202 | W202.A4670 | HRA Reactors Shutdown Essential Safety Cases | 2021-06-23 | 2021-10-13 | Gate C Planning | 18-May-21 A | 24-Aug-21 A | 70 | 0 | 69 | 100% |  | Completed
ER6661LT | W206 | W206.A4730 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-23 | 2021-06-29 | Confirm Objectives to be Delivered at Gate C | 18-May-21 A | 15-Jun-21 A | 20 | 0 | 20 | 100% |  | Completed
ER6661LT | W206 | W206.A4670 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-23 | 2021-09-29 | Gate C Planning | 18-May-21 A | 24-Aug-21 A | 70 | 0 | 70 | 100% |  | Completed
ER6650LT | W226 | W226.A27250 | HYA Fuel Handling Essential Safety Case | 2021-05-20 | 2021-05-27 | PSA Model TR | 20-May-21 A | 27-May-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A27250 | HRA Fuel Handling Essential Safety Case | 2021-05-20 | 2021-05-27 | PSA Model TR | 20-May-21 A | 27-May-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | W201.1170 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 0 - DA respond to comments | 20-May-21 A | 28-May-21 A | 5 | 0 | 6 | 100% |  | Completed
ER6370LT | W201 | W201.1190 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 1 - DA respond to comments | 20-May-21 A | 28-May-21 A | 5 | 0 | 6 | 100% |  | Completed
ER6370LT | W201 | W201.1250 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 3 - DA respond to comments | 20-May-21 A | 26-May-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | W201.1270 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 4 - DA respond to comments | 20-May-21 A | 26-May-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A23580 | HRA Fuel Handling Essential Safety Case |  | 2021-05-21 | Fast Fracture R6 Analysis EAN Available | 21-May-21 A | 21-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A23580 | HYA Fuel Handling Essential Safety Case |  | 2021-05-21 | Fast Fracture R6 Analysis EAN Available | 21-May-21 A | 21-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | W201.1340 | HNB Reactors Shutdown Essential Safety Cases |  |  | Interactions with NP/SC 7786 - DA respond to comments | 24-May-21 A | 28-May-21 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | W201.1380 | HNB Reactors Shutdown Essential Safety Cases |  |  | Update Cat 1 | 24-May-21 A | 28-May-21 A | 5 | 0 | 4 | 100% |  | Completed
ER6371LT | W202 | W202.A2206320 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> Optioneering - Draft and issue RFS | 24-May-21 A | 28-May-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A2206310 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> Optioneering - Summary | 24-May-21 A | 11-Jun-21 A | 9 | 0 | 14 | 100% |  | Completed
ER6661LT | W206 | W206.1140 | HYA Reactors Shutdown Essential Safety Cases | 2021-05-24 | 2021-05-28 | <NEW SCOPE PENDING CC> Optioneering - Draft and issue RFS | 24-May-21 A | 28-May-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.1135 | HYA Reactors Shutdown Essential Safety Cases | 2021-05-24 | 2021-06-11 | <NEW SCOPE PENDING CC> Optioneering - Summary | 24-May-21 A | 11-Jun-21 A | 9 | 0 | 14 | 100% |  | Completed
ER6378LT | W222 | W222.A23500 | HRA Fuel Handling Essential Safety Case | 2021-05-24 | 2021-05-28 | Complete TR Form and Upload Complex FEA (Dynamic R3 Analysis) EAN to CDMS | 24-May-21 A | 28-May-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A23500 | HYA Fuel Handling Essential Safety Case | 2021-05-24 | 2021-05-28 | Complete TR Form and Upload Complex FEA (Dynamic R3 Analysis) EAN to CDMS | 24-May-21 A | 28-May-21 A | 2 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | W201.1330 | HNB Reactors Shutdown Essential Safety Cases |  |  | Interactions with NP/SC 7786 | 24-May-21 A | 28-May-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | W201.1350 | HNB Reactors Shutdown Essential Safety Cases |  |  | Consolidated Comments Issued | 24-May-21 A | 27-May-21 A | 5 | 0 | 3 | 100% |  | Completed
ER6378LT | W222 | W222.A26470 | HRA Fuel Handling Essential Safety Case |  | 2021-05-26 | Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection Available | 26-May-21 A | 26-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A25560 | HRA Fuel Handling Essential Safety Case | 2021-05-26 | 2021-05-26 | Pre Job Brief for Worker Dose Assessment (REV 000) EAN | 26-May-21 A | 26-May-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A25570 | HRA Fuel Handling Essential Safety Case | 2021-05-26 | 2021-05-26 | Draft Worker Dose Assessment (REV 000) EAN | 26-May-21 A | 26-May-21 A | 20 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A25580 | HRA Fuel Handling Essential Safety Case | 2021-05-26 | 2021-05-26 | Verify Worker Dose Assessment (REV 000) EAN and Issue for Technical Review | 26-May-21 A | 26-May-21 A | 10 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A25590 | HRA Fuel Handling Essential Safety Case | 2021-05-26 | 2021-05-26 | Technical Review of Worker Dose Assessment (REV 000) EAN | 26-May-21 A | 26-May-21 A | 3 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A25600 | HRA Fuel Handling Essential Safety Case | 2021-05-26 | 2021-05-26 | Supplier Update and Issue Worker Dose Assessment (REV 000) EAN | 26-May-21 A | 26-May-21 A | 3 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A25610 | HRA Fuel Handling Essential Safety Case | 2021-05-26 | 2021-05-26 | Complete TR Form and Upload Worker Dose Assessment (REV 000) EAN to CDMS | 26-May-21 A | 26-May-21 A | 3 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A25620 | HRA Fuel Handling Essential Safety Case |  | 2021-05-26 | Worker Dose Assessment (REV 000) EAN Available | 26-May-21 A | 26-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A25010 | HRA Fuel Handling Essential Safety Case | 2021-05-26 | 2021-05-26 | Verify Dropped Fuel Head Document EAN and Issue for Technical Review | 26-May-21 A | 26-May-21 A | 5 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A25020 | HRA Fuel Handling Essential Safety Case | 2021-05-26 | 2021-05-26 | Technical Review of Dropped Fuel Head Document EAN | 26-May-21 A | 26-May-21 A | 5 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A25030 | HRA Fuel Handling Essential Safety Case | 2021-05-26 | 2021-05-26 | Supplier Update and Issue Dropped Fuel Head Document EAN | 26-May-21 A | 26-May-21 A | 5 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A25040 | HRA Fuel Handling Essential Safety Case | 2021-05-26 | 2021-05-26 | Complete TR Form and Upload Dropped Fuel Head Document EAN to CDMS | 26-May-21 A | 26-May-21 A | 5 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A25050 | HRA Fuel Handling Essential Safety Case |  | 2021-05-26 | Damage and Dropped Fuel Head Document EAN Available | 26-May-21 A | 26-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25050 | HYA Fuel Handling Essential Safety Case |  | 2021-05-26 | Damage and Dropped Fuel Head Document EAN Available | 26-May-21 A | 26-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25040 | HYA Fuel Handling Essential Safety Case | 2021-05-26 | 2021-05-26 | Complete TR Form and Upload Dropped Fuel Head Document EAN to CDMS | 26-May-21 A | 26-May-21 A | 5 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25030 | HYA Fuel Handling Essential Safety Case | 2021-05-26 | 2021-05-26 | Supplier Update and Issue Dropped Fuel Head Document EAN | 26-May-21 A | 26-May-21 A | 5 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25020 | HYA Fuel Handling Essential Safety Case | 2021-05-26 | 2021-05-26 | Technical Review of Dropped Fuel Head Document EAN | 26-May-21 A | 26-May-21 A | 5 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25010 | HYA Fuel Handling Essential Safety Case | 2021-05-26 | 2021-05-26 | Verify Dropped Fuel Head Document EAN and Issue for Technical Review | 26-May-21 A | 26-May-21 A | 5 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25620 | HYA Fuel Handling Essential Safety Case |  | 2021-05-26 | Worker Dose Assessment (REV 000) EAN Available | 26-May-21 A | 26-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25610 | HYA Fuel Handling Essential Safety Case | 2021-05-26 | 2021-05-26 | Complete TR Form and Upload Worker Dose Assessment (REV 000) EAN to CDMS | 26-May-21 A | 26-May-21 A | 3 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25600 | HYA Fuel Handling Essential Safety Case | 2021-05-26 | 2021-05-26 | Supplier Update and Issue Worker Dose Assessment (REV 000) EAN | 26-May-21 A | 26-May-21 A | 3 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25590 | HYA Fuel Handling Essential Safety Case | 2021-05-26 | 2021-05-26 | Technical Review of Worker Dose Assessment (REV 000) EAN | 26-May-21 A | 26-May-21 A | 3 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25580 | HYA Fuel Handling Essential Safety Case | 2021-05-26 | 2021-05-26 | Verify Worker Dose Assessment (REV 000) EAN and Issue for Technical Review | 26-May-21 A | 26-May-21 A | 10 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25570 | HYA Fuel Handling Essential Safety Case | 2021-05-26 | 2021-05-26 | Draft Worker Dose Assessment (REV 000) EAN | 26-May-21 A | 26-May-21 A | 4 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25560 | HYA Fuel Handling Essential Safety Case | 2021-05-26 | 2021-05-26 | Pre Job Brief for Worker Dose Assessment (REV 000) EAN | 26-May-21 A | 26-May-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A26470 | HYA Fuel Handling Essential Safety Case |  | 2021-05-26 | Diverse Weight Sensing matters arising from Reveiw of HH1 FM Protection Available | 26-May-21 A | 26-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | W201.1230 | HNB Reactors Shutdown Essential Safety Cases |  |  | Discovery milestone - FPU vibration approach accepted | 26-May-21 A | 26-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A24810 | HRA Fuel Handling Essential Safety Case | 2021-05-27 | 2021-06-02 | Technical Review of Human Factors Assessment of FM Movements during Defuelling Operations EAN | 27-May-21 A | 02-Jun-21 A | 5 | 0 | 4 | 100% |  | Completed
ER6378LT | W222 | W222.A12680 | HRA Fuel Handling Essential Safety Case | 2021-05-27 | 2021-06-08 | Complete TR Form and Upload Development of Fuel Free Verification Methods (File Note) | 27-May-21 A | 08-Jun-21 A | 10 | 0 | 7 | 100% |  | Completed
ER6650LT | W226 | W226.A12680 | HYA Fuel Handling Essential Safety Case | 2021-05-27 | 2021-06-08 | Complete TR Form and Upload Development of Fuel Free Verification Methods (File Note) | 27-May-21 A | 08-Jun-21 A | 10 | 0 | 7 | 100% |  | Completed
ER6650LT | W226 | W226.A24810 | HYA Fuel Handling Essential Safety Case | 2021-05-27 | 2021-06-02 | Technical Review of Human Factors Assessment of FM Movements during Defuelling Operations EAN | 27-May-21 A | 02-Jun-21 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1350 | HNB Reactors Shutdown Essential Safety Cases |  |  | INA provision of full comments | 27-May-21 A | 27-May-21 A | 18 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | W201.1220 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 2 - DA respond to comments | 27-May-21 A | 01-Jun-21 A | 5 | 0 | 3 | 100% |  | Completed
ER6371LT | W202 | W202.A2206130 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-03-08 | >>>INCOMING ENABLER (W222.A22270) Structural Integrity Analysis for Dropped FPU EAN Available | 28-May-21 A | 28-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206140 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-02-15 | >>>MIRROR OF INCOMING ENABLER (W222.A22270) Structural Integrity Analysis for Dropped FPU EAN Available | 28-May-21 A | 28-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206130 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-03-02 | >>>INCOMING ENABLER (W226) Structural Integrity Analysis for Dropped FPU EAN Available | 28-May-21 A | 28-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206140 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-02-15 | >>>MIRROR OF INCOMING ENABLER (W226.A22270) Structural Integrity Analysis for Dropped FPU EAN Available | 28-May-21 A | 28-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5550 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-02-15 | INTERFACE MILESTONE - (W222.A22270) Structural Integrity Analysis for Dropped FPU EAN Available | 28-May-21 A | 28-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17610 | HNB Reactors Shutdown Essential Safety Cases |  |  | >>>MIRROR of INCOMING ENABLER (W283) - LSD verification complete | 28-May-21 A | 28-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1330 | HNB Reactors Shutdown Essential Safety Cases |  |  | INTERFACE MILESTONE - (W283) LSD verification complete | 28-May-21 A | 28-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A26820 | HRA Fuel Handling Essential Safety Case |  | 2021-05-28 | HOLD POINT 2 - Confirm Technical Works on all Claims is Sufficient | 28-May-21 A | 28-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A9030 | HRA Fuel Handling Essential Safety Case | 2021-05-28 | 2021-05-28 | Supplier Update and Issue Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN | 28-May-21 A | 28-May-21 A | 5 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A9040 | HRA Fuel Handling Essential Safety Case | 2021-05-28 | 2021-05-28 | Complete TR Form & Upload Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN to CDMS | 28-May-21 A | 28-May-21 A | 5 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A9050 | HRA Fuel Handling Essential Safety Case |  | 2021-05-28 | Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN Available | 28-May-21 A | 28-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A17770 | HRA Fuel Handling Essential Safety Case |  | 2021-05-28 | Claim 3 - P6.2 HRA/HYA Essential Defuelling SC - Lifting, Stringer & Pressure Boundary Integrity Complete | 28-May-21 A | 28-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A18750 | HRA Fuel Handling Essential Safety Case | 2021-05-28 | 2021-05-28 | Claim 3 - P6.2 HRA/HYA Essential Defuelling SC - Lifting, Stringer & Pressure Boundary Integrity | 28-May-21 A | 28-May-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A22270 | HRA Fuel Handling Essential Safety Case |  | 2021-05-28 | >>>OUTGOING ENABLER (W202.A8500?) Structural Integrity Analysis for Dropped FPU EAN Available | 28-May-21 A | 28-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A26830 | HRA Fuel Handling Essential Safety Case |  | 2021-05-28 | HRA References not impacted by core support plate/shock absorber decision complete (2020) | 28-May-21 A | 28-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A26830 | HYA Fuel Handling Essential Safety Case |  | 2021-05-28 | HYA References not impacted by core support plate/shock absorber decision complete (2020) | 28-May-21 A | 28-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A18750 | HYA Fuel Handling Essential Safety Case | 2021-05-28 | 2021-05-28 | Claim 3 - P6.2 HYA/HYA Essential Defuelling SC - Lifting, Stringer & Pressure Boundary Integrity | 28-May-21 A | 28-May-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A17770 | HYA Fuel Handling Essential Safety Case |  | 2021-05-28 | Claim 3 - P6.2 HYA/HYA Essential Defuelling SC - Lifting, Stringer & Pressure Boundary Integrity Complete | 28-May-21 A | 28-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A9040 | HYA Fuel Handling Essential Safety Case | 2021-05-28 | 2021-05-28 | Complete TR Form & Upload Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN to CDMS | 28-May-21 A | 28-May-21 A | 5 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A9030 | HYA Fuel Handling Essential Safety Case | 2021-05-28 | 2021-05-28 | Supplier Update and Issue Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN | 28-May-21 A | 28-May-21 A | 5 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27240 | HYA Fuel Handling Essential Safety Case |  | 2021-05-28 | >>>OUTGOING ENABLER (W206.A8500?) Structural Integrity Analysis for Dropped FPU EAN Available | 28-May-21 A | 28-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | W201.1290 | HNB Reactors Shutdown Essential Safety Cases |  |  | Claim 5 - DA respond to comments | 28-May-21 A | 01-Jun-21 A | 5 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | W201.1390 | HNB Reactors Shutdown Essential Safety Cases |  |  | Re- Verify | 28-May-21 A | 02-Jun-21 A | 5 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | W201.1370 | HNB Reactors Shutdown Essential Safety Cases |  |  | Responses Received | 28-May-21 A | 01-Jun-21 A | 10 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A5550 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-02-15 | INTERFACE MILESTONE - (W222.A22270) Structural Integrity Analysis for Dropped FPU EAN Available | 28-May-21 A | 28-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17600 | HNB Reactors Shutdown Essential Safety Cases |  |  | >>>INCOMING ENABLER (W283) - LSD verification complete | 28-May-21 A | 28-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A25190 | HRA Fuel Handling Essential Safety Case |  | 2021-05-28 | HOLD POINT 1 - Core Support Plate (CSP) Qualification Milestone | 28-May-21 A | 28-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A23510 | HRA Fuel Handling Essential Safety Case |  | 2021-05-28 | Complex FEA (Dynamic R3 Analysis) EAN Available | 28-May-21 A | 28-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A9050 | HYA Fuel Handling Essential Safety Case |  | 2021-05-28 | Revised Maint Regime to Provide Adequate In-service Assurance of the FH Equipment EAN Available | 28-May-21 A | 28-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A23510 | HYA Fuel Handling Essential Safety Case |  | 2021-05-28 | Complex FEA (Dynamic R3 Analysis) EAN Available | 28-May-21 A | 28-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25190 | HYA Fuel Handling Essential Safety Case |  | 2021-05-28 | HOLD POINT 1 - Core Support Plate (CSP) Qualification Milestone | 28-May-21 A | 28-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A26820 | HYA Fuel Handling Essential Safety Case |  | 2021-05-28 | HOLD POINT 2 - Confirm Technical Works on all Claims is Sufficient | 28-May-21 A | 28-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.1020 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - Issue Draft EAN to EDF for Review. | 28-May-21 A | 28-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.1020 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-09-01 | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - Issue Draft EAN to EDF for Review. | 28-May-21 A | 28-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | W201.1300 | HNB Reactors Shutdown Essential Safety Cases |  |  | Discovery milestone - Significant comments raised | 28-May-21 A | 28-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | W201.1360 | HNB Reactors Shutdown Essential Safety Cases |  |  | Discovery milestone - Update to Cat 1 required | 28-May-21 A | 28-May-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206330 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> Optioneering - Supplier prepare and issue Offer | 31-May-21 A | 07-Jun-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.1150 | HYA Reactors Shutdown Essential Safety Cases | 2021-05-31 | 2021-06-07 | <NEW SCOPE PENDING CC> Optioneering - Supplier prepare and issue Offer | 31-May-21 A | 07-Jun-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6372LT | W203 | W203.A1290 | HNB Enhanced Defuelling Safety Cases | 2020-09-29 | 2020-12-07 | Flow Diversion EAN - Summary | 01-Jun-21 A | 22-Sep-21 A | 59 | 0 | 81 | 100% |  | Completed
ER6372LT | W203 | W203.A1300 | HNB Enhanced Defuelling Safety Cases | 2020-09-29 | 2020-10-26 | Flow Diversion EAN - Prepare Draft EAN | 01-Jun-21 A | 25-Jun-21 A | 20 | 0 | 18 | 100% |  | Completed
ER6372LT | W203 | W203.A2610 | HNB Enhanced Defuelling Safety Cases | 2020-08-19 | 2020-09-02 | Flow Diversion EAN - Supplier prepare and issue Offer | 01-Jun-21 A | 01-Jun-21 A | 10 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A2620 | HNB Enhanced Defuelling Safety Cases | 2020-09-03 | 2020-09-09 | Flow Diversion EAN - Review Offer, prepare and issue CI | 01-Jun-21 A | 01-Jun-21 A | 5 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A2630 | HNB Enhanced Defuelling Safety Cases | 2020-09-10 | 2020-09-23 | Flow Diversion EAN - Supplier mobilisation time | 01-Jun-21 A | 01-Jun-21 A | 10 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A2640 | HNB Enhanced Defuelling Safety Cases | 2020-09-24 | 2020-09-24 | Flow Diversion EAN - Pre Job Brief | 01-Jun-21 A | 01-Jun-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1430 | HNB Reactors Shutdown Essential Safety Cases | 2020-09-28 | 2020-10-02 | Prepare Station Director's Brief (HNB) | 01-Jun-21 A | 07-Jun-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6372LT | W203 | W203.A1520 | HNB Enhanced Defuelling Safety Cases | 2020-10-27 | 2020-11-09 | Effect of air admission on reactor containment (Coolant conditions CO2) EAN up Rev - Address Comments from EDF Review | 01-Jun-21 A | 14-Jun-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | W202.1030 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - Draft EAN Reviewed by EDF SQEP | 01-Jun-21 A | 16-Jun-21 A | 12 | 0 | 12 | 100% |  | Completed
ER6661LT | W206 | W206.1030 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-01 | 2021-06-16 | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - Draft EAN Reviewed by EDF SQEP | 01-Jun-21 A | 16-Jun-21 A | 12 | 0 | 12 | 100% |  | Completed
ER6371LT | W202 | W202.1170 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - RFS - Reactivity Assessment of Misloading Fault - Summary | 01-Jun-21 A | 22-Jun-21 A | 15 | 0 | 15 | 100% |  | Completed
ER6371LT | W202 | W202.1180 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - RFS - Reactivity Assessment of Misloading Fault - Draft and issue RFS | 01-Jun-21 A | 11-Jun-21 A | 9 | 0 | 9 | 100% |  | Completed
ER6661LT | W206 | W206.1280 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-01 | 2021-06-22 | <NEW SCOPE PENDING CC> - RFS - Reactivity Assessment of Misloading Fault - Summary | 01-Jun-21 A | 22-Jun-21 A | 15 | 0 | 15 | 100% |  | Completed
ER6661LT | W206 | W206.1290 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-01 | 2021-06-11 | <NEW SCOPE PENDING CC> - RFS - Reactivity Assessment of Misloading Fault - Draft and issue RFS | 01-Jun-21 A | 11-Jun-21 A | 9 | 0 | 9 | 100% |  | Completed
ER6378LT | W222 | W222.A26370 | HRA Fuel Handling Essential Safety Case | 2021-06-02 | 2021-06-04 | Supplier Update and Issue The Grab Extend FPU Ledge/ Fault and Associated Protection Needs EAN | 02-Jun-21 A | 04-Jun-21 A | 3 | 0 | 3 | 100% |  | Completed
ER6650LT | W226 | W226.A26370 | HYA Fuel Handling Essential Safety Case | 2021-06-02 | 2021-06-04 | Supplier Update and Issue The Grab Extend FPU Ledge/ Fault and Associated Protection Needs EAN | 02-Jun-21 A | 04-Jun-21 A | 3 | 0 | 3 | 100% |  | Completed
ER6378LT | W222 | W222.A24040 | HRA Fuel Handling Essential Safety Case | 2021-06-03 | 2021-06-04 | Technical Review of Dropped FPU Optioneering Documents EAN | 03-Jun-21 A | 04-Jun-21 A | 7 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | W226.A24040 | HYA Fuel Handling Essential Safety Case | 2021-06-03 | 2021-06-04 | Technical Review of Dropped FPU Optioneering Documents EAN | 03-Jun-21 A | 04-Jun-21 A | 7 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | W222.A25360 | HRA Fuel Handling Essential Safety Case | 2021-06-03 | 2021-07-01 | Verify Update to Fault Schedule/PSA (REV 000) EAN and Issue for Technical Review | 03-Jun-21 A | 01-Jul-21 A | 7 | 0 | 21 | 100% |  | Completed
ER6378LT | W222 | W222.A24820 | HRA Fuel Handling Essential Safety Case | 2021-06-03 | 2021-07-07 | Supplier Update and Human Factors Assessment of FM Movements during Defuelling Operations EAN | 03-Jun-21 A | 07-Jul-21 A | 5 | 0 | 25 | 100% |  | Completed
ER6650LT | W226 | W226.A24820 | HYA Fuel Handling Essential Safety Case | 2021-06-03 | 2021-07-07 | Supplier Update and Human Factors Assessment of FM Movements during Defuelling Operations EAN | 03-Jun-21 A | 07-Jul-21 A | 5 | 0 | 25 | 100% |  | Completed
ER6650LT | W226 | W226.A25360 | HYA Fuel Handling Essential Safety Case | 2021-06-03 | 2021-07-01 | Verify Update to Fault Schedule/PSA (REV 000) EAN and Issue for Technical Review | 03-Jun-21 A | 01-Jul-21 A | 7 | 0 | 21 | 100% |  | Completed
ER6370LT | W201 | W201.1410 | HNB Reactors Shutdown Essential Safety Cases |  |  | INSA Substantially Complete | 03-Jun-21 A | 03-Jun-21 A | 4 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16180 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-11-13 | INSA Assessment substantially comp (T - 3 weeks before NSC date) EC 364023 <NSRS SC Approach & Outline> (Cat 1 MS) (HNB) | 03-Jun-21 A | 03-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18420 | HNB Reactors Shutdown Essential Safety Cases |  |  | >>>OUTGOING ENABLER (W221, HNB Security Plan) INSA Assessment substantially comp (T - 3 weeks before NSC date) | 03-Jun-21 A | 03-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A26380 | HRA Fuel Handling Essential Safety Case | 2021-06-07 | 2021-06-11 | Complete The Grab Extend FPU Ledge/ Fault and Associated Protection Needs EAN to CDMS | 07-Jun-21 A | 11-Jun-21 A | 3 | 0 | 4 | 100% |  | Completed
ER6378LT | W222 | W222.A25440 | HRA Fuel Handling Essential Safety Case | 2021-06-07 | 2021-07-02 | Verification of Defuelling NSPs/SAGs (REV 000) EAN | 07-Jun-21 A | 02-Jul-21 A | 5 | 0 | 19 | 100% |  | Completed
ER6378LT | W222 | W222.A25170 | HRA Fuel Handling Essential Safety Case | 2021-06-07 | 2021-06-11 | Complete TR Form and Upload Dropped FPU Fault Definition Document (FDD) EAN to CDMS (REV 001) | 07-Jun-21 A | 11-Jun-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A24050 | HRA Fuel Handling Essential Safety Case | 2021-06-07 | 2021-06-08 | Supplier Update and Issue Dropped FPU Optioneering Documents EAN | 07-Jun-21 A | 08-Jun-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | W226.A24050 | HYA Fuel Handling Essential Safety Case | 2021-06-07 | 2021-06-08 | Supplier Update and Issue Dropped FPU Optioneering Documents EAN | 07-Jun-21 A | 08-Jun-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | W226.A25170 | HYA Fuel Handling Essential Safety Case | 2021-06-07 | 2021-06-11 | Complete TR Form and Upload Dropped FPU Fault Definition Document (FDD) EAN to CDMS (REV 001) | 07-Jun-21 A | 11-Jun-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A25440 | HYA Fuel Handling Essential Safety Case | 2021-06-07 | 2021-07-02 | Verification of Defuelling NSPs/SAGs (REV 000) EAN | 07-Jun-21 A | 02-Jul-21 A | 5 | 0 | 19 | 100% |  | Completed
ER6650LT | W226 | W226.A26380 | HYA Fuel Handling Essential Safety Case | 2021-06-07 | 2021-06-11 | Complete The Grab Extend FPU Ledge/ Fault and Associated Protection Needs EAN to CDMS | 07-Jun-21 A | 11-Jun-21 A | 3 | 0 | 4 | 100% |  | Completed
ER6378LT | W222 | W222.A12690 | HRA Fuel Handling Essential Safety Case |  | 2021-06-08 | Development of Fuel Free Verification Methods (File Note) Available | 08-Jun-21 A | 08-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A17750 | HRA Fuel Handling Essential Safety Case |  | 2021-06-08 | Claim 1 - P6.2 HRA/HYA Essential Defuelling SC - Proposed Defuelling Strategy Complete | 08-Jun-21 A | 08-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A18730 | HRA Fuel Handling Essential Safety Case | 2021-06-08 | 2021-06-08 | Claim 1 - P6.2 HRA/HYA Essential Defuelling SC - Proposed Defuelling Strategy | 08-Jun-21 A | 08-Jun-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A18730 | HYA Fuel Handling Essential Safety Case | 2021-06-08 | 2021-06-08 | Claim 1 - P6.2 HYA/HYA Essential Defuelling SC - Proposed Defuelling Strategy | 08-Jun-21 A | 08-Jun-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A17750 | HYA Fuel Handling Essential Safety Case |  | 2021-06-08 | Claim 1 - P6.2 HYA/HYA Essential Defuelling SC - Proposed Defuelling Strategy Complete | 08-Jun-21 A | 08-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A12690 | HYA Fuel Handling Essential Safety Case |  | 2021-06-08 | Development of Fuel Free Verification Methods (File Note) Available | 08-Jun-21 A | 08-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206340 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> Optioneering - Review Offer, prepare and issue CI | 08-Jun-21 A | 09-Jun-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.1160 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-08 | 2021-06-09 | <NEW SCOPE PENDING CC> Optioneering - Review Offer, prepare and issue CI | 08-Jun-21 A | 09-Jun-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | W222.A24060 | HRA Fuel Handling Essential Safety Case | 2021-06-09 | 2021-06-11 | Complete TR Form and Upload Dropped FPU Optioneering Documents EAN to CDMS | 09-Jun-21 A | 11-Jun-21 A | 3 | 0 | 3 | 100% |  | Completed
ER6650LT | W226 | W226.A24060 | HYA Fuel Handling Essential Safety Case | 2021-06-09 | 2021-06-11 | Complete TR Form and Upload Dropped FPU Optioneering Documents EAN to CDMS | 09-Jun-21 A | 11-Jun-21 A | 3 | 0 | 3 | 100% |  | Completed
ER6371LT | W202 | W202.A2206350 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> Optioneering - Supplier mobilisation time | 10-Jun-21 A | 10-Jun-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.1170 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-10 | 2021-06-10 | <NEW SCOPE PENDING CC> Optioneering - Supplier mobilisation time | 10-Jun-21 A | 10-Jun-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16870 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-11-20 | Review NSC Presentation Paper and Brief Station Director - HNB | 10-Jun-21 A | 10-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A26390 | HRA Fuel Handling Essential Safety Case |  | 2021-06-11 | The Grab Extend FPU Ledge/ Fault and Associated Protection Needs EAN Available | 11-Jun-21 A | 11-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A18500 | HRA Fuel Handling Essential Safety Case |  | 2021-06-11 | Claim 5 - P6.2 HRA/HYA Essential Defuelling SC - Dropped Fuel and Non-Fuel Complete | 11-Jun-21 A | 11-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A18770 | HRA Fuel Handling Essential Safety Case | 2021-06-11 | 2021-06-11 | Claim 5 - P6.2 HRA/HYA Essential Defuelling SC - Dropped Fuel and Non-Fuel | 11-Jun-21 A | 11-Jun-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A18770 | HYA Fuel Handling Essential Safety Case | 2021-06-11 | 2021-06-11 | Claim 5 - P6.2 HYA/HYA Essential Defuelling SC - Dropped Fuel and Non-Fuel | 11-Jun-21 A | 11-Jun-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A18500 | HYA Fuel Handling Essential Safety Case |  | 2021-06-11 | Claim 5 - P6.2 HYA/HYA Essential Defuelling SC - Dropped Fuel and Non-Fuel Complete | 11-Jun-21 A | 11-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A26390 | HYA Fuel Handling Essential Safety Case |  | 2021-06-11 | The Grab Extend FPU Ledge/ Fault and Associated Protection Needs EAN Available | 11-Jun-21 A | 11-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A18360 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - Verify Vibration in the FPU EAN | 11-Jun-21 A | 09-Jul-21 A | 10 | 0 | 21 | 100% |  | Completed
ER6661LT | W206 | W206.A18360 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-11 | 2021-07-09 | <NEW SCOPE PENDING CC> - Verify Vibration in the FPU Report | 11-Jun-21 A | 09-Jul-21 A | 10 | 0 | 21 | 100% |  | Completed
ER6371LT | W202 | W202.A2206360 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> Optioneering - Pre Job Brief | 11-Jun-21 A | 11-Jun-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.1180 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-11 | 2021-06-11 | <NEW SCOPE PENDING CC> Optioneering - Pre Job Brief | 11-Jun-21 A | 11-Jun-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A25180 | HRA Fuel Handling Essential Safety Case |  | 2021-06-11 | Dropped FPU Fault Definition Document (FDD) EAN Available (REV 001) | 11-Jun-21 A | 11-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A24070 | HRA Fuel Handling Essential Safety Case |  | 2021-06-11 | Dropped FPU Optioneering Documents EAN Available | 11-Jun-21 A | 11-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A24070 | HYA Fuel Handling Essential Safety Case |  | 2021-06-11 | Dropped FPU Optioneering Documents EAN Available | 11-Jun-21 A | 11-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25180 | HYA Fuel Handling Essential Safety Case |  | 2021-06-11 | Dropped FPU Fault Definition Document (FDD) EAN Available (REV 001) | 11-Jun-21 A | 11-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.1140 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> Optioneering - Develop Options for Workshop | 14-Jun-21 A | 25-Jun-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | W202.1190 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - RFS - Reactivity Assessment of Misloading Fault - Supplier prepare and issue Offer | 14-Jun-21 A | 16-Jun-21 A | 3 | 0 | 3 | 100% |  | Completed
ER6371LT | W202 | W202.1135 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> Optioneering - Summary | 14-Jun-21 A | 20-Aug-21 A | 71 | 0 | 49 | 100% |  | Completed
ER6661LT | W206 | W206.1200 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-14 | 2021-06-25 | <NEW SCOPE PENDING CC> Optioneering - Develop Options for Workshop | 14-Jun-21 A | 25-Jun-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.1300 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-14 | 2021-06-16 | <NEW SCOPE PENDING CC> - RFS - Reactivity Assessment of Misloading Fault - Supplier prepare and issue Offer | 14-Jun-21 A | 16-Jun-21 A | 3 | 0 | 3 | 100% |  | Completed
ER6661LT | W206 | W206.1195 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-14 | 2021-08-20 | <NEW SCOPE PENDING CC> Optioneering - Summary | 14-Jun-21 A | 20-Aug-21 A | 50 | 0 | 49 | 100% |  | Completed
ER6372LT | W203 | W203.A1580 | HNB Enhanced Defuelling Safety Cases |  | 2020-11-09 | Effect of air admission on reactor containment (Coolant conditions CO2) EAN up Rev - Issue Final Report | 14-Jun-21 A | 14-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A1610 | HNB Enhanced Defuelling Safety Cases | 2020-11-10 | 2020-11-23 | Effect of air admission on reactor containment (Coolant conditions CO2) EAN up Rev - Completed and Uploaded to CDMS | 15-Jun-21 A | 28-Jun-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6378LT | W222 | W222.A24970 | HRA Fuel Handling Essential Safety Case | 2021-06-16 | 2021-06-16 | Complete Review of Human Factors Defuelling Issues Management (DIM) Report EAN to CDMS | 16-Jun-21 A | 16-Jun-21 A | 5 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A24970 | HYA Fuel Handling Essential Safety Case | 2021-06-16 | 2021-06-16 | Complete Review of Human Factors Defuelling Issues Management (DIM) Report EAN to CDMS | 16-Jun-21 A | 16-Jun-21 A | 5 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A24880 | HRA Fuel Handling Essential Safety Case | 2021-06-16 | 2021-06-28 | Update DRAFT Human Reliability Baseline Report | 16-Jun-21 A | 28-Jun-21 A | 5 | 0 | 8 | 100% |  | Completed
ER6650LT | W226 | W226.A27300 | HYA Fuel Handling Essential Safety Case | 2021-06-16 | 2021-06-28 | Update DRAFT Human Reliability Baseline Report | 16-Jun-21 A | 28-Jun-21 A | 5 | 0 | 9 | 100% |  | Completed
ER6378LT | W222 | W222.A24980 | HRA Fuel Handling Essential Safety Case |  | 2021-06-16 | Human Factors Defuelling Issues Management Report EAN Available | 16-Jun-21 A | 16-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A24980 | HYA Fuel Handling Essential Safety Case |  | 2021-06-16 | Human Factors Defuelling Issues Management Report EAN Available | 16-Jun-21 A | 16-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.1040 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - Address Comments from EDF Review on Draft EAN | 17-Jun-21 A | 09-Jul-21 A | 10 | 0 | 17 | 100% |  | Completed
ER6661LT | W206 | W206.1040 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-17 | 2021-07-09 | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - Address Comments from EDF Review on Draft EAN | 17-Jun-21 A | 09-Jul-21 A | 10 | 0 | 17 | 100% |  | Completed
ER6371LT | W202 | W202.1200 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - RFS - Reactivity Assessment of Misloading Fault - Review Offer, prepare and issue CI | 17-Jun-21 A | 17-Jun-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.1310 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-17 | 2021-06-17 | <NEW SCOPE PENDING CC> - RFS - Reactivity Assessment of Misloading Fault - Review Offer, prepare and issue CI | 17-Jun-21 A | 17-Jun-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.1150 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> Optioneering - Peer Review | 17-Jun-21 A | 17-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.1210 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-09-01 | <NEW SCOPE PENDING CC> Optioneering - Peer Review | 17-Jun-21 A | 17-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.1210 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - RFS - Reactivity Assessment of Misloading Fault - Supplier mobilisation time | 18-Jun-21 A | 18-Jun-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.1320 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-18 | 2021-06-18 | <NEW SCOPE PENDING CC> - RFS - Reactivity Assessment of Misloading Fault - Supplier mobilisation time | 18-Jun-21 A | 18-Jun-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A25510 | HRA Fuel Handling Essential Safety Case | 2021-06-21 | 2021-07-02 | Verify Assessment of Worker Risk (REV 000) EAN and Issue for Technical Review | 21-Jun-21 A | 02-Jul-21 A | 9 | 0 | 9 | 100% |  | Completed
ER6650LT | W226 | W226.A25510 | HYA Fuel Handling Essential Safety Case | 2021-06-21 | 2021-07-02 | Verify Assessment of Worker Risk (REV 000) EAN and Issue for Technical Review | 21-Jun-21 A | 02-Jul-21 A | 9 | 0 | 9 | 100% |  | Completed
ER6378LT | W222 | W222.A25220 | HRA Fuel Handling Essential Safety Case | 2021-06-21 | 2021-06-30 | Verify Hazard and Interlock Schedule EAN (REV 000) EAN and Issue for Technical Review | 21-Jun-21 A | 30-Jun-21 A | 5 | 0 | 8 | 100% |  | Completed
ER6378LT | W222 | W222.A24760 | HRA Fuel Handling Essential Safety Case | 2021-06-21 | 2021-06-25 | Complete Review of Human Factors Assessment of Dropped FPU Fault Sequencess EAN to CDMS | 21-Jun-21 A | 25-Jun-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A24760 | HYA Fuel Handling Essential Safety Case | 2021-06-21 | 2021-06-25 | Complete Review of Human Factors Assessment of Dropped FPU Fault Sequencess EAN to CDMS | 21-Jun-21 A | 25-Jun-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A25220 | HYA Fuel Handling Essential Safety Case | 2021-06-21 | 2021-06-30 | Verify Hazard and Interlock Schedule EAN (REV 000) EAN and Issue for Technical Review | 21-Jun-21 A | 30-Jun-21 A | 5 | 0 | 7 | 100% |  | Completed
ER6371LT | W202 | W202.1220 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - RFS - Reactivity Assessment of Misloading Fault - Pre Job Brief | 21-Jun-21 A | 22-Jun-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.1330 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-21 | 2021-06-22 | <NEW SCOPE PENDING CC> - RFS - Reactivity Assessment of Misloading Fault - Pre Job Brief | 21-Jun-21 A | 22-Jun-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A2206460 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - Verify HF Assessment of Misloading Fault EAN | 22-Jun-21 A | 09-Jul-21 A | 5 | 0 | 14 | 100% |  | Completed
ER6661LT | W206 | W206.1390 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-22 | 2021-07-09 | <NEW SCOPE PENDING CC> - Verify HF Assessment of Misloading Fault EAN | 22-Jun-21 A | 09-Jul-21 A | 5 | 0 | 14 | 100% |  | Completed
ER6372LT | W203 | W203.A2660 | HNB Enhanced Defuelling Safety Cases |  |  | DISCOVERY MILESTONE: Scope of Technical References and Delivery Dates Agreed | 23-Jun-21 A | 23-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16190 | HNB Reactors Shutdown Essential Safety Cases |  | 2020-12-04 | NSC Presentation Date (T) EC (HNB-364023) Reactor Shutdown Essential Safety Case | 24-Jun-21 A | 24-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18180 | HNB Reactors Shutdown Essential Safety Cases |  |  | DA SC Support for NSC Presentation Date (T) EC (HNB-364023) | 24-Jun-21 A | 24-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18190 | HNB Reactors Shutdown Essential Safety Cases |  |  | INA SC Support for NSC Presentation Date (T) EC (HNB-364023) | 24-Jun-21 A | 24-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A24770 | HRA Fuel Handling Essential Safety Case |  | 2021-06-25 | Human Factors Assessment of Dropped FPU Fault Sequences EAN Available | 25-Jun-21 A | 25-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A24770 | HYA Fuel Handling Essential Safety Case |  | 2021-06-25 | Human Factors Assessment of Dropped FPU Fault Sequences EAN Available | 25-Jun-21 A | 25-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.1160 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> Optioneering - Optioneering Workshop | 25-Jun-21 A | 25-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.1220 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-09-01 | <NEW SCOPE PENDING CC> Optioneering - Optioneering Workshop | 25-Jun-21 A | 25-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A24590 | HRA Fuel Handling Essential Safety Case | 2021-06-28 | 2021-07-07 | Verify Human Reliability Baseline Report EAN & Issue for Technical Review | 28-Jun-21 A | 07-Jul-21 A | 10 | 0 | 7 | 100% |  | Completed
ER6650LT | W226 | W226.A24590 | HYA Fuel Handling Essential Safety Case | 2021-06-28 | 2021-07-07 | Verify Human Reliability Baseline Report EAN & Issue for Technical Review | 28-Jun-21 A | 07-Jul-21 A | 10 | 0 | 7 | 100% |  | Completed
ER6371LT | W202 | W202.A2206370 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - Prepare Reactivity Assessment of Misloading Fault EAN | 28-Jun-21 A | 09-Jul-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | W202.A2206365 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - Reactivity Assessment of Misloading Fault EAN - Summary | 28-Jun-21 A | 22-Jul-21 A | 23 | 0 | 19 | 100% |  | Completed
ER6661LT | W206 | W206.1230 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-28 | 2021-07-09 | <NEW SCOPE PENDING CC> - Prepare Reactivity Assessment of Misloading Fault EAN | 28-Jun-21 A | 09-Jul-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.1225 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-28 | 2021-07-30 | <NEW SCOPE PENDING CC> - Reactivity Assessment of Misloading Fault EAN - Summary | 28-Jun-21 A | 30-Jul-21 A | 29 | 0 | 25 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1390 | HNB Reactors Shutdown Essential Safety Cases | 2020-12-07 | 2020-12-11 | NSC Consideration & advice to Station Director (HNB) | 28-Jun-21 A | 30-Jun-21 A | 5 | 0 | 2 | 100% |  | Completed
ER6372LT | W203 | W203.A1650 | HNB Enhanced Defuelling Safety Cases |  | 2020-11-23 | Effect of air admission on reactor containment (Coolant conditions CO2) EAN up Rev - Report Completed | 28-Jun-21 A | 28-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A4590 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-12-30 | Verified Core Cooling Head Document Draft Report Issued to EDF for Technical Review. | 30-Jun-21 A | 30-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A4600 | HRA Reactors Shutdown Essential Safety Cases | 2020-12-31 | 2021-01-14 | Core Cooling Head Document Draft Report Technically Reviewed by EDF SQEP | 30-Jun-21 A | 09-Jul-21 A | 10 | 0 | 8 | 100% |  | Completed
ER6661LT | W206 | W206.A4590 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-06-18 | Verified Core Cooling Head Document Draft Report Issued to EDF for Technical Review. | 30-Jun-21 A | 30-Jun-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4600 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-21 | 2021-07-02 | Core Cooling Head Document Draft Report Technically Reviewed by EDF SQEP | 30-Jun-21 A | 09-Jul-21 A | 10 | 0 | 8 | 100% |  | Completed
ER6378LT | W222 | W222.A25230 | HRA Fuel Handling Essential Safety Case | 2021-06-30 | 2021-07-02 | Technical Review of Hazard and Interlock Schedule (REV 000) EAN | 30-Jun-21 A | 02-Jul-21 A | 10 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | W226.A25230 | HYA Fuel Handling Essential Safety Case | 2021-06-30 | 2021-07-02 | Technical Review of Hazard and Interlock Schedule (REV 000) EAN | 30-Jun-21 A | 02-Jul-21 A | 10 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16200 | HNB Reactors Shutdown Essential Safety Cases |  | 2021-01-08 | INSA Final Approval EC 364023 <NSRS SC Approach & Outline> (Cat 1 Milestone) (HNB) (Reactor Shutdown Essential SC) | 01-Jul-21 A | 01-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18410 | HNB Reactors Shutdown Essential Safety Cases |  |  | >>>OUTGOING ENABLER (W283) CAT 1 Reactors Shutdown SC INSA Approved | 01-Jul-21 A | 01-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
W520LT | W520 | W520.A1060 | FLEETWIDE CTO Defueling Safety Case Delivery |  | 2021-07-01 | Confirm NSSB Board Availability | 01-Jul-21 A | 01-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A4700 | HRA Reactors Shutdown Essential Safety Cases | 2021-06-23 | 2021-06-24 | Produce verification plan (HRA,) | 01-Jul-21 A | 02-Aug-21 A | 2 | 0 | 22 | 100% |  | Completed
ER6371LT | W202 | W202.A4710 | HRA Reactors Shutdown Essential Safety Cases | 2021-06-23 | 2021-06-29 | Define Project Control Structures (WBS/CBS/OBS/PBS) | 01-Jul-21 A | 23-Jul-21 A | 5 | 0 | 16 | 100% |  | Completed
ER6371LT | W202 | W202.A4720 | HRA Reactors Shutdown Essential Safety Cases | 2021-06-23 | 2021-06-23 | Prepare Draft Project Definition Document (PDD) | 01-Jul-21 A | 02-Aug-21 A | 1 | 0 | 23 | 100% |  | Completed
ER6371LT | W202 | W202.A4740 | HRA Reactors Shutdown Essential Safety Cases | 2021-06-23 | 2021-06-29 | Initial high level scope of programme | 01-Jul-21 A | 07-Jul-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A4710 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-23 | 2021-06-29 | Define Project Control Structures (WBS/CBS/OBS/PBS) | 01-Jul-21 A | 23-Jul-21 A | 5 | 0 | 16 | 100% |  | Completed
ER6661LT | W206 | W206.A4720 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-23 | 2021-06-23 | Prepare Draft Project Definition Document (PDD) | 01-Jul-21 A | 02-Aug-21 A | 1 | 0 | 23 | 100% |  | Completed
ER6661LT | W206 | W206.A4740 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-23 | 2021-06-29 | Initial high level scope of programme | 01-Jul-21 A | 07-Jul-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A16330 | HRA Fuel Handling Essential Safety Case | 2021-07-01 | 2021-08-06 | Draft Defuelling Safety Case Head Documents EAN | 01-Jul-21 A | 06-Aug-21 A | 15 | 0 | 27 | 100% |  | Completed
ER6372LT | W203 | W203.A1540 | HNB Enhanced Defuelling Safety Cases | 2020-10-27 | 2020-11-09 | Flow Diversion EAN - Review/Verification | 01-Jul-21 A | 14-Jul-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | W226.A16330 | HYA Fuel Handling Essential Safety Case | 2021-07-01 | 2021-08-06 | Draft Defuelling Safety Case Head Documents EAN | 01-Jul-21 A | 06-Aug-21 A | 15 | 0 | 27 | 100% |  | Completed
ER6378LT | W222 | W222.A25240 | HRA Fuel Handling Essential Safety Case | 2021-07-02 | 2021-07-02 | Supplier Update and Issue Hazard and Interlock Schedule (REV 000) EAN | 02-Jul-21 A | 02-Jul-21 A | 5 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25240 | HYA Fuel Handling Essential Safety Case | 2021-07-02 | 2021-07-02 | Supplier Update and Issue Hazard and Interlock Schedule (REV 000) EAN | 02-Jul-21 A | 02-Jul-21 A | 5 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4700 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-23 | 2021-06-24 | Produce verification plan (HYA,) | 02-Jul-21 A | 02-Aug-21 A | 2 | 0 | 22 | 100% |  | Completed
ER6378LT | W222 | W222.A25370 | HRA Fuel Handling Essential Safety Case | 2021-07-02 | 2021-07-02 | Technical Review of Update to Fault Schedule/PSA (REV 000) EAN | 02-Jul-21 A | 02-Jul-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A25370 | HYA Fuel Handling Essential Safety Case | 2021-07-02 | 2021-07-02 | Technical Review of Update to Fault Schedule/PSA (REV 000) EAN | 02-Jul-21 A | 02-Jul-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17090 | HNB Reactors Shutdown Essential Safety Cases |  | 2021-01-08 | CAT 1 Satety Case Submitted to ONR - (Reactor Shutdown Essential SC) HNB | 02-Jul-21 A | 02-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A25450 | HRA Fuel Handling Essential Safety Case | 2021-07-05 | 2021-07-13 | Technical Review of Defuelling NSPs/SAGs (REV 000) EAN | 05-Jul-21 A | 13-Jul-21 A | 8 | 0 | 7 | 100% |  | Completed
ER6378LT | W222 | W222.A25250 | HRA Fuel Handling Essential Safety Case | 2021-07-05 | 2021-07-14 | Complete TR Form and Upload Hazard and Interlock Schedule (REV 000) EAN to CDMS (INITIAL H&I) | 05-Jul-21 A | 14-Jul-21 A | 5 | 0 | 7 | 100% |  | Completed
ER6650LT | W226 | W226.A25250 | HYA Fuel Handling Essential Safety Case | 2021-07-05 | 2021-07-14 | Complete TR Form and Upload Hazard and Interlock Schedule (REV 000) EAN to CDMS (INITIAL H&I) | 05-Jul-21 A | 14-Jul-21 A | 5 | 0 | 8 | 100% |  | Completed
ER6650LT | W226 | W226.A25450 | HYA Fuel Handling Essential Safety Case | 2021-07-05 | 2021-07-13 | Technical Review of Defuelling NSPs/SAGs (REV 000) EAN | 05-Jul-21 A | 13-Jul-21 A | 8 | 0 | 7 | 100% |  | Completed
ER6650LT | W226 | W226.A25520 | HYA Fuel Handling Essential Safety Case | 2021-07-05 | 2021-07-07 | Technical Review of Assessment of Worker Risk (REV 000) EAN | 05-Jul-21 A | 07-Jul-21 A | 5 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | W222.1050 | HRA Fuel Handling Essential Safety Case | 2021-07-05 | 2021-07-05 | Pre Job Brief Concept Definition of Elec Interlock for Prevention of F/Assembly Misloading in Defueling Reactors EAN | 05-Jul-21 A | 05-Jul-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.1060 | HRA Fuel Handling Essential Safety Case | 2021-07-05 | 2021-07-20 | Draft Concept Definition of Elec Interlock for Prevention of F/Assembly Misloading in Defueling Reactors EAN | 05-Jul-21 A | 20-Jul-21 A | 1 | 0 | 11 | 100% |  | Completed
ER6650LT | W226 | W226.1050 | HYA Fuel Handling Essential Safety Case | 2021-07-05 | 2021-07-05 | Pre Job Brief Concept Definition of Elec Interlock for Prevention of F/Assembly Misloading in Defueling Reactors EAN | 05-Jul-21 A | 05-Jul-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.1060 | HYA Fuel Handling Essential Safety Case | 2021-07-05 | 2021-07-20 | Draft Concept Definition of Elec Interlock for Prevention of F/Assembly Misloading in Defueling Reactors EAN | 05-Jul-21 A | 20-Jul-21 A | 1 | 0 | 11 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16210 | HNB Reactors Shutdown Essential Safety Cases | 2021-01-11 | 2021-07-01 | ONR Approval of Safety Case EC 364023 <NSRS SC Approach & Outline> (Cat 1 Milestone) (HNB) (FEEDS TO SUMMARY SHEDULE) | 05-Jul-21 A | 21-Mar-22 A | 60 | 0 | 181 | 100% |  | Completed
ER6378LT | W222 | W222.A25520 | HRA Fuel Handling Essential Safety Case | 2021-07-05 | 2021-07-07 | Technical Review of Assessment of Worker Risk (REV 000) EAN | 05-Jul-21 A | 07-Jul-21 A | 5 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | W222.A25380 | HRA Fuel Handling Essential Safety Case | 2021-07-05 | 2021-07-05 | Supplier Update and Issue Update to Fault Schedule/PSA (REV 000) EAN | 05-Jul-21 A | 05-Jul-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A24660 | HRA Fuel Handling Essential Safety Case | 2021-07-05 | 2021-07-07 | Verify Human Reliability Assessment of Unsubstantaited Claims & Issue for Technical Review | 05-Jul-21 A | 07-Jul-21 A | 3 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1400 | HNB Reactors Shutdown Essential Safety Cases |  |  | Progress Lessons Learned Review - INSA Final Approval EC 364023 <NSRS SC Approach & Outline> | 05-Jul-21 A | 27-Apr-22 A | 20 | 0 | 206 | 100% |  | Completed
ER6650LT | W226 | W226.A24660 | HYA Fuel Handling Essential Safety Case | 2021-07-05 | 2021-07-07 | Verify Human Reliability Assessment of Unsubstantaited Claims & Issue for Technical Review | 05-Jul-21 A | 07-Jul-21 A | 3 | 0 | 3 | 100% |  | Completed
ER6650LT | W226 | W226.A25380 | HYA Fuel Handling Essential Safety Case | 2021-07-05 | 2021-07-05 | Supplier Update and Issue Update to Fault Schedule/PSA (REV 000) EAN | 05-Jul-21 A | 05-Jul-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A25390 | HRA Fuel Handling Essential Safety Case | 2021-07-06 | 2021-07-22 | Complete TR Form and Upload Update to Fault Schedule/PSA (REV 000) EAN to CDMS | 06-Jul-21 A | 22-Jul-21 A | 3 | 0 | 12 | 100% |  | Completed
ER6650LT | W226 | W226.A25390 | HYA Fuel Handling Essential Safety Case | 2021-07-06 | 2021-07-22 | Complete TR Form and Upload Update to Fault Schedule/PSA (REV 000) EAN to CDMS | 06-Jul-21 A | 22-Jul-21 A | 3 | 0 | 12 | 100% |  | Completed
ER6378LT | W222 | W222.A24600 | HRA Fuel Handling Essential Safety Case | 2021-07-07 | 2021-07-15 | Technical Review of Human Reliability Baseline Report EAN | 07-Jul-21 A | 15-Jul-21 A | 7 | 0 | 7 | 100% |  | Completed
ER6650LT | W226 | W226.A24600 | HYA Fuel Handling Essential Safety Case | 2021-07-07 | 2021-07-15 | Technical Review of Human Reliability Baseline Report EAN | 07-Jul-21 A | 15-Jul-21 A | 7 | 0 | 7 | 100% |  | Completed
ER6378LT | W222 | W222.A25530 | HRA Fuel Handling Essential Safety Case | 2021-07-08 | 2021-07-14 | Supplier Update and Issue Assessment of Worker Risk (REV 000) EAN | 08-Jul-21 A | 14-Jul-21 A | 5 | 0 | 4 | 100% |  | Completed
ER6650LT | W226 | W226.A25530 | HYA Fuel Handling Essential Safety Case | 2021-07-08 | 2021-07-14 | Supplier Update and Issue Assessment of Worker Risk (REV 000) EAN | 08-Jul-21 A | 14-Jul-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A4750 | HRA Reactors Shutdown Essential Safety Cases | 2021-06-30 | 2021-07-13 | Plan Scope in Primavera (Level 2 C-D & Level 1 Lifecycle) | 08-Jul-21 A | 21-Jul-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | W202.A4760 | HRA Reactors Shutdown Essential Safety Cases | 2021-06-30 | 2021-06-30 | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 08-Jul-21 A | 03-Aug-21 A | 1 | 0 | 19 | 100% |  | Completed
ER6371LT | W202 | W202.A4770 | HRA Reactors Shutdown Essential Safety Cases | 2021-06-30 | 2021-07-13 | Workshop to agree scope, effort and links | 08-Jul-21 A | 23-Jul-21 A | 10 | 0 | 11 | 100% |  | Completed
ER6661LT | W206 | W206.A4750 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-30 | 2021-07-13 | Plan Scope in Primavera (Level 2 C-D & Level 1 Lifecycle) | 08-Jul-21 A | 21-Jul-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.A4760 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-30 | 2021-06-30 | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 08-Jul-21 A | 03-Aug-21 A | 1 | 0 | 19 | 100% |  | Completed
ER6661LT | W206 | W206.A4770 | HYA Reactors Shutdown Essential Safety Cases | 2021-06-30 | 2021-07-13 | Workshop to agree scope, effort and links | 08-Jul-21 A | 23-Jul-21 A | 10 | 0 | 11 | 100% |  | Completed
ER6378LT | W222 | W222.A24830 | HRA Fuel Handling Essential Safety Case | 2021-07-08 | 2021-07-28 | Complete Review of Human Factors Assessment of FM Movements during Defuelling Operations EAN to CDMS | 08-Jul-21 A | 28-Jul-21 A | 3 | 0 | 15 | 100% |  | Completed
ER6378LT | W222 | W222.A24670 | HRA Fuel Handling Essential Safety Case | 2021-07-08 | 2021-07-09 | Technical Review of Human Reliability Assessment of Unsubstantaited Claims EAN | 08-Jul-21 A | 09-Jul-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | W226.A24670 | HYA Fuel Handling Essential Safety Case | 2021-07-08 | 2021-07-09 | Technical Review of Human Reliability Assessment of Unsubstantaited Claims EAN | 08-Jul-21 A | 09-Jul-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | W226.A24830 | HYA Fuel Handling Essential Safety Case | 2021-07-08 | 2021-07-28 | Complete Review of Human Factors Assessment of FM Movements during Defuelling Operations EAN to CDMS | 08-Jul-21 A | 28-Jul-21 A | 3 | 0 | 15 | 100% |  | Completed
ER6378LT | W222 | W222.A26570 | HRA Fuel Handling Essential Safety Case | 2021-07-09 | 2021-07-22 | Verify Human Factors Integration Plan EAN and Issue for Technical Review (REV 001) | 09-Jul-21 A | 22-Jul-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | W226.A26570 | HYA Fuel Handling Essential Safety Case | 2021-07-09 | 2021-07-22 | Verify Human Factors Integration Plan EAN and Issue for Technical Review (REV 001) | 09-Jul-21 A | 22-Jul-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | W202.1050 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - Issue Final EAN | 09-Jul-21 A | 09-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.1050 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-09-01 | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - Issue Final EAN | 09-Jul-21 A | 09-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A4780 | HRA Reactors Shutdown Essential Safety Cases | 2021-01-15 | 2021-01-28 | TSA Address Comments on TR'd Core Cooling Head Document Draft Report | 12-Jul-21 A | 03-Aug-21 A | 5 | 0 | 17 | 100% |  | Completed
ER6661LT | W206 | W206.A4780 | HYA Reactors Shutdown Essential Safety Cases | 2021-07-05 | 2021-07-16 | TSA Address Comments on TR'd Core Cooling Head Document Draft Report | 12-Jul-21 A | 02-Aug-21 A | 5 | 0 | 16 | 100% |  | Completed
ER6378LT | W222 | W222.A24680 | HRA Fuel Handling Essential Safety Case | 2021-07-12 | 2021-07-12 | Supplier Update and Issue Human Reliability Assessment of Unsubstantaited Claims EAN | 12-Jul-21 A | 12-Jul-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A24680 | HYA Fuel Handling Essential Safety Case | 2021-07-12 | 2021-07-12 | Supplier Update and Issue Human Reliability Assessment of Unsubstantaited Claims EAN | 12-Jul-21 A | 12-Jul-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.1060 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - EAN Completed and Uploaded to CDMS | 12-Jul-21 A | 23-Jul-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.1060 | HYA Reactors Shutdown Essential Safety Cases | 2021-07-12 | 2021-07-23 | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - EAN Completed and Uploaded to CDMS | 12-Jul-21 A | 23-Jul-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | W202.A18390 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - Vibration in the FPU EAN Reviewed by EDF SQEP | 12-Jul-21 A | 16-Jul-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A18390 | HYA Reactors Shutdown Essential Safety Cases | 2021-07-12 | 2021-07-16 | <NEW SCOPE PENDING CC> - Vibration in the FPU EAN Reviewed by EDF SQEP | 12-Jul-21 A | 16-Jul-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A2206390 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - Verify Reactivity Assessment of Misloading Fault EAN | 12-Jul-21 A | 14-Jul-21 A | 3 | 0 | 3 | 100% |  | Completed
ER6371LT | W202 | W202.A2206490 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - HF Assessment of Misloading Fault EAN Reviewed by EDF SQEP | 12-Jul-21 A | 19-Jul-21 A | 6 | 0 | 6 | 100% |  | Completed
ER6661LT | W206 | W206.1250 | HYA Reactors Shutdown Essential Safety Cases | 2021-07-12 | 2021-07-19 | <NEW SCOPE PENDING CC> - Verify Reactivity Assessment of Misloading Fault EAN | 12-Jul-21 A | 19-Jul-21 A | 6 | 0 | 6 | 100% |  | Completed
ER6661LT | W206 | W206.1480 | HYA Reactors Shutdown Essential Safety Cases | 2021-07-12 | 2021-07-15 | <NEW SCOPE PENDING CC> - HF Assessment of Misloading Fault EAN Reviewed by EDF SQEP | 12-Jul-21 A | 15-Jul-21 A | 4 | 0 | 4 | 100% |  | Completed
ER6378LT | W222 | W222.A24690 | HRA Fuel Handling Essential Safety Case | 2021-07-13 | 2021-07-26 | Complete Human Reliability Assessment of Unsubstantaited Claims EAN to CDMS | 13-Jul-21 A | 26-Jul-21 A | 5 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | W226.A24690 | HYA Fuel Handling Essential Safety Case | 2021-07-13 | 2021-07-26 | Complete Human Reliability Assessment of Unsubstantaited Claims EAN to CDMS | 13-Jul-21 A | 26-Jul-21 A | 5 | 0 | 10 | 100% |  | Completed
ER6378LT | W222 | W222.A25260 | HRA Fuel Handling Essential Safety Case |  | 2021-07-14 | Hazard and Interlock Schedule (REV 000) EAN Available | 14-Jul-21 A | 14-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A25460 | HRA Fuel Handling Essential Safety Case | 2021-07-14 | 2021-07-23 | Supplier Update and Issue Defuelling NSPs/SAGs (REV 000) EAN | 14-Jul-21 A | 23-Jul-21 A | 3 | 0 | 8 | 100% |  | Completed
ER6650LT | W226 | W226.A25460 | HYA Fuel Handling Essential Safety Case | 2021-07-14 | 2021-07-23 | Supplier Update and Issue Defuelling NSPs/SAGs (REV 000) EAN | 14-Jul-21 A | 23-Jul-21 A | 3 | 0 | 8 | 100% |  | Completed
ER6650LT | W226 | W226.A25260 | HYA Fuel Handling Essential Safety Case |  | 2021-07-14 | Hazard and Interlock Schedule (REV 000) EAN Available | 14-Jul-21 A | 14-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A1630 | HNB Enhanced Defuelling Safety Cases | 2020-11-10 | 2020-11-23 | Flow Diversion EAN - Address Comments | 15-Jul-21 A | 10-Sep-21 A | 19 | 0 | 41 | 100% |  | Completed
ER6371LT | W202 | W202.A2206420 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - Reactivity Assessment of Misloading Fault EAN Reviewed by EDF SQEP | 15-Jul-21 A | 16-Jul-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | W226.A25540 | HYA Fuel Handling Essential Safety Case | 2021-07-16 | 2021-07-19 | Complete TR Form and Assessment of Worker Risk (REV 000) EAN to CDMS | 16-Jul-21 A | 19-Jul-21 A | 5 | 0 | 1 | 100% |  | Completed
W520LT | W520 | W520.A1070 | FLEETWIDE CTO Defueling Safety Case Delivery | 2021-07-16 | 2021-07-16 | Estimate Peer Review / Address Comments | 16-Jul-21 A | 16-Jul-21 A | 5 | 0 | 0 | 100% |  | Completed
W520LT | W520 | W520.A1080 | FLEETWIDE CTO Defueling Safety Case Delivery | 2021-07-16 | 2021-07-16 | Ensure Alignment of Schedule & Estimate (If Required) | 16-Jul-21 A | 16-Jul-21 A | 3 | 0 | 0 | 100% |  | Completed
W520LT | W520 | W520.A1090 | FLEETWIDE CTO Defueling Safety Case Delivery | 2021-07-16 | 2021-07-16 | Estimate Scope (If Required) | 16-Jul-21 A | 16-Jul-21 A | 5 | 0 | 0 | 100% |  | Completed
W520LT | W520 | W520.A1100 | FLEETWIDE CTO Defueling Safety Case Delivery | 2021-07-16 | 2021-07-16 | Plan Scope in Primavera (If Required) | 16-Jul-21 A | 16-Jul-21 A | 5 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A25540 | HRA Fuel Handling Essential Safety Case | 2021-07-16 | 2021-07-19 | Complete TR Form and Assessment of Worker Risk (REV 000) EAN to CDMS | 16-Jul-21 A | 19-Jul-21 A | 5 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A24610 | HRA Fuel Handling Essential Safety Case | 2021-07-16 | 2021-07-22 | Supplier Update and Issue Human Reliability Baseline Report EAN | 16-Jul-21 A | 22-Jul-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A24610 | HYA Fuel Handling Essential Safety Case | 2021-07-16 | 2021-07-22 | Supplier Update and Issue Human Reliability Baseline Report EAN | 16-Jul-21 A | 22-Jul-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.1490 | HYA Reactors Shutdown Essential Safety Cases | 2021-07-16 | 2021-07-19 | <NEW SCOPE PENDING CC> - Address Comments from EDF Review on HF Assessment of Misloading Fault EAN | 16-Jul-21 A | 19-Jul-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | W222.A25550 | HRA Fuel Handling Essential Safety Case |  | 2021-07-19 | Assessment of Worker Risk (REV 000) EAN Available | 19-Jul-21 A | 19-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25550 | HYA Fuel Handling Essential Safety Case |  | 2021-07-19 | Assessment of Worker Risk (REV 000) EAN Available | 19-Jul-21 A | 19-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A18400 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - Address Comments from EDF Review on Vibration in the FPU EAN | 19-Jul-21 A | 23-Jul-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A18400 | HYA Reactors Shutdown Essential Safety Cases | 2021-07-19 | 2021-07-23 | <NEW SCOPE PENDING CC> - Address Comments from EDF Review on Vibration in the FPU EAN | 19-Jul-21 A | 23-Jul-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A2206430 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - Address Comments from EDF Review on Reactivity Assessment of Misloading Fault EAN | 19-Jul-21 A | 20-Jul-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | W222.1070 | HRA Fuel Handling Essential Safety Case | 2021-07-20 | 2021-07-20 | Verification of Concept Definition of Elec Interlock for Prevention of F/Assembly Misloading in Defueling Reactors EAN | 20-Jul-21 A | 20-Jul-21 A | 6 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.1080 | HRA Fuel Handling Essential Safety Case | 2021-07-20 | 2021-07-20 | Complete/Upload Concept Def of Elec Interlock for Prevention of F/Assembly Misloading in Defueling Reactors EAN to CDMS | 20-Jul-21 A | 20-Jul-21 A | 5 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.1090 | HRA Fuel Handling Essential Safety Case |  | 2021-07-20 | Concept Definition of Elec Interlock for Prevention of F/Assembly Misloading in Defueling Reactors EAN Available | 20-Jul-21 A | 20-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.1100 | HRA Fuel Handling Essential Safety Case |  | 2021-07-20 | >>>OUTGOING ENABLER (W202) Concept Def of Elec Interlck for Prevntion of F/Assembly Misloading in Defing Rctrs EAN Avail | 20-Jul-21 A | 20-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.1070 | HYA Fuel Handling Essential Safety Case | 2021-07-20 | 2021-07-20 | Verification of Concept Definition of Elec Interlock for Prevention of F/Assembly Misloading in Defueling Reactors EAN | 20-Jul-21 A | 20-Jul-21 A | 6 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.1080 | HYA Fuel Handling Essential Safety Case | 2021-07-20 | 2021-07-20 | Complete/Upload Concept Def of Elec Interlock for Prevention of F/Assembly Misloading in Defueling Reactors EAN to CDMS | 20-Jul-21 A | 20-Jul-21 A | 5 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.1090 | HYA Fuel Handling Essential Safety Case |  | 2021-07-20 | Concept Definition of Elec Interlock for Prevention of F/Assembly Misloading in Defueling Reactors EAN Available | 20-Jul-21 A | 20-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.1100 | HYA Fuel Handling Essential Safety Case |  | 2021-07-20 | >>>OUTGOING ENABLER (W206) Concept Def of Elec Interlck for Prevntion of F/Assembly Misloading in Defing Rctrs EAN Avail | 20-Jul-21 A | 20-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.1300 | HRA Reactors Shutdown Essential Safety Cases |  |  | >>>INCOMING ENABLER (W222) Concept Def of Elec Interlck for Prevntion of F/Assembly Misloading in Defing Rctrs EAN Avail | 20-Jul-21 A | 20-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.1310 | HRA Reactors Shutdown Essential Safety Cases |  |  | >>>MIRROR of INCOMING ENABLER (W222) Concept Def of Elec Interlck for Prevntion of F/Assembly Misloading in Defing Rctrs | 20-Jul-21 A | 20-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.1320 | HRA Reactors Shutdown Essential Safety Cases |  |  | >>>INTERFACE MS (W222) Concept Def of Elec Interlck for Prevntion of F/Assembly Misloading in Defing Rctrs EAN Avail | 20-Jul-21 A | 20-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.13105 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-09-01 | >>>MIRROR of INCOMING ENABLER (W226) Concept Def of Elec Interlck for Prevntion of F/Assembly Misloading in Defing Rctrs | 20-Jul-21 A | 20-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.13115 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-09-01 | >>>INTERFACE MS (W226) Concept Def of Elec Interlck for Prevntion of F/Assembly Misloading in Defing Rctrs EAN Avail | 20-Jul-21 A | 20-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206500 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - Address Comments from EDF Review on HF Assessment of Misloading Fault EAN | 20-Jul-21 A | 26-Jul-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.1340 | HYA Reactors Shutdown Essential Safety Cases | 2021-07-20 | 2021-07-21 | <NEW SCOPE PENDING CC> - Reactivity Assessment of Misloading Fault EAN Reviewed by EDF SQEP | 20-Jul-21 A | 21-Jul-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.1400 | HYA Reactors Shutdown Essential Safety Cases | 2021-07-20 | 2021-07-21 | <NEW SCOPE PENDING CC> - HF Assessment of Misloading Fault EAN Completed and Uploaded to CDMS | 20-Jul-21 A | 21-Jul-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.13005 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-09-01 | >>>INCOMING ENABLER (W226) Concept Def of Elec Interlck for Prevntion of F/Assembly Misloading in Defing Rctrs EAN Avail | 20-Jul-21 A | 20-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206400 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - Reactivity Assessment of Misloading Fault EAN Completed and Uploaded to CDMS | 21-Jul-21 A | 22-Jul-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.1410 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-09-01 | <NEW SCOPE PENDING CC> - HF Assessment of Misloading Fault EAN Complete | 21-Jul-21 A | 21-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A18510 | HRA Fuel Handling Essential Safety Case |  | 2021-07-22 | Claim 6 - P6.2 HRA/HYA Essential Defuelling SC - NSPs and ALARP Complete | 22-Jul-21 A | 22-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A18510 | HYA Fuel Handling Essential Safety Case |  | 2021-07-22 | Claim 6 - P6.2 HYA/HYA Essential Defuelling SC - NSPs and ALARP Complete | 22-Jul-21 A | 22-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25400 | HYA Fuel Handling Essential Safety Case |  | 2021-07-22 | Update to Fault Schedule/PSA (REV 000) EAN Available | 22-Jul-21 A | 22-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.1350 | HYA Reactors Shutdown Essential Safety Cases | 2021-07-22 | 2021-07-26 | <NEW SCOPE PENDING CC> - Address Comments from EDF Review on Reactivity Assessment of Misloading Fault EAN | 22-Jul-21 A | 26-Jul-21 A | 3 | 0 | 3 | 100% |  | Completed
ER6378LT | W222 | W222.A25400 | HRA Fuel Handling Essential Safety Case |  | 2021-07-22 | Update to Fault Schedule/PSA (REV 000) EAN Available | 22-Jul-21 A | 22-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206410 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - Reactivity Assessment of Misloading Fault EAN Complete | 22-Jul-21 A | 22-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A26590 | HRA Fuel Handling Essential Safety Case | 2021-07-23 | 2021-07-29 | Complete TR Form and Upload Human Factors Integration Plan EAN to CDMS (REV 001) | 23-Jul-21 A | 29-Jul-21 A | 21 | 0 | 4 | 100% |  | Completed
ER6378LT | W222 | W222.A24620 | HRA Fuel Handling Essential Safety Case | 2021-07-23 | 2021-07-29 | Complete Review of Human Reliability Baseline Report EAN to CDMS | 23-Jul-21 A | 29-Jul-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A24620 | HYA Fuel Handling Essential Safety Case | 2021-07-23 | 2021-07-29 | Complete Review of Human Reliability Baseline Report EAN to CDMS | 23-Jul-21 A | 29-Jul-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A26590 | HYA Fuel Handling Essential Safety Case | 2021-07-23 | 2021-07-29 | Complete TR Form and Upload Human Factors Integration Plan EAN to CDMS (REV 001) | 23-Jul-21 A | 29-Jul-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.1070 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - EAN Completed | 23-Jul-21 A | 23-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.1070 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-09-01 | <NEW SCOPE PENDING CC> - OPEX/ Literature Review - EAN Completed | 23-Jul-21 A | 23-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A3810 | HRA Reactors Shutdown Essential Safety Cases | 2020-11-05 | 2020-11-05 | Shutdown Margin Head Document - Update due to initial RAWG Commmnets | 26-Jul-21 A | 20-Aug-21 A | 1 | 0 | 20 | 100% |  | Completed
ER6661LT | W206 | W206.A3810 | HYA Reactors Shutdown Essential Safety Cases | 2020-11-05 | 2020-11-06 | Shutdown Margin Head Document - Update due to initial RAWG Commmnets | 26-Jul-21 A | 20-Aug-21 A | 1 | 0 | 20 | 100% |  | Completed
ER6378LT | W222 | W222.A25470 | HRA Fuel Handling Essential Safety Case | 2021-07-26 | 2021-07-27 | Complete TR Form and Upload Defuelling NSPs/SAGs (REV 000) EAN to CDMS | 26-Jul-21 A | 27-Jul-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | W226.A25470 | HYA Fuel Handling Essential Safety Case | 2021-07-26 | 2021-07-27 | Complete TR Form and Upload Defuelling NSPs/SAGs (REV 000) EAN to CDMS | 26-Jul-21 A | 27-Jul-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A18370 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - Vibration in the FPU EAN Completed and Uploaded to CDMS | 26-Jul-21 A | 30-Jul-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A18370 | HYA Reactors Shutdown Essential Safety Cases | 2021-07-26 | 2021-07-30 | <NEW SCOPE PENDING CC> - Vibration in the FPU Report Completed and Uploaded to CDMS | 26-Jul-21 A | 30-Jul-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A24700 | HRA Fuel Handling Essential Safety Case |  | 2021-07-26 | Human Reliability Assessment of Unsubstantaited Claims EAN Available | 26-Jul-21 A | 26-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A24700 | HYA Fuel Handling Essential Safety Case |  | 2021-07-26 | Human Reliability Assessment of Unsubstantaited Claims EAN Available | 26-Jul-21 A | 26-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206470 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - HF Assessment of Misloading Fault EAN Completed and Uploaded to CDMS | 27-Jul-21 A | 30-Jul-21 A | 4 | 0 | 4 | 100% |  | Completed
ER6661LT | W206 | W206.1260 | HYA Reactors Shutdown Essential Safety Cases | 2021-07-27 | 2021-07-30 | <NEW SCOPE PENDING CC> - Reactivity Assessment of Misloading Fault EAN Completed and Uploaded to CDMS | 27-Jul-21 A | 30-Jul-21 A | 4 | 0 | 4 | 100% |  | Completed
ER6378LT | W222 | W222.A25480 | HRA Fuel Handling Essential Safety Case |  | 2021-07-27 | Defuelling NSPs/SAGs (REV 000) EAN Available | 27-Jul-21 A | 27-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A25480 | HYA Fuel Handling Essential Safety Case |  | 2021-07-27 | Defuelling NSPs/SAGs (REV 000) EAN Available | 27-Jul-21 A | 27-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A24840 | HRA Fuel Handling Essential Safety Case |  | 2021-07-28 | Human Factors Assessment of FM Movements during Defuelling Operations EAN Available | 28-Jul-21 A | 28-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A24840 | HYA Fuel Handling Essential Safety Case |  | 2021-07-28 | Human Factors Assessment of FM Movements during Defuelling Operations EAN Available | 28-Jul-21 A | 28-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A4690 | HRA Fuel Handling Essential Safety Case | 2021-07-29 | 2021-08-18 | Produce verification plan | 29-Jul-21 A | 18-Aug-21 A | 2 | 0 | 14 | 100% |  | Completed
ER6378LT | W222 | W222.A4780 | HRA Fuel Handling Essential Safety Case | 2021-07-29 | 2023-07-19 | Prepare and Populate Affected Documents List | 29-Jul-21 A | 15-Sep-23 A | 10 | 0 | 538 | 100% |  | Completed
ER6378LT | W222 | W222.A5080 | HRA Fuel Handling Essential Safety Case |  | 2021-07-29 | All key supporting references complete | 29-Jul-21 A | 29-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A17740 | HRA Fuel Handling Essential Safety Case |  | 2021-07-29 | HAR Fuel Handling Essential Safety Case - Technical References Issued | 29-Jul-21 A | 29-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A17760 | HRA Fuel Handling Essential Safety Case |  | 2021-07-29 | Claim 2 - P6.2 HRA/HYA Essential Defuelling SC - Sufficient Protection is in Place Complete | 29-Jul-21 A | 29-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A18740 | HRA Fuel Handling Essential Safety Case | 2021-07-29 | 2021-07-29 | Claim 2 - P6.2 HRA/HYA Essential Defuelling SC - Sufficient Protection is in Place | 29-Jul-21 A | 29-Jul-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A18780 | HRA Fuel Handling Essential Safety Case | 2021-07-29 | 2021-07-29 | Claim 6 - P6.2 HRA/HYA Essential Defuelling SC - NSPs and ALARP | 29-Jul-21 A | 29-Jul-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A18940 | HYA Fuel Handling Essential Safety Case | 2021-07-29 | 2021-12-10 | Prepare the Safety Case Proposal ##(Cost Summary)## | 29-Jul-21 A | 10-Dec-21 A | 60 | 0 | 96 | 100% |  | Completed
ER6650LT | W226 | W226.A18780 | HYA Fuel Handling Essential Safety Case | 2021-07-29 | 2021-07-29 | Claim 6 - P6.2 HYA/HYA Essential Defuelling SC - NSPs and ALARP | 29-Jul-21 A | 29-Jul-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A18740 | HYA Fuel Handling Essential Safety Case | 2021-07-29 | 2021-07-29 | Claim 2 - P6.2 HYA/HYA Essential Defuelling SC - Sufficient Protection is in Place | 29-Jul-21 A | 29-Jul-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A17760 | HYA Fuel Handling Essential Safety Case |  | 2021-07-29 | Claim 2 - P6.2 HYA/HYA Essential Defuelling SC - Sufficient Protection is in Place Complete | 29-Jul-21 A | 29-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A17740 | HYA Fuel Handling Essential Safety Case |  | 2021-07-29 | HYA Fuel Handling Essential Safety Case - Technical References Issued | 29-Jul-21 A | 29-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A5080 | HYA Fuel Handling Essential Safety Case |  | 2021-07-29 | All key supporting references complete | 29-Jul-21 A | 29-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A4780 | HYA Fuel Handling Essential Safety Case | 2021-07-29 | 2023-07-19 | Prepare and Populate Affected Documents List | 29-Jul-21 A | 15-Sep-23 A | 10 | 0 | 537 | 100% |  | Completed
ER6650LT | W226 | W226.A4690 | HYA Fuel Handling Essential Safety Case | 2021-07-29 | 2021-08-18 | Produce verification plan | 29-Jul-21 A | 18-Aug-21 A | 2 | 0 | 14 | 100% |  | Completed
ER6378LT | W222 | W222.A18940 | HRA Fuel Handling Essential Safety Case | 2021-07-29 | 2021-12-10 | Prepare the Safety Case Proposal ##(Cost Summary)## | 29-Jul-21 A | 10-Dec-21 A | 60 | 0 | 96 | 100% |  | Completed
ER6378LT | W222 | W222.A26600 | HRA Fuel Handling Essential Safety Case |  | 2021-07-29 | Human Factors Integration Plan EAN Available (REV 001) | 29-Jul-21 A | 29-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A24630 | HRA Fuel Handling Essential Safety Case |  | 2021-07-29 | Human Reliability Baseline Report EAN Available | 29-Jul-21 A | 29-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A24630 | HYA Fuel Handling Essential Safety Case |  | 2021-07-29 | Human Reliability Baseline Report EAN Available | 29-Jul-21 A | 29-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A26600 | HYA Fuel Handling Essential Safety Case |  | 2021-07-29 | Human Factors Integration Plan EAN Available (REV 001) | 29-Jul-21 A | 29-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A4650 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-06-22 | All supporting references Approved and Issued (HRA) | 30-Jul-21 A | 30-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A4640 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-06-22 | Supporting Technical References Completed for Hartlepool Essential Safety Case | 30-Jul-21 A | 30-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A4630 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-06-22 | HAR Shutdown Reactor Essential Safety Case - Technical References Issued | 30-Jul-21 A | 30-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4650 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-06-22 | All supporting references Approved and Issued (HYA) | 30-Jul-21 A | 30-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4640 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-06-22 | HYA Shutdown Reactor Essential Safety Case - Technical References Issued | 30-Jul-21 A | 30-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4270 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-03-29 | All Supporting Technical References Complete - Claim 2 Containment | 30-Jul-21 A | 30-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4630 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-06-22 | Essential Reactor Safety Case - Supporting Technical References Complete (HYA) | 30-Jul-21 A | 30-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A4270 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-03-29 | All Supporting Technical References Complete - Claim 2 Containment | 30-Jul-21 A | 30-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A18380 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - Vibration in the FPU EAN Complete | 30-Jul-21 A | 30-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A18380 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-09-01 | <NEW SCOPE PENDING CC> - Vibration in the FPU Report Complete | 30-Jul-21 A | 30-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206480 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> - HF Assessment of Misloading Fault EAN Complete | 30-Jul-21 A | 30-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.1270 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-09-01 | <NEW SCOPE PENDING CC> - Reactivity Assessment of Misloading Fault EAN Complete | 30-Jul-21 A | 30-Jul-21 A | 0 | 0 | 0 | 100% |  | Completed
W520LT | W520 | W520.A1000 | FLEETWIDE CTO Defueling Safety Case Delivery | 2021-10-12 | 2021-12-31 | 2021 Costs | 01-Aug-21 A | 31-Dec-21 A | 57 | 0 | 106 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17560 | HNB Reactors Shutdown Essential Safety Cases |  |  | >>>OUTGOING ENABLER (HNB Security Plan) Review SPPI File Against Issued Safety Cases (NOT REQUIRED) | 02-Aug-21 A | 02-Aug-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.1230 | HRA Reactors Shutdown Essential Safety Cases |  |  | <NEW SCOPE PENDING CC> Optioneering - Write-up Preferred Option | 02-Aug-21 A | 20-Aug-21 A | 15 | 0 | 14 | 100% |  | Completed
ER6371LT | W202 | W202.A4370 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-03-09 | Verified Containment Head Document Draft Report Issued to EDF for Technical Review. | 02-Aug-21 A | 02-Aug-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A4380 | HRA Reactors Shutdown Essential Safety Cases | 2021-03-10 | 2021-03-30 | Containment Head Document Draft Report Technically Reviewed by EDF SQEP | 02-Aug-21 A | 06-Aug-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A4790 | HYA Reactors Shutdown Essential Safety Cases | 2021-07-14 | 2021-07-15 | Ensure Alignment of Schedule & Estimate | 02-Aug-21 A | 03-Aug-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A4370 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-03-09 | Verified Containment Head Document Draft Report Issued to EDF for Technical Review. | 02-Aug-21 A | 02-Aug-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4380 | HYA Reactors Shutdown Essential Safety Cases | 2021-03-10 | 2021-03-30 | Containment Head Document Draft Report Technically Reviewed by EDF SQEP | 02-Aug-21 A | 06-Aug-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.1360 | HYA Reactors Shutdown Essential Safety Cases | 2021-08-02 | 2021-08-20 | <NEW SCOPE PENDING CC> Optioneering - Write-up Preferred Option | 02-Aug-21 A | 20-Aug-21 A | 15 | 0 | 14 | 100% |  | Completed
W520LT | W520 | W520.A1110 | FLEETWIDE CTO Defueling Safety Case Delivery | 2021-08-02 | 2021-08-02 | Plan Peer Review & SMART Check / Address Comments | 02-Aug-21 A | 02-Aug-21 A | 1 | 0 | 1 | 100% |  | Completed
W520LT | W520 | W520.A1120 | FLEETWIDE CTO Defueling Safety Case Delivery | 2021-08-02 | 2021-08-02 | Revise Project Definition Document (PDD) (If Required) | 02-Aug-21 A | 02-Aug-21 A | 1 | 0 | 1 | 100% |  | Completed
W520LT | W520 | W520.A1130 | FLEETWIDE CTO Defueling Safety Case Delivery | 2021-08-02 | 2021-08-02 | Complete Risk Log with Estimates (If Required) | 02-Aug-21 A | 02-Aug-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A4810 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-07-16 | TSA Issue Final Core Cooling Head Document Report | 02-Aug-21 A | 02-Aug-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A4790 | HRA Reactors Shutdown Essential Safety Cases | 2021-07-14 | 2021-07-15 | Ensure Alignment of Schedule & Estimate | 03-Aug-21 A | 03-Aug-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A4830 | HYA Reactors Shutdown Essential Safety Cases | 2021-07-19 | 2021-07-30 | Core Cooling Head Document Report TR Completed and uploaded to CDMS | 03-Aug-21 A | 09-Aug-21 A | 5 | 0 | 5 | 100% |  | Completed
W520LT | W520 | W520.A1140 | FLEETWIDE CTO Defueling Safety Case Delivery | 2021-08-03 | 2021-08-03 | Update Schedule/Estimate from Risk Log & Add Provisions (If Required) | 03-Aug-21 A | 03-Aug-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A4810 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-01-28 | TSA Issue Final Core Cooling Head Document Report | 03-Aug-21 A | 03-Aug-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A4800 | HRA Reactors Shutdown Essential Safety Cases | 2021-07-16 | 2021-07-16 | Hold Risk Workshop | 04-Aug-21 A | 04-Aug-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A4830 | HRA Reactors Shutdown Essential Safety Cases | 2021-01-29 | 2021-02-11 | Core Cooling Head Document Report TR Completed and uploaded to CDMS | 04-Aug-21 A | 10-Aug-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A4800 | HYA Reactors Shutdown Essential Safety Cases | 2021-07-16 | 2021-07-16 | Hold Risk Workshop | 04-Aug-21 A | 04-Aug-21 A | 1 | 0 | 1 | 100% |  | Completed
W520LT | W520 | W520.A1150 | FLEETWIDE CTO Defueling Safety Case Delivery | 2021-08-04 | 2021-08-05 | Update NSSB Paper | 04-Aug-21 A | 05-Aug-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A4820 | HRA Reactors Shutdown Essential Safety Cases | 2021-07-19 | 2021-07-20 | Complete Risk Log with Estimates | 05-Aug-21 A | 05-Aug-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A4820 | HYA Reactors Shutdown Essential Safety Cases | 2021-07-19 | 2021-07-20 | Complete Risk Log with Estimates | 05-Aug-21 A | 05-Aug-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A4840 | HRA Reactors Shutdown Essential Safety Cases | 2021-07-21 | 2021-07-22 | Update Schedule/Estimate from Risk Log & Add Provisions | 06-Aug-21 A | 06-Aug-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A4840 | HYA Reactors Shutdown Essential Safety Cases | 2021-07-21 | 2021-07-22 | Update Schedule/Estimate from Risk Log & Add Provisions | 06-Aug-21 A | 06-Aug-21 A | 1 | 0 | 1 | 100% |  | Completed
W520LT | W520 | W520.A1160 | FLEETWIDE CTO Defueling Safety Case Delivery | 2021-08-06 | 2021-09-13 | PCL Validate & Approve Baseline Package for NSSB Submission | 06-Aug-21 A | 13-Sep-21 A | 2 | 0 | 26 | 100% |  | Completed
ER6378LT | W222 | W222.A16320 | HRA Fuel Handling Essential Safety Case |  | 2021-08-06 | Defuelling Safety Case Head Documents EAN Drafted and Issued for Verification | 06-Aug-21 A | 06-Aug-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A16320 | HYA Fuel Handling Essential Safety Case |  | 2021-08-06 | Defuelling Safety Case Head Documents EAN Drafted and Issued for Verification | 06-Aug-21 A | 06-Aug-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A4850 | HRA Reactors Shutdown Essential Safety Cases | 2021-07-23 | 2021-07-26 | Add Data to IAB Paper | 09-Aug-21 A | 09-Aug-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A4420 | HRA Reactors Shutdown Essential Safety Cases | 2021-03-31 | 2021-04-15 | TSA Address Comments on TR'd Containment Head Document Draft Report | 09-Aug-21 A | 17-Aug-21 A | 7 | 0 | 7 | 100% |  | Completed
ER6661LT | W206 | W206.A4850 | HYA Reactors Shutdown Essential Safety Cases | 2021-07-23 | 2021-07-26 | Add Data to PRC Paper | 09-Aug-21 A | 09-Aug-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A4420 | HYA Reactors Shutdown Essential Safety Cases | 2021-03-31 | 2021-04-15 | TSA Address Comments on TR'd Containment Head Document Draft Report | 09-Aug-21 A | 17-Aug-21 A | 7 | 0 | 7 | 100% |  | Completed
ER6378LT | W222 | W222.A16340 | HRA Fuel Handling Essential Safety Case | 2021-08-09 | 2021-11-26 | Verification of Defuelling Safety Case Head Documents EAN | 09-Aug-21 A | 26-Nov-21 A | 38 | 0 | 79 | 100% |  | Completed
ER6650LT | W226 | W226.A16340 | HYA Fuel Handling Essential Safety Case | 2021-08-09 | 2021-11-26 | Verification of Defuelling Safety Case Head Documents EAN | 09-Aug-21 A | 26-Nov-21 A | 38 | 0 | 79 | 100% |  | Completed
ER6661LT | W206 | W206.A4880 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-07-30 | Core Cooling Head Document Report Completed | 09-Aug-21 A | 09-Aug-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A4860 | HRA Reactors Shutdown Essential Safety Cases | 2021-07-27 | 2021-07-29 | PCL Validate & Approve Baseline Package for PRC Submission | 10-Aug-21 A | 10-Aug-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A4860 | HYA Reactors Shutdown Essential Safety Cases | 2021-07-27 | 2021-07-29 | PCL Validate & Approve Baseline Package for PRC Submission | 10-Aug-21 A | 10-Aug-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A4880 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-02-11 | Core Cooling Head Document Report Completed | 10-Aug-21 A | 10-Aug-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A4900 | HRA Reactors Shutdown Essential Safety Cases | 2021-08-02 | 2021-08-05 | PRC Members Review PRC Documentation | 11-Aug-21 A | 16-Aug-21 A | 4 | 0 | 3 | 100% |  | Completed
ER6371LT | W202 | W202.A4890 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-08-02 | Gate C PRC Paper Submission | 11-Aug-21 A | 11-Aug-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4890 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-08-02 | Gate C PRC Paper Submission | 11-Aug-21 A | 11-Aug-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4900 | HYA Reactors Shutdown Essential Safety Cases | 2021-08-02 | 2021-08-05 | PRC Members Review PRC Documentation | 11-Aug-21 A | 16-Aug-21 A | 4 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | 970 | HNB Reactors Shutdown Essential Safety Cases |  |  | Review 6 impact areas with FH Case CO | 16-Aug-21 A | 16-Aug-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | 960 | HNB Reactors Shutdown Essential Safety Cases |  |  | Review Cat 1 proposal, head doc and tech refs to identify changes (if any) | 16-Aug-21 A | 16-Aug-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A4490 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-04-15 | TSA Issue Final Containment Head Document Report | 17-Aug-21 A | 17-Aug-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4490 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-04-15 | TSA Issue Final Containment Head Document Report | 17-Aug-21 A | 17-Aug-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A4500 | HRA Reactors Shutdown Essential Safety Cases | 2021-04-16 | 2021-04-29 | Containment Head Document Report TR Completed and uploaded to CDMS | 18-Aug-21 A | 24-Aug-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A4500 | HYA Reactors Shutdown Essential Safety Cases | 2021-04-16 | 2021-04-29 | Containment Head Document Report TR Completed and uploaded to CDMS | 18-Aug-21 A | 24-Aug-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A3690 | HRA Reactors Shutdown Essential Safety Cases |  | 2020-10-27 | Shutdown Margin Head Document Completed | 20-Aug-21 A | 20-Aug-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A3690 | HYA Reactors Shutdown Essential Safety Cases |  | 2020-10-27 | Shutdown Margin Head Document Completed | 20-Aug-21 A | 20-Aug-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5050 | HRA Reactors Shutdown Essential Safety Cases | 2021-10-15 | 2021-10-21 | Obtain peer review (if required) (HRA) | 23-Aug-21 A | 27-Aug-21 A | 5 | 0 | 4 | 100% |  | Completed
ER6661LT | W206 | W206.A5050 | HYA Reactors Shutdown Essential Safety Cases | 2021-10-15 | 2021-10-21 | Obtain peer review (if required) (HYA) | 23-Aug-21 A | 27-Aug-21 A | 5 | 0 | 4 | 100% |  | Completed
ER6370LT | W201 | 1040 | HNB Reactors Shutdown Essential Safety Cases |  |  | Draft updates to Cat 1 Proposal (a Dropped FPU section, b ALARP section, c Fuel Handling discussions, d Interaction | 23-Aug-21 A | 02-Sep-21 A | 8 | 0 | 8 | 100% |  | Completed
ER6370LT | W201 | 1030 | HNB Reactors Shutdown Essential Safety Cases |  |  | Complete review of FNC Report | 23-Aug-21 A | 24-Aug-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | 1020 | HNB Reactors Shutdown Essential Safety Cases |  |  | Review with INA | 23-Aug-21 A | 24-Aug-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | 1010 | HNB Reactors Shutdown Essential Safety Cases |  |  | Review with Stn RE's | 23-Aug-21 A | 24-Aug-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | 1000 | HNB Reactors Shutdown Essential Safety Cases |  |  | Review with CO | 23-Aug-21 A | 24-Aug-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | 990 | HNB Reactors Shutdown Essential Safety Cases |  |  | NSC Strategy (matter arising tbc) | 23-Aug-21 A | 09-Sep-21 A | 13 | 0 | 12 | 100% |  | Completed
ER6370LT | W201 | 980 | HNB Reactors Shutdown Essential Safety Cases |  |  | Finalise and constrain scope of changes to Reactor Case | 23-Aug-21 A | 23-Aug-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A4910 | HRA Reactors Shutdown Essential Safety Cases | 2021-08-10 | 2021-08-10 | Hold PRC Meeting | 24-Aug-21 A | 24-Aug-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A4920 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-08-10 | Gate C PRC Paper Approval | 24-Aug-21 A | 24-Aug-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1090 | HRA Reactors Shutdown Essential Safety Cases | 2021-08-27 | 2024-04-16 | Phase 2 Project Management - Gate C - D | 24-Aug-21 A | 21-Feb-25 A | 253 | 0 | 883 | 100% |  | Completed
ER6371LT | W202 | W202.A1010 | HRA Reactors Shutdown Essential Safety Cases | 2021-09-01 | 2023-03-01 | SC - Safety Case development - tech oversight Cat 1 - HRA - C-D - STN | 24-Aug-21 A | 02-Oct-24 A | 290 | 0 | 785 | 100% |  | Completed
ER6371LT | W202 | W202.A5030 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-10-13 | Gate C PRC Paper Approval - Region 1 Essential Safety Case (HRA) | 24-Aug-21 A | 24-Aug-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A1100 | HRA Reactors Shutdown Essential Safety Cases | 2021-08-27 | 2024-04-16 | Safety Case Dev Cat 1 - Station Oversight of tech work & SC - HRA - C-D - T&S NS | 24-Aug-21 A | 21-Feb-25 A | 254 | 0 | 883 | 100% |  | Completed
ER6371LT | W202 | W202.A5080 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-10-21 | Gate EC3 Completed 363682 (HRA) | 24-Aug-21 A | 24-Aug-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A4870 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-04-29 | Completion of Head Documents (Reactor Shutdown Essential SC) | 24-Aug-21 A | 24-Aug-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A1090 | HYA Reactors Shutdown Essential Safety Cases | 2021-08-27 | 2024-04-16 | Phase 2 Project Management - Gate C - D | 24-Aug-21 A | 21-Feb-25 A | 257 | 0 | 883 | 100% |  | Completed
ER6661LT | W206 | W206.A1010 | HYA Reactors Shutdown Essential Safety Cases | 2021-09-01 | 2023-03-01 | SC - Safety Case development - tech oversight Cat 1 - HYA - C-D - STN | 24-Aug-21 A | 10-Oct-24 A | 291 | 0 | 790 | 100% |  | Completed
ER6661LT | W206 | W206.A1100 | HYA Reactors Shutdown Essential Safety Cases | 2021-08-27 | 2024-04-16 | Safety Case Dev Cat 1 - Station Oversight of tech work & SC - HYA - C-D - T&S NS | 24-Aug-21 A | 21-Feb-25 A | 258 | 0 | 883 | 100% |  | Completed
ER6661LT | W206 | W206.A5080 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-10-21 | Gate EC3 Completed 363676 (HYA) | 24-Aug-21 A | 24-Aug-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4910 | HYA Reactors Shutdown Essential Safety Cases | 2021-08-10 | 2021-08-10 | Hold PRC Meeting | 24-Aug-21 A | 24-Aug-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A4530 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-04-29 | Containment Head Document Report Completed | 24-Aug-21 A | 24-Aug-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4920 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-08-10 | Gate C PRC Paper Approval | 24-Aug-21 A | 24-Aug-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4530 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-04-29 | Containment Head Document Report Completed | 24-Aug-21 A | 24-Aug-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5030 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-10-13 | Gate C PRC Paper Approval - Region 1 Essential Safety Case (HYA) | 24-Aug-21 A | 24-Aug-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5140 | HRA Reactors Shutdown Essential Safety Cases | 2021-09-01 |  | Verification Commenced (T-11) (HRA) | 25-Aug-21 A | 25-Aug-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5140 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-09-01 | Verification Commenced (T-11) (HYA) | 25-Aug-21 A | 25-Aug-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A4870 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-07-30 | Completion of Head Documents (Reactor Shutdown Essential SC) | 27-Aug-21 A | 27-Aug-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5110 | HRA Reactors Shutdown Essential Safety Cases | 2021-09-01 | 2021-09-15 | First Round of Verification - Verifier Name | 01-Sep-21 A | 15-Sep-21 A | 11 | 0 | 11 | 100% |  | Completed
ER6371LT | W202 | W202.A5130 | HRA Reactors Shutdown Essential Safety Cases | 2021-09-01 | 2021-09-21 | Specialist Assessments if Necessary (Expand as Required) (HRA) | 01-Sep-21 A | 04-Nov-21 A | 15 | 0 | 47 | 100% |  | Completed
ER6371LT | W202 | W202.A5120 | HRA Reactors Shutdown Essential Safety Cases | 2021-09-01 | 2021-12-21 | SC - Safety Case development - Cat 1 Case verification & SA - HRA - C-D | 01-Sep-21 A | 26-Nov-21 A | 63 | 0 | 63 | 100% |  | Completed
ER6371LT | W202 | W202.A5070 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-10-21 | Safety Case Proposal Authoring Complete EC 363682 <Reactor Shutdown Essential SC>(Cat 1 KDM) (HRA) | 01-Sep-21 A | 01-Sep-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5090 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-10-21 | Safety Case Proposal Authoring Complete EC 363682 <Reactor Shutdown Essential SC> (Cat 1 KDM) (HRA) | 01-Sep-21 A | 01-Sep-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5110 | HYA Reactors Shutdown Essential Safety Cases | 2021-09-01 | 2021-09-15 | First Round of Verification - Verifier Name | 01-Sep-21 A | 15-Sep-21 A | 11 | 0 | 11 | 100% |  | Completed
ER6661LT | W206 | W206.A5130 | HYA Reactors Shutdown Essential Safety Cases | 2021-09-01 | 2021-09-21 | Specialist Assessments if Necessary (Expand as Required) (HYA) | 01-Sep-21 A | 04-Nov-21 A | 15 | 0 | 47 | 100% |  | Completed
ER6661LT | W206 | W206.A5120 | HYA Reactors Shutdown Essential Safety Cases | 2021-09-01 | 2021-12-21 | SC - Safety Case development - Cat 1 Case verification & SA - HYA - C-D | 01-Sep-21 A | 26-Nov-21 A | 58 | 0 | 63 | 100% |  | Completed
ER6661LT | W206 | W206.A5070 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-09-01 | Safety Case Proposal Authoring Complete EC 363676 <Reactor Shutdown Essential SC>(Cat 1 KDM) (HYA) | 01-Sep-21 A | 01-Sep-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5090 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-10-21 | Safety Case Proposal Authoring Complete EC 363676 <Reactor Shutdown Essential SC> (Cat 1 KDM) (HYA) | 01-Sep-21 A | 01-Sep-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A14270 | HRA Fuel Handling Essential Safety Case | 2021-09-01 | 2021-09-07 | Revise Project Definition Document (PDD) | 01-Sep-21 A | 07-Sep-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A14260 | HRA Fuel Handling Essential Safety Case | 2021-09-01 | 2021-09-07 | Estimate Scope +/- 10% Lifecycle | 01-Sep-21 A | 07-Sep-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A14250 | HRA Fuel Handling Essential Safety Case | 2021-09-01 | 2021-09-01 | Plan Scope in Primavera Level 2 Lifecycle) | 01-Sep-21 A | 01-Sep-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A14250 | HYA Fuel Handling Essential Safety Case | 2021-09-01 | 2021-09-01 | Plan Scope in Primavera Level 2 Lifecycle) | 01-Sep-21 A | 01-Sep-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A14260 | HYA Fuel Handling Essential Safety Case | 2021-09-01 | 2021-09-07 | Estimate Scope +/- 10% Lifecycle | 01-Sep-21 A | 07-Sep-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A14270 | HYA Fuel Handling Essential Safety Case | 2021-09-01 | 2021-09-07 | Revise Project Definition Document (PDD) | 01-Sep-21 A | 07-Sep-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A5150 | HRA Reactors Shutdown Essential Safety Cases | 2021-09-01 | 2021-09-21 | Nuclear Safety | 01-Sep-21 A | 21-Sep-21 A | 15 | 0 | 15 | 100% |  | Completed
ER6371LT | W202 | W202.A5590 | HRA Reactors Shutdown Essential Safety Cases | 2021-09-01 | 2021-09-21 | Environment/Rad Protection | 01-Sep-21 A | 04-Nov-21 A | 15 | 0 | 47 | 100% |  | Completed
ER6371LT | W202 | W202.A5600 | HRA Reactors Shutdown Essential Safety Cases | 2021-09-01 | 2021-09-21 | Ops & PSSR | 01-Sep-21 A | 04-Nov-21 A | 15 | 0 | 47 | 100% |  | Completed
ER6371LT | W202 | W202.A5610 | HRA Reactors Shutdown Essential Safety Cases | 2021-09-01 | 2021-09-21 | Civils | 01-Sep-21 A | 21-Sep-21 A | 15 | 0 | 15 | 100% |  | Completed
ER6371LT | W202 | W202.A5620 | HRA Reactors Shutdown Essential Safety Cases | 2021-09-01 | 2021-09-21 | Emergency Arrangements | 01-Sep-21 A | 11-Oct-21 A | 15 | 0 | 29 | 100% |  | Completed
ER6371LT | W202 | W202.A5630 | HRA Reactors Shutdown Essential Safety Cases | 2021-09-01 | 2021-09-21 | Nuclear Liabilities | 01-Sep-21 A | 21-Sep-21 A | 15 | 0 | 15 | 100% |  | Completed
ER6371LT | W202 | W202.A5640 | HRA Reactors Shutdown Essential Safety Cases | 2021-09-01 | 2021-09-21 | Decommissioning | 01-Sep-21 A | 21-Sep-21 A | 15 | 0 | 15 | 100% |  | Completed
ER6371LT | W202 | W202.A5135 | HRA Reactors Shutdown Essential Safety Cases | 2021-09-01 | 2021-09-03 | Confirm Specialist Assessments Required | 01-Sep-21 A | 03-Sep-21 A | 3 | 0 | 3 | 100% |  | Completed
ER6661LT | W206 | W206.A5155 | HYA Reactors Shutdown Essential Safety Cases | 2021-09-01 | 2021-09-21 | Nuclear Safety | 01-Sep-21 A | 21-Sep-21 A | 15 | 0 | 15 | 100% |  | Completed
ER6661LT | W206 | W206.A5590 | HYA Reactors Shutdown Essential Safety Cases | 2021-09-01 | 2021-09-21 | Environment/Rad Protection | 01-Sep-21 A | 04-Nov-21 A | 15 | 0 | 47 | 100% |  | Completed
ER6661LT | W206 | W206.A5600 | HYA Reactors Shutdown Essential Safety Cases | 2021-09-01 | 2021-09-21 | Ops & PSSR | 01-Sep-21 A | 04-Nov-21 A | 15 | 0 | 47 | 100% |  | Completed
ER6661LT | W206 | W206.A5610 | HYA Reactors Shutdown Essential Safety Cases | 2021-09-01 | 2021-09-21 | Civils | 01-Sep-21 A | 21-Sep-21 A | 15 | 0 | 15 | 100% |  | Completed
ER6661LT | W206 | W206.A5620 | HYA Reactors Shutdown Essential Safety Cases | 2021-09-01 | 2021-09-21 | Emergency Arrangements | 01-Sep-21 A | 11-Oct-21 A | 15 | 0 | 29 | 100% |  | Completed
ER6661LT | W206 | W206.A5630 | HYA Reactors Shutdown Essential Safety Cases | 2021-09-01 | 2021-09-21 | Nuclear Liabilities | 01-Sep-21 A | 21-Sep-21 A | 15 | 0 | 15 | 100% |  | Completed
ER6661LT | W206 | W206.A5640 | HYA Reactors Shutdown Essential Safety Cases | 2021-09-01 | 2021-09-21 | Decommissioning | 01-Sep-21 A | 21-Sep-21 A | 15 | 0 | 15 | 100% |  | Completed
ER6661LT | W206 | W206.A5135 | HYA Reactors Shutdown Essential Safety Cases | 2021-09-01 | 2021-09-03 | Confirm Specialist Assessments Required | 01-Sep-21 A | 03-Sep-21 A | 3 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | 1050 | HNB Reactors Shutdown Essential Safety Cases |  |  | Early review updated Proposal by Tech Lead | 01-Sep-21 A | 02-Sep-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | W222.A26700 | HRA Fuel Handling Essential Safety Case | 2021-09-02 | 2021-09-08 | Verify Review of Interlock Maintenance Review EAN & Issue for Technical Review (REV 000) | 02-Sep-21 A | 08-Sep-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A26700 | HYA Fuel Handling Essential Safety Case | 2021-09-02 | 2021-09-08 | Verify Review of Interlock Maintenance Review EAN & Issue for Technical Review (REV 000) | 02-Sep-21 A | 08-Sep-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | 1080 | HNB Reactors Shutdown Essential Safety Cases |  |  | Review updated Proposal by Station RE's | 02-Sep-21 A | 03-Sep-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | 1120 | HNB Reactors Shutdown Essential Safety Cases |  |  | HPB LSD 2.14d Updates | 06-Sep-21 A | 29-Sep-21 A | 9 | 0 | 17 | 100% |  | Completed
ER6370LT | W201 | 1110 | HNB Reactors Shutdown Essential Safety Cases |  |  | Agree with NSG to update LSDs in parallel with Verification | 06-Sep-21 A | 07-Sep-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | 1090 | HNB Reactors Shutdown Essential Safety Cases |  |  | Incorporate review comments | 06-Sep-21 A | 10-Sep-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | 1070 | HNB Reactors Shutdown Essential Safety Cases |  |  | Review | 06-Sep-21 A | 06-Sep-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | 1060 | HNB Reactors Shutdown Essential Safety Cases |  |  | Review updated Proposal by Case Officer | 07-Sep-21 A | 10-Sep-21 A | 4 | 0 | 4 | 100% |  | Completed
ER6378LT | W222 | W222.A14280 | HRA Fuel Handling Essential Safety Case | 2021-09-08 | 2021-09-10 | Ensure Alignment of Schedule & Estimate | 08-Sep-21 A | 10-Sep-21 A | 3 | 0 | 3 | 100% |  | Completed
ER6650LT | W226 | W226.A14280 | HYA Fuel Handling Essential Safety Case | 2021-09-08 | 2021-09-10 | Ensure Alignment of Schedule & Estimate | 08-Sep-21 A | 10-Sep-21 A | 3 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | 1140 | HNB Reactors Shutdown Essential Safety Cases |  |  | Produce Verification Plan | 08-Sep-21 A | 10-Sep-21 A | 3 | 0 | 3 | 100% |  | Completed
ER6378LT | W222 | W222.A26730 | HRA Fuel Handling Essential Safety Case | 2021-09-09 | 2021-09-14 | Complete Review of Interlock Maintenance Review EAN to CDMS (REV 000) | 09-Sep-21 A | 14-Sep-21 A | 4 | 0 | 4 | 100% |  | Completed
ER6650LT | W226 | W226.A26730 | HYA Fuel Handling Essential Safety Case | 2021-09-09 | 2021-09-14 | Complete Review of Interlock Maintenance Review EAN to CDMS (REV 000) | 09-Sep-21 A | 14-Sep-21 A | 4 | 0 | 4 | 100% |  | Completed
ER6378LT | W222 | W222.A14290 | HRA Fuel Handling Essential Safety Case | 2021-09-13 | 2021-09-13 | Hold Risk Workshop | 13-Sep-21 A | 13-Sep-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1680 | HNB Enhanced Defuelling Safety Cases | 2020-11-24 | 2020-12-07 | Flow Diversion EAN - Complete and Upload to CDMS | 13-Sep-21 A | 22-Sep-21 A | 8 | 0 | 8 | 100% |  | Completed
ER6650LT | W226 | W226.A14290 | HYA Fuel Handling Essential Safety Case | 2021-09-13 | 2021-09-13 | Hold Risk Workshop | 13-Sep-21 A | 13-Sep-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | 1180 | HNB Reactors Shutdown Essential Safety Cases |  |  | Nuclear Safety Specialist Assessment(s) | 13-Sep-21 A | 21-Sep-21 A | 5 | 0 | 6 | 100% |  | Completed
ER6370LT | W201 | 1170 | HNB Reactors Shutdown Essential Safety Cases |  |  | Sub-verifier(s) | 13-Sep-21 A | 20-Sep-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | 1160 | HNB Reactors Shutdown Essential Safety Cases |  |  | Verification (Lead Verifier) | 13-Sep-21 A | 23-Sep-21 A | 4 | 0 | 8 | 100% |  | Completed
ER6370LT | W201 | 1150 | HNB Reactors Shutdown Essential Safety Cases |  |  | Verification PJB | 13-Sep-21 A | 13-Sep-21 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A14300 | HRA Fuel Handling Essential Safety Case | 2021-09-14 | 2021-09-15 | Complete Risk Log with Estimates | 14-Sep-21 A | 15-Sep-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | W226.A14300 | HYA Fuel Handling Essential Safety Case | 2021-09-14 | 2021-09-15 | Complete Risk Log with Estimates | 14-Sep-21 A | 15-Sep-21 A | 2 | 0 | 2 | 100% |  | Completed
W520LT | W520 | W520.A1170 | FLEETWIDE CTO Defueling Safety Case Delivery | 2021-09-14 | 2021-09-20 | Obtain 'Pre-NSSB Signatures' | 14-Sep-21 A | 20-Sep-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A26740 | HRA Fuel Handling Essential Safety Case |  | 2021-09-14 | Review of Interlock Maintenance Review EAN Available (REV 000) | 14-Sep-21 A | 14-Sep-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A26740 | HYA Fuel Handling Essential Safety Case |  | 2021-09-14 | Review of Interlock Maintenance Review EAN Available (REV 000) | 14-Sep-21 A | 14-Sep-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | 1100 | HNB Reactors Shutdown Essential Safety Cases |  |  | AMS Milestone - Ready for Review | 14-Sep-21 A | 14-Sep-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | 1190 | HNB Reactors Shutdown Essential Safety Cases |  |  | Respond to Verification Comments and Updates | 15-Sep-21 A | 21-Sep-21 A | 4 | 0 | 4 | 100% |  | Completed
ER6661LT | W206 | W206.A5150 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-09-15 | First round verification comments received (HYA) | 15-Sep-21 A | 15-Sep-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5170 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-09-15 | First round verification comments received (HRA) | 15-Sep-21 A | 15-Sep-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5180 | HYA Reactors Shutdown Essential Safety Cases | 2021-09-16 | 2021-09-28 | Case Author address first round verification comments | 16-Sep-21 A | 29-Sep-21 A | 9 | 0 | 9 | 100% |  | Completed
ER6378LT | W222 | W222.A14310 | HRA Fuel Handling Essential Safety Case | 2021-09-16 | 2021-09-17 | Update Schedule/Estimate from Risk Log & Add Provisions | 16-Sep-21 A | 17-Sep-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | W226.A14310 | HYA Fuel Handling Essential Safety Case | 2021-09-16 | 2021-09-17 | Update Schedule/Estimate from Risk Log & Add Provisions | 16-Sep-21 A | 17-Sep-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A5200 | HRA Reactors Shutdown Essential Safety Cases | 2021-09-16 | 2021-09-28 | Case Author address first round verification comments | 16-Sep-21 A | 29-Sep-21 A | 9 | 0 | 9 | 100% |  | Completed
ER6370LT | W201 | 1210 | HNB Reactors Shutdown Essential Safety Cases |  |  | Stn RE Endorsed | 20-Sep-21 A | 23-Sep-21 A | 3 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | 1200 | HNB Reactors Shutdown Essential Safety Cases |  |  | CO Endorsed | 20-Sep-21 A | 23-Sep-21 A | 3 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | 930 | HNB Reactors Shutdown Essential Safety Cases |  |  | Draft HPB Formal ONR Letter/Review | 20-Sep-21 A | 22-Sep-21 A | 8 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | W222.A14320 | HRA Fuel Handling Essential Safety Case | 2021-09-20 | 2021-09-21 | Add Data to PRC Paper | 20-Sep-21 A | 21-Sep-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | W226.A14320 | HYA Fuel Handling Essential Safety Case | 2021-09-20 | 2021-09-21 | Add Data to IRM Paper | 20-Sep-21 A | 21-Sep-21 A | 2 | 0 | 2 | 100% |  | Completed
W520LT | W520 | W520.A1180 | FLEETWIDE CTO Defueling Safety Case Delivery |  | 2021-09-20 | Issue Paper to NSSB Secretary | 20-Sep-21 A | 20-Sep-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5160 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-09-15 | Discovery Milestone - Confirm Verification Period | 21-Sep-21 A | 21-Sep-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5160 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-09-15 | Discovery Milestone - Confirm Verification Period | 21-Sep-21 A | 21-Sep-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5240 | HYA Reactors Shutdown Essential Safety Cases | 2021-09-16 |  | Programme Review | 21-Sep-21 A | 21-Sep-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5240 | HRA Reactors Shutdown Essential Safety Cases | 2021-09-21 |  | Programme Review | 21-Sep-21 A | 21-Sep-21 A | 0 | 0 | 0 | 100% |  | Completed
W520LT | W520 | W520.A1190 | FLEETWIDE CTO Defueling Safety Case Delivery | 2021-09-21 | 2021-09-27 | NSSB Members Review Documentation | 21-Sep-21 A | 27-Sep-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6372LT | W203 | W203.A2430 | HNB Enhanced Defuelling Safety Cases |  | 2020-12-14 | All key supporting technical references complete <SUSPENDED 22.09.2021> | 22-Sep-21 A | 22-Sep-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A14230 | HRA Fuel Handling Essential Safety Case | 2021-09-22 | 2021-11-10 | PCL Validate & Approve Baseline Package for PRC Submission | 22-Sep-21 A | 10-Nov-21 A | 3 | 0 | 36 | 100% |  | Completed
ER6650LT | W226 | W226.A14230 | HYA Fuel Handling Essential Safety Case | 2021-09-22 | 2021-11-10 | PCL Validate & Approve Baseline Package for PRC Submission | 22-Sep-21 A | 10-Nov-21 A | 3 | 0 | 36 | 100% |  | Completed
ER6370LT | W201 | 1230 | HNB Reactors Shutdown Essential Safety Cases |  |  | Other INA assessor(s) | 23-Sep-21 A | 11-Oct-21 A | 5 | 0 | 12 | 100% |  | Completed
ER6370LT | W201 | 1220 | HNB Reactors Shutdown Essential Safety Cases |  |  | Lead INA assessor | 23-Sep-21 A | 11-Oct-21 A | 5 | 0 | 12 | 100% |  | Completed
W520LT | W520 | W520.A1200 | FLEETWIDE CTO Defueling Safety Case Delivery | 2021-09-28 | 2021-09-28 | Present Paper to NSSB | 28-Sep-21 A | 28-Sep-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A5560 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-09-28 | First round comments addressed and revised draft re-circulated | 29-Sep-21 A | 29-Sep-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5565 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-09-28 | First round comments addressed and revised draft re-circulated | 29-Sep-21 A | 29-Sep-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | 1130 | HNB Reactors Shutdown Essential Safety Cases |  |  | Re-attach to HPB ADL | 29-Sep-21 A | 29-Sep-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206210 | HRA Reactors Shutdown Essential Safety Cases | 2021-09-29 | 2021-10-12 | Second Round of Verification - Verifier Name | 29-Sep-21 A | 15-Oct-21 A | 13 | 0 | 13 | 100% |  | Completed
ER6661LT | W206 | W206.A2206210 | HYA Reactors Shutdown Essential Safety Cases | 2021-09-29 | 2021-10-12 | Second Round of Verification - Verifier Name | 29-Sep-21 A | 15-Oct-21 A | 13 | 0 | 13 | 100% |  | Completed
W520LT | W520 | W520.A1210 | FLEETWIDE CTO Defueling Safety Case Delivery | 2021-09-29 | 2021-10-05 | Address NSSB Comments | 29-Sep-21 A | 05-Oct-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.1020 | HYB Essential Defueling Safety Case | 2021-10-01 | 2025-01-28 | Summary for HYB Reactors Shutdown Essential Safety Cases W209 | 01-Oct-21 A | 2025-08-06 | 1082 | 109 | 971 | 0% | 14 | In Progress
ER6666LT | W209 | W209.1030 | HYB Essential Defueling Safety Case | 2021-10-01 |  | Project Start | 01-Oct-21 A | 01-Oct-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.3000 | HYB Essential Defueling Safety Case | 2021-10-01 | 2021-11-05 | Problem Statement - Summary | 01-Oct-21 A | 05-Nov-21 A | 26 | 0 | 26 | 100% |  | Completed
ER6666LT | W209 | W209.3010 | HYB Essential Defueling Safety Case | 2021-10-01 | 2021-10-08 | Problem Statement - Prepare Problem Statement | 01-Oct-21 A | 08-Oct-21 A | 25 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.1855 | HYB Essential Defueling Safety Case | 2021-10-01 | 2022-02-23 | Technical Development / Project Management - Pre Gate A - (Cost Summary) ## | 01-Oct-21 A | 23-Feb-22 A | 106 | 0 | 100 | 100% |  | Completed
ER6668LT | W213 | W213.1020 | TOR Essential Defueling Safety Case | 2021-10-01 | 2025-01-28 | Summary for TOR Reactors Shutdown Essential Safety Cases W209 | 01-Oct-21 A | 2025-08-06 | 1082 | 109 | 971 | 0% | 14 | In Progress
ER6668LT | W213 | W213.1030 | TOR Essential Defueling Safety Case | 2021-10-01 |  | Project Start | 01-Oct-21 A | 01-Oct-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.3000 | TOR Essential Defueling Safety Case | 2021-10-01 | 2021-11-05 | Problem Statement - Summary | 01-Oct-21 A | 05-Nov-21 A | 26 | 0 | 26 | 100% |  | Completed
ER6668LT | W213 | W213.3010 | TOR Essential Defueling Safety Case | 2021-10-01 | 2021-10-08 | Problem Statement - Prepare Problem Statement | 01-Oct-21 A | 08-Oct-21 A | 25 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.1855 | TOR Essential Defueling Safety Case | 2021-10-01 | 2022-02-23 | Technical Development / Project Management - Pre Gate A - (Cost Summary) ## | 01-Oct-21 A | 23-Feb-22 A | 106 | 0 | 100 | 100% |  | Completed
W520LT | W520 | W520.A1220 | FLEETWIDE CTO Defueling Safety Case Delivery | 2021-10-06 | 2021-10-07 | Obtain 'Post-NSSB Meeting Signatures' | 06-Oct-21 A | 07-Oct-21 A | 2 | 0 | 2 | 100% |  | Completed
W520LT | W520 | W520.A1230 | FLEETWIDE CTO Defueling Safety Case Delivery | 2021-10-08 | 2021-10-11 | Request Direction Sanction Approval | 08-Oct-21 A | 11-Oct-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6370LT | W201 | 1240 | HNB Reactors Shutdown Essential Safety Cases |  |  | Final INSA Approval | 11-Oct-21 A | 11-Oct-21 A | 0 | 0 | 0 | 100% |  | Completed
W520LT | W520 | W520.A1050 | FLEETWIDE CTO Defueling Safety Case Delivery |  | 2021-10-11 | NSSB Sanction Approval | 11-Oct-21 A | 11-Oct-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | 920 | HNB Reactors Shutdown Essential Safety Cases |  |  | Draft HNB Formal ONR Letter/Review | 12-Oct-21 A | 29-Oct-21 A | 8 | 0 | 13 | 100% |  | Completed
W520LT | W520 | W520.A1240 | FLEETWIDE CTO Defueling Safety Case Delivery | 2021-10-12 | 2021-10-25 | Finance Shuffle Budgets | 12-Oct-21 A | 25-Oct-21 A | 10 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | W202.A2206220 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-10-12 | Second round verification comments received (HRA) | 15-Oct-21 A | 15-Oct-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206225 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-10-12 | Second round verification comments received (HYA) | 15-Oct-21 A | 15-Oct-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206230 | HRA Reactors Shutdown Essential Safety Cases | 2021-10-13 | 2021-10-26 | Case Author address Second round verification comments | 18-Oct-21 A | 05-Nov-21 A | 15 | 0 | 15 | 100% |  | Completed
ER6661LT | W206 | W206.A2206235 | HYA Reactors Shutdown Essential Safety Cases | 2021-10-13 | 2021-10-26 | Case Author address Second round verification comments | 18-Oct-21 A | 05-Nov-21 A | 15 | 0 | 15 | 100% |  | Completed
ER6666LT | W209 | W209.3020 | HYB Essential Defueling Safety Case |  | 2021-10-29 | Problem Statement - Issue Problem Statement for Comment. | 29-Oct-21 A | 29-Oct-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.3020 | TOR Essential Defueling Safety Case |  | 2021-10-29 | Problem Statement - Issue Problem Statement for Comment. | 29-Oct-21 A | 29-Oct-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5060 | HRA Reactors Shutdown Essential Safety Cases | 2021-10-15 | 2021-10-28 | Prepare and Populate Affected Documents List (HRA) | 01-Nov-21 A | 13-Dec-21 A | 10 | 0 | 30 | 100% |  | Completed
ER6661LT | W206 | W206.A5060 | HYA Reactors Shutdown Essential Safety Cases | 2021-10-15 | 2021-10-28 | Prepare and Populate Affected Documents List (HYA) | 01-Nov-21 A | 13-Dec-21 A | 10 | 0 | 30 | 100% |  | Completed
ER6666LT | W209 | W209.3030 | HYB Essential Defueling Safety Case | 2021-11-01 | 2021-11-05 | Problem Statement - Agree Problem Statement | 01-Nov-21 A | 05-Nov-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | 940 | HNB Reactors Shutdown Essential Safety Cases |  |  | Station Directors sign letters | 01-Nov-21 A | 03-Nov-21 A | 4 | 0 | 2 | 100% |  | Completed
ER6668LT | W213 | W213.3030 | TOR Essential Defueling Safety Case | 2021-11-01 | 2021-11-05 | Problem Statement - Agree Problem Statement | 01-Nov-21 A | 05-Nov-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6370LT | W201 | W201.1550 | HNB Reactors Shutdown Essential Safety Cases |  |  | Event Recovery Milestone - Safety Case Submitted to the ONR | 03-Nov-21 A | 03-Nov-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | 950 | HNB Reactors Shutdown Essential Safety Cases |  |  | Safety Case Submitted to the ONR | 03-Nov-21 A | 03-Nov-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | W201.1560 | HNB Reactors Shutdown Essential Safety Cases |  |  | Event Recovery - ONR Assessment Period | 05-Nov-21 A | 21-Mar-22 A | 43 | 0 | 93 | 100% |  | Completed
ER6666LT | W209 | W209.3050 | HYB Essential Defueling Safety Case |  | 2021-11-05 | Problem Statement - Issue Problem Statement to Stakeholders | 05-Nov-21 A | 05-Nov-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206250 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-10-26 | Second round comments addressed and revised draft re-circulated | 05-Nov-21 A | 05-Nov-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206255 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-10-26 | Second round comments addressed and revised draft re-circulated | 05-Nov-21 A | 05-Nov-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.3050 | TOR Essential Defueling Safety Case |  | 2021-11-05 | Problem Statement - Issue Problem Statement to Stakeholders | 05-Nov-21 A | 05-Nov-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206260 | HRA Reactors Shutdown Essential Safety Cases | 2021-10-27 | 2021-11-09 | Third Round of Verification - Verifier Name | 08-Nov-21 A | 08-Nov-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2206260 | HYA Reactors Shutdown Essential Safety Cases | 2021-10-27 | 2021-11-09 | Third Round of Verification - Verifier Name | 08-Nov-21 A | 08-Nov-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A2206270 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-11-09 | Third round verification comments received (HRA) | 08-Nov-21 A | 08-Nov-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206270 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-11-09 | Third round verification comments received (HYA) | 08-Nov-21 A | 08-Nov-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206280 | HRA Reactors Shutdown Essential Safety Cases | 2021-11-10 | 2021-11-23 | Case Author address Third round verification comments | 09-Nov-21 A | 09-Nov-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2206280 | HYA Reactors Shutdown Essential Safety Cases | 2021-11-10 | 2021-11-23 | Case Author address Third round verification comments | 09-Nov-21 A | 09-Nov-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A2206300 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-11-23 | Third round comments addressed and revised draft re-circulated | 09-Nov-21 A | 09-Nov-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206300 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-11-23 | Third round comments addressed and revised draft re-circulated | 09-Nov-21 A | 09-Nov-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A14240 | HRA Fuel Handling Essential Safety Case |  | 2021-11-10 | Issue PRC Paper to R4 PRC Members | 10-Nov-21 A | 10-Nov-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A14240 | HYA Fuel Handling Essential Safety Case |  | 2021-11-10 | Issue IRM Paper to R4 PRC Members | 10-Nov-21 A | 10-Nov-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A14330 | HRA Fuel Handling Essential Safety Case | 2021-11-11 | 2021-11-17 | PRC Members Review PRC Documentation | 11-Nov-21 A | 17-Nov-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A14330 | HYA Fuel Handling Essential Safety Case | 2021-11-11 | 2021-11-17 | PRC Members Review IRM Documentation | 11-Nov-21 A | 17-Nov-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A5180 | HRA Reactors Shutdown Essential Safety Cases | 2021-11-24 | 2021-12-07 | SQEP sign off of verification (HRA) | 15-Nov-21 A | 19-Nov-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A2206230 | HYA Reactors Shutdown Essential Safety Cases | 2021-11-24 | 2021-12-07 | SQEP sign off of verification (HYA) | 15-Nov-21 A | 19-Nov-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A5190 | HRA Reactors Shutdown Essential Safety Cases | 2021-12-08 | 2021-12-21 | CO Sign-off (HRA) | 22-Nov-21 A | 26-Nov-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A5190 | HYA Reactors Shutdown Essential Safety Cases | 2021-12-08 | 2021-12-21 | CO Sign-off (HYA) | 22-Nov-21 A | 26-Nov-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A13300 | HRA Fuel Handling Essential Safety Case |  | 2021-11-23 | Gate C for Region 1 - HRA Defuelling Fuel Handling Essential Safety Case | 23-Nov-21 A | 23-Nov-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A13300 | HYA Fuel Handling Essential Safety Case |  | 2021-11-23 | Gate C for Region 1 - HYA Defuelling Fuel Handling Essential Safety Case | 23-Nov-21 A | 23-Nov-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A14340 | HRA Fuel Handling Essential Safety Case | 2021-11-23 | 2021-11-23 | Hold R4 PRC Meeting | 23-Nov-21 A | 23-Nov-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A14340 | HYA Fuel Handling Essential Safety Case | 2021-11-23 | 2021-11-23 | Hold R4 PRC Meeting | 23-Nov-21 A | 23-Nov-21 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A14350 | HRA Fuel Handling Essential Safety Case | 2021-11-24 | 2021-11-25 | Modify Estimate, Schedule & Risk Log as Required | 24-Nov-21 A | 25-Nov-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | W226.A14350 | HYA Fuel Handling Essential Safety Case | 2021-11-24 | 2021-11-25 | Modify Estimate, Schedule & Risk Log as Required | 24-Nov-21 A | 25-Nov-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | W222.A14380 | HRA Fuel Handling Essential Safety Case | 2021-11-26 | 2021-12-23 | Update Cost Management Tool | 26-Nov-21 A | 23-Dec-21 A | 5 | 0 | 19 | 100% |  | Completed
ER6650LT | W226 | W226.A14380 | HYA Fuel Handling Essential Safety Case | 2021-11-26 | 2021-12-23 | Update Cost Management Tool | 26-Nov-21 A | 23-Dec-21 A | 5 | 0 | 19 | 100% |  | Completed
ER6371LT | W202 | W202.A5210 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-11-26 | Verified Draft Available for INSA (T-7) EC 363682 <Reactor Shutdown Essential SC> (Cat 1 KDM) (HRA) | 26-Nov-21 A | 26-Nov-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5220 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-12-21 | Verification complete (HRA) | 26-Nov-21 A | 26-Nov-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5230 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-12-21 | Verified Draft Available for INSA (T-7) EC 363682 <Reactor Shutdown Essential SC> (Cat 1 KDM) (HRA) | 26-Nov-21 A | 26-Nov-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5210 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-11-26 | Verified Draft Available for INSA (T-7) EC 363676 <Reactor Shutdown Essential SC> (Cat 1 KDM) (HYA) | 26-Nov-21 A | 26-Nov-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5220 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-12-21 | Verification complete (HYA) | 26-Nov-21 A | 26-Nov-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5230 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-12-21 | Verified Draft Available for INSA (T-7) EC 363676 <Reactor Shutdown Essential SC> (Cat 1 KDM) (HYA) | 26-Nov-21 A | 26-Nov-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A16370 | HRA Fuel Handling Essential Safety Case | 2021-11-29 | 2021-12-24 | Complete TR Form and Upload Defuelling Safety Case Head Documents EAN to CDMS | 29-Nov-21 A | 24-Dec-21 A | 5 | 0 | 20 | 100% |  | Completed
ER6650LT | W226 | W226.A16370 | HYA Fuel Handling Essential Safety Case | 2021-11-29 | 2021-12-24 | Complete TR Form and Upload Defuelling Safety Case Head Documents EAN to CDMS | 29-Nov-21 A | 24-Dec-21 A | 5 | 0 | 19 | 100% |  | Completed
ER6666LT | W209 | W209.1000 | HYB Essential Defueling Safety Case | 2021-12-01 | 2021-12-02 | Confirm Objectives to be Delivered at Gate A (FEEDS TO SUMMARY SCHEDULE) | 01-Dec-21 A | 02-Dec-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6668LT | W213 | W213.1000 | TOR Essential Defueling Safety Case | 2021-12-01 | 2021-12-02 | Confirm Objectives to be Delivered at Gate A (FEEDS TO SUMMARY SCHEDULE) | 01-Dec-21 A | 02-Dec-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.1040 | HYB Essential Defueling Safety Case | 2021-12-03 | 2021-12-06 | Initial high level scope of programme | 03-Dec-21 A | 06-Dec-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6668LT | W213 | W213.1040 | TOR Essential Defueling Safety Case | 2021-12-03 | 2021-12-06 | Initial high level scope of programme | 03-Dec-21 A | 06-Dec-21 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A5250 | HRA Reactors Shutdown Essential Safety Cases | 2021-12-06 | 2022-02-01 | INSA review & iteration of comments (using BARRIER MODEL) (HRA) (Suspended for Event Recovery) | 06-Dec-21 A | 01-Feb-22 A | 40 | 0 | 38 | 100% |  | Completed
ER6371LT | W202 | W202.A5260 | HRA Reactors Shutdown Essential Safety Cases | 2021-12-06 | 2021-12-06 | <NOT REQUIRED> DA (Authorised Designer) Approval of CAT1 Safety Case (HRA) | 06-Dec-21 A | 06-Dec-21 A | 5 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5250 | HYA Reactors Shutdown Essential Safety Cases | 2021-12-06 | 2022-02-01 | INSA review & iteration of comments (using BARRIER MODEL) (HYA) (Suspended for Event Recovery) | 06-Dec-21 A | 01-Feb-22 A | 40 | 0 | 38 | 100% |  | Completed
ER6661LT | W206 | W206.A5260 | HYA Reactors Shutdown Essential Safety Cases | 2021-12-06 | 2021-12-06 | <NOT REQUIRED> DA (Authorised Designer) Approval of CAT1 Safety Case (HYA) | 06-Dec-21 A | 06-Dec-21 A | 5 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A24310 | HRA Fuel Handling Essential Safety Case | 2021-12-06 | 2022-02-17 | Verify Living Safety Document EAN and Issue for Technical Review | 06-Dec-21 A | 17-Feb-22 A | 10 | 0 | 51 | 100% |  | Completed
ER6378LT | W222 | W222.A4660 | HRA Fuel Handling Essential Safety Case | 2021-12-06 | 2021-12-10 | Obtain peer review (if required) | 06-Dec-21 A | 10-Dec-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A4660 | HYA Fuel Handling Essential Safety Case | 2021-12-06 | 2021-12-10 | Obtain peer review (if required) | 06-Dec-21 A | 10-Dec-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A24310 | HYA Fuel Handling Essential Safety Case | 2021-12-06 | 2022-02-17 | Verify Living Safety Document EAN and Issue for Technical Review | 06-Dec-21 A | 17-Feb-22 A | 10 | 0 | 50 | 100% |  | Completed
ER6666LT | W209 | W209.1050 | HYB Essential Defueling Safety Case | 2021-12-07 | 2021-12-13 | Prepare Draft Project Definition Document (PDD) | 07-Dec-21 A | 13-Dec-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.1050 | TOR Essential Defueling Safety Case | 2021-12-07 | 2021-12-13 | Prepare Draft Project Definition Document (PDD) | 07-Dec-21 A | 13-Dec-21 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.1000 | HRA Fuel Handling Essential Safety Case |  | 2021-12-07 | Discovery Milestone - Confirm Verification Period | 07-Dec-21 A | 07-Dec-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.1000 | HYA Fuel Handling Essential Safety Case |  | 2021-12-07 | Discovery Milestone - Confirm Verification Period | 07-Dec-21 A | 07-Dec-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A4790 | HRA Fuel Handling Essential Safety Case |  | 2021-12-10 | Safety Case Prop Authoring Complete ECs (HRA-363840) HRA Essential Fuel Handling Safety Case | 10-Dec-21 A | 10-Dec-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A4790 | HYA Fuel Handling Essential Safety Case |  | 2021-12-10 | Safety Case Prop Authoring Complete ECs (HYA-363839) HYA Essential Fuel Handling Safety Case | 10-Dec-21 A | 10-Dec-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A4800 | HRA Fuel Handling Essential Safety Case |  | 2021-12-13 | HRA HYA Essential Fuel Handling SC: Verification Commenced (T-11) | 13-Dec-21 A | 13-Dec-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A4800 | HYA Fuel Handling Essential Safety Case |  | 2021-12-13 | HYA HYA Essential Fuel Handling SC: Verification Commenced (T-11) | 13-Dec-21 A | 13-Dec-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5320 | HYA Reactors Shutdown Essential Safety Cases |  | 2021-12-31 | Discovery Milestone: Confirm INA Period | 13-Dec-21 A | 13-Dec-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A13380 | HRA Fuel Handling Essential Safety Case | 2021-12-13 | 2024-02-05 | Safety Case Development - Costs - AR / CETS / Support to CO ##(Cost Summary)## (C to D) ** | 13-Dec-21 A | 24-Jan-25 A | 176 | 0 | 786 | 100% |  | Completed
ER6378LT | W222 | W222.A4700 | HRA Fuel Handling Essential Safety Case | 2021-12-13 | 2022-02-21 | Verification of the case (using BARRIER MODEL) | 13-Dec-21 A | 21-Feb-22 A | 40 | 0 | 47 | 100% |  | Completed
ER6378LT | W222 | W222.A4770 | HRA Fuel Handling Essential Safety Case | 2021-12-13 | 2023-07-19 | Specialist Assessments if Necessary (Expand as Required) | 13-Dec-21 A | 31-Aug-23 A | 10 | 0 | 430 | 100% |  | Completed
ER6650LT | W226 | W226.A4770 | HYA Fuel Handling Essential Safety Case | 2021-12-13 | 2023-07-19 | Specialist Assessments if Necessary (Expand as Required) | 13-Dec-21 A | 31-Aug-23 A | 10 | 0 | 430 | 100% |  | Completed
ER6650LT | W226 | W226.A4700 | HYA Fuel Handling Essential Safety Case | 2021-12-13 | 2022-02-21 | Verification of the case (using BARRIER MODEL) | 13-Dec-21 A | 21-Feb-22 A | 40 | 0 | 47 | 100% |  | Completed
ER6378LT | W222 | W222.1110 | HRA Fuel Handling Essential Safety Case | 2021-12-13 | 2023-08-08 | Project Management Costs - Verification Phase (C to D ) ##Cost Summary## ** | 13-Dec-21 A | 17-Jul-24 A | 70 | 0 | 653 | 100% |  | Completed
ER6378LT | W222 | W222.1120 | HRA Fuel Handling Essential Safety Case | 2021-12-13 | 2023-08-08 | Safety Case Development Costs - Verification Phase (C to D ) ##Cost Summary## ** | 13-Dec-21 A | 17-Jul-24 A | 70 | 0 | 653 | 100% |  | Completed
ER6650LT | W226 | W226.A13380 | HYA Fuel Handling Essential Safety Case | 2021-12-13 | 2024-02-05 | Safety Case Development - Costs - AR / CETS / Support to CO ##(Cost Summary)## (C to D) ** | 13-Dec-21 A | 13-Jan-25 A | 176 | 0 | 777 | 100% |  | Completed
ER6650LT | W226 | W226.1120 | HYA Fuel Handling Essential Safety Case | 2021-12-13 | 2023-08-08 | Safety Case Development Costs - Verification Phase (C to D ) ##Cost Summary## ** | 13-Dec-21 A | 17-Jul-24 A | 70 | 0 | 653 | 100% |  | Completed
ER6650LT | W226 | W226.1110 | HYA Fuel Handling Essential Safety Case | 2021-12-13 | 2023-08-08 | Project Management Costs - Verification Phase (C to D ) ##Cost Summary## ** | 13-Dec-21 A | 17-Jul-24 A | 70 | 0 | 653 | 100% |  | Completed
ER6371LT | W202 | W202.A5320 | HRA Reactors Shutdown Essential Safety Cases |  | 2021-12-13 | Discovery Milestone: Confirm INA Period | 13-Dec-21 A | 13-Dec-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1130 | HYB Essential Defueling Safety Case | 2021-12-14 | 2022-01-28 | Update Schedule/Estimate from Risk Log & Add Provisions | 14-Dec-21 A | 28-Jan-22 A | 5 | 0 | 31 | 100% |  | Completed
ER6668LT | W213 | W213.1130 | TOR Essential Defueling Safety Case | 2021-12-14 | 2022-01-28 | Update Schedule/Estimate from Risk Log & Add Provisions | 14-Dec-21 A | 28-Jan-22 A | 5 | 0 | 31 | 100% |  | Completed
ER6650LT | W226 | W226.A16360 | HYA Fuel Handling Essential Safety Case |  | 2021-12-24 | Defuelling Safety Case Head Documents EAN Available | 24-Dec-21 A | 24-Dec-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A16360 | HRA Fuel Handling Essential Safety Case |  | 2021-12-24 | Defuelling Safety Case Head Documents EAN Available | 24-Dec-21 A | 24-Dec-21 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1260 | HYB Essential Defueling Safety Case | 2022-01-04 | 2022-07-14 | Project Management - Gate A-B - (Cost Summary) ## | 04-Jan-22 A | 14-Jul-22 A | 282 | 0 | 133 | 100% |  | Completed
ER6666LT | W209 | W209.1280 | HYB Essential Defueling Safety Case | 2022-01-04 | 2022-07-14 | SC - Oversight Support - A-B - (Cost Summary) ## | 04-Jan-22 A | 14-Jul-22 A | 282 | 0 | 133 | 100% |  | Completed
ER6666LT | W209 | W209.3280 | HYB Essential Defueling Safety Case | 2022-01-04 | 2022-02-04 | Release and Receive Comments from Stakeholders | 04-Jan-22 A | 04-Feb-22 A | 10 | 0 | 24 | 100% |  | Completed
ER6666LT | W209 | W209.3290 | HYB Essential Defueling Safety Case | 2022-01-04 | 2022-02-04 | Develop Optioneering Options | 04-Jan-22 A | 04-Feb-22 A | 5 | 0 | 24 | 100% |  | Completed
ER6666LT | W209 | W209.4280 | HYB Essential Defueling Safety Case | 2022-01-04 | 2022-05-13 | Defueling Order / Fuel Management - (Cost Summary) ## | 04-Jan-22 A | 13-May-22 A | 84 | 0 | 91 | 100% |  | Completed
ER6666LT | W209 | W209.4290 | HYB Essential Defueling Safety Case | 2022-01-04 | 2022-07-13 | Fuel Handling - (Cost Summary) ## | 04-Jan-22 A | 13-Jul-22 A | 282 | 0 | 132 | 100% |  | Completed
ER6666LT | W209 | W209.5680 | HYB Essential Defueling Safety Case | 2022-01-04 | 2022-01-17 | Prepare Spec for Judgement Based Work Diversion EAN | 04-Jan-22 A | 17-Jan-22 A | 5 | 0 | 9 | 100% |  | Completed
ER6666LT | W209 | W209.25960 | HYB Essential Defueling Safety Case | 2022-02-24 | 2022-07-13 | Technical Development / Project Management - Gate A - B - (Cost Summary) ## | 04-Jan-22 A | 14-Jul-22 A | 282 | 0 | 133 | 100% |  | Completed
ER6668LT | W213 | W213.1260 | TOR Essential Defueling Safety Case | 2022-01-04 | 2022-07-14 | Project Management - Gate A-B - (Cost Summary) ## | 04-Jan-22 A | 14-Jul-22 A | 282 | 0 | 133 | 100% |  | Completed
ER6668LT | W213 | W213.1280 | TOR Essential Defueling Safety Case | 2022-01-04 | 2022-07-14 | SC - Oversight Support - A-B - (Cost Summary) ## | 04-Jan-22 A | 14-Jul-22 A | 282 | 0 | 133 | 100% |  | Completed
ER6668LT | W213 | W213.3280 | TOR Essential Defueling Safety Case | 2022-01-04 | 2022-02-04 | Release and Receive Comments from Stakeholders | 04-Jan-22 A | 04-Feb-22 A | 10 | 0 | 24 | 100% |  | Completed
ER6668LT | W213 | W213.3290 | TOR Essential Defueling Safety Case | 2022-01-04 | 2022-02-04 | Develop Optioneering Options | 04-Jan-22 A | 04-Feb-22 A | 5 | 0 | 24 | 100% |  | Completed
ER6668LT | W213 | W213.4280 | TOR Essential Defueling Safety Case | 2022-01-04 | 2022-05-13 | Defueling Order / Fuel Management - (Cost Summary) ## | 04-Jan-22 A | 13-May-22 A | 84 | 0 | 91 | 100% |  | Completed
ER6668LT | W213 | W213.4290 | TOR Essential Defueling Safety Case | 2022-01-04 | 2022-07-13 | Fuel Handling - (Cost Summary) ## | 04-Jan-22 A | 13-Jul-22 A | 282 | 0 | 132 | 100% |  | Completed
ER6668LT | W213 | W213.5680 | TOR Essential Defueling Safety Case | 2022-01-04 | 2022-01-17 | Prepare Spec for Judgement Based Work Diversion EAN | 04-Jan-22 A | 17-Jan-22 A | 5 | 0 | 9 | 100% |  | Completed
ER6668LT | W213 | W213.25960 | TOR Essential Defueling Safety Case | 2022-02-24 | 2022-07-13 | Technical Development / Project Management - Gate A - B - (Cost Summary) ## | 04-Jan-22 A | 14-Jul-22 A | 282 | 0 | 133 | 100% |  | Completed
W520LT | W520 | W520.A1010 | FLEETWIDE CTO Defueling Safety Case Delivery | 2022-01-04 | 2022-12-30 | 2022 Costs | 04-Jan-22 A | 30-Dec-22 A | 253 | 0 | 250 | 100% |  | Completed
ER6666LT | W209 | W209.3260 | HYB Essential Defueling Safety Case | 2022-01-04 | 2022-02-04 | Develop Optioneering Question Set | 04-Jan-22 A | 04-Feb-22 A | 15 | 0 | 24 | 100% |  | Completed
ER6666LT | W209 | W209.3270 | HYB Essential Defueling Safety Case | 2022-01-04 | 2022-02-04 | Develop Optioneering Criteria | 04-Jan-22 A | 04-Feb-22 A | 15 | 0 | 24 | 100% |  | Completed
ER6666LT | W209 | W209.3580 | HYB Essential Defueling Safety Case | 2022-01-04 | 2022-01-24 | Specify Scope for Delivery | 04-Jan-22 A | 24-Jan-22 A | 9 | 0 | 14 | 100% |  | Completed
ER6666LT | W209 | W209.3890 | HYB Essential Defueling Safety Case | 2022-01-04 | 2022-02-11 | Develop Optioneering Question Set | 04-Jan-22 A | 11-Feb-22 A | 10 | 0 | 29 | 100% |  | Completed
ER6666LT | W209 | W209.3900 | HYB Essential Defueling Safety Case | 2022-01-04 | 2022-02-11 | Develop Optioneering Criteria & Options | 04-Jan-22 A | 11-Feb-22 A | 10 | 0 | 29 | 100% |  | Completed
ER6666LT | W209 | W209.3990 | HYB Essential Defueling Safety Case | 2022-01-04 | 2022-04-27 | Defueling PM OPEX | 04-Jan-22 A | 27-Apr-22 A | 40 | 0 | 79 | 100% |  | Completed
ER6666LT | W209 | W209.4340 | HYB Essential Defueling Safety Case | 2022-01-04 | 2022-03-01 | Generate Draft Fuel Route Process Flow Commentary | 04-Jan-22 A | 01-Mar-22 A | 15 | 0 | 41 | 100% |  | Completed
ER6666LT | W209 | W209.4440 | HYB Essential Defueling Safety Case | 2022-01-04 | 2022-01-17 | Generate RFS (A-B Phase) | 04-Jan-22 A | 17-Jan-22 A | 10 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.4460 | HYB Essential Defueling Safety Case | 2022-01-04 | 2022-02-01 | Ratify HYB TOR Defueling Assumptions List with Station | 04-Jan-22 A | 01-Feb-22 A | 20 | 0 | 21 | 100% |  | Completed
ER6666LT | W209 | W209.4490 | HYB Essential Defueling Safety Case | 2022-01-04 | 2022-05-17 | Lead & Learn Workstream - (Cost Summary) ## | 04-Jan-22 A | 17-May-22 A | 93 | 0 | 93 | 100% |  | Completed
ER6666LT | W209 | W209.1085 | HYB Essential Defueling Safety Case | 2022-01-04 | 2022-04-01 | Produce draft NSRS (using BARRIER MODEL) | 04-Jan-22 A | 01-Apr-22 A | 40 | 0 | 64 | 100% |  | Completed
ER6666LT | W209 | W209.4640 | HYB Essential Defueling Safety Case | 2022-01-04 | 2022-07-01 | Defueling Cooling Operations - (Cost Summary) ## | 04-Jan-22 A | 01-Jul-22 A | 106 | 0 | 124 | 100% |  | Completed
ER6666LT | W209 | W209.4890 | HYB Essential Defueling Safety Case | 2022-06-01 | 2022-07-13 | Defueling Cooling Operations - De-risking Scope - (Cost Summary) ## | 04-Jan-22 A | 13-Jul-22 A | 132 | 0 | 132 | 100% |  | Completed
ER6668LT | W213 | W213.3260 | TOR Essential Defueling Safety Case | 2022-01-04 | 2022-02-04 | Develop Optioneering Question Set | 04-Jan-22 A | 04-Feb-22 A | 15 | 0 | 24 | 100% |  | Completed
ER6668LT | W213 | W213.3270 | TOR Essential Defueling Safety Case | 2022-01-04 | 2022-02-04 | Develop Optioneering Criteria | 04-Jan-22 A | 04-Feb-22 A | 15 | 0 | 24 | 100% |  | Completed
ER6668LT | W213 | W213.3580 | TOR Essential Defueling Safety Case | 2022-01-04 | 2022-01-24 | Specify Scope for Delivery | 04-Jan-22 A | 24-Jan-22 A | 9 | 0 | 14 | 100% |  | Completed
ER6668LT | W213 | W213.3890 | TOR Essential Defueling Safety Case | 2022-01-04 | 2022-02-11 | Develop Optioneering Question Set | 04-Jan-22 A | 11-Feb-22 A | 10 | 0 | 29 | 100% |  | Completed
ER6668LT | W213 | W213.3900 | TOR Essential Defueling Safety Case | 2022-01-04 | 2022-02-11 | Develop Optioneering Criteria & Options | 04-Jan-22 A | 11-Feb-22 A | 10 | 0 | 29 | 100% |  | Completed
ER6668LT | W213 | W213.3990 | TOR Essential Defueling Safety Case | 2022-01-04 | 2022-04-27 | Defueling PM OPEX | 04-Jan-22 A | 27-Apr-22 A | 40 | 0 | 79 | 100% |  | Completed
ER6668LT | W213 | W213.4340 | TOR Essential Defueling Safety Case | 2022-01-04 | 2022-03-01 | Generate Draft Fuel Route Process Flow Commentary | 04-Jan-22 A | 01-Mar-22 A | 15 | 0 | 41 | 100% |  | Completed
ER6668LT | W213 | W213.4440 | TOR Essential Defueling Safety Case | 2022-01-04 | 2022-01-17 | Generate RFS (A-B Phase) | 04-Jan-22 A | 17-Jan-22 A | 10 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.4460 | TOR Essential Defueling Safety Case | 2022-01-04 | 2022-02-01 | Ratify TOR TOR Defueling Assumptions List with Station | 04-Jan-22 A | 01-Feb-22 A | 20 | 0 | 21 | 100% |  | Completed
ER6668LT | W213 | W213.4490 | TOR Essential Defueling Safety Case | 2022-01-04 | 2022-05-17 | Lead & Learn Workstream - (Cost Summary) ## | 04-Jan-22 A | 17-May-22 A | 93 | 0 | 93 | 100% |  | Completed
ER6668LT | W213 | W213.1085 | TOR Essential Defueling Safety Case | 2022-01-04 | 2022-04-01 | Produce draft NSRS (using BARRIER MODEL) | 04-Jan-22 A | 01-Apr-22 A | 40 | 0 | 64 | 100% |  | Completed
ER6668LT | W213 | W213.4640 | TOR Essential Defueling Safety Case | 2022-01-04 | 2022-07-01 | Defueling Cooling Operations - (Cost Summary) ## | 04-Jan-22 A | 01-Jul-22 A | 106 | 0 | 124 | 100% |  | Completed
ER6668LT | W213 | W213.4890 | TOR Essential Defueling Safety Case | 2022-06-01 | 2022-07-13 | Defueling Cooling Operations - De-risking Scope - (Cost Summary) ## | 04-Jan-22 A | 13-Jul-22 A | 132 | 0 | 132 | 100% |  | Completed
ER6666LT | W209 | W209.1005 | HYB Essential Defueling Safety Case |  | 2022-01-04 | PM / CO and PCE Create Initial Plan of Work | 04-Jan-22 A | 04-Jan-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1015 | HYB Essential Defueling Safety Case |  | 2022-01-04 | Initial Categorisation by Station | 04-Jan-22 A | 04-Jan-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1005 | TOR Essential Defueling Safety Case |  | 2022-01-04 | PM / CO and PCE Create Initial Plan of Work | 04-Jan-22 A | 04-Jan-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1015 | TOR Essential Defueling Safety Case |  | 2022-01-04 | Initial Categorisation by Station | 04-Jan-22 A | 04-Jan-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1035 | HYB Essential Defueling Safety Case | 2022-01-05 | 2022-01-05 | Appoint CO | 05-Jan-22 A | 05-Jan-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.1035 | TOR Essential Defueling Safety Case | 2022-01-05 | 2022-01-05 | Appoint CO | 05-Jan-22 A | 05-Jan-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.1025 | HYB Essential Defueling Safety Case | 2022-01-06 | 2022-01-06 | Commence NSRS | 06-Jan-22 A | 06-Jan-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1025 | TOR Essential Defueling Safety Case | 2022-01-06 | 2022-01-06 | Commence NSRS | 06-Jan-22 A | 06-Jan-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.4020 | HYB Essential Defueling Safety Case | 2022-01-06 | 2022-01-06 | SC Strategy Workshop | 06-Jan-22 A | 06-Jan-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.4020 | TOR Essential Defueling Safety Case | 2022-01-06 | 2022-01-06 | SC Strategy Workshop | 06-Jan-22 A | 06-Jan-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.4500 | HYB Essential Defueling Safety Case | 2022-01-07 | 2022-03-03 | Share Safety Case Strategy with Stakeholders (Central / Station / Regulatory) | 07-Jan-22 A | 03-Mar-22 A | 40 | 0 | 40 | 100% |  | Completed
ER6668LT | W213 | W213.4500 | TOR Essential Defueling Safety Case | 2022-01-07 | 2022-03-03 | Share Safety Case Strategy with Stakeholders (Central / Station / Regulatory) | 07-Jan-22 A | 03-Mar-22 A | 40 | 0 | 40 | 100% |  | Completed
ER6666LT | W209 | W209.4990 | HYB Essential Defueling Safety Case | 2022-01-10 | 2022-01-17 | Contract Instruction issues to Atkins by EDF Energy | 10-Jan-22 A | 17-Jan-22 A | 0 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.5180 | HYB Essential Defueling Safety Case | 2022-01-10 | 2022-07-01 | Dropped FPU - Basis of Analysis - (Cost Summary) ## | 10-Jan-22 A | 01-Jul-22 A | 92 | 0 | 120 | 100% |  | Completed
ER6666LT | W209 | W209.5190 | HYB Essential Defueling Safety Case | 2022-06-01 | 2022-07-13 | DE-RISKING SCOPE - Fuel Handling - (Cost Summary) ## | 10-Jan-22 A | 13-Jul-22 A | 69 | 0 | 128 | 100% |  | Completed
ER6666LT | W209 | W209.6580 | HYB Essential Defueling Safety Case | 2022-01-10 | 2022-01-14 | Prepare Spec for Radiological Consequences Following Failed CSP EAN | 10-Jan-22 A | 14-Jan-22 A | 5 | 0 | 4 | 100% |  | Completed
ER6668LT | W213 | W213.4990 | TOR Essential Defueling Safety Case | 2022-01-10 | 2022-01-17 | Contract Instruction issues to Atkins by EDF Energy | 10-Jan-22 A | 17-Jan-22 A | 0 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.5180 | TOR Essential Defueling Safety Case | 2022-01-10 | 2022-07-01 | Dropped FPU - Basis of Analysis - (Cost Summary) ## | 10-Jan-22 A | 01-Jul-22 A | 92 | 0 | 120 | 100% |  | Completed
ER6668LT | W213 | W213.5190 | TOR Essential Defueling Safety Case | 2022-06-01 | 2022-07-13 | DE-RISKING SCOPE - Fuel Handling - (Cost Summary) ## | 10-Jan-22 A | 13-Jul-22 A | 69 | 0 | 128 | 100% |  | Completed
ER6668LT | W213 | W213.6580 | TOR Essential Defueling Safety Case | 2022-01-10 | 2022-01-14 | Prepare Spec for Radiological Consequences Following Failed CSP EAN | 10-Jan-22 A | 14-Jan-22 A | 5 | 0 | 4 | 100% |  | Completed
ER6666LT | W209 | W209.5000 | HYB Essential Defueling Safety Case | 2022-01-17 | 2022-01-17 | PJB Held | 17-Jan-22 A | 17-Jan-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.6590 | HYB Essential Defueling Safety Case | 2022-01-17 | 2022-01-21 | Prepare Task Sheet for Radiological Consequences Following Failed CSP EAN | 17-Jan-22 A | 21-Jan-22 A | 10 | 0 | 4 | 100% |  | Completed
ER6668LT | W213 | W213.5000 | TOR Essential Defueling Safety Case | 2022-01-17 | 2022-01-17 | PJB Held | 17-Jan-22 A | 17-Jan-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.6590 | TOR Essential Defueling Safety Case | 2022-01-17 | 2022-01-21 | Prepare Task Sheet for Radiological Consequences Following Failed CSP EAN | 17-Jan-22 A | 21-Jan-22 A | 10 | 0 | 4 | 100% |  | Completed
ER6666LT | W209 | W209.4710 | HYB Essential Defueling Safety Case | 2022-01-17 | 2022-01-21 | Review Region 1 & Existing Fault Schedules | 17-Jan-22 A | 21-Jan-22 A | 10 | 0 | 4 | 100% |  | Completed
ER6668LT | W213 | W213.4710 | TOR Essential Defueling Safety Case | 2022-01-17 | 2022-01-21 | Review Region 1 & Existing Fault Schedules | 17-Jan-22 A | 21-Jan-22 A | 10 | 0 | 4 | 100% |  | Completed
ER6666LT | W209 | W209.5050 | HYB Essential Defueling Safety Case | 2022-01-18 | 2022-02-15 | Define Nuclear Safety Issues | 18-Jan-22 A | 15-Feb-22 A | 1 | 0 | 20 | 100% |  | Completed
ER6666LT | W209 | W209.5690 | HYB Essential Defueling Safety Case | 2022-01-18 | 2022-01-20 | Prepare Task Sheet for Judgement Based Work Diversion EAN | 18-Jan-22 A | 20-Jan-22 A | 10 | 0 | 2 | 100% |  | Completed
ER6668LT | W213 | W213.5050 | TOR Essential Defueling Safety Case | 2022-01-18 | 2022-02-15 | Define Nuclear Safety Issues | 18-Jan-22 A | 15-Feb-22 A | 1 | 0 | 20 | 100% |  | Completed
ER6668LT | W213 | W213.5690 | TOR Essential Defueling Safety Case | 2022-01-18 | 2022-01-20 | Prepare Task Sheet for Judgement Based Work Diversion EAN | 18-Jan-22 A | 20-Jan-22 A | 10 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.4660 | HYB Essential Defueling Safety Case | 2022-01-18 | 2022-01-20 | Review & Approve RFS (A-B Phase) | 18-Jan-22 A | 20-Jan-22 A | 5 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.4660 | TOR Essential Defueling Safety Case | 2022-01-18 | 2022-01-20 | Review & Approve RFS (A-B Phase) | 18-Jan-22 A | 20-Jan-22 A | 5 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.5700 | HYB Essential Defueling Safety Case | 2022-01-21 | 2022-01-21 | Approve Task Sheet for Judgement Based Work Diversion EAN | 21-Jan-22 A | 21-Jan-22 A | 7 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.5700 | TOR Essential Defueling Safety Case | 2022-01-21 | 2022-01-21 | Approve Task Sheet for Judgement Based Work Diversion EAN | 21-Jan-22 A | 21-Jan-22 A | 7 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.4670 | HYB Essential Defueling Safety Case | 2022-01-21 | 2022-01-21 | Issue RFS (A-B Phase) | 21-Jan-22 A | 21-Jan-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.4670 | TOR Essential Defueling Safety Case | 2022-01-21 | 2022-01-21 | Issue RFS (A-B Phase) | 21-Jan-22 A | 21-Jan-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.3590 | HYB Essential Defueling Safety Case | 2022-01-24 | 2022-02-17 | TSA/EDF Best Athlete Review | 24-Jan-22 A | 17-Feb-22 A | 10 | 0 | 18 | 100% |  | Completed
ER6666LT | W209 | W209.4720 | HYB Essential Defueling Safety Case | 2022-01-24 | 2022-03-01 | Defueling Safety Case Team Review | 24-Jan-22 A | 01-Mar-22 A | 10 | 0 | 27 | 100% |  | Completed
ER6666LT | W209 | W209.6600 | HYB Essential Defueling Safety Case | 2022-01-24 | 2022-02-04 | Approve Task Sheet for Radiological Consequences Following Failed CSP EAN | 24-Jan-22 A | 04-Feb-22 A | 7 | 0 | 9 | 100% |  | Completed
ER6668LT | W213 | W213.3590 | TOR Essential Defueling Safety Case | 2022-01-24 | 2022-02-17 | TSA/EDF Best Athlete Review | 24-Jan-22 A | 17-Feb-22 A | 10 | 0 | 18 | 100% |  | Completed
ER6668LT | W213 | W213.4720 | TOR Essential Defueling Safety Case | 2022-01-24 | 2022-03-01 | Defueling Safety Case Team Review | 24-Jan-22 A | 01-Mar-22 A | 10 | 0 | 27 | 100% |  | Completed
ER6668LT | W213 | W213.6600 | TOR Essential Defueling Safety Case | 2022-01-24 | 2022-02-04 | Approve Task Sheet for Radiological Consequences Following Failed CSP EAN | 24-Jan-22 A | 04-Feb-22 A | 7 | 0 | 9 | 100% |  | Completed
ER6666LT | W209 | W209.4680 | HYB Essential Defueling Safety Case | 2022-01-24 | 2022-02-07 | Supplier Respond to RFS (A-B Phase) | 24-Jan-22 A | 07-Feb-22 A | 15 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.4680 | TOR Essential Defueling Safety Case | 2022-01-24 | 2022-02-07 | Supplier Respond to RFS (A-B Phase) | 24-Jan-22 A | 07-Feb-22 A | 15 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.5210 | HYB Essential Defueling Safety Case | 2022-01-31 | 2022-05-06 | De-Risking Scope - Consequences Assessment - (Cost Summary) ## | 31-Jan-22 A | 06-May-22 A | 26 | 0 | 66 | 100% |  | Completed
ER6668LT | W213 | W213.5210 | TOR Essential Defueling Safety Case | 2022-01-31 | 2022-05-06 | De-Risking Scope - Consequences Assessment - (Cost Summary) ## | 31-Jan-22 A | 06-May-22 A | 26 | 0 | 66 | 100% |  | Completed
ER6666LT | W209 | W209.1140 | HYB Essential Defueling Safety Case | 2022-01-31 | 2022-02-01 | Add Data to IAB Paper | 31-Jan-22 A | 01-Feb-22 A | 2 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.3410 | HYB Essential Defueling Safety Case | 2022-01-31 | 2022-01-31 | Dropped FPU Scoping Workshop | 31-Jan-22 A | 31-Jan-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.1140 | TOR Essential Defueling Safety Case | 2022-01-31 | 2022-02-01 | Add Data to IAB Paper | 31-Jan-22 A | 01-Feb-22 A | 2 | 0 | 2 | 100% |  | Completed
ER6668LT | W213 | W213.3410 | TOR Essential Defueling Safety Case | 2022-01-31 | 2022-01-31 | Dropped FPU Scoping Workshop | 31-Jan-22 A | 31-Jan-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.3430 | HYB Essential Defueling Safety Case | 2022-02-01 | 2022-04-20 | Develop Dropped FPU Substantiation De-risking scope | 01-Feb-22 A | 20-Apr-22 A | 10 | 0 | 55 | 100% |  | Completed
ER6666LT | W209 | W209.3830 | HYB Essential Defueling Safety Case | 2022-02-01 | 2022-03-16 | Specify Seismic Assessment Scope for Delivery | 01-Feb-22 A | 16-Mar-22 A | 10 | 0 | 31 | 100% |  | Completed
ER6668LT | W213 | W213.3430 | TOR Essential Defueling Safety Case | 2022-02-01 | 2022-04-20 | Develop Dropped FPU Substantiation De-risking scope | 01-Feb-22 A | 20-Apr-22 A | 10 | 0 | 55 | 100% |  | Completed
ER6668LT | W213 | W213.3830 | TOR Essential Defueling Safety Case | 2022-02-01 | 2022-03-16 | Specify Seismic Assessment Scope for Delivery | 01-Feb-22 A | 16-Mar-22 A | 10 | 0 | 31 | 100% |  | Completed
ER6666LT | W209 | W209.3780 | HYB Essential Defueling Safety Case | 2022-02-01 | 2022-03-16 | Specify PCPV Integrity Justification Scope for Delivery | 01-Feb-22 A | 16-Mar-22 A | 10 | 0 | 31 | 100% |  | Completed
ER6668LT | W213 | W213.3780 | TOR Essential Defueling Safety Case | 2022-02-01 | 2022-03-16 | Specify PCPV Integrity Justification Scope for Delivery | 01-Feb-22 A | 16-Mar-22 A | 10 | 0 | 31 | 100% |  | Completed
ER6666LT | W209 | W209.1150 | HYB Essential Defueling Safety Case | 2022-02-02 | 2022-02-08 | PCL Validate & Approve Baseline Package for PRC Submission | 02-Feb-22 A | 08-Feb-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.4470 | HYB Essential Defueling Safety Case | 2022-02-02 | 2022-03-01 | Pre PSRG to Review and Approve Defueling Assumptions List | 02-Feb-22 A | 01-Mar-22 A | 5 | 0 | 20 | 100% |  | Completed
ER6666LT | W209 | W209.5070 | HYB Essential Defueling Safety Case | 2022-02-02 | 2022-02-02 | Formal Pre Job Brief | 02-Feb-22 A | 02-Feb-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.1150 | TOR Essential Defueling Safety Case | 2022-02-02 | 2022-02-08 | PCL Validate & Approve Baseline Package for PRC Submission | 02-Feb-22 A | 08-Feb-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.4470 | TOR Essential Defueling Safety Case | 2022-02-02 | 2022-03-01 | Pre PSRG to Review and Approve Defueling Assumptions List | 02-Feb-22 A | 01-Mar-22 A | 5 | 0 | 20 | 100% |  | Completed
ER6668LT | W213 | W213.5070 | TOR Essential Defueling Safety Case | 2022-02-02 | 2022-02-02 | Formal Pre Job Brief | 02-Feb-22 A | 02-Feb-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.5080 | HYB Essential Defueling Safety Case | 2022-02-03 | 2022-03-02 | Issue of QA Grade 4 Skeleton Document | 03-Feb-22 A | 02-Mar-22 A | 18 | 0 | 20 | 100% |  | Completed
ER6668LT | W213 | W213.5080 | TOR Essential Defueling Safety Case | 2022-02-03 | 2022-03-02 | Issue of QA Grade 4 Skeleton Document | 03-Feb-22 A | 02-Mar-22 A | 18 | 0 | 20 | 100% |  | Completed
ER6666LT | W209 | W209.3310 | HYB Essential Defueling Safety Case | 2022-02-04 | 2022-02-04 | PJB Workshop Attendees | 04-Feb-22 A | 04-Feb-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.3310 | TOR Essential Defueling Safety Case | 2022-02-04 | 2022-02-04 | PJB Workshop Attendees | 04-Feb-22 A | 04-Feb-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.3300 | HYB Essential Defueling Safety Case |  | 2022-02-04 | Release Draft Optioneering Report for Workshop | 04-Feb-22 A | 04-Feb-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.3300 | TOR Essential Defueling Safety Case |  | 2022-02-04 | Release Draft Optioneering Report for Workshop | 04-Feb-22 A | 04-Feb-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A25700 | HYB Essential Defueling Safety Case | 2022-02-07 | 2022-02-07 | Pre Job Brief for Judgement Based Work Diversion EAN | 07-Feb-22 A | 07-Feb-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A28580 | HYB Essential Defueling Safety Case | 2022-02-07 | 2022-02-07 | Pre Job Brief for Radiological Consequences Following Failed CSP EAN | 07-Feb-22 A | 07-Feb-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A25700 | TOR Essential Defueling Safety Case | 2022-02-07 | 2022-02-07 | Pre Job Brief for Judgement Based Work Diversion EAN | 07-Feb-22 A | 07-Feb-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A28580 | TOR Essential Defueling Safety Case | 2022-02-07 | 2022-02-07 | Pre Job Brief for Radiological Consequences Following Failed CSP EAN | 07-Feb-22 A | 07-Feb-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.4700 | HYB Essential Defueling Safety Case | 2022-02-08 | 2022-06-29 | Undertake Analysis (A-B Phase) | 08-Feb-22 A | 01-Jul-22 A | 69 | 0 | 99 | 100% |  | Completed
ER6666LT | W209 | W209.A25710 | HYB Essential Defueling Safety Case | 2022-02-08 | 2022-06-15 | Draft Judgement Based Work Diversion EAN | 08-Feb-22 A | 01-Jul-22 A | 30 | 0 | 99 | 100% |  | Completed
ER6666LT | W209 | W209.A28590 | HYB Essential Defueling Safety Case | 2022-02-08 | 2022-06-01 | Draft Radiological Consequences Following Failed CSP EAN | 08-Feb-22 A | 01-Jul-22 A | 30 | 0 | 99 | 100% |  | Completed
ER6668LT | W213 | W213.4700 | TOR Essential Defueling Safety Case | 2022-02-08 | 2022-06-29 | Undertake Analysis (A-B Phase) | 08-Feb-22 A | 01-Jul-22 A | 69 | 0 | 99 | 100% |  | Completed
ER6668LT | W213 | W213.A25710 | TOR Essential Defueling Safety Case | 2022-02-08 | 2022-06-15 | Draft Judgement Based Work Diversion EAN | 08-Feb-22 A | 01-Jul-22 A | 30 | 0 | 99 | 100% |  | Completed
ER6668LT | W213 | W213.A28590 | TOR Essential Defueling Safety Case | 2022-02-08 | 2022-06-01 | Draft Radiological Consequences Following Failed CSP EAN | 08-Feb-22 A | 01-Jul-22 A | 30 | 0 | 99 | 100% |  | Completed
ER6666LT | W209 | W209.1160 | HYB Essential Defueling Safety Case | 2022-02-09 | 2022-02-09 | Gate A PRC Paper Submission | 09-Feb-22 A | 09-Feb-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.1160 | TOR Essential Defueling Safety Case | 2022-02-09 | 2022-02-09 | Gate A PRC Paper Submission | 09-Feb-22 A | 09-Feb-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.3320 | HYB Essential Defueling Safety Case | 2022-02-10 | 2022-02-10 | Hold Optioneering Workshop | 10-Feb-22 A | 10-Feb-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.4150 | HYB Essential Defueling Safety Case | 2022-02-10 | 2022-07-13 | HF Workstream - (Cost Summary) ## | 10-Feb-22 A | 13-Jul-22 A | 106 | 0 | 105 | 100% |  | Completed
ER6666LT | W209 | W209.5200 | HYB Essential Defueling Safety Case | 2022-02-10 | 2022-02-10 | Attend Defueling Order Optioneering Workshop | 10-Feb-22 A | 10-Feb-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.3320 | TOR Essential Defueling Safety Case | 2022-02-10 | 2022-02-10 | Hold Optioneering Workshop | 10-Feb-22 A | 10-Feb-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.4150 | TOR Essential Defueling Safety Case | 2022-02-10 | 2022-07-13 | HF Workstream - (Cost Summary) ## | 10-Feb-22 A | 13-Jul-22 A | 106 | 0 | 105 | 100% |  | Completed
ER6668LT | W213 | W213.5200 | TOR Essential Defueling Safety Case | 2022-02-10 | 2022-02-10 | Attend Defueling Order Optioneering Workshop | 10-Feb-22 A | 10-Feb-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1170 | HYB Essential Defueling Safety Case | 2022-02-10 | 2022-02-16 | PRC Members Review IAB Documentation | 10-Feb-22 A | 16-Feb-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.1170 | TOR Essential Defueling Safety Case | 2022-02-10 | 2022-02-16 | PRC Members Review IAB Documentation | 10-Feb-22 A | 16-Feb-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.3330 | HYB Essential Defueling Safety Case | 2022-02-11 | 2022-02-24 | Update Report Post Workshop | 11-Feb-22 A | 24-Feb-22 A | 10 | 0 | 9 | 100% |  | Completed
ER6666LT | W209 | W209.3350 | HYB Essential Defueling Safety Case | 2022-02-11 | 2022-02-24 | Define Case Production Scope (RFS) | 11-Feb-22 A | 24-Feb-22 A | 10 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.4110 | HYB Essential Defueling Safety Case | 2022-02-11 | 2022-04-01 | Review Existing Documentation | 11-Feb-22 A | 01-Apr-22 A | 5 | 0 | 36 | 100% |  | Completed
ER6668LT | W213 | W213.3330 | TOR Essential Defueling Safety Case | 2022-02-11 | 2022-02-24 | Update Report Post Workshop | 11-Feb-22 A | 24-Feb-22 A | 10 | 0 | 9 | 100% |  | Completed
ER6668LT | W213 | W213.3350 | TOR Essential Defueling Safety Case | 2022-02-11 | 2022-02-24 | Define Case Production Scope (RFS) | 11-Feb-22 A | 24-Feb-22 A | 10 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.4110 | TOR Essential Defueling Safety Case | 2022-02-11 | 2022-04-01 | Review Existing Documentation | 11-Feb-22 A | 01-Apr-22 A | 5 | 0 | 36 | 100% |  | Completed
ER6666LT | W209 | W209.3910 | HYB Essential Defueling Safety Case | 2022-02-14 | 2022-02-18 | Release and Respond to Comments | 14-Feb-22 A | 18-Feb-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.3910 | TOR Essential Defueling Safety Case | 2022-02-14 | 2022-02-18 | Release and Respond to Comments | 14-Feb-22 A | 18-Feb-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.5010 | HYB Essential Defueling Safety Case |  | 2022-02-15 | HOLD POINT 1 - Nuclear Safety Issues Identified | 15-Feb-22 A | 15-Feb-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.5010 | TOR Essential Defueling Safety Case |  | 2022-02-15 | HOLD POINT 1 - Nuclear Safety Issues Identified | 15-Feb-22 A | 15-Feb-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.3680 | HYB Essential Defueling Safety Case | 2022-02-15 | 2022-03-01 | Specify Flow Induced Vibration EAN Scope for Delivery | 15-Feb-22 A | 01-Mar-22 A | 10 | 0 | 11 | 100% |  | Completed
ER6668LT | W213 | W213.3680 | TOR Essential Defueling Safety Case | 2022-02-15 | 2022-03-01 | Specify Flow Induced Vibration EAN Scope for Delivery | 15-Feb-22 A | 01-Mar-22 A | 10 | 0 | 11 | 100% |  | Completed
ER6666LT | W209 | W209.5060 | HYB Essential Defueling Safety Case | 2022-02-16 | 2022-04-01 | Review Legacy Assessments & Determine Future Assessments Required | 16-Feb-22 A | 01-Apr-22 A | 43 | 0 | 32 | 100% |  | Completed
ER6370LT | W201 | W201.1570 | HNB Reactors Shutdown Essential Safety Cases |  |  | Cat 1 Proposal Updates Authoring | 16-Feb-22 A | 25-Feb-22 A | 0 | 0 | 7 | 100% |  | Completed
ER6668LT | W213 | W213.5060 | TOR Essential Defueling Safety Case | 2022-02-16 | 2022-04-01 | Review Legacy Assessments & Determine Future Assessments Required | 16-Feb-22 A | 01-Apr-22 A | 43 | 0 | 32 | 100% |  | Completed
ER6650LT | W226 | W226.A24320 | HYA Fuel Handling Essential Safety Case | 2022-02-18 | 2023-05-12 | Technical Review of Living Safety Document EAN | 18-Feb-22 A | 25-Mar-24 A | 3 | 0 | 528 | 100% |  | Completed
ER6378LT | W222 | W222.A24320 | HRA Fuel Handling Essential Safety Case | 2022-02-18 | 2023-05-12 | Technical Review of Living Safety Document EAN | 18-Feb-22 A | 25-Mar-24 A | 3 | 0 | 528 | 100% |  | Completed
ER6666LT | W209 | W209.5860 | HYB Essential Defueling Safety Case | 2022-02-21 | 2022-02-25 | Prepare Spec for Pressure Boundary Integrity of Seals Report EAN | 21-Feb-22 A | 25-Feb-22 A | 5 | 0 | 4 | 100% |  | Completed
ER6666LT | W209 | W209.6850 | HYB Essential Defueling Safety Case | 2022-02-21 | 2022-02-25 | Prepare Spec for Reactor Pressure Boundary Seals Integrity (Tech Report) | 21-Feb-22 A | 25-Feb-22 A | 5 | 0 | 4 | 100% |  | Completed
ER6668LT | W213 | W213.5860 | TOR Essential Defueling Safety Case | 2022-02-21 | 2022-02-25 | Prepare Spec for Pressure Boundary Integrity of Seals Report EAN | 21-Feb-22 A | 25-Feb-22 A | 5 | 0 | 4 | 100% |  | Completed
ER6668LT | W213 | W213.6850 | TOR Essential Defueling Safety Case | 2022-02-21 | 2022-02-25 | Prepare Spec for Reactor Pressure Boundary Seals Integrity (Tech Report) | 21-Feb-22 A | 25-Feb-22 A | 5 | 0 | 4 | 100% |  | Completed
ER6666LT | W209 | W209.5220 | HYB Essential Defueling Safety Case | 2022-02-21 | 2022-03-03 | Generate Schedule of Seals Tasksheet | 21-Feb-22 A | 03-Mar-22 A | 9 | 0 | 9 | 100% |  | Completed
ER6668LT | W213 | W213.5220 | TOR Essential Defueling Safety Case | 2022-02-21 | 2022-03-03 | Generate Schedule of Seals Tasksheet | 21-Feb-22 A | 03-Mar-22 A | 9 | 0 | 9 | 100% |  | Completed
ER6666LT | W209 | W209.1056 | HYB Essential Defueling Safety Case |  | 2022-02-22 | Gate A - PRC Paper Approval (HYB) | 22-Feb-22 A | 22-Feb-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1056 | TOR Essential Defueling Safety Case |  | 2022-02-22 | Gate A - PRC Paper Approval (TOR) | 22-Feb-22 A | 22-Feb-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1180 | HYB Essential Defueling Safety Case | 2022-02-22 | 2022-02-22 | Hold PRC Meeting | 22-Feb-22 A | 22-Feb-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.1180 | TOR Essential Defueling Safety Case | 2022-02-22 | 2022-02-22 | Hold PRC Meeting | 22-Feb-22 A | 22-Feb-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.1190 | HYB Essential Defueling Safety Case |  | 2022-02-22 | Gate A PRC Paper Approval | 22-Feb-22 A | 22-Feb-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1190 | TOR Essential Defueling Safety Case |  | 2022-02-22 | Gate A PRC Paper Approval | 22-Feb-22 A | 22-Feb-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1210 | HYB Essential Defueling Safety Case | 2022-02-23 | 2022-02-23 | Modify PRC Paper as Required | 23-Feb-22 A | 23-Feb-22 A | 22 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1200 | HYB Essential Defueling Safety Case | 2022-02-23 | 2022-02-23 | Modify Estimate, Schedule & Risk Log as Required | 23-Feb-22 A | 23-Feb-22 A | 22 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.3930 | HYB Essential Defueling Safety Case | 2022-02-23 | 2022-02-23 | PJB (All Attendees) | 23-Feb-22 A | 23-Feb-22 A | 5 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.5320 | HYB Essential Defueling Safety Case | 2022-02-23 | 2022-03-01 | Pre-Job Brief of Previous Lessons Learned (DNB) | 23-Feb-22 A | 01-Mar-22 A | 1 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.1210 | TOR Essential Defueling Safety Case | 2022-02-23 | 2022-02-23 | Modify PRC Paper as Required | 23-Feb-22 A | 23-Feb-22 A | 22 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1200 | TOR Essential Defueling Safety Case | 2022-02-23 | 2022-02-23 | Modify Estimate, Schedule & Risk Log as Required | 23-Feb-22 A | 23-Feb-22 A | 22 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.3930 | TOR Essential Defueling Safety Case | 2022-02-23 | 2022-02-23 | PJB (All Attendees) | 23-Feb-22 A | 23-Feb-22 A | 5 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.5320 | TOR Essential Defueling Safety Case | 2022-02-23 | 2022-03-01 | Pre-Job Brief of Previous Lessons Learned (DNB) | 23-Feb-22 A | 01-Mar-22 A | 1 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.3340 | HYB Essential Defueling Safety Case | 2022-02-25 | 2022-05-03 | Verify Report Post Workshop | 25-Feb-22 A | 03-May-22 A | 10 | 0 | 45 | 100% |  | Completed
ER6370LT | W201 | W201.1580 | HNB Reactors Shutdown Essential Safety Cases |  |  | AMS Milestone - Ready for Review | 25-Feb-22 A | 25-Feb-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.3340 | TOR Essential Defueling Safety Case | 2022-02-25 | 2022-05-03 | Verify Report Post Workshop | 25-Feb-22 A | 03-May-22 A | 10 | 0 | 45 | 100% |  | Completed
ER6666LT | W209 | W209.4160 | HYB Essential Defueling Safety Case | 2022-02-25 | 2022-03-08 | Approve & Issue RFS / Task Sheet | 25-Feb-22 A | 08-Mar-22 A | 10 | 0 | 8 | 100% |  | Completed
ER6668LT | W213 | W213.4160 | TOR Essential Defueling Safety Case | 2022-02-25 | 2022-03-08 | Approve & Issue RFS / Task Sheet | 25-Feb-22 A | 08-Mar-22 A | 10 | 0 | 8 | 100% |  | Completed
ER6666LT | W209 | W209.5870 | HYB Essential Defueling Safety Case | 2022-02-28 | 2022-03-03 | Prepare Task Sheet for Pressure Boundary Integrity of Seals Report EAN | 28-Feb-22 A | 03-Mar-22 A | 10 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.6860 | HYB Essential Defueling Safety Case | 2022-02-28 | 2022-03-03 | Prepare Task Sheet for Reactor Pressure Boundary Seals Integrity (Tech Report) | 28-Feb-22 A | 03-Mar-22 A | 10 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | W201.1590 | HNB Reactors Shutdown Essential Safety Cases |  |  | Verification (Lead Verifier) | 28-Feb-22 A | 14-Mar-22 A | 1 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.5870 | TOR Essential Defueling Safety Case | 2022-02-28 | 2022-03-03 | Prepare Task Sheet for Pressure Boundary Integrity of Seals Report EAN | 28-Feb-22 A | 03-Mar-22 A | 10 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.6860 | TOR Essential Defueling Safety Case | 2022-02-28 | 2022-03-03 | Prepare Task Sheet for Reactor Pressure Boundary Seals Integrity (Tech Report) | 28-Feb-22 A | 03-Mar-22 A | 10 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.4180 | HYB Essential Defueling Safety Case | 2022-03-01 | 2022-04-22 | Supplier Generates Task Sheet | 01-Mar-22 A | 22-Apr-22 A | 10 | 0 | 36 | 100% |  | Completed
ER6666LT | W209 | W209.5170 | HYB Essential Defueling Safety Case | 2022-03-01 | 2022-05-13 | Defuelling Order / Fuel Management - De-risking scope - (Cost Summary) ## | 01-Mar-22 A | 13-Jul-22 A | 69 | 0 | 92 | 100% |  | Completed
ER6666LT | W209 | W209.5560 | HYB Essential Defueling Safety Case | 2022-03-01 | 2022-03-15 | Prepare Spec for Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 01-Mar-22 A | 15-Mar-22 A | 5 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.5590 | HYB Essential Defueling Safety Case | 2022-03-01 | 2022-03-15 | Prepare Spec for Review of flux detector suitability EAN | 01-Mar-22 A | 15-Mar-22 A | 5 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.5620 | HYB Essential Defueling Safety Case | 2022-03-01 | 2022-03-15 | Prepare Spec for Boron Bead Injection Feasibility & Control Rod Isolation EAN | 01-Mar-22 A | 15-Mar-22 A | 5 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.8290 | HYB Essential Defueling Safety Case | 2022-03-01 | 2022-03-04 | Prepare Spec for FPU Maintenance Analysis EAN | 01-Mar-22 A | 04-Mar-22 A | 5 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.8480 | HYB Essential Defueling Safety Case | 2022-03-01 | 2022-03-15 | Prepare Spec for Define Nuclear Data (PANTHER Validation Calcs) EAN | 01-Mar-22 A | 15-Mar-22 A | 5 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.8520 | HYB Essential Defueling Safety Case | 2022-03-01 | 2022-03-15 | Prepare Spec for PANTHER SCM Assessments - Agree Defuelling Order | 01-Mar-22 A | 15-Mar-22 A | 5 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.4180 | TOR Essential Defueling Safety Case | 2022-03-01 | 2022-04-22 | Supplier Generates Task Sheet | 01-Mar-22 A | 22-Apr-22 A | 10 | 0 | 36 | 100% |  | Completed
ER6668LT | W213 | W213.5170 | TOR Essential Defueling Safety Case | 2022-03-01 | 2022-05-13 | Defuelling Order / Fuel Management - De-risking scope - (Cost Summary) ## | 01-Mar-22 A | 13-Jul-22 A | 69 | 0 | 92 | 100% |  | Completed
ER6668LT | W213 | W213.5560 | TOR Essential Defueling Safety Case | 2022-03-01 | 2022-03-15 | Prepare Spec for Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 01-Mar-22 A | 15-Mar-22 A | 5 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.5590 | TOR Essential Defueling Safety Case | 2022-03-01 | 2022-03-15 | Prepare Spec for Review of flux detector suitability EAN | 01-Mar-22 A | 15-Mar-22 A | 5 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.5620 | TOR Essential Defueling Safety Case | 2022-03-01 | 2022-03-15 | Prepare Spec for Boron Bead Injection Feasibility & Control Rod Isolation EAN | 01-Mar-22 A | 15-Mar-22 A | 5 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.8290 | TOR Essential Defueling Safety Case | 2022-03-01 | 2022-03-04 | Prepare Spec for FPU Maintenance Analysis EAN | 01-Mar-22 A | 04-Mar-22 A | 5 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.8480 | TOR Essential Defueling Safety Case | 2022-03-01 | 2022-03-15 | Prepare Spec for Define Nuclear Data (PANTHER Validation Calcs) EAN | 01-Mar-22 A | 15-Mar-22 A | 5 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.8520 | TOR Essential Defueling Safety Case | 2022-03-01 | 2022-03-15 | Prepare Spec for PANTHER SCM Assessments - Agree Defuelling Order | 01-Mar-22 A | 15-Mar-22 A | 5 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.4370 | HYB Essential Defueling Safety Case | 2022-03-01 | 2022-03-07 | Generate Review of Protection Systems EANTask Sheet | 01-Mar-22 A | 07-Mar-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.5340 | HYB Essential Defueling Safety Case | 2022-03-01 | 2022-04-27 | Pre-Job Brief of Previous Lessons Learned (HNB HPB) | 01-Mar-22 A | 27-Apr-22 A | 21 | 0 | 39 | 100% |  | Completed
ER6666LT | W209 | W209.5350 | HYB Essential Defueling Safety Case | 2022-03-01 | 2022-04-27 | Pre-Job Brief of Previous Lessons Learned (HRA HYA) | 01-Mar-22 A | 27-Apr-22 A | 21 | 0 | 39 | 100% |  | Completed
ER6668LT | W213 | W213.4370 | TOR Essential Defueling Safety Case | 2022-03-01 | 2022-03-07 | Generate Review of Protection Systems EANTask Sheet | 01-Mar-22 A | 07-Mar-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.5340 | TOR Essential Defueling Safety Case | 2022-03-01 | 2022-04-27 | Pre-Job Brief of Previous Lessons Learned (HNB HPB) | 01-Mar-22 A | 27-Apr-22 A | 21 | 0 | 39 | 100% |  | Completed
ER6668LT | W213 | W213.5350 | TOR Essential Defueling Safety Case | 2022-03-01 | 2022-04-27 | Pre-Job Brief of Previous Lessons Learned (HRA HYA) | 01-Mar-22 A | 27-Apr-22 A | 21 | 0 | 39 | 100% |  | Completed
ER6666LT | W209 | W209.4740 | HYB Essential Defueling Safety Case | 2022-03-02 | 2022-03-02 | Draft Summary Findings EAN | 02-Mar-22 A | 02-Mar-22 A | 10 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | W201.1680 | HNB Reactors Shutdown Essential Safety Cases |  |  | March NSC MA deadline on 2 March | 02-Mar-22 A | 02-Mar-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.4740 | TOR Essential Defueling Safety Case | 2022-03-02 | 2022-03-02 | Draft Summary Findings EAN | 02-Mar-22 A | 02-Mar-22 A | 10 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.3690 | HYB Essential Defueling Safety Case | 2022-03-02 | 2022-03-15 | TSA/EDF Best Athlete Review for Flow Induced Vibration EAN | 02-Mar-22 A | 15-Mar-22 A | 10 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.3940 | HYB Essential Defueling Safety Case | 2022-03-02 | 2022-03-03 | Optioneering Workshop | 02-Mar-22 A | 03-Mar-22 A | 2 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.4350 | HYB Essential Defueling Safety Case | 2022-03-02 | 2022-03-15 | Technical Review | 02-Mar-22 A | 15-Mar-22 A | 10 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.4480 | HYB Essential Defueling Safety Case | 2022-03-02 | 2022-03-04 | Incorporate Defueling Assumptions List into PDD | 02-Mar-22 A | 04-Mar-22 A | 5 | 0 | 2 | 100% |  | Completed
ER6668LT | W213 | W213.3690 | TOR Essential Defueling Safety Case | 2022-03-02 | 2022-03-15 | TSA/EDF Best Athlete Review for Flow Induced Vibration EAN | 02-Mar-22 A | 15-Mar-22 A | 10 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.3940 | TOR Essential Defueling Safety Case | 2022-03-02 | 2022-03-03 | Optioneering Workshop | 02-Mar-22 A | 03-Mar-22 A | 2 | 0 | 2 | 100% |  | Completed
ER6668LT | W213 | W213.4350 | TOR Essential Defueling Safety Case | 2022-03-02 | 2022-03-15 | Technical Review | 02-Mar-22 A | 15-Mar-22 A | 10 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.4480 | TOR Essential Defueling Safety Case | 2022-03-02 | 2022-03-04 | Incorporate Defueling Assumptions List into PDD | 02-Mar-22 A | 04-Mar-22 A | 5 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.4750 | HYB Essential Defueling Safety Case | 2022-03-03 | 2022-04-26 | Verify EAN | 03-Mar-22 A | 26-Apr-22 A | 10 | 0 | 36 | 100% |  | Completed
ER6668LT | W213 | W213.4750 | TOR Essential Defueling Safety Case | 2022-03-03 | 2022-04-26 | Verify EAN | 03-Mar-22 A | 26-Apr-22 A | 10 | 0 | 36 | 100% |  | Completed
ER6666LT | W209 | W209.5090 | HYB Essential Defueling Safety Case | 2022-03-03 | 2022-03-07 | Recieve EDF Comments on Skeleton Document | 03-Mar-22 A | 07-Mar-22 A | 10 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.5090 | TOR Essential Defueling Safety Case | 2022-03-03 | 2022-03-07 | Recieve EDF Comments on Skeleton Document | 03-Mar-22 A | 07-Mar-22 A | 10 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.3250 | HYB Essential Defueling Safety Case |  | 2022-03-04 | >>>OUTGOING ENABLER (W150) Assumption List Complete (within PDD) | 04-Mar-22 A | 04-Mar-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.5880 | HYB Essential Defueling Safety Case | 2022-03-04 | 2022-03-17 | Approve Task Sheet for Pressure Boundary Integrity of Seals Report EAN | 04-Mar-22 A | 17-Mar-22 A | 7 | 0 | 9 | 100% |  | Completed
ER6666LT | W209 | W209.6870 | HYB Essential Defueling Safety Case | 2022-03-04 | 2022-03-17 | Approve Task Sheet for Reactor Pressure Boundary Seals Integrity (Tech Report) | 04-Mar-22 A | 17-Mar-22 A | 7 | 0 | 9 | 100% |  | Completed
ER6668LT | W213 | W213.3250 | TOR Essential Defueling Safety Case |  | 2022-03-04 | >>>OUTGOING ENABLER (W150) Assumption List Complete (within PDD) | 04-Mar-22 A | 04-Mar-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.5880 | TOR Essential Defueling Safety Case | 2022-03-04 | 2022-03-17 | Approve Task Sheet for Pressure Boundary Integrity of Seals Report EAN | 04-Mar-22 A | 17-Mar-22 A | 7 | 0 | 9 | 100% |  | Completed
ER6668LT | W213 | W213.6870 | TOR Essential Defueling Safety Case | 2022-03-04 | 2022-03-17 | Approve Task Sheet for Reactor Pressure Boundary Seals Integrity (Tech Report) | 04-Mar-22 A | 17-Mar-22 A | 7 | 0 | 9 | 100% |  | Completed
ER6666LT | W209 | W209.3950 | HYB Essential Defueling Safety Case | 2022-03-04 | 2022-03-22 | Update Report Post Workshop | 04-Mar-22 A | 22-Mar-22 A | 5 | 0 | 12 | 100% |  | Completed
ER6666LT | W209 | W209.5230 | HYB Essential Defueling Safety Case | 2022-03-04 | 2022-04-28 | PJB & Generate Schedule of Seals | 04-Mar-22 A | 28-Apr-22 A | 10 | 0 | 37 | 100% |  | Completed
ER6668LT | W213 | W213.3950 | TOR Essential Defueling Safety Case | 2022-03-04 | 2022-03-22 | Update Report Post Workshop | 04-Mar-22 A | 22-Mar-22 A | 5 | 0 | 12 | 100% |  | Completed
ER6668LT | W213 | W213.5230 | TOR Essential Defueling Safety Case | 2022-03-04 | 2022-04-28 | PJB & Generate Schedule of Seals | 04-Mar-22 A | 28-Apr-22 A | 10 | 0 | 37 | 100% |  | Completed
ER6666LT | W209 | W209.7580 | HYB Essential Defueling Safety Case | 2022-03-07 | 2022-03-07 | PJB for Review of Protection Systems EAN | 07-Mar-22 A | 07-Mar-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.8300 | HYB Essential Defueling Safety Case | 2022-03-07 | 2022-03-11 | Prepare Task Sheet for FPU Maintenance Analysis EAN | 07-Mar-22 A | 11-Mar-22 A | 10 | 0 | 4 | 100% |  | Completed
ER6668LT | W213 | W213.7580 | TOR Essential Defueling Safety Case | 2022-03-07 | 2022-03-07 | PJB for Review of Protection Systems EAN | 07-Mar-22 A | 07-Mar-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.8300 | TOR Essential Defueling Safety Case | 2022-03-07 | 2022-03-11 | Prepare Task Sheet for FPU Maintenance Analysis EAN | 07-Mar-22 A | 11-Mar-22 A | 10 | 0 | 4 | 100% |  | Completed
ER6666LT | W209 | W209.7590 | HYB Essential Defueling Safety Case | 2022-03-08 | 2022-05-17 | Issue FM Load Protection EAN | 08-Mar-22 A | 17-May-22 A | 1 | 0 | 48 | 100% |  | Completed
ER6668LT | W213 | W213.7590 | TOR Essential Defueling Safety Case | 2022-03-08 | 2022-05-17 | Issue FM Load Protection EAN | 08-Mar-22 A | 17-May-22 A | 1 | 0 | 48 | 100% |  | Completed
ER6666LT | W209 | W209.5100 | HYB Essential Defueling Safety Case | 2022-03-08 | 2022-03-11 | Meeting to Discuss Skeleton Document & Recommendations | 08-Mar-22 A | 11-Mar-22 A | 4 | 0 | 4 | 100% |  | Completed
ER6668LT | W213 | W213.5100 | TOR Essential Defueling Safety Case | 2022-03-08 | 2022-03-11 | Meeting to Discuss Skeleton Document & Recommendations | 08-Mar-22 A | 11-Mar-22 A | 4 | 0 | 4 | 100% |  | Completed
ER6666LT | W209 | W209.4170 | HYB Essential Defueling Safety Case |  | 2022-03-08 | RFS Issued | 08-Mar-22 A | 08-Mar-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.4170 | TOR Essential Defueling Safety Case |  | 2022-03-08 | RFS Issued | 08-Mar-22 A | 08-Mar-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | W201.1600 | HNB Reactors Shutdown Essential Safety Cases |  |  | Nuclear Safety Specialist Assessment HNB | 12-Mar-22 A | 14-Mar-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | W201.1610 | HNB Reactors Shutdown Essential Safety Cases |  |  | Nuclear Safety Specialist Assessment HPB | 12-Mar-22 A | 14-Mar-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7520 | HYB Essential Defueling Safety Case | 2022-03-14 | 2022-04-01 | Prepare Spec for Cooling Plant Availability Review EAN | 14-Mar-22 A | 01-Apr-22 A | 5 | 0 | 15 | 100% |  | Completed
ER6666LT | W209 | W209.7550 | HYB Essential Defueling Safety Case | 2022-03-14 | 2022-04-01 | Prepare Spec for Cooling Plant OPEX Study EAN | 14-Mar-22 A | 01-Apr-22 A | 5 | 0 | 15 | 100% |  | Completed
ER6370LT | W201 | W201.1620 | HNB Reactors Shutdown Essential Safety Cases |  |  | CO Endorsed | 14-Mar-22 A | 14-Mar-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | W201.1630 | HNB Reactors Shutdown Essential Safety Cases |  |  | Stn RE Endorsed | 14-Mar-22 A | 14-Mar-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | W201.1640 | HNB Reactors Shutdown Essential Safety Cases |  |  | Lead INA assessor | 14-Mar-22 A | 27-Apr-22 A | 20 | 0 | 30 | 100% |  | Completed
ER6666LT | W209 | W209.8310 | HYB Essential Defueling Safety Case | 2022-03-14 | 2022-03-28 | Approve Task Sheet for FPU Maintenance Analysis EAN | 14-Mar-22 A | 28-Mar-22 A | 7 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.7520 | TOR Essential Defueling Safety Case | 2022-03-14 | 2022-04-01 | Prepare Spec for Cooling Plant Availability Review EAN | 14-Mar-22 A | 01-Apr-22 A | 5 | 0 | 15 | 100% |  | Completed
ER6668LT | W213 | W213.7550 | TOR Essential Defueling Safety Case | 2022-03-14 | 2022-04-01 | Prepare Spec for Cooling Plant OPEX Study EAN | 14-Mar-22 A | 01-Apr-22 A | 5 | 0 | 15 | 100% |  | Completed
ER6668LT | W213 | W213.8310 | TOR Essential Defueling Safety Case | 2022-03-14 | 2022-03-28 | Approve Task Sheet for FPU Maintenance Analysis EAN | 14-Mar-22 A | 28-Mar-22 A | 7 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.5110 | HYB Essential Defueling Safety Case | 2022-03-14 | 2022-03-23 | Generate Integrity Analysis Task Sheet (Atkins) | 14-Mar-22 A | 23-Mar-22 A | 5 | 0 | 7 | 100% |  | Completed
ER6668LT | W213 | W213.5110 | TOR Essential Defueling Safety Case | 2022-03-14 | 2022-03-23 | Generate Integrity Analysis Task Sheet (Atkins) | 14-Mar-22 A | 23-Mar-22 A | 5 | 0 | 7 | 100% |  | Completed
ER6666LT | W209 | W209.4400 | HYB Essential Defueling Safety Case | 2022-03-16 | 2022-04-01 | Draft Scope for Case Production | 16-Mar-22 A | 01-Apr-22 A | 10 | 0 | 12 | 100% |  | Completed
ER6666LT | W209 | W209.5570 | HYB Essential Defueling Safety Case | 2022-03-16 | 2022-03-28 | Prepare Task Sheet for Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 16-Mar-22 A | 28-Mar-22 A | 10 | 0 | 8 | 100% |  | Completed
ER6666LT | W209 | W209.5600 | HYB Essential Defueling Safety Case | 2022-03-16 | 2022-03-28 | Prepare Task Sheet for Review of flux detector suitability EAN | 16-Mar-22 A | 28-Mar-22 A | 10 | 0 | 8 | 100% |  | Completed
ER6666LT | W209 | W209.5630 | HYB Essential Defueling Safety Case | 2022-03-16 | 2022-03-28 | Prepare Task Sheet for Boron Bead Injection Feasibility & Control Rod Isolation EAN | 16-Mar-22 A | 28-Mar-22 A | 10 | 0 | 8 | 100% |  | Completed
ER6666LT | W209 | W209.7670 | HYB Essential Defueling Safety Case | 2022-03-16 | 2022-03-16 | Prepare Spec for Flow Induced Vibration EAN | 16-Mar-22 A | 16-Mar-22 A | 5 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.8490 | HYB Essential Defueling Safety Case | 2022-03-16 | 2022-03-28 | Prepare Task Sheet for Define Nuclear Data (PANTHER Validation Calcs) EAN | 16-Mar-22 A | 28-Mar-22 A | 10 | 0 | 8 | 100% |  | Completed
ER6666LT | W209 | W209.8530 | HYB Essential Defueling Safety Case | 2022-03-16 | 2022-03-28 | Prepare Task Sheet for PANTHER SCM Assessments - Agree Defuelling Order | 16-Mar-22 A | 28-Mar-22 A | 10 | 0 | 8 | 100% |  | Completed
ER6668LT | W213 | W213.4400 | TOR Essential Defueling Safety Case | 2022-03-16 | 2022-04-01 | Draft Scope for Case Production | 16-Mar-22 A | 01-Apr-22 A | 10 | 0 | 12 | 100% |  | Completed
ER6668LT | W213 | W213.5570 | TOR Essential Defueling Safety Case | 2022-03-16 | 2022-03-28 | Prepare Task Sheet for Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 16-Mar-22 A | 28-Mar-22 A | 10 | 0 | 8 | 100% |  | Completed
ER6668LT | W213 | W213.5600 | TOR Essential Defueling Safety Case | 2022-03-16 | 2022-03-28 | Prepare Task Sheet for Review of flux detector suitability EAN | 16-Mar-22 A | 28-Mar-22 A | 10 | 0 | 8 | 100% |  | Completed
ER6668LT | W213 | W213.5630 | TOR Essential Defueling Safety Case | 2022-03-16 | 2022-03-28 | Prepare Task Sheet for Boron Bead Injection Feasibility & Control Rod Isolation EAN | 16-Mar-22 A | 28-Mar-22 A | 10 | 0 | 8 | 100% |  | Completed
ER6668LT | W213 | W213.7670 | TOR Essential Defueling Safety Case | 2022-03-16 | 2022-03-16 | Prepare Spec for Flow Induced Vibration EAN | 16-Mar-22 A | 16-Mar-22 A | 5 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.8490 | TOR Essential Defueling Safety Case | 2022-03-16 | 2022-03-28 | Prepare Task Sheet for Define Nuclear Data (PANTHER Validation Calcs) EAN | 16-Mar-22 A | 28-Mar-22 A | 10 | 0 | 8 | 100% |  | Completed
ER6668LT | W213 | W213.8530 | TOR Essential Defueling Safety Case | 2022-03-16 | 2022-03-28 | Prepare Task Sheet for PANTHER SCM Assessments - Agree Defuelling Order | 16-Mar-22 A | 28-Mar-22 A | 10 | 0 | 8 | 100% |  | Completed
ER6666LT | W209 | W209.3790 | HYB Essential Defueling Safety Case | 2022-03-17 | 2022-03-17 | TSA/EDF Best Athlete Review for PCPV Integrity Justification (Civils Internal Resource) | 17-Mar-22 A | 17-Mar-22 A | 10 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.3840 | HYB Essential Defueling Safety Case | 2022-03-17 | 2022-03-17 | Iteration of Scope for Seismic Assessment | 17-Mar-22 A | 17-Mar-22 A | 10 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.3850 | HYB Essential Defueling Safety Case | 2022-03-17 | 2022-03-17 | TSA/EDF Best Athlete Review for Seismic Assessment (Civils Internal Resource) | 17-Mar-22 A | 17-Mar-22 A | 10 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.4230 | HYB Essential Defueling Safety Case | 2022-03-17 | 2022-03-17 | Iteration of Scope for PCPV Integrity Justification | 17-Mar-22 A | 17-Mar-22 A | 10 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7680 | HYB Essential Defueling Safety Case | 2022-03-17 | 2022-03-21 | Prepare Task Sheet for Flow Induced Vibration EAN | 17-Mar-22 A | 21-Mar-22 A | 10 | 0 | 2 | 100% |  | Completed
ER6668LT | W213 | W213.3790 | TOR Essential Defueling Safety Case | 2022-03-17 | 2022-03-17 | TSA/EDF Best Athlete Review for PCPV Integrity Justification (Civils Internal Resource) | 17-Mar-22 A | 17-Mar-22 A | 10 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.3840 | TOR Essential Defueling Safety Case | 2022-03-17 | 2022-03-17 | Iteration of Scope for Seismic Assessment | 17-Mar-22 A | 17-Mar-22 A | 10 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.3850 | TOR Essential Defueling Safety Case | 2022-03-17 | 2022-03-17 | TSA/EDF Best Athlete Review for Seismic Assessment (Civils Internal Resource) | 17-Mar-22 A | 17-Mar-22 A | 10 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.4230 | TOR Essential Defueling Safety Case | 2022-03-17 | 2022-03-17 | Iteration of Scope for PCPV Integrity Justification | 17-Mar-22 A | 17-Mar-22 A | 10 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.7680 | TOR Essential Defueling Safety Case | 2022-03-17 | 2022-03-21 | Prepare Task Sheet for Flow Induced Vibration EAN | 17-Mar-22 A | 21-Mar-22 A | 10 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.A26180 | HYB Essential Defueling Safety Case | 2022-03-18 | 2022-06-01 | Pre Job Brief for Pressure Boundary Integrity of Seals Report EAN | 18-Mar-22 A | 01-Jun-22 A | 0 | 0 | 51 | 100% |  | Completed
ER6666LT | W209 | W209.A29300 | HYB Essential Defueling Safety Case | 2022-03-18 | 2022-05-20 | Mid Job Brief for Reactor Pressure Boundary Seals Integrity (Tech Report) | 18-Mar-22 A | 20-May-22 A | 0 | 0 | 43 | 100% |  | Completed
ER6666LT | W209 | W209.28770 | HYB Essential Defueling Safety Case |  |  | Production of Civils Assessment Report for PCPV Integrity Justification (A-B De-risk) | 18-Mar-22 A | 13-Jul-22 A | 1 | 0 | 78 | 100% |  | Completed
ER6666LT | W209 | W209.28780 | HYB Essential Defueling Safety Case |  |  | Production of Civils Assessment Report for Seismic Assessment (A-B De-risk) | 18-Mar-22 A | 13-Jul-22 A | 40 | 0 | 78 | 100% |  | Completed
ER6668LT | W213 | W213.A26180 | TOR Essential Defueling Safety Case | 2022-03-18 | 2022-06-01 | Pre Job Brief for Pressure Boundary Integrity of Seals Report EAN | 18-Mar-22 A | 01-Jun-22 A | 0 | 0 | 51 | 100% |  | Completed
ER6668LT | W213 | W213.A29300 | TOR Essential Defueling Safety Case | 2022-03-18 | 2022-05-20 | Mid Job Brief for Reactor Pressure Boundary Seals Integrity (Tech Report) | 18-Mar-22 A | 20-May-22 A | 0 | 0 | 43 | 100% |  | Completed
ER6668LT | W213 | W213.28770 | TOR Essential Defueling Safety Case |  |  | Production of Civils Assessment Report for PCPV Integrity Justification (A-B De-risk) | 18-Mar-22 A | 13-Jul-22 A | 1 | 0 | 78 | 100% |  | Completed
ER6668LT | W213 | W213.28780 | TOR Essential Defueling Safety Case |  |  | Production of Civils Assessment Report for Seismic Assessment (A-B De-risk) | 18-Mar-22 A | 13-Jul-22 A | 40 | 0 | 78 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16230 | HNB Reactors Shutdown Essential Safety Cases |  | 2021-07-01 | ONR Agree/Acknowledge Safety Case EC 364023 <NSRS SC Approach & Outline> (Cat 1 MS) (HNB)(Reactor Shutdown Essential SC) | 21-Mar-22 A | 21-Mar-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17570 | HNB Reactors Shutdown Essential Safety Cases |  |  | >>>OUTGOING ENABLER (W104, W153 HNB Security Plan) ONR Approved | 21-Mar-22 A | 21-Mar-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18430 | HNB Reactors Shutdown Essential Safety Cases |  |  | >>>INCOMING ENABLER (W221) HNB Fuel Handling Essential Safety Case ONR Approved | 21-Mar-22 A | 21-Mar-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18440 | HNB Reactors Shutdown Essential Safety Cases |  |  | >>>MIRROR OF INCOMING ENABLER (W221) HNB Fuel Handling Essential Safety Case ONR Approved | 21-Mar-22 A | 21-Mar-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16240 | HNB Reactors Shutdown Essential Safety Cases |  |  | Station Approval Period | 21-Mar-22 A | 24-Mar-22 A | 10 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18450 | HNB Reactors Shutdown Essential Safety Cases |  |  | >>> INTERFACE MILESTONE (W221) HNB Fuel Handling Essential Safety Case ONR Approved | 21-Mar-22 A | 21-Mar-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7690 | HYB Essential Defueling Safety Case | 2022-03-22 | 2022-03-23 | Approve Task Sheet for Flow Induced Vibration EAN | 22-Mar-22 A | 23-Mar-22 A | 7 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.7690 | TOR Essential Defueling Safety Case | 2022-03-22 | 2022-03-23 | Approve Task Sheet for Flow Induced Vibration EAN | 22-Mar-22 A | 23-Mar-22 A | 7 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.3960 | HYB Essential Defueling Safety Case | 2022-03-23 | 2022-05-24 | Verify Report Post Workshop | 23-Mar-22 A | 24-May-22 A | 15 | 0 | 42 | 100% |  | Completed
ER6666LT | W209 | W209.3970 | HYB Essential Defueling Safety Case | 2022-03-23 | 2022-04-01 | Define Case Production Scope (RFS) | 23-Mar-22 A | 01-Apr-22 A | 15 | 0 | 7 | 100% |  | Completed
ER6370LT | W201 | W201.1690 | HNB Reactors Shutdown Essential Safety Cases |  |  | March NSC Meeting on 23 March (pm) | 23-Mar-22 A | 23-Mar-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.3960 | TOR Essential Defueling Safety Case | 2022-03-23 | 2022-05-24 | Verify Report Post Workshop | 23-Mar-22 A | 24-May-22 A | 15 | 0 | 42 | 100% |  | Completed
ER6668LT | W213 | W213.3970 | TOR Essential Defueling Safety Case | 2022-03-23 | 2022-04-01 | Define Case Production Scope (RFS) | 23-Mar-22 A | 01-Apr-22 A | 15 | 0 | 7 | 100% |  | Completed
ER6370LT | W201 | ER6370.A16220 | HNB Reactors Shutdown Essential Safety Cases |  | 2021-07-01 | HNB Shutdown Reactor Essential Safety Case Approved | 24-Mar-22 A | 24-Mar-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18400 | HNB Reactors Shutdown Essential Safety Cases |  |  | >>>OUTGOING ENABLER (W283) CAT 1 Reactors Shutdown SC Station Approved | 24-Mar-22 A | 24-Mar-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A29530 | HYB Essential Defueling Safety Case | 2022-03-24 | 2022-04-04 | Pre Job Brief for Flow Induced Vibration EAN | 24-Mar-22 A | 04-Apr-22 A | 0 | 0 | 8 | 100% |  | Completed
ER6666LT | W209 | W209.7850 | HYB Essential Defueling Safety Case | 2022-03-24 | 2022-03-24 | Prepare Spec for FPU Integrity Work EAN EAN | 24-Mar-22 A | 24-Mar-22 A | 5 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7860 | HYB Essential Defueling Safety Case | 2022-03-24 | 2022-03-24 | Prepare Task Sheet for FPU Integrity Work EAN | 24-Mar-22 A | 24-Mar-22 A | 10 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7870 | HYB Essential Defueling Safety Case | 2022-03-24 | 2022-03-24 | Approve Task Sheet for FPU Integrity Work EAN | 24-Mar-22 A | 24-Mar-22 A | 7 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A29530 | TOR Essential Defueling Safety Case | 2022-03-24 | 2022-04-04 | Pre Job Brief for Flow Induced Vibration EAN | 24-Mar-22 A | 04-Apr-22 A | 0 | 0 | 8 | 100% |  | Completed
ER6668LT | W213 | W213.7850 | TOR Essential Defueling Safety Case | 2022-03-24 | 2022-03-24 | Prepare Spec for FPU Integrity Work EAN EAN | 24-Mar-22 A | 24-Mar-22 A | 5 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.7860 | TOR Essential Defueling Safety Case | 2022-03-24 | 2022-03-24 | Prepare Task Sheet for FPU Integrity Work EAN | 24-Mar-22 A | 24-Mar-22 A | 10 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.7870 | TOR Essential Defueling Safety Case | 2022-03-24 | 2022-03-24 | Approve Task Sheet for FPU Integrity Work EAN | 24-Mar-22 A | 24-Mar-22 A | 7 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.5440 | HYB Essential Defueling Safety Case | 2022-03-25 | 2022-03-25 | Workshop Pre-reading pack sent out | 25-Mar-22 A | 25-Mar-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A29650 | HYB Essential Defueling Safety Case | 2022-03-25 | 2022-03-25 | Pre Job Brief for FPU Integrity Work EAN | 25-Mar-22 A | 25-Mar-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.5440 | TOR Essential Defueling Safety Case | 2022-03-25 | 2022-03-25 | Workshop Pre-reading pack sent out | 25-Mar-22 A | 25-Mar-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A29650 | TOR Essential Defueling Safety Case | 2022-03-25 | 2022-03-25 | Pre Job Brief for FPU Integrity Work EAN | 25-Mar-22 A | 25-Mar-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A30520 | HYB Essential Defueling Safety Case | 2022-03-28 | 2022-07-08 | Draft FPU Integrity Work EAN | 28-Mar-22 A | 11-Jul-22 A | 30 | 0 | 70 | 100% |  | Completed
ER6668LT | W213 | W213.A30520 | TOR Essential Defueling Safety Case | 2022-03-28 | 2022-07-08 | Draft FPU Integrity Work EAN | 28-Mar-22 A | 11-Jul-22 A | 30 | 0 | 70 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1580 | HNB Reactors Shutdown Essential Safety Cases | 2021-07-02 | 2021-07-15 | Revise all Affected Drawings and Documents for EC Approval (HNB) | 28-Mar-22 A | 10-Jun-22 A | 10 | 0 | 50 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1500 | HNB Reactors Shutdown Essential Safety Cases |  |  | Progress Lessons Learned Review- Station Approve EC 364023 | 28-Mar-22 A | 10-Aug-22 A | 20 | 0 | 92 | 100% |  | Completed
ER6666LT | W209 | W209.5580 | HYB Essential Defueling Safety Case | 2022-03-29 | 2022-05-03 | Approve Task Sheet for Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 29-Mar-22 A | 03-May-22 A | 7 | 0 | 23 | 100% |  | Completed
ER6666LT | W209 | W209.5610 | HYB Essential Defueling Safety Case | 2022-03-29 | 2022-05-03 | Approve Task Sheet for Review of flux detector suitability EAN | 29-Mar-22 A | 03-May-22 A | 7 | 0 | 22 | 100% |  | Completed
ER6666LT | W209 | W209.5640 | HYB Essential Defueling Safety Case | 2022-03-29 | 2022-04-29 | Approve Task Sheet for Boron Bead Injection Feasibility & Control Rod Isolation EAN | 29-Mar-22 A | 29-Apr-22 A | 7 | 0 | 21 | 100% |  | Completed
ER6666LT | W209 | W209.8500 | HYB Essential Defueling Safety Case | 2022-03-29 | 2022-05-03 | Approve Task Sheet for Define Nuclear Data (PANTHER Validation Calcs) EAN | 29-Mar-22 A | 03-May-22 A | 7 | 0 | 23 | 100% |  | Completed
ER6666LT | W209 | W209.8540 | HYB Essential Defueling Safety Case | 2022-03-29 | 2022-05-03 | Approve Task Sheet for PANTHER SCM Assessments - Agree Defuelling Order | 29-Mar-22 A | 03-May-22 A | 7 | 0 | 23 | 100% |  | Completed
ER6668LT | W213 | W213.5580 | TOR Essential Defueling Safety Case | 2022-03-29 | 2022-05-03 | Approve Task Sheet for Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 29-Mar-22 A | 03-May-22 A | 7 | 0 | 23 | 100% |  | Completed
ER6668LT | W213 | W213.5610 | TOR Essential Defueling Safety Case | 2022-03-29 | 2022-05-03 | Approve Task Sheet for Review of flux detector suitability EAN | 29-Mar-22 A | 03-May-22 A | 7 | 0 | 22 | 100% |  | Completed
ER6668LT | W213 | W213.5640 | TOR Essential Defueling Safety Case | 2022-03-29 | 2022-04-29 | Approve Task Sheet for Boron Bead Injection Feasibility & Control Rod Isolation EAN | 29-Mar-22 A | 29-Apr-22 A | 7 | 0 | 21 | 100% |  | Completed
ER6668LT | W213 | W213.8500 | TOR Essential Defueling Safety Case | 2022-03-29 | 2022-05-03 | Approve Task Sheet for Define Nuclear Data (PANTHER Validation Calcs) EAN | 29-Mar-22 A | 03-May-22 A | 7 | 0 | 23 | 100% |  | Completed
ER6668LT | W213 | W213.8540 | TOR Essential Defueling Safety Case | 2022-03-29 | 2022-05-03 | Approve Task Sheet for PANTHER SCM Assessments - Agree Defuelling Order | 29-Mar-22 A | 03-May-22 A | 7 | 0 | 23 | 100% |  | Completed
ER6666LT | W209 | W209.6880 | HYB Essential Defueling Safety Case | 2022-03-31 | 2022-03-31 | PJB - HFIP | 31-Mar-22 A | 31-Mar-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.6880 | TOR Essential Defueling Safety Case | 2022-03-31 | 2022-03-31 | PJB - HFIP | 31-Mar-22 A | 31-Mar-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7920 | HYB Essential Defueling Safety Case | 2022-04-01 | 2022-05-13 | Draft Human Factors Integration Plan EAN (REV 000) | 01-Apr-22 A | 13-May-22 A | 48 | 0 | 28 | 100% |  | Completed
ER6668LT | W213 | W213.7920 | TOR Essential Defueling Safety Case | 2022-04-01 | 2022-05-13 | Draft Human Factors Integration Plan EAN (REV 000) | 01-Apr-22 A | 13-May-22 A | 48 | 0 | 28 | 100% |  | Completed
ER6666LT | W209 | W209.1105 | HYB Essential Defueling Safety Case | 2022-04-01 | 2022-05-27 | Station comments on NSRS | 01-Apr-22 A | 27-May-22 A | 15 | 0 | 38 | 100% |  | Completed
ER6666LT | W209 | W209.5740 | HYB Essential Defueling Safety Case | 2022-04-01 | 2022-04-07 | Prepare Spec for Safety Case Requirements EAN - TASK E EAN | 01-Apr-22 A | 07-Apr-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.5890 | HYB Essential Defueling Safety Case | 2022-04-01 | 2022-04-07 | Prepare Spec for Reactor Internals & Structural Integrity During Defueling Report EAN | 01-Apr-22 A | 07-Apr-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.1105 | TOR Essential Defueling Safety Case | 2022-04-01 | 2022-05-27 | Station comments on NSRS | 01-Apr-22 A | 27-May-22 A | 15 | 0 | 38 | 100% |  | Completed
ER6668LT | W213 | W213.5740 | TOR Essential Defueling Safety Case | 2022-04-01 | 2022-04-07 | Prepare Spec for Safety Case Requirements EAN - TASK E EAN | 01-Apr-22 A | 07-Apr-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.5890 | TOR Essential Defueling Safety Case | 2022-04-01 | 2022-04-07 | Prepare Spec for Reactor Internals & Structural Integrity During Defueling Report EAN | 01-Apr-22 A | 07-Apr-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.4240 | HYB Essential Defueling Safety Case | 2022-04-04 | 2022-04-04 | Approve & Issue RFS | 04-Apr-22 A | 04-Apr-22 A | 5 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.4250 | HYB Essential Defueling Safety Case |  | 2022-04-04 | RFS Issued | 04-Apr-22 A | 04-Apr-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.4240 | TOR Essential Defueling Safety Case | 2022-04-04 | 2022-04-04 | Approve & Issue RFS | 04-Apr-22 A | 04-Apr-22 A | 5 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.4250 | TOR Essential Defueling Safety Case |  | 2022-04-04 | RFS Issued | 04-Apr-22 A | 04-Apr-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1095 | HYB Essential Defueling Safety Case | 2022-04-04 | 2022-06-01 | INA comments on NSRS | 04-Apr-22 A | 01-Jun-22 A | 15 | 0 | 40 | 100% |  | Completed
ER6666LT | W209 | W209.4770 | HYB Essential Defueling Safety Case | 2022-04-04 | 2022-04-28 | Register EC and identify Milestones in AMS EC 371387 | 04-Apr-22 A | 28-Apr-22 A | 7 | 0 | 17 | 100% |  | Completed
ER6666LT | W209 | W209.7530 | HYB Essential Defueling Safety Case | 2022-04-04 | 2022-05-03 | Prepare Task Sheet for Cooling Plant Availability Review EAN | 04-Apr-22 A | 03-May-22 A | 10 | 0 | 18 | 100% |  | Completed
ER6666LT | W209 | W209.7560 | HYB Essential Defueling Safety Case | 2022-04-04 | 2022-05-03 | Prepare Task Sheet for Cooling Plant OPEX Study EAN | 04-Apr-22 A | 03-May-22 A | 10 | 0 | 18 | 100% |  | Completed
ER6668LT | W213 | W213.1095 | TOR Essential Defueling Safety Case | 2022-04-04 | 2022-06-01 | INA comments on NSRS | 04-Apr-22 A | 01-Jun-22 A | 15 | 0 | 40 | 100% |  | Completed
ER6668LT | W213 | W213.4770 | TOR Essential Defueling Safety Case | 2022-04-04 | 2022-04-28 | Register EC and identify Milestones in AMS EC 371387 | 04-Apr-22 A | 28-Apr-22 A | 7 | 0 | 17 | 100% |  | Completed
ER6668LT | W213 | W213.7530 | TOR Essential Defueling Safety Case | 2022-04-04 | 2022-05-03 | Prepare Task Sheet for Cooling Plant Availability Review EAN | 04-Apr-22 A | 03-May-22 A | 10 | 0 | 18 | 100% |  | Completed
ER6668LT | W213 | W213.7560 | TOR Essential Defueling Safety Case | 2022-04-04 | 2022-05-03 | Prepare Task Sheet for Cooling Plant OPEX Study EAN | 04-Apr-22 A | 03-May-22 A | 10 | 0 | 18 | 100% |  | Completed
ER6666LT | W209 | W209.4260 | HYB Essential Defueling Safety Case | 2022-04-05 | 2022-04-22 | Supplier Respond to RFS | 05-Apr-22 A | 22-Apr-22 A | 10 | 0 | 11 | 100% |  | Completed
ER6668LT | W213 | W213.4260 | TOR Essential Defueling Safety Case | 2022-04-05 | 2022-04-22 | Supplier Respond to RFS | 05-Apr-22 A | 22-Apr-22 A | 10 | 0 | 11 | 100% |  | Completed
ER6666LT | W209 | W209.A29540 | HYB Essential Defueling Safety Case | 2022-04-05 | 2022-05-31 | Draft Review of Flow Induced Vibration EAN | 05-Apr-22 A | 31-May-22 A | 38 | 0 | 38 | 100% |  | Completed
ER6668LT | W213 | W213.A29540 | TOR Essential Defueling Safety Case | 2022-04-05 | 2022-05-31 | Draft Review of Flow Induced Vibration EAN | 05-Apr-22 A | 31-May-22 A | 38 | 0 | 38 | 100% |  | Completed
ER6666LT | W209 | W209.1390 | HYB Essential Defueling Safety Case | 2022-04-06 | 2022-04-06 | Confirm Objectives to be Delivered at Gate B | 06-Apr-22 A | 06-Apr-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.5450 | HYB Essential Defueling Safety Case | 2022-04-06 | 2022-04-06 | Optioneering Workshop | 06-Apr-22 A | 06-Apr-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.1390 | TOR Essential Defueling Safety Case | 2022-04-06 | 2022-04-06 | Confirm Objectives to be Delivered at Gate B | 06-Apr-22 A | 06-Apr-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.5450 | TOR Essential Defueling Safety Case | 2022-04-06 | 2022-04-06 | Optioneering Workshop | 06-Apr-22 A | 06-Apr-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.1400 | HYB Essential Defueling Safety Case | 2022-04-07 | 2022-04-07 | Initial high level scope of programme | 07-Apr-22 A | 07-Apr-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.4580 | HYB Essential Defueling Safety Case | 2022-04-07 | 2022-04-07 | Hold Station Workshop to Share OPEX | 07-Apr-22 A | 07-Apr-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.5460 | HYB Essential Defueling Safety Case | 2022-04-07 | 2022-04-19 | Workshop Minutes Issued | 07-Apr-22 A | 19-Apr-22 A | 3 | 0 | 7 | 100% |  | Completed
ER6668LT | W213 | W213.1400 | TOR Essential Defueling Safety Case | 2022-04-07 | 2022-04-07 | Initial high level scope of programme | 07-Apr-22 A | 07-Apr-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.4580 | TOR Essential Defueling Safety Case | 2022-04-07 | 2022-04-07 | Hold Station Workshop to Share OPEX | 07-Apr-22 A | 07-Apr-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.5460 | TOR Essential Defueling Safety Case | 2022-04-07 | 2022-04-19 | Workshop Minutes Issued | 07-Apr-22 A | 19-Apr-22 A | 3 | 0 | 7 | 100% |  | Completed
ER6666LT | W209 | W209.8620 | HYB Essential Defueling Safety Case | 2022-04-08 | 2022-04-08 | Prepare Spec for FPU Maintenance Work EAN | 08-Apr-22 A | 08-Apr-22 A | 5 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.8630 | HYB Essential Defueling Safety Case | 2022-04-08 | 2022-04-08 | Prepare Task Sheet for FPU Maintenance Work EAN | 08-Apr-22 A | 08-Apr-22 A | 10 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.8640 | HYB Essential Defueling Safety Case | 2022-04-08 | 2022-04-08 | Approve Task Sheet for FPU Maintenance Work EAN | 08-Apr-22 A | 08-Apr-22 A | 7 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.8620 | TOR Essential Defueling Safety Case | 2022-04-08 | 2022-04-08 | Prepare Spec for FPU Maintenance Work EAN | 08-Apr-22 A | 08-Apr-22 A | 5 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.8630 | TOR Essential Defueling Safety Case | 2022-04-08 | 2022-04-08 | Prepare Task Sheet for FPU Maintenance Work EAN | 08-Apr-22 A | 08-Apr-22 A | 10 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.8640 | TOR Essential Defueling Safety Case | 2022-04-08 | 2022-04-08 | Approve Task Sheet for FPU Maintenance Work EAN | 08-Apr-22 A | 08-Apr-22 A | 7 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1410 | HYB Essential Defueling Safety Case | 2022-04-08 | 2022-05-31 | Define Project Control Structures (WBS/CBS/OBS/PBS) | 08-Apr-22 A | 31-May-22 A | 1 | 0 | 35 | 100% |  | Completed
ER6666LT | W209 | W209.5750 | HYB Essential Defueling Safety Case | 2022-04-08 | 2022-05-04 | Prepare Task Sheet for Safety Case Requirements EAN - TASK E EAN | 08-Apr-22 A | 04-May-22 A | 10 | 0 | 16 | 100% |  | Completed
ER6666LT | W209 | W209.5900 | HYB Essential Defueling Safety Case | 2022-04-08 | 2022-04-11 | Prepare Task Sheet for Reactor Internals & Structural Integrity During Defueling Report EAN | 08-Apr-22 A | 11-Apr-22 A | 10 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.1410 | TOR Essential Defueling Safety Case | 2022-04-08 | 2022-05-31 | Define Project Control Structures (WBS/CBS/OBS/PBS) | 08-Apr-22 A | 31-May-22 A | 1 | 0 | 35 | 100% |  | Completed
ER6668LT | W213 | W213.5750 | TOR Essential Defueling Safety Case | 2022-04-08 | 2022-05-04 | Prepare Task Sheet for Safety Case Requirements EAN - TASK E EAN | 08-Apr-22 A | 04-May-22 A | 10 | 0 | 16 | 100% |  | Completed
ER6668LT | W213 | W213.5900 | TOR Essential Defueling Safety Case | 2022-04-08 | 2022-04-11 | Prepare Task Sheet for Reactor Internals & Structural Integrity During Defueling Report EAN | 08-Apr-22 A | 11-Apr-22 A | 10 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 2160 | HYA Fuel Handling Essential Safety Case |  |  | INA of EC without ER updates | 08-Apr-22 A | 10-Nov-22 A | 149 | 0 | 149 | 100% |  | Completed
ER6666LT | W209 | W209.5910 | HYB Essential Defueling Safety Case | 2022-04-11 | 2022-04-12 | Approve Task Sheet for Reactor Internals & Structural Integrity During Defueling Report EAN | 11-Apr-22 A | 12-Apr-22 A | 7 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A30450 | HYB Essential Defueling Safety Case | 2022-04-11 | 2022-04-11 | Pre Job Brief for FPU Maintenance Work EAN | 11-Apr-22 A | 11-Apr-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.5910 | TOR Essential Defueling Safety Case | 2022-04-11 | 2022-04-12 | Approve Task Sheet for Reactor Internals & Structural Integrity During Defueling Report EAN | 11-Apr-22 A | 12-Apr-22 A | 7 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A30450 | TOR Essential Defueling Safety Case | 2022-04-11 | 2022-04-11 | Pre Job Brief for FPU Maintenance Work EAN | 11-Apr-22 A | 11-Apr-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A30570 | HYB Essential Defueling Safety Case | 2022-04-12 | 2022-07-13 | Draft FPU Maintenance Work EAN | 12-Apr-22 A | 24-Jun-22 A | 30 | 0 | 48 | 100% |  | Completed
ER6668LT | W213 | W213.A30570 | TOR Essential Defueling Safety Case | 2022-04-12 | 2022-07-13 | Draft FPU Maintenance Work EAN | 12-Apr-22 A | 24-Jun-22 A | 30 | 0 | 48 | 100% |  | Completed
ER6666LT | W209 | W209.A26260 | HYB Essential Defueling Safety Case | 2022-04-13 | 2022-04-13 | Pre Job Brief for Reactor Internals & Structural Integrity During Defueling Report EAN | 13-Apr-22 A | 13-Apr-22 A | 0 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A26260 | TOR Essential Defueling Safety Case | 2022-04-13 | 2022-04-13 | Pre Job Brief for Reactor Internals & Structural Integrity During Defueling Report EAN | 13-Apr-22 A | 13-Apr-22 A | 0 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.5020 | HYB Essential Defueling Safety Case |  | 2022-04-13 | HOLD POINT 2 - Share Preliminary Analysis Findings Pre-Tech Review | 13-Apr-22 A | 13-Apr-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.5020 | TOR Essential Defueling Safety Case |  | 2022-04-13 | HOLD POINT 2 - Share Preliminary Analysis Findings Pre-Tech Review | 13-Apr-22 A | 13-Apr-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.5030 | HYB Essential Defueling Safety Case | 2022-04-14 | 2022-05-27 | Issue of Dropped FPU BoA for Tech Review | 14-Apr-22 A | 27-May-22 A | 27 | 0 | 29 | 100% |  | Completed
ER6666LT | W209 | W209.A26270 | HYB Essential Defueling Safety Case | 2022-04-14 | 2022-06-09 | Draft Reactor Internals & Structural Integrity During Defueling Report EAN | 14-Apr-22 A | 18-May-22 A | 30 | 0 | 21 | 100% |  | Completed
ER6668LT | W213 | W213.5030 | TOR Essential Defueling Safety Case | 2022-04-14 | 2022-05-27 | Issue of Dropped FPU BoA for Tech Review | 14-Apr-22 A | 27-May-22 A | 27 | 0 | 29 | 100% |  | Completed
ER6668LT | W213 | W213.A26270 | TOR Essential Defueling Safety Case | 2022-04-14 | 2022-06-09 | Draft Reactor Internals & Structural Integrity During Defueling Report EAN | 14-Apr-22 A | 18-May-22 A | 30 | 0 | 21 | 100% |  | Completed
ER6666LT | W209 | W209.5470 | HYB Essential Defueling Safety Case | 2022-04-19 | 2022-04-19 | (Draft) Optioneering Report Issued for Verification | 19-Apr-22 A | 19-Apr-22 A | 3 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.5470 | TOR Essential Defueling Safety Case | 2022-04-19 | 2022-04-19 | (Draft) Optioneering Report Issued for Verification | 19-Apr-22 A | 19-Apr-22 A | 3 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.4190 | HYB Essential Defueling Safety Case | 2022-04-20 | 2022-04-20 | Approve & Issue RFS | 20-Apr-22 A | 20-Apr-22 A | 5 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.4200 | HYB Essential Defueling Safety Case |  | 2022-04-20 | RFS Issued | 20-Apr-22 A | 20-Apr-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.5490 | HYB Essential Defueling Safety Case | 2022-04-20 | 2022-05-18 | Verification | 20-Apr-22 A | 18-May-22 A | 10 | 0 | 20 | 100% |  | Completed
ER6668LT | W213 | W213.4190 | TOR Essential Defueling Safety Case | 2022-04-20 | 2022-04-20 | Approve & Issue RFS | 20-Apr-22 A | 20-Apr-22 A | 5 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.4200 | TOR Essential Defueling Safety Case |  | 2022-04-20 | RFS Issued | 20-Apr-22 A | 20-Apr-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.5490 | TOR Essential Defueling Safety Case | 2022-04-20 | 2022-05-18 | Verification | 20-Apr-22 A | 18-May-22 A | 10 | 0 | 20 | 100% |  | Completed
ER6371LT | W202 | 2900 | HRA Reactors Shutdown Essential Safety Cases | 2022-04-20 | 2022-05-06 | Produce draft NSRS (using BARRIER MODEL) | 20-Apr-22 A | 06-May-22 A | 12 | 0 | 12 | 100% |  | Completed
ER6661LT | W206 | 2900 | HYA Reactors Shutdown Essential Safety Cases | 2022-04-20 | 2022-05-06 | Produce draft NSRS (using BARRIER MODEL) | 20-Apr-22 A | 06-May-22 A | 12 | 0 | 12 | 100% |  | Completed
ER6666LT | W209 | W209.4210 | HYB Essential Defueling Safety Case | 2022-04-21 | 2022-05-06 | Supplier Respond to RFS | 21-Apr-22 A | 06-May-22 A | 10 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.4210 | TOR Essential Defueling Safety Case | 2022-04-21 | 2022-05-06 | Supplier Respond to RFS | 21-Apr-22 A | 06-May-22 A | 10 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.4270 | HYB Essential Defueling Safety Case |  | 2022-04-22 | RFS Responses Recieved | 22-Apr-22 A | 22-Apr-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.4270 | TOR Essential Defueling Safety Case |  | 2022-04-22 | RFS Responses Recieved | 22-Apr-22 A | 22-Apr-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 2700 | HYA Fuel Handling Essential Safety Case |  |  | Produce draft NSRS (using BARRIER MODEL) | 26-Apr-22 A | 18-May-22 A | 8 | 0 | 15 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18160 | HNB Reactors Shutdown Essential Safety Cases |  |  | Review of Reactor Essential Safety Cases 1 - Lessons Learned Review Complete | 27-Apr-22 A | 27-Apr-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.4760 | HYB Essential Defueling Safety Case | 2022-04-27 | 2022-05-17 | Approve EAN | 27-Apr-22 A | 17-May-22 A | 10 | 0 | 14 | 100% |  | Completed
ER6666LT | W209 | W209.5330 | HYB Essential Defueling Safety Case |  | 2022-04-27 | PJBs of Previous Lessons Learned | 27-Apr-22 A | 27-Apr-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | W201.1650 | HNB Reactors Shutdown Essential Safety Cases |  |  | INSA complete/INA Approved | 27-Apr-22 A | 27-Apr-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.4760 | TOR Essential Defueling Safety Case | 2022-04-27 | 2022-05-17 | Approve EAN | 27-Apr-22 A | 17-May-22 A | 10 | 0 | 14 | 100% |  | Completed
ER6668LT | W213 | W213.5330 | TOR Essential Defueling Safety Case |  | 2022-04-27 | PJBs of Previous Lessons Learned | 27-Apr-22 A | 27-Apr-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A26740 | HYB Essential Defueling Safety Case | 2022-04-29 | 2022-04-29 | Pre Job Brief for Boron Bead Injection Feasibility & Control Rod Isolation EAN | 29-Apr-22 A | 29-Apr-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.5430 | HYB Essential Defueling Safety Case | 2022-04-29 | 2022-06-01 | Verification | 29-Apr-22 A | 01-Jun-22 A | 4 | 0 | 23 | 100% |  | Completed
ER6666LT | W209 | W209.5980 | HYB Essential Defueling Safety Case | 2022-04-29 | 2022-04-29 | Prepare Spec for Review of FM Cyclic Duty EAN | 29-Apr-22 A | 29-Apr-22 A | 5 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A29730 | HYB Essential Defueling Safety Case | 2022-04-29 | 2022-04-29 | Pre Job Brief for ALARP Review of Not Draining the PVCS (Report) | 29-Apr-22 A | 29-Apr-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A26740 | TOR Essential Defueling Safety Case | 2022-04-29 | 2022-04-29 | Pre Job Brief for Boron Bead Injection Feasibility & Control Rod Isolation EAN | 29-Apr-22 A | 29-Apr-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.5430 | TOR Essential Defueling Safety Case | 2022-04-29 | 2022-06-01 | Verification | 29-Apr-22 A | 01-Jun-22 A | 4 | 0 | 23 | 100% |  | Completed
ER6668LT | W213 | W213.5980 | TOR Essential Defueling Safety Case | 2022-04-29 | 2022-04-29 | Prepare Spec for Review of FM Cyclic Duty EAN | 29-Apr-22 A | 29-Apr-22 A | 5 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A29730 | TOR Essential Defueling Safety Case | 2022-04-29 | 2022-04-29 | Pre Job Brief for ALARP Review of Not Draining the PVCS (Report) | 29-Apr-22 A | 29-Apr-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7700 | HYB Essential Defueling Safety Case | 2022-04-29 | 2022-06-01 | Update NSRS to address comments | 29-Apr-22 A | 01-Jun-22 A | 13 | 0 | 23 | 100% |  | Completed
ER6668LT | W213 | W213.7700 | TOR Essential Defueling Safety Case | 2022-04-29 | 2022-06-01 | Update NSRS to address comments | 29-Apr-22 A | 01-Jun-22 A | 13 | 0 | 23 | 100% |  | Completed
ER6666LT | W209 | W209.5990 | HYB Essential Defueling Safety Case | 2022-05-02 | 2022-05-20 | Prepare Task Sheet for Review of FM Cyclic Duty EAN | 02-May-22 A | 20-May-22 A | 10 | 0 | 14 | 100% |  | Completed
ER6666LT | W209 | W209.A30310 | HYB Essential Defueling Safety Case | 2022-05-02 | 2022-07-13 | Draft Boron Bead Injection Feasibility & Control Rod Isolation EAN (CLAIM 1 - A - B De-risking) | 02-May-22 A | 13-Jul-22 A | 48 | 0 | 50 | 100% |  | Completed
ER6666LT | W209 | W209.A30360 | HYB Essential Defueling Safety Case | 2022-05-02 | 2022-07-13 | Draft ALARP Review of Not Draining the PVCS (Report) (A - B De-risking) | 02-May-22 A | 13-Jul-22 A | 29 | 0 | 50 | 100% |  | Completed
ER6668LT | W213 | W213.5990 | TOR Essential Defueling Safety Case | 2022-05-02 | 2022-05-20 | Prepare Task Sheet for Review of FM Cyclic Duty EAN | 02-May-22 A | 20-May-22 A | 10 | 0 | 14 | 100% |  | Completed
ER6668LT | W213 | W213.A30310 | TOR Essential Defueling Safety Case | 2022-05-02 | 2022-07-13 | Draft Boron Bead Injection Feasibility & Control Rod Isolation EAN (CLAIM 1 - A - B De-risking) | 02-May-22 A | 13-Jul-22 A | 48 | 0 | 50 | 100% |  | Completed
ER6668LT | W213 | W213.A30360 | TOR Essential Defueling Safety Case | 2022-05-02 | 2022-07-13 | Draft ALARP Review of Not Draining the PVCS (Report) (A - B De-risking) | 02-May-22 A | 13-Jul-22 A | 29 | 0 | 50 | 100% |  | Completed
ER6666LT | W209 | W209.A25940 | HYB Essential Defueling Safety Case | 2022-05-03 | 2022-05-10 | Pre Job Brief for Civil Assesment of the Ponds at Low Temperature EAN | 03-May-22 A | 10-May-22 A | 0 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.A26020 | HYB Essential Defueling Safety Case | 2022-05-03 | 2022-05-03 | Pre Job Brief for Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN | 03-May-22 A | 03-May-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A26660 | HYB Essential Defueling Safety Case | 2022-05-03 | 2022-05-20 | Pre Job Brief for Review of flux detector suitability EAN | 03-May-22 A | 20-May-22 A | 1 | 0 | 14 | 100% |  | Completed
ER6666LT | W209 | W209.6370 | HYB Essential Defueling Safety Case | 2022-05-03 | 2022-05-13 | Prepare Spec for Update Basis of Analysis document EAN | 03-May-22 A | 13-May-22 A | 5 | 0 | 9 | 100% |  | Completed
ER6666LT | W209 | W209.7540 | HYB Essential Defueling Safety Case | 2022-05-03 | 2022-05-06 | Approve Task Sheet for Cooling Plant Availability Review EAN | 03-May-22 A | 06-May-22 A | 7 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | W201.1660 | HNB Reactors Shutdown Essential Safety Cases |  |  | Station Approve EC | 03-May-22 A | 05-May-22 A | 3 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.8260 | HYB Essential Defueling Safety Case | 2022-05-03 | 2022-05-04 | Prepare Spec for Feasibility of Draining PVCS (Report) | 03-May-22 A | 04-May-22 A | 10 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A29870 | HYB Essential Defueling Safety Case | 2022-05-03 | 2022-05-03 | Pre Job Brief for FPU Maintenance Analysis EAN | 03-May-22 A | 03-May-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A30380 | HYB Essential Defueling Safety Case | 2022-05-03 | 2022-07-13 | Draft Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN (A-B De-risking) | 03-May-22 A | 13-Jul-22 A | 50 | 0 | 50 | 100% |  | Completed
ER6668LT | W213 | W213.A25940 | TOR Essential Defueling Safety Case | 2022-05-03 | 2022-05-10 | Pre Job Brief for Civil Assesment of the Ponds at Low Temperature EAN | 03-May-22 A | 10-May-22 A | 0 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A26020 | TOR Essential Defueling Safety Case | 2022-05-03 | 2022-05-03 | Pre Job Brief for Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN | 03-May-22 A | 03-May-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A26660 | TOR Essential Defueling Safety Case | 2022-05-03 | 2022-05-20 | Pre Job Brief for Review of flux detector suitability EAN | 03-May-22 A | 20-May-22 A | 1 | 0 | 14 | 100% |  | Completed
ER6668LT | W213 | W213.6370 | TOR Essential Defueling Safety Case | 2022-05-03 | 2022-05-13 | Prepare Spec for Update Basis of Analysis document EAN | 03-May-22 A | 13-May-22 A | 5 | 0 | 9 | 100% |  | Completed
ER6668LT | W213 | W213.7540 | TOR Essential Defueling Safety Case | 2022-05-03 | 2022-05-06 | Approve Task Sheet for Cooling Plant Availability Review EAN | 03-May-22 A | 06-May-22 A | 7 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.8260 | TOR Essential Defueling Safety Case | 2022-05-03 | 2022-05-04 | Prepare Spec for Feasibility of Draining PVCS (Report) | 03-May-22 A | 04-May-22 A | 10 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A29870 | TOR Essential Defueling Safety Case | 2022-05-03 | 2022-05-03 | Pre Job Brief for FPU Maintenance Analysis EAN | 03-May-22 A | 03-May-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A30380 | TOR Essential Defueling Safety Case | 2022-05-03 | 2022-07-13 | Draft Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN (A-B De-risking) | 03-May-22 A | 13-Jul-22 A | 50 | 0 | 50 | 100% |  | Completed
ER6666LT | W209 | W209.3390 | HYB Essential Defueling Safety Case |  | 2022-05-03 | EDF Approve Task Sheet | 03-May-22 A | 03-May-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.3390 | TOR Essential Defueling Safety Case |  | 2022-05-03 | EDF Approve Task Sheet | 03-May-22 A | 03-May-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7570 | HYB Essential Defueling Safety Case | 2022-05-04 | 2022-05-06 | Approve Task Sheet for Cooling Plant OPEX Study EAN | 04-May-22 A | 06-May-22 A | 7 | 0 | 2 | 100% |  | Completed
ER6668LT | W213 | W213.7570 | TOR Essential Defueling Safety Case | 2022-05-04 | 2022-05-06 | Approve Task Sheet for Cooling Plant OPEX Study EAN | 04-May-22 A | 06-May-22 A | 7 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.3360 | HYB Essential Defueling Safety Case | 2022-05-04 | 2022-05-13 | Optioneering Report Completed | 04-May-22 A | 13-May-22 A | 1 | 0 | 8 | 100% |  | Completed
ER6666LT | W209 | W209.A30550 | HYB Essential Defueling Safety Case | 2022-05-04 | 2022-07-13 | Draft Review of FPU Maintenance Analysis EAN (A-B De-risking) | 04-May-22 A | 13-Jul-22 A | 49 | 0 | 49 | 100% |  | Completed
ER6668LT | W213 | W213.3360 | TOR Essential Defueling Safety Case | 2022-05-04 | 2022-05-13 | Optioneering Report Completed | 04-May-22 A | 13-May-22 A | 1 | 0 | 8 | 100% |  | Completed
ER6668LT | W213 | W213.A30550 | TOR Essential Defueling Safety Case | 2022-05-04 | 2022-07-13 | Draft Review of FPU Maintenance Analysis EAN (A-B De-risking) | 04-May-22 A | 13-Jul-22 A | 49 | 0 | 49 | 100% |  | Completed
ER6666LT | W209 | W209.8270 | HYB Essential Defueling Safety Case | 2022-05-05 | 2022-05-13 | Prepare Task Sheet for Feasibility of Draining PVCS (Report) | 05-May-22 A | 13-May-22 A | 10 | 0 | 7 | 100% |  | Completed
ER6668LT | W213 | W213.8270 | TOR Essential Defueling Safety Case | 2022-05-05 | 2022-05-13 | Prepare Task Sheet for Feasibility of Draining PVCS (Report) | 05-May-22 A | 13-May-22 A | 10 | 0 | 7 | 100% |  | Completed
ER6666LT | W209 | W209.5760 | HYB Essential Defueling Safety Case | 2022-05-05 | 2022-05-06 | Approve Task Sheet for Safety Case Requirements EAN - TASK E EAN | 05-May-22 A | 06-May-22 A | 7 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.5760 | TOR Essential Defueling Safety Case | 2022-05-05 | 2022-05-06 | Approve Task Sheet for Safety Case Requirements EAN - TASK E EAN | 05-May-22 A | 06-May-22 A | 7 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | W201.1670 | HNB Reactors Shutdown Essential Safety Cases |  |  | EC Approved | 05-May-22 A | 05-May-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.4220 | HYB Essential Defueling Safety Case |  | 2022-05-06 | RFS Responses Recieved | 06-May-22 A | 06-May-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.28660 | HYB Essential Defueling Safety Case | 2023-01-03 | 2023-01-03 | Pre Job Brief for PCPV Liner Impact Assessment | 06-May-22 A | 06-May-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.6420 | HYB Essential Defueling Safety Case | 2022-05-06 | 2022-05-06 | Receive Responses from TSA for Develop FEA Model | 06-May-22 A | 06-May-22 A | 10 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | W201.1700 | HNB Reactors Shutdown Essential Safety Cases |  |  | Start of Defuelling HNB R3 - Target date | 06-May-22 A | 06-May-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.4220 | TOR Essential Defueling Safety Case |  | 2022-05-06 | RFS Responses Recieved | 06-May-22 A | 06-May-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.28660 | TOR Essential Defueling Safety Case | 2023-01-03 | 2023-01-03 | Pre Job Brief for PCPV Liner Impact Assessment | 06-May-22 A | 06-May-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.6420 | TOR Essential Defueling Safety Case | 2022-05-06 | 2022-05-06 | Receive Responses from TSA for Develop FEA Model | 06-May-22 A | 06-May-22 A | 10 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A25860 | HYB Essential Defueling Safety Case | 2022-05-09 | 2022-05-23 | Pre Job Brief for Safety Case Requirements EAN - TASK E EAN | 09-May-22 A | 23-May-22 A | 0 | 0 | 11 | 100% |  | Completed
ER6666LT | W209 | W209.28670 | HYB Essential Defueling Safety Case | 2023-01-04 | 2023-02-14 | Draft PCPV Liner Impact Assessment | 09-May-22 A | 18-May-22 A | 30 | 0 | 7 | 100% |  | Completed
ER6666LT | W209 | W209.A29380 | HYB Essential Defueling Safety Case | 2022-05-09 | 2022-05-16 | Pre Job Brief for Cooling Plant Availability Review EAN | 09-May-22 A | 16-May-22 A | 0 | 0 | 6 | 100% |  | Completed
ER6666LT | W209 | W209.A29460 | HYB Essential Defueling Safety Case | 2022-05-09 | 2022-05-17 | Pre Job Brief for Cooling Plant OPEX Study EAN | 09-May-22 A | 17-May-22 A | 0 | 0 | 7 | 100% |  | Completed
ER6666LT | W209 | W209.7810 | HYB Essential Defueling Safety Case | 2022-05-09 | 2022-05-10 | Select Supplier for Develop FEA Model | 09-May-22 A | 10-May-22 A | 10 | 0 | 2 | 100% |  | Completed
ER6668LT | W213 | W213.A25860 | TOR Essential Defueling Safety Case | 2022-05-09 | 2022-05-23 | Pre Job Brief for Safety Case Requirements EAN - TASK E EAN | 09-May-22 A | 23-May-22 A | 0 | 0 | 11 | 100% |  | Completed
ER6668LT | W213 | W213.28670 | TOR Essential Defueling Safety Case | 2023-01-04 | 2023-02-14 | Draft PCPV Liner Impact Assessment | 09-May-22 A | 18-May-22 A | 30 | 0 | 7 | 100% |  | Completed
ER6668LT | W213 | W213.A29380 | TOR Essential Defueling Safety Case | 2022-05-09 | 2022-05-16 | Pre Job Brief for Cooling Plant Availability Review EAN | 09-May-22 A | 16-May-22 A | 0 | 0 | 6 | 100% |  | Completed
ER6668LT | W213 | W213.A29460 | TOR Essential Defueling Safety Case | 2022-05-09 | 2022-05-17 | Pre Job Brief for Cooling Plant OPEX Study EAN | 09-May-22 A | 17-May-22 A | 0 | 0 | 7 | 100% |  | Completed
ER6668LT | W213 | W213.7810 | TOR Essential Defueling Safety Case | 2022-05-09 | 2022-05-10 | Select Supplier for Develop FEA Model | 09-May-22 A | 10-May-22 A | 10 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | 2910 | HRA Reactors Shutdown Essential Safety Cases | 2022-05-09 | 2022-05-20 | Station comments on NSRS | 09-May-22 A | 20-May-22 A | 10 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | 2920 | HRA Reactors Shutdown Essential Safety Cases | 2022-05-09 | 2022-05-20 | ED (Peer) comments on NSRS | 09-May-22 A | 20-May-22 A | 10 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | 2930 | HRA Reactors Shutdown Essential Safety Cases | 2022-05-09 | 2022-05-20 | SRD comments on NSRS | 09-May-22 A | 20-May-22 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | 2910 | HYA Reactors Shutdown Essential Safety Cases | 2022-05-09 | 2022-05-20 | Station comments on NSRS | 09-May-22 A | 20-May-22 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | 2920 | HYA Reactors Shutdown Essential Safety Cases | 2022-05-09 | 2022-05-20 | ED (Peer) comments on NSRS | 09-May-22 A | 20-May-22 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | 2930 | HYA Reactors Shutdown Essential Safety Cases | 2022-05-09 | 2022-05-20 | SRD comments on NSRS | 09-May-22 A | 20-May-22 A | 10 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | 2730 | HYA Fuel Handling Essential Safety Case |  |  | SRD comments on NSRS | 09-May-22 A | 20-May-22 A | 10 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | 2720 | HYA Fuel Handling Essential Safety Case |  |  | ED (Peer) comments on NSRS | 09-May-22 A | 20-May-22 A | 10 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | 2710 | HYA Fuel Handling Essential Safety Case |  |  | Station comments on NSRS | 09-May-22 A | 20-May-22 A | 10 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.A30240 | HYB Essential Defueling Safety Case | 2022-05-10 | 2022-05-10 | Pre Job Brief for Define Nuclear Data (PANTHER Validation Calcs) EAN | 10-May-22 A | 10-May-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A30280 | HYB Essential Defueling Safety Case | 2022-05-10 | 2022-05-10 | Pre Job Brief for PANTHER SCM Assessments - Agree Defuelling Order EAN | 10-May-22 A | 10-May-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A30330 | HYB Essential Defueling Safety Case | 2022-05-10 | 2022-07-13 | Draft Civil Assesment of the Ponds at Low Temperature EAN (A - B De-risking) | 10-May-22 A | 13-Jul-22 A | 41 | 0 | 45 | 100% |  | Completed
ER6668LT | W213 | W213.A30240 | TOR Essential Defueling Safety Case | 2022-05-10 | 2022-05-10 | Pre Job Brief for Define Nuclear Data (PANTHER Validation Calcs) EAN | 10-May-22 A | 10-May-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A30280 | TOR Essential Defueling Safety Case | 2022-05-10 | 2022-05-10 | Pre Job Brief for PANTHER SCM Assessments - Agree Defuelling Order EAN | 10-May-22 A | 10-May-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A30330 | TOR Essential Defueling Safety Case | 2022-05-10 | 2022-07-13 | Draft Civil Assesment of the Ponds at Low Temperature EAN (A - B De-risking) | 10-May-22 A | 13-Jul-22 A | 41 | 0 | 45 | 100% |  | Completed
ER6666LT | W209 | W209.A26490 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-09-07 | PANTHER SCM Assessments - Agree Defuelling Order EAN ## (Cost Summary) (Claim 1) | 11-May-22 A | 17-Jan-23 A | 175 | 0 | 173 | 100% |  | Completed
ER6666LT | W209 | W209.A28100 | HYB Essential Defueling Safety Case | 2022-05-11 | 2022-05-17 | Pre Job Brief for Develop FEA Model | 11-May-22 A | 17-May-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.A30250 | HYB Essential Defueling Safety Case | 2022-05-11 | 2022-06-01 | Draft Define Nuclear Data (PANTHER Validation Calcs) EAN | 11-May-22 A | 01-Jul-22 A | 30 | 0 | 36 | 100% |  | Completed
ER6666LT | W209 | W209.A30290 | HYB Essential Defueling Safety Case | 2022-05-11 | 2022-07-01 | Draft PANTHER SCM Assessments - Agree Defuelling Order EAN | 11-May-22 A | 12-Sep-22 A | 4 | 0 | 86 | 100% |  | Completed
ER6668LT | W213 | W213.A26490 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-09-07 | PANTHER SCM Assessments - Agree Defuelling Order EAN ## (Cost Summary) (Claim 1) | 11-May-22 A | 17-Jan-23 A | 175 | 0 | 173 | 100% |  | Completed
ER6668LT | W213 | W213.A28100 | TOR Essential Defueling Safety Case | 2022-05-11 | 2022-05-17 | Pre Job Brief for Develop FEA Model | 11-May-22 A | 17-May-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A30250 | TOR Essential Defueling Safety Case | 2022-05-11 | 2022-06-01 | Draft Define Nuclear Data (PANTHER Validation Calcs) EAN | 11-May-22 A | 01-Jul-22 A | 30 | 0 | 36 | 100% |  | Completed
ER6668LT | W213 | W213.A30290 | TOR Essential Defueling Safety Case | 2022-05-11 | 2022-07-01 | Draft PANTHER SCM Assessments - Agree Defuelling Order EAN | 11-May-22 A | 12-Sep-22 A | 4 | 0 | 86 | 100% |  | Completed
ER6666LT | W209 | W209.4900 | HYB Essential Defueling Safety Case | 2022-05-11 | 2022-05-31 | Case Production Plan Peer Review & Update | 11-May-22 A | 31-May-22 A | 15 | 0 | 15 | 100% |  | Completed
ER6668LT | W213 | W213.4900 | TOR Essential Defueling Safety Case | 2022-05-11 | 2022-05-31 | Case Production Plan Peer Review & Update | 11-May-22 A | 31-May-22 A | 15 | 0 | 15 | 100% |  | Completed
ER6666LT | W209 | W209.6380 | HYB Essential Defueling Safety Case | 2022-05-16 | 2022-06-01 | Prepare Task Sheet for Update Basis of Analysis document EAN | 16-May-22 A | 01-Jun-22 A | 10 | 0 | 13 | 100% |  | Completed
ER6666LT | W209 | W209.8280 | HYB Essential Defueling Safety Case | 2022-05-16 | 2022-05-16 | Approve Task Sheet for Feasibility of Draining PVCS (Report) | 16-May-22 A | 16-May-22 A | 7 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.6380 | TOR Essential Defueling Safety Case | 2022-05-16 | 2022-06-01 | Prepare Task Sheet for Update Basis of Analysis document EAN | 16-May-22 A | 01-Jun-22 A | 10 | 0 | 13 | 100% |  | Completed
ER6668LT | W213 | W213.8280 | TOR Essential Defueling Safety Case | 2022-05-16 | 2022-05-16 | Approve Task Sheet for Feasibility of Draining PVCS (Report) | 16-May-22 A | 16-May-22 A | 7 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A30340 | HYB Essential Defueling Safety Case | 2022-05-17 | 2022-07-13 | Draft Cooling Plant Availability Review EAN (A - B De-risking) | 17-May-22 A | 13-Jul-22 A | 40 | 0 | 40 | 100% |  | Completed
ER6668LT | W213 | W213.A30340 | TOR Essential Defueling Safety Case | 2022-05-17 | 2022-07-13 | Draft Cooling Plant Availability Review EAN (A - B De-risking) | 17-May-22 A | 13-Jul-22 A | 40 | 0 | 40 | 100% |  | Completed
ER6666LT | W209 | W209.7600 | HYB Essential Defueling Safety Case | 2022-05-18 | 2022-06-07 | Review Process Flows for Defueling | 18-May-22 A | 01-Jul-22 A | 13 | 0 | 31 | 100% |  | Completed
ER6666LT | W209 | W209.A30350 | HYB Essential Defueling Safety Case | 2022-05-18 | 2022-07-13 | Draft Cooling Plant OPEX Study EAN (A - B De-risking) | 18-May-22 A | 13-Jul-22 A | 28 | 0 | 39 | 100% |  | Completed
ER6666LT | W209 | W209.A30410 | HYB Essential Defueling Safety Case | 2022-05-18 | 2022-07-13 | Develop FEA Model (A - B De Risking) | 18-May-22 A | 13-Jul-22 A | 39 | 0 | 39 | 100% |  | Completed
ER6668LT | W213 | W213.7600 | TOR Essential Defueling Safety Case | 2022-05-18 | 2022-06-07 | Review Process Flows for Defueling | 18-May-22 A | 01-Jul-22 A | 13 | 0 | 31 | 100% |  | Completed
ER6668LT | W213 | W213.A30350 | TOR Essential Defueling Safety Case | 2022-05-18 | 2022-07-13 | Draft Cooling Plant OPEX Study EAN (A - B De-risking) | 18-May-22 A | 13-Jul-22 A | 28 | 0 | 39 | 100% |  | Completed
ER6668LT | W213 | W213.A30410 | TOR Essential Defueling Safety Case | 2022-05-18 | 2022-07-13 | Develop FEA Model (A - B De Risking) | 18-May-22 A | 13-Jul-22 A | 39 | 0 | 39 | 100% |  | Completed
ER6666LT | W209 | W209.A26280 | HYB Essential Defueling Safety Case | 2022-06-10 | 2022-07-07 | Verify Reactor Internals & Structural Integrity During Defueling Report EAN Issue for Technical Review | 19-May-22 A | 25-May-22 A | 20 | 0 | 4 | 100% |  | Completed
ER6666LT | W209 | W209.28680 | HYB Essential Defueling Safety Case | 2023-02-15 | 2023-02-28 | Verify PCPV Liner Impact Assessment & Issue for Technical Review | 19-May-22 A | 26-May-22 A | 10 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A26280 | TOR Essential Defueling Safety Case | 2022-06-10 | 2022-07-07 | Verify Reactor Internals & Structural Integrity During Defueling Report EAN Issue for Technical Review | 19-May-22 A | 25-May-22 A | 20 | 0 | 4 | 100% |  | Completed
ER6668LT | W213 | W213.28680 | TOR Essential Defueling Safety Case | 2023-02-15 | 2023-02-28 | Verify PCPV Liner Impact Assessment & Issue for Technical Review | 19-May-22 A | 26-May-22 A | 10 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.5480 | HYB Essential Defueling Safety Case | 2022-05-19 | 2022-05-20 | Issue Optioneering Report | 19-May-22 A | 20-May-22 A | 9 | 0 | 2 | 100% |  | Completed
ER6668LT | W213 | W213.5480 | TOR Essential Defueling Safety Case | 2022-05-19 | 2022-05-20 | Issue Optioneering Report | 19-May-22 A | 20-May-22 A | 9 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.1480 | HYB Essential Defueling Safety Case | 2022-05-23 | 2022-05-31 | Update Schedule/Estimate from Risk Log & Add Provisions | 23-May-22 A | 31-May-22 A | 1 | 0 | 6 | 100% |  | Completed
ER6668LT | W213 | W213.1480 | TOR Essential Defueling Safety Case | 2022-05-23 | 2022-05-31 | Update Schedule/Estimate from Risk Log & Add Provisions | 23-May-22 A | 31-May-22 A | 1 | 0 | 6 | 100% |  | Completed
ER6666LT | W209 | W209.A26650 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-09-14 | Review of flux detector suitability EAN ## (Cost Summary) (Claim 1) | 23-May-22 A | 21-Nov-22 A | 128 | 0 | 128 | 100% |  | Completed
ER6666LT | W209 | W209.6000 | HYB Essential Defueling Safety Case | 2022-05-23 | 2022-05-31 | Approve Task Sheet for Review of FM Cyclic Duty EAN | 23-May-22 A | 31-May-22 A | 7 | 0 | 7 | 100% |  | Completed
ER6666LT | W209 | W209.A30300 | HYB Essential Defueling Safety Case | 2022-05-23 | 2022-06-30 | Draft Review of flux detector suitability EAN | 23-May-22 A | 31-Aug-22 A | 38 | 0 | 69 | 100% |  | Completed
ER6371LT | W202 | 2950 | HRA Reactors Shutdown Essential Safety Cases | 2022-05-23 | 2022-05-27 | Incorporate SRD, Station, ED (peer) comments | 23-May-22 A | 27-May-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | 2950 | HYA Reactors Shutdown Essential Safety Cases | 2022-05-23 | 2022-05-27 | Incorporate SRD, Station, ED (peer) comments | 23-May-22 A | 27-May-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A26650 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-09-14 | Review of flux detector suitability EAN ## (Cost Summary) (Claim 1) | 23-May-22 A | 21-Nov-22 A | 128 | 0 | 128 | 100% |  | Completed
ER6668LT | W213 | W213.6000 | TOR Essential Defueling Safety Case | 2022-05-23 | 2022-05-31 | Approve Task Sheet for Review of FM Cyclic Duty EAN | 23-May-22 A | 31-May-22 A | 7 | 0 | 7 | 100% |  | Completed
ER6668LT | W213 | W213.A30300 | TOR Essential Defueling Safety Case | 2022-05-23 | 2022-06-30 | Draft Review of flux detector suitability EAN | 23-May-22 A | 31-Aug-22 A | 38 | 0 | 69 | 100% |  | Completed
ER6650LT | W226 | 2750 | HYA Fuel Handling Essential Safety Case |  |  | Incorporate SRD, Station, ED (peer) comments | 23-May-22 A | 27-May-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.1460 | HYB Essential Defueling Safety Case | 2022-05-24 | 2022-05-24 | Hold Risk Workshop | 24-May-22 A | 24-May-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.3240 | HYB Essential Defueling Safety Case |  | 2022-07-13 | >>>OUTGOING ENABLER (W150) Optioneering Complete | 24-May-22 A | 24-May-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.3240 | TOR Essential Defueling Safety Case |  | 2022-07-13 | >>>OUTGOING ENABLER (W150) Optioneering Complete | 24-May-22 A | 24-May-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1460 | TOR Essential Defueling Safety Case | 2022-05-24 | 2022-05-24 | Hold Risk Workshop | 24-May-22 A | 24-May-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A30320 | HYB Essential Defueling Safety Case | 2022-05-24 | 2022-07-13 | Draft Safety Case Requirements EAN - TASK E EAN (A - B De-risking) | 24-May-22 A | 13-Jul-22 A | 33 | 0 | 35 | 100% |  | Completed
ER6668LT | W213 | W213.A30320 | TOR Essential Defueling Safety Case | 2022-05-24 | 2022-07-13 | Draft Safety Case Requirements EAN - TASK E EAN (A - B De-risking) | 24-May-22 A | 13-Jul-22 A | 33 | 0 | 35 | 100% |  | Completed
ER6666LT | W209 | W209.5310 | HYB Essential Defueling Safety Case |  | 2022-05-24 | Optioneering Complete - HYB Essential Defueling Safety Case | 24-May-22 A | 24-May-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.5310 | TOR Essential Defueling Safety Case |  | 2022-05-24 | Optioneering Complete - TOR Essential Defueling Safety Case | 24-May-22 A | 24-May-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1420 | HYB Essential Defueling Safety Case | 2022-05-25 | 2022-05-31 | Prepare Draft Project Definition Document (PDD) | 25-May-22 A | 31-May-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.1490 | HYB Essential Defueling Safety Case | 2022-05-25 | 2022-05-31 | Add Data to IAB Paper | 25-May-22 A | 31-May-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.1440 | HYB Essential Defueling Safety Case | 2022-05-25 | 2022-05-31 | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 25-May-22 A | 31-May-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.1430 | HYB Essential Defueling Safety Case | 2022-05-25 | 2022-05-31 | Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 25-May-22 A | 31-May-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.1420 | TOR Essential Defueling Safety Case | 2022-05-25 | 2022-05-31 | Prepare Draft Project Definition Document (PDD) | 25-May-22 A | 31-May-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.1490 | TOR Essential Defueling Safety Case | 2022-05-25 | 2022-05-31 | Add Data to IAB Paper | 25-May-22 A | 31-May-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.1440 | TOR Essential Defueling Safety Case | 2022-05-25 | 2022-05-31 | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 25-May-22 A | 31-May-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.1430 | TOR Essential Defueling Safety Case | 2022-05-25 | 2022-05-31 | Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 25-May-22 A | 31-May-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.7930 | HYB Essential Defueling Safety Case | 2022-05-26 | 2022-06-30 | Verify Human Factors Integration Plan EAN and Issue for Technical Review (REV 000) | 26-May-22 A | 17-Jun-22 A | 4 | 0 | 14 | 100% |  | Completed
ER6666LT | W209 | W209.A30430 | HYB Essential Defueling Safety Case | 2022-07-08 | 2022-07-13 | Technical Review of Reactor Internals & Structural Integrity During Defueling Report EAN (A-B-De-Risking) | 26-May-22 A | 13-Jul-22 A | 4 | 0 | 33 | 100% |  | Completed
ER6668LT | W213 | W213.7930 | TOR Essential Defueling Safety Case | 2022-05-26 | 2022-06-30 | Verify Human Factors Integration Plan EAN and Issue for Technical Review (REV 000) | 26-May-22 A | 17-Jun-22 A | 4 | 0 | 14 | 100% |  | Completed
ER6668LT | W213 | W213.A30430 | TOR Essential Defueling Safety Case | 2022-07-08 | 2022-07-13 | Technical Review of Reactor Internals & Structural Integrity During Defueling Report EAN (A-B-De-Risking) | 26-May-22 A | 13-Jul-22 A | 4 | 0 | 33 | 100% |  | Completed
ER6666LT | W209 | W209.28690 | HYB Essential Defueling Safety Case | 2023-03-01 | 2023-03-21 | Technical Review of PCPV Liner Impact Assessment | 27-May-22 A | 01-Jul-22 A | 15 | 0 | 24 | 100% |  | Completed
ER6668LT | W213 | W213.28690 | TOR Essential Defueling Safety Case | 2023-03-01 | 2023-03-21 | Technical Review of PCPV Liner Impact Assessment | 27-May-22 A | 01-Jul-22 A | 15 | 0 | 24 | 100% |  | Completed
ER6371LT | W202 | 2940 | HRA Reactors Shutdown Essential Safety Cases |  | 2022-05-27 | Issue final NSRS | 27-May-22 A | 27-May-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | 2940 | HYA Reactors Shutdown Essential Safety Cases |  | 2022-05-27 | Issue final NSRS | 27-May-22 A | 27-May-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 2740 | HYA Fuel Handling Essential Safety Case |  |  | Issue final NSRS | 27-May-22 A | 27-May-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1450 | HYB Essential Defueling Safety Case | 2022-05-30 | 2022-05-31 | Ensure Alignment of Schedule & Estimate | 30-May-22 A | 31-May-22 A | 2 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.5040 | HYB Essential Defueling Safety Case | 2022-05-30 | 2022-06-15 | Response to Tech Review Comments | 30-May-22 A | 01-Jul-22 A | 11 | 0 | 23 | 100% |  | Completed
ER6668LT | W213 | W213.1450 | TOR Essential Defueling Safety Case | 2022-05-30 | 2022-05-31 | Ensure Alignment of Schedule & Estimate | 30-May-22 A | 31-May-22 A | 2 | 0 | 2 | 100% |  | Completed
ER6668LT | W213 | W213.5040 | TOR Essential Defueling Safety Case | 2022-05-30 | 2022-06-15 | Response to Tech Review Comments | 30-May-22 A | 01-Jul-22 A | 11 | 0 | 23 | 100% |  | Completed
ER6371LT | W202 | 2960 | HRA Reactors Shutdown Essential Safety Cases |  | 2022-05-30 | Station agree NSRS | 30-May-22 A | 30-May-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | 2980 | HRA Reactors Shutdown Essential Safety Cases |  | 2022-05-30 | ED (DA) agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 30-May-22 A | 30-May-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | 2960 | HYA Reactors Shutdown Essential Safety Cases |  | 2022-05-30 | Station agree NSRS | 30-May-22 A | 30-May-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | 2980 | HYA Reactors Shutdown Essential Safety Cases |  | 2022-05-30 | ED (DA) agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 30-May-22 A | 30-May-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 2760 | HYA Fuel Handling Essential Safety Case |  |  | Station agree NSRS | 30-May-22 A | 30-May-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1470 | HYB Essential Defueling Safety Case | 2022-05-31 | 2022-05-31 | Complete Risk Log with Estimates | 31-May-22 A | 31-May-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1470 | TOR Essential Defueling Safety Case | 2022-05-31 | 2022-05-31 | Complete Risk Log with Estimates | 31-May-22 A | 31-May-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 2780 | HYA Fuel Handling Essential Safety Case |  |  | ED (DA) agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 31-May-22 A | 31-May-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1500 | HYB Essential Defueling Safety Case | 2022-06-01 | 2022-06-06 | PCL Validate & Approve Baseline Package for PRC Submission | 01-Jun-22 A | 06-Jun-22 A | 2 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.5240 | HYB Essential Defueling Safety Case | 2022-06-01 | 2022-07-13 | Produce Summary Document Outlining Status of Quality of Build Records (Jacobs) - (Cost Summary) ## | 01-Jun-22 A | 13-Jul-22 A | 29 | 0 | 29 | 100% |  | Completed
ER6666LT | W209 | W209.A26980 | HYB Essential Defueling Safety Case | 2022-06-01 | 2022-06-01 | Pre Job Brief for Review of FM Cyclic Duty EAN | 01-Jun-22 A | 10-Jun-22 A | 1 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.6130 | HYB Essential Defueling Safety Case | 2022-06-01 | 2022-06-10 | Prepare Spec for Fuel Route PSA Update EAN | 01-Jun-22 A | 02-Jun-22 A | 6 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.6520 | HYB Essential Defueling Safety Case | 2022-06-01 | 2022-06-09 | Prepare Spec for Quality of Build Records Retrieval EAN | 01-Jun-22 A | 01-Jul-22 A | 21 | 0 | 21 | 100% |  | Completed
ER6666LT | W209 | W209.6670 | HYB Essential Defueling Safety Case | 2022-06-01 | 2022-06-09 | Prepare Spec for Define Failed Fuel Free Controls EAN | 01-Jun-22 A | 01-Jul-22 A | 5 | 0 | 21 | 100% |  | Completed
ER6666LT | W209 | W209.A29310 | HYB Essential Defueling Safety Case | 2022-06-01 | 2022-06-09 | Draft Civil Integrity of Reactor Pressure Boundary Seals Integrity (Tech Report) - A - B De-risk Point | 01-Jun-22 A | 13-Jul-22 A | 5 | 0 | 28 | 100% |  | Completed
ER6666LT | W209 | W209.A29550 | HYB Essential Defueling Safety Case | 2022-06-01 | 2022-06-30 | Verify Flow Induced Vibration EAN & Issue for Technical Review | 01-Jun-22 A | 01-Jul-22 A | 20 | 0 | 21 | 100% |  | Completed
ER6668LT | W213 | W213.1500 | TOR Essential Defueling Safety Case | 2022-06-01 | 2022-06-06 | PCL Validate & Approve Baseline Package for PRC Submission | 01-Jun-22 A | 06-Jun-22 A | 2 | 0 | 2 | 100% |  | Completed
ER6668LT | W213 | W213.5240 | TOR Essential Defueling Safety Case | 2022-06-01 | 2022-07-13 | Produce Summary Document Outlining Status of Quality of Build Records (Jacobs) - (Cost Summary) ## | 01-Jun-22 A | 13-Jul-22 A | 29 | 0 | 29 | 100% |  | Completed
ER6668LT | W213 | W213.A26980 | TOR Essential Defueling Safety Case | 2022-06-01 | 2022-06-01 | Pre Job Brief for Review of FM Cyclic Duty EAN | 01-Jun-22 A | 10-Jun-22 A | 1 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.6130 | TOR Essential Defueling Safety Case | 2022-06-01 | 2022-06-10 | Prepare Spec for Fuel Route PSA Update EAN | 01-Jun-22 A | 02-Jun-22 A | 6 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.6520 | TOR Essential Defueling Safety Case | 2022-06-01 | 2022-06-09 | Prepare Spec for Quality of Build Records Retrieval EAN | 01-Jun-22 A | 01-Jul-22 A | 21 | 0 | 21 | 100% |  | Completed
ER6668LT | W213 | W213.6670 | TOR Essential Defueling Safety Case | 2022-06-01 | 2022-06-09 | Prepare Spec for Define Failed Fuel Free Controls EAN | 01-Jun-22 A | 01-Jul-22 A | 5 | 0 | 21 | 100% |  | Completed
ER6668LT | W213 | W213.A29310 | TOR Essential Defueling Safety Case | 2022-06-01 | 2022-06-09 | Draft Civil Integrity of Reactor Pressure Boundary Seals Integrity (Tech Report) - A - B De-risk Point | 01-Jun-22 A | 13-Jul-22 A | 5 | 0 | 28 | 100% |  | Completed
ER6668LT | W213 | W213.A29550 | TOR Essential Defueling Safety Case | 2022-06-01 | 2022-06-30 | Verify Flow Induced Vibration EAN & Issue for Technical Review | 01-Jun-22 A | 01-Jul-22 A | 20 | 0 | 21 | 100% |  | Completed
ER6666LT | W209 | W209.6140 | HYB Essential Defueling Safety Case | 2022-06-13 | 2022-06-24 | Prepare Task Sheet for Fuel Route PSA Update EAN | 02-Jun-22 A | 02-Jun-22 A | 10 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.6150 | HYB Essential Defueling Safety Case | 2022-06-27 | 2022-07-05 | Approve Task Sheet for Fuel Route PSA Update EAN | 02-Jun-22 A | 02-Jun-22 A | 7 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.6140 | TOR Essential Defueling Safety Case | 2022-06-13 | 2022-06-24 | Prepare Task Sheet for Fuel Route PSA Update EAN | 02-Jun-22 A | 02-Jun-22 A | 10 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.6150 | TOR Essential Defueling Safety Case | 2022-06-27 | 2022-07-05 | Approve Task Sheet for Fuel Route PSA Update EAN | 02-Jun-22 A | 02-Jun-22 A | 7 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7830 | HYB Essential Defueling Safety Case | 2022-07-06 | 2022-07-06 | Scope Assumptions Review PJB | 03-Jun-22 A | 03-Jun-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.7830 | TOR Essential Defueling Safety Case | 2022-07-06 | 2022-07-06 | Scope Assumptions Review PJB | 03-Jun-22 A | 03-Jun-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.8680 | HYB Essential Defueling Safety Case | 2022-07-07 | 2022-07-13 | Scope Assumptions Review (A-B De-risking) | 06-Jun-22 A | 13-Jul-22 A | 5 | 0 | 28 | 100% |  | Completed
ER6668LT | W213 | W213.8680 | TOR Essential Defueling Safety Case | 2022-07-07 | 2022-07-13 | Scope Assumptions Review (A-B De-risking) | 06-Jun-22 A | 13-Jul-22 A | 5 | 0 | 28 | 100% |  | Completed
ER6666LT | W209 | W209.3530 | HYB Essential Defueling Safety Case | 2022-06-06 | 2022-06-09 | Review Comments Addressed | 06-Jun-22 A | 09-Jun-22 A | 4 | 0 | 4 | 100% |  | Completed
ER6666LT | W209 | W209.1115 | HYB Essential Defueling Safety Case | 2022-06-06 | 2022-06-06 | Issue final NSRS | 06-Jun-22 A | 06-Jun-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A26190 | HYB Essential Defueling Safety Case | 2022-06-06 | 2022-07-13 | Draft Civil Integrity of Pressure Boundary Integrity of Seals Report EAN (A-B-De-Risking) | 06-Jun-22 A | 13-Jul-22 A | 28 | 0 | 28 | 100% |  | Completed
ER6666LT | W209 | W209.6390 | HYB Essential Defueling Safety Case | 2022-06-06 | 2022-06-14 | Approve Task Sheet for Update Basis of Analysis document EAN | 06-Jun-22 A | 14-Jun-22 A | 7 | 0 | 7 | 100% |  | Completed
ER6666LT | W209 | W209.A30540 | HYB Essential Defueling Safety Case | 2022-06-06 | 2022-07-13 | Draft Review of FM Cyclic Duty EAN (A - B De-risking) | 06-Jun-22 A | 13-Jul-22 A | 28 | 0 | 28 | 100% |  | Completed
ER6668LT | W213 | W213.3530 | TOR Essential Defueling Safety Case | 2022-06-06 | 2022-06-09 | Review Comments Addressed | 06-Jun-22 A | 09-Jun-22 A | 4 | 0 | 4 | 100% |  | Completed
ER6668LT | W213 | W213.1115 | TOR Essential Defueling Safety Case | 2022-06-06 | 2022-06-06 | Issue final NSRS | 06-Jun-22 A | 06-Jun-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A26190 | TOR Essential Defueling Safety Case | 2022-06-06 | 2022-07-13 | Draft Civil Integrity of Pressure Boundary Integrity of Seals Report EAN (A-B-De-Risking) | 06-Jun-22 A | 13-Jul-22 A | 28 | 0 | 28 | 100% |  | Completed
ER6668LT | W213 | W213.6390 | TOR Essential Defueling Safety Case | 2022-06-06 | 2022-06-14 | Approve Task Sheet for Update Basis of Analysis document EAN | 06-Jun-22 A | 14-Jun-22 A | 7 | 0 | 7 | 100% |  | Completed
ER6668LT | W213 | W213.A30540 | TOR Essential Defueling Safety Case | 2022-06-06 | 2022-07-13 | Draft Review of FM Cyclic Duty EAN (A - B De-risking) | 06-Jun-22 A | 13-Jul-22 A | 28 | 0 | 28 | 100% |  | Completed
ER6666LT | W209 | W209.A29790 | HYB Essential Defueling Safety Case | 2022-06-07 | 2022-06-07 | Pre Job Brief for Feasibility of Draining PVCS (Report) | 07-Jun-22 A | 01-Jul-22 A | 1 | 0 | 19 | 100% |  | Completed
ER6668LT | W213 | W213.A29790 | TOR Essential Defueling Safety Case | 2022-06-07 | 2022-06-07 | Pre Job Brief for Feasibility of Draining PVCS (Report) | 07-Jun-22 A | 01-Jul-22 A | 1 | 0 | 19 | 100% |  | Completed
ER6666LT | W209 | W209.1510 | HYB Essential Defueling Safety Case | 2022-06-08 | 2022-06-08 | Gate B PRC Paper Submission | 08-Jun-22 A | 08-Jun-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.1125 | HYB Essential Defueling Safety Case | 2022-06-08 | 2022-06-10 | DA & INA agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 08-Jun-22 A | 10-Jun-22 A | 3 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.1135 | HYB Essential Defueling Safety Case | 2022-06-08 | 2022-06-10 | Station agree NSRS | 08-Jun-22 A | 10-Jun-22 A | 3 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.1510 | TOR Essential Defueling Safety Case | 2022-06-08 | 2022-06-08 | Gate B PRC Paper Submission | 08-Jun-22 A | 08-Jun-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.1125 | TOR Essential Defueling Safety Case | 2022-06-08 | 2022-06-10 | DA & INA agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 08-Jun-22 A | 10-Jun-22 A | 3 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.1135 | TOR Essential Defueling Safety Case | 2022-06-08 | 2022-06-10 | Station agree NSRS | 08-Jun-22 A | 10-Jun-22 A | 3 | 0 | 3 | 100% |  | Completed
ER6371LT | W202 | 2990 | HRA Reactors Shutdown Essential Safety Cases |  | 2022-06-08 | SRD agree NSRS | 08-Jun-22 A | 08-Jun-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | 2990 | HYA Reactors Shutdown Essential Safety Cases |  | 2022-06-08 | SRD agree NSRS | 08-Jun-22 A | 08-Jun-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 2790 | HYA Fuel Handling Essential Safety Case |  |  | SRD agree NSRS | 08-Jun-22 A | 08-Jun-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1520 | HYB Essential Defueling Safety Case | 2022-06-09 | 2022-06-15 | PRC Members Review IAB Documentation | 09-Jun-22 A | 15-Jun-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.1520 | TOR Essential Defueling Safety Case | 2022-06-09 | 2022-06-15 | PRC Members Review IAB Documentation | 09-Jun-22 A | 15-Jun-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | 2992 | HRA Reactors Shutdown Essential Safety Cases |  | 2022-06-09 | Share NSRS with NSC ahead of Meeting Date (T-2 wks) | 09-Jun-22 A | 09-Jun-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | 2992 | HYA Reactors Shutdown Essential Safety Cases |  | 2022-06-09 | Share NSRS with NSC ahead of Meeting Date (T-2 wks) | 09-Jun-22 A | 09-Jun-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 2794 | HYA Fuel Handling Essential Safety Case |  |  | Share NSRS with NSC ahead of Meeting Date (T-2 wks) | 09-Jun-22 A | 09-Jun-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1620 | HNB Reactors Shutdown Essential Safety Cases | 2021-07-16 | 2021-07-29 | Develop Implementation & closeout Plan (HNB) | 13-Jun-22 A | 10-Aug-22 A | 13 | 0 | 42 | 100% |  | Completed
ER6666LT | W209 | W209.7940 | HYB Essential Defueling Safety Case | 2022-07-01 | 2022-07-06 | Supplier Update and Issue Human Factors Integration Plan EAN (REV 000) | 20-Jun-22 A | 06-Jul-22 A | 4 | 0 | 13 | 100% |  | Completed
ER6668LT | W213 | W213.7940 | TOR Essential Defueling Safety Case | 2022-07-01 | 2022-07-06 | Supplier Update and Issue Human Factors Integration Plan EAN (REV 000) | 20-Jun-22 A | 06-Jul-22 A | 4 | 0 | 13 | 100% |  | Completed
ER6666LT | W209 | W209.1530 | HYB Essential Defueling Safety Case | 2022-06-21 | 2022-06-21 | Hold PRC Meeting | 21-Jun-22 A | 21-Jun-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.1530 | TOR Essential Defueling Safety Case | 2022-06-21 | 2022-06-21 | Hold PRC Meeting | 21-Jun-22 A | 21-Jun-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.1550 | HYB Essential Defueling Safety Case | 2022-06-22 | 2022-06-22 | Modify Estimate, Schedule & Risk Log as Required | 22-Jun-22 A | 22-Jun-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.1360 | HYB Essential Defueling Safety Case |  | 2022-06-22 | >>>OUTGOING ENABLER (W150, W273) NSRS Scope Complete | 22-Jun-22 A | 22-Jun-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.3160 | HYB Essential Defueling Safety Case |  | 2022-06-22 | Discovery Milestone - NSRS Completion - Proceed with Safety Case (HYB) | 22-Jun-22 A | 22-Jun-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1145 | HYB Essential Defueling Safety Case | 2022-06-22 | 2022-06-22 | NSRS Presented to NSC (for complex CAT 1 cases) | 22-Jun-22 A | 22-Jun-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | 2995 | HRA Reactors Shutdown Essential Safety Cases |  | 2022-06-22 | Share NSRS with NSC | 22-Jun-22 A | 22-Jun-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | 2995 | HYA Reactors Shutdown Essential Safety Cases |  | 2022-06-22 | Share NSRS with NSC | 22-Jun-22 A | 22-Jun-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1550 | TOR Essential Defueling Safety Case | 2022-06-22 | 2022-06-22 | Modify Estimate, Schedule & Risk Log as Required | 22-Jun-22 A | 22-Jun-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.3160 | TOR Essential Defueling Safety Case |  | 2022-06-22 | Discovery Milestone - NSRS Completion - Proceed with Safety Case (TOR) | 22-Jun-22 A | 22-Jun-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1145 | TOR Essential Defueling Safety Case | 2022-06-22 | 2022-06-22 | NSRS Presented to NSC (for complex CAT 1 cases) | 22-Jun-22 A | 22-Jun-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 2795 | HYA Fuel Handling Essential Safety Case |  |  | Present NSRS to NSC Meeting | 22-Jun-22 A | 22-Jun-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1032 | HYB Essential Defueling Safety Case |  | 2022-06-22 | NSRS Presented at NSC - EC 371387 - HYB Essential Defueling Safety Case | 22-Jun-22 A | 22-Jun-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1360 | TOR Essential Defueling Safety Case |  | 2022-06-22 | >>>OUTGOING ENABLER (W152, W274) NSRS Scope Complete | 22-Jun-22 A | 22-Jun-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1032 | TOR Essential Defueling Safety Case |  | 2022-06-22 | NSRS Presented at NSC - EC 371387 - TOR Essential Defueling Safety Case | 22-Jun-22 A | 22-Jun-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1560 | HYB Essential Defueling Safety Case | 2022-06-23 | 2022-06-23 | Modify IAB Paper as Required | 23-Jun-22 A | 24-Jun-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.28790 | HYB Essential Defueling Safety Case |  |  | Circulate NSRS for Relevant Stakeholders (A-B Part) | 23-Jun-22 A | 13-Jul-22 A | 5 | 0 | 14 | 100% |  | Completed
ER6668LT | W213 | W213.1560 | TOR Essential Defueling Safety Case | 2022-06-23 | 2022-06-23 | Modify IAB Paper as Required | 23-Jun-22 A | 24-Jun-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.28790 | TOR Essential Defueling Safety Case |  |  | Circulate NSRS for Relevant Stakeholders (A-B Part) | 23-Jun-22 A | 13-Jul-22 A | 5 | 0 | 14 | 100% |  | Completed
ER6666LT | W209 | W209.A30870 | HYB Essential Defueling Safety Case |  |  | Verify FPU Maintenance Work EAN & Issue for Technic (A-B De-Risking) | 27-Jun-22 A | 13-Jul-22 A | 25 | 0 | 12 | 100% |  | Completed
ER6668LT | W213 | W213.A30870 | TOR Essential Defueling Safety Case |  |  | Verify FPU Maintenance Work EAN & Issue for Technic (A-B De-Risking) | 27-Jun-22 A | 13-Jul-22 A | 25 | 0 | 12 | 100% |  | Completed
ER6666LT | W209 | W209.A28020 | HYB Essential Defueling Safety Case | 2022-06-15 | 2022-06-15 | Pre Job Brief for Update Basis of Analysis document EAN | 01-Jul-22 A | 01-Jul-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A28420 | HYB Essential Defueling Safety Case | 2022-06-27 | 2022-06-27 | Pre Job Brief for Quality of Build Records Retrieval EAN | 01-Jul-22 A | 01-Jul-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.6640 | HYB Essential Defueling Safety Case | 2022-07-01 | 2022-07-07 | Prepare Spec for Fuel Free Verification (FFV) Reports EAN | 01-Jul-22 A | 07-Jul-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A28020 | TOR Essential Defueling Safety Case | 2022-06-15 | 2022-06-15 | Pre Job Brief for Update Basis of Analysis document EAN | 01-Jul-22 A | 01-Jul-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A28420 | TOR Essential Defueling Safety Case | 2022-06-27 | 2022-06-27 | Pre Job Brief for Quality of Build Records Retrieval EAN | 01-Jul-22 A | 01-Jul-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.6640 | TOR Essential Defueling Safety Case | 2022-07-01 | 2022-07-07 | Prepare Spec for Fuel Free Verification (FFV) Reports EAN | 01-Jul-22 A | 07-Jul-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.1630 | HYB Essential Defueling Safety Case | 2022-07-04 | 2022-07-04 | Gate B IAB Paper Submission | 04-Jul-22 A | 04-Jul-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A25690 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-08-17 | Judgement Based Work Diversion EAN ## (Cost Summary) (Claim 2) | 04-Jul-22 A | 31-Mar-23 A | 191 | 0 | 191 | 100% |  | Completed
ER6666LT | W209 | W209.A28430 | HYB Essential Defueling Safety Case | 2022-06-28 | 2022-07-13 | Draft Quality of Build Records Retrieval EAN (A - B Derisk) | 04-Jul-22 A | 13-Jul-22 A | 8 | 0 | 8 | 100% |  | Completed
ER6666LT | W209 | W209.A28600 | HYB Essential Defueling Safety Case | 2022-06-06 | 2022-07-04 | Verify Radiological Consequences Following Failed CSP EAN & Issue for Technical Review | 04-Jul-22 A | 06-Jul-22 A | 3 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.28700 | HYB Essential Defueling Safety Case | 2023-03-22 | 2023-03-28 | Supplier Update and Issue PCPV Liner Impact Assessment | 04-Jul-22 A | 07-Jul-22 A | 4 | 0 | 4 | 100% |  | Completed
ER6666LT | W209 | W209.6680 | HYB Essential Defueling Safety Case | 2022-06-10 | 2022-06-23 | Prepare Task Sheet for Define Failed Fuel Free Controls EAN | 04-Jul-22 A | 05-Jul-22 A | 2 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.7610 | HYB Essential Defueling Safety Case | 2022-06-08 | 2022-06-20 | Issue Verified Defueling Engineering Specification | 04-Jul-22 A | 07-Jul-22 A | 4 | 0 | 4 | 100% |  | Completed
ER6666LT | W209 | W209.A30260 | HYB Essential Defueling Safety Case | 2022-06-06 | 2022-06-30 | Verify Define Nuclear Data (PANTHER Validation Calcs) EAN & Issue for Technical Review | 04-Jul-22 A | 06-Jul-22 A | 3 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.A30370 | HYB Essential Defueling Safety Case | 2022-06-08 | 2022-07-13 | Draft Feasibility of Draining PVCS (Report) (A - B De-risking) | 04-Jul-22 A | 13-Jul-22 A | 8 | 0 | 8 | 100% |  | Completed
ER6666LT | W209 | W209.A30390 | HYB Essential Defueling Safety Case | 2022-07-01 | 2022-07-13 | Technical Review of Review of Flow Induced Vibration EAN (A-B De-risking) | 04-Jul-22 A | 13-Jul-22 A | 8 | 0 | 8 | 100% |  | Completed
ER6666LT | W209 | W209.A30400 | HYB Essential Defueling Safety Case | 2022-06-16 | 2022-07-13 | Draft Update Basis of Analysis document EAN (A - B De-risking) | 04-Jul-22 A | 13-Jul-22 A | 8 | 0 | 8 | 100% |  | Completed
ER6666LT | W209 | W209.A30850 | HYB Essential Defueling Safety Case | 2022-06-16 | 2022-07-06 | Verify Judgement Based Work Diversion EAN and Issue for Technical Review | 04-Jul-22 A | 23-Sep-22 A | 3 | 0 | 58 | 100% |  | Completed
ER6668LT | W213 | W213.1630 | TOR Essential Defueling Safety Case | 2022-07-04 | 2022-07-04 | Gate B IAB Paper Submission | 04-Jul-22 A | 04-Jul-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A25690 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-08-17 | Judgement Based Work Diversion EAN ## (Cost Summary) (Claim 2) | 04-Jul-22 A | 31-Mar-23 A | 191 | 0 | 191 | 100% |  | Completed
ER6668LT | W213 | W213.A28430 | TOR Essential Defueling Safety Case | 2022-06-28 | 2022-07-13 | Draft Quality of Build Records Retrieval EAN (A - B Derisk) | 04-Jul-22 A | 13-Jul-22 A | 8 | 0 | 8 | 100% |  | Completed
ER6668LT | W213 | W213.A28600 | TOR Essential Defueling Safety Case | 2022-06-06 | 2022-07-04 | Verify Radiological Consequences Following Failed CSP EAN & Issue for Technical Review | 04-Jul-22 A | 06-Jul-22 A | 3 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.28700 | TOR Essential Defueling Safety Case | 2023-03-22 | 2023-03-28 | Supplier Update and Issue PCPV Liner Impact Assessment | 04-Jul-22 A | 07-Jul-22 A | 4 | 0 | 4 | 100% |  | Completed
ER6668LT | W213 | W213.6680 | TOR Essential Defueling Safety Case | 2022-06-10 | 2022-06-23 | Prepare Task Sheet for Define Failed Fuel Free Controls EAN | 04-Jul-22 A | 05-Jul-22 A | 2 | 0 | 2 | 100% |  | Completed
ER6668LT | W213 | W213.7610 | TOR Essential Defueling Safety Case | 2022-06-08 | 2022-06-20 | Issue Verified Defueling Engineering Specification | 04-Jul-22 A | 07-Jul-22 A | 4 | 0 | 4 | 100% |  | Completed
ER6668LT | W213 | W213.A30260 | TOR Essential Defueling Safety Case | 2022-06-06 | 2022-06-30 | Verify Define Nuclear Data (PANTHER Validation Calcs) EAN & Issue for Technical Review | 04-Jul-22 A | 06-Jul-22 A | 3 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.A30370 | TOR Essential Defueling Safety Case | 2022-06-08 | 2022-07-13 | Draft Feasibility of Draining PVCS (Report) (A - B De-risking) | 04-Jul-22 A | 13-Jul-22 A | 8 | 0 | 8 | 100% |  | Completed
ER6668LT | W213 | W213.A30390 | TOR Essential Defueling Safety Case | 2022-07-01 | 2022-07-13 | Technical Review of Review of Flow Induced Vibration EAN (A-B De-risking) | 04-Jul-22 A | 13-Jul-22 A | 8 | 0 | 8 | 100% |  | Completed
ER6668LT | W213 | W213.A30400 | TOR Essential Defueling Safety Case | 2022-06-16 | 2022-07-13 | Draft Update Basis of Analysis document EAN (A - B De-risking) | 04-Jul-22 A | 13-Jul-22 A | 8 | 0 | 8 | 100% |  | Completed
ER6668LT | W213 | W213.A30850 | TOR Essential Defueling Safety Case | 2022-06-16 | 2022-07-06 | Verify Judgement Based Work Diversion EAN and Issue for Technical Review | 04-Jul-22 A | 23-Sep-22 A | 3 | 0 | 58 | 100% |  | Completed
ER6666LT | W209 | W209.1580 | HYB Essential Defueling Safety Case | 2022-07-05 | 2022-07-08 | IAB Members Review IAB Documentation | 05-Jul-22 A | 08-Jul-22 A | 4 | 0 | 4 | 100% |  | Completed
ER6668LT | W213 | W213.1580 | TOR Essential Defueling Safety Case | 2022-07-05 | 2022-07-08 | IAB Members Review IAB Documentation | 05-Jul-22 A | 08-Jul-22 A | 4 | 0 | 4 | 100% |  | Completed
ER6666LT | W209 | W209.A26340 | HYB Essential Defueling Safety Case | 2022-06-01 | 2022-06-01 | Pre Job Brief for Graphite Summary Report EAN | 06-Jul-22 A | 06-Jul-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.6690 | HYB Essential Defueling Safety Case | 2022-06-24 | 2022-07-04 | Approve Task Sheet for Define Failed Fuel Free Controls EAN | 06-Jul-22 A | 07-Jul-22 A | 2 | 0 | 2 | 100% |  | Completed
ER6668LT | W213 | W213.A26340 | TOR Essential Defueling Safety Case | 2022-06-01 | 2022-06-01 | Pre Job Brief for Graphite Summary Report EAN | 06-Jul-22 A | 06-Jul-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.6690 | TOR Essential Defueling Safety Case | 2022-06-24 | 2022-07-04 | Approve Task Sheet for Define Failed Fuel Free Controls EAN | 06-Jul-22 A | 07-Jul-22 A | 2 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.A28610 | HYB Essential Defueling Safety Case | 2022-07-05 | 2022-07-13 | Technical Review of Radiological Consequences Following Failed CSP EAN (A - B Derisk) | 07-Jul-22 A | 13-Jul-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.7950 | HYB Essential Defueling Safety Case | 2022-07-07 | 2022-07-13 | Complete TR Form and Upload Human Factors Integration Plan EAN to CDMS (REV 000) | 07-Jul-22 A | 13-Jul-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.A30270 | HYB Essential Defueling Safety Case | 2022-07-01 | 2022-07-13 | Technical Review of Define Nuclear Data (PANTHER Validation Calcs) EAN - (CLAIM 1 - A - B De-risking) | 07-Jul-22 A | 13-Jul-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.A30530 | HYB Essential Defueling Safety Case | 2022-06-06 | 2022-07-13 | Draft Graphite Summary Report EAN (A-B De-risking) | 07-Jul-22 A | 13-Jul-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A28610 | TOR Essential Defueling Safety Case | 2022-07-05 | 2022-07-13 | Technical Review of Radiological Consequences Following Failed CSP EAN (A - B Derisk) | 07-Jul-22 A | 13-Jul-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.7950 | TOR Essential Defueling Safety Case | 2022-07-07 | 2022-07-13 | Complete TR Form and Upload Human Factors Integration Plan EAN to CDMS (REV 000) | 07-Jul-22 A | 13-Jul-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A30270 | TOR Essential Defueling Safety Case | 2022-07-01 | 2022-07-13 | Technical Review of Define Nuclear Data (PANTHER Validation Calcs) EAN - (CLAIM 1 - A - B De-risking) | 07-Jul-22 A | 13-Jul-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A30530 | TOR Essential Defueling Safety Case | 2022-06-06 | 2022-07-13 | Draft Graphite Summary Report EAN (A-B De-risking) | 07-Jul-22 A | 13-Jul-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.28710 | HYB Essential Defueling Safety Case | 2023-03-29 | 2023-04-04 | Complete TR Form and Upload PCPV Liner Impact Assessment to CDMS | 08-Jul-22 A | 13-Jul-22 A | 4 | 0 | 4 | 100% |  | Completed
ER6666LT | W209 | W209.A28820 | HYB Essential Defueling Safety Case | 2022-07-05 | 2022-07-05 | Pre Job Brief for Define Failed Fuel Free Controls EAN | 08-Jul-22 A | 08-Jul-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.7620 | HYB Essential Defueling Safety Case | 2022-06-21 | 2022-07-11 | EDF Technical Review | 08-Jul-22 A | 13-Jul-22 A | 4 | 0 | 4 | 100% |  | Completed
ER6666LT | W209 | W209.8690 | HYB Essential Defueling Safety Case | 2022-07-08 | 2022-07-13 | Prepare Task Sheet for Fuel Free Verification (FFV) Reports EAN | 08-Jul-22 A | 13-Jul-22 A | 4 | 0 | 4 | 100% |  | Completed
ER6668LT | W213 | W213.28710 | TOR Essential Defueling Safety Case | 2023-03-29 | 2023-04-04 | Complete TR Form and Upload PCPV Liner Impact Assessment to CDMS | 08-Jul-22 A | 13-Jul-22 A | 4 | 0 | 4 | 100% |  | Completed
ER6668LT | W213 | W213.A28820 | TOR Essential Defueling Safety Case | 2022-07-05 | 2022-07-05 | Pre Job Brief for Define Failed Fuel Free Controls EAN | 08-Jul-22 A | 08-Jul-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.7620 | TOR Essential Defueling Safety Case | 2022-06-21 | 2022-07-11 | EDF Technical Review | 08-Jul-22 A | 13-Jul-22 A | 4 | 0 | 4 | 100% |  | Completed
ER6668LT | W213 | W213.8690 | TOR Essential Defueling Safety Case | 2022-07-08 | 2022-07-13 | Prepare Task Sheet for Fuel Free Verification (FFV) Reports EAN | 08-Jul-22 A | 13-Jul-22 A | 4 | 0 | 4 | 100% |  | Completed
ER6666LT | W209 | W209.A30580 | HYB Essential Defueling Safety Case | 2022-07-06 | 2022-07-13 | Draft Define Failed Fuel Free Controls EAN | 11-Jul-22 A | 13-Jul-22 A | 3 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.A30780 | HYB Essential Defueling Safety Case | 2022-07-11 | 2022-07-13 | Verify FPU Integrity Work EAN & Issue for Technic (A - B Derisk to Claim 3 and 5) | 11-Jul-22 A | 13-Jul-22 A | 3 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.A30580 | TOR Essential Defueling Safety Case | 2022-07-06 | 2022-07-13 | Draft Define Failed Fuel Free Controls EAN | 11-Jul-22 A | 13-Jul-22 A | 3 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.A30780 | TOR Essential Defueling Safety Case | 2022-07-11 | 2022-07-13 | Verify FPU Integrity Work EAN & Issue for Technic (A - B Derisk to Claim 3 and 5) | 11-Jul-22 A | 13-Jul-22 A | 3 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.28720 | HYB Essential Defueling Safety Case |  | 2023-04-04 | PCPV Liner Impact Assessment Available | 13-Jul-22 A | 13-Jul-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7960 | HYB Essential Defueling Safety Case |  | 2022-07-13 | Human Factors Integration Plan EAN Available (REV 000) (A-B Derisk for WP1 & WP2) | 13-Jul-22 A | 13-Jul-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.28720 | TOR Essential Defueling Safety Case |  | 2023-04-04 | PCPV Liner Impact Assessment Available | 13-Jul-22 A | 13-Jul-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.7960 | TOR Essential Defueling Safety Case |  | 2022-07-13 | Human Factors Integration Plan EAN Available (REV 000) (A-B Derisk for WP1 & WP2) | 13-Jul-22 A | 13-Jul-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1058 | HYB Essential Defueling Safety Case |  | 2022-07-14 | Gate B - IAB Paper Approval (HYB) | 14-Jul-22 A | 14-Jul-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1155 | HYB Essential Defueling Safety Case | 2022-06-23 | 2022-06-29 | Circulate NSRS for Relevant Stakeholders | 14-Jul-22 A | 01-Aug-22 A | 5 | 0 | 13 | 100% |  | Completed
ER6666LT | W209 | W209.7630 | HYB Essential Defueling Safety Case | 2022-03-18 | 2022-05-31 | Production of Civils Assessment Report for PCPV Integrity Justification | 14-Jul-22 A | 05-Aug-22 A | 1 | 0 | 17 | 100% |  | Completed
ER6666LT | W209 | W209.7650 | HYB Essential Defueling Safety Case | 2022-03-18 | 2022-05-31 | Production of Civils Assessment Report for Seismic Assessment | 14-Jul-22 A | 05-Aug-22 A | 40 | 0 | 17 | 100% |  | Completed
ER6666LT | W209 | W209.A29720 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-10-28 | ALARP Review of Not Draining the PVCS (Report) ## (Cost Summary) (Claim 2) | 14-Jul-22 A | 19-May-23 A | 205 | 0 | 213 | 100% |  | Completed
ER6666LT | W209 | W209.A29740 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-09-09 | Draft PARTIAL Drain down of the PVCS prior to Defuelling (Report) | 14-Jul-22 A | 29-Jul-22 A | 41 | 0 | 11 | 100% |  | Completed
ER6668LT | W213 | W213.1058 | TOR Essential Defueling Safety Case |  | 2022-07-14 | Gate B - IAB Paper Approval (TOR) | 14-Jul-22 A | 14-Jul-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1155 | TOR Essential Defueling Safety Case | 2022-06-23 | 2022-06-29 | Circulate NSRS for Relevant Stakeholders | 14-Jul-22 A | 01-Aug-22 A | 5 | 0 | 13 | 100% |  | Completed
ER6668LT | W213 | W213.7630 | TOR Essential Defueling Safety Case | 2022-03-18 | 2022-05-31 | Production of Civils Assessment Report for PCPV Integrity Justification | 14-Jul-22 A | 05-Aug-22 A | 1 | 0 | 17 | 100% |  | Completed
ER6668LT | W213 | W213.7650 | TOR Essential Defueling Safety Case | 2022-03-18 | 2022-05-31 | Production of Civils Assessment Report for Seismic Assessment | 14-Jul-22 A | 05-Aug-22 A | 40 | 0 | 17 | 100% |  | Completed
ER6668LT | W213 | W213.A29720 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-10-28 | ALARP Review of Not Draining the PVCS (Report) ## (Cost Summary) (Claim 2) | 14-Jul-22 A | 19-May-23 A | 205 | 0 | 213 | 100% |  | Completed
ER6668LT | W213 | W213.A29740 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-09-09 | Draft PARTIAL Drain down of the PVCS prior to Defuelling (Report) | 14-Jul-22 A | 29-Jul-22 A | 41 | 0 | 11 | 100% |  | Completed
ER6666LT | W209 | W209.3110 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-07-14 | Hold IAB | 14-Jul-22 A | 14-Jul-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A25850 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-11-16 | Safety Case Requirements EAN - TASK E EAN ## (Cost Summary) (Claim 2) | 14-Jul-22 A | 21-Apr-23 A | 196 | 0 | 196 | 100% |  | Completed
ER6666LT | W209 | W209.A25870 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-08-31 | Draft Safety Case Requirements EAN - TASK E EAN | 14-Jul-22 A | 29-Sep-22 A | 34 | 0 | 55 | 100% |  | Completed
ER6666LT | W209 | W209.A25930 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-10-24 | Civil Assesment of the Ponds at Low Temperature EAN ## (Cost Summary) (Claim 2) | 14-Jul-22 A | 07-Dec-22 A | 104 | 0 | 104 | 100% |  | Completed
ER6666LT | W209 | W209.A25950 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-08-12 | Draft Civil Assesment of the Ponds at Low Temperature EAN | 14-Jul-22 A | 05-Aug-22 A | 22 | 0 | 17 | 100% |  | Completed
ER6666LT | W209 | W209.A26010 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-11-03 | Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN ## (Cost Summary) (Claim 3) | 14-Jul-22 A | 07-Dec-22 A | 104 | 0 | 104 | 100% |  | Completed
ER6666LT | W209 | W209.A26030 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-08-24 | Draft Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN | 14-Jul-22 A | 05-Aug-22 A | 30 | 0 | 16 | 100% |  | Completed
ER6666LT | W209 | W209.A26170 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-09-19 | Pressure Boundary Integrity of Seals Report EAN ## (Cost Summary) (Claim 3) | 14-Jul-22 A | 30-Nov-22 A | 99 | 0 | 99 | 100% |  | Completed
ER6666LT | W209 | W209.A26250 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-08-25 | Reactor Internals & Structural Integrity During Defueling Report EAN ## (Cost Summary) (Claim 3) | 14-Jul-22 A | 04-Nov-22 A | 86 | 0 | 81 | 100% |  | Completed
ER6666LT | W209 | W209.A26290 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-08-11 | Technical Review of Reactor Internals & Structural Integrity During Defueling Report EAN | 14-Jul-22 A | 19-Aug-22 A | 21 | 0 | 27 | 100% |  | Completed
ER6666LT | W209 | W209.A26330 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-10-31 | Graphite Summary Report EAN ## (Cost Summary) (Claim 3) | 14-Jul-22 A | 03-Mar-23 A | 163 | 0 | 163 | 100% |  | Completed
ER6666LT | W209 | W209.A26350 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-08-25 | Draft Graphite Summary Report EAN | 14-Jul-22 A | 31-Jan-23 A | 31 | 0 | 139 | 100% |  | Completed
ER6666LT | W209 | W209.A26730 | HYB Essential Defueling Safety Case | 2022-07-14 | 2023-01-03 | Boron Bead Inj Feasibility & Boron Bead Injection Feasibility & Control Rod Isolation EAN ## (Cost Summary) (Claim 1) | 14-Jul-22 A | 21-Apr-23 A | 196 | 0 | 196 | 100% |  | Completed
ER6666LT | W209 | W209.A26750 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-09-08 | Draft Boron Bead Injection Feasibility & Control Rod Isolation EAN | 14-Jul-22 A | 08-Sep-22 A | 40 | 0 | 40 | 100% |  | Completed
ER6666LT | W209 | W209.A26970 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-12-02 | Review of FM Cyclic Duty EAN ## (Cost Summary) (Claim 3) | 14-Jul-22 A | 31-Oct-22 A | 66 | 0 | 76 | 100% |  | Completed
ER6666LT | W209 | W209.A26990 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-09-09 | Draft Review of FM Cyclic Duty EAN | 14-Jul-22 A | 22-Jul-22 A | 41 | 0 | 6 | 100% |  | Completed
ER6666LT | W209 | W209.A27050 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-11-08 | FPU Integrity Analysis EAN ## (Cost Summary) (Claim 3) | 14-Jul-22 A | 12-May-23 A | 203 | 0 | 208 | 100% |  | Completed
ER6666LT | W209 | W209.A27080 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-09-13 | Verify Review of FPU Integrity Analysis EAN & Issue for Technical Review | 14-Jul-22 A | 17-Feb-23 A | 43 | 0 | 153 | 100% |  | Completed
ER6666LT | W209 | W209.A27170 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-07-21 | Technical Review of Review of Flow Induced Vibration EAN | 14-Jul-22 A | 02-Sep-22 A | 6 | 0 | 36 | 100% |  | Completed
ER6666LT | W209 | W209.A27370 | HYB Essential Defueling Safety Case | 2022-07-14 | 2023-11-15 | Fuel Route Defueling PSA Update ## (Cost Summary) (Claim 5) | 14-Jul-22 A | 31-Jul-24 A | 518 | 0 | 518 | 100% |  | Completed
ER6666LT | W209 | W209.A28010 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-09-19 | Update Basis of Analysis document ## (Cost Summary) (Claim 4) | 14-Jul-22 A | 07-Mar-23 A | 165 | 0 | 165 | 100% |  | Completed
ER6666LT | W209 | W209.A28030 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-07-15 | Draft Update Basis of Analysis document | 14-Jul-22 A | 15-Jul-22 A | 2 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.A28090 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-08-23 | Develop FEA Model ## (Cost Summary) (Claim 4) | 14-Jul-22 A | 31-Aug-22 A | 36 | 0 | 33 | 100% |  | Completed
ER6666LT | W209 | W209.A28110 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-07-18 | Develop FEA Model | 14-Jul-22 A | 18-Jul-22 A | 3 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.A28410 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-09-12 | Summary of Credible Start of Life Defects EAN ## (Cost Summary) (Claim 4) | 14-Jul-22 A | 22-Dec-22 A | 123 | 0 | 114 | 100% |  | Completed
ER6666LT | W209 | W209.A28570 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-12-14 | Radiological Consequences Following Failed CSP EAN ## (Cost Summary) (Claim 4) | 14-Jul-22 A | 07-Mar-23 A | 165 | 0 | 165 | 100% |  | Completed
ER6666LT | W209 | W209.A28730 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-12-13 | Fuel Free Verification (FFV) Reports EAN ## (Cost Summary) (Claim 6) | 14-Jul-22 A | 31-Mar-23 A | 163 | 0 | 182 | 100% |  | Completed
ER6666LT | W209 | W209.A28810 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-11-29 | Define Failed Fuel Free Controls File Note ## (Cost Summary) (Claim 6) | 14-Jul-22 A | 23-Dec-22 A | 116 | 0 | 116 | 100% |  | Completed
ER6666LT | W209 | W209.A28830 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-09-27 | Draft Define Failed Fuel Free Controls File Note (Rhod) | 14-Jul-22 A | 09-Dec-22 A | 53 | 0 | 106 | 100% |  | Completed
ER6666LT | W209 | W209.6650 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-07-21 | Prepare Task Sheet for Fuel Free Verification methods, an assessment against the ALARP principle EAN | 14-Jul-22 A | 15-Jul-22 A | 6 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A29370 | HYB Essential Defueling Safety Case | 2022-07-14 | 2023-01-12 | Cooling Plant Availability Review EAN ## (Cost Summary) (Claim 2) | 14-Jul-22 A | 17-Feb-23 A | 147 | 0 | 152 | 100% |  | Completed
ER6666LT | W209 | W209.A29390 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-10-17 | Draft Cooling Plant Availability Review EAN | 14-Jul-22 A | 24-Nov-22 A | 67 | 0 | 94 | 100% |  | Completed
ER6666LT | W209 | W209.A29450 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-10-28 | Cooling Plant OPEX Study EAN ## (Cost Summary) (Claim 2) | 14-Jul-22 A | 11-Nov-22 A | 86 | 0 | 86 | 100% |  | Completed
ER6666LT | W209 | W209.A29470 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-09-02 | Draft Cooling Plant OPEX Study EAN | 14-Jul-22 A | 19-Aug-22 A | 36 | 0 | 26 | 100% |  | Completed
ER6666LT | W209 | W209.7840 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-08-03 | Scope Assumptions Review | 14-Jul-22 A | 03-Aug-22 A | 15 | 0 | 15 | 100% |  | Completed
ER6666LT | W209 | W209.25760 | HYB Essential Defueling Safety Case | 2022-07-14 | 2023-10-04 | Human Factors ## (Cost Summary) (Claim 5) | 14-Jul-22 A | 28-Mar-24 A | 433 | 0 | 433 | 100% |  | Completed
ER6666LT | W209 | W209.A29780 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-11-07 | Feasibility of Draining PVCS (Report) ## (Cost Summary) (Claim 2) | 14-Jul-22 A | 23-Nov-22 A | 99 | 0 | 93 | 100% |  | Completed
ER6666LT | W209 | W209.A29800 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-09-12 | Draft Feasibility of Draining PVCS (Report) | 14-Jul-22 A | 05-Sep-22 A | 42 | 0 | 36 | 100% |  | Completed
ER6666LT | W209 | W209.A29860 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-11-11 | FPU Maintenance Analysis EAN ## (Cost Summary) (Claim 3) | 14-Jul-22 A | 09-Sep-22 A | 41 | 0 | 41 | 100% |  | Completed
ER6666LT | W209 | W209.A29880 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-08-18 | Draft Review of FPU Maintenance Analysis EAN | 14-Jul-22 A | 14-Jul-22 A | 26 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.8650 | HYB Essential Defueling Safety Case |  |  | PJB for Human Factors Integration Plan EAN (REV 000) | 14-Jul-22 A | 14-Jul-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A30590 | HYB Essential Defueling Safety Case | 2022-07-12 | 2023-04-19 | FM Direct Process Protection Design ## (Cost Summary) (Claim 5) | 14-Jul-22 A | 24-May-23 A | 360 | 0 | 216 | 100% |  | Completed
ER6666LT | W209 | W209.8720 | HYB Essential Defueling Safety Case | 2022-07-12 | 2022-07-12 | PJB for FM Direct Process Protection Design | 14-Jul-22 A | 24-May-23 A | 1 | 0 | 216 | 100% |  | Completed
ER6666LT | W209 | W209.A30660 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-08-05 | Flow Induced Vibration EAN ## (Cost Summary) (Claim 3) | 14-Jul-22 A | 31-Oct-22 A | 62 | 0 | 76 | 100% |  | Completed
ER6666LT | W209 | W209.8860 | HYB Essential Defueling Safety Case | 2022-07-14 | 2023-12-05 | (B - C SANCTION) - Project Management - (Cost Summary) ## (B to C) | 14-Jul-22 A | 23-Feb-24 A | 298 | 0 | 408 | 100% |  | Completed
ER6666LT | W209 | W209.8870 | HYB Essential Defueling Safety Case | 2022-07-14 | 2023-12-05 | (B - C SANCTION) - Safety Case Development - (Cost Summary) ## (B to C) | 14-Jul-22 A | 23-Feb-24 A | 298 | 0 | 408 | 100% |  | Completed
ER6666LT | W209 | W209.A30770 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-07-22 | Draft Summary of Credible Start of Life Defects EAN | 14-Jul-22 A | 22-Nov-22 A | 11 | 0 | 93 | 100% |  | Completed
ER6666LT | W209 | W209.A30790 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-07-29 | Technical Review of Define Nuclear Data (PANTHER Validation Calcs) EAN | 14-Jul-22 A | 16-Dec-22 A | 12 | 0 | 111 | 100% |  | Completed
ER6666LT | W209 | W209.A30810 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-07-15 | Draft Civil Integrity of Pressure Boundary Integrity of Seals Report EAN | 14-Jul-22 A | 15-Jul-22 A | 2 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.A30830 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-07-25 | Technical Review of Radiological Consequences Following Failed CSP EAN | 14-Jul-22 A | 20-Feb-23 A | 8 | 0 | 153 | 100% |  | Completed
ER6666LT | W209 | W209.A30840 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-08-11 | Define Nuclear Data (PANTHER Validation Calcs) EAN ## (Cost Summary) (Claim 1) | 14-Jul-22 A | 13-Jan-23 A | 123 | 0 | 127 | 100% |  | Completed
ER6668LT | W213 | W213.3110 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-07-14 | Hold IAB | 14-Jul-22 A | 14-Jul-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A25850 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-11-16 | Safety Case Requirements EAN - TASK E EAN ## (Cost Summary) (Claim 2) | 14-Jul-22 A | 21-Apr-23 A | 196 | 0 | 196 | 100% |  | Completed
ER6668LT | W213 | W213.A25870 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-08-31 | Draft Safety Case Requirements EAN - TASK E EAN | 14-Jul-22 A | 29-Sep-22 A | 34 | 0 | 55 | 100% |  | Completed
ER6668LT | W213 | W213.A25930 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-10-24 | Civil Assesment of the Ponds at Low Temperature EAN ## (Cost Summary) (Claim 2) | 14-Jul-22 A | 07-Dec-22 A | 104 | 0 | 104 | 100% |  | Completed
ER6668LT | W213 | W213.A25950 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-08-12 | Draft Civil Assesment of the Ponds at Low Temperature EAN | 14-Jul-22 A | 05-Aug-22 A | 22 | 0 | 17 | 100% |  | Completed
ER6668LT | W213 | W213.A26010 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-11-03 | Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN ## (Cost Summary) (Claim 3) | 14-Jul-22 A | 07-Dec-22 A | 104 | 0 | 104 | 100% |  | Completed
ER6668LT | W213 | W213.A26030 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-08-24 | Draft Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN | 14-Jul-22 A | 05-Aug-22 A | 30 | 0 | 16 | 100% |  | Completed
ER6668LT | W213 | W213.A26170 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-09-19 | Pressure Boundary Integrity of Seals Report EAN ## (Cost Summary) (Claim 3) | 14-Jul-22 A | 30-Nov-22 A | 99 | 0 | 99 | 100% |  | Completed
ER6668LT | W213 | W213.A26250 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-08-25 | Reactor Internals & Structural Integrity During Defueling Report EAN ## (Cost Summary) (Claim 3) | 14-Jul-22 A | 04-Nov-22 A | 86 | 0 | 81 | 100% |  | Completed
ER6668LT | W213 | W213.A26290 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-08-11 | Technical Review of Reactor Internals & Structural Integrity During Defueling Report EAN | 14-Jul-22 A | 19-Aug-22 A | 21 | 0 | 27 | 100% |  | Completed
ER6668LT | W213 | W213.A26330 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-10-31 | Graphite Summary Report EAN ## (Cost Summary) (Claim 3) | 14-Jul-22 A | 03-Mar-23 A | 163 | 0 | 163 | 100% |  | Completed
ER6668LT | W213 | W213.A26350 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-08-25 | Draft Graphite Summary Report EAN | 14-Jul-22 A | 31-Jan-23 A | 31 | 0 | 139 | 100% |  | Completed
ER6668LT | W213 | W213.A26730 | TOR Essential Defueling Safety Case | 2022-07-14 | 2023-01-03 | Boron Bead Inj Feasibility & Boron Bead Injection Feasibility & Control Rod Isolation EAN ## (Cost Summary) (Claim 1) | 14-Jul-22 A | 21-Apr-23 A | 196 | 0 | 196 | 100% |  | Completed
ER6668LT | W213 | W213.A26750 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-09-08 | Draft Boron Bead Injection Feasibility & Control Rod Isolation EAN | 14-Jul-22 A | 08-Sep-22 A | 40 | 0 | 40 | 100% |  | Completed
ER6668LT | W213 | W213.A26970 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-12-02 | Review of FM Cyclic Duty EAN ## (Cost Summary) (Claim 3) | 14-Jul-22 A | 31-Oct-22 A | 66 | 0 | 76 | 100% |  | Completed
ER6668LT | W213 | W213.A26990 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-09-09 | Draft Review of FM Cyclic Duty EAN | 14-Jul-22 A | 22-Jul-22 A | 41 | 0 | 6 | 100% |  | Completed
ER6668LT | W213 | W213.A27050 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-11-08 | FPU Integrity Analysis EAN ## (Cost Summary) (Claim 3) | 14-Jul-22 A | 12-May-23 A | 203 | 0 | 208 | 100% |  | Completed
ER6668LT | W213 | W213.A27080 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-09-13 | Verify Review of FPU Integrity Analysis EAN & Issue for Technical Review | 14-Jul-22 A | 17-Feb-23 A | 43 | 0 | 153 | 100% |  | Completed
ER6668LT | W213 | W213.A27170 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-07-21 | Technical Review of Review of Flow Induced Vibration EAN | 14-Jul-22 A | 02-Sep-22 A | 6 | 0 | 36 | 100% |  | Completed
ER6668LT | W213 | W213.A27370 | TOR Essential Defueling Safety Case | 2022-07-14 | 2023-11-15 | Fuel Route Defueling PSA Update ## (Cost Summary) (Claim 5) | 14-Jul-22 A | 31-Jul-24 A | 518 | 0 | 518 | 100% |  | Completed
ER6668LT | W213 | W213.A28010 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-09-19 | Update Basis of Analysis document ## (Cost Summary) (Claim 4) | 14-Jul-22 A | 07-Mar-23 A | 165 | 0 | 165 | 100% |  | Completed
ER6668LT | W213 | W213.A28030 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-07-15 | Draft Update Basis of Analysis document | 14-Jul-22 A | 15-Jul-22 A | 2 | 0 | 2 | 100% |  | Completed
ER6668LT | W213 | W213.A28090 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-08-23 | Develop FEA Model ## (Cost Summary) (Claim 4) | 14-Jul-22 A | 31-Aug-22 A | 36 | 0 | 33 | 100% |  | Completed
ER6668LT | W213 | W213.A28110 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-07-18 | Develop FEA Model | 14-Jul-22 A | 18-Jul-22 A | 3 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.A28410 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-09-12 | Summary of Credible Start of Life Defects EAN ## (Cost Summary) (Claim 4) | 14-Jul-22 A | 22-Dec-22 A | 123 | 0 | 114 | 100% |  | Completed
ER6668LT | W213 | W213.A28570 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-12-14 | Radiological Consequences Following Failed CSP EAN ## (Cost Summary) (Claim 4) | 14-Jul-22 A | 07-Mar-23 A | 165 | 0 | 165 | 100% |  | Completed
ER6668LT | W213 | W213.A28730 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-12-13 | Fuel Free Verification (FFV) Reports EAN ## (Cost Summary) (Claim 6) | 14-Jul-22 A | 31-Mar-23 A | 163 | 0 | 182 | 100% |  | Completed
ER6668LT | W213 | W213.A28810 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-11-29 | Define Failed Fuel Free Controls File Note ## (Cost Summary) (Claim 6) | 14-Jul-22 A | 23-Dec-22 A | 116 | 0 | 116 | 100% |  | Completed
ER6668LT | W213 | W213.A28830 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-09-27 | Draft Define Failed Fuel Free Controls File Note (Rhod) | 14-Jul-22 A | 09-Dec-22 A | 53 | 0 | 106 | 100% |  | Completed
ER6668LT | W213 | W213.6650 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-07-21 | Prepare Task Sheet for Fuel Free Verification methods, an assessment against the ALARP principle EAN | 14-Jul-22 A | 15-Jul-22 A | 6 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A29370 | TOR Essential Defueling Safety Case | 2022-07-14 | 2023-01-12 | Cooling Plant Availability Review EAN ## (Cost Summary) (Claim 2) | 14-Jul-22 A | 17-Feb-23 A | 147 | 0 | 152 | 100% |  | Completed
ER6668LT | W213 | W213.A29390 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-10-17 | Draft Cooling Plant Availability Review EAN | 14-Jul-22 A | 24-Nov-22 A | 67 | 0 | 94 | 100% |  | Completed
ER6668LT | W213 | W213.A29450 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-10-28 | Cooling Plant OPEX Study EAN ## (Cost Summary) (Claim 2) | 14-Jul-22 A | 11-Nov-22 A | 86 | 0 | 86 | 100% |  | Completed
ER6668LT | W213 | W213.A29470 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-09-02 | Draft Cooling Plant OPEX Study EAN | 14-Jul-22 A | 19-Aug-22 A | 36 | 0 | 26 | 100% |  | Completed
ER6668LT | W213 | W213.7840 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-08-03 | Scope Assumptions Review | 14-Jul-22 A | 03-Aug-22 A | 15 | 0 | 15 | 100% |  | Completed
ER6668LT | W213 | W213.25760 | TOR Essential Defueling Safety Case | 2022-07-14 | 2023-10-04 | Human Factors ## (Cost Summary) (Claim 5) | 14-Jul-22 A | 28-Mar-24 A | 466 | 0 | 432 | 100% |  | Completed
ER6668LT | W213 | W213.A29780 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-11-07 | Feasibility of Draining PVCS (Report) ## (Cost Summary) (Claim 2) | 14-Jul-22 A | 23-Nov-22 A | 99 | 0 | 93 | 100% |  | Completed
ER6668LT | W213 | W213.A29800 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-09-12 | Draft Feasibility of Draining PVCS (Report) | 14-Jul-22 A | 05-Sep-22 A | 42 | 0 | 36 | 100% |  | Completed
ER6668LT | W213 | W213.A29860 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-11-11 | FPU Maintenance Analysis EAN ## (Cost Summary) (Claim 3) | 14-Jul-22 A | 09-Sep-22 A | 41 | 0 | 41 | 100% |  | Completed
ER6668LT | W213 | W213.A29880 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-08-18 | Draft Review of FPU Maintenance Analysis EAN | 14-Jul-22 A | 14-Jul-22 A | 26 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.8650 | TOR Essential Defueling Safety Case |  |  | PJB for Human Factors Integration Plan EAN (REV 000) | 14-Jul-22 A | 14-Jul-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A30590 | TOR Essential Defueling Safety Case | 2022-07-12 | 2023-04-19 | FM Direct Process Protection Design ## (Cost Summary) (Claim 5) | 14-Jul-22 A | 24-May-23 A | 360 | 0 | 216 | 100% |  | Completed
ER6668LT | W213 | W213.8720 | TOR Essential Defueling Safety Case | 2022-07-12 | 2022-07-12 | PJB for FM Direct Process Protection Design | 14-Jul-22 A | 24-May-23 A | 1 | 0 | 216 | 100% |  | Completed
ER6668LT | W213 | W213.A30660 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-08-05 | Flow Induced Vibration EAN ## (Cost Summary) (Claim 3) | 14-Jul-22 A | 31-Oct-22 A | 62 | 0 | 76 | 100% |  | Completed
ER6668LT | W213 | W213.8860 | TOR Essential Defueling Safety Case | 2022-07-14 | 2023-12-05 | (B - C SANCTION) - Project Management - (Cost Summary) ## (B to C) | 14-Jul-22 A | 23-Feb-24 A | 298 | 0 | 408 | 100% |  | Completed
ER6668LT | W213 | W213.8870 | TOR Essential Defueling Safety Case | 2022-07-14 | 2023-12-06 | (B - C SANCTION) - Safety Case Development - (Cost Summary) ## (B to C) | 14-Jul-22 A | 23-Feb-24 A | 298 | 0 | 408 | 100% |  | Completed
ER6668LT | W213 | W213.A30770 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-07-22 | Draft Summary of Credible Start of Life Defects EAN | 14-Jul-22 A | 22-Nov-22 A | 11 | 0 | 93 | 100% |  | Completed
ER6668LT | W213 | W213.A30790 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-07-29 | Technical Review of Define Nuclear Data (PANTHER Validation Calcs) EAN | 14-Jul-22 A | 16-Dec-22 A | 12 | 0 | 111 | 100% |  | Completed
ER6668LT | W213 | W213.A30810 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-07-15 | Draft Civil Integrity of Pressure Boundary Integrity of Seals Report EAN | 14-Jul-22 A | 15-Jul-22 A | 2 | 0 | 2 | 100% |  | Completed
ER6668LT | W213 | W213.A30830 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-07-25 | Technical Review of Radiological Consequences Following Failed CSP EAN | 14-Jul-22 A | 20-Feb-23 A | 8 | 0 | 153 | 100% |  | Completed
ER6668LT | W213 | W213.A30840 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-08-11 | Define Nuclear Data (PANTHER Validation Calcs) EAN ## (Cost Summary) (Claim 1) | 14-Jul-22 A | 13-Jan-23 A | 123 | 0 | 127 | 100% |  | Completed
ER6666LT | W209 | W209.1395 | HYB Essential Defueling Safety Case |  | 2022-07-14 | Commence Supporting References or Supporting EC's | 15-Jul-22 A | 15-Jul-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A24570 | HYB Essential Defueling Safety Case | 2022-08-01 | 2022-08-01 | Pre Job Brief for Human Reliability Baseline Report EAN | 15-Jul-22 A | 15-Jul-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1395 | TOR Essential Defueling Safety Case |  | 2022-07-14 | Commence Supporting References or Supporting EC's | 15-Jul-22 A | 15-Jul-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A24570 | TOR Essential Defueling Safety Case | 2022-08-01 | 2022-08-01 | Pre Job Brief for Human Reliability Baseline Report EAN | 15-Jul-22 A | 15-Jul-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A29890 | HYB Essential Defueling Safety Case | 2022-08-19 | 2022-09-23 | Verify Review of FPU Maintenance Analysis EAN & Issue for Technical Review | 15-Jul-22 A | 20-Jul-22 A | 4 | 0 | 4 | 100% |  | Completed
ER6666LT | W209 | W209.A29940 | HYB Essential Defueling Safety Case | 2022-07-15 | 2023-06-02 | FM Underload Protection Mods Prelim Design (GLM) ## (Cost Summary) (Claim 5) | 15-Jul-22 A | 19-May-23 A | 216 | 0 | 212 | 100% |  | Completed
ER6666LT | W209 | W209.8320 | HYB Essential Defueling Safety Case | 2022-07-15 | 2022-07-21 | Prepare Spec for FM Underload Protection Mods Prelim Design (GLM) | 15-Jul-22 A | 21-Jul-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.8830 | HYB Essential Defueling Safety Case | 2022-07-15 | 2022-07-21 | Prepare Spec for Underload Veto Height | 15-Jul-22 A | 21-Jul-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.A30670 | HYB Essential Defueling Safety Case | 2022-07-15 | 2023-06-02 | Underload Veto Height ## (Cost Summary) (Claim 5) | 15-Jul-22 A | 14-Jul-23 A | 252 | 0 | 252 | 100% |  | Completed
ER6668LT | W213 | W213.A29890 | TOR Essential Defueling Safety Case | 2022-08-19 | 2022-09-23 | Verify Review of FPU Maintenance Analysis EAN & Issue for Technical Review | 15-Jul-22 A | 20-Jul-22 A | 4 | 0 | 4 | 100% |  | Completed
ER6668LT | W213 | W213.A29940 | TOR Essential Defueling Safety Case | 2022-07-15 | 2023-06-05 | FM Underload Protection Mods Prelim Design (GLM) ## (Cost Summary) (Claim 5) | 15-Jul-22 A | 19-May-23 A | 216 | 0 | 212 | 100% |  | Completed
ER6668LT | W213 | W213.8320 | TOR Essential Defueling Safety Case | 2022-07-15 | 2022-07-21 | Prepare Spec for FM Underload Protection Mods Prelim Design (GLM) | 15-Jul-22 A | 21-Jul-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.8830 | TOR Essential Defueling Safety Case | 2022-07-15 | 2022-07-21 | Prepare Spec for Underload Veto Height | 15-Jul-22 A | 21-Jul-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A30670 | TOR Essential Defueling Safety Case | 2022-07-15 | 2023-06-05 | Underload Veto Height ## (Cost Summary) (Claim 5) | 15-Jul-22 A | 14-Jul-23 A | 252 | 0 | 252 | 100% |  | Completed
ER6666LT | W209 | W209.6660 | HYB Essential Defueling Safety Case | 2022-07-22 | 2022-08-01 | Approve Task Sheet for Fuel Free Verification methods, an assessment against the ALARP principle EAN | 18-Jul-22 A | 18-Jul-22 A | 7 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A24580 | HYB Essential Defueling Safety Case | 2022-08-02 | 2022-09-27 | Step 1 - Review of Human Reliability Baseline Report EAN | 18-Jul-22 A | 16-Sep-22 A | 20 | 0 | 44 | 100% |  | Completed
ER6371LT | W202 | 1610 | HRA Reactors Shutdown Essential Safety Cases | 2022-08-01 | 2022-08-12 | Request and address comments from core team | 18-Jul-22 A | 25-Jul-22 A | 10 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | 1610 | HYA Reactors Shutdown Essential Safety Cases | 2022-08-01 | 2022-08-12 | Request and address comments from core team | 18-Jul-22 A | 25-Jul-22 A | 10 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.6660 | TOR Essential Defueling Safety Case | 2022-07-22 | 2022-08-01 | Approve Task Sheet for Fuel Free Verification methods, an assessment against the ALARP principle EAN | 18-Jul-22 A | 18-Jul-22 A | 7 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A24580 | TOR Essential Defueling Safety Case | 2022-08-02 | 2022-09-27 | Step 1 - Review of Human Reliability Baseline Report EAN | 18-Jul-22 A | 16-Sep-22 A | 20 | 0 | 44 | 100% |  | Completed
ER6666LT | W209 | W209.A26200 | HYB Essential Defueling Safety Case | 2022-07-18 | 2022-08-05 | Verify Pressure Boundary Integrity of Seals Report EAN & Issue for Technical Review | 18-Jul-22 A | 20-Jul-22 A | 15 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.A28040 | HYB Essential Defueling Safety Case | 2022-07-18 | 2022-08-05 | Verify Update Basis of Analysis document & Issue for Technical Review | 18-Jul-22 A | 19-Aug-22 A | 15 | 0 | 25 | 100% |  | Completed
ER6668LT | W213 | W213.A26200 | TOR Essential Defueling Safety Case | 2022-07-18 | 2022-08-05 | Verify Pressure Boundary Integrity of Seals Report EAN & Issue for Technical Review | 18-Jul-22 A | 20-Jul-22 A | 15 | 0 | 2 | 100% |  | Completed
ER6668LT | W213 | W213.A28040 | TOR Essential Defueling Safety Case | 2022-07-18 | 2022-08-05 | Verify Update Basis of Analysis document & Issue for Technical Review | 18-Jul-22 A | 19-Aug-22 A | 15 | 0 | 25 | 100% |  | Completed
ER6666LT | W209 | W209.A31080 | HYB Essential Defueling Safety Case |  |  | Defueling Process Flow## (Cost Summary) (Claim 5) | 19-Jul-22 A | 31-Jul-23 A | 208 | 0 | 261 | 100% |  | Completed
ER6666LT | W209 | W209.A31090 | HYB Essential Defueling Safety Case |  |  | Pre Job Brief for Defueling Process Flow | 19-Jul-22 A | 19-Jul-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A31080 | TOR Essential Defueling Safety Case |  |  | Defueling Process Flow## (Cost Summary) (Claim 5) | 19-Jul-22 A | 31-Jul-23 A | 208 | 0 | 261 | 100% |  | Completed
ER6668LT | W213 | W213.A31090 | TOR Essential Defueling Safety Case |  |  | Pre Job Brief for Defueling Process Flow | 19-Jul-22 A | 19-Jul-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A28120 | HYB Essential Defueling Safety Case | 2022-07-19 | 2022-07-26 | Verify FEA Model & Issue for Technical Review | 19-Jul-22 A | 26-Jul-22 A | 6 | 0 | 6 | 100% |  | Completed
ER6666LT | W209 | W209.A28740 | HYB Essential Defueling Safety Case | 2022-08-02 | 2022-08-02 | Pre Job Brief for Fuel Free Verification methods, an assessment against the ALARP principle EAN | 19-Jul-22 A | 19-Jul-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A28120 | TOR Essential Defueling Safety Case | 2022-07-19 | 2022-07-26 | Verify FEA Model & Issue for Technical Review | 19-Jul-22 A | 26-Jul-22 A | 6 | 0 | 6 | 100% |  | Completed
ER6668LT | W213 | W213.A28740 | TOR Essential Defueling Safety Case | 2022-08-02 | 2022-08-02 | Pre Job Brief for Fuel Free Verification methods, an assessment against the ALARP principle EAN | 19-Jul-22 A | 19-Jul-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A31100 | HYB Essential Defueling Safety Case |  |  | Draft Defueling Process Flow | 20-Jul-22 A | 31-Oct-22 A | 49 | 0 | 73 | 100% |  | Completed
ER6668LT | W213 | W213.A31100 | TOR Essential Defueling Safety Case |  |  | Draft Defueling Process Flow | 20-Jul-22 A | 31-Oct-22 A | 49 | 0 | 73 | 100% |  | Completed
ER6666LT | W209 | W209.A28750 | HYB Essential Defueling Safety Case | 2022-08-03 | 2022-10-11 | Draft Fuel Free Verification (FFV) Reports EAN | 20-Jul-22 A | 04-Nov-22 A | 49 | 0 | 77 | 100% |  | Completed
ER6668LT | W213 | W213.A28750 | TOR Essential Defueling Safety Case | 2022-08-03 | 2022-10-11 | Draft Fuel Free Verification (FFV) Reports EAN | 20-Jul-22 A | 04-Nov-22 A | 49 | 0 | 77 | 100% |  | Completed
ER6666LT | W209 | W209.A30420 | HYB Essential Defueling Safety Case | 2022-08-08 | 2022-09-05 | Technical Review of Pressure Boundary Integrity of Seals Report EAN | 21-Jul-22 A | 06-Oct-22 A | 20 | 0 | 55 | 100% |  | Completed
ER6668LT | W213 | W213.A30420 | TOR Essential Defueling Safety Case | 2022-08-08 | 2022-09-05 | Technical Review of Pressure Boundary Integrity of Seals Report EAN | 21-Jul-22 A | 06-Oct-22 A | 20 | 0 | 55 | 100% |  | Completed
ER6666LT | W209 | W209.A29900 | HYB Essential Defueling Safety Case | 2022-09-26 | 2022-10-28 | Technical Review of FPU Maintenance Analysis EAN | 21-Jul-22 A | 01-Aug-22 A | 25 | 0 | 8 | 100% |  | Completed
ER6668LT | W213 | W213.A29900 | TOR Essential Defueling Safety Case | 2022-09-26 | 2022-10-28 | Technical Review of FPU Maintenance Analysis EAN | 21-Jul-22 A | 01-Aug-22 A | 25 | 0 | 8 | 100% |  | Completed
ER6666LT | W209 | W209.A24780 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-07-14 | Pre Job Brief for Human Factors Assessment of Misloading / Mis-Defueling Faults EAN | 22-Jul-22 A | 22-Jul-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A24780 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-07-14 | Pre Job Brief for Human Factors Assessment of Misloading / Mis-Defueling Faults EAN | 22-Jul-22 A | 22-Jul-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.8330 | HYB Essential Defueling Safety Case | 2022-07-22 | 2022-08-04 | Prepare Task Sheet for FM Underload Protection Mods Prelim Design (GLM) | 22-Jul-22 A | 04-Aug-22 A | 10 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.8840 | HYB Essential Defueling Safety Case | 2022-07-22 | 2022-08-04 | Prepare Task Sheet for Underload Veto Height | 22-Jul-22 A | 04-Aug-22 A | 10 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.8330 | TOR Essential Defueling Safety Case | 2022-07-22 | 2022-08-04 | Prepare Task Sheet for FM Underload Protection Mods Prelim Design (GLM) | 22-Jul-22 A | 04-Aug-22 A | 10 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.8840 | TOR Essential Defueling Safety Case | 2022-07-22 | 2022-08-04 | Prepare Task Sheet for Underload Veto Height | 22-Jul-22 A | 04-Aug-22 A | 10 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.A27000 | HYB Essential Defueling Safety Case | 2022-09-12 | 2022-10-14 | Verify Review of FM Cyclic Duty EAN & Issue for Technical Review | 25-Jul-22 A | 05-Aug-22 A | 25 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.A24790 | HYB Essential Defueling Safety Case | 2022-07-15 | 2022-09-30 | Draft Review of Human Factors Assessment of Misloading / Mis-Defueling Faults EAN | 25-Jul-22 A | 11-Apr-23 A | 55 | 0 | 181 | 100% |  | Completed
ER6668LT | W213 | W213.A27000 | TOR Essential Defueling Safety Case | 2022-09-12 | 2022-10-14 | Verify Review of FM Cyclic Duty EAN & Issue for Technical Review | 25-Jul-22 A | 05-Aug-22 A | 25 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.A24790 | TOR Essential Defueling Safety Case | 2022-07-15 | 2022-09-30 | Draft Review of Human Factors Assessment of Misloading / Mis-Defueling Faults EAN | 25-Jul-22 A | 11-Apr-23 A | 55 | 0 | 181 | 100% |  | Completed
ER6666LT | W209 | W209.A28050 | HYB Essential Defueling Safety Case | 2022-08-08 | 2022-09-05 | Technical Review of Update Basis if Analysis document - (Issue 3) | 27-Jul-22 A | 04-Nov-22 A | 20 | 0 | 72 | 100% |  | Completed
ER6666LT | W209 | W209.A30680 | HYB Essential Defueling Safety Case | 2022-08-16 | 2022-08-16 | Pre Job Brief for Channel 1 - HYB | 27-Jul-22 A | 27-Jul-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A28050 | TOR Essential Defueling Safety Case | 2022-08-08 | 2022-09-05 | Technical Review of Update Basis if Analysis document - (Issue 3) | 27-Jul-22 A | 04-Nov-22 A | 20 | 0 | 72 | 100% |  | Completed
ER6668LT | W213 | W213.A30680 | TOR Essential Defueling Safety Case | 2022-08-16 | 2022-08-16 | Pre Job Brief for Channel 1 - TOR | 27-Jul-22 A | 27-Jul-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A28130 | HYB Essential Defueling Safety Case | 2022-07-27 | 2022-08-09 | Technical Review of FEA Model | 27-Jul-22 A | 09-Aug-22 A | 10 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | 1600 | HRA Reactors Shutdown Essential Safety Cases | 2022-07-27 | 2022-07-29 | Update Fault Definition Document | 27-Jul-22 A | 23-Aug-22 A | 3 | 0 | 19 | 100% |  | Completed
ER6661LT | W206 | 1600 | HYA Reactors Shutdown Essential Safety Cases | 2022-07-27 | 2022-07-29 | Update Fault Definition Document | 27-Jul-22 A | 23-Aug-22 A | 3 | 0 | 19 | 100% |  | Completed
ER6668LT | W213 | W213.A28130 | TOR Essential Defueling Safety Case | 2022-07-27 | 2022-08-09 | Technical Review of FEA Model | 27-Jul-22 A | 09-Aug-22 A | 10 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.A30690 | HYB Essential Defueling Safety Case | 2022-08-17 | 2023-01-23 | Functional Requirement Spec for Channel 1 - HYB | 28-Jul-22 A | 01-Nov-22 A | 110 | 0 | 68 | 100% |  | Completed
ER6668LT | W213 | W213.A30690 | TOR Essential Defueling Safety Case | 2022-08-17 | 2023-01-23 | Functional Requirement Spec for Channel 1 - TOR | 28-Jul-22 A | 01-Nov-22 A | 110 | 0 | 68 | 100% |  | Completed
ER6666LT | W209 | W209.A29750 | HYB Essential Defueling Safety Case | 2022-09-12 | 2022-10-21 | Verify PARTIAL Drain down of the PVCS prior to Defuelling (Report) & Issue for Technical Review | 29-Jul-22 A | 28-Feb-23 A | 30 | 0 | 149 | 100% |  | Completed
ER6668LT | W213 | W213.A29750 | TOR Essential Defueling Safety Case | 2022-09-12 | 2022-10-21 | Verify PARTIAL Drain down of the PVCS prior to Defuelling (Report) & Issue for Technical Review | 29-Jul-22 A | 28-Feb-23 A | 30 | 0 | 149 | 100% |  | Completed
ER6371LT | W202 | 1815 | HRA Reactors Shutdown Essential Safety Cases | 2022-08-15 | 2022-08-26 | Review previous ALARP Optioneering and update where appropriate | 01-Aug-22 A | 05-Aug-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | 1810 | HRA Reactors Shutdown Essential Safety Cases | 2022-08-15 | 2022-09-22 | Review ALARP Position for Safety Case - Summary | 01-Aug-22 A | 19-Oct-23 A | 69 | 0 | 308 | 100% |  | Completed
ER6661LT | W206 | 1815 | HYA Reactors Shutdown Essential Safety Cases | 2022-08-15 | 2022-08-26 | Review previous ALARP Optioneering and update where appropriate | 01-Aug-22 A | 05-Aug-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | 1810 | HYA Reactors Shutdown Essential Safety Cases | 2022-08-15 | 2022-09-22 | Review ALARP Position for Safety Case - Summary | 01-Aug-22 A | 19-Oct-23 A | 69 | 0 | 308 | 100% |  | Completed
ER6370LT | W201 | ER6370.A1490 | HNB Reactors Shutdown Essential Safety Cases | 2021-08-27 | 2021-08-27 | Safety Case Post Job Debrief (HNB) [FEEDS TO SUMMARY SCHEDULE] | 02-Aug-22 A | 10-Aug-22 A | 1 | 0 | 6 | 100% |  | Completed
ER6370LT | W201 | ER6370.A12225 | HNB Reactors Shutdown Essential Safety Cases | 2021-08-27 | 2021-08-31 | Hold Project Closeout and Lessons Learned Meeting | 02-Aug-22 A | 03-Aug-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A29910 | HYB Essential Defueling Safety Case | 2022-10-31 | 2022-11-04 | Supplier Update and Issue FPU Maintenance Analysis EAN | 02-Aug-22 A | 02-Sep-22 A | 5 | 0 | 23 | 100% |  | Completed
ER6668LT | W213 | W213.A29910 | TOR Essential Defueling Safety Case | 2022-10-31 | 2022-11-04 | Supplier Update and Issue FPU Maintenance Analysis EAN | 02-Aug-22 A | 02-Sep-22 A | 5 | 0 | 23 | 100% |  | Completed
ER6370LT | W201 | ER6370.A12235 | HNB Reactors Shutdown Essential Safety Cases | 2021-09-01 | 2021-09-03 | Produce Project Closeout Report | 03-Aug-22 A | 03-Aug-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A12240 | HNB Reactors Shutdown Essential Safety Cases | 2021-09-03 | 2021-09-13 | Prepare Gate D PRC Paper | 03-Aug-22 A | 03-Aug-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A12230 | HNB Reactors Shutdown Essential Safety Cases | 2021-08-31 | 2021-09-01 | Produce Lessons Learned Report | 03-Aug-22 A | 03-Aug-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.8450 | HYB Essential Defueling Safety Case | 2022-08-04 | 2022-09-01 | Tech Review Assumptions Review | 04-Aug-22 A | 03-Oct-22 A | 20 | 0 | 42 | 100% |  | Completed
ER6668LT | W213 | W213.8450 | TOR Essential Defueling Safety Case | 2022-08-04 | 2022-09-01 | Tech Review Assumptions Review | 04-Aug-22 A | 03-Oct-22 A | 20 | 0 | 42 | 100% |  | Completed
ER6666LT | W209 | W209.8340 | HYB Essential Defueling Safety Case | 2022-08-05 | 2022-08-15 | Approve Task Sheet for FM Underload Protection Mods Prelim Design (GLM) | 05-Aug-22 A | 08-Aug-22 A | 7 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.8850 | HYB Essential Defueling Safety Case | 2022-08-05 | 2022-08-15 | Approve Task Sheet for Underload Veto Height | 05-Aug-22 A | 08-Aug-22 A | 7 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.8340 | TOR Essential Defueling Safety Case | 2022-08-05 | 2022-08-15 | Approve Task Sheet for FM Underload Protection Mods Prelim Design (GLM) | 05-Aug-22 A | 08-Aug-22 A | 7 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.8850 | TOR Essential Defueling Safety Case | 2022-08-05 | 2022-08-15 | Approve Task Sheet for Underload Veto Height | 05-Aug-22 A | 08-Aug-22 A | 7 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A26040 | HYB Essential Defueling Safety Case | 2022-08-25 | 2022-10-20 | Verify Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN | 08-Aug-22 A | 30-Nov-22 A | 40 | 0 | 81 | 100% |  | Completed
ER6668LT | W213 | W213.A26040 | TOR Essential Defueling Safety Case | 2022-08-25 | 2022-10-20 | Verify Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN | 08-Aug-22 A | 30-Nov-22 A | 40 | 0 | 81 | 100% |  | Completed
ER6666LT | W209 | W209.A25960 | HYB Essential Defueling Safety Case | 2022-08-15 | 2022-10-10 | Verify Civil Assesment of the Ponds at Low Temperature EAN | 08-Aug-22 A | 30-Nov-22 A | 40 | 0 | 81 | 100% |  | Completed
ER6666LT | W209 | W209.A27010 | HYB Essential Defueling Safety Case | 2022-10-17 | 2022-11-18 | Technical Review of Review of FM Cyclic Duty EAN | 08-Aug-22 A | 12-Sep-22 A | 25 | 0 | 25 | 100% |  | Completed
ER6666LT | W209 | W209.7640 | HYB Essential Defueling Safety Case | 2022-06-01 | 2022-06-30 | Verification of Civils Assessment Report for PCPV Integrity Justification | 08-Aug-22 A | 07-Dec-22 A | 40 | 0 | 87 | 100% |  | Completed
ER6666LT | W209 | W209.7660 | HYB Essential Defueling Safety Case | 2022-06-01 | 2022-06-30 | Verification of Civils Assessment Report for Seismic Assessment | 08-Aug-22 A | 07-Dec-22 A | 40 | 0 | 87 | 100% |  | Completed
ER6668LT | W213 | W213.A25960 | TOR Essential Defueling Safety Case | 2022-08-15 | 2022-10-10 | Verify Civil Assesment of the Ponds at Low Temperature EAN | 08-Aug-22 A | 30-Nov-22 A | 40 | 0 | 81 | 100% |  | Completed
ER6668LT | W213 | W213.A27010 | TOR Essential Defueling Safety Case | 2022-10-17 | 2022-11-18 | Technical Review of Review of FM Cyclic Duty EAN | 08-Aug-22 A | 12-Sep-22 A | 25 | 0 | 25 | 100% |  | Completed
ER6668LT | W213 | W213.7640 | TOR Essential Defueling Safety Case | 2022-06-01 | 2022-06-30 | Verification of Civils Assessment Report for PCPV Integrity Justification | 08-Aug-22 A | 07-Dec-22 A | 40 | 0 | 87 | 100% |  | Completed
ER6668LT | W213 | W213.7660 | TOR Essential Defueling Safety Case | 2022-06-01 | 2022-06-30 | Verification of Civils Assessment Report for Seismic Assessment | 08-Aug-22 A | 07-Dec-22 A | 40 | 0 | 87 | 100% |  | Completed
ER6370LT | W201 | ER6370.A18170 | HNB Reactors Shutdown Essential Safety Cases |  |  | Review of Reactor Essential Safety Cases 2 - Lessons Learned Review Complete | 10-Aug-22 A | 10-Aug-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A28140 | HYB Essential Defueling Safety Case | 2022-08-10 | 2022-08-16 | Supplier Update and Issue of FEA Model | 10-Aug-22 A | 12-Aug-22 A | 24 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.A28140 | TOR Essential Defueling Safety Case | 2022-08-10 | 2022-08-16 | Supplier Update and Issue of FEA Model | 10-Aug-22 A | 12-Aug-22 A | 24 | 0 | 3 | 100% |  | Completed
ER6370LT | W201 | ER6370.A12245 | HNB Reactors Shutdown Essential Safety Cases | 2021-09-13 | 2021-09-14 | Gate D PRC Paper Submission | 10-Aug-22 A | 10-Aug-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.8040 | HYB Essential Defueling Safety Case | 2022-08-01 | 2022-08-01 | Pre Job Brief for HF Assessment of the Extant Fuel Movement in support of Defueling FFV Claim | 11-Aug-22 A | 11-Aug-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.8040 | TOR Essential Defueling Safety Case | 2022-08-01 | 2022-08-01 | Pre Job Brief for HF Assessment of the Extant Fuel Movement in support of Defueling FFV Claim | 11-Aug-22 A | 11-Aug-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.8050 | HYB Essential Defueling Safety Case | 2022-08-02 | 2022-11-08 | Draft HF Assessment of HF Assessment of the Extant Fuel Movement in support of Defueling FFV Claim | 12-Aug-22 A | 31-Oct-22 A | 70 | 0 | 56 | 100% |  | Completed
ER6668LT | W213 | W213.8050 | TOR Essential Defueling Safety Case | 2022-08-02 | 2022-11-08 | Draft HF Assessment of HF Assessment of the Extant Fuel Movement in support of Defueling FFV Claim | 12-Aug-22 A | 31-Oct-22 A | 70 | 0 | 56 | 100% |  | Completed
ER6666LT | W209 | W209.A28170 | HYB Essential Defueling Safety Case | 2022-07-27 | 2023-02-28 | CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN ## (Cost Summary) (Claim 4) | 15-Aug-22 A | 31-Mar-23 A | 169 | 0 | 160 | 100% |  | Completed
ER6666LT | W209 | W209.A28180 | HYB Essential Defueling Safety Case | 2022-07-27 | 2022-07-27 | Pre Job Brief for CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN | 15-Aug-22 A | 15-Aug-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A28330 | HYB Essential Defueling Safety Case | 2022-07-28 | 2023-02-24 | R6 Assessment of CSP & Diagrid EAN ## (Cost Summary) (Claim 4) | 15-Aug-22 A | 31-Mar-23 A | 169 | 0 | 160 | 100% |  | Completed
ER6668LT | W213 | W213.A28170 | TOR Essential Defueling Safety Case | 2022-07-27 | 2023-02-28 | CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN ## (Cost Summary) (Claim 4) | 15-Aug-22 A | 31-Mar-23 A | 169 | 0 | 160 | 100% |  | Completed
ER6668LT | W213 | W213.A28180 | TOR Essential Defueling Safety Case | 2022-07-27 | 2022-07-27 | Pre Job Brief for CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN | 15-Aug-22 A | 15-Aug-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A28330 | TOR Essential Defueling Safety Case | 2022-07-28 | 2023-02-24 | R6 Assessment of CSP & Diagrid EAN ## (Cost Summary) (Claim 4) | 15-Aug-22 A | 31-Mar-23 A | 169 | 0 | 160 | 100% |  | Completed
ER6666LT | W209 | W209.A28150 | HYB Essential Defueling Safety Case | 2022-08-17 | 2022-08-23 | Approve Model | 15-Aug-22 A | 31-Aug-22 A | 5 | 0 | 11 | 100% |  | Completed
ER6668LT | W213 | W213.A28150 | TOR Essential Defueling Safety Case | 2022-08-17 | 2022-08-23 | Approve Model | 15-Aug-22 A | 31-Aug-22 A | 5 | 0 | 11 | 100% |  | Completed
ER6666LT | W209 | W209.A28190 | HYB Essential Defueling Safety Case | 2022-07-28 | 2022-12-15 | Draft CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN | 16-Aug-22 A | 18-Nov-22 A | 100 | 0 | 67 | 100% |  | Completed
ER6668LT | W213 | W213.A28190 | TOR Essential Defueling Safety Case | 2022-07-28 | 2022-12-15 | Draft CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN | 16-Aug-22 A | 18-Nov-22 A | 100 | 0 | 67 | 100% |  | Completed
ER6371LT | W202 | 1820 | HRA Reactors Shutdown Essential Safety Cases | 2022-08-30 | 2022-08-30 | ALARP Meeting to Review Safety Case [Update] | 17-Aug-22 A | 17-Aug-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | 1820 | HYA Reactors Shutdown Essential Safety Cases | 2022-08-30 | 2022-08-30 | ALARP Meeting to Review Safety Case [Update] | 17-Aug-22 A | 17-Aug-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | 1830 | HRA Reactors Shutdown Essential Safety Cases | 2022-08-31 | 2022-09-13 | Update ALARP Document | 18-Aug-22 A | 26-Sep-22 A | 10 | 0 | 26 | 100% |  | Completed
ER6661LT | W206 | 1830 | HYA Reactors Shutdown Essential Safety Cases | 2022-08-31 | 2022-09-13 | Update ALARP Document | 18-Aug-22 A | 26-Sep-22 A | 10 | 0 | 26 | 100% |  | Completed
ER6666LT | W209 | W209.A26300 | HYB Essential Defueling Safety Case | 2022-08-12 | 2022-08-18 | Supplier Update and Issue Reactor Internals & Structural Integrity During Defueling Report EAN | 22-Aug-22 A | 04-Nov-22 A | 5 | 0 | 54 | 100% |  | Completed
ER6668LT | W213 | W213.A26300 | TOR Essential Defueling Safety Case | 2022-08-12 | 2022-08-18 | Supplier Update and Issue Reactor Internals & Structural Integrity During Defueling Report EAN | 22-Aug-22 A | 04-Nov-22 A | 5 | 0 | 54 | 100% |  | Completed
ER6370LT | W201 | ER6370.A12325 | HNB Reactors Shutdown Essential Safety Cases |  |  | Post PRC Actions Closeout | 23-Aug-22 A | 23-Aug-22 A | 5 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A12315 | HNB Reactors Shutdown Essential Safety Cases |  |  | Hold PRC Meeting | 23-Aug-22 A | 23-Aug-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13080 | HNB Reactors Shutdown Essential Safety Cases |  | 2021-08-27 | Gate D For Region 1 Essential Defuelling Safety Case (HNB) | 23-Aug-22 A | 23-Aug-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A29950 | HYB Essential Defueling Safety Case | 2022-08-16 | 2022-08-16 | Pre Job Brief for FM Underload Protection Mods Prelim Design (GLM) | 24-Aug-22 A | 24-Aug-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | 2997 | HRA Reactors Shutdown Essential Safety Cases |  | 2022-07-05 | Share NSRS with ONR | 24-Aug-22 A | 24-Aug-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | 2997 | HYA Reactors Shutdown Essential Safety Cases |  | 2022-07-05 | Share NSRS with ONR | 24-Aug-22 A | 24-Aug-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A30940 | HYB Essential Defueling Safety Case |  |  | Pre Job Brief for Channel X | 24-Aug-22 A | 24-Aug-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A29950 | TOR Essential Defueling Safety Case | 2022-08-16 | 2022-08-16 | Pre Job Brief for FM Underload Protection Mods Prelim Design (GLM) | 24-Aug-22 A | 24-Aug-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A30940 | TOR Essential Defueling Safety Case |  |  | Pre Job Brief for Channel X | 24-Aug-22 A | 24-Aug-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A29960 | HYB Essential Defueling Safety Case | 2022-08-17 | 2023-01-23 | Functional Requirement Spec for FM Underload Protection Mods Prelim Design (GLM) | 25-Aug-22 A | 01-Nov-22 A | 37 | 0 | 48 | 100% |  | Completed
ER6666LT | W209 | W209.A30950 | HYB Essential Defueling Safety Case |  |  | Functional Requirement Spec for Channel X | 25-Aug-22 A | 01-Nov-22 A | 37 | 0 | 48 | 100% |  | Completed
ER6668LT | W213 | W213.A29960 | TOR Essential Defueling Safety Case | 2022-08-17 | 2023-01-23 | Functional Requirement Spec for FM Underload Protection Mods Prelim Design (GLM) | 25-Aug-22 A | 01-Nov-22 A | 37 | 0 | 48 | 100% |  | Completed
ER6668LT | W213 | W213.A30950 | TOR Essential Defueling Safety Case |  |  | Functional Requirement Spec for Channel X | 25-Aug-22 A | 01-Nov-22 A | 37 | 0 | 48 | 100% |  | Completed
ER6650LT | W226 | 2797 | HYA Fuel Handling Essential Safety Case |  |  | Share NSRS with ONR | 25-Aug-22 A | 25-Aug-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | 1590 | HRA Reactors Shutdown Essential Safety Cases |  | 2022-07-29 | Update technical references for FDD | 26-Aug-22 A | 26-Aug-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | 1590 | HYA Reactors Shutdown Essential Safety Cases |  | 2022-07-29 | Update technical references for FDD | 26-Aug-22 A | 26-Aug-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A17330 | HNB Reactors Shutdown Essential Safety Cases | 2020-03-02 | 2021-09-13 | ETC (DD-PF) | 30-Aug-22 A | 30-Aug-22 A | 21 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A28160 | HYB Essential Defueling Safety Case |  | 2022-08-23 | FEA Model Approved | 31-Aug-22 A | 31-Aug-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A28160 | TOR Essential Defueling Safety Case |  | 2022-08-23 | FEA Model Approved | 31-Aug-22 A | 31-Aug-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6370LT | W201 | ER6370.A13050 | HNB Reactors Shutdown Essential Safety Cases |  | 2021-09-14 | Phase 2 Project Completion | 31-Aug-22 A | 31-Aug-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A26680 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-07-29 | Verify Review of flux detector suitability EAN & Issue for Technical Review | 01-Sep-22 A | 04-Oct-22 A | 20 | 0 | 23 | 100% |  | Completed
ER6668LT | W213 | W213.A26680 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-07-29 | Verify Review of flux detector suitability EAN & Issue for Technical Review | 01-Sep-22 A | 04-Oct-22 A | 20 | 0 | 23 | 100% |  | Completed
ER6666LT | W209 | W209.A29480 | HYB Essential Defueling Safety Case | 2022-09-05 | 2022-09-23 | Verify Cooling Plant OPEX Study EAN & Issue for Technical Review | 01-Sep-22 A | 05-Sep-22 A | 3 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.A29480 | TOR Essential Defueling Safety Case | 2022-09-05 | 2022-09-23 | Verify Cooling Plant OPEX Study EAN & Issue for Technical Review | 01-Sep-22 A | 05-Sep-22 A | 3 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.A27180 | HYB Essential Defueling Safety Case | 2022-07-22 | 2022-07-29 | Supplier Update and Issue Flow Induced Vibration EAN | 05-Sep-22 A | 03-Oct-22 A | 6 | 0 | 21 | 100% |  | Completed
ER6666LT | W209 | W209.A29920 | HYB Essential Defueling Safety Case | 2022-11-07 | 2022-11-11 | Complete TR Form and Upload FPU Maintenance Analysis EAN to CDMS | 05-Sep-22 A | 09-Sep-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A27180 | TOR Essential Defueling Safety Case | 2022-07-22 | 2022-07-29 | Supplier Update and Issue Flow Induced Vibration EAN | 05-Sep-22 A | 03-Oct-22 A | 6 | 0 | 21 | 100% |  | Completed
ER6668LT | W213 | W213.A29920 | TOR Essential Defueling Safety Case | 2022-11-07 | 2022-11-11 | Complete TR Form and Upload FPU Maintenance Analysis EAN to CDMS | 05-Sep-22 A | 09-Sep-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.A29810 | HYB Essential Defueling Safety Case | 2022-09-13 | 2022-10-03 | Verify Feasibility of Draining PVCS (Report) & Issue for Technical Review | 06-Sep-22 A | 09-Sep-22 A | 15 | 0 | 4 | 100% |  | Completed
ER6668LT | W213 | W213.A29810 | TOR Essential Defueling Safety Case | 2022-09-13 | 2022-10-03 | Verify Feasibility of Draining PVCS (Report) & Issue for Technical Review | 06-Sep-22 A | 09-Sep-22 A | 15 | 0 | 4 | 100% |  | Completed
ER6666LT | W209 | W209.A29490 | HYB Essential Defueling Safety Case | 2022-09-26 | 2022-10-14 | Technical Review of Cooling Plant OPEX Study EAN | 06-Sep-22 A | 21-Oct-22 A | 15 | 0 | 34 | 100% |  | Completed
ER6668LT | W213 | W213.A29490 | TOR Essential Defueling Safety Case | 2022-09-26 | 2022-10-14 | Technical Review of Cooling Plant OPEX Study EAN | 06-Sep-22 A | 21-Oct-22 A | 15 | 0 | 34 | 100% |  | Completed
ER6666LT | W209 | W209.A26760 | HYB Essential Defueling Safety Case | 2022-09-09 | 2022-10-20 | Verify Boron Bead Injection Feasibility & Control Rod Isolation EAN & Issue for Technical Review | 09-Sep-22 A | 15-Nov-22 A | 30 | 0 | 48 | 100% |  | Completed
ER6668LT | W213 | W213.A26760 | TOR Essential Defueling Safety Case | 2022-09-09 | 2022-10-20 | Verify Boron Bead Injection Feasibility & Control Rod Isolation EAN & Issue for Technical Review | 09-Sep-22 A | 15-Nov-22 A | 30 | 0 | 48 | 100% |  | Completed
ER6666LT | W209 | W209.A29930 | HYB Essential Defueling Safety Case |  | 2022-11-11 | FPU Maintenance Analysis EAN Available | 09-Sep-22 A | 09-Sep-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A29930 | TOR Essential Defueling Safety Case |  | 2022-11-11 | FPU Maintenance Analysis EAN Available | 09-Sep-22 A | 09-Sep-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A29820 | HYB Essential Defueling Safety Case | 2022-10-04 | 2022-10-24 | Technical Review of Feasibility of Draining PVCS (Report) | 12-Sep-22 A | 28-Oct-22 A | 15 | 0 | 35 | 100% |  | Completed
ER6668LT | W213 | W213.A29820 | TOR Essential Defueling Safety Case | 2022-10-04 | 2022-10-24 | Technical Review of Feasibility of Draining PVCS (Report) | 12-Sep-22 A | 28-Oct-22 A | 15 | 0 | 35 | 100% |  | Completed
ER6666LT | W209 | W209.A27020 | HYB Essential Defueling Safety Case | 2022-11-21 | 2022-11-25 | Supplier Update and Issue Review of FM Cyclic Duty EAN | 13-Sep-22 A | 07-Oct-22 A | 5 | 0 | 19 | 100% |  | Completed
ER6666LT | W209 | W209.A30800 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-07-29 | Verify PANTHER SCM Assessments - Agree Defuelling Order EAN & Issue for T Review | 13-Sep-22 A | 31-Oct-22 A | 20 | 0 | 34 | 100% |  | Completed
ER6668LT | W213 | W213.A27020 | TOR Essential Defueling Safety Case | 2022-11-21 | 2022-11-25 | Supplier Update and Issue Review of FM Cyclic Duty EAN | 13-Sep-22 A | 07-Oct-22 A | 5 | 0 | 19 | 100% |  | Completed
ER6668LT | W213 | W213.A30800 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-07-29 | Verify PANTHER SCM Assessments - Agree Defuelling Order EAN & Issue for T Review | 13-Sep-22 A | 31-Oct-22 A | 20 | 0 | 34 | 100% |  | Completed
ER6666LT | W209 | W209.A26890 | HYB Essential Defueling Safety Case | 2022-09-01 | 2022-12-21 | Chemistry Monitoring Strategy EAN ## (Cost Summary) (Claim 3) | 14-Sep-22 A | 03-Mar-23 A | 129 | 0 | 120 | 100% |  | Completed
ER6666LT | W209 | W209.A26900 | HYB Essential Defueling Safety Case | 2022-09-01 | 2022-09-01 | Pre Job Brief for Chemistry Monitoring Strategy EAN | 14-Sep-22 A | 14-Sep-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A26890 | TOR Essential Defueling Safety Case | 2022-09-01 | 2022-12-21 | Chemistry Monitoring Strategy EAN ## (Cost Summary) (Claim 3) | 14-Sep-22 A | 03-Mar-23 A | 129 | 0 | 120 | 100% |  | Completed
ER6668LT | W213 | W213.A26900 | TOR Essential Defueling Safety Case | 2022-09-01 | 2022-09-01 | Pre Job Brief for Chemistry Monitoring Strategy EAN | 14-Sep-22 A | 14-Sep-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A26910 | HYB Essential Defueling Safety Case | 2022-09-02 | 2022-11-09 | Draft Chemistry Monitoring Strategy EAN | 15-Sep-22 A | 09-Nov-22 A | 49 | 0 | 39 | 100% |  | Completed
ER6668LT | W213 | W213.A26910 | TOR Essential Defueling Safety Case | 2022-09-02 | 2022-11-09 | Draft Chemistry Monitoring Strategy EAN | 15-Sep-22 A | 09-Nov-22 A | 49 | 0 | 39 | 100% |  | Completed
ER6371LT | W202 | 1620 | HRA Reactors Shutdown Essential Safety Cases | 2022-08-15 | 2022-08-19 | Verify updated FDD | 27-Sep-22 A | 30-Nov-22 A | 10 | 0 | 46 | 100% |  | Completed
ER6661LT | W206 | 1620 | HYA Reactors Shutdown Essential Safety Cases | 2022-08-15 | 2022-08-19 | Verify updated FDD | 27-Sep-22 A | 30-Nov-22 A | 10 | 0 | 46 | 100% |  | Completed
ER6371LT | W202 | 1840 | HRA Reactors Shutdown Essential Safety Cases | 2022-09-14 | 2022-09-20 | EDF Verification | 28-Sep-22 A | 12-Oct-22 A | 5 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | 1840 | HYA Reactors Shutdown Essential Safety Cases | 2022-09-14 | 2022-09-20 | EDF Verification | 28-Sep-22 A | 12-Oct-22 A | 5 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.A25880 | HYB Essential Defueling Safety Case | 2022-09-01 | 2022-09-28 | Verify Safety Case Requirements EAN - TASK E EAN & Issue for Tech Review | 30-Sep-22 A | 13-Jan-23 A | 20 | 0 | 73 | 100% |  | Completed
ER6668LT | W213 | W213.A25880 | TOR Essential Defueling Safety Case | 2022-09-01 | 2022-09-28 | Verify Safety Case Requirements EAN - TASK E EAN & Issue for Tech Review | 30-Sep-22 A | 13-Jan-23 A | 20 | 0 | 73 | 100% |  | Completed
ER6650LT | W226 | 1950 | HYA Fuel Handling Essential Safety Case |  |  | Update Head Document | 03-Oct-22 A | 20-Jan-23 A | 20 | 0 | 73 | 100% |  | Completed
W232LT | W232 | W232.A1050 | DNB Enhanced Safety Cases | 2022-10-03 | 2023-01-31 | Project Management - Early Release Funding | 03-Oct-22 A | 31-Jan-23 A | 84 | 0 | 83 | 100% |  | Completed
W232LT | W232 | W232.A1060 | DNB Enhanced Safety Cases | 2022-10-03 |  | Project Start (FEED TO SUMMARY SCHEDULE) | 03-Oct-22 A | 03-Oct-22 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1690 | DNB Enhanced Safety Cases | 2022-10-03 | 2022-10-14 | Write PRC Paper | 03-Oct-22 A | 14-Oct-22 A | 10 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.A1680 | DNB Enhanced Safety Cases | 2022-10-03 | 2024-07-25 | Summary for DNB Fuel Handling Enhanced Safety Cases W232 | 03-Oct-22 A | 2026-02-20 | 63 | 247 | 857 | 70% | 5 | In Progress
ER6666LT | W209 | W209.A26570 | HYB Essential Defueling Safety Case | 2022-08-01 | 2022-10-14 | Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN ## (Cost Summary) (Claim 1) | 03-Oct-22 A | 24-Jan-23 A | 77 | 0 | 78 | 100% |  | Completed
ER6666LT | W209 | W209.A26580 | HYB Essential Defueling Safety Case | 2022-08-01 | 2022-08-01 | Pre Job Brief for Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 03-Oct-22 A | 03-Oct-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A28650 | HYB Essential Defueling Safety Case | 2023-01-03 | 2023-04-04 | CSP/Diagrid Structural Integrity Summary Report ## (Cost Summary) (Claim 4) | 03-Oct-22 A | 31-Mar-23 A | 127 | 0 | 127 | 100% |  | Completed
ER6666LT | W209 | W209.A28660 | HYB Essential Defueling Safety Case |  |  | Pre Job Brief for CSP/Diagrid Structural Integrity Summary Report | 03-Oct-22 A | 03-Oct-22 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A1030 | DNB Enhanced Safety Cases | 2022-10-03 | 2022-10-04 | Planning Workshop | 03-Oct-22 A | 04-Oct-22 A | 2 | 0 | 2 | 100% |  | Completed
W232LT | W232 | W232.A1040 | DNB Enhanced Safety Cases | 2022-10-03 | 2023-01-31 | Technical Oversight - Early Release Funding | 03-Oct-22 A | 31-Jan-23 A | 84 | 0 | 83 | 100% |  | Completed
W232LT | W232 | W232.A2660 | DNB Enhanced Safety Cases | 2022-10-03 | 2022-11-17 | Review Risks Related to needing FLSA | 03-Oct-22 A | 17-Nov-22 A | 34 | 0 | 34 | 100% |  | Completed
ER6668LT | W213 | W213.A26570 | TOR Essential Defueling Safety Case | 2022-08-01 | 2022-10-14 | Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN ## (Cost Summary) (Claim 1) | 03-Oct-22 A | 24-Jan-23 A | 77 | 0 | 78 | 100% |  | Completed
ER6668LT | W213 | W213.A26580 | TOR Essential Defueling Safety Case | 2022-08-01 | 2022-08-01 | Pre Job Brief for Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 03-Oct-22 A | 03-Oct-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A28650 | TOR Essential Defueling Safety Case | 2023-01-03 | 2023-04-04 | CSP/Diagrid Structural Integrity Summary Report ## (Cost Summary) (Claim 4) | 03-Oct-22 A | 31-Mar-23 A | 127 | 0 | 127 | 100% |  | Completed
ER6668LT | W213 | W213.A28660 | TOR Essential Defueling Safety Case |  |  | Pre Job Brief for CSP/Diagrid Structural Integrity Summary Report | 03-Oct-22 A | 03-Oct-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A25730 | HYB Essential Defueling Safety Case | 2022-07-14 | 2022-08-03 | Technical Review of Judgement Based Work Diversion EAN | 04-Oct-22 A | 10-Feb-23 A | 28 | 0 | 91 | 100% |  | Completed
ER6668LT | W213 | W213.A25730 | TOR Essential Defueling Safety Case | 2022-07-14 | 2022-08-03 | Technical Review of Judgement Based Work Diversion EAN | 04-Oct-22 A | 10-Feb-23 A | 28 | 0 | 91 | 100% |  | Completed
ER6666LT | W209 | W209.A26590 | HYB Essential Defueling Safety Case | 2022-08-02 | 2022-08-18 | Draft Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 04-Oct-22 A | 28-Oct-22 A | 13 | 0 | 19 | 100% |  | Completed
ER6666LT | W209 | W209.A27190 | HYB Essential Defueling Safety Case | 2022-08-01 | 2022-08-05 | Complete TR Form and Upload Flow Induced Vibration EAN to CDMS | 04-Oct-22 A | 31-Oct-22 A | 5 | 0 | 19 | 100% |  | Completed
ER6666LT | W209 | W209.A27380 | HYB Essential Defueling Safety Case | 2022-09-02 | 2022-09-02 | Pre Job Brief for Fuel Route PSA Update EAN | 04-Oct-22 A | 04-Oct-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A28670 | HYB Essential Defueling Safety Case |  |  | Draft CSP/Diagrid Structural Integrity Summary Report | 04-Oct-22 A | 21-Nov-22 A | 35 | 0 | 35 | 100% |  | Completed
ER6668LT | W213 | W213.A26590 | TOR Essential Defueling Safety Case | 2022-08-02 | 2022-08-18 | Draft Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 04-Oct-22 A | 28-Oct-22 A | 13 | 0 | 19 | 100% |  | Completed
ER6668LT | W213 | W213.A27190 | TOR Essential Defueling Safety Case | 2022-08-01 | 2022-08-05 | Complete TR Form and Upload Flow Induced Vibration EAN to CDMS | 04-Oct-22 A | 31-Oct-22 A | 5 | 0 | 19 | 100% |  | Completed
ER6668LT | W213 | W213.A27380 | TOR Essential Defueling Safety Case | 2022-09-02 | 2022-09-02 | Pre Job Brief for Fuel Route PSA Update EAN | 04-Oct-22 A | 04-Oct-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A28670 | TOR Essential Defueling Safety Case |  |  | Draft CSP/Diagrid Structural Integrity Summary Report | 04-Oct-22 A | 21-Nov-22 A | 35 | 0 | 35 | 100% |  | Completed
ER6666LT | W209 | W209.A26690 | HYB Essential Defueling Safety Case | 2022-08-01 | 2022-08-31 | Technical Review of Review of flux detector suitability EAN | 05-Oct-22 A | 11-Nov-22 A | 23 | 0 | 28 | 100% |  | Completed
ER6668LT | W213 | W213.A26690 | TOR Essential Defueling Safety Case | 2022-08-01 | 2022-08-31 | Technical Review of Review of flux detector suitability EAN | 05-Oct-22 A | 11-Nov-22 A | 23 | 0 | 28 | 100% |  | Completed
ER6666LT | W209 | W209.A27390 | HYB Essential Defueling Safety Case | 2022-09-05 | 2023-01-25 | Draft Fuel Route PSA Update | 05-Oct-22 A | 14-Dec-22 A | 58 | 0 | 51 | 100% |  | Completed
ER6668LT | W213 | W213.A27390 | TOR Essential Defueling Safety Case | 2022-09-05 | 2023-01-25 | Draft Fuel Route PSA Update | 05-Oct-22 A | 14-Dec-22 A | 58 | 0 | 51 | 100% |  | Completed
ER6666LT | W209 | W209.A26220 | HYB Essential Defueling Safety Case | 2022-09-06 | 2022-09-12 | Supplier Update and Issue Pressure Boundary Integrity of Seals Report EAN | 07-Oct-22 A | 24-Oct-22 A | 5 | 0 | 11 | 100% |  | Completed
ER6668LT | W213 | W213.A26220 | TOR Essential Defueling Safety Case | 2022-09-06 | 2022-09-12 | Supplier Update and Issue Pressure Boundary Integrity of Seals Report EAN | 07-Oct-22 A | 24-Oct-22 A | 5 | 0 | 11 | 100% |  | Completed
ER6666LT | W209 | W209.A27030 | HYB Essential Defueling Safety Case | 2022-11-28 | 2022-12-02 | Complete TR Form and Upload Review of FM Cyclic Duty EAN to CDMS | 10-Oct-22 A | 31-Oct-22 A | 5 | 0 | 15 | 100% |  | Completed
ER6371LT | W202 | 2350 | HRA Reactors Shutdown Essential Safety Cases | 2022-10-28 | 2022-10-31 | Update Verification Plan | 10-Oct-22 A | 11-Oct-22 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | 2450 | HRA Reactors Shutdown Essential Safety Cases | 2022-09-21 | 2022-09-23 | LSD Updates | 10-Oct-22 A | 23-Nov-22 A | 3 | 0 | 32 | 100% |  | Completed
ER6371LT | W202 | 2300 | HRA Reactors Shutdown Essential Safety Cases | 2022-09-21 | 2022-10-11 | Update EC | 10-Oct-22 A | 07-Nov-22 A | 5 | 0 | 21 | 100% |  | Completed
ER6371LT | W202 | 2250 | HRA Reactors Shutdown Essential Safety Cases | 2022-09-21 | 2022-10-27 | Paper - Summary | 10-Oct-22 A | 28-Feb-23 A | 99 | 0 | 98 | 100% |  | Completed
ER6371LT | W202 | 2345 | HRA Reactors Shutdown Essential Safety Cases | 2022-10-28 | 2022-12-07 | Verification Phase - Summary | 10-Oct-22 A | 12-Jun-23 A | 168 | 0 | 168 | 100% |  | Completed
ER6371LT | W202 | 2435 | HRA Reactors Shutdown Essential Safety Cases | 2022-09-21 | 2022-11-23 | LSD Updates - Summary | 10-Oct-22 A | 16-Mar-23 A | 111 | 0 | 111 | 100% |  | Completed
ER6661LT | W206 | 2350 | HYA Reactors Shutdown Essential Safety Cases | 2022-10-28 | 2022-10-31 | Update Verification Plan | 10-Oct-22 A | 11-Oct-22 A | 2 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | 2450 | HYA Reactors Shutdown Essential Safety Cases | 2022-09-21 | 2022-09-23 | LSD Updates | 10-Oct-22 A | 23-Nov-22 A | 3 | 0 | 32 | 100% |  | Completed
ER6661LT | W206 | 2300 | HYA Reactors Shutdown Essential Safety Cases | 2022-09-21 | 2022-10-11 | Update EC | 10-Oct-22 A | 07-Nov-22 A | 5 | 0 | 21 | 100% |  | Completed
ER6661LT | W206 | 2250 | HYA Reactors Shutdown Essential Safety Cases | 2022-09-21 | 2022-10-27 | Paper - Summary | 10-Oct-22 A | 28-Feb-23 A | 99 | 0 | 99 | 100% |  | Completed
ER6661LT | W206 | 2345 | HYA Reactors Shutdown Essential Safety Cases | 2022-10-28 | 2022-12-07 | Verification Phase - Summary | 10-Oct-22 A | 12-Jun-23 A | 168 | 0 | 168 | 100% |  | Completed
ER6661LT | W206 | 2435 | HYA Reactors Shutdown Essential Safety Cases | 2022-09-21 | 2022-11-23 | LSD Updates - Summary | 10-Oct-22 A | 16-Mar-23 A | 111 | 0 | 111 | 100% |  | Completed
ER6668LT | W213 | W213.A27030 | TOR Essential Defueling Safety Case | 2022-11-28 | 2022-12-02 | Complete TR Form and Upload Review of FM Cyclic Duty EAN to CDMS | 10-Oct-22 A | 31-Oct-22 A | 5 | 0 | 15 | 100% |  | Completed
ER6666LT | W209 | W209.8380 | HYB Essential Defueling Safety Case | 2022-10-12 | 2023-09-13 | Claim 4 Production ## (Cost Summary) | 12-Oct-22 A | 29-Feb-24 A | 312 | 0 | 349 | 100% |  | Completed
ER6666LT | W209 | W209.8940 | HYB Essential Defueling Safety Case |  | 2022-11-08 | Discovery Milestone - Dropped FPU Decision Point | 12-Oct-22 A | 12-Oct-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.8950 | HYB Essential Defueling Safety Case | 2022-11-08 | 2022-11-08 | Dropped FPU Decision Point | 12-Oct-22 A | 12-Oct-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.8380 | TOR Essential Defueling Safety Case | 2022-10-12 | 2023-09-13 | Claim 4 Production ## (Cost Summary) | 12-Oct-22 A | 29-Feb-24 A | 306 | 0 | 349 | 100% |  | Completed
ER6668LT | W213 | W213.8940 | TOR Essential Defueling Safety Case |  | 2022-11-08 | Discovery Milestone - Dropped FPU Decision Point | 12-Oct-22 A | 12-Oct-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.8950 | TOR Essential Defueling Safety Case | 2022-11-08 | 2022-11-08 | Dropped FPU Decision Point | 12-Oct-22 A | 12-Oct-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | 2360 | HRA Reactors Shutdown Essential Safety Cases | 2022-11-01 | 2022-11-01 | Secure Verification Resource | 12-Oct-22 A | 12-Oct-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | 2360 | HYA Reactors Shutdown Essential Safety Cases | 2022-11-01 | 2022-11-01 | Secure Verification Resource | 12-Oct-22 A | 12-Oct-22 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A1720 | DNB Enhanced Safety Cases | 2022-10-17 | 2022-12-14 | COST BAR - Obtain Gate A Funding | 14-Oct-22 A | 01-Dec-22 A | 43 | 0 | 33 | 100% |  | Completed
ER6666LT | W209 | W209.A29210 | HYB Essential Defueling Safety Case | 2022-11-01 | 2023-03-21 | Defuelling Hazards Review EAN ## (Cost Summary) (Claim 5) | 17-Oct-22 A | 31-Jul-23 A | 191 | 0 | 197 | 100% |  | Completed
ER6666LT | W209 | W209.6820 | HYB Essential Defueling Safety Case | 2022-11-01 | 2022-11-07 | Prepare Spec for Defuelling Hazards Review EAN | 17-Oct-22 A | 31-Oct-22 A | 5 | 0 | 11 | 100% |  | Completed
ER6668LT | W213 | W213.A29210 | TOR Essential Defueling Safety Case | 2022-11-01 | 2023-03-21 | Defuelling Hazards Review EAN ## (Cost Summary) (Claim 5) | 17-Oct-22 A | 31-Jul-23 A | 191 | 0 | 197 | 100% |  | Completed
ER6668LT | W213 | W213.6820 | TOR Essential Defueling Safety Case | 2022-11-01 | 2022-11-07 | Prepare Spec for Defuelling Hazards Review EAN | 17-Oct-22 A | 31-Oct-22 A | 5 | 0 | 11 | 100% |  | Completed
W232LT | W232 | W232.A1710 | DNB Enhanced Safety Cases | 2022-10-17 | 2022-10-21 | Prepare Schedule | 17-Oct-22 A | 21-Oct-22 A | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.A1290 | DNB Enhanced Safety Cases | 2022-10-17 | 2022-10-21 | Produce MF | 17-Oct-22 A | 21-Oct-22 A | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.A1300 | DNB Enhanced Safety Cases | 2022-10-17 | 2022-10-21 | Agree design proposals with Station in the case of hardware mods | 17-Oct-22 A | 21-Oct-22 A | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.A1270 | DNB Enhanced Safety Cases | 2022-10-17 |  | Mod requested, Initiate EC, identify RE, register EC & identify milestones in Passport | 17-Oct-22 A | 17-Oct-22 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1310 | DNB Enhanced Safety Cases | 2022-10-17 | 2022-10-21 | Produce supporting references | 17-Oct-22 A | 21-Oct-22 A | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.A1280 | DNB Enhanced Safety Cases | 2022-10-17 | 2022-10-18 | Develop deliverable plan with Work Management (using CAT 3 template) | 17-Oct-22 A | 18-Oct-22 A | 2 | 0 | 2 | 100% |  | Completed
W232LT | W232 | W232.A1320 | DNB Enhanced Safety Cases |  | 2022-10-18 | Deliverable plan baselined; all ECs & references identified | 18-Oct-22 A | 18-Oct-22 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1330 | DNB Enhanced Safety Cases |  | 2022-10-18 | Issue agreed work programme to stakeholders and suppliers | 18-Oct-22 A | 18-Oct-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7070 | HYB Essential Defueling Safety Case | 2022-09-02 | 2022-09-02 | PJB for Claim 3 Authoring | 19-Oct-22 A | 10-Jan-23 A | 1 | 0 | 57 | 100% |  | Completed
ER6666LT | W209 | W209.8370 | HYB Essential Defueling Safety Case | 2022-10-19 | 2023-08-25 | Claim 3 Production ## (Cost Summary) | 19-Oct-22 A | 24-Jan-24 A | 284 | 0 | 318 | 100% |  | Completed
ER6668LT | W213 | W213.7070 | TOR Essential Defueling Safety Case | 2022-09-02 | 2022-09-02 | PJB for Claim 3 Authoring | 19-Oct-22 A | 10-Jan-23 A | 1 | 0 | 57 | 100% |  | Completed
ER6668LT | W213 | W213.8370 | TOR Essential Defueling Safety Case | 2022-10-19 | 2023-08-25 | Claim 3 Production ## (Cost Summary) | 19-Oct-22 A | 24-Jan-24 A | 290 | 0 | 319 | 100% |  | Completed
ER6666LT | W209 | W209.7080 | HYB Essential Defueling Safety Case | 2022-09-29 | 2023-01-23 | Author Claim 3 | 20-Oct-22 A | 31-Mar-23 A | 80 | 0 | 114 | 100% |  | Completed
ER6668LT | W213 | W213.7080 | TOR Essential Defueling Safety Case | 2022-09-29 | 2023-01-23 | Author Claim 3 | 20-Oct-22 A | 31-Mar-23 A | 80 | 0 | 114 | 100% |  | Completed
ER6666LT | W209 | W209.6890 | HYB Essential Defueling Safety Case | 2022-08-02 | 2022-08-02 | PJB for Claim 1 Authoring | 21-Oct-22 A | 21-Oct-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.8350 | HYB Essential Defueling Safety Case | 2022-10-21 | 2023-08-07 | Claim 1 Production ## (Cost Summary) | 21-Oct-22 A | 29-Nov-23 A | 241 | 0 | 279 | 100% |  | Completed
ER6668LT | W213 | W213.6890 | TOR Essential Defueling Safety Case | 2022-08-02 | 2022-08-02 | PJB for Claim 1 Authoring | 21-Oct-22 A | 21-Oct-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.8350 | TOR Essential Defueling Safety Case | 2022-10-21 | 2023-08-07 | Claim 1 Production ## (Cost Summary) | 21-Oct-22 A | 29-Nov-23 A | 241 | 0 | 279 | 100% |  | Completed
W232LT | W232 | W232.A1340 | DNB Enhanced Safety Cases |  | 2022-10-21 | Issue MF | 21-Oct-22 A | 21-Oct-22 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1350 | DNB Enhanced Safety Cases |  | 2022-10-21 | CA appointed | 21-Oct-22 A | 21-Oct-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.6900 | HYB Essential Defueling Safety Case | 2022-08-25 | 2022-12-15 | Author Claim 1 | 24-Oct-22 A | 16-Dec-22 A | 42 | 0 | 40 | 100% |  | Completed
ER6668LT | W213 | W213.6900 | TOR Essential Defueling Safety Case | 2022-08-25 | 2022-12-15 | Author Claim 1 | 24-Oct-22 A | 16-Dec-22 A | 42 | 0 | 40 | 100% |  | Completed
W232LT | W232 | W232.A1730 | DNB Enhanced Safety Cases | 2022-10-24 | 2022-10-28 | Prepare Cost Estimates +/- 10% B-C & +/- 30% Lifecycle | 24-Oct-22 A | 01-Nov-22 A | 5 | 0 | 7 | 100% |  | Completed
ER6666LT | W209 | W209.A29500 | HYB Essential Defueling Safety Case | 2022-10-17 | 2022-10-21 | Supplier Update and Issue Cooling Plant OPEX Study EAN | 24-Oct-22 A | 28-Oct-22 A | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.A1370 | DNB Enhanced Safety Cases | 2022-10-24 | 2022-10-26 | Update MF (if necessary) | 24-Oct-22 A | 26-Oct-22 A | 3 | 0 | 3 | 100% |  | Completed
W232LT | W232 | W232.A1380 | DNB Enhanced Safety Cases | 2022-10-24 | 2022-10-25 | Identify verifier (V) for case | 24-Oct-22 A | 25-Oct-22 A | 2 | 0 | 2 | 100% |  | Completed
W232LT | W232 | W232.A1360 | DNB Enhanced Safety Cases | 2022-10-24 |  | Categorisation by station | 24-Oct-22 A | 24-Oct-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A29500 | TOR Essential Defueling Safety Case | 2022-10-17 | 2022-10-21 | Supplier Update and Issue Cooling Plant OPEX Study EAN | 24-Oct-22 A | 28-Oct-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.A26230 | HYB Essential Defueling Safety Case | 2022-09-13 | 2022-09-19 | Complete TR Form and Upload Pressure Boundary Integrity of Seals Report EAN to CDMS | 25-Oct-22 A | 30-Nov-22 A | 5 | 0 | 27 | 100% |  | Completed
ER6668LT | W213 | W213.A26230 | TOR Essential Defueling Safety Case | 2022-09-13 | 2022-09-19 | Complete TR Form and Upload Pressure Boundary Integrity of Seals Report EAN to CDMS | 25-Oct-22 A | 30-Nov-22 A | 5 | 0 | 27 | 100% |  | Completed
W232LT | W232 | W232.A1400 | DNB Enhanced Safety Cases | 2022-10-26 | 2022-10-26 | Produce verification plan | 26-Oct-22 A | 26-Oct-22 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A1410 | DNB Enhanced Safety Cases |  | 2022-10-26 | MF Complete | 26-Oct-22 A | 26-Oct-22 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1420 | DNB Enhanced Safety Cases | 2022-10-27 | 2022-11-02 | Prepare the Proposal | 27-Oct-22 A | 02-Nov-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.A26530 | HYB Essential Defueling Safety Case | 2022-08-01 | 2022-08-23 | Technical Review of PANTHER SCM Assessments - Agree Defuelling Order EAN | 31-Oct-22 A | 23-Dec-22 A | 17 | 0 | 40 | 100% |  | Completed
ER6666LT | W209 | W209.A27040 | HYB Essential Defueling Safety Case |  | 2022-12-02 | Review of FM Cyclic Duty EAN Available | 31-Oct-22 A | 31-Oct-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A27200 | HYB Essential Defueling Safety Case |  | 2022-08-05 | Flow Induced Vibration EAN Available | 31-Oct-22 A | 31-Oct-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A26530 | TOR Essential Defueling Safety Case | 2022-08-01 | 2022-08-23 | Technical Review of PANTHER SCM Assessments - Agree Defuelling Order EAN | 31-Oct-22 A | 23-Dec-22 A | 17 | 0 | 40 | 100% |  | Completed
ER6668LT | W213 | W213.A27040 | TOR Essential Defueling Safety Case |  | 2022-12-02 | Review of FM Cyclic Duty EAN Available | 31-Oct-22 A | 31-Oct-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A27200 | TOR Essential Defueling Safety Case |  | 2022-08-05 | Flow Induced Vibration EAN Available | 31-Oct-22 A | 31-Oct-22 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1740 | DNB Enhanced Safety Cases | 2022-10-31 | 2022-11-04 | PRC Paper stakeholder sign off | 31-Oct-22 A | 04-Nov-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.A26600 | HYB Essential Defueling Safety Case | 2022-08-19 | 2022-09-02 | Verify Fault Review - Impact on SCM, Misloading Consequences & Issue for Technical Review | 31-Oct-22 A | 13-Dec-22 A | 4 | 0 | 32 | 100% |  | Completed
ER6666LT | W209 | W209.A29510 | HYB Essential Defueling Safety Case | 2022-10-24 | 2022-10-28 | Complete TR Form and Upload Cooling Plant OPEX Study EAN to CDMS | 31-Oct-22 A | 11-Nov-22 A | 5 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.A29830 | HYB Essential Defueling Safety Case | 2022-10-25 | 2022-10-31 | Supplier Update and Issue Feasibility of Draining PVCS (Report) | 31-Oct-22 A | 18-Nov-22 A | 5 | 0 | 15 | 100% |  | Completed
ER6668LT | W213 | W213.A26600 | TOR Essential Defueling Safety Case | 2022-08-19 | 2022-09-02 | Verify Fault Review - Impact on SCM, Misloading Consequences & Issue for Technical Review | 31-Oct-22 A | 13-Dec-22 A | 4 | 0 | 32 | 100% |  | Completed
ER6668LT | W213 | W213.A29510 | TOR Essential Defueling Safety Case | 2022-10-24 | 2022-10-28 | Complete TR Form and Upload Cooling Plant OPEX Study EAN to CDMS | 31-Oct-22 A | 11-Nov-22 A | 5 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.A29830 | TOR Essential Defueling Safety Case | 2022-10-25 | 2022-10-31 | Supplier Update and Issue Feasibility of Draining PVCS (Report) | 31-Oct-22 A | 18-Nov-22 A | 5 | 0 | 15 | 100% |  | Completed
ER6666LT | W209 | W209.A28970 | HYB Essential Defueling Safety Case | 2022-11-01 | 2023-02-24 | Summary of Compliance with RADWASTE Assessment Principles EAN ## (Cost Summary) (Claim 7) | 01-Nov-22 A | 14-Apr-23 A | 114 | 0 | 114 | 100% |  | Completed
ER6666LT | W209 | W209.A28980 | HYB Essential Defueling Safety Case | 2022-11-01 | 2022-11-01 | Pre Job Brief for Summary of Compliance with RADWASTE Assessment Principles EAN | 01-Nov-22 A | 01-Nov-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.6830 | HYB Essential Defueling Safety Case | 2022-11-08 | 2022-11-21 | Prepare Task Sheet for Defuelling Hazards Review EAN | 01-Nov-22 A | 23-Dec-22 A | 10 | 0 | 39 | 100% |  | Completed
ER6666LT | W209 | W209.A29560 | HYB Essential Defueling Safety Case | 2022-11-01 | 2023-02-24 | TASK F Review of the Discharge Limits (Permits) EAN ## (Cost Summary) (Claim 7) | 01-Nov-22 A | 12-May-23 A | 132 | 0 | 132 | 100% |  | Completed
ER6666LT | W209 | W209.A29570 | HYB Essential Defueling Safety Case | 2022-11-01 | 2022-11-01 | Pre Job Brief for TASK F Review of the Discharge Limits (Permits) EAN | 01-Nov-22 A | 01-Nov-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.8060 | HYB Essential Defueling Safety Case | 2022-11-09 | 2022-12-06 | Verify HF Assessment of HF Assessment of the Extant Fuel Movement in support of Defueling FFV Claim | 01-Nov-22 A | 03-Feb-23 A | 20 | 0 | 66 | 100% |  | Completed
ER6666LT | W209 | W209.8980 | HYB Essential Defueling Safety Case |  | 2023-01-23 | Discovery Milestone - FM Underload Protection Mods - Drafted | 01-Nov-22 A | 01-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A28680 | HYB Essential Defueling Safety Case |  |  | Verify CSP/Diagrid Structural Integrity Summary Report & Issue for Technical Review | 01-Nov-22 A | 21-Nov-22 A | 15 | 0 | 15 | 100% |  | Completed
ER6668LT | W213 | W213.A28970 | TOR Essential Defueling Safety Case | 2022-11-01 | 2023-02-24 | Summary of Compliance with RADWASTE Assessment Principles EAN ## (Cost Summary) (Claim 7) | 01-Nov-22 A | 14-Apr-23 A | 114 | 0 | 114 | 100% |  | Completed
ER6668LT | W213 | W213.A28980 | TOR Essential Defueling Safety Case | 2022-11-01 | 2022-11-01 | Pre Job Brief for Summary of Compliance with RADWASTE Assessment Principles EAN | 01-Nov-22 A | 01-Nov-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.6830 | TOR Essential Defueling Safety Case | 2022-11-08 | 2022-11-21 | Prepare Task Sheet for Defuelling Hazards Review EAN | 01-Nov-22 A | 23-Dec-22 A | 10 | 0 | 39 | 100% |  | Completed
ER6668LT | W213 | W213.A29560 | TOR Essential Defueling Safety Case | 2022-11-01 | 2023-02-24 | TASK F Review of the Discharge Limits (Permits) EAN ## (Cost Summary) (Claim 7) | 01-Nov-22 A | 12-May-23 A | 132 | 0 | 132 | 100% |  | Completed
ER6668LT | W213 | W213.A29570 | TOR Essential Defueling Safety Case | 2022-11-01 | 2022-11-01 | Pre Job Brief for TASK F Review of the Discharge Limits (Permits) EAN | 01-Nov-22 A | 01-Nov-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.8060 | TOR Essential Defueling Safety Case | 2022-11-09 | 2022-12-06 | Verify HF Assessment of HF Assessment of the Extant Fuel Movement in support of Defueling FFV Claim | 01-Nov-22 A | 03-Feb-23 A | 20 | 0 | 66 | 100% |  | Completed
ER6668LT | W213 | W213.8980 | TOR Essential Defueling Safety Case |  | 2023-01-23 | Discovery Milestone - FM Underload Protection Mods - Drafted | 01-Nov-22 A | 01-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A28680 | TOR Essential Defueling Safety Case |  |  | Verify CSP/Diagrid Structural Integrity Summary Report & Issue for Technical Review | 01-Nov-22 A | 21-Nov-22 A | 15 | 0 | 15 | 100% |  | Completed
ER6666LT | W209 | W209.A28990 | HYB Essential Defueling Safety Case | 2022-11-02 | 2023-01-27 | Draft Summary of Compliance with RADWASTE Assessment Principles EAN | 02-Nov-22 A | 28-Feb-23 A | 60 | 0 | 82 | 100% |  | Completed
ER6668LT | W213 | W213.A28990 | TOR Essential Defueling Safety Case | 2022-11-02 | 2023-01-27 | Draft Summary of Compliance with RADWASTE Assessment Principles EAN | 02-Nov-22 A | 28-Feb-23 A | 60 | 0 | 82 | 100% |  | Completed
ER6666LT | W209 | W209.A29580 | HYB Essential Defueling Safety Case | 2022-11-02 | 2023-01-27 | Draft TASK F Review of the Discharge Limits (Permits) EAN | 02-Nov-22 A | 09-Jan-23 A | 50 | 0 | 45 | 100% |  | Completed
ER6666LT | W209 | W209.A29970 | HYB Essential Defueling Safety Case | 2023-01-24 | 2023-03-06 | Detailed Design Spec for FM Underload Protection Mods Prelim Design (GLM) | 02-Nov-22 A | 14-Apr-23 A | 32 | 0 | 113 | 100% |  | Completed
ER6666LT | W209 | W209.A30700 | HYB Essential Defueling Safety Case | 2023-01-24 | 2023-03-06 | Detailed Design Spec for Channel 1 - HYB | 02-Nov-22 A | 15-Feb-23 A | 54 | 0 | 73 | 100% |  | Completed
ER6371LT | W202 | 2370 | HRA Reactors Shutdown Essential Safety Cases | 2022-11-02 | 2022-11-02 | Verification PJB | 02-Nov-22 A | 02-Nov-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | 1850 | HRA Reactors Shutdown Essential Safety Cases | 2022-09-21 | 2022-09-22 | Upload ALARP Review use of SA and SSP's to AMS | 02-Nov-22 A | 19-Oct-23 A | 3 | 0 | 242 | 100% |  | Completed
ER6661LT | W206 | 2370 | HYA Reactors Shutdown Essential Safety Cases | 2022-11-02 | 2022-11-02 | Verification PJB | 02-Nov-22 A | 02-Nov-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | 1850 | HYA Reactors Shutdown Essential Safety Cases | 2022-09-21 | 2022-09-22 | Upload ALARP Review use of SA and SSP's to AMS | 02-Nov-22 A | 19-Oct-23 A | 3 | 0 | 242 | 100% |  | Completed
ER6666LT | W209 | W209.A30960 | HYB Essential Defueling Safety Case |  |  | Detailed Design Spec for Channel X | 02-Nov-22 A | 21-Apr-23 A | 63 | 0 | 117 | 100% |  | Completed
ER6668LT | W213 | W213.A29580 | TOR Essential Defueling Safety Case | 2022-11-02 | 2023-01-27 | Draft TASK F Review of the Discharge Limits (Permits) EAN | 02-Nov-22 A | 09-Jan-23 A | 50 | 0 | 45 | 100% |  | Completed
ER6668LT | W213 | W213.A29970 | TOR Essential Defueling Safety Case | 2023-01-24 | 2023-03-06 | Detailed Design Spec for FM Underload Protection Mods Prelim Design (GLM) | 02-Nov-22 A | 14-Apr-23 A | 32 | 0 | 113 | 100% |  | Completed
ER6668LT | W213 | W213.A30700 | TOR Essential Defueling Safety Case | 2023-01-24 | 2023-03-06 | Detailed Design Spec for Channel 1 - TOR | 02-Nov-22 A | 15-Feb-23 A | 54 | 0 | 73 | 100% |  | Completed
ER6668LT | W213 | W213.A30960 | TOR Essential Defueling Safety Case |  |  | Detailed Design Spec for Channel X | 02-Nov-22 A | 21-Apr-23 A | 63 | 0 | 117 | 100% |  | Completed
W232LT | W232 | W232.A1440 | DNB Enhanced Safety Cases |  | 2022-11-02 | Issue to SRE for comments | 02-Nov-22 A | 02-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1450 | DNB Enhanced Safety Cases | 2022-11-03 | 2022-11-09 | Incorporate SRE comments | 03-Nov-22 A | 09-Nov-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.A26310 | HYB Essential Defueling Safety Case | 2022-08-19 | 2022-08-25 | Complete TR Form and Upload Reactor Internals & Structural Integrity During Defueling Report EAN to CDMS | 04-Nov-22 A | 04-Nov-22 A | 5 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A26320 | HYB Essential Defueling Safety Case |  | 2022-08-25 | Reactor Internals & Structural Integrity During Defueling Report EAN Available | 04-Nov-22 A | 04-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A26310 | TOR Essential Defueling Safety Case | 2022-08-19 | 2022-08-25 | Complete TR Form and Upload Reactor Internals & Structural Integrity During Defueling Report EAN to CDMS | 04-Nov-22 A | 04-Nov-22 A | 5 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A26320 | TOR Essential Defueling Safety Case |  | 2022-08-25 | Reactor Internals & Structural Integrity During Defueling Report EAN Available | 04-Nov-22 A | 04-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A28060 | HYB Essential Defueling Safety Case | 2022-09-06 | 2022-09-12 | Supplier Update and Issue Update Basis of Analysis document - (Issue 3) | 07-Nov-22 A | 21-Nov-22 A | 5 | 0 | 11 | 100% |  | Completed
ER6666LT | W209 | W209.A28760 | HYB Essential Defueling Safety Case | 2022-10-12 | 2022-11-01 | Verify Fuel Free Verification methods, an assessment against the ALARP principle EAN & Issue for Technical Review | 07-Nov-22 A | 18-Nov-22 A | 15 | 0 | 9 | 100% |  | Completed
ER6666LT | W209 | W209.6980 | HYB Essential Defueling Safety Case | 2022-08-31 | 2022-08-31 | PJB for Claim 2 Authoring | 07-Nov-22 A | 07-Nov-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.8360 | HYB Essential Defueling Safety Case | 2022-11-07 | 2023-09-28 | Claim 2 Production ## (Cost Summary) | 07-Nov-22 A | 21-Dec-23 A | 266 | 0 | 284 | 100% |  | Completed
ER6666LT | W209 | W209.A31210 | HYB Essential Defueling Safety Case |  |  | Draft Update Basis of Analysis document | 07-Nov-22 A | 01-Dec-22 A | 15 | 0 | 19 | 100% |  | Completed
ER6668LT | W213 | W213.A28060 | TOR Essential Defueling Safety Case | 2022-09-06 | 2022-09-12 | Supplier Update and Issue Update Basis of Analysis document - (Issue 3) | 07-Nov-22 A | 21-Nov-22 A | 5 | 0 | 11 | 100% |  | Completed
ER6668LT | W213 | W213.A28760 | TOR Essential Defueling Safety Case | 2022-10-12 | 2022-11-01 | Verify Fuel Free Verification methods, an assessment against the ALARP principle EAN & Issue for Technical Review | 07-Nov-22 A | 18-Nov-22 A | 15 | 0 | 9 | 100% |  | Completed
ER6668LT | W213 | W213.6980 | TOR Essential Defueling Safety Case | 2022-08-31 | 2022-08-31 | PJB for Claim 2 Authoring | 07-Nov-22 A | 07-Nov-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.8360 | TOR Essential Defueling Safety Case | 2022-11-07 | 2023-09-28 | Claim 2 Production ## (Cost Summary) | 07-Nov-22 A | 21-Dec-23 A | 251 | 0 | 284 | 100% |  | Completed
ER6668LT | W213 | W213.A31210 | TOR Essential Defueling Safety Case |  |  | Draft Update Basis of Analysis document | 07-Nov-22 A | 01-Dec-22 A | 15 | 0 | 19 | 100% |  | Completed
ER6666LT | W209 | W209.6990 | HYB Essential Defueling Safety Case | 2022-09-01 | 2022-12-28 | Author Claim 2 | 08-Nov-22 A | 24-Feb-23 A | 53 | 0 | 76 | 100% |  | Completed
ER6371LT | W202 | 2330 | HRA Reactors Shutdown Essential Safety Cases | 2022-10-26 | 2022-10-27 | CO Review | 08-Nov-22 A | 14-Nov-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | 2310 | HRA Reactors Shutdown Essential Safety Cases | 2022-10-12 | 2022-10-14 | Review with Station RE's | 08-Nov-22 A | 14-Nov-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | 2330 | HYA Reactors Shutdown Essential Safety Cases | 2022-10-26 | 2022-10-27 | CO Review | 08-Nov-22 A | 14-Nov-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | 2310 | HYA Reactors Shutdown Essential Safety Cases | 2022-10-12 | 2022-10-14 | Review with Station RE's | 08-Nov-22 A | 14-Nov-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.6990 | TOR Essential Defueling Safety Case | 2022-09-01 | 2022-12-28 | Author Claim 2 | 08-Nov-22 A | 24-Feb-23 A | 53 | 0 | 76 | 100% |  | Completed
W232LT | W232 | W232.A1830 | DNB Enhanced Safety Cases | 2022-11-09 | 2022-11-09 | Gate A PRC Paper Submission | 09-Nov-22 A | 09-Nov-22 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A1460 | DNB Enhanced Safety Cases |  | 2022-11-09 | Issue the case for review & verification | 09-Nov-22 A | 09-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A26920 | HYB Essential Defueling Safety Case | 2022-11-10 | 2022-12-14 | Verify Chemistry Monitoring Strategy EAN & Issue for Technical Review | 10-Nov-22 A | 30-Nov-22 A | 16 | 0 | 14 | 100% |  | Completed
ER6668LT | W213 | W213.A26920 | TOR Essential Defueling Safety Case | 2022-11-10 | 2022-12-14 | Verify Chemistry Monitoring Strategy EAN & Issue for Technical Review | 10-Nov-22 A | 30-Nov-22 A | 16 | 0 | 14 | 100% |  | Completed
W232LT | W232 | W232.A1020 | DNB Enhanced Safety Cases | 2022-11-10 | 2022-11-16 | Agree resource & timescales with suppliers for delivering key refs, incl contingency, risk & allowance for rework | 10-Nov-22 A | 16-Nov-22 A | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.A1010 | DNB Enhanced Safety Cases | 2022-11-10 |  | Mod requested, Initiate EC, identify RE, register EC & identify milestones in AMS | 10-Nov-22 A | 10-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1000 | DNB Enhanced Safety Cases | 2022-11-10 | 2022-11-10 | Raise Engineering Request (as required) | 10-Nov-22 A | 10-Nov-22 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A1470 | DNB Enhanced Safety Cases | 2022-11-10 | 2022-11-16 | Cat 3 EC - FPU Maintenance Reduction Verification of the case | 10-Nov-22 A | 16-Nov-22 A | 5 | 0 | 4 | 100% |  | Completed
W232LT | W232 | W232.A1950 | DNB Enhanced Safety Cases | 2022-11-10 | 2022-12-07 | Cat 2 EC Rate Increase Scoping Exercise | 10-Nov-22 A | 07-Dec-22 A | 20 | 0 | 20 | 100% |  | Completed
W232LT | W232 | W232.A1080 | DNB Enhanced Safety Cases |  | 2022-11-10 | CO & CA appointed | 10-Nov-22 A | 10-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1090 | DNB Enhanced Safety Cases |  | 2022-11-10 | Key Stakeholders Identified | 10-Nov-22 A | 10-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1100 | DNB Enhanced Safety Cases | 2022-11-11 | 2022-11-17 | Develop initial programme plan using mandatory template | 11-Nov-22 A | 17-Nov-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.A29520 | HYB Essential Defueling Safety Case |  | 2022-10-28 | Cooling Plant OPEX Study EAN Available | 11-Nov-22 A | 11-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A29520 | TOR Essential Defueling Safety Case |  | 2022-10-28 | Cooling Plant OPEX Study EAN Available | 11-Nov-22 A | 11-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A26700 | HYB Essential Defueling Safety Case | 2022-09-01 | 2022-09-07 | Supplier Update and Issue Review of flux detector suitability EAN | 14-Nov-22 A | 14-Nov-22 A | 5 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A26700 | TOR Essential Defueling Safety Case | 2022-09-01 | 2022-09-07 | Supplier Update and Issue Review of flux detector suitability EAN | 14-Nov-22 A | 14-Nov-22 A | 5 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | 2340 | HRA Reactors Shutdown Essential Safety Cases |  | 2022-10-27 | AMS Milestone - Ready for Review | 14-Nov-22 A | 14-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | 2340 | HYA Reactors Shutdown Essential Safety Cases |  | 2022-10-27 | AMS Milestone - Ready for Review | 14-Nov-22 A | 14-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A26770 | HYB Essential Defueling Safety Case | 2022-10-21 | 2022-12-15 | Technical Review of Boron Bead Injection Feasibility & Control Rod Isolation EAN | 15-Nov-22 A | 06-Jan-23 A | 40 | 0 | 36 | 100% |  | Completed
ER6668LT | W213 | W213.A26770 | TOR Essential Defueling Safety Case | 2022-10-21 | 2022-12-15 | Technical Review of Boron Bead Injection Feasibility & Control Rod Isolation EAN | 15-Nov-22 A | 06-Jan-23 A | 40 | 0 | 36 | 100% |  | Completed
ER6666LT | W209 | W209.A26710 | HYB Essential Defueling Safety Case | 2022-09-08 | 2022-09-14 | Complete TR Form and Upload Review of flux detector suitability EAN to CDMS | 15-Nov-22 A | 21-Nov-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | 2390 | HRA Reactors Shutdown Essential Safety Cases | 2022-11-03 | 2022-11-23 | Sub-verifier(s) including GAP review (HHB Opexs) | 15-Nov-22 A | 03-Jan-23 A | 7 | 0 | 33 | 100% |  | Completed
ER6371LT | W202 | 2380 | HRA Reactors Shutdown Essential Safety Cases | 2022-11-03 | 2022-11-23 | Verification including GAP review (Lead Verifier)( (HHB Opexs) | 15-Nov-22 A | 03-Jan-23 A | 7 | 0 | 33 | 100% |  | Completed
ER6371LT | W202 | 2320 | HRA Reactors Shutdown Essential Safety Cases | 2022-10-17 | 2022-10-25 | Review changes with INA | 15-Nov-22 A | 23-Nov-22 A | 7 | 0 | 7 | 100% |  | Completed
ER6661LT | W206 | 2390 | HYA Reactors Shutdown Essential Safety Cases | 2022-11-03 | 2022-11-23 | Sub-verifier(s) including GAP review (HHB Opexs) | 15-Nov-22 A | 03-Jan-23 A | 7 | 0 | 33 | 100% |  | Completed
ER6661LT | W206 | 2380 | HYA Reactors Shutdown Essential Safety Cases | 2022-11-03 | 2022-11-23 | Verification including GAP review (Lead Verifier)( (HHB Opexs) | 15-Nov-22 A | 03-Jan-23 A | 7 | 0 | 33 | 100% |  | Completed
ER6661LT | W206 | 2320 | HYA Reactors Shutdown Essential Safety Cases | 2022-10-17 | 2022-10-25 | Review changes with INA | 15-Nov-22 A | 23-Nov-22 A | 7 | 0 | 7 | 100% |  | Completed
ER6668LT | W213 | W213.A26710 | TOR Essential Defueling Safety Case | 2022-09-08 | 2022-09-14 | Complete TR Form and Upload Review of flux detector suitability EAN to CDMS | 15-Nov-22 A | 21-Nov-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.A28200 | HYB Essential Defueling Safety Case | 2022-12-16 | 2023-01-17 | Verify CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN & Issue for Technical Review | 16-Nov-22 A | 18-Nov-22 A | 10 | 0 | 2 | 100% |  | Completed
ER6668LT | W213 | W213.A28200 | TOR Essential Defueling Safety Case | 2022-12-16 | 2023-01-17 | Verify CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN & Issue for Technical Review | 16-Nov-22 A | 18-Nov-22 A | 10 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.A28250 | HYB Essential Defueling Safety Case | 2022-11-17 | 2023-07-28 | Fault Definition Document (FDD) EAN ## (Cost Summary) (Claim 4) | 17-Nov-22 A | 10-Oct-23 A | 219 | 0 | 224 | 100% |  | Completed
ER6666LT | W209 | W209.A28260 | HYB Essential Defueling Safety Case | 2022-08-31 | 2022-08-31 | Pre Job Brief for Fault Definition Document (FDD) EAN | 17-Nov-22 A | 17-Nov-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A28250 | TOR Essential Defueling Safety Case | 2022-11-17 | 2023-07-28 | Fault Definition Document (FDD) EAN ## (Cost Summary) (Claim 4) | 17-Nov-22 A | 12-Oct-23 A | 218 | 0 | 227 | 100% |  | Completed
ER6668LT | W213 | W213.A28260 | TOR Essential Defueling Safety Case | 2022-08-31 | 2022-08-31 | Pre Job Brief for Fault Definition Document (FDD) EAN | 17-Nov-22 A | 17-Nov-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | 2400 | HRA Reactors Shutdown Essential Safety Cases | 2022-11-03 | 2022-11-16 | Nuclear Safety Specialist Assessment(s) | 17-Nov-22 A | 25-Nov-22 A | 5 | 0 | 6 | 100% |  | Completed
ER6661LT | W206 | 2400 | HYA Reactors Shutdown Essential Safety Cases | 2022-11-03 | 2022-11-16 | Nuclear Safety Specialist Assessment(s) | 17-Nov-22 A | 25-Nov-22 A | 5 | 0 | 6 | 100% |  | Completed
W232LT | W232 | W232.A1110 | DNB Enhanced Safety Cases | 2022-11-17 | 2022-11-23 | Hold project kick start meeting with Station & key suppliers | 17-Nov-22 A | 23-Nov-22 A | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.A1500 | DNB Enhanced Safety Cases | 2022-11-17 | 2022-11-18 | Produce verification file | 17-Nov-22 A | 18-Nov-22 A | 2 | 0 | 2 | 100% |  | Completed
W232LT | W232 | W232.A1120 | DNB Enhanced Safety Cases |  | 2022-11-17 | CA PJB Held | 17-Nov-22 A | 17-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A28270 | HYB Essential Defueling Safety Case | 2022-09-01 | 2022-12-20 | Draft Fault Definition Document (FDD) EAN | 18-Nov-22 A | 22-Mar-23 A | 14 | 0 | 86 | 100% |  | Completed
ER6668LT | W213 | W213.A28270 | TOR Essential Defueling Safety Case | 2022-09-01 | 2022-12-20 | Draft Fault Definition Document (FDD) EAN | 18-Nov-22 A | 22-Mar-23 A | 14 | 0 | 86 | 100% |  | Completed
W232LT | W232 | W232.A1130 | DNB Enhanced Safety Cases | 2022-11-18 | 2022-11-18 | Produce MF (as required) | 18-Nov-22 A | 18-Nov-22 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2670 | DNB Enhanced Safety Cases | 2022-11-18 | 2022-11-30 | Prepare Decision Paper | 18-Nov-22 A | 05-Dec-22 A | 9 | 0 | 12 | 100% |  | Completed
W232LT | W232 | W232.A1160 | DNB Enhanced Safety Cases |  | 2022-11-18 | Issue MF (as required) | 18-Nov-22 A | 18-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1530 | DNB Enhanced Safety Cases |  | 2022-11-18 | Verification complete | 18-Nov-22 A | 18-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1540 | DNB Enhanced Safety Cases |  | 2022-11-18 | Submit to Station Approvers | 18-Nov-22 A | 18-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A28210 | HYB Essential Defueling Safety Case | 2023-01-18 | 2023-02-14 | Technical Review of CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN | 21-Nov-22 A | 13-Jan-23 A | 20 | 0 | 37 | 100% |  | Completed
ER6666LT | W209 | W209.A28780 | HYB Essential Defueling Safety Case | 2022-11-30 | 2022-12-06 | Supplier Update and Issue Fuel Free Verification methods, an assessment against the ALARP principle EAN | 21-Nov-22 A | 05-Jan-23 A | 5 | 0 | 31 | 100% |  | Completed
ER6666LT | W209 | W209.7160 | HYB Essential Defueling Safety Case | 2022-11-03 | 2022-11-03 | PJB for Claim 5 Authoring | 21-Nov-22 A | 21-Nov-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.8390 | HYB Essential Defueling Safety Case | 2022-11-03 | 2023-07-19 | Claim 5 Production ## (Cost Summary) | 21-Nov-22 A | 15-Dec-23 A | 267 | 0 | 270 | 100% |  | Completed
ER6668LT | W213 | W213.A28210 | TOR Essential Defueling Safety Case | 2023-01-18 | 2023-02-14 | Technical Review of CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN | 21-Nov-22 A | 13-Jan-23 A | 20 | 0 | 37 | 100% |  | Completed
ER6668LT | W213 | W213.A28780 | TOR Essential Defueling Safety Case | 2022-11-30 | 2022-12-06 | Supplier Update and Issue Fuel Free Verification methods, an assessment against the ALARP principle EAN | 21-Nov-22 A | 05-Jan-23 A | 5 | 0 | 31 | 100% |  | Completed
ER6668LT | W213 | W213.7160 | TOR Essential Defueling Safety Case | 2022-11-03 | 2022-11-03 | PJB for Claim 5 Authoring | 21-Nov-22 A | 21-Nov-22 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.8390 | TOR Essential Defueling Safety Case | 2022-11-03 | 2023-07-20 | Claim 5 Production ## (Cost Summary) | 21-Nov-22 A | 15-Dec-23 A | 257 | 0 | 270 | 100% |  | Completed
ER6666LT | W209 | W209.A29840 | HYB Essential Defueling Safety Case | 2022-11-01 | 2022-11-07 | Complete TR Form and Upload Feasibility of Draining PVCS (Report) to CDMS | 21-Nov-22 A | 23-Nov-22 A | 5 | 0 | 2 | 100% |  | Completed
W232LT | W232 | W232.A1180 | DNB Enhanced Safety Cases | 2022-11-21 | 2022-12-09 | Produce draft NSRS (using BARRIER MODEL) | 21-Nov-22 A | 09-Dec-22 A | 15 | 0 | 15 | 100% |  | Completed
W232LT | W232 | W232.A1170 | DNB Enhanced Safety Cases | 2022-11-21 | 2022-11-21 | Categorisation by RE / Station | 21-Nov-22 A | 21-Nov-22 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A1190 | DNB Enhanced Safety Cases | 2022-11-21 | 2022-11-25 | Identify verifier for the case & establish all other resources | 21-Nov-22 A | 05-Dec-22 A | 5 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.A29840 | TOR Essential Defueling Safety Case | 2022-11-01 | 2022-11-07 | Complete TR Form and Upload Feasibility of Draining PVCS (Report) to CDMS | 21-Nov-22 A | 23-Nov-22 A | 5 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.A26720 | HYB Essential Defueling Safety Case |  | 2022-09-14 | Review of flux detector suitability EAN Available - (CLAIM 1 - A - B De-risking) | 21-Nov-22 A | 21-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A26720 | TOR Essential Defueling Safety Case |  | 2022-09-14 | Review of flux detector suitability EAN Available - (CLAIM 1 - A - B De-risking) | 21-Nov-22 A | 21-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1940 | DNB Enhanced Safety Cases |  | 2022-12-30 | Gate A IAB Paper Approval (DNB) (Not Required 22.11.2022 DP) | 22-Nov-22 A | 22-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1920 | DNB Enhanced Safety Cases | 2022-12-14 | 2022-12-14 | Hold IAB Meeting (Not Required 22.11.2022 DP) | 22-Nov-22 A | 22-Nov-22 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1890 | DNB Enhanced Safety Cases | 2022-12-02 | 2022-12-02 | Gate A IAB Paper Submission (Not Required 22.11.2022 DP) | 22-Nov-22 A | 22-Nov-22 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1860 | DNB Enhanced Safety Cases |  | 2022-11-22 | Gate A PRC Paper Approval | 22-Nov-22 A | 22-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1850 | DNB Enhanced Safety Cases | 2022-11-22 | 2022-11-22 | Hold PRC | 22-Nov-22 A | 22-Nov-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A28070 | HYB Essential Defueling Safety Case | 2022-09-13 | 2022-09-19 | Complete TR Form and Upload Update Basis of Analysis document to CDMS - (Issue 3) | 22-Nov-22 A | 29-Nov-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.A28690 | HYB Essential Defueling Safety Case |  |  | Technical Review of CSP/Diagrid Structural Integrity Summary Report | 22-Nov-22 A | 13-Jan-23 A | 15 | 0 | 36 | 100% |  | Completed
W232LT | W232 | W232.A1210 | DNB Enhanced Safety Cases | 2022-11-22 | 2022-11-23 | INSA agree MF (as required) *(KDM)* | 22-Nov-22 A | 23-Nov-22 A | 2 | 0 | 2 | 100% |  | Completed
ER6668LT | W213 | W213.A28070 | TOR Essential Defueling Safety Case | 2022-09-13 | 2022-09-19 | Complete TR Form and Upload Update Basis of Analysis document to CDMS - (Issue 3) | 22-Nov-22 A | 29-Nov-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A28690 | TOR Essential Defueling Safety Case |  |  | Technical Review of CSP/Diagrid Structural Integrity Summary Report | 22-Nov-22 A | 13-Jan-23 A | 15 | 0 | 36 | 100% |  | Completed
ER6666LT | W209 | W209.A29850 | HYB Essential Defueling Safety Case |  | 2022-11-07 | Feasibility of Draining PVCS (Report) Available | 23-Nov-22 A | 23-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A29850 | TOR Essential Defueling Safety Case |  | 2022-11-07 | Feasibility of Draining PVCS (Report) Available | 23-Nov-22 A | 23-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A30560 | HYB Essential Defueling Safety Case | 2022-07-25 | 2022-08-12 | Verify Summary of Credible Start of Life Defects EAN & Issue for Technical Review (A - B De-Risking) | 23-Nov-22 A | 01-Dec-22 A | 7 | 0 | 6 | 100% |  | Completed
ER6668LT | W213 | W213.A30560 | TOR Essential Defueling Safety Case | 2022-07-25 | 2022-08-12 | Verify Summary of Credible Start of Life Defects EAN & Issue for Technical Review (A - B De-Risking) | 23-Nov-22 A | 01-Dec-22 A | 7 | 0 | 6 | 100% |  | Completed
W232LT | W232 | W232.A1240 | DNB Enhanced Safety Cases |  | 2022-11-23 | INSA Approval Date Identified | 23-Nov-22 A | 23-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1250 | DNB Enhanced Safety Cases |  | 2022-11-23 | Provide Provisional NSC Date (Not required DP 23.11.2022) | 23-Nov-22 A | 23-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A26950 | HYB Essential Defueling Safety Case | 2022-12-15 | 2022-12-21 | Upload Chemistry Monitoring Strategy EAN to CDMS | 24-Nov-22 A | 03-Mar-23 A | 12 | 0 | 69 | 100% |  | Completed
ER6668LT | W213 | W213.A26950 | TOR Essential Defueling Safety Case | 2022-12-15 | 2022-12-21 | Upload Chemistry Monitoring Strategy EAN to CDMS | 24-Nov-22 A | 03-Mar-23 A | 12 | 0 | 69 | 100% |  | Completed
ER6666LT | W209 | W209.A29400 | HYB Essential Defueling Safety Case | 2022-10-18 | 2022-11-21 | Verify Cooling Plant Availability Review EAN & Issue for Technical Review | 25-Nov-22 A | 16-Dec-22 A | 6 | 0 | 16 | 100% |  | Completed
ER6668LT | W213 | W213.A29400 | TOR Essential Defueling Safety Case | 2022-10-18 | 2022-11-21 | Verify Cooling Plant Availability Review EAN & Issue for Technical Review | 25-Nov-22 A | 16-Dec-22 A | 6 | 0 | 16 | 100% |  | Completed
W232LT | W232 | W232.A1960 | DNB Enhanced Safety Cases | 2022-11-25 | 2022-11-28 | Cat 2 EC Scoping Workshop | 25-Nov-22 A | 28-Nov-22 A | 2 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.A26460 | HYB Essential Defueling Safety Case | 2022-08-01 | 2022-08-04 | Supplier Update and Issue Define Nuclear Data (PANTHER Validation Calcs) EAN | 28-Nov-22 A | 20-Dec-22 A | 5 | 0 | 17 | 100% |  | Completed
ER6666LT | W209 | W209.A26540 | HYB Essential Defueling Safety Case | 2022-08-24 | 2022-08-31 | Supplier Update and Issue PANTHER SCM Assessments - Agree Defuelling Order EAN | 28-Nov-22 A | 04-Jan-23 A | 5 | 0 | 25 | 100% |  | Completed
ER6668LT | W213 | W213.A26460 | TOR Essential Defueling Safety Case | 2022-08-01 | 2022-08-04 | Supplier Update and Issue Define Nuclear Data (PANTHER Validation Calcs) EAN | 28-Nov-22 A | 20-Dec-22 A | 5 | 0 | 17 | 100% |  | Completed
ER6668LT | W213 | W213.A26540 | TOR Essential Defueling Safety Case | 2022-08-24 | 2022-08-31 | Supplier Update and Issue PANTHER SCM Assessments - Agree Defuelling Order EAN | 28-Nov-22 A | 04-Jan-23 A | 5 | 0 | 25 | 100% |  | Completed
ER6666LT | W209 | W209.A28080 | HYB Essential Defueling Safety Case |  | 2022-09-19 | Update Basis of Analysis document Available - (Issue 3) | 29-Nov-22 A | 29-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | 3000 | HRA Reactors Shutdown Essential Safety Cases |  |  | Address Recommendations and Observations | 29-Nov-22 A | 24-Feb-23 A | 51 | 0 | 60 | 100% |  | Completed
ER6661LT | W206 | 3000 | HYA Reactors Shutdown Essential Safety Cases |  |  | Address Recommendations and Observations | 29-Nov-22 A | 24-Feb-23 A | 51 | 0 | 60 | 100% |  | Completed
ER6668LT | W213 | W213.A28080 | TOR Essential Defueling Safety Case |  | 2022-09-19 | Update Basis of Analysis document Available - (Issue 3) | 29-Nov-22 A | 29-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.28760 | HYB Essential Defueling Safety Case |  |  | Discovery Milestone - Confirm Additional Protections Needed for Preventing ML/MD Faults | 30-Nov-22 A | 30-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.28760 | TOR Essential Defueling Safety Case |  |  | Discovery Milestone - Confirm Additional Protections Needed for Preventing ML/MD Faults | 30-Nov-22 A | 30-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A26240 | HYB Essential Defueling Safety Case |  | 2022-09-19 | Pressure Boundary Integrity of Seals Report EAN Available | 30-Nov-22 A | 30-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A26240 | TOR Essential Defueling Safety Case |  | 2022-09-19 | Pressure Boundary Integrity of Seals Report EAN Available | 30-Nov-22 A | 30-Nov-22 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1930 | DNB Enhanced Safety Cases | 2022-12-15 | 2022-12-30 | Release of Funds | 01-Dec-22 A | 14-Dec-22 A | 10 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.A25990 | HYB Essential Defueling Safety Case | 2022-10-11 | 2022-10-24 | Upload Civil Assesment of the Ponds at Low Temperature EAN to CDMS | 01-Dec-22 A | 07-Dec-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.A26070 | HYB Essential Defueling Safety Case | 2022-10-21 | 2022-11-03 | Upload Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN to CDMS | 01-Dec-22 A | 07-Dec-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.A31110 | HYB Essential Defueling Safety Case |  |  | Verify Defueling Process Flow & Issue | 01-Dec-22 A | 17-Jul-23 A | 10 | 0 | 155 | 100% |  | Completed
ER6668LT | W213 | W213.A25990 | TOR Essential Defueling Safety Case | 2022-10-11 | 2022-10-24 | Upload Civil Assesment of the Ponds at Low Temperature EAN to CDMS | 01-Dec-22 A | 07-Dec-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A26070 | TOR Essential Defueling Safety Case | 2022-10-21 | 2022-11-03 | Upload Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN to CDMS | 01-Dec-22 A | 07-Dec-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A31110 | TOR Essential Defueling Safety Case |  |  | Verify Defueling Process Flow & Issue | 01-Dec-22 A | 17-Jul-23 A | 10 | 0 | 155 | 100% |  | Completed
ER6666LT | W209 | W209.A28460 | HYB Essential Defueling Safety Case | 2022-08-30 | 2022-09-05 | Supplier Update and Issue Summary of Credible Start of Life Defects EAN | 02-Dec-22 A | 05-Dec-22 A | 5 | 0 | 2 | 100% |  | Completed
ER6668LT | W213 | W213.A28460 | TOR Essential Defueling Safety Case | 2022-08-30 | 2022-09-05 | Supplier Update and Issue Summary of Credible Start of Life Defects EAN | 02-Dec-22 A | 05-Dec-22 A | 5 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.A31220 | HYB Essential Defueling Safety Case |  |  | Verify Update Basis of Analysis document & Issue for Technical Review | 02-Dec-22 A | 20-Jan-23 A | 2 | 0 | 33 | 100% |  | Completed
ER6668LT | W213 | W213.A31220 | TOR Essential Defueling Safety Case |  |  | Verify Update Basis of Analysis document & Issue for Technical Review | 02-Dec-22 A | 20-Jan-23 A | 2 | 0 | 33 | 100% |  | Completed
ER6666LT | W209 | W209.28990 | HYB Essential Defueling Safety Case |  |  | OPEX Review (Stations) against existing Misloading / Mis-Defueling Faults | 05-Dec-22 A | 06-Jan-23 A | 1 | 0 | 22 | 100% |  | Completed
ER6666LT | W209 | W209.29000 | HYB Essential Defueling Safety Case |  |  | OPEX Review Internal Review and Gap analysis against existing Misloading / Mis-Defueling Faults | 05-Dec-22 A | 06-Jan-23 A | 1 | 0 | 22 | 100% |  | Completed
ER6668LT | W213 | W213.28990 | TOR Essential Defueling Safety Case |  |  | OPEX Review (Stations) against existing Misloading / Mis-Defueling Faults | 05-Dec-22 A | 06-Jan-23 A | 1 | 0 | 22 | 100% |  | Completed
ER6668LT | W213 | W213.29000 | TOR Essential Defueling Safety Case |  |  | OPEX Review Internal Review and Gap analysis against existing Misloading / Mis-Defueling Faults | 05-Dec-22 A | 06-Jan-23 A | 1 | 0 | 22 | 100% |  | Completed
ER6666LT | W209 | W209.28920 | HYB Essential Defueling Safety Case |  |  | Mid Job Brief for WP5 | 05-Dec-22 A | 05-Dec-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.28920 | TOR Essential Defueling Safety Case |  |  | Mid Job Brief for WP5 | 05-Dec-22 A | 05-Dec-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A28470 | HYB Essential Defueling Safety Case | 2022-09-06 | 2022-09-12 | Complete TR Form and Upload Summary of Credible Start of Life Defects EAN to CDMS | 06-Dec-22 A | 22-Dec-22 A | 5 | 0 | 12 | 100% |  | Completed
ER6668LT | W213 | W213.A28470 | TOR Essential Defueling Safety Case | 2022-09-06 | 2022-09-12 | Complete TR Form and Upload Summary of Credible Start of Life Defects EAN to CDMS | 06-Dec-22 A | 22-Dec-22 A | 5 | 0 | 12 | 100% |  | Completed
ER6666LT | W209 | W209.3820 | HYB Essential Defueling Safety Case |  | 2022-06-30 | Civils Assessment Report Received for PCPV Integrity Justification - Report Available | 07-Dec-22 A | 07-Dec-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.3880 | HYB Essential Defueling Safety Case |  | 2022-06-30 | Civils Assessment Report Received for Seismic Assessment - Report Available | 07-Dec-22 A | 07-Dec-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A26000 | HYB Essential Defueling Safety Case |  | 2022-10-24 | Civil Assesment of the Ponds at Low Temperature EAN Available | 07-Dec-22 A | 07-Dec-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A26080 | HYB Essential Defueling Safety Case |  | 2022-11-03 | Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN Available | 07-Dec-22 A | 07-Dec-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.3820 | TOR Essential Defueling Safety Case |  | 2022-06-30 | Civils Assessment Report Received for PCPV Integrity Justification - Report Available | 07-Dec-22 A | 07-Dec-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.3880 | TOR Essential Defueling Safety Case |  | 2022-06-30 | Civils Assessment Report Received for Seismic Assessment - Report Available | 07-Dec-22 A | 07-Dec-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A26000 | TOR Essential Defueling Safety Case |  | 2022-10-24 | Civil Assesment of the Ponds at Low Temperature EAN Available | 07-Dec-22 A | 07-Dec-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A26080 | TOR Essential Defueling Safety Case |  | 2022-11-03 | Civil Integrity of Reactor - Plug Units Hanging from Top of Reactor EAN Available | 07-Dec-22 A | 07-Dec-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A27300 | HYB Essential Defueling Safety Case | 2022-11-02 | 2022-11-02 | Pre Job Brief for Reactor Fault Schedule Amendments EAN | 08-Dec-22 A | 08-Dec-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A27290 | HYB Essential Defueling Safety Case | 2022-12-08 | 2024-01-10 | Costs Reactor Fault Schedule Amendments EAN ## (Cost Summary) (Claim 5) | 08-Dec-22 A | 31-Jan-24 A | 314 | 0 | 287 | 100% |  | Completed
ER6668LT | W213 | W213.A27300 | TOR Essential Defueling Safety Case | 2022-11-02 | 2022-11-02 | Pre Job Brief for Reactor Fault Schedule Amendments EAN | 08-Dec-22 A | 08-Dec-22 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A27290 | TOR Essential Defueling Safety Case | 2022-12-08 | 2024-01-10 | Costs Reactor Fault Schedule Amendments EAN ## (Cost Summary) (Claim 5) | 08-Dec-22 A | 31-Jan-24 A | 314 | 0 | 287 | 100% |  | Completed
W232LT | W232 | W232.A2680 | DNB Enhanced Safety Cases | 2022-12-01 | 2022-12-15 | Obtain Agreement from Programme Board | 12-Dec-22 A | 17-Feb-23 A | 11 | 0 | 47 | 100% |  | Completed
ER6666LT | W209 | W209.A28850 | HYB Essential Defueling Safety Case | 2022-10-19 | 2022-11-15 | Technical Review by Case Officer for Define Failed Fuel Free Controls File Note | 12-Dec-22 A | 16-Dec-22 A | 10 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.A1510 | DNB Enhanced Safety Cases | 2022-12-12 | 2022-12-21 | Station comments on NSRS | 12-Dec-22 A | 21-Dec-22 A | 8 | 0 | 8 | 100% |  | Completed
W232LT | W232 | W232.A1520 | DNB Enhanced Safety Cases | 2022-12-12 | 2022-12-21 | Key Stakeholders (Peer) comments on NSRS (as required) | 12-Dec-22 A | 21-Dec-22 A | 8 | 0 | 8 | 100% |  | Completed
ER6668LT | W213 | W213.A28850 | TOR Essential Defueling Safety Case | 2022-10-19 | 2022-11-15 | Technical Review by Case Officer for Define Failed Fuel Free Controls File Note | 12-Dec-22 A | 16-Dec-22 A | 10 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.A26610 | HYB Essential Defueling Safety Case | 2022-09-05 | 2022-09-30 | Technical Review of Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 14-Dec-22 A | 06-Jan-23 A | 8 | 0 | 15 | 100% |  | Completed
ER6668LT | W213 | W213.A26610 | TOR Essential Defueling Safety Case | 2022-09-05 | 2022-09-30 | Technical Review of Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 14-Dec-22 A | 06-Jan-23 A | 8 | 0 | 15 | 100% |  | Completed
ER6666LT | W209 | W209.A27400 | HYB Essential Defueling Safety Case | 2023-01-26 | 2023-02-22 | Verify Fuel Route PSA Update EAN & Issue for Technical Review | 15-Dec-22 A | 20-Mar-23 A | 20 | 0 | 65 | 100% |  | Completed
ER6668LT | W213 | W213.A27400 | TOR Essential Defueling Safety Case | 2023-01-26 | 2023-02-22 | Verify Fuel Route PSA Update EAN & Issue for Technical Review | 15-Dec-22 A | 20-Mar-23 A | 20 | 0 | 65 | 100% |  | Completed
ER6666LT | W209 | W209.29070 | HYB Essential Defueling Safety Case |  |  | Review EAT and Phase Imbalance cases and understand defuelling impact | 19-Dec-22 A | 03-Feb-23 A | 1 | 0 | 32 | 100% |  | Completed
ER6666LT | W209 | W209.29080 | HYB Essential Defueling Safety Case |  |  | Identify shortfalls against the SCC | 19-Dec-22 A | 28-Feb-23 A | 1 | 0 | 49 | 100% |  | Completed
ER6666LT | W209 | W209.29130 | HYB Essential Defueling Safety Case |  |  | Ongoing update of Fault schedule as safety case references and claim text becomes available | 19-Dec-22 A | 03-Feb-23 A | 1 | 0 | 32 | 100% |  | Completed
ER6668LT | W213 | W213.29070 | TOR Essential Defueling Safety Case |  |  | Review EAT and Phase Imbalance cases and understand defuelling impact | 19-Dec-22 A | 03-Feb-23 A | 1 | 0 | 32 | 100% |  | Completed
ER6668LT | W213 | W213.29080 | TOR Essential Defueling Safety Case |  |  | Identify shortfalls against the SCC | 19-Dec-22 A | 28-Feb-23 A | 1 | 0 | 49 | 100% |  | Completed
ER6668LT | W213 | W213.29130 | TOR Essential Defueling Safety Case |  |  | Ongoing update of Fault schedule as safety case references and claim text becomes available | 19-Dec-22 A | 03-Feb-23 A | 1 | 0 | 32 | 100% |  | Completed
ER6666LT | W209 | W209.A28870 | HYB Essential Defueling Safety Case | 2022-11-23 | 2022-11-29 | Complete TR Form and Approve Define Failed Fuel Free Controls File Note | 19-Dec-22 A | 23-Dec-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.6910 | HYB Essential Defueling Safety Case | 2022-12-16 | 2023-01-17 | Case Officer Tech Lead Review Claim 1 | 19-Dec-22 A | 27-Jan-23 A | 30 | 0 | 26 | 100% |  | Completed
ER6666LT | W209 | W209.A29410 | HYB Essential Defueling Safety Case | 2022-11-22 | 2022-12-28 | Technical Review of Cooling Plant Availability Review EAN | 19-Dec-22 A | 02-Feb-23 A | 17 | 0 | 31 | 100% |  | Completed
ER6668LT | W213 | W213.A28870 | TOR Essential Defueling Safety Case | 2022-11-23 | 2022-11-29 | Complete TR Form and Approve Define Failed Fuel Free Controls File Note | 19-Dec-22 A | 23-Dec-22 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.6910 | TOR Essential Defueling Safety Case | 2022-12-16 | 2023-01-17 | Case Officer Tech Lead Review Claim 1 | 19-Dec-22 A | 27-Jan-23 A | 30 | 0 | 26 | 100% |  | Completed
ER6668LT | W213 | W213.A29410 | TOR Essential Defueling Safety Case | 2022-11-22 | 2022-12-28 | Technical Review of Cooling Plant Availability Review EAN | 19-Dec-22 A | 02-Feb-23 A | 17 | 0 | 31 | 100% |  | Completed
ER6666LT | W209 | W209.A26470 | HYB Essential Defueling Safety Case | 2022-08-05 | 2022-08-11 | Complete TR Form and Upload Define Nuclear Data (PANTHER Validation Calcs) EAN to CDMS | 21-Dec-22 A | 13-Jan-23 A | 5 | 0 | 14 | 100% |  | Completed
ER6668LT | W213 | W213.A26470 | TOR Essential Defueling Safety Case | 2022-08-05 | 2022-08-11 | Complete TR Form and Upload Define Nuclear Data (PANTHER Validation Calcs) EAN to CDMS | 21-Dec-22 A | 13-Jan-23 A | 5 | 0 | 14 | 100% |  | Completed
W232LT | W232 | W232.A1560 | DNB Enhanced Safety Cases |  | 2022-12-21 | INSA Resource Identified | 21-Dec-22 A | 21-Dec-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A28480 | HYB Essential Defueling Safety Case |  | 2022-09-12 | Summary of Credible Start of Life Defects EAN Available | 22-Dec-22 A | 22-Dec-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A28480 | TOR Essential Defueling Safety Case |  | 2022-09-12 | Summary of Credible Start of Life Defects EAN Available | 22-Dec-22 A | 22-Dec-22 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1570 | DNB Enhanced Safety Cases | 2022-12-22 | 2023-01-09 | INA comments on NSRS | 22-Dec-22 A | 27-Jan-23 A | 10 | 0 | 23 | 100% |  | Completed
ER6666LT | W209 | W209.A28880 | HYB Essential Defueling Safety Case |  | 2022-11-29 | Define Failed Fuel Free Controls File Note Available | 23-Dec-22 A | 23-Dec-22 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A28880 | TOR Essential Defueling Safety Case |  | 2022-11-29 | Define Failed Fuel Free Controls File Note Available | 23-Dec-22 A | 23-Dec-22 A | 0 | 0 | 0 | 100% |  | Completed
W520LT | W520 | W520.A1020 | FLEETWIDE CTO Defueling Safety Case Delivery | 2023-01-03 | 2023-12-29 | 2023 Costs | 03-Jan-23 A | 29-Dec-23 A | 252 | 0 | 251 | 100% |  | Completed
ER6666LT | W209 | W209.28870 | HYB Essential Defueling Safety Case |  |  | Update PSA to REV 001 Following all Works | 03-Jan-23 A | 17-Nov-23 A | 10 | 0 | 223 | 100% |  | Completed
ER6668LT | W213 | W213.28870 | TOR Essential Defueling Safety Case |  |  | Update PSA to REV 001 Following all Works | 03-Jan-23 A | 17-Nov-23 A | 10 | 0 | 222 | 100% |  | Completed
ER6666LT | W209 | W209.A29050 | HYB Essential Defueling Safety Case | 2023-01-03 | 2023-10-11 | Defuelling Handling Deterministic Assessment EAN ## (Cost Summary) (Claim 7) | 03-Jan-23 A | 31-Jan-24 A | 276 | 0 | 272 | 100% |  | Completed
ER6666LT | W209 | W209.A29130 | HYB Essential Defueling Safety Case | 2023-01-03 | 2023-09-27 | Defuelling Worker Risk Assessment EAN ## (Cost Summary) (Claim 7) | 03-Jan-23 A | 09-Aug-24 A | 406 | 0 | 406 | 100% |  | Completed
ER6666LT | W209 | W209.6760 | HYB Essential Defueling Safety Case | 2022-10-03 | 2022-10-07 | Prepare Spec for Defuelling Handling Deterministic Assessment EAN | 03-Jan-23 A | 09-Jan-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.6790 | HYB Essential Defueling Safety Case | 2022-10-03 | 2022-10-07 | Prepare Spec for Defuelling Worker Risk Assessment EAN | 03-Jan-23 A | 09-Jan-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.6840 | HYB Essential Defueling Safety Case | 2022-11-22 | 2022-11-30 | Approve Task Sheet for Defuelling Hazards Review EAN | 03-Jan-23 A | 27-Jan-23 A | 5 | 0 | 19 | 100% |  | Completed
ER6666LT | W209 | W209.28800 | HYB Essential Defueling Safety Case |  |  | Step 2 - Create Draft Operator Claims Matrix | 03-Jan-23 A | 24-Mar-23 A | 19 | 0 | 59 | 100% |  | Completed
ER6371LT | W202 | 2325 | HRA Reactors Shutdown Essential Safety Cases |  |  | Update EC (Version 5) | 03-Jan-23 A | 10-Feb-23 A | 29 | 0 | 29 | 100% |  | Completed
ER6661LT | W206 | 2325 | HYA Reactors Shutdown Essential Safety Cases |  |  | Update EC (Version 5) | 03-Jan-23 A | 10-Feb-23 A | 29 | 0 | 29 | 100% |  | Completed
ER6668LT | W213 | W213.A29050 | TOR Essential Defueling Safety Case | 2023-01-03 | 2023-10-11 | Defuelling Handling Deterministic Assessment EAN ## (Cost Summary) (Claim 7) | 03-Jan-23 A | 31-Jan-24 A | 278 | 0 | 272 | 100% |  | Completed
ER6668LT | W213 | W213.A29130 | TOR Essential Defueling Safety Case | 2023-01-03 | 2023-09-27 | Defuelling Worker Risk Assessment EAN ## (Cost Summary) (Claim 7) | 03-Jan-23 A | 09-Aug-24 A | 406 | 0 | 406 | 100% |  | Completed
ER6668LT | W213 | W213.6760 | TOR Essential Defueling Safety Case | 2022-10-03 | 2022-10-07 | Prepare Spec for Defuelling Handling Deterministic Assessment EAN | 03-Jan-23 A | 09-Jan-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.6790 | TOR Essential Defueling Safety Case | 2022-10-03 | 2022-10-07 | Prepare Spec for Defuelling Worker Risk Assessment EAN | 03-Jan-23 A | 09-Jan-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.6840 | TOR Essential Defueling Safety Case | 2022-11-22 | 2022-11-30 | Approve Task Sheet for Defuelling Hazards Review EAN | 03-Jan-23 A | 27-Jan-23 A | 5 | 0 | 19 | 100% |  | Completed
ER6668LT | W213 | W213.28800 | TOR Essential Defueling Safety Case |  |  | Step 2 - Create Draft Operator Claims Matrix | 03-Jan-23 A | 24-Mar-23 A | 19 | 0 | 59 | 100% |  | Completed
ER6666LT | W209 | W209.A26550 | HYB Essential Defueling Safety Case | 2022-09-01 | 2022-09-07 | Complete TR Form and Upload PANTHER SCM Assessments - Agree Defuelling Order EAN to CDMS | 05-Jan-23 A | 17-Jan-23 A | 5 | 0 | 8 | 100% |  | Completed
ER6668LT | W213 | W213.A26550 | TOR Essential Defueling Safety Case | 2022-09-01 | 2022-09-07 | Complete TR Form and Upload PANTHER SCM Assessments - Agree Defuelling Order EAN to CDMS | 05-Jan-23 A | 17-Jan-23 A | 5 | 0 | 8 | 100% |  | Completed
ER6666LT | W209 | W209.A28790 | HYB Essential Defueling Safety Case | 2022-12-07 | 2022-12-13 | Complete TR Form and Upload Fuel Free Verification methods, an assessment against the ALARP principle EAN | 06-Jan-23 A | 31-Mar-23 A | 5 | 0 | 60 | 100% |  | Completed
ER6668LT | W213 | W213.A28790 | TOR Essential Defueling Safety Case | 2022-12-07 | 2022-12-13 | Complete TR Form and Upload Fuel Free Verification methods, an assessment against the ALARP principle EAN | 06-Jan-23 A | 31-Mar-23 A | 5 | 0 | 60 | 100% |  | Completed
ER6666LT | W209 | W209.A26620 | HYB Essential Defueling Safety Case | 2022-10-03 | 2022-10-07 | Supplier Update and Issue Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 09-Jan-23 A | 13-Jan-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.A26780 | HYB Essential Defueling Safety Case | 2022-12-16 | 2022-12-22 | Supplier Update and Issue Boron Bead Injection Feasibility & Control Rod Isolation EAN | 09-Jan-23 A | 28-Feb-23 A | 5 | 0 | 37 | 100% |  | Completed
ER6666LT | W209 | W209.A29590 | HYB Essential Defueling Safety Case | 2023-01-30 | 2023-02-17 | Verify TASK F Review of the Discharge Limits (Permits) EAN & Issue for Technical Review | 09-Jan-23 A | 28-Feb-23 A | 5 | 0 | 37 | 100% |  | Completed
ER6668LT | W213 | W213.A26620 | TOR Essential Defueling Safety Case | 2022-10-03 | 2022-10-07 | Supplier Update and Issue Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN | 09-Jan-23 A | 13-Jan-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A26780 | TOR Essential Defueling Safety Case | 2022-12-16 | 2022-12-22 | Supplier Update and Issue Boron Bead Injection Feasibility & Control Rod Isolation EAN | 09-Jan-23 A | 28-Feb-23 A | 5 | 0 | 37 | 100% |  | Completed
ER6668LT | W213 | W213.A29590 | TOR Essential Defueling Safety Case | 2023-01-30 | 2023-02-17 | Verify TASK F Review of the Discharge Limits (Permits) EAN & Issue for Technical Review | 09-Jan-23 A | 28-Feb-23 A | 5 | 0 | 37 | 100% |  | Completed
W232LT | W232 | W232.A1580 | DNB Enhanced Safety Cases | 2023-01-11 | 2023-01-24 | Develop plan with further iterations | 11-Jan-23 A | 24-Jan-23 A | 10 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.A26480 | HYB Essential Defueling Safety Case |  | 2022-08-11 | Define Nuclear Data (PANTHER Validation Calcs) EAN Available | 13-Jan-23 A | 13-Jan-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A26480 | TOR Essential Defueling Safety Case |  | 2022-08-11 | Define Nuclear Data (PANTHER Validation Calcs) EAN Available | 13-Jan-23 A | 13-Jan-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A25890 | HYB Essential Defueling Safety Case | 2022-09-29 | 2022-11-02 | Technical Review of Safety Case Requirements EAN - TASK E EAN | 16-Jan-23 A | 17-Feb-23 A | 5 | 0 | 24 | 100% |  | Completed
ER6666LT | W209 | W209.A26630 | HYB Essential Defueling Safety Case | 2022-10-10 | 2022-10-14 | Complete TR Form and Upload Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN to CDMS | 16-Jan-23 A | 24-Jan-23 A | 5 | 0 | 6 | 100% |  | Completed
ER6666LT | W209 | W209.A28220 | HYB Essential Defueling Safety Case | 2023-02-15 | 2023-02-21 | Supplier Update and Issue CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN | 16-Jan-23 A | 17-Mar-23 A | 5 | 0 | 45 | 100% |  | Completed
ER6666LT | W209 | W209.A28700 | HYB Essential Defueling Safety Case |  |  | Supplier Update and Issue CSP/Diagrid Structural Integrity Summary Report | 16-Jan-23 A | 17-Mar-23 A | 5 | 0 | 45 | 100% |  | Completed
ER6668LT | W213 | W213.A25890 | TOR Essential Defueling Safety Case | 2022-09-29 | 2022-11-02 | Technical Review of Safety Case Requirements EAN - TASK E EAN | 16-Jan-23 A | 17-Feb-23 A | 5 | 0 | 24 | 100% |  | Completed
ER6668LT | W213 | W213.A26630 | TOR Essential Defueling Safety Case | 2022-10-10 | 2022-10-14 | Complete TR Form and Upload Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN to CDMS | 16-Jan-23 A | 24-Jan-23 A | 5 | 0 | 6 | 100% |  | Completed
ER6668LT | W213 | W213.A28220 | TOR Essential Defueling Safety Case | 2023-02-15 | 2023-02-21 | Supplier Update and Issue CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN | 16-Jan-23 A | 17-Mar-23 A | 5 | 0 | 45 | 100% |  | Completed
ER6668LT | W213 | W213.A28700 | TOR Essential Defueling Safety Case |  |  | Supplier Update and Issue CSP/Diagrid Structural Integrity Summary Report | 16-Jan-23 A | 17-Mar-23 A | 5 | 0 | 45 | 100% |  | Completed
ER6666LT | W209 | W209.A26560 | HYB Essential Defueling Safety Case |  | 2022-09-07 | PANTHER SCM Assessments - Agree Defuelling Order EAN Available | 17-Jan-23 A | 17-Jan-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A26560 | TOR Essential Defueling Safety Case |  | 2022-09-07 | PANTHER SCM Assessments - Agree Defuelling Order EAN Available | 17-Jan-23 A | 17-Jan-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1550 | DNB Enhanced Safety Cases | 2022-11-21 | 2022-11-21 | Station approval for mod implementation (inlcuding station review meeting) | 20-Jan-23 A | 20-Jan-23 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A31230 | HYB Essential Defueling Safety Case |  |  | Technical Review of Update Basis if Analysis document - (Issue 5) | 23-Jan-23 A | 21-Feb-23 A | 10 | 0 | 21 | 100% |  | Completed
ER6371LT | W202 | 3010 | HRA Reactors Shutdown Essential Safety Cases |  |  | Update Summary Report | 23-Jan-23 A | 24-Feb-23 A | 20 | 0 | 24 | 100% |  | Completed
ER6661LT | W206 | 3010 | HYA Reactors Shutdown Essential Safety Cases |  |  | Update Summary Report | 23-Jan-23 A | 24-Feb-23 A | 20 | 0 | 24 | 100% |  | Completed
ER6668LT | W213 | W213.A31230 | TOR Essential Defueling Safety Case |  |  | Technical Review of Update Basis if Analysis document - (Issue 5) | 23-Jan-23 A | 21-Feb-23 A | 10 | 0 | 21 | 100% |  | Completed
ER6666LT | W209 | W209.A26640 | HYB Essential Defueling Safety Case |  | 2022-10-14 | Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN Available | 24-Jan-23 A | 24-Jan-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.25950 | HYB Essential Defueling Safety Case |  | 2022-10-14 | Discovery Milestone - Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN Available | 24-Jan-23 A | 24-Jan-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A26640 | TOR Essential Defueling Safety Case |  | 2022-10-14 | Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN Available | 24-Jan-23 A | 24-Jan-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.25950 | TOR Essential Defueling Safety Case |  | 2022-10-14 | Discovery Milestone - Summary Report - Fault Review e.g. LoC - Impact on SCM, Misloading Consequences EAN Available | 24-Jan-23 A | 24-Jan-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1640 | DNB Enhanced Safety Cases |  | 2023-01-24 | Verifier PJB Held | 24-Jan-23 A | 24-Jan-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.8900 | HYB Essential Defueling Safety Case | 2022-12-05 | 2022-12-06 | Human Factors Decision Making (Pre Workshop) Activities on Quantifying ML/MD Faults | 25-Jan-23 A | 25-Jan-23 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.8910 | HYB Essential Defueling Safety Case |  | 2022-12-06 | Human Factors Decision Making Workshop on Quantifying ML/MD Faults | 25-Jan-23 A | 25-Jan-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.8920 | HYB Essential Defueling Safety Case |  | 2022-12-06 | Discovery Milestone - Human Factors Decisions on Scope for WP4 | 25-Jan-23 A | 25-Jan-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.29090 | HYB Essential Defueling Safety Case |  |  | Fault schedule sentencing workshop | 25-Jan-23 A | 25-Jan-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.8900 | TOR Essential Defueling Safety Case | 2022-12-05 | 2022-12-06 | Human Factors Decision Making (Pre Workshop) Activities on Quantifying ML/MD Faults | 25-Jan-23 A | 25-Jan-23 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.8910 | TOR Essential Defueling Safety Case |  | 2022-12-06 | Human Factors Decision Making Workshop on Quantifying ML/MD Faults | 25-Jan-23 A | 25-Jan-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.8920 | TOR Essential Defueling Safety Case |  | 2022-12-06 | Discovery Milestone - Human Factors Decisions on Scope for WP4 | 25-Jan-23 A | 25-Jan-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.29090 | TOR Essential Defueling Safety Case |  |  | Fault schedule sentencing workshop | 25-Jan-23 A | 25-Jan-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.6770 | HYB Essential Defueling Safety Case | 2022-10-10 | 2022-10-21 | Prepare Task Sheet for Defuelling Handling Deterministic Assessment EAN | 26-Jan-23 A | 30-Jan-23 A | 10 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.6800 | HYB Essential Defueling Safety Case | 2022-10-10 | 2022-10-21 | Prepare Task Sheet for Defuelling Worker Risk Assessment EAN | 26-Jan-23 A | 06-Feb-23 A | 10 | 0 | 8 | 100% |  | Completed
ER6668LT | W213 | W213.6770 | TOR Essential Defueling Safety Case | 2022-10-10 | 2022-10-21 | Prepare Task Sheet for Defuelling Handling Deterministic Assessment EAN | 26-Jan-23 A | 30-Jan-23 A | 10 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.6800 | TOR Essential Defueling Safety Case | 2022-10-10 | 2022-10-21 | Prepare Task Sheet for Defuelling Worker Risk Assessment EAN | 26-Jan-23 A | 06-Feb-23 A | 10 | 0 | 8 | 100% |  | Completed
ER6666LT | W209 | W209.6920 | HYB Essential Defueling Safety Case | 2023-01-30 | 2023-07-03 | Verification of Claim 1 | 30-Jan-23 A | 18-Sep-23 A | 20 | 0 | 159 | 100% |  | Completed
W232LT | W232 | W232.A1590 | DNB Enhanced Safety Cases | 2023-01-10 | 2023-01-16 | Incorporate INA, Station, ED (peer) comments | 30-Jan-23 A | 03-Feb-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.6920 | TOR Essential Defueling Safety Case | 2023-01-30 | 2023-07-03 | Verification of Claim 1 | 30-Jan-23 A | 18-Sep-23 A | 20 | 0 | 159 | 100% |  | Completed
ER6666LT | W209 | W209.A26360 | HYB Essential Defueling Safety Case | 2022-08-26 | 2022-10-24 | Verify Graphite Summary Report EAN | 31-Jan-23 A | 24-Feb-23 A | 21 | 0 | 19 | 100% |  | Completed
ER6666LT | W209 | W209.A29230 | HYB Essential Defueling Safety Case | 2022-12-02 | 2023-01-17 | Draft Defuelling Hazards Review EAN | 31-Jan-23 A | 10-Mar-23 A | 28 | 0 | 29 | 100% |  | Completed
ER6666LT | W209 | W209.9040 | HYB Essential Defueling Safety Case |  | 2022-12-13 | Discovery Milestone - Fuel Free Verification (FFV) - EAN available | 31-Jan-23 A | 31-Jan-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1390 | DNB Enhanced Safety Cases |  | 2023-01-31 | End of Release Funding | 31-Jan-23 A | 31-Jan-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2700 | DNB Enhanced Safety Cases | 2023-02-01 | 2024-02-15 | Project Management - A-B | 31-Jan-23 A | 23-Apr-24 A | 278 | 0 | 310 | 100% |  | Completed
W232LT | W232 | W232.A2710 | DNB Enhanced Safety Cases | 2023-02-01 | 2024-02-15 | Technical Oversight - A-B | 31-Jan-23 A | 23-Apr-24 A | 278 | 0 | 310 | 100% |  | Completed
ER6668LT | W213 | W213.A26360 | TOR Essential Defueling Safety Case | 2022-08-26 | 2022-10-24 | Verify Graphite Summary Report EAN | 31-Jan-23 A | 24-Feb-23 A | 21 | 0 | 19 | 100% |  | Completed
ER6668LT | W213 | W213.A29230 | TOR Essential Defueling Safety Case | 2022-12-02 | 2023-01-17 | Draft Defuelling Hazards Review EAN | 31-Jan-23 A | 10-Mar-23 A | 28 | 0 | 29 | 100% |  | Completed
ER6668LT | W213 | W213.9040 | TOR Essential Defueling Safety Case |  | 2022-12-13 | Discovery Milestone - Fuel Free Verification (FFV) - EAN available | 31-Jan-23 A | 31-Jan-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A29220 | HYB Essential Defueling Safety Case | 2022-12-01 | 2022-12-01 | Pre Job Brief for Defuelling Hazards Review EAN | 31-Jan-23 A | 31-Jan-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.6780 | HYB Essential Defueling Safety Case | 2022-10-24 | 2022-10-31 | Approve Task Sheet for Defuelling Handling Deterministic Assessment EAN | 31-Jan-23 A | 03-Feb-23 A | 6 | 0 | 4 | 100% |  | Completed
ER6668LT | W213 | W213.A29220 | TOR Essential Defueling Safety Case | 2022-12-01 | 2022-12-01 | Pre Job Brief for Defuelling Hazards Review EAN | 31-Jan-23 A | 31-Jan-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.6780 | TOR Essential Defueling Safety Case | 2022-10-24 | 2022-10-31 | Approve Task Sheet for Defuelling Handling Deterministic Assessment EAN | 31-Jan-23 A | 03-Feb-23 A | 6 | 0 | 4 | 100% |  | Completed
W232LT | W232 | W232.A1670 | DNB Enhanced Safety Cases |  | 2023-01-31 | Issue agreed work programme to stakeholders & suppliers | 31-Jan-23 A | 31-Jan-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A29000 | HYB Essential Defueling Safety Case | 2023-01-30 | 2023-02-17 | Verify Summary of Compliance with RADWASTE Assessment Principles EAN | 01-Feb-23 A | 31-Mar-23 A | 15 | 0 | 43 | 100% |  | Completed
ER6666LT | W209 | W209.6940 | HYB Essential Defueling Safety Case | 2023-02-01 | 2023-07-10 | RAWG Endorse Claim 1 | 01-Feb-23 A | 07-Nov-23 A | 20 | 0 | 193 | 100% |  | Completed
ER6666LT | W209 | W209.28950 | HYB Essential Defueling Safety Case |  |  | Review & Integrate TASK F Data Prior to Draft Completion | 01-Feb-23 A | 28-Feb-23 A | 25 | 0 | 20 | 100% |  | Completed
ER6666LT | W209 | W209.29460 | HYB Essential Defueling Safety Case |  |  | Thermal Modelling - (Civils Follow-On Work) | 01-Feb-23 A | 21-Apr-23 A | 1 | 0 | 55 | 100% |  | Completed
ER6668LT | W213 | W213.A29000 | TOR Essential Defueling Safety Case | 2023-01-30 | 2023-02-17 | Verify Summary of Compliance with RADWASTE Assessment Principles EAN | 01-Feb-23 A | 31-Mar-23 A | 15 | 0 | 43 | 100% |  | Completed
ER6668LT | W213 | W213.6940 | TOR Essential Defueling Safety Case | 2023-02-01 | 2023-07-10 | RAWG Endorse Claim 1 | 01-Feb-23 A | 07-Nov-23 A | 20 | 0 | 193 | 100% |  | Completed
ER6668LT | W213 | W213.28950 | TOR Essential Defueling Safety Case |  |  | Review & Integrate TASK F Data Prior to Draft Completion | 01-Feb-23 A | 28-Feb-23 A | 25 | 0 | 20 | 100% |  | Completed
ER6668LT | W213 | W213.29460 | TOR Essential Defueling Safety Case |  |  | Thermal Modelling - (Civils Follow-On Work) | 01-Feb-23 A | 21-Apr-23 A | 1 | 0 | 55 | 100% |  | Completed
ER6666LT | W209 | W209.A29420 | HYB Essential Defueling Safety Case | 2022-12-29 | 2023-01-05 | Supplier Update and Issue Cooling Plant Availability Review EAN | 03-Feb-23 A | 03-Feb-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A29420 | TOR Essential Defueling Safety Case | 2022-12-29 | 2023-01-05 | Supplier Update and Issue Cooling Plant Availability Review EAN | 03-Feb-23 A | 03-Feb-23 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A1600 | DNB Enhanced Safety Cases | 2023-01-17 | 2023-01-24 | Issue final NSRS | 06-Feb-23 A | 13-Feb-23 A | 6 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.A29430 | HYB Essential Defueling Safety Case | 2023-01-06 | 2023-01-12 | Complete TR Form and Upload Cooling Plant Availability Review EAN to CDMS | 06-Feb-23 A | 17-Feb-23 A | 4 | 0 | 9 | 100% |  | Completed
ER6666LT | W209 | W209.8080 | HYB Essential Defueling Safety Case | 2023-01-09 | 2023-01-20 | Supplier Update and Issue HF Assessment of the Extant Fuel Movement in support of Defueling FFV Claim | 06-Feb-23 A | 24-Feb-23 A | 3 | 0 | 14 | 100% |  | Completed
W232LT | W232 | W232.A2510 | DNB Enhanced Safety Cases | 2023-02-06 | 2023-02-20 | Produce Discussion Paper on Approach to Cold Defuelling Feasibility | 06-Feb-23 A | 20-Feb-23 A | 11 | 0 | 11 | 100% |  | Completed
W232LT | W232 | W232.B2560 | DNB Enhanced Safety Cases | 2023-02-06 | 2023-02-20 | Review Initial Optioneering Report | 06-Feb-23 A | 20-Feb-23 A | 11 | 0 | 11 | 100% |  | Completed
ER6666LT | W209 | W209.29140 | HYB Essential Defueling Safety Case |  |  | Draft revision 002 including revised fault schedule | 06-Feb-23 A | 06-Oct-23 A | 61 | 0 | 168 | 100% |  | Completed
ER6668LT | W213 | W213.A29430 | TOR Essential Defueling Safety Case | 2023-01-06 | 2023-01-12 | Complete TR Form and Upload Cooling Plant Availability Review EAN to CDMS | 06-Feb-23 A | 17-Feb-23 A | 4 | 0 | 9 | 100% |  | Completed
ER6668LT | W213 | W213.8080 | TOR Essential Defueling Safety Case | 2023-01-09 | 2023-01-20 | Supplier Update and Issue HF Assessment of the Extant Fuel Movement in support of Defueling FFV Claim | 06-Feb-23 A | 24-Feb-23 A | 3 | 0 | 14 | 100% |  | Completed
ER6668LT | W213 | W213.29140 | TOR Essential Defueling Safety Case |  |  | Draft revision 002 including revised fault schedule | 06-Feb-23 A | 06-Oct-23 A | 61 | 0 | 168 | 100% |  | Completed
ER6666LT | W209 | W209.6810 | HYB Essential Defueling Safety Case | 2022-10-24 | 2022-10-31 | Approve Task Sheet for Defuelling Worker Risk Assessment EAN | 07-Feb-23 A | 24-Feb-23 A | 6 | 0 | 14 | 100% |  | Completed
ER6666LT | W209 | W209.7250 | HYB Essential Defueling Safety Case | 2022-09-20 | 2022-09-20 | PJB for Claim 4 Authoring | 07-Feb-23 A | 07-Feb-23 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2720 | DNB Enhanced Safety Cases | 2023-02-01 | 2023-02-07 | Agree design proposals with Station in the case of hardware mods | 07-Feb-23 A | 13-Feb-23 A | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.A2715 | DNB Enhanced Safety Cases | 2023-02-01 | 2023-04-13 | Maintenance Review of FR Plant - Summary | 07-Feb-23 A | 30-Jun-23 A | 82 | 0 | 98 | 100% |  | Completed
ER6668LT | W213 | W213.6810 | TOR Essential Defueling Safety Case | 2022-10-24 | 2022-10-31 | Approve Task Sheet for Defuelling Worker Risk Assessment EAN | 07-Feb-23 A | 24-Feb-23 A | 6 | 0 | 14 | 100% |  | Completed
ER6668LT | W213 | W213.7250 | TOR Essential Defueling Safety Case | 2022-09-20 | 2022-09-20 | PJB for Claim 4 Authoring | 07-Feb-23 A | 07-Feb-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.1165 | HYB Essential Defueling Safety Case | 2022-06-30 | 2022-06-30 | Send NSRS to ONR to determine level of review required (Acknowledgement or Agreement) | 08-Feb-23 A | 08-Feb-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.7260 | HYB Essential Defueling Safety Case | 2023-02-08 | 2023-08-18 | Author Claim 4 | 08-Feb-23 A | 13-Oct-23 A | 20 | 0 | 172 | 100% |  | Completed
ER6668LT | W213 | W213.1165 | TOR Essential Defueling Safety Case | 2022-06-30 | 2022-06-30 | Send NSRS to ONR to determine level of review required (Acknowledgement or Agreement) | 08-Feb-23 A | 08-Feb-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.7260 | TOR Essential Defueling Safety Case | 2023-02-08 | 2023-08-18 | Author Claim 4 | 08-Feb-23 A | 13-Oct-23 A | 20 | 0 | 171 | 100% |  | Completed
W232LT | W232 | W232.A1220 | DNB Enhanced Safety Cases | 2023-02-01 | 2023-02-02 | Produce verification plan | 13-Feb-23 A | 17-Feb-23 A | 2 | 0 | 4 | 100% |  | Completed
ER6666LT | W209 | W209.A25740 | HYB Essential Defueling Safety Case | 2022-08-04 | 2022-08-10 | Supplier Update and Issue Judgement Based Work Diversion EAN | 13-Feb-23 A | 28-Feb-23 A | 5 | 0 | 12 | 100% |  | Completed
ER6371LT | W202 | 2385 | HRA Reactors Shutdown Essential Safety Cases |  |  | Verification - Focused (Lead Verifier)(HHB Opexs) | 13-Feb-23 A | 16-Mar-23 A | 20 | 0 | 24 | 100% |  | Completed
ER6371LT | W202 | 2395 | HRA Reactors Shutdown Essential Safety Cases |  |  | Sub-verifier(s) including GAP review (HHB Opexs) | 13-Feb-23 A | 16-Mar-23 A | 20 | 0 | 23 | 100% |  | Completed
ER6661LT | W206 | 2385 | HYA Reactors Shutdown Essential Safety Cases |  |  | Verification - Focused (Lead Verifier)(HHB Opexs) | 13-Feb-23 A | 16-Mar-23 A | 20 | 0 | 24 | 100% |  | Completed
ER6661LT | W206 | 2395 | HYA Reactors Shutdown Essential Safety Cases |  |  | Sub-verifier(s) including GAP review (HHB Opexs) | 13-Feb-23 A | 16-Mar-23 A | 20 | 0 | 23 | 100% |  | Completed
ER6668LT | W213 | W213.A25740 | TOR Essential Defueling Safety Case | 2022-08-04 | 2022-08-10 | Supplier Update and Issue Judgement Based Work Diversion EAN | 13-Feb-23 A | 28-Feb-23 A | 5 | 0 | 12 | 100% |  | Completed
W232LT | W232 | W232.A1610 | DNB Enhanced Safety Cases |  | 2023-01-24 | Station agree NSRS *(KDM)* | 13-Feb-23 A | 13-Feb-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1620 | DNB Enhanced Safety Cases |  | 2023-01-24 | Key Stakeholders agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 13-Feb-23 A | 13-Feb-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1630 | DNB Enhanced Safety Cases |  | 2023-01-24 | INA agree NSRS | 13-Feb-23 A | 13-Feb-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A29060 | HYB Essential Defueling Safety Case | 2022-11-01 | 2022-11-01 | Pre Job Brief for Defuelling Handling Deterministic Assessment EAN | 14-Feb-23 A | 14-Feb-23 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A1140 | DNB Enhanced Safety Cases | 2023-02-01 | 2023-02-07 | Agree design proposals with Station in the case of hardware mods | 14-Feb-23 A | 20-Feb-23 A | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.A1650 | DNB Enhanced Safety Cases | 2023-01-25 | 2023-01-31 | Consolidate & issue to stakeholders & suppliers agreed NSRS (as required) | 14-Feb-23 A | 15-Feb-23 A | 5 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2730 | DNB Enhanced Safety Cases | 2023-02-01 | 2023-03-14 | Produce supporting reference <Maintenance Review of FR Plant> | 14-Feb-23 A | 14-Apr-23 A | 30 | 0 | 41 | 100% |  | Completed
W232LT | W232 | W232.A1135 | DNB Enhanced Safety Cases | 2023-02-01 | 2023-04-13 | PSA Sensitivity Study - Summary | 14-Feb-23 A | 14-Apr-23 A | 55 | 0 | 41 | 100% |  | Completed
ER6668LT | W213 | W213.A29060 | TOR Essential Defueling Safety Case | 2022-11-01 | 2022-11-01 | Pre Job Brief for Defuelling Handling Deterministic Assessment EAN | 14-Feb-23 A | 14-Feb-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A29070 | HYB Essential Defueling Safety Case | 2023-02-15 | 2023-08-08 | Draft Defuelling Handling Deterministic Assessment EAN | 15-Feb-23 A | 16-Nov-23 A | 30 | 0 | 190 | 100% |  | Completed
ER6668LT | W213 | W213.A29070 | TOR Essential Defueling Safety Case | 2023-02-15 | 2023-08-08 | Draft Defuelling Handling Deterministic Assessment EAN | 15-Feb-23 A | 16-Nov-23 A | 30 | 0 | 190 | 100% |  | Completed
ER6666LT | W209 | W209.A30710 | HYB Essential Defueling Safety Case | 2023-03-07 | 2023-05-18 | Technical Review of Underload Veto Height for Channel 1 - HYB | 16-Feb-23 A | 22-Mar-23 A | 32 | 0 | 24 | 100% |  | Completed
ER6668LT | W213 | W213.A30710 | TOR Essential Defueling Safety Case | 2023-03-07 | 2023-05-18 | Technical Review of Underload Veto Height for Channel 1 - TOR | 16-Feb-23 A | 22-Mar-23 A | 32 | 0 | 24 | 100% |  | Completed
ER6666LT | W209 | W209.A29440 | HYB Essential Defueling Safety Case |  | 2023-01-12 | Cooling Plant Availability Review EAN Available | 17-Feb-23 A | 17-Feb-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A29440 | TOR Essential Defueling Safety Case |  | 2023-01-12 | Cooling Plant Availability Review EAN Available | 17-Feb-23 A | 17-Feb-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1200 | DNB Enhanced Safety Cases | 2023-02-06 | 2023-02-07 | CA to agree with CO format of the safety case & produce agreed contents page | 17-Feb-23 A | 20-Feb-23 A | 2 | 0 | 2 | 100% |  | Completed
W232LT | W232 | W232.A2960 | DNB Enhanced Safety Cases |  |  | Decision Milestone - Progress FLSA's | 17-Feb-23 A | 17-Feb-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A25900 | HYB Essential Defueling Safety Case | 2022-11-03 | 2022-11-09 | Supplier Update and Issue Safety Case Requirements EAN - TASK E EAN | 20-Feb-23 A | 28-Feb-23 A | 5 | 0 | 6 | 100% |  | Completed
ER6668LT | W213 | W213.A25900 | TOR Essential Defueling Safety Case | 2022-11-03 | 2022-11-09 | Supplier Update and Issue Safety Case Requirements EAN - TASK E EAN | 20-Feb-23 A | 28-Feb-23 A | 5 | 0 | 6 | 100% |  | Completed
ER6666LT | W209 | W209.A27090 | HYB Essential Defueling Safety Case | 2022-09-14 | 2022-10-25 | Technical Review of FPU Integrity Analysis EAN | 20-Feb-23 A | 16-Mar-23 A | 19 | 0 | 19 | 100% |  | Completed
ER6668LT | W213 | W213.A27090 | TOR Essential Defueling Safety Case | 2022-09-14 | 2022-10-25 | Technical Review of FPU Integrity Analysis EAN | 20-Feb-23 A | 16-Mar-23 A | 19 | 0 | 19 | 100% |  | Completed
ER6666LT | W209 | W209.A28620 | HYB Essential Defueling Safety Case | 2022-07-26 | 2022-08-12 | Supplier Update and Issue Radiological Consequences Following Failed CSP EAN | 21-Feb-23 A | 28-Feb-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.7170 | HYB Essential Defueling Safety Case | 2022-12-29 | 2023-04-24 | Author Claim 5 | 21-Feb-23 A | 01-Dec-23 A | 62 | 0 | 197 | 100% |  | Completed
ER6668LT | W213 | W213.A28620 | TOR Essential Defueling Safety Case | 2022-07-26 | 2022-08-12 | Supplier Update and Issue Radiological Consequences Following Failed CSP EAN | 21-Feb-23 A | 28-Feb-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.7170 | TOR Essential Defueling Safety Case | 2022-12-29 | 2023-04-24 | Author Claim 5 | 21-Feb-23 A | 01-Dec-23 A | 62 | 0 | 198 | 100% |  | Completed
ER6666LT | W209 | W209.25880 | HYB Essential Defueling Safety Case | 2022-12-30 | 2022-12-30 | Pre Job Brief for Human Reliability Assessment of Unsubstantiated Claims EAN | 21-Feb-23 A | 21-Feb-23 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A1150 | DNB Enhanced Safety Cases | 2023-02-01 | 2023-03-14 | Produce supporting reference <PSA Sensitivity Study> | 21-Feb-23 A | 03-Apr-23 A | 30 | 0 | 30 | 100% |  | Completed
W232LT | W232 | W232.A2520 | DNB Enhanced Safety Cases | 2023-02-21 | 2023-03-06 | Develop Worklist and Schedule | 21-Feb-23 A | 06-Mar-23 A | 10 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.A2530 | DNB Enhanced Safety Cases | 2023-02-21 | 2023-03-06 | Specify Discovery Milestones | 21-Feb-23 A | 06-Mar-23 A | 10 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.B2550 | DNB Enhanced Safety Cases | 2023-02-21 | 2023-04-20 | Assess Options for Providing Moisture Detection Capability | 21-Feb-23 A | 20-Apr-23 A | 41 | 0 | 41 | 100% |  | Completed
ER6668LT | W213 | W213.25880 | TOR Essential Defueling Safety Case | 2022-12-30 | 2022-12-30 | Pre Job Brief for Human Reliability Assessment of Unsubstantiated Claims EAN | 21-Feb-23 A | 21-Feb-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A31240 | HYB Essential Defueling Safety Case |  |  | Supplier Update and Issue Update Basis of Analysis document - (Issue 5) | 22-Feb-23 A | 28-Feb-23 A | 15 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A31240 | TOR Essential Defueling Safety Case |  |  | Supplier Update and Issue Update Basis of Analysis document - (Issue 5) | 22-Feb-23 A | 28-Feb-23 A | 15 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.29370 | HYB Essential Defueling Safety Case |  |  | Screening Activity | 22-Feb-23 A | 16-Mar-23 A | 15 | 0 | 17 | 100% |  | Completed
ER6668LT | W213 | W213.29370 | TOR Essential Defueling Safety Case |  |  | Screening Activity | 22-Feb-23 A | 16-Mar-23 A | 15 | 0 | 17 | 100% |  | Completed
ER6666LT | W209 | W209.7090 | HYB Essential Defueling Safety Case | 2023-01-24 | 2023-02-20 | Case Officer Tech Lead Review Claim 3 | 24-Feb-23 A | 26-May-23 A | 20 | 0 | 61 | 100% |  | Completed
ER6668LT | W213 | W213.7090 | TOR Essential Defueling Safety Case | 2023-01-24 | 2023-02-20 | Case Officer Tech Lead Review Claim 3 | 24-Feb-23 A | 26-May-23 A | 20 | 0 | 61 | 100% |  | Completed
ER6666LT | W209 | W209.8090 | HYB Essential Defueling Safety Case | 2023-01-23 | 2023-02-03 | Complete TR Form and Upload HF Assessment of the Extant Fuel Movement in support of Defueling FFV Claim | 27-Feb-23 A | 03-Mar-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.8090 | TOR Essential Defueling Safety Case | 2023-01-23 | 2023-02-03 | Complete TR Form and Upload HF Assessment of the Extant Fuel Movement in support of Defueling FFV Claim | 27-Feb-23 A | 03-Mar-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.A26390 | HYB Essential Defueling Safety Case | 2022-10-25 | 2022-10-31 | Approve & Upload Graphite Summary Report EAN to CDMS | 27-Feb-23 A | 03-Mar-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.A29140 | HYB Essential Defueling Safety Case | 2022-11-01 | 2022-11-01 | Pre Job Brief for Defuelling Worker Risk Assessment EAN | 27-Feb-23 A | 23-May-23 A | 1 | 0 | 58 | 100% |  | Completed
ER6666LT | W209 | W209.7000 | HYB Essential Defueling Safety Case | 2022-12-29 | 2023-01-26 | Case Officer Tech Lead Review Claim 2 | 27-Feb-23 A | 16-Mar-23 A | 10 | 0 | 13 | 100% |  | Completed
ER6668LT | W213 | W213.A26390 | TOR Essential Defueling Safety Case | 2022-10-25 | 2022-10-31 | Approve & Upload Graphite Summary Report EAN to CDMS | 27-Feb-23 A | 03-Mar-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A29140 | TOR Essential Defueling Safety Case | 2022-11-01 | 2022-11-01 | Pre Job Brief for Defuelling Worker Risk Assessment EAN | 27-Feb-23 A | 23-May-23 A | 1 | 0 | 58 | 100% |  | Completed
ER6668LT | W213 | W213.7000 | TOR Essential Defueling Safety Case | 2022-12-29 | 2023-01-26 | Case Officer Tech Lead Review Claim 2 | 27-Feb-23 A | 16-Mar-23 A | 10 | 0 | 13 | 100% |  | Completed
ER6372LT | W203 | W203.A2320 | HNB Enhanced Defuelling Safety Cases |  |  | <SCOPE REMOVED CN571> Consideration of Deliberate Admission of Air to a Defuelling Reactor - SC Approved | 28-Feb-23 A | 28-Feb-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A1280 | HNB Enhanced Defuelling Safety Cases |  |  | < SCOPE REMOVED CN571> Cooling faults (decay heats) EAN updated - Prepare Draft Report | 28-Feb-23 A | 28-Feb-23 A | 10 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A1380 | HNB Enhanced Defuelling Safety Cases |  |  | < SCOPE REMOVED CN571> Cooling faults (decay heats) EAN updated - Issued Draft Report to EDF for Review. | 28-Feb-23 A | 28-Feb-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A1430 | HNB Enhanced Defuelling Safety Cases |  |  | < SCOPE REMOVED CN571> Cooling faults (decay heats) EAN updated - Reviewed by EDF SQEP | 28-Feb-23 A | 28-Feb-23 A | 10 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A1530 | HNB Enhanced Defuelling Safety Cases |  |  | < SCOPE REMOVED CN571> Cooling faults (decay heats) EAN updated - Address Comments from EDF Review | 28-Feb-23 A | 28-Feb-23 A | 10 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A1590 | HNB Enhanced Defuelling Safety Cases |  |  | < SCOPE REMOVED CN571> Cooling faults (decay heats) EAN updated - Issue Final Report | 28-Feb-23 A | 28-Feb-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A1620 | HNB Enhanced Defuelling Safety Cases |  |  | < SCOPE REMOVED CN571> Cooling faults (decay heats) EAN updated - Completed and Uploaded to CDMS | 28-Feb-23 A | 28-Feb-23 A | 10 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A1660 | HNB Enhanced Defuelling Safety Cases |  |  | < SCOPE REMOVED CN571> Cooling faults (decay heats) EAN updated - Report Completed | 28-Feb-23 A | 28-Feb-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A1270 | HNB Enhanced Defuelling Safety Cases |  |  | < SCOPE REMOVED CN571> Cooling faults (decay heats) EAN updated - Summary | 28-Feb-23 A | 28-Feb-23 A | 40 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A2440 | HNB Enhanced Defuelling Safety Cases |  |  | <SCOPE REMOVED CN571> Admission to Air technical work progressed | 28-Feb-23 A | 28-Feb-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A25750 | HYB Essential Defueling Safety Case | 2022-08-11 | 2022-08-17 | Complete TR Form and Upload Judgement Based Work Diversion EAN Requirements to CDMS | 28-Feb-23 A | 31-Mar-23 A | 1 | 0 | 24 | 100% |  | Completed
ER6666LT | W209 | W209.A25910 | HYB Essential Defueling Safety Case | 2022-11-10 | 2022-11-16 | Complete TR Form and Upload Safety Case Requirements EAN - TASK E EAN to CDMS | 28-Feb-23 A | 21-Apr-23 A | 5 | 0 | 37 | 100% |  | Completed
ER6666LT | W209 | W209.A26790 | HYB Essential Defueling Safety Case | 2022-12-23 | 2023-01-03 | Complete TR Form and Upload Boron Bead Injection Feasibility & Control Rod Isolation EAN to CDMS | 28-Feb-23 A | 21-Apr-23 A | 5 | 0 | 37 | 100% |  | Completed
ER6666LT | W209 | W209.A28630 | HYB Essential Defueling Safety Case | 2022-12-08 | 2022-12-14 | Complete TR Form and Upload Radiological Consequences Following Failed CSP EAN to CDMS | 28-Feb-23 A | 07-Mar-23 A | 5 | 0 | 6 | 100% |  | Completed
ER6666LT | W209 | W209.A29620 | HYB Essential Defueling Safety Case | 2023-02-20 | 2023-02-24 | Complete TR Form and Upload TASK F Review of the Discharge Limits (Permits) EAN to CDMS | 28-Feb-23 A | 12-May-23 A | 5 | 0 | 50 | 100% |  | Completed
ER6666LT | W209 | W209.A31250 | HYB Essential Defueling Safety Case |  |  | Complete TR Form and Upload Update Basis of Analysis document to CDMS - (Issue 5) | 28-Feb-23 A | 07-Mar-23 A | 5 | 0 | 6 | 100% |  | Completed
ER6371LT | W202 | 2335 | HRA Reactors Shutdown Essential Safety Cases |  |  | Lesson Learn - Authoring Phase | 28-Feb-23 A | 28-Feb-23 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A25750 | TOR Essential Defueling Safety Case | 2022-08-11 | 2022-08-17 | Complete TR Form and Upload Judgement Based Work Diversion EAN Requirements to CDMS | 28-Feb-23 A | 31-Mar-23 A | 1 | 0 | 24 | 100% |  | Completed
ER6668LT | W213 | W213.A25910 | TOR Essential Defueling Safety Case | 2022-11-10 | 2022-11-16 | Complete TR Form and Upload Safety Case Requirements EAN - TASK E EAN to CDMS | 28-Feb-23 A | 21-Apr-23 A | 5 | 0 | 37 | 100% |  | Completed
ER6668LT | W213 | W213.A26790 | TOR Essential Defueling Safety Case | 2022-12-23 | 2023-01-03 | Complete TR Form and Upload Boron Bead Injection Feasibility & Control Rod Isolation EAN to CDMS | 28-Feb-23 A | 21-Apr-23 A | 5 | 0 | 37 | 100% |  | Completed
ER6668LT | W213 | W213.A28630 | TOR Essential Defueling Safety Case | 2022-12-08 | 2022-12-14 | Complete TR Form and Upload Radiological Consequences Following Failed CSP EAN to CDMS | 28-Feb-23 A | 07-Mar-23 A | 5 | 0 | 6 | 100% |  | Completed
ER6668LT | W213 | W213.A29620 | TOR Essential Defueling Safety Case | 2023-02-20 | 2023-02-24 | Complete TR Form and Upload TASK F Review of the Discharge Limits (Permits) EAN to CDMS | 28-Feb-23 A | 12-May-23 A | 5 | 0 | 50 | 100% |  | Completed
ER6668LT | W213 | W213.A31250 | TOR Essential Defueling Safety Case |  |  | Complete TR Form and Upload Update Basis of Analysis document to CDMS - (Issue 5) | 28-Feb-23 A | 07-Mar-23 A | 5 | 0 | 6 | 100% |  | Completed
ER6661LT | W206 | 2335 | HYA Reactors Shutdown Essential Safety Cases |  |  | Lesson Learn - Authoring Phase | 28-Feb-23 A | 28-Feb-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A2120 | HNB Enhanced Defuelling Safety Cases | 2023-05-24 | 2024-06-25 | Technical Oversight Gate B - C | 01-Mar-23 A | 19-Nov-24 A | 149 | 0 | 436 | 100% |  | Completed
ER6372LT | W203 | W203.A2130 | HNB Enhanced Defuelling Safety Cases | 2023-05-24 | 2024-06-25 | Station Oversight Gate B - C | 01-Mar-23 A | 19-Nov-24 A | 149 | 0 | 436 | 100% |  | Completed
ER6666LT | W209 | W209.A29760 | HYB Essential Defueling Safety Case | 2022-10-24 | 2022-10-28 | Complete TR Form and Upload PARTIAL Drain down of the PVCS prior to Defuelling (Report) to CDMS | 01-Mar-23 A | 19-May-23 A | 5 | 0 | 53 | 100% |  | Completed
ER6666LT | W209 | W209.29100 | HYB Essential Defueling Safety Case |  |  | Draft Revision 001 | 01-Mar-23 A | 10-Mar-23 A | 8 | 0 | 8 | 100% |  | Completed
ER6371LT | W202 | 1625 | HRA Reactors Shutdown Essential Safety Cases |  |  | Update Fault Definition Document | 01-Mar-23 A | 21-Mar-23 A | 15 | 0 | 15 | 100% |  | Completed
ER6661LT | W206 | 1625 | HYA Reactors Shutdown Essential Safety Cases |  |  | Update Fault Definition Document | 01-Mar-23 A | 21-Mar-23 A | 15 | 0 | 15 | 100% |  | Completed
ER6371LT | W202 | W202.A2206690 | HRA Reactors Shutdown Essential Safety Cases | 2023-03-01 | 2023-03-14 | Confirm Objectives to be Delivered at Gate C+ | 01-Mar-23 A | 14-Mar-23 A | 10 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | W202.A2206720 | HRA Reactors Shutdown Essential Safety Cases | 2023-03-01 | 2023-04-25 | Gate C+ Planning | 01-Mar-23 A | 25-Apr-23 A | 38 | 0 | 38 | 100% |  | Completed
ER6661LT | W206 | W206.A2206690 | HYA Reactors Shutdown Essential Safety Cases |  |  | Confirm Objectives to be Delivered at Gate C+ | 01-Mar-23 A | 14-Mar-23 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.A2206720 | HYA Reactors Shutdown Essential Safety Cases |  |  | Gate C+ Planning | 01-Mar-23 A | 25-Apr-23 A | 38 | 0 | 38 | 100% |  | Completed
ER6372LT | W203 | W203.A3400 | HNB Enhanced Defuelling Safety Cases | 2023-05-24 | 2023-05-31 | Raise Engineering Request | 01-Mar-23 A | 07-Mar-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6372LT | W203 | W203.A3910 | HNB Enhanced Defuelling Safety Cases | 2023-05-24 | 2023-05-31 | Raise Engineering Request | 01-Mar-23 A | 07-Mar-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A29760 | TOR Essential Defueling Safety Case | 2022-10-24 | 2022-10-28 | Complete TR Form and Upload PARTIAL Drain down of the PVCS prior to Defuelling (Report) to CDMS | 01-Mar-23 A | 19-May-23 A | 5 | 0 | 53 | 100% |  | Completed
ER6668LT | W213 | W213.29100 | TOR Essential Defueling Safety Case |  |  | Draft Revision 001 | 01-Mar-23 A | 10-Mar-23 A | 8 | 0 | 8 | 100% |  | Completed
ER6666LT | W209 | W209.A26400 | HYB Essential Defueling Safety Case |  | 2022-10-31 | Graphite Summary Report EAN Available | 03-Mar-23 A | 03-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A26960 | HYB Essential Defueling Safety Case |  | 2022-12-21 | Chemistry Monitoring Strategy EAN EAN Available | 03-Mar-23 A | 03-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.8100 | HYB Essential Defueling Safety Case |  | 2023-02-03 | HF Assessment of the Extant Fuel Movement in support of Defueling FFV Claim EAN Available (System) | 03-Mar-23 A | 03-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A26400 | TOR Essential Defueling Safety Case |  | 2022-10-31 | Graphite Summary Report EAN Available | 03-Mar-23 A | 03-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A26960 | TOR Essential Defueling Safety Case |  | 2022-12-21 | Chemistry Monitoring Strategy EAN EAN Available | 03-Mar-23 A | 03-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.8100 | TOR Essential Defueling Safety Case |  | 2023-02-03 | HF Assessment of the Extant Fuel Movement in support of Defueling FFV Claim EAN Available (System) | 03-Mar-23 A | 03-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.9000 | HYB Essential Defueling Safety Case |  | 2023-03-14 | Discovery Milestone - PSA Reviewed Following Dropped FPU Case Conference | 07-Mar-23 A | 07-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2570 | DNB Enhanced Safety Cases | 2023-03-22 | 2023-04-04 | Define Required Lift Lower Trials | 07-Mar-23 A | 17-Mar-23 A | 10 | 0 | 8 | 100% |  | Completed
ER6668LT | W213 | W213.9000 | TOR Essential Defueling Safety Case |  | 2023-03-14 | Discovery Milestone - PSA Reviewed Following Dropped FPU Case Conference | 07-Mar-23 A | 07-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2540 | DNB Enhanced Safety Cases | 2023-03-07 | 2023-04-11 | Document Basis of Safety Case Claims | 07-Mar-23 A | 03-Apr-23 A | 24 | 0 | 20 | 100% |  | Completed
W232LT | W232 | W232.A2580 | DNB Enhanced Safety Cases | 2023-03-07 | 2023-03-21 | Confirm Approach to Re-entrant Seal Stiction Issue | 07-Mar-23 A | 21-Mar-23 A | 11 | 0 | 11 | 100% |  | Completed
ER6666LT | W209 | W209.A28640 | HYB Essential Defueling Safety Case |  | 2022-12-14 | Radiological Consequences Following Failed CSP EAN Available | 07-Mar-23 A | 07-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.8460 | HYB Essential Defueling Safety Case |  | 2023-03-14 | Reviewed PSA following CSP/Diagrid Structural Integrity Summary Report | 07-Mar-23 A | 07-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A31260 | HYB Essential Defueling Safety Case |  |  | Update Basis of Analysis document Available - (Issue 5) | 07-Mar-23 A | 07-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A28640 | TOR Essential Defueling Safety Case |  | 2022-12-14 | Radiological Consequences Following Failed CSP EAN Available | 07-Mar-23 A | 07-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.8460 | TOR Essential Defueling Safety Case |  | 2023-03-14 | Reviewed PSA following CSP/Diagrid Structural Integrity Summary Report | 07-Mar-23 A | 07-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A31260 | TOR Essential Defueling Safety Case |  |  | Update Basis of Analysis document Available - (Issue 5) | 07-Mar-23 A | 07-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3320 | HNB Enhanced Defuelling Safety Cases | 2023-06-01 |  | Mod req'd, Initiate EC, identify RE, register EC & identify MS in Passport | 08-Mar-23 A | 08-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3390 | HNB Enhanced Defuelling Safety Cases | 2023-06-01 | 2023-06-07 | Develop initial programme plan using mandatory template | 08-Mar-23 A | 14-Mar-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6372LT | W203 | W203.A3830 | HNB Enhanced Defuelling Safety Cases | 2023-06-01 |  | Mod req'd, Initiate EC, identify RE, register EC & identify MS in Passport | 08-Mar-23 A | 08-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3900 | HNB Enhanced Defuelling Safety Cases | 2023-06-01 | 2023-06-07 | Develop initial programme plan using mandatory template | 08-Mar-23 A | 14-Mar-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | 3020 | HRA Reactors Shutdown Essential Safety Cases |  |  | Lesson Learn - Event Recovery Phase | 10-Mar-23 A | 10-Mar-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | 3020 | HYA Reactors Shutdown Essential Safety Cases |  |  | Lesson Learn - Event Recovery Phase | 10-Mar-23 A | 10-Mar-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A29240 | HYB Essential Defueling Safety Case | 2023-01-18 | 2023-02-07 | Verify Defuelling Hazards Review EAN & Issue for Technical Review | 13-Mar-23 A | 06-Apr-23 A | 15 | 0 | 19 | 100% |  | Completed
ER6668LT | W213 | W213.A29240 | TOR Essential Defueling Safety Case | 2023-01-18 | 2023-02-07 | Verify Defuelling Hazards Review EAN & Issue for Technical Review | 13-Mar-23 A | 06-Apr-23 A | 15 | 0 | 19 | 100% |  | Completed
ER6666LT | W209 | W209.7340 | HYB Essential Defueling Safety Case | 2022-08-03 | 2022-08-03 | PJB for Claim 6 Authoring | 14-Mar-23 A | 14-Mar-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.8400 | HYB Essential Defueling Safety Case | 2023-03-14 | 2023-10-09 | Claim 6 Production ## (Cost Summary) | 14-Mar-23 A | 10-Nov-23 A | 183 | 0 | 167 | 100% |  | Completed
ER6371LT | W202 | 2460 | HRA Reactors Shutdown Essential Safety Cases | 2022-11-21 | 2022-11-23 | Re-attach to ADL | 14-Mar-23 A | 16-Mar-23 A | 3 | 0 | 3 | 100% |  | Completed
ER6661LT | W206 | 2460 | HYA Reactors Shutdown Essential Safety Cases | 2022-11-21 | 2022-11-23 | Re-attach to ADL | 14-Mar-23 A | 16-Mar-23 A | 3 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.7340 | TOR Essential Defueling Safety Case | 2022-08-03 | 2022-08-03 | PJB for Claim 6 Authoring | 14-Mar-23 A | 14-Mar-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.8400 | TOR Essential Defueling Safety Case | 2023-03-14 | 2023-10-09 | Claim 6 Production ## (Cost Summary) | 14-Mar-23 A | 10-Nov-23 A | 188 | 0 | 168 | 100% |  | Completed
ER6666LT | W209 | W209.A29150 | HYB Essential Defueling Safety Case | 2023-03-15 | 2023-08-08 | Draft Defuelling Worker Risk Assessment EAN | 15-Mar-23 A | 28-Jun-24 A | 30 | 0 | 325 | 100% |  | Completed
ER6668LT | W213 | W213.A29150 | TOR Essential Defueling Safety Case | 2023-03-15 | 2023-08-08 | Draft Defuelling Worker Risk Assessment EAN | 15-Mar-23 A | 28-Jun-24 A | 30 | 0 | 325 | 100% |  | Completed
ER6666LT | W209 | W209.7350 | HYB Essential Defueling Safety Case | 2022-12-09 | 2023-04-04 | Author Claim 6 | 15-Mar-23 A | 17-Apr-23 A | 24 | 0 | 22 | 100% |  | Completed
ER6371LT | W202 | W202.A2206560 | HRA Reactors Shutdown Essential Safety Cases | 2023-03-15 | 2023-03-21 | Define Project Control Structures (WBS/CBS/OBS/PBS) | 15-Mar-23 A | 21-Mar-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A2206650 | HRA Reactors Shutdown Essential Safety Cases | 2023-03-15 | 2023-03-15 | Prepare Draft Project Definition Document (PDD) | 15-Mar-23 A | 15-Mar-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A2206700 | HRA Reactors Shutdown Essential Safety Cases | 2023-03-15 | 2023-03-21 | Initial high level scope of programme | 15-Mar-23 A | 21-Mar-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A2206560 | HYA Reactors Shutdown Essential Safety Cases |  |  | Define Project Control Structures (WBS/CBS/OBS/PBS) | 15-Mar-23 A | 21-Mar-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A2206650 | HYA Reactors Shutdown Essential Safety Cases |  |  | Prepare Draft Project Definition Document (PDD) | 15-Mar-23 A | 15-Mar-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2206700 | HYA Reactors Shutdown Essential Safety Cases |  |  | Initial high level scope of programme | 15-Mar-23 A | 21-Mar-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.7350 | TOR Essential Defueling Safety Case | 2022-12-09 | 2023-04-04 | Author Claim 6 | 15-Mar-23 A | 17-Apr-23 A | 24 | 0 | 22 | 100% |  | Completed
ER6666LT | W209 | W209.29010 | HYB Essential Defueling Safety Case |  |  | Discovery Milestone - Define scope for WP6 - Claims to be Substantiated | 16-Mar-23 A | 16-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.29010 | TOR Essential Defueling Safety Case |  |  | Discovery Milestone - Define scope for WP6 - Claims to be Substantiated | 16-Mar-23 A | 16-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.6930 | HYB Essential Defueling Safety Case | 2023-03-17 | 2023-07-10 | Update Claim 1 | 17-Mar-23 A | 18-Sep-23 A | 20 | 0 | 125 | 100% |  | Completed
ER6666LT | W209 | W209.7010 | HYB Essential Defueling Safety Case | 2023-03-17 | 2023-07-03 | Verification of Claim 2 | 17-Mar-23 A | 27-Oct-23 A | 20 | 0 | 154 | 100% |  | Completed
ER6666LT | W209 | W209.25890 | HYB Essential Defueling Safety Case | 2023-01-03 | 2023-02-03 | Draft of Human Reliability Assessment of Unsubstantiated Claims EAN | 17-Mar-23 A | 28-Apr-23 A | 5 | 0 | 28 | 100% |  | Completed
ER6666LT | W209 | W209.29430 | HYB Essential Defueling Safety Case |  |  | Qualitative Analysis & Write Up (Supporting Drafting of the Refeence) | 17-Mar-23 A | 28-Apr-23 A | 1 | 0 | 29 | 100% |  | Completed
ER6668LT | W213 | W213.6930 | TOR Essential Defueling Safety Case | 2023-03-17 | 2023-07-10 | Update Claim 1 | 17-Mar-23 A | 18-Sep-23 A | 20 | 0 | 125 | 100% |  | Completed
ER6668LT | W213 | W213.7010 | TOR Essential Defueling Safety Case | 2023-03-17 | 2023-07-03 | Verification of Claim 2 | 17-Mar-23 A | 27-Oct-23 A | 20 | 0 | 154 | 100% |  | Completed
ER6668LT | W213 | W213.25890 | TOR Essential Defueling Safety Case | 2023-01-03 | 2023-02-03 | Draft of Human Reliability Assessment of Unsubstantiated Claims EAN | 17-Mar-23 A | 28-Apr-23 A | 5 | 0 | 28 | 100% |  | Completed
ER6668LT | W213 | W213.29430 | TOR Essential Defueling Safety Case |  |  | Qualitative Analysis & Write Up (Supporting Drafting of the Refeence) | 17-Mar-23 A | 28-Apr-23 A | 1 | 0 | 29 | 100% |  | Completed
ER6666LT | W209 | W209.A27100 | HYB Essential Defueling Safety Case | 2022-10-26 | 2022-11-01 | Supplier Update and Issue FPU Integrity Analysis EAN | 17-Mar-23 A | 25-Apr-23 A | 5 | 0 | 26 | 100% |  | Completed
ER6371LT | W202 | 2410 | HRA Reactors Shutdown Essential Safety Cases | 2022-11-24 | 2022-12-07 | Respond to Verification Comments and Updates | 17-Mar-23 A | 30-Mar-23 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | 2410 | HYA Reactors Shutdown Essential Safety Cases | 2022-11-24 | 2022-12-07 | Respond to Verification Comments and Updates | 17-Mar-23 A | 30-Mar-23 A | 10 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.A27100 | TOR Essential Defueling Safety Case | 2022-10-26 | 2022-11-01 | Supplier Update and Issue FPU Integrity Analysis EAN | 17-Mar-23 A | 25-Apr-23 A | 5 | 0 | 26 | 100% |  | Completed
ER6666LT | W209 | W209.29110 | HYB Essential Defueling Safety Case |  |  | Verification | 20-Mar-23 A | 12-Jun-23 A | 21 | 0 | 56 | 100% |  | Completed
ER6668LT | W213 | W213.29110 | TOR Essential Defueling Safety Case |  |  | Verification | 20-Mar-23 A | 12-Jun-23 A | 21 | 0 | 56 | 100% |  | Completed
ER6666LT | W209 | W209.A28230 | HYB Essential Defueling Safety Case | 2023-02-22 | 2023-02-28 | Complete TR Form and Upload CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN to CDMS | 20-Mar-23 A | 31-Mar-23 A | 5 | 0 | 9 | 100% |  | Completed
ER6666LT | W209 | W209.A28710 | HYB Essential Defueling Safety Case |  |  | Complete TR Form and CSP/Diagrid Structural Integrity Summary Report to CDMS | 20-Mar-23 A | 31-Mar-23 A | 5 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.A28230 | TOR Essential Defueling Safety Case | 2023-02-22 | 2023-02-28 | Complete TR Form and Upload CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN to CDMS | 20-Mar-23 A | 31-Mar-23 A | 5 | 0 | 9 | 100% |  | Completed
ER6668LT | W213 | W213.A28710 | TOR Essential Defueling Safety Case |  |  | Complete TR Form and CSP/Diagrid Structural Integrity Summary Report to CDMS | 20-Mar-23 A | 31-Mar-23 A | 5 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.A1660 | DNB Enhanced Safety Cases | 2023-03-01 | 2023-04-13 | Prepare the Safety Case Proposal (including OPEX Review) | 21-Mar-23 A | 22-Jun-23 A | 30 | 0 | 62 | 100% |  | Completed
ER6666LT | W209 | W209.A30720 | HYB Essential Defueling Safety Case | 2023-05-19 | 2023-05-25 | Supplier Update and Issue Channel 1 - HYB | 22-Mar-23 A | 15-Jun-23 A | 5 | 0 | 57 | 100% |  | Completed
ER6668LT | W213 | W213.A30720 | TOR Essential Defueling Safety Case | 2023-05-19 | 2023-05-25 | Supplier Update and Issue Channel 1 - TOR | 22-Mar-23 A | 15-Jun-23 A | 5 | 0 | 57 | 100% |  | Completed
ER6371LT | W202 | 1626 | HRA Reactors Shutdown Essential Safety Cases |  |  | 6 Verify updated FDD v2 | 22-Mar-23 A | 12-Jun-23 A | 10 | 0 | 53 | 100% |  | Completed
ER6661LT | W206 | 1626 | HYA Reactors Shutdown Essential Safety Cases |  |  | 6 Verify updated FDD | 22-Mar-23 A | 12-Jun-23 A | 5 | 0 | 53 | 100% |  | Completed
ER6371LT | W202 | W202.A2206570 | HRA Reactors Shutdown Essential Safety Cases | 2023-03-22 | 2023-03-28 | Plan Scope in Primavera (Level 2 C+-D & Level 1 Lifecycle) | 22-Mar-23 A | 28-Mar-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6661LT | W206 | W206.A2206570 | HYA Reactors Shutdown Essential Safety Cases |  |  | Plan Scope in Primavera (Level 2 C+-D & Level 1 Lifecycle) | 22-Mar-23 A | 28-Mar-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.A28280 | HYB Essential Defueling Safety Case | 2023-03-23 | 2023-07-21 | Verify Fault Definition Document (FDD) EAN | 23-Mar-23 A | 05-Oct-23 A | 33 | 0 | 135 | 100% |  | Completed
ER6668LT | W213 | W213.A28280 | TOR Essential Defueling Safety Case | 2023-03-23 | 2023-07-21 | Verify Fault Definition Document (FDD) EAN | 23-Mar-23 A | 05-Oct-23 A | 33 | 0 | 135 | 100% |  | Completed
ER6371LT | W202 | 2396 | HRA Reactors Shutdown Essential Safety Cases |  |  | First Round Verifier Comments Addressed | 24-Mar-23 A | 30-Mar-23 A | 1 | 0 | 4 | 100% |  | Completed
ER6661LT | W206 | 2396 | HYA Reactors Shutdown Essential Safety Cases |  |  | First Round Verifier Comments Addressed | 24-Mar-23 A | 30-Mar-23 A | 1 | 0 | 4 | 100% |  | Completed
W232LT | W232 | W232.A2590 | DNB Enhanced Safety Cases | 2023-04-05 | 2023-07-24 | Agree Implementation of Lift Lower Trials with Station | 27-Mar-23 A | 15-Jun-23 A | 75 | 0 | 53 | 100% |  | Completed
ER6666LT | W209 | W209.29360 | HYB Essential Defueling Safety Case |  |  | Step 3 - Draft Human Reliability Baseline Report EAN | 27-Mar-23 A | 21-Apr-23 A | 20 | 0 | 17 | 100% |  | Completed
ER6668LT | W213 | W213.29360 | TOR Essential Defueling Safety Case |  |  | Step 3 - Draft Human Reliability Baseline Report EAN | 27-Mar-23 A | 21-Apr-23 A | 20 | 0 | 17 | 100% |  | Completed
ER6666LT | W209 | W209.29220 | HYB Essential Defueling Safety Case |  |  | Verify Operator Claims Matrix | 27-Mar-23 A | 21-Apr-23 A | 9 | 0 | 18 | 100% |  | Completed
ER6668LT | W213 | W213.29220 | TOR Essential Defueling Safety Case |  |  | Verify Operator Claims Matrix | 27-Mar-23 A | 21-Apr-23 A | 9 | 0 | 18 | 100% |  | Completed
ER6371LT | W202 | W202.A2206600 | HRA Reactors Shutdown Essential Safety Cases | 2023-03-30 | 2023-03-30 | Hold Risk Workshop | 30-Mar-23 A | 30-Mar-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2206600 | HYA Reactors Shutdown Essential Safety Cases |  |  | Hold Risk Workshop | 30-Mar-23 A | 30-Mar-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A28240 | HYB Essential Defueling Safety Case |  | 2023-02-28 | CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN Available | 31-Mar-23 A | 31-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A28800 | HYB Essential Defueling Safety Case |  | 2022-12-13 | Fuel Free Verification methods, an assessment against the ALARP principle EAN Available | 31-Mar-23 A | 31-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A28240 | TOR Essential Defueling Safety Case |  | 2023-02-28 | CSP & Diagrid Dynamic Response & R6 Following Dropped FPU EAN Available | 31-Mar-23 A | 31-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A28800 | TOR Essential Defueling Safety Case |  | 2022-12-13 | Fuel Free Verification methods, an assessment against the ALARP principle EAN Available | 31-Mar-23 A | 31-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | 2430 | HRA Reactors Shutdown Essential Safety Cases | 2022-12-05 | 2022-12-06 | Stn RE Endorsed | 31-Mar-23 A | 26-May-23 A | 5 | 0 | 36 | 100% |  | Completed
ER6371LT | W202 | 2420 | HRA Reactors Shutdown Essential Safety Cases | 2022-12-05 | 2022-12-07 | CO Endorsed | 31-Mar-23 A | 26-May-23 A | 5 | 0 | 36 | 100% |  | Completed
ER6661LT | W206 | 2430 | HYA Reactors Shutdown Essential Safety Cases | 2022-12-05 | 2022-12-06 | Stn RE Endorsed | 31-Mar-23 A | 26-May-23 A | 5 | 0 | 36 | 100% |  | Completed
ER6661LT | W206 | 2420 | HYA Reactors Shutdown Essential Safety Cases | 2022-12-05 | 2022-12-07 | CO Endorsed | 31-Mar-23 A | 26-May-23 A | 5 | 0 | 36 | 100% |  | Completed
ER6371LT | W202 | W202.A2206610 | HRA Reactors Shutdown Essential Safety Cases | 2023-03-31 | 2023-03-31 | Complete Risk Log with Estimates | 31-Mar-23 A | 31-Mar-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2206610 | HYA Reactors Shutdown Essential Safety Cases |  |  | Complete Risk Log with Estimates | 31-Mar-23 A | 31-Mar-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A25760 | HYB Essential Defueling Safety Case |  | 2022-08-17 | Judgement Based Work Diversion EAN Available | 31-Mar-23 A | 31-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.8990 | HYB Essential Defueling Safety Case |  | 2023-01-23 | Discovery Milestone - FM Underload Veto - Drafted | 31-Mar-23 A | 31-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A28720 | HYB Essential Defueling Safety Case |  |  | CSP/Diagrid Structural Integrity Summary Report Available | 31-Mar-23 A | 31-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A25760 | TOR Essential Defueling Safety Case |  | 2022-08-17 | Judgement Based Work Diversion EAN Available | 31-Mar-23 A | 31-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.8990 | TOR Essential Defueling Safety Case |  | 2023-01-23 | Discovery Milestone - FM Underload Veto - Drafted | 31-Mar-23 A | 31-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A28720 | TOR Essential Defueling Safety Case |  |  | CSP/Diagrid Structural Integrity Summary Report Available | 31-Mar-23 A | 31-Mar-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3150 | HNB Enhanced Defuelling Safety Cases | 2023-06-08 | 2023-06-14 | Produce MF | 03-Apr-23 A | 11-Apr-23 A | 5 | 0 | 4 | 100% |  | Completed
ER6378LT | W222 | W222.3060 | HRA Fuel Handling Essential Safety Case | 2023-04-03 | 2023-04-28 | ETC (DD-PF) April 23 only | 03-Apr-23 A | 28-Apr-23 A | 18 | 0 | 17 | 100% |  | Completed
ER6650LT | W226 | W226.3060 | HYA Fuel Handling Essential Safety Case | 2023-04-03 | 2023-04-28 | ETC (April 23 Only) | 03-Apr-23 A | 28-Apr-23 A | 14 | 0 | 17 | 100% |  | Completed
ER6666LT | W209 | W209.29480 | HYB Essential Defueling Safety Case |  |  | Structural Integrity (SI) Justification - Liner & Penetrations - (Civils Follow-On Work) | 03-Apr-23 A | 19-May-23 A | 1 | 0 | 30 | 100% |  | Completed
ER6666LT | W209 | W209.A31270 | HYB Essential Defueling Safety Case |  |  | Draft PSA Documentation | 03-Apr-23 A | 15-Dec-23 A | 0 | 0 | 179 | 100% |  | Completed
ER6666LT | W209 | W209.A31330 | HYB Essential Defueling Safety Case |  |  | Fuelling Machine Purging Requirements During Defueling (Cost Summary) (Claim 5) | 03-Apr-23 A | 28-Jul-23 A | 187 | 0 | 79 | 100% |  | Completed
ER6666LT | W209 | W209.A31350 | HYB Essential Defueling Safety Case |  |  | Draft Fuelling Machine Purging Requirements During Defueling | 03-Apr-23 A | 14-Apr-23 A | 0 | 0 | 8 | 100% |  | Completed
ER6668LT | W213 | W213.29480 | TOR Essential Defueling Safety Case |  |  | Structural Integrity (SI) Justification - Liner & Penetrations - (Civils Follow-On Work) | 03-Apr-23 A | 19-May-23 A | 1 | 0 | 30 | 100% |  | Completed
ER6668LT | W213 | W213.A31270 | TOR Essential Defueling Safety Case |  |  | Draft PSA Documentation | 03-Apr-23 A | 15-Dec-23 A | 0 | 0 | 178 | 100% |  | Completed
ER6668LT | W213 | W213.A31330 | TOR Essential Defueling Safety Case |  |  | Fuelling Machine Purging Requirements During Defueling (Cost Summary) (Claim 5) | 03-Apr-23 A | 28-Jul-23 A | 187 | 0 | 79 | 100% |  | Completed
ER6668LT | W213 | W213.A31350 | TOR Essential Defueling Safety Case |  |  | Draft Fuelling Machine Purging Requirements During Defueling | 03-Apr-23 A | 14-Apr-23 A | 0 | 0 | 8 | 100% |  | Completed
ER6666LT | W209 | W209.A29030 | HYB Essential Defueling Safety Case | 2023-02-20 | 2023-02-24 | Complete TR Form and Upload Summary of Compliance with RADWASTE Assessment Principles EAN to CDMS | 03-Apr-23 A | 14-Apr-23 A | 8 | 0 | 8 | 100% |  | Completed
ER6371LT | W202 | W202.A2206580 | HRA Reactors Shutdown Essential Safety Cases | 2023-04-03 | 2023-04-03 | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 03-Apr-23 A | 03-Apr-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A2206590 | HRA Reactors Shutdown Essential Safety Cases | 2023-04-03 | 2023-04-03 | Ensure Alignment of Schedule & Estimate | 03-Apr-23 A | 03-Apr-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A2206710 | HRA Reactors Shutdown Essential Safety Cases | 2023-04-03 | 2023-04-04 | Workshop to agree scope, effort and links | 03-Apr-23 A | 04-Apr-23 A | 2 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | W206.A2206580 | HYA Reactors Shutdown Essential Safety Cases |  |  | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 03-Apr-23 A | 03-Apr-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2206590 | HYA Reactors Shutdown Essential Safety Cases |  |  | Ensure Alignment of Schedule & Estimate | 03-Apr-23 A | 03-Apr-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2206710 | HYA Reactors Shutdown Essential Safety Cases |  |  | Workshop to agree scope, effort and links | 03-Apr-23 A | 04-Apr-23 A | 2 | 0 | 2 | 100% |  | Completed
ER6372LT | W203 | W203.A3660 | HNB Enhanced Defuelling Safety Cases | 2023-06-08 | 2023-06-14 | Produce MF | 03-Apr-23 A | 11-Apr-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A29030 | TOR Essential Defueling Safety Case | 2023-02-20 | 2023-02-24 | Complete TR Form and Upload Summary of Compliance with RADWASTE Assessment Principles EAN to CDMS | 03-Apr-23 A | 14-Apr-23 A | 8 | 0 | 8 | 100% |  | Completed
W232LT | W232 | W232.A1260 | DNB Enhanced Safety Cases | 2023-03-15 | 2023-03-28 | Verify supporting reference <PSA Sensitivity Study> | 04-Apr-23 A | 07-Apr-23 A | 10 | 0 | 3 | 100% |  | Completed
W232LT | W232 | W232.A1230 | DNB Enhanced Safety Cases | 2023-04-12 | 2023-04-24 | FEGO / TOG Stakeholder Mgmt | 04-Apr-23 A | 11-Apr-23 A | 9 | 0 | 4 | 100% |  | Completed
ER6371LT | W202 | W202.A2206620 | HRA Reactors Shutdown Essential Safety Cases | 2023-04-04 | 2023-04-04 | Update Schedule/Estimate from Risk Log & Add Provisions | 04-Apr-23 A | 04-Apr-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2206620 | HYA Reactors Shutdown Essential Safety Cases |  |  | Update Schedule/Estimate from Risk Log & Add Provisions | 04-Apr-23 A | 04-Apr-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A2206630 | HRA Reactors Shutdown Essential Safety Cases | 2023-04-05 | 2023-04-05 | Add Data to IAB Paper | 05-Apr-23 A | 05-Apr-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2206630 | HYA Reactors Shutdown Essential Safety Cases |  |  | Add Data to IAB Paper | 05-Apr-23 A | 05-Apr-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A2206640 | HRA Reactors Shutdown Essential Safety Cases | 2023-04-06 | 2023-04-06 | PCL Validate & Approve Baseline Package for PRC Submission | 06-Apr-23 A | 06-Apr-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2206640 | HYA Reactors Shutdown Essential Safety Cases |  |  | PCL Validate & Approve Baseline Package for PRC Submission | 06-Apr-23 A | 06-Apr-23 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A1430 | DNB Enhanced Safety Cases | 2023-03-29 | 2023-04-13 | EDF Technical review of supporting reference <PSA Sensitivity Study> | 10-Apr-23 A | 12-Apr-23 A | 10 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A3330 | HNB Enhanced Defuelling Safety Cases |  | 2023-06-14 | Issue MF | 11-Apr-23 A | 11-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3380 | HNB Enhanced Defuelling Safety Cases |  | 2023-06-14 | CO & CA appointed | 11-Apr-23 A | 11-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A29250 | HYB Essential Defueling Safety Case | 2023-02-08 | 2023-03-07 | Technical Review of Defuelling Hazards Review EAN | 11-Apr-23 A | 14-Apr-23 A | 20 | 0 | 4 | 100% |  | Completed
ER6668LT | W213 | W213.A29250 | TOR Essential Defueling Safety Case | 2023-02-08 | 2023-03-07 | Technical Review of Defuelling Hazards Review EAN | 11-Apr-23 A | 14-Apr-23 A | 20 | 0 | 4 | 100% |  | Completed
ER6372LT | W203 | W203.A3840 | HNB Enhanced Defuelling Safety Cases |  | 2023-06-14 | Issue MF | 11-Apr-23 A | 11-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3890 | HNB Enhanced Defuelling Safety Cases |  | 2023-06-14 | CO & CA appointed | 11-Apr-23 A | 11-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3210 | HNB Enhanced Defuelling Safety Cases | 2023-06-08 | 2023-06-14 | Hold project kick start meeting with Station & key suppliers | 12-Apr-23 A | 18-Apr-23 A | 5 | 0 | 4 | 100% |  | Completed
ER6372LT | W203 | W203.A3480 | HNB Enhanced Defuelling Safety Cases | 2023-06-15 | 2023-06-21 | Identify verifier for the case & establish all other resources | 12-Apr-23 A | 18-Apr-23 A | 5 | 0 | 4 | 100% |  | Completed
ER6666LT | W209 | W209.A24800 | HYB Essential Defueling Safety Case | 2022-10-03 | 2022-10-28 | Verify Human Factors Assessment of Misloading / Mis-Defueling Faults EAN & Issue | 12-Apr-23 A | 16-Jun-23 A | 14 | 0 | 45 | 100% |  | Completed
ER6371LT | W202 | W202.A2206550 | HRA Reactors Shutdown Essential Safety Cases |  | 2023-04-12 | Gate C+ PRC Paper Submission | 12-Apr-23 A | 12-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206670 | HRA Reactors Shutdown Essential Safety Cases | 2023-04-12 | 2023-04-17 | PRC Members Review PRC Documentation | 12-Apr-23 A | 17-Apr-23 A | 4 | 0 | 4 | 100% |  | Completed
ER6661LT | W206 | W206.A2206550 | HYA Reactors Shutdown Essential Safety Cases |  |  | Gate C+ PRC Paper Submission | 12-Apr-23 A | 12-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206670 | HYA Reactors Shutdown Essential Safety Cases |  |  | PRC Members Review PRC Documentation | 12-Apr-23 A | 17-Apr-23 A | 4 | 0 | 4 | 100% |  | Completed
ER6372LT | W203 | W203.A3720 | HNB Enhanced Defuelling Safety Cases | 2023-06-08 | 2023-06-14 | Hold project kick start meeting with Station & key suppliers | 12-Apr-23 A | 18-Apr-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6372LT | W203 | W203.A3990 | HNB Enhanced Defuelling Safety Cases | 2023-06-15 | 2023-06-21 | Identify verifier for the case & establish all other resources | 12-Apr-23 A | 18-Apr-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A24800 | TOR Essential Defueling Safety Case | 2022-10-03 | 2022-10-28 | Verify Human Factors Assessment of Misloading / Mis-Defueling Faults EAN & Issue | 12-Apr-23 A | 16-Jun-23 A | 14 | 0 | 45 | 100% |  | Completed
W232LT | W232 | W232.A1480 | DNB Enhanced Safety Cases |  | 2023-04-13 | Supporting reference <PSA Sensitivity Study> approved | 14-Apr-23 A | 14-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.28900 | HYB Essential Defueling Safety Case |  |  | Discover Milestone - Review need for Further HF Assessment | 14-Apr-23 A | 14-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.2020 | DNB Enhanced Safety Cases |  |  | >>>OUTGOING ENABLER PSA Sensitivity Study Complete | 14-Apr-23 A | 14-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.28900 | TOR Essential Defueling Safety Case |  |  | Discover Milestone - Review need for Further HF Assessment | 14-Apr-23 A | 14-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A29040 | HYB Essential Defueling Safety Case |  | 2023-02-24 | Summary of Compliance with RADWASTE Assessment Principles EAN Available | 14-Apr-23 A | 14-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A29040 | TOR Essential Defueling Safety Case |  | 2023-02-24 | Summary of Compliance with RADWASTE Assessment Principles EAN Available | 14-Apr-23 A | 14-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2740 | DNB Enhanced Safety Cases | 2023-03-15 | 2023-03-28 | Verify supporting reference <Maintenance Review of FR Plant> | 17-Apr-23 A | 23-May-23 A | 10 | 0 | 25 | 100% |  | Completed
ER6666LT | W209 | W209.A29260 | HYB Essential Defueling Safety Case | 2023-03-08 | 2023-03-14 | Supplier Update and Issue Defuelling Hazards Review EAN | 17-Apr-23 A | 20-Jul-23 A | 5 | 0 | 66 | 100% |  | Completed
ER6666LT | W209 | W209.A29980 | HYB Essential Defueling Safety Case | 2023-03-07 | 2023-05-18 | Technical Review of FM Underload Protection Mods Prelim Design (GLM) | 17-Apr-23 A | 10-May-23 A | 16 | 0 | 16 | 100% |  | Completed
ER6666LT | W209 | W209.A31360 | HYB Essential Defueling Safety Case |  |  | Verify Fuelling Machine Purging Requirements During Defueling | 17-Apr-23 A | 21-Jul-23 A | 32 | 0 | 67 | 100% |  | Completed
ER6668LT | W213 | W213.A29260 | TOR Essential Defueling Safety Case | 2023-03-08 | 2023-03-14 | Supplier Update and Issue Defuelling Hazards Review EAN | 17-Apr-23 A | 20-Jul-23 A | 5 | 0 | 66 | 100% |  | Completed
ER6668LT | W213 | W213.A29980 | TOR Essential Defueling Safety Case | 2023-03-07 | 2023-05-18 | Technical Review of FM Underload Protection Mods Prelim Design (GLM) | 17-Apr-23 A | 10-May-23 A | 16 | 0 | 16 | 100% |  | Completed
ER6668LT | W213 | W213.A31360 | TOR Essential Defueling Safety Case |  |  | Verify Fuelling Machine Purging Requirements During Defueling | 17-Apr-23 A | 21-Jul-23 A | 32 | 0 | 67 | 100% |  | Completed
ER6666LT | W209 | W209.7360 | HYB Essential Defueling Safety Case | 2023-04-05 | 2023-05-05 | Case Officer Tech Lead Review Claim 6 and Address Comments | 18-Apr-23 A | 13-Jun-23 A | 20 | 0 | 38 | 100% |  | Completed
ER6668LT | W213 | W213.7360 | TOR Essential Defueling Safety Case | 2023-04-05 | 2023-05-05 | Case Officer Tech Lead Review Claim 6 and Address Comments | 18-Apr-23 A | 13-Jun-23 A | 20 | 0 | 38 | 100% |  | Completed
ER6372LT | W203 | W203.A3450 | HNB Enhanced Defuelling Safety Cases | 2023-06-22 |  | Categorisation by station | 19-Apr-23 A | 19-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3960 | HNB Enhanced Defuelling Safety Cases | 2023-06-22 |  | Categorisation by station | 19-Apr-23 A | 19-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3220 | HNB Enhanced Defuelling Safety Cases | 2023-06-01 | 2023-06-07 | Agree resource & timescales with suppliers for delivering key refs, incl contingency, risk & allowance for rework | 20-Apr-23 A | 20-Apr-23 A | 5 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3730 | HNB Enhanced Defuelling Safety Cases | 2023-06-01 | 2023-06-07 | Agree resource & timescales with suppliers for delivering key refs, incl contingency, risk & allowance for rework | 20-Apr-23 A | 20-Apr-23 A | 5 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 1955 | HYA Fuel Handling Essential Safety Case |  |  | Final Update of Head Document (Needs PSA Numbers and Verified Draft FDD **ACTION** Review Predecsessors ie 5 key Docs) | 20-Apr-23 A | 22-Nov-23 A | 20 | 0 | 151 | 100% |  | Completed
ER6666LT | W209 | W209.A30970 | HYB Essential Defueling Safety Case |  |  | Technical Review of Channel X | 21-Apr-23 A | 22-May-23 A | 30 | 0 | 19 | 100% |  | Completed
W232LT | W232 | W232.A2930 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727> Discovery Milestone: Moisture Detection Capability | 21-Apr-23 A | 21-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A30970 | TOR Essential Defueling Safety Case |  |  | Technical Review of Channel X | 21-Apr-23 A | 22-May-23 A | 30 | 0 | 19 | 100% |  | Completed
W232LT | W232 | W232.B6620 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Summary | 21-Apr-23 A | 21-Apr-23 A | 69 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6630 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Summary | 21-Apr-23 A | 21-Apr-23 A | 10 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6640 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Approve Task Sheet | 21-Apr-23 A | 21-Apr-23 A | 2 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6650 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Pre Job Brief | 21-Apr-23 A | 21-Apr-23 A | 2 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6660 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Draft and issue Task Sheet | 21-Apr-23 A | 21-Apr-23 A | 10 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6670 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Prepare Draft EAN | 21-Apr-23 A | 21-Apr-23 A | 20 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6690 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Draft EAN Reviewed by EDF SQEP | 21-Apr-23 A | 21-Apr-23 A | 10 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6700 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Address Comments from EDF Review on Draft EAN | 21-Apr-23 A | 21-Apr-23 A | 10 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6720 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727> Moisture Detection Capability - EAN Completed and Uploaded to CDMS | 21-Apr-23 A | 21-Apr-23 A | 10 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6740 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727> Moisture Detection Capability - TSA Internal Review of Draft EAN | 21-Apr-23 A | 21-Apr-23 A | 5 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A25920 | HYB Essential Defueling Safety Case |  | 2022-11-16 | Safety Case Requirements EAN - TASK E EAN Available | 21-Apr-23 A | 21-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A26800 | HYB Essential Defueling Safety Case |  | 2023-01-03 | Boron Bead Injection Feasibility & Control Rod Isolation EAN Available | 21-Apr-23 A | 21-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B6680 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Issue Draft EAN to EDF for Review. | 21-Apr-23 A | 21-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B6710 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727> Moisture Detection Capability - Issue Final EAN | 21-Apr-23 A | 21-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B6730 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727> Moisture Detection Capability - EAN Completed | 21-Apr-23 A | 21-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A25920 | TOR Essential Defueling Safety Case |  | 2022-11-16 | Safety Case Requirements EAN - TASK E EAN Available | 21-Apr-23 A | 21-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A26800 | TOR Essential Defueling Safety Case |  | 2023-01-03 | Boron Bead Injection Feasibility & Control Rod Isolation EAN Available | 21-Apr-23 A | 21-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A24590 | HYB Essential Defueling Safety Case | 2022-09-28 | 2022-10-25 | Verify Human Reliability Baseline Report EAN & Issue for Technical Review | 24-Apr-23 A | 03-Jul-23 A | 15 | 0 | 48 | 100% |  | Completed
ER6372LT | W203 | W203.A3620 | HNB Enhanced Defuelling Safety Cases | 2023-06-15 | 2023-07-12 | Produce supporting reference <Purge and Pressurisation> | 24-Apr-23 A | 19-May-23 A | 20 | 0 | 18 | 100% |  | Completed
ER6372LT | W203 | W203.A4130 | HNB Enhanced Defuelling Safety Cases | 2023-06-15 | 2023-07-12 | Produce supporting reference <IFD Deluge> | 24-Apr-23 A | 09-Jun-23 A | 10 | 0 | 31 | 100% |  | Completed
ER6372LT | W203 | W203.B1030 | HNB Enhanced Defuelling Safety Cases | 2023-06-15 | 2023-07-12 | Produce supporting reference <Dropped Fuel Consequences EAN> | 24-Apr-23 A | 26-May-23 A | 20 | 0 | 22 | 100% |  | Completed
ER6668LT | W213 | W213.A24590 | TOR Essential Defueling Safety Case | 2022-09-28 | 2022-10-25 | Verify Human Reliability Baseline Report EAN & Issue for Technical Review | 24-Apr-23 A | 03-Jul-23 A | 15 | 0 | 48 | 100% |  | Completed
ER6666LT | W209 | W209.28980 | HYB Essential Defueling Safety Case |  |  | Decision Milestone on Boron Bead Injection | 25-Apr-23 A | 25-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A27290 | HRA Fuel Handling Essential Safety Case | 2023-04-25 | 2023-04-25 | Revise Project Definition Document (PDD) | 25-Apr-23 A | 25-Apr-23 A | 5 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A27380 | HRA Fuel Handling Essential Safety Case | 2023-04-25 | 2023-04-25 | Hold Risk Workshop | 25-Apr-23 A | 25-Apr-23 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A27400 | HRA Fuel Handling Essential Safety Case | 2023-04-25 | 2023-05-02 | Estimate Scope +/- 10% Lifecycle | 25-Apr-23 A | 02-May-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A27410 | HRA Fuel Handling Essential Safety Case | 2023-04-25 | 2023-05-02 | Plan Scope in Primavera Level 2 Lifecycle) | 25-Apr-23 A | 02-May-23 A | 1 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A27290 | HYA Fuel Handling Essential Safety Case | 2023-04-25 | 2023-04-25 | Revise Project Definition Document (PDD) | 25-Apr-23 A | 25-Apr-23 A | 5 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27380 | HYA Fuel Handling Essential Safety Case | 2023-04-25 | 2023-04-25 | Hold Risk Workshop | 25-Apr-23 A | 25-Apr-23 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27400 | HYA Fuel Handling Essential Safety Case | 2023-04-25 | 2023-05-02 | Estimate Scope +/- 10% Lifecycle | 25-Apr-23 A | 02-May-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A27410 | HYA Fuel Handling Essential Safety Case | 2023-04-25 | 2023-05-02 | Plan Scope in Primavera Level 2 Lifecycle) | 25-Apr-23 A | 02-May-23 A | 1 | 0 | 5 | 100% |  | Completed
ER6372LT | W203 | W203.A3340 | HNB Enhanced Defuelling Safety Cases |  | 2023-06-28 | INSA agree MF and Identify INSA Resource (KDM) | 25-Apr-23 A | 25-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3540 | HNB Enhanced Defuelling Safety Cases |  | 2023-06-28 | INSA Approval Date Identified | 25-Apr-23 A | 25-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3550 | HNB Enhanced Defuelling Safety Cases |  | 2023-06-28 | Provide Provisional NSC Date | 25-Apr-23 A | 25-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.28980 | TOR Essential Defueling Safety Case |  |  | Decision Milestone on Boron Bead Injection | 25-Apr-23 A | 25-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206660 | HRA Reactors Shutdown Essential Safety Cases | 2023-04-25 | 2023-04-25 | Hold PRC Meeting | 25-Apr-23 A | 25-Apr-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | W206.A2206660 | HYA Reactors Shutdown Essential Safety Cases |  |  | Hold PRC Meeting | 25-Apr-23 A | 25-Apr-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A2206680 | HRA Reactors Shutdown Essential Safety Cases |  | 2023-04-25 | Gate C+ PRC Paper Approval | 25-Apr-23 A | 25-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206680 | HYA Reactors Shutdown Essential Safety Cases |  |  | Gate C+ PRC Paper Approval | 25-Apr-23 A | 25-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206730 | HRA Reactors Shutdown Essential Safety Cases |  | 2023-04-25 | Gate C+ PRC Paper Approval | 25-Apr-23 A | 25-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206730 | HYA Reactors Shutdown Essential Safety Cases |  |  | Gate C+ PRC Paper Approval | 25-Apr-23 A | 25-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3850 | HNB Enhanced Defuelling Safety Cases |  | 2023-06-28 | INSA agree MF and Identify INSA Resource (KDM) - <IFD Deluge> | 25-Apr-23 A | 25-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A4050 | HNB Enhanced Defuelling Safety Cases |  | 2023-06-28 | INSA Approval Date Identified | 25-Apr-23 A | 25-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A4060 | HNB Enhanced Defuelling Safety Cases |  | 2023-06-28 | Provide Provisional NSC Date | 25-Apr-23 A | 25-Apr-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5205 | HRA Reactors Shutdown Essential Safety Cases | 2023-04-11 | 2023-10-05 | SC - Safety Case development - INSA - HRA - C-D - INSA | 26-Apr-23 A | 02-Oct-24 A | 124 | 0 | 364 | 100% |  | Completed
ER6661LT | W206 | W206.A5205 | HYA Reactors Shutdown Essential Safety Cases | 2023-04-11 | 2023-10-05 | SC - Safety Case development - INSA - HYA - C-D - INSA | 26-Apr-23 A | 10-Oct-24 A | 124 | 0 | 369 | 100% |  | Completed
ER6371LT | W202 | W202.A5255 | HRA Reactors Shutdown Essential Safety Cases | 2023-04-11 | 2023-05-17 | INSA review & iteration of comments (using BARRIER MODEL) (HRA) (Resumed after Event Recovery) | 26-Apr-23 A | 31-Jul-23 A | 25 | 0 | 65 | 100% |  | Completed
ER6661LT | W206 | W206.A5255 | HYA Reactors Shutdown Essential Safety Cases | 2023-04-11 | 2023-05-17 | INSA review & iteration of comments (using BARRIER MODEL) (HYA) (Resumed after Event Recovery) | 26-Apr-23 A | 31-Jul-23 A | 25 | 0 | 65 | 100% |  | Completed
ER6372LT | W203 | W203.A3160 | HNB Enhanced Defuelling Safety Cases | 2023-06-29 | 2023-07-12 | Produce draft NSRS (using BARRIER MODEL) | 26-Apr-23 A | 31-May-23 A | 10 | 0 | 22 | 100% |  | Completed
ER6666LT | W209 | W209.A27110 | HYB Essential Defueling Safety Case | 2022-11-02 | 2022-11-08 | Complete TR Form and Upload FPU Integrity Analysis EAN to CDMS | 26-Apr-23 A | 12-May-23 A | 5 | 0 | 10 | 100% |  | Completed
ER6372LT | W203 | W203.A3670 | HNB Enhanced Defuelling Safety Cases | 2023-06-29 | 2023-07-12 | Produce draft NSRS (using BARRIER MODEL) | 26-Apr-23 A | 31-Jul-23 A | 15 | 0 | 65 | 100% |  | Completed
ER6668LT | W213 | W213.A27110 | TOR Essential Defueling Safety Case | 2022-11-02 | 2022-11-08 | Complete TR Form and Upload FPU Integrity Analysis EAN to CDMS | 26-Apr-23 A | 12-May-23 A | 5 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.25900 | HYB Essential Defueling Safety Case | 2023-04-28 | 2023-07-21 | Verify Human Reliability Assessment of Unsubstantiated Claims EAN & Issue for Technical Review | 28-Apr-23 A | 28-Jul-23 A | 15 | 0 | 63 | 100% |  | Completed
ER6668LT | W213 | W213.25900 | TOR Essential Defueling Safety Case | 2023-04-28 | 2023-07-21 | Verify Human Reliability Assessment of Unsubstantiated Claims EAN & Issue for Technical Review | 28-Apr-23 A | 28-Jul-23 A | 15 | 0 | 63 | 100% |  | Completed
ER6666LT | W209 | W209.7020 | HYB Essential Defueling Safety Case | 2023-07-04 | 2023-08-31 | Update Claim 2 | 01-May-23 A | 27-Oct-23 A | 9 | 0 | 126 | 100% |  | Completed
ER6668LT | W213 | W213.7020 | TOR Essential Defueling Safety Case | 2023-07-04 | 2023-08-31 | Update Claim 2 | 01-May-23 A | 27-Oct-23 A | 9 | 0 | 125 | 100% |  | Completed
ER6666LT | W209 | W209.29510 | HYB Essential Defueling Safety Case |  |  | PVCS Draindown Volume Calc Note - EAN Available | 02-May-23 A | 10-Jan-24 A | 1 | 0 | 175 | 100% |  | Completed
ER6668LT | W213 | W213.29510 | TOR Essential Defueling Safety Case |  |  | PVCS Draindown Volume Calc Note - EAN Available | 02-May-23 A | 10-Jan-24 A | 1 | 0 | 175 | 100% |  | Completed
ER6666LT | W209 | W209.A24640 | HYB Essential Defueling Safety Case | 2022-12-07 | 2022-12-07 | Pre Job Brief for Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN | 02-May-23 A | 02-May-23 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6500 | DNB Enhanced Safety Cases | 2023-04-12 | 2023-05-02 | Core Support Plate Structural Integrity Criticality - Summary | 02-May-23 A | 23-Jun-23 A | 30 | 0 | 36 | 100% |  | Completed
W232LT | W232 | W232.B6530 | DNB Enhanced Safety Cases | 2023-04-12 | 2023-04-25 | Core Support Plate Structural Integrity Criticality - Draft and issue Task Sheet | 02-May-23 A | 31-May-23 A | 10 | 0 | 19 | 100% |  | Completed
ER6668LT | W213 | W213.A24640 | TOR Essential Defueling Safety Case | 2022-12-07 | 2022-12-07 | Pre Job Brief for Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN | 02-May-23 A | 02-May-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A24650 | HYB Essential Defueling Safety Case | 2022-12-08 | 2023-02-06 | Draft Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN | 03-May-23 A | 03-May-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A30600 | HYB Essential Defueling Safety Case | 2022-07-13 | 2022-11-30 | Draft FM Direct Process Protection Design | 03-May-23 A | 24-May-23 A | 68 | 0 | 14 | 100% |  | Completed
ER6378LT | W222 | W222.A27390 | HRA Fuel Handling Essential Safety Case | 2023-05-03 | 2023-05-03 | Ensure Alignment of Schedule & Estimate | 03-May-23 A | 03-May-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A27390 | HYA Fuel Handling Essential Safety Case | 2023-05-03 | 2023-05-03 | Ensure Alignment of Schedule & Estimate | 03-May-23 A | 03-May-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A24650 | TOR Essential Defueling Safety Case | 2022-12-08 | 2023-02-06 | Draft Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN | 03-May-23 A | 03-May-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A30600 | TOR Essential Defueling Safety Case | 2022-07-13 | 2022-11-30 | Draft FM Direct Process Protection Design | 03-May-23 A | 24-May-23 A | 68 | 0 | 14 | 100% |  | Completed
ER6666LT | W209 | W209.A31390 | HYB Essential Defueling Safety Case |  |  | Pre Job Brief for Stress Modelling | 04-May-23 A | 04-May-23 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A31390 | TOR Essential Defueling Safety Case |  |  | Pre Job Brief for Stress Modelling | 04-May-23 A | 04-May-23 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A24660 | HYB Essential Defueling Safety Case | 2023-02-07 | 2023-02-27 | Verify Human Reliability Assessment of New and/or Modified Human Based Safety Claims & Issue for Technical Review | 04-May-23 A | 04-May-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A27370 | HRA Fuel Handling Essential Safety Case | 2023-05-04 | 2023-05-04 | Complete Risk Log with Estimates | 04-May-23 A | 04-May-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A27370 | HYA Fuel Handling Essential Safety Case | 2023-05-04 | 2023-05-04 | Complete Risk Log with Estimates | 04-May-23 A | 04-May-23 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2490 | DNB Enhanced Safety Cases |  |  | Structural Integrity TOG Engagement | 04-May-23 A | 04-May-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A24660 | TOR Essential Defueling Safety Case | 2023-02-07 | 2023-02-27 | Verify Human Reliability Assessment of New and/or Modified Human Based Safety Claims & Issue for Technical Review | 04-May-23 A | 04-May-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A31400 | HYB Essential Defueling Safety Case |  |  | Draft Review of Stress Modelling EAN | 05-May-23 A | 24-May-23 A | 0 | 0 | 12 | 100% |  | Completed
ER6668LT | W213 | W213.A31400 | TOR Essential Defueling Safety Case |  |  | Draft Review of Stress Modelling EAN | 05-May-23 A | 24-May-23 A | 0 | 0 | 12 | 100% |  | Completed
ER6666LT | W209 | W209.A24670 | HYB Essential Defueling Safety Case | 2023-02-28 | 2023-03-13 | Technical Review of Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN | 05-May-23 A | 05-May-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A27360 | HRA Fuel Handling Essential Safety Case | 2023-05-05 | 2023-05-05 | Update Schedule/Estimate from Risk Log & Add Provisions | 05-May-23 A | 05-May-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A27360 | HYA Fuel Handling Essential Safety Case | 2023-05-05 | 2023-05-05 | Update Schedule/Estimate from Risk Log & Add Provisions | 05-May-23 A | 05-May-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A24670 | TOR Essential Defueling Safety Case | 2023-02-28 | 2023-03-13 | Technical Review of Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN | 05-May-23 A | 05-May-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A24680 | HYB Essential Defueling Safety Case | 2023-03-14 | 2023-03-27 | Supplier Update and Issue Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN | 09-May-23 A | 09-May-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A27350 | HRA Fuel Handling Essential Safety Case | 2023-05-09 | 2023-05-09 | Add Data to PRC Paper | 09-May-23 A | 09-May-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A27350 | HYA Fuel Handling Essential Safety Case | 2023-05-09 | 2023-05-09 | Add Data to PRC Paper | 09-May-23 A | 09-May-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A24680 | TOR Essential Defueling Safety Case | 2023-03-14 | 2023-03-27 | Supplier Update and Issue Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN | 09-May-23 A | 09-May-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A24690 | HYB Essential Defueling Safety Case | 2023-03-28 | 2023-04-03 | Complete Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN to CDMS | 10-May-23 A | 10-May-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A27340 | HRA Fuel Handling Essential Safety Case | 2023-05-10 | 2023-05-10 | PCL Validate & Approve Baseline Package for PRC Submission | 10-May-23 A | 10-May-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A27340 | HYA Fuel Handling Essential Safety Case | 2023-05-10 | 2023-05-10 | PCL Validate & Approve Baseline Package for PRC Submission | 10-May-23 A | 10-May-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A24690 | TOR Essential Defueling Safety Case | 2023-03-28 | 2023-04-03 | Complete Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN to CDMS | 10-May-23 A | 10-May-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A24700 | HYB Essential Defueling Safety Case |  | 2023-04-03 | Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN Available | 10-May-23 A | 10-May-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A27420 | HRA Fuel Handling Essential Safety Case |  | 2023-05-10 | Issue PRC Paper to R4 PRC Members | 10-May-23 A | 10-May-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27420 | HYA Fuel Handling Essential Safety Case |  | 2023-05-10 | Issue PRC Paper to R4 PRC Members | 10-May-23 A | 10-May-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A24700 | TOR Essential Defueling Safety Case |  | 2023-04-03 | Human Reliability Assessment of New and/or Modified Human Based Safety Claims EAN Available | 10-May-23 A | 10-May-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A29990 | HYB Essential Defueling Safety Case | 2023-05-19 | 2023-05-25 | Supplier Update and Issue FM Underload Protection Mods Prelim Design (GLM) | 11-May-23 A | 17-May-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A27330 | HRA Fuel Handling Essential Safety Case | 2023-05-11 | 2023-05-17 | PRC Members Review PRC Documentation | 11-May-23 A | 17-May-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A27335 | HYA Fuel Handling Essential Safety Case | 2023-05-11 | 2023-05-17 | PRC Members Review PRC Documentation | 11-May-23 A | 17-May-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A29990 | TOR Essential Defueling Safety Case | 2023-05-19 | 2023-05-25 | Supplier Update and Issue FM Underload Protection Mods Prelim Design (GLM) | 11-May-23 A | 17-May-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.A27120 | HYB Essential Defueling Safety Case |  | 2022-11-08 | FPU Integrity Analysis EAN Available | 12-May-23 A | 12-May-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A27120 | TOR Essential Defueling Safety Case |  | 2022-11-08 | FPU Integrity Analysis EAN Available | 12-May-23 A | 12-May-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A29630 | HYB Essential Defueling Safety Case |  | 2023-02-24 | TASK F Review of the Discharge Limits (Permits) EAN Available | 12-May-23 A | 12-May-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A29630 | TOR Essential Defueling Safety Case |  | 2023-02-24 | TASK F Review of the Discharge Limits (Permits) EAN Available | 12-May-23 A | 12-May-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A4960 | DNB Enhanced Safety Cases |  |  | Discovery Milestone: What Further Supporting Work Do We Require? | 15-May-23 A | 15-May-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.29500 | HYB Essential Defueling Safety Case |  |  | Fuel Plug Unit Thermal Shield Performance During Defuelling - EAN Available | 17-May-23 A | 15-Jun-23 A | 1 | 0 | 21 | 100% |  | Completed
ER6668LT | W213 | W213.29500 | TOR Essential Defueling Safety Case |  |  | Fuel Plug Unit Thermal Shield Performance During Defuelling - EAN Available | 17-May-23 A | 15-Jun-23 A | 1 | 0 | 21 | 100% |  | Completed
ER6666LT | W209 | W209.A30000 | HYB Essential Defueling Safety Case | 2023-05-26 | 2023-06-02 | Complete TR Form and Upload FM Underload Protection Mods Prelim Design (GLM) to CDMS | 18-May-23 A | 19-May-23 A | 5 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.A30000 | TOR Essential Defueling Safety Case | 2023-05-26 | 2023-06-02 | Complete TR Form and Upload FM Underload Protection Mods Prelim Design (GLM) to CDMS | 18-May-23 A | 19-May-23 A | 5 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A29770 | HYB Essential Defueling Safety Case |  | 2022-10-28 | ALARP Review of Not Draining the PVCS (Report) Available | 19-May-23 A | 19-May-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A30010 | HYB Essential Defueling Safety Case |  | 2023-06-02 | FM Underload Protection Mods Prelim Design (GLM) Available | 19-May-23 A | 19-May-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A29770 | TOR Essential Defueling Safety Case |  | 2022-10-28 | ALARP Review of Not Draining the PVCS (Report) Available | 19-May-23 A | 19-May-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A30010 | TOR Essential Defueling Safety Case |  | 2023-06-02 | FM Underload Protection Mods Prelim Design (GLM) Available | 19-May-23 A | 19-May-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A30980 | HYB Essential Defueling Safety Case |  |  | Supplier Update and Issue Channel X | 22-May-23 A | 22-May-23 A | 5 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A30990 | HYB Essential Defueling Safety Case |  |  | Complete TR Form and Upload Channel X to CDMS | 22-May-23 A | 31-May-23 A | 5 | 0 | 6 | 100% |  | Completed
ER6668LT | W213 | W213.A30980 | TOR Essential Defueling Safety Case |  |  | Supplier Update and Issue Channel X | 22-May-23 A | 22-May-23 A | 5 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A30990 | TOR Essential Defueling Safety Case |  |  | Complete TR Form and Upload Channel X to CDMS | 22-May-23 A | 31-May-23 A | 5 | 0 | 6 | 100% |  | Completed
ER6372LT | W203 | W203.A3610 | HNB Enhanced Defuelling Safety Cases | 2023-07-13 | 2023-07-26 | Verify supporting reference <Purge and Pressurisation> | 22-May-23 A | 24-May-23 A | 3 | 0 | 3 | 100% |  | Completed
ER6378LT | W222 | W222.A27430 | HRA Fuel Handling Essential Safety Case |  | 2023-05-23 | Gate C+ for Region 1 - HRA Defuelling Fuel Handling Essential Safety Case | 23-May-23 A | 23-May-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W222.A27430 | HYA Fuel Handling Essential Safety Case |  | 2023-05-23 | Gate C+ for Region 1 - HYA Defuelling Fuel Handling Essential Safety Case | 23-May-23 A | 23-May-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A27320 | HRA Fuel Handling Essential Safety Case | 2023-05-23 | 2023-05-23 | Hold R4 PRC Meeting | 23-May-23 A | 23-May-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A27325 | HYA Fuel Handling Essential Safety Case | 2023-05-23 | 2023-05-23 | Hold R4 PRC Meeting | 23-May-23 A | 23-May-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A30610 | HYB Essential Defueling Safety Case | 2022-12-01 | 2023-01-30 | Verify FM Direct Process Protection Design & Issue for Technic | 24-May-23 A | 24-May-23 A | 40 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A30620 | HYB Essential Defueling Safety Case | 2023-01-31 | 2023-03-13 | Technical Review of FM Direct Process Protection Design | 24-May-23 A | 24-May-23 A | 30 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A30630 | HYB Essential Defueling Safety Case | 2023-03-14 | 2023-04-12 | Supplier Update and Issue FM Direct Process Protection Design | 24-May-23 A | 24-May-23 A | 15 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A30640 | HYB Essential Defueling Safety Case | 2023-04-13 | 2023-04-19 | Complete TR Form and Upload FM Direct Process Protection Design | 24-May-23 A | 24-May-23 A | 5 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A30650 | HYB Essential Defueling Safety Case |  | 2023-04-19 | FM Direct Process Protection Design Available | 24-May-23 A | 24-May-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.9010 | HYB Essential Defueling Safety Case |  | 2022-11-30 | Discovery Milestone - FM Direct Process Protection Design - Drafted | 24-May-23 A | 24-May-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A30610 | TOR Essential Defueling Safety Case | 2022-12-01 | 2023-01-30 | Verify FM Direct Process Protection Design & Issue for Technic | 24-May-23 A | 24-May-23 A | 40 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A30620 | TOR Essential Defueling Safety Case | 2023-01-31 | 2023-03-13 | Technical Review of FM Direct Process Protection Design | 24-May-23 A | 24-May-23 A | 30 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A30630 | TOR Essential Defueling Safety Case | 2023-03-14 | 2023-04-12 | Supplier Update and Issue FM Direct Process Protection Design | 24-May-23 A | 24-May-23 A | 15 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A30640 | TOR Essential Defueling Safety Case | 2023-04-13 | 2023-04-19 | Complete TR Form and Upload FM Direct Process Protection Design | 24-May-23 A | 24-May-23 A | 5 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A30650 | TOR Essential Defueling Safety Case |  | 2023-04-19 | FM Direct Process Protection Design Available | 24-May-23 A | 24-May-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.9010 | TOR Essential Defueling Safety Case |  | 2022-11-30 | Discovery Milestone - FM Direct Process Protection Design - Drafted | 24-May-23 A | 24-May-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2750 | DNB Enhanced Safety Cases | 2023-03-29 | 2023-04-13 | EDF Technical review of supporting reference <Maintenance Review of FR Plant> | 24-May-23 A | 30-Jun-23 A | 10 | 0 | 26 | 100% |  | Completed
ER6378LT | W222 | W222.A27310 | HRA Fuel Handling Essential Safety Case | 2023-05-24 | 2023-05-25 | Modify Estimate, Schedule & Risk Log as Required | 24-May-23 A | 25-May-23 A | 2 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | W226.A27315 | HYA Fuel Handling Essential Safety Case | 2023-05-24 | 2023-05-25 | Modify Estimate, Schedule & Risk Log as Required | 24-May-23 A | 25-May-23 A | 2 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.A31410 | HYB Essential Defueling Safety Case |  |  | Verify Review of Stress Modelling EAN & Issue for Technical Review | 25-May-23 A | 30-Jun-23 A | 0 | 0 | 25 | 100% |  | Completed
ER6668LT | W213 | W213.A31410 | TOR Essential Defueling Safety Case |  |  | Verify Review of Stress Modelling EAN & Issue for Technical Review | 25-May-23 A | 30-Jun-23 A | 0 | 0 | 25 | 100% |  | Completed
ER6372LT | W203 | W203.A3600 | HNB Enhanced Defuelling Safety Cases | 2023-07-27 | 2023-08-09 | BE Technical review of supporting reference <Purge and Pressurisation> | 25-May-23 A | 30-May-23 A | 3 | 0 | 3 | 100% |  | Completed
ER6378LT | W222 | W222.A27300 | HRA Fuel Handling Essential Safety Case | 2023-05-26 | 2023-05-26 | Update Cost Management Tool | 26-May-23 A | 26-May-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A27305 | HYA Fuel Handling Essential Safety Case | 2023-05-26 | 2023-05-26 | Update Cost Management Tool | 26-May-23 A | 26-May-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.B1020 | HNB Enhanced Defuelling Safety Cases | 2023-07-13 | 2023-07-26 | Verify supporting reference <Dropped Fuel Consequences EAN> | 29-May-23 A | 31-May-23 A | 3 | 0 | 1 | 100% |  | Completed
ER6371LT | W202 | W202.A5545 | HRA Reactors Shutdown Essential Safety Cases |  | 2023-04-06 | Verification Complete - (Event Recovery) - EC 363682 | 30-May-23 A | 30-May-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5545 | HYA Reactors Shutdown Essential Safety Cases |  | 2023-04-06 | Verification Complete - (Event Recovery) - EC 363676 | 30-May-23 A | 30-May-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A2670 | HNB Enhanced Defuelling Safety Cases |  | 2023-08-09 | All key supporting technical references complete <RESUMED 01.03.2023> - Purge and Pressurisation | 30-May-23 A | 30-May-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3590 | HNB Enhanced Defuelling Safety Cases |  | 2023-08-09 | Supporting reference <Purge and Pressurisation> approved | 30-May-23 A | 30-May-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3640 | HNB Enhanced Defuelling Safety Cases |  | 2023-08-09 | All supporting references completed | 30-May-23 A | 30-May-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A2590 | HNB Enhanced Defuelling Safety Cases |  | 2020-12-14 | XXXX DISCOVERY MILESTONE: Decision to Proceed with EC Production XXXX | 31-May-23 A | 31-May-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A31000 | HYB Essential Defueling Safety Case |  |  | Channel X Available | 31-May-23 A | 31-May-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3650 | HNB Enhanced Defuelling Safety Cases |  | 2023-07-12 | Draft NSRS complete - Purge and Pressurisation | 31-May-23 A | 31-May-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A31000 | TOR Essential Defueling Safety Case |  |  | Channel X Available | 31-May-23 A | 31-May-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.B1010 | HNB Enhanced Defuelling Safety Cases | 2023-07-27 | 2023-08-09 | BE Technical review of supporting reference <Dropped Fuel Consequences EAN> | 01-Jun-23 A | 05-Jun-23 A | 3 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.29520 | HYB Essential Defueling Safety Case |  |  | Draft - HYB R:77 (Deformed Standpipe Liner) EAN | 01-Jun-23 A | 16-Jun-23 A | 1 | 0 | 12 | 100% |  | Completed
ER6668LT | W213 | W213.29520 | TOR Essential Defueling Safety Case |  |  | Draft - TOR R:77 (Deformed Standpipe Liner) EAN | 01-Jun-23 A | 16-Jun-23 A | 1 | 0 | 12 | 100% |  | Completed
ER6372LT | W203 | W203.A1870 | HNB Enhanced Defuelling Safety Cases |  |  | < SCOPE REMOVED CN571> Define Project Control Structures (WBS/CBS/OBS/PBS) | 01-Jun-23 A | 01-Jun-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1890 | HNB Enhanced Defuelling Safety Cases |  |  | < SCOPE REMOVED CN571> Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 01-Jun-23 A | 01-Jun-23 A | 5 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1900 | HNB Enhanced Defuelling Safety Cases |  |  | < SCOPE REMOVED CN571> Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 01-Jun-23 A | 01-Jun-23 A | 5 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1920 | HNB Enhanced Defuelling Safety Cases |  |  | < SCOPE REMOVED CN571> Ensure Alignment of Schedule & Estimate | 01-Jun-23 A | 01-Jun-23 A | 3 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1930 | HNB Enhanced Defuelling Safety Cases |  |  | < SCOPE REMOVED CN571> Hold Risk Workshop | 01-Jun-23 A | 01-Jun-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1940 | HNB Enhanced Defuelling Safety Cases |  |  | < SCOPE REMOVED CN571> Complete Risk Log with Estimates | 01-Jun-23 A | 01-Jun-23 A | 2 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1950 | HNB Enhanced Defuelling Safety Cases |  |  | < SCOPE REMOVED CN571> Update Schedule/Estimate from Risk Log & Add Provisions | 01-Jun-23 A | 01-Jun-23 A | 2 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1960 | HNB Enhanced Defuelling Safety Cases |  |  | < SCOPE REMOVED CN571> Add Data to PRC Paper | 01-Jun-23 A | 01-Jun-23 A | 2 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1970 | HNB Enhanced Defuelling Safety Cases |  |  | < SCOPE REMOVED CN571> PCL Validate & Approve Baseline Package for PRC Submission | 01-Jun-23 A | 01-Jun-23 A | 3 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1880 | HNB Enhanced Defuelling Safety Cases |  |  | < SCOPE REMOVED CN571> Prepare Draft Project Definition Document (PDD) | 01-Jun-23 A | 01-Jun-23 A | 5 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A2000 | HNB Enhanced Defuelling Safety Cases |  |  | < SCOPE REMOVED CN571> Hold PRC Meeting | 01-Jun-23 A | 01-Jun-23 A | 1 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A1990 | HNB Enhanced Defuelling Safety Cases |  |  | < SCOPE REMOVED CN571> PRC Members Review PRC Documentation | 01-Jun-23 A | 01-Jun-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1850 | HNB Enhanced Defuelling Safety Cases |  |  | < SCOPE REMOVED CN571> Confirm Objectives to be Delivered at Gate B | 01-Jun-23 A | 01-Jun-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1860 | HNB Enhanced Defuelling Safety Cases |  |  | < SCOPE REMOVED CN571> Initial high level scope of programme | 01-Jun-23 A | 01-Jun-23 A | 2 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1910 | HNB Enhanced Defuelling Safety Cases |  |  | < SCOPE REMOVED CN571> Workshop to agree scope, effort and links | 01-Jun-23 A | 01-Jun-23 A | 5 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A2110 | HNB Enhanced Defuelling Safety Cases | 2023-04-03 | 2024-06-25 | Project Management Gate B - C | 01-Jun-23 A | 19-Nov-24 A | 107 | 0 | 375 | 100% |  | Completed
W232LT | W232 | W232.B6510 | DNB Enhanced Safety Cases | 2023-04-26 | 2023-04-27 | Core Support Plate Structural Integrity Criticality - Approve Task Sheet | 01-Jun-23 A | 20-Jun-23 A | 5 | 0 | 13 | 100% |  | Completed
ER6372LT | W203 | W203.A3170 | HNB Enhanced Defuelling Safety Cases | 2023-07-13 | 2023-07-26 | Station comments on NSRS | 01-Jun-23 A | 23-Jun-23 A | 10 | 0 | 17 | 100% |  | Completed
ER6372LT | W203 | W203.A3180 | HNB Enhanced Defuelling Safety Cases | 2023-07-13 | 2023-07-26 | Key Stakeholders (Peer) comments on NSRS | 01-Jun-23 A | 23-Jun-23 A | 10 | 0 | 17 | 100% |  | Completed
ER6372LT | W203 | W203.A4040 | HNB Enhanced Defuelling Safety Cases |  |  | < SCOPE REMOVED CN571> Develop plan with further iterations | 01-Jun-23 A | 01-Jun-23 A | 10 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A1980 | HNB Enhanced Defuelling Safety Cases |  |  | < SCOPE REMOVED CN571> Gate B PRC Paper Submission | 01-Jun-23 A | 01-Jun-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A2020 | HNB Enhanced Defuelling Safety Cases |  |  | < SCOPE REMOVED CN571> Gate B PRC Paper Approval | 01-Jun-23 A | 01-Jun-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A4000 | HNB Enhanced Defuelling Safety Cases |  |  | < SCOPE REMOVED CN571> Issue agreed work programme to stakeholders & suppliers | 01-Jun-23 A | 01-Jun-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.B1000 | HNB Enhanced Defuelling Safety Cases |  | 2023-08-09 | Supporting reference <Dropped Fuel Consequences EAN> approved | 05-Jun-23 A | 05-Jun-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7100 | HYB Essential Defueling Safety Case | 2023-06-07 | 2023-07-14 | Verification of Claim 3 | 07-Jun-23 A | 13-Nov-23 A | 28 | 0 | 112 | 100% |  | Completed
ER6668LT | W213 | W213.7100 | TOR Essential Defueling Safety Case | 2023-06-07 | 2023-07-14 | Verification of Claim 3 | 07-Jun-23 A | 13-Nov-23 A | 28 | 0 | 113 | 100% |  | Completed
W232LT | W232 | W232.A1700 | DNB Enhanced Safety Cases | 2023-04-14 | 2023-05-12 | Verification of the case (using BARRIER MODEL) | 08-Jun-23 A | 12-Jul-23 A | 20 | 0 | 24 | 100% |  | Completed
ER6666LT | W209 | W209.7440 | HYB Essential Defueling Safety Case | 2023-06-12 | 2023-10-02 | Author Claim 7 | 12-Jun-23 A | 12-Jan-24 A | 40 | 0 | 151 | 100% |  | Completed
ER6666LT | W209 | W209.8410 | HYB Essential Defueling Safety Case | 2023-06-12 | 2023-10-18 | Claim 7 Production ## (Cost Summary) | 12-Jun-23 A | 26-Jan-24 A | 156 | 0 | 161 | 100% |  | Completed
ER6372LT | W203 | W203.A4120 | HNB Enhanced Defuelling Safety Cases | 2023-07-13 | 2023-07-26 | Verify supporting reference <IFD Deluge> | 12-Jun-23 A | 15-Jun-23 A | 3 | 0 | 3 | 100% |  | Completed
ER6372LT | W203 | W203.B1070 | HNB Enhanced Defuelling Safety Cases | 2023-06-15 | 2023-07-12 | Produce supporting reference <PSA Updates> | 12-Jun-23 A | 03-Nov-23 A | 20 | 0 | 104 | 100% |  | Completed
ER6668LT | W213 | W213.7440 | TOR Essential Defueling Safety Case | 2023-06-12 | 2023-10-02 | Author Claim 7 | 12-Jun-23 A | 12-Jan-24 A | 40 | 0 | 151 | 100% |  | Completed
ER6668LT | W213 | W213.8410 | TOR Essential Defueling Safety Case | 2023-06-12 | 2023-10-18 | Claim 7 Production ## (Cost Summary) | 12-Jun-23 A | 26-Jan-24 A | 152 | 0 | 161 | 100% |  | Completed
ER6371LT | W202 | 3010 | HRA Reactors Shutdown Essential Safety Cases |  |  | Lesson Learn - Verification Phase | 12-Jun-23 A | 12-Jun-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6661LT | W206 | 3010 | HYA Reactors Shutdown Essential Safety Cases |  |  | Lesson Learn - Verification Phase | 12-Jun-23 A | 12-Jun-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.29120 | HYB Essential Defueling Safety Case |  |  | Upload to CDMS | 13-Jun-23 A | 19-Jun-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.29120 | TOR Essential Defueling Safety Case |  |  | Upload to CDMS | 13-Jun-23 A | 19-Jun-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.7370 | HYB Essential Defueling Safety Case | 2023-06-14 | 2023-08-25 | Verification of Claim 6 | 14-Jun-23 A | 10-Nov-23 A | 20 | 0 | 106 | 100% |  | Completed
ER6668LT | W213 | W213.7370 | TOR Essential Defueling Safety Case | 2023-06-14 | 2023-08-25 | Verification of Claim 6 | 14-Jun-23 A | 10-Nov-23 A | 20 | 0 | 107 | 100% |  | Completed
ER6372LT | W203 | W203.A4110 | HNB Enhanced Defuelling Safety Cases | 2023-07-27 | 2023-08-09 | BE Technical review of supporting reference <IFD Deluge> | 15-Jun-23 A | 30-Jun-23 A | 3 | 0 | 11 | 100% |  | Completed
ER6666LT | W209 | W209.A30730 | HYB Essential Defueling Safety Case | 2023-05-26 | 2023-06-02 | Complete TR Form and Issue Channel 1 - HYB to CDMS | 16-Jun-23 A | 14-Jul-23 A | 15 | 0 | 21 | 100% |  | Completed
ER6668LT | W213 | W213.A30730 | TOR Essential Defueling Safety Case | 2023-05-26 | 2023-06-02 | Complete TR Form and Issue Channel 1 - TOR to CDMS | 16-Jun-23 A | 14-Jul-23 A | 15 | 0 | 21 | 100% |  | Completed
ER6371LT | W202 | 1636 | HRA Reactors Shutdown Essential Safety Cases |  |  | Re-Write of FDD v3 | 19-Jun-23 A | 18-Jul-23 A | 1 | 0 | 21 | 100% |  | Completed
ER6661LT | W206 | 1636 | HYA Reactors Shutdown Essential Safety Cases |  |  | Re-Write of FDD v3 | 19-Jun-23 A | 18-Jul-23 A | 1 | 0 | 21 | 100% |  | Completed
ER6666LT | W209 | W209.29440 | HYB Essential Defueling Safety Case |  |  | Complete TR Form and Upload Human Factors Assessment of Misloading / Mis-Defueling Faults EAN to CDMS | 19-Jun-23 A | 30-Jun-23 A | 5 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.29530 | HYB Essential Defueling Safety Case |  |  | Verify - HYB R:77 (Deformed Standpipe Liner) EAN | 19-Jun-23 A | 20-Jul-23 A | 1 | 0 | 24 | 100% |  | Completed
ER6668LT | W213 | W213.29440 | TOR Essential Defueling Safety Case |  |  | Complete TR Form and Upload Human Factors Assessment of Misloading / Mis-Defueling Faults EAN to CDMS | 19-Jun-23 A | 30-Jun-23 A | 5 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.29530 | TOR Essential Defueling Safety Case |  |  | Verify - TOR R:77 (Deformed Standpipe Liner) EAN | 19-Jun-23 A | 20-Jul-23 A | 1 | 0 | 24 | 100% |  | Completed
ER6666LT | W209 | W209.7430 | HYB Essential Defueling Safety Case | 2022-12-02 | 2022-12-02 | PJB for Claim 7 Authoring | 20-Jun-23 A | 20-Jun-23 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B6520 | DNB Enhanced Safety Cases | 2023-04-28 | 2023-05-02 | Core Support Plate Structural Integrity Criticality - Pre Job Brief | 20-Jun-23 A | 23-Jun-23 A | 5 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.7430 | TOR Essential Defueling Safety Case | 2022-12-02 | 2022-12-02 | PJB for Claim 7 Authoring | 20-Jun-23 A | 20-Jun-23 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7180 | HYB Essential Defueling Safety Case | 2023-04-25 | 2023-05-23 | Case Officer Tech Lead Review Claim 5 | 21-Jun-23 A | 15-Dec-23 A | 10 | 0 | 126 | 100% |  | Completed
ER6668LT | W213 | W213.7180 | TOR Essential Defueling Safety Case | 2023-04-25 | 2023-05-23 | Case Officer Tech Lead Review Claim 5 | 21-Jun-23 A | 15-Dec-23 A | 10 | 0 | 126 | 100% |  | Completed
ER6372LT | W203 | W203.A3510 | HNB Enhanced Defuelling Safety Cases | 2023-07-13 | 2023-07-26 | INA comments on NSRS | 23-Jun-23 A | 24-Jul-23 A | 10 | 0 | 21 | 100% |  | Completed
W232LT | W232 | W232.B6490 | DNB Enhanced Safety Cases | 2023-05-03 | 2023-07-19 | Core Support Plate Structural Integrity Criticality - Summary | 26-Jun-23 A | 25-Sep-23 A | 87 | 0 | 64 | 100% |  | Completed
W232LT | W232 | W232.B6540 | DNB Enhanced Safety Cases | 2023-05-03 | 2023-05-31 | Core Support Plate Structural Integrity Criticality - Prepare Draft EAN | 26-Jun-23 A | 21-Aug-23 A | 20 | 0 | 40 | 100% |  | Completed
ER6666LT | W209 | W209.9020 | HYB Essential Defueling Safety Case |  | 2022-12-02 | Discovery Milestone - HF assessment of Misloading/Misdefueling - EAN Available | 30-Jun-23 A | 30-Jun-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1490 | DNB Enhanced Safety Cases |  | 2023-04-13 | All supporting references completed | 30-Jun-23 A | 30-Jun-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2760 | DNB Enhanced Safety Cases |  | 2023-04-13 | Supporting reference <Maintenance Review of FR Plant> approved | 30-Jun-23 A | 30-Jun-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A4100 | HNB Enhanced Defuelling Safety Cases |  | 2023-08-09 | Supporting reference <IFD Deluge> approved | 30-Jun-23 A | 30-Jun-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.9020 | TOR Essential Defueling Safety Case |  | 2022-12-02 | Discovery Milestone - HF assessment of Misloading/Misdefueling - EAN Available | 30-Jun-23 A | 30-Jun-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.29450 | HYB Essential Defueling Safety Case |  |  | Human Factors Assessment of Misloading / Mis-Defueling Faults EAN Available (REV 001) | 30-Jun-23 A | 30-Jun-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.29450 | TOR Essential Defueling Safety Case |  |  | Human Factors Assessment of Misloading / Mis-Defueling Faults EAN Available (REV 001) | 30-Jun-23 A | 30-Jun-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3240 | HNB Enhanced Defuelling Safety Cases | 2023-08-11 | 2023-08-14 | CA to agree with CO format of the safety case & produce agreed contents page | 03-Jul-23 A | 06-Jul-23 A | 2 | 0 | 3 | 100% |  | Completed
ER6372LT | W203 | W203.A3530 | HNB Enhanced Defuelling Safety Cases | 2023-07-20 | 2023-08-02 | Develop plan with further iterations | 03-Jul-23 A | 14-Jul-23 A | 10 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.A24600 | HYB Essential Defueling Safety Case | 2023-07-04 | 2023-07-25 | Technical Review of Human Reliability Baseline Report EAN | 04-Jul-23 A | 31-Jul-23 A | 16 | 0 | 20 | 100% |  | Completed
ER6668LT | W213 | W213.A24600 | TOR Essential Defueling Safety Case | 2023-07-04 | 2023-07-25 | Technical Review of Human Reliability Baseline Report EAN | 04-Jul-23 A | 31-Jul-23 A | 16 | 0 | 20 | 100% |  | Completed
ER6372LT | W203 | W203.A3250 | HNB Enhanced Defuelling Safety Cases | 2023-08-15 | 2023-09-26 | Prepare the Safety Case Proposal - <Purge and Pressurisation> | 10-Jul-23 A | 19-Aug-23 A | 12 | 0 | 30 | 100% |  | Completed
W232LT | W232 | W232.A1750 | DNB Enhanced Safety Cases |  | 2023-05-12 | Issue to CO & Station for comments | 12-Jul-23 A | 12-Jul-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A30740 | HYB Essential Defueling Safety Case |  | 2023-06-02 | Channel 1 Detailed Design Spec - HYB Available | 14-Jul-23 A | 14-Jul-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A30740 | TOR Essential Defueling Safety Case |  | 2023-06-02 | Channel 1 Detailed Design Spec - TOR Available | 14-Jul-23 A | 14-Jul-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3760 | HNB Enhanced Defuelling Safety Cases | 2023-08-15 | 2023-09-26 | Prepare the Safety Case Proposal | 17-Jul-23 A | 20-Nov-23 A | 28 | 0 | 90 | 100% |  | Completed
W232LT | W232 | W232.A1760 | DNB Enhanced Safety Cases | 2023-05-15 | 2023-05-19 | Incorporate CO & Station comments | 17-Jul-23 A | 21-Jul-23 A | 5 | 0 | 4 | 100% |  | Completed
ER6666LT | W209 | W209.A31120 | HYB Essential Defueling Safety Case |  |  | Upload Defueling Process Flow to CDMS | 18-Jul-23 A | 31-Jul-23 A | 5 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.A31120 | TOR Essential Defueling Safety Case |  |  | Upload Defueling Process Flow to CDMS | 18-Jul-23 A | 31-Jul-23 A | 5 | 0 | 10 | 100% |  | Completed
ER6371LT | W202 | 1646 | HRA Reactors Shutdown Essential Safety Cases |  |  | Verifed updated FDD v3 | 19-Jul-23 A | 09-Oct-23 A | 10 | 0 | 57 | 100% |  | Completed
ER6661LT | W206 | 1646 | HYA Reactors Shutdown Essential Safety Cases |  |  | Verifed updated FDD v3 | 19-Jul-23 A | 09-Oct-23 A | 10 | 0 | 57 | 100% |  | Completed
ER6666LT | W209 | W209.A29270 | HYB Essential Defueling Safety Case | 2023-03-15 | 2023-03-21 | Complete TR Form and Upload Defuelling Hazards Review EAN to CDMS | 21-Jul-23 A | 31-Jul-23 A | 5 | 0 | 6 | 100% |  | Completed
ER6666LT | W209 | W209.29540 | HYB Essential Defueling Safety Case |  |  | Complete HYB R:77 (Deformed Standpipe Liner) EAN and Upload to CDMS | 21-Jul-23 A | 31-Jul-23 A | 5 | 0 | 6 | 100% |  | Completed
ER6668LT | W213 | W213.A29270 | TOR Essential Defueling Safety Case | 2023-03-15 | 2023-03-21 | Complete TR Form and Upload Defuelling Hazards Review EAN to CDMS | 21-Jul-23 A | 31-Jul-23 A | 5 | 0 | 6 | 100% |  | Completed
ER6668LT | W213 | W213.29540 | TOR Essential Defueling Safety Case |  |  | Complete TOR R:77 (Deformed Standpipe Liner) EAN and Upload to CDMS | 21-Jul-23 A | 31-Jul-23 A | 5 | 0 | 6 | 100% |  | Completed
W232LT | W232 | W232.A1810 | DNB Enhanced Safety Cases | 2023-05-15 | 2023-05-19 | Key Stakeholders Approval, if requested | 24-Jul-23 A | 25-Jul-23 A | 5 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.29150 | HYB Essential Defueling Safety Case |  |  | Verification | 24-Jul-23 A | 20-Oct-23 A | 12 | 0 | 64 | 100% |  | Completed
ER6372LT | W203 | W203.A3350 | HNB Enhanced Defuelling Safety Cases | 2023-07-27 | 2023-08-02 | Incorporate INA, Station, ED (peer) comments | 24-Jul-23 A | 25-Jul-23 A | 3 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.A31420 | HYB Essential Defueling Safety Case |  |  | Technical Review of Stress Modelling EAN | 24-Jul-23 A | 11-Aug-23 A | 10 | 0 | 14 | 100% |  | Completed
ER6668LT | W213 | W213.29150 | TOR Essential Defueling Safety Case |  |  | Verification | 24-Jul-23 A | 20-Oct-23 A | 12 | 0 | 63 | 100% |  | Completed
ER6668LT | W213 | W213.A31420 | TOR Essential Defueling Safety Case |  |  | Technical Review of Stress Modelling EAN | 24-Jul-23 A | 11-Aug-23 A | 10 | 0 | 14 | 100% |  | Completed
ER6666LT | W209 | W209.A31370 | HYB Essential Defueling Safety Case |  |  | Upload Fuelling Machine Purging Requirements During Defueling to CDMS | 24-Jul-23 A | 28-Jul-23 A | 5 | 0 | 4 | 100% |  | Completed
ER6668LT | W213 | W213.A31370 | TOR Essential Defueling Safety Case |  |  | Upload Fuelling Machine Purging Requirements During Defueling to CDMS | 24-Jul-23 A | 28-Jul-23 A | 5 | 0 | 4 | 100% |  | Completed
ER6372LT | W203 | W203.A3490 | HNB Enhanced Defuelling Safety Cases |  | 2023-08-10 | Issue agreed work programme to stakeholders & suppliers | 24-Jul-23 A | 24-Jul-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A2450 | HNB Enhanced Defuelling Safety Cases |  | 2023-08-03 | NSRS approved - Purge and Pressurisation | 25-Jul-23 A | 25-Jul-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3190 | HNB Enhanced Defuelling Safety Cases |  | 2023-08-02 | Issue final NSRS - <Purge and Pressurisation> | 25-Jul-23 A | 25-Jul-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3200 | HNB Enhanced Defuelling Safety Cases |  | 2023-08-03 | Station agree NSRS (KDM) - <Purge and Pressurisation> | 25-Jul-23 A | 25-Jul-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3230 | HNB Enhanced Defuelling Safety Cases | 2023-08-04 | 2023-08-10 | Consolidate & issue to stakeholders & suppliers agreed NSRS | 25-Jul-23 A | 26-Jul-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A3370 | HNB Enhanced Defuelling Safety Cases |  | 2023-08-03 | Key Stakeholders (DA) agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 25-Jul-23 A | 25-Jul-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3520 | HNB Enhanced Defuelling Safety Cases |  | 2023-08-03 | INA agree NSRS - <Purge and Pressurisation> | 25-Jul-23 A | 25-Jul-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1770 | DNB Enhanced Safety Cases | 2023-05-15 | 2023-05-16 | Produce verification file | 26-Jul-23 A | 28-Jul-23 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A5290 | HRA Reactors Shutdown Essential Safety Cases | 2023-05-18 | 2023-05-31 | Incorporate INSA comments (HRA) | 28-Jul-23 A | 19-Sep-23 A | 9 | 0 | 36 | 100% |  | Completed
ER6661LT | W206 | W206.A5290 | HYA Reactors Shutdown Essential Safety Cases | 2023-05-18 | 2023-05-31 | Incorporate INSA comments (HYA) | 28-Jul-23 A | 19-Sep-23 A | 9 | 0 | 36 | 100% |  | Completed
W232LT | W232 | W232.A4930 | DNB Enhanced Safety Cases |  |  | Lessons Learned Workshop 2 - FPU Safety Case Authored | 28-Jul-23 A | 28-Jul-23 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A31380 | HYB Essential Defueling Safety Case |  |  | Fuelling Machine Purging Requirements During Defueling Available | 28-Jul-23 A | 28-Jul-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A31380 | TOR Essential Defueling Safety Case |  |  | Fuelling Machine Purging Requirements During Defueling Available | 28-Jul-23 A | 28-Jul-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A29280 | HYB Essential Defueling Safety Case |  | 2023-03-21 | Defuelling Hazards Review EAN Available | 31-Jul-23 A | 31-Jul-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A24610 | HYB Essential Defueling Safety Case | 2023-07-26 | 2023-08-08 | Supplier Update and Issue Human Reliability Baseline Report EAN | 31-Jul-23 A | 23-Aug-23 A | 5 | 0 | 18 | 100% |  | Completed
ER6668LT | W213 | W213.A29280 | TOR Essential Defueling Safety Case |  | 2023-03-21 | Defuelling Hazards Review EAN Available | 31-Jul-23 A | 31-Jul-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A24610 | TOR Essential Defueling Safety Case | 2023-07-26 | 2023-08-08 | Supplier Update and Issue Human Reliability Baseline Report EAN | 31-Jul-23 A | 23-Aug-23 A | 5 | 0 | 18 | 100% |  | Completed
ER6666LT | W209 | W209.25910 | HYB Essential Defueling Safety Case | 2023-07-24 | 2023-07-31 | Technical Review of Human Reliability Assessment of Unsubstantiated Claims EAN | 31-Jul-23 A | 29-Sep-23 A | 6 | 0 | 44 | 100% |  | Completed
ER6668LT | W213 | W213.25910 | TOR Essential Defueling Safety Case | 2023-07-24 | 2023-07-31 | Technical Review of Human Reliability Assessment of Unsubstantiated Claims EAN | 31-Jul-23 A | 29-Sep-23 A | 6 | 0 | 44 | 100% |  | Completed
ER6666LT | W209 | W209.A31130 | HYB Essential Defueling Safety Case |  |  | Defueling Process Flow Available | 31-Jul-23 A | 31-Jul-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A4160 | HNB Enhanced Defuelling Safety Cases |  | 2023-07-12 | Draft NSRS complete - IFD Deluge | 31-Jul-23 A | 31-Jul-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A31130 | TOR Essential Defueling Safety Case |  |  | Defueling Process Flow Available | 31-Jul-23 A | 31-Jul-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1800 | DNB Enhanced Safety Cases |  | 2023-05-19 | Issue high quality verified draft issue A with verification file to INSA & station (T - 3 weeks before NSC date) *(KDM)* | 02-Aug-23 A | 02-Aug-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1780 | DNB Enhanced Safety Cases |  | 2023-05-19 | Verification complete | 02-Aug-23 A | 02-Aug-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1790 | DNB Enhanced Safety Cases |  | 2023-05-19 | Submit for approval - Categoriser ratifies; RE/CO endorsement | 02-Aug-23 A | 02-Aug-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7380 | HYB Essential Defueling Safety Case | 2023-08-29 | 2023-09-11 | Update Claim 6 | 03-Aug-23 A | 10-Nov-23 A | 19 | 0 | 70 | 100% |  | Completed
ER6668LT | W213 | W213.7380 | TOR Essential Defueling Safety Case | 2023-08-29 | 2023-09-11 | Update Claim 6 | 03-Aug-23 A | 10-Nov-23 A | 19 | 0 | 71 | 100% |  | Completed
ER6666LT | W209 | W209.28860 | HYB Essential Defueling Safety Case |  |  | Verification of PSA following Updates | 04-Aug-23 A | 08-Dec-23 A | 5 | 0 | 90 | 100% |  | Completed
ER6668LT | W213 | W213.28860 | TOR Essential Defueling Safety Case |  |  | Verification of PSA following Updates | 04-Aug-23 A | 08-Dec-23 A | 5 | 0 | 89 | 100% |  | Completed
W232LT | W232 | W232.A1820 | DNB Enhanced Safety Cases | 2023-05-22 | 2023-06-05 | INSA review & iteration of comments (using BARRIER MODEL) | 04-Aug-23 A | 08-Aug-23 A | 10 | 0 | 2 | 100% |  | Completed
W232LT | W232 | W232.A2870 | DNB Enhanced Safety Cases | 2023-08-07 | 2023-09-22 | Carry out ALARP Review of OEM NSP Removal | 07-Aug-23 A | 25-Sep-23 A | 34 | 0 | 34 | 100% |  | Completed
ER6372LT | W203 | W203.B1060 | HNB Enhanced Defuelling Safety Cases | 2023-07-13 | 2023-07-26 | Verify supporting reference <PSA Updates> | 08-Aug-23 A | 08-Nov-23 A | 3 | 0 | 66 | 100% |  | Completed
W232LT | W232 | W232.A1840 | DNB Enhanced Safety Cases | 2023-06-06 | 2023-06-12 | Incorporate INSA comments | 09-Aug-23 A | 15-Aug-23 A | 5 | 0 | 4 | 100% |  | Completed
ER6372LT | W203 | W203.A3280 | HNB Enhanced Defuelling Safety Cases | 2023-09-27 | 2023-10-24 | Verification of the case (using BARRIER MODEL) - <Purge and Pressurisation> | 11-Aug-23 A | 25-Aug-23 A | 13 | 0 | 10 | 100% |  | Completed
ER6372LT | W203 | W203.A3570 | HNB Enhanced Defuelling Safety Cases | 2023-09-27 | 2023-10-10 | Specialist Assessment | 11-Aug-23 A | 25-Aug-23 A | 13 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.1435 | HYB Essential Defueling Safety Case | 2023-10-16 | 2023-10-16 | Prepare the Safety Case Proposal - Part 1 | 14-Aug-23 A | 22-Dec-23 A | 1 | 0 | 93 | 100% |  | Completed
ER6666LT | W209 | W209.A31430 | HYB Essential Defueling Safety Case |  |  | Supplier Update and Issue Stress Modelling EAN | 14-Aug-23 A | 18-Aug-23 A | 5 | 0 | 4 | 100% |  | Completed
ER6668LT | W213 | W213.1435 | TOR Essential Defueling Safety Case | 2023-10-16 | 2023-10-16 | Prepare the Safety Case Proposal - Part 1 | 14-Aug-23 A | 22-Dec-23 A | 1 | 0 | 93 | 100% |  | Completed
ER6668LT | W213 | W213.A31430 | TOR Essential Defueling Safety Case |  |  | Supplier Update and Issue Stress Modelling EAN | 14-Aug-23 A | 18-Aug-23 A | 5 | 0 | 4 | 100% |  | Completed
W232LT | W232 | W232.A1870 | DNB Enhanced Safety Cases | 2023-06-13 | 2023-06-19 | INSA Final Approval *(KDM)* | 16-Aug-23 A | 17-Aug-23 A | 5 | 0 | 2 | 100% |  | Completed
ER6372LT | W203 | W203.A3680 | HNB Enhanced Defuelling Safety Cases | 2023-07-13 | 2023-07-26 | Station comments on NSRS | 18-Aug-23 A | 24-Aug-23 A | 5 | 0 | 4 | 100% |  | Completed
ER6372LT | W203 | W203.A3690 | HNB Enhanced Defuelling Safety Cases | 2023-07-13 | 2023-07-26 | Key Stakeholders (Peer) comments on NSRS | 18-Aug-23 A | 24-Aug-23 A | 5 | 0 | 4 | 100% |  | Completed
W232LT | W232 | W232.A4940 | DNB Enhanced Safety Cases |  |  | Lessons Learned Workshop 3 - FPU Safety Case Verified | 18-Aug-23 A | 18-Aug-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A3270 | HNB Enhanced Defuelling Safety Cases | 2023-08-22 | 2023-08-23 | Produce verification plan | 19-Aug-23 A | 20-Aug-23 A | 2 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A31440 | HYB Essential Defueling Safety Case |  |  | Complete TR Form and Upload Stress Modelling EAN to CDMS | 21-Aug-23 A | 25-Aug-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A31440 | TOR Essential Defueling Safety Case |  |  | Complete TR Form and Upload Stress Modelling EAN to CDMS | 21-Aug-23 A | 25-Aug-23 A | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.A2600 | DNB Enhanced Safety Cases | 2023-08-21 | 2023-09-01 | Assess Results of Lift Lower Trials | 21-Aug-23 A | 25-Aug-23 A | 9 | 0 | 4 | 100% |  | Completed
W232LT | W232 | W232.B6610 | DNB Enhanced Safety Cases | 2023-06-01 | 2023-06-07 | Core Support Plate Structural Integrity Criticality - TSA Internal Review of Draft EAN | 22-Aug-23 A | 04-Sep-23 A | 5 | 0 | 8 | 100% |  | Completed
ER6372LT | W203 | W203.A4020 | HNB Enhanced Defuelling Safety Cases | 2023-07-13 | 2023-07-26 | INA comments on NSRS | 24-Aug-23 A | 03-Nov-23 A | 5 | 0 | 51 | 100% |  | Completed
ER6666LT | W209 | W209.A24620 | HYB Essential Defueling Safety Case | 2023-08-09 | 2023-08-15 | Complete Review of Human Reliability Baseline Report EAN to CDMS | 24-Aug-23 A | 31-Aug-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A24620 | TOR Essential Defueling Safety Case | 2023-08-09 | 2023-08-15 | Complete Review of Human Reliability Baseline Report EAN to CDMS | 24-Aug-23 A | 31-Aug-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6372LT | W203 | W203.A3460 | HNB Enhanced Defuelling Safety Cases |  | 2023-10-24 | Issue to CO & Station for comments - <Purge and Pressurisation> | 25-Aug-23 A | 25-Aug-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A31450 | HYB Essential Defueling Safety Case |  |  | Stress Modelling EAN Available | 25-Aug-23 A | 25-Aug-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A31450 | TOR Essential Defueling Safety Case |  |  | Stress Modelling EAN Available | 25-Aug-23 A | 25-Aug-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3260 | HNB Enhanced Defuelling Safety Cases | 2023-10-25 | 2023-10-31 | Incorporate CO & Station comments | 28-Aug-23 A | 29-Aug-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A3290 | HNB Enhanced Defuelling Safety Cases | 2023-10-25 | 2023-10-26 | Produce verification file | 29-Aug-23 A | 29-Aug-23 A | 2 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A3300 | HNB Enhanced Defuelling Safety Cases |  | 2023-10-31 | Issue high quality verified draft issue A with verification file to INSA & station (KDM) - <Purge and Pressurisation> | 29-Aug-23 A | 29-Aug-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3310 | HNB Enhanced Defuelling Safety Cases | 2023-11-01 | 2023-11-14 | INSA review & iteration of comments (using BARRIER MODEL) | 29-Aug-23 A | 12-Sep-23 A | 10 | 0 | 11 | 100% |  | Completed
ER6372LT | W203 | W203.A3410 | HNB Enhanced Defuelling Safety Cases |  | 2023-10-31 | Verification complete | 29-Aug-23 A | 29-Aug-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3420 | HNB Enhanced Defuelling Safety Cases |  | 2023-10-31 | Submit for approval - Categoriser ratifies; RE/CO endorsement | 29-Aug-23 A | 29-Aug-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3430 | HNB Enhanced Defuelling Safety Cases | 2023-11-01 | 2023-11-07 | Key Stakeholders Approval, if requested | 29-Aug-23 A | 05-Sep-23 A | 5 | 0 | 6 | 100% |  | Completed
ER6666LT | W209 | W209.A31280 | HYB Essential Defueling Safety Case |  |  | Verify PSA Documentation & Issue for Technical Review | 29-Aug-23 A | 03-Jun-24 A | 31 | 0 | 193 | 100% |  | Completed
ER6668LT | W213 | W213.A31280 | TOR Essential Defueling Safety Case |  |  | Verify PSA Documentation & Issue for Technical Review | 29-Aug-23 A | 03-Jun-24 A | 31 | 0 | 193 | 100% |  | Completed
ER6666LT | W209 | W209.9030 | HYB Essential Defueling Safety Case |  | 2023-08-15 | Discovery Milestone - Human Reliability Baseline Report - EAN Available | 31-Aug-23 A | 31-Aug-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.9030 | TOR Essential Defueling Safety Case |  | 2023-08-15 | Discovery Milestone - Human Reliability Baseline Report - EAN Available | 31-Aug-23 A | 31-Aug-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A24630 | HYB Essential Defueling Safety Case |  | 2023-08-15 | Human Reliability Baseline Report EAN Available | 31-Aug-23 A | 31-Aug-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A24630 | TOR Essential Defueling Safety Case |  | 2023-08-15 | Human Reliability Baseline Report EAN Available | 31-Aug-23 A | 31-Aug-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1880 | DNB Enhanced Safety Cases | 2023-06-20 | 2023-06-26 | Station Approval for mod implementation (including station review meeting) | 01-Sep-23 A | 07-Sep-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.7970 | HYB Essential Defueling Safety Case | 2023-07-27 | 2023-08-09 | Draft Human Factors Integration Plan EAN (REV 001) | 04-Sep-23 A | 13-Oct-23 A | 10 | 0 | 30 | 100% |  | Completed
ER6668LT | W213 | W213.7970 | TOR Essential Defueling Safety Case | 2023-07-27 | 2023-08-09 | Draft Human Factors Integration Plan EAN (REV 001) | 04-Sep-23 A | 13-Oct-23 A | 10 | 0 | 29 | 100% |  | Completed
W232LT | W232 | W232.B6550 | DNB Enhanced Safety Cases |  | 2023-06-07 | Core Support Plate Structural Integrity Criticality - Issue Draft EAN to EDF for Review. | 04-Sep-23 A | 04-Sep-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B6560 | DNB Enhanced Safety Cases | 2023-06-08 | 2023-06-21 | Core Support Plate Structural Integrity Criticality - Draft EAN Reviewed by EDF SQEP | 05-Sep-23 A | 18-Sep-23 A | 10 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | 001955a | HYA Fuel Handling Essential Safety Case |  |  | Claim 5 Updates - Needs FDD | 05-Sep-23 A | 21-Sep-23 A | 15 | 0 | 12 | 100% |  | Completed
W232LT | W232 | W232.A1900 | DNB Enhanced Safety Cases |  | 2023-06-26 | Station Approval Obtained and CAT 2 Safety Case Complete *(KDM)* | 07-Sep-23 A | 07-Sep-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2610 | DNB Enhanced Safety Cases | 2023-10-16 | 2023-11-03 | Define Benefits and Objectives of Cold Defuelling | 11-Sep-23 A | 25-Sep-23 A | 15 | 0 | 10 | 100% |  | Completed
ER6372LT | W203 | W203.A3470 | HNB Enhanced Defuelling Safety Cases | 2023-11-15 | 2023-11-21 | Incorporate INSA comments | 13-Sep-23 A | 29-Sep-23 A | 1 | 0 | 12 | 100% |  | Completed
ER6666LT | W209 | W209.A27410 | HYB Essential Defueling Safety Case | 2023-08-09 | 2023-08-30 | Technical Review of Fuel Route PSA Update EAN | 18-Sep-23 A | 22-Dec-23 A | 15 | 0 | 70 | 100% |  | Completed
ER6668LT | W213 | W213.A27410 | TOR Essential Defueling Safety Case | 2023-08-09 | 2023-08-30 | Technical Review of Fuel Route PSA Update EAN | 18-Sep-23 A | 22-Dec-23 A | 15 | 0 | 69 | 100% |  | Completed
ER6666LT | W209 | W209.28940 | HYB Essential Defueling Safety Case | 2023-07-17 | 2023-07-28 | Update Claim 3 | 18-Sep-23 A | 13-Nov-23 A | 5 | 0 | 40 | 100% |  | Completed
ER6668LT | W213 | W213.28940 | TOR Essential Defueling Safety Case | 2023-07-17 | 2023-07-28 | Update Claim 3 | 18-Sep-23 A | 13-Nov-23 A | 5 | 0 | 41 | 100% |  | Completed
ER6666LT | W209 | W209.7710 | HYB Essential Defueling Safety Case | 2023-07-11 | 2023-08-07 | Early INA Review Claim 1 | 19-Sep-23 A | 29-Nov-23 A | 20 | 0 | 51 | 100% |  | Completed
ER6668LT | W213 | W213.7710 | TOR Essential Defueling Safety Case | 2023-07-11 | 2023-08-07 | INSA Pre Review Claim 1 | 19-Sep-23 A | 29-Nov-23 A | 20 | 0 | 51 | 100% |  | Completed
W232LT | W232 | W232.B6570 | DNB Enhanced Safety Cases | 2023-06-22 | 2023-07-05 | Core Support Plate Structural Integrity Criticality - Address Comments from EDF Review on Draft EAN | 19-Sep-23 A | 22-Sep-23 A | 10 | 0 | 3 | 100% |  | Completed
W232LT | W232 | W232.B6580 | DNB Enhanced Safety Cases |  | 2023-07-05 | Core Support Plate Structural Integrity Criticality - Issue Final EAN | 22-Sep-23 A | 22-Sep-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B6590 | DNB Enhanced Safety Cases | 2023-07-06 | 2023-07-19 | Core Support Plate Structural Integrity Criticality - EAN Completed and Uploaded to CDMS | 22-Sep-23 A | 25-Sep-23 A | 10 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 001955b | HYA Fuel Handling Essential Safety Case |  |  | Claim 6 Updates - ALARP | 22-Sep-23 A | 07-Nov-23 A | 4 | 0 | 33 | 100% |  | Completed
W232LT | W232 | W232.B6600 | DNB Enhanced Safety Cases |  | 2023-07-19 | Core Support Plate Structural Integrity Criticality - EAN Completed | 25-Sep-23 A | 25-Sep-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.29180 | HYB Essential Defueling Safety Case |  |  | Produce new Defuelling SSR text | 25-Sep-23 A | 08-Dec-23 A | 20 | 0 | 55 | 100% |  | Completed
ER6668LT | W213 | W213.29180 | TOR Essential Defueling Safety Case |  |  | Produce new Defuelling SSR text | 25-Sep-23 A | 08-Dec-23 A | 20 | 0 | 55 | 100% |  | Completed
W232LT | W232 | W232.A2880 | DNB Enhanced Safety Cases | 2023-09-25 | 2023-10-13 | Discovery Milestone - Warm Extraction Acceptable Y/N | 25-Sep-23 A | 01-Nov-23 A | 15 | 0 | 28 | 100% |  | Completed
ER6666LT | W209 | W209.5360 | HYB Essential Defueling Safety Case |  | 2023-08-07 | CLAIM 1 - Sub Critical Margin (SCM) | 28-Sep-23 A | 28-Sep-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.6960 | HYB Essential Defueling Safety Case |  | 2023-08-07 | Claim 1 Ready | 28-Sep-23 A | 28-Sep-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.5360 | TOR Essential Defueling Safety Case |  | 2023-08-07 | CLAIM 1 - Sub Critical Margin (SCM) | 28-Sep-23 A | 28-Sep-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.6960 | TOR Essential Defueling Safety Case |  | 2023-08-07 | Claim 1 Ready | 28-Sep-23 A | 28-Sep-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A2650 | HNB Enhanced Defuelling Safety Cases |  |  | >>>OUTGOING ENABLER (W104, W153) Reactor S/D Enhanced INSA Finally Approved | 29-Sep-23 A | 29-Sep-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.25920 | HYB Essential Defueling Safety Case | 2023-08-01 | 2023-08-07 | Supplier Update and Issue Human Reliability Assessment of Unsubstantiated Claims EAN | 29-Sep-23 A | 06-Oct-23 A | 5 | 0 | 6 | 100% |  | Completed
ER6372LT | W203 | W203.A3500 | HNB Enhanced Defuelling Safety Cases |  | 2023-11-21 | INSA Final Approval (KDM) - <Purge and Pressurisation> | 29-Sep-23 A | 29-Sep-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.25920 | TOR Essential Defueling Safety Case | 2023-08-01 | 2023-08-07 | Supplier Update and Issue Human Reliability Assessment of Unsubstantiated Claims EAN | 29-Sep-23 A | 06-Oct-23 A | 5 | 0 | 6 | 100% |  | Completed
W232LT | W232 | W232.A2620 | DNB Enhanced Safety Cases | 2023-11-06 | 2023-11-17 | Review Output from the Discovery Milestones | 02-Oct-23 A | 13-Oct-23 A | 10 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.A2920 | DNB Enhanced Safety Cases |  | 2023-07-19 | Discovery Milestone: Core Support Plate Structural Integrity Criticality | 02-Oct-23 A | 02-Oct-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2560 | DNB Enhanced Safety Cases |  |  | TOG sentences CSP strategy | 02-Oct-23 A | 02-Oct-23 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A1910 | DNB Enhanced Safety Cases | 2023-06-27 | 2023-06-27 | Post Job Debrief | 04-Oct-23 A | 04-Oct-23 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.28910 | HYB Essential Defueling Safety Case |  | 2023-07-21 | Discovery Milestone - Review need for any Post Fault Actions | 05-Oct-23 A | 05-Oct-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.28910 | TOR Essential Defueling Safety Case |  | 2023-07-21 | Discovery Milestone - Review need for any Post Fault Actions | 05-Oct-23 A | 05-Oct-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2150 | DNB Enhanced Safety Cases | 2023-06-28 |  | Mod requested, Initiate EC, identify RE, register EC & identify milestones in AMS | 05-Oct-23 A | 05-Oct-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2220 | DNB Enhanced Safety Cases | 2023-06-28 | 2023-07-04 | Raise Engineering Request (as required) | 05-Oct-23 A | 11-Oct-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.A28310 | HYB Essential Defueling Safety Case | 2023-07-24 | 2023-07-28 | Complete TR Form and Upload Fault Definition Document (FDD) EAN to CDMS | 06-Oct-23 A | 10-Oct-23 A | 5 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.25930 | HYB Essential Defueling Safety Case | 2023-08-08 | 2023-08-14 | Complete Review of Human Reliability Assessment of Unsubstantiated Claims EAN to CDMS | 06-Oct-23 A | 06-Oct-23 A | 5 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.25940 | HYB Essential Defueling Safety Case |  | 2023-08-14 | Human Reliability Assessment of Unsubstantiated Claims EAN Available | 06-Oct-23 A | 06-Oct-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.25930 | TOR Essential Defueling Safety Case | 2023-08-08 | 2023-08-14 | Complete Review of Human Reliability Assessment of Unsubstantiated Claims EAN to CDMS | 06-Oct-23 A | 06-Oct-23 A | 5 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.25940 | TOR Essential Defueling Safety Case |  | 2023-08-14 | Human Reliability Assessment of Unsubstantiated Claims EAN Available | 06-Oct-23 A | 06-Oct-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A28310 | TOR Essential Defueling Safety Case | 2023-07-24 | 2023-07-28 | Complete TR Form and Upload Fault Definition Document (FDD) EAN to CDMS | 06-Oct-23 A | 10-Oct-23 A | 5 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | 1630 | HRA Reactors Shutdown Essential Safety Cases | 2022-08-22 | 2022-08-26 | Upload Fault Definition Document to AMS | 09-Oct-23 A | 11-Oct-23 A | 1 | 0 | 2 | 100% |  | Completed
ER6661LT | W206 | 1630 | HYA Reactors Shutdown Essential Safety Cases | 2022-08-22 | 2022-08-26 | Upload Fault Definition Document to AMS | 09-Oct-23 A | 11-Oct-23 A | 1 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | W222.A25270 | HRA Fuel Handling Essential Safety Case |  |  | Reauthor FDD in Report REP (REV 000) & approve on AMS (EVENT RECOVERY 1630) | 09-Oct-23 A | 11-Oct-23 A | 1 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | W226.A25270 | HYA Fuel Handling Essential Safety Case |  |  | Reauthor FDD in Report REP (REV 000) & approve on AMS (EVENT RECOVERY 1630) | 09-Oct-23 A | 11-Oct-23 A | 1 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.A28320 | HYB Essential Defueling Safety Case |  | 2023-07-28 | Fault Definition Document (FDD) EAN Available | 10-Oct-23 A | 10-Oct-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | 1940 | HRA Reactors Shutdown Essential Safety Cases | 2022-09-14 | 2022-09-14 | Updated All technical references for SC's | 10-Oct-23 A | 22-Dec-23 A | 1 | 0 | 53 | 100% |  | Completed
ER6661LT | W206 | 1940 | HYA Reactors Shutdown Essential Safety Cases | 2022-09-14 | 2022-09-14 | Updated All technical references for SC's | 10-Oct-23 A | 22-Dec-23 A | 1 | 0 | 53 | 100% |  | Completed
W232LT | W232 | W232.A2430 | DNB Enhanced Safety Cases |  | 2023-07-04 | CO & CA appointed | 11-Oct-23 A | 11-Oct-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2440 | DNB Enhanced Safety Cases |  | 2023-07-04 | Key Stakeholders Identified | 11-Oct-23 A | 11-Oct-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.3070 | HRA Fuel Handling Essential Safety Case |  |  | FDD Post Job Debrief & Lessons Learnt | 12-Oct-23 A | 12-Oct-23 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A27465 | HRA Fuel Handling Essential Safety Case |  |  | FDD Lessons Learnt Complete | 12-Oct-23 A | 12-Oct-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27465 | HYA Fuel Handling Essential Safety Case |  |  | FDD Lessons Learnt Complete | 12-Oct-23 A | 12-Oct-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.3070 | HYA Fuel Handling Essential Safety Case |  |  | FDD Post Job Debrief & Lessons Learnt | 12-Oct-23 A | 12-Oct-23 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2210 | DNB Enhanced Safety Cases | 2023-07-05 | 2023-07-11 | Develop initial programme plan using mandatory template | 12-Oct-23 A | 18-Oct-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A28320 | TOR Essential Defueling Safety Case |  | 2023-07-28 | Fault Definition Document (FDD) EAN Available | 12-Oct-23 A | 12-Oct-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3440 | HNB Enhanced Defuelling Safety Cases | 2023-12-06 | 2023-12-06 | Station approval for mod implementation (including station review meeting) | 13-Oct-23 A | 13-Oct-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A3580 | HNB Enhanced Defuelling Safety Cases |  | 2023-12-06 | Station Approval Obtained and CAT 2 Safety Case Complete *(KDM)* (FEEDS TO SUMMARY SCHEDULE) | 13-Oct-23 A | 13-Oct-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1980 | DNB Enhanced Safety Cases | 2023-07-19 | 2023-09-12 | Produce Draft NSRS (using BARRIER MODEL) | 16-Oct-23 A | 07-Dec-23 A | 39 | 0 | 38 | 100% |  | Completed
ER6668LT | W213 | W213.7270 | TOR Essential Defueling Safety Case | 2023-08-21 | 2023-09-04 | Case Officer Tech Lead Review Claim 4 | 16-Oct-23 A | 19-Oct-23 A | 5 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.7270 | HYB Essential Defueling Safety Case | 2023-08-21 | 2023-09-04 | Case Officer Tech Lead Review Claim 4 | 16-Oct-23 A | 19-Oct-23 A | 5 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.7980 | HYB Essential Defueling Safety Case | 2023-08-10 | 2023-08-25 | Verify Human Factors Integration Plan EAN and Issue for Technical Review (REV 001) | 16-Oct-23 A | 06-Nov-23 A | 12 | 0 | 16 | 100% |  | Completed
W232LT | W232 | W232.A2630 | DNB Enhanced Safety Cases | 2023-11-20 | 2023-12-01 | Prepare Decision Paper | 16-Oct-23 A | 27-Oct-23 A | 10 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.7980 | TOR Essential Defueling Safety Case | 2023-08-10 | 2023-08-25 | Verify Human Factors Integration Plan EAN and Issue for Technical Review (REV 001) | 16-Oct-23 A | 06-Nov-23 A | 12 | 0 | 16 | 100% |  | Completed
W232LT | W232 | W232.A2450 | DNB Enhanced Safety Cases |  | 2023-07-11 | CA PJB Held | 18-Oct-23 A | 18-Oct-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A4980 | DNB Enhanced Safety Cases |  |  | Discovery Milestone: Cat 2 Case Feasible- go/no go | 18-Oct-23 A | 18-Oct-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B6760 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727> Re-entrant Seal Stiction - Summary | 19-Oct-23 A | 19-Oct-23 A | 14 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6770 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727> Re-entrant Seal Stiction - Approve Task Sheet | 19-Oct-23 A | 19-Oct-23 A | 2 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B6790 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727> Re-entrant Seal Stiction - Draft and issue Task Sheet | 19-Oct-23 A | 19-Oct-23 A | 10 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1970 | DNB Enhanced Safety Cases | 2023-07-12 | 2023-07-18 | Produce MF (as required) | 19-Oct-23 A | 25-Oct-23 A | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.B6750 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727> Re-entrant Seal Stiction - Summary | 19-Oct-23 A | 19-Oct-23 A | 22 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6780 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727> Re-entrant Seal Stiction - Pre Job Brief | 19-Oct-23 A | 19-Oct-23 A | 2 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6800 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727> Re-entrant Seal Stiction - Prepare Draft EAN | 19-Oct-23 A | 19-Oct-23 A | 20 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6820 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727>Re-entrant Seal Stiction - Draft EAN Reviewed by EDF SQEP | 19-Oct-23 A | 19-Oct-23 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6830 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727>Re-entrant Seal Stiction - Address Comments from EDF Review on Draft EAN | 19-Oct-23 A | 19-Oct-23 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6850 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727>Re-entrant Seal Stiction - EAN Completed and Uploaded to CDMS | 19-Oct-23 A | 19-Oct-23 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6870 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727>Re-entrant Seal Stiction - TSA Internal Review of Draft EAN | 19-Oct-23 A | 19-Oct-23 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B6810 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727>Re-entrant Seal Stiction - Issue Draft EAN to EDF for Review. | 19-Oct-23 A | 19-Oct-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B6840 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727>Re-entrant Seal Stiction - Issue Final EAN | 19-Oct-23 A | 19-Oct-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B6860 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727>Re-entrant Seal Stiction - EAN Completed (FEED TOS UMMARY SCHEDULE) | 19-Oct-23 A | 19-Oct-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2940 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 1727>Discovery Milestone: Re-entrant Seal Stiction | 19-Oct-23 A | 19-Oct-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7280 | HYB Essential Defueling Safety Case | 2023-09-05 | 2023-10-02 | Verification of Claim 4 | 20-Oct-23 A | 01-Dec-23 A | 5 | 0 | 31 | 100% |  | Completed
ER6666LT | W209 | W209.7290 | HYB Essential Defueling Safety Case | 2023-10-03 | 2023-10-16 | Update Claim 4 | 20-Oct-23 A | 20-Dec-23 A | 8 | 0 | 43 | 100% |  | Completed
ER6668LT | W213 | W213.7280 | TOR Essential Defueling Safety Case | 2023-09-05 | 2023-10-02 | Verification of Claim 4 | 20-Oct-23 A | 01-Dec-23 A | 10 | 0 | 31 | 100% |  | Completed
ER6668LT | W213 | W213.7290 | TOR Essential Defueling Safety Case | 2023-10-03 | 2023-10-16 | Update Claim 4 | 20-Oct-23 A | 20-Dec-23 A | 4 | 0 | 43 | 100% |  | Completed
ER6650LT | W226 | 001955d | HYA Fuel Handling Essential Safety Case |  |  | Claim 2 Updates - H&I PSA Worker Risk | 20-Oct-23 A | 16-Nov-23 A | 4 | 0 | 20 | 100% |  | Completed
ER6668LT | W213 | W213.29160 | TOR Essential Defueling Safety Case |  |  | Technical Review | 23-Oct-23 A | 27-Nov-23 A | 10 | 0 | 25 | 100% |  | Completed
ER6666LT | W209 | W209.29160 | HYB Essential Defueling Safety Case |  |  | Technical Review | 23-Oct-23 A | 27-Nov-23 A | 7 | 0 | 26 | 100% |  | Completed
W232LT | W232 | W232.A4950 | DNB Enhanced Safety Cases |  |  | Lessons Learned Workshop 1 - TOG Learning | 25-Oct-23 A | 25-Oct-23 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2160 | DNB Enhanced Safety Cases |  | 2023-07-18 | Issue MF (as required) | 25-Oct-23 A | 25-Oct-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2270 | DNB Enhanced Safety Cases | 2023-07-19 | 2023-07-25 | Categorisation by RE / Station | 26-Oct-23 A | 01-Nov-23 A | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.A2300 | DNB Enhanced Safety Cases | 2023-07-19 | 2023-07-25 | Identify verifier for the case & establish all other resources | 26-Oct-23 A | 01-Nov-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | 001955e | HYA Fuel Handling Essential Safety Case |  |  | Claim 4 Updates - Refuelling Cooling | 26-Oct-23 A | 16-Nov-23 A | 4 | 0 | 15 | 100% |  | Completed
ER6666LT | W209 | W209.5370 | HYB Essential Defueling Safety Case |  | 2023-09-28 | CLAIM 2 - Shutdown and Fuel Handling Cooling | 27-Oct-23 A | 27-Oct-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.5370 | TOR Essential Defueling Safety Case |  | 2023-09-28 | CLAIM 2 - Shutdown and Fuel Handling Cooling | 27-Oct-23 A | 27-Oct-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.7050 | TOR Essential Defueling Safety Case |  | 2023-09-28 | Claim 2 Ready | 27-Oct-23 A | 27-Oct-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3560 | HNB Enhanced Defuelling Safety Cases | 2023-12-20 | 2023-12-20 | Post Job Debrief | 27-Oct-23 A | 27-Oct-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 001955f | HYA Fuel Handling Essential Safety Case |  |  | Claim 3 - No updates Required | 27-Oct-23 A | 27-Oct-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7050 | HYB Essential Defueling Safety Case |  | 2023-09-28 | Claim 2 Ready | 27-Oct-23 A | 27-Oct-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.7720 | TOR Essential Defueling Safety Case | 2023-09-01 | 2023-09-28 | INSA Pre Review Claim 2 | 30-Oct-23 A | 21-Dec-23 A | 20 | 0 | 38 | 100% |  | Completed
ER6666LT | W209 | W209.7720 | HYB Essential Defueling Safety Case | 2023-09-01 | 2023-09-28 | Early INA Review Claim 2 | 30-Oct-23 A | 21-Dec-23 A | 20 | 0 | 38 | 100% |  | Completed
W232LT | W232 | W232.A2640 | DNB Enhanced Safety Cases | 2023-12-04 | 2023-12-15 | Obtain Agreement from Programme Board | 30-Oct-23 A | 14-Dec-23 A | 10 | 0 | 34 | 100% |  | Completed
ER6371LT | W202 | W202.B5540 | HRA Reactors Shutdown Essential Safety Cases |  | 2023-05-31 | Reactor Case INSA held for FH Case INSA | 31-Oct-23 A | 31-Oct-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.B5540 | HYA Reactors Shutdown Essential Safety Cases |  | 2023-05-31 | Reactor Case INSA held for FH Case INSA | 31-Oct-23 A | 31-Oct-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A25660 | HRA Fuel Handling Essential Safety Case |  |  | Worker Risk Assessment Updates (REV 001) (EVENT RECOVERY 2000f) | 01-Nov-23 A | 02-Nov-23 A | 22 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A25660 | HYA Fuel Handling Essential Safety Case |  |  | Worker Risk Assessment Updates (REV 001) (EVENT RECOVERY 2000f) | 01-Nov-23 A | 02-Nov-23 A | 2 | 0 | 2 | 100% |  | Completed
W232LT | W232 | W232.A2170 | DNB Enhanced Safety Cases | 2023-07-26 | 2023-07-27 | INSA agree MF (as required) *(KDM)* | 02-Nov-23 A | 03-Nov-23 A | 2 | 0 | 2 | 100% |  | Completed
W232LT | W232 | W232.A2400 | DNB Enhanced Safety Cases |  | 2023-07-27 | INSA Approval Date Identified | 03-Nov-23 A | 03-Nov-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2410 | DNB Enhanced Safety Cases |  | 2023-07-27 | Provide Provisional NSC Date (as required) | 03-Nov-23 A | 03-Nov-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3860 | HNB Enhanced Defuelling Safety Cases | 2023-07-27 | 2023-08-02 | Incorporate INA, Station, ED (peer) comments | 06-Nov-23 A | 10-Nov-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.28840 | HYB Essential Defueling Safety Case | 2023-08-29 | 2023-09-13 | Technical Review of Human Factors Integration Plan EAN (REV 001) | 07-Nov-23 A | 17-Jan-24 A | 10 | 0 | 49 | 100% |  | Completed
ER6668LT | W213 | W213.28840 | TOR Essential Defueling Safety Case | 2023-08-29 | 2023-09-13 | Technical Review of Human Factors Integration Plan EAN (REV 001) | 07-Nov-23 A | 17-Jan-24 A | 10 | 0 | 49 | 100% |  | Completed
ER6650LT | W226 | 001955c | HYA Fuel Handling Essential Safety Case |  |  | Claim 1 Updates - Defuelling Process Specification | 08-Nov-23 A | 16-Nov-23 A | 3 | 0 | 6 | 100% |  | Completed
ER6372LT | W203 | W203.B1050 | HNB Enhanced Defuelling Safety Cases | 2023-07-27 | 2023-08-09 | BE Technical review of supporting reference <PSA Updates> | 09-Nov-23 A | 14-Nov-23 A | 4 | 0 | 4 | 100% |  | Completed
ER6666LT | W209 | W209.5410 | HYB Essential Defueling Safety Case |  | 2023-10-09 | CLAIM 6 - Configuration Control | 10-Nov-23 A | 10-Nov-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7410 | HYB Essential Defueling Safety Case |  | 2023-10-09 | Claim 6 Ready | 10-Nov-23 A | 10-Nov-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7760 | HYB Essential Defueling Safety Case | 2023-09-12 | 2023-10-09 | Early INA Review Claim 6 | 10-Nov-23 A | 10-Nov-23 A | 20 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.5410 | TOR Essential Defueling Safety Case |  | 2023-10-09 | CLAIM 6 - Configuration Control | 10-Nov-23 A | 10-Nov-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.7760 | TOR Essential Defueling Safety Case | 2023-09-12 | 2023-10-09 | INSA Pre Review Claim 6 | 10-Nov-23 A | 10-Nov-23 A | 20 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3700 | HNB Enhanced Defuelling Safety Cases |  | 2023-08-02 | Issue final NSRS | 10-Nov-23 A | 10-Nov-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.7410 | TOR Essential Defueling Safety Case |  | 2023-10-09 | Claim 6 Ready | 10-Nov-23 A | 10-Nov-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.5380 | HYB Essential Defueling Safety Case |  | 2023-08-25 | CLAIM 3 - Containment and Structural Integrity | 13-Nov-23 A | 13-Nov-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7140 | HYB Essential Defueling Safety Case |  | 2023-08-25 | Claim 3 Ready | 13-Nov-23 A | 13-Nov-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A4170 | HNB Enhanced Defuelling Safety Cases |  | 2023-08-03 | NSRS approved - IFD Deluge | 13-Nov-23 A | 13-Nov-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.5380 | TOR Essential Defueling Safety Case |  | 2023-08-25 | CLAIM 3 - Containment and Structural Integrity | 13-Nov-23 A | 13-Nov-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 001955g | HYA Fuel Handling Essential Safety Case |  |  | Head Document Formatting Checks | 13-Nov-23 A | 21-Nov-23 A | 2 | 0 | 7 | 100% |  | Completed
ER6372LT | W203 | W203.A3710 | HNB Enhanced Defuelling Safety Cases |  | 2023-08-03 | Station agree NSRS (KDM) - <IFD Deluge> | 13-Nov-23 A | 13-Nov-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3880 | HNB Enhanced Defuelling Safety Cases |  | 2023-08-03 | Key Stakeholders (DA) agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 13-Nov-23 A | 13-Nov-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A4030 | HNB Enhanced Defuelling Safety Cases |  | 2023-08-03 | INA agree NSRS | 13-Nov-23 A | 13-Nov-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.7140 | TOR Essential Defueling Safety Case |  | 2023-08-25 | Claim 3 Ready | 13-Nov-23 A | 13-Nov-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7730 | HYB Essential Defueling Safety Case | 2023-07-31 | 2023-08-25 | Early INA Review Claim 3 | 14-Nov-23 A | 24-Jan-24 A | 20 | 0 | 48 | 100% |  | Completed
ER6372LT | W203 | W203.A4180 | HNB Enhanced Defuelling Safety Cases |  | 2023-08-09 | All key supporting technical references complete <RESUMED 01.03.2023> - IFD Deluge | 14-Nov-23 A | 14-Nov-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3740 | HNB Enhanced Defuelling Safety Cases | 2023-08-04 | 2023-08-10 | Consolidate & issue to stakeholders & suppliers agreed NSRS | 14-Nov-23 A | 14-Nov-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.7730 | TOR Essential Defueling Safety Case | 2023-07-31 | 2023-08-25 | Early INA Review Claim 3 | 14-Nov-23 A | 24-Jan-24 A | 20 | 0 | 49 | 100% |  | Completed
ER6372LT | W203 | W203.A4150 | HNB Enhanced Defuelling Safety Cases |  | 2023-08-09 | All supporting references completed | 14-Nov-23 A | 14-Nov-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.B1040 | HNB Enhanced Defuelling Safety Cases |  | 2023-08-09 | Supporting reference <PSA Updates> approved | 14-Nov-23 A | 14-Nov-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3750 | HNB Enhanced Defuelling Safety Cases | 2023-08-11 | 2023-08-14 | CA to agree with CO format of the safety case & produce agreed contents page | 15-Nov-23 A | 16-Nov-23 A | 2 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.A29080 | HYB Essential Defueling Safety Case | 2023-08-09 | 2023-08-30 | Verify Defuelling Handling Deterministic Assessment EAN & Issue for Technical Review | 17-Nov-23 A | 19-Jan-24 A | 5 | 0 | 43 | 100% |  | Completed
ER6668LT | W213 | W213.A29080 | TOR Essential Defueling Safety Case | 2023-08-09 | 2023-08-30 | Verify Defuelling Handling Deterministic Assessment EAN & Issue for Technical Review | 17-Nov-23 A | 19-Jan-24 A | 5 | 0 | 43 | 100% |  | Completed
ER6372LT | W203 | W203.A3780 | HNB Enhanced Defuelling Safety Cases | 2023-08-22 | 2023-08-23 | Produce verification plan | 17-Nov-23 A | 20-Nov-23 A | 2 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | 1956 | HYA Fuel Handling Essential Safety Case |  |  | Verification Pre Job Brief (Head Document) | 20-Nov-23 A | 20-Nov-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A3790 | HNB Enhanced Defuelling Safety Cases | 2023-09-27 | 2023-10-24 | Verification of the case (using BARRIER MODEL) | 21-Nov-23 A | 04-Dec-23 A | 10 | 0 | 10 | 100% |  | Completed
ER6372LT | W203 | W203.A4080 | HNB Enhanced Defuelling Safety Cases | 2023-09-27 | 2023-10-10 | Specialist Assessment | 21-Nov-23 A | 04-Dec-23 A | 10 | 0 | 10 | 100% |  | Completed
ER6378LT | W222 | 001962a | HRA Fuel Handling Essential Safety Case |  |  | Station RE Verification | 22-Nov-23 A | 28-Dec-23 A | 13 | 0 | 24 | 100% |  | Completed
ER6378LT | W222 | 1963 | HRA Fuel Handling Essential Safety Case |  |  | Sub Verifiers First Round Comments | 22-Nov-23 A | 20-Dec-23 A | 13 | 0 | 21 | 100% |  | Completed
ER6378LT | W222 | 1962 | HRA Fuel Handling Essential Safety Case |  |  | Station RE Verification | 22-Nov-23 A | 27-Nov-23 A | 13 | 0 | 4 | 100% |  | Completed
ER6378LT | W222 | 1961 | HRA Fuel Handling Essential Safety Case |  |  | Lead Verifier and Detail checkers first Round comments | 22-Nov-23 A | 17-Dec-23 A | 13 | 0 | 25 | 100% |  | Completed
ER6378LT | W222 | 1960 | HRA Fuel Handling Essential Safety Case |  |  | Verification of Head Document | 22-Nov-23 A | 21-Mar-24 A | 25 | 0 | 80 | 100% |  | Completed
ER6650LT | W226 | 001962a | HYA Fuel Handling Essential Safety Case |  |  | Station RE Verification Grant | 22-Nov-23 A | 28-Dec-23 A | 13 | 0 | 24 | 100% |  | Completed
ER6650LT | W226 | 1963 | HYA Fuel Handling Essential Safety Case |  |  | Sub Verifiers First Round Comments Grant | 22-Nov-23 A | 20-Dec-23 A | 13 | 0 | 21 | 100% |  | Completed
ER6650LT | W226 | 1962 | HYA Fuel Handling Essential Safety Case |  |  | Station RE Verification Grant | 22-Nov-23 A | 27-Nov-23 A | 13 | 0 | 4 | 100% |  | Completed
ER6650LT | W226 | 1961 | HYA Fuel Handling Essential Safety Case |  |  | Lead Verifier and Detail checkers first Round comments Grant | 22-Nov-23 A | 17-Dec-23 A | 13 | 0 | 25 | 100% |  | Completed
ER6650LT | W226 | 001955h | HYA Fuel Handling Essential Safety Case |  |  | Cross Referencing Checks | 22-Nov-23 A | 22-Nov-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 1960 | HYA Fuel Handling Essential Safety Case |  |  | Verification of Head Document Grant | 22-Nov-23 A | 22-Feb-24 A | 25 | 0 | 60 | 100% |  | Completed
ER6668LT | W213 | W213.29170 | TOR Essential Defueling Safety Case |  |  | Upload to CDMS | 28-Nov-23 A | 22-Dec-23 A | 12 | 0 | 18 | 100% |  | Completed
ER6666LT | W209 | W209.29170 | HYB Essential Defueling Safety Case |  |  | Upload to CDMS | 28-Nov-23 A | 22-Dec-23 A | 5 | 0 | 19 | 100% |  | Completed
W520LT | W520 | W520.A1260 | FLEETWIDE CTO Defueling Safety Case Delivery |  |  | ETC (DD-PF) 2023 | 01-Dec-23 A | 22-Dec-23 A | 16 | 0 | 15 | 100% |  | Completed
ER6666LT | W209 | W209.7450 | HYB Essential Defueling Safety Case | 2023-10-03 | 2023-10-16 | Case Officer Tech Lead Review Claim 7 | 01-Dec-23 A | 17-Jan-24 A | 5 | 0 | 31 | 100% |  | Completed
ER6668LT | W213 | W213.7450 | TOR Essential Defueling Safety Case | 2023-10-03 | 2023-10-16 | Case Officer Tech Lead Review Claim 7 | 01-Dec-23 A | 17-Jan-24 A | 5 | 0 | 31 | 100% |  | Completed
ER6372LT | W203 | W203.A3800 | HNB Enhanced Defuelling Safety Cases | 2023-10-25 | 2023-10-26 | Produce verification file | 05-Dec-23 A | 06-Dec-23 A | 2 | 0 | 2 | 100% |  | Completed
ER6372LT | W203 | W203.A3970 | HNB Enhanced Defuelling Safety Cases |  | 2023-10-24 | Issue to CO & Station for comments | 06-Dec-23 A | 06-Dec-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3770 | HNB Enhanced Defuelling Safety Cases | 2023-10-25 | 2023-10-31 | Incorporate CO & Station comments | 07-Dec-23 A | 11-Dec-23 A | 4 | 0 | 2 | 100% |  | Completed
ER6372LT | W203 | W203.A3940 | HNB Enhanced Defuelling Safety Cases | 2023-11-01 | 2023-11-07 | Key Stakeholders Approval, if requested | 07-Dec-23 A | 11-Dec-23 A | 5 | 0 | 2 | 100% |  | Completed
W232LT | W232 | W232.A2980 | DNB Enhanced Safety Cases |  | 2023-12-07 | Produce Draft NSRS Complete | 07-Dec-23 A | 07-Dec-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3810 | HNB Enhanced Defuelling Safety Cases |  | 2023-10-31 | Issue high quality verified draft issue A with verification file to INSA & station (KDM) - <IFD Deluge> | 11-Dec-23 A | 11-Dec-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3920 | HNB Enhanced Defuelling Safety Cases |  | 2023-10-31 | Verification complete | 11-Dec-23 A | 11-Dec-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A3930 | HNB Enhanced Defuelling Safety Cases |  | 2023-10-31 | Submit for approval - Categoriser ratifies; RE/CO endorsement | 11-Dec-23 A | 11-Dec-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.29190 | HYB Essential Defueling Safety Case |  |  | Include verified defuelling fault schedule from Task 2 to complete defuelling SSR | 11-Dec-23 A | 11-Dec-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.29190 | TOR Essential Defueling Safety Case |  |  | Include verified defuelling fault schedule from Task 2 to complete defuelling SSR | 11-Dec-23 A | 11-Dec-23 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.1425 | HYB Essential Defueling Safety Case | 2023-10-16 | 2023-10-17 | Produce verification plan | 12-Dec-23 A | 12-Dec-23 A | 1 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.29210 | HYB Essential Defueling Safety Case |  |  | Verification/TR/specialist assessment (station review) of SSR text only as fault schedule already QA2 | 12-Dec-23 A | 31-Jan-24 A | 6 | 0 | 33 | 100% |  | Completed
ER6372LT | W203 | W203.A3820 | HNB Enhanced Defuelling Safety Cases | 2023-11-01 | 2023-11-14 | INSA review & iteration of comments (using BARRIER MODEL) | 12-Dec-23 A | 15-Dec-23 A | 10 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.1425 | TOR Essential Defueling Safety Case | 2023-10-16 | 2023-10-17 | Produce verification plan | 12-Dec-23 A | 12-Dec-23 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.29210 | TOR Essential Defueling Safety Case |  |  | Verification/TR/specialist assessment (station review) of SSR text only as fault schedule already QA2 | 12-Dec-23 A | 31-Jan-24 A | 6 | 0 | 33 | 100% |  | Completed
ER6666LT | W209 | W209.29200 | HYB Essential Defueling Safety Case |  |  | Draft SSR Ready for review and uploaded to ADL alongside Cat 1 Ready to Review | 12-Dec-23 A | 31-Jan-24 A | 1 | 0 | 33 | 100% |  | Completed
ER6668LT | W213 | W213.29200 | TOR Essential Defueling Safety Case |  |  | Draft SSR Ready for review and uploaded to ADL alongside Cat 1 Ready to Review | 12-Dec-23 A | 31-Jan-24 A | 1 | 0 | 33 | 100% |  | Completed
ER6372LT | W203 | W203.1010 | HNB Enhanced Defuelling Safety Cases |  |  | Purge and Pressurisation - Lessons Learnt Review Complete | 14-Dec-23 A | 14-Dec-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7230 | HYB Essential Defueling Safety Case |  | 2023-07-19 | Claim 5 Ready | 15-Dec-23 A | 15-Dec-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.7230 | TOR Essential Defueling Safety Case |  | 2023-07-19 | Claim 5 Ready | 15-Dec-23 A | 15-Dec-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2650 | DNB Enhanced Safety Cases | 2023-12-18 | 2023-12-22 | Obtain Agreement from Executive (FEED TO SUMMARY SCHEDULE) | 15-Dec-23 A | 21-Dec-23 A | 5 | 0 | 5 | 100% |  | Completed
ER6372LT | W203 | W203.A3980 | HNB Enhanced Defuelling Safety Cases | 2023-11-15 | 2023-11-21 | Incorporate INSA comments | 16-Dec-23 A | 19-Dec-23 A | 10 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A29090 | HYB Essential Defueling Safety Case | 2023-08-31 | 2023-09-27 | Technical Review of Defuelling Handling Deterministic Assessment EAN | 18-Dec-23 A | 24-Jan-24 A | 5 | 0 | 24 | 100% |  | Completed
ER6668LT | W213 | W213.A29090 | TOR Essential Defueling Safety Case | 2023-08-31 | 2023-09-27 | Technical Review of Defuelling Handling Deterministic Assessment EAN | 18-Dec-23 A | 24-Jan-24 A | 5 | 0 | 25 | 100% |  | Completed
ER6378LT | W222 | 001964a | HRA Fuel Handling Essential Safety Case |  |  | Repsond to First Round Comments | 18-Dec-23 A | 08-Feb-24 A | 14 | 0 | 35 | 100% |  | Completed
ER6378LT | W222 | 1964 | HRA Fuel Handling Essential Safety Case |  |  | Respond to First Round comments (Claim 5 Re-write & Peer Review) | 18-Dec-23 A | 08-Feb-24 A | 14 | 0 | 32 | 100% |  | Completed
ER6650LT | W226 | 001964a | HYA Fuel Handling Essential Safety Case |  |  | Repsond to First Round Comments | 18-Dec-23 A | 08-Feb-24 A | 14 | 0 | 35 | 100% |  | Completed
ER6650LT | W226 | 1964 | HYA Fuel Handling Essential Safety Case |  |  | Respond to First Round comments (Claim 5 Re-write & Peer Review) Grant | 18-Dec-23 A | 31-Jan-24 A | 14 | 0 | 26 | 100% |  | Completed
ER6666LT | W209 | W209.5400 | HYB Essential Defueling Safety Case |  | 2023-11-13 | CLAIM 4 - Dropped Fuel Plug Assemblies | 20-Dec-23 A | 20-Dec-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7320 | HYB Essential Defueling Safety Case |  | 2023-11-13 | Claim 4 Ready | 20-Dec-23 A | 20-Dec-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.5400 | TOR Essential Defueling Safety Case |  | 2023-11-13 | CLAIM 4 - Dropped Fuel Plug Assemblies | 20-Dec-23 A | 20-Dec-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.7320 | TOR Essential Defueling Safety Case |  | 2023-11-13 | Claim 4 Ready | 20-Dec-23 A | 20-Dec-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1990 | DNB Enhanced Safety Cases | 2023-09-13 | 2023-09-22 | Station comments on NSRS | 20-Dec-23 A | 19-Jan-24 A | 8 | 0 | 19 | 100% |  | Completed
W232LT | W232 | W232.A2000 | DNB Enhanced Safety Cases | 2023-09-13 | 2023-09-22 | Key Stakeholders (Peer) comments on NSRS (as required) | 20-Dec-23 A | 19-Jan-24 A | 8 | 0 | 19 | 100% |  | Completed
ER6372LT | W203 | W203.A3950 | HNB Enhanced Defuelling Safety Cases | 2023-12-06 | 2023-12-06 | Station approval for mod implementation (including station review meeting) | 21-Dec-23 A | 21-Dec-23 A | 1 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A4010 | HNB Enhanced Defuelling Safety Cases |  | 2023-11-21 | INSA Final Approval (KDM) - <IFD Deluge> | 21-Dec-23 A | 21-Dec-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A4090 | HNB Enhanced Defuelling Safety Cases |  | 2023-12-06 | Station Approval Obtained and CAT 2 Safety Case Complete *(KDM)* (FEEDS TO SUMMARY SCHEDULE) - <IFD Deluge> | 21-Dec-23 A | 21-Dec-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1465 | HYB Essential Defueling Safety Case | 2023-10-17 | 2024-03-27 | Cost Summary for Veriification - (Cost Summary) ## | 22-Dec-23 A | 31-May-24 A | 95 | 0 | 108 | 100% |  | Completed
ER6666LT | W209 | W209.5390 | HYB Essential Defueling Safety Case |  | 2023-09-19 | CLAIM 5 - Faults | 22-Dec-23 A | 22-Dec-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.8700 | HYB Essential Defueling Safety Case | 2023-10-17 | 2023-11-13 | Claims Integration | 22-Dec-23 A | 31-Jan-24 A | 5 | 0 | 26 | 100% |  | Completed
ER6668LT | W213 | W213.1465 | TOR Essential Defueling Safety Case | 2023-10-17 | 2024-03-27 | Cost Summary for Veriification - (Cost Summary) ## | 22-Dec-23 A | 31-May-24 A | 93 | 0 | 108 | 100% |  | Completed
ER6668LT | W213 | W213.5390 | TOR Essential Defueling Safety Case |  | 2023-09-19 | CLAIM 5 - Faults | 22-Dec-23 A | 22-Dec-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.8700 | TOR Essential Defueling Safety Case | 2023-10-17 | 2023-11-13 | Claims Integration | 22-Dec-23 A | 31-Jan-24 A | 5 | 0 | 25 | 100% |  | Completed
ER6378LT | W222 | W222.A27445 | HRA Fuel Handling Essential Safety Case |  |  | All Technical References (EVENT RECOVERY) Complete | 22-Dec-23 A | 22-Dec-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27445 | HYA Fuel Handling Essential Safety Case |  |  | All Technical References (EVENT RECOVERY) Complete | 22-Dec-23 A | 22-Dec-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2950 | DNB Enhanced Safety Cases |  |  | Decision Milestone - Cold Defuelling Feasibility and Benefits | 22-Dec-23 A | 22-Dec-23 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A4970 | DNB Enhanced Safety Cases |  |  | >>>OUTGOING ENABLER Decision Milestone - Cold Defuelling Feasibility and Benefits | 22-Dec-23 A | 22-Dec-23 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A27420 | TOR Essential Defueling Safety Case | 2023-08-31 | 2023-09-06 | Supplier Update and Issue Fuel Route PSA Update EAN | 27-Dec-23 A | 12-Jan-24 A | 5 | 0 | 12 | 100% |  | Completed
ER6666LT | W209 | W209.A27420 | HYB Essential Defueling Safety Case | 2023-08-31 | 2023-09-06 | Supplier Update and Issue Fuel Route PSA Update EAN | 27-Dec-23 A | 12-Jan-24 A | 10 | 0 | 12 | 100% |  | Completed
ER6666LT | W209 | W209.A30020 | HYB Essential Defueling Safety Case | 2023-01-03 | 2023-04-13 | Compliance Arrangement Review EAN - Scope No Longer Required ## (Cost Summary) (Claim 6) | 02-Jan-24 A | 31-Jan-24 A | 71 | 0 | 21 | 100% |  | Completed
ER6666LT | W209 | W209.A30030 | HYB Essential Defueling Safety Case | 2023-01-03 | 2023-01-03 | HOLDING LINE - Compliance Arrangement Review EAN - Scope No Longer Required | 02-Jan-24 A | 31-Jan-24 A | 71 | 0 | 21 | 100% |  | Completed
ER6666LT | W209 | W209.A30110 | HYB Essential Defueling Safety Case | 2023-01-03 | 2023-01-03 | HOLDING LINE - Substantiate Station Comply with New Controls - Scope No Longer Required | 02-Jan-24 A | 31-Jan-24 A | 71 | 0 | 21 | 100% |  | Completed
ER6666LT | W209 | W209.A30100 | HYB Essential Defueling Safety Case | 2023-01-03 | 2023-04-13 | Substantiate Station Comply with New Controls - Scope No Longer Required ## (Cost Summary) (Claim 6) | 02-Jan-24 A | 31-Jan-24 A | 71 | 0 | 21 | 100% |  | Completed
ER6666LT | W209 | W209.A30880 | HYB Essential Defueling Safety Case |  |  | Plant Area Review in Support of Argument 6.1 EAN - Scope No Longer Required ## (Cost Summary) (Claim 6) | 02-Jan-24 A | 31-Jan-24 A | 24 | 0 | 21 | 100% |  | Completed
ER6666LT | W209 | W209.A30890 | HYB Essential Defueling Safety Case |  |  | HOLDING LINE - Plant Area Review in Support of Argument 6.1 EAN - Scope No Longer Required | 02-Jan-24 A | 31-Jan-24 A | 24 | 0 | 21 | 100% |  | Completed
W232LT | W232 | W232.A2890 | DNB Enhanced Safety Cases |  |  | <TRANSFER SCOPE TO W699 CN 1727> Cat 2 EC for Cold Extraction (if required) | 02-Jan-24 A | 01-Feb-24 A | 62 | 0 | 22 | 100% |  | Completed
ER6668LT | W213 | W213.A30020 | TOR Essential Defueling Safety Case | 2023-01-03 | 2023-04-13 | Compliance Arrangement Review EAN - Scope No Longer Required ## (Cost Summary) (Claim 6) | 02-Jan-24 A | 31-Jan-24 A | 71 | 0 | 21 | 100% |  | Completed
ER6668LT | W213 | W213.A30030 | TOR Essential Defueling Safety Case | 2023-01-03 | 2023-01-03 | HOLDING LINE - Compliance Arrangement Review EAN - Scope No Longer Required | 02-Jan-24 A | 31-Jan-24 A | 71 | 0 | 21 | 100% |  | Completed
ER6668LT | W213 | W213.A30110 | TOR Essential Defueling Safety Case | 2023-01-03 | 2023-01-03 | HOLDING LINE - Substantiate Station Comply with New Controls - Scope No Longer Required | 02-Jan-24 A | 31-Jan-24 A | 71 | 0 | 21 | 100% |  | Completed
ER6668LT | W213 | W213.A30100 | TOR Essential Defueling Safety Case | 2023-01-03 | 2023-04-13 | Substantiate Station Comply with New Controls - Scope No Longer Required ## (Cost Summary) (Claim 6) | 02-Jan-24 A | 31-Jan-24 A | 71 | 0 | 21 | 100% |  | Completed
ER6668LT | W213 | W213.A30880 | TOR Essential Defueling Safety Case |  |  | Plant Area Review in Support of Argument 6.1 EAN - Scope No Longer Required ## (Cost Summary) (Claim 6) | 02-Jan-24 A | 31-Jan-24 A | 24 | 0 | 21 | 100% |  | Completed
ER6668LT | W213 | W213.A30890 | TOR Essential Defueling Safety Case |  |  | HOLDING LINE - Plant Area Review in Support of Argument 6.1 EAN - Scope No Longer Required | 02-Jan-24 A | 31-Jan-24 A | 24 | 0 | 21 | 100% |  | Completed
ER6666LT | W209 | W209.1445 | HYB Essential Defueling Safety Case | 2023-11-28 | 2023-12-04 | Obtain CO Review & Detail Checker | 08-Jan-24 A | 01-Feb-24 A | 5 | 0 | 18 | 100% |  | Completed
ER6666LT | W209 | W209.29490 | HYB Essential Defueling Safety Case | 2023-11-14 | 2023-12-04 | Final Authoring Consolidation Check | 08-Jan-24 A | 01-Feb-24 A | 5 | 0 | 18 | 100% |  | Completed
ER6668LT | W213 | W213.1445 | TOR Essential Defueling Safety Case | 2023-11-28 | 2023-12-04 | Obtain CO Review & Detail Checker | 08-Jan-24 A | 01-Feb-24 A | 5 | 0 | 18 | 100% |  | Completed
ER6668LT | W213 | W213.29490 | TOR Essential Defueling Safety Case | 2023-11-14 | 2023-12-04 | Final Authoring Consolidation Check | 08-Jan-24 A | 01-Feb-24 A | 5 | 0 | 18 | 100% |  | Completed
ER6668LT | W213 | W213.A27430 | TOR Essential Defueling Safety Case | 2023-09-07 | 2023-09-13 | Complete TR Form and Upload Fuel Route PSA Update EAN to CDMS | 15-Jan-24 A | 31-Jan-24 A | 13 | 0 | 13 | 100% |  | Completed
ER6666LT | W209 | W209.A27430 | HYB Essential Defueling Safety Case | 2023-09-07 | 2023-09-13 | Complete TR Form and Upload Fuel Route PSA Update EAN to CDMS | 15-Jan-24 A | 31-Jan-24 A | 5 | 0 | 13 | 100% |  | Completed
ER6666LT | W209 | W209.7460 | HYB Essential Defueling Safety Case | 2023-10-17 | 2023-10-17 | Verification of Claim 7 | 17-Jan-24 A | 17-Jan-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.7470 | HYB Essential Defueling Safety Case | 2023-10-18 | 2023-10-18 | Update Claim 7 | 17-Jan-24 A | 26-Jan-24 A | 1 | 0 | 8 | 100% |  | Completed
ER6668LT | W213 | W213.7460 | TOR Essential Defueling Safety Case | 2023-10-17 | 2023-10-17 | Verification of Claim 7 | 17-Jan-24 A | 17-Jan-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.7470 | TOR Essential Defueling Safety Case | 2023-10-18 | 2023-10-18 | Update Claim 7 | 17-Jan-24 A | 26-Jan-24 A | 1 | 0 | 8 | 100% |  | Completed
ER6666LT | W209 | W209.28850 | HYB Essential Defueling Safety Case | 2023-09-14 | 2023-09-27 | Supplier Update and Issue Human Factors Integration Plan EAN (REV 001) | 18-Jan-24 A | 15-Mar-24 A | 3 | 0 | 42 | 100% |  | Completed
ER6668LT | W213 | W213.28850 | TOR Essential Defueling Safety Case | 2023-09-14 | 2023-09-27 | Supplier Update and Issue Human Factors Integration Plan EAN (REV 001) | 18-Jan-24 A | 15-Mar-24 A | 9 | 0 | 41 | 100% |  | Completed
W232LT | W232 | W232.A2040 | DNB Enhanced Safety Cases | 2023-10-10 | 2023-10-16 | Agree resource & timescales with suppliers for delivering key refs, incl contingency, risk & allowance for rework | 19-Jan-24 A | 11-Mar-24 A | 5 | 0 | 36 | 100% |  | Completed
W232LT | W232 | W232.A2970 | DNB Enhanced Safety Cases |  |  | Incorporate Station, ED (peer) comments | 22-Jan-24 A | 26-Jan-24 A | 1 | 0 | 4 | 100% |  | Completed
ER6372LT | W203 | W203.C1020 | HNB Enhanced Defuelling Safety Cases | 2024-01-23 | 2024-01-29 | Agree resource & timescales with suppliers for delivering key refs, incl contingency, risk & allowance for rework | 23-Jan-24 A | 29-Jan-24 A | 5 | 0 | 5 | 100% |  | Completed
ER6372LT | W203 | W203.C1010 | HNB Enhanced Defuelling Safety Cases | 2024-01-23 |  | Mod requested, Initiate EC, identify RE, register EC & identify milestones in AMS | 23-Jan-24 A | 23-Jan-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1000 | HNB Enhanced Defuelling Safety Cases | 2024-01-23 | 2024-01-29 | Raise Engineering Request (as required) | 23-Jan-24 A | 29-Jan-24 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.A29100 | HYB Essential Defueling Safety Case | 2023-09-28 | 2023-10-04 | Supplier Update and Issue Defuelling Handling Deterministic Assessment EAN | 25-Jan-24 A | 29-Jan-24 A | 3 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.A29100 | TOR Essential Defueling Safety Case | 2023-09-28 | 2023-10-04 | Supplier Update and Issue Defuelling Handling Deterministic Assessment EAN | 25-Jan-24 A | 29-Jan-24 A | 3 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.5420 | HYB Essential Defueling Safety Case |  | 2023-11-13 | CLAIM 7 - NSP / ALARP | 26-Jan-24 A | 26-Jan-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.5420 | TOR Essential Defueling Safety Case |  | 2023-11-13 | CLAIM 7 - NSP / ALARP | 26-Jan-24 A | 26-Jan-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2030 | DNB Enhanced Safety Cases | 2023-10-17 | 2023-10-23 | Hold project kick start meeting with Station & key suppliers | 26-Jan-24 A | 26-Mar-24 A | 5 | 0 | 42 | 100% |  | Completed
ER6666LT | W209 | W209.7500 | HYB Essential Defueling Safety Case |  | 2023-10-18 | Claim 7 Ready | 26-Jan-24 A | 26-Jan-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.7500 | TOR Essential Defueling Safety Case |  | 2023-10-18 | Claim 7 Ready | 26-Jan-24 A | 26-Jan-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.7750 | HYB Essential Defueling Safety Case | 2023-10-17 | 2023-11-13 | Early INA Review Claim 4 | 29-Jan-24 A | 29-Feb-24 A | 3 | 0 | 23 | 100% |  | Completed
ER6668LT | W213 | W213.7750 | TOR Essential Defueling Safety Case | 2023-10-17 | 2023-11-13 | Early INA Review Claim 4 | 29-Jan-24 A | 29-Feb-24 A | 3 | 0 | 23 | 100% |  | Completed
ER6372LT | W203 | W203.C1030 | HNB Enhanced Defuelling Safety Cases |  | 2024-01-29 | CO & CA appointed | 29-Jan-24 A | 29-Jan-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1040 | HNB Enhanced Defuelling Safety Cases |  | 2024-01-29 | Key Stakeholders Identified | 29-Jan-24 A | 29-Jan-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A29110 | TOR Essential Defueling Safety Case | 2023-10-05 | 2023-10-11 | Complete TR Form and Upload Defuelling Handling Deterministic Assessment EAN to CDMS | 30-Jan-24 A | 31-Jan-24 A | 5 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A29110 | HYB Essential Defueling Safety Case | 2023-10-05 | 2023-10-11 | Complete TR Form and Upload Defuelling Handling Deterministic Assessment EAN to CDMS | 30-Jan-24 A | 31-Jan-24 A | 5 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.C1060 | HNB Enhanced Defuelling Safety Cases | 2024-01-30 | 2024-02-05 | Hold project kick start meeting with Station & key suppliers | 30-Jan-24 A | 31-Jan-24 A | 5 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.C1050 | HNB Enhanced Defuelling Safety Cases | 2024-01-30 | 2024-02-05 | Develop initial programme plan using mandatory template | 30-Jan-24 A | 05-Feb-24 A | 5 | 0 | 5 | 100% |  | Completed
W730LT_UN | W730 | W730.1180 | HYB Enhanced Defueling Safety Cases |  | 2025-01-02 | >>>INCOMING ENABLER (W209) Supporting References Complete | 31-Jan-24 A | 31-Jan-24 A | 0 | 0 | 0 | 100% |  | Completed
W730LT_UN | W730 | W730.1190 | HYB Enhanced Defueling Safety Cases |  | 2025-01-02 | >>>MIRROR OF INCOMING ENABLER (W209) Supporting References Complete | 31-Jan-24 A | 31-Jan-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1034 | HYB Essential Defueling Safety Case |  | 2023-10-11 | All Key Supporting Technical References Completed for HYB Essential Defueling Safety Case | 31-Jan-24 A | 31-Jan-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1350 | HYB Essential Defueling Safety Case |  | 2023-10-11 | >>>OUTGOING ENABLER (W730, W305) Supporting References Complete | 31-Jan-24 A | 31-Jan-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1405 | HYB Essential Defueling Safety Case |  | 2023-10-11 | All Supporting References Approved and Issued | 31-Jan-24 A | 31-Jan-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A29120 | HYB Essential Defueling Safety Case |  | 2023-10-11 | Defuelling Handling Deterministic Assessment EAN Available | 31-Jan-24 A | 31-Jan-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1350 | TOR Essential Defueling Safety Case |  | 2023-10-11 | >>>OUTGOING ENABLER (W731, W214) Supporting References Complete | 31-Jan-24 A | 31-Jan-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1034 | TOR Essential Defueling Safety Case |  | 2023-10-11 | All Key Supporting Technical References Completed for TOR Essential Defueling Safety Case | 31-Jan-24 A | 31-Jan-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1405 | TOR Essential Defueling Safety Case |  | 2023-10-11 | All Supporting References Approved and Issued | 31-Jan-24 A | 31-Jan-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A29120 | TOR Essential Defueling Safety Case |  | 2023-10-11 | Defuelling Handling Deterministic Assessment EAN Available | 31-Jan-24 A | 31-Jan-24 A | 0 | 0 | 0 | 100% |  | Completed
W731LT_UN | W731 | W731.1000 | TOR Enhanced Defueling Safety Cases |  | 2025-01-02 | >>>MIRROR OF INCOMING ENABLER (W209) Supporting References Complete | 31-Jan-24 A | 31-Jan-24 A | 0 | 0 | 0 | 100% |  | Completed
W731LT_UN | W731 | W731.1010 | TOR Enhanced Defueling Safety Cases |  | 2025-01-02 | >>>INCOMING ENABLER (W209) Supporting References Complete | 31-Jan-24 A | 31-Jan-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A27440 | HYB Essential Defueling Safety Case |  | 2023-09-13 | Fuel Route PSA Update EAN Available | 31-Jan-24 A | 31-Jan-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A27440 | TOR Essential Defueling Safety Case |  | 2023-09-13 | Fuel Route PSA Update EAN Available | 31-Jan-24 A | 31-Jan-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2900 | DNB Enhanced Safety Cases | 2024-01-15 | 2024-01-26 | Clearance to Remove High Risk OEM NSPs | 01-Feb-24 A | 01-Feb-24 A | 10 | 0 | 0 | 100% |  | Completed
W230LT | W230 | W230.1010 | HYB Enhanced Defueling Safety Case Strategy |  | 2024-02-01 | Project Start | 01-Feb-24 A | 01-Feb-24 A | 0 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.1010 | TOR Enhanced Defueling Safety Case Strategy |  | 2024-02-01 | Project Start | 01-Feb-24 A | 01-Feb-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2050 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 1727> Agree design proposals with Station in the case of hardware mods | 01-Feb-24 A | 01-Feb-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2200 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 1727> Produce supporting reference <Structural Integrity Report 1 EAN> | 01-Feb-24 A | 01-Feb-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B3020 | DNB Enhanced Safety Cases | 2023-11-01 | 2023-11-01 | Confirm Objectives to be Delivered at Gate B | 01-Feb-24 A | 16-Feb-24 A | 1 | 0 | 11 | 100% |  | Completed
W232LT | W232 | W232.A2820 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 1727> Agree design proposals with Station in the case of hardware mods | 01-Feb-24 A | 01-Feb-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2830 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 1727> Produce supporting reference <OEM Lifting Integrity> | 01-Feb-24 A | 01-Feb-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2045 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 1727> Structural Integrity Report 1 - Summary | 01-Feb-24 A | 05-Feb-24 A | 3 | 0 | 3 | 100% |  | Completed
W232LT | W232 | W232.A2815 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 1727> OEM Lifting Integrity - Summary | 01-Feb-24 A | 05-Feb-24 A | 3 | 0 | 3 | 100% |  | Completed
ER6372LT | W203 | W203.C1090 | HNB Enhanced Defuelling Safety Cases | 2024-02-01 | 2024-02-07 | Agree design proposals with Station in the case of hardware mods | 01-Feb-24 A | 07-Feb-24 A | 5 | 0 | 5 | 100% |  | Completed
ER6372LT | W203 | W203.C1100 | HNB Enhanced Defuelling Safety Cases | 2024-02-01 | 2024-02-16 | Produce supporting reference <Enhanced Defueling rate EC> | 01-Feb-24 A | 08-Apr-24 A | 20 | 0 | 45 | 100% |  | Completed
ER6378LT | W222 | 001965i | HRA Fuel Handling Essential Safety Case |  |  | Second Round Verification | 01-Feb-24 A | 14-Feb-24 A | 10 | 0 | 10 | 100% |  | Completed
ER6378LT | W222 | 001965g | HRA Fuel Handling Essential Safety Case |  |  | Second Round Verification | 01-Feb-24 A | 21-Feb-24 A | 10 | 0 | 14 | 100% |  | Completed
ER6378LT | W222 | 001965f | HRA Fuel Handling Essential Safety Case |  |  | Second Round Verification | 01-Feb-24 A | 20-Feb-24 A | 10 | 0 | 13 | 100% |  | Completed
ER6378LT | W222 | 001965h | HRA Fuel Handling Essential Safety Case |  |  | Second Round Verification | 01-Feb-24 A | 22-Feb-24 A | 10 | 0 | 15 | 100% |  | Completed
ER6378LT | W222 | 001965e | HRA Fuel Handling Essential Safety Case |  |  | Second Round Verification | 01-Feb-24 A | 22-Feb-24 A | 10 | 0 | 15 | 100% |  | Completed
ER6378LT | W222 | 001965d | HRA Fuel Handling Essential Safety Case |  |  | Second Round Verification | 01-Feb-24 A | 23-Feb-24 A | 10 | 0 | 16 | 100% |  | Completed
ER6378LT | W222 | 001965c | HRA Fuel Handling Essential Safety Case |  |  | Second Round Verification | 01-Feb-24 A | 19-Mar-24 A | 10 | 0 | 33 | 100% |  | Completed
ER6378LT | W222 | 001965b | HRA Fuel Handling Essential Safety Case |  |  | Second Round Verification (Claim 5) | 01-Feb-24 A | 21-Feb-24 A | 15 | 0 | 15 | 100% |  | Completed
ER6378LT | W222 | 001965a | HRA Fuel Handling Essential Safety Case |  |  | Second Round Verification | 01-Feb-24 A | 08-Feb-24 A | 15 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | 1965 | HRA Fuel Handling Essential Safety Case |  |  | Second Round Verification | 01-Feb-24 A | 29-Feb-24 A | 10 | 0 | 20 | 100% |  | Completed
W232LT | W232 | W232.C1390 | DNB Enhanced Safety Cases | 2024-02-01 | 2024-04-03 | <NEW SCOPE CN 1727><Review of Lifting Integrity Faults> - Summary Bar | 01-Feb-24 A | 03-Apr-24 A | 43 | 0 | 43 | 100% |  | Completed
W232LT | W232 | W232.C1400 | DNB Enhanced Safety Cases | 2024-02-01 | 2024-02-14 | <NEW SCOPE CN 1727><Review of Lifting Integrity Faults> - Draft and issue RFS | 01-Feb-24 A | 14-Feb-24 A | 10 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.C1630 | DNB Enhanced Safety Cases | 2024-02-01 | 2024-04-03 | <NEW SCOPE CN 1727><Further Review of Shock Loaded Unit Events> - Summary Bar | 01-Feb-24 A | 03-Apr-24 A | 43 | 0 | 43 | 100% |  | Completed
W232LT | W232 | W232.C1640 | DNB Enhanced Safety Cases | 2024-02-01 | 2024-02-14 | <NEW SCOPE CN 1727><Further Review of Shock Loaded Unit Events> - Draft and issue RFS | 01-Feb-24 A | 14-Feb-24 A | 10 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.1475 | HYB Essential Defueling Safety Case |  | 2024-01-10 | Issue to Peer CO & Station for comments | 02-Feb-24 A | 02-Feb-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.8730 | HYB Essential Defueling Safety Case | 2023-12-05 | 2024-01-04 | Chemistry - Specialist Assessments | 02-Feb-24 A | 30-Apr-24 A | 20 | 0 | 60 | 100% |  | Completed
ER6666LT | W209 | W209.8740 | HYB Essential Defueling Safety Case | 2023-12-05 | 2024-01-04 | Civils - Specialist Assessments | 02-Feb-24 A | 30-Apr-24 A | 20 | 0 | 60 | 100% |  | Completed
ER6666LT | W209 | W209.8750 | HYB Essential Defueling Safety Case | 2023-12-05 | 2024-01-04 | Emergency Arrangements - Specialist Assessments | 02-Feb-24 A | 30-Apr-24 A | 20 | 0 | 60 | 100% |  | Completed
ER6666LT | W209 | W209.8770 | HYB Essential Defueling Safety Case | 2023-12-05 | 2024-01-04 | Env Protection & Radwaste - Specialist Assessments | 02-Feb-24 A | 30-Apr-24 A | 20 | 0 | 60 | 100% |  | Completed
ER6666LT | W209 | W209.8780 | HYB Essential Defueling Safety Case | 2023-12-05 | 2024-01-04 | Health Physics - Specialist Assessments | 02-Feb-24 A | 30-Apr-24 A | 20 | 0 | 60 | 100% |  | Completed
ER6666LT | W209 | W209.8790 | HYB Essential Defueling Safety Case | 2023-12-05 | 2024-01-04 | Liabilities - Specialist Assessments | 02-Feb-24 A | 30-Apr-24 A | 20 | 0 | 60 | 100% |  | Completed
ER6666LT | W209 | W209.8800 | HYB Essential Defueling Safety Case | 2023-12-05 | 2024-01-04 | Nuclear Safety - Specialist Assessments | 02-Feb-24 A | 30-Apr-24 A | 20 | 0 | 60 | 100% |  | Completed
ER6666LT | W209 | W209.8810 | HYB Essential Defueling Safety Case | 2023-12-05 | 2024-01-04 | Ops - Specialist Assessments | 02-Feb-24 A | 30-Apr-24 A | 20 | 0 | 60 | 100% |  | Completed
ER6666LT | W209 | W209.8820 | HYB Essential Defueling Safety Case | 2023-12-05 | 2024-01-04 | PSSR - Liner & Pens - Specialist Assessments | 02-Feb-24 A | 30-Apr-24 A | 20 | 0 | 60 | 100% |  | Completed
ER6666LT | W209 | W209.8880 | HYB Essential Defueling Safety Case | 2023-12-05 | 2025-03-17 | (C - D SANCTION) - Safety Case Development - (Cost Summary) ## (C to D) | 02-Feb-24 A | 2025-09-23 | 395 | 142 | 415 | 75% | 0 | In Progress
ER6666LT | W209 | W209.8890 | HYB Essential Defueling Safety Case | 2023-12-05 | 2025-03-17 | (C - D SANCTION) - Project Management - (Cost Summary) ## (C to D) | 02-Feb-24 A | 2025-09-23 | 395 | 142 | 415 | 75% | 0 | In Progress
ER6666LT | W209 | W209.28930 | HYB Essential Defueling Safety Case | 2023-12-08 | 2024-01-10 | Verification of the case - First Round Comments (using BARRIER MODEL) | 02-Feb-24 A | 30-Apr-24 A | 20 | 0 | 61 | 100% |  | Completed
ER6668LT | W213 | W213.1475 | TOR Essential Defueling Safety Case |  | 2024-01-10 | Issue to Peer CO & Station for comments | 02-Feb-24 A | 02-Feb-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.8730 | TOR Essential Defueling Safety Case | 2023-12-05 | 2024-01-04 | Chemistry - Specialist Assessments (if Necessary) | 02-Feb-24 A | 30-Apr-24 A | 20 | 0 | 60 | 100% |  | Completed
ER6668LT | W213 | W213.8740 | TOR Essential Defueling Safety Case | 2023-12-05 | 2024-01-04 | Civils - Specialist Assessments (if Necessary) | 02-Feb-24 A | 30-Apr-24 A | 20 | 0 | 60 | 100% |  | Completed
ER6668LT | W213 | W213.8750 | TOR Essential Defueling Safety Case | 2023-12-05 | 2024-01-04 | Emergency Arrangements - Specialist Assessments (if Necessary) | 02-Feb-24 A | 30-Apr-24 A | 20 | 0 | 60 | 100% |  | Completed
ER6668LT | W213 | W213.8770 | TOR Essential Defueling Safety Case | 2023-12-05 | 2024-01-04 | Env Protection & Radwaste - Specialist Assessments (if Necessary) | 02-Feb-24 A | 30-Apr-24 A | 20 | 0 | 60 | 100% |  | Completed
ER6668LT | W213 | W213.8780 | TOR Essential Defueling Safety Case | 2023-12-05 | 2024-01-04 | H&V - Specialist Assessments (if Necessary) | 02-Feb-24 A | 30-Apr-24 A | 20 | 0 | 60 | 100% |  | Completed
ER6668LT | W213 | W213.8790 | TOR Essential Defueling Safety Case | 2023-12-05 | 2024-01-04 | Liabilities - Specialist Assessments (if Necessary) | 02-Feb-24 A | 30-Apr-24 A | 20 | 0 | 60 | 100% |  | Completed
ER6668LT | W213 | W213.8800 | TOR Essential Defueling Safety Case | 2023-12-05 | 2024-01-04 | Nuclear Safety - Specialist Assessments (if Necessary) | 02-Feb-24 A | 30-Apr-24 A | 20 | 0 | 60 | 100% |  | Completed
ER6668LT | W213 | W213.8810 | TOR Essential Defueling Safety Case | 2023-12-05 | 2024-01-04 | Ops - Specialist Assessments (if Necessary) | 02-Feb-24 A | 30-Apr-24 A | 20 | 0 | 60 | 100% |  | Completed
ER6668LT | W213 | W213.8820 | TOR Essential Defueling Safety Case | 2023-12-05 | 2024-01-04 | PSSR - Specialist Assessments (if Necessary) | 02-Feb-24 A | 30-Apr-24 A | 20 | 0 | 60 | 100% |  | Completed
ER6668LT | W213 | W213.8880 | TOR Essential Defueling Safety Case | 2023-12-05 | 2025-03-17 | (C - D SANCTION) - Safety Case Development - (Cost Summary) ## (C to D) | 02-Feb-24 A | 2025-09-23 | 395 | 142 | 415 | 75% | 0 | In Progress
ER6668LT | W213 | W213.8890 | TOR Essential Defueling Safety Case | 2023-12-05 | 2025-03-17 | (C - D SANCTION) - Project Management - (Cost Summary) ## (C to D) | 02-Feb-24 A | 2025-09-23 | 395 | 142 | 415 | 75% | 0 | In Progress
ER6668LT | W213 | W213.28930 | TOR Essential Defueling Safety Case | 2023-12-08 | 2024-01-10 | Verification of the case (using BARRIER MODEL) | 02-Feb-24 A | 30-Apr-24 A | 20 | 0 | 60 | 100% |  | Completed
ER6666LT | W209 | W209.29620 | HYB Essential Defueling Safety Case |  |  | PSSR - PCPV - Specialist Assessments | 02-Feb-24 A | 30-Apr-24 A | 20 | 0 | 60 | 100% |  | Completed
ER6666LT | W209 | W209.29630 | HYB Essential Defueling Safety Case |  |  | APEX - PCPV Specialist Assessments | 02-Feb-24 A | 30-Apr-24 A | 20 | 0 | 60 | 100% |  | Completed
W232LT | W232 | W232.A2350 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 1727> Verify supporting reference <Structural Integrity Report 1 EAN> | 02-Feb-24 A | 02-Feb-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B3030 | DNB Enhanced Safety Cases | 2023-11-02 | 2023-11-02 | Initial high level scope of programme | 02-Feb-24 A | 16-Feb-24 A | 1 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.A2770 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 1727> Agree design proposals with Station in the case of hardware mods | 02-Feb-24 A | 02-Feb-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2780 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 1727> Produce supporting reference <Structural Integrity Report 2 EAN> | 02-Feb-24 A | 02-Feb-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2840 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 1727> Verify supporting reference <OEM Lifting Integrity> | 02-Feb-24 A | 02-Feb-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2765 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 1727> Structural Integrity Report 2 - Summary | 02-Feb-24 A | 06-Feb-24 A | 3 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.1455 | HYB Essential Defueling Safety Case |  | 2023-12-04 | Verification Commenced (T-11) | 02-Feb-24 A | 02-Feb-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1036 | HYB Essential Defueling Safety Case |  | 2023-12-04 | Safety Case Paper Authoring Complete EC 371387 -HYB Essential Defueling Safety Case | 02-Feb-24 A | 02-Feb-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1455 | TOR Essential Defueling Safety Case |  | 2023-12-04 | Verification Commenced (T-11) | 02-Feb-24 A | 02-Feb-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1036 | TOR Essential Defueling Safety Case |  | 2023-12-04 | Safety Case Paper Authoring Complete EC 371386 -TOR Essential Defueling Safety Case | 02-Feb-24 A | 02-Feb-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2360 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 1727> BE Technical review of supporting reference <Structural Integrity Report 1 EAN> | 05-Feb-24 A | 05-Feb-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2790 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 1727> Verify supporting reference <Structural Integrity Report 2 EAN> | 05-Feb-24 A | 05-Feb-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2850 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 1727> BE Technical review of supporting reference <OEM Lifting Integrity> | 05-Feb-24 A | 05-Feb-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2370 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 1727> Supporting reference <Structural Integrity Report 1 EAN> approved | 05-Feb-24 A | 05-Feb-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2860 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 1727> Supporting reference <OEM Lifting Integrity> approved | 05-Feb-24 A | 05-Feb-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 001965f | HYA Fuel Handling Essential Safety Case |  |  | Second Round Verification Grant | 06-Feb-24 A | 20-Feb-24 A | 10 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.A2800 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 1727> BE Technical review of supporting reference <Structural Integrity Report 2 EAN> | 06-Feb-24 A | 06-Feb-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1240 | DNB Enhanced Safety Cases | 2024-02-01 | 2024-04-03 | <NEW SCOPE CN 1727><Review of Weld Inspection Data> - Summary Bar | 06-Feb-24 A | 03-Apr-24 A | 40 | 0 | 40 | 100% |  | Completed
W232LT | W232 | W232.C1250 | DNB Enhanced Safety Cases | 2024-02-06 | 2024-02-19 | <NEW SCOPE CN 1727><Review of Weld Inspection Data> - Draft and issue RFS | 06-Feb-24 A | 19-Feb-24 A | 10 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.A2810 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 1727> Supporting reference <Structural Integrity Report 2 EAN> approved | 06-Feb-24 A | 06-Feb-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 001965g | HYA Fuel Handling Essential Safety Case |  |  | Second Round Verification Grant | 07-Feb-24 A | 21-Feb-24 A | 10 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.C1460 | DNB Enhanced Safety Cases | 2024-02-07 | 2024-04-04 | <NEW SCOPE CN 1727><Review of Shock Loaded Unit Events> - Prepare Draft EAN | 07-Feb-24 A | 04-Apr-24 A | 40 | 0 | 40 | 100% |  | Completed
ER6372LT | W203 | W203.A4070 | HNB Enhanced Defuelling Safety Cases | 2023-12-20 | 2023-12-20 | Post Job Debrief | 08-Feb-24 A | 08-Feb-24 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 001965h | HYA Fuel Handling Essential Safety Case |  |  | Second Round Verification Grant | 08-Feb-24 A | 22-Feb-24 A | 10 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | 001965e | HYA Fuel Handling Essential Safety Case |  |  | Second Round Verification Grant | 08-Feb-24 A | 22-Feb-24 A | 10 | 0 | 10 | 100% |  | Completed
ER6372LT | W203 | W203.1020 | HNB Enhanced Defuelling Safety Cases |  |  | IFD Deluge - Lessons Learnt Review Complete | 08-Feb-24 A | 08-Feb-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 001965a | HYA Fuel Handling Essential Safety Case |  |  | Second Round Verification Grant | 09-Feb-24 A | 01-Mar-24 A | 15 | 0 | 15 | 100% |  | Completed
ER6372LT | W203 | W203.C1140 | HNB Enhanced Defuelling Safety Cases | 2024-02-13 | 2024-02-14 | CA to agree with CO format of the safety case & produce agreed contents page | 13-Feb-24 A | 14-Feb-24 A | 2 | 0 | 2 | 100% |  | Completed
ER6372LT | W203 | W203.C1130 | HNB Enhanced Defuelling Safety Cases | 2024-02-13 | 2024-02-19 | Identify verifier for the case & establish all other resources | 13-Feb-24 A | 19-Feb-24 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | 1965 | HYA Fuel Handling Essential Safety Case |  |  | Second Round Verification Grant | 15-Feb-24 A | 29-Feb-24 A | 10 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.C1410 | DNB Enhanced Safety Cases | 2024-02-15 | 2024-02-26 | <NEW SCOPE CN 1727><Review of Lifting Integrity Faults> - Supplier prepare and issue Offer | 15-Feb-24 A | 15-Mar-24 A | 8 | 0 | 21 | 100% |  | Completed
W232LT | W232 | W232.C1650 | DNB Enhanced Safety Cases | 2024-02-15 | 2024-02-26 | <NEW SCOPE CN 1727><Further Review of Shock Loaded Unit Events> - Supplier prepare and issue Offer | 15-Feb-24 A | 15-Mar-24 A | 8 | 0 | 21 | 100% |  | Completed
W232LT | W232 | W232.A2470 | DNB Enhanced Safety Cases |  | 2023-09-22 | INSA Resource Identified | 19-Feb-24 A | 19-Feb-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.2020 | HYB Essential Defueling Safety Case | 2023-12-05 | 2023-12-05 | Hold Gate C Equivalent Mid Job Brief | 20-Feb-24 A | 23-Feb-24 A | 25 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.29260 | HYB Essential Defueling Safety Case |  |  | Lessons Learnt Activity – Following Technical References | 20-Feb-24 A | 23-Feb-24 A | 25 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.29280 | HYB Essential Defueling Safety Case | 2023-12-05 | 2023-12-18 | Lessons Learnt Activitiy - Following Authoring of SC | 20-Feb-24 A | 23-Feb-24 A | 20 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.2020 | TOR Essential Defueling Safety Case | 2023-12-05 | 2023-12-05 | Hold Gate C Equivalent Mid Job Brief | 20-Feb-24 A | 23-Feb-24 A | 25 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.29260 | TOR Essential Defueling Safety Case |  |  | Lessons Learnt Activity – Following Technical References | 20-Feb-24 A | 23-Feb-24 A | 25 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W213.29280 | TOR Essential Defueling Safety Case | 2023-12-05 | 2023-12-18 | Lessons Learnt Activitiy - Following Authoring of SC | 20-Feb-24 A | 23-Feb-24 A | 20 | 0 | 3 | 100% |  | Completed
ER6372LT | W203 | W203.C1170 | HNB Enhanced Defuelling Safety Cases | 2024-02-20 | 2024-02-21 | Produce verification plan | 20-Feb-24 A | 21-Feb-24 A | 2 | 0 | 2 | 100% |  | Completed
W232LT | W232 | W232.C1260 | DNB Enhanced Safety Cases | 2024-02-20 | 2024-02-29 | <NEW SCOPE CN 1727><Review of Weld Inspection Data> - Supplier prepare and issue Offer | 20-Feb-24 A | 15-Mar-24 A | 8 | 0 | 18 | 100% |  | Completed
W232LT | W232 | W232.A2330 | DNB Enhanced Safety Cases | 2023-09-25 | 2023-09-29 | INA comments on NSRS | 21-Feb-24 A | 28-Feb-24 A | 5 | 0 | 5 | 100% |  | Completed
W230LT | W230 | W230.1850 | HYB Enhanced Defueling Safety Case Strategy | 2024-02-22 | 2024-06-28 | ## Technical Development / Project Management - Pre Gate A - (Cost Summary) ## | 22-Feb-24 A | 28-Jun-24 A | 626 | 0 | 88 | 100% |  | Completed
W230LT | W230 | W230.1910 | HYB Enhanced Defueling Safety Case Strategy | 2024-02-22 | 2024-02-22 | HYB Enhanced SC's & Cat C MoTA Workshop | 22-Feb-24 A | 22-Feb-24 A | 1 | 0 | 0 | 100% |  | Completed
W230LT | W230 | W230.3730 | HYB Enhanced Defueling Safety Case Strategy | 2024-02-22 | 2024-06-28 | ## Technical Development / Project Management - Pre Gate A - (Cost Summary) ## SUNK COSTS | 22-Feb-24 A | 28-Jun-24 A | 626 | 0 | 88 | 100% |  | Completed
W234LT | W234 | W234.1850 | TOR Enhanced Defueling Safety Case Strategy | 2024-02-22 | 2024-06-28 | ## Technical Development / Project Management - Pre Gate A - (Cost Summary) ## | 22-Feb-24 A | 28-Jun-24 A | 626 | 0 | 88 | 100% |  | Completed
W234LT | W234 | W234.1910 | TOR Enhanced Defueling Safety Case Strategy | 2024-02-22 | 2024-02-22 | TOR Enhanced SC's & Cat C MoTA Workshop | 22-Feb-24 A | 22-Feb-24 A | 1 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.3730 | TOR Enhanced Defueling Safety Case Strategy | 2024-02-22 | 2024-06-28 | ## Technical Development / Project Management - Pre Gate A - (Cost Summary) ## SUNK COSTS | 22-Feb-24 A | 28-Jun-24 A | 626 | 0 | 88 | 100% |  | Completed
ER6666LT | W209 | W209.1062 | HYB Essential Defueling Safety Case |  | 2023-12-05 | Gate C Equivalent Mid Job Brief Held | 23-Feb-24 A | 23-Feb-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.29270 | HYB Essential Defueling Safety Case |  | 2023-10-25 | Lessons Learnt Milestone - Technical References | 23-Feb-24 A | 23-Feb-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.29290 | HYB Essential Defueling Safety Case |  | 2023-12-18 | Lessons Learnt Milestone - Authoring of the Safety Case | 23-Feb-24 A | 23-Feb-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1062 | TOR Essential Defueling Safety Case |  | 2023-12-05 | Gate C Equivalent Mid Job Brief Held | 23-Feb-24 A | 23-Feb-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.29270 | TOR Essential Defueling Safety Case |  | 2023-10-25 | Lessons Learnt Milestone - Technical References | 23-Feb-24 A | 23-Feb-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.29290 | TOR Essential Defueling Safety Case |  | 2023-12-18 | Lessons Learnt Milestone - Authoring of the Safety Case | 23-Feb-24 A | 23-Feb-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1485 | HYB Essential Defueling Safety Case | 2024-01-11 | 2024-01-31 | Incorporate all stakeholder comments | 29-Feb-24 A | 31-May-24 A | 10 | 0 | 63 | 100% |  | Completed
ER6668LT | W213 | W213.1485 | TOR Essential Defueling Safety Case | 2024-01-11 | 2024-01-31 | Incorporate all stakeholder comments | 29-Feb-24 A | 31-May-24 A | 10 | 0 | 63 | 100% |  | Completed
W230LT | W230 | W230.1920 | HYB Enhanced Defueling Safety Case Strategy | 2024-02-29 | 2024-02-29 | TOR Enhanced SC's & Cat C MoTA Workshop | 29-Feb-24 A | 29-Feb-24 A | 1 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.1920 | TOR Enhanced Defueling Safety Case Strategy | 2024-02-29 | 2024-02-29 | TOR Enhanced SC's & Cat C MoTA Workshop | 29-Feb-24 A | 29-Feb-24 A | 1 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.1020 | HRA Enhanced Defueling Safety Case | 2024-03-01 | 2024-03-29 | Review of station OPEX | 01-Mar-24 A | 29-Mar-24 A | 1 | 0 | 20 | 100% |  | Completed
ER6698LT | W224 | W224.1030 | HRA Enhanced Defueling Safety Case | 2024-03-01 | 2024-03-29 | Mass | 01-Mar-24 A | 29-Mar-24 A | 1 | 0 | 20 | 100% |  | Completed
ER6698LT | W224 | W224.1040 | HRA Enhanced Defueling Safety Case | 2024-03-01 | 2024-03-29 | MSM Handling and attachment to Tie Bar | 01-Mar-24 A | 29-Mar-24 A | 1 | 0 | 20 | 100% |  | Completed
ER6698LT | W224 | W224.1050 | HRA Enhanced Defueling Safety Case | 2024-03-01 | 2024-03-29 | Storing and loading into the IFDF | 01-Mar-24 A | 29-Mar-24 A | 1 | 0 | 20 | 100% |  | Completed
ER6698LT | W224 | W224.1060 | HRA Enhanced Defueling Safety Case | 2024-03-01 | 2024-03-29 | Operations Tooling | 01-Mar-24 A | 29-Mar-24 A | 1 | 0 | 20 | 100% |  | Completed
ER6698LT | W224 | W224.1070 | HRA Enhanced Defueling Safety Case | 2024-03-01 | 2024-03-29 | Removal/Release mechanism | 01-Mar-24 A | 29-Mar-24 A | 1 | 0 | 20 | 100% |  | Completed
ER6698LT | W224 | W224.1080 | HRA Enhanced Defueling Safety Case | 2024-03-01 | 2024-04-30 | Chamfers and curves | 01-Mar-24 A | 30-Apr-24 A | 1 | 0 | 40 | 100% |  | Completed
ER6698LT | W224 | W224.A1110 | HRA Enhanced Defueling Safety Case | 2024-03-01 |  | Project Start | 01-Mar-24 A | 01-Mar-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.3530 | HRA Enhanced Defueling Safety Case | 2024-03-01 | 2024-05-24 | Pre Gate A Actual Cost | 01-Mar-24 A | 24-May-24 A | 62 | 0 | 58 | 100% |  | Completed
ER6701LT | W228 | W228.3530 | HYA Enhanced Defueling Safety Case | 2024-03-01 | 2024-05-24 | Pre Gate A Actual Cost | 01-Mar-24 A | 24-May-24 A | 62 | 0 | 58 | 100% |  | Completed
ER6701LT | W228 | W228.A1110 | HYA Enhanced Defueling Safety Case | 2024-03-01 |  | Project Start | 01-Mar-24 A | 01-Mar-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6701LT | W228 | W228.1080 | HYA Enhanced Defueling Safety Case | 2024-03-01 | 2024-04-30 | Chamfers and curves | 01-Mar-24 A | 30-Apr-24 A | 1 | 0 | 40 | 100% |  | Completed
ER6701LT | W228 | W228.1070 | HYA Enhanced Defueling Safety Case | 2024-03-01 | 2024-03-29 | Removal/Release mechanism | 01-Mar-24 A | 29-Mar-24 A | 1 | 0 | 20 | 100% |  | Completed
ER6701LT | W228 | W228.1060 | HYA Enhanced Defueling Safety Case | 2024-03-01 | 2024-03-29 | Operations Tooling | 01-Mar-24 A | 29-Mar-24 A | 1 | 0 | 20 | 100% |  | Completed
ER6701LT | W228 | W228.1050 | HYA Enhanced Defueling Safety Case | 2024-03-01 | 2024-03-29 | Storing and loading into the IFDF | 01-Mar-24 A | 29-Mar-24 A | 1 | 0 | 20 | 100% |  | Completed
ER6701LT | W228 | W228.1040 | HYA Enhanced Defueling Safety Case | 2024-03-01 | 2024-03-29 | MSM Handling and attachment to Tie Bar | 01-Mar-24 A | 29-Mar-24 A | 1 | 0 | 20 | 100% |  | Completed
ER6701LT | W228 | W228.1030 | HYA Enhanced Defueling Safety Case | 2024-03-01 | 2024-03-29 | Mass | 01-Mar-24 A | 29-Mar-24 A | 1 | 0 | 20 | 100% |  | Completed
ER6701LT | W228 | W228.1020 | HYA Enhanced Defueling Safety Case | 2024-03-01 | 2024-03-29 | Review of station OPEX | 01-Mar-24 A | 29-Mar-24 A | 1 | 0 | 20 | 100% |  | Completed
ER6701LT | W228 | W228.1010 | HYA Enhanced Defueling Safety Case | 2024-03-01 | 2024-12-31 | Sunk Cost (Mar - Dec 24) | 01-Mar-24 A | 31-Dec-24 A | 1 | 0 | 210 | 100% |  | Completed
ER6666LT | W209 | W209.8760 | HYB Essential Defueling Safety Case | 2023-12-05 | 2024-01-04 | Computing - Specialist Assessments (Not Required) | 01-Mar-24 A | 04-Mar-24 A | 20 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2180 | DNB Enhanced Safety Cases | 2023-10-02 | 2023-10-06 | Incorporate INA, Station, ED (peer) comments | 01-Mar-24 A | 04-Mar-24 A | 4 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2500 | DNB Enhanced Safety Cases | 2023-10-31 | 2023-11-01 | Cat 2 EC Scoping Workshop | 01-Mar-24 A | 04-Mar-24 A | 2 | 0 | 2 | 100% |  | Completed
W232LT | W232 | W232.B3120 | DNB Enhanced Safety Cases | 2023-11-03 | 2023-11-03 | Define Project Control Structures (WBS/CBS/OBS/PBS) | 01-Mar-24 A | 01-Mar-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.8760 | TOR Essential Defueling Safety Case | 2023-12-05 | 2024-01-04 | Computing - Specialist Assessments (if Necessary) | 01-Mar-24 A | 04-Mar-24 A | 20 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 2130 | HYA Fuel Handling Essential Safety Case |  |  | LSD Updates | 01-Mar-24 A | 07-Mar-24 A | 5 | 0 | 5 | 100% |  | Completed
ER6698LT | W224 | W224.1090 | HRA Enhanced Defueling Safety Case | 2024-03-01 | 2024-04-30 | Latching / nonsliding | 01-Mar-24 A | 30-Apr-24 A | 1 | 0 | 40 | 100% |  | Completed
ER6701LT | W228 | W228.1090 | HYA Enhanced Defueling Safety Case | 2024-03-01 | 2024-04-30 | Latching / nonsliding | 01-Mar-24 A | 30-Apr-24 A | 1 | 0 | 40 | 100% |  | Completed
W232LT | W232 | W232.A2010 | DNB Enhanced Safety Cases | 2023-10-09 | 2023-10-09 | Issue final NSRS | 04-Mar-24 A | 04-Mar-24 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2020 | DNB Enhanced Safety Cases |  | 2023-10-09 | Station agree NSRS *(KDM)* | 04-Mar-24 A | 04-Mar-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2190 | DNB Enhanced Safety Cases |  | 2023-10-09 | Key Stakeholders agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 04-Mar-24 A | 04-Mar-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2340 | DNB Enhanced Safety Cases |  | 2023-10-09 | INA agree NSRS | 04-Mar-24 A | 04-Mar-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A3000 | DNB Enhanced Safety Cases |  | 2024-03-04 | NSRS Station Approval | 04-Mar-24 A | 04-Mar-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B3140 | DNB Enhanced Safety Cases | 2023-11-06 | 2023-11-08 | Prepare Draft Project Definition Document (PDD) | 04-Mar-24 A | 28-Mar-24 A | 1 | 0 | 18 | 100% |  | Completed
W232LT | W232 | W232.B3150 | DNB Enhanced Safety Cases | 2023-11-06 | 2023-11-08 | Plan Scope in Primavera (Level 2 B-C & Level 1 Lifecycle) | 04-Mar-24 A | 04-Mar-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2990 | DNB Enhanced Safety Cases |  | 2024-03-04 | NSRS INA Review/Approval | 04-Mar-24 A | 04-Mar-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2390 | DNB Enhanced Safety Cases | 2023-11-02 | 2023-11-15 | Develop plan with further iterations | 05-Mar-24 A | 26-Mar-24 A | 10 | 0 | 15 | 100% |  | Completed
W232LT | W232 | W232.B3350 | DNB Enhanced Safety Cases | 2023-11-09 | 2023-11-13 | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 05-Mar-24 A | 28-Mar-24 A | 1 | 0 | 17 | 100% |  | Completed
ER6650LT | W226 | 001965i | HYA Fuel Handling Essential Safety Case |  |  | Second Round Verification Grant | 05-Mar-24 A | 15-Mar-24 A | 10 | 0 | 8 | 100% |  | Completed
ER6650LT | W226 | 001965d | HYA Fuel Handling Essential Safety Case |  |  | Second Round Verification | 05-Mar-24 A | 19-Apr-24 A | 10 | 0 | 31 | 100% |  | Completed
ER6650LT | W226 | 001965c | HYA Fuel Handling Essential Safety Case |  |  | Second Round Verification Grant | 05-Mar-24 A | 19-Mar-24 A | 10 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | 001965b | HYA Fuel Handling Essential Safety Case |  |  | Second Round Verification (Claim 5) | 05-Mar-24 A | 22-Mar-24 A | 15 | 0 | 13 | 100% |  | Completed
W232LT | W232 | W232.B3370 | DNB Enhanced Safety Cases | 2023-11-14 | 2023-11-15 | Ensure Alignment of Schedule & Estimate | 06-Mar-24 A | 28-Mar-24 A | 1 | 0 | 16 | 100% |  | Completed
W232LT | W232 | W232.B3440 | DNB Enhanced Safety Cases | 2023-11-16 | 2023-11-16 | Hold Risk Workshop | 07-Mar-24 A | 07-Mar-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B3490 | DNB Enhanced Safety Cases | 2023-11-17 | 2023-11-17 | Complete Risk Log with Estimates | 08-Mar-24 A | 28-Mar-24 A | 1 | 0 | 14 | 100% |  | Completed
W232LT | W232 | W232.B3500 | DNB Enhanced Safety Cases | 2023-11-20 | 2023-11-20 | Update Schedule/Estimate from Risk Log & Add Provisions | 11-Mar-24 A | 28-Mar-24 A | 1 | 0 | 13 | 100% |  | Completed
W232LT | W232 | W232.B3580 | DNB Enhanced Safety Cases | 2023-11-21 | 2023-11-21 | Add Data to PRC Paper | 12-Mar-24 A | 28-Mar-24 A | 1 | 0 | 12 | 100% |  | Completed
W230LT | W230 | W230.1930 | HYB Enhanced Defueling Safety Case Strategy | 2024-03-13 | 2024-03-13 | Kick-Off/Setting to Work Meeting | 13-Mar-24 A | 13-Mar-24 A | 1 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.1930 | TOR Enhanced Defueling Safety Case Strategy | 2024-03-13 | 2024-03-13 | Kick-Off/Setting to Work Meeting | 13-Mar-24 A | 13-Mar-24 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B3670 | DNB Enhanced Safety Cases | 2023-11-22 | 2023-11-22 | PCL Validate & Approve Baseline Package for PRC Submission | 13-Mar-24 A | 28-Mar-24 A | 1 | 0 | 11 | 100% |  | Completed
ER6668LT | W213 | W213.7990 | TOR Essential Defueling Safety Case | 2023-09-28 | 2023-10-04 | Complete TR Form and Upload Human Factors Integration Plan EAN to CDMS (REV 001) | 18-Mar-24 A | 28-Mar-24 A | 5 | 0 | 8 | 100% |  | Completed
ER6650LT | W226 | 1990 | HYA Fuel Handling Essential Safety Case |  |  | Update Proposal (First Draft) Including Appendices & Implementation | 18-Mar-24 A | 09-May-24 A | 25 | 0 | 36 | 100% |  | Completed
ER6666LT | W209 | W209.7990 | HYB Essential Defueling Safety Case | 2023-09-28 | 2023-10-04 | Complete TR Form and Upload Human Factors Integration Plan EAN to CDMS (REV 001) | 18-Mar-24 A | 28-Mar-24 A | 5 | 0 | 9 | 100% |  | Completed
W232LT | W232 | W232.C1270 | DNB Enhanced Safety Cases | 2024-03-18 | 2024-03-22 | <NEW SCOPE CN 1727><Review of Weld Inspection Data> - Review Offer, prepare and issue CI | 18-Mar-24 A | 22-Mar-24 A | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.C1420 | DNB Enhanced Safety Cases | 2024-03-18 | 2024-03-22 | <NEW SCOPE CN 1727><Review of Lifting Integrity Faults> - Review Offer, prepare and issue CI | 18-Mar-24 A | 22-Mar-24 A | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.C1660 | DNB Enhanced Safety Cases | 2024-03-18 | 2024-03-22 | <NEW SCOPE CN 1727><Further Review of Shock Loaded Unit Events> - Review Offer, prepare and issue CI | 18-Mar-24 A | 22-Mar-24 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | 1990 | HRA Fuel Handling Essential Safety Case |  |  | Update Proposal (First Draft) Including Appendices & Implementation | 19-Mar-24 A | 13-May-24 A | 25 | 0 | 37 | 100% |  | Completed
W232LT | W232 | W232.A2025 | DNB Enhanced Safety Cases | 2024-03-20 | 2024-03-20 | <NEW SCOPE CN1743> NSRS Presented to NSC (for complex CAT 2 cases) | 20-Mar-24 A | 20-Mar-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2060 | DNB Enhanced Safety Cases | 2023-10-24 | 2023-10-30 | Consolidate & issue to stakeholders & suppliers agreed NSRS (as required) | 21-Mar-24 A | 27-Mar-24 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | 1968 | HRA Fuel Handling Essential Safety Case |  |  | Repsond to Second Round and Tidy Up | 22-Mar-24 A | 05-Apr-24 A | 10 | 0 | 8 | 100% |  | Completed
ER6378LT | W222 | W222.A24330 | HRA Fuel Handling Essential Safety Case | 2023-05-15 | 2023-05-19 | Supplier Update and Issue Living Safety Document EAN | 25-Mar-24 A | 26-Mar-24 A | 5 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A24330 | HYA Fuel Handling Essential Safety Case | 2023-05-15 | 2023-05-19 | Supplier Update and Issue Living Safety Document EAN | 25-Mar-24 A | 26-Mar-24 A | 5 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1280 | DNB Enhanced Safety Cases | 2024-03-25 | 2024-04-02 | <NEW SCOPE CN 1727><Review of Weld Inspection Data> - Supplier mobilisation time | 25-Mar-24 A | 02-Apr-24 A | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.C1430 | DNB Enhanced Safety Cases | 2024-03-25 | 2024-04-02 | <NEW SCOPE CN 1727><Review of Lifting Integrity Faults> - Supplier mobilisation time | 25-Mar-24 A | 02-Apr-24 A | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.C1670 | DNB Enhanced Safety Cases | 2024-03-25 | 2024-04-02 | <NEW SCOPE CN 1727><Further Review of Shock Loaded Unit Events> - Supplier mobilisation time | 25-Mar-24 A | 02-Apr-24 A | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.A2310 | DNB Enhanced Safety Cases |  | 2023-11-15 | Issue agreed work programme to stakeholders & suppliers | 26-Mar-24 A | 26-Mar-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2460 | DNB Enhanced Safety Cases |  | 2023-11-15 | Verifier PJB Held | 26-Mar-24 A | 26-Mar-24 A | 0 | 0 | 0 | 100% |  | Completed
W230LT | W230 | W230.1870 | HYB Enhanced Defueling Safety Case Strategy |  | 2024-03-26 | Initial Categorisation by Station | 26-Mar-24 A | 26-Mar-24 A | 0 | 0 | 0 | 100% |  | Completed
W230LT | W230 | W230.1940 | HYB Enhanced Defueling Safety Case Strategy | 2024-03-26 | 2024-03-26 | H2T Enhanced SC's EC Strategy Opex/L&L | 26-Mar-24 A | 26-Mar-24 A | 1 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.1870 | TOR Enhanced Defueling Safety Case Strategy |  | 2024-03-26 | Initial Categorisation by Station | 26-Mar-24 A | 26-Mar-24 A | 0 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.1940 | TOR Enhanced Defueling Safety Case Strategy | 2024-03-26 | 2024-03-26 | H2T Enhanced SC's EC Strategy Opex/L&L | 26-Mar-24 A | 26-Mar-24 A | 1 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 1968 | HYA Fuel Handling Essential Safety Case |  |  | Repsond to Second Round and Tidy Up | 26-Mar-24 A | 05-Apr-24 A | 10 | 0 | 6 | 100% |  | Completed
ER6378LT | W222 | W222.A24340 | HRA Fuel Handling Essential Safety Case | 2023-05-22 | 2023-05-26 | Complete TR Form and Upload Living Safety Document EAN to CDMS | 27-Mar-24 A | 22-Jul-24 A | 5 | 0 | 80 | 100% |  | Completed
ER6650LT | W226 | W226.A24340 | HYA Fuel Handling Essential Safety Case | 2023-05-22 | 2023-05-26 | Complete TR Form and Upload Living Safety Document EAN to CDMS | 27-Mar-24 A | 02-Sep-24 A | 5 | 0 | 108 | 100% |  | Completed
W230LT | W230 | W230.1950 | HYB Enhanced Defueling Safety Case Strategy | 2024-03-27 | 2024-03-27 | Pre Job Brief | 27-Mar-24 A | 27-Mar-24 A | 1 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.1950 | TOR Enhanced Defueling Safety Case Strategy | 2024-03-27 | 2024-03-27 | Pre Job Brief | 27-Mar-24 A | 27-Mar-24 A | 1 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.8000 | TOR Essential Defueling Safety Case |  | 2023-10-04 | Human Factors Integration Plan EAN Available (REV 001) | 28-Mar-24 A | 28-Mar-24 A | 0 | 0 | 0 | 100% |  | Completed
W230LT | W230 | W230.1310 | HYB Enhanced Defueling Safety Case Strategy | 2024-03-28 | 2024-04-03 | Confirm Objectives to be Delivered at Gate A (FEEDS TO SUMMARY SCHEDULE) | 28-Mar-24 A | 03-Apr-24 A | 10 | 0 | 3 | 100% |  | Completed
W230LT | W230 | W230.1960 | HYB Enhanced Defueling Safety Case Strategy | 2024-03-28 | 2024-06-03 | Draft Report | 28-Mar-24 A | 03-Jun-24 A | 1 | 0 | 44 | 100% |  | Completed
W234LT | W234 | W234.1310 | TOR Enhanced Defueling Safety Case Strategy | 2024-03-28 | 2024-04-03 | Confirm Objectives to be Delivered at Gate A (FEEDS TO SUMMARY SCHEDULE) | 28-Mar-24 A | 03-Apr-24 A | 10 | 0 | 3 | 100% |  | Completed
W234LT | W234 | W234.1960 | TOR Enhanced Defueling Safety Case Strategy | 2024-03-28 | 2024-06-03 | Draft Report | 28-Mar-24 A | 03-Jun-24 A | 1 | 0 | 44 | 100% |  | Completed
ER6666LT | W209 | W209.8000 | HYB Essential Defueling Safety Case |  | 2023-10-04 | Human Factors Integration Plan - EAN Available (REV 001) | 28-Mar-24 A | 28-Mar-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.1110 | HRA Enhanced Defueling Safety Case | 2024-04-02 | 2024-05-10 | Feasibility Workshop Tech Reports CNL) - early technical reference | 02-Apr-24 A | 10-May-24 A | 21 | 0 | 28 | 100% |  | Completed
ER6698LT | W224 | W224.1120 | HRA Enhanced Defueling Safety Case | 2024-04-02 | 2024-04-30 | Requirements Elicitation Workshop | 02-Apr-24 A | 30-Apr-24 A | 21 | 0 | 20 | 100% |  | Completed
ER6698LT | W224 | W224.1130 | HRA Enhanced Defueling Safety Case | 2024-04-02 | 2024-05-24 | Meeting Output/Notes | 02-Apr-24 A | 24-May-24 A | 21 | 0 | 38 | 100% |  | Completed
ER6698LT | W224 | W224.1170 | HRA Enhanced Defueling Safety Case | 2024-04-02 | 2024-08-07 | Scheme Design | 02-Apr-24 A | 07-Aug-24 A | 42 | 0 | 89 | 100% |  | Completed
ER6698LT | W224 | W224.1180 | HRA Enhanced Defueling Safety Case | 2024-04-02 | 2024-10-31 | Main/Key Features , for estimating purposes | 02-Apr-24 A | 31-Oct-24 A | 42 | 0 | 149 | 100% |  | Completed
ER6701LT | W228 | W228.1180 | HYA Enhanced Defueling Safety Case | 2024-04-02 | 2024-10-31 | Main/Key Features , for estimating purposes | 02-Apr-24 A | 31-Oct-24 A | 42 | 0 | 149 | 100% |  | Completed
ER6701LT | W228 | W228.1170 | HYA Enhanced Defueling Safety Case | 2024-04-02 | 2024-08-07 | Scheme Design | 02-Apr-24 A | 07-Aug-24 A | 42 | 0 | 89 | 100% |  | Completed
ER6701LT | W228 | W228.1130 | HYA Enhanced Defueling Safety Case | 2024-04-02 | 2024-05-24 | Meeting Output/Notes | 02-Apr-24 A | 24-May-24 A | 21 | 0 | 38 | 100% |  | Completed
ER6701LT | W228 | W228.1120 | HYA Enhanced Defueling Safety Case | 2024-04-02 | 2024-04-30 | Requirements Elicitation Workshop | 02-Apr-24 A | 30-Apr-24 A | 21 | 0 | 20 | 100% |  | Completed
ER6701LT | W228 | W228.1110 | HYA Enhanced Defueling Safety Case | 2024-04-02 | 2024-05-10 | Feasibility Workshop Tech Reports CNL) - early technical reference | 02-Apr-24 A | 10-May-24 A | 21 | 0 | 28 | 100% |  | Completed
ER6666LT | W209 | W209.1415 | HYB Essential Defueling Safety Case | 2023-10-12 | 2023-10-25 | Populate Affected Documents List | 02-Apr-24 A | 28-Jun-24 A | 10 | 0 | 62 | 100% |  | Completed
ER6668LT | W213 | W213.1415 | TOR Essential Defueling Safety Case | 2023-10-12 | 2023-10-25 | Populate Affected Documents List | 02-Apr-24 A | 28-Jun-24 A | 10 | 0 | 62 | 100% |  | Completed
W232LT | W232 | W232.C1290 | DNB Enhanced Safety Cases | 2024-04-03 | 2024-04-03 | <NEW SCOPE CN 1727><Review of Weld Inspection Data> - Pre Job Brief | 03-Apr-24 A | 03-Apr-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1440 | DNB Enhanced Safety Cases | 2024-04-03 | 2024-04-03 | <NEW SCOPE CN 1727><Review of Lifting Integrity Faults> - Pre Job Brief | 03-Apr-24 A | 03-Apr-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1680 | DNB Enhanced Safety Cases | 2024-04-03 | 2024-04-03 | <NEW SCOPE CN 1727><Further Review of Shock Loaded Unit Events> - Pre Job Brief | 03-Apr-24 A | 03-Apr-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C3040 | DNB Enhanced Safety Cases | 2024-04-04 | 2024-04-23 | <NEW SCOPE CN 1727><Review of Weld Inspection Data> - Prepare Draft EAN - Part 1 | 04-Apr-24 A | 23-Apr-24 A | 14 | 0 | 14 | 100% |  | Completed
W232LT | W232 | W232.C3050 | DNB Enhanced Safety Cases | 2024-04-04 | 2024-04-23 | <NEW SCOPE CN 1727><Review of Lifting Integrity Faults> - Prepare Draft EAN - Part 1 | 04-Apr-24 A | 23-Apr-24 A | 14 | 0 | 14 | 100% |  | Completed
W232LT | W232 | W232.A5680 | DNB Enhanced Safety Cases | 2024-04-04 | 2024-04-23 | <NEW SCOPE CN 1727><Further Review of Shock Loaded Unit Events> - Prepare Draft EAN - Part 1 | 04-Apr-24 A | 23-Apr-24 A | 14 | 0 | 14 | 100% |  | Completed
W230LT | W230 | W230.1300 | HYB Enhanced Defueling Safety Case Strategy | 2024-04-04 | 2024-05-07 | Initial high level scope of programme | 04-Apr-24 A | 07-May-24 A | 5 | 0 | 23 | 100% |  | Completed
W234LT | W234 | W234.1300 | TOR Enhanced Defueling Safety Case Strategy | 2024-04-04 | 2024-05-07 | Initial high level scope of programme | 04-Apr-24 A | 07-May-24 A | 5 | 0 | 23 | 100% |  | Completed
W232LT | W232 | W232.C1470 | DNB Enhanced Safety Cases |  | 2024-04-04 | <NEW SCOPE CN 1727><Review of Shock Loaded Unit Events> - Issue Draft EAN to EDF for Review. | 04-Apr-24 A | 04-Apr-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | 1970 | HRA Fuel Handling Essential Safety Case |  |  | Upload into AMS | 05-Apr-24 A | 19-Jul-24 A | 1 | 0 | 74 | 100% |  | Completed
ER6650LT | W226 | 1970 | HYA Fuel Handling Essential Safety Case |  |  | Upload into AMS | 05-Apr-24 A | 19-Jul-24 A | 1 | 0 | 74 | 100% |  | Completed
ER6378LT | W222 | 1969 | HRA Fuel Handling Essential Safety Case |  |  | Head Document Verification Complete | 05-Apr-24 A | 05-Apr-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 1969 | HYA Fuel Handling Essential Safety Case |  |  | Head Document Verification Complete | 05-Apr-24 A | 05-Apr-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3060 | DNB Enhanced Safety Cases | 2024-04-05 | 2024-04-23 | <NEW SCOPE CN 1727><Review of Shock Loaded Unit Events> - Draft EAN Reviewed by EDF SQEP - Part 1 | 05-Apr-24 A | 23-Apr-24 A | 13 | 0 | 13 | 100% |  | Completed
ER6666LT | W209 | W209.29570 | HYB Essential Defueling Safety Case | 2024-02-01 | 2024-03-27 | Verification Schedule Risk - (Risk Ref 28381) | 08-Apr-24 A | 08-Apr-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.29580 | HYB Essential Defueling Safety Case |  | 2024-03-28 | Risk Milestone - Verification (Risk Ref 28381) - Verification Substantially Complete | 08-Apr-24 A | 08-Apr-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.29570 | TOR Essential Defueling Safety Case | 2024-02-01 | 2024-03-27 | Verification Schedule Risk - (Risk Ref 28381) | 08-Apr-24 A | 08-Apr-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.29580 | TOR Essential Defueling Safety Case |  | 2024-03-28 | Risk Milestone - Verification (Risk Ref 28381) - Verification Substantially Complete | 08-Apr-24 A | 08-Apr-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1220 | HNB Enhanced Defuelling Safety Cases | 2024-02-19 | 2024-03-01 | Verify supporting reference <Enhanced Defueling rate EC> | 08-Apr-24 A | 19-Apr-24 A | 10 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.B4020 | DNB Enhanced Safety Cases | 2023-11-29 | 2023-11-29 | Gate B PRC Paper Submission | 10-Apr-24 A | 10-Apr-24 A | 1 | 0 | 1 | 100% |  | Completed
W230LT | W230 | W230.1860 | HYB Enhanced Defueling Safety Case Strategy | 2024-04-11 | 2024-05-15 | PM / CO and PCE Create Initial Plan of Work | 11-Apr-24 A | 15-May-24 A | 0 | 0 | 24 | 100% |  | Completed
W234LT | W234 | W234.1860 | TOR Enhanced Defueling Safety Case Strategy | 2024-04-11 | 2024-05-15 | PM / CO and PCE Create Initial Plan of Work | 11-Apr-24 A | 15-May-24 A | 0 | 0 | 24 | 100% |  | Completed
W232LT | W232 | W232.B4030 | DNB Enhanced Safety Cases | 2023-11-30 | 2023-12-06 | PRC Members Review PRC Documentation | 11-Apr-24 A | 17-Apr-24 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.29640 | HYB Essential Defueling Safety Case |  |  | Complete TR Statement - IFD EAN | 12-Apr-24 A | 23-Apr-24 A | 1 | 0 | 7 | 100% |  | Completed
ER6666LT | W209 | W209.29660 | HYB Essential Defueling Safety Case |  |  | Close Out TR Comments - (Dose Band Review & Post Fault Action EAN) | 12-Apr-24 A | 20-May-24 A | 1 | 0 | 26 | 100% |  | Completed
ER6666LT | W209 | W209.29690 | HYB Essential Defueling Safety Case |  |  | Complete Verification - (Failed Fuel Handling in ODR condition) | 12-Apr-24 A | 12-Jun-24 A | 1 | 0 | 41 | 100% |  | Completed
ER6668LT | W213 | W209.29640 | TOR Essential Defueling Safety Case |  |  | Complete TR Statement - IFD EAN | 12-Apr-24 A | 23-Apr-24 A | 1 | 0 | 7 | 100% |  | Completed
ER6668LT | W213 | W209.29660 | TOR Essential Defueling Safety Case |  |  | Close Out TR Comments - (Dose Band Review & Post Fault Action EAN) | 12-Apr-24 A | 20-May-24 A | 1 | 0 | 26 | 100% |  | Completed
ER6668LT | W213 | W209.29690 | TOR Essential Defueling Safety Case |  |  | Complete Verification - (Failed Fuel Handling in ODR condition) | 12-Apr-24 A | 12-Jun-24 A | 1 | 0 | 41 | 100% |  | Completed
ER6372LT | W203 | W203.C1270 | HNB Enhanced Defuelling Safety Cases | 2024-03-04 | 2024-03-15 | BE Technical review of supporting reference <Enhanced Defueling rate EC> | 22-Apr-24 A | 28-Jun-24 A | 10 | 0 | 48 | 100% |  | Completed
W232LT | W232 | W232.A2690 | DNB Enhanced Safety Cases |  | 2024-04-23 | Gate B PRC Paper Approval (DNB) | 23-Apr-24 A | 23-Apr-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B4300 | DNB Enhanced Safety Cases | 2023-12-12 | 2023-12-12 | Hold PRC Meeting | 23-Apr-24 A | 23-Apr-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.B4310 | DNB Enhanced Safety Cases |  | 2023-12-12 | Gate B PRC Paper Approval | 23-Apr-24 A | 23-Apr-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.B1000 | DNB Enhanced Safety Cases | 2024-04-24 | 2026-03-23 | < BASELINE COST INCREASE PENDING CN 3472>Project Management - B-D | 23-Apr-24 A | 2026-02-20 | 412 | 247 | 464 | 45% | 5 | In Progress
W232LT | W232 | W232.B1010 | DNB Enhanced Safety Cases | 2024-04-24 | 2026-03-23 | Technical Oversight - B-D | 23-Apr-24 A | 2026-02-20 | 412 | 247 | 464 | 45% | 5 | In Progress
ER6666LT | W209 | W209.29650 | HYB Essential Defueling Safety Case |  |  | Issue on CDMS - IFD EAN | 24-Apr-24 A | 30-Apr-24 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W209.29650 | TOR Essential Defueling Safety Case |  |  | Issue on CDMS - IFD EAN | 24-Apr-24 A | 30-Apr-24 A | 5 | 0 | 4 | 100% |  | Completed
W232LT | W232 | W232.C1150 | DNB Enhanced Safety Cases | 2024-04-24 | 2024-07-19 | <Review of Weld Inspection Data> - Summary | 24-Apr-24 A | 30-Sep-24 A | 106 | 0 | 110 | 100% |  | Completed
W232LT | W232 | W232.C1160 | DNB Enhanced Safety Cases | 2024-04-24 | 2024-05-23 | <Review of Weld Inspection Data> - Prepare Draft EAN - Part 2 | 24-Apr-24 A | 23-May-24 A | 21 | 0 | 21 | 100% |  | Completed
W232LT | W232 | W232.C1300 | DNB Enhanced Safety Cases | 2024-04-24 | 2024-07-12 | <Review of Lifting Integrity Faults> - Summary | 24-Apr-24 A | 30-Sep-24 A | 105 | 0 | 110 | 100% |  | Completed
W232LT | W232 | W232.C1310 | DNB Enhanced Safety Cases | 2024-04-24 | 2024-05-23 | <Review of Lifting Integrity Faults> - Prepare Draft EAN - Part 2 | 24-Apr-24 A | 13-May-24 A | 21 | 0 | 12 | 100% |  | Completed
W232LT | W232 | W232.C1450 | DNB Enhanced Safety Cases | 2024-04-24 | 2024-06-04 | <Review of Shock Loaded Unit Events> - Summary | 24-Apr-24 A | 24-May-24 A | 28 | 0 | 21 | 100% |  | Completed
W232LT | W232 | W232.C1480 | DNB Enhanced Safety Cases | 2024-04-24 | 2024-05-03 | <Review of Shock Loaded Unit Events> - Draft EAN Reviewed by EDF SQEP - Part 2 | 24-Apr-24 A | 03-May-24 A | 8 | 0 | 8 | 100% |  | Completed
W232LT | W232 | W232.C1540 | DNB Enhanced Safety Cases | 2024-04-24 | 2024-07-19 | <SCOPE NAME CHANGE CN 2615><Further Review of Shock Loaded Unit Events (Group 1)> - Summary | 24-Apr-24 A | 08-Oct-24 A | 115 | 0 | 116 | 100% |  | Completed
W232LT | W232 | W232.C1550 | DNB Enhanced Safety Cases | 2024-04-24 | 2024-05-23 | <SCOPE NAME CHANGE CN 2615><Further Review of Shock Loaded Unit Events (Group 1)> - Prepare Draft EAN - Part 2 | 24-Apr-24 A | 08-Aug-24 A | 21 | 0 | 75 | 100% |  | Completed
ER6372LT | W203 | W203.C1070 | HNB Enhanced Defuelling Safety Cases |  | 2024-03-05 | CA PJB Held | 25-Apr-24 A | 25-Apr-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1080 | HNB Enhanced Defuelling Safety Cases | 2024-03-05 | 2024-03-11 | Produce MF (as required) | 29-Apr-24 A | 10-Jun-24 A | 5 | 0 | 29 | 100% |  | Completed
ER6372LT | W203 | W203.C1380 | HNB Enhanced Defuelling Safety Cases | 2024-03-18 | 2024-04-02 | Prepare the Safety Case Proposal (including OPEX Review) | 29-Apr-24 A | 28-Jun-24 A | 10 | 0 | 42 | 100% |  | Completed
W232LT | W232 | W232.A2080 | DNB Enhanced Safety Cases | 2024-07-10 | 2024-08-28 | Rev 000 - Prepare the Safety Case Proposal (including OPEX Review) | 01-May-24 A | 08-Oct-24 A | 35 | 0 | 111 | 100% |  | Completed
ER6698LT | W224 | W224. A1010 | HRA Enhanced Defueling Safety Case | 2024-05-01 | 2024-05-28 | Prepare Schedule [FEEDS TO SUMMARY SCHEDULE] | 01-May-24 A | 28-May-24 A | 5 | 0 | 17 | 100% |  | Completed
ER6698LT | W224 | W224. A1020 | HRA Enhanced Defueling Safety Case | 2024-05-01 | 2024-05-28 | Prepare Cost Estimates | 01-May-24 A | 28-May-24 A | 5 | 0 | 17 | 100% |  | Completed
ER6698LT | W224 | W224. A1030 | HRA Enhanced Defueling Safety Case | 2024-05-01 | 2024-05-22 | Write IRM Paper | 01-May-24 A | 22-May-24 A | 15 | 0 | 15 | 100% |  | Completed
ER6701LT | W228 | W228. A1030 | HYA Enhanced Defueling Safety Case | 2024-05-01 | 2024-05-22 | Write IRM Paper | 01-May-24 A | 22-May-24 A | 15 | 0 | 15 | 100% |  | Completed
ER6701LT | W228 | W228. A1020 | HYA Enhanced Defueling Safety Case | 2024-05-01 | 2024-05-28 | Prepare Cost Estimates | 01-May-24 A | 28-May-24 A | 5 | 0 | 17 | 100% |  | Completed
ER6701LT | W228 | W228. A1010 | HYA Enhanced Defueling Safety Case | 2024-05-01 | 2024-05-28 | Prepare Schedule [FEEDS TO SUMMARY SCHEDULE] | 01-May-24 A | 28-May-24 A | 5 | 0 | 17 | 100% |  | Completed
W232LT | W232 | W232.C1490 | DNB Enhanced Safety Cases | 2024-05-07 | 2024-05-20 | <Review of Shock Loaded Unit Events> - Address Comments from EDF Review on Draft EAN | 07-May-24 A | 20-May-24 A | 10 | 0 | 10 | 100% |  | Completed
W230LT | W230 | W230.1290 | HYB Enhanced Defueling Safety Case Strategy | 2024-05-08 | 2024-05-14 | Update Schedule/Estimate from Risk Log & Add Provisions | 08-May-24 A | 14-May-24 A | 5 | 0 | 5 | 100% |  | Completed
W234LT | W234 | W234.1290 | TOR Enhanced Defueling Safety Case Strategy | 2024-05-08 | 2024-05-14 | Update Schedule/Estimate from Risk Log & Add Provisions | 08-May-24 A | 14-May-24 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | 2030 | HRA Fuel Handling Essential Safety Case |  |  | Update Verification Plan | 09-May-24 A | 10-May-24 A | 2 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | 2030 | HYA Fuel Handling Essential Safety Case |  |  | Update Verification Plan | 09-May-24 A | 10-May-24 A | 2 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | 1991 | HYA Fuel Handling Essential Safety Case |  |  | Update Proposal Peer Review | 10-May-24 A | 14-May-24 A | 3 | 0 | 3 | 100% |  | Completed
ER6378LT | W222 | 1991 | HRA Fuel Handling Essential Safety Case |  |  | Update Proposal Peer Review | 13-May-24 A | 14-May-24 A | 2 | 0 | 2 | 100% |  | Completed
ER6378LT | W222 | 2040 | HRA Fuel Handling Essential Safety Case |  |  | Secure Verification Resource | 13-May-24 A | 13-May-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 2040 | HYA Fuel Handling Essential Safety Case |  |  | Secure Verification Resource | 13-May-24 A | 13-May-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1380 | DNB Enhanced Safety Cases | 2024-05-24 | 2024-06-07 | <Review of Lifting Integrity Faults> - TSA Internal Review of Draft EAN | 14-May-24 A | 23-Jul-24 A | 10 | 0 | 49 | 100% |  | Completed
ER6378LT | W222 | 2050 | HRA Fuel Handling Essential Safety Case |  |  | Verification PJB | 14-May-24 A | 14-May-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 2050 | HYA Fuel Handling Essential Safety Case |  |  | Verification PJB | 14-May-24 A | 14-May-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | 2071 | HRA Fuel Handling Essential Safety Case |  |  | Sub-verifier(s) including GAP review (HHB OPEX) First Round | 15-May-24 A | 05-Jun-24 A | 15 | 0 | 15 | 100% |  | Completed
ER6378LT | W222 | 1992 | HRA Fuel Handling Essential Safety Case |  |  | Update Proposal (Second Draft) | 15-May-24 A | 21-May-24 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | 2068 | HRA Fuel Handling Essential Safety Case |  |  | First Round Verification - Stn Verifier Comments | 15-May-24 A | 05-Jun-24 A | 15 | 0 | 15 | 100% |  | Completed
ER6378LT | W222 | 2060 | HRA Fuel Handling Essential Safety Case |  |  | Verification including GAP review (Lead Verifier)(HHB OPEX) First Round | 15-May-24 A | 05-Jun-24 A | 15 | 0 | 15 | 100% |  | Completed
ER6378LT | W222 | 2070 | HRA Fuel Handling Essential Safety Case |  |  | Sub-verifier(s) including GAP review (HHB OPEX) First Round | 15-May-24 A | 05-Jun-24 A | 15 | 0 | 15 | 100% |  | Completed
ER6650LT | W226 | 2071 | HYA Fuel Handling Essential Safety Case |  |  | Sub-verifier(s) including GAP review (HHB OPEX) First Round | 15-May-24 A | 08-Jul-24 A | 15 | 0 | 38 | 100% |  | Completed
ER6650LT | W226 | 1992 | HYA Fuel Handling Essential Safety Case |  |  | Update Proposal (Second Draft) | 15-May-24 A | 21-May-24 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | 2068 | HYA Fuel Handling Essential Safety Case |  |  | First Round Verification - Stn Verifier Comments | 15-May-24 A | 08-Jul-24 A | 15 | 0 | 38 | 100% |  | Completed
ER6650LT | W226 | 2060 | HYA Fuel Handling Essential Safety Case |  |  | Verification including GAP review (Lead Verifier)(HHB OPEX) First Round | 15-May-24 A | 01-Jul-24 A | 15 | 0 | 32 | 100% |  | Completed
ER6650LT | W226 | 2070 | HYA Fuel Handling Essential Safety Case |  |  | Sub-verifier(s) including GAP review (HHB OPEX) First Round | 15-May-24 A | 08-Jul-24 A | 15 | 0 | 38 | 100% |  | Completed
W230LT | W230 | W230.1280 | HYB Enhanced Defueling Safety Case Strategy | 2024-05-15 | 2024-06-03 | Draft / Add Data to PRC/IMS2 Paper | 15-May-24 A | 03-Jun-24 A | 5 | 0 | 13 | 100% |  | Completed
W230LT | W230 | W230.1270 | HYB Enhanced Defueling Safety Case Strategy | 2024-05-15 | 2025-08-19 | Summary for HYB Fuel Handling Enhanced Safety Cases W230 | 15-May-24 A | 2026-05-19 | 321 | 306 | 509 | 0% | 0 | In Progress
W234LT | W234 | W234.1280 | TOR Enhanced Defueling Safety Case Strategy | 2024-05-15 | 2024-06-03 | Draft / Add Data to PRC/IMS2 Paper | 15-May-24 A | 03-Jun-24 A | 5 | 0 | 13 | 100% |  | Completed
W234LT | W234 | W234.1270 | TOR Enhanced Defueling Safety Case Strategy | 2024-05-15 | 2025-08-19 | Summary for TOR Fuel Handling Enhanced Safety Cases W230 | 15-May-24 A | 2026-05-19 | 321 | 306 | 509 | 0% | 0 | In Progress
W230LT | W230 | W230.1880 | HYB Enhanced Defueling Safety Case Strategy | 2024-05-16 | 2024-05-16 | Appoint CO / AE / RE | 16-May-24 A | 16-May-24 A | 1 | 0 | 1 | 100% |  | Completed
W234LT | W234 | W234.1880 | TOR Enhanced Defueling Safety Case Strategy | 2024-05-16 | 2024-05-16 | Appoint CO / AE / RE | 16-May-24 A | 16-May-24 A | 1 | 0 | 1 | 100% |  | Completed
W230LT | W230 | W230.1890 | HYB Enhanced Defueling Safety Case Strategy | 2024-05-17 | 2024-05-17 | Key Stakeholders Identified | 17-May-24 A | 17-May-24 A | 1 | 0 | 1 | 100% |  | Completed
W234LT | W234 | W234.1890 | TOR Enhanced Defueling Safety Case Strategy | 2024-05-17 | 2024-05-17 | Key Stakeholders Identified | 17-May-24 A | 17-May-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1500 | DNB Enhanced Safety Cases |  | 2024-05-20 | <Review of Shock Loaded Unit Events> - Issue Final EAN | 20-May-24 A | 20-May-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A4990 | DNB Enhanced Safety Cases |  |  | Lessons Learned Workshop - FPU Safety Case Ph 3 NSRS Approved | 21-May-24 A | 21-May-24 A | 1 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.1200 | HRA Fuel Handling Essential Safety Case | 2023-07-10 | 2023-08-04 | Verification and SAs of the case (using BARRIER MODEL) (PART 2 - IMPACT from EVENT RECOVERY) | 21-May-24 A | 16-Jul-24 A | 40 | 0 | 40 | 100% |  | Completed
ER6650LT | W226 | W226.1200 | HYA Fuel Handling Essential Safety Case | 2023-07-10 | 2023-08-04 | Verification of the case (using BARRIER MODEL) (PART 2 - IMPACT from EVENT RECOVERY) | 21-May-24 A | 16-Jul-24 A | 40 | 0 | 40 | 100% |  | Completed
ER6650LT | W226 | W226.3020 | HYA Fuel Handling Essential Safety Case | 2023-07-10 | 2023-07-10 | Lesson Learn - Event Recovery Phase | 21-May-24 A | 21-May-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1510 | DNB Enhanced Safety Cases | 2024-05-21 | 2024-06-04 | <Review of Shock Loaded Unit Events> - EAN Completed and Uploaded to CDMS | 21-May-24 A | 24-May-24 A | 10 | 0 | 3 | 100% |  | Completed
ER6666LT | W209 | W209.29670 | HYB Essential Defueling Safety Case |  |  | Complete TR Statement - (Dose Band Review & Post Fault Action EAN) | 21-May-24 A | 23-May-24 A | 3 | 0 | 3 | 100% |  | Completed
ER6668LT | W213 | W209.29670 | TOR Essential Defueling Safety Case |  |  | Complete TR Statement - (Dose Band Review & Post Fault Action EAN) | 21-May-24 A | 23-May-24 A | 3 | 0 | 3 | 100% |  | Completed
ER6378LT | W222 | W222.1210 | HRA Fuel Handling Essential Safety Case |  | 2023-07-07 | EVENT RECOVERY MILESTONE - AMS Milestone - EC Ready for Review - Activity No 2020 | 21-May-24 A | 21-May-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.1210 | HYA Fuel Handling Essential Safety Case |  | 2023-07-07 | EVENT RECOVERY MILESTONE - AMS Milestone - EC Ready for Review - Activity No 2020 | 21-May-24 A | 21-May-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 2020 | HYA Fuel Handling Essential Safety Case |  |  | AMS Milestone - Ready for Review | 21-May-24 A | 21-May-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A27485 | HRA Fuel Handling Essential Safety Case |  |  | AMS Ready for Review | 21-May-24 A | 21-May-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27485 | HYA Fuel Handling Essential Safety Case |  |  | AMS Ready for Review | 21-May-24 A | 21-May-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224. A1040 | HRA Enhanced Defueling Safety Case | 2024-05-23 | 2024-06-07 | IRM Paper stakeholder sign off | 23-May-24 A | 07-Jun-24 A | 5 | 0 | 11 | 100% |  | Completed
ER6701LT | W228 | W228. A1040 | HYA Enhanced Defueling Safety Case | 2024-05-23 | 2024-06-07 | IRM Paper stakeholder sign off | 23-May-24 A | 07-Jun-24 A | 5 | 0 | 11 | 100% |  | Completed
W232LT | W232 | W232.C1520 | DNB Enhanced Safety Cases |  | 2024-06-04 | <Review of Shock Loaded Unit Events> - EAN Completed | 24-May-24 A | 24-May-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1230 | DNB Enhanced Safety Cases | 2024-05-24 | 2024-06-07 | <Review of Weld Inspection Data> - TSA Internal Review of Draft EAN | 24-May-24 A | 21-Jun-24 A | 10 | 0 | 19 | 100% |  | Completed
ER6666LT | W209 | W209.29680 | HYB Essential Defueling Safety Case |  |  | Issue on CDMS - (Dose Band Review & Post Fault Action EAN) | 24-May-24 A | 03-Jun-24 A | 5 | 0 | 6 | 100% |  | Completed
ER6668LT | W213 | W209.29680 | TOR Essential Defueling Safety Case |  |  | Issue on CDMS - (Dose Band Review & Post Fault Action EAN) | 24-May-24 A | 03-Jun-24 A | 5 | 0 | 6 | 100% |  | Completed
ER6698LT | W224 | W224.1340 | HRA Enhanced Defueling Safety Case | 2024-05-28 | 2024-06-07 | RFS | 28-May-24 A | 07-Jun-24 A | 10 | 0 | 9 | 100% |  | Completed
ER6701LT | W228 | W228.1340 | HYA Enhanced Defueling Safety Case | 2024-05-28 | 2024-06-07 | RFS | 28-May-24 A | 07-Jun-24 A | 10 | 0 | 9 | 100% |  | Completed
ER6378LT | W222 | W222.3020 | HRA Fuel Handling Essential Safety Case | 2023-07-10 | 2023-07-10 | Lesson Learn - Event Recovery Phase | 28-May-24 A | 28-May-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.1495 | HYB Essential Defueling Safety Case | 2024-03-28 | 2024-04-26 | Final Verification - (Including = CLAIM 7 Update and Detailed Check) | 31-May-24 A | 18-Sep-24 A | 20 | 0 | 78 | 100% |  | Completed
ER6668LT | W213 | W213.1495 | TOR Essential Defueling Safety Case | 2024-03-28 | 2024-04-26 | Final Verification - (Including = CLAIM 7 Update and Detailed Check) | 31-May-24 A | 18-Sep-24 A | 20 | 0 | 78 | 100% |  | Completed
ER6698LT | W224 | W224.1250 | HRA Enhanced Defueling Safety Case | 2024-06-03 | 2024-06-14 | RFS | 03-Jun-24 A | 14-Jun-24 A | 1 | 0 | 10 | 100% |  | Completed
ER6698LT | W224 | W224.3810 | HRA Enhanced Defueling Safety Case | 2024-06-03 | 2025-02-04 | WBS Cost Summary Analysis in support of Tie Bar Buckling | 03-Jun-24 A | 2025-03-03 | 162 | 0 | 191 | 100% | 251 | In Progress
ER6701LT | W228 | W228.3810 | HYA Enhanced Defueling Safety Case | 2024-06-03 | 2025-02-03 | WBS Cost Summary Analysis in support of Tie Bar Buckling | 03-Jun-24 A | 03-Feb-25 A | 162 | 0 | 171 | 100% |  | Completed
ER6701LT | W228 | W228.1250 | HYA Enhanced Defueling Safety Case | 2024-06-03 | 2024-06-14 | RFS | 03-Jun-24 A | 14-Jun-24 A | 1 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.A31290 | HYB Essential Defueling Safety Case |  |  | Technical Review of PSA Documentation | 04-Jun-24 A | 17-Jun-24 A | 10 | 0 | 10 | 100% |  | Completed
ER6668LT | W213 | W213.A31290 | TOR Essential Defueling Safety Case |  |  | Technical Review of PSA Documentation | 04-Jun-24 A | 17-Jun-24 A | 10 | 0 | 10 | 100% |  | Completed
W230LT | W230 | W230.1320 | HYB Enhanced Defueling Safety Case Strategy | 2024-06-04 | 2024-06-07 | Prepare Draft Project Definition Document (PDD) | 04-Jun-24 A | 07-Jun-24 A | 4 | 0 | 4 | 100% |  | Completed
W230LT | W230 | W230.1970 | HYB Enhanced Defueling Safety Case Strategy | 2024-06-04 | 2024-06-17 | Verified by TSA | 04-Jun-24 A | 17-Jun-24 A | 10 | 0 | 10 | 100% |  | Completed
W234LT | W234 | W234.1320 | TOR Enhanced Defueling Safety Case Strategy | 2024-06-04 | 2024-06-07 | Prepare Draft Project Definition Document (PDD) | 04-Jun-24 A | 07-Jun-24 A | 4 | 0 | 4 | 100% |  | Completed
W234LT | W234 | W234.1970 | TOR Enhanced Defueling Safety Case Strategy | 2024-06-04 | 2024-06-17 | Verified by TSA | 04-Jun-24 A | 17-Jun-24 A | 10 | 0 | 10 | 100% |  | Completed
ER6378LT | W222 | 2072 | HRA Fuel Handling Essential Safety Case |  |  | Respond to First Round Comments | 06-Jun-24 A | 08-Jul-24 A | 23 | 0 | 23 | 100% |  | Completed
W230LT | W230 | W230.1330 | HYB Enhanced Defueling Safety Case Strategy | 2024-06-10 | 2024-06-11 | PCL Validate & Approve Baseline Package for PRC Submission | 10-Jun-24 A | 11-Jun-24 A | 2 | 0 | 2 | 100% |  | Completed
W234LT | W234 | W234.1330 | TOR Enhanced Defueling Safety Case Strategy | 2024-06-10 | 2024-06-11 | PCL Validate & Approve Baseline Package for PRC Submission | 10-Jun-24 A | 11-Jun-24 A | 2 | 0 | 2 | 100% |  | Completed
ER6372LT | W203 | W203.C1110 | HNB Enhanced Defuelling Safety Cases |  | 2024-03-11 | Issue MF (as required) | 10-Jun-24 A | 10-Jun-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1160 | HNB Enhanced Defuelling Safety Cases | 2024-03-12 | 2024-03-18 | Produce draft NSRS (using BARRIER MODEL) | 11-Jun-24 A | 14-Jun-24 A | 4 | 0 | 4 | 100% |  | Completed
ER6372LT | W203 | W203.C1120 | HNB Enhanced Defuelling Safety Cases | 2024-03-12 | 2024-03-18 | Categorisation by RE / Station | 11-Jun-24 A | 12-Jun-24 A | 2 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.29700 | HYB Essential Defueling Safety Case |  |  | Issue on CDMS - (Failed Fuel Handling in ODR condition) | 12-Jun-24 A | 12-Jun-24 A | 5 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W209.29700 | TOR Essential Defueling Safety Case |  |  | Issue on CDMS - (Failed Fuel Handling in ODR condition) | 12-Jun-24 A | 12-Jun-24 A | 5 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224. A1050 | HRA Enhanced Defueling Safety Case |  | 2024-06-12 | Gate A PRC Paper Submission | 12-Jun-24 A | 12-Jun-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6701LT | W228 | W228. A1050 | HYA Enhanced Defueling Safety Case |  | 2024-06-12 | Gate A PRC Paper Submission | 12-Jun-24 A | 12-Jun-24 A | 0 | 0 | 0 | 100% |  | Completed
W230LT | W230 | W230.1340 | HYB Enhanced Defueling Safety Case Strategy | 2024-06-12 | 2024-06-12 | Gate A PRC Paper Submission | 12-Jun-24 A | 12-Jun-24 A | 1 | 0 | 1 | 100% |  | Completed
W234LT | W234 | W234.1340 | TOR Enhanced Defueling Safety Case Strategy | 2024-06-12 | 2024-06-12 | Gate A PRC Paper Submission | 12-Jun-24 A | 12-Jun-24 A | 1 | 0 | 1 | 100% |  | Completed
W230LT | W230 | W230.1360 | HYB Enhanced Defueling Safety Case Strategy | 2024-06-13 | 2024-06-24 | PRC Members Review PRC/IMS2 Documentation | 13-Jun-24 A | 24-Jun-24 A | 8 | 0 | 8 | 100% |  | Completed
W234LT | W234 | W234.1360 | TOR Enhanced Defueling Safety Case Strategy | 2024-06-13 | 2024-06-24 | PRC Members Review PRC/IMS2 Documentation | 13-Jun-24 A | 24-Jun-24 A | 8 | 0 | 8 | 100% |  | Completed
ER6372LT | W203 | W203.C1200 | HNB Enhanced Defuelling Safety Cases | 2024-03-19 | 2024-03-28 | Station comments on NSRS | 17-Jun-24 A | 18-Jun-24 A | 2 | 0 | 2 | 100% |  | Completed
ER6372LT | W203 | W203.C1210 | HNB Enhanced Defuelling Safety Cases | 2024-03-19 | 2024-03-28 | Key Stakeholders (Peer) comments on NSRS (as required) | 17-Jun-24 A | 18-Jun-24 A | 2 | 0 | 2 | 100% |  | Completed
ER6372LT | W203 | W203.C1250 | HNB Enhanced Defuelling Safety Cases | 2024-04-03 | 2024-04-16 | Develop plan with further iterations | 17-Jun-24 A | 26-Jun-24 A | 10 | 0 | 7 | 100% |  | Completed
W230LT | W230 | W230.1980 | HYB Enhanced Defueling Safety Case Strategy |  | 2024-06-17 | Issued to EDF for Technical Reviews | 17-Jun-24 A | 17-Jun-24 A | 0 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.1980 | TOR Enhanced Defueling Safety Case Strategy |  | 2024-06-17 | Issued to EDF for Technical Reviews | 17-Jun-24 A | 17-Jun-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A31300 | HYB Essential Defueling Safety Case |  |  | Supplier Update and Issue PSA Documentation | 18-Jun-24 A | 24-Jun-24 A | 5 | 0 | 5 | 100% |  | Completed
ER6668LT | W213 | W213.A31300 | TOR Essential Defueling Safety Case |  |  | Supplier Update and Issue PSA Documentation | 18-Jun-24 A | 24-Jun-24 A | 5 | 0 | 5 | 100% |  | Completed
W230LT | W230 | W230.1990 | HYB Enhanced Defueling Safety Case Strategy | 2024-06-18 | 2024-06-28 | Tech Review by EDF SQEP | 18-Jun-24 A | 28-Jun-24 A | 9 | 0 | 9 | 100% |  | Completed
W234LT | W234 | W234.1990 | TOR Enhanced Defueling Safety Case Strategy | 2024-06-18 | 2024-06-28 | Tech Review by EDF SQEP | 18-Jun-24 A | 28-Jun-24 A | 9 | 0 | 9 | 100% |  | Completed
ER6372LT | W203 | W203.C1230 | HNB Enhanced Defuelling Safety Cases |  | 2024-03-28 | INSA Resource Identified | 18-Jun-24 A | 18-Jun-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1150 | HNB Enhanced Defuelling Safety Cases | 2024-03-19 | 2024-03-20 | INSA agree MF (as required) *(EC375412)* | 20-Jun-24 A | 20-Jun-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.C1180 | HNB Enhanced Defuelling Safety Cases |  | 2024-03-20 | INSA Approval Date Identified | 20-Jun-24 A | 20-Jun-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1190 | HNB Enhanced Defuelling Safety Cases |  | 2024-03-20 | Provide Provisional NSC Date (as required) | 20-Jun-24 A | 20-Jun-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1170 | DNB Enhanced Safety Cases |  | 2024-06-07 | <Review of Weld Inspection Data> - Issue Draft EAN to EDF for Review. | 21-Jun-24 A | 21-Jun-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1240 | HNB Enhanced Defuelling Safety Cases | 2024-04-02 | 2024-04-08 | INA comments on NSRS | 24-Jun-24 A | 28-Jun-24 A | 5 | 0 | 5 | 100% |  | Completed
ER6698LT | W224 | W224.1010 | HRA Enhanced Defueling Safety Case | 2024-06-24 | 2024-12-31 | Sunk Cost (Mar - Dec 24) | 24-Jun-24 A | 31-Dec-24 A | 1 | 0 | 133 | 100% |  | Completed
ER6698LT | W224 | W224.A1010 | HRA Enhanced Defueling Safety Case |  | 2024-06-25 | Gate A for Defuelling Programme Enhancement ECs (HH1) | 25-Jun-24 A | 25-Jun-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6701LT | W228 | W228.A1010 | HYA Enhanced Defueling Safety Case |  | 2024-06-25 | Gate A for Defuelling Programme Enhancement ECs (HH1) | 25-Jun-24 A | 25-Jun-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.A1061 | HRA Enhanced Defueling Safety Case | 2024-06-25 | 2024-06-25 | Hold PRC | 25-Jun-24 A | 25-Jun-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.A31310 | HYB Essential Defueling Safety Case |  |  | Complete TR Form and PSA Documentation to CDMS | 25-Jun-24 A | 31-Jul-24 A | 10 | 0 | 27 | 100% |  | Completed
ER6668LT | W213 | W213.A31310 | TOR Essential Defueling Safety Case |  |  | Complete TR Form and PSA Documentation to CDMS | 25-Jun-24 A | 31-Jul-24 A | 10 | 0 | 27 | 100% |  | Completed
ER6701LT | W228 | W228.A1061 | HYA Enhanced Defueling Safety Case | 2024-06-25 | 2024-06-25 | Hold PRC | 25-Jun-24 A | 25-Jun-24 A | 1 | 0 | 1 | 100% |  | Completed
W230LT | W230 | W230.1390 | HYB Enhanced Defueling Safety Case Strategy | 2024-06-25 | 2024-06-25 | Hold PRC Meeting | 25-Jun-24 A | 25-Jun-24 A | 1 | 0 | 1 | 100% |  | Completed
W234LT | W234 | W234.1390 | TOR Enhanced Defueling Safety Case Strategy | 2024-06-25 | 2024-06-25 | Hold PRC Meeting | 25-Jun-24 A | 25-Jun-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6698LT | W224 | W224. A1070 | HRA Enhanced Defueling Safety Case |  | 2024-06-25 | Gate A PRC Paper Approval | 25-Jun-24 A | 25-Jun-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6701LT | W228 | W228. A1070 | HYA Enhanced Defueling Safety Case |  | 2024-06-25 | Gate A PRC Paper Approval | 25-Jun-24 A | 25-Jun-24 A | 0 | 0 | 0 | 100% |  | Completed
W230LT | W230 | W230.1120 | HYB Enhanced Defueling Safety Case Strategy |  | 2024-06-25 | Gate A Approved | 25-Jun-24 A | 25-Jun-24 A | 0 | 0 | 0 | 100% |  | Completed
W230LT | W230 | W230.1350 | HYB Enhanced Defueling Safety Case Strategy |  | 2024-06-25 | Gate A PRC Paper Approval | 25-Jun-24 A | 25-Jun-24 A | 0 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.1120 | TOR Enhanced Defueling Safety Case Strategy |  | 2024-06-25 | Gate A Approved | 25-Jun-24 A | 25-Jun-24 A | 0 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.1350 | TOR Enhanced Defueling Safety Case Strategy |  | 2024-06-25 | Gate A PRC Paper Approval | 25-Jun-24 A | 25-Jun-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1330 | HNB Enhanced Defuelling Safety Cases |  | 2024-04-16 | Verifier PJB Held | 26-Jun-24 A | 26-Jun-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.A1160 | HRA Enhanced Defueling Safety Case | 2024-06-26 | 2025-02-12 | Gate A-B Programme Management External - Cost Summary | 26-Jun-24 A | 12-Feb-25 A | 127 | 0 | 162 | 100% |  | Completed
ER6698LT | W224 | W224.A1170 | HRA Enhanced Defueling Safety Case | 2024-06-26 | 2025-02-12 | Gate A-B Programme Management Internal - Cost Summary | 26-Jun-24 A | 12-Feb-25 A | 0 | 0 | 162 | 100% |  | Completed
ER6698LT | W224 | W224. A1080 | HRA Enhanced Defueling Safety Case | 2024-06-26 | 2024-07-10 | Funds Released | 26-Jun-24 A | 10-Jul-24 A | 12 | 0 | 11 | 100% |  | Completed
ER6701LT | W228 | W228. A1080 | HYA Enhanced Defueling Safety Case | 2024-06-26 | 2024-07-09 | Funds Released | 26-Jun-24 A | 09-Jul-24 A | 12 | 0 | 10 | 100% |  | Completed
ER6701LT | W228 | W228.A1170 | HYA Enhanced Defueling Safety Case | 2024-06-26 | 2025-02-12 | Gate A-B Programme Management Internal - Cost Summary | 26-Jun-24 A | 12-Feb-25 A | 0 | 0 | 162 | 100% |  | Completed
ER6701LT | W228 | W228.A1160 | HYA Enhanced Defueling Safety Case | 2024-06-26 | 2025-02-12 | Gate A-B Programme Management External - Cost Summary | 26-Jun-24 A | 12-Feb-25 A | 127 | 0 | 162 | 100% |  | Completed
W230LT | W230 | W230.1380 | HYB Enhanced Defueling Safety Case Strategy | 2024-06-26 | 2024-06-28 | Modify Estimate, Schedule & Risk Log as Required | 26-Jun-24 A | 28-Jun-24 A | 3 | 0 | 3 | 100% |  | Completed
W234LT | W234 | W234.1380 | TOR Enhanced Defueling Safety Case Strategy | 2024-06-26 | 2024-06-28 | Modify Estimate, Schedule & Risk Log as Required | 26-Jun-24 A | 28-Jun-24 A | 3 | 0 | 3 | 100% |  | Completed
W230LT | W230 | W230.1370 | HYB Enhanced Defueling Safety Case Strategy | 2024-06-27 | 2024-06-28 | Modify PRC Paper as Required | 27-Jun-24 A | 28-Jun-24 A | 2 | 0 | 2 | 100% |  | Completed
W234LT | W234 | W234.1370 | TOR Enhanced Defueling Safety Case Strategy | 2024-06-27 | 2024-06-28 | Modify PRC Paper as Required | 27-Jun-24 A | 28-Jun-24 A | 2 | 0 | 2 | 100% |  | Completed
ER6666LT | W209 | W209.A29160 | HYB Essential Defueling Safety Case | 2023-08-09 | 2023-08-30 | Verify Defuelling Worker Risk Assessment EAN & Issue for Technical Review | 28-Jun-24 A | 26-Jul-24 A | 5 | 0 | 21 | 100% |  | Completed
ER6668LT | W213 | W213.A29160 | TOR Essential Defueling Safety Case | 2023-08-09 | 2023-08-30 | Verify Defuelling Worker Risk Assessment EAN & Issue for Technical Review | 28-Jun-24 A | 26-Jul-24 A | 5 | 0 | 21 | 100% |  | Completed
ER6372LT | W203 | W203.C1280 | HNB Enhanced Defuelling Safety Cases | 2024-04-16 | 2024-04-16 | Issue final NSRS | 28-Jun-24 A | 28-Jun-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.C1290 | HNB Enhanced Defuelling Safety Cases |  | 2024-04-16 | Station agree NSRS *(EC375412)* | 28-Jun-24 A | 28-Jun-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1340 | HNB Enhanced Defuelling Safety Cases | 2024-04-17 | 2024-04-23 | Consolidate & issue to stakeholders & suppliers agreed NSRS (as required) | 28-Jun-24 A | 28-Jun-24 A | 1 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1260 | HNB Enhanced Defuelling Safety Cases | 2024-04-09 | 2024-04-15 | Incorporate INA, Station, ED (peer) comments | 28-Jun-24 A | 28-Jun-24 A | 2 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.C1300 | HNB Enhanced Defuelling Safety Cases |  | 2024-04-16 | Key Stakeholders agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 28-Jun-24 A | 28-Jun-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1350 | HNB Enhanced Defuelling Safety Cases |  | 2024-04-23 | Issue agreed work programme to stakeholders & suppliers | 28-Jun-24 A | 28-Jun-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1320 | HNB Enhanced Defuelling Safety Cases |  | 2024-04-16 | INA agree NSRS | 28-Jun-24 A | 28-Jun-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A4190 | HNB Enhanced Defuelling Safety Cases |  | 2024-03-15 | All key supporting technical references complete - Enhanced Defueling rate EC | 28-Jun-24 A | 28-Jun-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1360 | HNB Enhanced Defuelling Safety Cases |  | 2024-03-15 | Supporting reference <Enhanced Defueling rate EC> approved | 28-Jun-24 A | 28-Jun-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1370 | HNB Enhanced Defuelling Safety Cases |  | 2024-03-15 | All supporting references completed | 28-Jun-24 A | 28-Jun-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1330 | DNB Enhanced Safety Cases | 2024-06-10 | 2024-06-21 | <Review of Lifting Integrity Faults> - Draft EAN Reviewed by EDF SQEP | 01-Jul-24 A | 09-Aug-24 A | 10 | 0 | 30 | 100% |  | Completed
ER6650LT | W226 | 2072 | HYA Fuel Handling Essential Safety Case |  |  | Respond to First Round Comments | 01-Jul-24 A | 08-Jul-24 A | 6 | 0 | 6 | 100% |  | Completed
W232LT | W232 | W232.A3050 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 2164> Rev 000 - ONR Approval of Safety Case (Letter sent to initiate) EC 374183 KDM | 01-Jul-24 A | 01-Jul-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A3060 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 2164> Rev 000 - KDM - ONR Agree/Acknowledge Safety Case EC 374183 KDM | 01-Jul-24 A | 01-Jul-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5550 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 2164> Rev 001 - ONR Approval of Safety Case (Letter sent to initiate) EC 374183 KDM | 01-Jul-24 A | 01-Jul-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5560 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 2164> Rev 001 - KDM - ONR Agree/Acknowledge Safety Case EC 374183 KDM | 01-Jul-24 A | 01-Jul-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.1410 | HRA Enhanced Defueling Safety Case | 2024-07-01 | 2024-07-12 | Contract Award | 01-Jul-24 A | 12-Jul-24 A | 10 | 0 | 10 | 100% |  | Completed
ER6701LT | W228 | W228.1410 | HYA Enhanced Defueling Safety Case | 2024-07-01 | 2024-07-12 | Contract Award | 01-Jul-24 A | 12-Jul-24 A | 10 | 0 | 10 | 100% |  | Completed
W772LT | W772 | W772LT.A1260 | DNB Pull Harder Safety Case | 2024-07-01 | 2024-07-25 | Mod Requested, Identify RE and EC Request Raised and Screened | 01-Jul-24 A | 25-Jul-24 A | 19 | 0 | 19 | 100% |  | Completed
W772LT | W772 | W772LT.A2200 | DNB Pull Harder Safety Case | 2024-07-01 |  | Project Start | 01-Jul-24 A | 01-Jul-24 A | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.D2080 | DNB Pull Harder Safety Case | 2024-07-01 | 2024-11-22 | Project Management - Pre Gate A | 01-Jul-24 A | 04-Oct-24 A | 104 | 0 | 68 | 100% |  | Completed
W772LT | W772 | W772LT.D2110 | DNB Pull Harder Safety Case | 2024-07-01 | 2024-11-22 | Technical Support - Pre Gate A | 01-Jul-24 A | 04-Oct-24 A | 104 | 0 | 68 | 100% |  | Completed
ER6698LT | W224 | W224.1280 | HRA Enhanced Defueling Safety Case | 2024-07-03 | 2024-07-26 | EDF Review and contract awards | 03-Jul-24 A | 26-Jul-24 A | 15 | 0 | 18 | 100% |  | Completed
ER6701LT | W228 | W228.1280 | HYA Enhanced Defueling Safety Case | 2024-07-03 | 2024-07-26 | EDF Review and contract awards | 03-Jul-24 A | 26-Jul-24 A | 1 | 0 | 18 | 100% |  | Completed
ER6701LT | W228 | W228.3740 | HYA Enhanced Defueling Safety Case | 2024-07-05 | 2024-07-19 | EC Register | 05-Jul-24 A | 19-Jul-24 A | 10 | 0 | 11 | 100% |  | Completed
ER6698LT | W224 | W224.3740 | HRA Enhanced Defueling Safety Case | 2024-07-05 | 2024-07-15 | EC Register | 05-Jul-24 A | 15-Jul-24 A | 10 | 0 | 5 | 100% |  | Completed
ER6372LT | W203 | W203.C1400 | HNB Enhanced Defuelling Safety Cases |  | 2024-04-30 | Issue to CO & Station for comments | 05-Jul-24 A | 05-Jul-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.1190 | HRA Enhanced Defueling Safety Case | 2024-07-08 | 2024-08-09 | RFS - Trip Function | 08-Jul-24 A | 09-Aug-24 A | 10 | 0 | 25 | 100% |  | Completed
ER6701LT | W228 | W228.1190 | HYA Enhanced Defueling Safety Case | 2024-07-08 | 2024-08-09 | RFS - Trip Function | 08-Jul-24 A | 09-Aug-24 A | 10 | 0 | 25 | 100% |  | Completed
ER6372LT | W203 | W203.D1390 | HNB Enhanced Defuelling Safety Cases | 2024-07-08 |  | Mod requested, Initiate EC, identify RE, register EC & identify milestones in AMS | 08-Jul-24 A | 08-Jul-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1470 | HNB Enhanced Defuelling Safety Cases | 2024-07-08 | 2024-07-15 | Raise Engineering Request (as required) | 08-Jul-24 A | 15-Jul-24 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | 2075 | HYA Fuel Handling Essential Safety Case |  |  | Station Verifiers (HHB OPEX) Second Round | 08-Jul-24 A | 16-Jul-24 A | 7 | 0 | 7 | 100% |  | Completed
ER6650LT | W226 | 2076 | HYA Fuel Handling Essential Safety Case |  |  | Lead Verifier Second Round | 08-Jul-24 A | 16-Jul-24 A | 7 | 0 | 7 | 100% |  | Completed
ER6650LT | W226 | 2074 | HYA Fuel Handling Essential Safety Case |  |  | Sub-verifier(s) including GAP review (HHB OPEX) Second Round | 08-Jul-24 A | 16-Jul-24 A | 7 | 0 | 7 | 100% |  | Completed
ER6650LT | W226 | 2073 | HYA Fuel Handling Essential Safety Case |  |  | Sub-verifier(s) including GAP review (HHB OPEX) Second Round | 08-Jul-24 A | 16-Jul-24 A | 10 | 0 | 7 | 100% |  | Completed
ER6650LT | W226 | 2082 | HYA Fuel Handling Essential Safety Case |  |  | CTO Civils, Nuclear Liabilities, Environmental (GEM), Specialist Assessment(s) | 08-Jul-24 A | 16-Jul-24 A | 7 | 0 | 7 | 100% |  | Completed
ER6650LT | W226 | 2081 | HYA Fuel Handling Essential Safety Case |  |  | HYA Nuclear Safety, Env, Rad Protection, Radwaste, Ops, Emergency Arrangements, Specialist Assessment(s) | 08-Jul-24 A | 16-Jul-24 A | 7 | 0 | 7 | 100% |  | Completed
ER6650LT | W226 | 2080 | HYA Fuel Handling Essential Safety Case |  |  | HRA Nuclear Safety, Env, Rad Protection, Radwaste, Ops, Emergency Arrangements,Chemistry,Specialist Assessment(s) | 08-Jul-24 A | 16-Jul-24 A | 7 | 0 | 7 | 100% |  | Completed
ER6378LT | W222 | 2075 | HRA Fuel Handling Essential Safety Case |  |  | Station Verifiers (HHB OPEX) Second Round | 09-Jul-24 A | 16-Jul-24 A | 10 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | 2076 | HRA Fuel Handling Essential Safety Case |  |  | Lead Verifier Second Round | 09-Jul-24 A | 16-Jul-24 A | 10 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | 2074 | HRA Fuel Handling Essential Safety Case |  |  | Sub-verifier(s) including GAP review (HHB OPEX) Second Round | 09-Jul-24 A | 16-Jul-24 A | 10 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | 2073 | HRA Fuel Handling Essential Safety Case |  |  | Sub-verifier(s) including GAP review (HHB OPEX) Second Round | 09-Jul-24 A | 16-Jul-24 A | 10 | 0 | 6 | 100% |  | Completed
ER6378LT | W222 | 2082 | HRA Fuel Handling Essential Safety Case |  |  | CTO Civils, Nuclear Liabilities, Environmental (GEM), Specialist Assessment(s) | 09-Jul-24 A | 16-Jul-24 A | 10 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | 2081 | HRA Fuel Handling Essential Safety Case |  |  | HYA Nuclear Safety, Env, Rad Protection, Radwaste, Ops, Emergency Arrangements, Specialist Assessment(s) | 09-Jul-24 A | 16-Jul-24 A | 10 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | 2080 | HRA Fuel Handling Essential Safety Case |  |  | HRA Nuclear Safety, Env, Rad Protection, Radwaste, Ops, Emergency Arrangements,Chemistry,Specialist Assessment(s) | 09-Jul-24 A | 16-Jul-24 A | 10 | 0 | 5 | 100% |  | Completed
W230LT | W230 | W230.3710 | HYB Enhanced Defueling Safety Case Strategy | 2024-07-01 | 2024-07-05 | Tech Review by EDF SQEP (Continued) | 12-Jul-24 A | 18-Jul-24 A | 5 | 0 | 5 | 100% |  | Completed
W230LT | W230 | W230.3720 | HYB Enhanced Defueling Safety Case Strategy | 2024-07-01 | 2024-08-12 | ## Technical Development / Project Management - Gate A - D - (Cost Summary) ## | 12-Jul-24 A | 20-Dec-24 A | 115 | 0 | 115 | 100% |  | Completed
W234LT | W234 | W234.3710 | TOR Enhanced Defueling Safety Case Strategy | 2024-07-01 | 2024-07-05 | Tech Review by EDF SQEP (Continued) | 12-Jul-24 A | 18-Jul-24 A | 5 | 0 | 5 | 100% |  | Completed
W234LT | W234 | W234.3720 | TOR Enhanced Defueling Safety Case Strategy | 2024-07-01 | 2024-08-12 | ## Technical Development / Project Management - Gate A - D - (Cost Summary) ## | 12-Jul-24 A | 20-Dec-24 A | 115 | 0 | 115 | 100% |  | Completed
ER6372LT | W203 | W203.D1680 | HNB Enhanced Defuelling Safety Cases |  | 2024-07-15 | CO & CA appointed | 15-Jul-24 A | 15-Jul-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1690 | HNB Enhanced Defuelling Safety Cases |  | 2024-07-15 | Key Stakeholders Identified | 15-Jul-24 A | 15-Jul-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 2150 | HYA Fuel Handling Essential Safety Case |  |  | PJB with INA | 15-Jul-24 A | 15-Jul-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 2140 | HYA Fuel Handling Essential Safety Case |  |  | Re-attach to ADL | 15-Jul-24 A | 16-Jul-24 A | 2 | 0 | 2 | 100% |  | Completed
ER6698LT | W224 | W224.1260 | HRA Enhanced Defueling Safety Case | 2024-07-15 | 2024-07-19 | PJB | 15-Jul-24 A | 19-Jul-24 A | 5 | 0 | 5 | 100% |  | Completed
ER6701LT | W228 | W228.1260 | HYA Enhanced Defueling Safety Case | 2024-07-15 | 2024-07-19 | PJB | 15-Jul-24 A | 19-Jul-24 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A4720 | HRA Fuel Handling Essential Safety Case |  | 2023-08-04 | Issue to CO & Station for comments | 16-Jul-24 A | 16-Jul-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.A29170 | HYB Essential Defueling Safety Case | 2023-08-31 | 2023-09-13 | Technical Review of Defuelling Worker Risk Assessment EAN | 16-Jul-24 A | 31-Jul-24 A | 0 | 0 | 12 | 100% |  | Completed
ER6668LT | W213 | W213.A29170 | TOR Essential Defueling Safety Case | 2023-08-31 | 2023-09-13 | Technical Review of Defuelling Worker Risk Assessment EAN | 16-Jul-24 A | 31-Jul-24 A | 10 | 0 | 12 | 100% |  | Completed
ER6372LT | W203 | W203.D1460 | HNB Enhanced Defuelling Safety Cases | 2024-07-16 | 2024-07-22 | Develop initial programme plan using mandatory template | 16-Jul-24 A | 22-Jul-24 A | 5 | 0 | 4 | 100% |  | Completed
ER6698LT | W224 | W224.3720 | HRA Enhanced Defueling Safety Case | 2024-07-16 | 2024-07-29 | NSRS | 16-Jul-24 A | 29-Jul-24 A | 49 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | 2170 | HYA Fuel Handling Essential Safety Case |  |  | *****INSA****** | 17-Jul-24 A | 29-Aug-24 A | 30 | 0 | 31 | 100% |  | Completed
ER6378LT | W222 | W222.A4680 | HRA Fuel Handling Essential Safety Case | 2023-08-07 | 2023-08-07 | Incorporate all stakeholder comments and Final Sign Off | 17-Jul-24 A | 17-Jul-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A4740 | HRA Fuel Handling Essential Safety Case | 2023-08-08 | 2023-08-08 | Final Verification - Statement Issued | 17-Jul-24 A | 17-Jul-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A4970 | HRA Fuel Handling Essential Safety Case | 2023-08-08 | 2023-09-11 | INSA review & iteration of comments (using BARRIER MODEL) | 17-Jul-24 A | 27-Aug-24 A | 25 | 0 | 28 | 100% |  | Completed
ER6378LT | W222 | W222.A4990 | HRA Fuel Handling Essential Safety Case | 2023-08-09 | 2023-08-15 | DA (Authorised Designer) Approval of CAT1 Safety Case | 17-Jul-24 A | 23-Jul-24 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A4740 | HYA Fuel Handling Essential Safety Case | 2023-08-08 | 2023-08-08 | Final Verification | 17-Jul-24 A | 17-Jul-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A4680 | HYA Fuel Handling Essential Safety Case | 2023-08-07 | 2023-08-07 | Incorporate all stakeholder comments and Final Sign Off | 17-Jul-24 A | 17-Jul-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.1130 | HRA Fuel Handling Essential Safety Case | 2023-08-08 | 2023-10-18 | Safety Case Development Costs - INSA Phase (C to D ) ##Cost Summary## | 17-Jul-24 A | 18-Sep-24 A | 65 | 0 | 45 | 100% |  | Completed
ER6378LT | W222 | W222.1140 | HRA Fuel Handling Essential Safety Case | 2023-08-08 | 2023-10-18 | Project Management Costs - INSA Phase (C to D ) ##Cost Summary## | 17-Jul-24 A | 18-Sep-24 A | 65 | 0 | 45 | 100% |  | Completed
ER6650LT | W226 | 2100 | HYA Fuel Handling Essential Safety Case |  |  | CO Endorsed | 17-Jul-24 A | 17-Jul-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 2110 | HYA Fuel Handling Essential Safety Case |  |  | Stn RE Endorsed | 17-Jul-24 A | 17-Jul-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6378LT | W222 | W222.A4710 | HRA Fuel Handling Essential Safety Case |  | 2023-08-08 | Submit for approval - Categoriser ratifies; RE/CO endorsement | 17-Jul-24 A | 17-Jul-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A4960 | HRA Fuel Handling Essential Safety Case |  | 2023-08-08 | Verified Draft Available for INSA (T-7) ECs(HRA-363840) - HRA Defuelling Fuel Handling Essential SC | 17-Jul-24 A | 17-Jul-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A4960 | HYA Fuel Handling Essential Safety Case |  | 2023-08-08 | Verified Draft Available for INSA (T-7) ECs(HYA-363839) - HYA Defuelling Fuel Handling Essential SC | 17-Jul-24 A | 17-Jul-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A4720 | HYA Fuel Handling Essential Safety Case |  | 2023-08-04 | Issue to CO & Station for comments | 17-Jul-24 A | 17-Jul-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A4710 | HYA Fuel Handling Essential Safety Case |  | 2023-08-08 | Submit for approval - Categoriser ratifies; RE/CO endorsement | 17-Jul-24 A | 17-Jul-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A4990 | HYA Fuel Handling Essential Safety Case | 2023-08-09 | 2023-08-15 | DA (Authorised Designer) Approval of CAT1 Safety Case | 18-Jul-24 A | 24-Jul-24 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A4970 | HYA Fuel Handling Essential Safety Case | 2023-08-08 | 2023-09-11 | INSA review & iteration of comments (using BARRIER MODEL) | 18-Jul-24 A | 29-Aug-24 A | 25 | 0 | 30 | 100% |  | Completed
ER6650LT | W226 | W226.1130 | HYA Fuel Handling Essential Safety Case | 2023-08-08 | 2023-10-18 | Safety Case Development Costs - INSA Phase (C to D ) ##Cost Summary## | 18-Jul-24 A | 18-Sep-24 A | 64 | 0 | 44 | 100% |  | Completed
ER6650LT | W226 | W226.1140 | HYA Fuel Handling Essential Safety Case | 2023-08-08 | 2023-10-18 | Project Management Costs - INSA Phase (C to D ) ##Cost Summary## | 18-Jul-24 A | 18-Sep-24 A | 64 | 0 | 44 | 100% |  | Completed
ER6378LT | W222 | 1971 | HRA Fuel Handling Essential Safety Case |  |  | Issue Head Document onto CDMS | 18-Jul-24 A | 19-Jul-24 A | 2 | 0 | 2 | 100% |  | Completed
ER6650LT | W226 | 1971 | HYA Fuel Handling Essential Safety Case |  |  | Issue Head Document onto CDMS | 18-Jul-24 A | 19-Jul-24 A | 2 | 0 | 2 | 100% |  | Completed
W230LT | W230 | W230.2000 | HYB Enhanced Defueling Safety Case Strategy | 2024-07-08 | 2024-07-19 | TSA Addressess Comments | 19-Jul-24 A | 26-Nov-24 A | 10 | 0 | 92 | 100% |  | Completed
W772LT | W772 | W772LT.A1200 | DNB Pull Harder Safety Case | 2024-07-19 | 2024-07-25 | Initiate and Register EC and identify Milestones in AMS EC 375698<DNB Pull Harder SC> | 19-Jul-24 A | 26-Jul-24 A | 5 | 0 | 5 | 100% |  | Completed
W234LT | W234 | W234.2000 | TOR Enhanced Defueling Safety Case Strategy | 2024-07-08 | 2024-07-19 | TSA Addressess Comments | 19-Jul-24 A | 26-Nov-24 A | 10 | 0 | 92 | 100% |  | Completed
ER6701LT | W228 | W228.3720 | HYA Enhanced Defueling Safety Case | 2024-07-19 | 2024-08-02 | NSRS | 19-Jul-24 A | 02-Aug-24 A | 21 | 0 | 10 | 100% |  | Completed
ER6372LT | W203 | W203.D1710 | HNB Enhanced Defuelling Safety Cases |  | 2024-07-22 | CA PJB Held | 22-Jul-24 A | 22-Jul-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.1270 | HRA Enhanced Defueling Safety Case | 2024-07-22 | 2024-09-06 | Information Gathering | 22-Jul-24 A | 06-Sep-24 A | 29 | 0 | 34 | 100% |  | Completed
ER6701LT | W228 | W228.1270 | HYA Enhanced Defueling Safety Case | 2024-07-22 | 2024-09-06 | Information Gathering | 22-Jul-24 A | 06-Sep-24 A | 29 | 0 | 34 | 100% |  | Completed
ER6372LT | W203 | W203.D1280 | HNB Enhanced Defuelling Safety Cases | 2024-07-22 | 2024-07-26 | Agree resource & timescales with suppliers for delivering key refs, incl contingency, risk & allowance for rework | 22-Jul-24 A | 26-Jul-24 A | 5 | 0 | 5 | 100% |  | Completed
ER6378LT | W222 | W222.A24350 | HRA Fuel Handling Essential Safety Case |  | 2023-05-26 | Living Safety Document EAN Available | 22-Jul-24 A | 22-Jul-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1180 | DNB Enhanced Safety Cases | 2024-06-10 | 2024-06-21 | <Review of Weld Inspection Data> - Draft EAN Reviewed by EDF SQEP | 23-Jul-24 A | 05-Aug-24 A | 10 | 0 | 10 | 100% |  | Completed
ER6701LT | W228 | W228.1520 | HYA Enhanced Defueling Safety Case | 2024-07-23 | 2024-07-30 | Hold PJB | 23-Jul-24 A | 30-Jul-24 A | 1 | 0 | 6 | 100% |  | Completed
ER6698LT | W224 | W224.1520 | HRA Enhanced Defueling Safety Case | 2024-07-24 | 2024-07-29 | Hold PJB | 24-Jul-24 A | 29-Jul-24 A | 5 | 0 | 4 | 100% |  | Completed
W232LT | W232 | W232.A2110 | DNB Enhanced Safety Cases | 2024-08-30 | 2024-10-10 | Rev 000 - Verification of the case (using BARRIER MODEL) | 25-Jul-24 A | 08-Oct-24 A | 30 | 0 | 52 | 100% |  | Completed
W772LT | W772 | W772LT.A1680 | DNB Pull Harder Safety Case | 2024-07-26 | 2024-08-05 | CO and PCE Create Initial Plan of Work ==> KDM | 26-Jul-24 A | 05-Aug-24 A | 7 | 0 | 7 | 100% |  | Completed
ER6372LT | W203 | W203.D1270 | HNB Enhanced Defuelling Safety Cases | 2024-07-29 | 2024-11-19 | Hold project kick start meeting with Station & key suppliers | 29-Jul-24 A | 19-Nov-24 A | 5 | 0 | 80 | 100% |  | Completed
ER6701LT | W228 | W228.1590 | HYA Enhanced Defueling Safety Case | 2024-07-30 | 2024-08-30 | Analysis | 30-Jul-24 A | 30-Aug-24 A | 1 | 0 | 23 | 100% |  | Completed
ER6698LT | W224 | W224.1590 | HRA Enhanced Defueling Safety Case | 2024-07-30 | 2024-08-30 | Analysis | 30-Jul-24 A | 30-Aug-24 A | 15 | 0 | 23 | 100% |  | Completed
ER6666LT | W209 | W209.A29180 | HYB Essential Defueling Safety Case | 2023-09-14 | 2023-09-20 | Supplier Update and Issue Defuelling Worker Risk Assessment EAN | 31-Jul-24 A | 07-Aug-24 A | 5 | 0 | 6 | 100% |  | Completed
ER6666LT | W209 | W209.A29190 | HYB Essential Defueling Safety Case | 2023-09-21 | 2023-09-27 | Complete TR Form and Upload Defuelling Worker Risk Assessment EAN to CDMS | 31-Jul-24 A | 09-Aug-24 A | 4 | 0 | 8 | 100% |  | Completed
ER6668LT | W213 | W213.A29180 | TOR Essential Defueling Safety Case | 2023-09-14 | 2023-09-20 | Supplier Update and Issue Defuelling Worker Risk Assessment EAN | 31-Jul-24 A | 07-Aug-24 A | 5 | 0 | 6 | 100% |  | Completed
ER6668LT | W213 | W213.A29190 | TOR Essential Defueling Safety Case | 2023-09-21 | 2023-09-27 | Complete TR Form and Upload Defuelling Worker Risk Assessment EAN to CDMS | 31-Jul-24 A | 09-Aug-24 A | 5 | 0 | 8 | 100% |  | Completed
ER6666LT | W209 | W209.A31320 | HYB Essential Defueling Safety Case |  |  | PSA Documentation Available | 31-Jul-24 A | 31-Jul-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A31320 | TOR Essential Defueling Safety Case |  |  | PSA Documentation Available | 31-Jul-24 A | 31-Jul-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1320 | DNB Enhanced Safety Cases |  | 2024-06-07 | <Review of Lifting Integrity Faults> - Issue Draft EAN to EDF for Review. | 01-Aug-24 A | 01-Aug-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.2510 | HRA Enhanced Defueling Safety Case | 2024-08-01 | 2024-08-14 | RFS Load Trace TSA Support | 01-Aug-24 A | 14-Aug-24 A | 10 | 0 | 10 | 100% |  | Completed
ER6701LT | W228 | W228.2510 | HYA Enhanced Defueling Safety Case | 2024-08-01 | 2024-08-14 | RFS Load Trace TSA Support | 01-Aug-24 A | 14-Aug-24 A | 10 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.C1190 | DNB Enhanced Safety Cases | 2024-06-24 | 2024-07-05 | <Review of Weld Inspection Data> - Address Comments from EDF Review on Draft EAN | 06-Aug-24 A | 19-Aug-24 A | 10 | 0 | 10 | 100% |  | Completed
W772LT | W772 | W772LT.A1000 | DNB Pull Harder Safety Case | 2024-08-06 | 2024-08-16 | Produce MF EC 375698 <DNB Pull Harder SC> & obtain approval | 06-Aug-24 A | 16-Aug-24 A | 9 | 0 | 9 | 100% |  | Completed
ER6378LT | W222 | W222.1010 | HRA Fuel Handling Essential Safety Case |  | 2023-08-29 | Discovery Milestone - Confirm INSA Review Period | 06-Aug-24 A | 06-Aug-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6701LT | W228 | W228.3650 | HYA Enhanced Defueling Safety Case | 2024-08-07 | 2024-08-20 | Production/Author CETS | 07-Aug-24 A | 20-Aug-24 A | 35 | 0 | 9 | 100% |  | Completed
ER6701LT | W228 | W228.1300 | HYA Enhanced Defueling Safety Case | 2024-08-07 | 2024-09-09 | EDF Review | 07-Aug-24 A | 09-Sep-24 A | 23 | 0 | 23 | 100% |  | Completed
ER6698LT | W224 | W224.1300 | HRA Enhanced Defueling Safety Case | 2024-08-07 | 2024-09-09 | EDF Review | 07-Aug-24 A | 09-Sep-24 A | 23 | 0 | 23 | 100% |  | Completed
ER6698LT | W224 | W224.3650 | HRA Enhanced Defueling Safety Case | 2024-08-07 | 2024-08-20 | Production/Author CETS | 07-Aug-24 A | 20-Aug-24 A | 25 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | W226.1010 | HYA Fuel Handling Essential Safety Case |  | 2023-08-29 | Discovery Milestone - Confirm INSA Review Period | 07-Aug-24 A | 07-Aug-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1020 | HNB Enhanced Defuelling Safety Cases |  |  | Plan Scope in Primavera Level 2 Lifecycle) | 08-Aug-24 A | 14-Aug-24 A | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.C1620 | DNB Enhanced Safety Cases | 2024-05-24 | 2024-06-07 | <SCOPE NAME CHANGE CN 2615><Further Review of Shock Loaded Unit Events (Group 1)> - TSA Internal Review of Draft | 09-Aug-24 A | 22-Aug-24 A | 10 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.A29200 | HYB Essential Defueling Safety Case |  | 2023-09-27 | Defuelling Worker Risk Assessment EAN Available | 09-Aug-24 A | 09-Aug-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.A29200 | TOR Essential Defueling Safety Case |  | 2023-09-27 | Defuelling Worker Risk Assessment EAN Available | 09-Aug-24 A | 09-Aug-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6701LT | W228 | W228.2150 | HYA Enhanced Defueling Safety Case | 2024-08-12 | 2024-08-29 | Outline Safety Case Strategy - Trip function change | 12-Aug-24 A | 29-Aug-24 A | 10 | 0 | 12 | 100% |  | Completed
ER6701LT | W228 | W228.2140 | HYA Enhanced Defueling Safety Case | 2024-08-12 | 2024-08-29 | Outline Safety Case Strategy - Software based load trace change | 12-Aug-24 A | 29-Aug-24 A | 10 | 0 | 12 | 100% |  | Completed
ER6701LT | W228 | W228.2130 | HYA Enhanced Defueling Safety Case | 2024-08-12 | 2024-08-29 | Outline Safety Case Strategy - Gripping Sleeve/BoB Weight | 12-Aug-24 A | 29-Aug-24 A | 10 | 0 | 12 | 100% |  | Completed
W232LT | W232 | W232.C1340 | DNB Enhanced Safety Cases | 2024-06-24 | 2024-07-05 | <Review of Lifting Integrity Faults> - Address Comments from EDF Review on Draft EAN | 12-Aug-24 A | 23-Aug-24 A | 10 | 0 | 10 | 100% |  | Completed
ER6698LT | W224 | W224.1200 | HRA Enhanced Defueling Safety Case | 2024-08-12 | 2024-09-02 | EDF Review and contract awards | 12-Aug-24 A | 02-Sep-24 A | 15 | 0 | 15 | 100% |  | Completed
ER6698LT | W224 | W224.2130 | HRA Enhanced Defueling Safety Case | 2024-08-12 | 2024-08-29 | Outline Safety Case Strategy - Gripping Sleeve/BoB Weight | 12-Aug-24 A | 29-Aug-24 A | 10 | 0 | 12 | 100% |  | Completed
ER6698LT | W224 | W224.2140 | HRA Enhanced Defueling Safety Case | 2024-08-12 | 2024-08-29 | Outline Safety Case Strategy - Software based load trace change | 12-Aug-24 A | 29-Aug-24 A | 10 | 0 | 12 | 100% |  | Completed
ER6698LT | W224 | W224.2150 | HRA Enhanced Defueling Safety Case | 2024-08-12 | 2024-08-29 | Outline Safety Case Strategy - Trip function change | 12-Aug-24 A | 29-Aug-24 A | 10 | 0 | 12 | 100% |  | Completed
ER6701LT | W228 | W228.1200 | HYA Enhanced Defueling Safety Case | 2024-08-12 | 2024-09-02 | EDF Review and contract awards | 12-Aug-24 A | 02-Sep-24 A | 15 | 0 | 15 | 100% |  | Completed
ER6701LT | W228 | W228.3660 | HYA Enhanced Defueling Safety Case | 2024-08-13 | 2024-10-31 | Author | 13-Aug-24 A | 31-Oct-24 A | 1 | 0 | 56 | 100% |  | Completed
ER6698LT | W224 | W224.3660 | HRA Enhanced Defueling Safety Case | 2024-08-13 | 2024-11-01 | Author | 13-Aug-24 A | 01-Nov-24 A | 16 | 0 | 57 | 100% |  | Completed
ER6698LT | W224 | W224.2460 | HRA Enhanced Defueling Safety Case | 2024-08-15 | 2024-08-30 | Supplier Return Period | 15-Aug-24 A | 30-Aug-24 A | 10 | 0 | 11 | 100% |  | Completed
ER6701LT | W228 | W228.2460 | HYA Enhanced Defueling Safety Case | 2024-08-15 | 2024-08-30 | Supplier Return Period | 15-Aug-24 A | 30-Aug-24 A | 10 | 0 | 11 | 100% |  | Completed
ER6372LT | W203 | W203.D1030 | HNB Enhanced Defuelling Safety Cases |  |  | Estimate Scope +/- 10% Lifecycle | 15-Aug-24 A | 21-Aug-24 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | 2205 | HYA Fuel Handling Essential Safety Case |  |  | *******INA Support paper going to NSC (T-3) Target******* | 19-Aug-24 A | 19-Aug-24 A | 1 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772LT.A1310 | DNB Pull Harder Safety Case | 2024-08-19 | 2024-08-19 | Initial Categorisation by Station ==> KDM | 19-Aug-24 A | 19-Aug-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1200 | DNB Enhanced Safety Cases |  | 2024-07-05 | <Review of Weld Inspection Data> - Issue Final EAN | 19-Aug-24 A | 19-Aug-24 A | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.KDM.SP01 | DNB Pull Harder Safety Case |  | 2024-08-19 | KDM - Gate EC1 completed EC 375698 <DNB Pull Harder SC> | 19-Aug-24 A | 19-Aug-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1210 | DNB Enhanced Safety Cases | 2024-07-08 | 2024-07-19 | <Review of Weld Inspection Data> - EAN Completed and Uploaded to CDMS | 20-Aug-24 A | 30-Sep-24 A | 5 | 0 | 28 | 100% |  | Completed
W772LT | W772 | W772LT.A1010 | DNB Pull Harder Safety Case | 2024-08-20 | 2024-09-27 | Produce draft NSRS (using BARRIER MODEL) | 20-Aug-24 A | 10-Oct-24 A | 28 | 0 | 36 | 100% |  | Completed
W772LT | W772 | W772LT.A1250 | DNB Pull Harder Safety Case | 2024-08-20 | 2024-08-20 | Appoint CO & CA | 20-Aug-24 A | 20-Aug-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6701LT | W228 | W228.3700 | HYA Enhanced Defueling Safety Case | 2024-08-21 | 2024-09-04 | Verify | 21-Aug-24 A | 04-Sep-24 A | 1 | 0 | 10 | 100% |  | Completed
ER6698LT | W224 | W224.3700 | HRA Enhanced Defueling Safety Case | 2024-08-21 | 2024-09-04 | Verify | 21-Aug-24 A | 04-Sep-24 A | 11 | 0 | 10 | 100% |  | Completed
W772LT | W772 | W772LT.A1110 | DNB Pull Harder Safety Case | 2024-08-21 | 2024-08-22 | CA to agree with CO format of the safety case | 21-Aug-24 A | 22-Aug-24 A | 2 | 0 | 2 | 100% |  | Completed
W772LT | W772 | W772LT.A1340 | DNB Pull Harder Safety Case | 2024-08-21 | 2024-08-30 | Identify verifier for the case & establish all other resources | 21-Aug-24 A | 30-Aug-24 A | 7 | 0 | 7 | 100% |  | Completed
ER6698LT | W224 | W224.1290 | HRA Enhanced Defueling Safety Case | 2024-08-22 | 2024-09-13 | Author SWIFT Briefing Pack | 22-Aug-24 A | 13-Sep-24 A | 16 | 0 | 16 | 100% |  | Completed
ER6701LT | W228 | W228.1290 | HYA Enhanced Defueling Safety Case | 2024-08-22 | 2024-09-13 | Author Draft SWIFT Report - Confirm Nodes | 22-Aug-24 A | 13-Sep-24 A | 16 | 0 | 16 | 100% |  | Completed
ER6372LT | W203 | W203.D1040 | HNB Enhanced Defuelling Safety Cases |  |  | Ensure Alignment of Schedule & Estimate | 22-Aug-24 A | 27-Aug-24 A | 3 | 0 | 3 | 100% |  | Completed
W232LT | W232 | W232.C1560 | DNB Enhanced Safety Cases |  | 2024-06-07 | <SCOPE NAME CHANGE CN 2615><Further Review of Shock Loaded Unit Events (Group 1)> - Issue Draft EAN to EDF for R | 22-Aug-24 A | 22-Aug-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1570 | DNB Enhanced Safety Cases | 2024-06-10 | 2024-06-21 | <SCOPE NAME CHANGE CN 2615><Further Review of Shock Loaded Unit Events (Group 1)> - Draft EAN Reviewed by EDF SQ | 23-Aug-24 A | 06-Sep-24 A | 10 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.C1350 | DNB Enhanced Safety Cases |  | 2024-07-05 | <Review of Lifting Integrity Faults> - Issue Final EAN | 23-Aug-24 A | 23-Aug-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1200 | HNB Enhanced Defuelling Safety Cases |  |  | Revise Project Definition Document (PDD) | 26-Aug-24 A | 02-Oct-24 A | 5 | 0 | 26 | 100% |  | Completed
W232LT | W232 | W232.C1360 | DNB Enhanced Safety Cases | 2024-07-08 | 2024-07-12 | <Review of Lifting Integrity Faults> - EAN Completed and Uploaded to CDMS | 27-Aug-24 A | 30-Sep-24 A | 5 | 0 | 24 | 100% |  | Completed
ER6698LT | W224 | W224.2430 | HRA Enhanced Defueling Safety Case | 2024-08-28 | 2024-08-30 | EDF Review and contract awards | 28-Aug-24 A | 30-Aug-24 A | 10 | 0 | 3 | 100% |  | Completed
ER6701LT | W228 | W228.2430 | HYA Enhanced Defueling Safety Case | 2024-08-28 | 2024-08-30 | EDF Review and contract awards | 28-Aug-24 A | 30-Aug-24 A | 10 | 0 | 3 | 100% |  | Completed
ER6372LT | W203 | W203.D1050 | HNB Enhanced Defuelling Safety Cases |  |  | Hold Risk Workshop | 28-Aug-24 A | 28-Aug-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 2200 | HYA Fuel Handling Essential Safety Case |  |  | INA Support paper going to NSC (T-3) | 29-Aug-24 A | 29-Aug-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.D1060 | HNB Enhanced Defuelling Safety Cases |  |  | Complete Risk Log with Estimates | 29-Aug-24 A | 30-Aug-24 A | 2 | 0 | 2 | 100% |  | Completed
ER6371LT | W202 | W202.A5300 | HRA Reactors Shutdown Essential Safety Cases |  | 2023-08-30 | INSA Assessment substantially comp (T-3 weeks before NSC date) EC 363682 <Reactor Shutdown Essential SC> (Cat 1 MS) HRA | 29-Aug-24 A | 29-Aug-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5310 | HRA Reactors Shutdown Essential Safety Cases |  | 2023-08-30 | INSA Assessment substantially comp (T-3 weeks before NSC date) EC 363682 Reactor Shutdown Essential SC (Cat 1 MS) (HRA) | 29-Aug-24 A | 29-Aug-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5300 | HYA Reactors Shutdown Essential Safety Cases |  | 2023-08-30 | INSA Assessment substantially comp (T-3 weeks before NSC date) EC 363676 <Reactor Shutdown Essential SC> (Cat 1 MS) HYA | 29-Aug-24 A | 29-Aug-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5310 | HYA Reactors Shutdown Essential Safety Cases |  | 2023-08-30 | INSA Assessment substantially comp (T-3 weeks before NSC date) EC 363676 Reactor Shutdown Essential SC (Cat 1 MS) (HYA) | 29-Aug-24 A | 29-Aug-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A5010 | HRA Fuel Handling Essential Safety Case |  | 2023-09-19 | INSA Assess substantially comp (T-3 wks<NSC date) ECs (HRA-363840) Essential Fuel Handling Safety Case | 29-Aug-24 A | 29-Aug-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A5010 | HYA Fuel Handling Essential Safety Case |  | 2023-09-19 | INSA Assess substntlly comp (T-3 wks<NSC date) ECs (HYA-363839) Essential Fuel Handling Safety Case | 29-Aug-24 A | 29-Aug-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206180 | HRA Reactors Shutdown Essential Safety Cases |  |  | >>>OUTGOING ENABLER (W222, HRA Security Plan) INSA Assessment substantially comp (T - 3 weeks before NSC date) | 29-Aug-24 A | 29-Aug-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206240 | HYA Reactors Shutdown Essential Safety Cases |  | 2022-02-25 | >>>OUTGOING ENABLER (W226, HYA Security Plan) INSA Assessment substantially comp (T - 3 weeks before NSC date) | 29-Aug-24 A | 29-Aug-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.1020 | HRA Fuel Handling Essential Safety Case |  | 2023-09-19 | >>>OUTGOING ENABLER (HRA Security Plan (W155)) INSA Assessment substantially comp (T - 3 weeks before NSC date) | 29-Aug-24 A | 29-Aug-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.1020 | HYA Fuel Handling Essential Safety Case |  | 2023-09-19 | >>>OUTGOING ENABLER (HYA Security Plan (W156)) INSA Assessment substantially comp (T - 3 weeks before NSC date) | 29-Aug-24 A | 29-Aug-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.1360 | HRA Reactors Shutdown Essential Safety Cases |  |  | >>>INCOMING ENABLER (W222) INA Support paper going to NSC (T-3) | 29-Aug-24 A | 29-Aug-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.1370 | HRA Reactors Shutdown Essential Safety Cases |  |  | >>>MIRROR of INCOMING ENABLER (W222) INA Support paper going to NSC (T-3) | 29-Aug-24 A | 29-Aug-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.B1360 | HYA Reactors Shutdown Essential Safety Cases |  |  | >>>INCOMING ENABLER (W226) INA Support paper going to NSC (T-3) | 29-Aug-24 A | 29-Aug-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.B1370 | HYA Reactors Shutdown Essential Safety Cases |  |  | >>>MIRROR of INCOMING ENABLER (W226) INA Support paper going to NSC (T-3) | 29-Aug-24 A | 29-Aug-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5540 | HYA Reactors Shutdown Essential Safety Cases |  |  | >>>INTERFACE MILESTONE (W226) INA Support paper going to NSC (T-3) | 29-Aug-24 A | 29-Aug-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206540 | HRA Reactors Shutdown Essential Safety Cases |  |  | >>>INTERFACE MILESTONE (W222) INA Support paper going to NSC (T-3) | 29-Aug-24 A | 29-Aug-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5270 | HRA Reactors Shutdown Essential Safety Cases | 2023-08-31 | 2023-09-06 | Prepare Station Director's Brief (HRA) | 30-Aug-24 A | 11-Sep-24 A | 5 | 0 | 8 | 100% |  | Completed
ER6661LT | W206 | W206.A5270 | HYA Reactors Shutdown Essential Safety Cases | 2023-08-31 | 2023-09-06 | Prepare Station Director's Brief (HYA) | 30-Aug-24 A | 11-Sep-24 A | 5 | 0 | 8 | 100% |  | Completed
ER6378LT | W222 | W222.A1520 | HRA Fuel Handling Essential Safety Case | 2023-09-20 | 2023-09-26 | Prepare Station Director's Brief | 30-Aug-24 A | 11-Sep-24 A | 5 | 0 | 9 | 100% |  | Completed
ER6378LT | W222 | W222.A5000 | HRA Fuel Handling Essential Safety Case | 2023-09-12 | 2023-09-19 | Incorporate INSA comments | 30-Aug-24 A | 05-Sep-24 A | 5 | 0 | 5 | 100% |  | Completed
ER6650LT | W226 | W226.A5000 | HYA Fuel Handling Essential Safety Case | 2023-09-12 | 2023-09-19 | Incorporate INSA comments | 30-Aug-24 A | 05-Sep-24 A | 5 | 0 | 4 | 100% |  | Completed
ER6650LT | W226 | W226.A1520 | HYA Fuel Handling Essential Safety Case | 2023-09-20 | 2023-09-26 | Prepare Station Director's Brief | 30-Aug-24 A | 11-Sep-24 A | 5 | 0 | 8 | 100% |  | Completed
ER6650LT | W226 | 2180 | HYA Fuel Handling Essential Safety Case |  |  | Respond to Minor INSA Comments | 30-Aug-24 A | 05-Sep-24 A | 5 | 0 | 4 | 100% |  | Completed
ER6650LT | W226 | 2210 | HYA Fuel Handling Essential Safety Case |  |  | pre-NSC notification period to be determined/agreed (T-3)(Jun=29 May)(Jul=26 Jun) | 30-Aug-24 A | 30-Aug-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 2190 | HYA Fuel Handling Essential Safety Case |  |  | Close Out Minor INSA Comments | 30-Aug-24 A | 05-Sep-24 A | 5 | 0 | 4 | 100% |  | Completed
ER6701LT | W228 | W228.1400 | HYA Enhanced Defueling Safety Case | 2024-09-02 | 2025-01-02 | HYA Reduce IFDF Cooling Requirements Reduce cooling to one blower | 02-Sep-24 A | 02-Jan-25 A | 64 | 0 | 86 | 100% |  | Completed
ER6650LT | W226 | W226.A24350 | HYA Fuel Handling Essential Safety Case |  | 2023-05-26 | Living Safety Document EAN Available | 02-Sep-24 A | 02-Sep-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.1400 | HRA Enhanced Defueling Safety Case | 2024-09-02 | 2025-01-02 | HRA Reduce IFDF Cooling Requirements Reduce Cooling to one Blower | 02-Sep-24 A | 02-Jan-25 A | 64 | 0 | 85 | 100% |  | Completed
ER6698LT | W224 | W224.2530 | HRA Enhanced Defueling Safety Case | 2024-09-02 | 2024-09-02 | Hold PJB for TSA Support | 02-Sep-24 A | 02-Sep-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6698LT | W224 | W224.2570 | HRA Enhanced Defueling Safety Case | 2024-09-02 | 2024-09-17 | Technical Discussion | 02-Sep-24 A | 17-Sep-24 A | 12 | 0 | 12 | 100% |  | Completed
ER6701LT | W228 | W228.2570 | HYA Enhanced Defueling Safety Case | 2024-09-02 | 2024-09-17 | Technical Discussion for PC1/PC2 software | 02-Sep-24 A | 17-Sep-24 A | 1 | 0 | 12 | 100% |  | Completed
ER6701LT | W228 | W228.2530 | HYA Enhanced Defueling Safety Case | 2024-09-02 | 2024-09-02 | Hold PJB for TSA Support | 02-Sep-24 A | 02-Sep-24 A | 1 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772LT.D3000 | DNB Pull Harder Safety Case | 2024-09-02 | 2024-09-02 | Define Project Control Structures (WBS/CBS/OBS/PBS) | 02-Sep-24 A | 02-Sep-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6698LT | W224 | W224.1210 | HRA Enhanced Defueling Safety Case | 2024-09-03 | 2024-09-16 | Hold PJB | 03-Sep-24 A | 16-Sep-24 A | 5 | 0 | 9 | 100% |  | Completed
ER6701LT | W228 | W228.1210 | HYA Enhanced Defueling Safety Case | 2024-09-03 | 2024-09-16 | Hold PJB | 03-Sep-24 A | 16-Sep-24 A | 5 | 0 | 9 | 100% |  | Completed
W772LT | W772 | W772LT.D3010 | DNB Pull Harder Safety Case | 2024-09-03 | 2024-10-18 | Plan Scope in Primavera (level 2 for Phase A to B & Level 1 for Lifecycle | 03-Sep-24 A | 18-Oct-24 A | 34 | 0 | 34 | 100% |  | Completed
W772LT | W772 | W772LT.D3020 | DNB Pull Harder Safety Case | 2024-09-03 | 2024-10-18 | Estimate scope (+/- 10% A-B & +/- 50% Lifecycle | 03-Sep-24 A | 18-Oct-24 A | 34 | 0 | 34 | 100% |  | Completed
ER6698LT | W224 | W224.3710 | HRA Enhanced Defueling Safety Case | 2024-09-05 | 2024-09-05 | TR of CETS (may Not be Needed) | 05-Sep-24 A | 05-Sep-24 A | 11 | 0 | 1 | 100% |  | Completed
ER6701LT | W228 | W228.3710 | HYA Enhanced Defueling Safety Case | 2024-09-05 | 2024-09-05 | TR of CETS | 05-Sep-24 A | 05-Sep-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6698LT | W224 | W224.1325 | HRA Enhanced Defueling Safety Case |  | 2024-09-09 | KDM - CETS ISSUE PoC and Detailed Design for BoB Weight and Gripping Sleeve | 09-Sep-24 A | 09-Sep-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1580 | DNB Enhanced Safety Cases | 2024-06-24 | 2024-07-05 | <SCOPE NAME CHANGE CN 2615><Further Review of Shock Loaded Unit Events (Group 1)> - Address Comments from EDF Re | 09-Sep-24 A | 08-Oct-24 A | 10 | 0 | 21 | 100% |  | Completed
ER6698LT | W224 | W224.1330 | HRA Enhanced Defueling Safety Case |  | 2024-09-09 | KDM - CETS ISSUE Approval | 09-Sep-24 A | 09-Sep-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6701LT | W228 | W228.1330 | HYA Enhanced Defueling Safety Case |  | 2024-09-09 | KDM - CETS ISSUE Approval | 09-Sep-24 A | 09-Sep-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6701LT | W228 | W228.1325 | HYA Enhanced Defueling Safety Case |  | 2024-09-09 | KDM - CETS ISSUE PoC and Detailed Design for BoB Weight and Gripping Sleeve | 09-Sep-24 A | 09-Sep-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.2200 | HRA Enhanced Defueling Safety Case | 2024-09-10 | 2024-09-26 | Issue CETS for Tender | 10-Sep-24 A | 26-Sep-24 A | 5 | 0 | 12 | 100% |  | Completed
ER6701LT | W228 | W228.2200 | HYA Enhanced Defueling Safety Case | 2024-09-10 | 2024-09-26 | Issue CETS for Tender | 10-Sep-24 A | 26-Sep-24 A | 5 | 0 | 12 | 100% |  | Completed
ER6701LT | W228 | W228.1220 | HYA Enhanced Defueling Safety Case | 2024-09-16 | 2025-01-02 | Optioneering Workshop | 16-Sep-24 A | 02-Jan-25 A | 5 | 0 | 75 | 100% |  | Completed
ER6698LT | W224 | W224.1220 | HRA Enhanced Defueling Safety Case | 2024-09-16 | 2025-01-02 | Optioneering Studying Report | 16-Sep-24 A | 02-Jan-25 A | 5 | 0 | 75 | 100% |  | Completed
ER6371LT | W202 | W202.A5330 | HRA Reactors Shutdown Essential Safety Cases |  | 2023-09-20 | NSC Presentation Date EC 363682 <Reactor Shutdown Essential SC> (Cat 1 B KDM) (T) (HRA) | 18-Sep-24 A | 18-Sep-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5350 | HRA Reactors Shutdown Essential Safety Cases | 2023-09-21 | 2023-10-05 | NSC Consideration & advice to Station Director (HRA) | 18-Sep-24 A | 02-Oct-24 A | 11 | 0 | 11 | 100% |  | Completed
ER6371LT | W202 | W202.A5340 | HRA Reactors Shutdown Essential Safety Cases |  | 2023-09-20 | NSC Presentation Date (T) EC (HRA-363682) Reactor Shutdown Essential Safety Case | 18-Sep-24 A | 18-Sep-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5330 | HYA Reactors Shutdown Essential Safety Cases |  | 2023-09-20 | NSC Presentation Date EC 363676 <Reactor Shutdown Essential SC> (Cat 1 B KDM) (T) (HYA) | 18-Sep-24 A | 18-Sep-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5350 | HYA Reactors Shutdown Essential Safety Cases | 2023-09-21 | 2023-10-05 | NSC Consideration & advice to Station Director (HYA) | 18-Sep-24 A | 02-Oct-24 A | 11 | 0 | 11 | 100% |  | Completed
ER6661LT | W206 | W206.A5340 | HYA Reactors Shutdown Essential Safety Cases |  | 2023-09-20 | NSC Presentation Date (T) EC (HYA-363676) Reactor Shutdown Essential Safety Case | 18-Sep-24 A | 18-Sep-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A4980 | HRA Fuel Handling Essential Safety Case |  | 2023-10-18 | NSC Presentation Date (T) ECs (HRA-363840) Essential Fuel Handling Safety Case | 18-Sep-24 A | 18-Sep-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1038 | TOR Essential Defueling Safety Case |  | 2024-04-26 | Verification Complete/ Verified Draft A Issued for INSA (T-7) EC 371386 - TOR Essential Defueling Safety Case | 18-Sep-24 A | 18-Sep-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A27280 | HRA Fuel Handling Essential Safety Case | 2023-10-18 | 2023-10-18 | NSC Presentation Date (T) ECs (HRA-363840) Essential Fuel Handling Safety Case | 18-Sep-24 A | 18-Sep-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A27330 | HYA Fuel Handling Essential Safety Case | 2023-10-18 | 2023-10-18 | NSC Presentation Date (T) ECs (HYA-363839) Essential Fuel Handling Safety Case | 18-Sep-24 A | 18-Sep-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 2220 | HYA Fuel Handling Essential Safety Case |  |  | NSC Meeting | 18-Sep-24 A | 18-Sep-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.A4980 | HYA Fuel Handling Essential Safety Case |  | 2023-10-18 | NSC Presentation Date (T) ECs (HYA-363839) Essential Fuel Handling Safety Case | 18-Sep-24 A | 18-Sep-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1505 | HYB Essential Defueling Safety Case |  | 2024-04-26 | Submit for approval - Categoriser ratifies; RE/CO endorsement | 18-Sep-24 A | 18-Sep-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1038 | HYB Essential Defueling Safety Case |  | 2024-04-26 | Verification Complete/ Verified Draft A Issued for INSA (T-7) EC 371387 - HYB Essential Defueling Safety Case | 18-Sep-24 A | 18-Sep-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1505 | TOR Essential Defueling Safety Case |  | 2024-04-26 | Submit for approval - Categoriser ratifies; RE/CO endorsement | 18-Sep-24 A | 18-Sep-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1525 | TOR Essential Defueling Safety Case | 2024-04-29 | 2024-05-03 | DA (Authorised Designer) Approval of CAT1 Safety Case | 19-Sep-24 A | 20-Sep-24 A | 5 | 0 | 2 | 100% |  | Completed
ER6668LT | W213 | W213.1535 | TOR Essential Defueling Safety Case | 2024-04-29 | 2024-05-28 | INSA review & iteration of comments (using BARRIER MODEL) | 19-Sep-24 A | 31-Jan-25 A | 20 | 0 | 93 | 100% |  | Completed
ER6378LT | W222 | W222.A1660 | HRA Fuel Handling Essential Safety Case | 2023-10-19 | 2023-11-01 | NSC Consideration & advice to Station Director | 19-Sep-24 A | 02-Oct-24 A | 10 | 0 | 9 | 100% |  | Completed
ER6650LT | W226 | W226.A1660 | HYA Fuel Handling Essential Safety Case | 2023-10-19 | 2023-11-01 | NSC Consideration & advice to Station Director | 19-Sep-24 A | 02-Oct-24 A | 10 | 0 | 10 | 100% |  | Completed
ER6666LT | W209 | W209.1525 | HYB Essential Defueling Safety Case | 2024-04-29 | 2024-05-03 | DA (Authorised Designer) Approval of CAT1 Safety Case | 19-Sep-24 A | 20-Sep-24 A | 5 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.1535 | HYB Essential Defueling Safety Case | 2024-04-29 | 2024-05-28 | INSA review & iteration of comments (using BARRIER MODEL) | 19-Sep-24 A | 31-Jan-25 A | 20 | 0 | 94 | 100% |  | Completed
ER6666LT | W209 | W209.29300 | HYB Essential Defueling Safety Case | 2024-04-29 | 2024-05-13 | Lessons Learnt Activity - Following Verification of the SC | 19-Sep-24 A | 23-Oct-24 A | 10 | 0 | 24 | 100% |  | Completed
ER6668LT | W213 | W213.29300 | TOR Essential Defueling Safety Case | 2024-04-29 | 2024-05-13 | Lessons Learnt Activity - Following Verification of the SC | 19-Sep-24 A | 23-Oct-24 A | 10 | 0 | 25 | 100% |  | Completed
ER6650LT | W226 | 2240 | HYA Fuel Handling Essential Safety Case |  |  | Respond to NSC as appropriate | 19-Sep-24 A | 02-Oct-24 A | 10 | 0 | 9 | 100% |  | Completed
ER6650LT | W226 | 2230 | HYA Fuel Handling Essential Safety Case |  |  | NSC Minutes Issued | 19-Sep-24 A | 10-Oct-24 A | 10 | 0 | 15 | 100% |  | Completed
ER6698LT | W224 | W224.2520 | HRA Enhanced Defueling Safety Case | 2024-09-23 | 2025-02-03 | Author CETS Issue for Load Trace | 23-Sep-24 A | 2025-03-07 | 30 | 5 | 117 | 80% | 190 | In Progress
ER6701LT | W228 | W228.2520 | HYA Enhanced Defueling Safety Case | 2024-09-23 | 2025-02-03 | Author Issue for Load Trace | 23-Sep-24 A | 2025-03-07 | 30 | 5 | 117 | 80% | 190 | In Progress
W232LT | W232 | W232.A2100 | DNB Enhanced Safety Cases | 2024-07-08 | 2024-07-09 | Rev 000 - Produce verification plan | 23-Sep-24 A | 30-Sep-24 A | 2 | 0 | 5 | 100% |  | Completed
ER6372LT | W203 | W203.C1390 | HNB Enhanced Defuelling Safety Cases | 2024-04-03 | 2024-04-30 | Verification of the case (using BARRIER MODEL) | 26-Sep-24 A | 15-Nov-24 A | 0 | 0 | 37 | 100% |  | Completed
ER6378LT | W222 | W222.3090 | HRA Fuel Handling Essential Safety Case |  | 2024-08-08 | Verification of Proposal Lessons Learnt Review Complete | 26-Sep-24 A | 26-Sep-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.3080 | HYA Fuel Handling Essential Safety Case |  | 2024-08-08 | Verification of Proposal - Lesson Learnt Review Complete | 26-Sep-24 A | 26-Sep-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.2210 | HRA Enhanced Defueling Safety Case | 2024-09-27 | 2025-01-02 | Supplier Return Period | 27-Sep-24 A | 02-Jan-25 A | 14 | 0 | 66 | 100% |  | Completed
ER6701LT | W228 | W228.2210 | HYA Enhanced Defueling Safety Case | 2024-09-27 | 2025-01-02 | Supplier Return Period | 27-Sep-24 A | 02-Jan-25 A | 14 | 0 | 66 | 100% |  | Completed
ER6378LT | W222 | W222.3050 | HRA Fuel Handling Essential Safety Case | 2023-08-09 | 2023-08-09 | Lesson Learn - Verification Phase | 27-Sep-24 A | 27-Sep-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | W226.3050 | HYA Fuel Handling Essential Safety Case | 2023-08-09 | 2023-08-09 | Lesson Learn - Verification Phase | 27-Sep-24 A | 27-Sep-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1220 | DNB Enhanced Safety Cases |  | 2024-07-19 | <Review of Weld Inspection Data> - EAN Completed | 30-Sep-24 A | 30-Sep-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1370 | DNB Enhanced Safety Cases |  | 2024-07-12 | <Review of Lifting Integrity Faults> - EAN Completed | 30-Sep-24 A | 30-Sep-24 A | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A1070 | DNB Pull Harder Safety Case | 2024-09-30 | 2024-09-30 | Create EC Definition Document if not part of Project Definition Document (Insert Template Ref) | 30-Sep-24 A | 30-Sep-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2090 | DNB Enhanced Safety Cases | 2024-10-11 | 2024-10-17 | Rev 000 - Incorporate CO & Station comments | 01-Oct-24 A | 08-Oct-24 A | 5 | 0 | 5 | 100% |  | Completed
W772LT | W772 | W772LT.A1460 | DNB Pull Harder Safety Case | 2024-12-03 | 2024-12-03 | Continue to Develop & resource mandatory template ==> KDM | 01-Oct-24 A | 01-Oct-24 A | 1 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A1060 | DNB Pull Harder Safety Case | 2024-10-01 | 2024-10-02 | Hold project kick start meeting with Station & key suppliers | 01-Oct-24 A | 02-Oct-24 A | 2 | 0 | 2 | 100% |  | Completed
W772LT | W772 | W772LT.A1350 | DNB Pull Harder Safety Case | 2024-12-04 | 2024-12-10 | Circulate work programme to stakeholders for agreement | 02-Oct-24 A | 09-Oct-24 A | 5 | 0 | 5 | 100% |  | Completed
W772LT | W772 | W772LT.KDM.SP03 | DNB Pull Harder Safety Case |  | 2024-12-04 | KDM - Gate EC2 completed and Cat 1 Baselined EC 375698 <DNB Pull Harder SC> | 02-Oct-24 A | 02-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1600 | DNB Enhanced Safety Cases | 2024-07-08 | 2024-07-19 | <SCOPE NAME CHANGE CN 2615><Further Review of Shock Loaded Unit Events (Group 1)> - EAN Completed and Uploaded t | 02-Oct-24 A | 08-Oct-24 A | 3 | 0 | 4 | 100% |  | Completed
ER6372LT | W203 | W203.D1070 | HNB Enhanced Defuelling Safety Cases |  |  | Update Schedule/Estimate from Risk Log & Add Provisions | 03-Oct-24 A | 11-Oct-24 A | 2 | 0 | 6 | 100% |  | Completed
W772LT | W772 | W772LT.A1090 | DNB Pull Harder Safety Case | 2024-10-03 | 2024-10-04 | Agree INSA resource with INA | 03-Oct-24 A | 04-Oct-24 A | 2 | 0 | 2 | 100% |  | Completed
W772LT | W772 | W772LT.A1520 | DNB Pull Harder Safety Case | 2024-11-25 |  | Commence Supporting References or Supporting EC's | 04-Oct-24 A | 04-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.D2090 | DNB Pull Harder Safety Case | 2024-11-25 | 2025-10-15 | Project Management - Gate A - D | 04-Oct-24 A | 2025-09-18 | 225 | 139 | 242 | 42% | 4 | In Progress
W772LT | W772 | W772LT.D2100 | DNB Pull Harder Safety Case | 2024-11-25 | 2025-10-15 | Technical Support - Gate A - D | 04-Oct-24 A | 2025-09-18 | 225 | 139 | 242 | 42% | 4 | In Progress
W772LT | W772 | W772LT.T1250 | DNB Pull Harder Safety Case | 2024-09-16 | 2024-10-04 | <Operating Strategy for Pull Harder Facility> - Prepare Draft EAN / Report | 04-Oct-24 A | 25-Oct-24 A | 15 | 0 | 15 | 100% |  | Completed
W232LT | W232 | W232.A2120 | DNB Enhanced Safety Cases | 2024-10-11 | 2024-10-14 | Rev 000 - Produce verification file | 07-Oct-24 A | 08-Oct-24 A | 2 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2250 | DNB Enhanced Safety Cases | 2024-10-14 | 2024-10-18 | Rev 000 - Key Stakeholders Approval, if requested | 07-Oct-24 A | 08-Oct-24 A | 5 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.A2070 | DNB Enhanced Safety Cases | 2024-07-08 | 2024-07-09 | Rev 000 - CA to agree with CO format of the safety case & produce agreed contents page | 07-Oct-24 A | 08-Oct-24 A | 2 | 0 | 2 | 100% |  | Completed
W232LT | W232 | W232.A2130 | DNB Enhanced Safety Cases |  | 2024-10-18 | Rev 000 - Verified Draft Issue A with verification file to INSA & station *(KDM)* | 08-Oct-24 A | 08-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2140 | DNB Enhanced Safety Cases | 2024-10-21 | 2024-11-15 | Rev 000 - INSA review & iteration of comments (using BARRIER MODEL) | 08-Oct-24 A | 18-Oct-24 A | 20 | 0 | 8 | 100% |  | Completed
W232LT | W232 | W232.A2230 | DNB Enhanced Safety Cases |  | 2024-10-17 | Rev 000 - Verification complete | 08-Oct-24 A | 08-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2240 | DNB Enhanced Safety Cases |  | 2024-10-18 | Rev 000 - Submit for approval - Categoriser ratifies; RE/CO endorsement | 08-Oct-24 A | 08-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2280 | DNB Enhanced Safety Cases |  | 2024-10-10 | Rev 000 - Issue to CO & Station for comments | 08-Oct-24 A | 08-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A3010 | DNB Enhanced Safety Cases |  | 2024-07-19 | All Technical References Complete - Rev 000 | 08-Oct-24 A | 08-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A3020 | DNB Enhanced Safety Cases |  | 2024-08-28 | Safety Case Authoring Complete - Rev 000 | 08-Oct-24 A | 08-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A3030 | DNB Enhanced Safety Cases |  | 2024-10-17 | Safety Case Verification Complete - Rev 000 | 08-Oct-24 A | 08-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1590 | DNB Enhanced Safety Cases |  | 2024-07-05 | <SCOPE NAME CHANGE CN 2615><Further Review of Shock Loaded Unit Events (Group 1)> - Issue Final EAN | 08-Oct-24 A | 08-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1610 | DNB Enhanced Safety Cases |  | 2024-07-19 | <SCOPE NAME CHANGE CN 2615><Further Review of Shock Loaded Unit Events (Group 1)> - EAN Completed | 08-Oct-24 A | 08-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2380 | DNB Enhanced Safety Cases |  | 2024-07-19 | Rev 000 - All supporting references completed | 08-Oct-24 A | 08-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A1630 | DNB Pull Harder Safety Case | 2024-12-11 | 2024-12-11 | Baseline Plan to Verification Commenced (T-11) ==> KDM | 09-Oct-24 A | 09-Oct-24 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5360 | HRA Reactors Shutdown Essential Safety Cases |  | 2023-10-05 | INSA Final Approval EC 363682 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HRA) | 10-Oct-24 A | 10-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5380 | HRA Reactors Shutdown Essential Safety Cases |  | 2023-10-05 | INSA Final Approval EC 363682 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HRA) | 10-Oct-24 A | 10-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5360 | HYA Reactors Shutdown Essential Safety Cases |  | 2023-10-05 | INSA Final Approval EC 363676 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HYA) | 10-Oct-24 A | 10-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5380 | HYA Reactors Shutdown Essential Safety Cases |  | 2023-10-05 | INSA Final Approval EC 363676 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HYA) | 10-Oct-24 A | 10-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206510 | HRA Reactors Shutdown Essential Safety Cases |  |  | >>>OUTGOING ENABLER (W285)(W148) INSA Finally Approved | 10-Oct-24 A | 10-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206310 | HYA Reactors Shutdown Essential Safety Cases |  | 2022-04-01 | >>>OUTGOING ENABLER (W286) (W148) INSA Finally Approved | 10-Oct-24 A | 10-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A1015 | DNB Pull Harder Safety Case | 2024-09-30 | 2024-10-11 | Draft NSRS Verify - Atkins | 10-Oct-24 A | 31-Oct-24 A | 10 | 0 | 15 | 100% |  | Completed
ER6378LT | W222 | W222.A17490 | HRA Fuel Handling Essential Safety Case |  | 2023-11-01 | INSA Final Approval EC 363840 HRA Defuelling Fuel Handling Essential Safety Case (Cat 1 Milestone) | 10-Oct-24 A | 10-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A17490 | HYA Fuel Handling Essential Safety Case |  | 2023-11-01 | INSA Final Approval EC 363839 HYA Defuelling Fuel Handling Essential Safety Case (Cat 1 Milestone) | 10-Oct-24 A | 10-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.1040 | HRA Fuel Handling Essential Safety Case |  | 2023-11-01 | >>>OUTGOING ENABLER (W285) INSA Final Approval | 10-Oct-24 A | 10-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27320 | HYA Fuel Handling Essential Safety Case |  | 2023-11-01 | >>>OUTGOING ENABLER (W286) CAT 1 Fuel Handling SC INSA Finally Approved | 10-Oct-24 A | 10-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5370 | HRA Reactors Shutdown Essential Safety Cases |  | 2023-10-05 | CAT 1 Satety Case Submitted to ONR - Reactor Shutdown Essential SC HRA | 10-Oct-24 A | 11-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5370 | HYA Reactors Shutdown Essential Safety Cases |  | 2023-10-05 | CAT 1 Satety Case Submitted to ONR - Reactor Shutdown Essential SC HYA | 10-Oct-24 A | 11-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.1220 | HRA Fuel Handling Essential Safety Case | 2023-11-02 |  | Letter Sent to ONR to Initiate Acknowlegement / Agreement | 11-Oct-24 A | 11-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.1190 | HYA Fuel Handling Essential Safety Case | 2023-11-02 |  | Letter Sent to ONR to Initiate Acknowledgement / Agreement | 11-Oct-24 A | 11-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 2250 | HYA Fuel Handling Essential Safety Case |  |  | Draft HRA Formal ONR Letter/Review | 11-Oct-24 A | 11-Oct-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 2260 | HYA Fuel Handling Essential Safety Case |  |  | Draft HYA Formal ONR Letter/Review | 11-Oct-24 A | 11-Oct-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 2270 | HYA Fuel Handling Essential Safety Case |  |  | Station Directors sign letters | 11-Oct-24 A | 11-Oct-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6650LT | W226 | 2280 | HYA Fuel Handling Essential Safety Case |  |  | Safety Case Submitted to the ONR | 11-Oct-24 A | 11-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5390 | HRA Reactors Shutdown Essential Safety Cases | 2023-10-06 | 2024-01-05 | ONR Approval of Safety Case EC 363682 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HRA) | 14-Oct-24 A | 24-Jan-25 A | 63 | 0 | 71 | 100% |  | Completed
ER6661LT | W206 | W206.A5390 | HYA Reactors Shutdown Essential Safety Cases | 2023-10-06 | 2024-01-05 | ONR Approval of Safety Case EC 363676 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HYA) | 14-Oct-24 A | 24-Jan-25 A | 63 | 0 | 71 | 100% |  | Completed
ER6378LT | W222 | W222.A17500 | HRA Fuel Handling Essential Safety Case | 2023-11-02 | 2024-02-05 | ONR Approval of SC (Letter sent to initiate) HYA HRA Defuelling Fuel Handling Essential Safety Case | 14-Oct-24 A | 24-Jan-25 A | 63 | 0 | 71 | 100% |  | Completed
ER6378LT | W222 | W222.1150 | HRA Fuel Handling Essential Safety Case | 2023-11-02 | 2024-02-05 | Safety Case Development Costs - ONR Phase (C to D ) ##Cost Summary## | 14-Oct-24 A | 24-Jan-25 A | 63 | 0 | 72 | 100% |  | Completed
ER6378LT | W222 | W222.1160 | HRA Fuel Handling Essential Safety Case | 2023-11-02 | 2024-02-05 | Project Management Costs - ONR Phase (C to D ) ##Cost Summary## | 14-Oct-24 A | 24-Jan-25 A | 63 | 0 | 72 | 100% |  | Completed
ER6371LT | W202 | W202.A2206530 | HRA Reactors Shutdown Essential Safety Cases | 2023-03-02 | 2024-04-16 | SC - Safety Case development - tech oversight Cat 1 - HRA - C-D - STN | 14-Oct-24 A | 21-Feb-25 A | 94 | 0 | 91 | 100% |  | Completed
ER6661LT | W206 | W206.A2206330 | HYA Reactors Shutdown Essential Safety Cases | 2023-03-02 | 2024-04-16 | SC - Safety Case development - tech oversight Cat 1 - HYA - C-D - STN | 14-Oct-24 A | 21-Feb-25 A | 94 | 0 | 91 | 100% |  | Completed
ER6372LT | W203 | W203.D1080 | HNB Enhanced Defuelling Safety Cases |  |  | Add Data to PRC Paper | 14-Oct-24 A | 18-Oct-24 A | 2 | 0 | 4 | 100% |  | Completed
ER6650LT | W226 | W226.A17500 | HYA Fuel Handling Essential Safety Case | 2023-11-02 | 2024-02-05 | ONR Approval of SC (Letter sent to initiate) HYA HRA Defuelling Fuel Handling Essential Safety Case | 14-Oct-24 A | 24-Jan-25 A | 64 | 0 | 71 | 100% |  | Completed
ER6650LT | W226 | W226.1150 | HYA Fuel Handling Essential Safety Case | 2023-11-02 | 2024-02-05 | Safety Case Development Costs - ONR Phase (C to D ) ##Cost Summary## | 14-Oct-24 A | 13-Jan-25 A | 63 | 0 | 63 | 100% |  | Completed
ER6650LT | W226 | W226.1160 | HYA Fuel Handling Essential Safety Case | 2023-11-02 | 2024-02-05 | Project Management Costs - ONR Phase (C to D ) ##Cost Summary## | 14-Oct-24 A | 24-Jan-25 A | 63 | 0 | 72 | 100% |  | Completed
W772LT | W772 | W772LT.A1020 | DNB Pull Harder Safety Case | 2024-10-14 | 2024-10-23 | Station comments on NSRS | 14-Oct-24 A | 31-Oct-24 A | 8 | 0 | 13 | 100% |  | Completed
W772LT | W772 | W772LT.A1030 | DNB Pull Harder Safety Case | 2024-10-14 | 2024-10-23 | DA (Peer) comments on NSRS | 14-Oct-24 A | 31-Oct-24 A | 8 | 0 | 13 | 100% |  | Completed
W772LT | W772 | W772LT.A2000 | DNB Pull Harder Safety Case | 2024-10-14 | 2024-11-22 | Load Path Assessment - Preliminary Work - DNB Defuelling | 14-Oct-24 A | 22-Nov-24 A | 30 | 0 | 30 | 100% |  | Completed
W772LT | W772 | W772LT.A2250 | DNB Pull Harder Safety Case | 2024-10-14 | 2024-11-22 | Load Path Assessment - Preliminary Work - Atkins | 14-Oct-24 A | 22-Nov-24 A | 30 | 0 | 30 | 100% |  | Completed
W772LT | W772 | W772LT.T1170 | DNB Pull Harder Safety Case | 2024-10-14 | 2024-10-18 | <Specification for Pull Harder Facility> - Prepare Draft EAN / Report | 14-Oct-24 A | 18-Oct-24 A | 5 | 0 | 5 | 100% |  | Completed
ER6698LT | W224 | W224.2190 | HRA Enhanced Defueling Safety Case | 2024-10-15 | 2024-10-15 | SWIFT Workshop | 15-Oct-24 A | 15-Oct-24 A | 5 | 0 | 1 | 100% |  | Completed
ER6701LT | W228 | W228.2190 | HYA Enhanced Defueling Safety Case | 2024-10-15 | 2024-10-21 | SWIFT Workshop | 15-Oct-24 A | 21-Oct-24 A | 5 | 0 | 5 | 100% |  | Completed
ER6701LT | W228 | W228.2180 | HYA Enhanced Defueling Safety Case | 2024-10-16 | 2025-01-02 | SWIFT Report (Update & Verify) | 16-Oct-24 A | 02-Jan-25 A | 20 | 0 | 53 | 100% |  | Completed
ER6698LT | W224 | W224.2180 | HRA Enhanced Defueling Safety Case | 2024-10-16 | 2025-01-02 | SWIFT Report (Update & Verify) | 16-Oct-24 A | 02-Jan-25 A | 20 | 0 | 53 | 100% |  | Completed
W232LT | W232 | W232.A2290 | DNB Enhanced Safety Cases | 2024-11-18 | 2024-11-22 | Rev 000 - Incorporate INSA comments | 18-Oct-24 A | 25-Oct-24 A | 10 | 0 | 5 | 100% |  | Completed
W772LT | W772 | W772LT.T1180 | DNB Pull Harder Safety Case |  | 2024-10-18 | <Specification for Pull Harder Facility> - Issue Draft EAN / Report for Tech Review. | 18-Oct-24 A | 18-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1090 | HNB Enhanced Defuelling Safety Cases |  |  | PCL Validate & Approve Baseline Package for PRC Submission | 21-Oct-24 A | 25-Oct-24 A | 3 | 0 | 4 | 100% |  | Completed
W772LT | W772 | W772LT.D3030 | DNB Pull Harder Safety Case | 2024-10-21 | 2024-10-22 | Ensure Alignment of Schedule & Estimate | 21-Oct-24 A | 22-Oct-24 A | 2 | 0 | 2 | 100% |  | Completed
W772LT | W772 | W772LT.T1190 | DNB Pull Harder Safety Case | 2024-10-21 | 2024-10-25 | <Specification for Pull Harder Facility> - Draft EAN / Report Tech Reviewed by EDF SQEP | 21-Oct-24 A | 28-Oct-24 A | 5 | 0 | 5 | 100% |  | Completed
ER6666LT | W209 | W209.29310 | HYB Essential Defueling Safety Case |  | 2024-05-13 | Lessons Learnt Milestone - Verification of the Safety Case | 23-Oct-24 A | 23-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.D3040 | DNB Pull Harder Safety Case | 2024-10-23 | 2024-10-23 | Hold Risk Workshop | 23-Oct-24 A | 23-Oct-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6668LT | W213 | W213.29310 | TOR Essential Defueling Safety Case |  | 2024-05-13 | Lessons Learnt Milestone - Verification of the Safety Case | 23-Oct-24 A | 23-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.D3050 | DNB Pull Harder Safety Case | 2024-10-24 | 2024-10-25 | Finalise Risk Log | 24-Oct-24 A | 25-Oct-24 A | 2 | 0 | 2 | 100% |  | Completed
W772LT | W772 | W772LT.T1260 | DNB Pull Harder Safety Case |  | 2024-10-04 | <Operating Strategy for Pull Harder Facility> - Issue Draft EAN / Report for Tech Review. | 25-Oct-24 A | 25-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.D3060 | DNB Pull Harder Safety Case | 2024-10-28 | 2024-10-30 | Update Schedule from Risk Log/Estimate, Adding Provisions | 28-Oct-24 A | 30-Oct-24 A | 3 | 0 | 3 | 100% |  | Completed
W772LT | W772 | W772LT.T1200 | DNB Pull Harder Safety Case | 2024-10-28 | 2024-10-28 | <Specification for Pull Harder Facility> - Address Comments from EDF Review on Draft EAN / Report | 28-Oct-24 A | 28-Oct-24 A | 1 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772LT.T1210 | DNB Pull Harder Safety Case |  | 2024-10-28 | <Specification for Pull Harder Facility> - Issue Final EAN / Report to FMAPS | 28-Oct-24 A | 28-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2320 | DNB Enhanced Safety Cases |  | 2024-12-13 | Rev 000 - INSA Final Approval *(KDM)* | 28-Oct-24 A | 29-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5000 | DNB Enhanced Safety Cases |  |  | Lessons Learned Workshop - FPU Safety Case Ph 3 Rev 000 Technical References complete | 29-Oct-24 A | 29-Oct-24 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5010 | DNB Enhanced Safety Cases |  |  | Lessons Learned Workshop - FPU Safety Case Ph 3 Rev 000 Authored | 29-Oct-24 A | 29-Oct-24 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5020 | DNB Enhanced Safety Cases |  |  | Lessons Learned Workshop - FPU Safety Case Ph 3 Rev 000 Verified | 29-Oct-24 A | 29-Oct-24 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A3040 | DNB Enhanced Safety Cases |  | 2024-12-16 | Safety Case INA Final Approval - Rev 000 | 29-Oct-24 A | 29-Oct-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5330 | DNB Enhanced Safety Cases | 2024-07-22 | 2024-07-26 | Hold project kick start meeting with Station & key suppliers | 29-Oct-24 A | 07-Nov-24 A | 5 | 0 | 7 | 100% |  | Completed
W232LT | W232 | W232.A5340 | DNB Enhanced Safety Cases | 2024-07-29 | 2024-08-02 | Agree resource & timescales with suppliers for delivering key refs, incl contingency, risk & allowance for rework | 29-Oct-24 A | 07-Nov-24 A | 5 | 0 | 7 | 100% |  | Completed
W772LT | W772 | W772LT.T1220 | DNB Pull Harder Safety Case | 2024-10-29 | 2024-11-04 | <Specification for Pull Harder Facility> - FMAPS Review EAN / Report | 29-Oct-24 A | 04-Nov-24 A | 5 | 0 | 5 | 100% |  | Completed
W772LT | W772 | W772LT.A1035 | DNB Pull Harder Safety Case | 2024-10-07 | 2024-10-18 | INSA comments on NSRS | 31-Oct-24 A | 08-Nov-24 A | 10 | 0 | 6 | 100% |  | Completed
W772LT | W772 | W772LT.D3070 | DNB Pull Harder Safety Case | 2024-10-31 | 2024-10-31 | Add Data to PRC Paper | 31-Oct-24 A | 31-Oct-24 A | 1 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772LT.D3080 | DNB Pull Harder Safety Case | 2024-11-01 | 2024-11-05 | PCL Validate & Approve Baseline Package for PRC Submission | 01-Nov-24 A | 05-Nov-24 A | 3 | 0 | 3 | 100% |  | Completed
W232LT | W232 | W232.A2260 | DNB Enhanced Safety Cases | 2025-01-14 | 2025-01-20 | Rev 000 - Station Approval for mod implementation (including station review meeting) | 04-Nov-24 A | 07-Nov-24 A | 5 | 0 | 3 | 100% |  | Completed
W772LT | W772 | W772LT.T1230 | DNB Pull Harder Safety Case |  | 2024-11-04 | <Specification for Pull Harder Facility> - EAN / Report Completed | 04-Nov-24 A | 04-Nov-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.3670 | HRA Enhanced Defueling Safety Case | 2024-11-05 | 2025-01-02 | Verify | 05-Nov-24 A | 02-Jan-25 A | 10 | 0 | 39 | 100% |  | Completed
ER6701LT | W228 | W228.3670 | HYA Enhanced Defueling Safety Case | 2024-11-05 | 2025-01-02 | Verify | 05-Nov-24 A | 02-Jan-25 A | 10 | 0 | 39 | 100% |  | Completed
ER6372LT | W203 | W203.D1000 | HNB Enhanced Defuelling Safety Cases |  |  | Issue PRC Paper to PRC Members | 06-Nov-24 A | 06-Nov-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1100 | HNB Enhanced Defuelling Safety Cases |  |  | PRC Members Review IRM Documentation | 06-Nov-24 A | 12-Nov-24 A | 5 | 0 | 5 | 100% |  | Completed
W772LT | W772 | W772LT.D3090 | DNB Pull Harder Safety Case |  | 2024-11-06 | Gate A PRC Paper Submission | 06-Nov-24 A | 06-Nov-24 A | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.D3100 | DNB Pull Harder Safety Case | 2024-11-06 | 2024-11-12 | PRC Members Review PRC Documentation | 06-Nov-24 A | 12-Nov-24 A | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.2010 | DNB Enhanced Safety Cases |  |  | >>>OUTGOING ENABLER DNB Enhanced Safety Case Station Approved - Rev 000 | 07-Nov-24 A | 07-Nov-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A1070 | DNB Enhanced Safety Cases |  | 2025-01-21 | All Safety Cases Approved - Rev 000 (FEED TO SUMMARY SCHEDULE) | 07-Nov-24 A | 07-Nov-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A2480 | DNB Enhanced Safety Cases |  | 2025-01-20 | Rev 000 - Station Approval Obtained and CAT 2 Safety Case Complete *(KDM)* | 07-Nov-24 A | 07-Nov-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5390 | DNB Enhanced Safety Cases |  | 2024-08-02 | Issue agreed work programme to stakeholders & suppliers | 07-Nov-24 A | 07-Nov-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5400 | DNB Enhanced Safety Cases | 2024-08-05 | 2024-08-16 | Develop plan with further iterations and confirm approval from key stakeholders | 07-Nov-24 A | 18-Dec-24 A | 10 | 0 | 29 | 100% |  | Completed
W232LT | W232 | W232.A5420 | DNB Enhanced Safety Cases |  | 2024-07-19 | Key Stakeholders Identified | 07-Nov-24 A | 07-Nov-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5430 | DNB Enhanced Safety Cases |  | 2024-07-19 | CA PJB Held | 07-Nov-24 A | 07-Nov-24 A | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A1037 | DNB Pull Harder Safety Case | 2024-10-24 | 2024-11-06 | Incorporate INSA, Station, DA (peer) comments | 08-Nov-24 A | 21-Nov-24 A | 10 | 0 | 9 | 100% |  | Completed
W772LT | W772 | W772.A1000 | DNB Pull Harder Safety Case |  | 2024-11-08 | Discovery Milestone: Human Factors Confirm Requirements | 08-Nov-24 A | 08-Nov-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.1380 | HRA Reactors Shutdown Essential Safety Cases |  |  | Review of Reactor Ess Safety Case 1 - (INSA) Lessons Learnt Review Complete | 11-Nov-24 A | 11-Nov-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.1380 | HYA Reactors Shutdown Essential Safety Cases |  |  | Review of Reactor Ess Safety Case 1 - (INSA) Lessons Learnt Review Complete | 11-Nov-24 A | 11-Nov-24 A | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2130 | DNB Pull Harder Safety Case | 2024-11-11 | 2024-12-06 | <Human Factors> - Advice and Review | 11-Nov-24 A | 17-Dec-24 A | 20 | 0 | 26 | 100% |  | Completed
ER6650LT | W226 | W226.1380 | HYA Fuel Handling Essential Safety Case |  | 2023-11-01 | Review of Reactor Ess Safety Case 1 - Lessons Learnt Review Complete | 11-Nov-24 A | 11-Nov-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.1385 | HRA Fuel Handling Essential Safety Case |  | 2024-10-30 | INSA Final Approval - Lessons Learnt Review Complete | 11-Nov-24 A | 11-Nov-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.1385 | HYA Fuel Handling Essential Safety Case |  | 2024-10-30 | INSA Final Approval - Lessons Learnt Review Complete | 11-Nov-24 A | 11-Nov-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C1930 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 3472><FPU Handling with Uninspected Welds item 6> - Summary Bar | 12-Nov-24 A | 12-Nov-24 A | 29 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1940 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 3472><FPU Handling with Uninspected Welds item 6> - Draft and issue RFS | 12-Nov-24 A | 12-Nov-24 A | 10 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1950 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 3472><FPU Handling with Uninspected Welds item 6> - Supplier prepare and issue Offer | 12-Nov-24 A | 12-Nov-24 A | 8 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1960 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 3472><FPU Handling with Uninspected Welds item 6> - Review Offer, prepare and issue CI | 12-Nov-24 A | 12-Nov-24 A | 5 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1970 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 3472><FPU Handling with Uninspected Welds item 6> - Supplier mobilisation time | 12-Nov-24 A | 12-Nov-24 A | 5 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1980 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 3472><FPU Handling with Uninspected Welds item 6> - Pre Job Brief | 12-Nov-24 A | 12-Nov-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2170 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 3472><ESA Handling with OEM NSPs item 8> - Summary Bar | 12-Nov-24 A | 12-Nov-24 A | 29 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2180 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 3472><ESA Handling with OEM NSPs item 8> - Draft and issue RFS | 12-Nov-24 A | 12-Nov-24 A | 10 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2190 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 3472><ESA Handling with OEM NSPs item 8> - Supplier prepare and issue Offer | 12-Nov-24 A | 12-Nov-24 A | 8 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2200 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 3472><ESA Handling with OEM NSPs item 8> - Review Offer, prepare and issue CI | 12-Nov-24 A | 12-Nov-24 A | 5 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2210 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 3472><ESA Handling with OEM NSPs item 8> - Supplier mobilisation time | 12-Nov-24 A | 12-Nov-24 A | 5 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2220 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 3472><ESA Handling with OEM NSPs item 8> - Pre Job Brief | 12-Nov-24 A | 12-Nov-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2410 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 10> - Summary Bar | 12-Nov-24 A | 12-Nov-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2420 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 10> - Draft and issue RFS | 12-Nov-24 A | 12-Nov-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2430 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 10> - Supplier prepare and issue Offer | 12-Nov-24 A | 12-Nov-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2440 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 10> - Review Offer, prepare and issue CI | 12-Nov-24 A | 12-Nov-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2450 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 10> - Supplier mobilisation time | 12-Nov-24 A | 12-Nov-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2460 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 10> - Pre Job Brief | 12-Nov-24 A | 12-Nov-24 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2740 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 13> - Summary Bar | 12-Nov-24 A | 12-Nov-24 A | 29 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2750 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 13> - Draft and issue RFS | 12-Nov-24 A | 12-Nov-24 A | 10 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2760 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 13> - Supplier prepare and issue Offer | 12-Nov-24 A | 12-Nov-24 A | 8 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2770 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 13> - Review Offer, prepare and issue CI | 12-Nov-24 A | 12-Nov-24 A | 5 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2780 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 13> - Supplier mobilisation time | 12-Nov-24 A | 12-Nov-24 A | 5 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C2790 | DNB Enhanced Safety Cases |  |  | < SCOPE REMOVED CN 3472><FPU Handling with OEM NSPs item 13> - Pre Job Brief | 12-Nov-24 A | 12-Nov-24 A | 1 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772.A1010 | DNB Pull Harder Safety Case | 2024-10-07 | 2024-11-01 | <S'standt'n of Funct'l Cap of PWTS and DWTS at the Enh'ed Overload Trip Settings> - Prepare Draft EAN / Report | 13-Nov-24 A | 14-Feb-25 A | 20 | 0 | 65 | 100% |  | Completed
W232LT | W232 | W232.C2890 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Summary | 14-Nov-24 A | 14-Nov-24 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C2900 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Prepare Draft EAN | 14-Nov-24 A | 14-Nov-24 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C2910 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Issue Draft EAN to EDF for Review. | 14-Nov-24 A | 14-Nov-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C2920 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Draft EAN Reviewed by EDF SQEP | 14-Nov-24 A | 14-Nov-24 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C2930 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Address Comments from EDF Review on Draft EAN | 14-Nov-24 A | 14-Nov-24 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C2940 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Issue Final EAN | 14-Nov-24 A | 14-Nov-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C2950 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - EAN Completed and Uploaded to CDMS | 14-Nov-24 A | 14-Nov-24 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C2960 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - EAN Completed | 14-Nov-24 A | 14-Nov-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C2970 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Summary Bar | 14-Nov-24 A | 14-Nov-24 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C2980 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Draft and issue RFS | 14-Nov-24 A | 14-Nov-24 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C2990 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Supplier prepare and issue Offer | 14-Nov-24 A | 14-Nov-24 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3000 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Review Offer, prepare and issue CI | 14-Nov-24 A | 14-Nov-24 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3010 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Supplier mobilisation time | 14-Nov-24 A | 14-Nov-24 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3020 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - Pre Job Brief | 14-Nov-24 A | 14-Nov-24 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3030 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN3472> <FPU Handling with Shock Loaded Units item 15> - TSA Internal Review of Draft EAN | 14-Nov-24 A | 14-Nov-24 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5690 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events (Group 2)> - Draft Task Sheet | 14-Nov-24 A | 14-Nov-24 A | 15 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5700 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events (Group 2)> - Issue Task sheet | 14-Nov-24 A | 14-Nov-24 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5710 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events (Group 2)> - Review Task sheet | 14-Nov-24 A | 14-Nov-24 A | 5 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5720 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events (Group 2)> - Approve Task sheet | 14-Nov-24 A | 14-Nov-24 A | 5 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5730 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events (Group 2)> - Search for station Lifetime Record | 14-Nov-24 A | 14-Nov-24 A | 20 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5740 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events (Group 2)> - Review station Lifetime Record | 14-Nov-24 A | 14-Nov-24 A | 20 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5750 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit (Group 2)>-Issue finding from Review of Lifetime Record | 14-Nov-24 A | 14-Nov-24 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5760 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit (Grp 2)> Hold scoping session with DA, SAG and Station | 14-Nov-24 A | 14-Nov-24 A | 5 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5770 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events (Group 2)> - Issue scope for review | 14-Nov-24 A | 14-Nov-24 A | 10 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5780 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events (Group 2)> - Approve Scope | 14-Nov-24 A | 14-Nov-24 A | 10 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 2290 | HYA Fuel Handling Essential Safety Case |  |  | ONR issue letter of No Objection | 14-Nov-24 A | 24-Jan-25 A | 37 | 0 | 45 | 100% |  | Completed
ER6698LT | W224 | W224. A1550 | HRA Enhanced Defueling Safety Case | 2024-11-18 | 2025-01-02 | Write & Prepare IRM Paper [Schedule, Cost, Estimates, Risks] | 18-Nov-24 A | 02-Jan-25 A | 15 | 0 | 30 | 100% |  | Completed
ER6701LT | W228 | W228. A1550 | HYA Enhanced Defueling Safety Case | 2024-11-18 | 2025-01-02 | Write & Prepare IRM Paper [Schedule, Cost, Estimates, Risks] | 18-Nov-24 A | 02-Jan-25 A | 15 | 0 | 30 | 100% |  | Completed
ER6372LT | W203 | W203.C1410 | HNB Enhanced Defuelling Safety Cases | 2024-05-01 | 2024-05-08 | Incorporate CO & Station comments | 18-Nov-24 A | 18-Nov-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1420 | HNB Enhanced Defuelling Safety Cases | 2024-05-09 | 2024-05-10 | Produce verification file | 18-Nov-24 A | 18-Nov-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1120 | HNB Enhanced Defuelling Safety Cases |  |  | Modify Estimate, Schedule & Risk Log as Required | 19-Nov-24 A | 19-Nov-24 A | 3 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.A4220 | HNB Enhanced Defuelling Safety Cases | 2024-11-20 | 2025-04-10 | SC - Cost of Contract - Atkins realis Contract | 19-Nov-24 A | 17-Jan-25 A | 99 | 0 | 40 | 100% |  | Completed
ER6372LT | W203 | W203.D1110 | HNB Enhanced Defuelling Safety Cases |  |  | Hold PRC Meeting | 19-Nov-24 A | 19-Nov-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.E4200 | HNB Enhanced Defuelling Safety Cases | 2024-11-19 | 2025-04-11 | Project Management C - D | 19-Nov-24 A | 17-Jan-25 A | 101 | 0 | 40 | 100% |  | Completed
ER6372LT | W203 | W203.E1550 | HNB Enhanced Defuelling Safety Cases | 2024-11-19 | 2025-04-11 | Station Oversight C - D | 19-Nov-24 A | 17-Jan-25 A | 101 | 0 | 40 | 100% |  | Completed
W772LT | W772 | W772LT.D3110 | DNB Pull Harder Safety Case | 2024-11-19 | 2024-11-19 | Hold PRC Meeting | 19-Nov-24 A | 19-Nov-24 A | 1 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772LT.D3120 | DNB Pull Harder Safety Case | 2024-11-19 | 2024-11-19 | Modify Estimate, Schedule & Risk Log as Required | 19-Nov-24 A | 19-Nov-24 A | 1 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.A4210 | HNB Enhanced Defuelling Safety Cases |  | 2024-11-19 | Gate C PRC Paper Approval | 19-Nov-24 A | 19-Nov-24 A | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.D3130 | DNB Pull Harder Safety Case |  | 2024-11-19 | Gate A PRC Paper Approval | 19-Nov-24 A | 19-Nov-24 A | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.D2065 | DNB Pull Harder Safety Case |  | 2024-11-19 | Gate A PRC Paper Approval | 19-Nov-24 A | 19-Nov-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1290 | HNB Enhanced Defuelling Safety Cases | 2024-11-20 | 2024-11-26 | Agree design proposals with Station in the case of hardware mods | 20-Nov-24 A | 26-Nov-24 A | 5 | 0 | 4 | 100% |  | Completed
ER6372LT | W203 | W203.D1450 | HNB Enhanced Defuelling Safety Cases | 2024-11-20 | 2024-12-17 | Produce supporting reference <Generic Hoist Trip Setting Increase SC> | 20-Nov-24 A | 17-Dec-24 A | 20 | 0 | 19 | 100% |  | Completed
ER6372LT | W203 | W203.D1550 | HNB Enhanced Defuelling Safety Cases | 2024-11-20 | 2024-11-26 | Identify verifier for the case & establish all other resources | 20-Nov-24 A | 26-Nov-24 A | 5 | 0 | 4 | 100% |  | Completed
ER6372LT | W203 | W203.D1310 | HNB Enhanced Defuelling Safety Cases | 2024-11-25 | 2024-11-26 | CA to agree with CO format of the safety case & produce agreed contents page | 25-Nov-24 A | 26-Nov-24 A | 2 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772LT.A2260 | DNB Pull Harder Safety Case | 2024-11-25 | 2025-05-21 | <Load Path Assessment> - Summary | 25-Nov-24 A | 2025-04-23 | 103 | 36 | 103 | 0% | 8 | In Progress
W772LT | W772 | W772LT.A2270 | DNB Pull Harder Safety Case | 2024-11-25 | 2025-02-03 | <Load Path Assessment> - Prepare Draft EAN | 25-Nov-24 A | 2025-03-07 | 37 | 5 | 72 | 85% | 8 | In Progress
W232LT | W232 | W232.C3070 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events> - Summary | 26-Nov-24 A | 26-Nov-24 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3080 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events> - Prepare Draft EAN - Group 2 | 26-Nov-24 A | 26-Nov-24 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3090 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events> - Issue Draft EAN to EDF for Review. | 26-Nov-24 A | 26-Nov-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3100 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events> - Draft EAN Reviewed by EDF SQEP | 26-Nov-24 A | 26-Nov-24 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3110 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events> - Address Comments from EDF Review on | 26-Nov-24 A | 26-Nov-24 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3120 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events> - Issue Final EAN | 26-Nov-24 A | 26-Nov-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3130 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events> - EAN Completed and Uploaded to CDMS | 26-Nov-24 A | 26-Nov-24 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3140 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events> - EAN Completed | 26-Nov-24 A | 26-Nov-24 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3085 | DNB Enhanced Safety Cases |  |  | <SCOPE REMOVED CN 3472><Further Review of Shock Loaded Unit Events> - TSA Internal Review of Draft EAN | 26-Nov-24 A | 26-Nov-24 A | 1 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1220 | HNB Enhanced Defuelling Safety Cases | 2024-11-27 | 2024-12-03 | Produce draft NSRS (using BARRIER MODEL) | 27-Nov-24 A | 03-Dec-24 A | 5 | 0 | 4 | 100% |  | Completed
ER6372LT | W203 | W203.D1340 | HNB Enhanced Defuelling Safety Cases | 2024-11-27 | 2024-11-28 | Produce verification plan | 27-Nov-24 A | 28-Nov-24 A | 2 | 0 | 1 | 100% |  | Completed
W230LT | W230 | W230.2010 | HYB Enhanced Defueling Safety Case Strategy | 2024-07-22 | 2024-07-22 | TSA Issue Final Report | 27-Nov-24 A | 18-Dec-24 A | 1 | 0 | 16 | 100% |  | Completed
W234LT | W234 | W234.2010 | TOR Enhanced Defueling Safety Case Strategy | 2024-07-22 | 2024-07-22 | TSA Issue Final Report | 27-Nov-24 A | 18-Dec-24 A | 1 | 0 | 16 | 100% |  | Completed
W232LT | W232 | W232.A2420 | DNB Enhanced Safety Cases | 2025-01-21 | 2025-01-21 | Rev 000 - Post Job Debrief | 28-Nov-24 A | 28-Nov-24 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5030 | DNB Enhanced Safety Cases |  |  | Lessons Learned Workshop - FPU Safety Case Ph 3 Rev 000 Station approved | 28-Nov-24 A | 28-Nov-24 A | 1 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5220 | DNB Enhanced Safety Cases |  |  | Lessons Learned Workshop - FPU Safety Case Ph 3 Rev 000 INSA | 28-Nov-24 A | 28-Nov-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A27130 | HRA Fuel Handling Essential Safety Case | 2023-05-02 | 2024-05-31 | ETC (DD-PF) 2024 | 02-Dec-24 A | 31-Dec-24 A | 20 | 0 | 20 | 100% |  | Completed
ER6650LT | W226 | W226.A27130 | HYA Fuel Handling Essential Safety Case | 2023-05-02 | 2024-05-31 | ETC (DD-PF) 2024 | 02-Dec-24 A | 31-Dec-24 A | 20 | 0 | 20 | 100% |  | Completed
W520LT | W520 | W520.A1030 | FLEETWIDE CTO Defueling Safety Case Delivery | 2024-01-02 | 2024-12-31 | 2024 Costs | 02-Dec-24 A | 27-Dec-24 A | 18 | 0 | 18 | 100% |  | Completed
W520LT | W520 | W520.A1290 | FLEETWIDE CTO Defueling Safety Case Delivery |  |  | ETC (DD-PF) 2024 | 02-Dec-24 A | 02-Dec-24 A | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.T1270 | DNB Pull Harder Safety Case | 2024-10-07 | 2024-10-18 | <Operating Strategy for Pull Harder Facility> - Draft EAN / Report Tech Reviewed by EDF SQEP | 02-Dec-24 A | 13-Dec-24 A | 10 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.C3410 | DNB Enhanced Safety Cases | 2024-12-02 | 2024-12-27 | <NEW SCOPE CN3472> Scoping of Requirement | 02-Dec-24 A | 31-Dec-24 A | 18 | 0 | 19 | 100% |  | Completed
ER6372LT | W203 | W203.D1230 | HNB Enhanced Defuelling Safety Cases | 2024-12-04 | 2024-12-13 | Station comments on NSRS | 04-Dec-24 A | 13-Dec-24 A | 8 | 0 | 7 | 100% |  | Completed
ER6372LT | W203 | W203.D1240 | HNB Enhanced Defuelling Safety Cases | 2024-12-04 | 2024-12-13 | Key Stakeholders (Peer) comments on NSRS (as required) | 04-Dec-24 A | 13-Dec-24 A | 8 | 0 | 7 | 100% |  | Completed
W772LT | W772 | W772LT.KDM.A1047-1 | DNB Pull Harder Safety Case |  | 2024-12-04 | KDM - <NEW SCOPE CN 3373> - NSRS presented at NSC | 04-Dec-24 A | 04-Dec-24 A | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A1047 | DNB Pull Harder Safety Case | 2024-12-04 | 2024-12-04 | <NEW SCOPE CN 3373> - NSRS presented at NSC | 04-Dec-24 A | 04-Dec-24 A | 1 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772.A1110 | DNB Pull Harder Safety Case |  |  | <New SCOPE PENDING CN3634> - <Cavendish PWTS Funct Capability Report> - Produce Report | 05-Dec-24 A | 06-Jan-25 A | 1 | 0 | 20 | 100% |  | Completed
W772LT | W772 | W772LT.A1057 | DNB Pull Harder Safety Case | 2024-12-05 | 2024-12-18 | <NEW SCOPE CN 3373> - Address NSC Comments | 05-Dec-24 A | 18-Dec-24 A | 10 | 0 | 10 | 100% |  | Completed
W232LT | W232 | W232.C1840 | DNB Enhanced Safety Cases | 2024-12-06 | 2025-09-17 | <SCOPE CHANGE CN3472><FPU Uninspected Welds lifting integrity (including sub-veto faults)> - Summary | 06-Dec-24 A | 2025-09-05 | 188 | 130 | 188 | 0% | 5 | In Progress
W232LT | W232 | W232.C3150 | DNB Enhanced Safety Cases | 2024-12-06 | 2024-12-27 | <NEW SCOPE CN3472> - Review faults | 06-Dec-24 A | 10-Jan-25 A | 14 | 0 | 22 | 100% |  | Completed
W232LT | W232 | W232.C3330 | DNB Enhanced Safety Cases | 2024-12-06 | 2024-12-20 | <NEW SCOPE CN3472> Review Technical note to be issued to SAG | 06-Dec-24 A | 10-Jan-25 A | 11 | 0 | 23 | 100% |  | Completed
W232LT | W232 | W232.A5470 | DNB Enhanced Safety Cases |  |  | Draft task sheet | 06-Dec-24 A | 24-Jan-25 A | 33 | 0 | 33 | 100% |  | Completed
W232LT | W232 | W232.C3325 | DNB Enhanced Safety Cases | 2024-12-06 | 2025-06-03 | <SCOPE CHANGE CN3472><NSP Pin Failure> - Summary | 06-Dec-24 A | 2025-08-07 | 168 | 110 | 168 | 0% | 25 | In Progress
ER6666LT | W209 | W209.1545 | HYB Essential Defueling Safety Case | 2024-07-24 | 2024-08-06 | Incorporate INSA comments | 09-Dec-24 A | 19-Feb-25 A | 22 | 0 | 50 | 100% |  | Completed
ER6668LT | W213 | W213.1545 | TOR Essential Defueling Safety Case | 2024-07-24 | 2024-08-06 | Incorporate INSA comments | 09-Dec-24 A | 19-Feb-25 A | 27 | 0 | 49 | 100% |  | Completed
ER6372LT | W203 | W203.D1730 | HNB Enhanced Defuelling Safety Cases |  | 2024-12-13 | INSA Resource Identified | 13-Dec-24 A | 13-Dec-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1580 | HNB Enhanced Defuelling Safety Cases | 2024-12-16 | 2024-12-20 | INA comments on NSRS | 16-Dec-24 A | 20-Dec-24 A | 5 | 0 | 4 | 100% |  | Completed
W772LT | W772 | W772LT.T1280 | DNB Pull Harder Safety Case | 2024-10-21 | 2024-10-25 | <Operating Strategy for Pull Harder Facility> - Address Comments from EDF Review on Draft EAN / Report | 16-Dec-24 A | 28-Feb-25 A | 5 | 0 | 51 | 100% |  | Completed
ER6372LT | W203 | W203.D1640 | HNB Enhanced Defuelling Safety Cases | 2024-12-17 | 2025-01-02 | Develop plan with further iterations | 17-Dec-24 A | 02-Jan-25 A | 10 | 0 | 9 | 100% |  | Completed
W772LT | W772 | W772LT.A2140 | DNB Pull Harder Safety Case | 2024-12-09 | 2024-12-09 | <Human Factors> - Populate HF Template | 17-Dec-24 A | 17-Dec-24 A | 5 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1600 | HNB Enhanced Defuelling Safety Cases | 2024-12-18 | 2025-01-03 | Verify supporting reference <Generic Hoist Trip Setting Increase SC> | 18-Dec-24 A | 03-Jan-25 A | 10 | 0 | 9 | 100% |  | Completed
W772LT | W772 | W772LT.A1125 | DNB Pull Harder Safety Case | 2025-02-04 | 2025-03-11 | Proposal - Preliminary Work | 18-Dec-24 A | 06-Jan-25 A | 26 | 0 | 11 | 100% |  | Completed
W232LT | W232 | W232.C1850 | DNB Enhanced Safety Cases | 2025-03-03 | 2025-03-28 | <SCOPE CHANGE CN3472><FPU Uninspected Welds lifting integrity (including sub-veto faults)> - Prepare Draft EAN Part 1 | 19-Dec-24 A | 23-Jan-25 A | 20 | 0 | 22 | 100% |  | Completed
W772LT | W772 | W772LT.KDM.A1067-1 | DNB Pull Harder Safety Case |  | 2025-01-08 | KDM - <NEW SCOPE CN 3373> - Final INSA Approval and Re-sign Milestones | 19-Dec-24 A | 19-Dec-24 A | 0 | 0 | 0 | 100% |  | Completed
W230LT | W230 | W230.2020 | HYB Enhanced Defueling Safety Case Strategy | 2024-07-23 | 2024-07-29 | TR Completed and Uploaded to CDMS | 19-Dec-24 A | 20-Dec-24 A | 2 | 0 | 2 | 100% |  | Completed
W772LT | W772 | W772LT.A1040 | DNB Pull Harder Safety Case | 2025-01-09 | 2025-01-09 | Issue final NSRS | 19-Dec-24 A | 19-Dec-24 A | 1 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772LT.A1050 | DNB Pull Harder Safety Case | 2025-01-13 | 2025-01-24 | Station agree NSRS ==> KDM | 19-Dec-24 A | 19-Dec-24 A | 10 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772LT.A1235 | DNB Pull Harder Safety Case | 2025-01-27 | 2025-01-31 | Circulate NSRS for Relevant Stakeholders | 19-Dec-24 A | 19-Dec-24 A | 5 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772LT.A1230 | DNB Pull Harder Safety Case | 2025-01-13 | 2025-01-24 | DA & INSA agree NSRS (for authorised designers-NSRS must be reviewed by DA) ==> KDM | 19-Dec-24 A | 19-Dec-24 A | 10 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772LT.A1500 | DNB Pull Harder Safety Case | 2025-02-03 | 2025-02-03 | Send NSRS to ONR to determine level of review required (Acknowledgement or Agreement) | 19-Dec-24 A | 19-Dec-24 A | 1 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772LT.A1510 | DNB Pull Harder Safety Case | 2025-02-04 | 2025-02-04 | ONR L4 Meeting | 19-Dec-24 A | 19-Dec-24 A | 1 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772LT.A1067 | DNB Pull Harder Safety Case | 2024-12-19 | 2025-01-08 | <NEW SCOPE CN 3373> - Final INSA Approval and Re-sign Milestones | 19-Dec-24 A | 19-Dec-24 A | 12 | 0 | 1 | 100% |  | Completed
W234LT | W234 | W234.2020 | TOR Enhanced Defueling Safety Case Strategy | 2024-07-23 | 2024-07-29 | TR Completed and Uploaded to CDMS | 19-Dec-24 A | 20-Dec-24 A | 2 | 0 | 2 | 100% |  | Completed
W772LT | W772 | W772LT.KDM.SP02 | DNB Pull Harder Safety Case |  | 2025-01-24 | KDM - NSRS agreed by stakeholders EC 375698 <DNB Pull Harder SC> | 19-Dec-24 A | 19-Dec-24 A | 0 | 0 | 0 | 100% |  | Completed
W230LT | W230 | W230.1900 | HYB Enhanced Defueling Safety Case Strategy | 2024-07-30 | 2024-08-12 | EC Kick Off Meeting & Early Strategy Development | 20-Dec-24 A | 20-Dec-24 A | 2 | 0 | 1 | 100% |  | Completed
W230LT | W230 | W230.3760 | HYB Enhanced Defueling Safety Case Strategy |  |  | HYB Enhanced Defueling Rate: Strategy EAN Complete | 20-Dec-24 A | 20-Dec-24 A | 0 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.1900 | TOR Enhanced Defueling Safety Case Strategy | 2024-07-30 | 2024-08-12 | EC Kick Off Meeting & Early Strategy Development | 20-Dec-24 A | 20-Dec-24 A | 2 | 0 | 1 | 100% |  | Completed
W234LT | W234 | W234.3760 | TOR Enhanced Defueling Safety Case Strategy |  |  | TOR Enhanced Defueling Rate: Strategy EAN Complete | 20-Dec-24 A | 20-Dec-24 A | 0 | 0 | 0 | 100% |  | Completed
W230LT | W230 | W230.2030 | HYB Enhanced Defueling Safety Case Strategy |  | 2024-07-29 | Strategy EAN Complete | 20-Dec-24 A | 20-Dec-24 A | 0 | 0 | 0 | 100% |  | Completed
W230LT | W230 | W230.3740 | HYB Enhanced Defueling Safety Case Strategy |  |  | HYB - EC Kick Off Meeting & Early Strategy Development | 20-Dec-24 A | 20-Dec-24 A | 0 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.2030 | TOR Enhanced Defueling Safety Case Strategy |  | 2024-07-29 | Strategy EAN Complete | 20-Dec-24 A | 20-Dec-24 A | 0 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.3740 | TOR Enhanced Defueling Safety Case Strategy |  |  | TOR - EC Kick Off Meeting & Early Strategy Development | 20-Dec-24 A | 20-Dec-24 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1420 | HNB Enhanced Defuelling Safety Cases | 2024-12-23 | 2024-12-31 | Incorporate INA, Station, ED (peer) comments | 23-Dec-24 A | 31-Dec-24 A | 5 | 0 | 4 | 100% |  | Completed
W232LT | W232 | W232.A5050 | DNB Enhanced Safety Cases | 2025-09-09 | 2025-10-27 | <SCOPE CHANGE CN3472> Rev 001 - Prepare the Safety Case Proposal (including OPEX Review) | 02-Jan-25 A | 2025-09-19 | 45 | 33 | 182 | 0% | 5 | In Progress
W232LT | W232 | W232.C2230 | DNB Enhanced Safety Cases | 2025-02-14 | 2025-07-29 | <SCOPE NAME CHANGE CN3472><FPU and ESA Handling with OEM NSPs> - Summary | 02-Jan-25 A | 2025-08-06 | 109 | 104 | 151 | 0% | 26 | In Progress
W232LT | W232 | W232.C2240 | DNB Enhanced Safety Cases | 2025-02-14 | 2025-03-13 | <SCOPE NAME CHANGE CN3472><FPU and ESA Handling with OEM NSPs> - Prepare Draft EAN Part1 | 02-Jan-25 A | 2025-03-24 | 20 | 0 | 57 | 50% | 6 | In Progress
ER6701LT | W228 | W228.2220 | HYA Enhanced Defueling Safety Case | 2025-01-02 | 2025-02-03 | Contract Negotiations | 02-Jan-25 A | 03-Feb-25 A | 1 | 0 | 23 | 100% |  | Completed
ER6372LT | W203 | W203.D1250 | HNB Enhanced Defuelling Safety Cases | 2025-01-02 | 2025-01-02 | Issue final NSRS | 02-Jan-25 A | 02-Jan-25 A | 1 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1260 | HNB Enhanced Defuelling Safety Cases |  | 2025-01-02 | Station agree NSRS *(KDM)* <Generic Hoist Trip Setting Increase EC375945> | 02-Jan-25 A | 02-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1720 | HNB Enhanced Defuelling Safety Cases |  | 2025-01-02 | Verifier PJB Held | 02-Jan-25 A | 02-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5570 | DNB Enhanced Safety Cases |  |  | <NEW SCOPE PENDING CN3754> - Prepare and Populate Affected Documents List Rev 000 | 02-Jan-25 A | 2025-03-07 | 10 | 5 | 47 | 1% | 244 | In Progress
ER6372LT | W203 | W203.C1460 | HNB Enhanced Defuelling Safety Cases |  | 2024-05-10 | Issue high quality verified draft iss A with verification file to INSA & station (T - 3 wks before NSC date) *(E375412)* | 02-Jan-25 A | 02-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1480 | HNB Enhanced Defuelling Safety Cases | 2024-05-20 | 2024-06-03 | INSA review & iteration of comments (using BARRIER MODEL) | 02-Jan-25 A | 04-Feb-25 A | 6 | 0 | 23 | 100% |  | Completed
ER6372LT | W203 | W203.C1430 | HNB Enhanced Defuelling Safety Cases |  | 2024-05-10 | Verification complete | 02-Jan-25 A | 02-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1440 | HNB Enhanced Defuelling Safety Cases |  | 2024-05-10 | Submit for approval - Categoriser ratifies; RE/CO endorsement | 02-Jan-25 A | 02-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1470 | HNB Enhanced Defuelling Safety Cases | 2024-05-13 | 2024-05-17 | Key Stakeholders Approval, if requested | 02-Jan-25 A | 10-Jan-25 A | 7 | 0 | 7 | 100% |  | Completed
ER6378LT | W222 | W222.A27475 | HRA Fuel Handling Essential Safety Case |  |  | ETC (DD-PF) 2025 | 02-Jan-25 A | 2025-03-31 | 63 | 21 | 63 | 50% | 0 | In Progress
ER6650LT | W226 | W226.A27475 | HYA Fuel Handling Essential Safety Case |  |  | ETC (DD-PF) 2025 | 02-Jan-25 A | 2025-03-31 | 63 | 21 | 63 | 50% | 0 | In Progress
ER6698LT | W224 | W224.1230 | HRA Enhanced Defueling Safety Case | 2025-01-02 | 2025-01-08 | Design Feedback into Scheme | 02-Jan-25 A | 08-Jan-25 A | 5 | 0 | 5 | 100% |  | Completed
ER6698LT | W224 | W224.1310 | HRA Enhanced Defueling Safety Case | 2025-01-02 | 2025-01-02 | HAZOP - Feed into CETS (trip Function) | 02-Jan-25 A | 02-Jan-25 A | 1 | 0 | 1 | 100% |  | Completed
ER6698LT | W224 | W224.1530 | HRA Enhanced Defueling Safety Case | 2025-01-02 | 2025-01-15 | Review & Approval | 02-Jan-25 A | 15-Jan-25 A | 10 | 0 | 10 | 100% |  | Completed
ER6698LT | W224 | W224.2220 | HRA Enhanced Defueling Safety Case | 2025-01-02 | 2025-02-03 | Contract Negotiations | 02-Jan-25 A | 03-Feb-25 A | 9 | 0 | 22 | 100% |  | Completed
ER6698LT | W224 | W224.2580 | HRA Enhanced Defueling Safety Case | 2025-01-02 | 2025-02-14 | Author CETS CETS for Trip Functions | 02-Jan-25 A | 2025-03-07 | 10 | 5 | 47 | 89% | 26 | In Progress
ER6698LT | W224 | W224. A1560 | HRA Enhanced Defueling Safety Case | 2025-01-02 | 2025-01-06 | IRM Paper Stakeholder Sign Off | 02-Jan-25 A | 06-Jan-25 A | 8 | 0 | 2 | 100% |  | Completed
ER6698LT | W224 | W224.1240 | HRA Enhanced Defueling Safety Case | 2025-01-02 | 2025-02-14 | TR of Optioneering | 02-Jan-25 A | 2025-03-03 | 10 | 1 | 43 | 100% | 30 | In Progress
ER6698LT | W224 | W224.3680 | HRA Enhanced Defueling Safety Case | 2025-01-02 | 2025-01-31 | EdF Technical Review | 02-Jan-25 A | 31-Jan-25 A | 11 | 0 | 21 | 100% |  | Completed
ER6701LT | W228 | W228.3680 | HYA Enhanced Defueling Safety Case | 2025-01-02 | 2025-01-28 | EdF Technical Review | 02-Jan-25 A | 28-Jan-25 A | 11 | 0 | 18 | 100% |  | Completed
ER6701LT | W228 | W228.1240 | HYA Enhanced Defueling Safety Case | 2025-01-02 | 2025-02-14 | TR of Optioneering | 02-Jan-25 A | 2025-03-03 | 10 | 1 | 43 | 97% | 30 | In Progress
ER6701LT | W228 | W228. A1560 | HYA Enhanced Defueling Safety Case | 2025-01-02 | 2025-01-06 | IRM Paper stakeholder sign off | 02-Jan-25 A | 06-Jan-25 A | 8 | 0 | 2 | 100% |  | Completed
ER6701LT | W228 | W228.2580 | HYA Enhanced Defueling Safety Case | 2025-01-02 | 2025-02-14 | Author CETS for Trip Functions | 02-Jan-25 A | 2025-03-07 | 10 | 5 | 47 | 89% | 26 | In Progress
ER6701LT | W228 | W228.1530 | HYA Enhanced Defueling Safety Case | 2025-01-02 | 2025-01-15 | Review & Approval | 02-Jan-25 A | 15-Jan-25 A | 10 | 0 | 10 | 100% |  | Completed
ER6701LT | W228 | W228.1310 | HYA Enhanced Defueling Safety Case | 2025-01-02 | 2025-01-02 | HAZOP - Feed into CETS (trip Function) | 02-Jan-25 A | 02-Jan-25 A | 1 | 0 | 1 | 100% |  | Completed
ER6701LT | W228 | W228.1230 | HYA Enhanced Defueling Safety Case | 2025-01-02 | 2025-01-08 | Design Feedback into Scheme | 02-Jan-25 A | 08-Jan-25 A | 5 | 0 | 5 | 100% |  | Completed
ER6372LT | W203 | W203.D1210 | HNB Enhanced Defuelling Safety Cases | 2024-11-20 | 2024-11-20 | Produce MF (as required) | 02-Jan-25 A | 02-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1400 | HNB Enhanced Defuelling Safety Cases |  | 2024-11-20 | Issue MF (as required) | 02-Jan-25 A | 02-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1520 | HNB Enhanced Defuelling Safety Cases | 2024-11-20 | 2024-11-26 | Categorisation by RE / Station | 02-Jan-25 A | 08-Jan-25 A | 5 | 0 | 5 | 100% |  | Completed
W232LT | W232 | W232.C3420 | DNB Enhanced Safety Cases | 2024-12-30 | 2025-01-17 | <NEW SCOPE CN3472> Draft SCDP | 02-Jan-25 A | 07-Jan-25 A | 14 | 0 | 3 | 100% |  | Completed
ER6372LT | W203 | W203.D1430 | HNB Enhanced Defuelling Safety Cases |  | 2025-01-02 | NSORC agree NSRS (SZB Only) | 02-Jan-25 A | 02-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1440 | HNB Enhanced Defuelling Safety Cases |  | 2025-01-02 | Key Stakeholders agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 02-Jan-25 A | 02-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1590 | HNB Enhanced Defuelling Safety Cases |  | 2025-01-02 | INA agree NSRS | 02-Jan-25 A | 02-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1300 | HNB Enhanced Defuelling Safety Cases | 2025-01-03 | 2025-01-09 | Consolidate & issue to stakeholders & suppliers agreed NSRS (as required) | 03-Jan-25 A | 09-Jan-25 A | 5 | 0 | 4 | 100% |  | Completed
ER6372LT | W203 | W203.D1610 | HNB Enhanced Defuelling Safety Cases | 2025-01-06 | 2025-01-17 | BE Technical review of supporting reference <Generic Hoist Trip Setting Increase SC> | 06-Jan-25 A | 17-Jan-25 A | 10 | 0 | 9 | 100% |  | Completed
W772LT | W772 | W772.A1120 | DNB Pull Harder Safety Case |  |  | <New SCOPE PENDING CN3634> - <Cavendish PWTS Report> - EDF TR Round 1 | 06-Jan-25 A | 10-Jan-25 A | 1 | 0 | 5 | 100% |  | Completed
W772LT | W772 | W772LT.A1145 | DNB Pull Harder Safety Case | 2025-03-12 | 2025-03-25 | Pre Job Brief | 06-Jan-25 A | 06-Jan-25 A | 10 | 0 | 1 | 100% |  | Completed
W772LT | W772 | W772LT.A1130 | DNB Pull Harder Safety Case | 2025-04-08 | 2025-06-06 | Prepare the Safety Case Proposal | 07-Jan-25 A | 2025-04-29 | 40 | 35 | 79 | 50% | 4 | In Progress
ER6698LT | W224 | W224. A1570 | HRA Enhanced Defueling Safety Case |  | 2025-01-08 | Gate B-D PRC Paper Submission | 08-Jan-25 A | 08-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3430 | DNB Enhanced Safety Cases | 2025-01-20 | 2025-01-31 | <NEW SCOPE CN3472> Review SCDP | 08-Jan-25 A | 16-Jan-25 A | 10 | 0 | 6 | 100% |  | Completed
ER6372LT | W203 | W203.D1560 | HNB Enhanced Defuelling Safety Cases |  | 2025-01-09 | Issue agreed work programme to stakeholders & suppliers | 09-Jan-25 A | 09-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1410 | HNB Enhanced Defuelling Safety Cases | 2024-11-27 | 2024-11-28 | INSA agree MF (as required) *(KDM)* <Generic Hoist Trip Setting Increase EC375945> | 09-Jan-25 A | 10-Jan-25 A | 2 | 0 | 2 | 100% |  | Completed
W772LT | W772 | W772.A1130 | DNB Pull Harder Safety Case |  |  | <New SCOPE PENDING CN3634> - <Cavendish PWTS Report> - Address Comments | 10-Jan-25 A | 28-Jan-25 A | 1 | 0 | 13 | 100% |  | Completed
W232LT | W232 | W232.C3160 | DNB Enhanced Safety Cases | 2024-12-30 | 2025-01-17 | <NEW SCOPE CN3472> - Draft specification of R6 assessment to be issue to SAG will include OEM NSPs | 10-Jan-25 A | 13-Jan-25 A | 14 | 0 | 2 | 100% |  | Completed
ER6372LT | W203 | W203.D1650 | HNB Enhanced Defuelling Safety Cases |  | 2024-11-28 | INSA Approval Date Identified | 10-Jan-25 A | 10-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1660 | HNB Enhanced Defuelling Safety Cases |  | 2024-11-28 | Provide Provisional NSC Date (as required) | 10-Jan-25 A | 10-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224. A1580 | HRA Enhanced Defueling Safety Case | 2025-01-13 | 2025-01-22 | Hold PRC | 13-Jan-25 A | 22-Jan-25 A | 1 | 0 | 1 | 100% |  | Completed
ER6701LT | W228 | W228. A1580 | HYA Enhanced Defueling Safety Case | 2025-01-13 | 2025-01-22 | Hold PRC | 13-Jan-25 A | 22-Jan-25 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C3340 | DNB Enhanced Safety Cases |  | 2024-12-20 | <NEW SCOPE CN3472> Atkins to issue Technical note to SAG | 13-Jan-25 A | 13-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3360 | DNB Enhanced Safety Cases |  |  | Decision Point Milestone - (NSP Pin Failure) | 13-Jan-25 A | 13-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3170 | DNB Enhanced Safety Cases |  | 2025-01-17 | <NEW SCOPE CN3472> - Issue specification to SAG | 13-Jan-25 A | 13-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.1190 | HRA Fuel Handling Essential Safety Case | 2024-02-06 | 2024-02-19 | Station Approval of HRA Defuelling Fuel Handling Essential Safety Case | 14-Jan-25 A | 27-Jan-25 A | 10 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | W226.1195 | HYA Fuel Handling Essential Safety Case | 2024-02-06 | 2024-02-19 | Station Approval of HYA Defuelling Fuel Handling Essential Safety Case | 14-Jan-25 A | 29-Jan-25 A | 10 | 0 | 11 | 100% |  | Completed
ER6698LT | W224 | W224.2160 | HRA Enhanced Defueling Safety Case | 2025-01-16 | 2025-01-29 | Best Option/ALARP Strategy >>> Discovery Milestone | 16-Jan-25 A | 29-Jan-25 A | 10 | 0 | 10 | 100% |  | Completed
ER6701LT | W228 | W228.2160 | HYA Enhanced Defueling Safety Case | 2025-01-16 | 2025-01-29 | Best Option/ALARP Strategy | 16-Jan-25 A | 29-Jan-25 A | 10 | 0 | 10 | 100% |  | Completed
W772LT | W772 | W772LT.A2630 | DNB Pull Harder Safety Case |  |  | <<NEW SCOPE PENDING CN3634><Load Path Assessment Appendix - Fixed DWTS> > - Pre Job Brief | 16-Jan-25 A | 16-Jan-25 A | 133 | 0 | 1 | 100% |  | Completed
ER6372LT | W203 | W203.D1320 | HNB Enhanced Defuelling Safety Cases | 2025-01-03 | 2025-02-13 | Prepare the Safety Case Proposal (including OPEX Review) | 17-Jan-25 A | 17-Jan-25 A | 30 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1330 | HNB Enhanced Defuelling Safety Cases | 2025-03-14 | 2025-03-20 | Incorporate CO & Station comments | 17-Jan-25 A | 17-Jan-25 A | 5 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1350 | HNB Enhanced Defuelling Safety Cases | 2025-02-14 | 2025-03-13 | Verification of the case (using BARRIER MODEL) | 17-Jan-25 A | 17-Jan-25 A | 20 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1360 | HNB Enhanced Defuelling Safety Cases | 2025-03-14 | 2025-03-17 | Produce verification file | 17-Jan-25 A | 17-Jan-25 A | 2 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1380 | HNB Enhanced Defuelling Safety Cases | 2025-03-21 | 2025-04-03 | INSA review & iteration of comments (using BARRIER MODEL) | 17-Jan-25 A | 17-Jan-25 A | 10 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1480 | HNB Enhanced Defuelling Safety Cases |  | 2025-03-20 | Verification complete | 17-Jan-25 A | 17-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1510 | HNB Enhanced Defuelling Safety Cases | 2025-04-04 | 2025-04-10 | Station Approval for mod implementation (including station review meeting) | 17-Jan-25 A | 17-Jan-25 A | 5 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1530 | HNB Enhanced Defuelling Safety Cases |  | 2025-03-13 | Issue to CO & Station for comments | 17-Jan-25 A | 17-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1570 | HNB Enhanced Defuelling Safety Cases |  | 2025-04-03 | INSA Final Approval *(KDM)* <Generic Hoist Trip Setting Increase EC375945> | 17-Jan-25 A | 17-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1620 | HNB Enhanced Defuelling Safety Cases |  | 2025-01-17 | Supporting reference <Generic Hoist Trip Setting Increase SC> approved | 17-Jan-25 A | 17-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1630 | HNB Enhanced Defuelling Safety Cases |  | 2025-01-17 | All supporting references completed | 17-Jan-25 A | 17-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1670 | HNB Enhanced Defuelling Safety Cases | 2025-04-11 | 2025-04-11 | Post Job Debrief | 17-Jan-25 A | 17-Jan-25 A | 1 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1740 | HNB Enhanced Defuelling Safety Cases |  | 2025-04-10 | Station Approval Obtained and CAT 2 Safety Case Complete *(KDM)* <Generic Hoist Trip Setting Increase EC375945> | 17-Jan-25 A | 17-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D1900 | HNB Enhanced Defuelling Safety Cases |  | 2025-01-17 | All key supporting technical references complete - Generic Hoist Trip Setting Increase SC | 17-Jan-25 A | 17-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.3690 | HRA Enhanced Defueling Safety Case | 2025-01-17 | 2025-02-04 | Approve | 17-Jan-25 A | 2025-03-03 | 2 | 0 | 31 | 98% | 251 | In Progress
ER6701LT | W228 | W228.3690 | HYA Enhanced Defueling Safety Case | 2025-01-17 | 2025-02-04 | Approve | 17-Jan-25 A | 2025-03-03 | 2 | 0 | 31 | 100% | 251 | In Progress
W772LT | W772 | W772LT.A2640 | DNB Pull Harder Safety Case |  |  | <<NEW SCOPE PENDING CN3634><Load Path Assessment Appendix - Fixed DWTS> > - Prepare Draft Report | 17-Jan-25 A | 28-Feb-25 A | 21 | 0 | 30 | 100% |  | Completed
ER6698LT | W224 | W224.3920 | HRA Enhanced Defueling Safety Case | 2025-01-21 | 2025-02-05 | Issue RFS | 21-Jan-25 A | 05-Feb-25 A | 10 | 0 | 12 | 100% |  | Completed
ER6701LT | W228 | W228.3920 | HYA Enhanced Defueling Safety Case | 2025-01-21 | 2025-02-04 | Issue RFS | 21-Jan-25 A | 07-Feb-25 A | 10 | 0 | 13 | 100% |  | Completed
ER6698LT | W224 | W224.A1600 | HRA Enhanced Defueling Safety Case | 2025-01-21 | 2025-07-15 | Cost Summary - CFD & AMP2D | 21-Jan-25 A | 2025-07-15 | 122 | 93 | 122 | 0% | 158 | In Progress
ER6701LT | W228 | W228.A1600 | HYA Enhanced Defueling Safety Case | 2025-01-21 | 2025-07-15 | Cost Summary - CFD & AMP2D | 21-Jan-25 A | 2025-07-16 | 123 | 94 | 123 | 20.56% | 157 | In Progress
W232LT | W232 | W232.C3440 | DNB Enhanced Safety Cases |  |  | Decision Point Milestone - Hold Safety Case Decision Panel | 23-Jan-25 A | 23-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.C3580 | DNB Enhanced Safety Cases | 2025-03-31 | 2025-03-31 | <SCOPE CHANGE CN3472><FPU Uninspected Welds lifting integrity incl'g sub-veto faults> - Mid Job Brief | 23-Jan-25 A | 23-Jan-25 A | 1 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5400 | HRA Reactors Shutdown Essential Safety Cases |  | 2024-01-09 | ONR Agree/Acknowledge Safety Case EC 363682 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HRA) | 24-Jan-25 A | 24-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5410 | HRA Reactors Shutdown Essential Safety Cases |  | 2024-01-09 | ONR Agree/Acknowledge Safety Case EC 363682 <Reactor Shutdown Essential SC> (Cat 1 MS) (HRA) (FEEDS SUMMARY SCHEDULE) | 24-Jan-25 A | 24-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5400 | HYA Reactors Shutdown Essential Safety Cases |  | 2024-01-09 | ONR Agree/Acknowledge Safety Case EC 363676 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HYA) | 24-Jan-25 A | 24-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5410 | HYA Reactors Shutdown Essential Safety Cases |  | 2024-01-09 | ONR Agree/Acknowledge Safety Case EC 363676 <Reactor Shutdown Essential SC> (Cat 1 MS) (HYA) (FEEDS SUMMARY SCHEDULE) | 24-Jan-25 A | 24-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206250 | HYA Reactors Shutdown Essential Safety Cases |  | 2022-06-30 | >>>OUTGOING ENABLER (W104, HNB Security Plan) ONR Approved | 24-Jan-25 A | 24-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.1030 | HYA Fuel Handling Essential Safety Case |  | 2024-02-05 | >>>OUTGOING ENABLER (W283, HYA Security Plan, W206) HYA Fuel Handling Essential Safety Case ONR Approved | 24-Jan-25 A | 24-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.1330 | HRA Reactors Shutdown Essential Safety Cases |  |  | >>>INCOMING ENABLER (W222) HRA Fuel Handling Essential Safety Case ONR Approved | 24-Jan-25 A | 24-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.1340 | HRA Reactors Shutdown Essential Safety Cases |  |  | >>>MIRROR of INCOMING ENABLER(W222) HRA Fuel Handling Essential Safety Case ONR Approved | 24-Jan-25 A | 24-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.13125 | HYA Reactors Shutdown Essential Safety Cases |  | 2022-08-17 | >>>INCOMING ENABLER (W226) HYA Fuel Handling Essential Safety Case ONR Approved | 24-Jan-25 A | 24-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.13135 | HYA Reactors Shutdown Essential Safety Cases |  | 2022-08-17 | >>>MIRROR of INCOMING ENABLER (W226) HYA Fuel Handling Essential Safety Case ONR Approved | 24-Jan-25 A | 24-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.13145 | HYA Reactors Shutdown Essential Safety Cases |  | 2024-01-09 | >>>INTERFACE MILESTONE (W226) HYA Fuel Handling Essential Safety Case ONR Approved | 24-Jan-25 A | 24-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A1150 | DNB Pull Harder Safety Case | 2025-04-08 | 2025-04-09 | Produce verification plan | 24-Jan-25 A | 31-Jan-25 A | 2 | 0 | 6 | 100% |  | Completed
ER6378LT | W222 | W222.A13370 | HRA Fuel Handling Essential Safety Case |  | 2024-02-05 | Cat 1 Safety Case Complete (ONR LI Issued) HRA Defuelling Fuel Handling Essential Safety Case | 24-Jan-25 A | 24-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A17480 | HRA Fuel Handling Essential Safety Case |  | 2024-02-05 | ONR Agree/Acknowledge SC ECs(HRA-363840) HRA Defuelling Fuel Handling Essential SC (Cat 1 KDM) (FEEDS SUMMARY SCHEDULE) | 24-Jan-25 A | 24-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A17480 | HYA Fuel Handling Essential Safety Case |  | 2024-02-05 | ONR Agree/Acknowledge SC ECs(HYA-363839) HYA Defuelling Fuel Handling Essential SC (Cat 1 KDM) (FEEDS SUMMARY SCHEDULE) | 24-Jan-25 A | 24-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A13370 | HYA Fuel Handling Essential Safety Case |  | 2024-02-05 | Cat 1 Safety Case Complete (ONR LI Issued) HYA Defuelling Fuel Handling Essential Safety Case | 24-Jan-25 A | 24-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.1030 | HRA Fuel Handling Essential Safety Case |  | 2024-02-05 | >>>OUTGOING ENABLER (HRA Security Plan (W155), W202) - HRA Fuel Handling Essential Safety Case ONR Approved | 24-Jan-25 A | 24-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.1180 | HRA Fuel Handling Essential Safety Case | 2024-02-06 | 2024-05-29 | Safety Case Development Costs - Safety Case Closeout & Gate D Prep ##Cost Summary## | 24-Jan-25 A | 2025-03-31 | 55 | 21 | 46 | 50% | 0 | In Progress
ER6378LT | W222 | W222.1170 | HRA Fuel Handling Essential Safety Case | 2024-02-06 | 2024-05-29 | Project Management Costs - Safety Case Closeout & Gate D Prep ##Cost Summary## | 24-Jan-25 A | 2025-03-31 | 55 | 21 | 46 | 50% | 0 | In Progress
ER6650LT | W226 | W226.1170 | HYA Fuel Handling Essential Safety Case | 2024-02-06 | 2024-05-29 | Project Management Costs - Safety Case Closeout & Gate D Prep ##Cost Summary## | 24-Jan-25 A | 2025-03-31 | 55 | 21 | 46 | 50% | 0 | In Progress
ER6650LT | W226 | W226.1180 | HYA Fuel Handling Essential Safety Case | 2024-02-06 | 2024-05-29 | Safety Case Development Costs - Safety Case Closeout & Gate D Prep ##Cost Summary## | 24-Jan-25 A | 2025-03-31 | 55 | 21 | 46 | 50% | 0 | In Progress
ER6371LT | W202 | W202.1350 | HRA Reactors Shutdown Essential Safety Cases |  | 2024-01-09 | >>>INTERFACE MILESTONE (W222) HRA Fuel Handling Essential Safety Case ONR Approved | 24-Jan-25 A | 24-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5530 | HRA Reactors Shutdown Essential Safety Cases | 2024-01-10 | 2024-01-23 | Station Approval Period | 27-Jan-25 A | 27-Jan-25 A | 10 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C1690 | DNB Enhanced Safety Cases | 2025-01-13 | 2025-05-19 | <SCOPE CHANGE CN3472><FPU Sub-veto fault frequency> - Summary | 27-Jan-25 A | 2025-06-03 | 98 | 63 | 88 | 0% | 72 | In Progress
W232LT | W232 | W232.C1700 | DNB Enhanced Safety Cases | 2025-01-13 | 2025-02-07 | <SCOPE CHANGE CN3472><FPU Sub-veto fault frequency> - Prepare Draft EAN Part 1 | 27-Jan-25 A | 21-Feb-25 A | 20 | 0 | 20 | 100% |  | Completed
ER6701LT | W228 | W228. A1591 | HYA Enhanced Defueling Safety Case |  | 2025-01-27 | Gate B PRC Paper Approval | 27-Jan-25 A | 27-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2420 | DNB Pull Harder Safety Case |  |  | <Load Path Assessment> - R6 Monte Carlo Assessment | 27-Jan-25 A | 28-Feb-25 A | 10 | 0 | 24 | 100% |  | Completed
ER6378LT | W222 | W222.A18960 | HRA Fuel Handling Essential Safety Case | 2024-01-23 | 2024-02-05 | Prepare PRC Paper & Gate Package for Gate D | 27-Jan-25 A | 2025-03-05 | 10 | 3 | 28 | 10% | 0 | In Progress
ER6650LT | W226 | W226.A18960 | HYA Fuel Handling Essential Safety Case | 2024-01-23 | 2024-02-05 | Prepare PRC Paper & Gate Package for Gate D | 27-Jan-25 A | 2025-03-05 | 10 | 3 | 28 | 0% | 0 | In Progress
W232LT | W232 | W232.A5480 | DNB Enhanced Safety Cases |  |  | Review task sheet | 27-Jan-25 A | 31-Jan-25 A | 5 | 0 | 5 | 100% |  | Completed
ER6371LT | W202 | W202.A5420 | HRA Reactors Shutdown Essential Safety Cases |  | 2024-01-23 | Station Approve EC 363682 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HRA) (FEEDS TO SUMMARY SCHEDULE) | 27-Jan-25 A | 27-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A18480 | HRA Fuel Handling Essential Safety Case |  | 2024-02-19 | Station Approve ECs (HRA-363840) HRA Defuelling Fuel Handling Essential Safety Case (Cat 1 KDM) Delivered (FEEDS TO SUMM | 27-Jan-25 A | 27-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A2206200 | HRA Reactors Shutdown Essential Safety Cases |  |  | >>>OUTGOING ENABLER (W104 HPB Security Plan)(W285)(W148) CAT 1 Reactors Shutdown SC Station Approved | 27-Jan-25 A | 27-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.A27270 | HRA Fuel Handling Essential Safety Case |  | 2024-02-19 | >>>OUTGOING ENABLER (W285)(W148) CAT 1 Fuel Handling SC Station Approved | 27-Jan-25 A | 27-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772.A1140 | DNB Pull Harder Safety Case |  |  | <New SCOPE PENDING CN3634> - <Cavendish PWTS Report> - EDF TR Round 2 | 28-Jan-25 A | 31-Jan-25 A | 1 | 0 | 4 | 100% |  | Completed
ER6371LT | W202 | W202.A5430 | HRA Reactors Shutdown Essential Safety Cases | 2024-01-24 | 2024-02-06 | Revise all Affected Drawings and Documents for EC Approval (HRA) | 28-Jan-25 A | 14-Feb-25 A | 10 | 0 | 13 | 100% |  | Completed
ER6378LT | W222 | W222.A17470 | HRA Fuel Handling Essential Safety Case | 2024-02-20 | 2024-03-04 | Revise all Affected Drawings and Documents Following EC Approval | 28-Jan-25 A | 10-Feb-25 A | 10 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | W226.A17470 | HYA Fuel Handling Essential Safety Case | 2024-02-20 | 2024-03-04 | Revise all Affected Drawings and Documents following EC Approval | 28-Jan-25 A | 10-Feb-25 A | 10 | 0 | 10 | 100% |  | Completed
ER6650LT | W226 | W226.A18480 | HYA Fuel Handling Essential Safety Case |  | 2024-02-19 | Station Approve ECs (HYA-363839) HYA Defuelling Fuel Handling Essential Safety Case (Cat 1 KDM) Delivered (FEEDS TO SUMM | 29-Jan-25 A | 29-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2150 | DNB Pull Harder Safety Case | 2024-12-10 | 2024-12-10 | <Human Factors> - Review and Finalise HF Template | 29-Jan-25 A | 29-Jan-25 A | 5 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2180 | DNB Pull Harder Safety Case | 2024-12-10 | 2024-12-10 | <Human Factors> - HF Template Complete | 29-Jan-25 A | 29-Jan-25 A | 5 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5430 | HYA Reactors Shutdown Essential Safety Cases | 2024-01-24 | 2024-02-06 | Revise all Affected Drawings and Documents for EC Approval (HYA) | 31-Jan-25 A | 14-Feb-25 A | 10 | 0 | 10 | 100% |  | Completed
ER6661LT | W206 | W206.A5420 | HYA Reactors Shutdown Essential Safety Cases |  | 2024-01-23 | Station Approve EC 363676 <Reactor Shutdown Essential SC> (Cat 1 Milestone) (HYA) (FEEDS TO SUMMARY SCHEDULE) | 31-Jan-25 A | 31-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A2206220 | HYA Reactors Shutdown Essential Safety Cases |  | 2022-07-07 | >>>OUTGOING ENABLER (W286)(W149) CAT 1 Reactors Shutdown SC Station Approved | 31-Jan-25 A | 31-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.A27310 | HYA Fuel Handling Essential Safety Case |  | 2024-02-19 | >>>OUTGOING ENABLER (W286)(W149) CAT 1 Fuel Handling SC Station Approved | 31-Jan-25 A | 31-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5530 | HYA Reactors Shutdown Essential Safety Cases | 2024-01-10 | 2024-01-23 | Station Approval Period | 31-Jan-25 A | 31-Jan-25 A | 10 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | 2295 | HYA Fuel Handling Essential Safety Case |  |  | Station Approval of Safety Case | 31-Jan-25 A | 31-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224. A1591 | HRA Enhanced Defueling Safety Case |  | 2025-01-31 | Gate B PRC Paper Approval | 31-Jan-25 A | 31-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6701LT | W228 | W228. A1570 | HYA Enhanced Defueling Safety Case |  | 2025-01-31 | Gate B-D PRC Paper Submission | 31-Jan-25 A | 31-Jan-25 A | 0 | 0 | 0 | 100% |  | Completed
W730LT_UN | W730 | W730.1270 | HYB Enhanced Defueling Safety Cases | 2025-02-03 | 2028-03-27 | Summary for HYB Fuel Handling Enhanced Safety Cases W230 | 03-Feb-25 A | 2028-03-27 | 801 | 781 | 801 | 0% | 0 | In Progress
W730LT_UN | W730 | W730.1010 | HYB Enhanced Defueling Safety Cases | 2025-02-03 |  | Project Start | 03-Feb-25 A | 03-Feb-25 A | 0 | 0 | 0 | 100% |  | Completed
W730LT_UN | W730 | W730.1410 | HYB Enhanced Defueling Safety Cases | 2025-02-03 | 2025-02-13 | Confirm Objectives to be Delivered at Gate B | 03-Feb-25 A | 13-Feb-25 A | 9 | 0 | 9 | 100% |  | Completed
ER6698LT | W224 | W224. A1600 | HRA Enhanced Defueling Safety Case | 2025-02-03 | 2025-02-12 | Funds Released | 03-Feb-25 A | 12-Feb-25 A | 8 | 0 | 8 | 100% |  | Completed
ER6701LT | W228 | W228. A1600 | HYA Enhanced Defueling Safety Case | 2025-02-03 | 2025-02-12 | Funds Released | 03-Feb-25 A | 12-Feb-25 A | 8 | 0 | 8 | 100% |  | Completed
W230LT | W230 | W230.2050 | HYB Enhanced Defueling Safety Case Strategy | 2024-08-13 | 2025-01-16 | ## HYB Enhanced Defueling Rate: A - D Phase Funding - (Cost Summary) ## | 03-Feb-25 A | 2025-06-20 | 96 | 76 | 96 | 0% | 230 | In Progress
W230LT | W230 | W230.2060 | HYB Enhanced Defueling Safety Case Strategy | 2024-08-13 | 2024-08-29 | HYB Enhanced Defueling Rate: Strategy Development & Produce MF EC NNNNN & Obtain Approval | 03-Feb-25 A | 10-Feb-25 A | 6 | 0 | 6 | 100% |  | Completed
ER6698LT | W224 | W224.A1590 | HRA Enhanced Defueling Safety Case |  | 2025-02-03 | Gate B for Defuelling Programme Enhancement ECs (HH1) | 03-Feb-25 A | 03-Feb-25 A | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2105 | DNB Pull Harder Safety Case | 2024-09-16 | 2024-10-25 | EC Appendix 4 - Test Schedule - Preliminary Work & Authour - EDF | 03-Feb-25 A | 14-Feb-25 A | 10 | 0 | 10 | 100% |  | Completed
ER6701LT | W228 | W228.A1590 | HYA Enhanced Defueling Safety Case |  | 2025-02-03 | Gate B for Defuelling Programme Enhancement ECs (HH1) | 03-Feb-25 A | 03-Feb-25 A | 0 | 0 | 0 | 100% |  | Completed
W232LT | W232 | W232.A5490 | DNB Enhanced Safety Cases |  |  | Approve task sheet | 03-Feb-25 A | 2025-03-21 | 5 | 15 | 35 | 50% | 6 | In Progress
W772LT | W772 | W772.A1150 | DNB Pull Harder Safety Case |  |  | <New SCOPE PENDING CN3634> - <Cavendish PWTS Report> - Complete ( Incorporated into Appendix 1 ) | 03-Feb-25 A | 21-Feb-25 A | 5 | 0 | 14 | 100% |  | Completed
W234LT | W234 | W234.2050 | TOR Enhanced Defueling Safety Case Strategy | 2024-08-13 | 2025-01-16 | ## TOR Enhanced Defueling Rate: A - D Phase Funding - (Cost Summary) ## | 03-Feb-25 A | 2025-06-20 | 96 | 76 | 96 | 0% | 230 | In Progress
W234LT | W234 | W234.2130 | TOR Enhanced Defueling Safety Case Strategy | 2024-09-17 | 2024-09-30 | TOR Enhanced Defueling Rate: Produce draft NSRS (using BARRIER MODEL) | 03-Feb-25 A | 28-Feb-25 A | 20 | 0 | 20 | 100% |  | Completed
W234LT | W234 | W234.2060 | TOR Enhanced Defueling Safety Case Strategy | 2024-08-13 | 2024-08-29 | TOR Enhanced Defueling Rate: Strategy Development & Produce MF EC NNNNN & Obtain Approval | 03-Feb-25 A | 10-Feb-25 A | 6 | 0 | 6 | 100% |  | Completed
W772LT | W772 | W772LT.A2460 | DNB Pull Harder Safety Case |  |  | <Load Path Assessment> - Analysis of Fault Case 18cs of Pull Harder Loads | 03-Feb-25 A | 2025-03-07 | 10 | 5 | 25 | 90% | 8 | In Progress
W772LT | W772 | W772LT.A2720 | DNB Pull Harder Safety Case |  |  | <Load Path Assessment> -Cyclic Loading of Seized OEM NSP Welds Assessment | 03-Feb-25 A | 28-Feb-25 A | 10 | 0 | 19 | 100% |  | Completed
W731LT_UN | W731 | W731.1020 | TOR Enhanced Defueling Safety Cases | 2025-02-03 | 2025-02-13 | Confirm Objectives to be Delivered at Gate B | 03-Feb-25 A | 13-Feb-25 A | 9 | 0 | 9 | 100% |  | Completed
W731LT_UN | W731 | W731.1030 | TOR Enhanced Defueling Safety Cases | 2025-02-03 |  | Project Start | 03-Feb-25 A | 03-Feb-25 A | 0 | 0 | 0 | 100% |  | Completed
W731LT_UN | W731 | W731.1040 | TOR Enhanced Defueling Safety Cases | 2025-02-03 | 2028-03-27 | Summary for TOR Fuel Handling Enhanced Safety Cases W230 | 03-Feb-25 A | 2028-03-27 | 801 | 781 | 801 | 0% | 0 | In Progress
ER6372LT | W203 | W203.C1510 | HNB Enhanced Defuelling Safety Cases | 2024-06-18 | 2024-06-24 | Station Approval for mod implementation (including station review meeting) | 04-Feb-25 A | 04-Feb-25 A | 5 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1490 | HNB Enhanced Defuelling Safety Cases | 2024-06-04 | 2024-06-10 | Incorporate INSA comments | 04-Feb-25 A | 04-Feb-25 A | 5 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1500 | HNB Enhanced Defuelling Safety Cases | 2024-06-11 | 2024-06-17 | INSA Final Approval *(EC375412)* | 04-Feb-25 A | 04-Feb-25 A | 5 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1530 | HNB Enhanced Defuelling Safety Cases | 2024-06-25 | 2024-06-25 | Post Job Debrief | 04-Feb-25 A | 04-Feb-25 A | 1 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.C1520 | HNB Enhanced Defuelling Safety Cases |  | 2024-06-24 | Station Approval Obtained and CAT 2 Safety Case Complete *(EC375412)* | 04-Feb-25 A | 04-Feb-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6372LT | W203 | W203.D4230 | HNB Enhanced Defuelling Safety Cases |  |  | EC Station Approved - EC375412 | 04-Feb-25 A | 04-Feb-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6701LT | W228 | W228.3930 | HYA Enhanced Defueling Safety Case | 2025-02-05 | 2025-03-04 | Supplier Return RFS | 06-Feb-25 A | 2025-03-05 | 20 | 3 | 20 | 80% | 36 | In Progress
ER6698LT | W224 | W224.3930 | HRA Enhanced Defueling Safety Case | 2025-02-06 | 2025-03-05 | Supplier Return RFS | 06-Feb-25 A | 2025-03-05 | 20 | 3 | 20 | 85% | 36 | In Progress
ER6378LT | W222 | W222.A17460 | HRA Fuel Handling Essential Safety Case | 2024-03-05 | 2024-03-18 | Develop Implementation & closeout Plan | 11-Feb-25 A | 2025-03-10 | 10 | 6 | 20 | 10% | 14 | In Progress
ER6650LT | W226 | W226.A17460 | HYA Fuel Handling Essential Safety Case | 2024-03-05 | 2024-03-18 | Develop Implementation & closeout Plan | 11-Feb-25 A | 2025-03-10 | 10 | 6 | 20 | 10% | 14 | In Progress
W230LT | W230 | W230.2130 | HYB Enhanced Defueling Safety Case Strategy | 2024-09-17 | 2024-09-30 | HYB Enhanced Defueling Rate: Produce draft NSRS (using BARRIER MODEL) | 11-Feb-25 A | 28-Feb-25 A | 14 | 0 | 14 | 100% |  | Completed
W232LT | W232 | W232.C3590 | DNB Enhanced Safety Cases | 2025-04-01 | 2025-05-30 | <SCOPE CHANGE CN3472><FPU Uninspected Welds lifting integrity incl'g sub-veto faults> - Prepare Draft EAN Part 2 | 13-Feb-25 A | 2025-05-19 | 40 | 28 | 65 | 0% | 5 | In Progress
ER6698LT | W224 | W224.1580 | HRA Enhanced Defueling Safety Case | 2025-02-13 | 2025-02-21 | PJB | 13-Feb-25 A | 21-Feb-25 A | 7 | 0 | 7 | 100% |  | Completed
ER6698LT | W224 | W224.1680 | HRA Enhanced Defueling Safety Case | 2025-02-13 | 2025-03-05 | Design Activities – Bob Weight & Gripping Sleeve | 13-Feb-25 A | 2025-03-05 | 15 | 3 | 15 | 80% | 37 | In Progress
ER6698LT | W224 | W224.1690 | HRA Enhanced Defueling Safety Case | 2025-02-13 | 2025-02-26 | Draft Drawings - Bob Weight & Gripping Sleeve | 13-Feb-25 A | 2025-03-03 | 10 | 1 | 13 | 80% | 29 | In Progress
ER6698LT | W224 | W224.3200 | HRA Enhanced Defueling Safety Case | 2025-02-13 |  | Start Gate B Activities | 13-Feb-25 A | 13-Feb-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6698LT | W224 | W224.3300 | HRA Enhanced Defueling Safety Case | 2025-02-13 | 2026-01-19 | Gate B-D Programme Management External - Cost Summary | 13-Feb-25 A | 2026-01-19 | 235 | 223 | 235 | 5% | 26 | In Progress
ER6698LT | W224 | W224.3400 | HRA Enhanced Defueling Safety Case | 2025-02-13 | 2026-01-19 | Gate B-D Programme Management Internal - Cost Summary | 13-Feb-25 A | 2026-01-19 | 235 | 223 | 235 | 5% | 26 | In Progress
ER6701LT | W228 | W228.3400 | HYA Enhanced Defueling Safety Case | 2025-02-13 | 2026-01-19 | Gate B-D Programme Management Internal - Cost Summary | 13-Feb-25 A | 2026-01-19 | 235 | 223 | 235 | 5% | 26 | In Progress
ER6701LT | W228 | W228.3300 | HYA Enhanced Defueling Safety Case | 2025-02-13 | 2026-01-19 | Gate B-D Programme Management External - Cost Summary | 13-Feb-25 A | 2026-01-19 | 235 | 223 | 235 | 5% | 26 | In Progress
ER6701LT | W228 | W228.3200 | HYA Enhanced Defueling Safety Case | 2025-02-13 |  | Start Gate B Activities | 13-Feb-25 A | 13-Feb-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6701LT | W228 | W228.1690 | HYA Enhanced Defueling Safety Case | 2025-02-13 | 2025-02-26 | Draft Drawings – Bob Weight & Gripping Sleeve | 13-Feb-25 A | 2025-03-03 | 10 | 1 | 13 | 80% | 30 | In Progress
ER6701LT | W228 | W228.1680 | HYA Enhanced Defueling Safety Case | 2025-02-13 | 2025-03-05 | Design Activities – Bob Weight & Gripping Sleeve | 13-Feb-25 A | 2025-03-05 | 15 | 3 | 15 | 80% | 37 | In Progress
ER6701LT | W228 | W228.1580 | HYA Enhanced Defueling Safety Case | 2025-02-13 | 2025-02-21 | PJB | 13-Feb-25 A | 21-Feb-25 A | 7 | 0 | 7 | 100% |  | Completed
ER6371LT | W202 | W202.A5440 | HRA Reactors Shutdown Essential Safety Cases | 2024-02-07 | 2024-02-20 | Develop Implementation & closeout Plan (HRA) | 14-Feb-25 A | 21-Feb-25 A | 10 | 0 | 6 | 100% |  | Completed
ER6371LT | W202 | W202.A5500 | HRA Reactors Shutdown Essential Safety Cases | 2024-03-25 | 2024-04-03 | Prepare Gate D PRC Paper | 14-Feb-25 A | 2025-03-11 | 6 | 3 | 18 | 25% | 0 | In Progress
ER6661LT | W206 | W206.A5500 | HYA Reactors Shutdown Essential Safety Cases | 2024-03-25 | 2024-04-03 | Prepare Gate D PRC Paper | 14-Feb-25 A | 2025-03-11 | 6 | 3 | 18 | 25% | 0 | In Progress
ER6371LT | W202 | W202.A2206520 | HRA Reactors Shutdown Essential Safety Cases | 2024-03-19 | 2024-04-23 | Phase 2 Project Management - Gate D - E | 14-Feb-25 A | 2025-03-31 | 37 | 21 | 32 | 43% | 0 | In Progress
ER6661LT | W206 | W206.A2206320 | HYA Reactors Shutdown Essential Safety Cases | 2024-03-19 | 2024-04-23 | Phase 2 Project Management - Gate D - E | 14-Feb-25 A | 2025-03-31 | 33 | 21 | 32 | 43% | 0 | In Progress
W730LT_UN | W730 | W730.1400 | HYB Enhanced Defueling Safety Cases | 2025-02-14 | 2025-02-20 | Initial high level scope of programme | 14-Feb-25 A | 20-Feb-25 A | 5 | 0 | 5 | 100% |  | Completed
W772LT | W772 | W772.A1100 | DNB Pull Harder Safety Case |  |  | Annual Leave - James Derbyshire | 14-Feb-25 A | 2025-03-14 | 21 | 10 | 21 | 50% | 152 | In Progress
W232LT | W232 | W232.A5810 | DNB Enhanced Safety Cases |  |  | Annual Leave - James Derbyshire | 14-Feb-25 A | 2025-03-14 | 21 | 10 | 21 | 50% | 259 | In Progress
W731LT_UN | W731 | W731.1070 | TOR Enhanced Defueling Safety Cases | 2025-02-14 | 2025-02-20 | Initial high level scope of programme | 14-Feb-25 A | 20-Feb-25 A | 5 | 0 | 5 | 100% |  | Completed
W772LT | W772 | W772.A1020 | DNB Pull Harder Safety Case |  | 2024-11-01 | <S'standt'n of Funct'l Cap of PWTS & DWTS at the Enh'ed O'load Trip Sett's> - Issue Draft EAN / Report for Tech Review. | 14-Feb-25 A | 14-Feb-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5440 | HYA Reactors Shutdown Essential Safety Cases | 2024-02-07 | 2024-02-20 | Develop Implementation & closeout Plan (HYA) | 17-Feb-25 A | 21-Feb-25 A | 10 | 0 | 5 | 100% |  | Completed
ER6701LT | W228 | W228.2690 | HYA Enhanced Defueling Safety Case | 2025-02-17 | 2025-03-28 | Preliminary Design (including drawings and relevant analysis) | 17-Feb-25 A | 2025-03-28 | 30 | 20 | 30 | 33% | 20 | In Progress
W232LT | W232 | W232.A5820 | DNB Enhanced Safety Cases |  |  | <NEW SCOPE PENDING CN3754> - Review of OEMNSP growth values load Trace OpEX (To confirm growth values unchanged) | 17-Feb-25 A | 2025-04-17 | 34 | 34 | 44 | 30% | 101 | In Progress
ER6698LT | W224 | W224.2690 | HRA Enhanced Defueling Safety Case | 2025-02-17 | 2025-03-28 | Preliminary Design (including drawings and relevant analysis) | 17-Feb-25 A | 2025-03-28 | 30 | 20 | 30 | 33% | 20 | In Progress
W772LT | W772 | W772LT.A2160 | DNB Pull Harder Safety Case | 2024-11-25 | 2024-12-06 | <Test Schedulet> - Prepare Draft Report | 17-Feb-25 A | 21-Feb-25 A | 10 | 0 | 4 | 100% |  | Completed
W772LT | W772 | W772LT.A2340 | DNB Pull Harder Safety Case | 2025-02-04 | 2025-03-03 | <Load Path Assessment> - TSA Review/Verify Draft EAN | 17-Feb-25 A | 2025-03-10 | 16 | 1 | 16 | 50% | 8 | In Progress
ER6371LT | W202 | W202.1390 | HRA Reactors Shutdown Essential Safety Cases |  |  | Review of Reactor Ess Safety Case 2 - (ONR & Station Approved) Lessons Learnt Review Complete | 18-Feb-25 A | 18-Feb-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.1391 | HYA Reactors Shutdown Essential Safety Cases |  |  | Review of Reactor Ess Safety Case 2 - (ONR & Station Approved) Lessons Learnt Review Complete | 18-Feb-25 A | 18-Feb-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.1390 | HYA Fuel Handling Essential Safety Case |  | 2024-02-19 | Review of Reactor Ess Safety Case 2 - Lessons Learnt Review Complete | 18-Feb-25 A | 18-Feb-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6378LT | W222 | W222.1395 | HRA Fuel Handling Essential Safety Case |  | 2025-02-14 | Station Approval of Safety Case - Lessons Learnt Review Complete | 18-Feb-25 A | 18-Feb-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6650LT | W226 | W226.1395 | HYA Fuel Handling Essential Safety Case |  | 2025-02-14 | Station Approval of Safety Case - Lessons Learnt Review Complete | 18-Feb-25 A | 18-Feb-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1555 | TOR Essential Defueling Safety Case | 2024-04-29 | 2024-05-03 | Prepare Station Director's Brief | 20-Feb-25 A | 20-Feb-25 A | 5 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.29590 | TOR Essential Defueling Safety Case | 2024-05-29 | 2024-07-23 | INSA Schedule Risk - (Risk Ref 28382) - Generic (Potential) | 20-Feb-25 A | 24-Feb-25 A | 0 | 0 | 2 | 100% |  | Completed
W772LT | W772 | W772LT.A1580 | DNB Pull Harder Safety Case | 2025-06-09 | 2025-07-04 | Specialist Assessments if Necessary (Expand as Required) | 20-Feb-25 A | 2025-05-29 | 20 | 20 | 67 | 0% | 8 | In Progress
W772LT | W772 | W772LT.A2470 | DNB Pull Harder Safety Case | 2025-06-09 | 2025-06-20 | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Nuclear Fuel Group - Review and Comment | 20-Feb-25 A | 20-Feb-25 A | 10 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2480 | DNB Pull Harder Safety Case | 2025-06-09 | 2025-06-20 | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Human Factors (Human Reliability Assessment) - Review and Comment | 20-Feb-25 A | 20-Feb-25 A | 10 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2490 | DNB Pull Harder Safety Case | 2025-06-09 | 2025-06-20 | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Human Factors - (Work Procedures) - Review and Comment | 20-Feb-25 A | 20-Feb-25 A | 10 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2500 | DNB Pull Harder Safety Case | 2025-06-09 | 2025-06-20 | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Engineering (Instrumentation & Control) - Review and Comment | 20-Feb-25 A | 20-Feb-25 A | 10 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2510 | DNB Pull Harder Safety Case | 2025-06-09 | 2025-06-20 | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Engineering (Mechanical Systems) - Review and Comment | 20-Feb-25 A | 20-Feb-25 A | 10 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2520 | DNB Pull Harder Safety Case | 2025-06-09 | 2025-06-20 | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Structural Integrity (Structural Analysis) - Review and Comment | 20-Feb-25 A | 20-Feb-25 A | 10 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2550 | DNB Pull Harder Safety Case | 2025-06-23 | 2025-07-04 | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Nuclear Fuel Group - Close Comments | 20-Feb-25 A | 20-Feb-25 A | 10 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2560 | DNB Pull Harder Safety Case | 2025-06-23 | 2025-07-04 | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Human Factors (Human Reliability Assessment) - Close Comments | 20-Feb-25 A | 20-Feb-25 A | 10 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2570 | DNB Pull Harder Safety Case | 2025-06-23 | 2025-07-04 | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Human Factors - (Work Procedures) - Close Comments | 20-Feb-25 A | 20-Feb-25 A | 10 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2580 | DNB Pull Harder Safety Case | 2025-06-23 | 2025-07-04 | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Engineering (Instrumentation & Control) - Close Comments | 20-Feb-25 A | 20-Feb-25 A | 10 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2590 | DNB Pull Harder Safety Case | 2025-06-23 | 2025-07-04 | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Engineering (Mechanical Systems) - Close Comments | 20-Feb-25 A | 20-Feb-25 A | 10 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2600 | DNB Pull Harder Safety Case | 2025-06-23 | 2025-07-04 | <SCOPE REMOVED PENDING CN3615> <Specialist Assessment> Structural Integrity (Structural Analysis) - Close Comments | 20-Feb-25 A | 20-Feb-25 A | 10 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.1555 | HYB Essential Defueling Safety Case | 2024-04-29 | 2024-05-03 | Prepare Station Director's Brief | 20-Feb-25 A | 20-Feb-25 A | 1 | 0 | 1 | 100% |  | Completed
ER6666LT | W209 | W209.29590 | HYB Essential Defueling Safety Case | 2024-05-29 | 2024-07-23 | INSA Schedule Risk - (Risk Ref 28382) - Generic (Unknown) | 20-Feb-25 A | 24-Feb-25 A | 3 | 0 | 3 | 100% |  | Completed
ER6698LT | W224 | W224.2230 | HRA Enhanced Defueling Safety Case | 2025-02-20 | 2025-02-25 | Contract Award | 20-Feb-25 A | 2025-03-04 | 4 | 2 | 9 | 70% | 240 | In Progress
ER6701LT | W228 | W228.2230 | HYA Enhanced Defueling Safety Case | 2025-02-20 | 2025-02-25 | Contract Award | 20-Feb-25 A | 2025-03-04 | 4 | 2 | 9 | 70% | 240 | In Progress
ER6371LT | W202 | W202.A5450 | HRA Reactors Shutdown Essential Safety Cases | 2024-03-18 | 2024-03-18 | Safety Case Post Job Debrief (HRA) | 21-Feb-25 A | 21-Feb-25 A | 1 | 0 | 0 | 100% |  | Completed
ER6661LT | W206 | W206.A5450 | HYA Reactors Shutdown Essential Safety Cases | 2024-03-18 | 2024-03-18 | Safety Case Post Job Debrief (HYA) | 21-Feb-25 A | 21-Feb-25 A | 1 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2350 | DNB Pull Harder Safety Case |  | 2024-12-06 | <Test Schedule> - Issue Draft EAN / Report for Tech Review. | 21-Feb-25 A | 21-Feb-25 A | 0 | 0 | 0 | 100% |  | Completed
W730LT_UN | W730 | W730.1420 | HYB Enhanced Defueling Safety Cases | 2025-02-21 | 2025-03-06 | Prepare Draft Project Definition Document (PDD) | 21-Feb-25 A | 2025-03-06 | 10 | 4 | 10 | 80% | 3 | In Progress
W730LT_UN | W730 | W730.1430 | HYB Enhanced Defueling Safety Cases | 2025-02-21 | 2025-03-06 | PCL Validate & Approve Baseline Package for PRC Submission | 21-Feb-25 A | 2025-03-06 | 10 | 4 | 10 | 80% | 3 | In Progress
W730LT_UN | W730 | W730.1440 | HYB Enhanced Defueling Safety Cases | 2025-02-21 | 2025-03-06 | Add Data to PRC / IMS2 Paper | 21-Feb-25 A | 2025-03-06 | 10 | 4 | 10 | 80% | 3 | In Progress
W730LT_UN | W730 | W730.1450 | HYB Enhanced Defueling Safety Cases | 2025-02-21 | 2025-03-06 | Update Schedule/Estimate from Risk Log & Add Provisions | 21-Feb-25 A | 2025-03-06 | 10 | 4 | 10 | 80% | 3 | In Progress
W730LT_UN | W730 | W730.1510 | HYB Enhanced Defueling Safety Cases | 2025-02-21 | 2025-03-06 | Define Project Control Structures (WBS/CBS/OBS/PBS) | 21-Feb-25 A | 2025-03-06 | 10 | 4 | 10 | 80% | 3 | In Progress
W731LT_UN | W731 | W731.1080 | TOR Enhanced Defueling Safety Cases | 2025-02-21 | 2025-03-06 | Define Project Control Structures (WBS/CBS/OBS/PBS) | 21-Feb-25 A | 2025-03-06 | 10 | 4 | 10 | 80% | 3 | In Progress
W731LT_UN | W731 | W731.1090 | TOR Enhanced Defueling Safety Cases | 2025-02-21 | 2025-03-06 | Update Schedule/Estimate from Risk Log & Add Provisions | 21-Feb-25 A | 2025-03-06 | 10 | 4 | 10 | 80% | 3 | In Progress
W731LT_UN | W731 | W731.1100 | TOR Enhanced Defueling Safety Cases | 2025-02-21 | 2025-03-06 | Add Data to PRC / IMS2 Paper | 21-Feb-25 A | 2025-03-06 | 10 | 4 | 10 | 80% | 3 | In Progress
W731LT_UN | W731 | W731.1110 | TOR Enhanced Defueling Safety Cases | 2025-02-21 | 2025-03-06 | PCL Validate & Approve Baseline Package for PRC Submission | 21-Feb-25 A | 2025-03-06 | 10 | 4 | 10 | 80% | 3 | In Progress
W731LT_UN | W731 | W731.1120 | TOR Enhanced Defueling Safety Cases | 2025-02-21 | 2025-03-06 | Prepare Draft Project Definition Document (PDD) | 21-Feb-25 A | 2025-03-06 | 10 | 4 | 10 | 80% | 3 | In Progress
ER6666LT | W209 | W209.29600 | HYB Essential Defueling Safety Case |  | 2024-07-23 | Risk Milestone - INSA Schedule Risk - (Risk Ref 28382) - INSA Substantially Complete | 24-Feb-25 A | 24-Feb-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.29600 | TOR Essential Defueling Safety Case |  | 2024-07-23 | Risk Milestone - INSA Schedule Risk - (Risk Ref 28382) - INSA Substantially Complete | 24-Feb-25 A | 24-Feb-25 A | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.A2170 | DNB Pull Harder Safety Case | 2024-12-09 | 2024-12-13 | <Test Schedule> - Draft EAN / Report Tech Reviewed by EDF SQEP | 24-Feb-25 A | 28-Feb-25 A | 5 | 0 | 4 | 100% |  | Completed
W772LT | W772 | W772.A1030 | DNB Pull Harder Safety Case | 2024-11-04 | 2024-11-08 | <S'standt'n of Funct'l Cap of PWTS & DWTS at the Enh'ed O'load Trip Sett's> - Draft EAN / Report TR by EDF SQEP | 24-Feb-25 A | 28-Feb-25 A | 5 | 0 | 4 | 100% |  | Completed
W232LT | W232 | W232.C3560 | DNB Enhanced Safety Cases | 2025-02-10 | 2025-02-10 | <SCOPE CHANGE CN3472><FPU Sub-veto fault frequency> - Mid Job Brief | 24-Feb-25 A | 24-Feb-25 A | 1 | 0 | 1 | 100% |  | Completed
W232LT | W232 | W232.C3570 | DNB Enhanced Safety Cases | 2025-02-11 | 2025-03-17 | <SCOPE CHANGE CN3472><FPU Sub-veto fault frequency> - Prepare Draft EAN Part 2 | 25-Feb-25 A | 2025-03-31 | 25 | 21 | 25 | 10% | 56 | In Progress
ER6666LT | W209 | W209.1042 | HYB Essential Defueling Safety Case |  | 2024-08-06 | INSA Assessment Substantially Comp (T-3) weeks before NSC date)) | 26-Feb-25 A | 26-Feb-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6666LT | W209 | W209.4970 | HYB Essential Defueling Safety Case |  | 2024-08-06 | >>>OUTGOING ENABLER (W273) INSA Approved | 26-Feb-25 A | 26-Feb-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.4970 | TOR Essential Defueling Safety Case |  | 2024-08-06 | >>>OUTGOING ENABLER (W274) INSA Approved | 26-Feb-25 A | 26-Feb-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6668LT | W213 | W213.1042 | TOR Essential Defueling Safety Case |  | 2024-08-06 | INSA Assessment Substantially Comp (T-3) weeks before NSC date)) | 26-Feb-25 A | 26-Feb-25 A | 0 | 0 | 0 | 100% |  | Completed
W230LT | W230 | W230.3770 | HYB Enhanced Defueling Safety Case Strategy |  |  | HYB Enhanced Defueling Rate: Produce draft NSRS (using BARRIER MODEL) | 28-Feb-25 A | 28-Feb-25 A | 0 | 0 | 0 | 100% |  | Completed
W772LT | W772 | W772LT.T1290 | DNB Pull Harder Safety Case |  | 2024-10-25 | <Operating Strategy for Pull Harder Facility> - Issue Final EAN / Report | 28-Feb-25 A | 28-Feb-25 A | 0 | 0 | 0 | 100% |  | Completed
W234LT | W234 | W234.3770 | TOR Enhanced Defueling Safety Case Strategy |  |  | TOR Enhanced Defueling Rate: Produce draft NSRS (using BARRIER MODEL) | 28-Feb-25 A | 28-Feb-25 A | 0 | 0 | 0 | 100% |  | Completed
ER6371LT | W202 | W202.A5460 | HRA Reactors Shutdown Essential Safety Cases | 2024-03-19 | 2024-03-19 | Hold Project Closeout and Lessons Learned Meeting [FEEDS TO SUMMARY SCHEDULE] | 2025-03-03 | 2025-03-03 | 1 | 1 | 1 | 0% | 0 | Not Started
ER6371LT | W202 | W202.A1480 | HRA Reactors Shutdown Essential Safety Cases | 2020-03-02 | 2022-12-19 | ETC (DD-PF) | 2025-03-03 | 2025-03-28 | 20 | 20 | 20 | 0% | 1 | Not Started
ER6661LT | W206 | W206.A5460 | HYA Reactors Shutdown Essential Safety Cases | 2024-03-19 | 2024-03-19 | Hold Project Closeout and Lessons Learned Meeting [FEEDS TO SUMMARY SCHEDULE] | 2025-03-03 | 2025-03-03 | 1 | 1 | 1 | 0% | 0 | Not Started
ER6661LT | W206 | W206.A1480 | HYA Reactors Shutdown Essential Safety Cases | 2020-03-02 | 2021-01-28 | ETC (DD -PF) | 2025-03-03 | 2025-03-28 | 20 | 20 | 20 | 0% | 1 | Not Started
W232LT | W232 | W232.10001 | DNB Enhanced Safety Cases |  |  | ETC (DD-PF) | 2025-03-03 | 2026-03-23 | 268 | 268 | 268 | 0% | 1 | Not Started
W730LT_UN | W730 | W730.1150 | HYB Enhanced Defueling Safety Cases |  | 2025-03-03 | >>>OUTGOING ENABLER (HYB Security - Preparing for Defuelling) Review SPPI File Against Issued Essential Safety Cases | 2025-03-03 | 2025-03-03 | 0 | 0 | 0 | 0% | 781 | Not Started
W730LT_UN | W730 | W730.1000 | HYB Enhanced Defueling Safety Cases | 2025-03-03 | 2027-11-26 | ETC (DD-PF) | 2025-03-03 | 2027-11-26 | 695 | 695 | 695 | 0% | 86 | Not Started
ER6666LT | W209 | W209.1010 | HYB Essential Defueling Safety Case | 2022-06-01 | 2022-06-01 | ETC (DD-PF) | 2025-03-03 | 2025-09-22 | 141 | 141 | 141 | 0% | 1 | Not Started
ER6372LT | W203 | W203.A1000 | HNB Enhanced Defuelling Safety Cases |  |  | ETC (DD-PF) | 2025-03-03 | 2025-05-19 | 53 | 53 | 53 | 0% | 1 | Not Started
ER6666LT | W209 | W209.29320 | HYB Essential Defueling Safety Case | 2024-08-07 | 2024-08-20 | Lessons Learnt Activity - Following Completeion of INSA | 03-Mar-25* | 2025-03-14 | 10 | 10 | 10 | 0% | 113 | Not Started
W520LT | W520 | W520.A1270 | FLEETWIDE CTO Defueling Safety Case Delivery |  |  | 2025 Costs | 03-Mar-25* | 2025-12-31 | 211 | 211 | 211 | 0% | 251 | Not Started
W520LT | W520 | W520.A1300 | FLEETWIDE CTO Defueling Safety Case Delivery |  |  | ETC (DD-PF) 2025 | 03-Mar-25* | 2025-12-29 | 209 | 209 | 209 | 0% | 253 | Not Started
ER6668LT | W213 | W213.1010 | TOR Essential Defueling Safety Case | 2022-06-01 | 2022-06-01 | ETC (DD-PF) | 2025-03-03 | 2025-09-22 | 141 | 141 | 141 | 0% | 1 | Not Started
ER6668LT | W213 | W213.29320 | TOR Essential Defueling Safety Case | 2024-08-07 | 2024-08-20 | Lessons Learnt Activity - Following Completeion of INSA | 03-Mar-25* | 2025-03-14 | 10 | 10 | 10 | 0% | 113 | Not Started
ER6372LT | W203 | W203.1030 | HNB Enhanced Defuelling Safety Cases |  |  | Enhanced Defueling rate EC - Lessons Learnt Review Complete | 2025-03-03 | 2025-03-03 | 0 | 0 | 0 | 0% | 28 | Not Started
ER6698LT | W224 | W224.1600 | HRA Enhanced Defueling Safety Case | 2025-02-24 | 2025-04-04 | Design Software Change Lifecycle for PC1/PC2 Software | 2025-03-03 | 2025-04-11 | 30 | 30 | 30 | 0% | 0 | Not Started
ER6701LT | W228 | W228.3280 | HYA Enhanced Defueling Safety Case | 2025-02-13 | 2026-02-19 | Cost Summary - Overarching CAT 2 EC | 2025-03-03 | 2026-02-26 | 251 | 251 | 251 | 0% | 0 | Not Started
ER6701LT | W228 | W228.2850 | HYA Enhanced Defueling Safety Case |  | 2025-02-03 | KDM - Discovery Milestone – Trip Reliability | 2025-03-03 | 2025-03-03 | 0 | 0 | 0 | 0% | 50 | Not Started
ER6701LT | W228 | W228.1600 | HYA Enhanced Defueling Safety Case | 2025-02-24 | 2025-04-04 | Design Software Change Lifecycle for PC1/PC2 Software | 2025-03-03 | 2025-04-11 | 30 | 30 | 30 | 0% | 0 | Not Started
W230LT | W230 | W230.1000 | HYB Enhanced Defueling Safety Case Strategy | 2024-07-01 | 2025-08-18 | ETC (DD-PF) | 2025-03-03 | 2026-05-18 | 305 | 305 | 305 | 0% | 1 | Not Started
W230LT | W230 | W230.2070 | HYB Enhanced Defueling Safety Case Strategy | 2024-08-30 | 2024-09-16 | HYB Enhanced Defueling Rate: Mod Requested and EC Request Raised and Screened | 2025-03-03 | 2025-03-10 | 6 | 6 | 6 | 0% | 12 | Not Started
ER6698LT | W224 | W224.1000 | HRA Enhanced Defueling Safety Case | 2025-02-03 | 2026-02-12 | ETC (DD-PF) W224 | 2025-03-03 | 2026-02-12 | 241 | 241 | 241 | 0% | 10 | Not Started
W772LT | W772 | W772LT.T1300 | DNB Pull Harder Safety Case | 2024-10-28 | 2024-11-08 | <Operating Strategy for Pull Harder Facility> - EAN / Report Completed and Uploaded to CDMS | 2025-03-03 | 2025-03-07 | 5 | 5 | 5 | 0% | 19 | Not Started
W772LT | W772 | W772LT.A2360 | DNB Pull Harder Safety Case | 2024-12-16 | 2024-12-20 | <Test Schedule> - Address Comments from EDF Review on Draft EAN / Report | 2025-03-03 | 2025-03-07 | 5 | 5 | 5 | 0% | 29 | Not Started
ER6701LT | W228 | W228.1000 | HYA Enhanced Defueling Safety Case | 2025-02-03 | 2026-02-12 | ETC (DD-PF) W228 | 2025-03-03 | 2026-02-12 | 241 | 241 | 241 | 0% | 10 | Not Started
W772LT | W772 | W772.A1040 | DNB Pull Harder Safety Case | 2024-11-11 | 2024-11-15 | <S'standt'n of Funct'l Cap of PWTS & DWTS at the Enh'ed O'load Trip Sett's> - Address Comments from EDF TR on Draft EAN | 2025-03-03 | 2025-03-07 | 5 | 5 | 5 | 0% | 39 | Not Started
W232LT | W232 | W232.C3180 | DNB Enhanced Safety Cases | 2025-01-20 | 2025-01-31 | <NEW SCOPE CN3472> - R6 assessment | 03-Mar-25* | 2025-03-07 | 5 | 5 | 5 | 0% | 5 | Not Started
W232LT | W232 | W232.C3350 | DNB Enhanced Safety Cases | 2024-12-23 | 2025-01-15 | <NEW SCOPE CN3472> Review Technical note | 03-Mar-25* | 2025-03-21 | 15 | 15 | 15 | 0% | 5 | Not Started
W772LT | W772 | W772.A1090 | DNB Pull Harder Safety Case |  |  | ETC (DD-PF) | 2025-03-03 | 2025-10-20 | 161 | 161 | 161 | 0% | 1 | Not Started
W772LT | W772 | W772LT.A2660 | DNB Pull Harder Safety Case |  |  | <<NEW SCOPE PENDING CN3634><Load Path Assessment Appendix - Fixed DWTS> > - Verification Comments Received | 2025-03-03 | 2025-03-14 | 10 | 10 | 10 | 0% | 4 | Not Started
ER6701LT | W228 | W228.4450 | HYA Enhanced Defueling Safety Case | 2025-02-13 | 2025-02-18 | Produce MF (as required) | 2025-03-03 | 2025-03-06 | 4 | 4 | 4 | 0% | 84 | Not Started
W234LT | W234 | W234.1000 | TOR Enhanced Defueling Safety Case Strategy | 2024-07-01 | 2025-08-18 | ETC (DD-PF) | 2025-03-03 | 2026-05-18 | 305 | 305 | 305 | 0% | 1 | Not Started
W234LT | W234 | W234.2070 | TOR Enhanced Defueling Safety Case Strategy | 2024-08-30 | 2024-09-16 | TOR Enhanced Defueling Rate: Mod Requested and EC Request Raised and Screened | 2025-03-03 | 2025-03-10 | 6 | 6 | 6 | 0% | 12 | Not Started
W731LT_UN | W731 | W731.1050 | TOR Enhanced Defueling Safety Cases | 2025-03-03 | 2027-11-26 | ETC (DD-PF) | 2025-03-03 | 2027-11-26 | 695 | 695 | 695 | 0% | 86 | Not Started
W731LT_UN | W731 | W731.1060 | TOR Enhanced Defueling Safety Cases |  | 2025-03-03 | >>>OUTGOING ENABLER (TOR Security - Preparing for Defuelling) Review SPPI File Against Issued Essential Safety Cases | 2025-03-04 | 2025-03-03 | 0 | 0 | 0 | 0% | 781 | Not Started
ER6698LT | W224 | W224.3870 | HRA Enhanced Defueling Safety Case |  | 2025-02-14 | KDM Discovery Milestone - TR of Optioneering Complete | 2025-03-05 | 2025-03-03 | 0 | 0 | 0 | 0% | 250 | Not Started
ER6701LT | W228 | W228.3870 | HYA Enhanced Defueling Safety Case |  | 2025-02-14 | KDM Discovery Milestone - TR Optioneering Complete | 2025-03-06 | 2025-03-03 | 0 | 0 | 0 | 0% | 250 | Not Started
ER6371LT | W202 | W202.A5480 | HRA Reactors Shutdown Essential Safety Cases | 2024-03-20 | 2024-03-20 | Produce Lessons Learned Report | 2025-03-04 | 2025-03-04 | 1 | 1 | 1 | 0% | 0 | Not Started
ER6661LT | W206 | W206.A5480 | HYA Reactors Shutdown Essential Safety Cases | 2024-03-20 | 2024-03-20 | Produce Lessons Learned Report | 2025-03-04 | 2025-03-04 | 1 | 1 | 1 | 0% | 0 | Not Started
ER6698LT | W224 | W224.1700 | HRA Enhanced Defueling Safety Case | 2025-02-27 | 2025-03-12 | Finalise Design Drawings ( Supplier internal process ID A1430) | 2025-03-04 | 2025-03-17 | 10 | 10 | 10 | 0% | 29 | Not Started
ER6701LT | W228 | W228.1700 | HYA Enhanced Defueling Safety Case | 2025-02-27 | 2025-03-12 | Finalise Design Drawings ( Supplier internal process ID A1430) | 2025-03-04 | 2025-03-14 | 9 | 9 | 9 | 0% | 30 | Not Started
ER6371LT | W202 | W202.A5490 | HRA Reactors Shutdown Essential Safety Cases | 2024-03-21 | 2024-03-22 | Produce Project Closeout Report | 2025-03-05 | 2025-03-06 | 2 | 2 | 2 | 0% | 0 | Not Started
ER6661LT | W206 | W206.A5490 | HYA Reactors Shutdown Essential Safety Cases | 2024-03-21 | 2024-03-22 | Produce Project Closeout Report | 2025-03-05 | 2025-03-06 | 2 | 2 | 2 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.1460 | HYB Enhanced Defueling Safety Cases | 2025-03-05 | 2025-03-06 | Complete Risk Log with Estimates | 2025-03-05 | 2025-03-06 | 2 | 2 | 2 | 0% | 3 | Not Started
W730LT_UN | W730 | W730.1470 | HYB Enhanced Defueling Safety Cases | 2025-03-05 | 2025-03-06 | Hold Risk Workshop | 2025-03-05 | 2025-03-06 | 2 | 2 | 2 | 0% | 3 | Not Started
W730LT_UN | W730 | W730.1480 | HYB Enhanced Defueling Safety Cases | 2025-03-05 | 2025-03-06 | Ensure Alignment of Schedule & Estimate | 2025-03-05 | 2025-03-06 | 2 | 2 | 2 | 0% | 3 | Not Started
W730LT_UN | W730 | W730.1490 | HYB Enhanced Defueling Safety Cases | 2025-03-05 | 2025-03-06 | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 2025-03-05 | 2025-03-06 | 2 | 2 | 2 | 0% | 3 | Not Started
W730LT_UN | W730 | W730.1500 | HYB Enhanced Defueling Safety Cases | 2025-03-05 | 2025-03-06 | Plan Scope in Primavera (Level 2 B-B+ & Level 1 Lifecycle) | 2025-03-05 | 2025-03-06 | 2 | 2 | 2 | 0% | 3 | Not Started
W730LT_UN | W730 | W730.1530 | HYB Enhanced Defueling Safety Cases | 2025-03-05 | 2025-03-06 | Case Production Plan Peer Review & Update | 2025-03-05 | 2025-03-06 | 2 | 2 | 2 | 0% | 3 | Not Started
W731LT_UN | W731 | W731.1130 | TOR Enhanced Defueling Safety Cases | 2025-03-05 | 2025-03-06 | Case Production Plan Peer Review & Update | 2025-03-05 | 2025-03-06 | 2 | 2 | 2 | 0% | 3 | Not Started
W731LT_UN | W731 | W731.1140 | TOR Enhanced Defueling Safety Cases | 2025-03-05 | 2025-03-06 | Plan Scope in Primavera (Level 2 B-B+ & Level 1 Lifecycle) | 2025-03-05 | 2025-03-06 | 2 | 2 | 2 | 0% | 3 | Not Started
W731LT_UN | W731 | W731.1150 | TOR Enhanced Defueling Safety Cases | 2025-03-05 | 2025-03-06 | Estimate Scope +/- 10% B-C & +/- 30% Lifecycle | 2025-03-05 | 2025-03-06 | 2 | 2 | 2 | 0% | 3 | Not Started
W731LT_UN | W731 | W731.1160 | TOR Enhanced Defueling Safety Cases | 2025-03-05 | 2025-03-06 | Ensure Alignment of Schedule & Estimate | 2025-03-05 | 2025-03-06 | 2 | 2 | 2 | 0% | 3 | Not Started
W731LT_UN | W731 | W731.1170 | TOR Enhanced Defueling Safety Cases | 2025-03-05 | 2025-03-06 | Hold Risk Workshop | 2025-03-05 | 2025-03-06 | 2 | 2 | 2 | 0% | 3 | Not Started
W731LT_UN | W731 | W731.1180 | TOR Enhanced Defueling Safety Cases | 2025-03-05 | 2025-03-06 | Complete Risk Log with Estimates | 2025-03-05 | 2025-03-06 | 2 | 2 | 2 | 0% | 3 | Not Started
ER6378LT | W222 | W222.A18970 | HRA Fuel Handling Essential Safety Case | 2024-02-06 | 2024-04-12 | Conduct Gate Review (Stakeholders Sign On) | 2025-03-06 | 2025-03-12 | 5 | 5 | 5 | 0% | 0 | Not Started
ER6650LT | W226 | W226.A18970 | HYA Fuel Handling Essential Safety Case | 2024-02-06 | 2024-04-12 | Conduct Gate Review (Stakeholders Sign On) | 2025-03-06 | 2025-03-12 | 5 | 5 | 5 | 0% | 0 | Not Started
ER6698LT | W224 | W224.3940 | HRA Enhanced Defueling Safety Case | 2025-03-06 | 2025-03-19 | EDF Review & Contract Award | 2025-03-06 | 2025-03-19 | 10 | 10 | 10 | 0% | 36 | Not Started
ER6701LT | W228 | W228.3940 | HYA Enhanced Defueling Safety Case | 2025-03-05 | 2025-03-18 | EDF Review & Contract Award | 2025-03-06 | 2025-03-19 | 10 | 10 | 10 | 0% | 36 | Not Started
ER6701LT | W228 | W228.3950 | HYA Enhanced Defueling Safety Case | 2025-03-06 | 2025-04-03 | Design of Handling Equipment | 2025-03-06 | 2025-04-03 | 21 | 21 | 21 | 0% | 38 | Not Started
ER6698LT | W224 | W224.3950 | HRA Enhanced Defueling Safety Case | 2025-03-06 | 2025-04-03 | Design of Handling Equipment | 2025-03-06 | 2025-04-03 | 21 | 21 | 21 | 0% | 38 | Not Started
ER6701LT | W228 | W228.4460 | HYA Enhanced Defueling Safety Case |  | 2025-02-18 | Issue MF (as required) | 2025-03-07 | 2025-03-06 | 0 | 0 | 0 | 0% | 84 | Not Started
W730LT_UN | W730 | W730.1850 | HYB Enhanced Defueling Safety Cases | 2025-03-07 | 2025-04-03 | ## Technical Development / Project Management - Pre Gate B - (Cost Summary) ## | 2025-03-07 | 2025-04-03 | 20 | 20 | 20 | 0% | 11 | Not Started
W730LT_UN | W730 | W730.3700 | HYB Enhanced Defueling Safety Cases | 2025-03-07 | 2025-04-03 | Pre-Gate B - Delivery Strategy | 2025-03-07 | 2025-04-03 | 20 | 20 | 20 | 0% | 11 | Not Started
W772LT | W772 | W772.A1050 | DNB Pull Harder Safety Case | 2024-11-18 | 2024-11-18 | <S'standt'n of Funct'l Cap of PWTS & DWTS at the Enh'ed O'load Trip Sett's> - Issue Final EAN / Report to FMAPS | 2025-03-07 | 2025-03-07 | 1 | 1 | 1 | 0% | 39 | Not Started
ER6701LT | W228 | W228.4470 | HYA Enhanced Defueling Safety Case | 2025-02-19 | 2025-02-24 | Categorisation by RE / Station | 2025-03-07 | 2025-03-12 | 4 | 4 | 4 | 0% | 84 | Not Started
W731LT_UN | W731 | W731.1190 | TOR Enhanced Defueling Safety Cases | 2025-03-07 | 2025-04-03 | Pre-Gate B - Delivery Strategy | 2025-03-07 | 2025-04-03 | 20 | 20 | 20 | 0% | 11 | Not Started
W731LT_UN | W731 | W731.1200 | TOR Enhanced Defueling Safety Cases | 2025-03-07 | 2025-04-03 | ## Technical Development / Project Management - Pre Gate B - (Cost Summary) ## | 2025-03-07 | 2025-04-03 | 20 | 20 | 20 | 0% | 11 | Not Started
ER6698LT | W224 | W224.2500 | HRA Enhanced Defueling Safety Case |  | 2025-02-03 | KDM - CETS ISSUE Load Trace | 2025-03-07 | 2025-03-07 | 0 | 0 | 0 | 0% | 200 | Not Started
ER6698LT | W224 | W224.2630 | HRA Enhanced Defueling Safety Case |  | 2025-02-14 | KDM - CETS ISSUE Trip Function | 2025-03-07 | 2025-03-07 | 0 | 0 | 0 | 0% | 46 | Not Started
ER6701LT | W228 | W228.2630 | HYA Enhanced Defueling Safety Case |  | 2025-02-14 | KDM - CETS ISSUE Trip Function | 2025-03-07 | 2025-03-07 | 0 | 0 | 0 | 0% | 46 | Not Started
ER6701LT | W228 | W228.2500 | HYA Enhanced Defueling Safety Case |  | 2025-02-03 | KDM - CETS ISSUE Load Trace | 2025-03-07 | 2025-03-07 | 0 | 0 | 0 | 0% | 200 | Not Started
W772LT | W772 | W772LT.T1310 | DNB Pull Harder Safety Case |  | 2024-11-08 | <Operating Strategy for Pull Harder Facility> - EAN / Report Completed | 2025-03-07 | 2025-03-07 | 0 | 0 | 0 | 0% | 19 | Not Started
W772LT | W772 | W772LT.A2370 | DNB Pull Harder Safety Case |  | 2024-12-20 | <Test Schedule> - Issue Final EAN / Report | 2025-03-07 | 2025-03-07 | 0 | 0 | 0 | 0% | 29 | Not Started
W772LT | W772 | W772.A1060 | DNB Pull Harder Safety Case |  | 2024-11-18 | <S'standt'n of Funct'l Cap of PWTS & DWTS at the Enh'ed O'load Trip Sett's> - EAN / Report Completed | 2025-03-07 | 2025-03-07 | 0 | 0 | 0 | 0% | 39 | Not Started
ER6698LT | W224 | W224.2440 | HRA Enhanced Defueling Safety Case | 2025-02-03 | 2025-02-14 | Verify CETS Issue for Load Trace | 2025-03-10 | 2025-03-21 | 10 | 10 | 10 | 0% | 190 | Not Started
ER6698LT | W224 | W224.2590 | HRA Enhanced Defueling Safety Case | 2025-02-17 | 2025-03-14 | Verify CETS for Trip Functions | 2025-03-10 | 2025-04-04 | 20 | 20 | 20 | 0% | 26 | Not Started
ER6701LT | W228 | W228.2590 | HYA Enhanced Defueling Safety Case | 2025-02-17 | 2025-03-14 | Verify CETS for Trip Functions | 2025-03-10 | 2025-04-04 | 20 | 20 | 20 | 0% | 26 | Not Started
ER6701LT | W228 | W228.2440 | HYA Enhanced Defueling Safety Case | 2025-02-04 | 2025-02-17 | Verify Issue for Load Trace | 2025-03-10 | 2025-03-21 | 10 | 10 | 10 | 0% | 190 | Not Started
W772LT | W772 | W772LT.A1160 | DNB Pull Harder Safety Case | 2025-06-09 | 2025-06-20 | Verification of the case (using BARRIER MODEL) | 2025-03-10 | 2025-05-08 | 41 | 41 | 41 | 0% | 4 | Not Started
W772LT | W772 | W772LT.A2380 | DNB Pull Harder Safety Case | 2024-12-23 | 2025-01-08 | <Test Schedule> - EAN / Report Completed and Uploaded to CDMS | 2025-03-10 | 2025-03-21 | 10 | 10 | 10 | 0% | 29 | Not Started
W772LT | W772 | W772LT.A2400 | DNB Pull Harder Safety Case | 2024-11-11 | 2024-11-22 | <Admin Controls / Tech Spec> - Prepare Draft Report | 2025-03-10 | 2025-03-21 | 10 | 10 | 10 | 0% | 19 | Not Started
W232LT | W232 | W232.C3190 | DNB Enhanced Safety Cases | 2025-02-03 | 2025-02-14 | <NEW SCOPE CN3472> - Verification of R6 assessment and inclusion of FPU Sub-veto fault frequency report | 2025-03-10 | 2025-03-21 | 10 | 10 | 10 | 0% | 5 | Not Started
W232LT | W232 | W232.A5800 | DNB Enhanced Safety Cases |  |  | >>>MIRROR OF INCOMING ENABLER (W772) - Load Path Assessment | 2025-03-10 | 10-Mar-25* | 0 | 0 | 0 | 0% | 16 | Not Started
W232LT | W232 | W232.C2470 | DNB Enhanced Safety Cases |  | 2025-02-14 | >>>INTERFACE MILESTONE - (772) Load Path Assessment - Draft EAN Issued | 2025-03-10 | 2025-03-10 | 0 | 0 | 0 | 0% | 16 | Not Started
W772LT | W772 | W772LT.A2280 | DNB Pull Harder Safety Case |  | 2025-03-03 | <Load Path Assessment> - Issue Draft EAN to EDF for Tech Review. | 2025-03-10 | 2025-03-10 | 0 | 0 | 0 | 0% | 8 | Not Started
W232LT | W232 | W232.A5790 | DNB Enhanced Safety Cases |  |  | >>>INCOMING ENABLER (772) - Load Path Assessment | 2025-03-10 | 2025-03-10 | 0 | 0 | 0 | 0% | 263 | Not Started
W772LT | W772 | W772.A1080 | DNB Pull Harder Safety Case |  |  | >>>OUTGOING ENABLER (W232) FPU and ESA Handling with OEM NSPs | 2025-03-10 | 2025-03-10 | 0 | 0 | 0 | 0% | 156 | Not Started
ER6378LT | W222 | W222.A17510 | HRA Fuel Handling Essential Safety Case | 2024-03-19 | 2024-03-19 | Post Job Debrief | 2025-03-11 | 2025-03-11 | 1 | 1 | 1 | 0% | 14 | Not Started
ER6650LT | W226 | W226.A17510 | HYA Fuel Handling Essential Safety Case | 2024-03-19 | 2024-03-19 | Post Job Debrief | 2025-03-11 | 2025-03-11 | 1 | 1 | 1 | 0% | 14 | Not Started
W230LT | W230 | W230.2170 | HYB Enhanced Defueling Safety Case Strategy | 2024-10-01 | 2024-10-07 | HYB Enhanced Defueling Rate: Hold Case Conference / Optioneering Strategy Workshop as Appropriate | 2025-03-11 | 2025-03-17 | 5 | 5 | 5 | 0% | 12 | Not Started
W772LT | W772 | W772LT.A2290 | DNB Pull Harder Safety Case | 2025-03-04 | 2025-03-17 | <Load Path Assessment> - Draft EAN Tech Reviewed by EDF SQEP | 2025-03-11 | 2025-03-24 | 10 | 10 | 10 | 0% | 8 | Not Started
W234LT | W234 | W234.2170 | TOR Enhanced Defueling Safety Case Strategy | 2024-10-01 | 2024-10-07 | TOR Enhanced Defueling Rate: Hold Case Conference / Optioneering Strategy Workshop as Appropriate | 2025-03-11 | 2025-03-17 | 5 | 5 | 5 | 0% | 12 | Not Started
ER6371LT | W202 | W202.A5510 | HRA Reactors Shutdown Essential Safety Cases | 2024-04-10 | 2024-04-10 | Gate D PRC Paper Submission | 2025-03-12 | 2025-03-12 | 1 | 1 | 1 | 0% | 0 | Not Started
ER6661LT | W206 | W206.A5510 | HYA Reactors Shutdown Essential Safety Cases | 2024-04-10 | 2024-04-10 | Gate D PRC Paper Submission | 2025-03-12 | 2025-03-12 | 1 | 1 | 1 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.1520 | HYB Enhanced Defueling Safety Cases | 2025-03-12 | 2025-03-12 | Gate B PRC Paper Submission | 2025-03-12 | 2025-03-12 | 1 | 1 | 1 | 0% | 0 | Not Started
ER6698LT | W224 | W224.2240 | HRA Enhanced Defueling Safety Case | 2025-03-05 | 2025-03-10 | Inaugural meeting/PJB | 2025-03-12 | 2025-03-17 | 4 | 4 | 4 | 0% | 240 | Not Started
ER6701LT | W228 | W228.2240 | HYA Enhanced Defueling Safety Case | 2025-03-05 | 2025-03-10 | Inaugural meeting/PJB | 2025-03-12 | 2025-03-17 | 4 | 4 | 4 | 0% | 240 | Not Started
W731LT_UN | W731 | W731.1210 | TOR Enhanced Defueling Safety Cases | 2025-03-12 | 2025-03-12 | Gate B PRC Paper Submission | 2025-03-12 | 2025-03-12 | 1 | 1 | 1 | 0% | 0 | Not Started
ER6378LT | W222 | W222.A18980 | HRA Fuel Handling Essential Safety Case |  | 2024-05-08 | Submission Date for Paper to R4 PRC | 2025-03-12 | 2025-03-12 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6650LT | W226 | W226.A18980 | HYA Fuel Handling Essential Safety Case |  | 2024-05-08 | Submission Date for Paper to R4 PRC | 2025-03-12 | 2025-03-12 | 0 | 0 | 0 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.1540 | HYB Enhanced Defueling Safety Cases | 2025-03-13 | 2025-03-14 | PRC Members Review PRC / IMS2 Documentation | 2025-03-13 | 2025-03-14 | 2 | 2 | 2 | 0% | 6 | Not Started
ER6701LT | W228 | W228.4480 | HYA Enhanced Defueling Safety Case | 2025-02-25 | 2025-02-26 | INSA Agree MF (as required) *(KDM)* | 2025-03-13 | 2025-03-14 | 2 | 2 | 2 | 0% | 84 | Not Started
W731LT_UN | W731 | W731.1220 | TOR Enhanced Defueling Safety Cases | 2025-03-13 | 2025-03-14 | PRC Members Review PRC / IMS2 Documentation | 2025-03-13 | 2025-03-14 | 2 | 2 | 2 | 0% | 6 | Not Started
ER6666LT | W209 | W209.29330 | HYB Essential Defueling Safety Case |  | 2024-08-20 | Lessons Learnt Milestone - INSA Review of the Safety Case | 2025-03-14 | 2025-03-14 | 0 | 0 | 0 | 0% | 113 | Not Started
ER6668LT | W213 | W213.29330 | TOR Essential Defueling Safety Case |  | 2024-08-20 | Lessons Learnt Milestone - INSA Review of the Safety Case | 2025-03-14 | 2025-03-14 | 0 | 0 | 0 | 0% | 113 | Not Started
ER6701LT | W228 | W228.4490 | HYA Enhanced Defueling Safety Case |  | 2025-02-26 | INSA Approval Date Identified | 2025-03-14 | 2025-03-14 | 0 | 0 | 0 | 0% | 84 | Not Started
ER6701LT | W228 | W228.4500 | HYA Enhanced Defueling Safety Case |  | 2025-02-26 | Provide Provisional NSC Date (as required) | 2025-03-14 | 2025-03-14 | 0 | 0 | 0 | 0% | 84 | Not Started
ER6701LT | W228 | W228.3120 | HYA Enhanced Defueling Safety Case | 2025-03-13 | 2025-04-25 | Supporting Analysis for Inclusion within Substantiation Report | 2025-03-17 | 2025-04-29 | 30 | 30 | 30 | 0% | 74 | Not Started
ER6701LT | W228 | W228.1710 | HYA Enhanced Defueling Safety Case | 2025-03-13 | 2025-03-26 | EdF Technical Review | 2025-03-17 | 2025-03-28 | 10 | 10 | 10 | 0% | 30 | Not Started
W772LT | W772 | W772LT.A2670 | DNB Pull Harder Safety Case |  |  | <<NEW SCOPE PENDING CN3634><Load Path Assessment Appendix - Fixed DWTS> > - Verification Comments Addressed | 2025-03-17 | 2025-03-21 | 5 | 5 | 5 | 0% | 4 | Not Started
ER6701LT | W228 | W228.4510 | HYA Enhanced Defueling Safety Case | 2025-02-27 | 2025-03-05 | Produce Draft NSRS (using BARRIER MODEL) | 2025-03-17 | 2025-03-21 | 5 | 5 | 5 | 0% | 84 | Not Started
ER6698LT | W224 | W224.1710 | HRA Enhanced Defueling Safety Case | 2025-03-13 | 2025-03-26 | EdF Technical Review | 2025-03-18 | 2025-03-31 | 10 | 10 | 10 | 0% | 29 | Not Started
ER6698LT | W224 | W224.3120 | HRA Enhanced Defueling Safety Case | 2025-03-13 | 2025-04-25 | Supporting Analysis for inclusion within Substantiation Report | 2025-03-18 | 2025-04-30 | 30 | 30 | 30 | 0% | 73 | Not Started
W230LT | W230 | W230.2120 | HYB Enhanced Defueling Safety Case Strategy | 2024-10-08 | 2024-10-21 | HYB Enhanced Defueling Rate: Station comments on NSRS | 2025-03-18 | 2025-03-31 | 10 | 10 | 10 | 0% | 12 | Not Started
W230LT | W230 | W230.2190 | HYB Enhanced Defueling Safety Case Strategy | 2024-10-08 | 2024-10-21 | HYB Enhanced Defueling Rate: DA (Peer) Comments on NSRS | 2025-03-18 | 2025-03-31 | 10 | 10 | 10 | 0% | 12 | Not Started
W234LT | W234 | W234.2120 | TOR Enhanced Defueling Safety Case Strategy | 2024-10-08 | 2024-10-21 | TOR Enhanced Defueling Rate: Station comments on NSRS | 2025-03-18 | 2025-03-31 | 10 | 10 | 10 | 0% | 12 | Not Started
W234LT | W234 | W234.2190 | TOR Enhanced Defueling Safety Case Strategy | 2024-10-08 | 2024-10-21 | TOR Enhanced Defueling Rate: DA (Peer) Comments on NSRS | 2025-03-18 | 2025-03-31 | 10 | 10 | 10 | 0% | 12 | Not Started
ER6666LT | W209 | W209.4950 | HYB Essential Defueling Safety Case | 2024-09-11 | 2024-09-11 | NSC Presentation Date | 2025-03-19 | 2025-03-19 | 1 | 1 | 1 | 0% | 0 | Not Started
ER6668LT | W213 | W213.4950 | TOR Essential Defueling Safety Case | 2024-09-11 | 2024-09-11 | NSC Presentation Date | 2025-03-19 | 2025-03-19 | 1 | 1 | 1 | 0% | 0 | Not Started
ER6666LT | W209 | W209.1044 | HYB Essential Defueling Safety Case |  | 2024-09-11 | NSC Presentation Date (T) - EC 371387 - HYB Essential Defueling Safety Case | 2025-03-19 | 2025-03-19 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6668LT | W213 | W213.1044 | TOR Essential Defueling Safety Case |  | 2024-09-11 | NSC Presentation Date (T) - EC 371386 - TOR Essential Defueling Safety Case | 2025-03-19 | 2025-03-19 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6666LT | W209 | W209.1565 | HYB Essential Defueling Safety Case | 2024-09-12 | 2024-09-18 | NSC Consideration & advice to Station Director | 2025-03-20 | 2025-04-02 | 10 | 10 | 10 | 0% | 5 | Not Started
ER6668LT | W213 | W213.1565 | TOR Essential Defueling Safety Case | 2024-09-12 | 2024-09-18 | NSC Consideration & advice to Station Director | 2025-03-20 | 2025-04-02 | 10 | 10 | 10 | 0% | 5 | Not Started
ER6698LT | W224 | W224.3820 | HRA Enhanced Defueling Safety Case | 2025-03-20 | 2025-05-02 | CFD Analysis | 2025-03-20 | 2025-05-02 | 30 | 30 | 30 | 0% | 36 | Not Started
ER6701LT | W228 | W228.3820 | HYA Enhanced Defueling Safety Case | 2025-03-19 | 2025-05-01 | CFD Analysis | 2025-03-20 | 2025-05-02 | 30 | 30 | 30 | 0% | 36 | Not Started
ER6698LT | W224 | W224.4000 | HRA Enhanced Defueling Safety Case | 2025-03-20 | 2025-05-02 | AMP2D Analysis | 2025-03-20 | 2025-05-02 | 30 | 30 | 30 | 0% | 158 | Not Started
ER6701LT | W228 | W228.4000 | HYA Enhanced Defueling Safety Case | 2025-03-19 | 2025-05-01 | AMP2D Analysis | 2025-03-20 | 2025-05-02 | 30 | 30 | 30 | 0% | 158 | Not Started
W232LT | W232 | W232.A5830 | DNB Enhanced Safety Cases |  |  | <NEW SCOPE PENDING CN3754> - ALARP Justification for no more push out tests and direct length | 20-Mar-25* | 2025-05-09 | 34 | 34 | 34 | 0% | 88 | Not Started
W232LT | W232 | W232.A5840 | DNB Enhanced Safety Cases |  |  | <NEW SCOPE PENDING CN3754> - Use of IFD emergency clamps to free stuck SCAs. | 20-Mar-25* | 2025-05-09 | 34 | 34 | 34 | 0% | 88 | Not Started
W232LT | W232 | W232.A5850 | DNB Enhanced Safety Cases |  |  | <NEW SCOPE PENDING CN3754> - Justify use of 'high risk' NSPs for final R21 defuelled channels | 20-Mar-25* | 2025-05-09 | 34 | 34 | 34 | 0% | 88 | Not Started
W232LT | W232 | W232.A5860 | DNB Enhanced Safety Cases |  |  | <NEW SCOPE PENDING CN3754> - Justify increased tie bar slack. | 20-Mar-25* | 2025-05-09 | 34 | 34 | 34 | 0% | 88 | Not Started
W232LT | W232 | W232.C2560 | DNB Enhanced Safety Cases | 2025-02-03 | 2025-07-01 | <Agree approach to OEM NSP replacement> - Summary | 2025-03-21 | 2025-08-04 | 93 | 93 | 93 | 0% | 28 | Not Started
W232LT | W232 | W232.C2570 | DNB Enhanced Safety Cases | 2025-02-03 | 2025-02-28 | <Agree approach to OEM NSP replacement> - Prepare Draft EAN Part 1 | 21-Mar-25* | 2025-04-03 | 10 | 10 | 10 | 0% | 8 | Not Started
W772LT | W772 | W772LT.A2190 | DNB Pull Harder Safety Case |  | 2025-01-08 | <Test Schedule> - EAN / Report Completed | 2025-03-21 | 2025-03-21 | 0 | 0 | 0 | 0% | 29 | Not Started
W772LT | W772 | W772LT.A2430 | DNB Pull Harder Safety Case |  | 2024-11-22 | <Admin Controls / Tech Spec> - Issue Draft EAN / Report for Tech Review. | 2025-03-21 | 2025-03-21 | 0 | 0 | 0 | 0% | 19 | Not Started
W232LT | W232 | W232.C1990 | DNB Enhanced Safety Cases | 2025-02-10 | 2025-02-10 | <SCOPE CHANGE CN3472> <Justification for no fast fracture on FPUs (if required)> - Summary | 2025-03-24 | 2025-06-26 | 65 | 65 | 65 | 0% | 55 | Not Started
W232LT | W232 | W232.C2000 | DNB Enhanced Safety Cases | 2025-02-10 | 2025-04-04 | <SCOPE CHANGE CN3472><Justification for no fast fracture on FPUs (if required)> - Prepare Draft EAN | 24-Mar-25* | 2025-04-04 | 10 | 10 | 10 | 0% | 35 | Not Started
W232LT | W232 | W232.C2080 | DNB Enhanced Safety Cases | 2025-02-10 | 2025-06-12 | <SCOPE CHANGE CN3472><Reduction in DWTS sub-veto setting for FPUs (if required)> - Summary | 2025-03-24 | 2025-06-12 | 55 | 55 | 55 | 0% | 65 | Not Started
W232LT | W232 | W232.C2090 | DNB Enhanced Safety Cases | 2025-02-10 | 2025-04-04 | <SCOPE CHANGE CN3472><Reduction in DWTS sub-veto setting for FPUs (if required)> - Prepare Draft EAN | 24-Mar-25* | 2025-04-04 | 10 | 10 | 10 | 0% | 45 | Not Started
W232LT | W232 | W232.C2320 | DNB Enhanced Safety Cases | 2025-02-10 | 2025-04-08 | Team monitoring - to write straight into the case | 24-Mar-25* | 2025-05-23 | 42 | 42 | 42 | 0% | 8 | Not Started
W232LT | W232 | W232.C2480 | DNB Enhanced Safety Cases | 2025-01-16 | 2025-03-18 | <SCOPE CHANGE CN3472><NSP Pin Failure> - Prepare Draft EAN | 2025-03-24 | 2025-05-28 | 44 | 44 | 44 | 0% | 5 | Not Started
W232LT | W232 | W232.C2650 | DNB Enhanced Safety Cases | 2025-03-03 | 2025-07-21 | <SCOPE CHANGE CN3472>-<Demonstration of adequate integrity for Grp2 shock-loaded units> - Summary | 2025-03-24 | 2025-07-28 | 87 | 87 | 87 | 0% | 33 | Not Started
W232LT | W232 | W232.C2660 | DNB Enhanced Safety Cases | 2025-03-03 | 2025-03-28 | <SCOPE CHANGE CN3472>-<Demonstration of adequate integrity for Grp2 shock-loaded units> - Prepare Draft EAN Part 1 | 24-Mar-25* | 2025-04-04 | 10 | 10 | 10 | 0% | 13 | Not Started
W232LT | W232 | W232.C2800 | DNB Enhanced Safety Cases | 2025-03-31 | 2025-08-18 | <SCOPE CHANGE CN3472>-<Agree strategy for handling of Group 2 shock-loaded units> - Summary | 2025-03-24 | 2025-08-11 | 97 | 97 | 97 | 0% | 23 | Not Started
W232LT | W232 | W232.C2810 | DNB Enhanced Safety Cases | 2025-03-31 | 2025-04-29 | <SCOPE CHANGE CN3472>-<Agree strategy for handling of Group 2 shock-loaded units> - Prepare Draft EAN Part 1 | 2025-03-24 | 2025-04-22 | 20 | 20 | 20 | 0% | 23 | Not Started
ER6698LT | W224 | W224.2450 | HRA Enhanced Defueling Safety Case | 2025-02-17 | 2025-03-07 | Issue CETS for Tender for Load Trace | 2025-03-24 | 2025-04-11 | 15 | 15 | 15 | 0% | 190 | Not Started
ER6701LT | W228 | W228.2450 | HYA Enhanced Defueling Safety Case | 2025-02-18 | 2025-03-10 | Issue CETS for Tender for Load Trace | 2025-03-24 | 2025-04-11 | 15 | 15 | 15 | 0% | 190 | Not Started
W772LT | W772 | W772LT.A2410 | DNB Pull Harder Safety Case | 2024-11-25 | 2024-11-29 | <Admin Controls / Tech Spec> - Draft EAN / Report Tech Reviewed by EDF SQEP | 2025-03-24 | 2025-03-28 | 5 | 5 | 5 | 0% | 19 | Not Started
W232LT | W232 | W232.C3200 | DNB Enhanced Safety Cases | 2025-02-17 | 2025-02-28 | <NEW SCOPE CN3472> - Consolidation of pof from SAG | 2025-03-24 | 2025-04-04 | 10 | 10 | 10 | 0% | 5 | Not Started
W232LT | W232 | W232.C3600 | DNB Enhanced Safety Cases | 2025-03-14 | 2025-03-14 | <SCOPE NAME CHANGE CN3472><FPU and ESA Handling with OEM NSPs> - Mid Job Brief | 2025-03-24 | 2025-03-24 | 1 | 1 | 1 | 0% | 6 | Not Started
W772LT | W772 | W772LT.A2680 | DNB Pull Harder Safety Case |  |  | <<NEW SCOPE PENDING CN3634><Load Path Assessment Appendix - Fixed DWTS> > - Verification Complete | 2025-03-24 | 2025-03-28 | 5 | 5 | 5 | 0% | 4 | Not Started
ER6701LT | W228 | W228.4520 | HYA Enhanced Defueling Safety Case | 2025-03-06 | 2025-03-17 | Station Comments on NSRS | 2025-03-24 | 2025-04-02 | 8 | 8 | 8 | 0% | 89 | Not Started
ER6701LT | W228 | W228.4530 | HYA Enhanced Defueling Safety Case | 2025-03-06 | 2025-03-17 | Key Stakeholders (Peer) comments on NSRS (as required) | 2025-03-24 | 2025-04-02 | 8 | 8 | 8 | 0% | 84 | Not Started
ER6378LT | W222 | W222.A18990 | HRA Fuel Handling Essential Safety Case | 2024-05-21 | 2024-05-21 | Hold Project Review Committee (R4 PRC) | 2025-03-25 | 2025-03-25 | 1 | 1 | 1 | 0% | 0 | Not Started
ER6650LT | W226 | W226.A18990 | HYA Fuel Handling Essential Safety Case | 2024-05-21 | 2024-05-21 | Hold Project Review Committee (R4 PRC) | 2025-03-25 | 2025-03-25 | 1 | 1 | 1 | 0% | 0 | Not Started
ER6371LT | W202 | W202.A5650 | HRA Reactors Shutdown Essential Safety Cases | 2024-04-23 | 2024-04-23 | Hold PRC Meeting | 2025-03-25 | 2025-03-25 | 1 | 1 | 1 | 0% | 0 | Not Started
ER6661LT | W206 | W206.A5650 | HYA Reactors Shutdown Essential Safety Cases | 2024-04-23 | 2024-04-23 | Hold PRC Meeting | 2025-03-25 | 2025-03-25 | 1 | 1 | 1 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.1570 | HYB Enhanced Defueling Safety Cases | 2025-03-25 | 2025-03-25 | Hold PRC Meeting | 2025-03-25 | 2025-03-25 | 1 | 1 | 1 | 0% | 0 | Not Started
W772LT | W772 | W772LT.A2300 | DNB Pull Harder Safety Case | 2025-03-18 | 2025-05-22 | <Load Path Assessment> - Address Comments from EDF Review on Draft EAN | 2025-03-25 | 2025-04-07 | 10 | 10 | 10 | 0% | 8 | Not Started
W232LT | W232 | W232.C3610 | DNB Enhanced Safety Cases | 2025-03-17 | 2025-05-14 | <SCOPE NAME CHANGE CN3472><FPU and ESA Handling with OEM NSPs> - Prepare Draft EAN Part 2 | 2025-03-25 | 2025-05-22 | 40 | 40 | 40 | 0% | 6 | Not Started
W731LT_UN | W731 | W731.1230 | TOR Enhanced Defueling Safety Cases | 2025-03-25 | 2025-03-25 | Hold PRC Meeting | 2025-03-25 | 2025-03-25 | 1 | 1 | 1 | 0% | 0 | Not Started
ER6371LT | W202 | W202.A5470 | HRA Reactors Shutdown Essential Safety Cases |  | 2024-04-23 | Gate D For Region 1 Essential Defuelling Safety Case | 2025-03-25 | 2025-03-25 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6661LT | W206 | W206.A5470 | HYA Reactors Shutdown Essential Safety Cases |  | 2024-04-23 | Gate D For Region 1 Essential Defuelling Safety Case | 2025-03-25 | 2025-03-25 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6378LT | W222 | W222.A13310 | HRA Fuel Handling Essential Safety Case |  | 2024-05-21 | Gate D for Region 1 - HRA Defuelling Fuel Handling Essential Safety Case | 2025-03-25 | 2025-03-25 | 0 | 0 | 0 | 0% | 4 | Not Started
ER6650LT | W226 | W226.A13310 | HYA Fuel Handling Essential Safety Case |  | 2024-05-21 | Gate D for Region 1 - HYA Defuelling Fuel Handling Essential Safety Case | 2025-03-25 | 2025-03-25 | 0 | 0 | 0 | 0% | 4 | Not Started
ER6378LT | W222 | W222.A19000 | HRA Fuel Handling Essential Safety Case | 2024-05-22 | 2024-05-29 | Incorporate Comments from R4 PRC | 2025-03-26 | 2025-03-31 | 4 | 4 | 4 | 0% | 0 | Not Started
ER6650LT | W226 | W226.A19000 | HYA Fuel Handling Essential Safety Case | 2024-05-22 | 2024-05-29 | Incorporate Comments from R4 PRC | 2025-03-26 | 2025-03-31 | 4 | 4 | 4 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.1550 | HYB Enhanced Defueling Safety Cases | 2025-03-26 | 2025-03-27 | Modify PRC Paper as Required | 2025-03-26 | 2025-03-27 | 2 | 2 | 2 | 0% | 16 | Not Started
W730LT_UN | W730 | W730.1560 | HYB Enhanced Defueling Safety Cases | 2025-03-26 | 2025-03-27 | Modify Estimate, Schedule & Risk Log as Required | 2025-03-26 | 2025-03-27 | 2 | 2 | 2 | 0% | 16 | Not Started
W731LT_UN | W731 | W731.1240 | TOR Enhanced Defueling Safety Cases | 2025-03-26 | 2025-03-27 | Modify Estimate, Schedule & Risk Log as Required | 2025-03-26 | 2025-03-27 | 2 | 2 | 2 | 0% | 16 | Not Started
W731LT_UN | W731 | W731.1250 | TOR Enhanced Defueling Safety Cases | 2025-03-26 | 2025-03-27 | Modify PRC Paper as Required | 2025-03-26 | 2025-03-27 | 2 | 2 | 2 | 0% | 16 | Not Started
W730LT_UN | W730 | W730.1580 | HYB Enhanced Defueling Safety Cases |  | 2025-03-27 | Gate B PRC Paper Approval | 2025-03-27 | 2025-03-27 | 0 | 0 | 0 | 0% | 16 | Not Started
W730LT_UN | W730 | W730.1130 | HYB Enhanced Defueling Safety Cases |  | 2025-03-27 | Gate B Approved | 2025-03-27 | 2025-03-27 | 0 | 0 | 0 | 0% | 16 | Not Started
W731LT_UN | W731 | W731.1260 | TOR Enhanced Defueling Safety Cases |  | 2025-03-27 | Gate B Approved | 2025-03-27 | 2025-03-27 | 0 | 0 | 0 | 0% | 16 | Not Started
W731LT_UN | W731 | W731.1270 | TOR Enhanced Defueling Safety Cases |  | 2025-03-27 | Gate B PRC Paper Approval | 2025-03-28 | 2025-03-27 | 0 | 0 | 0 | 0% | 16 | Not Started
ER6701LT | W228 | W228.2100 | HYA Enhanced Defueling Safety Case |  | 2025-03-26 | KDM - Detailed Design Bob Weight & Gripping Sleeve | 2025-03-28 | 2025-03-28 | 0 | 0 | 0 | 0% | 231 | Not Started
ER6701LT | W228 | W228.1720 | HYA Enhanced Defueling Safety Case |  | 2025-03-26 | Approval of Drawings Subject to Substantiation | 2025-03-28 | 2025-03-28 | 0 | 0 | 0 | 0% | 181 | Not Started
ER6698LT | W224 | W224.2710 | HRA Enhanced Defueling Safety Case | 2025-03-31 | 2025-04-11 | Technical Review | 2025-03-31 | 2025-04-11 | 10 | 10 | 10 | 0% | 221 | Not Started
ER6698LT | W224 | W224.2720 | HRA Enhanced Defueling Safety Case | 2025-03-31 | 2025-04-11 | Design Review | 2025-03-31 | 2025-04-11 | 10 | 10 | 10 | 0% | 20 | Not Started
ER6701LT | W228 | W228.3600 | HYA Enhanced Defueling Safety Case | 2025-03-27 | 2025-04-17 | Appropriate NDT and QA/Records/Material Certs etc | 2025-03-31 | 2025-04-23 | 16 | 16 | 16 | 0% | 81 | Not Started
ER6701LT | W228 | W228.3590 | HYA Enhanced Defueling Safety Case | 2025-03-27 | 2025-07-01 | Small Batch Manufacture of Bob Weight & Griping Sleeve | 2025-03-31 | 2025-07-03 | 65 | 65 | 65 | 0% | 32 | Not Started
ER6701LT | W228 | W228.3140 | HYA Enhanced Defueling Safety Case | 2025-03-27 | 2025-04-25 | Consolidation of Analaysis and Matrix into the DSR document | 2025-03-31 | 2025-04-29 | 20 | 20 | 20 | 0% | 119 | Not Started
ER6701LT | W228 | W228.3130 | HYA Enhanced Defueling Safety Case | 2025-03-27 | 2025-04-25 | Requirements Traceability Matrix | 2025-03-31 | 2025-04-29 | 20 | 20 | 20 | 0% | 119 | Not Started
ER6701LT | W228 | W228.2720 | HYA Enhanced Defueling Safety Case | 2025-03-31 | 2025-04-11 | Design Review | 2025-03-31 | 2025-04-11 | 10 | 10 | 10 | 0% | 20 | Not Started
ER6701LT | W228 | W228.2710 | HYA Enhanced Defueling Safety Case | 2025-03-31 | 2025-04-11 | Technical Review | 2025-03-31 | 2025-04-11 | 10 | 10 | 10 | 0% | 221 | Not Started
W772LT | W772 | W772LT.A1135 | DNB Pull Harder Safety Case | 2025-05-09 | 2025-06-06 | Obtain peer review (if required) ==> KDM | 2025-03-31 | 2025-04-29 | 20 | 20 | 20 | 0% | 4 | Not Started
W772LT | W772 | W772LT.A2440 | DNB Pull Harder Safety Case | 2024-12-02 | 2024-12-06 | <Admin Controls / Tech Spec> - Address Comments from EDF Review on Draft EAN / Report | 2025-03-31 | 2025-04-04 | 5 | 5 | 5 | 0% | 19 | Not Started
ER6701LT | W228 | W224.3880 | HYA Enhanced Defueling Safety Case | 2025-03-27 | 2025-04-25 | Author Bob Weight & Gripping Sleeve Procurement Specification | 2025-03-31 | 2025-04-29 | 20 | 20 | 20 | 0% | 181 | Not Started
W772LT | W772 | W772LT.A2690 | DNB Pull Harder Safety Case |  |  | <<NEW SCOPE PENDING CN3634><Load Path Assessment Appendix - Fixed DWTS> > - EDF TR Comments Provided | 2025-03-31 | 2025-04-04 | 5 | 5 | 5 | 0% | 4 | Not Started
ER6701LT | W228 | W228.5210 | HYA Enhanced Defueling Safety Case | 2025-03-27 | 2025-04-01 | Produce MF (as required) | 2025-03-31 | 2025-04-03 | 4 | 4 | 4 | 0% | 30 | Not Started
ER6371LT | W202 | W202.A5520 | HRA Reactors Shutdown Essential Safety Cases |  | 2024-04-23 | Phase 2 Project Completion | 2025-03-31 | 2025-03-31 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6661LT | W206 | W206.A5520 | HYA Reactors Shutdown Essential Safety Cases |  | 2024-04-23 | Phase 2 Project Completion | 2025-03-31 | 2025-03-31 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6378LT | W222 | W222.A27170 | HRA Fuel Handling Essential Safety Case |  | 2024-05-29 | Project Completed | 2025-03-31 | 2025-03-31 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6650LT | W226 | W226.A27170 | HYA Fuel Handling Essential Safety Case |  | 2024-05-29 | Project Completed | 2025-03-31 | 2025-03-31 | 0 | 0 | 0 | 0% | 0 | Not Started
W232LT | W232 | W232.C1770 | DNB Enhanced Safety Cases |  | 2025-03-17 | <SCOPE CHANGE CN3472><FPU Sub-veto fault frequency> - Issue Draft EAN to EDF for Review | 2025-03-31 | 2025-03-31 | 0 | 0 | 0 | 0% | 56 | Not Started
ER6698LT | W224 | W224.1720 | HRA Enhanced Defueling Safety Case |  | 2025-03-26 | Approval of Drawings Subject to Substantiation | 2025-03-31 | 2025-03-31 | 0 | 0 | 0 | 0% | 180 | Not Started
ER6698LT | W224 | W224.2100 | HRA Enhanced Defueling Safety Case |  | 2025-03-26 | KDM - Detailed Design Bob Weight & Gripping Sleeve | 2025-03-31 | 2025-03-31 | 0 | 0 | 0 | 0% | 230 | Not Started
W232LT | W232 | W232.C1710 | DNB Enhanced Safety Cases | 2025-03-18 | 2025-04-14 | <SCOPE CHANGE CN3472><FPU Sub-veto fault frequency> - Draft EAN Reviewed by EDF SQEP | 2025-04-01 | 2025-04-30 | 20 | 20 | 20 | 0% | 56 | Not Started
ER6698LT | W224 | W224.3130 | HRA Enhanced Defueling Safety Case | 2025-03-27 | 2025-04-25 | Requirements Traceability Matrix | 2025-04-01 | 2025-04-30 | 20 | 20 | 20 | 0% | 118 | Not Started
ER6698LT | W224 | W224.3140 | HRA Enhanced Defueling Safety Case | 2025-03-27 | 2025-04-25 | Consolidation of Analaysis and Matrix into the DSR document | 2025-04-01 | 2025-04-30 | 20 | 20 | 20 | 0% | 118 | Not Started
ER6698LT | W224 | W224.3590 | HRA Enhanced Defueling Safety Case | 2025-03-27 | 2025-07-01 | Small Batch Manufacture of Bob Weight & Griping Sleeve | 2025-04-01 | 2025-07-04 | 65 | 65 | 65 | 0% | 31 | Not Started
ER6698LT | W224 | W224.3600 | HRA Enhanced Defueling Safety Case | 2025-03-27 | 2025-04-17 | Appropriate NDT and QA/Records/Material Certs etc | 2025-04-01 | 2025-04-24 | 16 | 16 | 16 | 0% | 80 | Not Started
W230LT | W230 | W230.2080 | HYB Enhanced Defueling Safety Case Strategy | 2024-10-22 | 2024-11-04 | HYB Enhanced Defueling Rate: INA comments on NSRS | 2025-04-01 | 2025-04-14 | 10 | 10 | 10 | 0% | 12 | Not Started
ER6698LT | W224 | W224.3880 | HRA Enhanced Defueling Safety Case | 2025-03-27 | 2025-04-25 | Author Bob Weight & Gripping Sleeve Procurement Specification | 2025-04-01 | 2025-04-30 | 20 | 20 | 20 | 0% | 180 | Not Started
ER6698LT | W224 | W224.5210 | HRA Enhanced Defueling Safety Case | 2025-03-27 | 2025-04-01 | Produce MF (as required) | 2025-04-01 | 2025-04-04 | 4 | 4 | 4 | 0% | 29 | Not Started
W234LT | W234 | W234.2080 | TOR Enhanced Defueling Safety Case Strategy | 2024-10-22 | 2024-11-04 | TOR Enhanced Defueling Rate: INA comments on NSRS | 2025-04-01 | 2025-04-14 | 10 | 10 | 10 | 0% | 12 | Not Started
ER6666LT | W209 | W209.1046 | HYB Essential Defueling Safety Case |  | 2024-09-18 | INSA Final Approval EC 371387 - HYB Essential Defueling Safety Case | 2025-04-02 | 2025-04-02 | 0 | 0 | 0 | 0% | 5 | Not Started
ER6668LT | W213 | W213.1046 | TOR Essential Defueling Safety Case |  | 2024-09-18 | INSA Final Approval EC 371386 - TOR Essential Defueling Safety Case | 2025-04-02 | 2025-04-02 | 0 | 0 | 0 | 0% | 5 | Not Started
ER6701LT | W228 | W228.4540 | HYA Enhanced Defueling Safety Case |  | 2025-03-17 | INSA Resource Identified | 2025-04-02 | 2025-04-02 | 0 | 0 | 0 | 0% | 84 | Not Started
ER6666LT | W209 | W209.1575 | HYB Essential Defueling Safety Case | 2024-10-17 | 2025-01-13 | ONR Approval of Safety Case (Letter sent to initiate) EC 371387 - HYB Essential Defueling SC - (FEEDS SUMMARY SCHEDULE) | 2025-04-03 | 2025-07-01 | 60 | 60 | 60 | 0% | 5 | Not Started
ER6668LT | W213 | W213.1575 | TOR Essential Defueling Safety Case | 2024-10-17 | 2025-01-13 | ONR Approval of Safety Case (Letter sent to initiate) EC 371386 - TOR Essential Defueling SC - (FEEDS SUMMARY SCHEDULE) | 2025-04-03 | 2025-07-01 | 60 | 60 | 60 | 0% | 5 | Not Started
ER6701LT | W228 | W228.4550 | HYA Enhanced Defueling Safety Case | 2025-03-18 | 2025-03-24 | INA Comments on NSRS | 2025-04-03 | 2025-04-09 | 5 | 5 | 5 | 0% | 84 | Not Started
W730LT_UN | W730 | W730.2230 | HYB Enhanced Defueling Safety Cases | 2025-04-03 | 2026-09-10 | ## HYB Enhanced Defueling Rate: B - B+ Phase Funding - (Cost Summary) ## | 2025-04-03 | 2026-09-10 | 362 | 362 | 362 | 0% | 395 | Not Started
W730LT_UN | W730 | W730.2240 | HYB Enhanced Defueling Safety Cases |  | 2025-04-03 | HYB Enhanced Defueling Rate: Commence Supporting References or Supporting EC's | 2025-04-03 | 2025-04-03 | 0 | 0 | 0 | 0% | 11 | Not Started
ER6701LT | W228 | W228.5220 | HYA Enhanced Defueling Safety Case |  | 2025-04-01 | Issue MF (as required) | 2025-04-03 | 2025-04-03 | 0 | 0 | 0 | 0% | 30 | Not Started
W731LT_UN | W731 | W731.1280 | TOR Enhanced Defueling Safety Cases |  | 2025-04-03 | TOR Enhanced Defueling Rate: Commence Supporting References or Supporting EC's | 2025-04-03 | 2025-04-03 | 0 | 0 | 0 | 0% | 11 | Not Started
W731LT_UN | W731 | W731.1300 | TOR Enhanced Defueling Safety Cases | 2025-04-03 | 2026-09-10 | ## TOR Enhanced Defueling Rate: B - B+ Phase Funding - (Cost Summary) ## | 2025-04-03 | 2026-09-10 | 362 | 362 | 362 | 0% | 395 | Not Started
W232LT | W232 | W232.C3620 | DNB Enhanced Safety Cases | 2025-03-03 | 2025-03-03 | <SCOPE CHANGE CN3472><Agree approach to OEM NSP replacement> - Mid Job Brief | 2025-04-04 | 2025-04-04 | 1 | 1 | 1 | 0% | 8 | Not Started
ER6701LT | W228 | W228.3960 | HYA Enhanced Defueling Safety Case | 2025-04-04 | 2025-04-17 | EDF TR Handling Equipment | 2025-04-04 | 2025-04-17 | 10 | 10 | 10 | 0% | 38 | Not Started
ER6698LT | W224 | W224.3960 | HRA Enhanced Defueling Safety Case | 2025-04-04 | 2025-04-17 | EDF TR Handling Equipment | 2025-04-04 | 2025-04-17 | 10 | 10 | 10 | 0% | 38 | Not Started
ER6701LT | W228 | W228.5230 | HYA Enhanced Defueling Safety Case | 2025-04-02 | 2025-04-07 | Categorisation by RE / Station | 2025-04-04 | 2025-04-09 | 4 | 4 | 4 | 0% | 30 | Not Started
W730LT_UN | W730 | W730.3710 | HYB Enhanced Defueling Safety Cases | 2025-04-04 | 2025-07-30 | HYB Enhanced Defueling Rate: PSA Modeling & Updates | 2025-04-04 | 2025-07-30 | 80 | 80 | 80 | 0% | 11 | Not Started
W731LT_UN | W731 | W731.1290 | TOR Enhanced Defueling Safety Cases | 2025-04-04 | 2025-07-30 | TOR Enhanced Defueling Rate: PSA Modeling & Updates | 2025-04-04 | 2025-07-30 | 80 | 80 | 80 | 0% | 11 | Not Started
W772LT | W772 | W772LT.A2450 | DNB Pull Harder Safety Case |  | 2024-12-06 | <Admin Controls / Tech Spec> - Issue Final EAN / Report | 2025-04-04 | 2025-04-04 | 0 | 0 | 0 | 0% | 19 | Not Started
W232LT | W232 | W232.C3210 | DNB Enhanced Safety Cases |  |  | Discovery milestone - (Justification for no fast fracture on FPUs (if required)) | 2025-04-04 | 2025-04-04 | 0 | 0 | 0 | 0% | 5 | Not Started
ER6698LT | W224 | W224.5220 | HRA Enhanced Defueling Safety Case |  | 2025-04-01 | Issue MF (as required) | 2025-04-04 | 2025-04-04 | 0 | 0 | 0 | 0% | 29 | Not Started
ER6372LT | W203 | W203.A2580 | HNB Enhanced Defuelling Safety Cases | 2025-04-14 | 2025-06-24 | Project Management Gate D - E | 2025-04-07 | 2025-05-20 | 29 | 29 | 29 | 0% | 0 | Not Started
ER6372LT | W203 | W203.B2310 | HNB Enhanced Defuelling Safety Cases | 2025-04-14 | 2025-04-14 | Hold Project Closeout and Lessons Learnt Meeting | 07-Apr-25* | 2025-04-07 | 1 | 1 | 1 | 0% | 3 | Not Started
W232LT | W232 | W232.C2160 | DNB Enhanced Safety Cases | 2025-04-07 | 2025-04-22 | <SCOPE CHANGE CN3472><Reduction in DWTS sub-veto setting for FPUs (if required)> - TSA Internal Review of Draft EAN | 2025-04-07 | 2025-04-22 | 10 | 10 | 10 | 0% | 45 | Not Started
ER6698LT | W224 | W224.2640 | HRA Enhanced Defueling Safety Case | 2025-03-17 | 2025-03-21 | Issue CETS for Tender for Trip Functions | 2025-04-07 | 2025-04-11 | 5 | 5 | 5 | 0% | 26 | Not Started
ER6701LT | W228 | W228.2640 | HYA Enhanced Defueling Safety Case | 2025-03-17 | 2025-03-21 | Issue CETS for Tender for Trip Functions | 2025-04-07 | 2025-04-11 | 5 | 5 | 5 | 0% | 26 | Not Started
W232LT | W232 | W232.C3220 | DNB Enhanced Safety Cases | 2025-04-07 | 2025-04-22 | <SCOPE CHANGE CN3472> <Justification for no fast fracture on FPUs (if required)> - TSA Internal Review of Draft EAN | 2025-04-07 | 2025-04-22 | 10 | 10 | 10 | 0% | 35 | Not Started
W232LT | W232 | W232.C3630 | DNB Enhanced Safety Cases | 2025-03-04 | 2025-04-14 | <SCOPE CHANGE CN3472><Agree approach to OEM NSP replacement> - Prepare Draft EAN Part 2 | 2025-04-07 | 2025-05-21 | 30 | 30 | 30 | 0% | 8 | Not Started
W232LT | W232 | W232.C3640 | DNB Enhanced Safety Cases | 2025-03-31 | 2025-03-31 | <SCOPE CHANGE CN3472><Demonstration of adequate integrity for Grp2 shock-loaded units> - Mid Job Brief | 2025-04-07 | 2025-04-07 | 1 | 1 | 1 | 0% | 13 | Not Started
ER6698LT | W224 | W224.5230 | HRA Enhanced Defueling Safety Case | 2025-04-02 | 2025-04-07 | Categorisation by RE / Station | 2025-04-07 | 2025-04-10 | 4 | 4 | 4 | 0% | 29 | Not Started
W772LT | W772 | W772LT.A2700 | DNB Pull Harder Safety Case |  |  | <<NEW SCOPE PENDING CN3634><Load Path Assessment Appendix - Fixed DWTS> > - EDF TR Complete | 2025-04-07 | 2025-04-22 | 10 | 10 | 10 | 0% | 4 | Not Started
W772LT | W772 | W772LT.A2310 | DNB Pull Harder Safety Case |  | 2025-05-22 | <Load Path Assessment> - Issue Final EAN | 2025-04-07 | 2025-04-07 | 0 | 0 | 0 | 0% | 8 | Not Started
ER6372LT | W203 | W203.B2330 | HNB Enhanced Defuelling Safety Cases | 2025-04-15 | 2025-04-15 | Produce Lessons Learned Report | 2025-04-08 | 2025-04-08 | 1 | 1 | 1 | 0% | 3 | Not Started
W772LT | W772 | W772LT.A2320 | DNB Pull Harder Safety Case | 2025-05-23 | 2025-06-06 | <Load Path Assessment> - EAN Completed and Uploaded to CDMS | 2025-04-08 | 2025-04-23 | 10 | 10 | 10 | 0% | 8 | Not Started
W232LT | W232 | W232.C3650 | DNB Enhanced Safety Cases | 2025-04-01 | 2025-05-08 | <SCOPE CHANGE CN3472><Demonstration of adequate integrity for Grp2 shock-loaded units> - Prepare Draft EAN Part 2 | 2025-04-08 | 2025-05-15 | 25 | 25 | 25 | 0% | 13 | Not Started
ER6372LT | W203 | W203.A2300 | HNB Enhanced Defuelling Safety Cases | 2025-04-16 | 2025-05-01 | Write PRC Paper [FEEDS TO SUMMARY SCHEDULE] | 2025-04-09 | 2025-04-24 | 10 | 10 | 10 | 0% | 3 | Not Started
ER6701LT | W228 | W228.4560 | HYA Enhanced Defueling Safety Case | 2025-03-25 | 2025-03-31 | Incorporate INA, Station, ED (peer) comments | 2025-04-10 | 2025-04-16 | 5 | 5 | 5 | 0% | 84 | Not Started
ER6701LT | W228 | W228.5240 | HYA Enhanced Defueling Safety Case | 2025-04-08 | 2025-04-09 | INSA Agree MF (as required) *(KDM)* | 2025-04-10 | 2025-04-11 | 2 | 2 | 2 | 0% | 30 | Not Started
ER6698LT | W224 | W224.5240 | HRA Enhanced Defueling Safety Case | 2025-04-08 | 2025-04-09 | INSA Agree MF (as required) *(KDM)* | 2025-04-11 | 2025-04-14 | 2 | 2 | 2 | 0% | 29 | Not Started
ER6698LT | W224 | W224.2850 | HRA Enhanced Defueling Safety Case |  | 2025-04-11 | KDM - Discovery Milestone – Trip Reliability | 2025-04-11 | 2025-04-11 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6698LT | W224 | W224.2560 | HRA Enhanced Defueling Safety Case |  | 2025-03-07 | KDM - CETS ISSUE Approval for Load Trace | 2025-04-11 | 2025-04-11 | 0 | 0 | 0 | 0% | 190 | Not Started
ER6698LT | W224 | W224.3510 | HRA Enhanced Defueling Safety Case |  | 2025-03-21 | KDM - CETS ISSUE Approval for Trip Functions | 2025-04-11 | 2025-04-11 | 0 | 0 | 0 | 0% | 26 | Not Started
ER6698LT | W224 | W224.2940 | HRA Enhanced Defueling Safety Case |  | 2025-04-11 | KDM - Discovery Milestone – Trip Reliability | 2025-04-11 | 2025-04-11 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6701LT | W228 | W228.2940 | HYA Enhanced Defueling Safety Case |  | 2025-04-11 | KDM - Discovery Milestone – Trip Reliability | 2025-04-11 | 2025-04-11 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6701LT | W228 | W228.3510 | HYA Enhanced Defueling Safety Case |  | 2025-03-21 | KDM - CETS ISSUE Approval for Trip Functions | 2025-04-11 | 2025-04-11 | 0 | 0 | 0 | 0% | 26 | Not Started
ER6701LT | W228 | W228.2560 | HYA Enhanced Defueling Safety Case |  | 2025-03-10 | KDM - CETS ISSUE Approval for Load Trace | 2025-04-11 | 2025-04-11 | 0 | 0 | 0 | 0% | 190 | Not Started
ER6701LT | W228 | W228.5250 | HYA Enhanced Defueling Safety Case |  | 2025-04-09 | INSA Approval Date Identified | 2025-04-11 | 2025-04-11 | 0 | 0 | 0 | 0% | 30 | Not Started
ER6701LT | W228 | W228.5260 | HYA Enhanced Defueling Safety Case |  | 2025-04-09 | Provide Provisional NSC Date (as required) | 2025-04-11 | 2025-04-11 | 0 | 0 | 0 | 0% | 30 | Not Started
ER6698LT | W224 | W224.1610 | HRA Enhanced Defueling Safety Case | 2025-04-07 | 2025-05-07 | EdF Technical Review | 2025-04-14 | 2025-05-14 | 20 | 20 | 20 | 0% | 0 | Not Started
ER6698LT | W224 | W224.2550 | HRA Enhanced Defueling Safety Case | 2025-03-10 | 2025-04-04 | Supplier Return Period for Load Trace | 2025-04-14 | 2025-05-14 | 20 | 20 | 20 | 0% | 190 | Not Started
ER6698LT | W224 | W224.2650 | HRA Enhanced Defueling Safety Case | 2025-03-24 | 2025-04-22 | Supplier Return Period for Trip Functions | 2025-04-14 | 2025-05-14 | 20 | 20 | 20 | 0% | 26 | Not Started
ER6701LT | W228 | W228.2650 | HYA Enhanced Defueling Safety Case | 2025-03-24 | 2025-04-22 | Supplier Return Period for Trip Functions | 2025-04-14 | 2025-05-14 | 20 | 20 | 20 | 0% | 26 | Not Started
ER6701LT | W228 | W228.2550 | HYA Enhanced Defueling Safety Case | 2025-03-11 | 2025-04-07 | Supplier Return Period for Load Trace | 2025-04-14 | 2025-05-14 | 20 | 20 | 20 | 0% | 190 | Not Started
ER6701LT | W228 | W228.1610 | HYA Enhanced Defueling Safety Case | 2025-04-07 | 2025-05-07 | EdF Technical Review | 2025-04-14 | 2025-05-14 | 20 | 20 | 20 | 0% | 0 | Not Started
ER6698LT | W224 | W224.4080 | HRA Enhanced Defueling Safety Case | 2025-04-14 | 2025-04-17 | Produce MF (as required) | 2025-04-14 | 2025-04-17 | 4 | 4 | 4 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4080 | HYA Enhanced Defueling Safety Case | 2025-04-14 | 2025-04-17 | Produce MF (as required) | 2025-04-14 | 2025-04-17 | 4 | 4 | 4 | 0% | 20 | Not Started
ER6701LT | W228 | W228.5270 | HYA Enhanced Defueling Safety Case | 2025-04-10 | 2025-04-16 | Produce Draft NSRS (using BARRIER MODEL) | 2025-04-14 | 2025-04-22 | 5 | 5 | 5 | 0% | 30 | Not Started
ER6698LT | W224 | W224.A1620 | HRA Enhanced Defueling Safety Case |  |  | Cost Summary - Trip Functions EC 1 | 2025-04-14 | 2025-06-11 | 39 | 39 | 39 | 0% | 20 | Not Started
ER6701LT | W228 | W228.A1620 | HYA Enhanced Defueling Safety Case |  |  | Cost Summary - Trip Function EC 1 | 2025-04-14 | 2025-06-11 | 39 | 39 | 39 | 0% | 20 | Not Started
W230LT | W230 | W230.3750 | HYB Enhanced Defueling Safety Case Strategy |  |  | HYB Enhanced Defueling Rate: INA comments on NSRS | 2025-04-14 | 2025-04-14 | 0 | 0 | 0 | 0% | 275 | Not Started
ER6698LT | W224 | W224.5250 | HRA Enhanced Defueling Safety Case |  | 2025-04-09 | INSA Approval Date Identified | 2025-04-14 | 2025-04-14 | 0 | 0 | 0 | 0% | 29 | Not Started
ER6698LT | W224 | W224.5260 | HRA Enhanced Defueling Safety Case |  | 2025-04-09 | Provide Provisional NSC Date (as required) | 2025-04-14 | 2025-04-14 | 0 | 0 | 0 | 0% | 29 | Not Started
W234LT | W234 | W234.3750 | TOR Enhanced Defueling Safety Case Strategy |  |  | TOR Enhanced Defueling Rate: INA comments on NSRS | 2025-04-14 | 2025-04-14 | 0 | 0 | 0 | 0% | 275 | Not Started
W230LT | W230 | W230.2140 | HYB Enhanced Defueling Safety Case Strategy | 2024-11-05 | 2024-11-05 | HYB Enhanced Defueling Rate: Register EC and identify Milestones in AMS EC NNNNNN | 2025-04-15 | 2025-04-15 | 1 | 1 | 1 | 0% | 12 | Not Started
ER6698LT | W224 | W224.5270 | HRA Enhanced Defueling Safety Case | 2025-04-10 | 2025-04-16 | Produce Draft NSRS (using BARRIER MODEL) | 2025-04-15 | 2025-04-23 | 5 | 5 | 5 | 0% | 29 | Not Started
W234LT | W234 | W234.2140 | TOR Enhanced Defueling Safety Case Strategy | 2024-11-05 | 2024-11-05 | TOR Enhanced Defueling Rate: Register EC and identify Milestones in AMS EC NNNNNN | 2025-04-15 | 2025-04-15 | 1 | 1 | 1 | 0% | 12 | Not Started
W230LT | W230 | W230.2150 | HYB Enhanced Defueling Safety Case Strategy | 2024-11-06 | 2024-11-06 | HYB Enhanced Defueling Rate: Update NSRS to address comments | 2025-04-16 | 2025-04-16 | 1 | 1 | 1 | 0% | 12 | Not Started
W234LT | W234 | W234.2150 | TOR Enhanced Defueling Safety Case Strategy | 2024-11-06 | 2024-11-06 | TOR Enhanced Defueling Rate: Update NSRS to address comments | 2025-04-16 | 2025-04-16 | 1 | 1 | 1 | 0% | 12 | Not Started
W230LT | W230 | W230.2110 | HYB Enhanced Defueling Safety Case Strategy | 2024-11-14 | 2024-11-14 | HYB Enhanced Defueling Rate: Issue final NSRS | 2025-04-17 | 2025-04-17 | 1 | 1 | 1 | 0% | 12 | Not Started
W230LT | W230 | W230.2210 | HYB Enhanced Defueling Safety Case Strategy | 2024-11-07 | 2024-11-13 | HYB Enhanced Defueling Rate: Risk Ref 38976 TBC - NSRS Production | 2025-04-17 | 2025-04-17 | 0 | 0 | 0 | 0% | 12 | Not Started
W230LT | W230 | W230.1210 | HYB Enhanced Defueling Safety Case Strategy |  | 2024-11-13 | HYB Enhanced Defueling Rate: Risk Milestone - NSRS Production Complete (Risk Ref 38976) | 2025-04-17 | 2025-04-17 | 0 | 0 | 0 | 0% | 12 | Not Started
ER6701LT | W228 | W228.4570 | HYA Enhanced Defueling Safety Case | 2025-04-01 | 2025-04-01 | Issue Final NSRS | 2025-04-17 | 2025-04-17 | 1 | 1 | 1 | 0% | 84 | Not Started
W234LT | W234 | W234.2110 | TOR Enhanced Defueling Safety Case Strategy | 2024-11-14 | 2024-11-14 | TOR Enhanced Defueling Rate: Issue final NSRS | 2025-04-17 | 2025-04-17 | 1 | 1 | 1 | 0% | 12 | Not Started
W234LT | W234 | W234.2210 | TOR Enhanced Defueling Safety Case Strategy | 2024-11-07 | 2024-11-13 | TOR Enhanced Defueling Rate: Risk Ref 38976 TBC - NSRS Production | 2025-04-17 | 2025-04-17 | 0 | 0 | 0 | 0% | 12 | Not Started
W234LT | W234 | W234.1210 | TOR Enhanced Defueling Safety Case Strategy |  | 2024-11-13 | TOR Enhanced Defueling Rate: Risk Milestone - NSRS Production Complete (Risk Ref 38976) | 2025-04-17 | 2025-04-17 | 0 | 0 | 0 | 0% | 12 | Not Started
ER6698LT | W224 | W224.4090 | HRA Enhanced Defueling Safety Case |  | 2025-04-17 | Issue MF (as required) | 2025-04-17 | 2025-04-17 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4090 | HYA Enhanced Defueling Safety Case |  | 2025-04-17 | Issue MF (as required) | 2025-04-17 | 2025-04-17 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4580 | HYA Enhanced Defueling Safety Case |  | 2025-04-01 | Station Agree NSRS *(KDM)* | 2025-04-17 | 2025-04-17 | 0 | 0 | 0 | 0% | 84 | Not Started
ER6701LT | W228 | W228.4590 | HYA Enhanced Defueling Safety Case |  | 2025-04-01 | Key Stakeholders Agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2025-04-17 | 2025-04-17 | 0 | 0 | 0 | 0% | 84 | Not Started
ER6701LT | W228 | W228.4600 | HYA Enhanced Defueling Safety Case |  | 2025-04-01 | INA Agree NSRS | 2025-04-17 | 2025-04-17 | 0 | 0 | 0 | 0% | 84 | Not Started
ER6698LT | W224 | W224.3970 | HRA Enhanced Defueling Safety Case | 2025-04-22 | 2025-06-25 | Manufacture of Handling Equipment | 2025-04-22 | 2025-06-25 | 45 | 45 | 45 | 0% | 38 | Not Started
ER6701LT | W228 | W228.3970 | HYA Enhanced Defueling Safety Case | 2025-04-22 | 2025-06-25 | Manufacture of Handling Equipment | 2025-04-22 | 2025-06-25 | 45 | 45 | 45 | 0% | 38 | Not Started
ER6698LT | W224 | W224.4100 | HRA Enhanced Defueling Safety Case | 2025-04-22 | 2025-04-25 | Categorisation by RE / Station | 2025-04-22 | 2025-04-25 | 4 | 4 | 4 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4100 | HYA Enhanced Defueling Safety Case | 2025-04-22 | 2025-04-25 | Categorisation by RE / Station | 2025-04-22 | 2025-04-25 | 4 | 4 | 4 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4610 | HYA Enhanced Defueling Safety Case | 2025-04-02 | 2025-04-08 | Consolidate & Issue to Stakeholders & Suppliers Agreed NSRS (as required) | 2025-04-22 | 2025-04-28 | 5 | 5 | 5 | 0% | 84 | Not Started
W232LT | W232 | W232.C2010 | DNB Enhanced Safety Cases |  | 2025-04-22 | <SCOPE CHANGE CN3472><Justification for no fast fracture on FPUs (if required)> - Issue Draft EAN to EDF for Review. | 2025-04-22 | 2025-04-22 | 0 | 0 | 0 | 0% | 35 | Not Started
W232LT | W232 | W232.C2100 | DNB Enhanced Safety Cases |  | 2025-04-22 | <SCOPE CHANGE CN3472><Reduction in DWTS sub-veto setting for FPUs (if required)> - Issue Draft EAN to EDF for Review. | 2025-04-22 | 2025-04-22 | 0 | 0 | 0 | 0% | 45 | Not Started
W232LT | W232 | W232.C2020 | DNB Enhanced Safety Cases | 2025-04-23 | 2025-05-21 | <SCOPE CHANGE CN3472><Justification for no fast fracture on FPUs (if required)> - Draft EAN Reviewed by EDF SQEP | 2025-04-23 | 2025-05-21 | 20 | 20 | 20 | 0% | 35 | Not Started
W232LT | W232 | W232.C2110 | DNB Enhanced Safety Cases | 2025-04-23 | 2025-05-21 | <SCOPE CHANGE CN3472><Reduction in DWTS sub-veto setting for FPUs (if required)> - Draft EAN Reviewed by EDF SQEP | 2025-04-23 | 2025-05-21 | 20 | 20 | 20 | 0% | 45 | Not Started
W230LT | W230 | W230.2090 | HYB Enhanced Defueling Safety Case Strategy | 2024-11-18 | 2024-12-06 | HYB Enhanced Defueling Rate: DA & INA agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2025-04-23 | 2025-05-14 | 15 | 15 | 15 | 0% | 12 | Not Started
W232LT | W232 | W232.C3660 | DNB Enhanced Safety Cases | 2025-04-30 | 2025-04-30 | <SCOPE CHANGE CN3472><Agree strategy for handling of Group 2 shock-loaded units> - Mid Job Brief | 2025-04-23 | 2025-04-23 | 1 | 1 | 1 | 0% | 23 | Not Started
W772LT | W772 | W772LT.A2710 | DNB Pull Harder Safety Case |  |  | <<NEW SCOPE PENDING CN3634><Load Path Assessment Appendix - Fixed DWTS> > - Document Complete and Uploaded to CDMS | 2025-04-23 | 2025-04-29 | 5 | 5 | 5 | 0% | 4 | Not Started
ER6701LT | W228 | W228.5280 | HYA Enhanced Defueling Safety Case | 2025-04-17 | 2025-04-30 | Station Comments on NSRS | 2025-04-23 | 2025-05-02 | 8 | 8 | 8 | 0% | 35 | Not Started
ER6701LT | W228 | W228.5290 | HYA Enhanced Defueling Safety Case | 2025-04-17 | 2025-04-30 | Key Stakeholders (Peer) comments on NSRS (as required) | 2025-04-23 | 2025-05-02 | 8 | 8 | 8 | 0% | 30 | Not Started
W234LT | W234 | W234.2090 | TOR Enhanced Defueling Safety Case Strategy | 2024-11-18 | 2024-12-06 | TOR Enhanced Defueling Rate: DA & INA agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2025-04-23 | 2025-05-14 | 15 | 15 | 15 | 0% | 12 | Not Started
W772LT | W772 | W772LT.A2330 | DNB Pull Harder Safety Case |  | 2025-06-06 | <Load Path Assessment> - EAN Completed | 2025-04-23 | 2025-04-23 | 0 | 0 | 0 | 0% | 8 | Not Started
W772LT | W772 | W772.A1070 | DNB Pull Harder Safety Case |  | 2025-05-21 | Discovery Milestone: Load Path Assessment | 2025-04-23 | 2025-04-23 | 0 | 0 | 0 | 0% | 8 | Not Started
W232LT | W232 | W232.C3670 | DNB Enhanced Safety Cases | 2025-05-01 | 2025-06-06 | <SCOPE CHANGE CN3472><Agree strategy for handling of Group 2 shock-loaded units> - Prepare Draft EAN Part 2 | 2025-04-24 | 2025-05-30 | 25 | 25 | 25 | 0% | 23 | Not Started
ER6698LT | W224 | W224.5280 | HRA Enhanced Defueling Safety Case | 2025-04-17 | 2025-04-30 | Station Comments on NSRS | 2025-04-24 | 2025-05-06 | 8 | 8 | 8 | 0% | 34 | Not Started
ER6698LT | W224 | W224.5290 | HRA Enhanced Defueling Safety Case | 2025-04-17 | 2025-04-30 | Key Stakeholders (Peer) comments on NSRS (as required) | 2025-04-24 | 2025-05-06 | 8 | 8 | 8 | 0% | 29 | Not Started
ER6666LT | W209 | W209.29610 | HYB Essential Defueling Safety Case |  | 2024-07-23 | Discovery Milestone - L4 Meeting Held with Regulators | 24-Apr-25* | 24-Apr-25* | 0 | 0 | 0 | 0% | 51 | Not Started
ER6668LT | W213 | W213.29610 | TOR Essential Defueling Safety Case |  | 2024-07-23 | Discovery Milestone - L4 Meeting Held with Regulators | 24-Apr-25* | 24-Apr-25* | 0 | 0 | 0 | 0% | 51 | Not Started
ER6372LT | W203 | W203.A2340 | HNB Enhanced Defuelling Safety Cases | 2025-05-02 | 2025-05-09 | PRC Paper stakeholder sign off | 2025-04-25 | 2025-05-01 | 5 | 5 | 5 | 0% | 3 | Not Started
ER6698LT | W224 | W224.4110 | HRA Enhanced Defueling Safety Case | 2025-04-28 | 2025-04-29 | INSA agree MF (as required) *(KDM)* | 2025-04-28 | 2025-04-29 | 2 | 2 | 2 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4110 | HYA Enhanced Defueling Safety Case | 2025-04-28 | 2025-04-29 | INSA agree MF (as required) *(KDM)* | 2025-04-28 | 2025-04-29 | 2 | 2 | 2 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4620 | HYA Enhanced Defueling Safety Case | 2025-04-09 | 2025-04-10 | CA to Agree with CO Format of the Safety Case & Produce Agreed Contents Page | 2025-04-29 | 2025-04-30 | 2 | 2 | 2 | 0% | 84 | Not Started
W772LT | W772 | W772LT.A1525 | DNB Pull Harder Safety Case |  | 2025-05-21 | All supporting references Approved and Issued | 2025-04-29 | 2025-04-29 | 0 | 0 | 0 | 0% | 4 | Not Started
W772LT | W772 | W772LT.KDM.PR02 | DNB Pull Harder Safety Case |  | 2025-06-06 | KDM - Safety Case Paper Authoring Complete EC 375698 <DNB Pull Harder SC> (Cat 1 KDM) ==> KDM | 2025-04-29 | 2025-04-29 | 0 | 0 | 0 | 0% | 4 | Not Started
W772LT | W772 | W772LT.A1670 | DNB Pull Harder Safety Case |  | 2025-06-06 | Verification Commenced (T-11) | 2025-04-29 | 2025-04-29 | 0 | 0 | 0 | 0% | 4 | Not Started
W772LT | W772 | W772LT.A2390 | DNB Pull Harder Safety Case |  | 2025-05-21 | All supporting references Approved and Issued | 2025-04-29 | 2025-04-29 | 0 | 0 | 0 | 0% | 4 | Not Started
W772LT | W772 | W772LT.KDM.PR02-1 | DNB Pull Harder Safety Case |  | 2025-06-06 | KDM - Safety Case Paper Authoring Complete EC 375698 <DNB Pull Harder SC> (Cat 1 KDM) ==> KDM | 2025-04-29 | 2025-04-29 | 0 | 0 | 0 | 0% | 4 | Not Started
ER6698LT | W224 | W224.4120 | HRA Enhanced Defueling Safety Case |  | 2025-04-29 | INSA Approval Date Identified | 2025-04-29 | 2025-04-29 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6698LT | W224 | W224.4130 | HRA Enhanced Defueling Safety Case |  | 2025-04-29 | Provide Provisional NSC Date (as required) | 2025-04-29 | 2025-04-29 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4120 | HYA Enhanced Defueling Safety Case |  | 2025-04-29 | INSA Approval Date Identified | 2025-04-29 | 2025-04-29 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4130 | HYA Enhanced Defueling Safety Case |  | 2025-04-29 | Provide Provisional NSC Date (as required) | 2025-04-29 | 2025-04-29 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6701LT | W228 | W228.3150 | HYA Enhanced Defueling Safety Case | 2025-04-28 | 2025-07-08 | Authorship | 2025-04-30 | 2025-07-10 | 50 | 50 | 50 | 0% | 74 | Not Started
W230LT | W230 | W230.2100 | HYB Enhanced Defueling Safety Case Strategy | 2024-11-25 | 2024-12-06 | HYB Enhanced Defueling Rate: Station agree NSRS | 2025-04-30 | 2025-05-14 | 10 | 10 | 10 | 0% | 12 | Not Started
W772LT | W772 | W772LT.A1640 | DNB Pull Harder Safety Case | 2025-06-09 | 2025-06-20 | Prepare and Populate Affected Documents List | 2025-04-30 | 2025-05-14 | 10 | 10 | 10 | 0% | 72 | Not Started
W772LT | W772 | W772LT.A2530 | DNB Pull Harder Safety Case | 2025-06-09 | 2025-06-20 | <Specialist Assessment> Structural Integrity (Material Chemistry & Welding) - Review and Comment | 2025-04-30 | 2025-05-14 | 10 | 10 | 10 | 0% | 8 | Not Started
W772LT | W772 | W772LT.A2540 | DNB Pull Harder Safety Case | 2025-06-09 | 2025-06-20 | <Specialist Assessment> LOLER Inspector - Review and Comment | 2025-04-30 | 2025-05-14 | 10 | 10 | 10 | 0% | 8 | Not Started
ER6701LT | W228 | W224.3890 | HYA Enhanced Defueling Safety Case | 2025-04-28 | 2025-05-12 | Verify Bob Weight & Gripping Sleeve Procurement Specification | 2025-04-30 | 2025-05-14 | 10 | 10 | 10 | 0% | 181 | Not Started
ER6698LT | W224 | W224.4140 | HRA Enhanced Defueling Safety Case | 2025-04-30 | 2025-05-07 | Produce draft NSRS (using BARRIER MODEL) | 2025-04-30 | 2025-05-07 | 5 | 5 | 5 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4140 | HYA Enhanced Defueling Safety Case | 2025-04-30 | 2025-05-07 | Produce draft NSRS (using BARRIER MODEL) | 2025-04-30 | 2025-05-07 | 5 | 5 | 5 | 0% | 20 | Not Started
W234LT | W234 | W234.2100 | TOR Enhanced Defueling Safety Case Strategy | 2024-11-25 | 2024-12-06 | TOR Enhanced Defueling Rate: Station agree NSRS | 2025-04-30 | 2025-05-14 | 10 | 10 | 10 | 0% | 12 | Not Started
W232LT | W232 | W232.C1720 | DNB Enhanced Safety Cases | 2025-04-15 | 2025-04-28 | <SCOPE CHANGE CN3472><FPU Sub-veto fault frequency> - Address Comments from EDF Review | 2025-05-01 | 2025-05-13 | 8 | 8 | 8 | 0% | 56 | Not Started
ER6698LT | W224 | W224.3150 | HRA Enhanced Defueling Safety Case | 2025-04-28 | 2025-07-08 | Authorship | 2025-05-01 | 2025-07-11 | 50 | 50 | 50 | 0% | 73 | Not Started
ER6698LT | W224 | W224.3890 | HRA Enhanced Defueling Safety Case | 2025-04-28 | 2025-05-12 | Verify Bob Weight & Gripping Sleeve Procurement Specification | 2025-05-01 | 2025-05-15 | 10 | 10 | 10 | 0% | 180 | Not Started
ER6701LT | W228 | W228.4630 | HYA Enhanced Defueling Safety Case | 2025-04-11 | 2025-08-06 | Supporting Documentation Updates | 2025-05-01 | 2025-08-22 | 80 | 80 | 80 | 0% | 84 | Not Started
ER6701LT | W228 | W228.4640 | HYA Enhanced Defueling Safety Case | 2025-04-11 | 2025-05-13 | Prepare the Safety Case Proposal (including OPEX Review) | 2025-05-01 | 2025-05-30 | 20 | 20 | 20 | 0% | 84 | Not Started
ER6701LT | W228 | W228.4650 | HYA Enhanced Defueling Safety Case | 2025-04-11 | 2025-04-14 | Produce Verification Plan | 2025-05-01 | 2025-05-02 | 2 | 2 | 2 | 0% | 162 | Not Started
ER6701LT | W228 | W228.5300 | HYA Enhanced Defueling Safety Case |  | 2025-04-30 | INSA Resource Identified | 2025-05-02 | 2025-05-02 | 0 | 0 | 0 | 0% | 30 | Not Started
ER6698LT | W224 | W224.3830 | HRA Enhanced Defueling Safety Case | 2025-05-06 | 2025-06-03 | Author CFD Report | 2025-05-06 | 2025-06-03 | 20 | 20 | 20 | 0% | 36 | Not Started
ER6701LT | W228 | W228.3830 | HYA Enhanced Defueling Safety Case | 2025-05-02 | 2025-06-02 | Author CFD Report | 2025-05-06 | 2025-06-03 | 20 | 20 | 20 | 0% | 36 | Not Started
ER6698LT | W224 | W224.4010 | HRA Enhanced Defueling Safety Case | 2025-05-06 | 2025-06-03 | Author AMP2D Report | 2025-05-06 | 2025-06-03 | 20 | 20 | 20 | 0% | 158 | Not Started
ER6701LT | W228 | W228.4010 | HYA Enhanced Defueling Safety Case | 2025-05-02 | 2025-06-02 | Author AMP2D Report | 2025-05-06 | 2025-06-03 | 20 | 20 | 20 | 0% | 158 | Not Started
ER6701LT | W228 | W228.5310 | HYA Enhanced Defueling Safety Case | 2025-05-01 | 2025-05-08 | INA Comments on NSRS | 2025-05-06 | 2025-05-12 | 5 | 5 | 5 | 0% | 30 | Not Started
ER6698LT | W224 | W224.5300 | HRA Enhanced Defueling Safety Case |  | 2025-04-30 | INSA Resource Identified | 2025-05-06 | 2025-05-06 | 0 | 0 | 0 | 0% | 29 | Not Started
ER6372LT | W203 | W203.A2350 | HNB Enhanced Defuelling Safety Cases |  | 2025-06-11 | Gate D PRC Paper Submission | 2025-05-07 | 2025-05-07 | 0 | 0 | 0 | 0% | 1 | Not Started
ER6698LT | W224 | W224.2470 | HRA Enhanced Defueling Safety Case | 2025-03-28 | 2025-04-04 | Contract Negotiations for Load Trace | 2025-05-07 | 2025-05-14 | 6 | 6 | 6 | 0% | 190 | Not Started
ER6701LT | W228 | W228.2470 | HYA Enhanced Defueling Safety Case | 2025-03-31 | 2025-04-07 | Contract Negotiations for Load Trace | 2025-05-07 | 2025-05-14 | 6 | 6 | 6 | 0% | 190 | Not Started
ER6698LT | W224 | W224.5310 | HRA Enhanced Defueling Safety Case | 2025-05-01 | 2025-05-08 | INA Comments on NSRS | 2025-05-07 | 2025-05-13 | 5 | 5 | 5 | 0% | 29 | Not Started
ER6698LT | W224 | W224.2660 | HRA Enhanced Defueling Safety Case | 2025-04-14 | 2025-04-22 | Contract Negotiations for Trip Functions | 2025-05-08 | 2025-05-14 | 5 | 5 | 5 | 0% | 26 | Not Started
ER6701LT | W228 | W228.2660 | HYA Enhanced Defueling Safety Case | 2025-04-14 | 2025-04-22 | Contract Negotiationsfor Trip Functions | 2025-05-08 | 2025-05-14 | 5 | 5 | 5 | 0% | 26 | Not Started
ER6698LT | W224 | W224.4160 | HRA Enhanced Defueling Safety Case | 2025-05-08 | 2025-05-19 | Station Comments on NSRS | 2025-05-08 | 2025-05-19 | 8 | 8 | 8 | 0% | 25 | Not Started
ER6698LT | W224 | W224.4150 | HRA Enhanced Defueling Safety Case | 2025-05-08 | 2025-05-19 | Key Stakeholders (Peer) comments on NSRS (as required) | 2025-05-08 | 2025-05-19 | 8 | 8 | 8 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4160 | HYA Enhanced Defueling Safety Case | 2025-05-08 | 2025-05-19 | Station comments on NSRS | 2025-05-08 | 2025-05-19 | 8 | 8 | 8 | 0% | 25 | Not Started
ER6701LT | W228 | W228.4150 | HYA Enhanced Defueling Safety Case | 2025-05-08 | 2025-05-19 | Key Stakeholders (Peer) comments on NSRS (as required) | 2025-05-08 | 2025-05-19 | 8 | 8 | 8 | 0% | 20 | Not Started
W772LT | W772 | W772LT.A1320 | DNB Pull Harder Safety Case |  | 2025-06-20 | Issue to CO & Station for comments | 2025-05-08 | 2025-05-08 | 0 | 0 | 0 | 0% | 4 | Not Started
W772LT | W772 | W772LT.A1140 | DNB Pull Harder Safety Case | 2025-06-23 | 2025-07-16 | Incorporate all stakeholder comments | 2025-05-09 | 2025-06-04 | 18 | 18 | 18 | 0% | 4 | Not Started
ER6698LT | W224 | W224.4450 | HRA Enhanced Defueling Safety Case | 2025-05-13 | 2025-05-16 | Produce MF (as required) | 2025-05-13 | 2025-05-16 | 4 | 4 | 4 | 0% | 36 | Not Started
ER6701LT | W228 | W228.5320 | HYA Enhanced Defueling Safety Case | 2025-05-09 | 2025-05-15 | Incorporate INA, Station, ED (peer) Comments | 2025-05-13 | 2025-05-19 | 5 | 5 | 5 | 0% | 30 | Not Started
ER6698LT | W224 | W224.5620 | HRA Enhanced Defueling Safety Case |  |  | Cost Summary - Reduce IFDF Cooling EC 1 | 2025-05-13 | 2025-07-07 | 39 | 39 | 39 | 0% | 36 | Not Started
W232LT | W232 | W232.C1730 | DNB Enhanced Safety Cases |  | 2025-04-28 | <SCOPE CHANGE CN3472><FPU Sub-veto fault frequency> - Issue EAN | 2025-05-13 | 2025-05-13 | 0 | 0 | 0 | 0% | 56 | Not Started
W232LT | W232 | W232.C1740 | DNB Enhanced Safety Cases | 2025-04-29 | 2025-05-06 | <SCOPE CHANGE CN3472><FPU Sub-veto fault frequency> - Updated EAN Reviewed by EDF SQEP | 2025-05-14 | 2025-05-20 | 5 | 5 | 5 | 0% | 56 | Not Started
ER6698LT | W224 | W224.5320 | HRA Enhanced Defueling Safety Case | 2025-05-09 | 2025-05-15 | Incorporate INA, Station, ED (peer) Comments | 2025-05-14 | 2025-05-20 | 5 | 5 | 5 | 0% | 29 | Not Started
W230LT | W230 | W230.1070 | HYB Enhanced Defueling Safety Case Strategy |  | 2024-12-06 | HYB Enhanced Defueling Rate: Station Agree NSRS | 2025-05-14 | 2025-05-14 | 0 | 0 | 0 | 0% | 256 | Not Started
W230LT | W230 | W230.1200 | HYB Enhanced Defueling Safety Case Strategy |  | 2024-12-06 | HYB Enhanced Defueling Rate: Discovery Milestone - NSRS Completion - Proceed with Safety Case (HYB) | 2025-05-14 | 2025-05-14 | 0 | 0 | 0 | 0% | 12 | Not Started
W234LT | W234 | W234.1070 | TOR Enhanced Defueling Safety Case Strategy |  | 2024-12-06 | TOR Enhanced Defueling Rate: Station Agree NSRS | 2025-05-14 | 2025-05-14 | 0 | 0 | 0 | 0% | 256 | Not Started
W234LT | W234 | W234.1200 | TOR Enhanced Defueling Safety Case Strategy |  | 2024-12-06 | TOR Enhanced Defueling Rate: Discovery Milestone - NSRS Completion - Proceed with Safety Case (TOR) | 2025-05-14 | 2025-05-14 | 0 | 0 | 0 | 0% | 12 | Not Started
ER6698LT | W224 | W224.1650 | HRA Enhanced Defueling Safety Case | 2025-05-08 | 2025-05-08 | Test Readiness Review | 2025-05-15 | 2025-05-15 | 1 | 1 | 1 | 0% | 59 | Not Started
ER6698LT | W224 | W224.2480 | HRA Enhanced Defueling Safety Case | 2025-04-07 | 2025-04-11 | Contract Award for Load Trace | 2025-05-15 | 2025-05-21 | 5 | 5 | 5 | 0% | 190 | Not Started
ER6698LT | W224 | W224.2670 | HRA Enhanced Defueling Safety Case | 2025-04-23 | 2025-04-29 | Contract Award for Trip Functions | 2025-05-15 | 2025-05-21 | 5 | 5 | 5 | 0% | 26 | Not Started
ER6701LT | W228 | W228.2670 | HYA Enhanced Defueling Safety Case | 2025-04-23 | 2025-04-29 | Contract Award for Trip Functions | 2025-05-15 | 2025-05-21 | 5 | 5 | 5 | 0% | 26 | Not Started
ER6701LT | W228 | W228.2480 | HYA Enhanced Defueling Safety Case | 2025-04-08 | 2025-04-14 | Contract Award for Load Trace | 2025-05-15 | 2025-05-21 | 5 | 5 | 5 | 0% | 190 | Not Started
ER6701LT | W228 | W228.1650 | HYA Enhanced Defueling Safety Case | 2025-05-08 | 2025-05-08 | Test Readiness Review | 2025-05-15 | 2025-05-15 | 1 | 1 | 1 | 0% | 59 | Not Started
W230LT | W230 | W230.2160 | HYB Enhanced Defueling Safety Case Strategy | 2024-12-09 | 2024-12-13 | HYB Enhanced Defueling Rate: Circulate NSRS for Relevant Stakeholders (A-B Part) | 2025-05-15 | 2025-05-21 | 5 | 5 | 5 | 0% | 12 | Not Started
W772LT | W772 | W772LT.A2610 | DNB Pull Harder Safety Case | 2025-06-23 | 2025-07-04 | <Specialist Assessment> Structural Integrity (Material Chemistry & Welding) - Close Comments | 2025-05-15 | 2025-05-29 | 10 | 10 | 10 | 0% | 8 | Not Started
W772LT | W772 | W772LT.A2620 | DNB Pull Harder Safety Case | 2025-06-23 | 2025-07-04 | <Specialist Assessment> LOLER Inspector - Close Comments | 2025-05-15 | 2025-05-29 | 10 | 10 | 10 | 0% | 8 | Not Started
ER6701LT | W228 | W224.3900 | HYA Enhanced Defueling Safety Case | 2025-05-13 | 2025-06-10 | EDF TR of Bob Weight & Gripping Sleeve Procurement Specification | 2025-05-15 | 2025-06-12 | 20 | 20 | 20 | 0% | 181 | Not Started
ER6701LT | W228 | W228.4830 | HYA Enhanced Defueling Safety Case | 2025-05-08 | 2025-05-13 | Produce MF (as required) | 2025-05-15 | 2025-05-20 | 4 | 4 | 4 | 0% | 0 | Not Started
ER6698LT | W224 | W224.4830 | HRA Enhanced Defueling Safety Case | 2025-05-08 | 2025-05-13 | Produce MF (as required) | 2025-05-15 | 2025-05-20 | 4 | 4 | 4 | 0% | 0 | Not Started
W234LT | W234 | W234.2160 | TOR Enhanced Defueling Safety Case Strategy | 2024-12-09 | 2024-12-13 | TOR Enhanced Defueling Rate: Circulate NSRS for Relevant Stakeholders (A-B Part) | 2025-05-15 | 2025-05-21 | 5 | 5 | 5 | 0% | 12 | Not Started
ER6698LT | W224 | W224.A1610 | HRA Enhanced Defueling Safety Case |  |  | Cost Summary - Load Trace EC 1 | 2025-05-15 | 2026-02-26 | 201 | 201 | 201 | 0% | 0 | Not Started
W232LT | W232 | W232.C2730 | DNB Enhanced Safety Cases | 2025-05-09 | 2025-05-20 | <SCOPE CHANGE CN3472>-<Demonstration of adequate integrity for Grp2 shock-loaded units>-TSA Internal Review of Draft EAN | 2025-05-16 | 2025-05-28 | 8 | 8 | 8 | 0% | 13 | Not Started
ER6698LT | W224 | W224.1660 | HRA Enhanced Defueling Safety Case | 2025-05-09 | 2025-06-09 | PC1/PC2 Document suite updates | 2025-05-16 | 2025-06-16 | 21 | 21 | 21 | 0% | 59 | Not Started
ER6701LT | W228 | W228.1660 | HYA Enhanced Defueling Safety Case | 2025-05-09 | 2025-06-09 | PC1/PC2 Document suite updates | 2025-05-16 | 2025-06-16 | 21 | 21 | 21 | 0% | 59 | Not Started
ER6698LT | W224 | W224.3900 | HRA Enhanced Defueling Safety Case | 2025-05-13 | 2025-06-10 | EDF TR of Bob Weight & Gripping Sleeve Procurement Specification | 2025-05-16 | 2025-06-13 | 20 | 20 | 20 | 0% | 180 | Not Started
ER6698LT | W224 | W224.4460 | HRA Enhanced Defueling Safety Case |  | 2025-05-16 | Issue MF (as required) | 2025-05-16 | 2025-05-16 | 0 | 0 | 0 | 0% | 36 | Not Started
ER6698LT | W224 | W224.4470 | HRA Enhanced Defueling Safety Case | 2025-05-19 | 2025-05-22 | Categorisation by RE / Station | 2025-05-19 | 2025-05-22 | 4 | 4 | 4 | 0% | 36 | Not Started
ER6698LT | W224 | W224.4170 | HRA Enhanced Defueling Safety Case |  | 2025-05-19 | INSA Resource Identified | 2025-05-19 | 2025-05-19 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4170 | HYA Enhanced Defueling Safety Case |  | 2025-05-19 | INSA Resource Identified | 2025-05-19 | 2025-05-19 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6372LT | W203 | W203.A2360 | HNB Enhanced Defuelling Safety Cases | 2025-06-24 | 2025-06-24 | Hold PRC | 2025-05-20 | 2025-05-20 | 1 | 1 | 1 | 0% | 0 | Not Started
W232LT | W232 | W232.C1920 | DNB Enhanced Safety Cases | 2025-06-02 | 2025-06-19 | <SCOPE CHANGE CN3472><FPU Uninspected Welds lifting integrity incl'g sub-veto faults> - TSA Internal Review of Draft EAN | 2025-05-20 | 2025-06-09 | 14 | 14 | 14 | 0% | 5 | Not Started
ER6698LT | W224 | W224.4180 | HRA Enhanced Defueling Safety Case | 2025-05-20 | 2025-05-27 | INA comments on NSRS | 2025-05-20 | 2025-05-27 | 5 | 5 | 5 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4180 | HYA Enhanced Defueling Safety Case | 2025-05-20 | 2025-05-27 | INA comments on NSRS | 2025-05-20 | 2025-05-27 | 5 | 5 | 5 | 0% | 20 | Not Started
ER6701LT | W228 | W228.5330 | HYA Enhanced Defueling Safety Case | 2025-05-16 | 2025-05-16 | Issue Final NSRS | 2025-05-20 | 2025-05-20 | 1 | 1 | 1 | 0% | 30 | Not Started
ER6372LT | W203 | W203.A2370 | HNB Enhanced Defuelling Safety Cases |  | 2025-06-24 | Gate D PRC Paper Approval | 2025-05-20 | 2025-05-20 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6372LT | W203 | W203.A2400 | HNB Enhanced Defuelling Safety Cases |  | 2025-06-24 | Gate D PRC Paper Approval | 2025-05-20 | 2025-05-20 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6372LT | W203 | W203.B2420 | HNB Enhanced Defuelling Safety Cases |  | 2025-06-24 | Project Completion | 2025-05-20 | 2025-05-20 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6701LT | W228 | W228.4840 | HYA Enhanced Defueling Safety Case |  | 2025-05-13 | Issue MF (as required) | 2025-05-20 | 2025-05-20 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6698LT | W224 | W224.4840 | HRA Enhanced Defueling Safety Case |  | 2025-05-13 | Issue MF (as required) | 2025-05-20 | 2025-05-20 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6701LT | W228 | W228.5340 | HYA Enhanced Defueling Safety Case |  | 2025-05-16 | Station Agree NSRS *(KDM)* | 2025-05-20 | 2025-05-20 | 0 | 0 | 0 | 0% | 30 | Not Started
ER6701LT | W228 | W228.5350 | HYA Enhanced Defueling Safety Case |  | 2025-05-16 | Key Stakeholders Agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2025-05-20 | 2025-05-20 | 0 | 0 | 0 | 0% | 30 | Not Started
ER6701LT | W228 | W228.5360 | HYA Enhanced Defueling Safety Case |  | 2025-05-16 | INA Agree NSRS | 2025-05-20 | 2025-05-20 | 0 | 0 | 0 | 0% | 30 | Not Started
W232LT | W232 | W232.C1750 | DNB Enhanced Safety Cases | 2025-05-07 | 2025-05-12 | <SCOPE CHANGE CN3472><FPU Sub-veto fault frequency> - Address Comments from EDF Review | 2025-05-21 | 2025-05-27 | 4 | 4 | 4 | 0% | 72 | Not Started
ER6701LT | W228 | W228.4850 | HYA Enhanced Defueling Safety Case | 2025-05-14 | 2025-05-19 | Categorisation by RE / Station | 2025-05-21 | 2025-05-27 | 4 | 4 | 4 | 0% | 0 | Not Started
ER6698LT | W224 | W224.4850 | HRA Enhanced Defueling Safety Case | 2025-05-14 | 2025-05-19 | Categorisation by RE / Station | 2025-05-21 | 2025-05-27 | 4 | 4 | 4 | 0% | 0 | Not Started
ER6698LT | W224 | W224.5330 | HRA Enhanced Defueling Safety Case | 2025-05-16 | 2025-05-16 | Issue Final NSRS | 2025-05-21 | 2025-05-21 | 1 | 1 | 1 | 0% | 29 | Not Started
ER6701LT | W228 | W228.5370 | HYA Enhanced Defueling Safety Case | 2025-05-19 | 2025-05-23 | Consolidate & Issue to Stakeholders & Suppliers Agreed NSRS (as required) | 2025-05-21 | 2025-05-28 | 5 | 5 | 5 | 0% | 30 | Not Started
ER6701LT | W228 | W228.A1610 | HYA Enhanced Defueling Safety Case |  |  | Cost Summary - Load Trace EC 1 | 2025-05-21 | 2025-07-02 | 30 | 30 | 30 | 0% | 0 | Not Started
ER6698LT | W224 | W224.5340 | HRA Enhanced Defueling Safety Case |  | 2025-05-16 | Station Agree NSRS *(KDM)* | 2025-05-21 | 2025-05-21 | 0 | 0 | 0 | 0% | 29 | Not Started
ER6698LT | W224 | W224.5350 | HRA Enhanced Defueling Safety Case |  | 2025-05-16 | Key Stakeholders Agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2025-05-21 | 2025-05-21 | 0 | 0 | 0 | 0% | 29 | Not Started
ER6698LT | W224 | W224.5360 | HRA Enhanced Defueling Safety Case |  | 2025-05-16 | INA Agree NSRS | 2025-05-21 | 2025-05-21 | 0 | 0 | 0 | 0% | 29 | Not Started
W232LT | W232 | W232.C2030 | DNB Enhanced Safety Cases | 2025-05-22 | 2025-06-05 | <SCOPE CHANGE CN3472><Justification for no fast fracture on FPUs (if required)> - Address Comments from EDF Review on Dr | 2025-05-22 | 2025-06-05 | 10 | 10 | 10 | 0% | 35 | Not Started
W232LT | W232 | W232.C2120 | DNB Enhanced Safety Cases | 2025-05-22 | 2025-06-05 | <SCOPE CHANGE CN3472><Reduction in DWTS sub-veto setting for FPUs (if required)> - Address Comments from EDF Review on D | 2025-05-22 | 2025-06-05 | 10 | 10 | 10 | 0% | 45 | Not Started
ER6698LT | W224 | W224.2680 | HRA Enhanced Defueling Safety Case | 2025-04-30 | 2025-05-14 | Inaugural Meeting/PJB for Trip Functions | 2025-05-22 | 2025-06-05 | 10 | 10 | 10 | 0% | 26 | Not Started
ER6701LT | W228 | W228.2680 | HYA Enhanced Defueling Safety Case | 2025-04-30 | 2025-05-14 | Inaugural meeting/PJB for Trip Functions | 2025-05-22 | 2025-06-05 | 10 | 10 | 10 | 0% | 26 | Not Started
W230LT | W230 | W230.2180 | HYB Enhanced Defueling Safety Case Strategy | 2024-12-16 | 2024-12-16 | HYB Enhanced Defueling Rate: Send NSRS to ONR to Determine Level of Review Required (Acknowledgement or Agreement) | 2025-05-22 | 2025-05-22 | 1 | 1 | 1 | 0% | 12 | Not Started
W232LT | W232 | W232.C3450 | DNB Enhanced Safety Cases | 2025-04-15 | 2025-04-29 | <Agree approach to OEM NSP replacement> - TSA Internal Review of Draft EAN | 2025-05-22 | 2025-06-04 | 9 | 9 | 9 | 0% | 8 | Not Started
ER6698LT | W224 | W224.5370 | HRA Enhanced Defueling Safety Case | 2025-05-19 | 2025-05-23 | Consolidate & Issue to Stakeholders & Suppliers Agreed NSRS (as required) | 2025-05-22 | 2025-05-29 | 5 | 5 | 5 | 0% | 29 | Not Started
W234LT | W234 | W234.2180 | TOR Enhanced Defueling Safety Case Strategy | 2024-12-16 | 2024-12-16 | TOR Enhanced Defueling Rate: Send NSRS to ONR to Determine Level of Review Required (Acknowledgement or Agreement) | 2025-05-22 | 2025-05-22 | 1 | 1 | 1 | 0% | 12 | Not Started
W230LT | W230 | W230.2200 | HYB Enhanced Defueling Safety Case Strategy | 2024-12-17 | 2025-01-16 | HYB Enhanced Defueling Rate: Outline Safety Case / ALARP Strategy | 2025-05-23 | 2025-06-20 | 20 | 20 | 20 | 0% | 12 | Not Started
W230LT | W230 | W230.2220 | HYB Enhanced Defueling Safety Case Strategy | 2024-12-17 | 2024-12-19 | HYB Enhanced Defueling Rate: Lessons Learned Activity - NSRS Approval | 2025-05-23 | 2025-05-28 | 3 | 3 | 3 | 0% | 247 | Not Started
W232LT | W232 | W232.C3260 | DNB Enhanced Safety Cases | 2025-05-15 | 2025-05-28 | <SCOPE NAME CHANGE CN3472><FPU and ESA Handling with OEM NSPs> - TSA Internal Review of Draft EAN | 2025-05-23 | 2025-06-05 | 9 | 9 | 9 | 0% | 6 | Not Started
ER6698LT | W224 | W224.4480 | HRA Enhanced Defueling Safety Case | 2025-05-23 | 2025-05-27 | INSA Agree MF (as required) *(KDM)* | 2025-05-23 | 2025-05-27 | 2 | 2 | 2 | 0% | 36 | Not Started
W234LT | W234 | W234.2200 | TOR Enhanced Defueling Safety Case Strategy | 2024-12-17 | 2025-01-16 | TOR Enhanced Defueling Rate: Outline Safety Case / ALARP Strategy | 2025-05-23 | 2025-06-20 | 20 | 20 | 20 | 0% | 12 | Not Started
W234LT | W234 | W234.2220 | TOR Enhanced Defueling Safety Case Strategy | 2024-12-17 | 2024-12-19 | TOR Enhanced Defueling Rate: Lessons Learned Activity - NSRS Approval | 2025-05-23 | 2025-05-28 | 3 | 3 | 3 | 0% | 247 | Not Started
W232LT | W232 | W232.C2330 | DNB Enhanced Safety Cases | 2025-04-09 | 2025-04-15 | <SCOPE NAME CHANGE CN3472>Confirm measures to mitigate for non-engineered load path (vis inspect) - Prepare Draft EAN | 2025-05-27 | 2025-06-02 | 5 | 5 | 5 | 0% | 8 | Not Started
W232LT | W232 | W232.C1760 | DNB Enhanced Safety Cases |  | 2025-05-12 | <SCOPE CHANGE CN3472><FPU Sub-veto fault frequency> - Issue Final EAN | 2025-05-27 | 2025-05-27 | 0 | 0 | 0 | 0% | 72 | Not Started
ER6698LT | W224 | W224.4490 | HRA Enhanced Defueling Safety Case |  | 2025-05-27 | INSA Approval Date Identified | 2025-05-27 | 2025-05-27 | 0 | 0 | 0 | 0% | 36 | Not Started
ER6698LT | W224 | W224.4500 | HRA Enhanced Defueling Safety Case |  | 2025-05-27 | Provide Provisional NSC Date (as required) | 2025-05-27 | 2025-05-27 | 0 | 0 | 0 | 0% | 36 | Not Started
W232LT | W232 | W232.C2070 | DNB Enhanced Safety Cases | 2025-05-13 | 2025-05-19 | <SCOPE CHANGE CN3472><FPU Sub-veto fault frequency> - EAN Completed and Uploaded to CDMS | 2025-05-28 | 2025-06-03 | 5 | 5 | 5 | 0% | 72 | Not Started
ER6698LT | W224 | W224.4190 | HRA Enhanced Defueling Safety Case | 2025-05-28 | 2025-06-03 | Incorporate INA, Station, ED (peer) comments | 2025-05-28 | 2025-06-03 | 5 | 5 | 5 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4190 | HYA Enhanced Defueling Safety Case | 2025-05-28 | 2025-06-03 | Incorporate INA, Station, ED (peer) comments | 2025-05-28 | 2025-06-03 | 5 | 5 | 5 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4860 | HYA Enhanced Defueling Safety Case | 2025-05-20 | 2025-05-21 | INSA agree MF (as required) *(KDM)* | 2025-05-28 | 2025-05-29 | 2 | 2 | 2 | 0% | 0 | Not Started
ER6698LT | W224 | W224.4510 | HRA Enhanced Defueling Safety Case | 2025-05-28 | 2025-06-03 | Produce Draft NSRS (using BARRIER MODEL) | 2025-05-28 | 2025-06-03 | 5 | 5 | 5 | 0% | 36 | Not Started
ER6698LT | W224 | W224.4860 | HRA Enhanced Defueling Safety Case | 2025-05-20 | 2025-05-21 | INSA Agree MF (as required) *(KDM)* | 2025-05-28 | 2025-05-29 | 2 | 2 | 2 | 0% | 0 | Not Started
W232LT | W232 | W232.C2670 | DNB Enhanced Safety Cases |  | 2025-05-20 | <SCOPE CHANGE CN3472>-<Demonstration of adequate integrity for Grp2 shock-loaded units> - Issue Draft EAN to EDF for | 2025-05-28 | 2025-05-28 | 0 | 0 | 0 | 0% | 13 | Not Started
W230LT | W230 | W230.1220 | HYB Enhanced Defueling Safety Case Strategy |  | 2024-12-19 | HYB Enhanced Defueling Rate: Lessons Learned Milestone - NSRS Approval | 2025-05-28 | 2025-05-28 | 0 | 0 | 0 | 0% | 247 | Not Started
W234LT | W234 | W234.1220 | TOR Enhanced Defueling Safety Case Strategy |  | 2024-12-19 | TOR Enhanced Defueling Rate: Lessons Learned Milestone - NSRS Approval | 2025-05-28 | 2025-05-28 | 0 | 0 | 0 | 0% | 247 | Not Started
W232LT | W232 | W232.C2680 | DNB Enhanced Safety Cases | 2025-05-21 | 2025-06-17 | <SCOPE CHANGE CN3472>-<Demonstration of adequate integrity for Grp2 shock-loaded units> - Draft EAN Reviewed by EDF S | 2025-05-29 | 2025-06-24 | 19 | 19 | 19 | 0% | 13 | Not Started
ER6701LT | W228 | W228.A1150 | HYA Enhanced Defueling Safety Case | 2025-02-13 | 2025-10-16 | Cost Summary - Bob Weight & Gripping Sleeve EC 2 | 2025-05-29 | 2026-01-15 | 162 | 162 | 162 | 0% | 30 | Not Started
W232LT | W232 | W232.C3370 | DNB Enhanced Safety Cases | 2025-03-19 | 2025-04-01 | <SCOPE CHANGE CN3472><NSP Pin Failure> - TSA Internal Review of Draft EAN | 2025-05-29 | 2025-06-11 | 10 | 10 | 10 | 0% | 5 | Not Started
ER6701LT | W228 | W228.5380 | HYA Enhanced Defueling Safety Case | 2025-05-27 | 2025-05-28 | CA to Agree with CO format of the Safety Case & Produce Agreed Contents Page | 2025-05-29 | 2025-05-30 | 2 | 2 | 2 | 0% | 30 | Not Started
ER6701LT | W228 | W228.4870 | HYA Enhanced Defueling Safety Case |  | 2025-05-21 | INSA Approval Date Identified | 2025-05-29 | 2025-05-29 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6701LT | W228 | W228.4880 | HYA Enhanced Defueling Safety Case |  | 2025-05-21 | Provide Provisional NSC Date (as required) | 2025-05-29 | 2025-05-29 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6698LT | W224 | W224.4870 | HRA Enhanced Defueling Safety Case |  | 2025-05-21 | INSA Approval Date Identified | 2025-05-29 | 2025-05-29 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6698LT | W224 | W224.4880 | HRA Enhanced Defueling Safety Case |  | 2025-05-21 | Provide Provisional NSC Date (as required) | 2025-05-29 | 2025-05-29 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6698LT | W224 | W224.A1150 | HRA Enhanced Defueling Safety Case | 2025-02-13 | 2025-10-16 | Cost Summary - Bob Weight & Gripping Sleeve EC 2 | 2025-05-30 | 2026-01-16 | 162 | 162 | 162 | 0% | 29 | Not Started
ER6698LT | W224 | W224.2490 | HRA Enhanced Defueling Safety Case | 2025-04-23 | 2025-04-23 | Inaugural meeting/PJB for Load Trace | 2025-05-30 | 2025-05-30 | 1 | 1 | 1 | 0% | 190 | Not Started
ER6701LT | W228 | W228.2490 | HYA Enhanced Defueling Safety Case | 2025-04-24 | 2025-04-24 | Inaugural meeting/PJB for Load Trace | 2025-05-30 | 2025-05-30 | 1 | 1 | 1 | 0% | 190 | Not Started
ER6698LT | W224 | W224.4890 | HRA Enhanced Defueling Safety Case | 2025-05-22 | 2025-05-29 | Produce Draft NSRS (using BARRIER MODEL) | 2025-05-30 | 2025-06-05 | 5 | 5 | 5 | 0% | 0 | Not Started
ER6698LT | W224 | W224.5380 | HRA Enhanced Defueling Safety Case | 2025-05-27 | 2025-05-28 | CA to Agree with CO format of the Safety Case & Produce Agreed Contents Page | 2025-05-30 | 2025-06-02 | 2 | 2 | 2 | 0% | 29 | Not Started
ER6701LT | W228 | W228.4890 | HYA Enhanced Defueling Safety Case | 2025-05-22 | 2025-05-29 | Produce Draft NSRS (using BARRIER MODEL) | 2025-05-30 | 2025-06-05 | 5 | 5 | 5 | 0% | 0 | Not Started
W232LT | W232 | W232.C3490 | DNB Enhanced Safety Cases | 2025-06-09 | 2025-06-18 | <SCOPE CHANGE CN3472>-<Agree strategy for handling of Group 2 shock-loaded units> - TSA Internal Review of Draft EAN | 2025-06-02 | 2025-06-11 | 8 | 8 | 8 | 0% | 23 | Not Started
ER6701LT | W228 | W228.4660 | HYA Enhanced Defueling Safety Case | 2025-05-14 | 2025-06-25 | Specialist Assessment | 2025-06-02 | 2025-07-11 | 30 | 30 | 30 | 0% | 132 | Not Started
ER6701LT | W228 | W228.5390 | HYA Enhanced Defueling Safety Case | 2025-05-29 | 2025-10-29 | Supporting Documentation Updates | 2025-06-02 | 2025-10-31 | 109 | 109 | 109 | 0% | 30 | Not Started
ER6701LT | W228 | W228.5400 | HYA Enhanced Defueling Safety Case | 2025-05-29 | 2025-07-09 | Prepare the Safety Case Proposal (including OPEX Review) | 2025-06-02 | 2025-07-11 | 30 | 30 | 30 | 0% | 30 | Not Started
ER6701LT | W228 | W228.5410 | HYA Enhanced Defueling Safety Case | 2025-05-29 | 2025-05-30 | Produce Verification Plan | 2025-06-02 | 2025-06-03 | 2 | 2 | 2 | 0% | 137 | Not Started
W232LT | W232 | W232.C2400 | DNB Enhanced Safety Cases | 2025-04-16 | 2025-05-01 | <S N C CN3472>Confirm measures to mitigate for non-engineered load path (vis inspect) - TSA Internal Review of Draft EAN | 2025-06-03 | 2025-06-16 | 10 | 10 | 10 | 0% | 8 | Not Started
ER6698LT | W224 | W224.5390 | HRA Enhanced Defueling Safety Case | 2025-05-29 | 2025-10-29 | Supporting Documentation Updates | 2025-06-03 | 2025-11-03 | 109 | 109 | 109 | 0% | 29 | Not Started
ER6698LT | W224 | W224.5400 | HRA Enhanced Defueling Safety Case | 2025-05-29 | 2025-07-09 | Prepare the Safety Case Proposal (including OPEX Review) | 2025-06-03 | 2025-07-14 | 30 | 30 | 30 | 0% | 29 | Not Started
ER6698LT | W224 | W224.5410 | HRA Enhanced Defueling Safety Case | 2025-05-29 | 2025-05-30 | Produce Verification Plan | 2025-06-03 | 2025-06-04 | 2 | 2 | 2 | 0% | 136 | Not Started
W232LT | W232 | W232.C2310 | DNB Enhanced Safety Cases |  | 2025-05-19 | <SCOPE CHANGE CN3472><FPU Sub-veto fault frequency> - EAN Completed | 2025-06-03 | 2025-06-03 | 0 | 0 | 0 | 0% | 72 | Not Started
ER6698LT | W224 | W224.3840 | HRA Enhanced Defueling Safety Case | 2025-06-04 | 2025-06-17 | Verify CFD Report | 2025-06-04 | 2025-06-17 | 10 | 10 | 10 | 0% | 36 | Not Started
ER6701LT | W228 | W228.3840 | HYA Enhanced Defueling Safety Case | 2025-06-03 | 2025-06-16 | Verify CFD Report | 2025-06-04 | 2025-06-17 | 10 | 10 | 10 | 0% | 36 | Not Started
ER6698LT | W224 | W224.4020 | HRA Enhanced Defueling Safety Case | 2025-06-04 | 2025-06-17 | Verify AMP2D Report | 2025-06-04 | 2025-06-17 | 10 | 10 | 10 | 0% | 158 | Not Started
ER6701LT | W228 | W228.4020 | HYA Enhanced Defueling Safety Case | 2025-06-03 | 2025-06-16 | Verify AMP2D Report | 2025-06-04 | 2025-06-17 | 10 | 10 | 10 | 0% | 158 | Not Started
ER6698LT | W224 | W224.4200 | HRA Enhanced Defueling Safety Case | 2025-06-04 | 2025-06-04 | Issue Final NSRS | 2025-06-04 | 2025-06-04 | 1 | 1 | 1 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4200 | HYA Enhanced Defueling Safety Case | 2025-06-04 | 2025-06-04 | Issue final NSRS | 2025-06-04 | 2025-06-04 | 1 | 1 | 1 | 0% | 20 | Not Started
ER6698LT | W224 | W224.4520 | HRA Enhanced Defueling Safety Case | 2025-06-04 | 2025-06-13 | Station Comments on NSRS | 2025-06-04 | 2025-06-13 | 8 | 8 | 8 | 0% | 41 | Not Started
ER6698LT | W224 | W224.4530 | HRA Enhanced Defueling Safety Case | 2025-06-04 | 2025-06-13 | Key Stakeholders (Peer) comments on NSRS (as required) | 2025-06-04 | 2025-06-13 | 8 | 8 | 8 | 0% | 36 | Not Started
W232LT | W232 | W232.C2580 | DNB Enhanced Safety Cases |  | 2025-04-29 | <Agree approach to OEM NSP replacement> - Issue Draft EAN to EDF for Review. | 2025-06-04 | 2025-06-04 | 0 | 0 | 0 | 0% | 8 | Not Started
ER6698LT | W224 | W224.4210 | HRA Enhanced Defueling Safety Case |  | 2025-06-04 | Station Agree NSRS *(KDM)* | 2025-06-04 | 2025-06-04 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6698LT | W224 | W224.4230 | HRA Enhanced Defueling Safety Case |  | 2025-06-04 | Key Stakeholders Agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2025-06-04 | 2025-06-04 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6698LT | W224 | W224.4240 | HRA Enhanced Defueling Safety Case |  | 2025-06-04 | INA Agree NSRS | 2025-06-04 | 2025-06-04 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4210 | HYA Enhanced Defueling Safety Case |  | 2025-06-04 | Station agree NSRS *(KDM)* | 2025-06-04 | 2025-06-04 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4230 | HYA Enhanced Defueling Safety Case |  | 2025-06-04 | Key Stakeholders Agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2025-06-04 | 2025-06-04 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4240 | HYA Enhanced Defueling Safety Case |  | 2025-06-04 | INA agree NSRS | 2025-06-04 | 2025-06-04 | 0 | 0 | 0 | 0% | 20 | Not Started
W232LT | W232 | W232.C2590 | DNB Enhanced Safety Cases | 2025-04-30 | 2025-05-28 | <Agree approach to OEM NSP replacement> - Draft EAN Reviewed by EDF SQEP | 2025-06-05 | 2025-07-01 | 19 | 19 | 19 | 0% | 8 | Not Started
W772LT | W772 | W772LT.A1470 | DNB Pull Harder Safety Case | 2025-07-17 | 2025-07-25 | Final Verification ==> KDM | 2025-06-05 | 2025-06-13 | 7 | 7 | 7 | 0% | 4 | Not Started
ER6698LT | W224 | W224.4250 | HRA Enhanced Defueling Safety Case | 2025-06-05 | 2025-06-11 | Consolidate & Issue to Stakeholders & Suppliers Agreed NSRS (as required) | 2025-06-05 | 2025-06-11 | 5 | 5 | 5 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4250 | HYA Enhanced Defueling Safety Case | 2025-06-05 | 2025-06-11 | Consolidate & issue to stakeholders & suppliers agreed NSRS (as required) | 2025-06-05 | 2025-06-11 | 5 | 5 | 5 | 0% | 20 | Not Started
W232LT | W232 | W232.C2130 | DNB Enhanced Safety Cases |  | 2025-06-05 | <SCOPE CHANGE CN3472><Reduction in DWTS sub-veto setting for FPUs (if required)> - Issue Final EAN | 2025-06-05 | 2025-06-05 | 0 | 0 | 0 | 0% | 65 | Not Started
W232LT | W232 | W232.C2250 | DNB Enhanced Safety Cases |  | 2025-05-28 | <SCOPE NAME CHANGE CN3472><FPU and ESA Handling with OEM NSPs> - Issue Draft EAN to EDF for Review. | 2025-06-05 | 2025-06-05 | 0 | 0 | 0 | 0% | 6 | Not Started
W232LT | W232 | W232.C3230 | DNB Enhanced Safety Cases |  | 2025-06-05 | <SCOPE CHANGE CN3472> <Justification for no fast fracture on FPUs (if required)> - Issue EAN | 2025-06-05 | 2025-06-05 | 0 | 0 | 0 | 0% | 35 | Not Started
W232LT | W232 | W232.C2140 | DNB Enhanced Safety Cases | 2025-06-06 | 2025-06-12 | <SCOPE CHANGE CN3472><Reduction in DWTS sub-veto setting for FPUs (if required)> - EAN Completed and Uploaded to CDMS | 2025-06-06 | 2025-06-12 | 5 | 5 | 5 | 0% | 65 | Not Started
W232LT | W232 | W232.C2260 | DNB Enhanced Safety Cases | 2025-05-29 | 2025-06-24 | <SCOPE NAME CHANGE CN3472><FPU and ESA Handling with OEM NSPs> - Draft EAN Reviewed by EDF SQEP | 2025-06-06 | 2025-07-02 | 19 | 19 | 19 | 0% | 6 | Not Started
ER6698LT | W224 | W224.2800 | HRA Enhanced Defueling Safety Case | 2025-05-15 | 2025-06-26 | Design and Substantiation (including drawing and relevant analysis) | 2025-06-06 | 2025-07-17 | 30 | 30 | 30 | 0% | 26 | Not Started
ER6701LT | W228 | W228.2800 | HYA Enhanced Defueling Safety Case | 2025-05-15 | 2025-06-26 | Design and Substantiation (including drawing and relevant analysis) | 2025-06-06 | 2025-07-17 | 30 | 30 | 30 | 0% | 26 | Not Started
W232LT | W232 | W232.C3240 | DNB Enhanced Safety Cases | 2025-06-06 | 2025-06-12 | <SCOPE CHANGE CN3472> <Justification for no fast fracture on FPUs (if required)> - Updated EAN Reviewed by EDF SQEP | 2025-06-06 | 2025-06-12 | 5 | 5 | 5 | 0% | 35 | Not Started
ER6698LT | W224 | W224.4900 | HRA Enhanced Defueling Safety Case | 2025-05-30 | 2025-06-10 | Station Comments on NSRS | 2025-06-06 | 2025-06-17 | 8 | 8 | 8 | 0% | 5 | Not Started
ER6698LT | W224 | W224.4910 | HRA Enhanced Defueling Safety Case | 2025-05-30 | 2025-06-10 | Key Stakeholders (Peer) Comments on NSRS (as required) | 2025-06-06 | 2025-06-17 | 8 | 8 | 8 | 0% | 0 | Not Started
ER6701LT | W228 | W228.4900 | HYA Enhanced Defueling Safety Case | 2025-05-30 | 2025-06-10 | Station Comments on NSRS | 2025-06-06 | 2025-06-17 | 8 | 8 | 8 | 0% | 5 | Not Started
ER6701LT | W228 | W228.4910 | HYA Enhanced Defueling Safety Case | 2025-05-30 | 2025-06-10 | Key Stakeholders (Peer) Comments on NSRS (as required) | 2025-06-06 | 2025-06-17 | 8 | 8 | 8 | 0% | 0 | Not Started
W232LT | W232 | W232.C1860 | DNB Enhanced Safety Cases |  | 2025-06-19 | <SCOPE CHANGE CN3472><FPU Uninspected Welds lifting integrity (incl'g sub-veto faults)-Issue Draft EAN to EDF for Review | 2025-06-09 | 2025-06-09 | 0 | 0 | 0 | 0% | 5 | Not Started
W232LT | W232 | W232.C1870 | DNB Enhanced Safety Cases | 2025-06-20 | 2025-07-29 | <SCOPE CHANGE CN3472><FPU Uninspected Welds lifting integrity (including sub-veto faults)> - Draft EAN Reviewed by EDF | 2025-06-10 | 2025-07-17 | 28 | 28 | 28 | 0% | 5 | Not Started
W232LT | W232 | W232.C2490 | DNB Enhanced Safety Cases |  | 2025-04-01 | <SCOPE CHANGE CN3472><NSP Pin Failure> - Issue Draft EAN to EDF for Review. | 2025-06-11 | 2025-06-11 | 0 | 0 | 0 | 0% | 5 | Not Started
W232LT | W232 | W232.C2820 | DNB Enhanced Safety Cases |  | 2025-06-18 | <SCOPE CHANGE CN3472>-<Agree strategy for handling of Group 2 shock-loaded units> - Issue Draft EAN to EDF for Review. | 2025-06-11 | 2025-06-11 | 0 | 0 | 0 | 0% | 23 | Not Started
ER6698LT | W224 | W224.A1210 | HRA Enhanced Defueling Safety Case | 2025-02-17 | 2025-10-07 | Cost Summary - Trip Functions EC 2 | 2025-06-12 | 2026-01-29 | 162 | 162 | 162 | 0% | 20 | Not Started
W232LT | W232 | W232.C2500 | DNB Enhanced Safety Cases | 2025-04-02 | 2025-04-28 | <SCOPE CHANGE CN3472><NSP Pin Failure> - Draft EAN Reviewed by EDF SQEP | 2025-06-12 | 2025-07-04 | 17 | 17 | 17 | 0% | 5 | Not Started
W232LT | W232 | W232.C2830 | DNB Enhanced Safety Cases | 2025-06-19 | 2025-07-15 | <SCOPE CHANGE CN3472>-<Agree strategy for handling of Group 2 shock-loaded units> - Draft EAN Reviewed by EDF SQEP | 2025-06-12 | 2025-07-08 | 19 | 19 | 19 | 0% | 23 | Not Started
ER6701LT | W228 | W228.A1210 | HYA Enhanced Defueling Safety Case | 2025-02-17 | 2025-10-07 | Cost Summary - Trip Function EC 2 | 2025-06-12 | 2026-01-29 | 162 | 162 | 162 | 0% | 20 | Not Started
ER6698LT | W224 | W224.4260 | HRA Enhanced Defueling Safety Case | 2025-06-12 | 2025-06-13 | CA to Agree with CO Format of the Safety Case & Produce Agreed Contents Page | 2025-06-12 | 2025-06-13 | 2 | 2 | 2 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4260 | HYA Enhanced Defueling Safety Case | 2025-06-12 | 2025-06-13 | CA to Agree with CO Format of the Safety Case & Produce Agreed Contents Page | 2025-06-12 | 2025-06-13 | 2 | 2 | 2 | 0% | 20 | Not Started
W232LT | W232 | W232.C2150 | DNB Enhanced Safety Cases |  | 2025-06-12 | <SCOPE CHANGE CN3472><Reduction in DWTS sub-veto setting for FPUs (if required)> - EAN Completed | 2025-06-12 | 2025-06-12 | 0 | 0 | 0 | 0% | 65 | Not Started
W232LT | W232 | W232.C3250 | DNB Enhanced Safety Cases | 2025-06-13 | 2025-06-19 | <SCOPE CHANGE CN3472> <Justification for no fast fracture on FPUs (if required)> - Address Comments from EDF Review | 2025-06-13 | 2025-06-19 | 5 | 5 | 5 | 0% | 35 | Not Started
W772LT | W772 | W772LT.KDM.PR03 | DNB Pull Harder Safety Case |  | 2025-07-25 | KDM - Verification Complete/ Verified Draft A Issued for INSA (T-7) EC 375698 <DNB Pull Harder SC> ==> KDM | 2025-06-13 | 2025-06-13 | 0 | 0 | 0 | 0% | 4 | Not Started
W772LT | W772 | W772LT.A1270 | DNB Pull Harder Safety Case |  | 2025-07-25 | Submit for approval - Categoriser ratifies; RE/CO endorsement ==> KDM | 2025-06-13 | 2025-06-13 | 0 | 0 | 0 | 0% | 4 | Not Started
W772LT | W772 | W772LT.KDM.PR03-1 | DNB Pull Harder Safety Case |  | 2025-07-25 | KDM - Verification Complete/ Verified Draft A Issued for INSA (T-7) EC 375698 <DNB Pull Harder SC> ==> KDM | 2025-06-13 | 2025-06-13 | 0 | 0 | 0 | 0% | 4 | Not Started
ER6698LT | W224 | W224.4540 | HRA Enhanced Defueling Safety Case |  | 2025-06-13 | INSA Resource Identified | 2025-06-13 | 2025-06-13 | 0 | 0 | 0 | 0% | 36 | Not Started
W772LT | W772 | W772LT.A1180 | DNB Pull Harder Safety Case | 2025-07-28 | 2025-08-15 | INSA review & iteration of comments (using BARRIER MODEL) | 2025-06-16 | 2025-07-04 | 15 | 15 | 15 | 0% | 4 | Not Started
ER6698LT | W224 | W224.4070 | HRA Enhanced Defueling Safety Case | 2025-06-16 | 2025-11-14 | Supporting Documentation Updates | 2025-06-16 | 2025-11-14 | 109 | 109 | 109 | 0% | 20 | Not Started
ER6698LT | W224 | W224.4280 | HRA Enhanced Defueling Safety Case | 2025-06-16 | 2025-07-25 | Prepare the Safety Case Proposal (including OPEX Review) | 2025-06-16 | 2025-07-25 | 30 | 30 | 30 | 0% | 20 | Not Started
ER6698LT | W224 | W224.4270 | HRA Enhanced Defueling Safety Case | 2025-06-16 | 2025-06-17 | Produce Verification Plan | 2025-06-16 | 2025-06-17 | 2 | 2 | 2 | 0% | 127 | Not Started
ER6698LT | W224 | W224.4550 | HRA Enhanced Defueling Safety Case | 2025-06-16 | 2025-06-20 | INA Comments on NSRS | 2025-06-16 | 2025-06-20 | 5 | 5 | 5 | 0% | 36 | Not Started
ER6701LT | W228 | W228.4070 | HYA Enhanced Defueling Safety Case | 2025-06-16 | 2025-11-14 | Supporting Documentation Updates | 2025-06-16 | 2025-11-14 | 109 | 109 | 109 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4280 | HYA Enhanced Defueling Safety Case | 2025-06-16 | 2025-07-25 | Prepare the Safety Case Proposal (including OPEX Review) | 2025-06-16 | 2025-07-25 | 30 | 30 | 30 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4270 | HYA Enhanced Defueling Safety Case | 2025-06-16 | 2025-06-17 | Produce Verification Plan | 2025-06-16 | 2025-06-17 | 2 | 2 | 2 | 0% | 127 | Not Started
W232LT | W232 | W232.C2340 | DNB Enhanced Safety Cases |  | 2025-05-01 | <SNC CN3472>Confirm measures to mitigate for non-engineered load path (vis inspect) - Issue Draft EAN to EDF for Review. | 2025-06-16 | 2025-06-16 | 0 | 0 | 0 | 0% | 8 | Not Started
W232LT | W232 | W232.C2350 | DNB Enhanced Safety Cases | 2025-05-02 | 2025-05-16 | <S N C CN3472>Confirm measures to mitigate for non-engineered load path (vis inspect) - Draft EAN Reviewed by EDF SQEP | 2025-06-17 | 2025-06-30 | 10 | 10 | 10 | 0% | 8 | Not Started
ER6698LT | W224 | W224.3070 | HRA Enhanced Defueling Safety Case | 2025-06-10 | 2025-07-09 | Authorship | 2025-06-17 | 2025-07-16 | 22 | 22 | 22 | 0% | 59 | Not Started
ER6701LT | W228 | W228.3070 | HYA Enhanced Defueling Safety Case | 2025-06-10 | 2025-07-09 | Authorship | 2025-06-17 | 2025-07-16 | 22 | 22 | 22 | 0% | 59 | Not Started
ER6698LT | W224 | W224.1830 | HRA Enhanced Defueling Safety Case | 2025-06-10 | 2025-07-07 | FAT of Software Updates | 2025-06-17 | 2025-07-14 | 20 | 20 | 20 | 0% | 98 | Not Started
ER6701LT | W228 | W228.1830 | HYA Enhanced Defueling Safety Case | 2025-06-10 | 2025-07-07 | FAT of Software Updates | 2025-06-17 | 2025-07-14 | 20 | 20 | 20 | 0% | 98 | Not Started
ER6698LT | W224 | W224.4920 | HRA Enhanced Defueling Safety Case |  | 2025-06-10 | INSA Resource Identified | 2025-06-17 | 2025-06-17 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6701LT | W228 | W228.4920 | HYA Enhanced Defueling Safety Case |  | 2025-06-10 | INSA Resource Identified | 2025-06-17 | 2025-06-17 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6698LT | W224 | W224.3280 | HRA Enhanced Defueling Safety Case | 2025-03-27 | 2026-02-19 | Cost Summary - Overarching CAT 2 EC | 2025-06-18 | 2026-01-07 | 142 | 142 | 142 | 0% | 36 | Not Started
ER6698LT | W224 | W224.3500 | HRA Enhanced Defueling Safety Case | 2025-07-02 | 2025-08-29 | Cost Summary - Principle SC Justification EC | 2025-06-18 | 2026-01-07 | 142 | 142 | 142 | 0% | 36 | Not Started
ER6698LT | W224 | W224.3750 | HRA Enhanced Defueling Safety Case | 2025-06-18 | 2025-09-10 | EC Production | 2025-06-18 | 2025-09-10 | 60 | 60 | 60 | 0% | 36 | Not Started
ER6701LT | W228 | W228.3750 | HYA Enhanced Defueling Safety Case | 2025-06-17 | 2025-09-09 | EC Production | 2025-06-18 | 2025-09-10 | 60 | 60 | 60 | 0% | 36 | Not Started
ER6701LT | W228 | W228.3500 | HYA Enhanced Defueling Safety Case | 2025-07-02 | 2025-08-29 | Cost Summary - Principal Level SC Justification EC | 2025-06-18 | 2026-01-07 | 142 | 142 | 142 | 0% | 36 | Not Started
ER6698LT | W224 | W224.3850 | HRA Enhanced Defueling Safety Case | 2025-06-18 | 2025-07-15 | EDF Technical Review of CFD Report | 2025-06-18 | 2025-07-15 | 20 | 20 | 20 | 0% | 76 | Not Started
ER6701LT | W228 | W228.3850 | HYA Enhanced Defueling Safety Case | 2025-06-17 | 2025-07-15 | EDF Technical Review of CFD Report | 2025-06-18 | 2025-07-16 | 21 | 21 | 21 | 0% | 75 | Not Started
ER6698LT | W224 | W224.4030 | HRA Enhanced Defueling Safety Case | 2025-06-18 | 2025-07-15 | EDF Technical Review of AMP2D Report | 2025-06-18 | 2025-07-15 | 20 | 20 | 20 | 0% | 158 | Not Started
ER6701LT | W228 | W228.4030 | HYA Enhanced Defueling Safety Case | 2025-06-17 | 2025-07-15 | EDF Technical Review of AMP2D Report | 2025-06-18 | 2025-07-15 | 20 | 20 | 20 | 0% | 158 | Not Started
ER6698LT | W224 | W224.4050 | HRA Enhanced Defueling Safety Case | 2025-06-18 | 2025-11-07 | Supporting Documentation Updates | 2025-06-18 | 2025-11-07 | 102 | 102 | 102 | 0% | 36 | Not Started
ER6698LT | W224 | W224.4930 | HRA Enhanced Defueling Safety Case | 2025-06-11 | 2025-06-17 | INA Comments on NSRS | 2025-06-18 | 2025-06-24 | 5 | 5 | 5 | 0% | 0 | Not Started
ER6701LT | W228 | W228.4930 | HYA Enhanced Defueling Safety Case | 2025-06-11 | 2025-06-17 | INA Comments on NSRS | 2025-06-18 | 2025-06-24 | 5 | 5 | 5 | 0% | 0 | Not Started
ER6701LT | W228 | W228.4050 | HYA Enhanced Defueling Safety Case | 2025-06-17 | 2025-11-06 | Supporting Documentation Updates | 2025-06-18 | 2025-11-07 | 102 | 102 | 102 | 0% | 36 | Not Started
W232LT | W232 | W232.C2040 | DNB Enhanced Safety Cases |  | 2025-06-19 | <SCOPE CHANGE CN3472><Justification for no fast fracture on FPUs (if required)> - Issue Final EAN | 2025-06-19 | 2025-06-19 | 0 | 0 | 0 | 0% | 55 | Not Started
W232LT | W232 | W232.C2050 | DNB Enhanced Safety Cases | 2025-06-20 | 2025-06-26 | <SCOPE CHANGE CN3472><Justification for no fast fracture on FPUs (if required)> - EAN Completed and Uploaded to CDMS | 2025-06-20 | 2025-06-26 | 5 | 5 | 5 | 0% | 55 | Not Started
ER6698LT | W224 | W224.2810 | HRA Enhanced Defueling Safety Case | 2025-05-30 | 2025-06-26 | Drawings | 2025-06-20 | 2025-07-17 | 20 | 20 | 20 | 0% | 156 | Not Started
ER6701LT | W228 | W228.2810 | HYA Enhanced Defueling Safety Case | 2025-05-30 | 2025-06-26 | Drawings | 2025-06-20 | 2025-07-17 | 20 | 20 | 20 | 0% | 156 | Not Started
ER6698LT | W224 | W224.2820 | HRA Enhanced Defueling Safety Case | 2025-05-30 | 2025-06-26 | Finalise Procurement Specification for Trip Function | 2025-06-20 | 2025-07-17 | 20 | 20 | 20 | 0% | 26 | Not Started
ER6701LT | W228 | W228.2820 | HYA Enhanced Defueling Safety Case | 2025-05-30 | 2025-06-26 | Finalise Procurement Specification for Trip Function | 2025-06-20 | 2025-07-17 | 20 | 20 | 20 | 0% | 26 | Not Started
W230LT | W230 | W230.1100 | HYB Enhanced Defueling Safety Case Strategy |  | 2025-01-16 | HYB Enhanced Defueling Rate: Optioneering Complete (Outline Safety Case / ALARP Strategy) | 2025-06-20 | 2025-06-20 | 0 | 0 | 0 | 0% | 71 | Not Started
W234LT | W234 | W234.1100 | TOR Enhanced Defueling Safety Case Strategy |  | 2025-01-16 | TOR Enhanced Defueling Rate: Optioneering Complete (Outline Safety Case / ALARP Strategy) | 2025-06-20 | 2025-06-20 | 0 | 0 | 0 | 0% | 71 | Not Started
W230LT | W230 | W230.2500 | HYB Enhanced Defueling Safety Case Strategy | 2024-11-15 | 2025-04-07 | ## HYB Low Decay Heat: A - D Phase Funding - (Cost Summary) ## | 2025-06-23 | 2025-11-07 | 99 | 99 | 99 | 0% | 113 | Not Started
W230LT | W230 | W230.2630 | HYB Enhanced Defueling Safety Case Strategy | 2024-11-15 | 2024-12-02 | HYB Low Decay Heat: Strategy Development & Produce MF EC NNNNN & Obtain Approval | 2025-06-23 | 2025-07-08 | 12 | 12 | 12 | 0% | 12 | Not Started
ER6698LT | W224 | W224.4560 | HRA Enhanced Defueling Safety Case | 2025-06-23 | 2025-06-27 | Incorporate INA, Station, ED (peer) comments | 2025-06-23 | 2025-06-27 | 5 | 5 | 5 | 0% | 36 | Not Started
W234LT | W234 | W234.2500 | TOR Enhanced Defueling Safety Case Strategy | 2024-11-15 | 2025-04-07 | ## TOR Low Decay Heat: A - D Phase Funding - (Cost Summary) ## | 2025-06-23 | 2025-11-07 | 99 | 99 | 99 | 0% | 113 | Not Started
W234LT | W234 | W234.2630 | TOR Enhanced Defueling Safety Case Strategy | 2024-11-15 | 2024-12-02 | TOR Low Decay Heat: Strategy Development & Produce MF EC NNNNN & Obtain Approval | 2025-06-23 | 2025-07-08 | 12 | 12 | 12 | 0% | 12 | Not Started
W232LT | W232 | W232.C2690 | DNB Enhanced Safety Cases | 2025-06-18 | 2025-06-30 | <SCOPE CHANGE CN3472>-<Demonstration of adequate integrity for Grp2 shock-loaded units>- Address Comments from EDF TR | 2025-06-25 | 2025-07-07 | 9 | 9 | 9 | 0% | 13 | Not Started
ER6698LT | W224 | W224.4940 | HRA Enhanced Defueling Safety Case | 2025-06-18 | 2025-06-24 | Incorporate INA, Station, ED (peer) Comments | 2025-06-25 | 2025-07-01 | 5 | 5 | 5 | 0% | 0 | Not Started
ER6701LT | W228 | W228.4940 | HYA Enhanced Defueling Safety Case | 2025-06-18 | 2025-06-24 | Incorporate INA, Station, ED (peer) Comments | 2025-06-25 | 2025-07-01 | 5 | 5 | 5 | 0% | 0 | Not Started
W232LT | W232 | W232.C2060 | DNB Enhanced Safety Cases |  | 2025-06-26 | <SCOPE CHANGE CN3472><Justification for no fast fracture on FPUs (if required)> - EAN Completed | 2025-06-26 | 2025-06-26 | 0 | 0 | 0 | 0% | 55 | Not Started
ER6698LT | W224 | W224.4570 | HRA Enhanced Defueling Safety Case | 2025-06-30 | 2025-06-30 | Issue Final NSRS | 2025-06-30 | 2025-06-30 | 1 | 1 | 1 | 0% | 36 | Not Started
ER6698LT | W224 | W224.4580 | HRA Enhanced Defueling Safety Case |  | 2025-06-30 | Station Agree NSRS *(KDM)* | 2025-06-30 | 2025-06-30 | 0 | 0 | 0 | 0% | 36 | Not Started
ER6698LT | W224 | W224.4590 | HRA Enhanced Defueling Safety Case |  | 2025-06-30 | Key Stakeholders Agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2025-06-30 | 2025-06-30 | 0 | 0 | 0 | 0% | 36 | Not Started
ER6698LT | W224 | W224.4600 | HRA Enhanced Defueling Safety Case |  | 2025-06-30 | INA Agree NSRS | 2025-06-30 | 2025-06-30 | 0 | 0 | 0 | 0% | 36 | Not Started
W232LT | W232 | W232.C2360 | DNB Enhanced Safety Cases | 2025-05-19 | 2025-06-02 | CN3472 Confirm measures to mitigate for non-enginee'd load path(vis inspect)-Address Comments from EDF TR on Draft EAN | 2025-07-01 | 2025-07-14 | 10 | 10 | 10 | 0% | 8 | Not Started
ER6698LT | W224 | W224.4610 | HRA Enhanced Defueling Safety Case | 2025-07-01 | 2025-07-07 | Consolidate & Issue to Stakeholders & Suppliers Agreed NSRS (as required) | 2025-07-01 | 2025-07-07 | 5 | 5 | 5 | 0% | 36 | Not Started
ER6666LT | W209 | W209.29550 | HYB Essential Defueling Safety Case | 2024-09-19 | 2024-10-16 | ONR Assessment Schedule Risk - (Risk Ref 28383) | 2025-07-02 | 2025-07-22 | 15 | 15 | 15 | 0% | 5 | Not Started
ER6668LT | W213 | W213.29550 | TOR Essential Defueling Safety Case | 2024-09-19 | 2024-10-16 | ONR Assessment Schedule Risk - (Risk Ref 28383) | 2025-07-02 | 2025-07-22 | 15 | 15 | 15 | 0% | 5 | Not Started
W232LT | W232 | W232.C2600 | DNB Enhanced Safety Cases | 2025-05-29 | 2025-06-10 | <Agree approach to OEM NSP replacement> - Address Comments from EDF Review on Draft EAN | 2025-07-02 | 2025-07-14 | 9 | 9 | 9 | 0% | 8 | Not Started
ER6698LT | W224 | W224.4950 | HRA Enhanced Defueling Safety Case | 2025-06-25 | 2025-06-25 | Issue Final NSRS | 2025-07-02 | 2025-07-02 | 1 | 1 | 1 | 0% | 0 | Not Started
ER6701LT | W228 | W228.4950 | HYA Enhanced Defueling Safety Case | 2025-06-25 | 2025-06-25 | Issue Final NSRS | 2025-07-02 | 2025-07-02 | 1 | 1 | 1 | 0% | 0 | Not Started
ER6698LT | W224 | W224.4960 | HRA Enhanced Defueling Safety Case |  | 2025-06-25 | Station Agree NSRS *(KDM)* | 2025-07-02 | 2025-07-02 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6698LT | W224 | W224.4970 | HRA Enhanced Defueling Safety Case |  | 2025-06-25 | Key Stakeholders Agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2025-07-02 | 2025-07-02 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6698LT | W224 | W224.4980 | HRA Enhanced Defueling Safety Case |  | 2025-06-25 | INA Agree NSRS | 2025-07-02 | 2025-07-02 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6701LT | W228 | W228.4960 | HYA Enhanced Defueling Safety Case |  | 2025-06-25 | Station Agree NSRS *(KDM)* | 2025-07-02 | 2025-07-02 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6701LT | W228 | W228.4970 | HYA Enhanced Defueling Safety Case |  | 2025-06-25 | Key Stakeholders Agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2025-07-02 | 2025-07-02 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6701LT | W228 | W228.4980 | HYA Enhanced Defueling Safety Case |  | 2025-06-25 | INA Agree NSRS | 2025-07-02 | 2025-07-02 | 0 | 0 | 0 | 0% | 0 | Not Started
W232LT | W232 | W232.C2270 | DNB Enhanced Safety Cases | 2025-06-25 | 2025-07-08 | <SCOPE NAME CHANGE CN3472><FPU and ESA Handling with OEM NSPs> - Address Comments from EDF Review on Draft EAN | 2025-07-03 | 2025-07-16 | 10 | 10 | 10 | 0% | 6 | Not Started
ER6698LT | W224 | W224.4990 | HRA Enhanced Defueling Safety Case | 2025-06-26 | 2025-07-02 | Consolidate & Issue to Stakeholders & Suppliers Agreed NSRS (as required) | 2025-07-03 | 2025-07-09 | 5 | 5 | 5 | 0% | 0 | Not Started
ER6701LT | W228 | W228.4990 | HYA Enhanced Defueling Safety Case | 2025-06-26 | 2025-07-02 | Consolidate & Issue to Stakeholders & Suppliers Agreed NSRS (as required) | 2025-07-03 | 2025-07-09 | 5 | 5 | 5 | 0% | 0 | Not Started
ER6701LT | W228 | W228.3640 | HYA Enhanced Defueling Safety Case | 2025-07-02 | 2025-08-29 | Pull tests/Proof load checks | 2025-07-04 | 2025-09-02 | 42 | 42 | 42 | 0% | 32 | Not Started
ER6701LT | W228 | W228.3630 | HYA Enhanced Defueling Safety Case | 2025-07-02 | 2025-08-29 | Whetsone Buckle Dynamics/Loads Test/ Trip threshold design | 2025-07-04 | 2025-09-02 | 42 | 42 | 42 | 0% | 32 | Not Started
ER6701LT | W228 | W228.3620 | HYA Enhanced Defueling Safety Case | 2025-07-02 | 2025-08-29 | Manipulator Integration Trials | 2025-07-04 | 2025-09-02 | 42 | 42 | 42 | 0% | 32 | Not Started
ER6701LT | W228 | W228.3610 | HYA Enhanced Defueling Safety Case | 2025-07-02 | 2025-08-29 | Gripping Sleeve / Bob Weight Integration/Fit Trials | 2025-07-04 | 2025-09-02 | 42 | 42 | 42 | 0% | 32 | Not Started
W232LT | W232 | W232.C2510 | DNB Enhanced Safety Cases | 2025-04-29 | 2025-05-13 | <SCOPE CHANGE CN3472><NSP Pin Failure> - Address Comments from EDF Review on Draft EAN | 2025-07-07 | 2025-07-18 | 10 | 10 | 10 | 0% | 5 | Not Started
ER6698LT | W224 | W224.3610 | HRA Enhanced Defueling Safety Case | 2025-07-02 | 2025-08-29 | Gripping Sleeve / Bob Weight Integration/Fit Trials | 2025-07-07 | 2025-09-03 | 42 | 42 | 42 | 0% | 31 | Not Started
ER6698LT | W224 | W224.3620 | HRA Enhanced Defueling Safety Case | 2025-07-02 | 2025-08-29 | Manipulator Integration Trials | 2025-07-07 | 2025-09-03 | 42 | 42 | 42 | 0% | 31 | Not Started
ER6698LT | W224 | W224.3630 | HRA Enhanced Defueling Safety Case | 2025-07-02 | 2025-08-29 | Whetsone Buckle Dynamics/Loads Test/ Trip threshold design | 2025-07-07 | 2025-09-03 | 42 | 42 | 42 | 0% | 31 | Not Started
ER6698LT | W224 | W224.3640 | HRA Enhanced Defueling Safety Case | 2025-07-02 | 2025-08-29 | Pull tests/Proof load checks | 2025-07-07 | 2025-09-03 | 42 | 42 | 42 | 0% | 31 | Not Started
W772LT | W772 | W772LT.A1330 | DNB Pull Harder Safety Case | 2025-08-18 | 2025-09-29 | Incorporate INSA comments | 2025-07-07 | 2025-08-15 | 30 | 30 | 30 | 0% | 4 | Not Started
W232LT | W232 | W232.C3500 | DNB Enhanced Safety Cases |  | 2025-06-30 | <SCOPE CHANGE CN3472>-<Demonstration of adequate integrity for Grp2 shock-loaded units> - Issue EAN | 2025-07-07 | 2025-07-07 | 0 | 0 | 0 | 0% | 13 | Not Started
W232LT | W232 | W232.C3510 | DNB Enhanced Safety Cases | 2025-07-01 | 2025-07-07 | <SCOPE CHANGE CN3472>-<Demonstration of adequate integrity for Grp2 shock-loaded units> - Updated EAN Reviewed by EDF | 2025-07-08 | 2025-07-14 | 5 | 5 | 5 | 0% | 13 | Not Started
ER6698LT | W224 | W224.4620 | HRA Enhanced Defueling Safety Case | 2025-07-08 | 2025-07-09 | CA to Agree with CO Format of the Safety Case & Produce Agreed Contents Page | 2025-07-08 | 2025-07-09 | 2 | 2 | 2 | 0% | 36 | Not Started
ER6698LT | W224 | W224.5610 | HRA Enhanced Defueling Safety Case |  |  | Cost Summary - Reduce IFDF Cooling EC 2 | 2025-07-08 | 2026-01-07 | 128 | 128 | 128 | 0% | 36 | Not Started
W232LT | W232 | W232.C2840 | DNB Enhanced Safety Cases | 2025-07-16 | 2025-07-28 | <S C CN3472> <Agree strategy for handling of Group 2 shock-loaded units> - Address Comments from EDF Review on Draft EAN | 2025-07-09 | 2025-07-21 | 9 | 9 | 9 | 0% | 23 | Not Started
W230LT | W230 | W230.2640 | HYB Enhanced Defueling Safety Case Strategy | 2024-12-03 | 2024-12-18 | HYB Low Decay Heat: Mod Requested and EC Request Raised and Screened | 2025-07-09 | 2025-07-24 | 12 | 12 | 12 | 0% | 12 | Not Started
W234LT | W234 | W234.2640 | TOR Enhanced Defueling Safety Case Strategy | 2024-12-03 | 2024-12-18 | TOR Low Decay Heat: Mod Requested and EC Request Raised and Screened | 2025-07-09 | 2025-07-24 | 12 | 12 | 12 | 0% | 12 | Not Started
ER6698LT | W224 | W224.A1290 | HRA Enhanced Defueling Safety Case | 2025-02-13 | 2025-10-01 | Cost Summary - Load Trace EC 2 | 2025-07-10 | 2026-02-26 | 162 | 162 | 162 | 0% | 0 | Not Started
ER6701LT | W228 | W228.A1290 | HYA Enhanced Defueling Safety Case | 2025-02-13 | 2025-10-01 | Cost Summary - Load Trace EC 2 | 2025-07-10 | 2026-02-26 | 162 | 162 | 162 | 0% | 0 | Not Started
ER6698LT | W224 | W224.4630 | HRA Enhanced Defueling Safety Case | 2025-07-10 | 2025-10-30 | Supporting Documentation Updates | 2025-07-10 | 2025-10-30 | 80 | 80 | 80 | 0% | 36 | Not Started
ER6698LT | W224 | W224.4640 | HRA Enhanced Defueling Safety Case | 2025-07-10 | 2025-08-06 | Prepare the Safety Case Proposal (including OPEX Review) | 2025-07-10 | 2025-08-06 | 20 | 20 | 20 | 0% | 36 | Not Started
ER6698LT | W224 | W224.4650 | HRA Enhanced Defueling Safety Case | 2025-07-10 | 2025-07-11 | Produce Verification Plan | 2025-07-10 | 2025-07-11 | 2 | 2 | 2 | 0% | 114 | Not Started
ER6698LT | W224 | W224.5000 | HRA Enhanced Defueling Safety Case | 2025-07-03 | 2025-07-04 | CA to Agree with CO Format of the Safety Case & Produce Agreed Contents Page | 2025-07-10 | 2025-07-11 | 2 | 2 | 2 | 0% | 0 | Not Started
ER6701LT | W228 | W228.5000 | HYA Enhanced Defueling Safety Case | 2025-07-03 | 2025-07-04 | CA to Agree with CO Format of the Safety Case & Produce Agreed Contents Page | 2025-07-10 | 2025-07-11 | 2 | 2 | 2 | 0% | 0 | Not Started
ER6698LT | W224 | W224.5010 | HRA Enhanced Defueling Safety Case | 2025-07-07 | 2025-12-05 | Supporting Documentation Updates | 2025-07-14 | 2025-12-12 | 109 | 109 | 109 | 0% | 0 | Not Started
ER6698LT | W224 | W224.5020 | HRA Enhanced Defueling Safety Case | 2025-07-07 | 2025-08-15 | Prepare the Safety Case Proposal (including OPEX Review) | 2025-07-14 | 2025-08-22 | 30 | 30 | 30 | 0% | 0 | Not Started
ER6698LT | W224 | W224.5030 | HRA Enhanced Defueling Safety Case | 2025-07-07 | 2025-07-08 | Produce Verification Plan | 2025-07-14 | 2025-07-15 | 2 | 2 | 2 | 0% | 107 | Not Started
ER6701LT | W228 | W228.5010 | HYA Enhanced Defueling Safety Case | 2025-07-07 | 2025-12-05 | Supporting Documentation Updates | 2025-07-14 | 2025-12-12 | 109 | 109 | 109 | 0% | 0 | Not Started
ER6701LT | W228 | W228.5020 | HYA Enhanced Defueling Safety Case | 2025-07-07 | 2025-08-15 | Prepare the Safety Case Proposal (including OPEX Review) | 2025-07-14 | 2025-08-22 | 30 | 30 | 30 | 0% | 0 | Not Started
ER6701LT | W228 | W228.5030 | HYA Enhanced Defueling Safety Case | 2025-07-07 | 2025-07-08 | Produce Verification Plan | 2025-07-14 | 2025-07-15 | 2 | 2 | 2 | 0% | 107 | Not Started
ER6701LT | W228 | W228.5420 | HYA Enhanced Defueling Safety Case | 2025-07-10 | 2025-08-20 | Specialist Assessment | 2025-07-14 | 2025-08-22 | 30 | 30 | 30 | 0% | 102 | Not Started
W232LT | W232 | W232.C3300 | DNB Enhanced Safety Cases |  | 2025-06-02 | CN3472 Confirm measures to mitigate for non-enginee'd load path(vis inspect)- Issue EAN | 2025-07-14 | 2025-07-14 | 0 | 0 | 0 | 0% | 8 | Not Started
W232LT | W232 | W232.C3460 | DNB Enhanced Safety Cases |  | 2025-06-10 | <Agree approach to OEM NSP replacement> - Issue EAN | 2025-07-14 | 2025-07-14 | 0 | 0 | 0 | 0% | 8 | Not Started
ER6698LT | W224 | W224.1800 | HRA Enhanced Defueling Safety Case | 2025-07-08 | 2025-07-22 | Technical Review of PC1/PC2 | 2025-07-15 | 2025-07-29 | 11 | 11 | 11 | 0% | 98 | Not Started
ER6701LT | W228 | W228.1800 | HYA Enhanced Defueling Safety Case | 2025-07-08 | 2025-07-22 | Technical Review of PC1/PC2 | 2025-07-15 | 2025-07-29 | 11 | 11 | 11 | 0% | 98 | Not Started
W232LT | W232 | W232.C3310 | DNB Enhanced Safety Cases | 2025-06-03 | 2025-06-09 | CN3472 Confirm measures to mitigate for non-enginee'd load path(vis inspect)- Updated EAN Reviewed by EDF SQEP | 2025-07-15 | 2025-07-21 | 5 | 5 | 5 | 0% | 8 | Not Started
W232LT | W232 | W232.C3470 | DNB Enhanced Safety Cases | 2025-06-11 | 2025-06-17 | <Agree approach to OEM NSP replacement> - Updated EAN Reviewed by EDF SQEP | 2025-07-15 | 2025-07-21 | 5 | 5 | 5 | 0% | 8 | Not Started
W232LT | W232 | W232.C3520 | DNB Enhanced Safety Cases | 2025-07-08 | 2025-07-14 | <SCOPE CHANGE CN3472>-<Demonstration of adequate integrity for Grp2 shock-loaded units>- Address Comments from EDF TR | 2025-07-15 | 2025-07-21 | 5 | 5 | 5 | 0% | 13 | Not Started
ER6698LT | W224 | W224.5420 | HRA Enhanced Defueling Safety Case | 2025-07-10 | 2025-08-20 | Specialist Assessment | 2025-07-15 | 2025-08-26 | 30 | 30 | 30 | 0% | 101 | Not Started
ER6698LT | W224 | W224.3860 | HRA Enhanced Defueling Safety Case |  | 2025-07-15 | KDM Discovery Milestone - Effects of Gas Flow on Bob Weight | 2025-07-15 | 2025-07-15 | 0 | 0 | 0 | 0% | 76 | Not Started
ER6698LT | W224 | W224.3990 | HRA Enhanced Defueling Safety Case |  | 2025-07-15 | KDM - Discovery Milestone – Effects of Gas Flow on Bob Weight | 2025-07-15 | 2025-07-15 | 0 | 0 | 0 | 0% | 158 | Not Started
ER6698LT | W224 | W224.4040 | HRA Enhanced Defueling Safety Case |  | 2025-07-15 | KDM - Discovery Milestone - Ledge & Release Force Determined | 2025-07-15 | 2025-07-15 | 0 | 0 | 0 | 0% | 158 | Not Started
ER6701LT | W228 | W228.4040 | HYA Enhanced Defueling Safety Case |  | 2025-07-15 | KDM - Discovery Milestone - Ledge & Release Force Determined | 2025-07-15 | 2025-07-15 | 0 | 0 | 0 | 0% | 158 | Not Started
W232LT | W232 | W232.C3270 | DNB Enhanced Safety Cases |  | 2025-07-08 | <SCOPE NAME CHANGE CN3472><FPU and ESA Handling with OEM NSPs> - Issue EAN | 2025-07-16 | 2025-07-16 | 0 | 0 | 0 | 0% | 6 | Not Started
ER6701LT | W228 | W228.3860 | HYA Enhanced Defueling Safety Case |  | 2025-07-15 | KDM Discovery Milestone - Effects of Gas Flow on Bob Weight | 2025-07-16 | 2025-07-16 | 0 | 0 | 0 | 0% | 75 | Not Started
ER6701LT | W228 | W228.3990 | HYA Enhanced Defueling Safety Case |  | 2025-07-15 | KDM - Discovery Milestone – Effects of Gas Flow on Bob Weight | 2025-07-16 | 2025-07-16 | 0 | 0 | 0 | 0% | 157 | Not Started
ER6698LT | W224 | W224.3080 | HRA Enhanced Defueling Safety Case | 2025-07-10 | 2025-07-22 | Verification | 2025-07-17 | 2025-07-29 | 9 | 9 | 9 | 0% | 59 | Not Started
ER6701LT | W228 | W228.3080 | HYA Enhanced Defueling Safety Case | 2025-07-10 | 2025-07-22 | Verification | 2025-07-17 | 2025-07-29 | 9 | 9 | 9 | 0% | 59 | Not Started
W232LT | W232 | W232.C3280 | DNB Enhanced Safety Cases | 2025-07-09 | 2025-07-15 | <SCOPE NAME CHANGE CN3472><FPU and ESA Handling with OEM NSPs> - Updated EAN Reviewed by EDF SQEP | 2025-07-17 | 2025-07-23 | 5 | 5 | 5 | 0% | 6 | Not Started
W232LT | W232 | W232.C1880 | DNB Enhanced Safety Cases | 2025-07-30 | 2025-08-18 | <SCOPE CHANGE CN3472><FPU Uninspected Welds lifting integrity (incl'g sub-veto faults)> - Address Comments from EDF | 2025-07-18 | 2025-08-06 | 14 | 14 | 14 | 0% | 5 | Not Started
ER6698LT | W224 | W224.1730 | HRA Enhanced Defueling Safety Case | 2025-06-27 | 2025-08-07 | Supporting Analysis for inclusion within Substantiation Report | 2025-07-18 | 2025-08-29 | 30 | 30 | 30 | 0% | 26 | Not Started
ER6698LT | W224 | W224.2830 | HRA Enhanced Defueling Safety Case | 2025-06-27 | 2025-07-25 | EDF Technical Review of Procurement Specification | 2025-07-18 | 2025-08-15 | 21 | 21 | 21 | 0% | 26 | Not Started
ER6701LT | W228 | W228.2830 | HYA Enhanced Defueling Safety Case | 2025-06-27 | 2025-07-25 | EDF Technical Review of Procurement Specification | 2025-07-18 | 2025-08-15 | 21 | 21 | 21 | 0% | 26 | Not Started
ER6701LT | W228 | W228.1730 | HYA Enhanced Defueling Safety Case | 2025-06-27 | 2025-08-07 | Supporting Analysis for inclusion within Substantiation Report | 2025-07-18 | 2025-08-29 | 30 | 30 | 30 | 0% | 26 | Not Started
W232LT | W232 | W232.C3380 | DNB Enhanced Safety Cases |  | 2025-05-13 | <SCOPE CHANGE CN3472><NSP Pin Failure> - Issue EAN | 2025-07-18 | 2025-07-18 | 0 | 0 | 0 | 0% | 5 | Not Started
W232LT | W232 | W232.C3390 | DNB Enhanced Safety Cases | 2025-05-14 | 2025-05-19 | <SCOPE CHANGE CN3472><NSP Pin Failure> - Updated EAN Reviewed by EDF SQEP | 2025-07-21 | 2025-07-24 | 4 | 4 | 4 | 0% | 5 | Not Started
W232LT | W232 | W232.C2700 | DNB Enhanced Safety Cases |  | 2025-07-14 | <SCOPE CHANGE CN3472>-<Demonstration of adequate integrity for Grp2 shock-loaded units> - Issue Final EAN | 2025-07-21 | 2025-07-21 | 0 | 0 | 0 | 0% | 33 | Not Started
W232LT | W232 | W232.C3530 | DNB Enhanced Safety Cases |  | 2025-07-28 | <SCOPE CHANGE CN3472>-<Agree strategy for handling of Group 2 shock-loaded units> - Issue EAN | 2025-07-21 | 2025-07-21 | 0 | 0 | 0 | 0% | 23 | Not Started
W232LT | W232 | W232.C2710 | DNB Enhanced Safety Cases | 2025-07-15 | 2025-07-21 | <SCOPE CHANGE CN3472>-<Demonstration of adequate integrity for Grp2 shock-loaded units> - EAN Completed and Uploaded | 2025-07-22 | 2025-07-28 | 5 | 5 | 5 | 0% | 33 | Not Started
W232LT | W232 | W232.C3320 | DNB Enhanced Safety Cases | 2025-06-10 | 2025-06-16 | CN3472 Confirm measures to mitigate for non-enginee'd load path(vis inspect)- Address Comments from EDF Review | 2025-07-22 | 2025-07-28 | 5 | 5 | 5 | 0% | 8 | Not Started
W232LT | W232 | W232.C3480 | DNB Enhanced Safety Cases | 2025-06-18 | 2025-06-24 | <Agree approach to OEM NSP replacement> - Address Comments from EDF Review | 2025-07-22 | 2025-07-28 | 5 | 5 | 5 | 0% | 8 | Not Started
W232LT | W232 | W232.C3540 | DNB Enhanced Safety Cases | 2025-07-29 | 2025-08-04 | <SCOPE CHANGE CN3472>-<Agree strategy for handling of Group 2 shock-loaded units> - Updated EAN Reviewed by EDF SQEP | 2025-07-22 | 2025-07-28 | 5 | 5 | 5 | 0% | 23 | Not Started
ER6666LT | W209 | W209.1048 | HYB Essential Defueling Safety Case |  | 2025-01-13 | ONR Agree/Acknowledge Safety Case - HYB Essential Defueling Safety Case | 2025-07-22 | 2025-07-22 | 0 | 0 | 0 | 0% | 5 | Not Started
ER6666LT | W209 | W209.28750 | HYB Essential Defueling Safety Case |  | 2025-01-13 | >>>OUTGOING ENABLER (HYB Security Plan (W157) HYB Fuel Handling Essential Safety Case ONR Approved | 2025-07-22 | 2025-07-22 | 0 | 0 | 0 | 0% | 44 | Not Started
ER6668LT | W213 | W213.28750 | TOR Essential Defueling Safety Case |  | 2025-01-13 | >>>OUTGOING ENABLER (TOR Security Plan (W159) TOR Fuel Handling Essential Safety Case ONR Approved | 2025-07-22 | 2025-07-22 | 0 | 0 | 0 | 0% | 44 | Not Started
ER6666LT | W209 | W209.29560 | HYB Essential Defueling Safety Case |  | 2024-10-16 | Risk Milestone - ONR Assessment Schedule Risk - (Risk Ref 28383) - Letter of No Objection Received | 2025-07-22 | 2025-07-22 | 0 | 0 | 0 | 0% | 44 | Not Started
ER6668LT | W213 | W213.1048 | TOR Essential Defueling Safety Case |  | 2025-01-13 | ONR Agree/Acknowledge Safety Case - TOR Essential Defueling Safety Case | 2025-07-22 | 2025-07-22 | 0 | 0 | 0 | 0% | 5 | Not Started
ER6668LT | W213 | W213.29560 | TOR Essential Defueling Safety Case |  | 2024-10-16 | Risk Milestone - ONR Assessment Schedule Risk - (Risk Ref 28383) - Letter of No Objection Received | 2025-07-22 | 2025-07-22 | 0 | 0 | 0 | 0% | 44 | Not Started
ER6666LT | W209 | W209.5270 | HYB Essential Defueling Safety Case | 2025-01-14 | 2025-01-27 | Station Approve - HYB Essential Defueling Safety Case (FEEDS TO SUMMARY SCHEDULE) | 2025-07-23 | 2025-08-05 | 10 | 10 | 10 | 0% | 5 | Not Started
ER6668LT | W213 | W213.5270 | TOR Essential Defueling Safety Case | 2025-01-14 | 2025-01-27 | Station Approve - TOR Essential Defueling Safety Case (FEEDS TO SUMMARY SCHEDULE) | 2025-07-23 | 2025-08-05 | 10 | 10 | 10 | 0% | 5 | Not Started
W232LT | W232 | W232.C3290 | DNB Enhanced Safety Cases | 2025-07-16 | 2025-07-22 | <SCOPE NAME CHANGE CN3472><FPU and ESA Handling with OEM NSPs> - Address Comments from EDF Review | 2025-07-24 | 2025-07-30 | 5 | 5 | 5 | 0% | 6 | Not Started
W230LT | W230 | W230.2590 | HYB Enhanced Defueling Safety Case Strategy | 2024-12-19 | 2025-01-06 | HYB Low Decay Heat: Produce draft NSRS (using BARRIER MODEL) | 2025-07-25 | 2025-08-07 | 10 | 10 | 10 | 0% | 12 | Not Started
W232LT | W232 | W232.C3400 | DNB Enhanced Safety Cases | 2025-05-20 | 2025-05-27 | <SCOPE CHANGE CN3472><NSP Pin Failure> - Address Comments from EDF Review | 2025-07-25 | 2025-07-31 | 5 | 5 | 5 | 0% | 5 | Not Started
W234LT | W234 | W234.2590 | TOR Enhanced Defueling Safety Case Strategy | 2024-12-19 | 2025-01-06 | TOR Low Decay Heat: Produce draft NSRS (using BARRIER MODEL) | 2025-07-25 | 2025-08-07 | 10 | 10 | 10 | 0% | 12 | Not Started
ER6698LT | W224 | W224.1430 | HRA Enhanced Defueling Safety Case | 2025-07-28 | 2025-09-08 | Specialist Assessment | 2025-07-28 | 2025-09-08 | 30 | 30 | 30 | 0% | 92 | Not Started
ER6701LT | W228 | W228.1430 | HYA Enhanced Defueling Safety Case | 2025-07-28 | 2025-09-08 | Specialist Assessment | 2025-07-28 | 2025-09-08 | 30 | 30 | 30 | 0% | 92 | Not Started
W232LT | W232 | W232.C2370 | DNB Enhanced Safety Cases |  | 2025-06-16 | <SCOPE NAME CHANGE CN3472>Confirm measures to mitigate for non-engineered load path (vis inspect) - Issue Final EAN | 2025-07-28 | 2025-07-28 | 0 | 0 | 0 | 0% | 28 | Not Started
W232LT | W232 | W232.C2610 | DNB Enhanced Safety Cases |  | 2025-06-24 | <Agree approach to OEM NSP replacement> - Issue Final EAN | 2025-07-28 | 2025-07-28 | 0 | 0 | 0 | 0% | 28 | Not Started
W232LT | W232 | W232.C2720 | DNB Enhanced Safety Cases |  | 2025-07-21 | <SCOPE CHANGE CN3472>-<Demonstration of adequate integrity for Grp2 shock-loaded units> - EAN Completed | 2025-07-28 | 2025-07-28 | 0 | 0 | 0 | 0% | 33 | Not Started
W232LT | W232 | W232.C2380 | DNB Enhanced Safety Cases | 2025-06-17 | 2025-06-23 | <SNC CN3472>Confirm measures to mitigate for non-engineered load path (vis inspect) - EAN Completed and Uploaded to CDMS | 2025-07-29 | 2025-08-04 | 5 | 5 | 5 | 0% | 28 | Not Started
W232LT | W232 | W232.C2620 | DNB Enhanced Safety Cases | 2025-06-25 | 2025-07-01 | <Agree approach to OEM NSP replacement> - EAN Completed and Uploaded to CDMS | 2025-07-29 | 2025-08-04 | 5 | 5 | 5 | 0% | 28 | Not Started
W232LT | W232 | W232.C3550 | DNB Enhanced Safety Cases | 2025-08-05 | 2025-08-11 | <SCOPE CHANGE CN3472>-<Agree strategy for handling of Group 2 shock-loaded units> - Address Comments from EDF Review | 2025-07-29 | 2025-08-04 | 5 | 5 | 5 | 0% | 23 | Not Started
ER6698LT | W224 | W224.1670 | HRA Enhanced Defueling Safety Case | 2025-07-23 | 2025-09-03 | Produce Procurement Specification for Load Trace Equipment and Installation | 2025-07-30 | 2025-09-10 | 30 | 30 | 30 | 0% | 98 | Not Started
ER6698LT | W224 | W224.3090 | HRA Enhanced Defueling Safety Case | 2025-07-23 | 2025-08-20 | Technical Review | 2025-07-30 | 2025-08-28 | 21 | 21 | 21 | 0% | 59 | Not Started
ER6701LT | W228 | W228.3090 | HYA Enhanced Defueling Safety Case | 2025-07-23 | 2025-08-20 | Technical Review | 2025-07-30 | 2025-08-28 | 21 | 21 | 21 | 0% | 59 | Not Started
ER6701LT | W228 | W228.1670 | HYA Enhanced Defueling Safety Case | 2025-07-23 | 2025-09-03 | Produce Procurement Specification for Load Trace Equipment and Installation | 2025-07-30 | 2025-09-10 | 30 | 30 | 30 | 0% | 98 | Not Started
W232LT | W232 | W232.C2280 | DNB Enhanced Safety Cases |  | 2025-07-22 | <SCOPE NAME CHANGE CN3472><FPU and ESA Handling with OEM NSPs> - Issue Final EAN | 2025-07-30 | 2025-07-30 | 0 | 0 | 0 | 0% | 26 | Not Started
W232LT | W232 | W232.C2290 | DNB Enhanced Safety Cases | 2025-07-23 | 2025-07-29 | <SCOPE NAME CHANGE CN3472><FPU and ESA Handling with OEM NSPs> - EAN Completed and Uploaded to CDMS | 2025-07-31 | 2025-08-06 | 5 | 5 | 5 | 0% | 26 | Not Started
W730LT_UN | W730 | W730.3720 | HYB Enhanced Defueling Safety Cases | 2025-07-31 | 2025-08-06 | HYB Enhanced Defueling Rate: PSA Modeling Verification | 2025-07-31 | 2025-08-06 | 5 | 5 | 5 | 0% | 11 | Not Started
W731LT_UN | W731 | W731.1310 | TOR Enhanced Defueling Safety Cases | 2025-07-31 | 2025-08-06 | TOR Enhanced Defueling Rate: PSA Modeling Verification | 2025-07-31 | 2025-08-06 | 5 | 5 | 5 | 0% | 11 | Not Started
W232LT | W232 | W232.C2520 | DNB Enhanced Safety Cases |  | 2025-05-27 | <SCOPE CHANGE CN3472><NSP Pin Failure> - Issue Final EAN | 2025-07-31 | 2025-07-31 | 0 | 0 | 0 | 0% | 25 | Not Started
W232LT | W232 | W232.A5040 | DNB Enhanced Safety Cases | 2025-09-05 | 2025-09-08 | Rev 001 - CA to agree with CO format of the safety case & produce agreed contents page | 2025-08-01 | 2025-08-04 | 2 | 2 | 2 | 0% | 5 | Not Started
W232LT | W232 | W232.C2530 | DNB Enhanced Safety Cases | 2025-05-28 | 2025-06-03 | <SCOPE CHANGE CN3472><NSP Pin Failure> - EAN Completed and Uploaded to CDMS | 2025-08-01 | 2025-08-07 | 5 | 5 | 5 | 0% | 25 | Not Started
ER6698LT | W224 | W224.1740 | HRA Enhanced Defueling Safety Case | 2025-07-11 | 2025-08-07 | Requirements Traceability Matrix | 2025-08-01 | 2025-08-29 | 20 | 20 | 20 | 0% | 106 | Not Started
ER6701LT | W228 | W228.1740 | HYA Enhanced Defueling Safety Case | 2025-07-11 | 2025-08-07 | Requirements Traceability Matrix | 2025-08-01 | 2025-08-29 | 20 | 20 | 20 | 0% | 106 | Not Started
W232LT | W232 | W232.C2390 | DNB Enhanced Safety Cases |  | 2025-06-23 | <SCOPE NAME CHANGE CN3472>Confirm measures to mitigate for non-engineered load path (vis inspect) - EAN Completed | 2025-08-04 | 2025-08-04 | 0 | 0 | 0 | 0% | 28 | Not Started
W232LT | W232 | W232.C2630 | DNB Enhanced Safety Cases |  | 2025-07-01 | <Agree approach to OEM NSP replacement> - EAN Completed | 2025-08-04 | 2025-08-04 | 0 | 0 | 0 | 0% | 28 | Not Started
W232LT | W232 | W232.C2850 | DNB Enhanced Safety Cases |  | 2025-08-11 | <SCOPE CHANGE CN3472>-<Agree strategy for handling of Group 2 shock-loaded units> - Issue Final EAN | 2025-08-04 | 2025-08-04 | 0 | 0 | 0 | 0% | 23 | Not Started
W232LT | W232 | W232.C2860 | DNB Enhanced Safety Cases | 2025-08-12 | 2025-08-18 | <SCOPE CHANGE CN3472>-<Agree strategy for handling of Group 2 shock-loaded units> - EAN Completed and Uploaded to CDMS | 2025-08-05 | 2025-08-11 | 5 | 5 | 5 | 0% | 23 | Not Started
W232LT | W232 | W232.C3680 | DNB Enhanced Safety Cases |  |  | Discovery milestone - Review measured NSP growth values to plan use of ‘Rev 004’ SCAs during defuelling of R21 | 2025-08-05 | 2025-08-05 | 0 | 0 | 0 | 0% | 79 | Not Started
W232LT | W232 | W232.C3690 | DNB Enhanced Safety Cases |  |  | Discovery milestone - Develop an EC to justify building empty stringers with increased tie bar slack | 2025-08-05 | 2025-08-05 | 0 | 0 | 0 | 0% | 79 | Not Started
W232LT | W232 | W232.C3700 | DNB Enhanced Safety Cases |  |  | Discovery milestone - Develop updated procedure to use IFD emergency clamps to free stuck SCAs | 2025-08-05 | 2025-08-05 | 0 | 0 | 0 | 0% | 79 | Not Started
W232LT | W232 | W232.C3710 | DNB Enhanced Safety Cases |  |  | Discovery milestone - Go/No Go - Cat 3 EC374183 Rev 002 | 2025-08-05 | 2025-08-05 | 0 | 0 | 0 | 0% | 79 | Not Started
W232LT | W232 | W232.A5900 | DNB Enhanced Safety Cases |  |  | <NEW SCOPE PENDING CN3754> - Prepare and Populate Affected Documents List Rev 001 | 2025-08-05 | 2025-08-18 | 10 | 10 | 10 | 0% | 132 | Not Started
ER6666LT | W209 | W209.1052 | HYB Essential Defueling Safety Case |  | 2025-01-27 | HYB Essential Defueling Safety Case Approved - (Station Approval) - EC 371387 | 2025-08-05 | 2025-08-05 | 0 | 0 | 0 | 0% | 13 | Not Started
ER6666LT | W209 | W209.4980 | HYB Essential Defueling Safety Case |  | 2025-01-27 | >>>OUTGOING ENABLER (W273) STN Approved | 2025-08-05 | 2025-08-05 | 0 | 0 | 0 | 0% | 34 | Not Started
ER6668LT | W213 | W213.4980 | TOR Essential Defueling Safety Case |  | 2025-01-27 | >>>OUTGOING ENABLER (W274) STN Approved | 2025-08-05 | 2025-08-05 | 0 | 0 | 0 | 0% | 34 | Not Started
ER6668LT | W213 | W213.1052 | TOR Essential Defueling Safety Case |  | 2025-01-27 | TOR Essential Defueling Safety Case Approved - (Station Approval) - EC 371386 | 2025-08-05 | 2025-08-05 | 0 | 0 | 0 | 0% | 13 | Not Started
ER6666LT | W209 | W209.2100 | HYB Essential Defueling Safety Case | 2025-01-28 | 2025-01-28 | Hold Project Closeout and Lessons Learned Meeting | 2025-08-06 | 2025-08-06 | 1 | 1 | 1 | 0% | 14 | Not Started
ER6666LT | W209 | W209.1585 | HYB Essential Defueling Safety Case | 2025-01-28 | 2025-02-10 | Revise all Affected Drawings and Documents for EC Approval | 2025-08-06 | 2025-08-19 | 10 | 10 | 10 | 0% | 13 | Not Started
ER6666LT | W209 | W209.29340 | HYB Essential Defueling Safety Case | 2025-01-28 | 2025-02-10 | Lessons Learnt Activity - Project Completion | 2025-08-06 | 2025-08-19 | 10 | 10 | 10 | 0% | 5 | Not Started
ER6668LT | W213 | W213.2100 | TOR Essential Defueling Safety Case | 2025-01-28 | 2025-01-28 | Hold Project Closeout and Lessons Learned Meeting | 2025-08-06 | 2025-08-06 | 1 | 1 | 1 | 0% | 14 | Not Started
ER6668LT | W213 | W213.1585 | TOR Essential Defueling Safety Case | 2025-01-28 | 2025-02-10 | Revise all Affected Drawings and Documents for EC Approval | 2025-08-06 | 2025-08-19 | 10 | 10 | 10 | 0% | 13 | Not Started
ER6668LT | W213 | W213.29340 | TOR Essential Defueling Safety Case | 2025-01-28 | 2025-02-10 | Lessons Learnt Activity - Project Completion | 2025-08-06 | 2025-08-19 | 10 | 10 | 10 | 0% | 5 | Not Started
W232LT | W232 | W232.C2300 | DNB Enhanced Safety Cases |  | 2025-07-29 | <SCOPE NAME CHANGE CN3472><FPU and ESA Handling with OEM NSPs> - EAN Completed | 2025-08-06 | 2025-08-06 | 0 | 0 | 0 | 0% | 26 | Not Started
W232LT | W232 | W232.C2550 | DNB Enhanced Safety Cases |  | 2025-08-18 | <SCOPE CHANGE CN3472><FPU Uninspected Welds lifting integrity (including sub-veto faults)> - Issue EAN | 2025-08-06 | 2025-08-06 | 0 | 0 | 0 | 0% | 5 | Not Started
W232LT | W232 | W232.C2640 | DNB Enhanced Safety Cases | 2025-08-19 | 2025-08-28 | <SCOPE CHANGE CN3472><FPU Uninspe'd Welds lifting integrity (includ sub-veto faults)>-Updated EAN Reviewed by EDF SQEP | 2025-08-07 | 2025-08-15 | 7 | 7 | 7 | 0% | 5 | Not Started
ER6698LT | W224 | W224.4660 | HRA Enhanced Defueling Safety Case | 2025-08-07 | 2025-09-18 | Specialist Assessment | 2025-08-07 | 2025-09-18 | 30 | 30 | 30 | 0% | 84 | Not Started
W730LT_UN | W730 | W730.3730 | HYB Enhanced Defueling Safety Cases | 2025-08-07 | 2025-08-13 | HYB Enhanced Defueling Rate: PSA Modeling Technical Review | 2025-08-07 | 2025-08-13 | 5 | 5 | 5 | 0% | 11 | Not Started
W731LT_UN | W731 | W731.1320 | TOR Enhanced Defueling Safety Cases | 2025-08-07 | 2025-08-13 | TOR Enhanced Defueling Rate: PSA Modeling Technical Review | 2025-08-07 | 2025-08-13 | 5 | 5 | 5 | 0% | 11 | Not Started
W232LT | W232 | W232.C2540 | DNB Enhanced Safety Cases |  | 2025-06-03 | <SCOPE CHANGE CN3472><NSP Pin Failure> - EAN Completed | 2025-08-07 | 2025-08-07 | 0 | 0 | 0 | 0% | 25 | Not Started
W230LT | W230 | W230.2650 | HYB Enhanced Defueling Safety Case Strategy | 2025-01-07 | 2025-01-13 | HYB Low Decay Heat: Hold Case Conference / Optioneering Strategy Workshop as Appropriate | 2025-08-08 | 2025-08-14 | 5 | 5 | 5 | 0% | 12 | Not Started
W234LT | W234 | W234.2650 | TOR Enhanced Defueling Safety Case Strategy | 2025-01-07 | 2025-01-13 | TOR Low Decay Heat: Hold Case Conference / Optioneering Strategy Workshop as Appropriate | 2025-08-08 | 2025-08-14 | 5 | 5 | 5 | 0% | 12 | Not Started
W232LT | W232 | W232.C2870 | DNB Enhanced Safety Cases |  | 2025-08-18 | <SCOPE CHANGE CN3472>-<Agree strategy for handling of Group 2 shock-loaded units> - EAN Completed | 2025-08-11 | 2025-08-11 | 0 | 0 | 0 | 0% | 23 | Not Started
W730LT_UN | W730 | W730.3740 | HYB Enhanced Defueling Safety Cases |  | 2025-08-13 | HYB Enhanced Defueling Rate: PSA Modeling Issued/ Approval | 2025-08-13 | 2025-08-13 | 0 | 0 | 0 | 0% | 11 | Not Started
W731LT_UN | W731 | W731.1330 | TOR Enhanced Defueling Safety Cases |  | 2025-08-13 | TOR Enhanced Defueling Rate: PSA Modeling Issued/ Approval | 2025-08-13 | 2025-08-13 | 0 | 0 | 0 | 0% | 11 | Not Started
W730LT_UN | W730 | W730.3750 | HYB Enhanced Defueling Safety Cases | 2025-08-14 | 2025-09-11 | HYB Enhanced Defueling Rate: PSA Modeling Production Risk (Risk ID 42008) | 2025-08-14 | 2025-09-11 | 20 | 20 | 20 | 0% | 11 | Not Started
W731LT_UN | W731 | W731.1340 | TOR Enhanced Defueling Safety Cases | 2025-08-14 | 2025-09-11 | TOR Enhanced Defueling Rate: PSA Modeling Production Risk (Risk ID 42008) | 2025-08-14 | 2025-09-11 | 20 | 20 | 20 | 0% | 11 | Not Started
W230LT | W230 | W230.2580 | HYB Enhanced Defueling Safety Case Strategy | 2025-01-14 | 2025-01-27 | HYB Low Decay Heat: Station comments on NSRS | 2025-08-15 | 2025-08-29 | 10 | 10 | 10 | 0% | 12 | Not Started
W230LT | W230 | W230.2670 | HYB Enhanced Defueling Safety Case Strategy | 2025-01-14 | 2025-01-27 | HYB Low Decay Heat: DA (Peer) Comments on NSRS | 2025-08-15 | 2025-08-29 | 10 | 10 | 10 | 0% | 12 | Not Started
W234LT | W234 | W234.2580 | TOR Enhanced Defueling Safety Case Strategy | 2025-01-14 | 2025-01-27 | TOR Low Decay Heat: Station comments on NSRS | 2025-08-15 | 2025-08-29 | 10 | 10 | 10 | 0% | 12 | Not Started
W234LT | W234 | W234.2670 | TOR Enhanced Defueling Safety Case Strategy | 2025-01-14 | 2025-01-27 | TOR Low Decay Heat: DA (Peer) Comments on NSRS | 2025-08-15 | 2025-08-29 | 10 | 10 | 10 | 0% | 12 | Not Started
ER6698LT | W224 | W224.3910 | HRA Enhanced Defueling Safety Case |  | 2025-07-25 | KDM - Issue Bob Weight & Gripping Sleeve Procurement Specification to Project W745 | 2025-08-15 | 2025-08-15 | 0 | 0 | 0 | 0% | 135 | Not Started
ER6701LT | W228 | W228.3910 | HYA Enhanced Defueling Safety Case |  | 2025-07-25 | KDM - Issue Bob Weight & Gripping Sleeve Procurement Specification to Project W746 | 2025-08-15 | 2025-08-15 | 0 | 0 | 0 | 0% | 135 | Not Started
ER6698LT | W224 | W224.3980 | HRA Enhanced Defueling Safety Case |  | 2025-07-25 | KDM - Issue of Trip Function Procurement Spec to Project W745 | 2025-08-15 | 2025-08-15 | 0 | 0 | 0 | 0% | 135 | Not Started
ER6701LT | W228 | W228.3980 | HYA Enhanced Defueling Safety Case |  | 2025-07-25 | KDM - Issue of Trip Function Procurement Spec to Project W746 | 2025-08-15 | 2025-08-15 | 0 | 0 | 0 | 0% | 135 | Not Started
W772LT | W772 | W772LT.A1360 | DNB Pull Harder Safety Case | 2025-09-30 | 2025-09-30 | Re -Verification and Milestone Signature | 2025-08-18 | 2025-08-18 | 1 | 1 | 1 | 0% | 4 | Not Started
W232LT | W232 | W232.C2880 | DNB Enhanced Safety Cases | 2025-08-29 | 2025-09-08 | <SCOPE CHANGE CN3472><FPU Uninspe'd Welds lifting integrity (includ sub-veto faults)>Address Comments from EDF Review | 2025-08-18 | 2025-08-27 | 7 | 7 | 7 | 0% | 5 | Not Started
W772LT | W772 | W772LT.A1370 | DNB Pull Harder Safety Case |  | 2025-09-30 | INSA Assessment Substantially Comp (T - 3 weeks before XXX date) ==> KDM | 2025-08-18 | 2025-08-18 | 0 | 0 | 0 | 0% | 4 | Not Started
W772LT | W772 | W772LT.KDM.SP05 | DNB Pull Harder Safety Case |  | 2025-09-30 | KDM - INSA Final Approval EC 375698 <DNB Pull Harder SC> | 2025-08-18 | 2025-08-18 | 0 | 0 | 0 | 0% | 4 | Not Started
W772LT | W772 | W772LT.KDM.SP05-1 | DNB Pull Harder Safety Case |  | 2025-09-30 | KDM - INSA Final Approval EC 375698 <DNB Pull Harder SC> | 2025-08-18 | 2025-08-18 | 0 | 0 | 0 | 0% | 4 | Not Started
W772LT | W772 | W772LT.KDM.BU.02 | DNB Pull Harder Safety Case | 2025-10-01 | 2025-10-01 | KDM - Station Approve EC 375698 <DNB Pull Harder SC> | 2025-08-19 | 2025-08-19 | 1 | 1 | 1 | 0% | 4 | Not Started
ER6666LT | W209 | W209.29350 | HYB Essential Defueling Safety Case |  | 2025-02-10 | Lessons Learnt Milestone - Project Completion | 2025-08-19 | 2025-08-19 | 0 | 0 | 0 | 0% | 5 | Not Started
ER6668LT | W213 | W213.29350 | TOR Essential Defueling Safety Case |  | 2025-02-10 | Lessons Learnt Milestone - Project Completion | 2025-08-19 | 2025-08-19 | 0 | 0 | 0 | 0% | 5 | Not Started
W772LT | W772 | W772LT.KDM.BU.02-1 | DNB Pull Harder Safety Case |  | 2025-10-01 | KDM - Station Approve EC 375698 <DNB Pull Harder SC> | 2025-08-19 | 2025-08-19 | 0 | 0 | 0 | 0% | 4 | Not Started
ER6666LT | W209 | W209.2110 | HYB Essential Defueling Safety Case | 2025-02-11 | 2025-02-11 | Produce Lessons Learned Report | 2025-08-20 | 2025-08-20 | 1 | 1 | 1 | 0% | 5 | Not Started
ER6666LT | W209 | W209.1595 | HYB Essential Defueling Safety Case | 2025-02-11 | 2025-02-24 | Develop Implementation & closeout Plan | 2025-08-20 | 2025-09-03 | 10 | 10 | 10 | 0% | 13 | Not Started
ER6668LT | W213 | W213.2110 | TOR Essential Defueling Safety Case | 2025-02-11 | 2025-02-11 | Produce Lessons Learned Report | 2025-08-20 | 2025-08-20 | 1 | 1 | 1 | 0% | 5 | Not Started
ER6668LT | W213 | W213.1595 | TOR Essential Defueling Safety Case | 2025-02-11 | 2025-02-24 | Develop Implementation & closeout Plan | 2025-08-20 | 2025-09-03 | 10 | 10 | 10 | 0% | 13 | Not Started
W772LT | W772 | W772LT.A1590 | DNB Pull Harder Safety Case | 2025-10-02 | 2025-10-15 | Revise all Affected Drawings and Documents for EC Approval | 2025-08-20 | 2025-09-03 | 10 | 10 | 10 | 0% | 4 | Not Started
W772LT | W772 | W772LT.A2210 | DNB Pull Harder Safety Case | 2025-10-02 | 2025-10-08 | Review Test Schedule | 2025-08-20 | 2025-08-27 | 5 | 5 | 5 | 0% | 9 | Not Started
ER6666LT | W209 | W209.2120 | HYB Essential Defueling Safety Case | 2025-02-12 | 2025-02-13 | Produce Project Closeout Report | 2025-08-21 | 2025-08-22 | 2 | 2 | 2 | 0% | 5 | Not Started
ER6668LT | W213 | W213.2120 | TOR Essential Defueling Safety Case | 2025-02-12 | 2025-02-13 | Produce Project Closeout Report | 2025-08-21 | 2025-08-22 | 2 | 2 | 2 | 0% | 5 | Not Started
ER6701LT | W228 | W228.4670 | HYA Enhanced Defueling Safety Case |  | 2025-08-06 | All supporting References Completed | 2025-08-22 | 2025-08-22 | 0 | 0 | 0 | 0% | 84 | Not Started
ER6666LT | W209 | W209.2130 | HYB Essential Defueling Safety Case | 2025-02-14 | 2025-02-21 | Prepare Gate D PRC Paper | 2025-08-26 | 2025-09-02 | 6 | 6 | 6 | 0% | 5 | Not Started
ER6668LT | W213 | W213.2130 | TOR Essential Defueling Safety Case | 2025-02-14 | 2025-02-21 | Prepare Gate D PRC Paper | 2025-08-26 | 2025-09-02 | 6 | 6 | 6 | 0% | 5 | Not Started
ER6698LT | W224 | W224.5040 | HRA Enhanced Defueling Safety Case | 2025-08-18 | 2025-09-29 | Specialist Assessment | 2025-08-26 | 2025-10-06 | 30 | 30 | 30 | 0% | 72 | Not Started
ER6701LT | W228 | W228.5040 | HYA Enhanced Defueling Safety Case | 2025-08-18 | 2025-09-29 | Specialist Assessment | 2025-08-26 | 2025-10-06 | 30 | 30 | 30 | 0% | 72 | Not Started
ER6701LT | W228 | W228.4680 | HYA Enhanced Defueling Safety Case | 2025-08-07 | 2025-08-28 | Verification of the case (using BARRIER MODEL) | 2025-08-26 | 2025-09-15 | 15 | 15 | 15 | 0% | 84 | Not Started
W232LT | W232 | W232.C1890 | DNB Enhanced Safety Cases |  | 2025-09-08 | <SCOPE CHANGE CN3472><FPU Uninspected Welds lifting integrity (including sub-veto faults)> - Issue Final EAN | 2025-08-27 | 2025-08-27 | 0 | 0 | 0 | 0% | 5 | Not Started
W232LT | W232 | W232.C1900 | DNB Enhanced Safety Cases | 2025-09-09 | 2025-09-17 | <SCOPE CHANGE CN3472><FPU Uninspected Welds lifting integrity (including sub-veto faults)> - EAN Completed and Uploade | 2025-08-28 | 2025-09-05 | 7 | 7 | 7 | 0% | 5 | Not Started
W772LT | W772 | W772LT.A2220 | DNB Pull Harder Safety Case | 2025-10-09 | 2025-10-15 | Perform Tests | 2025-08-28 | 2025-09-03 | 5 | 5 | 5 | 0% | 9 | Not Started
ER6698LT | W224 | W224.3100 | HRA Enhanced Defueling Safety Case | 2025-08-21 | 2025-09-04 | Approval | 2025-08-29 | 2025-09-11 | 10 | 10 | 10 | 0% | 59 | Not Started
ER6701LT | W228 | W228.3100 | HYA Enhanced Defueling Safety Case | 2025-08-21 | 2025-09-04 | Approval | 2025-08-29 | 2025-09-11 | 10 | 10 | 10 | 0% | 59 | Not Started
ER6698LT | W224 | W224.1750 | HRA Enhanced Defueling Safety Case | 2025-08-08 | 2025-09-05 | Consolidation of Analaysis and Matrix into the DSR document | 2025-09-01 | 2025-09-26 | 20 | 20 | 20 | 0% | 106 | Not Started
ER6698LT | W224 | W224.1760 | HRA Enhanced Defueling Safety Case | 2025-08-08 | 2025-09-09 | Authorship | 2025-09-01 | 2025-09-30 | 22 | 22 | 22 | 0% | 26 | Not Started
ER6701LT | W228 | W228.1760 | HYA Enhanced Defueling Safety Case | 2025-08-08 | 2025-09-09 | Authorship | 2025-09-01 | 2025-09-30 | 22 | 22 | 22 | 0% | 26 | Not Started
ER6701LT | W228 | W228.1750 | HYA Enhanced Defueling Safety Case | 2025-08-08 | 2025-09-05 | Consolidation of Analaysis and Matrix into the DSR document | 2025-09-01 | 2025-09-26 | 20 | 20 | 20 | 0% | 106 | Not Started
W230LT | W230 | W230.2540 | HYB Enhanced Defueling Safety Case Strategy | 2025-01-28 | 2025-02-10 | HYB Low Decay Heat: INA comments on NSRS | 2025-09-01 | 2025-09-12 | 10 | 10 | 10 | 0% | 12 | Not Started
W234LT | W234 | W234.2540 | TOR Enhanced Defueling Safety Case Strategy | 2025-01-28 | 2025-02-10 | TOR Low Decay Heat: INA comments on NSRS | 2025-09-01 | 2025-09-12 | 10 | 10 | 10 | 0% | 12 | Not Started
ER6701LT | W228 | W228.3320 | HYA Enhanced Defueling Safety Case | 2025-09-01 | 2025-09-05 | Incorporate Test Result into DSR | 2025-09-03 | 2025-09-09 | 5 | 5 | 5 | 0% | 32 | Not Started
ER6666LT | W209 | W209.1605 | HYB Essential Defueling Safety Case | 2025-02-25 | 2025-02-25 | Post Job Debrief | 2025-09-04 | 2025-09-04 | 1 | 1 | 1 | 0% | 13 | Not Started
ER6668LT | W213 | W213.1605 | TOR Essential Defueling Safety Case | 2025-02-25 | 2025-02-25 | Post Job Debrief | 2025-09-04 | 2025-09-04 | 1 | 1 | 1 | 0% | 13 | Not Started
W772LT | W772 | W772LT.A1660 | DNB Pull Harder Safety Case | 2025-10-16 | 2025-10-29 | Develop Implementation & closeout Plan | 2025-09-04 | 2025-09-17 | 10 | 10 | 10 | 0% | 4 | Not Started
W772LT | W772 | W772LT.A2230 | DNB Pull Harder Safety Case | 2025-10-16 | 2025-10-22 | Report on Test Outcomes | 2025-09-04 | 2025-09-10 | 5 | 5 | 5 | 0% | 9 | Not Started
ER6698LT | W224 | W224.3320 | HRA Enhanced Defueling Safety Case | 2025-09-01 | 2025-09-05 | Incorporate Test Result into DSR | 2025-09-04 | 2025-09-10 | 5 | 5 | 5 | 0% | 31 | Not Started
W232LT | W232 | W232.A5190 | DNB Enhanced Safety Cases |  | 2025-09-17 | Rev 001 - All supporting references completed | 2025-09-05 | 2025-09-05 | 0 | 0 | 0 | 0% | 5 | Not Started
W232LT | W232 | W232.C1910 | DNB Enhanced Safety Cases |  | 2025-09-17 | <SCOPE CHANGE CN3472><FPU Uninspected Welds lifting integrity (including sub-veto faults)> - EAN Completed | 2025-09-05 | 2025-09-05 | 0 | 0 | 0 | 0% | 5 | Not Started
W232LT | W232 | W232.A5280 | DNB Enhanced Safety Cases |  | 2025-09-17 | All Technical References Complete - Rev 001 | 2025-09-05 | 2025-09-05 | 0 | 0 | 0 | 0% | 5 | Not Started
W232LT | W232 | W232.A5440 | DNB Enhanced Safety Cases |  | 2024-08-16 | Verifier PJB Held | 2025-09-05 | 2025-09-05 | 0 | 0 | 0 | 0% | 14 | Not Started
W232LT | W232 | W232.A5070 | DNB Enhanced Safety Cases | 2025-09-18 | 2025-09-19 | Rev 001 - Produce verification plan | 2025-09-08 | 2025-09-09 | 2 | 2 | 2 | 0% | 14 | Not Started
W232LT | W232 | W232.A5510 | DNB Enhanced Safety Cases |  |  | Lessons Learned Workshop - FPU Safety Case Ph 3 Rev 001 Technical References complete | 2025-09-08 | 2025-09-08 | 1 | 1 | 1 | 0% | 14 | Not Started
ER6666LT | W209 | W209.2140 | HYB Essential Defueling Safety Case | 2025-03-04 | 2025-03-04 | Gate D PRC Paper Submission | 2025-09-10 | 2025-09-10 | 1 | 1 | 1 | 0% | 0 | Not Started
ER6668LT | W213 | W213.2140 | TOR Essential Defueling Safety Case | 2025-03-04 | 2025-03-04 | Gate D PRC Paper Submission | 2025-09-10 | 2025-09-10 | 1 | 1 | 1 | 0% | 0 | Not Started
ER6701LT | W228 | W228.3160 | HYA Enhanced Defueling Safety Case | 2025-09-08 | 2025-09-17 | Verification | 2025-09-10 | 2025-09-19 | 8 | 8 | 8 | 0% | 32 | Not Started
ER6698LT | W224 | W224.3160 | HRA Enhanced Defueling Safety Case | 2025-09-08 | 2025-09-17 | Verification | 2025-09-11 | 2025-09-22 | 8 | 8 | 8 | 0% | 31 | Not Started
ER6698LT | W224 | W224.1810 | HRA Enhanced Defueling Safety Case | 2025-09-04 | 2025-10-01 | Technical Review of Procurement Spec | 2025-09-11 | 2025-10-08 | 20 | 20 | 20 | 0% | 98 | Not Started
ER6698LT | W224 | W224.3760 | HRA Enhanced Defueling Safety Case | 2025-09-11 | 2025-10-22 | Specialist Assessment | 2025-09-11 | 2025-10-22 | 30 | 30 | 30 | 0% | 48 | Not Started
ER6698LT | W224 | W224.3770 | HRA Enhanced Defueling Safety Case | 2025-09-11 | 2025-11-07 | Verification | 2025-09-11 | 2025-11-07 | 42 | 42 | 42 | 0% | 36 | Not Started
ER6701LT | W228 | W228.3770 | HYA Enhanced Defueling Safety Case | 2025-09-10 | 2025-11-06 | Verification | 2025-09-11 | 2025-11-07 | 42 | 42 | 42 | 0% | 36 | Not Started
ER6701LT | W228 | W228.3760 | HYA Enhanced Defueling Safety Case | 2025-09-10 | 2025-10-21 | Specialist Assessment | 2025-09-11 | 2025-10-22 | 30 | 30 | 30 | 0% | 48 | Not Started
ER6701LT | W228 | W228.1810 | HYA Enhanced Defueling Safety Case | 2025-09-04 | 2025-10-01 | Technical Review of Procurement Spec | 2025-09-11 | 2025-10-08 | 20 | 20 | 20 | 0% | 98 | Not Started
ER6698LT | W224 | W224.3110 | HRA Enhanced Defueling Safety Case |  | 2025-09-04 | KDM - Design Substantiation Report Load Trace | 2025-09-11 | 2025-09-11 | 0 | 0 | 0 | 0% | 59 | Not Started
ER6698LT | W224 | W224.3310 | HRA Enhanced Defueling Safety Case |  | 2025-09-04 | KDM - Design Substantiation Report Approval | 2025-09-11 | 2025-09-11 | 0 | 0 | 0 | 0% | 117 | Not Started
ER6701LT | W228 | W228.3310 | HYA Enhanced Defueling Safety Case |  | 2025-09-04 | KDM - Design Substantiation Report Approval | 2025-09-11 | 2025-09-11 | 0 | 0 | 0 | 0% | 117 | Not Started
ER6701LT | W228 | W228.3110 | HYA Enhanced Defueling Safety Case |  | 2025-09-04 | KDM - Design Substantiation Report Load Trace | 2025-09-11 | 2025-09-11 | 0 | 0 | 0 | 0% | 59 | Not Started
W730LT_UN | W730 | W730.4200 | HYB Enhanced Defueling Safety Cases |  | 2025-09-11 | HYB Enhanced Defueling Rate: Discovery Milestone - HF Scope Review of New Significant HBSC | 2025-09-11 | 2025-09-11 | 0 | 0 | 0 | 0% | 647 | Not Started
W731LT_UN | W731 | W730.1000 | TOR Enhanced Defueling Safety Cases |  | 2025-09-11 | TOR Enhanced Defueling Rate: Discovery Milestone - HF Scope Review of New Significant HBSC | 2025-09-11 | 2025-09-11 | 0 | 0 | 0 | 0% | 647 | Not Started
W730LT_UN | W730 | W730.3760 | HYB Enhanced Defueling Safety Cases | 2025-09-12 | 2025-10-02 | HYB Enhanced Defueling Rate: PSA Main Summary Report Authroing | 2025-09-12 | 2025-10-02 | 15 | 15 | 15 | 0% | 11 | Not Started
W731LT_UN | W731 | W731.1350 | TOR Enhanced Defueling Safety Cases | 2025-09-12 | 2025-10-02 | TOR Enhanced Defueling Rate: PSA Main Summary Report Authroing | 2025-09-12 | 2025-10-02 | 15 | 15 | 15 | 0% | 11 | Not Started
W230LT | W230 | W230.2600 | HYB Enhanced Defueling Safety Case Strategy | 2025-02-11 | 2025-02-11 | HYB Low Decay Heat: Register EC and identify Milestones in AMS EC NNNNNN | 2025-09-15 | 2025-09-15 | 1 | 1 | 1 | 0% | 12 | Not Started
W234LT | W234 | W234.2600 | TOR Enhanced Defueling Safety Case Strategy | 2025-02-11 | 2025-02-11 | TOR Low Decay Heat: Register EC and identify Milestones in AMS EC NNNNNN | 2025-09-15 | 2025-09-15 | 1 | 1 | 1 | 0% | 12 | Not Started
ER6701LT | W228 | W228.4690 | HYA Enhanced Defueling Safety Case |  | 2025-08-28 | Issue to CO & Station for Comments | 2025-09-15 | 2025-09-15 | 0 | 0 | 0 | 0% | 84 | Not Started
W230LT | W230 | W230.2610 | HYB Enhanced Defueling Safety Case Strategy | 2025-02-12 | 2025-02-12 | HYB Low Decay Heat: Update NSRS to address comments | 2025-09-16 | 2025-09-16 | 1 | 1 | 1 | 0% | 12 | Not Started
ER6701LT | W228 | W228.4700 | HYA Enhanced Defueling Safety Case | 2025-08-29 | 2025-09-04 | Incorporate CO & Station Comments | 2025-09-16 | 2025-09-22 | 5 | 5 | 5 | 0% | 84 | Not Started
ER6701LT | W228 | W228.4710 | HYA Enhanced Defueling Safety Case | 2025-08-29 | 2025-09-01 | Produce Verification File | 2025-09-16 | 2025-09-17 | 2 | 2 | 2 | 0% | 87 | Not Started
W234LT | W234 | W234.2610 | TOR Enhanced Defueling Safety Case Strategy | 2025-02-12 | 2025-02-12 | TOR Low Decay Heat: Update NSRS to address comments | 2025-09-16 | 2025-09-16 | 1 | 1 | 1 | 0% | 12 | Not Started
W230LT | W230 | W230.2880 | HYB Enhanced Defueling Safety Case Strategy | 2025-02-13 | 2025-02-19 | HYB Low Decay Heat: Risk Ref 38976 TBC - NSRS Production | 2025-09-17 | 2025-09-23 | 5 | 5 | 5 | 0% | 12 | Not Started
W234LT | W234 | W234.2880 | TOR Enhanced Defueling Safety Case Strategy | 2025-02-13 | 2025-02-19 | TOR Low Decay Heat: Risk Ref 38976 TBC - NSRS Production | 2025-09-17 | 2025-09-23 | 5 | 5 | 5 | 0% | 12 | Not Started
W772LT | W772 | W772LT.A1430 | DNB Pull Harder Safety Case | 2025-10-30 | 2025-10-30 | Post Job Debrief | 2025-09-18 | 2025-09-18 | 1 | 1 | 1 | 0% | 4 | Not Started
W772LT | W772 | W772LT.D2010 | DNB Pull Harder Safety Case | 2025-10-31 | 2025-10-31 | Hold Project Closeout and Lessons Learned Meeting | 2025-09-19 | 2025-09-19 | 1 | 1 | 1 | 0% | 4 | Not Started
W772LT | W772 | W772LT.D2000 | DNB Pull Harder Safety Case | 2025-10-31 | 2025-12-16 | Project Management - Gate D-E | 2025-09-19 | 2025-10-21 | 23 | 23 | 23 | 0% | 0 | Not Started
W232LT | W232 | W232.A5290 | DNB Enhanced Safety Cases |  | 2025-10-27 | Safety Case Authoring Complete - Rev 001 | 2025-09-19 | 2025-09-19 | 0 | 0 | 0 | 0% | 6 | Not Started
W232LT | W232 | W232.A5520 | DNB Enhanced Safety Cases |  |  | Lessons Learned Workshop - FPU Safety Case Ph 3 Rev 001 Authored | 2025-09-22 | 2025-09-22 | 1 | 1 | 1 | 0% | 5 | Not Started
ER6701LT | W228 | W228.3170 | HYA Enhanced Defueling Safety Case | 2025-09-18 | 2025-10-16 | Technical Review | 2025-09-22 | 2025-10-20 | 21 | 21 | 21 | 0% | 32 | Not Started
W772LT | W772 | W772LT.D2020 | DNB Pull Harder Safety Case | 2025-11-03 | 2025-11-03 | Produce Lessons Learned Report | 2025-09-22 | 2025-09-22 | 1 | 1 | 1 | 0% | 4 | Not Started
ER6701LT | W228 | W228.4720 | HYA Enhanced Defueling Safety Case |  | 2025-09-04 | Issue High Quality Verified Draft Issue A with Verification File to INSA & Station (T - 3 weeks before NSC date) *(KDM)* | 2025-09-22 | 2025-09-22 | 0 | 0 | 0 | 0% | 84 | Not Started
ER6701LT | W228 | W228.4730 | HYA Enhanced Defueling Safety Case |  | 2025-09-04 | Verification Complete | 2025-09-22 | 2025-09-22 | 0 | 0 | 0 | 0% | 84 | Not Started
ER6701LT | W228 | W228.4740 | HYA Enhanced Defueling Safety Case |  | 2025-09-04 | Submit for Approval - Categoriser Ratifies; RE/CO Endorsement | 2025-09-22 | 2025-09-22 | 0 | 0 | 0 | 0% | 84 | Not Started
ER6701LT | W228 | W228.4750 | HYA Enhanced Defueling Safety Case |  | 2025-09-04 | NSORC Agreed Paper (SZB Only & as required) | 2025-09-22 | 2025-09-22 | 0 | 0 | 0 | 0% | 84 | Not Started
ER6666LT | W209 | W209.2150 | HYB Essential Defueling Safety Case | 2025-03-17 | 2025-03-17 | Hold PRC Meeting | 2025-09-23 | 2025-09-23 | 1 | 1 | 1 | 0% | 0 | Not Started
ER6668LT | W213 | W213.2150 | TOR Essential Defueling Safety Case | 2025-03-17 | 2025-03-17 | Hold PRC Meeting | 2025-09-23 | 2025-09-23 | 1 | 1 | 1 | 0% | 0 | Not Started
W232LT | W232 | W232.A5080 | DNB Enhanced Safety Cases | 2025-10-29 | 2025-12-23 | <TRANSFER RESOURCE EXT to INT PENDING CN3754> Rev 001 - Verification of the case (using BARRIER MODEL) | 2025-09-23 | 2025-11-17 | 40 | 40 | 40 | 0% | 5 | Not Started
ER6698LT | W224 | W224.3170 | HRA Enhanced Defueling Safety Case | 2025-09-18 | 2025-10-16 | Technical Review | 2025-09-23 | 2025-10-21 | 21 | 21 | 21 | 0% | 31 | Not Started
W772LT | W772 | W772LT.D2030 | DNB Pull Harder Safety Case | 2025-11-04 | 2025-11-04 | Produce Project Closeout Report | 2025-09-23 | 2025-09-23 | 1 | 1 | 1 | 0% | 4 | Not Started
ER6701LT | W228 | W228.4760 | HYA Enhanced Defueling Safety Case | 2025-09-05 | 2025-09-18 | INSA Review & Iteration of Comments (using BARRIER MODEL) | 2025-09-23 | 2025-10-06 | 10 | 10 | 10 | 0% | 84 | Not Started
ER6701LT | W228 | W228.4770 | HYA Enhanced Defueling Safety Case | 2025-09-05 | 2025-09-11 | Key Stakeholders Approval, if Requested | 2025-09-23 | 2025-09-29 | 5 | 5 | 5 | 0% | 94 | Not Started
ER6666LT | W209 | W209.1064 | HYB Essential Defueling Safety Case |  | 2025-03-17 | Gate D - PRC Paper Approval (HYB) | 2025-09-23 | 2025-09-23 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6666LT | W209 | W209.1054 | HYB Essential Defueling Safety Case |  | 2025-03-17 | Project Completion | 2025-09-23 | 2025-09-23 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6668LT | W213 | W213.1064 | TOR Essential Defueling Safety Case |  | 2025-03-17 | Gate D - PRC Paper Approval (TOR) | 2025-09-23 | 2025-09-23 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6668LT | W213 | W213.1054 | TOR Essential Defueling Safety Case |  | 2025-03-17 | Project Completion | 2025-09-23 | 2025-09-23 | 0 | 0 | 0 | 0% | 0 | Not Started
W230LT | W230 | W230.3580 | HYB Enhanced Defueling Safety Case Strategy |  | 2025-05-29 | HYB Low Decay Heat: Risk Milestone - NSRS Production Complete (Risk Ref 38976) | 2025-09-23 | 2025-09-23 | 0 | 0 | 0 | 0% | 12 | Not Started
W234LT | W234 | W234.3580 | TOR Enhanced Defueling Safety Case Strategy |  | 2025-05-29 | TOR Low Decay Heat: Risk Milestone - NSRS Production Complete (Risk Ref 38976) | 2025-09-23 | 2025-09-23 | 0 | 0 | 0 | 0% | 12 | Not Started
W230LT | W230 | W230.2570 | HYB Enhanced Defueling Safety Case Strategy | 2025-02-20 | 2025-02-20 | HYB Low Decay Heat: Issue final NSRS | 2025-09-24 | 2025-09-24 | 1 | 1 | 1 | 0% | 12 | Not Started
W772LT | W772 | W772LT.D2040 | DNB Pull Harder Safety Case | 2025-11-05 | 2025-11-12 | Prepare Gate D PRC Paper | 2025-09-24 | 2025-10-01 | 6 | 6 | 6 | 0% | 4 | Not Started
W234LT | W234 | W234.2570 | TOR Enhanced Defueling Safety Case Strategy | 2025-02-20 | 2025-02-20 | TOR Low Decay Heat: Issue final NSRS | 2025-09-24 | 2025-09-24 | 1 | 1 | 1 | 0% | 12 | Not Started
W230LT | W230 | W230.2550 | HYB Enhanced Defueling Safety Case Strategy | 2025-02-24 | 2025-03-14 | HYB Low Decay Heat: DA & INA agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2025-09-26 | 2025-10-16 | 15 | 15 | 15 | 0% | 12 | Not Started
W234LT | W234 | W234.2550 | TOR Enhanced Defueling Safety Case Strategy | 2025-02-24 | 2025-03-14 | TOR Low Decay Heat: DA & INA agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2025-09-26 | 2025-10-16 | 15 | 15 | 15 | 0% | 12 | Not Started
ER6698LT | W224 | W224.1770 | HRA Enhanced Defueling Safety Case | 2025-09-10 | 2025-09-24 | Verification | 2025-10-01 | 2025-10-15 | 11 | 11 | 11 | 0% | 26 | Not Started
ER6698LT | W224 | W224.1780 | HRA Enhanced Defueling Safety Case | 2025-09-10 | 2025-10-07 | Technical Review | 2025-10-01 | 2025-10-28 | 20 | 20 | 20 | 0% | 26 | Not Started
ER6701LT | W228 | W228.1780 | HYA Enhanced Defueling Safety Case | 2025-09-10 | 2025-10-07 | Technical Review | 2025-10-01 | 2025-10-28 | 20 | 20 | 20 | 0% | 26 | Not Started
ER6701LT | W228 | W228.1770 | HYA Enhanced Defueling Safety Case | 2025-09-10 | 2025-09-24 | Verification | 2025-10-01 | 2025-10-15 | 11 | 11 | 11 | 0% | 26 | Not Started
W230LT | W230 | W230.2560 | HYB Enhanced Defueling Safety Case Strategy | 2025-03-03 | 2025-03-14 | HYB Low Decay Heat: Station agree NSRS | 2025-10-03 | 2025-10-16 | 10 | 10 | 10 | 0% | 12 | Not Started
W234LT | W234 | W234.2560 | TOR Enhanced Defueling Safety Case Strategy | 2025-03-03 | 2025-03-14 | TOR Low Decay Heat: Station agree NSRS | 2025-10-03 | 2025-10-16 | 10 | 10 | 10 | 0% | 12 | Not Started
W730LT_UN | W730 | W730.3770 | HYB Enhanced Defueling Safety Cases | 2025-10-03 | 2025-10-06 | HYB Enhanced Defueling Rate: PSA Main Sumary Report Verification | 2025-10-03 | 2025-10-06 | 2 | 2 | 2 | 0% | 11 | Not Started
W731LT_UN | W731 | W731.1360 | TOR Enhanced Defueling Safety Cases | 2025-10-03 | 2025-10-06 | TOR Enhanced Defueling Rate: PSA Main Sumary Report Verification | 2025-10-03 | 2025-10-06 | 2 | 2 | 2 | 0% | 11 | Not Started
ER6701LT | W228 | W228.3180 | HYA Enhanced Defueling Safety Case | 2025-10-03 | 2025-10-16 | Approval | 2025-10-07 | 2025-10-20 | 10 | 10 | 10 | 0% | 32 | Not Started
ER6701LT | W228 | W228.4780 | HYA Enhanced Defueling Safety Case | 2025-09-19 | 2025-09-25 | Incorporate INSA Comments | 2025-10-07 | 2025-10-13 | 5 | 5 | 5 | 0% | 84 | Not Started
W730LT_UN | W730 | W730.3780 | HYB Enhanced Defueling Safety Cases | 2025-10-07 | 2025-10-08 | HYB Enhanced Defueling Rate: PSA Main Summary Report Technical Review | 2025-10-07 | 2025-10-08 | 2 | 2 | 2 | 0% | 11 | Not Started
W731LT_UN | W731 | W731.1370 | TOR Enhanced Defueling Safety Cases | 2025-10-07 | 2025-10-08 | TOR Enhanced Defueling Rate: PSA Main Summary Report Technical Review | 2025-10-07 | 2025-10-08 | 2 | 2 | 2 | 0% | 11 | Not Started
ER6698LT | W224 | W224.3180 | HRA Enhanced Defueling Safety Case | 2025-10-03 | 2025-10-16 | Approval | 2025-10-08 | 2025-10-21 | 10 | 10 | 10 | 0% | 31 | Not Started
W772LT | W772 | W772LT.D2050 | DNB Pull Harder Safety Case | 2025-12-03 | 2025-12-03 | Gate D PRC Paper Submission | 2025-10-08 | 2025-10-08 | 1 | 1 | 1 | 0% | 0 | Not Started
ER6698LT | W224 | W224.2090 | HRA Enhanced Defueling Safety Case |  | 2025-10-01 | KDM - Preliminary Design Load Trace | 2025-10-08 | 2025-10-08 | 0 | 0 | 0 | 0% | 98 | Not Started
ER6698LT | W224 | W224.1820 | HRA Enhanced Defueling Safety Case |  | 2025-10-01 | KDM - KDM Issue of Load Trace Procurement Spec to Project W745 | 2025-10-08 | 2025-10-08 | 0 | 0 | 0 | 0% | 98 | Not Started
ER6701LT | W228 | W228.1820 | HYA Enhanced Defueling Safety Case |  | 2025-10-01 | KDM - Issue of Load Trace Procurement spec to Project W746 | 2025-10-08 | 2025-10-08 | 0 | 0 | 0 | 0% | 98 | Not Started
ER6701LT | W228 | W228.2090 | HYA Enhanced Defueling Safety Case |  | 2025-10-01 | KDM - Preliminary Design Load Trace | 2025-10-08 | 2025-10-08 | 0 | 0 | 0 | 0% | 98 | Not Started
W730LT_UN | W730 | W730.3790 | HYB Enhanced Defueling Safety Cases |  | 2025-10-08 | HYB Enhanced Defueling Rate: PSA Main Summary Report Issued/ Approval | 2025-10-08 | 2025-10-08 | 0 | 0 | 0 | 0% | 11 | Not Started
W731LT_UN | W731 | W731.1380 | TOR Enhanced Defueling Safety Cases |  | 2025-10-08 | TOR Enhanced Defueling Rate: PSA Main Summary Report Issued/ Approval | 2025-10-08 | 2025-10-08 | 0 | 0 | 0 | 0% | 11 | Not Started
W730LT_UN | W730 | W730.3800 | HYB Enhanced Defueling Safety Cases | 2025-10-09 | 2025-10-15 | HYB Enhanced Defueling Rate: PSA Main Summary Report Production Risk (Risk ID 42008) | 2025-10-09 | 2025-10-15 | 5 | 5 | 5 | 0% | 11 | Not Started
W731LT_UN | W731 | W731.1390 | TOR Enhanced Defueling Safety Cases | 2025-10-09 | 2025-10-15 | TOR Enhanced Defueling Rate: PSA Main Summary Report Production Risk (Risk ID 42008) | 2025-10-09 | 2025-10-15 | 5 | 5 | 5 | 0% | 11 | Not Started
ER6698LT | W224 | W224.1790 | HRA Enhanced Defueling Safety Case | 2025-09-23 | 2025-10-07 | Approval | 2025-10-14 | 2025-10-28 | 11 | 11 | 11 | 0% | 26 | Not Started
ER6701LT | W228 | W228.1790 | HYA Enhanced Defueling Safety Case | 2025-09-23 | 2025-10-07 | Approval | 2025-10-14 | 2025-10-28 | 11 | 11 | 11 | 0% | 26 | Not Started
ER6701LT | W228 | W228.4790 | HYA Enhanced Defueling Safety Case | 2025-09-26 | 2025-10-02 | INSA Final Approval *(KDM)* | 2025-10-14 | 2025-10-20 | 5 | 5 | 5 | 0% | 84 | Not Started
W730LT_UN | W730 | W730.2280 | HYB Enhanced Defueling Safety Cases | 2025-10-16 | 2025-10-22 | HYB Enhanced Defueling Rate: Produce verification plan | 2025-10-16 | 2025-10-22 | 5 | 5 | 5 | 0% | 540 | Not Started
W730LT_UN | W730 | W730.2290 | HYB Enhanced Defueling Safety Cases | 2025-10-16 | 2026-02-09 | HYB Enhanced Defueling Rate: Prepare / Author the Safety Case Proposal | 2025-10-16 | 2026-02-09 | 80 | 80 | 80 | 0% | 11 | Not Started
W730LT_UN | W730 | W730.3810 | HYB Enhanced Defueling Safety Cases | 2025-10-16 | 2025-11-05 | HYB Enhanced Defueling Rate: PSA Appendices Authoring | 2025-10-16 | 2025-11-05 | 15 | 15 | 15 | 0% | 524 | Not Started
W731LT_UN | W731 | W731.1400 | TOR Enhanced Defueling Safety Cases | 2025-10-16 | 2025-11-05 | TOR Enhanced Defueling Rate: PSA Appendices Authoring | 2025-10-16 | 2025-11-05 | 15 | 15 | 15 | 0% | 524 | Not Started
W731LT_UN | W731 | W731.1410 | TOR Enhanced Defueling Safety Cases | 2025-10-16 | 2026-02-09 | TOR Enhanced Defueling Rate: Prepare / Author the Safety Case Proposal | 2025-10-16 | 2026-02-09 | 80 | 80 | 80 | 0% | 11 | Not Started
W731LT_UN | W731 | W731.1420 | TOR Enhanced Defueling Safety Cases | 2025-10-16 | 2025-10-22 | TOR Enhanced Defueling Rate: Produce verification plan | 2025-10-16 | 2025-10-22 | 5 | 5 | 5 | 0% | 540 | Not Started
W230LT | W230 | W230.3510 | HYB Enhanced Defueling Safety Case Strategy |  | 2025-06-23 | HYB Low Decay Heat: Station Agree NSRS | 2025-10-16 | 2025-10-16 | 0 | 0 | 0 | 0% | 147 | Not Started
W230LT | W230 | W230.3560 | HYB Enhanced Defueling Safety Case Strategy |  | 2025-06-23 | HYB Low Decay Heat: Discovery Milestone - NSRS Completion - Proceed with Safety Case (HYB) | 2025-10-16 | 2025-10-16 | 0 | 0 | 0 | 0% | 147 | Not Started
W234LT | W234 | W234.3510 | TOR Enhanced Defueling Safety Case Strategy |  | 2025-06-23 | TOR Low Decay Heat: Station Agree NSRS | 2025-10-16 | 2025-10-16 | 0 | 0 | 0 | 0% | 147 | Not Started
W234LT | W234 | W234.3560 | TOR Enhanced Defueling Safety Case Strategy |  | 2025-06-23 | TOR Low Decay Heat: Discovery Milestone - NSRS Completion - Proceed with Safety Case (TOR) | 2025-10-16 | 2025-10-16 | 0 | 0 | 0 | 0% | 147 | Not Started
W230LT | W230 | W230.2620 | HYB Enhanced Defueling Safety Case Strategy | 2025-03-17 | 2025-03-21 | HYB Low Decay Heat: Circulate NSRS for Relevant Stakeholders (A-B Part) | 2025-10-17 | 2025-10-23 | 5 | 5 | 5 | 0% | 12 | Not Started
W234LT | W234 | W234.2620 | TOR Enhanced Defueling Safety Case Strategy | 2025-03-17 | 2025-03-21 | TOR Low Decay Heat: Circulate NSRS for Relevant Stakeholders (A-B Part) | 2025-10-17 | 2025-10-23 | 5 | 5 | 5 | 0% | 12 | Not Started
ER6701LT | W228 | W228.3290 | HYA Enhanced Defueling Safety Case |  | 2025-10-16 | KDM - Design Substantiation Approval | 2025-10-20 | 2025-10-20 | 0 | 0 | 0 | 0% | 90 | Not Started
ER6701LT | W228 | W228.3190 | HYA Enhanced Defueling Safety Case |  | 2025-10-16 | KDM - Design Substantiation Report Bob Weight & Gripping Sleeve | 2025-10-20 | 2025-10-20 | 0 | 0 | 0 | 0% | 32 | Not Started
W772LT | W772 | W772LT.D2060 | DNB Pull Harder Safety Case | 2025-12-16 | 2025-12-16 | Hold PRC Meeting - Gate D | 2025-10-21 | 2025-10-21 | 1 | 1 | 1 | 0% | 0 | Not Started
ER6701LT | W228 | W228.4800 | HYA Enhanced Defueling Safety Case | 2025-10-03 | 2025-10-09 | Station Approval for Mod Implementation (including station review meeting) | 2025-10-21 | 2025-10-27 | 5 | 5 | 5 | 0% | 84 | Not Started
ER6698LT | W224 | W224.3190 | HRA Enhanced Defueling Safety Case |  | 2025-10-16 | KDM - Design Substantiation Report Bob Weight & Gripping Sleeve | 2025-10-21 | 2025-10-21 | 0 | 0 | 0 | 0% | 31 | Not Started
ER6698LT | W224 | W224.3290 | HRA Enhanced Defueling Safety Case |  | 2025-10-16 | KDM - Design Substantiation Approval | 2025-10-21 | 2025-10-21 | 0 | 0 | 0 | 0% | 89 | Not Started
W772LT | W772 | W772LT.D2070 | DNB Pull Harder Safety Case |  | 2025-12-16 | Gate D PRC Paper Approval | 2025-10-21 | 2025-10-21 | 0 | 0 | 0 | 0% | 0 | Not Started
W772LT | W772 | W772LT.A2240 | DNB Pull Harder Safety Case |  | 2025-12-16 | Project Completion | 2025-10-21 | 2025-10-21 | 0 | 0 | 0 | 0% | 0 | Not Started
W230LT | W230 | W230.2660 | HYB Enhanced Defueling Safety Case Strategy | 2025-03-24 | 2025-03-24 | HYB Low Decay Heat: Send NSRS to ONR to Determine Level of Review Required (Acknowledgement or Agreemen | 2025-10-24 | 2025-10-24 | 1 | 1 | 1 | 0% | 12 | Not Started
W234LT | W234 | W234.2660 | TOR Enhanced Defueling Safety Case Strategy | 2025-03-24 | 2025-03-24 | TOR Low Decay Heat: Send NSRS to ONR to Determine Level of Review Required (Acknowledgement or Agreemen | 2025-10-24 | 2025-10-24 | 1 | 1 | 1 | 0% | 12 | Not Started
W230LT | W230 | W230.2680 | HYB Enhanced Defueling Safety Case Strategy | 2025-03-25 | 2025-04-07 | HYB Low Decay Heat: Outline Safety Case / ALARP Strategy | 2025-10-27 | 2025-11-07 | 10 | 10 | 10 | 0% | 12 | Not Started
W230LT | W230 | W230.2930 | HYB Enhanced Defueling Safety Case Strategy | 2025-03-25 | 2025-03-27 | HYB Low Decay Heat: Lessons Learned Activity - NSRS Approval | 2025-10-27 | 2025-10-29 | 3 | 3 | 3 | 0% | 120 | Not Started
W234LT | W234 | W234.2680 | TOR Enhanced Defueling Safety Case Strategy | 2025-03-25 | 2025-04-07 | TOR Low Decay Heat: Outline Safety Case / ALARP Strategy | 2025-10-27 | 2025-11-07 | 10 | 10 | 10 | 0% | 12 | Not Started
W234LT | W234 | W234.2930 | TOR Enhanced Defueling Safety Case Strategy | 2025-03-25 | 2025-03-27 | TOR Low Decay Heat: Lessons Learned Activity - NSRS Approval | 2025-10-27 | 2025-10-29 | 3 | 3 | 3 | 0% | 120 | Not Started
ER6701LT | W228 | W228.2050 | HYA Enhanced Defueling Safety Case |  | 2025-10-09 | KDM - CAT 2 EC Reduce IFDF Cooling Complete | 2025-10-27 | 2025-10-27 | 0 | 0 | 0 | 0% | 85 | Not Started
ER6701LT | W228 | W228.4810 | HYA Enhanced Defueling Safety Case |  | 2025-10-09 | Station Approval Obtained and CAT 2 Safety Case Complete *(KDM)* | 2025-10-27 | 2025-10-27 | 0 | 0 | 0 | 0% | 84 | Not Started
ER6701LT | W228 | W228.4820 | HYA Enhanced Defueling Safety Case | 2025-10-10 | 2025-10-10 | Post Job Debrief | 2025-10-28 | 2025-10-28 | 1 | 1 | 1 | 0% | 84 | Not Started
ER6698LT | W224 | W224.2110 | HRA Enhanced Defueling Safety Case |  | 2025-10-07 | KDM - Design Substantiation Report Trip Function | 2025-10-28 | 2025-10-28 | 0 | 0 | 0 | 0% | 26 | Not Started
ER6698LT | W224 | W224.2250 | HRA Enhanced Defueling Safety Case |  | 2025-10-07 | KDM - Design Substantiation Report Approval | 2025-10-28 | 2025-10-28 | 0 | 0 | 0 | 0% | 84 | Not Started
ER6701LT | W228 | W228.2250 | HYA Enhanced Defueling Safety Case |  | 2025-10-07 | KDM - Design Substantiation Report Approval | 2025-10-28 | 2025-10-28 | 0 | 0 | 0 | 0% | 84 | Not Started
ER6701LT | W228 | W228.2110 | HYA Enhanced Defueling Safety Case |  | 2025-10-07 | KDM - Design Substantiation Report Trip Function | 2025-10-28 | 2025-10-28 | 0 | 0 | 0 | 0% | 26 | Not Started
ER6698LT | W224 | W224. A1610 | HRA Enhanced Defueling Safety Case | 2025-10-17 | 2025-11-26 | W224 Tasks Closure | 2025-10-29 | 2025-12-08 | 29 | 29 | 29 | 0% | 26 | Not Started
ER6701LT | W228 | W228. A1610 | HYA Enhanced Defueling Safety Case | 2025-10-17 | 2025-11-26 | W228 Tasks Closure | 2025-10-29 | 2025-12-08 | 29 | 29 | 29 | 0% | 26 | Not Started
W230LT | W230 | W230.3640 | HYB Enhanced Defueling Safety Case Strategy |  | 2025-07-04 | HYB Low Decay Heat: Lessons Learned Milestone - NSRS Approval | 2025-10-29 | 2025-10-29 | 0 | 0 | 0 | 0% | 120 | Not Started
W234LT | W234 | W234.3640 | TOR Enhanced Defueling Safety Case Strategy |  | 2025-07-04 | TOR Low Decay Heat: Lessons Learned Milestone - NSRS Approval | 2025-10-29 | 2025-10-29 | 0 | 0 | 0 | 0% | 120 | Not Started
ER6698LT | W224 | W224.4670 | HRA Enhanced Defueling Safety Case |  | 2025-10-30 | All supporting References Completed | 2025-10-30 | 2025-10-30 | 0 | 0 | 0 | 0% | 36 | Not Started
ER6698LT | W224 | W224.4680 | HRA Enhanced Defueling Safety Case | 2025-10-31 | 2025-11-20 | Verification of the case (using BARRIER MODEL) | 2025-10-31 | 2025-11-20 | 15 | 15 | 15 | 0% | 36 | Not Started
ER6701LT | W228 | W228.5430 | HYA Enhanced Defueling Safety Case |  | 2025-10-29 | All supporting References Completed | 2025-10-31 | 2025-10-31 | 0 | 0 | 0 | 0% | 30 | Not Started
ER6701LT | W228 | W228.5440 | HYA Enhanced Defueling Safety Case | 2025-10-30 | 2025-11-26 | Verification of the case (using BARRIER MODEL) | 2025-11-03 | 2025-11-28 | 20 | 20 | 20 | 0% | 30 | Not Started
ER6698LT | W224 | W224.5430 | HRA Enhanced Defueling Safety Case |  | 2025-10-29 | All supporting References Completed | 2025-11-03 | 2025-11-03 | 0 | 0 | 0 | 0% | 29 | Not Started
ER6698LT | W224 | W224.5440 | HRA Enhanced Defueling Safety Case | 2025-10-30 | 2025-11-26 | Verification of the case (using BARRIER MODEL) | 2025-11-04 | 2025-12-01 | 20 | 20 | 20 | 0% | 29 | Not Started
W730LT_UN | W730 | W730.3820 | HYB Enhanced Defueling Safety Cases | 2025-11-06 | 2025-11-07 | HYB Enhanced Defueling Rate: PSA Appendices Verification | 2025-11-06 | 2025-11-07 | 2 | 2 | 2 | 0% | 524 | Not Started
W731LT_UN | W731 | W731.1430 | TOR Enhanced Defueling Safety Cases | 2025-11-06 | 2025-11-07 | TOR Enhanced Defueling Rate: PSA Appendices Verification | 2025-11-06 | 2025-11-07 | 2 | 2 | 2 | 0% | 524 | Not Started
W230LT | W230 | W230.3540 | HYB Enhanced Defueling Safety Case Strategy |  | 2025-07-15 | HYB Low Decay Heat: Optioneering Complete (Outline Safety Case / ALARP Strategy) | 2025-11-07 | 2025-11-07 | 0 | 0 | 0 | 0% | 71 | Not Started
W234LT | W234 | W234.3540 | TOR Enhanced Defueling Safety Case Strategy |  | 2025-07-15 | TOR Low Decay Heat: Optioneering Complete (Outline Safety Case / ALARP Strategy) | 2025-11-07 | 2025-11-07 | 0 | 0 | 0 | 0% | 71 | Not Started
ER6698LT | W224 | W224.3780 | HRA Enhanced Defueling Safety Case | 2025-11-10 | 2026-01-07 | INSA | 2025-11-10 | 2026-01-07 | 40 | 40 | 40 | 0% | 36 | Not Started
ER6701LT | W228 | W228.3780 | HYA Enhanced Defueling Safety Case | 2025-11-07 | 2026-01-06 | INSA | 2025-11-10 | 2026-01-07 | 40 | 40 | 40 | 0% | 36 | Not Started
W230LT | W230 | W230.2950 | HYB Enhanced Defueling Safety Case Strategy | 2025-02-21 | 2025-07-15 | ## HYB Reactor Inspections Relaxations: A - D Phase Funding - (Cost Summary) ## | 2025-11-10 | 2026-03-31 | 99 | 99 | 99 | 0% | 32 | Not Started
W230LT | W230 | W230.3080 | HYB Enhanced Defueling Safety Case Strategy | 2025-02-21 | 2025-03-10 | HYB Reactor Inspections Relaxations: Strategy Development & Produce MF EC NNNNN & Obtain Approval | 2025-11-10 | 2025-11-25 | 12 | 12 | 12 | 0% | 12 | Not Started
W234LT | W234 | W234.2950 | TOR Enhanced Defueling Safety Case Strategy | 2025-02-21 | 2025-07-15 | ## TOR Reactor Inspections Relaxations: A - D Phase Funding - (Cost Summary) ## | 2025-11-10 | 2026-03-31 | 99 | 99 | 99 | 0% | 32 | Not Started
W234LT | W234 | W234.3080 | TOR Enhanced Defueling Safety Case Strategy | 2025-02-21 | 2025-03-10 | TOR Reactor Inspections Relaxations: Strategy Development & Produce MF EC NNNNN & Obtain Approval | 2025-11-10 | 2025-11-25 | 12 | 12 | 12 | 0% | 12 | Not Started
W730LT_UN | W730 | W730.3830 | HYB Enhanced Defueling Safety Cases | 2025-11-10 | 2025-11-11 | HYB Enhanced Defueling Rate: PSA Appendices Technical Review | 2025-11-10 | 2025-11-11 | 2 | 2 | 2 | 0% | 524 | Not Started
W731LT_UN | W731 | W731.1440 | TOR Enhanced Defueling Safety Cases | 2025-11-10 | 2025-11-11 | TOR Enhanced Defueling Rate: PSA Appendices Technical Review | 2025-11-10 | 2025-11-11 | 2 | 2 | 2 | 0% | 524 | Not Started
W730LT_UN | W730 | W730.3840 | HYB Enhanced Defueling Safety Cases |  | 2025-11-11 | HYB Enhanced Defueling Rate: PSA Appendices Issued/ Approval | 2025-11-11 | 2025-11-11 | 0 | 0 | 0 | 0% | 524 | Not Started
W731LT_UN | W731 | W731.1450 | TOR Enhanced Defueling Safety Cases |  | 2025-11-11 | TOR Enhanced Defueling Rate: PSA Appendices Issued/ Approval | 2025-11-11 | 2025-11-11 | 0 | 0 | 0 | 0% | 524 | Not Started
W730LT_UN | W730 | W730.3850 | HYB Enhanced Defueling Safety Cases | 2025-11-12 | 2025-11-18 | HYB Enhanced Defueling Rate: PSA Appendices Production Risk (Risk ID 42008) | 2025-11-12 | 2025-11-18 | 5 | 5 | 5 | 0% | 524 | Not Started
W731LT_UN | W731 | W731.1460 | TOR Enhanced Defueling Safety Cases | 2025-11-12 | 2025-11-18 | TOR Enhanced Defueling Rate: PSA Appendices Production Risk (Risk ID 42008) | 2025-11-12 | 2025-11-18 | 5 | 5 | 5 | 0% | 524 | Not Started
ER6698LT | W224 | W224.4290 | HRA Enhanced Defueling Safety Case |  | 2025-11-14 | All supporting References Completed | 2025-11-14 | 2025-11-14 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4290 | HYA Enhanced Defueling Safety Case |  | 2025-11-14 | All supporting References Completed | 2025-11-14 | 2025-11-14 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6698LT | W224 | W224.4300 | HRA Enhanced Defueling Safety Case | 2025-11-17 | 2025-12-12 | Verification of the Case (using BARRIER MODEL) | 2025-11-17 | 2025-12-12 | 20 | 20 | 20 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4300 | HYA Enhanced Defueling Safety Case | 2025-11-17 | 2025-12-12 | Verification of the Case (using BARRIER MODEL) | 2025-11-17 | 2025-12-12 | 20 | 20 | 20 | 0% | 20 | Not Started
W232LT | W232 | W232.A5160 | DNB Enhanced Safety Cases |  | 2025-12-23 | Rev 001 - Issue to CO & Station for comments | 2025-11-17 | 2025-11-17 | 0 | 0 | 0 | 0% | 5 | Not Started
W232LT | W232 | W232.A5060 | DNB Enhanced Safety Cases | 2025-12-24 | 2026-01-02 | Rev 001 - Incorporate CO & Station comments | 2025-11-18 | 2025-11-24 | 5 | 5 | 5 | 0% | 5 | Not Started
W232LT | W232 | W232.A5090 | DNB Enhanced Safety Cases | 2025-12-24 | 2025-12-29 | Rev 001 - Produce verification file | 2025-11-18 | 2025-11-19 | 2 | 2 | 2 | 0% | 8 | Not Started
W232LT | W232 | W232.A5140 | DNB Enhanced Safety Cases | 2025-12-29 | 2026-01-05 | Rev 001 - Key Stakeholders Approval, if requested | 2025-11-19 | 2025-11-25 | 5 | 5 | 5 | 0% | 40 | Not Started
W730LT_UN | W730 | W730.3860 | HYB Enhanced Defueling Safety Cases | 2025-11-19 | 2025-12-09 | HYB Enhanced Defueling Rate: Worker Risk Authoring | 2025-11-19 | 2025-12-09 | 15 | 15 | 15 | 0% | 524 | Not Started
W731LT_UN | W731 | W731.1470 | TOR Enhanced Defueling Safety Cases | 2025-11-19 | 2025-12-09 | TOR Enhanced Defueling Rate: Worker Risk Authoring | 2025-11-19 | 2025-12-09 | 15 | 15 | 15 | 0% | 524 | Not Started
ER6698LT | W224 | W224.4690 | HRA Enhanced Defueling Safety Case |  | 2025-11-20 | Issue to CO & Station for Comments | 2025-11-20 | 2025-11-20 | 0 | 0 | 0 | 0% | 36 | Not Started
ER6698LT | W224 | W224.4700 | HRA Enhanced Defueling Safety Case | 2025-11-21 | 2025-11-27 | Incorporate CO & Station Comments | 2025-11-21 | 2025-11-27 | 5 | 5 | 5 | 0% | 36 | Not Started
ER6698LT | W224 | W224.4710 | HRA Enhanced Defueling Safety Case | 2025-11-21 | 2025-11-24 | Produce Verification File | 2025-11-21 | 2025-11-24 | 2 | 2 | 2 | 0% | 39 | Not Started
W232LT | W232 | W232.A5120 | DNB Enhanced Safety Cases |  | 2026-01-02 | Rev 001 - Verification complete | 2025-11-24 | 2025-11-24 | 0 | 0 | 0 | 0% | 5 | Not Started
W232LT | W232 | W232.A5300 | DNB Enhanced Safety Cases |  | 2026-01-02 | Safety Case Verification Complete - Rev 001 | 2025-11-24 | 2025-11-24 | 0 | 0 | 0 | 0% | 6 | Not Started
W232LT | W232 | W232.A5530 | DNB Enhanced Safety Cases |  |  | Lessons Learned Workshop - FPU Safety Case Ph 3 Rev 001 Verified | 2025-11-25 | 2025-11-25 | 1 | 1 | 1 | 0% | 5 | Not Started
W232LT | W232 | W232.A5100 | DNB Enhanced Safety Cases |  | 2026-01-05 | Rev 001 - Verified Draft Issue A with verification file to INSA & station *(KDM)* | 2025-11-25 | 2025-11-25 | 0 | 0 | 0 | 0% | 5 | Not Started
W232LT | W232 | W232.A5130 | DNB Enhanced Safety Cases |  | 2026-01-05 | Rev 001 - Submit for approval - Categoriser ratifies; RE/CO endorsement | 2025-11-25 | 2025-11-25 | 0 | 0 | 0 | 0% | 5 | Not Started
W232LT | W232 | W232.A5110 | DNB Enhanced Safety Cases | 2026-01-06 | 2026-02-02 | Rev 001 - INSA review & iteration of comments (using BARRIER MODEL) | 2025-11-26 | 2026-01-09 | 30 | 30 | 30 | 0% | 5 | Not Started
W230LT | W230 | W230.3090 | HYB Enhanced Defueling Safety Case Strategy | 2025-03-11 | 2025-03-26 | HYB Reactor Inspections Relaxations: Mod Requested and EC Request Raised and Screened | 2025-11-26 | 2025-12-11 | 12 | 12 | 12 | 0% | 12 | Not Started
W234LT | W234 | W234.3090 | TOR Enhanced Defueling Safety Case Strategy | 2025-03-11 | 2025-03-26 | TOR Reactor Inspections Relaxations: Mod Requested and EC Request Raised and Screened | 2025-11-26 | 2025-12-11 | 12 | 12 | 12 | 0% | 12 | Not Started
ER6698LT | W224 | W224.4720 | HRA Enhanced Defueling Safety Case |  | 2025-11-27 | Issue High Quality Verified Draft Issue A with Verification File to INSA & Station (T - 3 weeks before NSC date) *(KDM)* | 2025-11-27 | 2025-11-27 | 0 | 0 | 0 | 0% | 36 | Not Started
ER6698LT | W224 | W224.4730 | HRA Enhanced Defueling Safety Case |  | 2025-11-27 | Verification Complete | 2025-11-27 | 2025-11-27 | 0 | 0 | 0 | 0% | 36 | Not Started
ER6698LT | W224 | W224.4740 | HRA Enhanced Defueling Safety Case |  | 2025-11-27 | Submit for Approval - Categoriser Ratifies; RE/CO Endorsement | 2025-11-27 | 2025-11-27 | 0 | 0 | 0 | 0% | 36 | Not Started
ER6698LT | W224 | W224.4750 | HRA Enhanced Defueling Safety Case |  | 2025-11-27 | NSORC Agreed Paper (SZB Only & as required) | 2025-11-27 | 2025-11-27 | 0 | 0 | 0 | 0% | 36 | Not Started
ER6698LT | W224 | W224.4760 | HRA Enhanced Defueling Safety Case | 2025-11-28 | 2025-12-11 | INSA Review & Iteration of Comments (using BARRIER MODEL) | 2025-11-28 | 2025-12-11 | 10 | 10 | 10 | 0% | 36 | Not Started
ER6698LT | W224 | W224.4770 | HRA Enhanced Defueling Safety Case | 2025-11-28 | 2025-12-04 | Key Stakeholders Approval, if Requested | 2025-11-28 | 2025-12-04 | 5 | 5 | 5 | 0% | 46 | Not Started
ER6701LT | W228 | W228.5450 | HYA Enhanced Defueling Safety Case |  | 2025-11-26 | Issue to CO & Station for Comments | 2025-11-28 | 2025-11-28 | 0 | 0 | 0 | 0% | 30 | Not Started
ER6701LT | W228 | W228.5460 | HYA Enhanced Defueling Safety Case | 2025-11-27 | 2025-12-03 | Incorporate CO & Station Comments | 2025-12-01 | 2025-12-05 | 5 | 5 | 5 | 0% | 30 | Not Started
ER6701LT | W228 | W228.5470 | HYA Enhanced Defueling Safety Case | 2025-11-27 | 2025-11-28 | Produce Verification File | 2025-12-01 | 2025-12-02 | 2 | 2 | 2 | 0% | 33 | Not Started
ER6698LT | W224 | W224.5450 | HRA Enhanced Defueling Safety Case |  | 2025-11-26 | Issue to CO & Station for Comments | 2025-12-01 | 2025-12-01 | 0 | 0 | 0 | 0% | 29 | Not Started
ER6698LT | W224 | W224.5460 | HRA Enhanced Defueling Safety Case | 2025-11-27 | 2025-12-03 | Incorporate CO & Station Comments | 2025-12-02 | 2025-12-08 | 5 | 5 | 5 | 0% | 29 | Not Started
ER6698LT | W224 | W224.5470 | HRA Enhanced Defueling Safety Case | 2025-11-27 | 2025-11-28 | Produce Verification File | 2025-12-02 | 2025-12-03 | 2 | 2 | 2 | 0% | 32 | Not Started
ER6701LT | W228 | W228.5480 | HYA Enhanced Defueling Safety Case |  | 2025-12-03 | Issue High Quality Verified Draft Issue A with Verification File to INSA & Station (T - 3 weeks before NSC date) *(KDM)* | 2025-12-05 | 2025-12-05 | 0 | 0 | 0 | 0% | 30 | Not Started
ER6701LT | W228 | W228.5490 | HYA Enhanced Defueling Safety Case |  | 2025-12-03 | Verification Complete | 2025-12-05 | 2025-12-05 | 0 | 0 | 0 | 0% | 30 | Not Started
ER6701LT | W228 | W228.5500 | HYA Enhanced Defueling Safety Case |  | 2025-12-03 | Submit for Approval - Categoriser Ratifies; RE/CO Endorsement | 2025-12-05 | 2025-12-05 | 0 | 0 | 0 | 0% | 30 | Not Started
ER6701LT | W228 | W228.5510 | HYA Enhanced Defueling Safety Case |  | 2025-12-03 | NSORC Agreed Paper (SZB Only & as required) | 2025-12-05 | 2025-12-05 | 0 | 0 | 0 | 0% | 30 | Not Started
ER6698LT | W224 | W224.3790 | HRA Enhanced Defueling Safety Case | 2025-12-08 | 2026-01-07 | Approval | 2025-12-08 | 2026-01-07 | 20 | 20 | 20 | 0% | 36 | Not Started
ER6701LT | W228 | W228.3790 | HYA Enhanced Defueling Safety Case | 2025-12-05 | 2026-01-06 | Approval | 2025-12-08 | 2026-01-07 | 20 | 20 | 20 | 0% | 36 | Not Started
ER6701LT | W228 | W228.5520 | HYA Enhanced Defueling Safety Case | 2025-12-04 | 2025-12-17 | INSA Review & Iteration of Comments (using BARRIER MODEL) | 2025-12-08 | 2025-12-19 | 10 | 10 | 10 | 0% | 30 | Not Started
ER6701LT | W228 | W228.5530 | HYA Enhanced Defueling Safety Case | 2025-12-04 | 2025-12-10 | Key Stakeholders Approval, if Requested | 2025-12-08 | 2025-12-12 | 5 | 5 | 5 | 0% | 40 | Not Started
ER6698LT | W224 | W224.5480 | HRA Enhanced Defueling Safety Case |  | 2025-12-03 | Issue High Quality Verified Draft Issue A with Verification File to INSA & Station (T - 3 weeks before NSC date) *(KDM)* | 2025-12-08 | 2025-12-08 | 0 | 0 | 0 | 0% | 29 | Not Started
ER6698LT | W224 | W224.5490 | HRA Enhanced Defueling Safety Case |  | 2025-12-03 | Verification Complete | 2025-12-08 | 2025-12-08 | 0 | 0 | 0 | 0% | 29 | Not Started
ER6698LT | W224 | W224.5500 | HRA Enhanced Defueling Safety Case |  | 2025-12-03 | Submit for Approval - Categoriser Ratifies; RE/CO Endorsement | 2025-12-08 | 2025-12-08 | 0 | 0 | 0 | 0% | 29 | Not Started
ER6698LT | W224 | W224.5510 | HRA Enhanced Defueling Safety Case |  | 2025-12-03 | NSORC Agreed Paper (SZB Only & as required) | 2025-12-08 | 2025-12-08 | 0 | 0 | 0 | 0% | 29 | Not Started
ER6698LT | W224 | W224. A1500 | HRA Enhanced Defueling Safety Case | 2025-11-27 | 2025-12-16 | Write IRM Paper [Schedule, Cost, Estimates, Risks] | 2025-12-09 | 2025-12-30 | 14 | 14 | 14 | 0% | 26 | Not Started
ER6701LT | W228 | W228. A1500 | HYA Enhanced Defueling Safety Case | 2025-11-27 | 2025-12-16 | Write IRM Paper | 2025-12-09 | 2025-12-30 | 14 | 14 | 14 | 0% | 26 | Not Started
ER6698LT | W224 | W224.5520 | HRA Enhanced Defueling Safety Case | 2025-12-04 | 2025-12-17 | INSA Review & Iteration of Comments (using BARRIER MODEL) | 2025-12-09 | 2025-12-22 | 10 | 10 | 10 | 0% | 29 | Not Started
ER6698LT | W224 | W224.5530 | HRA Enhanced Defueling Safety Case | 2025-12-04 | 2025-12-10 | Key Stakeholders Approval, if Requested | 2025-12-09 | 2025-12-15 | 5 | 5 | 5 | 0% | 39 | Not Started
W730LT_UN | W730 | W730.3870 | HYB Enhanced Defueling Safety Cases | 2025-12-10 | 2025-12-11 | HYB Enhanced Defueling Rate: Worker Risk Verification | 2025-12-10 | 2025-12-11 | 2 | 2 | 2 | 0% | 524 | Not Started
W731LT_UN | W731 | W731.1480 | TOR Enhanced Defueling Safety Cases | 2025-12-10 | 2025-12-11 | TOR Enhanced Defueling Rate: Worker Risk Verification | 2025-12-10 | 2025-12-11 | 2 | 2 | 2 | 0% | 524 | Not Started
W230LT | W230 | W230.3040 | HYB Enhanced Defueling Safety Case Strategy | 2025-03-27 | 2025-04-09 | HYB Reactor Inspections Relaxations: Produce draft NSRS (using BARRIER MODEL) | 2025-12-12 | 2025-12-29 | 10 | 10 | 10 | 0% | 12 | Not Started
ER6698LT | W224 | W224.4780 | HRA Enhanced Defueling Safety Case | 2025-12-12 | 2025-12-18 | Incorporate INSA Comments | 2025-12-12 | 2025-12-18 | 5 | 5 | 5 | 0% | 36 | Not Started
W234LT | W234 | W234.3040 | TOR Enhanced Defueling Safety Case Strategy | 2025-03-27 | 2025-04-09 | TOR Reactor Inspections Relaxations: Produce draft NSRS (using BARRIER MODEL) | 2025-12-12 | 2025-12-29 | 10 | 10 | 10 | 0% | 12 | Not Started
W730LT_UN | W730 | W730.3880 | HYB Enhanced Defueling Safety Cases | 2025-12-12 | 2025-12-15 | HYB Enhanced Defueling Rate: Worker Risk Technical Review | 2025-12-12 | 2025-12-15 | 2 | 2 | 2 | 0% | 524 | Not Started
W731LT_UN | W731 | W731.1490 | TOR Enhanced Defueling Safety Cases | 2025-12-12 | 2025-12-15 | TOR Enhanced Defueling Rate: Worker Risk Technical Review | 2025-12-12 | 2025-12-15 | 2 | 2 | 2 | 0% | 524 | Not Started
ER6698LT | W224 | W224.4310 | HRA Enhanced Defueling Safety Case |  | 2025-12-12 | Issue to CO & Station for Comments | 2025-12-12 | 2025-12-12 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6698LT | W224 | W224.5050 | HRA Enhanced Defueling Safety Case |  | 2025-12-05 | All Supporting References Completed | 2025-12-12 | 2025-12-12 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6701LT | W228 | W228.4310 | HYA Enhanced Defueling Safety Case |  | 2025-12-12 | Issue to CO & Station for Comments | 2025-12-12 | 2025-12-12 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6701LT | W228 | W228.5050 | HYA Enhanced Defueling Safety Case |  | 2025-12-05 | All Supporting References Completed | 2025-12-12 | 2025-12-12 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6698LT | W224 | W224.4320 | HRA Enhanced Defueling Safety Case | 2025-12-15 | 2025-12-19 | Incorporate CO & Station Comments | 2025-12-15 | 2025-12-19 | 5 | 5 | 5 | 0% | 20 | Not Started
ER6698LT | W224 | W224.4330 | HRA Enhanced Defueling Safety Case | 2025-12-15 | 2025-12-16 | Produce Verification File | 2025-12-15 | 2025-12-16 | 2 | 2 | 2 | 0% | 23 | Not Started
ER6698LT | W224 | W224.5060 | HRA Enhanced Defueling Safety Case | 2025-12-08 | 2026-01-07 | Verification of the Case (using BARRIER MODEL) | 2025-12-15 | 2026-01-14 | 20 | 20 | 20 | 0% | 0 | Not Started
ER6701LT | W228 | W228.4320 | HYA Enhanced Defueling Safety Case | 2025-12-15 | 2025-12-19 | Incorporate CO & Station Comments | 2025-12-15 | 2025-12-19 | 5 | 5 | 5 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4330 | HYA Enhanced Defueling Safety Case | 2025-12-15 | 2025-12-16 | Produce Verification File | 2025-12-15 | 2025-12-16 | 2 | 2 | 2 | 0% | 23 | Not Started
ER6701LT | W228 | W228.5060 | HYA Enhanced Defueling Safety Case | 2025-12-08 | 2026-01-07 | Verification of the Case (using BARRIER MODEL) | 2025-12-15 | 2026-01-14 | 20 | 20 | 20 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3890 | HYB Enhanced Defueling Safety Cases |  | 2025-12-15 | HYB Enhanced Defueling Rate: Worker Risk Issued/ Approval | 2025-12-15 | 2025-12-15 | 0 | 0 | 0 | 0% | 524 | Not Started
W731LT_UN | W731 | W731.1500 | TOR Enhanced Defueling Safety Cases |  | 2025-12-15 | TOR Enhanced Defueling Rate: Worker Risk Issued/ Approval | 2025-12-15 | 2025-12-15 | 0 | 0 | 0 | 0% | 524 | Not Started
W730LT_UN | W730 | W730.3900 | HYB Enhanced Defueling Safety Cases | 2025-12-16 | 2025-12-22 | HYB Enhanced Defueling Rate: Worker Risk Production Risk (Risk 42008) | 2025-12-16 | 2025-12-22 | 5 | 5 | 5 | 0% | 524 | Not Started
W731LT_UN | W731 | W731.1510 | TOR Enhanced Defueling Safety Cases | 2025-12-16 | 2025-12-22 | TOR Enhanced Defueling Rate: Worker Risk Production Risk (Risk 42008) | 2025-12-16 | 2025-12-22 | 5 | 5 | 5 | 0% | 524 | Not Started
ER6698LT | W224 | W224.4790 | HRA Enhanced Defueling Safety Case | 2025-12-19 | 2025-12-29 | INSA Final Approval *(KDM)* | 2025-12-19 | 2025-12-29 | 5 | 5 | 5 | 0% | 36 | Not Started
ER6698LT | W224 | W224.4340 | HRA Enhanced Defueling Safety Case |  | 2025-12-19 | Issue High Quality Verified Draft Issue A with Verification File to INSA & Station (T - 3 weeks before NSC date) *(KDM)* | 2025-12-19 | 2025-12-19 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6698LT | W224 | W224.4350 | HRA Enhanced Defueling Safety Case |  | 2025-12-19 | Verification Complete | 2025-12-19 | 2025-12-19 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6698LT | W224 | W224.4360 | HRA Enhanced Defueling Safety Case |  | 2025-12-19 | Submit for Approval - Categoriser Ratifies; RE/CO Endorsement | 2025-12-19 | 2025-12-19 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6698LT | W224 | W224.4370 | HRA Enhanced Defueling Safety Case |  | 2025-12-19 | NSORC Agreed Paper (SZB Only & as required) | 2025-12-19 | 2025-12-19 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4340 | HYA Enhanced Defueling Safety Case |  | 2025-12-19 | Issue High Quality Verified Draft Issue A with Verification File to INSA & Station (T - 3 weeks before NSC date) *(KDM)* | 2025-12-19 | 2025-12-19 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4350 | HYA Enhanced Defueling Safety Case |  | 2025-12-19 | Verification Complete | 2025-12-19 | 2025-12-19 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4360 | HYA Enhanced Defueling Safety Case |  | 2025-12-19 | Submit for Approval - Categoriser Ratifies; RE/CO Endorsement | 2025-12-19 | 2025-12-19 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4370 | HYA Enhanced Defueling Safety Case |  | 2025-12-19 | NSORC Agreed Paper (SZB Only & as required) | 2025-12-19 | 2025-12-19 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6698LT | W224 | W224.4380 | HRA Enhanced Defueling Safety Case | 2025-12-22 | 2026-01-07 | INSA review & Iteration of Comments (using BARRIER MODEL) | 2025-12-22 | 2026-01-07 | 10 | 10 | 10 | 0% | 20 | Not Started
ER6698LT | W224 | W224.4390 | HRA Enhanced Defueling Safety Case | 2025-12-22 | 2025-12-30 | Key Stakeholders Approval, if Requested | 2025-12-22 | 2025-12-30 | 5 | 5 | 5 | 0% | 30 | Not Started
ER6701LT | W228 | W228.4380 | HYA Enhanced Defueling Safety Case | 2025-12-22 | 2026-01-07 | INSA review & Iteration of Comments (using BARRIER MODEL) | 2025-12-22 | 2026-01-07 | 10 | 10 | 10 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4390 | HYA Enhanced Defueling Safety Case | 2025-12-22 | 2025-12-30 | Key Stakeholders Approval, if Requested | 2025-12-22 | 2025-12-30 | 5 | 5 | 5 | 0% | 30 | Not Started
ER6701LT | W228 | W228.5540 | HYA Enhanced Defueling Safety Case | 2025-12-18 | 2025-12-24 | Incorporate INSA Comments | 2025-12-22 | 2025-12-30 | 5 | 5 | 5 | 0% | 30 | Not Started
ER6698LT | W224 | W224.5540 | HRA Enhanced Defueling Safety Case | 2025-12-18 | 2025-12-24 | Incorporate INSA Comments | 2025-12-23 | 2025-12-31 | 5 | 5 | 5 | 0% | 29 | Not Started
W730LT_UN | W730 | W730.3910 | HYB Enhanced Defueling Safety Cases | 2025-12-23 | 2026-01-15 | HYB Enhanced Defueling Rate: Deterministic Assessment Authoring | 2025-12-23 | 2026-01-15 | 15 | 15 | 15 | 0% | 524 | Not Started
W731LT_UN | W731 | W731.1520 | TOR Enhanced Defueling Safety Cases | 2025-12-23 | 2026-01-15 | TOR Enhanced Defueling Rate: Deterministic Assessment Authoring | 2025-12-23 | 2026-01-15 | 15 | 15 | 15 | 0% | 524 | Not Started
W230LT | W230 | W230.3100 | HYB Enhanced Defueling Safety Case Strategy | 2025-04-10 | 2025-04-16 | HYB Reactor Inspections Relaxations: Hold Case Conference / Optioneering Strategy Workshop as Appropriate | 2025-12-30 | 2026-01-06 | 5 | 5 | 5 | 0% | 12 | Not Started
ER6698LT | W224 | W224.4800 | HRA Enhanced Defueling Safety Case | 2025-12-30 | 2026-01-06 | Station Approval for Mod Implementation (including station review meeting) | 2025-12-30 | 2026-01-06 | 5 | 5 | 5 | 0% | 36 | Not Started
W234LT | W234 | W234.3100 | TOR Enhanced Defueling Safety Case Strategy | 2025-04-10 | 2025-04-16 | TOR Reactor Inspections Relaxations: Hold Case Conference / Optioneering Strategy Workshop as Appropriate | 2025-12-30 | 2026-01-06 | 5 | 5 | 5 | 0% | 12 | Not Started
ER6698LT | W224 | W224. A1510 | HRA Enhanced Defueling Safety Case | 2025-12-17 | 2025-12-22 | IRM Paper stakeholder sign off | 2025-12-31 | 2026-01-06 | 4 | 4 | 4 | 0% | 26 | Not Started
ER6701LT | W228 | W228. A1510 | HYA Enhanced Defueling Safety Case | 2025-12-17 | 2025-12-22 | IRM Paper stakeholder sign off | 2025-12-31 | 2026-01-06 | 4 | 4 | 4 | 0% | 26 | Not Started
ER6701LT | W228 | W228.5550 | HYA Enhanced Defueling Safety Case | 2025-12-29 | 2026-01-05 | INSA Final Approval *(KDM)* | 2025-12-31 | 2026-01-07 | 5 | 5 | 5 | 0% | 30 | Not Started
W520LT | W520 | W520.A1280 | FLEETWIDE CTO Defueling Safety Case Delivery |  |  | 2026 Costs | 02-Jan-26* | 2026-12-28 | 251 | 251 | 251 | 0% | 0 | Not Started
W520LT | W520 | W520.A1310 | FLEETWIDE CTO Defueling Safety Case Delivery |  |  | ETC (DD-PF) 2026 | 02-Jan-26* | 2026-12-28 | 251 | 251 | 251 | 0% | 0 | Not Started
ER6698LT | W224 | W224.5550 | HRA Enhanced Defueling Safety Case | 2025-12-29 | 2026-01-05 | INSA Final Approval *(KDM)* | 2026-01-02 | 2026-01-08 | 5 | 5 | 5 | 0% | 29 | Not Started
ER6698LT | W224 | W224.2050 | HRA Enhanced Defueling Safety Case |  | 2026-01-06 | KDM - CAT 2 EC Reduce IFDF Cooling Complete | 2026-01-06 | 2026-01-06 | 0 | 0 | 0 | 0% | 37 | Not Started
ER6698LT | W224 | W224.4810 | HRA Enhanced Defueling Safety Case |  | 2026-01-06 | Station Approval Obtained and CAT 2 Safety Case Complete *(KDM)* | 2026-01-06 | 2026-01-06 | 0 | 0 | 0 | 0% | 36 | Not Started
ER6698LT | W224 | W224. A1520 | HRA Enhanced Defueling Safety Case |  | 2026-01-07 | Gate D PRC Paper Submission | 2026-01-07 | 2026-01-07 | 0 | 0 | 0 | 0% | 2 | Not Started
ER6701LT | W228 | W228. A1520 | HYA Enhanced Defueling Safety Case |  | 2026-01-07 | Gate D PRC Paper Submission | 2026-01-07 | 2026-01-07 | 0 | 0 | 0 | 0% | 2 | Not Started
W230LT | W230 | W230.3030 | HYB Enhanced Defueling Safety Case Strategy | 2025-04-17 | 2025-05-02 | HYB Reactor Inspections Relaxations: Station comments on NSRS | 2026-01-07 | 2026-01-20 | 10 | 10 | 10 | 0% | 12 | Not Started
W230LT | W230 | W230.3120 | HYB Enhanced Defueling Safety Case Strategy | 2025-04-17 | 2025-05-02 | HYB Reactor Inspections Relaxations: DA (Peer) Comments on NSRS | 2026-01-07 | 2026-01-20 | 10 | 10 | 10 | 0% | 12 | Not Started
ER6698LT | W224 | W224.4820 | HRA Enhanced Defueling Safety Case | 2026-01-07 | 2026-01-07 | Post Job Debrief | 2026-01-07 | 2026-01-07 | 1 | 1 | 1 | 0% | 36 | Not Started
W234LT | W234 | W234.3030 | TOR Enhanced Defueling Safety Case Strategy | 2025-04-17 | 2025-05-02 | TOR Reactor Inspections Relaxations: Station comments on NSRS | 2026-01-07 | 2026-01-20 | 10 | 10 | 10 | 0% | 12 | Not Started
W234LT | W234 | W234.3120 | TOR Enhanced Defueling Safety Case Strategy | 2025-04-17 | 2025-05-02 | TOR Reactor Inspections Relaxations: DA (Peer) Comments on NSRS | 2026-01-07 | 2026-01-20 | 10 | 10 | 10 | 0% | 12 | Not Started
ER6698LT | W224 | W224.3800 | HRA Enhanced Defueling Safety Case |  | 2026-01-07 | KDM - CAT 2 Principal level Safety Case / Approved | 2026-01-07 | 2026-01-07 | 0 | 0 | 0 | 0% | 36 | Not Started
ER6701LT | W228 | W228.3800 | HYA Enhanced Defueling Safety Case |  | 2026-01-06 | KDM - CAT 2 Principal level Safety Case / Approved | 2026-01-07 | 2026-01-07 | 0 | 0 | 0 | 0% | 36 | Not Started
ER6698LT | W224 | W224.4400 | HRA Enhanced Defueling Safety Case | 2026-01-08 | 2026-01-14 | Incorporate INSA Comments | 2026-01-08 | 2026-01-14 | 5 | 5 | 5 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4400 | HYA Enhanced Defueling Safety Case | 2026-01-08 | 2026-01-14 | Incorporate INSA Comments | 2026-01-08 | 2026-01-14 | 5 | 5 | 5 | 0% | 20 | Not Started
ER6701LT | W228 | W228.5560 | HYA Enhanced Defueling Safety Case | 2026-01-06 | 2026-01-12 | Station Approval for Mod Implementation (including station review meeting) | 2026-01-08 | 2026-01-14 | 5 | 5 | 5 | 0% | 30 | Not Started
ER6698LT | W224 | W224.5560 | HRA Enhanced Defueling Safety Case | 2026-01-06 | 2026-01-12 | Station Approval for Mod Implementation (including station review meeting) | 2026-01-09 | 2026-01-15 | 5 | 5 | 5 | 0% | 29 | Not Started
W232LT | W232 | W232.A5170 | DNB Enhanced Safety Cases | 2026-02-03 | 2026-02-09 | Rev 001 - Incorporate INSA comments | 2026-01-12 | 2026-01-16 | 5 | 5 | 5 | 0% | 5 | Not Started
ER6701LT | W228 | W228.2060 | HYA Enhanced Defueling Safety Case |  | 2026-01-12 | KDM - CAT 2 Tie Bar and Bob Weight Complete | 2026-01-14 | 2026-01-14 | 0 | 0 | 0 | 0% | 31 | Not Started
ER6698LT | W224 | W224.5070 | HRA Enhanced Defueling Safety Case |  | 2026-01-07 | Issue to CO & Station for Comments | 2026-01-14 | 2026-01-14 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6701LT | W228 | W228.5070 | HYA Enhanced Defueling Safety Case |  | 2026-01-07 | Issue to CO & Station for Comments | 2026-01-14 | 2026-01-14 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6701LT | W228 | W228.5570 | HYA Enhanced Defueling Safety Case |  | 2026-01-12 | Station Approval Obtained and CAT 2 Safety Case Complete *(KDM)* | 2026-01-14 | 2026-01-14 | 0 | 0 | 0 | 0% | 30 | Not Started
ER6698LT | W224 | W224.4410 | HRA Enhanced Defueling Safety Case | 2026-01-15 | 2026-01-21 | INSA Final Approval *(KDM)* | 2026-01-15 | 2026-01-21 | 5 | 5 | 5 | 0% | 20 | Not Started
ER6698LT | W224 | W224.5080 | HRA Enhanced Defueling Safety Case | 2026-01-08 | 2026-01-14 | Incorporate CO & Station Comments | 2026-01-15 | 2026-01-21 | 5 | 5 | 5 | 0% | 0 | Not Started
ER6698LT | W224 | W224.5090 | HRA Enhanced Defueling Safety Case | 2026-01-08 | 2026-01-09 | Produce Verification File | 2026-01-15 | 2026-01-16 | 2 | 2 | 2 | 0% | 3 | Not Started
ER6701LT | W228 | W228.4410 | HYA Enhanced Defueling Safety Case | 2026-01-15 | 2026-01-21 | INSA Final Approval *(KDM)* | 2026-01-15 | 2026-01-21 | 5 | 5 | 5 | 0% | 20 | Not Started
ER6701LT | W228 | W228.5080 | HYA Enhanced Defueling Safety Case | 2026-01-08 | 2026-01-14 | Incorporate CO & Station Comments | 2026-01-15 | 2026-01-21 | 5 | 5 | 5 | 0% | 0 | Not Started
ER6701LT | W228 | W228.5090 | HYA Enhanced Defueling Safety Case | 2026-01-08 | 2026-01-09 | Produce Verification File | 2026-01-15 | 2026-01-16 | 2 | 2 | 2 | 0% | 3 | Not Started
ER6701LT | W228 | W228.5580 | HYA Enhanced Defueling Safety Case | 2026-01-13 | 2026-01-13 | Post Job Debrief | 2026-01-15 | 2026-01-15 | 1 | 1 | 1 | 0% | 30 | Not Started
ER6698LT | W224 | W224.2060 | HRA Enhanced Defueling Safety Case |  | 2026-01-12 | KDM - CAT 2 Tie Bar and Bob Weight Complete | 2026-01-15 | 2026-01-15 | 0 | 0 | 0 | 0% | 30 | Not Started
ER6698LT | W224 | W224.5570 | HRA Enhanced Defueling Safety Case |  | 2026-01-12 | Station Approval Obtained and CAT 2 Safety Case Complete *(KDM)* | 2026-01-15 | 2026-01-15 | 0 | 0 | 0 | 0% | 29 | Not Started
ER6698LT | W224 | W224.5580 | HRA Enhanced Defueling Safety Case | 2026-01-13 | 2026-01-13 | Post Job Debrief | 2026-01-16 | 2026-01-16 | 1 | 1 | 1 | 0% | 29 | Not Started
W730LT_UN | W730 | W730.3920 | HYB Enhanced Defueling Safety Cases | 2026-01-16 | 2026-01-19 | HYB Enhanced Defueling Rate: Deterministic Assessment Verification | 2026-01-16 | 2026-01-19 | 2 | 2 | 2 | 0% | 524 | Not Started
W731LT_UN | W731 | W731.1530 | TOR Enhanced Defueling Safety Cases | 2026-01-16 | 2026-01-19 | TOR Enhanced Defueling Rate: Deterministic Assessment Verification | 2026-01-16 | 2026-01-19 | 2 | 2 | 2 | 0% | 524 | Not Started
ER6698LT | W224 | W224. A1530 | HRA Enhanced Defueling Safety Case | 2026-01-19 | 2026-01-19 | Hold PRC | 2026-01-19 | 2026-01-19 | 1 | 1 | 1 | 0% | 1 | Not Started
ER6701LT | W228 | W228. A1530 | HYA Enhanced Defueling Safety Case | 2026-01-19 | 2026-01-19 | Hold PRC | 2026-01-19 | 2026-01-19 | 1 | 1 | 1 | 0% | 1 | Not Started
ER6698LT | W224 | W224. A1540 | HRA Enhanced Defueling Safety Case |  | 2026-01-19 | Gate D PRC Paper Approval | 2026-01-19 | 2026-01-19 | 0 | 0 | 0 | 0% | 1 | Not Started
ER6698LT | W224 | W224.A1100 | HRA Enhanced Defueling Safety Case |  | 2026-01-19 | Gate D for Defuelling Programme Enhancement ECs (HH1) | 2026-01-19 | 2026-01-19 | 0 | 0 | 0 | 0% | 28 | Not Started
ER6701LT | W228 | W228.A1100 | HYA Enhanced Defueling Safety Case |  | 2026-01-19 | Gate D for Defuelling Programme Enhancement ECs (HH1) | 2026-01-19 | 2026-01-19 | 0 | 0 | 0 | 0% | 28 | Not Started
ER6701LT | W228 | W228. A1540 | HYA Enhanced Defueling Safety Case |  | 2026-01-19 | Gate D PRC Paper Approval | 2026-01-19 | 2026-01-19 | 0 | 0 | 0 | 0% | 1 | Not Started
W730LT_UN | W730 | W730.3930 | HYB Enhanced Defueling Safety Cases | 2026-01-20 | 2026-01-21 | HYB Enhanced Defueling Rate: Deterministic Assessment Technical Review | 2026-01-20 | 2026-01-21 | 2 | 2 | 2 | 0% | 524 | Not Started
W731LT_UN | W731 | W731.1540 | TOR Enhanced Defueling Safety Cases | 2026-01-20 | 2026-01-21 | TOR Enhanced Defueling Rate: Deterministic Assessment Technical Review | 2026-01-20 | 2026-01-21 | 2 | 2 | 2 | 0% | 524 | Not Started
W230LT | W230 | W230.2990 | HYB Enhanced Defueling Safety Case Strategy | 2025-05-06 | 2025-05-19 | HYB Reactor Inspections Relaxations: INA comments on NSRS | 2026-01-21 | 2026-02-03 | 10 | 10 | 10 | 0% | 12 | Not Started
W234LT | W234 | W234.2990 | TOR Enhanced Defueling Safety Case Strategy | 2025-05-06 | 2025-05-19 | TOR Reactor Inspections Relaxations: INA comments on NSRS | 2026-01-21 | 2026-02-03 | 10 | 10 | 10 | 0% | 12 | Not Started
ER6698LT | W224 | W224.5100 | HRA Enhanced Defueling Safety Case |  | 2026-01-14 | Issue High Quality Verified Draft Issue A with Verification File to INSA & Station (T - 3 weeks before NSC date) *(KDM)* | 2026-01-21 | 2026-01-21 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6698LT | W224 | W224.5110 | HRA Enhanced Defueling Safety Case |  | 2026-01-14 | Verification Complete | 2026-01-21 | 2026-01-21 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6698LT | W224 | W224.5120 | HRA Enhanced Defueling Safety Case |  | 2026-01-14 | Submit for Approval - Categoriser Ratifies; RE/CO Endorsement | 2026-01-21 | 2026-01-21 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6698LT | W224 | W224.5130 | HRA Enhanced Defueling Safety Case |  | 2026-01-14 | NSORC Agreed Paper (SZB Only & as required) | 2026-01-21 | 2026-01-21 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6701LT | W228 | W228.5100 | HYA Enhanced Defueling Safety Case |  | 2026-01-14 | Issue High Quality Verified Draft Issue A with Verification File to INSA & Station (T - 3 weeks before NSC date) *(KDM)* | 2026-01-21 | 2026-01-21 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6701LT | W228 | W228.5110 | HYA Enhanced Defueling Safety Case |  | 2026-01-14 | Verification Complete | 2026-01-21 | 2026-01-21 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6701LT | W228 | W228.5120 | HYA Enhanced Defueling Safety Case |  | 2026-01-14 | Submit for Approval - Categoriser Ratifies; RE/CO Endorsement | 2026-01-21 | 2026-01-21 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6701LT | W228 | W228.5130 | HYA Enhanced Defueling Safety Case |  | 2026-01-14 | NSORC Agreed Paper (SZB Only & as required) | 2026-01-21 | 2026-01-21 | 0 | 0 | 0 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3940 | HYB Enhanced Defueling Safety Cases |  | 2026-01-21 | HYB Enhanced Defueling Rate: Deterministic Assessment Issued/ Approval | 2026-01-21 | 2026-01-21 | 0 | 0 | 0 | 0% | 524 | Not Started
W731LT_UN | W731 | W731.1550 | TOR Enhanced Defueling Safety Cases |  | 2026-01-21 | TOR Enhanced Defueling Rate: Deterministic Assessment Issued/ Approval | 2026-01-21 | 2026-01-21 | 0 | 0 | 0 | 0% | 524 | Not Started
ER6698LT | W224 | W224.4420 | HRA Enhanced Defueling Safety Case | 2026-01-22 | 2026-01-28 | Station Approval for Mod Implementation (including station review meeting) | 2026-01-22 | 2026-01-28 | 5 | 5 | 5 | 0% | 20 | Not Started
ER6698LT | W224 | W224.5140 | HRA Enhanced Defueling Safety Case | 2026-01-15 | 2026-01-28 | INSA Review & Iteration of Comments (using BARRIER MODEL) | 2026-01-22 | 2026-02-04 | 10 | 10 | 10 | 0% | 0 | Not Started
ER6698LT | W224 | W224.5150 | HRA Enhanced Defueling Safety Case | 2026-01-15 | 2026-01-21 | Key Stakeholders Approval, if Requested | 2026-01-22 | 2026-01-28 | 5 | 5 | 5 | 0% | 10 | Not Started
ER6701LT | W228 | W228.4420 | HYA Enhanced Defueling Safety Case | 2026-01-22 | 2026-01-28 | Station Approval for Mod Implementation (including station review meeting) | 2026-01-22 | 2026-01-28 | 5 | 5 | 5 | 0% | 20 | Not Started
ER6701LT | W228 | W228.5140 | HYA Enhanced Defueling Safety Case | 2026-01-15 | 2026-01-28 | INSA Review & Iteration of Comments (using BARRIER MODEL) | 2026-01-22 | 2026-02-04 | 10 | 10 | 10 | 0% | 0 | Not Started
ER6701LT | W228 | W228.5150 | HYA Enhanced Defueling Safety Case | 2026-01-15 | 2026-01-21 | Key Stakeholders Approval, if Requested | 2026-01-22 | 2026-01-28 | 5 | 5 | 5 | 0% | 10 | Not Started
W730LT_UN | W730 | W730.3950 | HYB Enhanced Defueling Safety Cases | 2026-01-22 | 2026-01-28 | HYB Enhanced Defueling Rate: Deterministic Assessment Production Risk (Risk 42008) | 2026-01-22 | 2026-01-28 | 5 | 5 | 5 | 0% | 524 | Not Started
W731LT_UN | W731 | W731.1560 | TOR Enhanced Defueling Safety Cases | 2026-01-22 | 2026-01-28 | TOR Enhanced Defueling Rate: Deterministic Assessment Production Risk (Risk 42008) | 2026-01-22 | 2026-01-28 | 5 | 5 | 5 | 0% | 524 | Not Started
ER6698LT | W224 | W224.2120 | HRA Enhanced Defueling Safety Case |  | 2026-01-28 | KDM - CAT 2 EC Trip Function Complete | 2026-01-28 | 2026-01-28 | 0 | 0 | 0 | 0% | 21 | Not Started
ER6701LT | W228 | W228.2120 | HYA Enhanced Defueling Safety Case |  | 2026-01-28 | KDM - CAT 2 EC Trip Function Complete | 2026-01-28 | 2026-01-28 | 0 | 0 | 0 | 0% | 21 | Not Started
ER6698LT | W224 | W224.4430 | HRA Enhanced Defueling Safety Case |  | 2026-01-28 | Station Approval Obtained and CAT 2 Safety Case Complete *(KDM)* | 2026-01-28 | 2026-01-28 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4430 | HYA Enhanced Defueling Safety Case |  | 2026-01-28 | Station Approval Obtained and CAT 2 Safety Case Complete *(KDM)* | 2026-01-28 | 2026-01-28 | 0 | 0 | 0 | 0% | 20 | Not Started
ER6698LT | W224 | W224.4440 | HRA Enhanced Defueling Safety Case | 2026-01-29 | 2026-01-29 | Post Job Debrief | 2026-01-29 | 2026-01-29 | 1 | 1 | 1 | 0% | 20 | Not Started
ER6701LT | W228 | W228.4440 | HYA Enhanced Defueling Safety Case | 2026-01-29 | 2026-01-29 | Post Job Debrief | 2026-01-29 | 2026-01-29 | 1 | 1 | 1 | 0% | 20 | Not Started
W730LT_UN | W730 | W730.3960 | HYB Enhanced Defueling Safety Cases | 2026-01-29 | 2026-02-18 | HYB Enhanced Defueling Rate: HF Report on HBSCs Authoring | 2026-01-29 | 2026-02-18 | 15 | 15 | 15 | 0% | 524 | Not Started
W731LT_UN | W731 | W731.1570 | TOR Enhanced Defueling Safety Cases | 2026-01-29 | 2026-02-18 | TOR Enhanced Defueling Rate: HF Report on HBSCs Authoring | 2026-01-29 | 2026-02-18 | 15 | 15 | 15 | 0% | 524 | Not Started
W230LT | W230 | W230.3050 | HYB Enhanced Defueling Safety Case Strategy | 2025-05-20 | 2025-05-20 | HYB Reactor Inspections Relaxations: Register EC and identify Milestones in AMS EC NNNNNN | 2026-02-04 | 2026-02-04 | 1 | 1 | 1 | 0% | 12 | Not Started
W234LT | W234 | W234.3050 | TOR Enhanced Defueling Safety Case Strategy | 2025-05-20 | 2025-05-20 | TOR Reactor Inspections Relaxations: Register EC and identify Milestones in AMS EC NNNNNN | 2026-02-04 | 2026-02-04 | 1 | 1 | 1 | 0% | 12 | Not Started
W230LT | W230 | W230.3060 | HYB Enhanced Defueling Safety Case Strategy | 2025-05-21 | 2025-05-21 | HYB Reactor Inspections Relaxations: Update NSRS to address comments | 2026-02-05 | 2026-02-05 | 1 | 1 | 1 | 0% | 12 | Not Started
ER6698LT | W224 | W224.5160 | HRA Enhanced Defueling Safety Case | 2026-01-29 | 2026-02-04 | Incorporate INSA Comments | 2026-02-05 | 2026-02-11 | 5 | 5 | 5 | 0% | 0 | Not Started
ER6701LT | W228 | W228.5160 | HYA Enhanced Defueling Safety Case | 2026-01-29 | 2026-02-04 | Incorporate INSA Comments | 2026-02-05 | 2026-02-11 | 5 | 5 | 5 | 0% | 0 | Not Started
W234LT | W234 | W234.3060 | TOR Enhanced Defueling Safety Case Strategy | 2025-05-21 | 2025-05-21 | TOR Reactor Inspections Relaxations: Update NSRS to address comments | 2026-02-05 | 2026-02-05 | 1 | 1 | 1 | 0% | 12 | Not Started
W230LT | W230 | W230.3330 | HYB Enhanced Defueling Safety Case Strategy | 2025-05-22 | 2025-05-29 | HYB Reactor Inspections Relaxations: Risk Ref 38976 TBC - NSRS Production | 2026-02-06 | 2026-02-12 | 5 | 5 | 5 | 0% | 12 | Not Started
W234LT | W234 | W234.3330 | TOR Enhanced Defueling Safety Case Strategy | 2025-05-22 | 2025-05-29 | TOR Reactor Inspections Relaxations: Risk Ref 38976 TBC - NSRS Production | 2026-02-06 | 2026-02-12 | 5 | 5 | 5 | 0% | 12 | Not Started
W232LT | W232 | W232.A5180 | DNB Enhanced Safety Cases |  | 2026-03-02 | Rev 001 - INSA Final Approval *(KDM)* | 2026-02-06 | 2026-02-06 | 0 | 0 | 0 | 0% | 5 | Not Started
W232LT | W232 | W232.A5230 | DNB Enhanced Safety Cases |  |  | Lessons Learned Workshop - FPU Safety Case Ph 3 Rev 001 INSA | 2026-02-09 | 2026-02-09 | 1 | 1 | 1 | 0% | 13 | Not Started
W232LT | W232 | W232.A5310 | DNB Enhanced Safety Cases |  | 2026-03-03 | Safety Case INA Final Approval - Rev 001 | 2026-02-06 | 2026-02-09 | 0 | 0 | 0 | 0% | 13 | Not Started
W730LT_UN | W730 | W730.2040 | HYB Enhanced Defueling Safety Cases | 2026-02-10 | 2026-02-11 | HYB Enhanced Defueling Rate: Requirements Capture | 2026-02-10 | 2026-02-11 | 2 | 2 | 2 | 0% | 14 | Not Started
W232LT | W232 | W232.A5150 | DNB Enhanced Safety Cases | 2026-03-04 | 2026-03-10 | Rev 001 - Station Approval for mod implementation (including station review meeting) | 2026-02-10 | 2026-02-16 | 5 | 5 | 5 | 0% | 5 | Not Started
W730LT_UN | W730 | W730.2310 | HYB Enhanced Defueling Safety Cases | 2026-02-10 | 2026-02-16 | HYB Enhanced Defueling Rate: Final Authoring Consolidation Check | 2026-02-10 | 2026-02-16 | 5 | 5 | 5 | 0% | 11 | Not Started
W730LT_UN | W730 | W730.2320 | HYB Enhanced Defueling Safety Cases | 2026-02-10 | 2026-02-12 | HYB Enhanced Defueling Rate: Lessons Learned Activitiy - Following Authoring of SC | 2026-02-10 | 2026-02-12 | 3 | 3 | 3 | 0% | 540 | Not Started
W731LT_UN | W731 | W731.1580 | TOR Enhanced Defueling Safety Cases | 2026-02-10 | 2026-02-12 | TOR Enhanced Defueling Rate: Lessons Learned Activitiy - Following Authoring of SC | 2026-02-10 | 2026-02-12 | 3 | 3 | 3 | 0% | 540 | Not Started
W731LT_UN | W731 | W731.1590 | TOR Enhanced Defueling Safety Cases | 2026-02-10 | 2026-02-16 | TOR Enhanced Defueling Rate: Final Authoring Consolidation Check | 2026-02-10 | 2026-02-16 | 5 | 5 | 5 | 0% | 11 | Not Started
W731LT_UN | W731 | W731.1600 | TOR Enhanced Defueling Safety Cases | 2026-02-10 | 2026-02-11 | TOR Enhanced Defueling Rate: Requirements Capture | 2026-02-10 | 2026-02-11 | 2 | 2 | 2 | 0% | 14 | Not Started
ER6698LT | W224 | W224.5170 | HRA Enhanced Defueling Safety Case | 2026-02-05 | 2026-02-11 | INSA Final Approval *(KDM)* | 2026-02-12 | 2026-02-18 | 5 | 5 | 5 | 0% | 0 | Not Started
ER6701LT | W228 | W228.5170 | HYA Enhanced Defueling Safety Case | 2026-02-05 | 2026-02-11 | INSA Final Approval *(KDM)* | 2026-02-12 | 2026-02-18 | 5 | 5 | 5 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.1240 | HYB Enhanced Defueling Safety Cases |  | 2026-02-12 | HYB Enhanced Defueling Rate: Lessons Learned Milestone - Authoring of the Safety Case | 2026-02-12 | 2026-02-12 | 0 | 0 | 0 | 0% | 540 | Not Started
W230LT | W230 | W230.3570 | HYB Enhanced Defueling Safety Case Strategy |  | 2025-02-19 | HYB Reactor Inspections Relaxations: Risk Milestone - NSRS Production Complete (Risk Ref 38976) | 2026-02-12 | 2026-02-12 | 0 | 0 | 0 | 0% | 12 | Not Started
W234LT | W234 | W234.3570 | TOR Enhanced Defueling Safety Case Strategy |  | 2025-02-19 | TOR Reactor Inspections Relaxations: Risk Milestone - NSRS Production Complete (Risk Ref 38976) | 2026-02-12 | 2026-02-12 | 0 | 0 | 0 | 0% | 12 | Not Started
W731LT_UN | W731 | W731.1610 | TOR Enhanced Defueling Safety Cases |  | 2026-02-12 | TOR Enhanced Defueling Rate: Lessons Learned Milestone - Authoring of the Safety Case | 2026-02-12 | 2026-02-12 | 0 | 0 | 0 | 0% | 540 | Not Started
W230LT | W230 | W230.3020 | HYB Enhanced Defueling Safety Case Strategy | 2025-05-30 | 2025-05-30 | HYB Reactor Inspections Relaxations: Issue final NSRS | 2026-02-13 | 2026-02-13 | 1 | 1 | 1 | 0% | 12 | Not Started
W234LT | W234 | W234.3020 | TOR Enhanced Defueling Safety Case Strategy | 2025-05-30 | 2025-05-30 | TOR Reactor Inspections Relaxations: Issue final NSRS | 2026-02-13 | 2026-02-13 | 1 | 1 | 1 | 0% | 12 | Not Started
W232LT | W232 | W232.A5210 | DNB Enhanced Safety Cases |  | 2026-03-10 | Rev 001 - Station Approval Obtained and CAT 2 Safety Case Complete *(KDM)* | 2026-02-16 | 2026-02-16 | 0 | 0 | 0 | 0% | 7 | Not Started
W232LT | W232 | W232.A5540 | DNB Enhanced Safety Cases |  |  | Lessons Learned Workshop - FPU Safety Case Ph 3 Rev 001 Station approved | 2026-02-17 | 2026-02-17 | 1 | 1 | 1 | 0% | 7 | Not Started
W730LT_UN | W730 | W730.2300 | HYB Enhanced Defueling Safety Cases | 2026-02-17 | 2026-03-02 | HYB Enhanced Defueling Rate: Obtain CO Review & Detail Checker | 2026-02-17 | 2026-03-02 | 10 | 10 | 10 | 0% | 11 | Not Started
W230LT | W230 | W230.3000 | HYB Enhanced Defueling Safety Case Strategy | 2025-06-03 | 2025-06-23 | HYB Reactor Inspections Relaxations: DA & INA agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2026-02-17 | 2026-03-09 | 15 | 15 | 15 | 0% | 12 | Not Started
W234LT | W234 | W234.3000 | TOR Enhanced Defueling Safety Case Strategy | 2025-06-03 | 2025-06-23 | TOR Reactor Inspections Relaxations: DA & INA agree NSRS (for authorised designers-NSRS must be reviewed by DA) | 2026-02-17 | 2026-03-09 | 15 | 15 | 15 | 0% | 12 | Not Started
W731LT_UN | W731 | W731.1620 | TOR Enhanced Defueling Safety Cases | 2026-02-17 | 2026-03-02 | TOR Enhanced Defueling Rate: Obtain CO Review & Detail Checker | 2026-02-17 | 2026-03-02 | 10 | 10 | 10 | 0% | 11 | Not Started
W232LT | W232 | W232.A5870 | DNB Enhanced Safety Cases |  |  | <NEW SCOPE PENDING CN3754> - Safety Case Developed (FEEDS TO SUMMARY SCHEDULE) | 2026-02-17 | 2026-02-17 | 1 | 1 | 1 | 0% | 5 | Not Started
W232LT | W232 | W232.A5320 | DNB Enhanced Safety Cases |  | 2026-03-11 | All Safety Cases Approved - Rev 001 (FEED TO SUMMARY SCHEDULE) | 2026-02-17 | 2026-02-17 | 0 | 0 | 0 | 0% | 8 | Not Started
W232LT | W232 | W232.A5500 | DNB Enhanced Safety Cases |  |  | >>>OUTGOING ENABLER DNB Enhanced Safety Case Station Approved - Rev 001 | 2026-02-17 | 2026-02-17 | 0 | 0 | 0 | 0% | 25 | Not Started
W232LT | W232 | W232.A5880 | DNB Enhanced Safety Cases |  |  | <NEW SCOPE PENDING CN3754> - Revise all Affected Drawings and Documents for EC Approval | 2026-02-18 | 2026-02-18 | 1 | 1 | 1 | 0% | 5 | Not Started
ER6698LT | W224 | W224.5180 | HRA Enhanced Defueling Safety Case | 2026-02-12 | 2026-02-18 | Station Approval for Mod Implementation (including station review meeting) | 2026-02-19 | 2026-02-25 | 5 | 5 | 5 | 0% | 0 | Not Started
ER6701LT | W228 | W228.5180 | HYA Enhanced Defueling Safety Case | 2026-02-12 | 2026-02-18 | Station Approval for Mod Implementation (including station review meeting) | 2026-02-19 | 2026-02-25 | 5 | 5 | 5 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3970 | HYB Enhanced Defueling Safety Cases | 2026-02-19 | 2026-02-20 | HYB Enhanced Defueling Rate: HF Report on HBSCs Verification | 2026-02-19 | 2026-02-20 | 2 | 2 | 2 | 0% | 524 | Not Started
W731LT_UN | W731 | W731.1630 | TOR Enhanced Defueling Safety Cases | 2026-02-19 | 2026-02-20 | TOR Enhanced Defueling Rate: HF Report on HBSCs Verification | 2026-02-19 | 2026-02-20 | 2 | 2 | 2 | 0% | 524 | Not Started
W232LT | W232 | W232.A5890 | DNB Enhanced Safety Cases |  |  | <NEW SCOPE PENDING CN3754> - Develop Implementation & closeout Plan (FEED TO SUMMARY SCHEDULE) | 2026-02-19 | 2026-02-19 | 1 | 1 | 1 | 0% | 5 | Not Started
W232LT | W232 | W232.A5200 | DNB Enhanced Safety Cases | 2026-03-12 | 2026-03-12 | Rev 001 - Post Job Debrief | 2026-02-20 | 2026-02-20 | 1 | 1 | 1 | 0% | 5 | Not Started
W232LT | W232 | W232.B5530 | DNB Enhanced Safety Cases | 2026-03-13 | 2026-03-13 | Hold Project Closeout and Lessons Learned Meeting | 2026-02-23 | 2026-02-23 | 1 | 1 | 1 | 0% | 5 | Not Started
W232LT | W232 | W232.B5525 | DNB Enhanced Safety Cases | 2026-03-13 | 2026-04-21 | Project Management - Gate D-E | 2026-02-23 | 2026-03-24 | 22 | 22 | 22 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3980 | HYB Enhanced Defueling Safety Cases | 2026-02-23 | 2026-02-24 | HYB Enhanced Defueling Rate: HF Report on HBSCs Technical Review | 2026-02-23 | 2026-02-24 | 2 | 2 | 2 | 0% | 524 | Not Started
W731LT_UN | W731 | W731.1640 | TOR Enhanced Defueling Safety Cases | 2026-02-23 | 2026-02-24 | TOR Enhanced Defueling Rate: HF Report on HBSCs Technical Review | 2026-02-23 | 2026-02-24 | 2 | 2 | 2 | 0% | 524 | Not Started
W232LT | W232 | W232.B5540 | DNB Enhanced Safety Cases | 2026-03-16 | 2026-03-16 | Produce Lessons Learned Report | 2026-02-24 | 2026-02-24 | 1 | 1 | 1 | 0% | 5 | Not Started
W230LT | W230 | W230.3010 | HYB Enhanced Defueling Safety Case Strategy | 2025-06-10 | 2025-06-23 | HYB Reactor Inspections Relaxations: Station agree NSRS | 2026-02-24 | 2026-03-09 | 10 | 10 | 10 | 0% | 12 | Not Started
W234LT | W234 | W234.3010 | TOR Enhanced Defueling Safety Case Strategy | 2025-06-10 | 2025-06-23 | TOR Reactor Inspections Relaxations: Station agree NSRS | 2026-02-24 | 2026-03-09 | 10 | 10 | 10 | 0% | 12 | Not Started
W730LT_UN | W730 | W730.3990 | HYB Enhanced Defueling Safety Cases |  | 2026-02-24 | HYB Enhanced Defueling Rate: HF Report on HBSCs Issued/ Approval | 2026-02-24 | 2026-02-24 | 0 | 0 | 0 | 0% | 524 | Not Started
W731LT_UN | W731 | W731.1650 | TOR Enhanced Defueling Safety Cases |  | 2026-02-24 | TOR Enhanced Defueling Rate: HF Report on HBSCs Issued/ Approval | 2026-02-24 | 2026-02-24 | 0 | 0 | 0 | 0% | 524 | Not Started
W232LT | W232 | W232.B5550 | DNB Enhanced Safety Cases | 2026-03-17 | 2026-03-18 | Produce Project Closeout Report | 2026-02-25 | 2026-02-26 | 2 | 2 | 2 | 0% | 5 | Not Started
W730LT_UN | W730 | W730.4000 | HYB Enhanced Defueling Safety Cases | 2026-02-25 | 2026-03-03 | HYB Enhanced Defueling Rate: HF Report on HBSCs Production Risk (Risk 42008) | 2026-02-25 | 2026-03-03 | 5 | 5 | 5 | 0% | 524 | Not Started
W731LT_UN | W731 | W731.1660 | TOR Enhanced Defueling Safety Cases | 2026-02-25 | 2026-03-03 | TOR Enhanced Defueling Rate: HF Report on HBSCs Production Risk (Risk 42008) | 2026-02-25 | 2026-03-03 | 5 | 5 | 5 | 0% | 524 | Not Started
ER6698LT | W224 | W224.2080 | HRA Enhanced Defueling Safety Case |  | 2026-02-18 | KDM - CAT 2 EC Load Trace Complete | 2026-02-25 | 2026-02-25 | 0 | 0 | 0 | 0% | 1 | Not Started
ER6701LT | W228 | W228.2080 | HYA Enhanced Defueling Safety Case |  | 2026-02-18 | KDM - CAT 2 EC Load Trace Complete | 2026-02-25 | 2026-02-25 | 0 | 0 | 0 | 0% | 1 | Not Started
ER6698LT | W224 | W224.5190 | HRA Enhanced Defueling Safety Case |  | 2026-02-18 | Station Approval Obtained and CAT 2 Safety Case Complete *(KDM)* | 2026-02-25 | 2026-02-25 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6701LT | W228 | W228.5190 | HYA Enhanced Defueling Safety Case |  | 2026-02-18 | Station Approval Obtained and CAT 2 Safety Case Complete *(KDM)* | 2026-02-25 | 2026-02-25 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6698LT | W224 | W224.5200 | HRA Enhanced Defueling Safety Case | 2026-02-19 | 2026-02-19 | Post Job Debrief | 2026-02-26 | 2026-02-26 | 1 | 1 | 1 | 0% | 0 | Not Started
ER6701LT | W228 | W228.5200 | HYA Enhanced Defueling Safety Case | 2026-02-19 | 2026-02-19 | Post Job Debrief | 2026-02-26 | 2026-02-26 | 1 | 1 | 1 | 0% | 0 | Not Started
ER6698LT | W224 | W224.A1120 | HRA Enhanced Defueling Safety Case |  | 2026-02-19 | Project Finish | 2026-02-26 | 2026-02-26 | 0 | 0 | 0 | 0% | 0 | Not Started
ER6701LT | W228 | W228.A1120 | HYA Enhanced Defueling Safety Case |  | 2026-02-19 | Project Finish | 2026-02-26 | 2026-02-26 | 0 | 0 | 0 | 0% | 0 | Not Started
W232LT | W232 | W232.B5560 | DNB Enhanced Safety Cases | 2026-03-19 | 2026-03-23 | Prepare Gate D PRC Paper | 2026-02-27 | 2026-03-03 | 3 | 3 | 3 | 0% | 5 | Not Started
W730LT_UN | W730 | W730.2500 | HYB Enhanced Defueling Safety Cases | 2026-03-03 | 2026-03-16 | HYB Enhanced Defueling Rate: Paper Authoring Risk (Risk 42008) | 2026-03-03 | 2026-03-16 | 10 | 10 | 10 | 0% | 11 | Not Started
W731LT_UN | W731 | W731.1670 | TOR Enhanced Defueling Safety Cases | 2026-03-03 | 2026-03-16 | TOR Enhanced Defueling Rate: Paper Authoring Risk (Risk 42008) | 2026-03-03 | 2026-03-16 | 10 | 10 | 10 | 0% | 11 | Not Started
W730LT_UN | W730 | W730.1030 | HYB Enhanced Defueling Safety Cases |  | 2026-03-03 | HYB Enhanced Defueling Rate: All Key Supporting Technical References Completed for Enhanced Defueling Rate | 2026-03-03 | 2026-03-03 | 0 | 0 | 0 | 0% | 527 | Not Started
W730LT_UN | W730 | W730.2250 | HYB Enhanced Defueling Safety Cases |  | 2026-03-03 | HYB Enhanced Defueling Rate: All Supporting References Approved and Issued | 2026-03-03 | 2026-03-03 | 0 | 0 | 0 | 0% | 524 | Not Started
W731LT_UN | W731 | W731.1680 | TOR Enhanced Defueling Safety Cases |  | 2026-03-03 | TOR Enhanced Defueling Rate: All Supporting References Approved and Issued | 2026-03-03 | 2026-03-03 | 0 | 0 | 0 | 0% | 524 | Not Started
W731LT_UN | W731 | W731.1690 | TOR Enhanced Defueling Safety Cases |  | 2026-03-03 | TOR Enhanced Defueling Rate: All Key Supporting Technical References Completed for Enhanced Defueling Rate | 2026-03-03 | 2026-03-03 | 0 | 0 | 0 | 0% | 527 | Not Started
W730LT_UN | W730 | W730.2270 | HYB Enhanced Defueling Safety Cases | 2026-03-04 | 2026-03-06 | HYB Enhanced Defueling Rate: Lessons Learned Activitiy - Following Completeion of Technical References | 2026-03-04 | 2026-03-06 | 3 | 3 | 3 | 0% | 524 | Not Started
W731LT_UN | W731 | W731.1700 | TOR Enhanced Defueling Safety Cases | 2026-03-04 | 2026-03-06 | TOR Enhanced Defueling Rate: Lessons Learned Activitiy - Following Completeion of Technical References | 2026-03-04 | 2026-03-06 | 3 | 3 | 3 | 0% | 524 | Not Started
W730LT_UN | W730 | W730.1230 | HYB Enhanced Defueling Safety Cases |  | 2026-03-06 | HYB Enhanced Defueling Rate: Lessons Learned Milestone - Technical References | 2026-03-06 | 2026-03-06 | 0 | 0 | 0 | 0% | 524 | Not Started
W731LT_UN | W731 | W731.1710 | TOR Enhanced Defueling Safety Cases |  | 2026-03-06 | TOR Enhanced Defueling Rate: Lessons Learned Milestone - Technical References | 2026-03-06 | 2026-03-06 | 0 | 0 | 0 | 0% | 524 | Not Started
W230LT | W230 | W230.3430 | HYB Enhanced Defueling Safety Case Strategy |  | 2025-03-14 | HYB Reactor Inspections Relaxations: Station Agree NSRS | 2026-03-06 | 2026-03-09 | 0 | 0 | 0 | 0% | 48 | Not Started
W230LT | W230 | W230.3550 | HYB Enhanced Defueling Safety Case Strategy |  | 2025-03-14 | HYB Reactor Inspections Relaxations - NSRS Completion - Proceed with Safety Case (HYB) | 2026-03-06 | 2026-03-09 | 0 | 0 | 0 | 0% | 48 | Not Started
W234LT | W234 | W234.3430 | TOR Enhanced Defueling Safety Case Strategy |  | 2025-03-14 | TOR Reactor Inspections Relaxations: Station Agree NSRS | 2026-03-09 | 2026-03-09 | 0 | 0 | 0 | 0% | 48 | Not Started
W234LT | W234 | W234.3550 | TOR Enhanced Defueling Safety Case Strategy |  | 2025-03-14 | TOR Reactor Inspections Relaxations - NSRS Completion - Proceed with Safety Case (TOR) | 2026-03-09 | 2026-03-09 | 0 | 0 | 0 | 0% | 48 | Not Started
W230LT | W230 | W230.3070 | HYB Enhanced Defueling Safety Case Strategy | 2025-06-24 | 2025-06-30 | HYB Reactor Inspections Relaxations: Circulate NSRS for Relevant Stakeholders (A-B Part) | 2026-03-10 | 2026-03-16 | 5 | 5 | 5 | 0% | 12 | Not Started
W234LT | W234 | W234.3070 | TOR Enhanced Defueling Safety Case Strategy | 2025-06-24 | 2025-06-30 | TOR Reactor Inspections Relaxations: Circulate NSRS for Relevant Stakeholders (A-B Part) | 2026-03-10 | 2026-03-16 | 5 | 5 | 5 | 0% | 12 | Not Started
W232LT | W232 | W232.B5570 | DNB Enhanced Safety Cases | 2026-04-08 | 2026-04-08 | Gate D PRC Paper Submission | 2026-03-11 | 2026-03-11 | 1 | 1 | 1 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.1040 | HYB Enhanced Defueling Safety Cases |  | 2026-03-16 | HYB Enhanced Defueling Rate: Safety Case Paper Authoring Complete EC NNNNNN - Enhanced Defueling Rate | 2026-03-16 | 2026-03-16 | 0 | 0 | 0 | 0% | 518 | Not Started
W730LT_UN | W730 | W730.2350 | HYB Enhanced Defueling Safety Cases |  | 2026-03-16 | HYB Enhanced Defueling Rate: Verification Commenced (T-11) | 2026-03-16 | 2026-03-16 | 0 | 0 | 0 | 0% | 440 | Not Started
W730LT_UN | W730 | W730.2370 | HYB Enhanced Defueling Safety Cases |  | 2026-03-16 | HYB Enhanced Defueling Rate: Issue to Peer CO & Station for comments | 2026-03-16 | 2026-03-16 | 0 | 0 | 0 | 0% | 440 | Not Started
W731LT_UN | W731 | W731.1720 | TOR Enhanced Defueling Safety Cases |  | 2026-03-16 | TOR Enhanced Defueling Rate: Issue to Peer CO & Station for comments | 2026-03-16 | 2026-03-16 | 0 | 0 | 0 | 0% | 440 | Not Started
W731LT_UN | W731 | W731.1730 | TOR Enhanced Defueling Safety Cases |  | 2026-03-16 | TOR Enhanced Defueling Rate: Verification Commenced (T-11) | 2026-03-16 | 2026-03-16 | 0 | 0 | 0 | 0% | 440 | Not Started
W731LT_UN | W731 | W731.1740 | TOR Enhanced Defueling Safety Cases |  | 2026-03-16 | TOR Enhanced Defueling Rate: Safety Case Paper Authoring Complete EC NNNNNN - Enhanced Defueling Rate | 2026-03-16 | 2026-03-16 | 0 | 0 | 0 | 0% | 518 | Not Started
W730LT_UN | W730 | W730.1600 | HYB Enhanced Defueling Safety Cases | 2026-03-17 | 2026-03-30 | Confirm Objectives to be Delivered at Gate B+ | 2026-03-17 | 2026-03-30 | 10 | 10 | 10 | 0% | 11 | Not Started
W230LT | W230 | W230.3110 | HYB Enhanced Defueling Safety Case Strategy | 2025-07-01 | 2025-07-01 | HYB Reactor Inspections Relaxations: Send NSRS to ONR to Determine Level of Review Required (Acknowledgement or Agreemen | 2026-03-17 | 2026-03-17 | 1 | 1 | 1 | 0% | 12 | Not Started
W234LT | W234 | W234.3110 | TOR Enhanced Defueling Safety Case Strategy | 2025-07-01 | 2025-07-01 | TOR Reactor Inspections Relaxations: Send NSRS to ONR to Determine Level of Review Required (Acknowledgement or Agreemen | 2026-03-17 | 2026-03-17 | 1 | 1 | 1 | 0% | 12 | Not Started
W731LT_UN | W731 | W731.1750 | TOR Enhanced Defueling Safety Cases | 2026-03-17 | 2026-03-30 | Confirm Objectives to be Delivered at Gate B+ | 2026-03-17 | 2026-03-30 | 10 | 10 | 10 | 0% | 11 | Not Started
W230LT | W230 | W230.3130 | HYB Enhanced Defueling Safety Case Strategy | 2025-07-02 | 2025-07-15 | HYB Reactor Inspections Relaxations: Outline Safety Case / ALARP Strategy | 2026-03-18 | 2026-03-31 | 10 | 10 | 10 | 0% | 12 | Not Started
W230LT | W230 | W230.3380 | HYB Enhanced Defueling Safety Case Strategy | 2025-07-02 | 2025-07-04 | HYB Reactor Inspections Relaxations: Lessons Learned Activity - NSRS Approval | 2026-03-18 | 2026-03-20 | 3 | 3 | 3 | 0% | 39 | Not Started
W234LT | W234 | W234.3130 | TOR Enhanced Defueling Safety Case Strategy | 2025-07-02 | 2025-07-15 | TOR Reactor Inspections Relaxations: Outline Safety Case / ALARP Strategy | 2026-03-18 | 2026-03-31 | 10 | 10 | 10 | 0% | 12 | Not Started
W234LT | W234 | W234.3380 | TOR Enhanced Defueling Safety Case Strategy | 2025-07-02 | 2025-07-04 | TOR Reactor Inspections Relaxations: Lessons Learned Activity - NSRS Approval | 2026-03-18 | 2026-03-20 | 3 | 3 | 3 | 0% | 39 | Not Started
W230LT | W230 | W230.3590 | HYB Enhanced Defueling Safety Case Strategy |  | 2025-03-27 | HYB Reactor Inspections Relaxations: Lessons Learned Milestone - NSRS Approval | 2026-03-20 | 2026-03-20 | 0 | 0 | 0 | 0% | 39 | Not Started
W234LT | W234 | W234.3590 | TOR Enhanced Defueling Safety Case Strategy |  | 2025-03-27 | TOR Reactor Inspections Relaxations: Lessons Learned Milestone - NSRS Approval | 2026-03-20 | 2026-03-20 | 0 | 0 | 0 | 0% | 39 | Not Started
W232LT | W232 | W232.B5580 | DNB Enhanced Safety Cases | 2026-04-21 | 2026-04-21 | Hold PRC Meeting - Gate D | 2026-03-24 | 2026-03-24 | 1 | 1 | 1 | 0% | 0 | Not Started
W232LT | W232 | W232.A2910 | DNB Enhanced Safety Cases |  | 2026-04-21 | Gate D PRC Paper Approval (DNB) | 2026-03-24 | 2026-03-24 | 0 | 0 | 0 | 0% | 0 | Not Started
W232LT | W232 | W232.A2550 | DNB Enhanced Safety Cases |  | 2026-04-21 | Project Completion | 2026-03-24 | 2026-03-24 | 0 | 0 | 0 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.1590 | HYB Enhanced Defueling Safety Cases | 2026-03-31 | 2026-04-15 | Initial high level scope of programme | 2026-03-31 | 2026-04-15 | 10 | 10 | 10 | 0% | 11 | Not Started
W731LT_UN | W731 | W731.1760 | TOR Enhanced Defueling Safety Cases | 2026-03-31 | 2026-04-15 | Initial high level scope of programme | 2026-03-31 | 2026-04-15 | 10 | 10 | 10 | 0% | 11 | Not Started
W230LT | W230 | W230.3460 | HYB Enhanced Defueling Safety Case Strategy |  | 2025-04-07 | HYB Reactor Inspections Relaxations: Optioneering Complete (Outline Safety Case / ALARP Strategy) | 2026-03-31 | 2026-03-31 | 0 | 0 | 0 | 0% | 12 | Not Started
W230LT | W230 | W230.3700 | HYB Enhanced Defueling Safety Case Strategy |  | 2025-07-15 | >>>OUTGOING ENABLER - NSRS's Complete - Feeds B-D Plan (Start Authoring References) | 2026-03-31 | 2026-03-31 | 0 | 0 | 0 | 0% | 32 | Not Started
W234LT | W234 | W234.3460 | TOR Enhanced Defueling Safety Case Strategy |  | 2025-04-07 | TOR Reactor Inspections Relaxations: Optioneering Complete (Outline Safety Case / ALARP Strategy) | 2026-03-31 | 2026-03-31 | 0 | 0 | 0 | 0% | 12 | Not Started
W234LT | W234 | W234.3700 | TOR Enhanced Defueling Safety Case Strategy |  | 2025-07-15 | >>>OUTGOING ENABLER - NSRS's Complete - Feeds B-D Plan (Start Authoring References) | 2026-03-31 | 2026-03-31 | 0 | 0 | 0 | 0% | 32 | Not Started
W230LT | W230 | W230.1780 | HYB Enhanced Defueling Safety Case Strategy | 2025-07-16 | 2025-08-19 | ## Gate D Submission - (Cost Summary) ## | 2026-04-01 | 2026-05-19 | 32 | 32 | 32 | 0% | 0 | Not Started
W230LT | W230 | W230.1830 | HYB Enhanced Defueling Safety Case Strategy | 2025-07-16 | 2025-07-16 | Hold Project Closeout and Lessons Learned Meeting | 2026-04-01 | 2026-04-01 | 1 | 1 | 1 | 0% | 12 | Not Started
W234LT | W234 | W234.1780 | TOR Enhanced Defueling Safety Case Strategy | 2025-07-16 | 2025-08-19 | ## Gate D Submission - (Cost Summary) ## | 2026-04-01 | 2026-05-19 | 32 | 32 | 32 | 0% | 0 | Not Started
W234LT | W234 | W234.1830 | TOR Enhanced Defueling Safety Case Strategy | 2025-07-16 | 2025-07-16 | Hold Project Closeout and Lessons Learned Meeting | 2026-04-01 | 2026-04-01 | 1 | 1 | 1 | 0% | 12 | Not Started
W730LT_UN | W730 | W730.1610 | HYB Enhanced Defueling Safety Cases | 2026-04-02 | 2026-04-17 | Prepare Draft Project Definition Document (PDD) | 2026-04-02 | 2026-04-17 | 10 | 10 | 10 | 0% | 11 | Not Started
W730LT_UN | W730 | W730.1620 | HYB Enhanced Defueling Safety Cases | 2026-04-02 | 2026-04-17 | PCL Validate & Approve Baseline Package for PRC Submission | 2026-04-02 | 2026-04-17 | 10 | 10 | 10 | 0% | 11 | Not Started
W730LT_UN | W730 | W730.1630 | HYB Enhanced Defueling Safety Cases | 2026-04-02 | 2026-04-17 | Add Data to PRC / IMS2 Paper | 2026-04-02 | 2026-04-17 | 10 | 10 | 10 | 0% | 11 | Not Started
W730LT_UN | W730 | W730.1640 | HYB Enhanced Defueling Safety Cases | 2026-04-02 | 2026-04-17 | Update Schedule/Estimate from Risk Log & Add Provisions | 2026-04-02 | 2026-04-17 | 10 | 10 | 10 | 0% | 11 | Not Started
W730LT_UN | W730 | W730.1650 | HYB Enhanced Defueling Safety Cases | 2026-04-02 | 2026-04-17 | Complete Risk Log with Estimates | 2026-04-02 | 2026-04-17 | 10 | 10 | 10 | 0% | 11 | Not Started
W730LT_UN | W730 | W730.1660 | HYB Enhanced Defueling Safety Cases | 2026-04-02 | 2026-04-17 | Hold Risk Workshop | 2026-04-02 | 2026-04-17 | 10 | 10 | 10 | 0% | 11 | Not Started
W230LT | W230 | W230.1820 | HYB Enhanced Defueling Safety Case Strategy | 2025-07-17 | 2025-07-17 | Produce Lessons Learned Report | 2026-04-02 | 2026-04-02 | 1 | 1 | 1 | 0% | 12 | Not Started
W234LT | W234 | W234.1820 | TOR Enhanced Defueling Safety Case Strategy | 2025-07-17 | 2025-07-17 | Produce Lessons Learned Report | 2026-04-02 | 2026-04-02 | 1 | 1 | 1 | 0% | 12 | Not Started
W731LT_UN | W731 | W731.1770 | TOR Enhanced Defueling Safety Cases | 2026-04-02 | 2026-04-17 | Hold Risk Workshop | 2026-04-02 | 2026-04-17 | 10 | 10 | 10 | 0% | 11 | Not Started
W731LT_UN | W731 | W731.1780 | TOR Enhanced Defueling Safety Cases | 2026-04-02 | 2026-04-17 | Complete Risk Log with Estimates | 2026-04-02 | 2026-04-17 | 10 | 10 | 10 | 0% | 11 | Not Started
W731LT_UN | W731 | W731.1790 | TOR Enhanced Defueling Safety Cases | 2026-04-02 | 2026-04-17 | Update Schedule/Estimate from Risk Log & Add Provisions | 2026-04-02 | 2026-04-17 | 10 | 10 | 10 | 0% | 11 | Not Started
W731LT_UN | W731 | W731.1800 | TOR Enhanced Defueling Safety Cases | 2026-04-02 | 2026-04-17 | Add Data to PRC / IMS2 Paper | 2026-04-02 | 2026-04-17 | 10 | 10 | 10 | 0% | 11 | Not Started
W731LT_UN | W731 | W731.1810 | TOR Enhanced Defueling Safety Cases | 2026-04-02 | 2026-04-17 | PCL Validate & Approve Baseline Package for PRC Submission | 2026-04-02 | 2026-04-17 | 10 | 10 | 10 | 0% | 11 | Not Started
W731LT_UN | W731 | W731.1820 | TOR Enhanced Defueling Safety Cases | 2026-04-02 | 2026-04-17 | Prepare Draft Project Definition Document (PDD) | 2026-04-02 | 2026-04-17 | 10 | 10 | 10 | 0% | 11 | Not Started
W230LT | W230 | W230.3690 | HYB Enhanced Defueling Safety Case Strategy |  | 2025-07-17 | All CAT 2 Safety Cases: Lessons Learned Milestone - Gate D Lessons Learned Report Produced | 2026-04-02 | 2026-04-02 | 0 | 0 | 0 | 0% | 12 | Not Started
W234LT | W234 | W234.3690 | TOR Enhanced Defueling Safety Case Strategy |  | 2025-07-17 | All CAT 2 Safety Cases: Lessons Learned Milestone - Gate D Lessons Learned Report Produced | 2026-04-02 | 2026-04-02 | 0 | 0 | 0 | 0% | 12 | Not Started
W230LT | W230 | W230.1810 | HYB Enhanced Defueling Safety Case Strategy | 2025-07-18 | 2025-07-21 | Produce Project Closeout Report | 2026-04-07 | 2026-04-08 | 2 | 2 | 2 | 0% | 12 | Not Started
W234LT | W234 | W234.1810 | TOR Enhanced Defueling Safety Case Strategy | 2025-07-18 | 2025-07-21 | Produce Project Closeout Report | 2026-04-07 | 2026-04-08 | 2 | 2 | 2 | 0% | 12 | Not Started
W230LT | W230 | W230.1790 | HYB Enhanced Defueling Safety Case Strategy | 2025-07-22 | 2025-07-29 | Prepare Gate D PRC Paper | 2026-04-09 | 2026-04-16 | 6 | 6 | 6 | 0% | 12 | Not Started
W234LT | W234 | W234.1790 | TOR Enhanced Defueling Safety Case Strategy | 2025-07-22 | 2025-07-29 | Prepare Gate D PRC Paper | 2026-04-09 | 2026-04-16 | 6 | 6 | 6 | 0% | 12 | Not Started
W730LT_UN | W730 | W730.1670 | HYB Enhanced Defueling Safety Cases | 2026-04-16 | 2026-04-17 | Ensure Alignment of Schedule & Estimate | 2026-04-16 | 2026-04-17 | 2 | 2 | 2 | 0% | 11 | Not Started
W730LT_UN | W730 | W730.1680 | HYB Enhanced Defueling Safety Cases | 2026-04-16 | 2026-04-17 | Estimate Scope +/- 10% B-B+ & +/- 30% Lifecycle | 2026-04-16 | 2026-04-17 | 2 | 2 | 2 | 0% | 11 | Not Started
W730LT_UN | W730 | W730.1690 | HYB Enhanced Defueling Safety Cases | 2026-04-16 | 2026-04-17 | Plan Scope in Primavera (Level 2 B-B+ & Level 1 Lifecycle) | 2026-04-16 | 2026-04-17 | 2 | 2 | 2 | 0% | 11 | Not Started
W730LT_UN | W730 | W730.1700 | HYB Enhanced Defueling Safety Cases | 2026-04-16 | 2026-04-17 | Define Project Control Structures (WBS/CBS/OBS/PBS) | 2026-04-16 | 2026-04-17 | 2 | 2 | 2 | 0% | 11 | Not Started
W730LT_UN | W730 | W730.1720 | HYB Enhanced Defueling Safety Cases | 2026-04-16 | 2026-04-17 | Case Production Plan Peer Review & Update | 2026-04-16 | 2026-04-17 | 2 | 2 | 2 | 0% | 11 | Not Started
W731LT_UN | W731 | W731.1830 | TOR Enhanced Defueling Safety Cases | 2026-04-16 | 2026-04-17 | Case Production Plan Peer Review & Update | 2026-04-16 | 2026-04-17 | 2 | 2 | 2 | 0% | 11 | Not Started
W731LT_UN | W731 | W731.1840 | TOR Enhanced Defueling Safety Cases | 2026-04-16 | 2026-04-17 | Define Project Control Structures (WBS/CBS/OBS/PBS) | 2026-04-16 | 2026-04-17 | 2 | 2 | 2 | 0% | 11 | Not Started
W731LT_UN | W731 | W731.1850 | TOR Enhanced Defueling Safety Cases | 2026-04-16 | 2026-04-17 | Plan Scope in Primavera (Level 2 B-B+ & Level 1 Lifecycle) | 2026-04-16 | 2026-04-17 | 2 | 2 | 2 | 0% | 11 | Not Started
W731LT_UN | W731 | W731.1860 | TOR Enhanced Defueling Safety Cases | 2026-04-16 | 2026-04-17 | Estimate Scope +/- 10% B-B+ & +/- 30% Lifecycle | 2026-04-16 | 2026-04-17 | 2 | 2 | 2 | 0% | 11 | Not Started
W731LT_UN | W731 | W731.1870 | TOR Enhanced Defueling Safety Cases | 2026-04-16 | 2026-04-17 | Ensure Alignment of Schedule & Estimate | 2026-04-16 | 2026-04-17 | 2 | 2 | 2 | 0% | 11 | Not Started
W730LT_UN | W730 | W730.1710 | HYB Enhanced Defueling Safety Cases | 2026-05-06 | 2026-05-06 | Gate B+ PRC Paper Submission | 2026-05-06 | 2026-05-06 | 1 | 1 | 1 | 0% | 0 | Not Started
W230LT | W230 | W230.1800 | HYB Enhanced Defueling Safety Case Strategy | 2025-08-06 | 2025-08-06 | Gate D PRC Paper Submission | 2026-05-06 | 2026-05-06 | 1 | 1 | 1 | 0% | 0 | Not Started
W234LT | W234 | W234.1800 | TOR Enhanced Defueling Safety Case Strategy | 2025-08-06 | 2025-08-06 | Gate D PRC Paper Submission | 2026-05-06 | 2026-05-06 | 1 | 1 | 1 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.1880 | TOR Enhanced Defueling Safety Cases | 2026-05-06 | 2026-05-06 | Gate B+ PRC Paper Submission | 2026-05-06 | 2026-05-06 | 1 | 1 | 1 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.1730 | HYB Enhanced Defueling Safety Cases | 2026-05-07 | 2026-05-08 | PRC Members Review PRC / IMS2 Documentation | 2026-05-07 | 2026-05-08 | 2 | 2 | 2 | 0% | 6 | Not Started
W731LT_UN | W731 | W731.1890 | TOR Enhanced Defueling Safety Cases | 2026-05-07 | 2026-05-08 | PRC Members Review PRC / IMS2 Documentation | 2026-05-07 | 2026-05-08 | 2 | 2 | 2 | 0% | 6 | Not Started
W730LT_UN | W730 | W730.1760 | HYB Enhanced Defueling Safety Cases | 2026-05-19 | 2026-05-19 | Hold PRC Meeting | 2026-05-19 | 2026-05-19 | 1 | 1 | 1 | 0% | 0 | Not Started
W230LT | W230 | W230.1840 | HYB Enhanced Defueling Safety Case Strategy | 2025-08-19 | 2025-08-19 | Gate D - Hold PRC Meeting | 2026-05-19 | 2026-05-19 | 1 | 1 | 1 | 0% | 0 | Not Started
W234LT | W234 | W234.1840 | TOR Enhanced Defueling Safety Case Strategy | 2025-08-19 | 2025-08-19 | Gate D - Hold PRC Meeting | 2026-05-19 | 2026-05-19 | 1 | 1 | 1 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.1900 | TOR Enhanced Defueling Safety Cases | 2026-05-19 | 2026-05-19 | Hold PRC Meeting | 2026-05-19 | 2026-05-19 | 1 | 1 | 1 | 0% | 0 | Not Started
W230LT | W230 | W230.1110 | HYB Enhanced Defueling Safety Case Strategy |  | 2025-08-19 | Gate D Approved | 2026-05-19 | 2026-05-19 | 0 | 0 | 0 | 0% | 0 | Not Started
W230LT | W230 | W230.1020 | HYB Enhanced Defueling Safety Case Strategy |  | 2025-08-19 | Project Finish | 2026-05-19 | 2026-05-19 | 0 | 0 | 0 | 0% | 0 | Not Started
W234LT | W234 | W234.1110 | TOR Enhanced Defueling Safety Case Strategy |  | 2025-08-19 | Gate D Approved | 2026-05-19 | 2026-05-19 | 0 | 0 | 0 | 0% | 0 | Not Started
W234LT | W234 | W234.1020 | TOR Enhanced Defueling Safety Case Strategy |  | 2025-08-19 | Project Finish | 2026-05-19 | 2026-05-19 | 0 | 0 | 0 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.1750 | HYB Enhanced Defueling Safety Cases | 2026-05-20 | 2026-05-21 | Modify Estimate, Schedule & Risk Log as Required | 2026-05-20 | 2026-05-21 | 2 | 2 | 2 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.1910 | TOR Enhanced Defueling Safety Cases | 2026-05-20 | 2026-05-21 | Modify Estimate, Schedule & Risk Log as Required | 2026-05-20 | 2026-05-21 | 2 | 2 | 2 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.1740 | HYB Enhanced Defueling Safety Cases | 2026-05-21 | 2026-05-21 | Modify PRC Paper as Required | 2026-05-21 | 2026-05-21 | 1 | 1 | 1 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.1920 | TOR Enhanced Defueling Safety Cases | 2026-05-21 | 2026-05-21 | Modify PRC Paper as Required | 2026-05-21 | 2026-05-21 | 1 | 1 | 1 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.1770 | HYB Enhanced Defueling Safety Cases |  | 2026-05-21 | Gate B+ PRC Paper Approval | 2026-05-21 | 2026-05-21 | 0 | 0 | 0 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.1140 | HYB Enhanced Defueling Safety Cases |  | 2026-05-21 | Gate B+ Approved | 2026-05-21 | 2026-05-21 | 0 | 0 | 0 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.2510 | HYB Enhanced Defueling Safety Cases | 2026-05-21 | 2027-05-06 | ## HYB Low Deacy Heat: B+ - B++ Phase Funding - (Cost Summary) ## | 2026-05-21 | 2027-05-06 | 243 | 243 | 243 | 0% | 230 | Not Started
W730LT_UN | W730 | W730.2690 | HYB Enhanced Defueling Safety Cases |  | 2026-05-21 | HYB Low Decay Heat: Commence Supporting References or Supporting EC's | 2026-05-21 | 2026-05-21 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.1930 | TOR Enhanced Defueling Safety Cases |  | 2026-05-21 | TOR Low Decay Heat: Commence Supporting References or Supporting EC's | 2026-05-21 | 2026-05-21 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.1970 | TOR Enhanced Defueling Safety Cases | 2026-05-21 | 2027-05-06 | ## TOR Low Deacy Heat: B+ - B++ Phase Funding - (Cost Summary) ## | 2026-05-21 | 2027-05-06 | 243 | 243 | 243 | 0% | 230 | Not Started
W731LT_UN | W731 | W731.1940 | TOR Enhanced Defueling Safety Cases |  | 2026-05-21 | Gate B+ Approved | 2026-05-21 | 2026-05-21 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.1950 | TOR Enhanced Defueling Safety Cases |  | 2026-05-21 | Gate B+ PRC Paper Approval | 2026-05-21 | 2026-05-21 | 0 | 0 | 0 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.2400 | HYB Enhanced Defueling Safety Cases | 2026-05-22 | 2026-06-19 | HYB Enhanced Defueling Rate: Verification of the case - First Round Comments (using BARRIER MODEL) | 2026-05-22 | 2026-06-19 | 20 | 20 | 20 | 0% | 395 | Not Started
W730LT_UN | W730 | W730.2860 | HYB Enhanced Defueling Safety Cases | 2026-05-22 | 2026-07-17 | HYB Low Decay Heat: Produce Supporting References Author / Verify / Approve | 2026-05-22 | 2026-07-17 | 40 | 40 | 40 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.1960 | TOR Enhanced Defueling Safety Cases | 2026-05-22 | 2026-07-17 | TOR Low Decay Heat: Produce Supporting References Author / Verify / Approve | 2026-05-22 | 2026-07-17 | 40 | 40 | 40 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.1980 | TOR Enhanced Defueling Safety Cases | 2026-05-22 | 2026-06-19 | TOR Enhanced Defueling Rate: Verification of the case - First Round Comments (using BARRIER MODEL) | 2026-05-22 | 2026-06-19 | 20 | 20 | 20 | 0% | 395 | Not Started
W730LT_UN | W730 | W730.2390 | HYB Enhanced Defueling Safety Cases | 2026-06-22 | 2026-06-26 | HYB Enhanced Defueling Rate: Incorporate all stakeholder comments | 2026-06-22 | 2026-06-26 | 5 | 5 | 5 | 0% | 395 | Not Started
W731LT_UN | W731 | W731.1990 | TOR Enhanced Defueling Safety Cases | 2026-06-22 | 2026-06-26 | TOR Enhanced Defueling Rate: Incorporate all stakeholder comments | 2026-06-22 | 2026-06-26 | 5 | 5 | 5 | 0% | 395 | Not Started
W730LT_UN | W730 | W730.2360 | HYB Enhanced Defueling Safety Cases | 2026-06-29 | 2026-07-03 | HYB Enhanced Defueling Rate: Final Verification | 2026-06-29 | 2026-07-03 | 5 | 5 | 5 | 0% | 395 | Not Started
W731LT_UN | W731 | W731.2000 | TOR Enhanced Defueling Safety Cases | 2026-06-29 | 2026-07-03 | TOR Enhanced Defueling Rate: Final Verification | 2026-06-29 | 2026-07-03 | 5 | 5 | 5 | 0% | 395 | Not Started
W784LT_UN | W784 | W784.1000 | DNB Cold Depressurised Defueling Safety Case | 2026-07-01 | 2027-07-30 | Project Management External | 01-Jul-26* | 2027-07-30 | 276 | 276 | 276 | 0% | 0 | Not Started
W784LT_UN | W784 | W784.1010 | DNB Cold Depressurised Defueling Safety Case | 2026-07-01 | 2027-07-30 | Project Management Internal | 01-Jul-26* | 2027-07-30 | 276 | 276 | 276 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.2410 | HYB Enhanced Defueling Safety Cases | 2026-07-06 | 2026-07-17 | HYB Enhanced Defueling Rate: Final Verification Risk (Risk 42008) | 2026-07-06 | 2026-07-17 | 10 | 10 | 10 | 0% | 395 | Not Started
W731LT_UN | W731 | W731.2010 | TOR Enhanced Defueling Safety Cases | 2026-07-06 | 2026-07-17 | TOR Enhanced Defueling Rate: Final Verification Risk (Risk 42008) | 2026-07-06 | 2026-07-17 | 10 | 10 | 10 | 0% | 395 | Not Started
W730LT_UN | W730 | W730.1090 | HYB Enhanced Defueling Safety Cases |  | 2026-07-17 | HYB Enhanced Defueling Rate: Verification Complete/ Verified Draft A Issued for INSA EC NNNNNN | 2026-07-17 | 2026-07-17 | 0 | 0 | 0 | 0% | 395 | Not Started
W730LT_UN | W730 | W730.2380 | HYB Enhanced Defueling Safety Cases |  | 2026-07-17 | HYB Enhanced Defueling Rate: Submit for approval - Categoriser ratifies; RE/CO endorsement | 2026-07-17 | 2026-07-17 | 0 | 0 | 0 | 0% | 395 | Not Started
W730LT_UN | W730 | W730.2700 | HYB Enhanced Defueling Safety Cases |  | 2026-07-17 | HYB Low Decay Heat: All Supporting References Approved and Issued | 2026-07-17 | 2026-07-17 | 0 | 0 | 0 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3390 | HYB Enhanced Defueling Safety Cases |  | 2026-07-17 | HYB Low Decay Heat: All Key Supporting Technical References Completed | 2026-07-17 | 2026-07-17 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2020 | TOR Enhanced Defueling Safety Cases |  | 2026-07-17 | TOR Low Decay Heat: All Key Supporting Technical References Completed | 2026-07-17 | 2026-07-17 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2030 | TOR Enhanced Defueling Safety Cases |  | 2026-07-17 | TOR Low Decay Heat: All Supporting References Approved and Issued | 2026-07-17 | 2026-07-17 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2040 | TOR Enhanced Defueling Safety Cases |  | 2026-07-17 | TOR Enhanced Defueling Rate: Submit for approval - Categoriser ratifies; RE/CO endorsement | 2026-07-17 | 2026-07-17 | 0 | 0 | 0 | 0% | 395 | Not Started
W731LT_UN | W731 | W731.2050 | TOR Enhanced Defueling Safety Cases |  | 2026-07-17 | TOR Enhanced Defueling Rate: Verification Complete/ Verified Draft A Issued for INSA EC NNNNNN | 2026-07-17 | 2026-07-17 | 0 | 0 | 0 | 0% | 395 | Not Started
W730LT_UN | W730 | W730.2420 | HYB Enhanced Defueling Safety Cases | 2026-07-20 | 2026-08-14 | HYB Enhanced Defueling Rate: INSA review & iteration of comments (using BARRIER MODEL) | 2026-07-20 | 2026-08-14 | 20 | 20 | 20 | 0% | 395 | Not Started
W730LT_UN | W730 | W730.2710 | HYB Enhanced Defueling Safety Cases | 2026-07-20 | 2026-07-24 | HYB Low Decay Heat: Produce verification plan | 2026-07-20 | 2026-07-24 | 5 | 5 | 5 | 0% | 61 | Not Started
W730LT_UN | W730 | W730.2720 | HYB Enhanced Defueling Safety Cases | 2026-07-20 | 2026-09-14 | HYB Low Decay Heat: Prepare / Author the Safety Case Proposal | 2026-07-20 | 2026-09-14 | 40 | 40 | 40 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.2920 | HYB Enhanced Defueling Safety Cases | 2026-07-20 | 2026-07-22 | HYB Low Decay Heat: Lessons Learned Activitiy - Following Completeion of Technical References | 2026-07-20 | 2026-07-22 | 3 | 3 | 3 | 0% | 430 | Not Started
W731LT_UN | W731 | W731.2060 | TOR Enhanced Defueling Safety Cases | 2026-07-20 | 2026-07-22 | TOR Low Decay Heat: Lessons Learned Activitiy - Following Completeion of Technical References | 2026-07-20 | 2026-07-22 | 3 | 3 | 3 | 0% | 430 | Not Started
W731LT_UN | W731 | W731.2070 | TOR Enhanced Defueling Safety Cases | 2026-07-20 | 2026-09-14 | TOR Low Decay Heat: Prepare / Author the Safety Case Proposal | 2026-07-20 | 2026-09-14 | 40 | 40 | 40 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2080 | TOR Enhanced Defueling Safety Cases | 2026-07-20 | 2026-07-24 | TOR Low Decay Heat: Produce verification plan | 2026-07-20 | 2026-07-24 | 5 | 5 | 5 | 0% | 61 | Not Started
W731LT_UN | W731 | W731.2090 | TOR Enhanced Defueling Safety Cases | 2026-07-20 | 2026-08-14 | TOR Enhanced Defueling Rate: INSA review & iteration of comments (using BARRIER MODEL) | 2026-07-20 | 2026-08-14 | 20 | 20 | 20 | 0% | 395 | Not Started
W730LT_UN | W730 | W730.3600 | HYB Enhanced Defueling Safety Cases |  | 2026-07-22 | HYB Low Decay Heat: Lessons Learned Milestone - Technical References | 2026-07-22 | 2026-07-22 | 0 | 0 | 0 | 0% | 430 | Not Started
W731LT_UN | W731 | W731.2100 | TOR Enhanced Defueling Safety Cases |  | 2026-07-22 | TOR Low Decay Heat: Lessons Learned Milestone - Technical References | 2026-07-22 | 2026-07-22 | 0 | 0 | 0 | 0% | 430 | Not Started
W730LT_UN | W730 | W730.1065 | HYB Enhanced Defueling Safety Cases |  | 2026-08-14 | HYB Enhanced Defueling Rate: INSA Final Approval EC NNNNNN - Enhanced Defueling Rate | 2026-08-14 | 2026-08-14 | 0 | 0 | 0 | 0% | 398 | Not Started
W731LT_UN | W731 | W731.2110 | TOR Enhanced Defueling Safety Cases |  | 2026-08-14 | TOR Enhanced Defueling Rate: INSA Final Approval EC NNNNNN - Enhanced Defueling Rate | 2026-08-14 | 2026-08-14 | 0 | 0 | 0 | 0% | 398 | Not Started
W730LT_UN | W730 | W730.2470 | HYB Enhanced Defueling Safety Cases | 2026-08-17 | 2026-08-19 | HYB Enhanced Defueling Rate: Lessons Learned Activitiy - Following Verification of the SC | 2026-08-17 | 2026-08-19 | 3 | 3 | 3 | 0% | 395 | Not Started
W731LT_UN | W731 | W731.2120 | TOR Enhanced Defueling Safety Cases | 2026-08-17 | 2026-08-19 | TOR Enhanced Defueling Rate: Lessons Learned Activitiy - Following Verification of the SC | 2026-08-17 | 2026-08-19 | 3 | 3 | 3 | 0% | 395 | Not Started
W730LT_UN | W730 | W730.1250 | HYB Enhanced Defueling Safety Cases |  | 2026-08-19 | HYB Enhanced Defueling Rate: Lessons Learned Milestone - Verification of the Safety Case | 2026-08-19 | 2026-08-19 | 0 | 0 | 0 | 0% | 410 | Not Started
W731LT_UN | W731 | W731.2130 | TOR Enhanced Defueling Safety Cases |  | 2026-08-19 | TOR Enhanced Defueling Rate: Lessons Learned Milestone - Verification of the Safety Case | 2026-08-19 | 2026-08-19 | 0 | 0 | 0 | 0% | 410 | Not Started
W730LT_UN | W730 | W730.2450 | HYB Enhanced Defueling Safety Cases | 2026-08-20 | 2026-08-20 | HYB Enhanced Defueling Rate: Send CAT 2 Paper to ONR to Determine Level of Review Required (Acknowledge or Agreement) | 2026-08-20 | 2026-08-20 | 1 | 1 | 1 | 0% | 395 | Not Started
W731LT_UN | W731 | W731.2140 | TOR Enhanced Defueling Safety Cases | 2026-08-20 | 2026-08-20 | TOR Enhanced Defueling Rate: Send CAT 2 Paper to ONR to Determine Level of Review Required (Acknowledge or Agreement) | 2026-08-20 | 2026-08-20 | 1 | 1 | 1 | 0% | 395 | Not Started
W730LT_UN | W730 | W730.1050 | HYB Enhanced Defueling Safety Cases |  | 2026-08-20 | HYB Enhanced Defueling Rate: ONR Agree/Acknowledge Safety Case - Enhanced Defueling Rate | 2026-08-20 | 2026-08-20 | 0 | 0 | 0 | 0% | 398 | Not Started
W731LT_UN | W731 | W731.2150 | TOR Enhanced Defueling Safety Cases |  | 2026-08-20 | TOR Enhanced Defueling Rate: ONR Agree/Acknowledge Safety Case - Enhanced Defueling Rate | 2026-08-20 | 2026-08-20 | 0 | 0 | 0 | 0% | 398 | Not Started
W730LT_UN | W730 | W730.2480 | HYB Enhanced Defueling Safety Cases | 2026-08-21 | 2026-08-25 | HYB Enhanced Defueling Rate: Lessons Learned Activitiy - Following INSA Review of the SC | 2026-08-21 | 2026-08-25 | 3 | 3 | 3 | 0% | 395 | Not Started
W731LT_UN | W731 | W731.2160 | TOR Enhanced Defueling Safety Cases | 2026-08-21 | 2026-08-25 | TOR Enhanced Defueling Rate: Lessons Learned Activitiy - Following INSA Review of the SC | 2026-08-21 | 2026-08-25 | 3 | 3 | 3 | 0% | 395 | Not Started
W730LT_UN | W730 | W730.1260 | HYB Enhanced Defueling Safety Cases |  | 2026-08-25 | HYB Enhanced Defueling Rate: Lessons Learned Milestone - INSA Review of the Safety Case | 2026-08-25 | 2026-08-25 | 0 | 0 | 0 | 0% | 406 | Not Started
W731LT_UN | W731 | W731.2170 | TOR Enhanced Defueling Safety Cases |  | 2026-08-25 | TOR Enhanced Defueling Rate: Lessons Learned Milestone - INSA Review of the Safety Case | 2026-08-25 | 2026-08-25 | 0 | 0 | 0 | 0% | 406 | Not Started
W730LT_UN | W730 | W730.2460 | HYB Enhanced Defueling Safety Cases | 2026-08-26 | 2026-09-02 | HYB Enhanced Defueling Rate: Station Approval | 2026-08-26 | 2026-09-02 | 5 | 5 | 5 | 0% | 395 | Not Started
W731LT_UN | W731 | W731.2180 | TOR Enhanced Defueling Safety Cases | 2026-08-26 | 2026-09-02 | TOR Enhanced Defueling Rate: Station Approval | 2026-08-26 | 2026-09-02 | 5 | 5 | 5 | 0% | 395 | Not Started
W730LT_UN | W730 | W730.2340 | HYB Enhanced Defueling Safety Cases |  | 2026-09-02 | HYB Enhanced Defueling Rate: Station Approved Safety Case | 2026-09-02 | 2026-09-02 | 0 | 0 | 0 | 0% | 395 | Not Started
W730LT_UN | W730 | W730.1080 | HYB Enhanced Defueling Safety Cases |  | 2026-09-02 | HYB Enhanced Defueling Rate: Safety Case Approved - (Station Approval) - EC NNNNNN | 2026-09-02 | 2026-09-02 | 0 | 0 | 0 | 0% | 395 | Not Started
W731LT_UN | W731 | W731.2190 | TOR Enhanced Defueling Safety Cases |  | 2026-09-02 | TOR Enhanced Defueling Rate: Safety Case Approved - (Station Approval) - EC NNNNNN | 2026-09-02 | 2026-09-02 | 0 | 0 | 0 | 0% | 395 | Not Started
W731LT_UN | W731 | W731.2200 | TOR Enhanced Defueling Safety Cases |  | 2026-09-02 | TOR Enhanced Defueling Rate: Station Approved Safety Case | 2026-09-02 | 2026-09-02 | 0 | 0 | 0 | 0% | 395 | Not Started
W730LT_UN | W730 | W730.2430 | HYB Enhanced Defueling Safety Cases | 2026-09-03 | 2026-09-09 | HYB Enhanced Defueling Rate: Develop Implementation & Closeout | 2026-09-03 | 2026-09-09 | 5 | 5 | 5 | 0% | 395 | Not Started
W731LT_UN | W731 | W731.2210 | TOR Enhanced Defueling Safety Cases | 2026-09-03 | 2026-09-09 | TOR Enhanced Defueling Rate: Develop Implementation & Closeout | 2026-09-03 | 2026-09-09 | 5 | 5 | 5 | 0% | 395 | Not Started
W730LT_UN | W730 | W730.2440 | HYB Enhanced Defueling Safety Cases | 2026-09-10 | 2026-09-10 | HYB Enhanced Defueling Rate: Post Job Debrief | 2026-09-10 | 2026-09-10 | 1 | 1 | 1 | 0% | 395 | Not Started
W731LT_UN | W731 | W731.2220 | TOR Enhanced Defueling Safety Cases | 2026-09-10 | 2026-09-10 | TOR Enhanced Defueling Rate: Post Job Debrief | 2026-09-10 | 2026-09-10 | 1 | 1 | 1 | 0% | 395 | Not Started
W730LT_UN | W730 | W730.3400 | HYB Enhanced Defueling Safety Cases |  | 2026-09-14 | HYB Low Decay Heat: Safety Case Paper Authoring Complete EC NNNNNN | 2026-09-14 | 2026-09-14 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2230 | TOR Enhanced Defueling Safety Cases |  | 2026-09-14 | TOR Low Decay Heat: Safety Case Paper Authoring Complete EC NNNNNN | 2026-09-14 | 2026-09-14 | 0 | 0 | 0 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.2490 | HYB Enhanced Defueling Safety Cases | 2026-09-15 | 2026-09-17 | HYB Low Decay Heat: Requirements Capture | 2026-09-15 | 2026-09-17 | 3 | 3 | 3 | 0% | 3 | Not Started
W730LT_UN | W730 | W730.2740 | HYB Enhanced Defueling Safety Cases | 2026-09-15 | 2026-09-22 | HYB Low Decay Heat: Final Authoring Consolidation Check | 2026-09-15 | 2026-09-22 | 6 | 6 | 6 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.2890 | HYB Enhanced Defueling Safety Cases | 2026-09-15 | 2026-09-17 | HYB Low Decay Heat: Lessons Learned Activitiy - Following Authoring of SC | 2026-09-15 | 2026-09-17 | 3 | 3 | 3 | 0% | 390 | Not Started
W731LT_UN | W731 | W731.2240 | TOR Enhanced Defueling Safety Cases | 2026-09-15 | 2026-09-17 | TOR Low Decay Heat: Lessons Learned Activitiy - Following Authoring of SC | 2026-09-15 | 2026-09-17 | 3 | 3 | 3 | 0% | 390 | Not Started
W731LT_UN | W731 | W731.2250 | TOR Enhanced Defueling Safety Cases | 2026-09-15 | 2026-09-22 | TOR Low Decay Heat: Final Authoring Consolidation Check | 2026-09-15 | 2026-09-22 | 6 | 6 | 6 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2260 | TOR Enhanced Defueling Safety Cases | 2026-09-15 | 2026-09-17 | TOR Low Decay Heat: Requirements Capture | 2026-09-15 | 2026-09-17 | 3 | 3 | 3 | 0% | 3 | Not Started
W730LT_UN | W730 | W730.3610 | HYB Enhanced Defueling Safety Cases |  | 2026-09-17 | HYB Low Decay Heat: Lessons Learned Milestone - Authoring of the Safety Case | 2026-09-17 | 2026-09-17 | 0 | 0 | 0 | 0% | 390 | Not Started
W731LT_UN | W731 | W731.2270 | TOR Enhanced Defueling Safety Cases |  | 2026-09-17 | TOR Low Decay Heat: Lessons Learned Milestone - Authoring of the Safety Case | 2026-09-17 | 2026-09-17 | 0 | 0 | 0 | 0% | 390 | Not Started
W730LT_UN | W730 | W730.2730 | HYB Enhanced Defueling Safety Cases | 2026-09-23 | 2026-10-20 | HYB Low Decay Heat: Obtain CO Review & Detail Checker | 2026-09-23 | 2026-10-20 | 20 | 20 | 20 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2280 | TOR Enhanced Defueling Safety Cases | 2026-09-23 | 2026-10-20 | TOR Low Decay Heat: Obtain CO Review & Detail Checker | 2026-09-23 | 2026-10-20 | 20 | 20 | 20 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.2750 | HYB Enhanced Defueling Safety Cases |  | 2026-10-20 | HYB Low Decay Heat: Verification Commenced (T-11) | 2026-10-20 | 2026-10-20 | 0 | 0 | 0 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.2770 | HYB Enhanced Defueling Safety Cases |  | 2026-10-20 | HYB Low Decay Heat: Issue to Peer CO & Station for comments | 2026-10-20 | 2026-10-20 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2290 | TOR Enhanced Defueling Safety Cases |  | 2026-10-20 | TOR Low Decay Heat: Issue to Peer CO & Station for comments | 2026-10-20 | 2026-10-20 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2300 | TOR Enhanced Defueling Safety Cases |  | 2026-10-20 | TOR Low Decay Heat: Verification Commenced (T-11) | 2026-10-20 | 2026-10-20 | 0 | 0 | 0 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.2800 | HYB Enhanced Defueling Safety Cases | 2026-10-21 | 2026-12-15 | HYB Low Decay Heat: Verification of the case - First Round Comments (using BARRIER MODEL) | 2026-10-21 | 2026-12-15 | 40 | 40 | 40 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2310 | TOR Enhanced Defueling Safety Cases | 2026-10-21 | 2026-12-15 | TOR Low Decay Heat: Verification of the case - First Round Comments (using BARRIER MODEL) | 2026-10-21 | 2026-12-15 | 40 | 40 | 40 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.2790 | HYB Enhanced Defueling Safety Cases | 2026-12-16 | 2027-01-21 | HYB Low Decay Heat: Incorporate all stakeholder comments | 2026-12-16 | 2027-01-21 | 25 | 25 | 25 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2320 | TOR Enhanced Defueling Safety Cases | 2026-12-16 | 2027-01-21 | TOR Low Decay Heat: Incorporate all stakeholder comments | 2026-12-16 | 2027-01-21 | 25 | 25 | 25 | 0% | 0 | Not Started
W520LT | W520 | W520.A1040 | FLEETWIDE CTO Defueling Safety Case Delivery |  | 2024-12-31 | Project Completed | 2026-12-28 | 2026-12-28 | 0 | 0 | 0 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.2760 | HYB Enhanced Defueling Safety Cases | 2027-01-22 | 2027-02-18 | HYB Low Decay Heat: Final Verification | 2027-01-22 | 2027-02-18 | 20 | 20 | 20 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2330 | TOR Enhanced Defueling Safety Cases | 2027-01-22 | 2027-02-18 | TOR Low Decay Heat: Final Verification | 2027-01-22 | 2027-02-18 | 20 | 20 | 20 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.2780 | HYB Enhanced Defueling Safety Cases |  | 2027-02-18 | HYB Low Decay Heat: Submit for approval - Categoriser ratifies; RE/CO endorsement | 2027-02-18 | 2027-02-18 | 0 | 0 | 0 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3450 | HYB Enhanced Defueling Safety Cases |  | 2027-02-18 | HYB Low Decay Heat: Verification Complete/ Verified Draft A Issued for INSA EC NNNNNN | 2027-02-18 | 2027-02-18 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2340 | TOR Enhanced Defueling Safety Cases |  | 2027-02-18 | TOR Low Decay Heat: Verification Complete/ Verified Draft A Issued for INSA EC NNNNNN | 2027-02-18 | 2027-02-18 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2350 | TOR Enhanced Defueling Safety Cases |  | 2027-02-18 | TOR Low Decay Heat: Submit for approval - Categoriser ratifies; RE/CO endorsement | 2027-02-18 | 2027-02-18 | 0 | 0 | 0 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.2820 | HYB Enhanced Defueling Safety Cases | 2027-02-19 | 2027-03-18 | HYB Low Decay Heat: INSA review & iteration of comments (using BARRIER MODEL) | 2027-02-19 | 2027-03-18 | 20 | 20 | 20 | 0% | 218 | Not Started
W730LT_UN | W730 | W730.2900 | HYB Enhanced Defueling Safety Cases | 2027-02-19 | 2027-02-23 | HYB Low Decay Heat: Lessons Learned Activitiy - Following Verification of the SC | 2027-02-19 | 2027-02-23 | 3 | 3 | 3 | 0% | 279 | Not Started
W730LT_UN | W730 | W730.4020 | HYB Enhanced Defueling Safety Cases | 2027-02-19 | 2027-03-04 | Confirm Objectives to be Delivered at Gate B++ | 2027-02-19 | 2027-03-04 | 10 | 10 | 10 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2360 | TOR Enhanced Defueling Safety Cases | 2027-02-19 | 2027-03-04 | Confirm Objectives to be Delivered at Gate B++ | 2027-02-19 | 2027-03-04 | 10 | 10 | 10 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2370 | TOR Enhanced Defueling Safety Cases | 2027-02-19 | 2027-02-23 | TOR Low Decay Heat: Lessons Learned Activitiy - Following Verification of the SC | 2027-02-19 | 2027-02-23 | 3 | 3 | 3 | 0% | 279 | Not Started
W731LT_UN | W731 | W731.2380 | TOR Enhanced Defueling Safety Cases | 2027-02-19 | 2027-03-18 | TOR Low Decay Heat: INSA review & iteration of comments (using BARRIER MODEL) | 2027-02-19 | 2027-03-18 | 20 | 20 | 20 | 0% | 218 | Not Started
W730LT_UN | W730 | W730.3620 | HYB Enhanced Defueling Safety Cases |  | 2027-02-23 | HYB Low Decay Heat: Lessons Learned Milestone - Verification of the Safety Case | 2027-02-23 | 2027-02-23 | 0 | 0 | 0 | 0% | 279 | Not Started
W731LT_UN | W731 | W731.2390 | TOR Enhanced Defueling Safety Cases |  | 2027-02-23 | TOR Low Decay Heat: Lessons Learned Milestone - Verification of the Safety Case | 2027-02-23 | 2027-02-23 | 0 | 0 | 0 | 0% | 279 | Not Started
W730LT_UN | W730 | W730.4010 | HYB Enhanced Defueling Safety Cases | 2027-03-05 | 2027-03-18 | Initial high level scope of programme | 2027-03-05 | 2027-03-18 | 10 | 10 | 10 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2400 | TOR Enhanced Defueling Safety Cases | 2027-03-05 | 2027-03-18 | Initial high level scope of programme | 2027-03-05 | 2027-03-18 | 10 | 10 | 10 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.4070 | HYB Enhanced Defueling Safety Cases | 2027-03-09 | 2027-03-22 | Prepare Draft Project Definition Document (PDD) | 2027-03-09 | 2027-03-22 | 10 | 10 | 10 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.4080 | HYB Enhanced Defueling Safety Cases | 2027-03-09 | 2027-03-22 | PCL Validate & Approve Baseline Package for PRC Submission | 2027-03-09 | 2027-03-22 | 10 | 10 | 10 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.4090 | HYB Enhanced Defueling Safety Cases | 2027-03-09 | 2027-03-22 | Add Data to PRC / IMS2 Paper | 2027-03-09 | 2027-03-22 | 10 | 10 | 10 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.4100 | HYB Enhanced Defueling Safety Cases | 2027-03-09 | 2027-03-22 | Update Schedule/Estimate from Risk Log & Add Provisions | 2027-03-09 | 2027-03-22 | 10 | 10 | 10 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.4110 | HYB Enhanced Defueling Safety Cases | 2027-03-09 | 2027-03-22 | Complete Risk Log with Estimates | 2027-03-09 | 2027-03-22 | 10 | 10 | 10 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.4120 | HYB Enhanced Defueling Safety Cases | 2027-03-09 | 2027-03-22 | Hold Risk Workshop | 2027-03-09 | 2027-03-22 | 10 | 10 | 10 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2410 | TOR Enhanced Defueling Safety Cases | 2027-03-09 | 2027-03-22 | Hold Risk Workshop | 2027-03-09 | 2027-03-22 | 10 | 10 | 10 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2420 | TOR Enhanced Defueling Safety Cases | 2027-03-09 | 2027-03-22 | Complete Risk Log with Estimates | 2027-03-09 | 2027-03-22 | 10 | 10 | 10 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2430 | TOR Enhanced Defueling Safety Cases | 2027-03-09 | 2027-03-22 | Update Schedule/Estimate from Risk Log & Add Provisions | 2027-03-09 | 2027-03-22 | 10 | 10 | 10 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2440 | TOR Enhanced Defueling Safety Cases | 2027-03-09 | 2027-03-22 | Add Data to PRC / IMS2 Paper | 2027-03-09 | 2027-03-22 | 10 | 10 | 10 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2450 | TOR Enhanced Defueling Safety Cases | 2027-03-09 | 2027-03-22 | PCL Validate & Approve Baseline Package for PRC Submission | 2027-03-09 | 2027-03-22 | 10 | 10 | 10 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2460 | TOR Enhanced Defueling Safety Cases | 2027-03-09 | 2027-03-22 | Prepare Draft Project Definition Document (PDD) | 2027-03-09 | 2027-03-22 | 10 | 10 | 10 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.2810 | HYB Enhanced Defueling Safety Cases | 2027-03-19 | 2027-04-05 | HYB Low Decay Heat: Incorporate INSA comments | 2027-03-19 | 2027-04-05 | 10 | 10 | 10 | 0% | 218 | Not Started
W730LT_UN | W730 | W730.4130 | HYB Enhanced Defueling Safety Cases | 2027-03-19 | 2027-03-22 | Ensure Alignment of Schedule & Estimate | 2027-03-19 | 2027-03-22 | 2 | 2 | 2 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.4140 | HYB Enhanced Defueling Safety Cases | 2027-03-19 | 2027-03-22 | Estimate Scope +/- 10% B+-B++ & +/- 30% Lifecycle | 2027-03-19 | 2027-03-22 | 2 | 2 | 2 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.4150 | HYB Enhanced Defueling Safety Cases | 2027-03-19 | 2027-03-22 | Plan Scope in Primavera (Level 2 B+-B++ & Level 1 Lifecycle) | 2027-03-19 | 2027-03-22 | 2 | 2 | 2 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.4160 | HYB Enhanced Defueling Safety Cases | 2027-03-19 | 2027-03-22 | Define Project Control Structures (WBS/CBS/OBS/PBS) | 2027-03-19 | 2027-03-22 | 2 | 2 | 2 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.4180 | HYB Enhanced Defueling Safety Cases | 2027-03-19 | 2027-03-22 | Case Production Plan Peer Review & Update | 2027-03-19 | 2027-03-22 | 2 | 2 | 2 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2470 | TOR Enhanced Defueling Safety Cases | 2027-03-19 | 2027-03-22 | Case Production Plan Peer Review & Update | 2027-03-19 | 2027-03-22 | 2 | 2 | 2 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2480 | TOR Enhanced Defueling Safety Cases | 2027-03-19 | 2027-03-22 | Define Project Control Structures (WBS/CBS/OBS/PBS) | 2027-03-19 | 2027-03-22 | 2 | 2 | 2 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2490 | TOR Enhanced Defueling Safety Cases | 2027-03-19 | 2027-03-22 | Plan Scope in Primavera (Level 2 B+-B++ & Level 1 Lifecycle) | 2027-03-19 | 2027-03-22 | 2 | 2 | 2 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2500 | TOR Enhanced Defueling Safety Cases | 2027-03-19 | 2027-03-22 | Estimate Scope +/- 10% B+-B++ & +/- 30% Lifecycle | 2027-03-19 | 2027-03-22 | 2 | 2 | 2 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2510 | TOR Enhanced Defueling Safety Cases | 2027-03-19 | 2027-03-22 | Ensure Alignment of Schedule & Estimate | 2027-03-19 | 2027-03-22 | 2 | 2 | 2 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2520 | TOR Enhanced Defueling Safety Cases | 2027-03-19 | 2027-04-05 | TOR Low Decay Heat: Incorporate INSA comments | 2027-03-19 | 2027-04-05 | 10 | 10 | 10 | 0% | 218 | Not Started
W730LT_UN | W730 | W730.4170 | HYB Enhanced Defueling Safety Cases | 2027-03-23 | 2027-03-23 | Gate B++ PRC Paper Submission | 2027-03-23 | 2027-03-23 | 1 | 1 | 1 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2530 | TOR Enhanced Defueling Safety Cases | 2027-03-23 | 2027-03-23 | Gate B++ PRC Paper Submission | 2027-03-23 | 2027-03-23 | 1 | 1 | 1 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.4030 | HYB Enhanced Defueling Safety Cases | 2027-03-24 | 2027-03-25 | PRC Members Review PRC / IMS2 Documentation | 2027-03-24 | 2027-03-25 | 2 | 2 | 2 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2540 | TOR Enhanced Defueling Safety Cases | 2027-03-24 | 2027-03-25 | PRC Members Review PRC / IMS2 Documentation | 2027-03-24 | 2027-03-25 | 2 | 2 | 2 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.4060 | HYB Enhanced Defueling Safety Cases | 2027-03-26 | 2027-03-26 | Hold PRC Meeting | 2027-03-26 | 2027-03-26 | 1 | 1 | 1 | 0% | 1 | Not Started
W731LT_UN | W731 | W731.2550 | TOR Enhanced Defueling Safety Cases | 2027-03-26 | 2027-03-26 | Hold PRC Meeting | 2027-03-26 | 2027-03-26 | 1 | 1 | 1 | 0% | 1 | Not Started
W730LT_UN | W730 | W730.4050 | HYB Enhanced Defueling Safety Cases | 2027-03-30 | 2027-03-31 | Modify Estimate, Schedule & Risk Log as Required | 2027-03-30 | 2027-03-31 | 2 | 2 | 2 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2560 | TOR Enhanced Defueling Safety Cases | 2027-03-30 | 2027-03-31 | Modify Estimate, Schedule & Risk Log as Required | 2027-03-30 | 2027-03-31 | 2 | 2 | 2 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.4040 | HYB Enhanced Defueling Safety Cases | 2027-03-31 | 2027-03-31 | Modify PRC Paper as Required | 2027-03-31 | 2027-03-31 | 1 | 1 | 1 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2570 | TOR Enhanced Defueling Safety Cases | 2027-03-31 | 2027-03-31 | Modify PRC Paper as Required | 2027-03-31 | 2027-03-31 | 1 | 1 | 1 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.2960 | HYB Enhanced Defueling Safety Cases | 2027-03-31 | 2028-03-09 | ## HYB Reactor Inspections Relaxations: B++ - D Phase Funding - (Cost Summary) ## | 2027-03-31 | 2028-03-09 | 243 | 243 | 243 | 0% | 12 | Not Started
W730LT_UN | W730 | W730.3140 | HYB Enhanced Defueling Safety Cases |  | 2027-03-31 | HYB Reactor Inspections Relaxations: Commence Supporting References or Supporting EC's | 2027-03-31 | 2027-03-31 | 0 | 0 | 0 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.4190 | HYB Enhanced Defueling Safety Cases |  | 2027-03-31 | Gate B++ PRC Paper Approval | 2027-03-31 | 2027-03-31 | 0 | 0 | 0 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.1200 | HYB Enhanced Defueling Safety Cases |  | 2027-03-31 | Gate B++ Approved | 2027-03-31 | 2027-03-31 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2580 | TOR Enhanced Defueling Safety Cases |  | 2027-03-31 | Gate B++ Approved | 2027-03-31 | 2027-03-31 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2590 | TOR Enhanced Defueling Safety Cases |  | 2027-03-31 | Gate B++ PRC Paper Approval | 2027-03-31 | 2027-03-31 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2600 | TOR Enhanced Defueling Safety Cases |  | 2027-03-31 | TOR Reactor Inspections Relaxations: Commence Supporting References or Supporting EC's | 2027-03-31 | 2027-03-31 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2620 | TOR Enhanced Defueling Safety Cases | 2027-03-31 | 2028-03-09 | ## TOR Reactor Inspections Relaxations: B++ - D Phase Funding - (Cost Summary) ## | 2027-03-31 | 2028-03-09 | 243 | 243 | 243 | 0% | 12 | Not Started
W730LT_UN | W730 | W730.3310 | HYB Enhanced Defueling Safety Cases | 2027-04-01 | 2027-05-27 | HYB Reactor Inspections Relaxations: Produce Supporting References Author / Verify / Approve | 2027-04-01 | 2027-05-27 | 40 | 40 | 40 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2610 | TOR Enhanced Defueling Safety Cases | 2027-04-01 | 2027-05-27 | TOR Reactor Inspections Relaxations: Produce Supporting References Author / Verify / Approve | 2027-04-01 | 2027-05-27 | 40 | 40 | 40 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3420 | HYB Enhanced Defueling Safety Cases |  | 2027-04-05 | HYB Low Decay Heat: INSA Final Approval EC NNNNNN | 2027-04-05 | 2027-04-05 | 0 | 0 | 0 | 0% | 218 | Not Started
W731LT_UN | W731 | W731.2630 | TOR Enhanced Defueling Safety Cases |  | 2027-04-05 | TOR Low Decay Heat: INSA Final Approval EC NNNNNN | 2027-04-05 | 2027-04-05 | 0 | 0 | 0 | 0% | 218 | Not Started
W730LT_UN | W730 | W730.2850 | HYB Enhanced Defueling Safety Cases | 2027-04-06 | 2027-04-06 | HYB Low Decay Heat: Send CAT 2 Paper to ONR to Determine Level of Review Required (Acknowledge or Agree | 2027-04-06 | 2027-04-06 | 1 | 1 | 1 | 0% | 218 | Not Started
W730LT_UN | W730 | W730.2910 | HYB Enhanced Defueling Safety Cases | 2027-04-06 | 2027-04-08 | HYB Low Decay Heat: Lessons Learned Activitiy - Following INSA Review of the SC | 2027-04-06 | 2027-04-08 | 3 | 3 | 3 | 0% | 249 | Not Started
W731LT_UN | W731 | W731.2640 | TOR Enhanced Defueling Safety Cases | 2027-04-06 | 2027-04-08 | TOR Low Decay Heat: Lessons Learned Activitiy - Following INSA Review of the SC | 2027-04-06 | 2027-04-08 | 3 | 3 | 3 | 0% | 249 | Not Started
W731LT_UN | W731 | W731.2650 | TOR Enhanced Defueling Safety Cases | 2027-04-06 | 2027-04-06 | TOR Low Decay Heat: Send CAT 2 Paper to ONR to Determine Level of Review Required (Acknowledge or Agree | 2027-04-06 | 2027-04-06 | 1 | 1 | 1 | 0% | 218 | Not Started
W730LT_UN | W730 | W730.3410 | HYB Enhanced Defueling Safety Cases |  | 2027-04-06 | HYB Low Decay Heat: ONR Agree/Acknowledge Safety Case | 2027-04-06 | 2027-04-06 | 0 | 0 | 0 | 0% | 218 | Not Started
W731LT_UN | W731 | W731.2660 | TOR Enhanced Defueling Safety Cases |  | 2027-04-06 | TOR Low Decay Heat: ONR Agree/Acknowledge Safety Case | 2027-04-06 | 2027-04-06 | 0 | 0 | 0 | 0% | 218 | Not Started
W730LT_UN | W730 | W730.2870 | HYB Enhanced Defueling Safety Cases | 2027-04-07 | 2027-04-20 | HYB Low Decay Heat: Station Approval | 2027-04-07 | 2027-04-20 | 10 | 10 | 10 | 0% | 218 | Not Started
W731LT_UN | W731 | W731.2670 | TOR Enhanced Defueling Safety Cases | 2027-04-07 | 2027-04-20 | TOR Low Decay Heat: Station Approval | 2027-04-07 | 2027-04-20 | 10 | 10 | 10 | 0% | 218 | Not Started
W730LT_UN | W730 | W730.3630 | HYB Enhanced Defueling Safety Cases |  | 2027-04-08 | HYB Low Decay Heat: Lessons Learned Milestone - INSA Review of the Safety Case | 2027-04-08 | 2027-04-08 | 0 | 0 | 0 | 0% | 249 | Not Started
W731LT_UN | W731 | W731.2680 | TOR Enhanced Defueling Safety Cases |  | 2027-04-08 | TOR Low Decay Heat: Lessons Learned Milestone - INSA Review of the Safety Case | 2027-04-08 | 2027-04-08 | 0 | 0 | 0 | 0% | 249 | Not Started
W730LT_UN | W730 | W730.2530 | HYB Enhanced Defueling Safety Cases |  | 2027-04-20 | HYB Low Decay Heat: Station Approved Safety Case | 2027-04-20 | 2027-04-20 | 0 | 0 | 0 | 0% | 218 | Not Started
W730LT_UN | W730 | W730.3440 | HYB Enhanced Defueling Safety Cases |  | 2027-04-20 | HYB Low Decay Heat: Safety Case Approved - (Station Approval) - EC NNNNNN | 2027-04-20 | 2027-04-20 | 0 | 0 | 0 | 0% | 218 | Not Started
W731LT_UN | W731 | W731.2690 | TOR Enhanced Defueling Safety Cases |  | 2027-04-20 | TOR Low Decay Heat: Safety Case Approved - (Station Approval) - EC NNNNNN | 2027-04-20 | 2027-04-20 | 0 | 0 | 0 | 0% | 218 | Not Started
W731LT_UN | W731 | W731.2700 | TOR Enhanced Defueling Safety Cases |  | 2027-04-20 | TOR Low Decay Heat: Station Approved Safety Case | 2027-04-20 | 2027-04-20 | 0 | 0 | 0 | 0% | 218 | Not Started
W730LT_UN | W730 | W730.2830 | HYB Enhanced Defueling Safety Cases | 2027-04-21 | 2027-05-05 | HYB Low Decay Heat: Develop Implementation & Closeout | 2027-04-21 | 2027-05-05 | 10 | 10 | 10 | 0% | 218 | Not Started
W731LT_UN | W731 | W731.2710 | TOR Enhanced Defueling Safety Cases | 2027-04-21 | 2027-05-05 | TOR Low Decay Heat: Develop Implementation & Closeout | 2027-04-21 | 2027-05-05 | 10 | 10 | 10 | 0% | 218 | Not Started
W730LT_UN | W730 | W730.2840 | HYB Enhanced Defueling Safety Cases | 2027-05-06 | 2027-05-06 | HYB Low Decay Heat: Post Job Debrief | 2027-05-06 | 2027-05-06 | 1 | 1 | 1 | 0% | 218 | Not Started
W731LT_UN | W731 | W731.2720 | TOR Enhanced Defueling Safety Cases | 2027-05-06 | 2027-05-06 | TOR Low Decay Heat: Post Job Debrief | 2027-05-06 | 2027-05-06 | 1 | 1 | 1 | 0% | 218 | Not Started
W730LT_UN | W730 | W730.3150 | HYB Enhanced Defueling Safety Cases |  | 2027-05-27 | HYB Reactor Inspections Relaxations: All Supporting References Approved and Issued | 2027-05-27 | 2027-05-27 | 0 | 0 | 0 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3470 | HYB Enhanced Defueling Safety Cases |  | 2027-05-27 | HYB Reactor Inspections Relaxations: All Key Supporting Technical References Completed | 2027-05-27 | 2027-05-27 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2730 | TOR Enhanced Defueling Safety Cases |  | 2027-05-27 | TOR Reactor Inspections Relaxations: All Key Supporting Technical References Completed | 2027-05-27 | 2027-05-27 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2740 | TOR Enhanced Defueling Safety Cases |  | 2027-05-27 | TOR Reactor Inspections Relaxations: All Supporting References Approved and Issued | 2027-05-27 | 2027-05-27 | 0 | 0 | 0 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3160 | HYB Enhanced Defueling Safety Cases | 2027-05-28 | 2027-06-04 | HYB Reactor Inspections Relaxations: Produce verification plan | 2027-05-28 | 2027-06-04 | 5 | 5 | 5 | 0% | 61 | Not Started
W730LT_UN | W730 | W730.3170 | HYB Enhanced Defueling Safety Cases | 2027-05-28 | 2027-07-23 | HYB Reactor Inspections Relaxations: Prepare / Author the Safety Case Proposal | 2027-05-28 | 2027-07-23 | 40 | 40 | 40 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3370 | HYB Enhanced Defueling Safety Cases | 2027-05-28 | 2027-06-02 | HYB Reactor Inspections Relaxations: Lessons Learned Activitiy - Following Completeion of Technical References | 2027-05-28 | 2027-06-02 | 3 | 3 | 3 | 0% | 212 | Not Started
W731LT_UN | W731 | W731.2750 | TOR Enhanced Defueling Safety Cases | 2027-05-28 | 2027-06-02 | TOR Reactor Inspections Relaxations: Lessons Learned Activitiy - Following Completeion of Technical References | 2027-05-28 | 2027-06-02 | 3 | 3 | 3 | 0% | 212 | Not Started
W731LT_UN | W731 | W731.2760 | TOR Enhanced Defueling Safety Cases | 2027-05-28 | 2027-07-23 | TOR Reactor Inspections Relaxations: Prepare / Author the Safety Case Proposal | 2027-05-28 | 2027-07-23 | 40 | 40 | 40 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2770 | TOR Enhanced Defueling Safety Cases | 2027-05-28 | 2027-06-04 | TOR Reactor Inspections Relaxations: Produce verification plan | 2027-05-28 | 2027-06-04 | 5 | 5 | 5 | 0% | 61 | Not Started
W730LT_UN | W730 | W730.3650 | HYB Enhanced Defueling Safety Cases |  | 2027-06-02 | HYB Reactor Inspections Relaxations: Lessons Learned Milestone - Technical References | 2027-06-02 | 2027-06-02 | 0 | 0 | 0 | 0% | 212 | Not Started
W731LT_UN | W731 | W731.2780 | TOR Enhanced Defueling Safety Cases |  | 2027-06-02 | TOR Reactor Inspections Relaxations: Lessons Learned Milestone - Technical References | 2027-06-02 | 2027-06-02 | 0 | 0 | 0 | 0% | 212 | Not Started
W730LT_UN | W730 | W730.1160 | HYB Enhanced Defueling Safety Cases |  | 2027-07-23 | >>>OUTGOING ENABLER (W295) Safety Cases Authored | 2027-06-02 | 2027-07-23 | 0 | 0 | 0 | 0% | 175 | Not Started
W730LT_UN | W730 | W730.3480 | HYB Enhanced Defueling Safety Cases |  | 2027-07-23 | HYB Reactor Inspections Relaxations: Safety Case Paper Authoring Complete EC NNNNNN | 2027-06-02 | 2027-07-23 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2790 | TOR Enhanced Defueling Safety Cases |  | 2027-07-23 | TOR Reactor Inspections Relaxations: Safety Case Paper Authoring Complete EC NNNNNN | 2027-06-02 | 2027-07-23 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2800 | TOR Enhanced Defueling Safety Cases |  | 2027-07-23 | >>>OUTGOING ENABLER (W295) Safety Cases Authored | 2027-06-02 | 2027-07-23 | 0 | 0 | 0 | 0% | 175 | Not Started
W730LT_UN | W730 | W730.2940 | HYB Enhanced Defueling Safety Cases | 2027-07-26 | 2027-07-28 | HYB Reactor Inspections Relaxations: Requirements Capture | 2027-07-26 | 2027-07-28 | 3 | 3 | 3 | 0% | 3 | Not Started
W730LT_UN | W730 | W730.3190 | HYB Enhanced Defueling Safety Cases | 2027-07-26 | 2027-08-02 | HYB Reactor Inspections Relaxations: Final Authoring Consolidation Check | 2027-07-26 | 2027-08-02 | 6 | 6 | 6 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3340 | HYB Enhanced Defueling Safety Cases | 2027-07-26 | 2027-07-28 | HYB Reactor Inspections Relaxations: Lessons Learned Activitiy - Following Authoring of SC | 2027-07-26 | 2027-07-28 | 3 | 3 | 3 | 0% | 172 | Not Started
W731LT_UN | W731 | W731.2810 | TOR Enhanced Defueling Safety Cases | 2027-07-26 | 2027-07-28 | TOR Reactor Inspections Relaxations: Lessons Learned Activitiy - Following Authoring of SC | 2027-07-26 | 2027-07-28 | 3 | 3 | 3 | 0% | 172 | Not Started
W731LT_UN | W731 | W731.2820 | TOR Enhanced Defueling Safety Cases | 2027-07-26 | 2027-08-02 | TOR Reactor Inspections Relaxations: Final Authoring Consolidation Check | 2027-07-26 | 2027-08-02 | 6 | 6 | 6 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2830 | TOR Enhanced Defueling Safety Cases | 2027-07-26 | 2027-07-28 | TOR Reactor Inspections Relaxations: Requirements Capture | 2027-07-26 | 2027-07-28 | 3 | 3 | 3 | 0% | 3 | Not Started
W730LT_UN | W730 | W730.3660 | HYB Enhanced Defueling Safety Cases |  | 2027-07-28 | HYB Reactor Inspections Relaxations: Lessons Learned Milestone - Authoring of the Safety Case | 2027-07-28 | 2027-07-28 | 0 | 0 | 0 | 0% | 172 | Not Started
W731LT_UN | W731 | W731.2840 | TOR Enhanced Defueling Safety Cases |  | 2027-07-28 | TOR Reactor Inspections Relaxations: Lessons Learned Milestone - Authoring of the Safety Case | 2027-07-28 | 2027-07-28 | 0 | 0 | 0 | 0% | 172 | Not Started
W730LT_UN | W730 | W730.3180 | HYB Enhanced Defueling Safety Cases | 2027-08-03 | 2027-08-31 | HYB Reactor Inspections Relaxations: Obtain CO Review & Detail Checker | 2027-08-03 | 2027-08-31 | 20 | 20 | 20 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2850 | TOR Enhanced Defueling Safety Cases | 2027-08-03 | 2027-08-31 | TOR Reactor Inspections Relaxations: Obtain CO Review & Detail Checker | 2027-08-03 | 2027-08-31 | 20 | 20 | 20 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3200 | HYB Enhanced Defueling Safety Cases |  | 2027-08-31 | HYB Reactor Inspections Relaxations: Verification Commenced (T-11) | 2027-08-31 | 2027-08-31 | 0 | 0 | 0 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3220 | HYB Enhanced Defueling Safety Cases |  | 2027-08-31 | HYB Reactor Inspections Relaxations: Issue to Peer CO & Station for comments | 2027-08-31 | 2027-08-31 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2860 | TOR Enhanced Defueling Safety Cases |  | 2027-08-31 | TOR Reactor Inspections Relaxations: Issue to Peer CO & Station for comments | 2027-08-31 | 2027-08-31 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2870 | TOR Enhanced Defueling Safety Cases |  | 2027-08-31 | TOR Reactor Inspections Relaxations: Verification Commenced (T-11) | 2027-08-31 | 2027-08-31 | 0 | 0 | 0 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3250 | HYB Enhanced Defueling Safety Cases | 2027-09-01 | 2027-10-26 | HYB Reactor Inspections Relaxations: Verification of the case - First Round Comments (using BARRIER MODEL) | 2027-09-01 | 2027-10-26 | 40 | 40 | 40 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2880 | TOR Enhanced Defueling Safety Cases | 2027-09-01 | 2027-10-26 | TOR Reactor Inspections Relaxations: Verification of the case - First Round Comments (using BARRIER MODEL) | 2027-09-01 | 2027-10-26 | 40 | 40 | 40 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3240 | HYB Enhanced Defueling Safety Cases | 2027-10-27 | 2027-11-30 | HYB Reactor Inspections Relaxations: Incorporate all stakeholder comments | 2027-10-27 | 2027-11-30 | 25 | 25 | 25 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2890 | TOR Enhanced Defueling Safety Cases | 2027-10-27 | 2027-11-30 | TOR Reactor Inspections Relaxations: Incorporate all stakeholder comments | 2027-10-27 | 2027-11-30 | 25 | 25 | 25 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3210 | HYB Enhanced Defueling Safety Cases | 2027-12-01 | 2027-12-28 | HYB Reactor Inspections Relaxations: Final Verification | 2027-12-01 | 2027-12-28 | 20 | 20 | 20 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2900 | TOR Enhanced Defueling Safety Cases | 2027-12-01 | 2027-12-28 | TOR Reactor Inspections Relaxations: Final Verification | 2027-12-01 | 2027-12-28 | 20 | 20 | 20 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3230 | HYB Enhanced Defueling Safety Cases |  | 2027-12-28 | HYB Reactor Inspections Relaxations: Submit for approval - Categoriser ratifies; RE/CO endorsement | 2027-12-28 | 2027-12-28 | 0 | 0 | 0 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3530 | HYB Enhanced Defueling Safety Cases |  | 2027-12-28 | HYB Reactor Inspections Relaxations: Verification Complete/ Verified Draft A Issued for INSA EC NNNNNN | 2027-12-28 | 2027-12-28 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2910 | TOR Enhanced Defueling Safety Cases |  | 2027-12-28 | TOR Reactor Inspections Relaxations: Verification Complete/ Verified Draft A Issued for INSA EC NNNNNN | 2027-12-28 | 2027-12-28 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2920 | TOR Enhanced Defueling Safety Cases |  | 2027-12-28 | TOR Reactor Inspections Relaxations: Submit for approval - Categoriser ratifies; RE/CO endorsement | 2027-12-28 | 2027-12-28 | 0 | 0 | 0 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3270 | HYB Enhanced Defueling Safety Cases | 2027-12-29 | 2028-01-25 | HYB Reactor Inspections Relaxations: INSA review & iteration of comments (using BARRIER MODEL) | 2027-12-29 | 2028-01-25 | 20 | 20 | 20 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3350 | HYB Enhanced Defueling Safety Cases | 2027-12-29 | 2027-12-31 | HYB Reactor Inspections Relaxations: Lessons Learned Activitiy - Following Verification of the SC | 2027-12-29 | 2027-12-31 | 3 | 3 | 3 | 0% | 61 | Not Started
W731LT_UN | W731 | W731.2930 | TOR Enhanced Defueling Safety Cases | 2027-12-29 | 2027-12-31 | TOR Reactor Inspections Relaxations: Lessons Learned Activitiy - Following Verification of the SC | 2027-12-29 | 2027-12-31 | 3 | 3 | 3 | 0% | 61 | Not Started
W731LT_UN | W731 | W731.2940 | TOR Enhanced Defueling Safety Cases | 2027-12-29 | 2028-01-25 | TOR Reactor Inspections Relaxations: INSA review & iteration of comments (using BARRIER MODEL) | 2027-12-29 | 2028-01-25 | 20 | 20 | 20 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3670 | HYB Enhanced Defueling Safety Cases |  | 2027-12-31 | HYB Reactor Inspections Relaxations: Lessons Learned Milestone - Verification of the Safety Case | 2027-12-31 | 2027-12-31 | 0 | 0 | 0 | 0% | 61 | Not Started
W731LT_UN | W731 | W731.2950 | TOR Enhanced Defueling Safety Cases |  | 2027-12-31 | TOR Reactor Inspections Relaxations: Lessons Learned Milestone - Verification of the Safety Case | 2027-12-31 | 2027-12-31 | 0 | 0 | 0 | 0% | 61 | Not Started
W730LT_UN | W730 | W730.3260 | HYB Enhanced Defueling Safety Cases | 2028-01-26 | 2028-02-08 | HYB Reactor Inspections Relaxations: Incorporate INSA comments | 2028-01-26 | 2028-02-08 | 10 | 10 | 10 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2960 | TOR Enhanced Defueling Safety Cases | 2028-01-26 | 2028-02-08 | TOR Reactor Inspections Relaxations: Incorporate INSA comments | 2028-01-26 | 2028-02-08 | 10 | 10 | 10 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3500 | HYB Enhanced Defueling Safety Cases |  | 2028-02-08 | HYB Reactor Inspections Relaxations: INSA Final Approval EC NNNNNN | 2028-02-08 | 2028-02-08 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.2970 | TOR Enhanced Defueling Safety Cases |  | 2028-02-08 | TOR Reactor Inspections Relaxations: INSA Final Approval EC NNNNNN | 2028-02-08 | 2028-02-08 | 0 | 0 | 0 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3300 | HYB Enhanced Defueling Safety Cases | 2028-02-09 | 2028-02-09 | HYB Reactor Inspections R: Send CAT 2 Paper to ONR to Determine Level of Review Required (Acknowledge or Agreement) | 2028-02-09 | 2028-02-09 | 1 | 1 | 1 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3360 | HYB Enhanced Defueling Safety Cases | 2028-02-09 | 2028-02-11 | HYB Reactor Inspections Relaxations: Lessons Learned Activitiy - Following INSA Review of the SC | 2028-02-09 | 2028-02-11 | 3 | 3 | 3 | 0% | 31 | Not Started
W731LT_UN | W731 | W731.2980 | TOR Enhanced Defueling Safety Cases | 2028-02-09 | 2028-02-11 | TOR Reactor Inspections Relaxations: Lessons Learned Activitiy - Following INSA Review of the SC | 2028-02-09 | 2028-02-11 | 3 | 3 | 3 | 0% | 31 | Not Started
W731LT_UN | W731 | W731.2990 | TOR Enhanced Defueling Safety Cases | 2028-02-09 | 2028-02-09 | TOR Reactor Inspections R: Send CAT 2 Paper to ONR to Determine Level of Review Required (Acknowledge or Agreement) | 2028-02-09 | 2028-02-09 | 1 | 1 | 1 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3490 | HYB Enhanced Defueling Safety Cases |  | 2028-02-09 | HYB Reactor Inspections Relaxations: ONR Agree/Acknowledge Safety Case | 2028-02-09 | 2028-02-09 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.3000 | TOR Enhanced Defueling Safety Cases |  | 2028-02-09 | TOR Reactor Inspections Relaxations: ONR Agree/Acknowledge Safety Case | 2028-02-09 | 2028-02-09 | 0 | 0 | 0 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3320 | HYB Enhanced Defueling Safety Cases | 2028-02-10 | 2028-02-23 | HYB Reactor Inspections Relaxations: Station Approval | 2028-02-10 | 2028-02-23 | 10 | 10 | 10 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.3010 | TOR Enhanced Defueling Safety Cases | 2028-02-10 | 2028-02-23 | TOR Reactor Inspections Relaxations: Station Approval | 2028-02-10 | 2028-02-23 | 10 | 10 | 10 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3680 | HYB Enhanced Defueling Safety Cases |  | 2028-02-11 | HYB Reactor Inspections Relaxations: Lessons Learned Milestone - INSA Review of the Safety Case | 2028-02-11 | 2028-02-11 | 0 | 0 | 0 | 0% | 31 | Not Started
W731LT_UN | W731 | W731.3020 | TOR Enhanced Defueling Safety Cases |  | 2028-02-11 | TOR Reactor Inspections Relaxations: Lessons Learned Milestone - INSA Review of the Safety Case | 2028-02-11 | 2028-02-11 | 0 | 0 | 0 | 0% | 31 | Not Started
W730LT_UN | W730 | W730.1170 | HYB Enhanced Defueling Safety Cases |  | 2028-02-23 | >>>OUTGOING ENABLER (W157 - HYB Security Plan) - EC / Station Approved | 2028-02-23 | 2028-02-23 | 0 | 0 | 0 | 0% | 23 | Not Started
W730LT_UN | W730 | W730.2980 | HYB Enhanced Defueling Safety Cases |  | 2028-02-23 | HYB Reactor Inspections Relaxations: Station Approved Safety Case | 2028-02-23 | 2028-02-23 | 0 | 0 | 0 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3520 | HYB Enhanced Defueling Safety Cases |  | 2028-02-23 | HYB Reactor Inspections Relaxations: Safety Case Approved - (Station Approval) - EC NNNNNN | 2028-02-23 | 2028-02-23 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.3030 | TOR Enhanced Defueling Safety Cases |  | 2028-02-23 | TOR Reactor Inspections Relaxations: Safety Case Approved - (Station Approval) - EC NNNNNN | 2028-02-23 | 2028-02-23 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.3040 | TOR Enhanced Defueling Safety Cases |  | 2028-02-23 | TOR Reactor Inspections Relaxations: Station Approved Safety Case | 2028-02-23 | 2028-02-23 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.3050 | TOR Enhanced Defueling Safety Cases |  | 2028-02-23 | >>>OUTGOING ENABLER (W157 - TOR Security Plan) - EC / Station Approved | 2028-02-23 | 2028-02-23 | 0 | 0 | 0 | 0% | 23 | Not Started
W730LT_UN | W730 | W730.3280 | HYB Enhanced Defueling Safety Cases | 2028-02-24 | 2028-03-08 | HYB Reactor Inspections Relaxations: Develop Implementation & Closeout | 2028-02-24 | 2028-03-08 | 10 | 10 | 10 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.3060 | TOR Enhanced Defueling Safety Cases | 2028-02-24 | 2028-03-08 | TOR Reactor Inspections Relaxations: Develop Implementation & Closeout | 2028-02-24 | 2028-03-08 | 10 | 10 | 10 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3290 | HYB Enhanced Defueling Safety Cases | 2028-03-09 | 2028-03-09 | HYB Reactor Inspections Relaxations: Post Job Debrief | 2028-03-09 | 2028-03-09 | 1 | 1 | 1 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.3070 | TOR Enhanced Defueling Safety Cases | 2028-03-09 | 2028-03-09 | TOR Reactor Inspections Relaxations: Post Job Debrief | 2028-03-09 | 2028-03-09 | 1 | 1 | 1 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.1780 | HYB Enhanced Defueling Safety Cases | 2028-03-10 | 2028-03-27 | ## Gate D Submission - (Cost Summary) ## | 2028-03-10 | 2028-03-27 | 12 | 12 | 12 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.1830 | HYB Enhanced Defueling Safety Cases | 2028-03-10 | 2028-03-10 | Hold Project Closeout and Lessons Learned Meeting | 2028-03-10 | 2028-03-10 | 1 | 1 | 1 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.3080 | TOR Enhanced Defueling Safety Cases | 2028-03-10 | 2028-03-10 | Hold Project Closeout and Lessons Learned Meeting | 2028-03-10 | 2028-03-10 | 1 | 1 | 1 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.3090 | TOR Enhanced Defueling Safety Cases | 2028-03-10 | 2028-03-27 | ## Gate D Submission - (Cost Summary) ## | 2028-03-10 | 2028-03-27 | 12 | 12 | 12 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.1820 | HYB Enhanced Defueling Safety Cases | 2028-03-13 | 2028-03-13 | Produce Lessons Learned Report | 2028-03-13 | 2028-03-13 | 1 | 1 | 1 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.3100 | TOR Enhanced Defueling Safety Cases | 2028-03-13 | 2028-03-13 | Produce Lessons Learned Report | 2028-03-13 | 2028-03-13 | 1 | 1 | 1 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.3690 | HYB Enhanced Defueling Safety Cases |  | 2028-03-13 | All CAT 2 Safety Cases: Lessons Learned Milestone - Gate D Lessons Learned Report Produced | 2028-03-13 | 2028-03-13 | 0 | 0 | 0 | 0% | 10 | Not Started
W731LT_UN | W731 | W731.3110 | TOR Enhanced Defueling Safety Cases |  | 2028-03-13 | All CAT 2 Safety Cases: Lessons Learned Milestone - Gate D Lessons Learned Report Produced | 2028-03-13 | 2028-03-13 | 0 | 0 | 0 | 0% | 10 | Not Started
W730LT_UN | W730 | W730.1810 | HYB Enhanced Defueling Safety Cases | 2028-03-14 | 2028-03-15 | Produce Project Closeout Report | 2028-03-14 | 2028-03-15 | 2 | 2 | 2 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.3120 | TOR Enhanced Defueling Safety Cases | 2028-03-14 | 2028-03-15 | Produce Project Closeout Report | 2028-03-14 | 2028-03-15 | 2 | 2 | 2 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.1790 | HYB Enhanced Defueling Safety Cases | 2028-03-16 | 2028-03-23 | Prepare Gate D PRC Paper | 2028-03-16 | 2028-03-23 | 6 | 6 | 6 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.3130 | TOR Enhanced Defueling Safety Cases | 2028-03-16 | 2028-03-23 | Prepare Gate D PRC Paper | 2028-03-16 | 2028-03-23 | 6 | 6 | 6 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.1800 | HYB Enhanced Defueling Safety Cases | 2028-03-24 | 2028-03-24 | Gate D PRC Paper Submission | 2028-03-24 | 2028-03-24 | 1 | 1 | 1 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.3140 | TOR Enhanced Defueling Safety Cases | 2028-03-24 | 2028-03-24 | Gate D PRC Paper Submission | 2028-03-24 | 2028-03-24 | 1 | 1 | 1 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.1840 | HYB Enhanced Defueling Safety Cases | 2028-03-27 | 2028-03-27 | Gate D - Hold PRC Meeting | 2028-03-27 | 2028-03-27 | 1 | 1 | 1 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.3150 | TOR Enhanced Defueling Safety Cases | 2028-03-27 | 2028-03-27 | Gate D - Hold PRC Meeting | 2028-03-27 | 2028-03-27 | 1 | 1 | 1 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.1110 | HYB Enhanced Defueling Safety Cases |  | 2028-03-27 | Gate D Approved | 2028-03-27 | 2028-03-27 | 0 | 0 | 0 | 0% | 0 | Not Started
W730LT_UN | W730 | W730.1020 | HYB Enhanced Defueling Safety Cases |  | 2028-03-27 | Project Finish | 2028-03-27 | 2028-03-27 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.3160 | TOR Enhanced Defueling Safety Cases |  | 2028-03-27 | Project Finish | 2028-03-27 | 2028-03-27 | 0 | 0 | 0 | 0% | 0 | Not Started
W731LT_UN | W731 | W731.3170 | TOR Enhanced Defueling Safety Cases |  | 2028-03-27 | Gate D Approved | 2028-03-27 | 2028-03-27 | 0 | 0 | 0 | 0% | 0 | Not Started

## Template
Activity ID | Activity Name | Start | Finish | Original Duration | Total Float
A1700 | ONR Approval of Safety Case (Letter sent to initiate) EC NNNNN <Enter Paper Title Here> ==> KDM | 2023-06-22 | 2023-12-07 | 120 | 0
A1430 | Prepare the Safety Case Proposal | 2022-10-24 | 2023-02-15 | 80 | 0
A1340 | Produce supporting reference <Insert Title> | 2022-07-28 | 2022-09-22 | 40 | 0
A1400 | Scope Work or Produce RFS | 2022-06-30 | 2022-07-27 | 20 | 0
A1570 | Specialist Assessments if Necessary (Expand as Required) | 2023-02-23 | 2023-03-22 | 20 | 6
A1350 | Verify supporting reference or EDF Technical review of supporting reference <Insert Title> | 2022-09-23 | 2022-10-13 | 15 | 0
A1620 | INSA review & iteration of comments (using BARRIER MODEL) | 2023-03-31 | 2023-04-24 | 15 | 0
A1060 | CO and PCE Create Initial Plan of Work ==> KDM | 2022-02-09 | 2022-02-22 | 10 | 17
A1730 | Develop Implementation & closeout Plan | 2023-12-27 | 2024-01-10 | 10 | 20
A1590 | Prepare and Populate Affected Documents List | 2022-10-21 | 2022-11-03 | 10 | 298
A1720 | Revise all Affected Drawings and Documents for EC Approval | 2023-12-11 | 2023-12-22 | 10 | 20
A1530 | Final Verification ==> KDM | 2023-03-17 | 2023-03-30 | 10 | 0
A1110 | SRD comments on NSRS | 2022-04-06 | 2022-04-21 | 10 | 17
A1150 | DA & SRD agree NSRS (for authorised designers-NSRS must be reviewed by DA) ==> KDM | 2022-05-11 | 2022-05-24 | 10 | 17
A1120 | Incorporate SRD, Station, DA (peer) comments | 2022-04-22 | 2022-05-06 | 10 | 17
A10100 | Initiate and Register EC and identify Milestones in AMS EC NNNNN<Enter Paper Title Here> | 2022-01-11 | 2022-01-24 | 10 | 17
A1460 | Verification of the case (using BARRIER MODEL) | 2023-02-23 | 2023-03-08 | 10 | 0
A1240 | Create EC Definition Document if not part of Project Definition Document (Insert Template Ref) | 2022-03-09 | 2022-03-22 | 10 | 17
A1140 | Station agree NSRS ==> KDM | 2022-05-11 | 2022-05-24 | 10 | 17
A1100 | DA (Peer) comments on NSRS | 2022-03-09 | 2022-03-22 | 10 | 37
A1090 | Station comments on NSRS | 2022-03-09 | 2022-03-22 | 10 | 37
A1080 | Produce draft NSRS (using BARRIER MODEL) | 2022-02-23 | 2022-03-08 | 10 | 17
A1010 | Produce MF EC NNNNN <Enter Paper Title Here> & obtain approval | 2022-01-25 | 2022-02-07 | 10 | 17
A1230 | Hold Case Conference as Appropriate | 2022-02-23 | 2022-03-01 | 5 | 490
A1380 | Address TR or Verifiers Comments <Insert Title> | 2022-10-14 | 2022-10-20 | 5 | 0
A1520 | Prepare Station Director's Brief | 2023-03-31 | 2023-04-06 | 5 | 45
A1280 | Circulate work programme to stakeholders for agreement | 2022-07-04 | 2022-07-08 | 5 | 401
A1260 | Identify verifier for the case & establish all other resources | 2022-02-10 | 2022-02-16 | 5 | 41
A1630 | Incorporate INSA comments | 2023-04-25 | 2023-05-02 | 5 | 0
A1660 | NSC Consideration & advice to Station Director ==> KDM | 2023-06-01 | 2023-06-07 | 5 | 10
A1610 | DA (Authorised Designer) Approval of CAT1 Safety Case | 2023-03-31 | 2023-04-06 | 5 | 15
A1000 | Mod Requested, Identify RE and EC Request Raised and Screened | 2022-01-04 | 2022-01-10 | 5 | 17
A1440 | Obtain peer review (if required) ==> KDM | 2023-02-16 | 2023-02-22 | 5 | 0
A1180 | Circulate NSRS for Relevant Stakeholders | 2022-06-23 | 2022-06-29 | 5 | 0
A1270 | Agree INSA resource with INA | 2022-03-30 | 2022-04-05 | 5 | 17
A1330 | Agree design proposals with Station in the case of hardware mods | 2022-03-30 | 2022-04-05 | 5 | 465
A1250 | Hold project kick start meeting with Station & key suppliers | 2022-03-23 | 2022-03-29 | 5 | 17
A1490 | Incorporate all stakeholder comments | 2023-03-09 | 2023-03-13 | 3 | 3
A1420 | Produce verification plan | 2022-10-24 | 2022-10-25 | 2 | 326
A1070 | CA to agree with CO format of the safety case | 2022-02-10 | 2022-02-11 | 2 | 173
A1320 | Baseline Plan to Verification Commenced (T-11) ==> KDM | 2022-07-11 | 2022-07-11 | 1 | 401
A1220 | NSRS Presented to NSC (for complex CAT 1 cases) | 2022-06-22 | 2022-06-22 | 1 | 0
A1190 | Send NSRS to ONR to determine level of review required (Acknowledgement or Agreement) | 2022-06-30 | 2022-06-30 | 1 | 79
A1290 | Continue to Develop & resource mandatory template ==> KDM | 2022-07-01 | 2022-07-01 | 1 | 401
A1470 | NSORC review and agree NSC CAT 1 Paper - < insert title > (SZB Only) | 2023-03-16 | 2023-03-16 | 1 | 0
A1690 | Post Job Debrief | 2024-02-08 | 2024-02-08 | 1 | 0
A1020 | Initial Categorisation by Station ==> KDM | 2022-02-08 | 2022-02-08 | 1 | 17
KDM.BU.02 | KDM - Station Approve EC NNNNN <Enter Paper Title Here> | 2023-12-08 | 2023-12-08 | 1 | 0
A1030 | Appoint CO & CA | 2022-02-09 | 2022-02-09 | 1 | 41
A1160 | NSORC agree NSRS (SZB) ==> KDM | 2022-05-25 | 2022-05-25 | 1 | 17
A1130 | Issue final NSRS | 2022-05-09 | 2022-05-09 | 1 | 17
A1550 | Verification Commenced (T-11) | 2023-02-23 | 2023-02-23 | 0 | 243
KDM.PR02 | KDM - Safety Case Paper Authoring Complete EC NNNNN <Enter Paper Title Here> (Cat 1 KDM) ==> KDM | 2023-02-22 | 2023-02-22 | 0 | 0
A1560 | Issue to NSORC (SZB) | 2023-03-08 | 2023-03-08 | 0 | 0
A1200 | Issue to NSORC (SZB Only) | 2022-05-06 | 2022-05-06 | 0 | 24
KDM.SP06 | KDM - ONR Agree/Acknowledge Safety Case EC NNNNN <Enter Paper Title Here> ==> KDM | 2023-12-07 | 2023-12-07 | 0 | 0
KDM.SP05 | KDM - INSA Final Approval EC NNNNN <Enter Paper Title Here> | 2023-06-21 | 2023-06-21 | 0 | 0
KDM.PR01 | KDM - Gate EC3 Completed and NSC/ONR dates Committed | 2023-02-22 | 2023-02-22 | 0 | 243
A1390 | Commence Supporting References or Supporting EC's | 2022-06-29 | 2022-06-29 | 0 | 0
KDM.SP03 | KDM - Gate EC2 completed and Cat 1 Baselined EC NNNNN <Enter Paper Title Here> | 2022-07-04 | 2022-07-04 | 0 | 406
KDM.SP01 | KDM - Gate EC1 completed EC NNNNN <Enter Paper Title Here> | 2022-02-22 | 2022-02-22 | 0 | 17
A1410 | All supporting references Approved and Issued | 2022-10-20 | 2022-10-20 | 0 | 0
A1370 | Supporting reference Complete <Insert Title> Approved and issued | 2022-10-20 | 2022-10-20 | 0 | 0
KDM.SP02 | KDM - NSRS agreed by stakeholders EC NNNNN <Enter Paper Title Here> | 2022-05-25 | 2022-05-25 | 0 | 17
A1640 | INSA Assessment Substantially Comp (T - 3 weeks before NSC date) ==> KDM | 2023-05-02 | 2023-05-02 | 0 | 0
A1480 | Issue to CO & Station for comments | 2023-03-08 | 2023-03-08 | 0 | 3
A1510 | Submit for approval - Categoriser ratifies; RE/CO endorsement ==> KDM | 2023-03-30 | 2023-03-30 | 0 | 0
KDM.BU01 | KDM - Safetc Case Presented at NSC EC NNNNN <Enter Paper Title Here> (Cat 1 KDM) (T) ==> KDM | 2023-05-23 | 2023-05-23 | 0 | 0
KDM.PR03 | KDM - Verification Complete/ Verified Draft A Issued for INSA (T-7) EC NNNNN <Enter Paper Title Here> ==> KDM | 2023-03-30 | 2023-03-30 | 0 | 0

## ALR2 2024 Year Table
Workpack | Project Name | Year of Month | Change in Submission Aug to Latest | Change in Submission June To Aug | Change in Submission Overall | Actuals & Gate 2 Submission Cost | Actuals & June Submission Cost | Actuals & Submission Cost
W200 | Prog 6.1-Reg.1 Reactors Shutdown SC | 2020 | £0K | £0K | £0K | -£4K | -£4K | -£4K
W200 | Prog 6.1-Reg.1 Reactors Shutdown SC | 2019 | £0K | £0K | £0K | £161K | £161K | £161K
W200 | Prog 6.1-Reg.1 Reactors Shutdown SC | 2018 | £0K | £0K | £0K | £1,371K | £1,371K | £1,371K
W200 | Prog 6.1-Reg.1 Reactors Shutdown SC | 2017 | £0K | £0K | £0K | £488K | £488K | £488K
W201 | HNB Reactors Shutdown Essential SC | 2022 | £0K | £0K | £0K | £27K | £27K | £27K
W201 | HNB Reactors Shutdown Essential SC | 2021 | £0K | £0K | £0K | £269K | £269K | £269K
W201 | HNB Reactors Shutdown Essential SC | 2020 | £0K | £0K | £0K | £1,309K | £1,309K | £1,309K
W201 | HNB Reactors Shutdown Essential SC | 2019 | £0K | £0K | £0K | £2,732K | £2,732K | £2,732K
W201 | HNB Reactors Shutdown Essential SC | 2018 | £0K | £0K | £0K | £42K | £42K | £42K
W202 | HRA Reactors Shutdown Essential Safety Cases | 2025 | £0K | £0K | £0K | £38K | £38K | £38K
W202 | HRA Reactors Shutdown Essential Safety Cases | 2024 | £0K | £0K | £0K | £103K | £103K | £103K
W202 | HRA Reactors Shutdown Essential Safety Cases | 2023 | £0K | £0K | £0K | £186K | £186K | £186K
W202 | HRA Reactors Shutdown Essential Safety Cases | 2022 | £0K | £0K | £0K | £354K | £354K | £354K
W202 | HRA Reactors Shutdown Essential Safety Cases | 2021 | £0K | £0K | £0K | £587K | £587K | £587K
W202 | HRA Reactors Shutdown Essential Safety Cases | 2020 | £0K | £0K | £0K | £808K | £808K | £808K
W202 | HRA Reactors Shutdown Essential Safety Cases | 2019 | £0K | £0K | £0K | £29K | £29K | £29K
W203 | HNB Enhanced Defuelling Safety Cases | 2025 | £0K | £0K | £0K | £30K | £30K | £30K
W203 | HNB Enhanced Defuelling Safety Cases | 2024 | £0K | £0K | £0K | £115K | £115K | £115K
W203 | HNB Enhanced Defuelling Safety Cases | 2023 | £0K | £0K | £0K | £142K | £142K | £142K
W203 | HNB Enhanced Defuelling Safety Cases | 2022 | £0K | £0K | £0K | £0K | £0K | £0K
W203 | HNB Enhanced Defuelling Safety Cases | 2021 | £0K | £0K | £0K | £22K | £22K | £22K
W203 | HNB Enhanced Defuelling Safety Cases | 2020 | £0K | £0K | £0K | £30K | £30K | £30K
W204 | HRA Reactors Shutdown Enhanced SC | 2020 | £0K | £0K | £0K | £0K | £0K | £0K
W205 | HPB Reactor Shutdown Essential SC | 2022 | £0K | £0K | £0K | £33K | £33K | £33K
W205 | HPB Reactor Shutdown Essential SC | 2021 | £0K | £0K | £0K | £275K | £275K | £275K
W205 | HPB Reactor Shutdown Essential SC | 2020 | £0K | £0K | £0K | £427K | £427K | £427K
W206 | HYA Reactors Shutdown Essential Safety Cases | 2025 | £0K | £0K | £0K | £38K | £38K | £38K
W206 | HYA Reactors Shutdown Essential Safety Cases | 2024 | £0K | £0K | £0K | £107K | £107K | £107K
W206 | HYA Reactors Shutdown Essential Safety Cases | 2023 | £0K | £0K | £0K | £173K | £173K | £173K
W206 | HYA Reactors Shutdown Essential Safety Cases | 2022 | £0K | £0K | £0K | £361K | £361K | £361K
W206 | HYA Reactors Shutdown Essential Safety Cases | 2021 | £0K | £0K | £0K | £586K | £586K | £586K
W206 | HYA Reactors Shutdown Essential Safety Cases | 2020 | £0K | £0K | £0K | £422K | £422K | £422K
W207 | HPB Enhanced Defuelling Safety Cases | 2025 | £0K | £0K | £0K | £30K | £30K | £30K
W207 | HPB Enhanced Defuelling Safety Cases | 2024 | £0K | £0K | £0K | £121K | £121K | £121K
W207 | HPB Enhanced Defuelling Safety Cases | 2023 | £0K | £0K | £0K | £176K | £176K | £176K
W207 | HPB Enhanced Defuelling Safety Cases | 2022 | £0K | £0K | £0K | £0K | £0K | £0K
W207 | HPB Enhanced Defuelling Safety Cases | 2021 | £0K | £0K | £0K | £35K | £35K | £35K
W207 | HPB Enhanced Defuelling Safety Cases | 2020 | £0K | £0K | £0K | £15K | £15K | £15K
W209 | HYB Essential Defueling Safety Case | 2025 | £0K | £0K | £0K | £94K | £94K | £94K
W209 | HYB Essential Defueling Safety Case | 2024 | £0K | £0K | £0K | £505K | £505K | £505K
W209 | HYB Essential Defueling Safety Case | 2023 | £0K | £0K | £0K | £1,087K | £1,087K | £1,087K
W209 | HYB Essential Defueling Safety Case | 2022 | £0K | £0K | £0K | £1,349K | £1,349K | £1,349K
W209 | HYB Essential Defueling Safety Case | 2021 | £0K | £0K | £0K | £100K | £100K | £100K
W211 | DNB Follow-on Defuelling Safety Case | 2025 | £0K | £0K | £0K | £15K | £15K | £15K
W211 | DNB Follow-on Defuelling Safety Case | 2024 | £0K | £0K | £0K | £416K | £416K | £416K
W211 | DNB Follow-on Defuelling Safety Case | 2023 | £0K | £0K | £0K | £805K | £805K | £805K
W211 | DNB Follow-on Defuelling Safety Case | 2022 | £0K | £0K | £0K | £1,016K | £1,016K | £1,016K
W211 | DNB Follow-on Defuelling Safety Case | 2021 | £0K | £0K | £0K | £78K | £78K | £78K
W211 | DNB Follow-on Defuelling Safety Case | 2020 | £0K | £0K | £0K | £136K | £136K | £136K
W213 | TOR Essential Defueling Safety Case | 2025 | £0K | £0K | £0K | £86K | £86K | £86K
W213 | TOR Essential Defueling Safety Case | 2024 | £0K | £0K | £0K | £457K | £457K | £457K
W213 | TOR Essential Defueling Safety Case | 2023 | £0K | £0K | £0K | £1,068K | £1,068K | £1,068K
W213 | TOR Essential Defueling Safety Case | 2022 | £0K | £0K | £0K | £1,332K | £1,332K | £1,332K
W213 | TOR Essential Defueling Safety Case | 2021 | £0K | £0K | £0K | £117K | £117K | £117K
W220 | Prog 6.2-Reg.1 Stn Fuel Route Handl.SC | 2020 | £0K | £0K | £0K | -£6K | -£6K | -£6K
W220 | Prog 6.2-Reg.1 Stn Fuel Route Handl.SC | 2019 | £0K | £0K | £0K | £109K | £109K | £109K
W220 | Prog 6.2-Reg.1 Stn Fuel Route Handl.SC | 2018 | £0K | £0K | £0K | £1,343K | £1,343K | £1,343K
W220 | Prog 6.2-Reg.1 Stn Fuel Route Handl.SC | 2017 | £0K | £0K | £0K | £531K | £531K | £531K
W221 | HNB Fuel Handling Essential Safety Case | 2022 | £0K | £0K | £0K | £66K | £66K | £66K
W221 | HNB Fuel Handling Essential Safety Case | 2021 | £0K | £0K | £0K | £304K | £304K | £304K
W221 | HNB Fuel Handling Essential Safety Case | 2020 | £0K | £0K | £0K | £1,204K | £1,204K | £1,204K
W221 | HNB Fuel Handling Essential Safety Case | 2019 | £0K | £0K | £0K | £2,479K | £2,479K | £2,479K
W221 | HNB Fuel Handling Essential Safety Case | 2018 | £0K | £0K | £0K | £226K | £226K | £226K
W222 | HRA Fuel Handling Essential Safety Case | 2025 | £0K | £0K | £0K | £45K | £45K | £45K
W222 | HRA Fuel Handling Essential Safety Case | 2024 | £0K | £0K | £0K | £299K | £299K | £299K
W222 | HRA Fuel Handling Essential Safety Case | 2023 | £0K | £0K | £0K | £338K | £338K | £338K
W222 | HRA Fuel Handling Essential Safety Case | 2022 | £0K | £0K | £0K | £435K | £435K | £435K
W222 | HRA Fuel Handling Essential Safety Case | 2021 | £0K | £0K | £0K | £963K | £963K | £963K
W222 | HRA Fuel Handling Essential Safety Case | 2020 | £0K | £0K | £0K | £1,291K | £1,291K | £1,291K
W222 | HRA Fuel Handling Essential Safety Case | 2019 | £0K | £0K | £0K | £43K | £43K | £43K
W224 | HRA Enhanced Defueling Safety Case | 2026 | £3K | £5K | £8K | £13K | £7K | £15K
W224 | HRA Enhanced Defueling Safety Case | 2025 | £43K | £117K | £160K | £788K | £671K | £831K
W224 | HRA Enhanced Defueling Safety Case | 2024 | £0K | £66K | £66K | £249K | £182K | £249K
W224 | HRA Enhanced Defueling Safety Case | 2023 | £0K | £0K | £0K | £17K | £17K | £17K
W225 | HPB Fuel Handling Essential SC | 2022 | £0K | £0K | £0K | £74K | £74K | £74K
W225 | HPB Fuel Handling Essential SC | 2021 | £0K | £0K | £0K | £284K | £284K | £284K
W225 | HPB Fuel Handling Essential SC | 2020 | £0K | £0K | £0K | £410K | £410K | £410K
W226 | HYA Fuel Handling Essential Safety Case | 2025 | £0K | £0K | £0K | £45K | £45K | £45K
W226 | HYA Fuel Handling Essential Safety Case | 2024 | £0K | £0K | £0K | £303K | £303K | £303K
W226 | HYA Fuel Handling Essential Safety Case | 2023 | £0K | £0K | £0K | £337K | £337K | £337K
W226 | HYA Fuel Handling Essential Safety Case | 2022 | £0K | £0K | £0K | £492K | £492K | £492K
W226 | HYA Fuel Handling Essential Safety Case | 2021 | £0K | £0K | £0K | £960K | £960K | £960K
W226 | HYA Fuel Handling Essential Safety Case | 2020 | £0K | £0K | £0K | £730K | £730K | £730K
W228 | HYA Enhanced Defueling Safety Case | 2026 | £3K | £5K | £8K | £13K | £7K | £15K
W228 | HYA Enhanced Defueling Safety Case | 2025 | £43K | £117K | £160K | £788K | £671K | £831K
W228 | HYA Enhanced Defueling Safety Case | 2024 | £0K | £68K | £68K | £250K | £182K | £250K
W228 | HYA Enhanced Defueling Safety Case | 2023 | £0K | £0K | £0K | £17K | £17K | £17K
W229 | HYB SC Superseded by W209 | 2022 | £0K | £0K | £0K | £0K | £0K | £0K
W229 | HYB SC Superseded by W209 | 2021 | £0K | £0K | £0K | £0K | £0K | £0K
W230 | HYB Enhanced Defueling Safety Case Strategy | 2025 | £0K | £0K | £0K | £154K | £154K | £154K
W230 | HYB Enhanced Defueling Safety Case Strategy | 2024 | £0K | £0K | £0K | £108K | £108K | £108K
W231 | DNB Fuel Handling Essential SC | 2023 | £0K | £0K | £0K | -£6K | -£6K | -£6K
W231 | DNB Fuel Handling Essential SC | 2022 | £0K | £0K | £0K | £9K | £9K | £9K
W231 | DNB Fuel Handling Essential SC | 2021 | £0K | £0K | £0K | £165K | £165K | £165K
W231 | DNB Fuel Handling Essential SC | 2020 | £0K | £0K | £0K | £29K | £29K | £29K
W232 | DNB Enhanced Safety Cases | 2025 | £0K | £0K | £0K | £403K | £403K | £403K
W232 | DNB Enhanced Safety Cases | 2024 | £0K | £0K | £0K | £473K | £473K | £473K
W232 | DNB Enhanced Safety Cases | 2023 | £0K | £0K | £0K | £613K | £613K | £613K
W232 | DNB Enhanced Safety Cases | 2022 | £0K | £0K | £0K | £57K | £57K | £57K
W233 | TOR Fuel Handling Essential SC | 2022 | £0K | £0K | £0K | -£13K | -£13K | -£13K
W233 | TOR Fuel Handling Essential SC | 2021 | £0K | £0K | £0K | £0K | £0K | £0K
W234 | TOR Enhanced Defueling Safety Case Strategy | 2025 | £0K | £0K | £0K | £154K | £154K | £154K
W234 | TOR Enhanced Defueling Safety Case Strategy | 2024 | £0K | £0K | £0K | £108K | £108K | £108K
W520 | FLEETWIDE CTO Defueling Safety Case Delivery | 2026 | £740K | £0K | £740K | £498K | £498K | £1,239K
W520 | FLEETWIDE CTO Defueling Safety Case Delivery | 2025 | £168K | £0K | £168K | £1,070K | £1,070K | £1,239K
W520 | FLEETWIDE CTO Defueling Safety Case Delivery | 2024 | £0K | £0K | £0K | £885K | £885K | £885K
W520 | FLEETWIDE CTO Defueling Safety Case Delivery | 2023 | £0K | £0K | £0K | £976K | £976K | £976K
W520 | FLEETWIDE CTO Defueling Safety Case Delivery | 2022 | £0K | £0K | £0K | £1,128K | £1,128K | £1,128K
W520 | FLEETWIDE CTO Defueling Safety Case Delivery | 2021 | £0K | £0K | £0K | £685K | £685K | £685K
W521 | DNB Initial Defuelling Safety Case | 2023 | £0K | £0K | £0K | £33K | £33K | £33K
W521 | DNB Initial Defuelling Safety Case | 2022 | £0K | £0K | £0K | £1,223K | £1,223K | £1,223K
W521 | DNB Initial Defuelling Safety Case | 2021 | £0K | £0K | £0K | £1,965K | £1,965K | £1,965K
W699 | DNB Cold Defuelling Safety Case | 2025 | £0K | £0K | £0K | £206K | £206K | £206K
W699 | DNB Cold Defuelling Safety Case | 2024 | £0K | £0K | £0K | £423K | £423K | £423K
W730 | HYB Enhanced Defueling Safety Cases | 2027 | £0K | £0K | £0K | £323K | £323K | £323K
W730 | HYB Enhanced Defueling Safety Cases | 2026 | £0K | £0K | £0K | £423K | £423K | £423K
W730 | HYB Enhanced Defueling Safety Cases | 2025 | £0K | £0K | £0K | £398K | £398K | £398K
W731 | TOR Enhanced Defueling Safety Cases | 2027 | £0K | £0K | £0K | £323K | £323K | £323K
W731 | TOR Enhanced Defueling Safety Cases | 2026 | £0K | £0K | £0K | £423K | £423K | £423K
W731 | TOR Enhanced Defueling Safety Cases | 2025 | £0K | £0K | £0K | £398K | £398K | £398K
W772 | DNB Pull Harder Safety Case | 2026 | £206K | £0K | £206K | 0 | 0 | £206K
W772 | DNB Pull Harder Safety Case | 2025 | £423K | £0K | £423K | 0 | 0 | £423K
W783 | DNB Tie Bar Cutting Removal Safety Case | 2025 | £315K | £0K | £315K | 0 | 0 | £315K
W784 | DNB Cold Depressurised Safety Case | 2026 | £206K | £0K | £206K | 0 | 0 | £206K
W784 | DNB Cold Depressurised Safety Case | 2025 | £423K | £0K | £423K | 0 | 0 | £423K