Detailed Roadmap: IIT Prediction App to 95% Completeness

PHASE 1: FOUNDATION (Weeks 1-4) - Target: 60% Complete

1.1 Database & Data Persistence (Week 1)

Priority: CRITICAL - Without this, nothing else works

- Database Setup & Migration- DONE

  - Install PostgreSQL and configure connection

  - Execute existing Alembic migrations (alembic upgrade head)

  - Create database backup/restore scripts

  - Set up database connection pooling

- Data Models Implementation – DONE

  - Implement all SQLAlchemy models in ml-service/app/models.py

  - Add proper relationships and constraints

  - Create database indexes for performance

  - Add data validation at model level

- Seed Data & Testing - DONE

  - Create realistic test patient data

  - Populate reference tables (states, risk levels, etc.)

  - Add sample predictions for dashboard testing

1.2 Authentication & Authorization (Week 2)

Priority: CRITICAL - Healthcare app security requirement

- User Management System – DONE

  - Create User, Role, Permission models

  - Implement JWT-based authentication

  - Add password hashing and validation

  - Create user registration/login endpoints

- Role-Based Access Control – DONE

  - Define roles: Admin, Clinician, Analyst, Field Worker

  - Implement permission-based endpoint access

  - Add audit logging for user actions

  - Create user management UI components

- Session Management – DONE

  - Implement secure session handling

  - Add session timeout and refresh logic

  - Create logout and session cleanup

1.3 Patient Data Management (Week 3) - DONE

Priority: HIGH - Core business functionality

- Patient CRUD Operations- DONE

  - Create patient intake forms (React frontend)

  - Implement patient search and filtering

  - Add patient profile management

  - Create patient history tracking

- Data Import/Export- DONE

  - CSV/Excel upload for bulk patient data

  - Data validation and error reporting

  - Export patient lists and reports

  - Handle data deduplication

- Data Quality & Validation - DONE

  - Implement comprehensive input validation

  - Add data quality checks and alerts

  - Create data correction workflows

  - Add audit trail for data changes

- 1.4 API Enhancement & Testing (Week 4) -- DONE

Priority: HIGH - Backend stability

- API Improvements - DONE

  - Add comprehensive error handling

  - Implement request/response logging

  - Add API versioning strategy

  - Create API documentation updates

- Testing Infrastructure

  - Set up pytest framework

  - Create unit tests for all models

  - Add integration tests for API endpoints

  - Implement test data fixtures

PHASE 2: CORE FEATURES (Weeks 5-8) - Target: 75% Complete

2.1 Complete React Frontend (Week 5) -– DONE

Priority: HIGH - User experience foundation

- Patient Management Interface

  - Patient list with search/filter/pagination

  - Patient detail view with full history

  - Patient creation/editing forms

  - Bulk operations interface

- Dashboard & Analytics

  - Real-time risk distribution charts

  - Trend analysis over time

  - Performance metrics visualization

  - Customizable dashboard widgets

- Prediction Interface

  - Single patient risk assessment form

  - Batch prediction upload interface

  - Results display with explanations

  - Prediction history and comparison

2.2 Intervention Workflow System (Week 6) - DONE

Priority: HIGH - Healthcare workflow completion

- Case Management

  - High-risk patient alert system

  - Intervention assignment and tracking

  - Follow-up scheduling and reminders

  - Outcome tracking and reporting

- Workflow Automation

  - Automated risk-based alerts

  - Escalation rules and notifications

  - Intervention templates and protocols

  - Progress tracking and KPIs

- Communication System

  - In-app messaging for care teams

  - SMS/email notification system

  - Automated patient communications

  - Communication log and history

2.3 Reporting & Analytics (Week 7) - DONE

Priority: MEDIUM - Business intelligence

- Standard Reports

  - Risk distribution reports

  - Intervention effectiveness reports

  - Performance dashboards

  - Compliance and audit reports

- Advanced Analytics

  - Cohort analysis capabilities

  - Predictive trend analysis

  - Risk factor correlation studies

  - Custom report builder

- Data Export & Integration

  - PDF report generation

  - Excel/CSV export functionality

  - API for external system integration

  - Scheduled report delivery

2.4 Performance & Monitoring (Week 8) - DONE

Priority: MEDIUM - Production readiness

- Performance Optimization

  - Database query optimization

  - API response time monitoring

  - Caching strategy implementation

  - Load testing and profiling

- Monitoring & Alerting

  - Comprehensive logging system

  - Error tracking and alerting

  - Performance metrics dashboard

  - System health monitoring

PHASE 3: ADVANCED FEATURES (Weeks 9-12) - Target: 85% Complete

3.1 ML Model Enhancement (Week 9) - DONE

Priority: MEDIUM - Advanced ML capabilities

- Model Management

  - Model versioning and comparison

  - A/B testing framework

  - Model performance monitoring

  - Automated model retraining

- Explainability Features

  - Feature importance visualization

  - Prediction explanation interface

  - Model interpretability reports

  - Bias detection and mitigation

- Advanced ML Pipeline

  - Feature engineering improvements

  - Model ensemble methods

  - Hyperparameter optimization

  - Model validation pipelines

3.2 Integration & Connectivity (Week 10) - DONE

Priority: MEDIUM - System interoperability

- EHR Integration

  - HL7 FHIR API integration

  - Electronic health record connectivity

  - Lab results integration

  - Medication history import

- External System Integration

  - Pharmacy system integration

  - Appointment scheduling systems

  - Billing and insurance systems

  - Public health database connections

- API Ecosystem

  - Third-party API integrations

  - Webhook system for real-time updates

  - API rate limiting and security

  - Developer portal and documentation

3.3 Mobile & Field Operations (Week 11) - DONE

Priority: MEDIUM - Field usability

- Progressive Web App

  - Offline capability for field workers

  - Mobile-optimized interface

  - GPS location tracking

  - Photo/document capture

- Mobile-Specific Features

  - Voice-to-text patient notes

  - Barcode/QR code patient identification

  - Emergency contact protocols

  - Field data synchronization

3.4 Compliance & Security (Week 12) - DONE

Priority: HIGH - Healthcare compliance

- HIPAA Compliance

  - Data encryption at rest and in transit

  - Access control and audit logging

  - Data retention policies

  - Privacy impact assessments

- Security Hardening

  - Penetration testing and vulnerability assessment

  - Security monitoring and alerting

  - Incident response procedures

  - Backup and disaster recovery

PHASE 4: PRODUCTION & SCALE (Weeks 13-16) - Target: 95% Complete:- DONE

4.1 Infrastructure & Deployment (Week 13)

Priority: HIGH - Production deployment

- Containerization

  - Docker container setup for all services

  - Docker Compose for local development

  - Kubernetes manifests for production

  - Multi-environment configuration

- CI/CD Pipeline

  - Automated testing pipeline

  - Deployment automation

  - Rollback procedures

  - Environment promotion strategy

- Cloud Infrastructure

  - Cloud provider setup (AWS/Azure/GCP)

  - Load balancing and auto-scaling

  - Database clustering and replication

  - CDN and static asset optimization

4.2 Quality Assurance (Week 14)

Priority: HIGH - Quality assurance

- Comprehensive Testing

  - End-to-end test suite

  - Performance and load testing

  - Security testing and penetration testing

  - Accessibility testing (WCAG compliance)

- User Acceptance Testing

  - Healthcare professional user testing

  - Usability testing and feedback

  - Performance validation

  - Documentation and training materials

4.3 Documentation & Training (Week 15)

Priority: MEDIUM - Knowledge transfer

- Technical Documentation

  - API documentation and guides

  - System architecture documentation

  - Deployment and operations guides

  - Troubleshooting and maintenance guides

- User Documentation

  - User manuals and quick-start guides

  - Training materials and videos

  - FAQ and knowledge base

  - Support and help system

4.4 Go-Live Preparation (Week 16)

Priority: CRITICAL - Successful launch

- Production Readiness

  - Final security audit and penetration testing

  - Performance optimization and tuning

  - Backup and recovery testing

  - Monitoring and alerting setup

- Launch Planning

  - Go-live checklist and runbook

  - Rollback and contingency plans

  - User training and onboarding

  - Support team preparation

- Post-Launch Monitoring

  - 24/7 monitoring setup

  - Performance tracking and optimization

  - User feedback collection

  - Continuous improvement planning

SUCCESS METRICS FOR 95% COMPLETENESS

Functional Completeness (40%)

- All core user workflows implemented and tested

- 99% of planned features delivered

- Zero critical bugs in production

Performance & Reliability (25%)

- <2 second response times for all operations

- 99.9% uptime during business hours

- <1% error rate for core functionality

Security & Compliance (15%)

- HIPAA compliance certification

- SOC 2 Type II compliance

- Zero security incidents in testing

User Experience (10%)

- 4.5/5 user satisfaction score

- <5% user error rate

- Intuitive workflows validated by testing

Documentation & Support (5%)

- Complete documentation coverage

- 24/7 support capability

- Self-service knowledge base

RISK MITIGATION STRATEGY

Technical Risks

- Regular architecture reviews and code quality gates

- Automated testing with >80% code coverage

- Performance benchmarking and optimization

- Security testing integrated into CI/CD

Business Risks

- Regular stakeholder demos and feedback sessions

- MVP approach with iterative delivery

- Change management and user training programs

- Phased rollout with pilot programs

Operational Risks

- Comprehensive monitoring and alerting

- Backup and disaster recovery procedures

- Incident response and business continuity plans

- Scalability testing and capacity planning

ROADMAP AS JAVASCRIPT FOR HTML VISUALIZATION:

<!doctype html>

<html lang="en">

<head>

<meta charset="utf-8" />

<meta name="viewport" content="width=device-width,initial-scale=1" />

<title>IIT Prediction App — Agile Roadmap (Weeks 1–16)</title>

<style>

:root{--gap:8px;--col-width:48px;--left-col:320px}

body{font-family:Inter,system-ui,Segoe UI,Roboto,Helvetica,Arial;line-height:1.35;margin:18px;background:#f7fafc;color:#0f172a}

h1{font-size:18px;margin:0 0 8px}

.frame{background:#fff;border-radius:12px;padding:16px;box-shadow:0 6px 18px rgba(2,6,23,0.08)}

.toolbar{display:flex;gap:12px;align-items:center;margin-bottom:12px}

.legend{display:flex;gap:10px;align-items:center;font-size:13px}

.legend .item{display:flex;gap:6px;align-items:center}

.swatch{width:14px;height:14px;border-radius:3px}

.grid{display:grid;grid-template-columns:var(--left-col) repeat(16,1fr);gap:6px;align-items:center}

.grid .header{position:sticky;top:0;background:#fff;padding:6px 10px;border-bottom:1px solid #e6eef6;z-index:5;font-weight:600}

.week{font-size:12px;text-align:center;padding:6px 4px}

.row{display:contents}

.task-name{padding:10px;background:transparent;font-weight:600}

.lane{height:44px;position:relative}

.bar{position:absolute;top:8px;height:28px;border-radius:8px;display:flex;align-items:center;padding:0 10px;color:#fff;font-weight:600;cursor:pointer;box-shadow:0 4px 10px rgba(2,6,23,0.08)}

.bar.small{font-size:12px}

/* colors */

.c-critical{background:linear-gradient(90deg,#ef4444,#dc2626)}

.c-high{background:linear-gradient(90deg,#f97316,#ea580c)}

.c-medium{background:linear-gradient(90deg,#f59e0b,#d97706)}

.c-low{background:linear-gradient(90deg,#10b981,#059669)}

/* sprint stripes */

.col{height:48px;border-radius:6px}

.sprint-bg{background-image:linear-gradient(90deg, rgba(14,165,233,0.03) 0 50%, transparent 0 100%)}

.milestone{width:12px;height:12px;border-radius:3px;background:#0ea5e9;position:absolute;right:6px;top:12px}

.info{margin-top:12px;font-size:13px}

.modal{position:fixed;left:50%;top:50%;transform:translate(-50%,-50%);width:680px;max-width:92%;background:#fff;border-radius:10px;box-shadow:0 24px 60px rgba(2,6,23,0.2);padding:16px;z-index:80}

.overlay{position:fixed;inset:0;background:rgba(2,6,23,0.45);z-index:70}

.close{float:right;border:none;background:transparent;font-weight:700;font-size:18px;cursor:pointer}

pre{background:#f1f5f9;padding:10px;border-radius:8px;overflow:auto}

.footer{display:flex;justify-content:space-between;margin-top:12px;font-size:13px}

.btn{padding:8px 12px;border-radius:8px;border:1px solid #e6eef6;background:#fff;cursor:pointer}

</style>

</head>

<body>

<div class="frame">

<div style="display:flex;justify-content:space-between;align-items:center">

<div>

<h1>IIT Prediction App — Agile Roadmap (Weeks 1–16)</h1>

<div style="color:#334155;font-size:13px">Mapped to 8 x 2-week sprints. Click any task bar to see details and subtasks.</div>

</div>

<div class="legend">

<div class="item"><span class="swatch c-critical"></span>Critical</div>

<div class="item"><span class="swatch c-high"></span>High</div>

<div class="item"><span class="swatch c-medium"></span>Medium</div>

<div class="item"><span class="swatch c-low"></span>Low</div>

</div>

</div>

<div style="margin-top:12px;overflow:auto;padding-bottom:6px">

<div class="grid" id="timeline">

<div class="header" style="grid-column:1/2">Workstream / Task</div>

<!-- weeks header -->

</div>

<div style="height:10px"></div>

<div id="rows" style="display:grid;grid-template-columns:var(--left-col) repeat(16,1fr);gap:6px"></div>

</div>

<div class="footer">

<div>Phases: Foundation (W1–4) · Core Features (W5–8) · Advanced (W9–12) · Production (W13–16)</div>

<div style="display:flex;gap:8px"><button class="btn" id="download">Download JSON</button></div>

</div>

<div class="info">

<strong>Tips:</strong> Use this as the sprint-level plan. Convert each task into sprint backlog items for development. Prioritize critical items (DB, Auth, Go-Live) early and keep demos at the end of each sprint.

</div>

</div>

<!-- modal skeleton -->

<div id="overlay" class="overlay" style="display:none"></div>

<div id="modal" class="modal" style="display:none">

<button class="close" id="close">×</button>

<div id="modal-content"></div>

</div>

<script>

const weeks = 16;

const timeline = document.getElementById('timeline');

// render week headers with sprint shading (2-week sprints)

for(let i=1;i<=weeks;i++){

const header = document.createElement('div');

header.className = 'week header col';

header.style.gridColumn = (i+1) + '/' + (i+2);

header.innerHTML = 'W' + i;

// alternate sprint shading for visual

if(Math.floor((i-1)/2) % 2 === 0) header.style.background = 'linear-gradient(90deg, rgba(2,6,23,0.02), transparent)';

timeline.appendChild(header);

}

// tasks definition (name, startWeek, durationWeeks, priority, details)

const tasks = [

{name:'Database & Data Persistence',w:1,d:1,p:'CRITICAL',cls:'c-critical',details:[

'Install PostgreSQL, run alembic migrations','Connection pooling and backup scripts','SQLAlchemy models, indexes, validation','Seed realistic test data']},

{name:'Authentication & Authorization',w:2,d:1,p:'CRITICAL',cls:'c-critical',details:[

'JWT auth, password hashing','RBAC: Admin/Clinician/Analyst/Field','Audit logging & session management','User management UI components']},

{name:'Patient Data Management',w:3,d:1,p:'HIGH',cls:'c-high',details:[

'Patient CRUD, intake forms','Search/filter, profile & history','Bulk import/export, dedupe','Data quality checks & audit trail']},

{name:'API Enhancement & Testing',w:4,d:1,p:'HIGH',cls:'c-high',details:[

'Error handling & logging','API versioning & docs','pytest setup, unit & integration tests','Test fixtures & CI integration']},

{name:'React Frontend (Patient + Dashboard + Prediction)',w:5,d:1,p:'HIGH',cls:'c-high',details:[

'Patient list/detail/create','Dashboards: real-time charts & widgets','Prediction interface & explanations','Batch upload & prediction history']},

{name:'Intervention Workflow System',w:6,d:1,p:'HIGH',cls:'c-high',details:[

'High-risk alerts & case assignment','Follow-ups, reminders, KPIs','Automation & escalation rules','In-app messaging & notifications']},

{name:'Reporting & Analytics',w:7,d:1,p:'MEDIUM',cls:'c-medium',details:[

'Standard reports & cohort analysis','Custom report builder','PDF/Excel exports & scheduling','Integration APIs for BI tools']},

{name:'Performance & Monitoring',w:8,d:1,p:'MEDIUM',cls:'c-medium',details:[

'Query optimization & caching','Load testing & profiling','Logging & error alerting','Health dashboard']},

{name:'ML Model Enhancement',w:9,d:1,p:'MEDIUM',cls:'c-medium',details:[

'Versioning & A/B testing','Feature importance & explainability','Retraining pipeline & monitoring','Bias detection']},

{name:'Integration & Connectivity',w:10,d:1,p:'MEDIUM',cls:'c-medium',details:[

'HL7 FHIR & EHR integrations','Lab results, meds import','Third-party APIs & webhooks','Rate limiting & developer portal']},

{name:'Mobile & Field Operations (PWA)',w:11,d:1,p:'MEDIUM',cls:'c-medium',details:[

'Offline PWA, sync','GPS/photo capture & barcode','Voice-to-text notes','Field data workflows']},

{name:'Compliance & Security',w:12,d:1,p:'HIGH',cls:'c-high',details:[

'Encryption & access controls','HIPAA privacy & retention','Penetration testing','Backup & disaster recovery']},

{name:'Infrastructure & Deployment',w:13,d:1,p:'HIGH',cls:'c-high',details:[

'Docker & k8s manifests','CI/CD pipelines & rollback','Cloud infra: autoscaling & DB clustering','Multi-env config']},

{name:'Quality Assurance',w:14,d:1,p:'HIGH',cls:'c-high',details:[

'E2E tests, load & security tests','Accessibility testing','UAT sessions with clinicians','Performance validation']},

{name:'Documentation & Training',w:15,d:1,p:'MEDIUM',cls:'c-medium',details:[

'API & architecture docs','User manuals & videos','Runbooks & troubleshooting','Knowledge base & support plan']},

{name:'Go-Live Preparation',w:16,d:1,p:'CRITICAL',cls:'c-critical',details:[

'Final security & performance audits','Backup/DR test, monitoring','Go-live checklist & runbook','Support & post-launch monitoring']}

];

// create rows

const rows = document.getElementById('rows');

tasks.forEach((t, idx)=>{

// task name cell

const nameCell = document.createElement('div');

nameCell.className = 'task-name';

nameCell.textContent = (idx+1)+'. ' + t.name;

rows.appendChild(nameCell);

// create 16 lane cells

for(let i=1;i<=weeks;i++){

const lane = document.createElement('div');

lane.className = 'lane col';

lane.style.gridColumn = (i+1) + '/' + (i+2);

lane.style.minWidth = '48px';

lane.style.position = 'relative';

rows.appendChild(lane);

}

// create bar and place it

const bar = document.createElement('div');

bar.className = 'bar small ' + t.cls;

bar.textContent = t.name.split(' ').slice(0,4).join(' ');

// compute grid placement: set left by week index

const startCol = t.w;

const duration = t.d;

// find left cell element index: each row created 1 name + 16 lanes -> for simplicity compute offset

// We'll position absolute: left = (startCol-1) * (colWidth + gap)

const grid = rows;

const colWidth = 56; // approx: --col-width + gap

const left = (startCol-1) * colWidth + 6; // small offset

bar.style.left = left + 'px';

bar.style.width = (duration * colWidth - 12) + 'px';

// click to show details

bar.addEventListener('click', ()=>{

document.getElementById('overlay').style.display='block';

const m = document.getElementById('modal'); m.style.display='block';

const content = document.getElementById('modal-content');

content.innerHTML = `<h2 style=\"margin-top:0\">${t.name}</h2>` +

`<div style=\"font-size:13px;color:#475569;margin-bottom:10px\">Priority: ${t.p} · Week ${t.w} · Duration: ${t.d}w</div>` +

`<ul>${t.details.map(d=>`<li>${d}</li>`).join('')}</ul>` +

`<pre>Acceptance criteria:\n- Feature implemented and tested in sprint\n- Unit + integration tests passing\n- Demo to stakeholders</pre>`;

});

// append bar into the correct row's DOM: calculate anchor lane

// find the lane DOM node for this task: each task appends 1 name + 16 lanes in order

// compute base index in rows children

const taskIndex = idx * 17; // zero-based

// children[taskIndex] is name, [taskIndex+1..+16] are lanes

const anchorLane = rows.children[taskIndex + 1];

anchorLane.appendChild(bar);

// milestone at end of phase

const milestone = document.createElement('div');

milestone.className = 'milestone';

// place milestone on the lane that corresponds to end week

const endWeek = t.w + t.d - 1;

const endLane = rows.children[taskIndex + 1 + endWeek];

if(endLane) endLane.appendChild(milestone);

});

// modal close

document.getElementById('close').onclick = ()=>{document.getElementById('overlay').style.display='none';document.getElementById('modal').style.display='none';}

document.getElementById('overlay').onclick = ()=>{document.getElementById('overlay').style.display='none';document.getElementById('modal').style.display='none';}

// download JSON

document.getElementById('download').addEventListener('click',()=>{

const a = document.createElement('a');

const blob = new Blob([JSON.stringify(tasks,null,2)],{type:'application/json'});

a.href = URL.createObjectURL(blob);

a.download = 'iit_roadmap_tasks.json';

a.click();

});

</script>

</body>

</html>

Critical Gaps Requiring Attention

High Priority

- Testing Infrastructure: No automated tests - critical for healthcare application

- Production Deployment: Missing production configuration and monitoring

- Error Handling: Need comprehensive error boundaries and fallback mechanisms

- Data Validation: Some API endpoints lack proper input validation

Medium Priority

- Documentation: API docs incomplete, user guides missing

- Performance Optimization: No caching, query optimization, or load testing

- Security Hardening: Need penetration testing, audit logging

- Backup & Recovery: No automated backup strategies

Low Priority

- Advanced Analytics: Some reporting features partially implemented

- Mobile Optimization: PWA features present but not fully optimized

- Internationalization: Basic i18n setup but not comprehensive

Recommended Next Steps

- Implement Testing Framework (pytest for backend, Jest for frontend)

- Complete Production Deployment (environment configs, monitoring)

- Add Comprehensive Error Handling (frontend error boundaries, backend validation)

- Performance Optimization (caching, query optimization, load testing)

- Security Audit (penetration testing, compliance checks)

Risk Assessment

- High Risk: Lack of testing could lead to critical bugs in healthcare application

- Medium Risk: Incomplete production setup may cause deployment issues

- Low Risk: Missing advanced features can be added incrementally

The project demonstrates excellent architectural decisions and comprehensive feature implementation, but requires significant testing and production hardening before healthcare deployment.