## Sheet1
Phase | Timeline | Key Activities | Deliverables | Responsible Parties | STATUS
1. Initiation & Approvals | Month 1 | - Acknowledge SI Director’s approval.- Draft and agree on Data Sharing & Governance Plan.- Identify focal persons from SI Unit and AI/ML Team.- Set up collaboration workspace (Teams/Slack). | - Signed data sharing and governance plan.- List of focal persons and roles.- Established communication channel. | SI Unit, AI/ML Project Lead | DONE
2. Data Extraction & Structuring | Month 2 | - Extract de-identified datasets (RADET, EMR, Lab, etc.).- Define key variables and create data dictionary.- Clean, transform, and standardize datasets for model ingestion. | - Structured and cleaned dataset.- Comprehensive data dictionary.- Documented data flow and schema. | SI Data Team, AI/ML Data Engineers
3. Data Quality Review & Integration | Month 3 | - Conduct data quality checks and validation.- Merge datasets across sources (clinical, lab, pharmacy, RADET).- Document completeness and missingness reports. | - Validated integrated dataset.- Data quality summary report. | SI M&E Team, AI/ML Data Analysts
4. Model Development & Baseline Testing | Month 4 | - Split data into training, validation, and test sets.- Develop baseline models (Random Forest, XGBoost, Neural Networks).- Evaluate using accuracy, recall, precision, and AUC. | - Prototype IIT & VLS prediction models.- Initial performance metrics and evaluation report. | AI/ML Technical Team
5. Model Optimization & Validation | Month 5 | - Fine-tune model parameters and algorithms.- Perform cross-validation and feature importance analysis.- Benchmark against baseline models. | - Optimized predictive models.- Model validation report and interpretability outputs. | AI/ML Lead, Data Science Team
6. Review, Presentation & Feedback Integration | Month 6 | - Present model outcomes and insights to SI Directorate.- Gather stakeholder feedback and refine models.- Document next steps for scale-up. | - Presentation slides and stakeholder report.- Updated models incorporating feedback. | AI/ML Lead, SI Directorate
7. Grant Application Preparation | Month 7 | - Integrate preliminary model data into AI/ML grant proposals.- Develop narrative and technical proposal sections.- Identify and respond to relevant funding calls (e.g., Gates, WHO, USAID). | - Completed AI/ML grant proposal draft.- Submission-ready package with preliminary results. | AI/ML Team, Grants Unit, SI Unit
Standing Engagements | Ongoing | - Weekly technical check-ins (AI/ML + SI focal persons).- Bi-weekly progress review meetings.- Monthly management brief to SI Director. | - Progress trackers and meeting minutes.- Monthly status reports. | All Stakeholders